## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | REPORTING QUARTER | QUANTITATIVE ACTUAL PROGRESS Q1 | QUANTITATIVE ACTUAL PROGRESS Q1-2 | QUANTITATIVE ACTUAL PROGRESS Q1-3 | QUANTITATIVE ACTUAL PROGRESS Q1-4 | QUALITATIVE ACTUAL PROGRESS Q1 | QUALITATIVE ACTUAL PROGRESS Q1-2 | QUALITATIVE ACTUAL PROGRESS Q1-3 | QUALITATIVE ACTUAL PROGRESS Q1-4 | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | Liberty | 2025-05-01 | Program |  |  | Covered conductor installation | See Column I | Reduce the risk of ignition from vegetation contact, wire slap during wind events, and wildlife interference. | Grid Design, Operations, and Maintenance | Covered conductor installation |  | 8.1.2.1 | WMP-GDOM-GH-01 | Liberty Grid Design, Operations, and Maintenance Covered conductor installation WMP-GDOM-GH-01 2025 | 144 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | NO | Circuit Miles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000001 | Liberty | 2025-05-01 | Program |  |  | Undergrounding of electric lines and/or equipment | See Column I | Eliminate wildfire ignition risks. | Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | WMP-GDOM-GH-02 | Liberty Grid Design, Operations, and Maintenance Undergrounding of electric lines and/or equipment WMP-GDOM-GH-02 2025 | 149 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | NO | Circuit Miles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000002 | Liberty | 2025-05-01 | Program |  |  | Distribution pole replacements and reinforcements | See Column I | Minimize the risk of faults due to pole and associated hardware failure and to maintain system reliability. | Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements |  | 8.1.2.3 | WMP-GDOM-GH-03 | Liberty Grid Design, Operations, and Maintenance Distribution pole replacements and reinforcements WMP-GDOM-GH-03 2025 | 150 | Equipment ignition likelihood | NO | Poles |  | 2025 | 1 | 249 | [7 empty] | In Progress
1010000003 | Liberty | 2025-05-01 | Program |  |  | Traditional overhead hardening | See Column I | Support both wildfire risk reduction and system reliability improvements. | Grid Design, Operations, and Maintenance | Traditional overhead hardening |  | 8.1.2.5 | WMP-GDOM-GH-05 | Liberty Grid Design, Operations, and Maintenance Traditional overhead hardening WMP-GDOM-GH-05 2025 | 151 | Equipment ignition likelihood | NO | Circuit Miles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000004 | Liberty | 2025-05-01 | Program |  |  | Emerging grid hardening technology installations and pilot progress | See Column I | Utilize fast trip settings and add more fault indicators to reduce wildfire risk during high fire threat days. | Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilot progress |  | 8.1.2.6 | WMP-GDOM-GH-06 | Liberty Grid Design, Operations, and Maintenance Emerging grid hardening technology installations and pilot progress WMP-GDOM-GH-06 2025 | 152 | Equipment ignition likelihood | NO | Implement SRP Program |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000005 | Liberty | 2025-05-01 | Program |  |  | Microgrids | See Column I | Reduce wildfire risk and eliminate the possibility of infrastructure ignition events on lines that are removed or taken out of service. | Grid Design, Operations, and Maintenance | Microgrids |  | 8.1.2.7 | WMP-GDOM-GH-07 | Liberty Grid Design, Operations, and Maintenance Microgrids WMP-GDOM-GH-07 2025 | 154 | PSPS likelihood PSPS exposure potential | NO | Microgrids |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000006 | Liberty | 2025-05-01 | Program |  |  | Installation of system automation equipment | See Column I | Liberty installs reclosers to help with sectionalization, opportunities for distribution automation, and opportunities for grid topology improvement to reduce the size and number of customers affected by faults on the system. Reclosers also help Liberty more quickly identify and restore power to affected customers. | Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | 8.1.2.8 | WMP-GDOM-GH-08 | Liberty Grid Design, Operations, and Maintenance Installation of system automation equipment WMP-GDOM-GH-08 2025 | 155 | Equipment ignition likelihood | NO | Automatic Reclosers |  | 2025 | 1 | 1 | [7 empty] | In Progress
1010000007 | Liberty | 2025-05-01 | Program |  |  | Line removal (in HFTD) | See Column I | Line removal eliminates the risk of infrastructure caused ignitions in the area where a line is removed. | Grid Design, Operations, and Maintenance | Line removal (in HFTD) |  | 8.1.2.9 | WMP-GDOM-GH-09 | Liberty Grid Design, Operations, and Maintenance Line removal (in HFTD) WMP-GDOM-GH-09 2025 | 156 | Equipment ignition likelihood | NO | Circuit Miles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000008 | Liberty | 2025-05-01 | Program |  |  | Tree attachment removals | See Column I | Reduce wildfire ignition risk by eliminating the potential for conductor-tree contact, which can lead to faults, arcing, or fire during wind events or tree movement. | Grid Design, Operations, and Maintenance | Tree attachment removals |  | 8.1.2.12 | WMP-GDOM-GH-12a | Liberty Grid Design, Operations, and Maintenance Tree attachment removals WMP-GDOM-GH-12a 2025 | 157 | Equipment ignition likelihood | NO | Tree Attachments |  | 2025 | 1 | 5 | [7 empty] | In Progress
1010000009 | Liberty | 2025-05-01 | Program |  |  | Expulsion fuse replacement | See Column I | Reduce risk of ignition by limiting energy release. | Grid Design, Operations, and Maintenance | Expulsion fuse replacement |  | 8.1.2.12 | WMP-GDOM-GH-12b | Liberty Grid Design, Operations, and Maintenance Expulsion fuse replacement WMP-GDOM-GH-12b 2025 | 157 | Equipment ignition likelihood | NO | Expulsion Fuses |  | 2025 | 1 | 139 | [7 empty] | In Progress
1010000010 | Liberty | 2025-05-01 | Program |  |  | Animal guards | See Column I | Reduce risk of ignition by installing insulating animal guards on exposed substation equipment. | Grid Design, Operations, and Maintenance | Animal guards |  | 8.1.2.12 | WMP-GDOM-GH-12c | Liberty Grid Design, Operations, and Maintenance Animal guards WMP-GDOM-GH-12c 2025 | 157 | Equipment ignition likelihood Contact by object ignition likelihood | NO | Animal Guards |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000011 | Liberty | 2025-05-01 | Program |  |  | Open wire/grey wire | See Column I | Reduces the risk of ignition and service interruptions, particularly in wildland-urban interface areas where homes and vegetation are in close proximity to overhead infrastructure. | Grid Design, Operations, and Maintenance | Open wire/grey wire |  | 8.1.2.12 | WMP-GDOM-GH-12e | Liberty Grid Design, Operations, and Maintenance Open wire/grey wire WMP-GDOM-GH-12e 2025 | 157 | Equipment ignition likelihood | NO | Circuit Miles |  | 2025 | 1 | 2.06 | [7 empty] | In Progress
1010000012 | Liberty | 2025-05-01 | Program |  |  | Detailed inspections of distribution electric lines and equipment | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Detailed inspections of distribution electric lines and equipment |  | 8.1.3.1 | WMP-GDOM-AI-01 | Liberty Grid Design, Operations, and Maintenance Detailed inspections of distribution electric lines and equipment WMP-GDOM-AI-01 2025 | 164 | Equipment ignition likelihood | YES | Circuit Miles |  | 2025 | 1 | 17.34 | [7 empty] | In Progress
1010000013 | Liberty | 2025-05-01 | Program |  |  | Intrusive pole inspections | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Intrusive pole inspections |  | 8.1.3.2 | WMP-GDOM-AI-02 | Liberty Grid Design, Operations, and Maintenance Intrusive pole inspections WMP-GDOM-AI-02 2025 | 164 | Equipment ignition likelihood | YES | Poles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000014 | Liberty | 2025-05-01 | Program |  |  | Patrol inspections of distribution electric lines and equipment | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Patrol inspections of distribution electric lines and equipment |  | 8.1.3.1 | WMP-GDOM-AI-03 | Liberty Grid Design, Operations, and Maintenance Patrol inspections of distribution electric lines and equipment WMP-GDOM-AI-03 2025 | 164 | Equipment ignition likelihood | YES | Circuit Miles |  | 2025 | 1 | 585.7 | [7 empty] | In Progress
1010000015 | Liberty | 2025-05-01 | Program |  |  | Other discretionary inspections of distribution electric lines and equipment | See Column I | Outage restoration. | Grid Design, Operations, and Maintenance | Other discretionary inspections of distribution electric lines and equipment |  | 8.1.3.4 | WMP-GDOM-AI-04 | Liberty Grid Design, Operations, and Maintenance Other discretionary inspections of distribution electric lines and equipment WMP-GDOM-AI-04 2025 | 165 | Equipment ignition likelihood | YES | Circuit Miles |  | 2025 | 1 | 0.87 | [7 empty] | In Progress
1010000016 | Liberty | 2025-05-01 | Program |  |  | Quality assurance / quality control of inspections | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Quality assurance / quality control of inspections |  | 8.1.3.5 | WMP-GDOM-AI-05 | Liberty Grid Design, Operations, and Maintenance Quality assurance / quality control of inspections WMP-GDOM-AI-05 2025 | 166 | Equipment ignition likelihood | NO | % of Detailed Inspections |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000017 | Liberty | 2025-05-01 | Program |  |  | Substation inspections | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Substation inspections |  | 8.1.3.6 | WMP-GDOM-AI-06 | Liberty Grid Design, Operations, and Maintenance Substation inspections WMP-GDOM-AI-06 2025 | 166 | Equipment ignition likelihood | YES | Substations |  | 2025 | 1 | 28 | [7 empty] | In Progress
1010000018 | Liberty | 2025-05-01 | Program |  |  | Equipment settings to reduce wildfire risk | See Column I | Utilize fast trip settings and add more fault indicators to reduce wildfire risk during high fire threat days. | Grid Design, Operations, and Maintenance | Equipment settings to reduce wildfire risk |  | 8.1.8.1 | WMP-GDOM-GO-01 | Liberty Grid Design, Operations, and Maintenance Equipment settings to reduce wildfire risk WMP-GDOM-GO-01 2025 | 174 | Equipment ignition likelihood | NO | # Circuits with SRP |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000019 | Liberty | 2025-05-01 | Program |  |  | Vegetation Management Inspection Program - Detailed | See Column I | Prescribe pruning and removal of vegetation as a safeguard against grow‐ins or fall‐ins and to comply with required laws and regulations. | Vegetation Management & Inspections | Vegetation Management Inspection Program - Detailed |  | 8.2.2.1 | WMP-VM-INSP-01 | Liberty Vegetation Management & Inspections Vegetation Management Inspection Program - Detailed WMP-VM-INSP-01 2025 | 193 | Contact from vegetation ignition likelihood | YES | Line Miles |  | 2025 | 1 | 45.36 | [7 empty] | In Progress
1010000020 | Liberty | 2025-05-01 | Program |  |  | Vegetation Management Inspection Program - Patrol | See Column I | Conduct as needed based on environmental conditions or other factors. | Vegetation Management & Inspections | Vegetation Management Inspection Program - Patrol |  | 8.2.2.2 | WMP-VM-INSP-02 | Liberty Vegetation Management & Inspections Vegetation Management Inspection Program - Patrol WMP-VM-INSP-02 2025 | 193 | Contact from vegetation ignition likelihood | NO | Line Miles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000021 | Liberty | 2025-05-01 | Program |  |  | Vegetation Management Inspection Program - LiDar | See Column I | Measure vegetation to conductor distances, tree height, and proximity to overhead lines. | Vegetation Management & Inspections | Vegetation Management Inspection Program - LiDar |  | 8.2.2.3 | WMP-VM-INSP-03 | Liberty Vegetation Management & Inspections Vegetation Management Inspection Program - LiDar WMP-VM-INSP-03 2025 | 193 | Contact from vegetation ignition likelihood | YES | Line Miles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000022 | Liberty | 2025-05-01 | Program |  |  | Pole Clearing | See Column I | Reduce wildfire risk by removing vegetation at base of poles. | Vegetation Management & Inspections | Pole Clearing |  | 8.2.3.1 | WMP-VM-VFM-01 | Liberty Vegetation Management & Inspections Pole Clearing WMP-VM-VFM-01 2025 | 205 | Wildfire spread Wildfire hazard | NO | Subject Poles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000023 | Liberty | 2025-05-01 | Program |  |  | Wood and Slash Management | See Column I | Reduce wildfire risks by removing wood and treating brush and slash after vegetation maintenance is performed. | Vegetation Management & Inspections | Wood and Slash Management |  | 8.2.3.2 | WMP-VM-VFM-02 | Liberty Vegetation Management & Inspections Wood and Slash Management WMP-VM-VFM-02 2025 | 205 | Wildfire spread Wildfire hazard | NO | Acres |  | 2025 | 1 | 18.85 | [7 empty] | In Progress
1010000024 | Liberty | 2025-05-01 | Program |  |  | Substation Defensible Space | See Column I | Maintain accessibility, safety, and adherence to all appropriate governmental regulations and Liberty policies. | Vegetation Management & Inspections | Substation Defensible Space |  | 8.2.3.5 | WMP-VM-VFM-03 | Liberty Vegetation Management & Inspections Substation Defensible Space WMP-VM-VFM-03 2025 | 213 | Wildfire spread Wildfire hazard | NO | Substation Treatments |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000025 | Liberty | 2025-05-01 | Program |  |  | Fire-Resilient Right-of-Ways | See Column I | Reduce future maintenance entries, protect infrastructure, increase fire-resiliency and are the initial step of the integrated vegetation management (“IVM”) program. | Vegetation Management & Inspections | Fire-Resilient Right-of-Ways |  | 8.2.3.7 | WMP-VM-VFM-04 | Liberty Vegetation Management & Inspections Fire-Resilient Right-of-Ways WMP-VM-VFM-04 2025 | 214 | Wildfire spread Wildfire hazard | NO | Line Miles |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000026 | Liberty | 2025-05-01 | Program |  |  | Clearance | See Column I | Prescribe mitigation of vegetation encroachments. | Vegetation Management & Inspections | Clearance |  | 8.2.3.3 | WMP-VM-VFM-05 | Liberty Vegetation Management & Inspections Clearance WMP-VM-VFM-05 2025 | 207 | Contact from vegetation ignition likelihood | NO | Line Miles |  | 2025 | 1 | 359.85 | [7 empty] | In Progress
1010000027 | Liberty | 2025-05-01 | Program |  |  | Fall-In Mitigation | See Column I | Identify trees that pose a high risk of failure. | Vegetation Management & Inspections | Fall-In Mitigation |  | 8.2.3.4 | WMP-VM-VFM-06 | Liberty Vegetation Management & Inspections Fall-In Mitigation WMP-VM-VFM-06 2025 | 209 | Contact from vegetation ignition likelihood | NO | Line Miles |  | 2025 | 1 | 0.5 | [7 empty] | In Progress
1010000028 | Liberty | 2025-05-01 | Program |  |  | Quality Assurance and Quality Control | See Column I | Provides VM program oversight to provide reasonable assurance that vegetation inspection and maintenance work is being effectively performed. | Vegetation Management & Inspections | Quality Assurance and Quality Control |  | 8.2.5 | WMP-VM-QAQC-01 | Liberty Vegetation Management & Inspections Quality Assurance and Quality Control WMP-VM-QAQC-01 2025 | 222 | Contact from vegetation ignition likelihood | YES | Line Miles |  | 2025 | 1 | 76.2 | [7 empty] | In Progress
1010000029 | Liberty | 2025-05-01 | Program |  |  | Environmental monitoring systems | See Column I | Monitor environmental conditions within service territory. | Situational Awareness & Forecasting | Environmental monitoring systems |  | 8.3.2 | WMP-SA-01 | Liberty Situational Awareness & Forecasting Environmental monitoring systems WMP-SA-01 2025 | 242 | Wildfire exposure potential PSPS exposure potential | NO | Weather Stations |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000030 | Liberty | 2025-05-01 | Program |  |  | Grid monitoring systems | See Column I | Expedite power restoration during an outage by helping line crews locate the fault. | Situational Awareness & Forecasting | Grid monitoring systems |  | 8.3.3 | WMP-SA-02 | Liberty Situational Awareness & Forecasting Grid monitoring systems WMP-SA-02 2025 | 246 | Equipment ignition likelihood | NO | Circuits With Fault Indicators |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000031 | Liberty | 2025-05-01 | Program |  |  | Fire detection and alarm systems | See Column I | Provide early detection, accurate forecasting, and effective response strategies. | Situational Awareness & Forecasting | Fire detection and alarm systems |  | 8.3.4 | WMP-SA-03 | Liberty Situational Awareness & Forecasting Fire detection and alarm systems WMP-SA-03 2025 | 249 | Equipment ignition likelihood | NO | DFA Units |  | 2025 | 1 | 0 | [7 empty] | In Progress
1010000032 | Liberty | 2025-05-01 | Program |  |  | Collaboration and coordination with public safety partners | See Column I | Inform external public safety partners and other interconnected electrical corporation partners of wildfire, PSPS, and re-energization events as required by G.O. 166 and Public Utilities Code Section 768.6. | Emergency Preparedness | Collaboration and coordination with public safety partners |  | 8.4.3 | WMP-EP-02 | Liberty Emergency Preparedness Collaboration and coordination with public safety partners WMP-EP-02 2025 | 287 | PSPS vulnerability Wildfire vulnerability | NO |  |  | 2025 | 1 |  |  |  |  | Engaged with stakeholders through participation in 11 community councils and working group meetings. |  |  |  | In Progress
1010000033 | Liberty | 2025-05-01 | Program |  |  | Customer support in wildfire and PSPS emergencies | See Column I | Increase awareness and community resiliency to wildfires and PSPS events. | Emergency Preparedness | Customer support in wildfire and PSPS emergencies |  | 8.4.6 | WMP-EP-05 | Liberty Emergency Preparedness Customer support in wildfire and PSPS emergencies WMP-EP-05 2025 | 319 | PSPS vulnerability Wildfire vulnerability | NO |  |  | 2025 | 1 |  |  |  |  | Liberty held its exercise planning meetings in Q1 and scheduled a tabletop exercise on May 21, 2025, and a full-scale exercise on June 26, 2025. |  |  |  | In Progress
1010000034 | Liberty | 2025-05-01 | Program |  |  | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | See Column I | Increase awareness and community resiliency to wildfires and PSPS events. | Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management |  | 8.5.2 | WMP-CO-01 | Liberty Community Outreach and Engagement Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management WMP-CO-01 2025 | 329 | PSPS vulnerability Wildfire vulnerability | NO |  |  | 2025 | 1 |  |  |  |  | 27 in-person events, 22 virtual events, and 15 rounds of emails, website posts, and social media posts focused on PSPS education and wildfire awareness, AFN outreach, and CBO collaboration. |  |  |  | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000001 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000002 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000003 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 18
1020000004 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000005 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000006 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000007 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 2
1020000008 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000009 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000010 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000011 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 4
1020000012 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000013 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000014 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000015 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 3
1020000016 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000017 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000018 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000019 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000020 | 1. Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000021 | 1. Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000022 | 1. Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000023 | 1. Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000024 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000025 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000026 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000027 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 51
1020000028 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000029 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000030 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000031 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 5
1020000032 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000033 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000034 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000035 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 5
1020000036 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000037 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000038 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000039 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 9
1020000040 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000041 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000042 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000043 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000044 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000045 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000046 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000047 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 1
1020000048 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000049 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000050 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000051 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000052 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000053 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000054 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000055 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000056 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000057 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000058 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000059 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1020000060 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | Liberty | 2025 | 1 | 26
1020000061 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | Liberty | 2025 | 1 | 155
1020000062 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | Liberty | 2025 | 1 | 45
1020000063 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | Liberty | 2025 | 1 | 56
1020000064 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | Liberty | 2025 | 1 | 8
1020000065 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | Liberty | 2025 | 1 | 22
1020000066 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | Liberty | 2025 | 1 | 0
1020000067 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | Liberty | 2025 | 1 | 0
1020000068 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | Liberty | 2025 | 1 | 0
1020000069 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | Liberty | 2025 | 1 | 0
1020000070 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  |  | Liberty | 2025 | 1 | 0
1020000071 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  |  | Liberty | 2025 | 1 | 0
1020000072 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000073 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000074 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000075 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000076 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000077 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000078 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000079 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000080 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000081 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000082 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000083 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000084 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 7560
1020000085 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 27494
1020000086 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000087 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000088 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 7392
1020000089 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 39432
1020000090 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000091 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000092 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000093 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000094 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000095 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000096 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 38760
1020000097 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 40269.6
1020000098 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000099 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000100 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 39432
1020000101 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | Liberty | 2025 | 1 | 39432
1020000102 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000103 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000104 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000105 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000106 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000107 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | Liberty | 2025 | 1 | 0
1020000108 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | Liberty | 2025 | 1 | 2977
1020000109 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | Liberty | 2025 | 1 | 0
1020000110 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | Liberty | 2025 | 1 | 9389
1020000111 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | Liberty | 2025 | 1 | 569
1020000112 | 8. Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  |  | Liberty | 2025 | 1 | 0
1020000113 | 9. Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | Liberty | 2025 | 1 | 0
1020000114 | 9. Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | Liberty | 2025 | 1 | 0
1020000115 | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | Liberty | 2025 | 1 | 0
1020000116 | 11. Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | Liberty | 2025 | 1 | 0
1020000117 | 11. Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | Liberty | 2025 | 1 | 0
1020000118 | 12. Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | Liberty | 2025 | 1 | 0
1020000119 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000120 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000121 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000122 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000123 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000124 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000125 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000126 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000127 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000128 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000129 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000130 | 13. Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | Liberty | 2025 | 1 | 0
1020000131 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000132 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000133 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000134 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 10
1020000135 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000136 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000137 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000138 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 533
1020000139 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000140 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000141 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000142 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000143 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000144 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000145 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000146 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 585.7
1020000147 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000148 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000149 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000150 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 16.99
1020000151 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000152 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000153 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000154 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000155 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000156 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000157 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000158 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000159 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000160 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000161 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000162 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 2
1020000163 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000164 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000165 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000166 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000167 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000168 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000169 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000170 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 5
1020000171 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000172 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000173 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000174 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 15
1020000175 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000176 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000177 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000178 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000179 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000180 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000181 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000182 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 2
1020000183 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000184 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000185 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000186 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 123
1020000187 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000188 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000189 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000190 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000191 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000192 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000193 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000194 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 1
1020000195 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000196 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000197 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000198 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000199 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000200 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000201 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000202 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000203 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000204 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000205 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000206 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000207 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000208 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000209 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000210 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000211 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000212 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000213 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000214 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000215 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000216 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000217 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000218 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000219 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000220 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000221 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000222 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000223 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000224 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000225 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000226 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000227 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000228 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000229 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000230 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 1
1020000231 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000232 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000233 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000234 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000235 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000236 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000237 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000238 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000239 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000240 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000241 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000242 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000243 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000244 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000245 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000246 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000247 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000248 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000249 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000250 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000251 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000252 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000253 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000254 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 6
1020000255 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000256 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000257 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000258 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 8
1020000259 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000260 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000261 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000262 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000263 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000264 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000265 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000266 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000267 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000268 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000269 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000270 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0.35
1020000271 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000272 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000273 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000274 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000275 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000276 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000277 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000278 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000279 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000280 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000281 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000282 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000283 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000284 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000285 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000286 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000287 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000288 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000289 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000290 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 3
1020000291 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000292 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000293 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000294 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 4
1020000295 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000296 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000297 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000298 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000299 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000300 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000301 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000302 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 3
1020000303 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000304 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000305 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000306 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 1
1020000307 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000308 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000309 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000310 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000311 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000312 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000313 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000314 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 1
1020000315 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000316 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000317 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000318 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 2
1020000319 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000320 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000321 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000322 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000323 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000324 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000325 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000326 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000327 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000328 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000329 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000330 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0.41
1020000331 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000332 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000333 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000334 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000335 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000336 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000337 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000338 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000339 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000340 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000341 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000342 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000343 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000344 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000345 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000346 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000347 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000348 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000349 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000350 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 1
1020000351 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000352 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000353 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000354 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000355 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000356 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000357 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000358 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000359 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000360 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000361 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000362 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000363 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000364 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000365 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000366 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000367 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000368 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000369 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000370 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000371 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000372 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000373 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000374 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000375 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000376 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000377 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000378 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000379 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000380 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000381 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000382 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000383 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000384 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000385 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000386 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000387 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000388 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000389 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000390 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000391 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000392 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000393 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000394 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000395 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000396 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000397 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000398 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000399 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000400 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000401 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000402 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000403 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000404 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000405 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000406 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000407 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000408 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000409 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000410 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000411 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000412 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000413 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000414 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000415 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000416 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000417 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000418 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000419 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000420 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000421 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000422 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000423 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000424 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000425 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000426 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000427 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000428 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000429 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000430 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000431 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000432 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000433 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000434 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000435 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000436 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000437 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000438 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000439 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000440 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000441 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000442 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000443 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000444 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000445 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000446 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000447 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000448 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000449 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000450 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000451 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000452 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000453 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000454 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | Liberty | 2025 | 1 | 0
1020000455 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000456 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000457 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000458 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000459 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000460 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000461 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000462 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000463 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000464 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000465 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000466 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000467 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000468 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000469 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000470 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000471 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000472 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000473 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000474 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000475 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000476 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000477 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000478 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000479 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000480 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000481 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000482 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000483 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000484 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000485 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000486 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000487 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000488 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000489 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000490 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | Liberty | 2025 | 1 | 0
1020000491 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000492 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000493 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000494 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000495 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000496 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000497 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000498 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 2
1020000499 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000500 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000501 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000502 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000503 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000504 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000505 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000506 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 1
1020000507 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000508 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000509 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000510 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 10
1020000511 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000512 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000513 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000514 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000515 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000516 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000517 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000518 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 1
1020000519 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000520 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000521 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000522 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 56
1020000523 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000524 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000525 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000526 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000527 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000528 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000529 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000530 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000531 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000532 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000533 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000534 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000535 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000536 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000537 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000538 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000539 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000540 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000541 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000542 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000543 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000544 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000545 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000546 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000547 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000548 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000549 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000550 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000551 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000552 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000553 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000554 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000555 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000556 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000557 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000558 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000559 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000560 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000561 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000562 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000563 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000564 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000565 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000566 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000567 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000568 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000569 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000570 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000571 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000572 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000573 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000574 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000575 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000576 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000577 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000578 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000579 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000580 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000581 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000582 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 7
1020000583 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000584 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000585 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000586 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000587 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000588 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000589 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000590 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000591 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000592 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000593 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000594 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 44
1020000595 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000596 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000597 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000598 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000599 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000600 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000601 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000602 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000603 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000604 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000605 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000606 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000607 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000608 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000609 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000610 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000611 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000612 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000613 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000614 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000615 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000616 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000617 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000618 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000619 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000620 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000621 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000622 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000623 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000624 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000625 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000626 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000627 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000628 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000629 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000630 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000631 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000632 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000633 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000634 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000635 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000636 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000637 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000638 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000639 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000640 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000641 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000642 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000643 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000644 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000645 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000646 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000647 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000648 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000649 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000650 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000651 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000652 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000653 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000654 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000655 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000656 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000657 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000658 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000659 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000660 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000661 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000662 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000663 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000664 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000665 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000666 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000667 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000668 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000669 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000670 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000671 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000672 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000673 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000674 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000675 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000676 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000677 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000678 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000679 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000680 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000681 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000682 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000683 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000684 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000685 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000686 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000687 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000688 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000689 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000690 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000691 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000692 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000693 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000694 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000695 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000696 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000697 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000698 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000699 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000700 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000701 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000702 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000703 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000704 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000705 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000706 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | Liberty | 2025 | 1 | 0
1020000707 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000708 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000709 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000710 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 1920
1020000711 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000712 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000713 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000714 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 45
1020000715 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000716 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000717 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000718 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 49
1020000719 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000720 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000721 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000722 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 6
1020000723 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000724 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000725 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000726 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 268
1020000727 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000728 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000729 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000730 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 10
1020000731 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000732 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000733 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000734 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 3
1020000735 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000736 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000737 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000738 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000739 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000740 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000741 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000742 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 49
1020000743 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000744 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000745 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000746 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000747 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000748 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000749 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000750 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000751 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000752 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000753 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000754 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000755 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000756 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000757 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000758 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000759 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000760 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000761 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000762 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000763 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000764 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000765 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000766 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000767 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000768 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000769 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000770 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000771 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000772 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000773 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000774 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000775 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000776 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000777 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000778 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000779 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000780 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000781 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000782 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000783 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000784 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000785 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000786 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000787 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000788 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000789 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000790 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000791 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000792 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000793 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000794 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000795 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000796 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000797 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000798 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000799 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000800 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000801 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000802 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | Liberty | 2025 | 1 | 0
1020000803 | 17. Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | Liberty did not experience a utility-ignited wildfire in Q1 of 2025 | Liberty | 2025 | 1

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000001 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000002 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000003 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000004 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000005 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000006 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 32.27
1040000007 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000008 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 1.16
1040000009 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000010 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000011 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000012 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000013 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000014 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000015 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000016 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000017 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000018 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000019 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000020 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000021 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000022 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0
1040000023 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | Liberty | 2025 | 1 | 0

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 2
1050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 3
1050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 2
1050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 9
1050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 5
1050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 5
1050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 2
1050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 2
1050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 5
1050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 4
1050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 1
1050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 22
1050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0
1050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2025 | 1 | 0

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0
1060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2025 | 1 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 4.59
1070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.04
1070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 12.73
1070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 5.41
1070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 52.54
1070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 15.99
1070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 307.65
1070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 17.95
1070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 582.93
1070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 165.32
1070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 114.41
1070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 72.62
1070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.03
1070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 109
1070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 15.71
1070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.46
1070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.39
1070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.1
1070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.16
1070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.57
1070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.18
1070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 5.69
1070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 20.68
1070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.29
1070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.03
1070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 2.32
1070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 21.7
1070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.05
1070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 3.42
1070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.52
1070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 8.84
1070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.84
1070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 103.76
1070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 11.88
1070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 297.61
1070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 77.48
1070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 35.42
1070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 10.52
1070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 8.76
1070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.46
1070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.06
1070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.09
1070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.15
1070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 17
1070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 2
1070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 16
1070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 3
1070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 102
1070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 19
1070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 385
1070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 63
1070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 408
1070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 104
1070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 66
1070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 35
1070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 0
1070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 0
1070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 62
1070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 5
1070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 0
1070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2025 | 1 | 0
1070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 1006
1070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 17
1070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 372
1070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 19
1070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 1465
1070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 38
1070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 14348
1070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 39
1070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 20133
1070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 1049
1070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 1764
1070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 202
1070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 1
1070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 0
1070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 2810
1070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 143
1070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 0
1070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | Liberty | 2025 | 1 | 0
1070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 103
1070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 11
1070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 76
1070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 90
1070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 217
1070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 86
1070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 1841
1070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 257
1070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 1508
1070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 344
1070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 139
1070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 89
1070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 0
1070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 0
1070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 59
1070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 6
1070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 0
1070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2025 | 1 | 0
1070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 202
1070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 5
1070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 98
1070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 4
1070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 589
1070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 21
1070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 4243
1070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 10
1070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 3833
1070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 209
1070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 565
1070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 76
1070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 0
1070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 0
1070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 635
1070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 35
1070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 0
1070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2025 | 1 | 0
1070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 1
1070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 1
1070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 2
1070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 5
1070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 2
1070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 1
1070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 1
1070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 1
1070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 1
1070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 4
1070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 2
1070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 8
1070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 11
1070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 5
1070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 7
1070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 1
1070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.01
1080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.09
1080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.03
1080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.37
1080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.04
1080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 2.29
1080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.05
1080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 5.38
1080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | -0.17
1080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 1.94
1080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.76
1080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.92
1080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.05
1080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | -0.03
1080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.06
1080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.09
1080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.56
1080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.23
1080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | -0.2
1080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.63
1080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.94
1080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0.05
1080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 1
1080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 1
1080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 1
1080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2025 | 1 | 0
1090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 1
1090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2025 | 1 | 0
1090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0
1090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2025 | 1 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | Liberty | 2025 | 1 | 0
1100000001 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | Liberty | 2025 | 1 | 0
1100000002 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | Liberty | 2025 | 1 | 0
1100000003 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | Liberty | 2025 | 1 | 0
1100000004 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | Liberty | 2025 | 1 | 0
1100000005 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | Liberty | 2025 | 1 | 0
1100000006 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | Liberty | 2025 | 1 | 0
1100000007 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | Liberty | 2025 | 1 | 0
1100000008 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | Liberty | 2025 | 1 | 0
1100000009 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | Liberty | 2025 | 1 | 0
1100000010 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | Liberty | 2025 | 1 | 0
1100000011 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | Liberty | 2025 | 1 | 0
1100000012 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | Liberty | 2025 | 1 | 0
1100000013 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | Liberty | 2025 | 1 | 1
1100000014 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | Liberty | 2025 | 1 | 0
1100000015 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | Liberty | 2025 | 1 | 1
1100000016 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | Liberty | 2025 | 1 | 0
1100000017 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | Liberty | 2025 | 1 | 185.0268
1100000018 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | Liberty | 2025 | 1 | 0
1100000019 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | Liberty | 2025 | 1 | 17.5786
1100000020 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | Liberty | 2025 | 1 | 10339
1100000021 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | Liberty | 2025 | 1 | 179602
1100000022 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | Liberty | 2025 | 1 | 0
1100000023 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | Liberty | 2025 | 1 | 220.6
1100000024 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | Liberty | 2025 | 1 | 220.6
1100000025 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | Liberty | 2025 | 1 | 0.74
1100000026 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | Liberty | 2025 | 1 | 0.74
1100000027 | 3. Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | Liberty | 2025 | 1 | 0
1100000028 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | Liberty | 2025 | 1 | 0
1100000029 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | Liberty | 2025 | 1 | 0
1100000030 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | Liberty | 2025 | 1 | 0
1100000031 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | Liberty | 2025 | 1 | 0
1100000032 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | Liberty | 2025 | 1 | 0
1100000033 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | Liberty | 2025 | 1 | 0
1100000034 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | Liberty | 2025 | 1 | 0
1100000035 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | Liberty | 2025 | 1 | 0
1100000036 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | Liberty | 2025 | 1 | 0
1100000037 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | Liberty | 2025 | 1 | 0
1100000038 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | Liberty | 2025 | 1 | 0
1100000039 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | Liberty | 2025 | 1 | 0
1100000040 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | Liberty | 2025 | 1 | 0
1100000041 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | Liberty | 2025 | 1 | 0
1100000042 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | Liberty | 2025 | 1 | 0
1100000043 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | Liberty | 2025 | 1 | 0

## Table 13
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED OR MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1130000000 | 6ef80bad-a949-4aaa-93a4-ce252d210ff9 | Pole | HFTD Tier 2 | Distribution | 2020-04-10 | 2025-04-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000001 | 27f273a9-f0c9-40a4-b1f5-7e56beb88eda | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000002 | e04d5835-06c4-4f71-a0bc-6ba9b71ed739 | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000003 | 186ec59a-27b4-4a1f-8ee5-e2dcbc4a1842 | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000004 | 0df54f4d-f917-4074-80a7-4da7e13d0a8e | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000005 | 621cd443-057c-44a9-986d-8f806b7066ef | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000006 | 0afe3999-0f69-4626-a966-c0ceaa8b79c7 | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000007 | fd1f5200-6859-4d8e-bea4-ed4554ecbb5a | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000008 | 77b1ed33-c2ab-4598-91cb-4058d358df04 | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000009 | 93655288-925f-4af3-9414-7c432241a9b6 | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000010 | be24cfc1-08ac-4c05-9d6f-9ef610d15aab | Pole | HFTD Tier 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000011 | 21f6294c-a614-43cb-853c-c50f5feb2c30 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000012 | 0883ebcb-778e-44b3-b8b4-6c1767d019ef | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000013 | 9e962665-bc94-4dd2-9062-556c722c2b2c | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000014 | 56e11b57-691a-4697-b525-2cc9925c9d0b | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000015 | 701c1854-9b5d-4972-bca6-55e4a6ad409a | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000016 | 047f3f3e-6600-42a1-8dda-fca0b5418a66 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000017 | 3a463e14-a140-4649-930a-e01b509326a5 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000018 | 04b22eaa-9f6a-4001-b5dc-dc2d078007bf | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000019 | d74dbdce-fd34-4113-9f24-df16414b3790 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000020 | 3f8e7a84-5a1c-4b8c-be93-c7602a4dc1d0 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000021 | bcb0f141-d8b6-4ed2-a4ab-d0ef12527dd5 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000022 | 3d8f4f08-f0e6-4a49-8880-c43fa308a8e0 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000023 | ba9b80e0-fd27-4a50-b92b-8b9fc34dad35 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000024 | c9c4fa62-81b0-4bdb-a049-43ab274bcbc1 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000025 | ad618fb7-6e8e-4ed1-bcf1-d07152b9feb1 | Pole | HFTD Tier 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000026 | c681123b-4b20-473d-bb7c-f7aabb18cf6f | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000027 | 64a178e6-fa47-4970-b56e-0b49b0d1028e | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000028 | ed3fe5c1-1ee2-4792-a1cf-e667c191531a | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000029 | 392be24c-9cc5-4951-81fb-c037186123e8 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000030 | fdcfeaab-dcdf-45be-9d3c-8ef2add63147 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000031 | 704f4cf0-4c90-444c-a9f8-fa3349b3dc48 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000032 | 4203a1f1-8128-4901-a86e-57a0bf730038 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000033 | 7cb55b62-90bc-4884-95a2-717037cc85b3 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000034 | 457c586b-b7c7-4316-997b-efa9afe8c124 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000035 | d0383438-6416-47a5-8811-fa20f6aa4877 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000036 | c1a92c54-9344-4296-94dc-9a4ee053aa85 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000037 | 92609d42-3a00-42d8-900a-c6f62ad88f9c | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000038 | bfe8b61c-6d2a-41cb-a337-8c60da0ca7ac | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000039 | 8f93aa1f-caa1-4ad6-b861-67acb766ebea | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000040 | babbf408-caae-4fbb-9ba5-3609e58c43ec | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000041 | 29507e3e-4130-4f9a-979a-fd16a2e7b536 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000042 | b2841180-667a-400c-b6b2-363f2826e918 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000043 | 3bd638bd-0190-4cb0-a3f1-7de71610b198 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000044 | a902c5a5-04f6-467d-b67f-015295133382 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000045 | 1bdc8b4b-2b00-4962-90d6-94803586f065 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000046 | 0b9c0fe9-444f-4135-aeef-d0a9972b32bb | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000047 | 1412eba2-827a-4857-94b1-f2d0421d01c4 | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000048 | 02691da4-35fb-4a11-8ab3-ec566dc61c4b | Pole | HFTD Tier 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000049 | 51b29948-21e5-4747-a454-690d9129d040 | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000050 | 012e6b14-40f9-40ee-8b0b-129121bbe713 | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000051 | d2f771b4-1fd1-416c-930e-35eab0a3cbe0 | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000052 | 0179ca7d-c005-4946-8475-d588b6401759 | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000053 | f39a5c5a-a70d-4e74-9e85-b442019dd0e7 | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000054 | f726b5d5-5780-4ec3-964c-9b9c75395b64 | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2021-04-17 | Level 2 | 2021-04-23 | 2022-04-23 |  | Pole needs to be changed out due to pole being deteriorated and stubbed. |  |  |  | Liberty | 2025 | 1
1130000055 | 0768ebec-fc3b-4135-aa8b-7f5b7db41a6d | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000056 | 424f1ca0-d53d-4289-a3fb-94a762bf16ad | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000057 | a9275406-a444-4867-b8be-c680679fb079 | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000058 | 5009dcc9-f8c7-4b1b-8499-04d3947f2d23 | Pole | HFTD Tier 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000059 | 65fe869f-1899-4d68-99de-af301e37f52a | Pole | HFTD Tier 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000060 | 53ad3a5b-5149-4e22-9eb1-6a7efbc43ee6 | Pole | HFTD Tier 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000061 | 45c8f5a8-5244-496e-a503-1d2fee48c9ac | Pole | HFTD Tier 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000062 | 4c23040e-31e4-45c2-8037-3a0726091cbc | Pole | HFTD Tier 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000063 | 6a64ce17-1a36-4066-939f-33ddd4490f32 | Pole | HFTD Tier 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000064 | 2395bd13-6049-4d62-9371-f6a71ae5eb56 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000065 | 56521823-2149-49ac-9d56-dc1d9cd34dfc | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000066 | 92f0442e-a417-4958-9667-8c877e5d7921 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000067 | bdb06a02-45e9-4a9c-9f9a-6f2d6b471542 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000068 | 85bb94f8-a5c3-466e-a765-7d91b7ab68cd | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000069 | c23594dd-16aa-43a8-afbc-c6cbccc8a83a | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000070 | 7a15f696-2919-4fc7-802a-00a25ea0b941 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000071 | 011fdb3d-c951-4a32-9f79-0bf6e20719ef | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000072 | 745b7f2e-ec59-44fc-b136-f0642b600204 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000073 | fc442c7a-2fbf-4697-baa0-40f4428d2ef4 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000074 | ef289629-0095-4247-90a8-e676f74b8c35 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000075 | ea8b7c5f-6bd5-40a7-a81b-6d4995b974c6 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000076 | acbf2db0-d5ea-4df1-b4cb-78d4950758df | Pole | Non-HFTD | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000077 | e987f4f9-db2e-4b0e-bc85-dfc9d1490c04 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000078 | cd271600-5414-4423-ac95-425a27d58550 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000079 | d9d62337-45f1-4842-9e75-2828497afee0 | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000080 | d7c82787-3415-4296-a1f7-c6ea3d73180f | Pole | HFTD Tier 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000081 | 2f95c48e-3d8b-426a-adc2-ea226366f938 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000082 | b4272723-6a32-4de2-b80a-58127ad84b42 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000083 | 1680450c-0582-432b-aeac-a5827ee1a94f | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000084 | fe1b98fa-0479-4aa7-bde5-fcd6b95614b0 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000085 | e87f2462-9024-4202-bef6-a8216a7b316b | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000086 | 9f5194d7-7ef2-45ce-8f61-268b60afca3f | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000087 | a73f63e2-0bdf-4362-84b7-f2aebcb3eef7 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000088 | d3b55c3b-f849-460a-b00c-d876394ffe3f | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000089 | 58b929de-5247-448b-a68c-fe41b5e3b24d | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000090 | d191e4b2-3e69-416d-b7e4-1701b534e01b | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000091 | e2ca8f63-ca7c-4267-a107-589ca5e1b013 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000092 | 9fc0ffa7-335e-433e-8a95-79934889322c | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000093 | 2dc6ab5f-32b8-4a7e-a16e-04a265f731c0 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000094 | 2a7d5cd6-c887-4f4a-80fe-2f789e1a9ef6 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000095 | 2c7d5038-f946-42fd-b48d-7f28c4bc4498 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000096 | 6b301545-6b00-4341-a430-7dfeabac34b4 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000097 | 1038cf65-c946-40b7-a2f4-77e5ec3305d7 | Pole | HFTD Tier 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000098 | 41373813-f3a1-40f3-8b6a-51620bcb51ad | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000099 | aeae9bb5-9123-4117-af70-cb9341ba2f26 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000100 | 09d5ec18-7ed2-44ae-898e-43cd5a2e90c7 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000101 | d2f2e459-deb6-469a-bfb6-688ad81186a7 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000102 | 6ca4fe7b-0bbf-4585-aace-3726f01d34d7 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000103 | 9ed46254-7134-419e-adf7-387fe6096557 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000104 | 968ca7e4-8732-4a66-827e-a1f034d16d78 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000105 | 930af33b-56d4-411c-8946-dadb7fca5b96 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000106 | 7d90a458-b5d8-4e50-b1e1-e8902f317992 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000107 | fea88618-8b64-4a43-8887-09db6fceb5d6 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000108 | ce8baa4c-bdf0-4539-b3f4-ea531d8c0858 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000109 | 9b690f08-76b7-4fae-bd57-13d2474b0ae1 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000110 | cd44ea95-389d-42d4-9258-541932298835 | Pole | HFTD Tier 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000111 | 34febe28-5276-477f-8cba-9171b96fee69 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000112 | 65ea9b8e-ebd7-468f-8e2b-a1e84a2bddb6 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000113 | 79fcdf9c-1b78-47bf-a59f-09843066c16d | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000114 | eaabc6a5-7887-4001-b7ab-b68af62b6af0 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000115 | 78705628-d02c-48cc-aa99-f45ce803a379 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000116 | c38ab4c8-f8ff-4694-a012-43c8cad96184 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000117 | 76c823e1-20c7-476c-ad3f-082f1f2f5312 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000118 | 3c571e2b-540d-4e9a-b23c-941815925a0c | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000119 | 83df61ef-a37e-4127-bc92-40be66c53d09 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000120 | 594207b9-1c2b-4223-aa8a-373fb19e1cc5 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000121 | 17be4394-07a7-4e09-bbd5-b7757f645743 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000122 | 14a8e0e7-64a6-4d57-b6fc-60fbb6db1198 | Pole | HFTD Tier 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000123 | 5b2dcaa5-ce5c-4b28-87e8-91db4577ff84 | Pole | HFTD Tier 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000124 | 8b339ae1-63b2-42b9-879f-1369b547f46d | Pole | HFTD Tier 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000125 | b3aa5ff1-2e11-4fcd-8bd5-d3b365476aef | Pole | HFTD Tier 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000126 | af059ab7-70f8-42ed-8863-864a800daac7 | Pole | HFTD Tier 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000127 | ce14771e-9686-4d33-90ce-30fdb3b084d6 | Pole | HFTD Tier 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000128 | 4dbec616-d185-4342-ae3c-bda82bd2db1f | Pole | HFTD Tier 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000129 | 70b70a5e-143e-4355-bff6-e4a5ca6bdf77 | Pole | HFTD Tier 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000130 | 22263dcf-3c6a-415b-b628-cb3020a24d21 | Pole | HFTD Tier 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000131 | e09d463f-2b2d-4cde-83c3-31f82e066b68 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000132 | 0cb86daa-8b95-44c7-8511-eed3b1ff75df | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000133 | b5ef5c4f-9165-496a-bd80-f8f3312b493b | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000134 | 358dbb48-3405-48d7-a534-aa2998c50fb5 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000135 | d7a5be38-5c2e-4e16-98df-e31ad6467bed | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000136 | f947711f-32df-4c92-b4d0-ddb1d2ee18b9 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000137 | d25291aa-f01a-4bf2-aff3-b3d8388fab22 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000138 | f346c9e4-0241-454f-8168-f46c74cae8c3 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000139 | 96d95561-583f-49d0-bdc1-6f4b9b60c165 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000140 | fdf225e1-57bd-4723-bd69-b9442cedb160 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000141 | a58e9d74-fc1a-4044-9f60-0dc239b4422b | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000142 | 052d2dca-85a3-441f-bd7b-1c872bed5b31 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000143 | 86ad855b-a238-408a-91c7-0cfa0f2641ee | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000144 | 14e64303-7777-4f98-a2cd-11d4d0b78db0 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000145 | 85e97c2c-4a72-448a-9f6c-05ac725c2882 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000146 | 58be6e1d-4c82-4459-9369-350933d98e5a | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000147 | 1513cbde-9513-4a2d-b368-c118048e6255 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000148 | 62140000-74be-412f-a13c-323014773a5f | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000149 | 0b20744c-7ce5-46c0-8662-d6ced55ce383 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000150 | 4d87377c-721b-4d68-8e25-42c016158f1c | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000151 | 305760d3-ae78-40be-9883-9813964cc033 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000152 | 35231c4f-2d82-4ed9-8941-f3d334697e52 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000153 | 20b078f5-16e1-41e6-82d1-906a27abb805 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000154 | 1906ceb7-2181-43ea-bb68-72b0f275c8b5 | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000155 | 19f52d03-65ae-47fb-968b-8a6af7f6974b | Pole | HFTD Tier 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000156 | 62c3fda6-08bc-45e5-8acf-64d416454ffa | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000157 | 47eff5b4-e383-417d-87c8-2ae90b78daf6 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000158 | aac3b5d7-4eec-4939-8f72-97303baa8232 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000159 | 89e32e9e-34d5-46ad-93f5-5c81514796f7 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000160 | aa752864-76a1-4ecd-82ce-20979837f59d | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000161 | b1a2b2dd-776c-484f-a18e-0c1c8aee0c98 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000162 | a589524d-986f-4ccc-8eb2-221838a26ba8 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000163 | af3ba445-3fc1-4727-8471-2d77b11eb2d3 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000164 | a331fcfa-a745-4e38-9ff8-696690322020 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000165 | abdccf8b-0d55-4fce-a61e-5237525935d1 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000166 | bbe541da-1c00-450b-b3ef-39beee439c05 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000167 | fea01f17-a03d-4af4-a45b-7a4782fb1f10 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000168 | c33c1b73-5222-437f-9258-b4814fc9cab9 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000169 | c886beca-9c20-4a89-b578-8a6e93e503a8 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000170 | 0d056eb0-3bf1-4fa6-b47c-01880a10fb9f | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000171 | 2110b418-c40c-44c4-87f5-1019f222072b | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000172 | f9bff972-e071-44b8-b006-3aa7695e8c1d | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000173 | 003532a5-f874-4897-86e2-01d263236200 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000174 | c8dd21e1-80c7-4423-b8b6-bce86b47a8f1 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000175 | bee7947b-f1ff-43ce-8cee-9063fc018f83 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000176 | 520771fc-2c29-42a4-a70e-0145754135a3 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000177 | 9321a826-8036-451a-aef9-c8dd8b9ea4a4 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000178 | adcd4bef-d719-4c53-a2a7-642f425852f6 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000179 | fc186ee5-1475-4748-ba65-5b858cce0ce2 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000180 | 4069606d-04ed-497e-a25e-884ebd7bfbe5 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000181 | 15171492-6852-4719-a1aa-18c406ae8fd8 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000182 | 83160693-5a95-4aa8-93c1-fcf36d4afa60 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | 2021-03-03 | 2026-03-02 | [5 empty] | Liberty | 2025 | 1
1130000183 | ce2f3699-c7f4-4fcc-ac90-d21d2f3d8861 | Pole | HFTD Tier 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000184 | 92a0b3d8-e180-4d0b-9528-42d1e72823cb | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000185 | c77635b3-e156-48d4-9908-34bc7f1d966c | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000186 | e55c30c6-d89a-48f4-b58e-81f9225c325f | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000187 | 1fb22a72-3638-412d-8b1d-7e382dbe9a28 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000188 | c54e1d26-1669-439a-94a3-c85444c46491 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000189 | f8531135-6865-4a21-8838-5e5df384c415 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000190 | 837080ef-05b3-4ad7-a623-e84c4ceee013 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000191 | 53b8cadc-146d-402b-935f-e9e4be740132 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000192 | e5ef72ba-a80a-49e6-8809-5298f6f42351 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000193 | a7552d2f-c6c4-47a3-82be-fa035cc237c4 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000194 | e50d8b8c-b58e-4a77-a4dc-618468c9d4dd | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000195 | d5cf375d-7ca2-470d-a1ad-6c35294240e4 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000196 | 9d2004b4-40db-4e87-822a-a2851681477a | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000197 | 41be9fe7-698c-4043-8c26-d6ef61797c6a | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000198 | 7bbeda37-855e-4278-a5f7-15d0f8e2ff1b | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000199 | 58fdb083-cfe6-4863-a8e0-88360b46afc0 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000200 | 1f5e92bb-7e8c-4628-93f0-4678b01822fb | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000201 | 443f664b-94f3-4d72-a10e-3a2e41625171 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000202 | 27e7ed88-e29b-442d-9c11-4cddbcb21692 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000203 | 46e1c6a3-9e32-4d82-bf99-baf27da9ddb4 | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000204 | 4fcfe9b5-fe35-4105-bc41-d71a14ce63aa | Pole | HFTD Tier 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000205 | 0e74556c-089a-4d47-bba2-be11f351b6b0 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000206 | 5be6da19-ee26-4bd5-ba31-722099741d01 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000207 | 7155a2df-d460-427e-8609-99c4e0340b1c | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000208 | 67c19923-31a3-4cdc-a311-9a2b71708c74 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000209 | ab516081-6c3a-4456-ab89-7faee59e4a20 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000210 | 6ad6aa60-8d22-4530-b319-499b4d2d77f7 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000211 | d4e7342a-ab96-4da6-b6ed-a462f7ac45d1 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000212 | a23b456a-f53d-46d6-9e66-600e6da1e621 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000213 | 30dbb492-2a83-4816-be14-3e8a88609e48 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000214 | 430f64f7-a95e-4e5a-8aec-2352fde5a289 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000215 | 91a1d565-acdd-421d-bf4d-96abb48027b0 | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000216 | c79ef9ab-12b8-4505-b97b-d7b8e6264fcb | Pole | HFTD Tier 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000217 | 90799aa6-b524-498d-a18f-795c5aa77db0 | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000218 | 3c182798-e4eb-44fa-91f1-443892bc1d1e | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000219 | d5720fbf-c827-4d09-9abe-8ee9fcbeeaf9 | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000220 | 1d548ab6-014a-4ffb-b7ce-e383eac221e4 | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000221 | db182d75-dbba-4957-adf0-58c264fc654b | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000222 | 513b111c-abdd-4e56-9431-bda8b50ed367 | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000223 | d9f903f5-d11f-4dca-a9e0-63cb69f961fb | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000224 | e0be06f9-e0c3-4c95-9268-cc3d71afcaf4 | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000225 | c165a378-e034-47c4-a56c-a8793eac1a90 | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000226 | 8e2c75f9-0cc2-4c3b-aec3-11e79c446ec0 | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000227 | 147cf57c-8f56-4434-b71d-f9bb704f4172 | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | 2022-03-02 | 2027-03-01 |  | Service to night guard light has been abandoned. Light not in use at this time. |  |  |  | Liberty | 2025 | 1
1130000228 | 143cb5b9-da5a-4e87-a81a-cbe730b6d4fa | Pole | HFTD Tier 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000229 | c5b926bf-86fe-44a2-8625-7488281a4644 | Pole | HFTD Tier 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000230 | 1ab641ac-174c-4edd-9ccb-23e3e8922632 | Pole | HFTD Tier 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000231 | 8b08687e-5a25-47c0-9739-cf881f303a81 | Pole | HFTD Tier 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000232 | d934a254-bca8-4aee-bb4c-769dc670e1fd | Pole | HFTD Tier 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000233 | b6f9b765-443c-49b0-a3e9-393b024e99af | Pole | HFTD Tier 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000234 | ff17b4b5-af21-4aea-88f1-59479d8b8c34 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000235 | 837204a4-0758-4fd1-85da-326293832aae | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000236 | f57052c8-6f90-454c-9868-f4c49bc18d23 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000237 | e60892f0-eea6-4860-bba2-816c5df82afa | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000238 | 46580a1d-244b-4ee5-8c52-7aac3429ca87 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000239 | 2042c71d-3113-48b1-910d-3a5598d405f3 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000240 | 3a473451-21c9-4248-9874-445e3a453a20 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000241 | 9ebe9fb2-4c28-4c29-be37-4f6d213f1649 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000242 | 0ac8c25e-5b2d-4874-83cd-b21898375815 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000243 | d4641a33-7d4c-4016-be19-80a2a185d123 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000244 | a7960325-9bc8-4dc9-84ba-44d10be9929f | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000245 | 5dc8dcbd-7e28-47cb-a413-682c7b17d8c1 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000246 | 576ee34c-4d43-4718-b9ec-0b9a586205c8 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000247 | bb4cff05-4607-4c67-b0ff-28be0df77de7 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000248 | a1985791-bec5-475e-ace0-f2c81d22227b | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000249 | a41c06be-6e87-40e1-a6eb-23e988908819 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000250 | 58e646eb-e8a4-4c0e-8c6f-b6c31c791770 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000251 | 54a954dc-4fa3-4bbc-9a0d-254206958f78 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000252 | 084175f2-7bd3-40aa-96d2-b8366849f297 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000253 | 6cb8822c-adea-4d81-aaa8-4ad0207d5e1c | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000254 | 5dd658a5-7315-445e-8e33-a68d54a67628 | Pole | HFTD Tier 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000255 | 4cd2fd2d-7805-4640-9f59-b3de4e2bc24a | Pole | HFTD Tier 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000256 | 6efa98bd-2c4d-46e9-bb45-897e5fd2772e | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000257 | b38179b8-df64-45fc-b9af-4cb462bbb102 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000258 | 874bfd68-e89f-4621-a4ac-d8d59b2200f8 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000259 | e97989c3-0227-425b-b15d-4280c14cb383 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000260 | 2418d01c-9971-40dd-b125-c30a27636ba5 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000261 | f9c7b66b-de01-470b-a6b0-539f32715790 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000262 | 235a2e58-1007-42c9-ac95-a928de663551 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000263 | 1fe5f67a-d7cd-4576-8c80-907b24a887d2 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000264 | 820e8a3c-6065-48e7-a24b-5c4ad6a3c509 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000265 | fb899cf2-302a-4494-90aa-492ce0cc10c5 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000266 | fe3576e4-0013-4cc1-ac7f-382ffa9892b6 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000267 | f614e3d2-f5a2-45e7-9d2b-e3c6db5d6e94 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000268 | e0f3279e-e97d-4e6a-9bf9-d79700f70a45 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000269 | cb721eb4-3536-4225-a2a7-c99249a8a59e | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000270 | 94606a0d-c0db-48a7-96db-7bbebc17da4e | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000271 | 74588346-5a86-4929-bbba-e2b44332404a | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000272 | 7f7f356f-1707-4f47-bfc6-749ab2a3c90f | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000273 | ed3eb46d-2e0a-46ea-89ea-f0d599033206 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000274 | 7bd01956-df26-458d-b9a3-278c53710e97 | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000275 | 4b0b0d75-3f5d-4893-81d7-65b13c29a2ea | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000276 | 18b77001-1728-4d75-ba2b-c916a2f57d0c | Pole | HFTD Tier 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000277 | 0a472885-8ce2-4131-92ed-98c0b602e0e7 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000278 | 77a6c29a-7286-4357-88c5-e88abb2fffdb | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000279 | 0f734ede-ab67-4b08-ac4b-238ea8069931 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000280 | 4cf81b5d-9aa1-4a6f-9e7f-1f3635736e13 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000281 | 7fe7c6ff-a2bb-4618-b592-1a04ab96f255 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000282 | adcd22a3-3967-4abe-9342-fd24d10b4b5c | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000283 | 9a5a27bb-174f-479d-ab21-c2071e6ab5f3 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000284 | b94a7a26-6cdd-4cd7-97af-900b7adcaffa | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000285 | 43b2ff6f-676f-4578-9be1-a4784f1e40b9 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000286 | f3d542ff-86e3-46b3-9317-60df2c91ccdd | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000287 | 0b593546-fb59-452b-8f51-bda6849fa20b | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000288 | 087a548c-b2ca-4812-996c-539d0ac2951f | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000289 | f2aa4ac3-5776-4e77-83d7-1c60a9c655b9 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000290 | fd267ec2-1b23-4346-b8a5-9d866f5be262 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000291 | c71fa9af-fd28-49b7-8daa-c5b3185298c6 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000292 | b676793a-7515-465e-8bc1-88ff76a3773a | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000293 | bc6a8e15-dfcc-43ce-b08a-b48e58c5b56a | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000294 | d28b39ac-900f-42ba-b1ea-60c1fe512d62 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000295 | ad432d86-1a01-48aa-9f8e-3ed66ed6f288 | Pole | HFTD Tier 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000296 | 93e262df-8418-460e-a1f5-6c19ea22a16b | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000297 | b28ef08d-df94-4e58-b883-314161d25093 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000298 | a5bdce12-8234-4147-aa95-76aff7277f20 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000299 | 974f76a9-a150-495f-b6b7-a5563defb33e | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000300 | 86e0983a-7b3a-4457-a319-a061265aae09 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000301 | 8b861111-56a7-4d6f-af31-978d2a1a8be2 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000302 | 854a7c06-8c13-4385-bab0-1dc63c5de6f4 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000303 | 8696c674-f9d8-421b-8a2d-5532d8e1fefa | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000304 | 86fb0fa0-ced6-4c72-99d7-af0e126b4bec | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000305 | c90447eb-aa47-4c74-9fc0-66bd65536d3c | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000306 | 1b356147-041a-4f4c-8746-d356fe3f94bd | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000307 | c3c94409-f784-410a-9679-b141c109d0ae | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000308 | 9ce10e49-3c4b-4e7c-8f46-4df48a42d12f | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000309 | ce8f30f3-6da7-4ce4-b5b6-cb174cab6f5f | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000310 | f9b1c9c3-bb3b-486f-96f4-19b930b9e6a0 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000311 | fb4a757e-148f-4087-8683-6b0a354f583c | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000312 | 33559564-5257-4c65-bc57-d6b2e7cd39ce | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000313 | 3103430c-6289-47f9-9763-f83bbd411174 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000314 | caa57011-9cf4-4fe6-9971-a5d394aa7353 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000315 | 25ae29be-4599-42e4-8d3e-5068934c3a24 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000316 | d8fb5c1a-36b4-45f0-8fee-7b23c51089f7 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000317 | eeb87e1a-a320-4c65-9b95-42224a8c1486 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000318 | e439c010-30d2-4f2c-9e2c-df2c4bccf5d6 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000319 | 7b7ad3bc-6ee8-4da3-8ba1-39bcaee2ff33 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000320 | ab5603f9-761a-46d9-9507-6f0026706245 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000321 | cab9b05e-dc1d-4803-9b71-dccfb5f12d23 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000322 | 743266c2-5a3e-43b6-9eaa-3a7e2d84499a | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000323 | 6d5824ba-7dd7-4361-b612-39ecf4c43161 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000324 | cd115a8a-b0af-48de-a7ee-55af3c97f726 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000325 | 8c045216-06d7-4459-9b52-cc43d3176fc9 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000326 | bdf9e004-1570-4586-9707-e5b4b61449aa | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000327 | 51c0f373-154d-4214-9405-a977744dbb0f | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000328 | 63ae0f58-192a-4e45-beac-a4c45b78f7ca | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000329 | 1b185877-7b36-4480-bc86-c5c202de6492 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000330 | b8585375-ab22-48cf-aa87-aaeab22f316f | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000331 | 494b5a07-b74d-4cb9-97fd-d9f6a8e6074d | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000332 | a3941a41-fcd9-4bc5-9366-143afd5a4766 | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000333 | b82124c1-708a-4f0a-bb54-392ece6e05ad | Pole | HFTD Tier 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000334 | a8a670f6-3efb-47a8-afb8-07313639c21e | Pole | HFTD Tier 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000335 | 69e3eadc-54cf-4204-b5cd-28aef412dde8 | Pole | HFTD Tier 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000336 | 7f961c1a-6c7c-4797-9760-4dc9a329062c | Pole | HFTD Tier 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000337 | 4fd236c0-7fe1-4b44-9d65-344d7c936ba6 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000338 | a71864ea-0516-44f6-b339-6f40e46af0ea | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000339 | 1e442a4c-6904-47b8-adf6-0df1ad10b047 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000340 | 379b5736-0e77-4891-9545-3cc3a20739a2 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000341 | 1b6164e0-69ec-4d84-8a13-49f4469860d7 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000342 | 77161aa9-b9c7-4a74-8dfe-7809c72fd552 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000343 | 73849316-6ee3-49ff-a442-56599d17825c | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000344 | aa1af4eb-7b46-4d45-92a1-2693d1bbe70b | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000345 | 8d80af29-cee7-42db-b2ed-17324163acf6 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000346 | 64936060-0067-482a-822b-2d137dcb1867 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000347 | ccc09d29-fee6-4267-bc86-cece4a79f36a | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000348 | bc290678-eed0-4999-ac82-496fd9598186 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000349 | 8bac5bc3-a5ac-4c48-af13-76fa21690590 | Pole | HFTD Tier 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000350 | b91850f9-27f5-4632-b7de-7a4bc61adb7d | Pole | HFTD Tier 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 | 2021-07-18 | 2026-07-17 |  | Need HV sign and to inspect neutral Hendrix top to be melted |  |  |  | Liberty | 2025 | 1
1130000351 | 326caf54-c51c-4d5a-bb0c-46bd95233ff2 | Pole | HFTD Tier 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000352 | a5c833b2-094d-4951-a7fe-e4ec3b9e005d | Pole | HFTD Tier 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000353 | 05b6dca4-4d19-46c6-8462-bc0fdecc75d1 | Pole | HFTD Tier 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000354 | ad010ba3-457c-4624-a5a3-b173a5995b91 | Pole | HFTD Tier 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000355 | 06e9d14b-d287-4818-b8d3-3397c8e89060 | Pole | HFTD Tier 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000356 | 8f3369c2-dba0-44b0-afe3-7a77978017b7 | Pole | HFTD Tier 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000357 | ec18621e-b025-4de9-af07-db20384faab7 | Pole | HFTD Tier 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 | 2021-07-18 | 2026-07-17 |  | Pole good and intact, missing above itwms |  |  |  | Liberty | 2025 | 1
1130000358 | 91549a1d-4b9f-485f-9953-ddfddcbe51ad | Pole | HFTD Tier 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000359 | d80e0c4b-16c5-4d4b-9fdf-6db86c2d1426 | Pole | HFTD Tier 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000360 | fb639ec5-b61f-44e2-bdba-796b5490571b | Pole | HFTD Tier 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000361 | fb4048fc-2030-47e2-b626-8570022422de | Pole | HFTD Tier 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000362 | 5f1d6604-7895-434c-8d0b-5f750f554b44 | Pole | HFTD Tier 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000363 | e012bca1-98dd-4843-b9c6-248c74cdcfed | Pole | HFTD Tier 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000364 | 8fba3f55-a097-4e38-a568-12695c576fe7 | Pole | HFTD Tier 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000365 | 89fa3ebf-b907-4136-8ebb-eb32238cb44a | Pole | HFTD Tier 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000366 | 6b8f67ff-67ff-4dbf-b318-3b5688c09ea6 | Pole | HFTD Tier 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000367 | 24219567-b721-4569-9039-9d8da67cdb26 | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000368 | 560f12e2-fa49-4cac-96bf-f27c1762b310 | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000369 | b05a5515-a2e6-4cf2-bbe3-2d377331ee8a | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000370 | 44a5ef5a-0990-4c87-8642-ac9f22725b38 | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000371 | 92303dab-032d-492d-a17c-65cb6a12ed5f | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000372 | 64bc557d-69ee-411d-80b9-965c38e24d50 | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000373 | 6cd22fb0-050b-4df8-ac7f-d45c3520d2bb | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000374 | 5f8d96f8-5dde-4237-822c-ddfa88d1853f | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000375 | fe96cde6-e725-465f-964c-1a786efce1ed | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000376 | 9480f630-f5fd-4e8f-80b9-fa41724cb2af | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000377 | 891678a7-8fce-4958-b836-933d5d8cfc67 | Pole | HFTD Tier 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000378 | 732b30cf-9323-4987-a1fd-018c45039dd9 | Pole | HFTD Tier 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000379 | afcd25ed-80f3-4710-9d92-a76f02827438 | Pole | HFTD Tier 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000380 | 6c4fc33d-43eb-459d-8745-433d7e9736ea | Pole | HFTD Tier 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000381 | 8863c212-da34-4eee-a1d1-2bf7ae2c1d60 | Pole | HFTD Tier 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000382 | c02852c9-0704-4665-94ed-3ab62e39d823 | Pole | HFTD Tier 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000383 | 042ab82f-0c8d-489b-a416-94c06e104e4b | Pole | HFTD Tier 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000384 | aaf293f6-f244-4e31-b52e-b5820a9527b2 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000385 | 8ee9b02e-7d14-4992-9708-1dd748ddb05d | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000386 | 22d87353-89d0-40aa-87a2-209c6e49f722 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000387 | bf6fa54a-f59d-4cf0-8da1-8d7988b0e429 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000388 | e7856048-dfee-476e-bc51-87785f15041c | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000389 | 56019431-6ed3-487d-8338-e116d210dbd2 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000390 | 15b027a4-45d1-48fa-a6f7-ee9afae5fe13 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000391 | f45f5cde-ec6e-475e-b0b0-7b7e550c8551 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000392 | 8619fd70-b12c-41ef-8b54-7dcf5c4788c9 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000393 | 8509e229-981f-4b69-86f6-cf19b8bedcc8 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000394 | d9656d1c-f0d1-4115-a01a-b249ab231187 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000395 | cbca5b3a-458c-4101-99b8-524b13c48d8b | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000396 | aa2afc70-11b3-4453-a8ba-c475c13f3373 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000397 | c374e464-70a4-4a0d-a325-d0bc55efab34 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000398 | bf9d2f32-faab-43b3-84a2-b18dbb39e559 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000399 | ae4833bf-1fda-4e03-8994-6900c6f63ad6 | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000400 | e2625e98-ad3b-4ba3-a1e2-85ed0a6db25c | Pole | HFTD Tier 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000401 | 91a28a7c-fe2d-4986-ab86-f27417a7a491 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000402 | 29810324-acc4-45f7-91dd-d3cecc49279c | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000403 | 80c21f99-d4ff-4301-b9bb-69b8b7163da5 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000404 | 8d2d86b3-ef49-4e9c-a762-b433a843cf81 | Pole | HFTD Tier 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000405 | fd8b8786-faf8-47f5-8792-5e667966c606 | Pole | HFTD Tier 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000406 | 71491fe0-7d6f-4e83-8af1-d79095464810 | Pole | HFTD Tier 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000407 | bf8b8222-f331-4ea8-93e6-3249da62d084 | Pole | HFTD Tier 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000408 | 9535265a-04ca-4a09-b71c-f2a6b1ee6336 | Pole | HFTD Tier 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000409 | 6b27f451-f0dc-4269-a840-d75e5b34b566 | Pole | HFTD Tier 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000410 | 131875ae-3128-4e84-bf4c-efdfc56713a3 | Pole | HFTD Tier 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000411 | ddee5057-698f-42a7-8cdd-1adbdd72fa29 | Pole | HFTD Tier 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000412 | 47fdb50e-08bc-49b1-b030-a1708b0d993b | Pole | HFTD Tier 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000413 | 3843097c-090b-45cf-a84a-0eccbae83213 | Pole | HFTD Tier 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000414 | c8ea586a-a2a0-4d25-bba7-ece86ef09e19 | Pole | HFTD Tier 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000415 | c9aa8721-2594-478d-90ea-a3cc79e75ae9 | Pole | HFTD Tier 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000416 | 0612c414-af3a-4c55-b1b3-de65e27559bd | Pole | HFTD Tier 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000417 | d3024389-ab7e-438f-ba4d-933ef69e9d0a | Pole | HFTD Tier 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000418 | 584a2ad4-6616-4e53-a150-fd7da3df079b | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000419 | eb8ea6ed-a522-4ff3-af56-edcfc06879da | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000420 | b0475d8e-21db-46ff-be02-44d63d9d98d8 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000421 | e891a2cf-274f-4f82-a8d3-ce36bb376abe | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000422 | e80b276d-e60f-4816-848b-9b3fa22c5c92 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000423 | 58b9b3cc-6110-4661-b21d-e7aae29f8c3b | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000424 | ebfa42cb-ce02-4436-b12c-81348cdb782a | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000425 | 04d42b15-f7c7-4887-be1d-39eedb6b041a | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000426 | 2fdf2a14-0af0-4f35-b5e7-3d906b5de7f2 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000427 | 5a3f69c9-cd0b-4b2b-8547-e2c9c7154cea | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000428 | 3f117007-e7bb-4065-bf39-9358ce376e3a | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000429 | 6a481b6e-6597-42e2-b26f-388d05b0b6e7 | Pole | HFTD Tier 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000430 | 212a8d75-764e-40bd-a7d5-384f98ffba3c | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000431 | a3b6a4b2-7c65-4c80-a09b-ccba8dc652a3 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000432 | 2b540719-fc7e-4b37-8568-85fdd48fb504 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000433 | 0b7d1737-4577-426b-b129-c5b15b3b7d4a | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000434 | e97574c7-efd1-44a2-9684-b3d4c8ab40d8 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000435 | adcdfe91-858d-436f-a41b-b179a0922201 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000436 | 250e00df-d4d4-4c89-ae53-a9ca3157d619 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000437 | 1ca119eb-337d-43b3-a385-476e595df367 | Pole | HFTD Tier 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000438 | a16662dc-7d00-4b29-9f5b-c7b468958946 | Pole | Non-HFTD | Distribution | 2020-06-03 | 2025-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000439 | 8e845c8f-03fa-4c64-9a47-101b9a8ffb8e | Pole | Non-HFTD | Distribution | 2020-06-03 | 2025-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000440 | 001b28b1-a788-460d-9767-d6b7fc992dcd | Pole | Non-HFTD | Distribution | 2020-06-03 | 2025-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000441 | be1398a6-2afa-4363-95b5-a5b27b182f3a | Pole | Non-HFTD | Distribution | 2020-06-03 | 2025-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000442 | 166595b4-e30c-477e-b2e0-ce3e384aa416 | Pole | Non-HFTD | Distribution | 2020-06-03 | 2025-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000443 | c93df8b3-40aa-4669-9f40-067e31dbba44 | Pole | HFTD Tier 2 | Distribution | 2020-06-05 | 2025-06-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000444 | 02344e6d-83e7-49f8-9d84-ff2e35b3a6f6 | Pole | HFTD Tier 2 | Distribution | 2020-06-05 | 2025-06-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000445 | 2548c863-b045-48c7-a426-a4ad9bea30b5 | Pole | HFTD Tier 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000446 | 6291db56-a064-4aba-b92a-7e2156cba41e | Pole | HFTD Tier 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000447 | 34d88b01-6c39-4059-b5a7-699ae79b9d5e | Pole | HFTD Tier 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000448 | 06e4038d-c548-4310-bda4-3813c1460585 | Pole | HFTD Tier 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000449 | 671f2925-2aae-4aee-a177-a5a1661638af | Pole | HFTD Tier 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000450 | d43ec500-5f73-4518-97f2-675408b934cf | Pole | HFTD Tier 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000451 | 004cc409-6767-4f47-922e-70a181b3111c | Pole | HFTD Tier 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000452 | ecf79453-46aa-4172-affe-23f89b20b9ae | Pole | HFTD Tier 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000453 | cfe2ccd5-422a-400c-80a6-92875bfed708 | Pole | HFTD Tier 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000454 | 9760bf70-9b7d-497f-a4e2-edb0753d230c | Pole | HFTD Tier 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000455 | fb5e081a-0154-47c7-aa31-2ee4aa6ab4e9 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000456 | 6f1a0b58-bf7f-4f9a-85ab-998425147884 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000457 | 98c62ce5-fdd6-462f-a119-8b62387e241e | Pole | Non-HFTD | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000458 | e6893d0f-e805-4d12-b81a-ff3230f48099 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000459 | bee7bcdc-d2fd-4b28-8ef9-945f5765540d | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000460 | aca4ece7-5ace-402e-8cf7-2154b11186d9 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000461 | 4c6750d6-1d06-4e02-b6aa-74a6a405019f | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000462 | d7fe47f9-c662-486c-b60f-3a561ddb9737 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000463 | 1ec593a7-4f68-4903-982a-0c8ee6dd9ec9 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000464 | 942e4bd1-9fd6-4fa4-a47c-4765099b899b | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000465 | 2ace12f2-9784-4ffa-8c4f-597075c9c8c4 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000466 | dbdc1909-681e-4867-b01b-fd2e312c7738 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000467 | 11658340-a951-426c-bc97-aef0d57266b3 | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000468 | d28d08da-8a9a-4a83-a251-2fed91f2436b | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000469 | 8550362b-1f26-4be8-a3d1-8fd8e75a871d | Pole | HFTD Tier 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000470 | 4d38c9a2-e0ea-4e68-9983-3ec0d32dc3d7 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000471 | 95958bba-fc1b-4c56-b82f-7dd30736e687 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000472 | 5385694c-b7ea-4e2a-9856-aba709463f69 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000473 | ddb274d6-023c-45b8-a868-5e452090d704 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000474 | a4b24059-d2ca-4db9-b7d9-7792cbaa8415 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000475 | 25fe7bf1-8a6a-4df0-ae24-fe9a006c4127 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000476 | a57bde98-bd3e-4ed3-9b2c-c132720e5b05 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000477 | 12588efb-58d3-4dd5-9415-3e45ef959629 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000478 | c2d60c9c-3ccc-437d-a313-29344358e42f | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000479 | 71a92032-cc44-4019-b3ef-03a16dea9727 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000480 | dd961bcb-c36c-40c4-b2ad-c672534e5f52 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000481 | 62958aed-5be4-4e80-941b-315f2de15eaf | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000482 | 43e8f4a9-00cb-4995-8799-b07472ced851 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000483 | 4b3d8b42-ec61-493a-b497-8c246586e6a2 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000484 | 42de0a8e-f463-431c-84f9-74b432827e48 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000485 | 2fac2070-83e2-49dd-8375-65f1ac739517 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000486 | 7a751178-337b-4718-93d3-cfbec13ef339 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000487 | 23e03bcd-46a3-4169-9aa2-ebb46e3b7988 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000488 | 4d75f31c-dc00-4a8f-b2e3-77f5e1ebe810 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000489 | be827ee8-6726-4ac3-958b-ea21d218938f | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000490 | c3e77797-3f5d-4bfb-bc9b-1d6ee05b3d7b | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000491 | 905504d0-9e30-43ce-910f-372bafa149cf | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000492 | 14e4d08b-32e9-464c-859c-206557919546 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000493 | 85725ea5-5553-4e30-b74c-27b04540523e | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000494 | b74d8cd0-e943-4604-9678-6af45864fcc8 | Pole | HFTD Tier 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000495 | f64acb2e-c98f-4038-98ae-5752f7650b31 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2021-06-17 | Level 2 | 2022-02-14 | 2023-02-14 |  | Secondary pole is broke off and needs replaced the tree is holing the pole up now. Not sure if itGÃ‡Ã–s our pole or customers pole. |  |  |  | Liberty | 2025 | 1
1130000496 | b7516126-c0ef-4d18-97e2-f4347694221a | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000497 | ce653643-a75e-47e3-a4f3-44fa8b82ea95 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000498 | 882db907-2e16-4705-8b13-fef0cd1d9fdd | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000499 | 3f660050-96ea-4eff-a87c-21b42e2a2770 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000500 | e009a6fd-a426-4242-b8b3-4aefdbf018c4 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000501 | 602c59c6-4284-466d-b49c-287b8b50a721 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000502 | c1599ab9-7266-41da-8c23-e9beadb09126 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000503 | 5543403c-cd01-4d57-bd23-d62d524d4e03 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000504 | bb98d7fa-2c72-4172-97b0-cb9abe553aae | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000505 | cd740d2f-4fb6-4d72-b109-b5af9413fc0f | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000506 | dce68f65-4f23-4363-93a6-d36f8c80fe9e | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000507 | dafffccc-49ae-4098-b8ea-97f3d339b228 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000508 | dcd2ac25-9eaf-44a8-9117-cd8540ec101d | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000509 | a93d94ef-5c3e-4e55-9aef-0d5cfd6f060f | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000510 | bd5f70f0-e7b1-43c4-959e-1ca538087e52 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000511 | 61e28d29-fb4b-4bd5-a644-a4445d70d0d9 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000512 | ccafc5d3-4780-48a7-92f0-4e3b77312a66 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000513 | 460366f8-75fb-4dfa-a44f-52869b92191e | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000514 | 23ac153c-a11e-4cc0-a74d-5ae3f4dc6f2e | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000515 | 67abe50f-763d-4505-90a1-5c21df6f0b00 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000516 | 2854f145-7758-4242-932b-40d9bf7c1f98 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000517 | bc73a106-27f2-453e-8017-c9de226194a0 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000518 | 363aa800-8034-4a9a-9647-4da1b7e8321d | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000519 | ba8e8ee3-723b-4739-b039-eb771634110a | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000520 | 47620d6b-5844-42aa-a240-480623dd2a10 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000521 | c014fa42-d1d4-48b9-898e-0b1885ce8878 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | 2021-04-05 | 2026-04-04 |  | Arm ok, no tracking. |  |  |  | Liberty | 2025 | 1
1130000522 | 69eb1326-21b2-4ed7-bd5a-3950afb0a371 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000523 | 80b89359-e257-4176-a191-fa0fde99f6d1 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000524 | 274cbf33-8770-4627-9dcf-95c261373c7a | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000525 | 042cd7f9-01c1-4c97-b3a3-2de190df6602 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000526 | 2d92a3ea-bd47-495a-943d-00aa49140d26 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000527 | 8f5a474e-b911-40b8-9956-1a73928a83f0 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000528 | 58eeeba5-cc3a-4625-94e0-dac6000e66bb | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000529 | 121b0a16-9f60-4cd0-81ec-de8f90975d6f | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000530 | 13b2b12c-4694-494b-bf0f-4949db7aa4c8 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000531 | 1849050b-a2be-4d37-9671-dbc35474c58f | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000532 | a7951fc7-f848-4f22-afc9-2a6ffc3a4ed9 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000533 | 3b7a4f42-efa3-4191-85e2-047e738de316 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000534 | 6f0f98f0-b3ad-4932-88db-869aad680f2c | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000535 | 3a7a2532-caae-4be5-bef2-3e7c196b622e | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000536 | 7252cb95-08ad-4ba8-9f0c-93deaf06e8dd | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000537 | 72a5e09d-451f-43de-a3c9-142a2221e2ca | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000538 | 75c6c19c-23e0-4a2f-9093-fbfd6b2c82aa | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000539 | 74385126-e8ff-4b62-9239-6fab093db6de | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | 2021-04-05 | 2026-04-04 | [5 empty] | Liberty | 2025 | 1
1130000540 | 76ca1961-26bd-4a53-8ddb-679109929708 | Pole | HFTD Tier 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000541 | bc082cc7-9d27-44f0-a03f-af80323e9115 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000542 | 733c4f3d-8676-404b-9d13-00014b5fcc47 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000543 | 6ddf18bd-5522-4b4e-a0a5-fc21bcd2a77a | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000544 | 3b41cf8b-8918-4512-bc2f-e96e4d9975d1 | Pole | Non-HFTD | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000545 | a1995b28-ab54-4271-8c21-865137b1185e | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000546 | 8a813efc-1f90-4ddb-81f4-a94aae52ce28 | Pole | Non-HFTD | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000547 | 6187ee35-27d0-408c-b25f-685c6f4cff86 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000548 | 7f4c1647-2eb1-4ff3-bf35-658ac45ba797 | Pole | Non-HFTD | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000549 | 5ea0e2a3-f49f-4d72-a98d-ba8f1bb89e60 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000550 | a870008a-7a56-4e4b-9081-62c247b984f8 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000551 | 4a40846c-d6f3-4ba9-a0d4-4f6c1783bcee | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000552 | 973242ce-6831-40b2-afb2-2ddfaea2e86c | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000553 | 52257f2f-699b-42ac-85bc-a8c0cba0ab37 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000554 | d1ddf84c-9ac3-4f8e-baec-29fb1c328e59 | Pole | Non-HFTD | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000555 | 9af747f0-dcc9-42fc-b9ad-6bbd91be0427 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000556 | b58c4337-fe71-470a-bf88-a860c1441de3 | Pole | Non-HFTD | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000557 | ceefe8f8-5fe1-48c9-8ba9-14f0a6acf560 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000558 | b1046a26-9670-4553-84d7-0244821568b2 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000559 | 0b01c3f8-5563-4fa9-be0d-ef8cee63ab86 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000560 | ac1e9bb3-2479-4d4f-a516-ace320ba0248 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000561 | 3360d1c9-02e2-4969-8c84-88e8fb2a69c7 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000562 | 0e4fff38-eca0-4ea6-9047-e7949160e310 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000563 | d1d7bcd7-6e85-4bcb-80e4-babf3c4eb51f | Pole | Non-HFTD | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000564 | 3fbb4c23-222c-4754-83f9-c06024bc26e4 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000565 | b7751c2c-6be5-43db-88c6-ec1edde17080 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000566 | 35247a14-7218-4971-8115-f2fbaeae2580 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000567 | dc7f9438-4285-4007-bb4b-c52e6a345abd | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000568 | 1f86e085-6bc6-4058-b916-bd7d81948fdc | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000569 | f86f93b7-c168-4c85-ae7e-8f251e43242a | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000570 | 1fedba06-3edc-4961-9265-f421931c2425 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000571 | fdc52b0c-8fd5-403a-ae54-5986169802de | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000572 | 024f1dfa-f5cf-47b7-8c39-bacda515e7ad | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000573 | f3400bd4-188d-4c92-982b-132bd4f1e955 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000574 | 02db2998-be85-4cd7-b008-30ed1fc15005 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000575 | 4d08eb59-41a9-4271-b73b-fa021f7cf60b | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000576 | 0ba37e80-2aaf-4a13-877f-5ef357f58c41 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000577 | 4a76a857-e0db-427b-b038-1bebfdd1c073 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000578 | 00cd6034-90ae-4c92-ab96-ec4797187743 | Pole | Non-HFTD | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000579 | 496409a8-957d-48ed-b939-11e31b43278e | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000580 | 6da1e94a-4500-43a6-b1ea-99040f7fa44a | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000581 | 24f11f4a-c7ce-4fd8-90e2-61a5ce2cf505 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000582 | 5e9e06b6-0807-4bf8-b61c-616fcf2b1ced | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000583 | 14eab584-ca74-449b-8b28-95e18ace810f | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000584 | 43c1b9f4-605d-43c2-af51-403c220536f7 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000585 | 111e8b90-16cb-4a16-be1c-5a78cd98bb84 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000586 | 3d5f3b0e-76e3-49a3-9ea3-45a25874adb3 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000587 | 1a5cab52-5491-4ecc-ada6-38ac1ecf5a75 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000588 | 3923537c-b2dc-42a5-ab41-2b6683866076 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000589 | 016bd0b4-ab54-4578-bebd-54201027436c | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000590 | 3ec938b7-fb1e-4d77-bd02-c1c6d191c956 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000591 | 4639ab5e-ff57-4d4b-b238-41d347b528fd | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000592 | 295e741b-0444-42cc-b9d4-a278db89ba1e | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000593 | 20bf6001-78af-4a0d-afc5-40110335257f | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000594 | 2186f6d4-80f9-457d-a4ec-b0ecad324911 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000595 | c7100f98-1b10-456e-a32e-364fff9b2ae0 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000596 | bffd744b-6f18-4239-bec0-0c1c39ab9b3c | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000597 | be89cbed-f794-4a3e-928f-9f1dc484a109 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000598 | 92db5668-0323-4947-8344-ef1cace2864d | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000599 | d587e5bf-ee41-4e4f-8f09-5fa7de5fc5e4 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000600 | d7ec684e-5593-49b5-87cc-962d05b13cdc | Pole | Non-HFTD | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000601 | d92edfbd-2989-499d-8710-3ef92315e503 | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000602 | 6759a367-0d01-47af-9fe9-ccfedd1ec6fc | Pole | HFTD Tier 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000603 | 9b52c8f2-ad8f-4689-bb38-ff05775d6ca3 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000604 | 2f43e28c-aea0-4720-9649-7d20005f0a30 | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | 2022-11-09 | 2027-11-08 |  | Anchor has been installed and new guy wire as well |  |  |  | Liberty | 2025 | 1
1130000605 | 0e5b9d25-4fb1-42fb-8e8c-1cede50f1535 | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000606 | 9dcda6d2-9adf-4968-bf8f-98defc9706d6 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000607 | 9763e357-b051-4e7d-93d5-fd7dafd2e2a0 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000608 | d70e2f5c-58de-4fdc-9c81-09adebd5a8c6 | Pole | HFTD Tier 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000609 | c8445fe5-6159-4042-82e0-d30b275daf4c | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000610 | d691ca28-27b1-4ec1-bc1c-a711cd2c027b | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000611 | ec7ab5d0-11c9-40f0-bfa0-ad5e59c02b6a | Pole | HFTD Tier 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000612 | d5fac83e-6961-43be-b824-6c76f4005b4b | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000613 | 9a3c901c-ec77-4714-9858-197191b3277e | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000614 | db3a2ec9-db5d-4664-990e-acee3e624953 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000615 | 9eb03c0d-d84d-4c47-ba5b-4dd9e449f92e | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000616 | e5b1e486-53bb-4adf-918f-e0864c6da55b | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000617 | adb95c06-6aa5-467b-9fd4-e4ccad54ab5f | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000618 | efc2d95c-e966-46b4-8cad-b1a9a0327fd3 | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000619 | f6a88c60-ba9a-468d-b550-240f277ba0f5 | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000620 | 239a01e1-ba2f-4513-9604-c58cca19516e | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000621 | 11307c9a-348a-4634-a842-17b2bc617e8e | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000622 | 265debab-6d68-4896-b119-01dc4f5fd30b | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000623 | f42dd436-4f49-43e4-846d-f473d1497df0 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000624 | 2dc10e8c-43ce-4889-9c0b-9571509d83c1 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000625 | 1f5076f0-909c-41b7-a5fc-b526edcd0171 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000626 | 7b093877-434e-4afe-82a3-0634ff7c2009 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000627 | 14b1b9bb-6399-4855-b711-9434da84ef08 | Pole | HFTD Tier 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000628 | 173567e0-cb2f-48ba-b379-95c413e4bbc5 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000629 | 0c384509-d31d-4f33-bc00-eee02296eb58 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000630 | 3f0aede7-2193-439a-ab5e-275d34e83af7 | Pole | HFTD Tier 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000631 | 11155b4e-d8a1-41de-80d1-721a10a46e01 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000632 | 4c853d16-73b0-4d07-99e1-fef395e67089 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000633 | bacbba9d-24cc-47d8-be54-5e0f4ac4db19 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000634 | d2b0813d-d7c9-41ee-9100-aaeab7ef8491 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000635 | cd6e785c-855d-4582-b955-f6b5517e27fa | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000636 | 945e5153-e460-4407-a38e-134b5a338b22 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000637 | e77bdbf4-a4f2-48ac-a141-9522595cccc2 | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000638 | 9b54d2b3-f79e-4b3e-93bf-4e02f4c577de | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000639 | a20cec94-5e73-4bb6-8753-d9fbe4874595 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000640 | 8dd92974-28ab-4178-b432-222e3bf66269 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000641 | 6a0101cc-b040-4785-a94d-6dfead3e4d35 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000642 | 2ca32e57-453d-4d14-aa06-2e98922bee0f | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000643 | 5397419f-3760-4435-9aa1-7259d14586ba | Pole | Non-HFTD | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000644 | 5cc87c91-672f-46a4-8132-e2abbb4528de | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000645 | 62b1cda1-254c-4bc1-bf8d-ca12df9f39d2 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000646 | a416bccc-e385-43bd-901f-6ef2f22a7f6f | Pole | HFTD Tier 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000647 | a4738ee0-32a1-46b0-92e3-8d9bfe6cf5ad | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000648 | b3978a2d-c517-41ee-b407-11a585bf96eb | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000649 | c11f75fd-d5cc-4832-a573-24d7abe136c0 | Pole | HFTD Tier 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000650 | 7dc399fc-6b05-4983-9192-bb113b582d0d | Pole | Non-HFTD | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000651 | 45060af8-637b-4b2d-b4f0-f8054ae16143 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000652 | 8361087a-9c3e-4fa0-aeff-af3355203f1b | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000653 | b88f5c63-1dd2-42be-8e24-594eb0d77642 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000654 | 79b23a67-d2e3-4ca3-9516-d9a10f2b7a40 | Pole | Non-HFTD | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000655 | a925c989-d261-4fdb-b7a5-7d5faa313422 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000656 | 912e00e4-d44f-4eba-a324-3c6cf9f58ab4 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000657 | 6a3cc61f-514f-4585-809a-ef0783b4978d | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000658 | 8f887f03-f5a7-40b3-9eb8-89626a5bee4a | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000659 | 9b003c92-caee-4c4d-b18a-16533f830aa5 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000660 | d0673a44-eec4-4dbb-a44e-98fd9f20a746 | Pole | Non-HFTD | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000661 | 671568b6-3d67-4abd-b075-b73a46ae9be1 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000662 | aed855f3-a0f4-441a-bd87-f53090f00454 | Pole | Non-HFTD | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000663 | 5a3b9384-33f6-4c84-bc81-9de47f7f43f8 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000664 | 12abae04-4c2a-4f18-84ed-89e038e285e9 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000665 | 485fccae-0846-4c6b-bcbd-841bee744d31 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000666 | 17ff1c88-8438-4a22-a3bb-f81a46a9b9e9 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000667 | 039d7ab9-5c89-4a2b-9302-08d477fabea0 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000668 | 1a28444f-0187-4d71-b066-4d637bf88df9 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000669 | 05856d6f-64e6-4102-9c88-f6809c0e9015 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000670 | 21dd1f4e-acec-4c91-bb6c-541016106b53 | Pole | Non-HFTD | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000671 | ee4aa1a6-ecbc-4a80-9018-bc7d3c2faf98 | Pole | Non-HFTD | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000672 | 5591e8ed-22be-45d7-96ec-1d89c99e28f2 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000673 | caad1ad2-21a1-4f6f-a931-7007a1c44fd2 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000674 | e5ed5acf-f90e-4443-b65b-49640baf5228 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000675 | ca6b90d4-2d4c-4056-ba6b-17f5b42947a4 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000676 | bcf04c9f-c76e-4d6f-90b2-5c88e4449b1a | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000677 | 44a3ef4b-98db-44d4-8a4a-eb043aa2ce8f | Pole | Non-HFTD | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000678 | 98724d3d-0e04-4127-a63d-89ced6dff3ad | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000679 | ef92b9c6-19de-4e27-83ee-12d8e99d778d | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000680 | de4b462d-ce0a-4f59-8d16-a1cab842d645 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000681 | f1bae1e0-c81d-47c7-9a49-b853bbaa8ea7 | Pole | Non-HFTD | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000682 | e030bb8a-cd30-475f-8e01-f23227c4d985 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000683 | 2476a927-6cc2-419c-a714-ac75e5e74f41 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000684 | deea4bc9-9ef1-45e2-8793-8c515cfc3031 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000685 | 34bd9831-dd25-45ae-9a5a-8505b1a230bd | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000686 | ad226c8a-0447-4453-ac74-ecc11dc58ac4 | Pole | HFTD Tier 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000687 | 61b6aff5-e6f3-4937-9cba-acb41beffd60 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000688 | a7cec7a9-9054-4fb7-8450-8b2d6283c877 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000689 | 698d282f-292d-4df2-bf40-834e8800b482 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000690 | b0a7f69a-37e8-4f80-94bb-32d35df8528d | Pole | HFTD Tier 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000691 | 29956b7f-ec0f-43f6-8fe9-f97990686847 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000692 | 19ae9250-ec80-4d6a-bc85-28213d7eca13 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000693 | 5570b5d7-33d6-4d2f-b389-06ed8022b1c3 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000694 | 04bebec8-8a5a-499e-839d-5f3635adebc3 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000695 | 10a25420-c12b-4fab-8fe0-7785fc4f162e | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000696 | d3b88be7-2c4d-4dcd-8965-8961cb73e174 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000697 | 1483d12b-e665-4576-aa1b-b010a6f21d74 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000698 | edf83bfa-6151-4eac-b63e-33abc518b217 | Pole | HFTD Tier 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000699 | 10994a1c-e862-499d-99aa-5c0d1d1a5721 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000700 | e80a4238-bee0-42f3-b4e2-a34b34278291 | Pole | HFTD Tier 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000701 | b49ba89a-e2f3-43d4-a762-1b64c9673c63 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000702 | 6ecd1eca-1fce-45b2-abda-82b5e17cea38 | Pole | HFTD Tier 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000703 | aaf091ac-d100-4aa7-9d32-ce8d06ff1d19 | Pole | Non-HFTD | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000704 | e7b77432-b78e-476f-9b9c-3c0c11045415 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000705 | d2682e02-7aba-4199-998e-69243c831842 | Pole | HFTD Tier 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000706 | 3e82aae9-a5ca-4755-bda8-016105f231ba | Pole | HFTD Tier 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000707 | 98ffcd3a-418b-4b1a-b964-c67028f62714 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000708 | 0b7c5dae-9b47-4f96-a4d2-7b64a75f7eb7 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000709 | ab11dd14-a0e5-4887-86ac-2c345dadd443 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000710 | e8218af6-7717-4d4a-a6b2-b1ba075e47b4 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000711 | 70339f64-6fd3-423f-91c0-197b9122e000 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000712 | f1834de7-8c0f-4f89-925b-8aa0436bc679 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000713 | 8c5882e1-dac8-4d1d-b0c5-192a405036bd | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000714 | 4b8791d8-ceb1-4a03-903e-a072c1a957fb | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000715 | 874e2e05-029c-447c-b6fe-9f4b8c57c95f | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000716 | 4cab09c3-8c60-4b58-b7ca-15f48cd94d07 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000717 | 54d42a26-1e38-4522-b8d8-fee85db89470 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000718 | bfe55a0f-3a28-441a-bdc5-d2e672bd5494 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000719 | c1db789b-2672-45e7-8b51-6223e1e69bee | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000720 | c3f2cbd6-ac4b-4ef0-aded-0cb7172a17e8 | Pole | HFTD Tier 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000721 | 87d3f39c-c1f2-4dce-834e-341f0bec52da | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000722 | c2866058-dd9a-42d4-8f90-cfc688e0cd46 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000723 | 71af0cbc-2934-4f81-97af-86d4407feb7e | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000724 | c4a45a4c-57ae-4334-a2c7-311ae6cfcf82 | Pole | HFTD Tier 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000725 | 716caf31-a3a5-4db2-bcef-9d175a8c12e4 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000726 | 56455d3f-cae2-4fdd-914e-46f91b0be54f | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000727 | 7b899d9f-eec2-4024-9b71-2ece1dcb79b3 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000728 | 52987523-dfe3-4bb6-aedc-c09e5df517e2 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000729 | d0228653-c7f8-4087-b513-ff1b4c937371 | Pole | HFTD Tier 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000730 | 4c864429-e355-4b71-afdd-21c5ebec5d02 | Pole | HFTD Tier 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000731 | b0aceb20-1ff8-4fe3-bb30-314f7b6d3db9 | Pole | HFTD Tier 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000732 | 49b74be3-0168-4d1e-952c-4450c7981ef9 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000733 | 26339124-825e-40ec-915a-fffa7052bdac | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000734 | 4b532bdf-88a2-4bb9-818c-d9127e2df87f | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000735 | e4429fe8-ede8-472f-b03e-00757d01375e | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000736 | d8a89991-219d-49a6-9a63-6febcf5a043d | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000737 | e3088ea0-f521-4bef-87fb-39cdc23e2bc5 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000738 | 02e58939-3c4d-4c0c-8aa6-205e085404ab | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000739 | 7b858153-914b-421c-98bf-79e93c373e0a | Pole | HFTD Tier 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000740 | 06afd339-c8d3-43f6-8464-7542998c4fc6 | Pole | HFTD Tier 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000741 | a4ff24a2-2757-43c8-ab0d-f9472decfbd1 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000742 | b1c14276-328a-486e-a4e7-6a67621b65a9 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000743 | 79396c85-28dc-41b7-97c0-10fd468e20ae | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000744 | a929ad9d-d48e-44dc-a3b2-bf54d8d7b99f | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000745 | 7cba5a89-d7bf-4934-8bea-36aac7c87da1 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000746 | 2bc59a40-d6a5-45fe-aad7-ccce00411051 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000747 | 44b178ae-c3ba-4f53-b211-e946903f463a | Pole | HFTD Tier 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | 2021-04-06 | 2026-04-05 |  | Pole top ok, arm needs attention |  |  |  | Liberty | 2025 | 1
1130000748 | 49191429-dff4-4d4f-a0d5-763c6a9305a3 | Pole | HFTD Tier 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000749 | 8c3df28b-caed-4749-a636-9b10cd12e431 | Pole | HFTD Tier 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000750 | d3efbae6-5a18-46b2-a87b-c0cc3b2dd8b4 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000751 | 1fffa40f-168c-4c5a-96f3-7ace5c433a87 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000752 | 51c12225-f0a7-4bde-bdcf-9be7fb3184b5 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000753 | 2cba7531-2b01-4ad6-a51b-c13d65176e13 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000754 | 6117b049-b1b7-4db0-97de-9b4d446a95d0 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000755 | bab2724b-f600-43ce-b63e-3c69af96fc57 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000756 | a3c0c5f7-c4e0-4669-90b5-4b324db82ee0 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000757 | e13a886f-4473-4389-829f-b8786a4c08ef | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000758 | 1f727005-d03d-4c80-b788-8b9f61afd3c2 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000759 | 90edf98c-3ea8-4aec-952d-32387489bb11 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000760 | bbbbacdd-82ac-4f75-a7e8-a7f6b3973088 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000761 | a76bcf26-87cb-4275-955b-582f6152e6ae | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000762 | d5253ffb-2d0f-4d58-8ade-62e43808e029 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000763 | c192c0d3-89c1-4ada-8475-774403aec93f | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000764 | 271dbae6-d155-4640-a474-23b6db1d9ab7 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000765 | 9e07b871-8577-4097-9c72-79efca0bd079 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000766 | 104366a6-69a6-4bc2-b570-c221d630521f | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000767 | 2ed05423-321b-4ad3-a8b2-caa4c423738b | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000768 | 2b43afe4-ffc3-4b43-9ccf-dba75c65bcdb | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000769 | 4da846b7-2d95-4710-8a88-0e60645e55b8 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000770 | 5cf7502e-b68f-4b18-be04-b0f14b66f219 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000771 | 7d031917-c268-45e9-99ce-9c1c631ae30e | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000772 | b04c6fff-951c-4d53-ae63-a00d2ba076c9 | Pole | HFTD Tier 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000773 | aa4a4f89-550c-434b-a987-2d285f6f57a5 | Pole | HFTD Tier 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000774 | 121083f7-cab6-402e-a038-b8b0d40729ed | Pole | HFTD Tier 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000775 | 17cc363b-bb3a-48fe-a6f7-ab19fc71200e | Pole | HFTD Tier 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000776 | be2c8d00-3ede-4f6c-9f34-fcc520ce8885 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000777 | 28228cbc-9c8c-4a42-acaa-8b5e532176bd | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000778 | fe200f70-1456-453e-a343-aab9690db571 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000779 | bb7900e9-22fd-4f03-9f50-549f3dac6d84 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000780 | e4951624-5c90-4133-a059-7ccd435c250a | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000781 | f43b4113-1e8b-4972-b255-6e7de666817c | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000782 | f71a341e-40c2-40dc-adcf-f7dda7623a1e | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000783 | 74b35813-f04c-42a6-a9e4-786970a9f75c | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000784 | afb77e87-6c87-467c-845c-6729d5c06cdb | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000785 | 7ab4984f-0e02-429a-a669-a28fbacb10a1 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000786 | ad7985d4-cd46-4f6e-84ab-61f86cc488a9 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000787 | 5d8e0cb4-a54a-4b14-9d5a-06f07a5076d0 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000788 | 6f49de98-44b8-42bd-9d32-cb230f76f77f | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000789 | 9ef8814d-191b-438b-bfcf-85d36dce3c7c | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000790 | 85951483-a278-464f-9fa7-0b3ba767d66c | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000791 | 14635e22-68db-492e-9390-bbb0b42f63eb | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000792 | 7d6d4e47-cfcd-4bf2-8b92-3dfde0dd8885 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000793 | aac4a932-fc7f-4c4e-9b8c-08537c9388be | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000794 | 410c85d8-c60b-4a47-8a2f-f518a34aa65a | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000795 | b957b650-276d-451b-8bdd-699c7dfba05c | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000796 | 10929716-ffdb-4809-8965-18dca0f94032 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000797 | 3f81c4c5-4e27-44c0-b0f3-8133c8a04c53 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000798 | 153a8b97-1037-42e1-a826-3e07d0398f0a | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000799 | 4761d2bd-df55-40bc-8b3f-685d08c65b50 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000800 | 3616faf2-70ac-49be-9038-f43a55d4a132 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000801 | 45b9385a-ff0d-46c3-a387-e629de452425 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000802 | 4a1ba934-7f4d-45fa-ae17-00b0aab98e7d | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000803 | fc4b0c68-1e8f-4ab5-9f5f-7f0481f8e37f | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000804 | 676309f5-4399-462d-bbe5-56f3eba2a109 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000805 | 037f1e9c-2fa5-4b2f-89d7-94b71533a86e | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000806 | 44f132df-06a2-4366-997f-abe300570334 | Pole | HFTD Tier 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000807 | 36de26e1-3f94-41d5-9cda-19889db7dc32 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000808 | 433a0535-2570-4e23-80d4-12c2fc438f06 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000809 | 147fb4d5-07ca-48c7-a541-91de53d4cd38 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000810 | 4148eb72-d1f1-448e-a4ee-f37ed6088bbc | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000811 | 0eea7117-0804-4eb3-8dcb-7b4b51b1bd60 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000812 | 09986968-41e9-4962-b795-6364930f9a48 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000813 | 1284b4d1-d833-429e-b933-a357e900a647 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000814 | 3ca0b151-623f-4e70-8f50-4250096f3517 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000815 | 37a47cf5-337d-4417-83c7-9b9e7b2d5d0a | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000816 | e7c7ceef-6e7f-4598-a673-b144b1c37c20 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000817 | 3d588a01-bbcb-494a-a689-113ef6616ad2 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000818 | 94d58262-0436-4c54-9bad-7125a07b2dc6 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000819 | 5333a12c-2e6e-4519-8b85-1a1564e03492 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000820 | e442d116-3c58-4eee-a889-3832325663cd | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000821 | 72bc0fba-0e18-4f06-9b8f-91ba2213beab | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000822 | 69d727d2-eedc-4298-9e8f-d3d62cd4e230 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000823 | 85ef6292-47ab-47cc-b945-fc2cdb60db9e | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000824 | a0b71633-ddd2-46c1-a6e8-e9a4b830df0c | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000825 | 712d8bff-7077-48ef-8ed5-a30cc9ce6fd3 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000826 | 6eabcfea-503c-49ff-b0fb-37889e91c08d | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000827 | 78b36adc-1733-4dfa-87a7-4a106a55ca90 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000828 | 8d0fbcf8-a48d-437a-b2ae-1620829e3d9b | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000829 | 72696d1f-1fda-4026-9d7b-0d38893f9287 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000830 | 556905b2-b911-4435-bcc2-364dc56bf95f | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000831 | e35752c3-be1f-40d4-ab58-98b3e3af8ba5 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000832 | 3969bf77-0256-4c83-b6a1-e5b79a9885ae | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000833 | 02ef93b2-f9e4-4147-88b8-94e6bca6ce8d | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000834 | 3b821410-34b9-408e-ac3c-e0fe85a9607a | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000835 | 9a1d3ded-fe52-4a59-a37d-6f97683426bf | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000836 | 603d293b-69d3-42a2-bd67-cc8b06f420c9 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000837 | e242ea4e-dd01-494d-9d35-b9cd1c397f61 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000838 | b0acd8a7-018b-4433-981a-0bdcfba8283c | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000839 | c3faa75c-5ee7-4d1d-900d-926287bef9c0 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000840 | f28f6101-8cd5-4d7d-b260-cd6aa9b2bfe5 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000841 | 187a3b78-cd7f-46b2-af5a-3b67deb63aba | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000842 | ce9c74b8-5406-4376-b450-30224704c272 | Pole | HFTD Tier 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000843 | e366110a-a17d-4d19-b020-4ac22956f496 | Pole | Non-HFTD | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000844 | fac8e6d2-6fd7-4a4d-8eb7-cecbaea24ab7 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000845 | e1fdfed8-d81a-4ac2-850c-4c8748bb721c | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000846 | 4816836e-d108-4928-95ff-bd9d22bd442b | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000847 | dddaf571-a30b-48dd-9bfc-345a72ac7d1f | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000848 | 621f1f70-d18a-4baf-a929-88724179afcc | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000849 | 21a861eb-0df7-466a-ae53-7c35c80d8164 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000850 | 94f93e8f-bfc5-4d7f-8645-6d4d3784b6f7 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000851 | ae900de9-ff22-4fd3-9141-a073c1bceaf0 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000852 | 504c40b7-cd0d-4f19-b30d-2e869850c6c7 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000853 | dec80bf3-ee49-4446-a0e4-a62785713791 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000854 | 44962482-c053-4446-9e43-8ff3c0b98109 | Pole | Non-HFTD | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000855 | 6b714a30-3bd4-4a5b-beb7-4aa4e85b633c | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000856 | 442ce52a-3ccf-4667-8b12-ab57d047ee6f | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000857 | 1e1e89d4-14b7-4fc7-8322-8afd029686a1 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000858 | 667dd612-ac84-42d9-b97f-8c04b6c2e2b1 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000859 | 6ee4fa0d-2562-4aae-9f07-00203a52bb61 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000860 | a6d73656-12e9-4681-abe8-0ad1733ddda0 | Pole | Non-HFTD | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000861 | 2107f36e-a842-424b-b58b-a6556228af91 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000862 | f136a2cb-4126-4ff4-97e9-be365ddb5961 | Pole | HFTD Tier 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000863 | 2e6afe47-8b4d-4b91-b05d-ea09faae6ebe | Pole | Non-HFTD | Distribution | 2020-06-29 | 2025-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000864 | 0d50f5e0-6b86-42ff-a529-0b77f181e8ac | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000865 | 0f0c18fa-ed86-4758-89c0-d19a7d095d38 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000866 | 0399be6e-35f2-410b-9925-5c644135282f | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000867 | 6adfa1cb-43a6-45dc-9c0e-9721bd8447d1 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000868 | 0398fe52-2ba3-40f5-baaf-591472bce0de | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000869 | 9dd71ebf-c328-45f5-b058-277917ca4169 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000870 | f73768b7-aef2-4297-a9b1-ac19bc9dcefc | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000871 | b10a44e0-31e3-4afb-a6e7-be0e9156b789 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000872 | e6c5804a-585e-4dbc-94d8-71c18cbaea2f | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000873 | b569d043-9aa1-47ae-a254-853040276277 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000874 | c2a14c40-f9af-4f1f-a412-0f929e414227 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000875 | 74bac55c-1eb6-47d5-83c4-0b00cda2400c | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000876 | bea4a1a8-d14b-4ac1-9c7c-6610cd1db4a5 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000877 | f9d98c21-da5a-481d-9141-b5b3e241c58f | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000878 | 5311c8c5-d4d3-4f79-ab1f-481dcf41bd9c | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000879 | cf7186fb-1763-44a6-9ee6-988cc6ae9297 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000880 | 52d25e4d-c469-4fec-8fe1-80762dc82227 | Pole | HFTD Tier 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000881 | d566079e-d3f5-4e65-b35a-e17117275520 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000882 | 17999798-87f1-4f99-b1ed-db74f51fb5b0 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000883 | 8c09ced1-900b-40fb-9b43-5153732e8573 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000884 | 26456949-a6fb-4af8-a1ce-169b430c9b9d | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000885 | 713a99d7-169c-4c4c-ae37-fa558a197479 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000886 | cf2407c0-3a11-479d-9dd8-e9c11ecf9df7 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000887 | b514cd60-bb09-45c3-8ff1-588f8b6d8191 | Pole | HFTD Tier 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000888 | 7ec94654-ca3f-410e-9ac5-13236eaa97d3 | Pole | HFTD Tier 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000889 | 4e92bd42-3149-4c89-8703-ceab0a955c16 | Pole | HFTD Tier 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000890 | b1fe51d8-68e2-4ac2-863e-f9a5efb7affc | Pole | HFTD Tier 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000891 | a9621bf2-8437-4ea5-910f-6db8fd57ef01 | Pole | HFTD Tier 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000892 | af23feef-c4b6-4a8f-ad12-492cf6b94286 | Pole | HFTD Tier 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000893 | 0cdcfefa-585e-4411-8005-f3ba4439e79b | Pole | HFTD Tier 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000894 | 9314ebea-407c-452d-97ed-5a114b37a1cb | Pole | HFTD Tier 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000895 | 52ebe1db-c269-4f7a-8371-f92894b3dd9f | Pole | HFTD Tier 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000896 | 728285a9-0039-4f09-bd8f-b5e3baf66d8b | Pole | HFTD Tier 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000897 | 62e557c2-ef6e-41d1-bbec-eb0e9f0b96a2 | Pole | HFTD Tier 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000898 | 21e0c81b-36e8-40d2-b1d0-d8e616cb36d9 | Pole | HFTD Tier 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000899 | a3b24d15-6bad-461d-809b-8b4e55389976 | Pole | HFTD Tier 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000900 | 638f8a87-2f23-4abb-8016-c16a2d31875c | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000901 | d8189565-6f54-47a3-96af-37d0e0c8cb1e | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000902 | f900cbb5-a9a3-491d-950d-c438424e3497 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000903 | c5affcf9-f7d4-4d53-8365-4554100de38d | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000904 | 0d59c623-85e0-4a88-81f5-75c003a6efa1 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000905 | f5680546-7a1d-479a-bf7e-ee89a155881c | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000906 | 2fbaf27d-5e82-405f-a1ba-850e6bbe4949 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000907 | 490d302b-80fa-4c9c-9c35-2c8584ef34bf | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000908 | 5995cc07-d3c3-42d2-9493-28fc9097cf98 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2021-07-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130000909 | 5c3f7a04-ad4c-4dd7-aaf3-c2d0d86848da | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000910 | 09789e8b-a0a4-451b-ae99-4fdc82a78836 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000911 | 6650820a-acf2-4374-b578-87596ef5a20f | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000912 | db9f0799-2bb9-4f61-a4f8-901221e66b31 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000913 | 57c7666d-c431-497a-b51d-a1c9ecacf456 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000914 | 88d655b9-11c2-469d-aa38-a877bf790a8d | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000915 | 75c12d75-f7ab-4d3f-956a-5e83cc171ea6 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000916 | 3c0eb500-e11c-493a-9f08-4bb1c84b3562 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000917 | 509f1361-6031-43b4-923d-ff8b75fa87ba | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000918 | b50dfc88-e6d6-4861-9730-67feea529433 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000919 | b983ea63-2431-4771-a381-96a53ce83e86 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000920 | be79c0fa-1065-4be5-ab0d-09bbf3bcfad4 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000921 | b4a13217-5857-4480-997a-a7fa3a142f31 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000922 | bb43f43b-84fe-433d-aef7-325e4f26608a | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000923 | b8b29138-2ce1-4ce6-b1df-d2c4cdf4b0e8 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000924 | 162252b0-ea0e-4964-ae08-628bc0d93fd2 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000925 | 3099c0f9-3ace-4cae-8478-f4ddd8ff247c | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000926 | 20b61a44-5209-4ce0-b705-5067d2780bfc | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000927 | 96d8d3f2-57a8-4a90-a89b-5e198f305d84 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000928 | 7a755d73-b3aa-4eef-a717-16664cbf4b66 | Pole | HFTD Tier 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000929 | a510252a-8b76-4c18-8595-89194a2d5827 | Pole | HFTD Tier 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000930 | 932a79dd-1490-416c-bc1f-322b3541d400 | Pole | HFTD Tier 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000931 | a4515193-5a42-4a24-a5d7-6e865d9c9121 | Pole | HFTD Tier 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000932 | 88599f80-4282-4c60-8dfd-b74de6ab0141 | Pole | HFTD Tier 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000933 | 44402463-686c-49d2-9db5-3750d3c03ac9 | Pole | HFTD Tier 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000934 | b7e626c7-1448-4dd2-8ed3-7465dca1f582 | Pole | HFTD Tier 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000935 | 62a85437-6942-408c-af20-a47ff7985bbf | Pole | HFTD Tier 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000936 | 07b47977-02ab-41a6-bab0-a2f5302dccdc | Pole | HFTD Tier 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000937 | 6aacb92f-84a4-4e71-b7a6-41208188f31f | Pole | HFTD Tier 3 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000938 | 367eb169-e2da-450c-b405-e9da58bd38e3 | Pole | HFTD Tier 3 | Distribution | 2020-07-08 | 2025-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000939 | 28de7189-4749-474b-8420-97a96eeee4ce | Pole | HFTD Tier 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000940 | 4a8b18bf-13ce-45e8-ae56-e7419af93bca | Pole | HFTD Tier 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000941 | 7f6c9254-b686-4c48-9886-03ae426df60b | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000942 | a0abe18e-3705-47df-bf18-b480954c0e2d | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000943 | ffeeca76-70f8-491f-add1-5b6698252e01 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000944 | a1f9a0a2-e669-4fb4-a817-a2d105e65044 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000945 | fb871fe2-feb6-4397-a61b-be3cd4ff418b | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000946 | a1cce40d-56c2-42eb-8d3b-3f2bab0ef617 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000947 | ae881877-ae5b-4df7-be28-3b08c4886ce6 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000948 | 7a933010-5609-4515-ab08-3a982ae744df | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000949 | 94670d55-bb6c-4b2b-90a9-60cfa5b4fa0f | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000950 | 72aca320-85d9-4a46-85a9-4b5ead644d56 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000951 | 284aba57-8f5a-406e-a1c2-8a5249514420 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000952 | ec82d171-f80f-4c41-9fd5-3e15894b2942 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000953 | 389e10e8-a939-4438-9e46-f5911de6b854 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000954 | 029131b4-0785-4c56-a449-d29a9f038cc0 | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000955 | 6fc92763-275d-4223-b5f8-d6dc1fdf00af | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000956 | 7c8dc814-d882-4c81-8df4-372dd3c350ef | Pole | HFTD Tier 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000957 | 217869cb-f684-418c-9654-6378bf3dbddd | Pole | Non-HFTD | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000958 | 749c4458-f0ef-4a06-a7fc-a81f415b9e72 | Pole | Non-HFTD | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000959 | cd1090b9-c0f3-47a0-9d79-3f4123ffa402 | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000960 | 75253ccb-161f-4d9e-9845-9208899056a5 | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000961 | 56873713-bee0-42aa-bdd0-67301e8755f6 | Pole | Non-HFTD | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000962 | 74ad17b2-94fa-484a-a23e-10219704ab89 | Pole | Non-HFTD | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000963 | 63c5c14f-7b73-4783-9033-a0d6afd485c7 | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000964 | 9a69eced-85c0-4013-98bf-0c1090de5121 | Pole | Non-HFTD | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000965 | 62d22d83-e2c3-4cf6-bf1a-714d8711b0e8 | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000966 | b0ceec1e-d446-42bc-96f1-b6eadaf6378e | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000967 | 68dbe3cf-51a5-4a8b-a69b-1470441af42f | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000968 | 1d92fff8-9a0e-4add-a7b8-4a3d8cbef31c | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000969 | 02ab1997-8c82-4fb2-b9a9-5a60b1cacb34 | Pole | Non-HFTD | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000970 | 2f06ca57-5ba2-437e-a1a7-843137e805ca | Pole | Non-HFTD | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000971 | e4defeb2-fd3c-462d-be4f-e1e992aa0946 | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000972 | 957def5e-9283-4ab8-92eb-474b7d9ae653 | Pole | HFTD Tier 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000973 | 975dd9b4-3e59-45f3-896e-f2caee795652 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000974 | ad1b880b-50eb-4073-8e89-34c2f78a37c6 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2021-07-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130000975 | 61726dab-05cf-4d18-a83c-63985a3a274f | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000976 | e2a9d5d3-bbcc-4546-851d-9bc70f285421 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000977 | bad09e72-aaf4-45ef-bea1-5c1458b3e263 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000978 | f668d65b-a29d-400b-b075-24f26c06c982 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000979 | c63a44b0-0588-4c9b-adaf-b97da5b8f899 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000980 | 8a9cb10a-a529-483f-bb27-5ba21e1b394e | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000981 | c931e7b2-c5c8-4423-9a35-3da57752328c | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000982 | 8e8b354f-a8c1-4f66-be8d-84a0f54eacec | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000983 | fc7b7975-62c7-4fe9-b9ff-dd6296f2f82a | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000984 | a383d047-e090-4873-99a5-63f9e264dbfd | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000985 | 85e50f89-6285-492b-aa29-10b3640a6c70 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000986 | 1be2113f-541a-4e01-ac94-5a027d03f037 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000987 | 076acbaa-b9cb-4d2a-9226-fee4160a29a3 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000988 | 0f9bce5d-8ce8-4055-8a8d-6d20c3d800fb | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000989 | cef367a7-b2c9-4ad5-8f80-121802ecda91 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000990 | b0fb093e-b5aa-4bcf-b75a-1856e6b6ff28 | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000991 | ab7e51a4-7b28-4a86-9bcc-c2907a0371fc | Pole | HFTD Tier 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000992 | 35e8f7a6-252b-4da9-8882-c6b0a97da0b8 | Pole | Non-HFTD | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000993 | afdf6967-245c-4d1d-b770-6592348bf19d | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000994 | f32a3838-ac6f-4d72-b52e-0d27cb592ee6 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000995 | 9afb25a7-8e56-4334-911d-d028ee55accf | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000996 | c78c1a41-acd4-4896-b17c-e13250784c85 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000997 | 956c84f9-db01-4958-a608-fe93cb8dfdba | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000998 | c880847e-38b9-4790-9b1d-d71d6c16cc5f | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130000999 | 6f16aa83-0e34-496a-b063-5d5de5da5dd4 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001000 | ea5e7a63-0ef1-4bfd-ba9f-02db6bfc5e19 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001001 | 3a663fab-ccab-43b3-9855-436f204b5456 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001002 | a03bbac5-6bfc-438c-b8c2-31c0c054bed2 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001003 | 443e5d5e-531d-42b0-8d74-f81076661a30 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001004 | 5de3af97-792e-4441-9d67-ed157497ce0f | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001005 | 278b1280-99c0-4d0d-b5a0-20d34567cc9f | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001006 | cf3a3473-814f-4f90-b63e-61d09e46ab87 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001007 | b7be3051-26f3-4e9a-8ccb-2fa19c685529 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001008 | 03db0ec4-4589-4769-b418-ab0ad6033bfd | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001009 | b6ba2138-f206-4422-9413-18969e71f6cc | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001010 | 0951fe77-6d9d-435d-8a92-a65818b547ac | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001011 | 6c51d5cd-e64d-4d3e-a967-e5f3d2209bfb | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001012 | 0b2408bb-c402-4e00-b0e3-1e87406bedc1 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001013 | a9c25284-649c-44e3-90a6-eaae94b995e4 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001014 | 4418ad78-a931-4a91-81b6-5edf804a7ad7 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001015 | dea1d9ad-92bf-4f30-9cd5-add90bf97b9f | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001016 | 41b6bbbe-86fd-4427-82e1-3ee795c0b829 | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001017 | e369b04e-76dd-42fc-adf6-4973cd112cbf | Pole | HFTD Tier 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001018 | 056e4ce3-5902-4996-a68d-6f7306ec5bd6 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001019 | 6d511096-17b0-4c19-b602-da8243c37e94 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001020 | 5c9af004-5123-43b5-8fd4-e18472a598d3 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001021 | 66bdfca1-8808-4a2c-a7ba-5b2832c5b813 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001022 | 4a3d8b56-c88a-40fd-a4fb-0d1fc8fef922 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | 2021-11-19 | 2026-11-18 |  | Missing pole # |  |  |  | Liberty | 2025 | 1
1130001023 | 5b2459c9-0c84-490f-98be-a72b3270cd73 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001024 | 2ecd2313-5ce0-4fb1-8d43-7a55265fb8f4 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001025 | 4f789622-6ee9-4c56-b18f-207894de2d0c | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001026 | 57afcd7d-acd1-4dbd-b108-a8362e2028b2 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001027 | 3f56cc60-3519-486a-80ea-feda0f55f465 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001028 | 64f88342-f190-42eb-9149-603605a5a436 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001029 | f9df9a55-39c9-4d6c-bd88-503f1d4b58c2 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001030 | 859f4d1c-a87f-4bee-be47-aa2788edf1a8 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001031 | d59c5e89-d456-4dbf-856f-95f32b046148 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001032 | 99cb0f3b-95e7-4fa7-a3ef-f7c9eb39d343 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001033 | aba16b00-80bd-4bf6-92de-81f429fd6ca3 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001034 | 21913b3f-17c6-4042-b66d-43882c9c7356 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001035 | f1d7c57e-9957-423e-bee7-de69da3877bd | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001036 | 25c8ab34-c4d1-4906-a0bc-7c28476aa6c8 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001037 | 003a1b8e-3dd1-4fd5-b7e1-9d1aad092aca | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001038 | 38da69a1-062c-406d-92d1-a4bac2960717 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001039 | 6bcc5a1d-2d2d-4637-b413-681f433cd6b2 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001040 | 591c2e28-1e91-49c3-b8bc-b46ccecb7668 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001041 | 3a12d4cf-64f5-4eb4-8288-b822bc786964 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001042 | a6fe9675-0109-4adc-b758-352813f7f606 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001043 | 9011ec9a-91ef-45cb-9b94-350e82bee796 | Pole | HFTD Tier 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001044 | 0b04a3e1-67d8-4e0c-a93e-fc5f43765948 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001045 | 6ba35320-b539-45dd-8812-51f43f0c4703 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001046 | 18c3fff6-a0bd-4099-9727-456d63de6e14 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001047 | 482d19a2-4a63-4692-b1ea-b97df1d84a20 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001048 | 3a9dc097-e4f2-4859-9c9a-8814593ccb8a | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001049 | cf8753c5-d61c-4d35-a7f8-ff6b4ece8324 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001050 | 77bff4ba-7e52-4065-8efe-3139cd48cb3e | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001051 | c06d3336-ea87-4d00-b924-c66bdc5c197e | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001052 | 4ca456d0-8d09-4503-abcf-671eee9c3bfc | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001053 | 8b402724-3a2e-4d75-9544-a537ed05743e | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001054 | 4567128c-ff18-472d-89d4-92d0d7721df0 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001055 | 5d4c9934-081a-4483-a6d5-7c2c0b2bae25 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001056 | 2928656e-8f23-47e3-82d7-bc5f867d6533 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001057 | a6cbd979-8acd-40b8-b26d-154669f8795c | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001058 | 55a2bbd2-728d-4e0c-8dc0-1de2f7ff7e6c | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001059 | d3d24e91-b9a0-4161-b809-bb708c53b175 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001060 | 5e1d043f-b4ad-427b-beff-aa7026b36ff7 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001061 | d0bb3155-c65b-4a5a-a2e3-62b8af6e2f9e | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001062 | 168eceb0-93c6-45dc-b560-0396c5ff2b6f | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001063 | ec8f1c88-ca51-4c18-b26b-b985a8ea9e09 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001064 | a9f50b8c-543b-4c11-85bb-f384c1f33024 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001065 | 1f114070-f894-42c6-8b01-a5d4632aaccb | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001066 | fc87c65f-3146-4f17-beaa-5f90a8cffd09 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001067 | 0334c31c-299a-4b5f-b805-f2326f4f7220 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001068 | 61c93b86-24f7-46ea-be52-b2a36942afef | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001069 | 80207ad2-8e9a-4226-8076-c0529428f921 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001070 | b7eac2fd-45fd-4e75-9b14-086353456a7b | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001071 | efe1b942-82e5-408f-bfb3-a4852dbe45e3 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001072 | 4d3fe422-2c5f-47c1-99db-8aa5c1f0d789 | Pole | HFTD Tier 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001073 | b71347e2-5250-4981-bbcb-38ae685dc42d | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001074 | db932bb5-8bb9-4d90-80b3-855174819c6a | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001075 | 93609343-806f-4598-b67f-1eaa9784a017 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001076 | bad4e9da-5b75-43a8-95aa-b2c82050c272 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001077 | f9220b3c-33c9-4657-b286-389740b83b9b | Pole | HFTD Tier 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001078 | 93b03910-1519-4d79-bcd9-a5a6578a8a12 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001079 | 3f538d4a-ec5a-469d-9ef0-fa0a6260a2f9 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001080 | a05a06e1-9d4f-44f8-a4da-d7975a901ec0 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001081 | 0dc9c97f-7a17-4bad-a8e8-5f452181e982 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001082 | 241ba7fa-c720-4591-986c-d3b18dc938f9 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130001083 | 47575fa9-54ad-429b-9d93-235cc2d8c578 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 | 2021-04-05 | 2022-04-05 |  | Unsafe to climb leaning badly |  |  |  | Liberty | 2025 | 1
1130001084 | 0f5a4247-7f07-4c99-9ba4-4813ae448809 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001085 | 62db877e-3f07-4980-b74b-2bcb506a199d | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001086 | 01f717d1-7308-41ee-86a4-940501af91f9 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001087 | ec65114b-27f6-4e39-b7f9-03bb08b23d8f | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001088 | 926a72c5-58d0-4523-938a-7eb5f1b78a8d | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001089 | 92b50663-df2b-4ade-83f9-e6e8e754ec97 | Pole | HFTD Tier 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001090 | 70a0627f-ab7c-453f-8fcb-484b435c3452 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001091 | abf4326a-1ccd-4eea-9968-3990dfe656ac | Pole | HFTD Tier 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001092 | b95397ff-1bff-4008-b171-68cb2bd58e68 | Pole | HFTD Tier 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001093 | 96dee2f0-7179-49de-bb4c-d9be812d50f3 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001094 | 1c3e7cff-0c2a-47b4-8f03-7556f7ca60bb | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001095 | 24783cfb-5044-4bff-9a6b-281582e9c1e4 | Pole | HFTD Tier 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001096 | f833f559-06cd-4272-821e-21572ce4406e | Pole | HFTD Tier 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001097 | 12b002c6-86c3-46e5-ae29-fb22f34d2f94 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001098 | 4815b3e9-76d4-40cd-b715-ab9e63a62be4 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001099 | 344583d1-f707-4ff7-b50c-db6c291a323e | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001100 | d752e5ab-64bf-4cd9-8e3a-fd4624510d79 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | 2022-03-08 | 2027-03-07 |  | Pole in good condition just natural cracks doesnGÃ‡Ã–t need replaced |  |  |  | Liberty | 2025 | 1
1130001101 | 6f8b5209-cdcb-4711-8a9e-7d62f74c6144 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001102 | 6f2802bb-c03f-460c-8737-2d1e1d2e70f5 | Pole | HFTD Tier 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001103 | e7c16dd1-9c91-4812-972f-7c1bcb5708e5 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001104 | 8e116f2c-86dc-495b-b264-eb6b074fd4c0 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001105 | 9c401bfb-2322-4c76-833a-fa11e6204837 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001106 | 84c1ff77-3191-471a-a3a8-57f29fd2a95f | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001107 | e7ef003c-d2f5-4286-b943-78fb99c2f935 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001108 | 87aa3d4c-0fb2-4fba-9072-6727f95cc351 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001109 | 11908b5f-0fde-4dba-bfd3-92ed8e4a3545 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001110 | 6a2e5370-0f7a-4fe7-9e57-b33c403d3ef3 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001111 | f6e09d6b-a53a-4261-a4a3-d46456c8e254 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001112 | bc093c8c-ecf9-4a3a-9bf3-b45cd6bea5c5 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001113 | 60bcc842-a224-43e2-9dd6-e1ce849175b7 | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001114 | 6bc63adf-03d4-4b31-a0a9-bb5f638750bc | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001115 | 55f7fcbc-abba-4161-878b-35b0ebefbbdf | Pole | HFTD Tier 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001116 | fb2ccd4c-2017-44d2-87e7-ae25026ec653 | Pole | HFTD Tier 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001117 | c451203f-0202-4240-af51-175eba5a674b | Pole | HFTD Tier 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 | 2022-03-07 | 2027-03-06 |  | Still needs changed |  |  |  | Liberty | 2025 | 1
1130001118 | ac043725-2f27-47fa-99d9-f1ca294dfdf1 | Pole | HFTD Tier 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001119 | b21923de-223f-49b6-8122-51a19ce0791f | Pole | HFTD Tier 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001120 | 8509fa78-d222-4e74-aa72-1846f285b24d | Pole | HFTD Tier 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001121 | 19268f5c-dfbf-437c-b14d-e8ca4d8d5a2b | Pole | HFTD Tier 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001122 | 2804356c-9fe4-4a49-bc1f-17583af14fef | Pole | HFTD Tier 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 | 2022-06-25 | 2027-06-24 |  | Pole top rotten needs to be replaced |  |  |  | Liberty | 2025 | 1
1130001123 | c5dd986e-495d-48f7-be1c-a78e0835a290 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001124 | 17ed0436-cc43-45c9-bc37-3459a1b590b4 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001125 | b2f48594-f25a-46be-b4d9-2d3e50b21e20 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001126 | 28ddd9e1-2095-4504-a177-83922d788c04 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001127 | 5ad2e8a0-37a4-49aa-aecc-3e80de2e686f | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001128 | 85b474a4-0499-48ba-ab38-ffcfd2a4dfe2 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001129 | fa420072-be74-4196-9c4b-2558018eb189 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001130 | d0986280-a573-44b3-a36f-e142da9b98a6 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001131 | e6d06425-ead1-475f-bf9e-f3d3c7e5c790 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001132 | cc3eaf5b-8fe8-402d-876e-746bf55e7f85 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001133 | 73a73861-daa7-4c3f-a14c-58fbfb56a8b4 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001134 | 06ae4613-be32-4a1e-b034-6e1b01532978 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001135 | 9e52205a-a613-47de-a1e7-5457af2c7402 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001136 | 196bc163-a8b6-4590-b677-4f85b86ff3a6 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001137 | 290bf067-f873-4001-aa45-bc06dee2ade8 | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001138 | 7931707b-99c7-4120-8ed0-e097149de49d | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001139 | dbc765fd-5adf-420e-b00d-1544dbfcc9e2 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001140 | d0aecece-4e54-491c-a62a-125922771b26 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001141 | f8648ac4-9c88-441c-8e95-0dc27c7723d6 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001142 | 9cb15299-16b9-4f1b-90bf-330239be398b | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001143 | d2bc092e-634e-4ca0-be39-d42640e3999c | Pole | HFTD Tier 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001144 | 9564ef0a-02a7-4c72-9c69-ed3d50f1ac4b | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001145 | 30b87931-03c0-4850-b683-2f30d7609a4f | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001146 | d6528172-7ee0-4858-971b-2e0d6f19aaf2 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001147 | 2a28e0ca-8af6-4972-a0e6-028beafc7f84 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001148 | 611090df-9c8a-41d2-ae6f-82029f640a35 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001149 | 626ebcdd-4704-4010-a8f2-076f04d2b05a | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001150 | ff6992f4-747b-44c9-af52-294742064d1c | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001151 | 06e02a1a-8240-44e0-a277-b80eac4c6ff4 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001152 | 85db31c4-72df-4cf5-ad74-8cb2c82e946b | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001153 | 4305418b-d31a-4981-875c-5c025b4e9657 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001154 | e3976782-8580-4c31-9870-32e8c144e65b | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001155 | 816cb613-0007-4008-b5cf-dbd15e40c22c | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001156 | 7229fb24-2a3b-4ec6-a7ae-292bb838bea2 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001157 | 4b217c92-9fd5-4cf8-b6c7-3a1606ff6dd1 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001158 | c4551ab1-5a6f-4b02-9abf-7e1a8258ca49 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001159 | efdede95-9920-4017-b8bb-5a86b3615374 | Pole | HFTD Tier 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001160 | 6ed0ac91-9311-4139-9280-68f3823b8899 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | 2022-03-25 | 2027-03-24 |  | Base of pole sounds hollow |  |  |  | Liberty | 2025 | 1
1130001161 | fbc61eb1-b8c0-41c0-a335-9fbd4d1b5658 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001162 | a4c7d7a8-396c-4809-93e8-77154a7a0f9d | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001163 | 694ccc4e-d5b4-4526-9b6a-2ea31f8cf2b2 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001164 | a349e40b-0ddc-49ac-9e78-72a187d965bb | Pole | Non-HFTD | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001165 | 9409c75d-7c30-49b3-8146-fad952b09d54 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001166 | b6d853d6-f71e-430c-b623-547e88375d43 | Pole | Non-HFTD | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001167 | dc0837f1-e8bc-4868-aa00-9d32837d377c | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001168 | c21f4584-7d63-4012-a386-39d322e656ae | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001169 | 9cd705f6-8d6d-48f8-ab56-7a7bde2acd07 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001170 | ba08c030-cefb-4d9b-bfbe-5a994ecf831e | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001171 | 92d9ce94-74b2-4d6c-829e-41e7e46e7d08 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001172 | bda08f9b-eeb1-4fd5-88a8-3a0bd64601f9 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001173 | 72f98bc5-e352-4f42-9d9d-edc4089c6c16 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001174 | f7dc410d-8814-4910-bc35-62597dfda333 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001175 | 85c68410-ff3a-440c-bbcd-b64ef788ce01 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001176 | f68f4919-e060-40fa-80b9-832faaaaf89b | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001177 | e7cac274-98c8-44c9-b6bb-9feb6ff071ee | Pole | HFTD Tier 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001178 | f4aa5d71-2f63-4e72-b1d3-933e25c3c387 | Pole | Non-HFTD | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001179 | 8e34fb4f-63b5-4512-be3b-bfc452499ee4 | Pole | HFTD Tier 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001180 | 52abae4d-633f-4648-80e4-f87a66fdfcde | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001181 | 275c3a42-3c2e-4a82-83df-8f8cc7b3f614 | Pole | HFTD Tier 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001182 | 6ff3febb-d5f9-4fea-af9d-121db7f0cd8f | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001183 | 3253b362-4bba-4929-beb9-1c2410e24140 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001184 | ced979d4-fa4d-4d59-96bc-57639d2353f8 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001185 | 38358e00-bd4e-4880-8a0d-c4b02e134be4 | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001186 | da7599b7-749c-4b43-8474-2c4e8a0c3bad | Pole | HFTD Tier 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 | 2022-03-10 | 2027-03-09 |  | Pole has cracks but not bad enough to fail the pole. DoesnGÃ‡Ã–t need to be replaced |  |  |  | Liberty | 2025 | 1
1130001187 | 2e17ac99-11ae-45b8-a9f1-273d58ef5eb9 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | 2022-03-24 | 2027-03-23 |  | Base of pole missing big chunks has been hit by plow. Pole top rotten. Pole needs replaced |  |  |  | Liberty | 2025 | 1
1130001188 | cac63fa1-8a82-491d-92f8-e1330f14a5f9 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001189 | 132456e1-0066-4fe2-b241-25a488e5a680 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | 2021-03-15 | 2026-03-14 | [5 empty] | Liberty | 2025 | 1
1130001190 | 1d9584ef-ebf1-4864-b4f3-5789b70bf57a | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001191 | 84d37068-9341-44d8-964b-07ad838c664b | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001192 | 1963cb4c-b18a-4ebd-b74d-0182939b6df9 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001193 | 8004e28c-2a38-460b-8e21-887038ef0251 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001194 | 11120c99-a2ad-475d-8dbe-b54e7075998c | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001195 | 73b3a429-219d-4dd1-bf1d-10fce518c971 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001196 | 1a799a6a-5541-4ab2-82b8-3e5ed80819eb | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001197 | e00c735c-a286-43a1-a31a-00fb36379f4e | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001198 | 598c74c6-8ea9-4d3a-a02f-b83d41f8dc50 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001199 | c042e979-570b-4978-b783-689160cf81cb | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001200 | 0de55f19-e2f8-44be-9f62-df9912c0d1d7 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001201 | c678b42d-01f6-468f-b181-ced58d55b8ea | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001202 | 26e77652-6876-4728-a567-0a7925d3e879 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2021-07-22 | Level 2 | 2021-03-11 | 2022-03-11 |  | Pole is rotted and cracked. Pole carries mainline for 3100 |  |  |  | Liberty | 2025 | 1
1130001203 | 9d2cf61f-5a50-41c4-98b6-e174e1d019d6 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001204 | 24b987f4-5597-40e5-af46-782b541fa24b | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001205 | 9f1eafbe-ed7b-4906-acc1-7b1076608be3 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001206 | 61fad609-a547-4a6c-a6ad-bc8ce0eae09e | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001207 | 7914e5df-8243-4f12-874d-6f2b9c738878 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001208 | 66646f9d-524b-424c-a5f8-4cb771e41843 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001209 | f77c1508-8f47-4721-9e1b-92e915f963cf | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001210 | 3d7ba87d-8b13-4e08-bbcf-24c034797c1c | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001211 | d53a06b9-9c2d-4e7c-a637-ec8a8f9a59a9 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001212 | da133657-de75-4ac4-9604-1690dbe4c606 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001213 | d85f85ff-5cbe-43a2-9ec1-20846a6e0d00 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001214 | a08fb303-85d7-49de-8aec-e0829ad05dd3 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001215 | b7942559-3236-4f98-9a47-f6db44a637d7 | Pole | HFTD Tier 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001216 | 00ce0865-0dd5-4d91-aa90-01561d97be37 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001217 | d398e978-0e99-487c-9605-e8fbd109843b | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001218 | 54cebd87-2719-4443-a224-8b692043b06f | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001219 | 92c622fe-9ed7-4249-9005-3899c4084d2e | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001220 | 5972564a-69b3-47ab-8170-913e61e0276c | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | 2021-03-15 | 2026-03-14 | [5 empty] | Liberty | 2025 | 1
1130001221 | 863aa4f2-b747-4f64-ae9b-8879f0fabd8b | Pole | Non-HFTD | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001222 | 4d7435e7-f3b7-439e-bca6-5981e48ce258 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001223 | 354d9ceb-7af8-425e-881d-9e6dab935a0f | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001224 | 2c0100ac-11c8-437d-bdf9-717f38ec384a | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001225 | e3fd1a61-8c49-4ba8-9074-d018b8c85d2c | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001226 | 363e3f99-74c0-4428-b074-bdba35b4b9b9 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001227 | d7ffe809-1b0a-46e2-ad0d-6ab7239e3f48 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001228 | 1ad2d8df-a69e-473a-935e-3aaea16136ae | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001229 | 7acfc8db-4e08-45de-986e-ac95fde0dc49 | Pole | Non-HFTD | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001230 | 0d8ee1c4-f016-48f5-be8e-32869cd24322 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001231 | 7040eaef-d496-4f0b-8448-a8adad58fa11 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001232 | 05a3f811-7a19-4417-a272-2f63df0e7920 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001233 | 885704c2-940f-4d6c-834d-76a9dad1fc16 | Pole | Non-HFTD | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001234 | 3021d73c-a8be-44f2-b25a-46b72896598e | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001235 | 9c8222f1-a13b-4444-9c30-e8e4d6adc330 | Pole | Non-HFTD | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001236 | 8f09317d-dd5e-4588-a0db-2f9f2a0fef78 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | 2021-03-15 | 2026-03-14 | [5 empty] | Liberty | 2025 | 1
1130001237 | 1b06439d-9ad4-4df0-a7ba-1fc62015f25f | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001238 | e0776c6d-73f9-46e2-8f4b-28cf2d1d77a6 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001239 | 47fafa8c-cb3d-4110-9eb8-d8ecc0b3cf26 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001240 | f4719c35-e1e5-40f0-ae0d-44e4d223b884 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001241 | 37198e6e-e7ec-4d4d-af04-1ab1359c4c2c | Pole | Non-HFTD | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001242 | 9b6a594c-0c09-43cb-b4e3-b62302ba649e | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001243 | 25d9e6ee-5ea9-48ce-9fc5-e447f997294b | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001244 | c92ae763-7071-404f-9f90-fc83c0fd6867 | Pole | HFTD Tier 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 | 2021-03-10 | 2026-03-09 |  | Pole old and cracked, however no pole change needed at this time. |  |  |  | Liberty | 2025 | 1
1130001245 | 1d9c3aeb-79e0-4723-afcd-85eed64ca037 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001246 | 708a52bb-062e-4997-98ef-022033b3c3bb | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001247 | 7661cf2e-3116-4f35-976e-9a6cea7a067b | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | 2022-07-12 | 2027-07-11 |  | Needs pole replaced |  |  |  | Liberty | 2025 | 1
1130001248 | 0b47ebd7-c425-421d-86b4-5d53573a560f | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001249 | d545220d-91d9-4cba-81b2-77722478e04f | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001250 | b405f9e1-4769-4bcc-b9a1-0728c496b813 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001251 | e677af6b-a06c-40ee-94c3-7b25e6f97f7f | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001252 | f57b86e8-a119-4adf-9f83-408cde6cfcc2 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001253 | 62241ba0-b7e0-4af8-84bc-f9ce14c3a198 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | 2022-07-12 | 2027-07-11 |  | Need pole replacement |  |  |  | Liberty | 2025 | 1
1130001254 | f86cdc8b-1efb-440b-9f4c-e27753315103 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001255 | e0ba35fe-cb16-42cb-b192-aa5612a1b339 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001256 | aa64dc5b-aeee-4deb-9619-1f354a3e7fb3 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001257 | c0778902-b75b-4846-8def-337b8b43e207 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001258 | 802b8fc1-c6a7-4869-be3f-eadcd1ae393b | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001259 | 3d28c191-d444-4a96-9e89-299617c57217 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001260 | 1ac5ab46-f1b7-4aa0-8f25-f12dec34e942 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001261 | eb6cb0cd-04db-4cfa-afde-6d40409cb012 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001262 | 115994ac-439f-44cb-9ab8-f0de01013b7e | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001263 | 19baf206-5c26-4d6b-bbe5-8a2c704aa694 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001264 | 38687e2a-2c98-48e6-a05b-8ad2ab78fc64 | Pole | HFTD Tier 3 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001265 | aed073ee-3047-4e68-9716-9053c86c2125 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001266 | 6df356bf-63eb-4276-9bd9-0dd80497962b | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001267 | e0f896da-cf58-4b2c-a52e-6720c90a28d1 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001268 | 52e8104a-6e84-4f5b-87a5-fdb12a133772 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001269 | e6f77305-c823-4467-90b6-6c054a208c3c | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001270 | 59909e58-1b08-4e5e-a859-5afc39079d77 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001271 | 3d1aaf44-3d1a-4792-a657-a853978901a2 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001272 | a61eea3e-4d56-494b-b7ce-f440da7f71a4 | Pole | HFTD Tier 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001273 | a0ff8995-3177-47a1-8e4a-a49e3eb61fa0 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001274 | 31463294-66e3-4dfc-ad24-6c43d7ac1a8b | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001275 | a4ddd710-4d7e-460e-afd7-ba537d5f0c12 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001276 | cf986275-b8c9-4115-a8ba-1246522517b1 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001277 | a58ffd25-d7a5-473c-9c53-133b954cd1b9 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001278 | 8ac96b96-71e9-47bf-952d-0212e8762f58 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001279 | 2fce35c2-08fd-4336-97f7-70d8457934b3 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001280 | 8a06853d-dcc7-4258-917d-37d0cccd6351 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001281 | bc0d92df-f8e9-4213-a4b8-651c5f98d9bd | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001282 | bfb2b51f-0065-480f-b240-6d6d417138ef | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001283 | 40d16bb1-c5fd-4485-80db-25436f30aeaf | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001284 | 76e58a45-cb14-4453-92fd-dffae4d9172f | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001285 | a2d42460-8559-47cc-b617-62c7bfb82140 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001286 | b3708441-83ea-4bdf-b5bd-350e20511b75 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001287 | 653b50fa-bec5-4939-885d-46121f5cdcd9 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001288 | 9e72f818-3d7c-4d12-b55b-1ad6f5f80ba3 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001289 | faa804ab-0c23-4062-bbc9-394aa6f74b7d | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001290 | 24498ce0-e1fc-4109-808b-1d4071da1e88 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001291 | 5be44354-cfce-4926-af84-11da50b211fa | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001292 | 2414fa95-46c4-4c84-a207-61d4018eb31d | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001293 | 894bcc58-a829-418f-acd8-2ab8d55438f4 | Pole | HFTD Tier 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001294 | 410758f3-b72c-439b-af9e-fb1771285d7f | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001295 | ea2ee312-b599-48aa-a510-2375b951488a | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001296 | 6052ce87-bd3f-4ead-9833-c40e5fcbd947 | Pole | HFTD Tier 3 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001297 | c984bb3d-c177-4894-8d44-24d6feab679a | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001298 | 8534da5d-a8dc-4b42-8119-d0bd06e2f0e9 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001299 | caca63a5-c510-4cef-9de8-ddfdc645f616 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001300 | 8dc0c9db-6268-4b04-9b72-8c795e33b2d7 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001301 | 81180f46-e739-4a22-8676-936e05f70a26 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001302 | 802a7fd7-ed36-446c-83ed-e631c056bce6 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001303 | ca8196b6-beb6-4c75-82ba-61cc33c78fdb | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001304 | d6f48278-49b5-4c0d-9acd-d7d9bb6413c3 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001305 | f97e627e-7e39-4f41-98c0-61ba9b377a09 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001306 | 5626322e-0487-4f57-9373-d0ad1ad1c27d | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001307 | 7221de15-46e0-4765-b4ba-4f00db901a85 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001308 | e4a6e208-a721-4c91-af40-5065b5850b8b | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130001309 | 240f5504-42f5-45bb-85e1-f8371f776cc0 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001310 | e07056a8-fe97-4a0c-aa40-5667a7f90580 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001311 | 0aafad34-42ac-476e-ac8c-54c862e16cbb | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001312 | ce51b1b2-4597-4f79-a22f-87a947b51394 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001313 | 04fb1bc2-11a2-4207-8216-58d6856f9f21 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001314 | e3f47c04-c64c-47fe-aac7-7d357fe1a0e0 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001315 | bc9ed3f5-d2a1-416d-9e0a-1c7738dd7c37 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001316 | c1708261-48fa-4aca-b30b-a327cc7ae9c5 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130001317 | bac3de06-73bc-4427-bcb3-f9a181b0042c | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001318 | 9ad72806-0e0a-4d42-8d2a-0bad5c92f8ba | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001319 | c5eade21-f3b4-41d7-9e41-90b2f6e046d2 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001320 | b9516bdd-c9e5-4ec2-9ea7-ca8c8b7cc0bf | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001321 | 4a5579b2-7175-4948-9702-016a4d552df3 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001322 | c5bdc97f-e027-4039-8ec8-d3421ea340e3 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001323 | 5040948d-cecf-4677-a2de-3f9eaab147b9 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001324 | d85e5374-c715-4a59-8e9a-21ece63cf463 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001325 | 52a7be7e-b1fb-42b4-8801-a7f34327bde7 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001326 | 859602a5-0c5b-4ba9-9856-0375b091dbb4 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001327 | a9bf8b0b-9cef-44d2-b61f-b2ac60b9320b | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001328 | 24ede8d3-94c6-4693-9295-63130864f5a5 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001329 | a0c77977-a560-4a76-a444-7c7316b0995b | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001330 | 90449a01-0b54-412d-a266-58b3fb1c403a | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001331 | 536eeab0-bf6a-443b-ac5a-22f2b888f0f7 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001332 | e81cd987-ec11-40d2-acf4-67599cf5c5b9 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001333 | d1de505c-6b60-4c06-a3e8-5ec1da9cb29b | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001334 | bbb71932-fefe-47b1-83d0-5b92e63c3c98 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001335 | 377ea0e0-3b5a-49c2-bc35-e62fc260b8f9 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001336 | 4498c0e0-4771-4f08-b24c-c2bf5b087968 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001337 | 26cc9f27-6d88-4c56-84a3-79d74c0f16ea | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001338 | d0f14781-16ae-4395-acb6-bdc59bc37df6 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001339 | a63ebe2d-d7a5-42cf-9f66-e6d45152d6e1 | Pole | HFTD Tier 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001340 | 48ff97ee-f096-40e2-80c6-79ad6e0f1010 | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001341 | e0e41d57-2316-4497-be09-37f8403ddfd4 | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001342 | c26ed660-6679-4137-85dd-d702ec2bc333 | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001343 | aacebaa4-e2c7-4490-b0d2-6ad7bba36c17 | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001344 | e0aea6cb-3892-41a2-a92c-c10ae6d50647 | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001345 | ae5168cc-9f3e-4869-9dc2-a275595d773c | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001346 | 5cbc8dfb-85d1-4533-bad3-75ba5e67bd63 | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001347 | cf3366d4-2f94-4442-8694-a54ed5dbd9b1 | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001348 | 88bac969-6de0-4066-84fa-f923d58dd592 | Pole | HFTD Tier 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001349 | e433fabb-6d6e-4786-85be-7151856ba7fa | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001350 | 8a064dec-25f2-40c4-bb8a-f4d4250bb05a | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001351 | fdb40fdd-130a-4d12-8cac-410e008a66d2 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001352 | 7c69f66a-76c3-44f1-8297-8179bf540365 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001353 | c876d12c-2b23-46b0-884c-a1de489372c4 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001354 | 74285a22-5e06-46e1-a1c1-63eb5b833fc0 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001355 | cc63cf0b-6844-4d5e-b954-53d1f8ef0e80 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001356 | 7007ce8e-ee20-4f47-baa1-9e7661759f97 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001357 | eb6df2a8-0e23-4afa-8d55-a632337336c0 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001358 | 9ee2413c-d189-4b77-8edf-7431864abfa5 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001359 | edce0504-399c-4c3b-a2cb-8ed6ab0ba374 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001360 | 8dfc44b1-bf2e-4274-8197-6af57753517b | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001361 | e8d4af19-f666-4eff-a174-877bac0e1fa7 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001362 | d0bb76fd-5dca-481c-8b9e-8678aeaeaa8d | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001363 | c0abcb83-c54c-4502-ae34-f8a6b4272d59 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001364 | 248f7ed7-2e31-466d-9fc7-0b5c8af7eae9 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001365 | 6d58c532-f052-416a-951e-232b73d5ea98 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001366 | 1f916061-aaf9-4807-abe7-7d6191f0de6c | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001367 | 49b1aab9-da8c-4e05-a481-43e6c6b751ba | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001368 | 193e3815-f98e-4087-ab8c-a98e2ec355ff | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001369 | 4a9f5b49-79d2-4fbc-8854-78931865ba37 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001370 | 1b308029-a7a1-48cd-962d-4c49080299c3 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001371 | 5b37d8a4-3fd3-401b-8a92-ee6324dc52c4 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001372 | 3495b74b-f180-441f-8bc1-0e87be8ef2e4 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001373 | a631df52-39fc-4fea-8d46-4cf22257a836 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001374 | 3111d693-dfda-4ec7-9f2d-e2a45e58f8ee | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001375 | f22dd979-5340-48fd-abca-7d9ba7801da3 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001376 | 693709ed-c576-4234-af7c-41068ab22b0d | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001377 | 0ab79c47-1aee-490d-9cfa-74ce0f6d2067 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001378 | fe276f13-e176-4342-a789-6f96623eb761 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001379 | dfc9c00f-4892-46db-a67b-6729c6027b55 | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001380 | e4cbb4b7-6344-44d1-9040-8190f557bddc | Pole | HFTD Tier 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001381 | 0b82095c-23db-4106-a52b-1aa08b274c02 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001382 | dbe3d212-618f-48d1-b1c0-40858e895c62 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001383 | 06b847b3-fec7-403a-aef5-743294ba574f | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001384 | e84d9cfe-88b5-4eaa-8b9b-25ccca25c024 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001385 | 4190bffe-e431-4f1a-93e0-295ae2cdeff5 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001386 | eb960ef1-6022-44c4-ac45-76ee623e3e26 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001387 | b41fba4f-3a53-41bc-ab37-26ab8e59a45a | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001388 | e9f00fcb-48a4-4941-86ee-f9967f4b118d | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001389 | d53bbb7b-4ef8-4252-a579-5e39eef82efe | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001390 | 8a95f0dc-3de1-4647-a7be-e65e6605ffe9 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001391 | 8d8d8458-3a22-45b1-ae86-bbc984a36f85 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001392 | c703fc86-af30-48f2-a543-02218fd1832e | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001393 | 848051fa-fb95-415f-a8df-1d4f439fdf51 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001394 | adea6fd4-30e3-4863-ad07-8a0e3b1c559d | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001395 | 5fbd73d2-389e-49dd-b3de-9d8ead41b493 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001396 | ab225ffb-46ce-4cd2-b5da-7efe58fbbb8c | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001397 | 621f490a-019b-4906-8a66-c9c8709137df | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001398 | 8f07b11d-0467-4b2b-8b88-bd2251c54a23 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001399 | 67506e5e-7bd8-48ae-9efd-84cdd7f284d8 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001400 | 98a3f311-9d56-4693-8e97-bcd26455e683 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001401 | 467e2744-01dc-45b1-8cc4-09a5ed171bee | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001402 | cff6b214-5ccd-4972-9dce-2ed3393d64d8 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001403 | 56b5d1c3-0811-4df6-96f4-ea94411eec24 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001404 | b9b73726-0207-4b26-bc56-4ebdea9c8379 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001405 | 3bd02773-faf8-4a90-b71b-61909c00069f | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001406 | dfd7a173-f86e-4b4e-b5c4-febea764c9bd | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001407 | 2c28b806-2e23-414a-b770-db946a9555ed | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001408 | dc85d9e8-fcc4-4350-a14c-db8f1d853ca3 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001409 | fb45652f-bb6a-4972-a4f3-0fc3aa63669b | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001410 | d99a9ea9-dfb4-4e10-a395-fb86f8ebb618 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001411 | 39ab9892-5a96-47ee-9591-cce751d9ebce | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001412 | 7df02f3d-fc07-4472-b9d0-d330e9b786c6 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001413 | f21d7579-0fe1-4539-885f-fd8e9a067410 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001414 | 23d5be88-bb3b-429f-b665-1038cac42329 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001415 | 23e58721-722f-4dd5-a1e6-a5ba53f2d8a9 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001416 | 4db217ec-acb2-4333-a444-fe91a09a2c29 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001417 | 56c25b00-1b97-4e8b-a119-6b2885c2aa25 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001418 | 23b43a59-3d7f-41db-b121-1a6079b10cca | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001419 | 163fd724-f184-4fa5-ad4c-87c14616ceac | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001420 | 74dfafd9-7fcb-418b-92f8-65c3e4a9cba6 | Pole | HFTD Tier 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001421 | f5adcc77-8cea-4953-9be8-42183961fb0d | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001422 | 7cb9636b-fd28-489e-a13d-ea0273d0ab8e | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001423 | 3252dd4f-fc85-43fd-ac07-54e0bd73cec6 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001424 | 7c13e852-312a-461c-bb1c-43edb052e81c | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001425 | 171cf388-e301-40cd-a45e-645246fa6494 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001426 | 87452c8a-2cb3-4d27-985e-79f8b0281f06 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001427 | 96abef3b-ec1f-47fb-a988-f7c29c394695 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001428 | 97d57daf-34d2-408b-9d7d-b7854ea01e12 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001429 | ef021309-ef28-42e4-a38b-f52b39a3be3d | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001430 | 9e904ef8-ca92-4a6b-aceb-99903fd38385 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001431 | c05c5e37-46f8-4884-a4a1-02e55cf07d01 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001432 | 9e1cc321-18c6-4c0f-a7da-55392c1ab5d9 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001433 | a10efa60-7aaf-4d57-bd5d-3d98a3643c33 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001434 | 1622dcb3-4770-4139-932a-926a8334e95c | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001435 | a32e8679-ade5-4414-b7b0-ea711c924fbf | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001436 | 126fd123-11a6-4211-91a8-e3a25ad0a677 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001437 | a2c570fa-56be-4b0f-8341-14a6346dc187 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001438 | 0f600af8-e21d-4f48-a075-eaf85ac02ec8 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001439 | 56640363-305b-4796-8fe4-b6a3a4edb1e0 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001440 | 224341ad-2cc7-4fe5-9e3b-d64159e5c262 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001441 | 4992da7c-5d6b-406e-a560-46267d3355e9 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001442 | 1a100b9e-1185-41a1-bd2a-bdd3cb22140a | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001443 | 696f6861-cb91-4370-af66-0d7ed5758dd7 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001444 | 1cc64aac-3612-4b75-95dc-1f3a7e674aa3 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001445 | 5a441163-533b-45b0-9f6e-8b68f9d988dc | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001446 | 2c6a54aa-4837-43d0-9123-b98373e88c1e | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001447 | 5d02d0ed-383c-4006-95bc-02c4de96f23c | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001448 | 4ce1d739-0e10-4e61-ac8f-80b2d063391a | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001449 | 3f9ca84c-ed45-4a74-a1c2-30b1d847890f | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001450 | e2f77868-b496-4e70-b56e-3abff794696e | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001451 | 0a3582ac-30be-4318-a20e-b370c5b950b2 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001452 | d4ad8854-dd45-42e2-99b2-4372fd81d10f | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001453 | dc6844a5-dee1-4014-8e5e-f838a2050c65 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001454 | 9a38cb32-db3f-4718-ad8c-14d0301a8464 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001455 | 78d4a2b9-8bad-41af-9a78-08ea968e0b3b | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001456 | 889bff9f-a31d-4850-b111-451f0e2ddf96 | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001457 | 7fd72772-4251-4e41-9ab5-4b8eb355eb4c | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001458 | 9bc6a260-8b08-4388-b606-cf0be95967fe | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001459 | b9459af1-e01c-4ac5-97d4-f9c730bae24c | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001460 | ccd2c51e-0b96-404f-a200-df16ef8e251d | Pole | HFTD Tier 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001461 | 3edb2e98-a5ea-4b36-b962-97e7297549c9 | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001462 | 60d25ec9-0428-4b06-8fda-a2c588cbb12f | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001463 | 3ec305a7-aaae-4075-9af0-f3363bf414be | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001464 | 188852bf-7e31-4b74-a4c4-ab573fc2c8da | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001465 | 5ea04825-81db-43de-b679-1a8403c36582 | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001466 | 4dcd2a82-68dc-4042-814d-a94ea8fdbefa | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001467 | e8f9bdf8-b321-43d3-9de9-d98143e3eed3 | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001468 | 9d28af65-1aae-4c86-b959-1da10c160023 | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001469 | c4fccad2-0f9a-46a5-bf54-406f1f4bf58e | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001470 | 8e4e0149-8380-45bf-8b88-c4e89585699f | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001471 | 4a77bfff-337e-457c-a8d5-db6a23d03727 | Pole | HFTD Tier 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001472 | 9980b6f7-5641-47fe-8c2a-9baf7c4d7f63 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001473 | 488f9a81-77b7-4613-80da-f523e1254c92 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001474 | 940a2b00-fccb-4f4c-8a56-2bc8c598dba0 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001475 | 52ab1469-0867-4595-9493-2eb36542a309 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001476 | 9daaf1e5-89a2-4959-bf88-1dcf9a80ac27 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001477 | 5a597158-95ef-4c9b-8142-400bd172e179 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001478 | 9498c9ab-e901-42e2-9b13-41bd1e0eb7ab | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001479 | 3f92e769-2ca6-4559-9cec-124d6c66410a | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001480 | d05e2b24-da5d-448a-ba90-0babb4cddf0f | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001481 | 1107750b-4798-4e6f-bfe0-10f4c75a568f | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001482 | b1436b1c-8bcf-4a80-a466-9863da5a9aad | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001483 | c80d64e7-80f9-4c8c-97fe-d4a93e6ca127 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001484 | d0bf7dad-6410-408c-adb1-cda2ef9b8bfe | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001485 | c7f4c31a-bf49-42dd-a7eb-d8f3099fcc8b | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001486 | 87068f74-60ad-4336-86a6-860dd8b55f42 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001487 | caf4fd7d-271b-46d1-9397-e04d18e3f5b6 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001488 | 885217dd-8276-4bae-ac68-0ccee650d88b | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001489 | c8542491-e865-43e0-9a4f-67535513bdcb | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001490 | 8bdaf38b-c989-4c03-b4e1-936772e85375 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001491 | cc0bd53b-fa69-46de-ae60-616818616496 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001492 | 8b84ea1c-8793-48bd-9f46-3ce4aaf26963 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001493 | ea4358c6-86c1-436e-954e-e4d293d61fd9 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001494 | 8b81e8ce-de14-4e50-8b91-daee4836eae3 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001495 | e9dba797-a711-46e3-9e8a-6e53b7504b84 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001496 | 7bb558df-bd0a-4d42-ad2d-0eadf733395d | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001497 | 93ef954f-75a8-4751-bc2b-8ee73be93e61 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001498 | 721a006f-09c1-4752-a4e1-493d95098d0c | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001499 | c907274e-1b71-46b4-b27c-fca780cbcbb0 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001500 | 19d04e4a-0d37-47c3-b5fb-11be61ced039 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001501 | 224410c4-a0b1-40cb-bc33-1e20cd2ec6e7 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001502 | 1a5b203e-0bc2-4383-8309-bd1906cdf55f | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001503 | 3d4d78dd-42d1-4d3b-a50b-46859f1376a8 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001504 | 1e6fb41e-5421-4e77-b774-9513d2dfeab2 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001505 | 2cb6e554-25b3-4ec2-948b-5e678c0acf70 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001506 | 2df2ef07-ab06-4722-9193-34e78bf1b7f4 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001507 | d25628c9-a142-46d4-a40f-4dfa083cc8d2 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001508 | 2f266d5f-de7a-407f-b136-73d3655c7278 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001509 | fcbf3fd4-b0cd-4760-b7f9-b2af1c0f0ccd | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001510 | 304c4817-9e28-4f87-9f16-135ade81fdfe | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001511 | fb907482-ebcc-45e9-bdb7-7bb4c7325669 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001512 | 0ffc3f4c-b098-4c17-b57f-1cea71085925 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001513 | f78438a9-eb3d-4086-8839-40c985cbdb99 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001514 | 136f9d67-de17-43ab-ac44-412b12d45e4b | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001515 | f2bede69-3eb9-477e-872a-f8621fd8fad8 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001516 | 15d39de6-8a7c-492e-b609-485393d48f25 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001517 | f1335eb3-1fbd-4245-b8e8-692cb8406e6f | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001518 | 5dfd2579-bc42-435b-b102-9aec8fe0f2c0 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001519 | 5caae9f5-c314-4bad-bebd-5abad13f0a0d | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001520 | 81891eb4-0285-4b00-b3dd-11e17543c1c2 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001521 | 57bf5e4d-f016-4d6b-a6c7-0940cc00c167 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001522 | 85d49349-3372-4df2-81b7-cddd8249a552 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001523 | 67d2c9ff-bd9b-426f-93c4-ff16e405c140 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001524 | ebf595ee-2fc5-44e1-87d2-ab94f7c0ff64 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001525 | 4b8a30f6-302c-4b76-8519-c472c4d7f8d3 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001526 | 1e930df5-fef5-48bc-b718-c7c50f6d4e5b | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001527 | 489df34d-717f-4ac2-a712-1770661dddbf | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001528 | 8304f19b-186a-46f6-bffe-b3a05bafd516 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001529 | 4dfae9a6-30e1-471a-8045-b9a99c196d8d | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001530 | dc133c13-1dd4-4d88-a78b-aa847c1dc480 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001531 | 55501b28-ef41-46c4-bece-bf35aee83548 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001532 | df4fc912-ba3a-4c9e-a1db-761b3e0d19bf | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001533 | a0e042cb-4458-4e5a-888d-46f2868fd6e2 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001534 | dfeafac8-b4fb-45b8-8136-032b2c9e23aa | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001535 | aa8b3c73-cb52-4308-9434-cc1cf2addde7 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001536 | e356b4a7-a764-4a4a-b250-ad8182334898 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001537 | 6b661b0a-36a7-442c-b66d-3181bb9e6580 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001538 | e6a0f759-b684-40ca-9085-19665bd4fc0d | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001539 | bc0f2cc9-1474-4950-ac8b-6e6913b5e679 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001540 | fe634fba-7186-4898-a13b-626e52f7418d | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001541 | baec7f17-1d8d-4600-b986-4b813ce2beaa | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001542 | aa50cf13-be7c-4403-a954-0631041ae19a | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001543 | 0dfe9e62-034e-4e88-8e99-f9eb51cc13d1 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001544 | a2391e1c-451c-4256-9bff-b39d388eb895 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001545 | 4126f051-f83a-495b-b0e8-0badba462f0e | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001546 | db43b801-97eb-41eb-bf09-85908d5d355d | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001547 | 0b6c1320-fd8e-4acc-a649-1460e84bde4f | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001548 | ffbfb881-ae1b-4ba2-9e3b-c7d6cc7d423f | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001549 | 0c2a266b-6b1c-44e1-8939-d6e9d4526f41 | Pole | HFTD Tier 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001550 | eeb1defd-1415-4b79-9af7-ce79922ae44c | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001551 | 0aa31781-2582-4845-962c-8cdd2631662d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001552 | e4c08b8f-339d-4eab-8ec3-9f9833d47261 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001553 | 0c666485-386c-4b59-900d-1efda3b4f1ce | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001554 | ca15506c-e4b0-4ba2-bf8e-4ab83ab4c38b | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001555 | 092f20eb-d98b-4121-b115-56890e9c3a25 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001556 | bfd55422-aa1d-4c08-ae75-a4efd9a7f51d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001557 | 410d9361-8f75-40a8-a42e-46e8861c02bd | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001558 | dfbb6664-0216-49d1-802f-55a86a33ee09 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  |  |  | No longer trees in primary. Moved to level three after re-inspection. |  |  |  | Liberty | 2025 | 1
1130001559 | fa71151c-810d-415f-86d0-54c733efcefc | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001560 | e619b660-f1ea-4678-9fff-5c45931b6a7f | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001561 | 016de47e-ac16-4ae9-974c-85cb069a0068 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001562 | e3f816c8-d3ba-4b80-a92d-a318ec5a8d58 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001563 | bb6494c2-3cd1-4286-a88e-552f7da99374 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001564 | e13cdb5b-f8c6-4f15-8949-1f3f68280fa5 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001565 | c368069e-ab63-42e3-9d2d-acb03d404d1a | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001566 | e22be44a-1efa-4075-abfa-d0a2efa4b2d6 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001567 | 9f62e863-7b9e-40f4-97d6-570ef8aef2a0 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001568 | dec26b87-b825-4210-aea5-ac46932ea715 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001569 | 909d9418-0f50-4293-945d-e0318b0175d9 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001570 | e00d3961-74a0-4de0-b612-b3287720a3eb | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001571 | 55e5a746-db68-460f-95f4-5e49528826fa | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001572 | df8ab364-0589-4645-809a-dcf2aef9d528 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001573 | 4593022f-da59-4d37-a1ba-2c861ea2c86c | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001574 | db5e2e0c-f22d-482a-9ed5-eac4f6e1e987 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001575 | 456d3608-9550-4e96-9efc-3472a392ebd5 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001576 | d8c02533-cde1-4616-bcc4-764edfca56f2 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001577 | 6a2604ac-328b-4e68-8fe4-e3cf9ae985f3 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001578 | 932cc9ac-8528-4217-9936-e44a3bd76fa4 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001579 | 5b3d9ee6-6933-403d-8222-47592c421b9c | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001580 | 7dc95049-cce7-4bab-b1a8-a879afffc607 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001581 | 5f56bb5f-9cd6-4fb1-8a3c-a04c976b34dd | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | 2021-05-24 | 2026-05-23 |  | Climber needs a high voltage assign and guy guard |  |  |  | Liberty | 2025 | 1
1130001582 | 685a536c-c659-47fc-a9a1-413ab21c5d38 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001583 | 5eb88ab9-b27b-425c-917e-f94463d97d77 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001584 | b73c7276-6cb9-4da3-a489-87c3dcce1f37 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001585 | efb05e35-63c0-4d65-a961-5cf07756494f | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001586 | 155a9102-ce41-4525-96bb-4e9e218116d8 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001587 | f18fa482-e68f-4d93-9c77-59365cc3c7bc | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001588 | 12bd148b-ddbc-4f02-bc02-35d66aa798a6 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001589 | f515ffe5-fa3b-44c4-a54e-a214003da4b9 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001590 | 150a290a-fa44-431d-831a-0d45c6536cb9 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001591 | fc20c68f-8a02-4d1c-8816-196bec0ebb3d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001592 | 1130cbaf-ca1f-4143-82fa-dc54f3c73e93 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001593 | ec0e4c9e-7796-4b2f-904e-b8ae1c8560f7 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001594 | 2fc6b427-fc8d-4480-91dd-6e814be52699 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001595 | b3c8123c-8fa1-4a3b-a81a-dc33d7ecb83e | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001596 | 2ded5301-cdcd-4744-9dcb-b1ac19c707f2 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001597 | cf4df3f3-b5b8-465d-8dda-d02feb2c1058 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001598 | 2f5ffcfd-0698-465c-a3bf-2fe14e4ecde7 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001599 | 6a035814-8aac-432d-b0a9-3ae643effc8f | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001600 | 2a208ec8-3785-4200-81cf-7b99c6bd636d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001601 | c3c3981e-fbda-4e9d-9400-801dce639daf | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001602 | 33b09294-571f-4543-81f8-de4eef4a698d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001603 | 88338fbc-b0c9-46b8-9e36-fd0e0105b74d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001604 | 338cbd3a-4c85-405e-8b8f-bf4e678d6d11 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001605 | 6aad7281-c469-44b7-8bf0-c61d80443e2e | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001606 | 37441fdc-6a2b-4f0c-925a-fc14cdd0fe2d | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001607 | 68ede30f-4e51-4571-bfb7-3425113c7667 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001608 | 364233ba-48a9-4630-8bab-77ddb66c71e4 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001609 | ee40f41c-e415-4389-ad21-dd368a8dd9d2 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001610 | 384e7e46-9b7c-428e-a620-258d6f42a838 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001611 | e89d5933-a6c8-4c35-a3a6-c8dae02a3c41 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001612 | 1c1ad66d-52b3-4521-b5d0-1e86a18117d3 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001613 | e7ed035e-3882-4647-9f92-34f5b1b39e10 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001614 | 27db1a60-7eb3-41b3-bc90-36839b815a66 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001615 | ceb57227-dd31-4ad7-9090-151b25e4f856 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001616 | 726137b2-25fa-4d46-8530-4701ba8a5542 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001617 | cf0bdde3-9846-4959-bc29-f3d3957bdb01 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001618 | 71fcd5da-68f3-43ce-a2fa-85b365d8e59f | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001619 | c9acc18f-bd41-4539-b9ef-d3b4e3be4363 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001620 | 70509ffb-06f1-4f99-bc1b-924bd4a2fe25 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001621 | c94e826c-39a1-4559-8070-57d317f0c003 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001622 | 6fe5b755-9c35-4afa-99d3-7390003f0382 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001623 | c6e2e9e6-3af1-4670-b774-95928ffc94b7 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001624 | 39a94e2e-9455-437d-8111-959907cc1919 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001625 | 0e3ea69b-4419-4f6b-8cd0-36be8afde6a9 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001626 | 7a26ca39-760d-4032-a468-1f38ffcdb0bd | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001627 | 3b77ffb5-ce56-453b-bf22-8cba81c67564 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001628 | 79005cb1-9a4d-4559-8664-97238b311bd0 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001629 | 291692dd-fa0a-45b1-ab1d-7817cea70e53 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001630 | 7dd236f7-5255-403e-b2c6-60efeb44f5b6 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001631 | 5909e2c8-2bc2-4b0e-b24d-fe8bbaaa0213 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001632 | 8d733888-c52a-406a-8a05-c3876ea94763 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001633 | 59638746-062d-43d1-b52a-7a41723fe40c | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001634 | 863f4b77-9867-48bf-8863-d416d79d74d2 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | 2021-06-29 | 2026-06-28 |  | Changing to level three conductor that is not taped up is D energized once span to deadens pole |  |  |  | Liberty | 2025 | 1
1130001635 | 5ed22696-98cf-4d9b-91a0-7c4a728af6e9 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001636 | b114f1d0-0e21-4b9c-9155-d245a0563289 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001637 | d18a9d65-36a9-4723-9bbe-2626220b0667 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001638 | d21e9052-05af-4895-912a-4b87437d2abb | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001639 | 9e7c5562-1003-4660-8343-df5753778e7e | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001640 | ab285fb4-6940-4489-ad35-103d1972c094 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001641 | a77ff628-6127-4bd8-9b4d-1b05e7540605 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001642 | 997021d0-b955-4107-a0c3-ad96636ad6f1 | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001643 | 96e53035-709a-4439-9434-a986590e2dfa | Pole | HFTD Tier 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001644 | 59ccace7-f6fb-4def-b050-181734132481 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001645 | 9dbf5f10-0543-4aca-b696-74a03a69a732 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001646 | 2a886aa9-6ebd-4fe0-953c-ec90f93aa0a0 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001647 | 9a48666b-5954-4e17-8e2e-13c0c2af7ecd | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001648 | 460f2025-530b-4c60-b4f4-22343d8eea7c | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001649 | d285b588-71ca-4067-9f56-d9d53cdebf18 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001650 | 0989dc6e-ae07-4eda-8b9a-7947360344b6 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001651 | 8b2830f1-2494-4494-9581-97041f0d8d82 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001652 | 2235dfe3-7c8c-47b5-9bb3-bd5398c06db6 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001653 | 8a927bb1-878b-42bc-b8c5-fbabdb4834e5 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001654 | 00784bfc-aa4e-401d-8cb3-5ea57aa86b66 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001655 | 7bec93b9-3acf-43fe-af3d-4bd326ff1cca | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001656 | 049e3cdb-38a5-461d-8e69-7a855821562f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001657 | 7d381d25-7b50-49ba-921c-dcd194958e55 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001658 | cc10387c-8083-4a11-8741-08174f7ce52e | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001659 | 3bc8d9bc-10f2-4183-acf3-fdbeb7fbaeef | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | 2021-06-23 | 2026-06-22 |  | No immediate threat to reliability of service changing to level 3 |  |  |  | Liberty | 2025 | 1
1130001660 | b1990580-29f9-4f5b-9f4e-aecc429e9a05 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001661 | 287a91da-c557-46ac-975b-684d2d417462 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | 2021-06-23 | 2026-06-22 |  | No issue with service laying on the ground at pole did see service still in tree cut on both sides looks like itGÃ‡Ã–s for temp power when contractor gets panel set moving to level 3 8601 hwy 89 (Amanda lane) |  |  |  | Liberty | 2025 | 1
1130001662 | ea560e12-6bbe-4a21-8697-6ed8c3bd69d6 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001663 | 2257e7dc-45b9-4f4b-917e-fe1db5251496 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001664 | d523fe1f-f25b-4c80-abe0-90ef889f6d17 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001665 | 21814b91-fdf5-42f5-bd64-63d8de4714e5 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001666 | e00e6ee7-915b-4846-bd3d-d3467e3f9a97 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001667 | 1e47fb8a-633b-4db9-abfe-01d127932c0b | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001668 | f1caca33-bc9b-4326-ac62-14e643a2208a | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001669 | 1c49a69d-3c87-437d-99ae-9913f423aa6b | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001670 | 00ec779c-eb12-48d4-804f-c13cb846c68c | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001671 | 177ac5a9-cd72-4674-93be-03e0b26071a2 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001672 | 5fc9948a-a322-402b-8a36-c511e264de74 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001673 | 1e399946-4e29-446a-ada9-87a6f56a4436 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001674 | 5934d853-9693-4572-9eee-2f39c7cba159 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001675 | 1f55b1f0-e131-4dd8-a30f-9e0638fa8636 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001676 | 66e88ea4-2b44-4628-96fd-37f36ace2cf6 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001677 | 1e3cc06f-87cf-48f5-ba76-37fbf86dd601 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001678 | 656cd643-361c-4c01-8138-e727a53db9ff | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | 2021-06-23 | 2026-06-22 |  | No immediate hazard to service or reliability moving to level 3 |  |  |  | Liberty | 2025 | 1
1130001679 | 28e94845-96fb-4387-a992-0d43789dbb43 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001680 | 459f694b-8792-4467-ac68-cf8f98030fd1 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001681 | 28c6732b-7ce4-46c0-ae01-07714309cf4f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001682 | 4a99594b-e709-4232-85ed-f2f830356b6a | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2 | 2021-11-10 | 2022-11-10 |  | Pole needs to be replaced |  |  |  | Liberty | 2025 | 1
1130001683 | 2a9cb56e-db86-4e1d-82fc-a3e544af255f | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001684 | 5303fd3b-93bf-449e-a899-b0cbc43a43d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001685 | 14765d57-5199-4faf-8067-754407c46ec8 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001686 | a8db26bb-c05f-47e0-a589-2bf2a05276c7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001687 | 662a1fa6-a019-4578-86e2-e4d9e82bb285 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001688 | 6b7bc8f4-f818-4114-accc-0ba4383e9104 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | 2021-06-23 | 2026-06-22 |  | No threat to service reliability moving to level III |  |  |  | Liberty | 2025 | 1
1130001689 | 6ab39443-84d3-4b43-9d17-9347d1511f5e | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001690 | bf65479c-d7fc-4dab-be80-f42c588c48eb | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001691 | 7511b759-3986-49b9-8a46-92fc3f4daaf9 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001692 | ba4a9d4c-d19a-46bc-bba9-bbaa89a36618 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001693 | 70ec3213-18de-483f-93b3-f521470d788c | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001694 | 3fbcfa36-5e57-4280-9b0c-b3eceb5e1303 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001695 | 85591d6f-5225-401a-8421-1aa41d5e44e5 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001696 | 0b449792-eb3a-46c6-8f30-d04c1a4275a9 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001697 | b5bec8e3-8013-448c-9cd6-fd0017f81029 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001698 | 0af5cae6-5c55-43b8-bfe7-0e8e127c9cc2 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001699 | d7444693-fb4b-4bb8-8487-2c240599d7b2 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001700 | 0d1aeec7-c8ae-4d0e-890e-e418534f6367 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001701 | d6ae9d52-065b-40fc-aba4-fea0f364199d | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001702 | e4425c75-4c89-4ba2-a83a-726fd5ceb60a | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001703 | e731d4cd-5abd-43fa-9d39-0f3fe21fb5e8 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001704 | ff5a0709-52a6-403f-bfea-580d05329914 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001705 | bd906c22-52c1-4e53-855d-048666ebf3aa | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001706 | c6bda757-da5c-416e-a0d2-5f8b88c234e7 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001707 | 940ce92b-4bd0-4000-808a-814be67cbaf1 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001708 | c8917a6e-7690-4fd9-bf9b-6a5ad105f978 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001709 | 9d7ecb32-74e6-4b45-877d-45f01c9bb3c4 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001710 | 94b0cee8-ecfd-40fa-a49e-c72042900252 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001711 | e98947ef-2596-4287-af6c-fca455145239 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001712 | e8163cfe-dc38-44d4-9150-284e9a83f924 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001713 | d7cfd504-78f0-4148-8f07-a8bfc885fccd | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001714 | 948a7c6d-6da5-423f-b48d-7dd5785c6052 | Pole | HFTD Tier 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001715 | 0798a37c-6e73-43be-a6af-9d527de937ce | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001716 | f21b2d06-6edd-433c-98dd-c78c9d99d776 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001717 | 431d602f-04cd-40aa-9cd6-0a867182e4ed | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001718 | 94a0f837-7a7f-4e5b-a606-433ae1e2d179 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001719 | bf2ed20a-b677-454d-af48-a3a8b4f1ad2c | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001720 | a0c24945-a699-48c2-af2a-07715f737b44 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001721 | b20ef1aa-a86a-455b-b280-8532554c1277 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001722 | bed3caaa-573f-450d-943a-ea560626a283 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001723 | 8c673f87-a295-4fc9-b77d-9201603ef82a | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001724 | b86c43a0-ff8c-4e98-afea-44fd7fe37b3d | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001725 | fdc0f9b1-3315-40be-980b-beafe5bd0791 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001726 | d9dc8d8c-cb3b-4dc7-a651-b46e88169341 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001727 | 306a8452-4d4c-43e2-9429-343854a70dd1 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001728 | 8f591d33-5cb6-4257-825f-d8fae9d60b0c | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | 2021-06-01 | 2026-05-31 |  | Needs hardware tightedned |  |  |  | Liberty | 2025 | 1
1130001729 | 5baf9f7e-b80a-433a-a64d-d24ef462aedd | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001730 | 152f7142-95eb-443d-bf16-4adb53721e55 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001731 | 53c19b41-c407-4d31-ac65-922b982df8c5 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001732 | 2bb14fb0-8ed5-42b7-a13d-0dac281e73b5 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001733 | 1be441be-fd15-424a-b32e-08f638bdfdbd | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001734 | 22b04be1-4ccb-449f-9929-b94d8b5bc871 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001735 | 23702c38-4150-40ce-aff3-5a032fee91cb | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001736 | 3b142276-1b53-4ab6-b782-dcee543537f0 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001737 | 7b1a224c-d871-447b-b280-e65de7e8b020 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001738 | 8fa28f4b-faa9-425a-bb4f-3d10fbc02d78 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001739 | 90bf984b-2b8e-4ca4-98fb-561c49819037 | Pole | HFTD Tier 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001740 | 43990ec4-c3e9-4fee-bbba-626312ca730d | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2021-08-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130001741 | 8f11bc46-f3c2-4be1-9811-d23156f8ef5e | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001742 | 1a1496b2-c0c0-4a27-a30a-8ee41d4092a9 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001743 | 95307ad0-66fa-47d0-8150-7beb6e60c230 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001744 | f34e57ca-c632-4e55-b81e-9175f53c5a45 | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001745 | 96a1e0a9-c7aa-4293-bfe2-348cfbe5850b | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001746 | cae9bbb5-e019-46dc-b780-31c6d71512f7 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001747 | 952397e1-3130-49a7-8084-6dfaeb0da75e | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001748 | e95092dd-5f86-4f4d-9b14-e2faa64316d5 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001749 | 9cc4f567-2d93-4b55-8d49-86cda292dcb4 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001750 | ecbdd67b-529e-44b6-bbfb-e05edbc80dd1 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001751 | a603589d-404a-4163-a1de-9309aabe10e0 | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001752 | 6d2c645d-b53e-4655-bad5-5d56d72b64ef | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001753 | acdde7ec-7dd9-4c89-915f-5a09470831b7 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001754 | a0c744c0-8453-427b-934a-0d27604ea11a | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001755 | af96a897-1d36-4bd5-9434-6a28ba0fbb74 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001756 | 95d5b573-c3eb-44d5-b1dd-50aa9de901de | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | 2021-06-01 | 2026-05-31 |  | Hardware needs tightening |  |  |  | Liberty | 2025 | 1
1130001757 | ae7b9670-b59f-4cfb-9c42-5b0ae48ffede | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001758 | 54d6b2fd-d106-46b8-9913-881257d831fa | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001759 | 78c5593a-2ba5-436b-93ff-b66dda796582 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001760 | 6384113b-954c-4046-8962-86b2f630d0f6 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001761 | 78338716-93a0-4bb6-8fbe-dcfaf66d0376 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001762 | 631b9428-9efd-466b-833e-f73802a748a6 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001763 | 71b3b1c8-2433-43c1-84d3-721ddea6c241 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001764 | 441c15d8-87bb-4617-9b9e-834d29b1a0d9 | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001765 | 83c0920f-a3ea-488d-a74b-4bb14a3444c0 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | 2021-06-01 | 2026-05-31 |  | Tighten hardware HV Sign needs changed out; need new upset bolt. Non GO stirups & bird guard |  |  |  | Liberty | 2025 | 1
1130001766 | 3dfe287f-2078-422a-b56c-8ea1e47efac4 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001767 | 89b76d8a-6f80-4695-98ca-de37aac708e8 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001768 | 0d4077f1-04db-495f-b1ff-97570487daac | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001769 | 7637161e-21ee-44a7-80b6-f7b4d37eed11 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001770 | 62054625-3946-455b-98ee-8afbab0f20d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001771 | 1b6c5f96-1900-4cdd-ac81-f61ac23a20e4 | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001772 | 21aeb734-edba-4b2e-91b5-d718b296cd1b | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001773 | 2b7e82c2-5850-4e5e-8b28-00093f17b058 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001774 | 2cdefd32-ab80-4864-8b80-80dc20b3d859 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001775 | c7347d5b-8e51-455f-a754-0aae2c6da479 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001776 | 7969d91b-d734-4237-8c96-a44b4be48c1e | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001777 | 6a1a7c52-a491-41e1-b2bf-4bd62b7abb37 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001778 | db9e3513-c175-4a57-a482-e5e8f6282133 | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001779 | db98aabd-62dc-4bfe-beb9-e58c9734a5f0 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001780 | ff686600-44d8-454b-bb77-c03308af28e2 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001781 | 987f479b-8039-440a-b286-fcac2b2a7a09 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001782 | e38ade05-f812-4b3b-8351-e27efda55cc4 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001783 | 93b164b3-f9ef-4b13-9734-422b08aef464 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001784 | 949cf6f0-584d-44ab-8202-79dd1f5cfcdf | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001785 | f4cedd95-44a0-4ce2-b023-410875eb848f | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001786 | da86f739-68db-471b-878c-c43d5c67e176 | Pole | HFTD Tier 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001787 | 0033f633-775a-42a1-8d8b-5a5f681d458e | Pole | HFTD Tier 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001788 | 0b8ce194-b19c-4595-b2c8-95e5cc7a7415 | Pole | Non-HFTD | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001789 | b5b7eaa5-a391-49e3-9b2c-d01e9e86f1d0 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001790 | 0b168aec-76d1-48ec-9d86-6777d1afb3a6 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001791 | ce1fdb9c-d8ae-4185-ab97-3a3c61f60f32 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001792 | 09dfe4ef-a759-4b86-9016-2c895c06a713 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001793 | 96b8c7ca-f31a-484d-8570-396c38d818aa | Pole | Non-HFTD | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001794 | 6333adf6-3f33-44ba-bd44-0f5a0a6e1f85 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001795 | bb500cd1-4278-4b62-97f5-fd714f0c1778 | Pole | Non-HFTD | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001796 | 66711678-afd0-4a1e-829d-75dcdc438fa3 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001797 | af21bcd9-e913-49a9-9d60-d91e0175062a | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001798 | 67347856-db2e-4591-b79c-37ce9016f4f8 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001799 | e484adaa-c8d7-43d5-acb9-f93f4adc6695 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2021-08-08 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130001800 | 5df46407-b24d-4bd0-9a6b-52d6364d25b4 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001801 | e5fee9dc-b689-44d6-9157-f130b868ce51 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001802 | 556ef512-1961-49f4-a841-f5032e796ebb | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001803 | 9570cb38-1dc7-4630-815a-840d66c6d2fe | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001804 | 52bea135-6342-49c4-b224-96a154c6fdec | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001805 | de5ac015-6037-4fa5-8802-cf5c951b6b4d | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001806 | 4e768e82-a505-4442-b95d-0c69977ebcee | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001807 | d6b027b0-79c8-4973-907a-080eb0c68013 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001808 | 48c67562-3f9e-42fc-925c-e91777125ac4 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001809 | d94fe4fa-22a2-421b-b8ac-bce559f0ee3e | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001810 | a9873b68-eac2-4780-9b11-3d2a7967842d | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001811 | 8ed209a0-9924-4d32-a293-fd2c452feef2 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001812 | b4208164-897b-4fa0-81a8-16ecd0ff19ab | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001813 | 7f2afca6-7bd3-4b31-9e5b-91991cb25e05 | Pole | Non-HFTD | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001814 | b25d2d8c-4dca-40ac-a79f-7090a5638a54 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001815 | 114f1cc8-b4a5-434c-bcbe-d05606eb152f | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001816 | 6d34b0ea-e4e8-4d78-a276-f3dd283ef829 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001817 | 12451f30-7775-46bf-90e4-e5679e5678cb | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001818 | 6cd0a2e7-a269-4fda-aab6-0c9f54b5bdb0 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001819 | 0f39039f-7552-41e2-9292-8a858bb32cf4 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001820 | bbe6edfa-e325-47e1-843e-fa758a3a32cf | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001821 | 354e0b99-e20d-412f-bead-bee2b7ef7cb0 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001822 | b9ba4abf-b5a5-4766-a983-f6b105826f9f | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001823 | 376d17c0-bcc5-4a4f-a959-401440a0937c | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001824 | b94ed509-ec1f-4dc3-898b-b4b12f1f9dc4 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001825 | 3795a344-c14e-4004-a738-a09aa39db785 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001826 | c0651488-7b56-43f9-bd19-f8c1df98af19 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001827 | 381a9021-335e-4d31-8753-f4b5b3c3c402 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001828 | c160f3e8-6e96-4131-b409-7fcb66cc2237 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001829 | 262790ad-73d1-4107-acda-5f78efff53c9 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001830 | e9228c32-2489-481b-af57-491a11847902 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001831 | 88b05b64-e38e-4f30-9ab5-ea3da6b979bd | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001832 | e8ad5662-8c0f-4209-9a0a-7bf58ce843a4 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001833 | 7f48c2cd-6592-4f00-85ba-093f316fc9dc | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001834 | cc602c02-c923-4901-b516-a3ca9a30498e | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001835 | 71ef0733-318a-4aaf-b2e2-ce5df17c64b7 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001836 | cddb1b7b-d8a0-4f05-82ac-70f66e4095f4 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001837 | 76631a4f-4d31-4b6c-9853-09a5d1af81eb | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001838 | c846bcea-9f1c-4acf-8d31-f9c28e55a50e | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001839 | 79aac699-d5fc-4aff-91b7-77075ead77d1 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001840 | 1bebb68c-d6cc-4638-8dd7-e0af5c46e470 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001841 | d293ce12-3567-4dcf-9817-528cc753b2d9 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001842 | f31620c4-3cc4-450d-bbfd-a5ff3870e74a | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001843 | 9c137735-85a6-4d22-8473-2aaac15d119f | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001844 | f9dba5a7-7aa4-4822-b00a-f896dd24f44e | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001845 | 9557d04e-7e05-4905-8839-90a6778671f2 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001846 | 0d04d559-6add-494f-b154-163ddd155afc | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001847 | 980f09f8-9921-4048-825f-99afcb5d9c7c | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001848 | 0a62a4fc-08a0-4811-aad9-1b0d73fd17c4 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001849 | 9154720c-f78e-4969-a4da-a2d63af6b8c1 | Pole | HFTD Tier 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001850 | 0771a3fd-b22b-488a-bfea-ccb93d9025bc | Pole | Non-HFTD | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001851 | 49c141bd-86fd-4d37-94f5-2ee2479ab9fe | Pole | Non-HFTD | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001852 | 61146b59-2f58-4c33-83ac-a6892b4a75c4 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001853 | 384030ba-2fd3-40ce-8218-262c10ff1bb9 | Pole | HFTD Tier 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001854 | 4615da5e-caff-4528-92a2-3c84b03b294c | Pole | Non-HFTD | Distribution | 2020-08-08 | 2025-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001855 | 8efbfe7e-51f5-4ae3-9891-e1721e725657 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001856 | 40ab11a5-779a-4454-aa04-8b481458511f | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001857 | 9b86b828-25d3-42bc-864c-15a3a1fbaf41 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001858 | 31a10354-8cb5-44db-b3d0-1cc82f2b5971 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001859 | 83f69566-1b33-43b7-b18d-921305b57c0b | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001860 | 5c82b238-5f98-458a-956a-9c3545cdd839 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001861 | 7dd5160d-be73-4133-bd97-b755def7547d | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001862 | 13fdc2a0-0af6-4114-bb88-2223c46c8f56 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001863 | 829ea974-07c2-455f-a205-271d72e99bf7 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001864 | fd413ece-688f-4af9-ae39-b329fc71feb0 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001865 | 8cf50f29-a20f-47c2-8a96-fb48aeb7f68f | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001866 | f66910c8-8ab7-4037-a14a-6107b39e388f | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001867 | 27fbeef5-7241-4a5c-a0d7-947c2298347b | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001868 | fc0a968b-6754-48e5-8fab-990a67545535 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001869 | 1c041453-c3ee-40da-a0d9-f6120ab35595 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001870 | ee0e9526-dce6-43af-ac23-0935a028973c | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130001871 | 38217f5a-fd7d-4faf-994c-8b3a0c86ba9d | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001872 | ef6f0b72-be91-498e-9930-1eb6026ddc8a | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001873 | 344e7ce4-34cc-48a0-b396-4ebdda41cd7a | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001874 | cf3a9cd7-70de-4e90-8a99-349651712814 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001875 | 144fe3d9-06cc-42d6-aa6e-ef1285809bd7 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001876 | e7dc4542-65f8-4fe9-8032-7318a6a81059 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001877 | 7ec4a4b0-2347-4191-8718-65a3f7f16ec0 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001878 | ef27f034-6f79-4de5-819f-c68ba9cf9bc2 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001879 | 8032e7d3-27aa-4e0d-8b05-623edea9d822 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001880 | 6d34c4f4-418e-443a-8e05-fd1208133649 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001881 | 7c36f091-643d-436f-ac02-72472b8b16c9 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001882 | 50c1ca9e-2ef3-473d-995a-e1906b0e2f6b | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001883 | d48df17a-3d47-4e88-90de-b5f0cb1627b4 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001884 | 55cf549a-ff24-44a4-ab8d-c49bc1d902c4 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001885 | dc25532d-7634-433d-8268-bf0e8b64da12 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001886 | 6840d229-2c61-4b56-b767-50d2a9ba57be | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001887 | dfc0a50a-757e-4245-bb9e-0712f29de56b | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001888 | 0846c154-c3fb-429a-b0ef-0c4a15a265d9 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001889 | da757bf2-cf77-47a3-a2d6-96416db0d4b5 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001890 | 0cc66d0d-b590-46b6-a33d-70d8b2e6bcc3 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001891 | ff42a9a2-01e6-4fba-8c9f-fad3174eef84 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001892 | 3e1644dd-fa31-4155-830c-28a9db266c12 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001893 | bb32c5ff-216b-47e6-bff6-8db03de960f0 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001894 | 3f18ce0d-a86d-4518-a486-a74fe1d4c001 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001895 | 96a0cfa9-903b-4fde-ac99-3d4afe2a256f | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001896 | 058a6018-0adf-441f-98d4-700424598959 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001897 | 9a818497-6161-49c5-bc29-7d07af6968d1 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001898 | b2fe75f5-eb18-4b84-a7c3-77c92168e1d3 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001899 | af30944a-91df-4d34-ad3e-786e177bc4ae | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001900 | e6ae605c-f65c-4bc4-be0e-99a0a263fac7 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001901 | ec4891e0-82c4-49f5-aa0e-af537bf7ead4 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001902 | fe5f647f-afac-43d3-8dec-1dd946271f67 | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001903 | fa0a4eca-a786-442d-9a28-446dceefd54e | Pole | HFTD Tier 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001904 | 04e9ae6e-89fa-47da-9029-fc298ddc7393 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001905 | f8700744-ccdb-4253-850a-bd057f73c9d0 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001906 | 3f246742-297e-4197-82a4-038d21972036 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001907 | f6dd73bd-431b-493a-91ac-0c2f940d93eb | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001908 | 3e95def7-3fb4-4148-9e8c-7a41a080dd95 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001909 | 006bfd1d-bc17-44d5-8738-a5c00bbb089e | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001910 | 40343078-60d8-4c22-9592-1ce3ebfdc203 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001911 | ee54b362-5fa9-4de7-a0c0-0ae338c7f04f | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001912 | 0cf155d7-27fd-41b9-a1d0-4dc060be6bcc | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001913 | dbd4b02f-f6ee-4eca-94bd-477026884420 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001914 | 61908aa3-9b59-448a-ad92-021315eeff23 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001915 | db79698b-1db4-463b-a26e-5d6c05e9bf9e | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001916 | 5d72eebf-dc35-4ce8-b155-2f023a7b789b | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001917 | b845ee1f-9879-4778-ba4f-da52c528f605 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001918 | 56679041-8d59-4dd7-9c4f-1669ae7b6f5b | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001919 | b79fc751-e5f4-45dd-a9bb-49f2d37aeca1 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001920 | 547d5850-1bcc-49bc-8e15-cdad790e3961 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001921 | 9c785737-6de2-42fa-8b37-9e8c94180b33 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001922 | 4fb66361-1bdd-4b4d-9e00-35ba4094317a | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001923 | 97431d8c-ede0-4f6b-a296-038a5bda8bbe | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001924 | 4d3f9d2f-da3f-4bc8-a847-525eb2f0a355 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001925 | bafada88-8846-44d8-b260-8137cb4e898e | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001926 | 6013c15f-bb99-46e9-850e-4647a71c14d9 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001927 | cafd9538-2f84-4115-be4b-f05d84559eac | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001928 | a0e56827-87e1-4427-8715-2aa99ce2c9db | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001929 | c4127e7d-8eba-4059-8dc3-0b3cb3f78b99 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001930 | 6e09334c-2ea1-43b5-b31e-fa4c10074ecd | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001931 | c7ed9cd8-0fa1-4edc-ba92-0117dd529295 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001932 | a19ce921-79fa-4de1-85ff-e32b3808c4a7 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001933 | b5e5cf86-bd42-4ab7-a9e6-1e2656725532 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001934 | a1e4527f-4e9c-4311-a375-48b43d1f8c1b | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001935 | fee37963-6c31-4923-8cee-f839e20d3903 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001936 | a96bb538-7baf-4806-b79c-8d254e55a3c9 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001937 | e6bddca9-9ae9-49e5-a5e8-843636da981f | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001938 | b87c0910-ac42-4c1a-b720-74a05842bab5 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001939 | 985c20df-ae78-4612-bec9-4d1d89a69440 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001940 | 2bc3fc72-e7bd-4e7d-973e-20f8c7648c08 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130001941 | e1c755d9-3507-4bc9-9dba-b9d636ab4f0d | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001942 | 70d208eb-40bf-4003-8def-f3973169e86c | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001943 | dc4b7b1d-a604-4354-a5a4-0b84f1d6976b | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001944 | 35372b90-34f2-4d79-8fd5-85440191235b | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001945 | dd9aa1ef-64e2-4d00-9bd1-22c57afaed0d | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001946 | 7d9da2b0-9b08-4441-9e66-d9b9e22ddc40 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001947 | 986a7178-cadc-40e4-bd35-0db93472953f | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | 2021-02-11 | 2026-02-10 |  | Changed to level 3 pole does not need to be changed out, need to replace down guy, tighten hardware and replace 69kv jumper field phase. |  |  |  | Liberty | 2025 | 1
1130001948 | 0b877b59-c620-4def-8f73-d418140aff7f | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001949 | d814d3cf-5a3d-4819-8709-c06ff4799632 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001950 | 157bb57b-6160-4ad3-b33d-938a04cc3141 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001951 | 7db52768-7e70-4580-894d-084f51a8c2a9 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001952 | 075f2da0-2cc9-4c78-b741-83d30a00646a | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001953 | 7dd32696-157b-4907-a075-93889b3aea74 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001954 | 19ce6b24-5e85-426b-957d-23b4a8ec34b9 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001955 | 73109797-ac64-46e8-ae0c-b908f41072dd | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001956 | 00b9fd77-89d5-44dc-af68-b394b3bcb59b | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001957 | 75118536-2cbc-4dbc-8668-24172c2a4751 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001958 | 526ffd37-262c-4205-9eea-e5be282e2d83 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001959 | 75390c82-54f8-492e-b7d2-6dd9b53043d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001960 | 5f1d12d6-a743-4ce5-8562-e716b8f12997 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001961 | 8c33ff4a-24e7-4011-aec1-cb27983fe88f | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001962 | 46a075e5-4d51-44de-89d0-65f1654a7678 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001963 | 90e578ca-ed6b-4d1c-a108-c3fd9b5f3619 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001964 | 4b1f6b6f-ceda-41e0-813d-5e106b5832ec | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001965 | 682866e8-88a9-4cf2-9f01-3b3028168d22 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001966 | 5401313d-1f35-42fa-bf29-105eab38d294 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001967 | 6596c158-2bc3-4dca-9797-cd51ea69f4cd | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001968 | 51cbfc7e-9349-43ec-aa40-691a27a897ed | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001969 | 11237a51-1789-4e9b-ad4c-25c91e699457 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001970 | 381e4d13-0ee9-4bff-ae65-af96b01cf12a | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001971 | 0efd3256-decd-4030-83b8-2dd08fa277ff | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001972 | 31cab056-13dc-4efb-b5fe-0979fd87e6a9 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001973 | 35566c08-5d3d-419d-ae6a-90c12d56a86b | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001974 | 3e5fa1fa-12cb-446c-8a5a-9b65206fe7b8 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001975 | 38c48d19-ff5b-49d0-a69b-dff760465eee | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001976 | 3d7f74df-c904-4d91-85d4-2f337bd32aed | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001977 | 2b4afd08-e386-4417-bb5d-c42a9906f8d1 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001978 | 1d7bcd56-23be-4e6f-ba43-f6409db8d3e6 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001979 | 232fd5a5-85e0-4d13-94f2-75c6d28c6e6b | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001980 | 8550e1e9-b102-430e-a668-9e236f44565a | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001981 | 812c6d77-3d5e-4b4d-ab74-f87db9607451 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001982 | 84c01308-3a30-4c7d-b891-4cf7978f9c0c | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001983 | 9fd32fd6-56e5-4971-994e-530e138bb4f9 | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001984 | a84dbf8c-f31f-45e6-acaa-f8ae05bc7432 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001985 | 8df984a7-7a56-44d7-8f17-ed20bf4f9967 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130001986 | d2dfd70f-c13d-411a-9bf2-a3f7200ee5ce | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001987 | b15487ce-fe4e-4241-bf58-50ac4c3ac7dd | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001988 | ade3a6c4-99d2-43fb-aaa2-bf5a74f6ca22 | Pole | HFTD Tier 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001989 | ae907f3d-6a31-4c90-a77e-fd41d05d0cae | Pole | HFTD Tier 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001990 | 488a93a6-640b-4d58-8782-45cc2e8fe4b8 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001991 | 9c716cea-353d-40a1-9ec5-ce5f191c4d3c | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001992 | 3110ea1c-5bd1-457f-b99a-15d5e39200e2 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001993 | a6c10575-5828-49e3-983c-f0bd5fb7300b | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001994 | 2a755204-0c03-44e8-b0bc-d6f4c4883d86 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001995 | 7bdba4b8-b2a7-4a04-8aef-fee4078b2f93 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001996 | 4f526001-1185-4acd-a3e3-60ddce305dde | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001997 | 86a77624-595f-4d0b-b720-3c0289cb3762 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001998 | 5644e16a-bcab-4ca2-970c-151153bb536a | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130001999 | 7848c8f4-db12-42d8-b69b-34670cbd891e | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002000 | 5e4d35b4-9d47-45b9-ba0a-5cb3ebfc7c83 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002001 | 73d94ea0-b88f-407b-b54e-0e7fc593475a | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002002 | 0563280c-a8f1-4a91-bfb3-3d31002c2dab | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002003 | 20dfe33b-ccce-41bf-9f60-a04f09221578 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002004 | 5c4ccbe4-8c31-40a8-8222-7620c29065eb | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002005 | 290a2e00-67ef-4e7e-bcfb-5a58f387f714 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002006 | 1d900489-246c-49ae-aca1-fd1c881bfff7 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002007 | 1dbd14da-8dd6-4c21-ad69-ee62d193e122 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002008 | 1d4c5e9d-6f2c-401c-8741-1b03d4455716 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002009 | 1aff95be-7f01-45d1-96e4-8a282c990974 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002010 | 1ef6a2c4-325d-4852-ab96-9204729e35d3 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002011 | 1c8a0104-57fa-4757-87ff-7204c7128ea5 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002012 | d888170b-00e9-44fa-96d9-e5e4d9ac1296 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002013 | 391b6155-61f4-4c87-ac4a-913739009a25 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002014 | cdd62acb-4b9d-41e6-bf85-3409a1cf0683 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002015 | 348d0cd8-bdcf-4350-8b50-9b17e6015d4d | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002016 | fd30dacd-455a-4da7-9961-07ba7fea4e6f | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002017 | 34bd7f36-21ef-4a46-b460-399432e0849d | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002018 | fafad9e8-5ed6-4569-a6a7-b0b7d0b0e9bc | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002019 | 31b3ec69-01a1-4773-8def-094fddf0113d | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002020 | b40af3fe-918c-40a1-9123-9487ba1808d9 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002021 | 3198ca17-2857-4eca-83f3-f4d990bd6e69 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002022 | 8fdcb8f4-6664-48f7-9d21-67c6ddd6a9cf | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002023 | 102a4ac4-9bc5-4da9-bd67-297582af2a91 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002024 | 6db4ce95-3ecc-40ff-a7a4-e1d38fe36392 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002025 | 66ed57dd-4f41-48a5-9515-c46c6bd8832a | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002026 | 495c9d31-b037-4d23-8d6a-62b7ea696bbd | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002027 | 6e4eca6f-784a-422c-827f-2f2c48f752ee | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002028 | 485dd898-327e-4d73-92b2-fd071ccb2c13 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002029 | 6c87e8ba-2deb-4a68-82af-9846a0c87df2 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002030 | 4fc70023-0783-468a-9f20-b2d4849c3046 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002031 | 7a3541b1-889e-4a6d-b340-564b584c4e06 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002032 | 68a810e2-8dde-4b7f-8d92-0ba1ddb37f2a | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002033 | 7d4202ad-95e5-4a71-93f1-310e925e4c79 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002034 | 687a2a25-df42-4f4c-adbd-e537759e5154 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002035 | dd42ac7a-70eb-4ae6-a220-401ffe8e2add | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002036 | 69807d73-1c22-4d6f-9b92-bfab57e31c06 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002037 | 97191a49-590d-4e3e-bd8c-2aec9ca6b0ef | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 | 2021-05-10 | 2022-05-10 |  | King pin bent significantly |  |  |  | Liberty | 2025 | 1
1130002038 | 0b5564e3-e707-4425-8b96-2efcfaf76433 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002039 | d8069c6a-1394-4a06-9af3-e65bf837d125 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002040 | 3d45753b-7543-46eb-9e97-59c724149314 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002041 | d8efe912-1f0c-4e76-b582-024667a4f7b2 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002042 | 41019575-aed0-4603-8227-02f21ca13391 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002043 | d49a8cad-d360-44bf-9505-9e71c449e7ce | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002044 | 02ceb0c5-9c55-4bae-8743-1f002290c8af | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002045 | d49c7247-c0fd-420c-b685-e841c29f4220 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002046 | 062a10d4-0ad1-4b24-ae97-4ce6acd9b06b | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002047 | ddcb61a9-cd8e-4026-8f84-a3cdbba63208 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002048 | 0475b47e-4b35-4548-946e-126a6d8530a7 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002049 | d00bc188-d698-433c-9534-1cb37aeb1b34 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002050 | 01c4f125-4a07-4d39-ba73-b36005081ed9 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002051 | b968f4da-c5e9-44ce-ad50-349b008e5504 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002052 | 91a5c92f-e227-4365-8b07-fe02f190015f | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002053 | 9f5365f7-b542-4a6f-a2ff-ed82ae082bdc | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002054 | b195fce0-5199-4a1b-8bd2-05bc2a915fae | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002055 | acd58bd4-fd0f-4884-8143-6e2288e4e7b1 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002056 | aba25529-66af-4f4b-a588-37db8b05b647 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002057 | aacf146a-42a3-4109-ac98-33d80b5e8f82 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002058 | dcaa42ba-9515-4d6e-aee3-4c0aa0546ef3 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002059 | d554d4b8-0a2b-438d-b512-c819333654d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002060 | e65968f5-7e18-49b0-b78f-24e86351a72b | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002061 | e59f7617-02c2-4c0e-9eb7-bc597227bba0 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002062 | e75e0ef3-2fb6-49ef-9d05-22ac64fa2702 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002063 | ea472a04-0ce6-437c-85ff-7bf44bc30848 | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002064 | e69ace64-164d-45b6-8455-2ec519773e4d | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002065 | faa99ad4-c658-4666-b88c-3afb5c8f8d3a | Pole | HFTD Tier 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002066 | 3f29dd34-b394-40bc-a23c-fd0822e757c6 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002067 | d355c38d-c720-455a-88a2-474753e17391 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002068 | 0cb84489-4dea-4c60-b1e6-bbda3cdb677b | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002069 | 8f5f0054-1f46-4772-83f9-8dd4799107fe | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002070 | 0987eb82-2978-44d0-b7dd-206f5e9d4d47 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002071 | bdc915b2-a1db-4ec7-8168-55c97915d24a | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002072 | 697169ed-7b13-465a-b903-3ccc0b399a61 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002073 | e426e70c-83f0-4d97-b9d5-a489163aa24c | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002074 | 6891b239-c848-45c5-a415-81309ed07811 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002075 | 16055c60-98fa-4f7a-a5de-94d6ea4d85ab | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002076 | 6742c3d7-5014-4e77-89f7-f4dd00e36b2e | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002077 | 1651e3d4-1dc0-4225-92f1-72f11ec1776b | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002078 | 66def900-7600-469b-9faa-a900856c8057 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002079 | 35eabd22-f0ba-48a0-82b9-d5c0824ba6bd | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002080 | 65e9d501-aef8-489d-872b-ff59bcab4d54 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002081 | 3832ffc3-0b2e-4f35-99a9-07c81315971c | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002082 | 60e3173a-965b-4318-9238-e3b7f0b93670 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002083 | 2a17f094-ddf9-42ab-8c8b-bbbc100136bf | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002084 | 583ae9ad-9adf-4156-8917-af0092ae617b | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002085 | 2f10f4fd-3dfb-4327-a5f5-8a5937e213cb | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002086 | 5d2a72e3-8216-4bca-8ec0-14fe4a0eeb29 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002087 | 2fd1858b-a392-4140-8238-e41b1c936db7 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002088 | 5d67f1eb-e5cc-4c50-8fed-144807184d44 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002089 | 1bdc4cdb-ebb6-4fc1-a07b-4f54862572b3 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002090 | 4e8bef8e-2743-4080-afae-86c519fd1614 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002091 | 259f17ef-ae74-4b75-a494-b74bd2b14169 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002092 | 51f4b82e-c7d9-469f-82d6-abd100f15a7b | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002093 | 21abeddc-f80c-4a61-bfe5-8534997917af | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002094 | 6bc203fc-a5bc-4c9e-8d48-49fa7686d540 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002095 | 77377869-009b-45f5-9a6f-9ff1fb1b9245 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002096 | a054ba27-f49d-4d8c-9b15-37b8990d174e | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002097 | 792e710a-4a81-4ac8-a018-451aa41700f9 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002098 | a9eeaef3-a442-4961-8028-a646554e990b | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002099 | 701fb98a-9bcd-4ebf-8292-7ce080a7d127 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002100 | a42a1a2d-6bc7-4f90-ae84-278747f82a67 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002101 | 70f916c6-9efa-433b-971d-73c8f98228de | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002102 | fa21e8b1-a328-4e21-a4ad-8745a8356b5e | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002103 | 822f6a92-8e50-405d-a46b-85d0e9042c7c | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002104 | c07be6dd-70fd-46e8-b60d-b1efe6c8aace | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002105 | 9af49be3-c04f-4d03-8e26-0ce756b8d94f | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002106 | bd3a9134-f914-4056-aee1-43c622513394 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002107 | 978d0485-3a87-47ef-89f2-4b917128c02a | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002108 | ec7930f0-7f62-42ab-94a8-67802bfa1f5d | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002109 | 99e54a94-e9c5-4199-8644-420be1579690 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002110 | cb9ee7ef-be23-4461-982c-460181a3741c | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002111 | abf02d38-2319-469d-8797-bbc3891146c6 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002112 | cd4f05de-8abe-446a-afdd-4ded7fc6f609 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002113 | fb59c5da-9d0a-4da4-bf22-de2ebc621d54 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | 2021-06-29 | 2026-06-28 |  | Service is attached by wedge-bail on both sides wedge-bail is on service but no risk to public or reliability Considered idol hardware |  |  |  | Liberty | 2025 | 1
1130002114 | fc2a9cc0-b145-4d7e-82b2-581f5e3dae9f | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002115 | cc490623-3855-4887-8da3-a719f481840e | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002116 | 0b68a451-7788-4a8e-b2f6-22963332269a | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002117 | 933f8ec1-0cbe-4407-b4dc-31448210676a | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002118 | 2d0ff6d1-73bb-44f9-bdc0-35a427a5eeb8 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002119 | 9636fd8d-8d86-4506-a690-0bf7744b2b66 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002120 | d69c52d7-283c-4a45-b673-0af2dbdc1454 | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002121 | ab71b13d-5f8f-46e3-bc54-e128437b681b | Pole | HFTD Tier 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002122 | a8e69d42-444a-414c-b6b7-5ecd7bcdcbc8 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002123 | b3577643-12b2-4928-93db-ea4baf3358dd | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002124 | af0f6cf6-8a59-4e8f-9a6d-f31231274621 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002125 | 6b02b67e-2e4d-4745-b5b9-311f0e5e1df2 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002126 | d29b1171-3281-4930-a1bc-d58cd937c498 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002127 | 36ad5913-8cd7-42c7-828e-773a1888feda | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002128 | 9b71307c-dfdb-4711-ab2b-e8a20fda2dfd | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002129 | 4a8a7b63-cd99-40de-a477-f7d6bb21a378 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002130 | 9c9e4b93-3de4-4b0e-aa47-8de5833f9240 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002131 | 09cbf493-2005-4a68-b940-e61155dfb64c | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002132 | 813f1274-0381-4685-8794-0c66d8792b4f | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002133 | 637bed12-26e7-4561-8741-64f2eb372892 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002134 | 81b1a7bc-60f5-476e-a969-4cf9c68186ab | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002135 | 5997646b-b80e-44c2-9263-36338731aa4a | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002136 | 7de91a19-9b7c-4271-8135-01f57ebd2ffd | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002137 | b22e7a3e-f920-4e74-83e7-699d76adb9d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002138 | 71ed9e41-996b-43c0-a0da-87e5e5794a7f | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002139 | 5c5bcf67-be2a-4afd-a874-d7038f1d4ae7 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002140 | 1e6d628a-6c56-445f-910e-ddd39aad3653 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002141 | f87581c4-6579-4365-ac11-9e767761d3bb | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002142 | 2ec6b880-ab4c-4c7d-bab9-acef35d11f55 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002143 | cb687a34-fc7f-4367-909a-801ba3a2f0db | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002144 | 2d3df91d-46fa-4f41-b735-532d21dd4620 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002145 | b510c45f-c689-4756-a5f0-85bcdfb9fd50 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002146 | 2b2c9ece-414e-4010-bda5-1b1853947f6a | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002147 | c5992e72-d5f6-457b-a13e-0a23aae26ae6 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002148 | df364ea1-a48a-451f-9d09-93d13c19b9c5 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002149 | 6b233bca-6b80-4348-b1f8-c6c3b262269d | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002150 | fe4ee3a0-bb3f-4d86-9fab-f2a147fadab5 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002151 | 6ad4a601-476d-4bd6-b3ea-8bfb599b5d1d | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002152 | b12f5e9c-ac18-4f59-a37d-23c4f73437f2 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002153 | 535619d8-01bd-4ca8-bbbf-c2d65559bef2 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002154 | 916dda97-dded-4eaa-ab95-6abd17098b08 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002155 | 595085a2-838d-4df9-9371-e890f10e5b05 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002156 | c9243a75-de5f-4a88-a89c-a2bb48669383 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002157 | 61f32093-3370-4fe6-a39f-bf511de8c9c8 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002158 | b8b81add-0d53-499d-804c-a9aac3129e4d | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002159 | 43c865df-3edd-4779-8ab9-a6d019d91180 | Pole | HFTD Tier 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002160 | 1152a63a-2a0e-4a25-a0eb-47f97a651d89 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002161 | 0211e8f8-b6ff-4830-876a-48b93cbd08b3 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002162 | f4e36da8-0b4c-41b7-ac66-aa197514d18a | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002163 | 05800e39-c7d1-4b5b-a76e-c1c836d516bf | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002164 | e5a0be90-e1c2-4b80-bb6e-442635ce73d0 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002165 | 5a78c1b9-2070-470d-bdde-e2224132a44f | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002166 | 4836bf34-9269-4123-913f-a0d04f2507c3 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | 2022-10-21 | 2027-10-20 |  | Pole needs replaced. Com equipment attached. Transformer is leaking. |  |  |  | Liberty | 2025 | 1
1130002167 | 4f06e832-849d-449d-90b5-0407f1d96e58 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | 2022-01-17 | 2027-01-16 |  | Pole top split is not an issue. |  |  |  | Liberty | 2025 | 1
1130002168 | dc6c0124-508c-4376-9344-e45e9a81c989 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002169 | 54d9c368-af37-4469-96f2-0939976416d8 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002170 | da66590b-acbb-458e-bbf7-1a6ea54ae44d | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002171 | 490506b0-59ae-4dfe-bfd9-035280b95623 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002172 | e6f40188-8ccd-42dc-b207-172408ca5641 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002173 | 6db03cfe-d3c9-4a60-bf9a-6a3a06467bad | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002174 | fdede023-b3e1-457a-af88-47fa1f6bc977 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002175 | a1508a0e-8f74-4b2a-a416-b04d2dc3bc78 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002176 | 2fd3d56b-fe1f-4ded-bcb2-2cc3d2d4b39e | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002177 | a5866153-51df-47a2-93bf-3e873729c1f4 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002178 | 3617d431-76a1-4fb2-90d6-8ccca747ba20 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002179 | b348bcf3-f28f-47ac-89b4-e3176fb40321 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002180 | 31b80abc-d615-4816-9e40-40405a6bb6b5 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002181 | c0089e0e-773a-4bf5-812b-46dcb14260a0 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002182 | 1f8b0832-4db5-4553-87ff-77ad4bba8b8b | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002183 | b5041df4-aa6b-4bc2-8fe5-3481ed039ffa | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002184 | 7a92742c-4d5a-4c14-99a0-425bdefdef94 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002185 | 236604c4-9294-4cb2-b998-4538b47637bb | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002186 | 7562d2cf-2ae6-40f3-b2e3-b6bd5d1d3eb5 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002187 | 84dfda52-8222-4551-b993-ea82dc159805 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002188 | 8157bf08-64f7-4a4b-bfbf-6327d5b1c540 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002189 | 3b5d666d-34e6-4f28-a604-061ce9813249 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002190 | 87c9e503-e571-4bac-8aa7-fcd7e8bf852f | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002191 | fd668582-c75b-4e92-85c9-31d0f5ff75f7 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002192 | 89ce9c8d-6786-49e6-9aa1-7f340250f257 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002193 | 388da06a-d796-4401-b0c4-f0cd0f4f2d88 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002194 | 95f95bff-3d70-4da6-81ed-04f0d659589d | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002195 | 5a4bd463-45dd-4f9b-8430-6ab6cc5d383f | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002196 | 917ce863-0fe6-4434-9de4-9a2c0da7560d | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002197 | 91488720-29f3-45dd-b103-f3532d961515 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002198 | 9fcde381-bc44-4000-8ba4-81d05f6e1a21 | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002199 | ad650805-040b-4934-bb05-b83e22cbb3cf | Pole | HFTD Tier 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002200 | 52de37d7-ab7f-4b7c-a2de-48c6320659a1 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002201 | af718e4e-7ae4-4c6d-9257-92113c342ee9 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002202 | 53a5f6f2-079b-42f1-996e-4219f6bbdad2 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002203 | af6d4ddf-7a25-4c52-b979-d7f12bec1ce1 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002204 | aa78fa36-7666-4e67-986d-4320d1e1367a | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002205 | 7c78dff6-e125-4a0a-982d-a006e9900bce | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002206 | 2f8b5669-282b-4c29-902d-dfce109c59be | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002207 | ab4083ac-8340-4d40-a7f1-f0e60e08b1bd | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002208 | 56667e94-ec85-4255-96f4-c0de81248b9a | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002209 | d29561a7-8405-4a5e-b5b0-b3878fd954d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002210 | 51bfe483-4817-42c8-acbf-272e6b90525f | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002211 | 9605d1d6-55c8-44ad-b1ac-612445ea4b72 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002212 | 7f4f1a4a-e575-404b-9e28-e92223e83328 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002213 | a64ba217-551f-4721-8ee5-0aba3c66d87d | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002214 | f5f39dc4-94a1-49da-a567-f006b67ac6d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002215 | 84ebc02e-44a8-4f14-b714-69c304893e6a | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002216 | f1ce3b9f-2443-4abb-a2a3-7c38ba45c3de | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002217 | 9ccd0455-f1dc-4168-9bd6-d878bf39bfec | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002218 | 674722df-ed2e-4c30-9007-ec44c3488dbe | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002219 | 744d1497-f8e6-444e-ab2d-f2d73c919b1d | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002220 | c4ffec8e-09cb-4b96-9de1-e0052129e00e | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002221 | 1e4367f4-2c9d-42d0-844a-303194872c6c | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002222 | ced65230-8ce3-435d-b3cd-049e512f70f1 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002223 | 228db20d-9b6d-4847-9d06-ce75dcc32870 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002224 | b4031d0a-bf36-4ad6-85ac-bdd9db8d462b | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002225 | 251a0bb4-83f3-4b78-b4a1-ff8bbb9bd5d2 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002226 | b45fece8-d42d-467b-a9bf-e4345b362c31 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002227 | 28146eac-d943-411f-8889-deb211631540 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002228 | a28035f5-b9fc-4552-a383-28122d72a803 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002229 | 307d8277-ef02-442b-8ab6-fd169e6ca394 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002230 | a1fb95c3-ca88-473f-a284-331bfaa60309 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002231 | 32c57763-aefe-415f-bf04-69341fe31c28 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002232 | 6c2c97c0-5e55-4339-8638-93b95ed5fb96 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002233 | 2c114db1-886f-437c-b12c-1fb65ec0526e | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002234 | 48030b4f-b861-452c-9a92-4d2ac63cb503 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002235 | 161875ca-cdbd-4985-acce-7cbd1bb65e03 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002236 | 55ba0fec-d19e-4fcd-888a-c18a6a2dacd6 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002237 | e4be35d7-263d-42df-9492-8650436f5c1f | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002238 | 576ee34f-d0ae-480e-a976-b8a92aaa4971 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002239 | d794126c-74ad-4908-8120-3f7f9e5ddc95 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002240 | 58a009cc-6878-4e63-8c78-b7de977c6cb2 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002241 | d7c21f9f-9c8c-4152-8c10-516a78c9d365 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002242 | 015c2480-1383-4725-8533-0ab38fea2293 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002243 | c870e2d3-6d0c-4a62-a313-96eac2328b7c | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002244 | 42dac4db-8e0d-437c-bd90-a7b328ae40d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002245 | 2569924e-25dd-4879-8a83-33ccb91bae84 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002246 | 08ff3a2a-40ad-498f-b462-f6eb83c963f2 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002247 | 62a5cb90-d3b1-413b-be86-8b8d736caa62 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | 2022-10-21 | 2027-10-20 |  | Pole top split |  |  |  | Liberty | 2025 | 1
1130002248 | 08c5f11b-ad44-4173-b76c-b2af354dd03a | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002249 | 9d310ff6-a880-4d39-806b-4b1436070d18 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002250 | b9e9e230-6219-4fa4-8658-65c23f0e48f4 | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002251 | 89184d9c-8092-4880-8664-008afdf3310e | Pole | HFTD Tier 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002252 | 0874076c-938d-4888-9586-ba6f7d508656 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002253 | 6945c72c-9976-4651-906e-5bee6e6fa0b7 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002254 | 0e057503-38a7-46ae-aa73-161e8e7ef00b | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002255 | 8c36461c-d479-4f66-8004-085b96e9e8f9 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002256 | 3c71a6af-e6ec-43af-9769-781499060547 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002257 | 88dc3f26-449d-4b7a-a4d6-7cb485ff3f5f | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002258 | 037f4bb6-ff16-42da-b708-14e877054505 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002259 | dbc9e480-1418-493e-8314-302d2f3b7778 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002260 | 5d3b9254-7f11-4f5f-8862-a67c30ecaf43 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002261 | e02bb811-23f5-4894-93dd-95d83d0c2e11 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002262 | 5c93a722-7f9b-4af5-9dd5-92d18edd7c26 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002263 | 7c185836-647b-4458-a807-7d73341df16d | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002264 | 55031869-6936-4e29-9700-a254e3170282 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002265 | fe49a6bf-4d67-4632-b08d-43d24b4066b8 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002266 | 5339741f-0c7a-4201-a3b2-18e80f377f46 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002267 | dbef4d57-e519-4a39-bbac-b0006b42557e | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002268 | 451033b0-1758-4568-969d-3e6279118a92 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002269 | db5738d8-5ac3-4429-9c39-386354d2b0c6 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002270 | 453f9748-a296-48d3-bc0c-75f3653f60dc | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002271 | ee2b3e8f-93ef-47df-99fc-a7b002203614 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002272 | 4c2d2957-4fd0-4dbd-ac63-7e0dea3a1e58 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002273 | b5c34493-c737-4286-b045-6d7fd8db6f70 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002274 | b98ff61c-6834-46f1-8b40-a043d0ed0251 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002275 | afc78ec9-a571-452b-ba2f-e79af29f8ed4 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002276 | c5106f44-b5b7-4ebf-af75-cfdf2e5db260 | Pole | Non-HFTD | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002277 | 92c8b363-e6f3-479f-b643-2fab4f152750 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002278 | cab6999d-b6b5-48bd-8d28-dd7cfd260ea6 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002279 | 9f3147e5-5128-4243-84df-eaccad993da6 | Pole | Non-HFTD | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002280 | c96067ff-f30a-44be-8894-ae47b1c897cb | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002281 | c9295586-d953-48be-b98c-d4c5aa968576 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002282 | b3f06a93-8ca7-4681-bde3-fdd11bf86898 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002283 | 1485262f-ca19-4be9-a707-c50541d554a7 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002284 | f9379adc-61d5-4744-975e-09ec8614da3a | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002285 | 10ff2d43-ca85-472d-b3f9-89a9e90f8ed5 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002286 | f651612d-e0f7-4ad3-b916-652e318ff48a | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002287 | 2ae4a931-d30c-4f3f-89da-a031b868cc2a | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002288 | 50aee005-d410-4074-841d-9dd018e4d149 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002289 | 3548192a-ce1e-4a38-8955-52f57a6f4b0a | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002290 | 5b66073f-3706-4bf2-ac6d-8c79ccb83394 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002291 | 71be8d32-9e4f-4ba8-9a75-0a15e922a5ef | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002292 | 2f55ab03-6f57-4749-8aa2-98d5b1b65d85 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002293 | 723a389d-ac75-41d5-b5d8-4f27cc245836 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002294 | 2ca83bdb-bd87-4fe0-acb7-bf91f62b1ac6 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002295 | 3bdcc904-3039-4424-9d36-549b44cb56a5 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002296 | 9918e2d6-29a7-4611-8937-99fd60659765 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002297 | 6eb674d0-4723-45cf-808c-a6510fce7c67 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002298 | ab4369bc-bf7b-4d8c-adc1-b875d68c72c2 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002299 | 88c2707f-b121-4dfe-ba0d-789fdc2ad72e | Pole | Non-HFTD | Distribution | 2020-08-18 | 2021-08-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002300 | 18c35cdd-0462-4221-b7c8-aa3c5f36de69 | Pole | Non-HFTD | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002301 | 811b999d-c62d-44de-8362-ac538008ba82 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002302 | 14e9bde6-b391-4cef-b64f-54fc50ac9ae0 | Pole | Non-HFTD | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002303 | 9cf01289-ab07-4f46-a4cb-49479fd9534e | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002304 | 9d8c5c96-3dec-452b-8fd7-06d7412a2ce2 | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002305 | a877e69f-5cc3-42a3-b5b0-a702e90b470c | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002306 | d3372f1c-4378-4ab0-b729-13c787dc499f | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002307 | ab54b250-806c-4168-9e03-52650d47f7fe | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002308 | ab444256-8dc6-43fb-8978-e839456af26a | Pole | HFTD Tier 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002309 | afeb76ca-aa75-4cdb-8b3a-b8808df05d7c | Pole | Non-HFTD | Distribution | 2020-08-18 | 2025-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002310 | 09808cdd-b7ef-42fc-a490-904b7dd1a99c | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002311 | a8b5fe50-2c39-4c8a-b16f-793e6f10556a | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2021-08-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002312 | 01c4f200-327a-482e-9420-a4b74a4a5075 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002313 | 9bb9420d-a7db-4ba1-8e1a-90986940145e | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002314 | b5e5a689-b304-48b7-95c4-8966b0c2c421 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002315 | 7dd2857a-bc0c-412f-8aa5-d3dab831e510 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002316 | fd24a9a4-ef63-4840-bf6f-6a64480f8e27 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002317 | 7c01e3ad-66b4-41b2-b0de-539308e0a955 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002318 | be93ec67-49c5-4db6-8fa6-0246a9f2b08a | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002319 | 8aa38f18-e81d-45fa-a12d-856edbb8a495 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002320 | b45f0373-1ad9-4cfc-9278-7dd1ef3fc6ec | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002321 | 3aac25cd-18d4-42f6-8c11-945552fadc82 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002322 | 4b5f1c21-5255-482f-bda5-62bd6be6a9b4 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002323 | 38ae9491-c1c2-4fe1-9970-b14b5754915e | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002324 | 5709ba8f-816b-43cc-a89f-343c48fb2433 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002325 | 2663d61e-a9ea-4e55-9800-dc9d5647d33c | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002326 | 5cd5616c-6f7b-4efe-bc95-970d3669ce69 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002327 | 25c7c50e-099c-48f9-985a-8d9503285c1f | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002328 | 3d5fbd3d-7774-4969-89ec-0980349482fe | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002329 | 1095a1f7-41d8-41b3-9c4e-9a910624b565 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002330 | 443da5f5-40ff-4a48-9f8a-327cd6c62f82 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002331 | 93e27638-5729-44b6-b534-6dd6a741a88c | Pole | Non-HFTD | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002332 | f273512b-7a48-4b91-8957-7ec60a965b61 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002333 | fe2f857e-3972-40cd-b6d3-f614903a91a2 | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002334 | 72663578-72f0-4579-a218-40d4ffbcb42c | Pole | HFTD Tier 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002335 | 66466e1b-525a-4fef-91c5-975c99eb4cfb | Pole | Non-HFTD | Distribution | 2020-08-19 | 2025-08-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002336 | 080420c0-d108-4057-976b-0baf9dd9aeae | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002337 | e760087c-bb48-4c00-807c-29427a41bb11 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002338 | 046ce6c8-929e-41ad-9d43-7239d315b280 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002339 | d9cfb9d4-94f0-4570-b691-1d71d00d4460 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002340 | c129ca7d-ed0c-4254-b9c5-641333619ca9 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002341 | f442b77e-cb66-422e-a8ea-e0596c67fe0d | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002342 | e7a8049b-d174-4b61-891a-9918452f9b24 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002343 | 36ef9d67-8998-401c-99db-330696393cd6 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2021-08-20 | Level 2 | 2021-03-24 | 2022-03-24 |  | Will not meet clearance issue |  |  |  | Liberty | 2025 | 1
1130002344 | 98e69d14-a840-4608-a01a-e405bad3fe08 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002345 | 4f406a31-3d44-4b89-a8f6-8409844660f9 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002346 | 20037d15-fed1-4a24-b0fc-6db8a39955be | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002347 | 1d83f641-e17e-4a91-8a61-e8bdfd5a64f6 | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002348 | 49ad1175-8d66-4c68-8b57-22fad176056d | Pole | HFTD Tier 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002349 | 2acb6da7-16de-41b2-9381-8595a4426468 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002350 | 290bfdc5-072e-46f9-8c7c-2ae3816280ca | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002351 | 296e128c-6c61-446e-ad5b-afd9fea966f2 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002352 | 4d33210b-47ca-4af3-912c-4b60024ea558 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002353 | 2e56e6ed-6bf7-47b7-a989-fd412931f776 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002354 | 1b164444-d1c5-437a-90b4-67936087b88d | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002355 | 2404b8fe-084e-46d3-bb1d-b3f5a56f3794 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002356 | 1f4cdf85-591a-4ffc-ba96-bd0cf71a06fb | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002357 | 19b5d6be-7b33-440b-bfae-1db15d626e24 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002358 | 16a43eae-fc46-4dca-bdfa-371eb00bda01 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002359 | 18e3e729-8144-43cb-a98b-e6b18d99a77b | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002360 | c615d57c-94a5-409e-845f-f88c848eef43 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002361 | 1c0d7534-e690-4c0f-8e81-210c9bcee5c8 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002362 | ec57f022-d105-4971-a0a2-a20855e356ba | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002363 | 120a58a8-b0c3-41d3-bb84-da1f25905a69 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002364 | edb3418c-512f-46d7-8443-d9a508cc7672 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002365 | 17a99d36-eed9-40ad-9aa3-ec8d689230d7 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002366 | e9e09793-9636-4526-a13b-cb424e4e6672 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002367 | 181416d8-5923-4b0c-8cf5-091451d27d45 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002368 | fcf8168d-30e0-42ab-adb2-36e4655389f1 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002369 | 724b8804-5e98-40e5-bfce-24e62c9b9745 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002370 | eff1f07a-da92-4609-adfd-ff1fd725c85d | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002371 | 70170b6c-6ae3-4efc-9e25-bcfa526b0102 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002372 | b83e0265-85be-4f55-badd-a27c37b6edf2 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002373 | 7046a946-aa1c-4421-8be2-7dd426be470d | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002374 | bbed361c-7952-4b23-a0f6-1f576c0fbcf2 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002375 | 7464383b-60bf-474d-aa59-bac45025e8b1 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002376 | a4b560e6-1d75-40cb-a115-e7764c2bf7e1 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002377 | 8b195a16-3acf-4455-b579-1d75f8cac2bf | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002378 | a1f9bab8-3242-403f-8cf9-5a87f6f5b867 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002379 | d377aaf3-701d-4eff-ade6-67ccf33aab48 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002380 | a0fc2ac0-9e91-43d1-b7a4-6889bfaf3f09 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002381 | d065a93c-2b76-4ddb-a651-a0c8b1fec846 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002382 | 65ee9b37-0b7f-44c4-8af2-d2b13933f0f7 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002383 | d4a7cb65-7f1c-4982-8440-273be46d92ba | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002384 | 6788174a-cc61-4c97-ba38-c500cf43cfd3 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002385 | dd7db983-9c8b-466e-9335-6082c40a9b30 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002386 | 578bccc9-a71a-48e9-ba9b-019c616783d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002387 | d6c67903-58a8-4beb-8c54-31632b0ba073 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002388 | 503edd13-1405-4654-a70d-285465a4416c | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002389 | d32d0d18-c709-426c-b914-db34bd194039 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002390 | 460515e4-f6fc-4904-bab4-ee97dea0cd9d | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002391 | d8f09f6b-032a-4324-8d1b-23324449e63f | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002392 | 423b9eaa-1d6e-4bcb-b984-8aa9c584c967 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002393 | ff711c0b-540c-4490-8846-4c33771bf483 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002394 | 94149a5b-8f4a-4555-8f20-a0e5104bd592 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002395 | b02a0c2d-4dc9-4cf3-b256-40d1ff9ef270 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002396 | b046d6b5-9f41-4f25-a3bd-d4b59c7628af | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002397 | ac165c9b-15a1-49e8-965f-1769af3fd06e | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002398 | dfde9fdb-3f97-4c82-b1b2-c879ab736ccf | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002399 | dd1a9414-6087-40f5-bfcd-a04017f99b0d | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002400 | ff4ddf1d-a766-48e0-9172-3a52af9f0191 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002401 | e41a0e8d-d0b9-48f0-a74c-4433a5b2fe7c | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002402 | 708b9374-1d03-487e-9584-ffc790998eb3 | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002403 | 8ddd82c4-023f-4354-96e9-10b74739127e | Pole | HFTD Tier 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002404 | 43f9115b-9101-40f2-b41a-9f811941ddec | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002405 | ffe96216-db00-4a09-840d-c79543dffda4 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002406 | 4bd97999-6744-437d-a5d4-c513db99e08a | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002407 | e53b9ff8-377c-4624-8d57-fa8ae40e9fae | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002408 | 5047d9df-483e-463d-8cff-9352daba5a91 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002409 | fe7a8dd8-8790-45a2-b39e-812edd1361eb | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002410 | 5fcab607-b49a-44b8-a4d6-2e826096f695 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002411 | ce3f6533-b1db-4ecb-9b0b-109b863824b3 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002412 | 574110f9-6a32-4710-a86c-8915792b1042 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002413 | b1b3fce1-6e7e-41a6-b32a-45ae0b6a2b65 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002414 | a09e5d65-3ee8-438f-a62d-1b04fd7abca0 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002415 | 8f0be831-2257-4c68-899f-c8901df70abe | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002416 | 9f85ee01-9a5b-40f6-ab78-a3341136817a | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002417 | 8b3703a8-8b2a-4429-99e5-3ff8c9ff6d37 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002418 | a4062a4d-8e86-4645-a051-5fc867a0e355 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002419 | 8a735ec5-2713-47c2-91f0-271596c41001 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002420 | f9655750-ee7a-44a0-8f04-80135fcdcf77 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002421 | 8ce2769d-c402-41bc-a24f-6d47b4a2d5c4 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002422 | fa9c2cd1-dd55-4c6f-a638-084f2a81fe81 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002423 | 83ca67f8-eb62-4096-819e-6dd136034245 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002424 | ec3dcdd7-9c3f-41f4-97a2-a325d4153c1c | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002425 | 798006f7-b816-421d-a0e1-2119e0cc3dda | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002426 | e9254aff-9023-4222-8427-0642bb90b0f8 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002427 | 714cace7-bdee-4b10-a429-dbf01f0d8817 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002428 | c8f0f0b4-6bfd-40eb-b187-3e6bd285d61c | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002429 | 13c979b0-53df-42ea-b29a-161e807952fb | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002430 | caf10615-6298-43a4-83e3-6b71b9675914 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002431 | 25dde5d3-9c0e-4a3a-bb29-c29926f5cc49 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002432 | 9b6379f0-956a-4034-91c9-6ba5f91802f3 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002433 | 291ff5a2-1c7d-4228-b267-69eca0d406df | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002434 | 38b0a9f4-2f81-4691-9e88-0f0f66e84a2c | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002435 | 2a2c61a2-e97b-45ed-8a12-51f2093f176b | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002436 | 36ae1088-f3a9-4747-9692-adb8d2bebbe7 | Pole | HFTD Tier 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002437 | 3bc9967a-d0aa-4488-a474-f51e867c36e5 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002438 | 2a0d97f3-0303-4f8c-a13f-de23903c8c12 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002439 | 8d90996b-d904-47c1-a474-ddf27517edf7 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002440 | 2ad9e6bb-cd42-4107-b85d-713c55e549a1 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002441 | ccd99c5b-9b21-40f6-837f-4c788ec7d461 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002442 | 25a10e5e-b5b6-459b-a7e0-d85acf4759b7 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002443 | c646a5b5-fc57-4f5d-be09-9db12d1cc650 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002444 | 21d20f80-bd9d-4cf1-912d-28a5e25118d3 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002445 | eac3aa17-2c63-4359-91cc-5152023cdc1f | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002446 | 20494439-07b4-4765-bb9b-9a10b9919d39 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002447 | 0dfa2a0d-43aa-4e39-ac2f-a6e18bf117a3 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002448 | 194783d2-4339-4b29-aa4a-c5c6350ff681 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002449 | f3dcbfd8-0e2e-420c-847d-81f844cffd16 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002450 | 1a6bc9eb-b33f-4881-9b83-bd83882dc9d6 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002451 | b76bfd6a-40e2-4079-a87e-b850886417ae | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002452 | 1a86563e-f6fa-4bb1-bb29-907fe461d184 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002453 | b351a7f2-224d-4cd4-aca5-22122e479ac6 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002454 | 10e52de0-8ad8-47fd-ad88-4cc811f53231 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002455 | aa45a9d2-4e27-4911-9157-4dd9ddad9397 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002456 | 17c89b67-9c69-43d1-851a-cdbd04caad12 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002457 | 6b2bbb73-3f82-4f9c-a0e8-927f38bcc7dc | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002458 | 15cea97c-174c-4a49-a4a7-d4af04b3b229 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002459 | 6db749a1-1a5d-4c39-a1bd-7a12f61de856 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002460 | 0f277fe5-d973-4160-9ef4-936e0bf5473f | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002461 | bc4f3a85-7192-43eb-9f56-26bc260cb3e8 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002462 | 0f8278c0-5d4c-46ea-8eeb-0dcaae21c278 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002463 | b85d380c-57cf-4c64-9aad-1b995413088a | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002464 | 71d11db3-e944-414c-bfaa-ce24d212da3e | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002465 | c0b3e5af-87c0-40da-8175-68dfe2b2cf8a | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002466 | 74229587-c37a-4884-ad39-1b24a79243d3 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002467 | 5bc97d7f-e75e-464b-966c-8eaa206a0d12 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002468 | 737e8da1-2771-41f6-9524-ef0d3f6d00fe | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002469 | 653e39c2-86c5-420a-93bd-823a9b33cd47 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002470 | 83e35432-4064-4aae-afda-55c42783f64a | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002471 | 53d78c6e-5722-4446-9f01-09481e51ff20 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002472 | 7d43d86e-07fb-4fa3-ae2f-bd32605b066a | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002473 | 4bb4eb82-e238-4578-bb15-809d0e3feec5 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002474 | 7f7e2670-8d9b-4e1c-85d4-d16716bffc07 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002475 | 422d8a55-b179-4a29-ac5d-69f8235f292d | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002476 | 8746834e-548b-4ea1-8698-f62cdda2d08c | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002477 | 0c576fa3-328a-4596-b4a3-93a10eecf676 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002478 | b1b4e4d7-b056-4319-9efa-242c22516399 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002479 | 0509118a-5be4-4204-895d-5d9ca101510e | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002480 | a8c68e71-550f-4dd0-b3f4-8a768fe8728a | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002481 | 03959e41-5712-45e9-8064-9d0cd087740a | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002482 | ac887a93-6032-495d-9319-29a17c154294 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002483 | de0a915b-ead8-4c51-abbd-81b09d336567 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002484 | d9bf2872-c676-4c0e-9f77-33f997728f81 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002485 | e41dde77-3a78-4ad0-a169-2815a08ec305 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002486 | 9db055d7-2483-45fb-b97c-470efc2fc826 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002487 | e0deefa4-7549-4abd-b562-43394f0bc88c | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002488 | 9cb92896-3a35-4ec1-abd6-a0d3a2353e61 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | 2021-05-10 | 2026-05-09 |  | Bent stack |  |  |  | Liberty | 2025 | 1
1130002489 | b70951ed-fb8f-4576-ba69-5605aa6bf76a | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002490 | feb7c63c-674a-4f50-bf0b-b62233d13bd4 | Pole | HFTD Tier 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002491 | 04240fbe-8615-4a27-9b7d-38f9c513796e | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002492 | 898a9cae-21a5-4dfb-a943-0b88b56bd2ef | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002493 | 05735387-2b6f-47f4-aa1b-ed79fed23364 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002494 | e1eb8ed2-847e-4b3e-8bae-a61b99063acf | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002495 | 0689b605-fecd-4319-be07-2bdf5d64ae8d | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002496 | e5d333d2-d180-4deb-9e61-69d19076863f | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002497 | 0642d086-0be9-426b-b9ac-9a801b57a878 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002498 | fe2a45e3-0af5-4a9a-b946-826f08320464 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002499 | 08208c8b-bc39-4294-af3e-51e6ea1fb3bf | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002500 | d480a95b-8835-4a16-8963-49cb101fb3a1 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002501 | 091ac45c-1b4b-45e4-a73e-5e1b04c88ce6 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002502 | d7d0c8bc-56a1-4ced-90a6-cfa8b42e83bc | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002503 | 3ec8fbff-93a8-4042-8e0e-69bdb5d8cc91 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002504 | ab3fe644-3280-4509-a0cd-1ce9fe622fa5 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002505 | 3db2b8ec-f03f-4428-8c6c-29036754afe0 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002506 | af5a584c-12ce-4b47-8f8d-32dd295a4b8d | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002507 | 4bfebac9-2560-4f0c-a90e-91c671b8048e | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002508 | ae0e8e50-910d-472e-9c14-ed5c90828881 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002509 | 4639c896-33ba-4496-8a7f-7f79b405920a | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002510 | 9fcd68a0-7631-456c-9a09-053129464caf | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002511 | 51634ef9-6b28-4308-a0ae-e33bf474a973 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002512 | d2c000c7-e232-490a-bf7d-939c6e93f729 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002513 | 508c141b-125d-4ba6-8992-7ad79f3ae5a6 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002514 | 8f46bb38-599f-400c-ac58-15d64dcc60b0 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002515 | 5775b823-3452-45e4-9aac-6665444284ba | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002516 | 8e1d1a36-483e-4ccc-967d-8fab40e487f5 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002517 | 53479864-ed55-4c5c-9aa8-5d6d490e13fa | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002518 | 8dced52f-467e-4903-b7b7-0dc9c8f286c7 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002519 | 64d293f7-bc29-49bf-b88f-087ab25c52d8 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002520 | 91e29412-5c62-48a1-abad-8ec5da3020d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002521 | 63af1910-deea-4bc6-85da-9a84b0d40ecc | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002522 | 9979df8c-c3f8-4472-97a8-231e91ff0e6a | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002523 | 5b36e71b-745e-459d-b7a9-3f095b896ce4 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002524 | 974d755e-6c14-40a8-ac35-7f210a4b2b62 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002525 | 591890f5-503c-4d4f-89e7-57bbf4109907 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002526 | 976892ad-4b3a-4468-943b-f56b5bb6d73c | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002527 | 5ef33cea-2239-4aea-9dc3-0f0e36e42d49 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002528 | 9a7a7b73-82a9-49fe-ae6b-2f2ca24d9437 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002529 | 5ec95d73-3fa9-4f7e-b013-15dc90e532b7 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002530 | 9acc4129-1b85-4117-b0cf-508654e0bfb5 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002531 | 5eb99e4b-7408-4098-a89e-4f6e2401656f | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002532 | 9e15aaf0-92f3-46e6-b145-a670d9c44397 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002533 | 5c7eb72a-e97b-4b09-aabf-984b8fc9b0ed | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002534 | a7a57a60-4bb4-4295-955d-80307362806e | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002535 | c00bbb7b-7e1e-4b98-9f01-f0c187deb66e | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002536 | 9fae1d3d-4f03-44b4-8af0-6f867fb9a838 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002537 | c0bd06ff-25d5-4232-ac6c-646d5c7a30f6 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002538 | a6b117d3-dd97-4fec-8095-8c70969cffda | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002539 | c2d5ac84-42e3-44ff-831a-07e366207228 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002540 | 881aac50-c5ec-4d3b-880e-5d45778a6ba4 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002541 | bb270697-4253-4626-92da-a3daf117455e | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002542 | 8ae398fe-aa12-461e-b480-6aa1975fd365 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002543 | a0c62f60-bb66-4ba2-9d29-60ded7e52771 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002544 | 7cd7f51b-ae5a-43a0-bb83-dec7c55b1665 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002545 | a94e18ce-e4a2-43e7-b4c4-f086c045997f | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002546 | 79edce01-d09b-4375-bf3e-f7596c38ed13 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002547 | a9468f7c-0233-4c00-ad49-6b3c0d72f9a2 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002548 | 8376508e-1e64-4bf8-a050-2603dce0999d | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002549 | f2a0a66a-d58a-42dc-b1c4-a0981c57e4a1 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002550 | 767d3999-9b67-49b7-846f-b276f2ed11bb | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002551 | f02875d6-5cad-4e73-b6ae-5148e25ee977 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002552 | 6fba6b99-d8ef-499f-82b0-bd7e50630f65 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002553 | f045205c-8ebb-4859-baee-63ab05173ec9 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002554 | 158fc6d4-50af-45fe-b5f8-bc7132288d17 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002555 | d5dc456b-2d99-46ed-82bc-fd0788a1edff | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002556 | 1201c7d1-dad6-456a-976c-22e94956bdf3 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002557 | ffe3cc2a-5f07-4aa9-a1be-7a193e39762c | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002558 | 18e5d7d2-a28e-4db8-89fa-5d50abd3457a | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002559 | 6bac055d-196b-4d53-8f2e-cf18665e5ba6 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002560 | 1cfb9c8c-e949-4acc-b0d6-4a339c712a6d | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002561 | f99159a9-291e-4c1a-9c09-802b0256a515 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002562 | 290650ee-3e72-48ee-9fc6-a0c054289240 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002563 | ea35d793-e5cd-4dc2-a152-599e7c234d9b | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002564 | 21d5df52-4e67-445d-ac9c-725275a44f0e | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002565 | ed826ba9-0ab5-49e7-8845-63cc5f73c967 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002566 | 2c8ed2ac-b841-49a0-811e-814adf031065 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002567 | ef024a55-ce9d-4dd0-bb79-3fa86937f5a4 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002568 | 28b41204-6e2a-48ac-a8cd-775283fda1ba | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002569 | e7ffc440-e131-4120-a669-f5981d147d4c | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002570 | 356c03e0-a104-4da7-8cc6-0bac1ac8e8d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002571 | cf89e813-f253-4bab-8379-7659167d2626 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002572 | 31890bb4-24f5-4e2a-acb1-1a0b516b8fca | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002573 | 3a1eb240-3e97-4ea1-9eda-66939614ab67 | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002574 | 5ff5527d-4d84-4af6-a6f9-28f25451bd7c | Pole | HFTD Tier 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002575 | 3225f821-7503-4c43-a498-7a49db9521ca | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002576 | 45bfebba-bb22-422f-bea3-3ad3a143a596 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002577 | 29c2b704-f16f-4878-9132-7232a1bf211b | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002578 | ef411a7f-9675-4d79-99ba-fc84c5628345 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002579 | 22e4f44b-a759-490c-b839-445240cebcc1 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002580 | 7f6da5e2-be12-42fd-a778-f115bd52f6f3 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002581 | 1d14d146-58de-4807-b155-55bf84040336 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002582 | c72fb72e-9b56-4a1c-b1d1-ca179a14dc4a | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002583 | 1d7c21e1-e5c1-4a80-a34c-e2da39a18e4f | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002584 | c60d00a5-e438-45e0-b550-aaad016bcaeb | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002585 | 1dd0bae7-34c0-40d7-a0b3-535102a03610 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002586 | fd1904d9-72be-4cfb-8870-5c97cc031ef5 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002587 | 3a2d51a7-dfde-4c6f-bf0d-3fa928e81646 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002588 | f481de80-e9f0-4f28-9963-f82822e1d28e | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002589 | 77770603-c699-451e-9cd2-c89bee6fe724 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002590 | f543e580-9cd5-4e30-b2ea-2181ce187df9 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002591 | 93401b71-f7c5-4f02-9b22-8cbc2ce288ab | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002592 | a4f7f48f-db2c-42c9-9cdf-d1df945e981b | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002593 | d10d1ae8-fed7-4b57-95ad-26e705e8bd9d | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002594 | a99ec8cb-7f02-4209-bc41-4ce76aef82ca | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002595 | cf7c8f33-bdf1-4785-b5ef-eaa8042e9a1e | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002596 | c3d61466-d21f-4e92-9d0d-26b77aba4abe | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002597 | de085876-38a6-4ead-9c01-6002befaa8e9 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002598 | bf2218e3-0c44-4382-9254-b0622e8b71ff | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002599 | e6826095-e636-45b1-b778-9b4bb7f769a8 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002600 | 5ca9f5f0-d72d-473e-ac11-a09b29592f8b | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002601 | f9f29c55-d913-48c6-8637-d5c1f49368e6 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002602 | 5ff4555d-16d5-442b-b2cf-2e107f2a3d0a | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002603 | b637846d-8322-420a-8540-53ee8aa180cf | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002604 | 52fbbcf5-e938-464e-8da5-69fa5c9914bc | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002605 | 91886048-4ca0-4d03-a1e9-2dc2a82e1b66 | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002606 | 00d60a2f-06a0-42cc-b9a1-1f60d02c75ce | Pole | HFTD Tier 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002607 | d3ba9d5f-cfce-406b-ac3d-3bb283103ce4 | Pole | HFTD Tier 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002608 | 60747b85-18e5-4fcd-b6d1-a79930b5345e | Pole | HFTD Tier 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002609 | 8d38071c-b43f-43af-87f4-67878ec71e22 | Pole | HFTD Tier 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002610 | c4c48f43-911d-4df8-a64c-9892edfffc89 | Pole | HFTD Tier 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002611 | 226fe9dd-8318-4d44-9bed-6367747b2001 | Pole | HFTD Tier 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002612 | b4544187-8b3f-46aa-bd11-bab0baceabe4 | Pole | HFTD Tier 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002613 | 129abf4c-d429-4522-8b80-7014ad9394b2 | Pole | HFTD Tier 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002614 | 4b7f6609-6852-4b9f-8105-eb749f349cca | Pole | HFTD Tier 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002615 | 22d21458-98a9-46fc-885b-bfc1aadfcbee | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002616 | 658d77a9-52c3-49d5-8fd1-cd4cd55db7a9 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002617 | 19650172-b43b-4681-9819-4b227a0fe108 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002618 | c74f1c9e-e8c1-48de-a8db-a70736d33a9e | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002619 | 2c0d3320-e06e-415f-82bf-950b82787cb3 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002620 | e7e1fc8d-b959-406b-a0f0-8bf09bc89ca6 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002621 | 2faabb7c-eebb-4d7a-984f-167b91a13785 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002622 | f04a10be-6ca2-4c17-97e0-23be546faade | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002623 | 2f83882d-da96-4a9e-b5c6-a1306ac8134c | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002624 | efbb6374-935e-406f-93b4-f98e80901107 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002625 | 2cd4964f-54f9-4a2f-9030-a92d08681453 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002626 | fa290195-eb15-409d-86f3-43149eafba13 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002627 | 2e00d42c-a0ee-4987-968f-6eee4215b4b9 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002628 | 58ee8569-2d99-4124-9bd4-32301f5e328f | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002629 | 38e60757-40cc-4b7b-8ffe-b3134ca026e9 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002630 | 57b80639-bada-4ac9-9f99-646a5209da48 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002631 | 383b00ed-fd9c-431a-9a50-7fd5a9e59e09 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002632 | 5b0306e9-c656-4f5a-b553-5add00bc9e9b | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002633 | 3857a653-55e7-46c1-b39c-29a8c9df7b72 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002634 | 656a3474-e118-402c-b4b4-a1b934d97c14 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002635 | 8629dd4f-bb13-4e13-aa38-72edc96ee2d4 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002636 | 649596bb-7442-4225-baad-cdeee3342fac | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002637 | 86abc42d-2766-419c-bdcd-c171faad51ae | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002638 | 54ca7898-fb64-4326-a881-659240d53e8f | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002639 | 80f1c292-d8ad-44ab-b8aa-3e5c19bb6bf5 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002640 | 45ad98a6-b982-40ce-91ee-b5baef752587 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002641 | 7e69918a-900c-4839-badc-f389b42b74b3 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002642 | 47676695-7d3f-428b-a6ca-23950b1f09b4 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002643 | 7b8df639-6602-432c-8f3c-6ad8449e5a7e | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002644 | bc4bb32c-1e90-43b8-aadc-fe71bdd162a4 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002645 | 3b77507c-1f0b-43b5-8020-024453af8ba2 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002646 | b868d7b2-751f-4da4-8bb6-66dd65202301 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002647 | 3c1fe5cb-0cf2-4624-8b3f-c3d20a5bceea | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002648 | b8e566e1-4e8e-46ae-ae92-94221113717f | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002649 | d330751e-8cdf-4091-aeea-e690002ea98b | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002650 | a512b0a5-726e-4e41-9291-da8874724915 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002651 | d2dbf5ad-abbe-47ab-8703-243a822bd2dc | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002652 | 3efbc659-b90f-4e1f-a4e8-354c5950515e | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002653 | b33ac467-9a25-4186-95fb-718498acf0ba | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002654 | 0ae6c236-98da-4c1f-ad53-e30ae104f337 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002655 | aed0bfb8-4a5b-4b4b-9365-cd52214b81f3 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002656 | b0add2fe-8626-4508-9f61-558fc344dff0 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002657 | 9514ed02-f5f8-4ab3-a42b-792a3664635b | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002658 | 9f492354-d461-4fab-8ce3-2d27b07c4077 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002659 | 2c43fd7f-0a5d-47f9-84f0-42f5cee1653c | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002660 | d4479c95-ddd1-435a-af96-aa47f6900c49 | Pole | HFTD Tier 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002661 | 02154b5c-5733-475e-875d-70f6576fcc8a | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002662 | e233563f-1b50-420b-aefc-810d6cf91930 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002663 | 6db70c71-2f1c-42df-9183-6f6b6a7b5ad4 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002664 | 9d1ac5b8-87b4-406f-a331-4cd47be1fc6d | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002665 | be6d0c99-898b-4327-bea2-ee9854cd983f | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002666 | 93cbebe4-2038-4374-85d8-a9f38f38e7d1 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002667 | c0549cc1-32df-4aef-a0bb-82dfbb4f44f0 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002668 | 910b841d-ca3d-4e94-954a-7e3f4f32f836 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002669 | 4bae78ef-a3d8-46db-bb32-f8f1961b1542 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002670 | 9101ec35-8ae9-49e9-a4c8-d57fe2f99a7d | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002671 | 4e07c79a-398e-4ad5-8164-9cb68a487c5a | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002672 | afc49c8d-c96e-4371-8b01-2c61cdcb337a | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002673 | 649360f8-d65b-41a9-8b14-0a26a83052ce | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002674 | d0656d07-e935-452a-8214-2fc076b0b432 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002675 | 59e77797-a3ac-4efb-96dc-4a1615400290 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002676 | d1b7adea-2503-4dfb-948b-d562f3d4aa82 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002677 | f9ba4a13-894c-46ec-adf1-ec131be8da44 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002678 | 77106a3a-903b-46e9-8791-ba85e33dd47c | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002679 | f4af0ee8-60cb-4f1c-972e-f51c4ea9db87 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002680 | 79acb193-3355-46bb-a41a-75f656adf4be | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002681 | eaf2b7bf-d29b-4912-8ea4-494fe2d13d3f | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002682 | 849dad03-256e-433d-ab1f-793ad7b63aea | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002683 | cf15e6fe-975f-49d7-a55b-8f729d5208f3 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002684 | 87dc14f8-f0dc-4deb-8f7c-7a1ed269e219 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002685 | cfd2919a-372d-45b0-b103-c425fc173eb0 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002686 | 8a99b69e-6246-427e-a390-c9e44aa20e85 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002687 | a1646d65-ab36-4087-96cd-b05087cc6f8d | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2021-08-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002688 | 32802c40-6d99-4836-97d3-4270f76e3dcd | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002689 | 20725891-8460-4ad7-a407-514b072b7795 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002690 | 1370bfcb-0f40-4109-8523-e6b71d9eaf99 | Pole | HFTD Tier 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002691 | 160d63fe-1595-4fe3-8ea4-be158c40c27c | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002692 | 1d16959b-37ce-405f-b3f9-32c129e77915 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002693 | 51f67e93-04e1-4a0d-a2c7-8d664519d290 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002694 | 239ef321-6ebd-424e-b8bd-2461094f5392 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002695 | 5d09086a-2e2f-4ebd-9091-de50065ea0f7 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002696 | 25a748a8-a1d0-41c1-9722-b3f50ac2e647 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002697 | 6118cef0-2623-4972-b1f9-434eec962a7d | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002698 | 23c853f9-00c4-4b86-88e6-55f55127cdf7 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002699 | 2afb1480-243c-4bba-8e57-61d0019984e2 | Pole | Non-HFTD | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002700 | 3576262b-4b01-4543-93a0-522ea5aba78e | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002701 | cef986ba-2381-45dd-887c-dc7ba4435a13 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002702 | 3404e748-dec9-457d-895c-d21ecdd77e54 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002703 | c6c67015-c860-4b6b-8bb9-91902f2bce86 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002704 | 35c243a7-6cba-424c-bea9-943d130d74e2 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002705 | c4f224b7-c0a6-41d3-b214-37ad5049330c | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002706 | 2a3f068c-197a-411b-9db5-a959dcb804e2 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002707 | 59988cdd-c539-4a9e-a9ef-4c5d7aa4cd7e | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002708 | 87dac9fe-851d-4e22-b737-28b58fc487d1 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002709 | 5419ed02-11a9-4ccc-88ca-ce8eb98e509f | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002710 | 84755190-9622-402c-9776-541b9d281016 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002711 | bf438a78-0353-4109-a0a6-8f4a49f4ace2 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002712 | 77897dde-06a4-466f-b792-15fd3254a2ce | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002713 | bc12987d-59d7-49b1-b536-b51bc23cd288 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002714 | 80f63447-0533-4ada-b654-b9631e0347a3 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002715 | 020fd888-a02e-4dff-ac8f-888762d08506 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2021-08-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002716 | 741d6642-5be6-4219-9783-4948204d0833 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002717 | 0488d860-8e13-4301-b664-3755ac68f5e0 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002718 | 97307ef0-0ad2-42b2-bf8c-6571261d36ba | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002719 | 046dd7f6-f250-44ae-a93a-c471a0003ae3 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002720 | d539be7b-0e66-4011-9555-2d4dd5573359 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002721 | 02c0e15c-b416-4dbe-ada3-1e7c60fea209 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002722 | d64855d8-8843-4cfd-b0a1-cc0e45b9d810 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002723 | 0b1116ba-d827-4249-94ac-d4119160e231 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002724 | 8a669dc2-aa45-4129-b35f-92d3a2dca667 | Pole | Non-HFTD | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002725 | 3fa3b635-1bb3-4829-9667-3cc4b4066e8e | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002726 | 84e1196b-0153-4b13-ad7f-e99e0b0852ef | Pole | Non-HFTD | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002727 | 40df8c8d-034a-4fec-98bb-ef97da437b93 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002728 | 74f0ad61-dd7d-4a59-a5ed-51eaa371fefc | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002729 | 43db67da-deff-41c6-aa3c-b1bbeb12a316 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002730 | 6c63fcfd-6d66-4f0f-8097-da502f1d6929 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002731 | d137aa0a-c075-4b91-842e-14ebb0dfe363 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002732 | e11f3af3-6270-40e1-bfc4-d178f510132b | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002733 | f35cedbd-3d77-4094-b5e2-80ea631e78c0 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002734 | ecee9244-d93f-497b-877a-e525f2ae0b8d | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002735 | ecb2de1f-4edb-4d7a-9801-0deab7f37c3a | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002736 | b944276b-e247-456a-a95e-32db3f079b08 | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002737 | 95e3c09a-7baa-4037-a878-f9fd4f94af2a | Pole | HFTD Tier 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002738 | b86717c7-beb6-495e-92aa-2cb90869310c | Pole | Non-HFTD | Distribution | 2020-08-31 | 2025-08-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002739 | 02cf0692-0c5c-404d-9e77-c8c59dcd1e26 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002740 | be42a931-e725-48f5-870e-908d52782b4c | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002741 | bb64e499-75bd-4afb-9122-afbbc0e62239 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002742 | c493cdc8-1f5b-4e88-b75e-42d613be479c | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002743 | ecb93fbf-51c2-4fb4-96f5-d630752a56b2 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002744 | ce4b319a-5f73-48bb-8291-6378792d4f2c | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002745 | 4f81ed6c-143f-43d5-a56e-cf9d22866d8f | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002746 | ce36b1da-8f29-4946-8802-e0958bedf189 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002747 | 67abe691-35fb-4d6c-8251-a4930192d069 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002748 | cf0a15a1-73cc-4921-9e7e-bebccb0c4a6a | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002749 | 99e5ce0d-a2e3-4967-99cf-486898fd6ac9 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002750 | ce06f667-11fc-4299-8e9a-46d1a986fb8c | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002751 | fbaea623-918b-491c-aa89-4f5454ee1360 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002752 | 9cb83f2e-272e-434d-a99a-c2725ef521df | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002753 | 2d4c6ff4-4348-4546-b247-18a591d570e4 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002754 | b144cc85-6181-43d6-a3ba-9b8935c5ded5 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002755 | 300d4d28-de23-460e-ab98-c7a5345ee175 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002756 | eb6920ce-79a4-466f-ae37-87fc5dbb44de | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002757 | 338c0afb-45ac-4e4c-9c9d-632970961463 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002758 | e2ceb37a-cef6-4cad-8c6b-1496e1b1215f | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002759 | 45c9ec24-b788-4594-9024-ee3ca5fa0444 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002760 | dd62f31f-5529-4d25-aaa0-fe3c17fdabd9 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002761 | 40ca0c67-2eb0-4821-bdbb-9dad7fe6c6f9 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002762 | 69de7782-3e45-422b-aa80-0f036d3c6633 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002763 | 4ff2e1e9-3ff3-4dce-b435-7265a02b8a59 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002764 | 71425b1d-dc09-43c6-a239-b2fde62f8e57 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002765 | 0cd2f3fd-3c6c-4520-b5c6-70effe16c1bb | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002766 | 7c1a5ce5-a610-49f6-afa4-05ca3188b95c | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002767 | 241fa420-b339-4a73-a778-7cecbd4cf154 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002768 | 79c89fec-cf61-4fe4-a3fe-e23ccd0222df | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002769 | 0452c33f-6125-4ed5-bec4-ed3b8a65b199 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002770 | 820202a5-1469-4bbd-a65d-4040b42e812b | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002771 | 7e0a3f3e-3101-4967-9843-29656b0658d3 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002772 | 87be9d3b-5bc6-458b-9500-006d9bfab959 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002773 | 9021155c-d406-4db8-9a3e-68dc02c56483 | Pole | Non-HFTD | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002774 | e0997e6c-cca2-497b-b835-90d92aed5f6b | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002775 | fdcaeee7-fdfe-4fde-815e-8382fd31821d | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002776 | 9593c5bb-8859-4d0a-b89d-579a93190b97 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002777 | 81148ac1-dd0f-4a8f-bae2-86d37b95eaa1 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002778 | 28a1450d-3823-4925-b769-f2abc45ac855 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002779 | 2bf0adde-0e08-46de-92c7-a3163bfdf5c7 | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002780 | 1f430726-98d0-43d5-9ba1-978a9a60c34c | Pole | HFTD Tier 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002781 | 1f10ed99-3f21-4bec-a67b-d0361a453726 | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002782 | b25c2317-b76c-4b2e-baf9-08196d89a979 | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002783 | 59e8d255-b4aa-4c17-bc15-739a56cc2794 | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002784 | 6d0a4f46-f766-4226-9cc6-5065b4a1fed6 | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002785 | 19ce6161-2a94-41b7-bb83-fd8e507e286f | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002786 | 6ad850d4-7b6a-42d4-be9b-d2f23f4be085 | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002787 | 4ca9d859-fd9c-4ea1-b0d3-9bb871a98fa4 | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002788 | c31566fe-07e5-4295-a95f-065b8ef2b747 | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002789 | b7c0ceb6-811d-440e-a34f-7c8a0c8015fc | Pole | HFTD Tier 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002790 | cdf75ea9-fd3c-4178-a016-f0b75dfec632 | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002791 | 42af15cf-e466-4908-8db0-71e72dc1590c | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002792 | bee7f411-d34b-4f10-9e31-44f694ebd1f7 | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002793 | 32917b75-fa84-46c6-936f-b257d8ae43c5 | Pole | Non-HFTD | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002794 | c331422e-23c9-4e96-a6db-d4b80e116488 | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002795 | 59bcd9f1-8d47-432f-b030-1c50ccd6a341 | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002796 | c997713d-0e5f-405d-b451-ab03b96270ed | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002797 | 45bc74f6-1240-4d96-ae1a-817faddc4129 | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002798 | e716486c-85a7-48b1-a136-0e43efa7958a | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002799 | 7c1c83b4-0e4c-4f4a-824e-428a7ceeca4a | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002800 | 7c827a66-cdd9-4045-baa7-0c07096e7aa4 | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002801 | 859e89c7-bc68-41dd-8bdd-17ed9bb5e533 | Pole | HFTD Tier 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002802 | 4da17a15-1c32-40b8-8b6b-34c8a83edf07 | Pole | Non-HFTD | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002803 | ea88181f-b8ad-4a90-bde5-69b975ab296b | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2021-09-04 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130002804 | 59d8f02f-daa6-4005-aa82-b5201b40101a | Pole | Non-HFTD | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002805 | de8f1549-549d-4ca4-9f93-b3e94ec87361 | Pole | Non-HFTD | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002806 | 62a2a326-04f4-477f-a4b4-ffae717d4338 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002807 | f0c4d872-f970-4941-9bde-bfaad45c7af0 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002808 | 2fe5873d-68a3-4a36-85bc-6166cd9f3480 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002809 | a616811b-b3e8-4c0c-bbdf-e485917b6187 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002810 | 2b100b8e-37cd-41bc-a6e7-cf7b2c630ca6 | Pole | Non-HFTD | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002811 | 23322787-dee5-4e83-bd8c-ba5a35a7ac0a | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002812 | 1fc88df2-c68c-4200-9db2-f4a7e98e3de3 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002813 | 20f1b388-4757-4b77-b8c8-a89e117761af | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002814 | b17dbbaf-b321-4a53-943b-d6cff3d0037b | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002815 | 6118d409-b573-4433-b074-ebcc40146fca | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002816 | 3c73a0b7-ab99-4927-a417-92474c552f09 | Pole | HFTD Tier 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002817 | 30a71c3c-efbe-4569-b745-24354b8b0729 | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002818 | 609169e2-a165-4a27-a080-e51de78251fe | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002819 | 687591f2-36b9-44a0-b23a-77303cb79d5a | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002820 | 498947c7-4d35-4419-a553-7c1c34293f97 | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002821 | b84f5f6d-b861-4f42-817d-693d2c26e82f | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002822 | 2747e8ad-0167-406d-92b3-b10059bfa622 | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002823 | 406a7372-3a54-4637-9f03-7a745b469b3c | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002824 | c9c479a8-4418-43bb-84d0-e2eeb10e8ae5 | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002825 | 41b49b5f-9621-4809-b095-7288ac22ff6b | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002826 | 9e72ff63-ec9f-4430-ac3a-16f5b9ec1b94 | Pole | HFTD Tier 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002827 | 375ab800-c410-4131-b9c9-8fc3fabafa40 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002828 | dcae8831-43fb-4edc-8eef-f44370eef726 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002829 | 2fbda864-7b21-40d3-8a25-6992afe2fb9c | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002830 | f535d0c9-2c43-4f48-802c-066fbe4676d0 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002831 | 8fc0ecc6-5811-4fc1-8b13-4d4bc637f719 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002832 | 41e953e2-fc58-41c8-83a4-045ef44bab7e | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002833 | d041f2d5-d22d-47e2-be2a-89c5239369f1 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002834 | 2b4a46c4-f79c-41df-8856-36bf667578d5 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002835 | d3ebeb17-7ded-45c1-9864-239f5465c1d6 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002836 | 2c94f8e6-2da7-4ece-8f84-b8bfd465d47b | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002837 | abf0df36-36dd-4d10-a1be-dbe52a03f3d4 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002838 | 55a7ecde-57c4-4e64-91f9-102c42ac961e | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002839 | 806a044a-1e7e-4440-b9cf-3c946f102d01 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002840 | 4d07c03b-e33f-4224-b4cb-43d894302b47 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002841 | 2ea550ad-8ef0-49cb-9761-fdc48d5bfb8e | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002842 | 19a5b9fc-749c-40a4-948e-101072e56771 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002843 | 8102d5dc-0f2b-4c0b-a698-e9ad86f47ad8 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002844 | 42ae9b87-a6c6-43fc-9952-ce84e5559e6d | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002845 | 73490d40-4936-4a87-b5f1-77ab16ee65e2 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002846 | 54c59ffb-9223-4b48-983d-2196acdc90fa | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002847 | 76e896a7-6e8d-4b5d-91b2-b0fe5140136c | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002848 | 66120f86-56c2-4bfd-9430-bc20357231c1 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002849 | fa9f6063-133d-495c-8d5b-dfe8a4f89622 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002850 | 8f042e4a-6974-41d1-a522-8237c4793bac | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002851 | 78f5ca16-6f8b-4ae5-96dd-843cb92aac15 | Pole | HFTD Tier 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002852 | 5a2c25df-c168-43f8-a9dd-bc41d7455e19 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002853 | 73270fdb-d3b1-44f9-ac89-01721fc49d3a | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002854 | 58841f2d-54fe-4296-a20c-cbe15fcd1b56 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002855 | e1c723df-5942-452e-a8e4-5441e4ee90fa | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002856 | 54b5d292-9787-4c8a-bace-241cfa6831b7 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002857 | d9337983-775a-4461-beb0-697ac09c5a05 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002858 | bb4f430d-0792-4719-939e-2f40c5dc0d94 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002859 | dda1f78f-6c90-4366-abb5-ab36e6526399 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002860 | a494f653-fba6-4b1b-bffa-568c25c45f58 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002861 | ca5b430b-720c-45a8-87b8-72a944b0ec2c | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002862 | 3d386e16-9cf7-4545-a597-58fcfca2fcdb | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002863 | cdc01b4d-b15b-4e32-8681-7eb967089f58 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002864 | 879fb521-a0f6-4a66-815b-12940472578f | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002865 | bfc4e19a-ec42-4224-9b83-9793801b6ce0 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002866 | 0b3484ec-82c1-4898-b34b-c221ee045f70 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002867 | 07f6d1d4-a745-4314-bc68-39428f89bd87 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002868 | 2bad7dd0-0984-4602-9ffb-7fbecbb194dd | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002869 | 77196ef7-113b-49a4-a25c-5c97513578df | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002870 | 476fec00-2b69-4167-a662-f4f309809ea9 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002871 | 79818e87-1936-4878-8dae-4019320e079a | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002872 | fbb628c3-0e1a-4128-937d-d315aae2ebd0 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002873 | 3b971442-07c6-49ee-a7a9-a9f1e1349e29 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002874 | fcc9ee67-7cba-471b-ab96-8d89f84a73f8 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002875 | ad86ba97-47ad-40a9-a66b-401cf8a70f89 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002876 | 71e6de20-9815-48c1-ba65-939bb5bc05e2 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002877 | b14978a1-ae9d-4b9a-871c-22de517726e2 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002878 | 3a05872e-ab72-4941-b98f-0ab8e17e087a | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002879 | 9325734d-7db3-47aa-a039-385bd47c9ecc | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002880 | e48c593f-e666-448e-9885-7b5160303671 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002881 | 96ec0dd6-0c31-4ace-8a66-8d06853c2d85 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002882 | f1c8bf7d-aad6-463c-9df5-6e7a7efe2ec7 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002883 | 99f8a735-991d-4534-a5e2-bf46e44e9bdc | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002884 | 7bedcf8c-be74-4f77-a8b9-8050fe29473e | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002885 | 9bced209-5a6a-414b-821e-fc1df9483d55 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002886 | b723812c-70f2-44a0-9c8b-e9c4dc0cd642 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002887 | 385a498a-f6ca-459a-9057-e294cf77139b | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002888 | b6678cd0-091e-4dab-8177-3772efc3cd9a | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002889 | 353bc8c9-147e-41e8-851b-d03064a5c56e | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002890 | 6d30dc64-a57f-4fa5-a18c-87172319c6fb | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002891 | 11ec67f5-9c1e-45a5-9686-2e5d750bf4bd | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002892 | 8735d8b5-3937-4730-94aa-e7f489ce9e84 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002893 | 10b04f77-b488-47e9-b35c-4b311c07eff7 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002894 | 19fba032-bcc1-45cf-b87f-eb4ba2c174e7 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002895 | 1c655b60-d492-40cb-9257-6c92d764b412 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002896 | 3789f0d9-5a8a-4ce8-9e9b-c0218362de42 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002897 | c85d5613-8f6e-4bc6-87e5-a1c7252f5bd6 | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002898 | b50780e8-0311-4a48-b639-02a7f817676c | Pole | HFTD Tier 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002899 | 10c84829-41c9-4047-9d4a-16636a3128b5 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002900 | cb2a11f2-d208-4ee7-8dc6-dafde46aface | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002901 | 28e65c12-9e2e-474a-be83-454ac367bf56 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002902 | 71f40119-bc71-4064-8e99-7f18a6a2484c | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002903 | 24a52811-eb26-48a2-8e7f-238867955863 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002904 | 3b2f696c-1736-4687-b6f2-4192915f631c | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002905 | 19e12a14-1a05-45af-b0e6-954e28c9ea70 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002906 | 1dcb4be3-30cb-4828-9ae5-14b8ce742746 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002907 | 06094732-0d28-41d2-af3a-7302be409143 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002908 | 4010651b-9a16-4090-8425-5a10fab00e12 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002909 | 2dd013d8-8f60-46a8-a298-a040d821d64d | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002910 | 864c79c2-b840-436b-b20d-132d0d4c14b9 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002911 | a8916749-cc5f-479c-8804-e50c7dcc4268 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002912 | 8c52d151-6226-48f9-be80-b4d18df7b4f1 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002913 | 96d21b30-8e4d-4aef-b099-2cf7ddac941c | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002914 | d0cfdcf9-12d6-45d8-9dbb-79f957841f13 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002915 | cf928c1e-e5fb-45d2-adb9-787f81497bb6 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002916 | ef093c28-1799-456b-afde-e8118635aeba | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002917 | 6f71e2c7-ce89-40f6-bd18-e67d501c6dec | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002918 | e52524d3-0a65-42fd-a7c0-f408d6232394 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002919 | 70903d03-db04-46f8-b114-b595047587b8 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002920 | 0c3dbf29-5c48-4190-9f13-246d14cb1e4d | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002921 | 82f158c8-a3a2-47f3-a057-1cf7cc7f5983 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002922 | f881a56e-ac93-4cc4-97a4-3d2cf6f933e7 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002923 | 8bbaea22-21c4-4ad2-b7c1-c4df7f28f134 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002924 | e8df1698-f47e-42c7-9331-be67c8b7ef86 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002925 | bba20c57-5a90-4bc9-85ac-9f1c5d3e7f1e | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002926 | ef2f3830-8bdc-473b-bc6c-5d5e3c0a2257 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002927 | dffcc6e1-3005-4831-86a9-1b5d07ece2c6 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002928 | 5a2f144b-7621-42a0-8ea2-574ab12133cd | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002929 | d7674af9-0fc9-429f-8564-bab04a1bd0ba | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002930 | 3eba58dd-57a9-44cd-b792-ea6d6ec2a51f | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002931 | d6bb383a-d6c5-4757-ac41-cefb820d7c56 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002932 | 407bf218-0e81-4691-abed-136d398a3e35 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002933 | d5fd6047-4915-45f6-b2d5-9636c87fe220 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002934 | 3ddd2f2c-3e80-400d-b3b1-dd632ace2c40 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002935 | e19acc34-e06c-406b-b384-c461968b757f | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002936 | 435fc398-26bf-4571-9a80-f68662556def | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002937 | e30174c1-5673-4617-8c30-481419c386ea | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002938 | 08cc3064-e8d3-4142-a001-61100fa7252e | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002939 | b3787423-b15e-42a0-8144-eed040a1464a | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002940 | b4b7ef74-f0f1-4e35-8f7f-25f368e188b2 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002941 | 445468da-5be3-436a-9ef1-8a8b34522f3e | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002942 | c3f88970-c8ac-4350-9225-a98bb8ba1c5f | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002943 | 69c6a510-4a23-4767-b433-56414a4a8f55 | Pole | HFTD Tier 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002944 | d62b3434-70fe-47da-a47a-1a462d9826a4 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002945 | 66efadb2-d4e5-403d-8927-29a942926aad | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002946 | 94b9512c-28e8-4d4b-85f1-f86a654b30e7 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002947 | 632a2553-610b-48e4-8022-8a1d554914f1 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002948 | d8b2a13f-b851-4dbe-b751-090c379670b5 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002949 | 50a00ead-c7a9-4a04-92ed-ac72fd7b4b30 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002950 | dd7186c9-f289-460e-9a8c-04af99402f0e | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002951 | c211d9c7-f71c-4c80-8ec6-a6c53286dd0d | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002952 | b777cdb4-363f-42a4-828b-28109ffa5bef | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002953 | 7a2f9074-de47-48b2-a9c5-a81414e10b19 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002954 | c20fba24-b1c0-4eee-b816-d239cf852423 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002955 | bbedcc58-d59e-40b4-b5e8-e690f94981ff | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002956 | c9c01a04-41b6-46ba-b733-675fdca5698e | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002957 | bcb3a97f-456f-4489-8141-276490866959 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002958 | 9ca62d32-b106-408b-860a-11bbfaf6a79d | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002959 | 1fc849dd-2451-41a6-abdb-fb1049b05b14 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002960 | 98a5d338-02aa-435a-be64-3b77bcfdf4eb | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002961 | ba9b8ffe-4c61-482d-a9ad-d2f19342f84e | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002962 | 00be9e54-14e0-40b4-963f-783681085ee5 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002963 | 69b36e18-d30e-444c-9569-d89ae132554c | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002964 | dbc0d419-3c41-4821-849e-7c0247f230e6 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002965 | 0bc962f4-7e68-4ead-a677-b7910bf77c62 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002966 | dda6dcdb-915a-44b6-b01f-b4335150818d | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002967 | 0cebb518-40d5-402a-8f70-0778e1139389 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002968 | 88530dd5-6868-4f87-81dc-fd0022eea835 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002969 | 046fcf7f-3e1e-4a86-9129-9ff828622dac | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002970 | 8601578b-c58f-46e3-a0ca-0398c6bd2fa5 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002971 | 05de68df-cb14-47e4-b564-32e1008d89b9 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002972 | 39ffb9a0-9517-488b-bbb5-9261d40114ae | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002973 | 246e587c-ee06-4d07-9bb8-17e62a8b9e48 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002974 | ac2c3a92-5048-4329-8111-746b82aac626 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002975 | 07069fb2-5304-4444-99d6-5b165010b9cd | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002976 | ac70b546-3509-47d4-a30d-da199e16d0eb | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002977 | f8459cd4-a447-461a-9738-f47a8fc3b581 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002978 | ad0dc710-e286-4ca2-b190-7c54279903e9 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002979 | d153fc80-566f-4787-b331-8f300c39f0bc | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002980 | abb8cd0e-9b02-4d20-93ff-7d95cb1af307 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002981 | f51985c8-cb0e-4b2e-9da5-308ffa27e25a | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002982 | 9020629a-ccf4-4a82-a5f7-87fd81f23d2d | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002983 | 994f5a5c-4f3f-4179-8c5c-7bda58b75483 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002984 | 8e2d50e2-fe17-496c-ab82-7e0cfc9925d7 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002985 | ee54049b-aeba-4f2a-9c13-67ecaf4a25bf | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002986 | a87b6f9c-b48b-4f20-8c6a-d5d56bc572f6 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002987 | c0331e2c-fbf5-4cd3-b147-618faa155e33 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002988 | a6bb3f46-0dee-4029-b1e1-915f491d80b3 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002989 | eaabc698-88c3-4daa-9155-d77e053d1d86 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002990 | 9d979115-e9fd-4210-b01f-9dae17b6aef6 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002991 | ead94f8c-f29f-4fb0-840e-10878e1ecd49 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002992 | 17c1b3ed-698c-446e-b6a8-b17b92eaf191 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002993 | c01d86e4-cd0e-473f-ba4b-7ad4812a5047 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002994 | 1ee99fdc-4900-48ac-93c9-1998500ae93d | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002995 | 8b23e39c-cc65-451e-9eea-f2d1baebedba | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002996 | 2fedb42e-f08d-41c7-bff4-b6cc6791b7ec | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002997 | 8ae3071a-7787-452d-8866-325ddd8b4d2b | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002998 | 32320a52-aabf-4be4-be8f-7ca01287a010 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130002999 | 2036f882-4de9-4ad1-ab93-cff7634e5d35 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003000 | 38d52519-20ab-4359-8758-f701609e7a82 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003001 | 53b83bc1-c945-4103-810f-e103e07c8880 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003002 | 136576f3-067c-4c70-bc58-c3ed1d828cee | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003003 | 201df0c3-44ad-4f03-b2a7-6fd703227a4b | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003004 | 17c155f4-c258-40b0-a588-41e830848475 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003005 | 227076e0-3522-4396-a1fc-fd3126607bd9 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003006 | 0dfc1b39-c2b9-49e3-a640-e18a4609bba6 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003007 | 312028b5-da46-43de-b246-beaa87f8a2a2 | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003008 | 0ae4385d-8987-4a51-89d9-220c22a9d2cf | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003009 | c976e090-d0b9-4e22-b331-d72dd6d7e01f | Pole | HFTD Tier 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003010 | 163e8a9e-3a5a-43f6-9d4e-1ccfba73aacd | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003011 | c8f462f4-91d6-45eb-9a2d-153a801bf53b | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003012 | 38946370-0838-4111-be8b-cf241ddf1c33 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003013 | cf10adcf-7179-41eb-985c-19f1af5d42bc | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003014 | 1ca7a044-c332-463d-a98c-6b36b1fc90b6 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003015 | cdf0ecfb-1a7f-414b-9639-22d8cb3167db | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003016 | 257aedf9-3c0e-46f8-beda-b1beddbaacbd | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003017 | e78bc320-9752-4aa7-9564-47813cd6fb87 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003018 | 25f5c736-d551-4930-8e41-51a1cda4fbfa | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003019 | 15cf07a7-56d7-497b-bab4-84660d8b852a | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003020 | 21654e92-310e-4a09-b165-ee32b6bf795d | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003021 | b47a14d1-105d-4c69-8952-a08f3262052a | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003022 | 9f9043e8-b8c5-48e3-bf62-6239c569e427 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003023 | fcd9b46c-3491-4c49-b1c3-aeec9f576b91 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003024 | b0de87ba-e3b0-4f4f-8d06-76a3d8c60f6b | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003025 | fc88c135-f63c-4ca6-94f4-d22989f0e019 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003026 | d08c887b-7e80-4488-979f-3e6014235aa6 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003027 | 0f07545b-e55f-4d04-82fe-3cda2c6ae59b | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003028 | 6f00bbce-6bac-49c7-8616-27d9b0703203 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003029 | 06604983-fa04-4aaf-be86-ef07b43fc7b0 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003030 | 7220c249-f551-4bf2-ab9f-fe4038e72af9 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003031 | 06755211-ab07-441e-9981-3b4edef33865 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003032 | 7553da92-b5a5-4e3a-8e40-acb6726eda82 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003033 | 0712ed3c-753c-4061-b5f8-2836f1c77cef | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003034 | 734c6e77-d2eb-4181-a3f6-35dac2b83043 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003035 | 1691c318-562f-43d3-b54f-4030205c64ff | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003036 | 872a3935-9cd2-44bd-b21c-5d4738959eb4 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003037 | 9254e558-b0bc-4f80-a46a-d487b061c3a0 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003038 | 8b542ee7-b9d3-44f3-ad3b-f5eeda3cc86b | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003039 | 0c319c12-23a2-45d7-be58-283f2dcb12f4 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003040 | e3e35637-ec93-4ea9-a3ce-851c60d10b8c | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003041 | 06b0d8f4-a9d1-49fa-91bc-74efe51457ae | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003042 | d49a18d4-bfd1-4509-9a62-daf135a843ad | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003043 | 6c4a54ba-d370-4451-9756-d9a3f5a7c0f3 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003044 | d3df4e29-eb1b-4e76-8f19-8744e29f940f | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003045 | baf4cd56-dff3-49f1-9400-138a09cb5fb5 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003046 | e9c96776-7433-41eb-a7a3-4f5fab9fef0a | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003047 | be1a67ff-9ee5-424e-9c65-032689bdcca4 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003048 | e8505b70-dcf4-4dd6-922c-2ccaa4bb6d79 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003049 | 4d1cf6c4-cdb6-417d-9dbe-b90a5efeb6d6 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003050 | ff3c09cd-251d-4306-a517-6d9082c544b3 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003051 | 4e939279-f832-489f-948a-41ca884bc7e4 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003052 | f924a1a0-15ac-423a-a941-724e10b92eb0 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003053 | 4b06414f-8076-4c60-a1a2-e8805922d95e | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003054 | fb3e4972-d35d-4610-a425-83779eaf94aa | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003055 | 61f41eca-2114-4dcf-8232-a3559f12b6ae | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003056 | ef23e86c-4acf-463e-a10e-e3f74c580c3d | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003057 | 9a02260b-2a44-40ce-a817-7a4384261c63 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003058 | 9990b478-c4e4-4ecd-849e-ebe907e73454 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003059 | b4beaee6-2627-423f-90de-1e1e9d57a0d7 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003060 | cab342d0-2bef-4463-8368-1aa5d5ccb4df | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003061 | cdfba419-7c3e-49db-8f2d-88f8b2238cd0 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003062 | bb76c009-be7a-4bba-a483-da41b3743b91 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003063 | da72b4fd-0ad9-4747-a5b4-6911d648762b | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003064 | db063571-bea5-4468-bce5-2f3c382a3158 | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003065 | dc297714-4f0f-42c9-9348-412898baadcd | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003066 | d8f1a664-5636-4020-995b-4479eb02dc7c | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003067 | 9155ac75-ca35-4712-b5ab-146830acb411 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003068 | 66e156d8-e695-4d11-816e-f899d950c393 | Pole | Non-HFTD | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003069 | e27a9e6a-264e-4d80-bb44-f0f3e4ec453c | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003070 | b5e91be1-bd32-47e1-841a-32dd2ce308aa | Pole | HFTD Tier 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 | 2022-03-01 | 2027-02-28 |  | Arms are not in need of repair at this time. |  |  |  | Liberty | 2025 | 1
1130003071 | 679c7247-166d-4cda-8f68-754f0b779935 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003072 | 746d3295-42cc-44e6-9475-a5b550153674 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003073 | 666fb3ed-e20d-40f0-8b03-913de4682d4d | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003074 | 8aed9894-cd25-4c07-a7db-76de1b4ae368 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003075 | 4a08e08d-85bb-4562-88c5-937f0c2a8ae0 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003076 | d8d3ef4d-b13a-4c14-bf38-864feed58533 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003077 | ba4c3707-710f-40c8-b5f4-9bdab567945e | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003078 | d722d7ca-d9bb-422a-a8f2-6ae5321c69c3 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003079 | be8b262a-684c-4e47-9bdd-f065634ae952 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003080 | dc21539b-4d1f-4990-8084-407e0b5d592b | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003081 | be90295b-349a-4878-98bf-33a2a2d7ec67 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003082 | df9bfc8b-c32a-4240-b8de-64a94b1edba1 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003083 | 6b5a8c21-5912-495d-a809-0cdd73a5ade3 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003084 | e4fd0d7f-e763-44ab-9e26-9fc35bf3a22b | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003085 | a094e5f0-2dda-46f4-87b9-68b3aea4666e | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003086 | d0e4dcb4-f883-4a7b-b998-7e882a986b74 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003087 | 46a0c114-b7d3-4a0a-a855-772da5c09609 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003088 | cdec7f9b-9445-4227-b217-c1691deef7fb | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003089 | 9f883c68-681e-4422-a6b7-139e5c86449d | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003090 | a81f8630-108e-4a47-ade7-080ef714b268 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003091 | a51abbcd-cb0f-49ec-9cd1-db12da4b3f32 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003092 | a3493de1-a56d-4952-8ae9-b8383a85242d | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003093 | 43e21dca-aab9-4819-81c9-33bbda26f39e | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003094 | fc43f010-3bfd-4a9f-88cf-e50d24db8908 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003095 | 00eaccc4-4087-4125-ba38-91a7ed63a24b | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003096 | 818f8593-eea8-4d65-95e4-707b548ab5e2 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003097 | 78fc88c5-a130-4294-8c06-631a641c9794 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003098 | 83a8c1c4-e015-4089-865e-e4daacbcaf66 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003099 | 3db4a227-beba-4a17-bdd9-e48ca6425e88 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003100 | 7f98a276-aaef-4e4e-8020-a5a6b515e965 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003101 | 3f26fa99-0f48-494c-885e-9a95a886e0c8 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003102 | 7c387807-4864-49b9-9be7-eaf0a5c3dc11 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003103 | 3ed28385-0648-4977-87a6-65a7d7a1fe66 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003104 | 6e743dcd-99a5-4a3c-8223-2ee7bd1c376e | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003105 | 3d9319f3-88c4-422c-901b-4cd2e2dbc9c0 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003106 | 72783e60-b2da-468a-b64f-240f165d90a8 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003107 | 16404d5d-b241-4eac-8015-cc30df8852bf | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003108 | 714d193b-5ad9-44a9-9ec8-1bd95146278f | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003109 | 201a9dc9-63b6-45e9-ae6c-9534f67456b3 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003110 | 3a7a4299-3220-414f-859f-6d963ab6b87c | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003111 | 1c669c99-126c-4efc-862f-91480eea31c5 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003112 | d02ad81d-c36c-4f03-8446-63f38b87a1a0 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003113 | fdb3aa6e-3ea3-44f6-b303-5f01c602ff79 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003114 | d2a9aa10-7714-47f7-8cfc-652b51da1d80 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003115 | f86a644c-9338-40d8-92d2-a1f3b75e6a8f | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003116 | 9f774194-b8d7-4a48-9767-09e3fdfafa1a | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003117 | a574af9f-d02a-4e64-8ea5-08e12ccdde3b | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003118 | 9b827a8d-2e06-4358-9460-25ffbb47fa92 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003119 | 2ec02df7-19f7-410b-bfd0-9af776299377 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003120 | 984de1fa-faed-4291-919b-7e77f6b01246 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003121 | 3268f684-b4c0-4caa-bb35-a6f7a291a021 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003122 | 983f8ae9-03e1-49a3-b856-45d5f93c6135 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003123 | 1f01ee3c-8b7e-4501-9d96-6e8a76ee9633 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003124 | 21c27a95-45c8-4ae3-8cba-8a5ce930180c | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003125 | 1ae76144-8199-475a-a238-9c5c36d35793 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003126 | 236987f1-51e5-4077-aa3f-567e317677f4 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003127 | fe7a4988-1ccb-464e-814c-a7a524d0fb56 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003128 | 239ac3a8-1ac8-483a-ab08-bc48b883da89 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003129 | eadc47fb-a021-4234-a4e4-6b277b3a7e2f | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003130 | 289c49f7-0840-4bc0-a318-af0365dbc828 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003131 | c55a2456-6b93-4050-911b-48f71a4c3e8d | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003132 | 37b626c9-790c-4620-8ff6-503f9536079e | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003133 | e159490b-60f8-42ca-badb-3f026dd704ee | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003134 | 30ea35ba-82a2-4395-b5ca-23767c9f4cff | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003135 | daef9cc9-1a31-4b38-b101-652e946f8b70 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003136 | 2e8b6799-1d7f-4dbc-90c5-e1a2916a9c67 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003137 | d3753484-90c2-40c6-aa44-3ca624190873 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003138 | 2ccd4649-4bd2-4208-ab69-7024a37c3a7e | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003139 | ec50b6a9-9fe4-45f2-a5bc-45b6b71b6477 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003140 | 10054db1-627f-4676-9177-bcb9cd077701 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003141 | c67d3a4d-f21e-4d7b-a899-bc6aad27a9be | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003142 | c55a605a-ed89-47a6-b36d-2c75c05fac98 | Pole | HFTD Tier 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003143 | 14b98f8f-0c48-45db-8853-4a7482454431 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003144 | 3cb5e2a6-a19a-455c-bb52-4f0aecf94ff8 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003145 | 107ba6d0-e1b6-4f10-9919-f37f2e208575 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003146 | df909596-d684-4343-b007-72b96d93e505 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003147 | 10c9ccd2-308e-485c-a558-0008371562a9 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003148 | 69790a6f-42f7-41ea-86dd-965fae409c41 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003149 | 3075c30e-85cc-4db1-8118-945536b7b927 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003150 | 78972a0d-4932-4116-bc8b-092d55069718 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003151 | 27be5e51-b051-440d-af43-b3cb806b36c1 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003152 | 43a896f4-c675-4bf8-9b67-dd69d08d987a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003153 | 1a6ba33c-00cf-49b9-9043-41b91d4bc8e8 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003154 | ce59f6cf-4f6b-403e-8916-8d871077ed7d | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003155 | 8f90750d-0075-43ee-8c62-dccc27d04d6c | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003156 | e561d49f-34b7-4e88-ac3d-bb9024d46f51 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003157 | d138fc4d-6fd1-49d0-8f13-6968a31b9586 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003158 | 8d92b1e6-efd4-4596-a0b8-518b9710e5e0 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003159 | d13f7b66-b894-4757-8c5d-087da3ad415c | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003160 | e506a92a-c8cc-485e-81e8-79a8a9c1cc32 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003161 | 756ee04b-8cc6-402d-a244-88780a075a63 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003162 | 8122da08-bc53-4fd5-a516-05fbf08d7e43 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003163 | 7606eb99-8600-4603-aaac-200e22ef804d | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003164 | 9cb6165e-f9d4-4165-a703-cfd2b5194f41 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003165 | 7eaa1565-1ad5-40dc-ab59-a8217d453bef | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003166 | b5028673-0f01-4209-88bc-77c2e275cb10 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003167 | 802c6196-7321-4988-a5a4-70c294cc4944 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003168 | 664e2e7a-b144-464d-af7c-d1132438b573 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003169 | 89686f07-b95c-4cd6-91fc-00d97765fa55 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2021-09-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003170 | 8ae19aae-0071-4595-81dc-43884931423a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003171 | ec7d63bf-2694-48cb-b862-a7141a854db5 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003172 | f7cbe413-6fd2-43c6-8a6f-d6e1ea7b3266 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003173 | d7dbcda5-3b07-4167-a103-e2395c77a380 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003174 | f7141845-a515-4116-a3de-da48789f83c9 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003175 | b886b911-20b3-4066-92e3-e8cc20675f44 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003176 | f15f43c3-5a0c-4503-a204-6a5612dd845b | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003177 | c1720bef-4566-4d2f-8a1f-91269baad7f3 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003178 | f1b8fcf7-c299-4f9b-84f1-75bf884592bd | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003179 | 9df6dcd8-3dcc-4589-8ab5-7c5e81e01996 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003180 | 43d17037-cffa-4d8b-9374-3b091af9a85e | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003181 | d32c1bfb-84a2-43ff-a577-b81e9940f5c0 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003182 | 067e4ac0-886f-4ac1-af54-32a63eab9b42 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003183 | d1796ca6-f922-452d-890c-5dcf6bca29a6 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003184 | 07fca404-4dc4-44f7-a404-09d8523b587c | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003185 | d4a22035-e959-4264-9207-3c09be3820f9 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003186 | bcb375d3-66d5-4288-9aa7-41776c6ca9e7 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003187 | d8ecff38-59cd-442a-84a1-36f2be89cb4d | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003188 | bdc962b1-fa7f-4ca7-bfe5-8d6774347587 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003189 | d737cfbc-e4cf-40aa-be91-063577e7f4a1 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003190 | 498bdfc7-bad8-46cf-a701-ea01bdf5a587 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003191 | 8eb5ff86-91b6-440c-89ec-7c4dbdb06fcb | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003192 | 477ae48d-10f0-4d68-98ab-8fa0bb030f8a | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003193 | 90624ba7-6762-4402-9406-0b3d8e20251c | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003194 | 65e3b1da-37ee-4ec3-9bd3-4bc859c5a9b5 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003195 | 599ccb56-6f87-46da-9250-b2c7aaa4ba8f | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003196 | 5e644c34-f461-4598-a822-2f8d4f2319b9 | Pole | HFTD Tier 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003197 | ffcf7ca7-62a9-4256-a8b9-f71301012fff | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003198 | 591f3239-7835-4764-8b38-ddc7ed924b35 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003199 | b63d98e9-25ac-4df6-91ba-2a5e0883425f | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003200 | 582ff41a-00ee-4ba6-90a3-f21790ab6d84 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003201 | 7c1075e7-6c0c-43c7-a567-eebe29dc10fd | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003202 | bd6e233c-0f91-4150-9600-9b03016c7374 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003203 | e6e6e4b0-56dc-4017-9280-a0cfa7a65284 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003204 | aac668a0-e890-48b8-a57e-20028e3bc185 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003205 | b7785d70-15a8-4224-961e-d2173cb94f85 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003206 | a1367e0f-1f7a-455b-9696-278ddb5bab36 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003207 | d572c4ee-6734-4c64-9c51-c990f525caf2 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003208 | 3e69c394-2d6a-49f9-bf43-05ee6b6ffd72 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003209 | 6fd0ea63-d3ed-4f83-aad4-f6ae44c01438 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003210 | 00e53c6d-3ff6-452f-bf1c-fd95b05f1d8b | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003211 | afe872f4-e448-4231-ab4d-b3fd5ba0f220 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003212 | 06c91f96-2882-44df-a127-d9d7edb056e3 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003213 | 908b1516-b4d2-4365-8a8c-d8fe544c1598 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003214 | e2719427-d0b9-4433-b28e-d9237ed649ad | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003215 | 911c6faf-0b65-47ec-b1bd-9a34161166c1 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003216 | f79fa4df-f779-49ee-8bc9-0b1948b9a3a9 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003217 | 9128dc83-f3a8-4507-9eff-afd05f5e9abb | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003218 | 6e3025f3-316c-4dd5-9a86-76dd587a1607 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003219 | 92dd6c1f-e942-41c8-ac60-b0b426f174ba | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003220 | 72fd69f9-5bd4-428e-90b4-a7b4b42f0630 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003221 | 970ed103-bd33-4f27-b406-6f87814c3a7f | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003222 | a1e65cd2-52d2-4e57-8400-2591b1046bac | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003223 | 1920283a-ab84-4304-ba1c-b2b7e81a407b | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003224 | ef08833b-4fa6-4df6-bfb0-10e45e6a8bfb | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003225 | 25d3161f-6f1c-453b-be04-853f01ed7245 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003226 | ccfe3f15-bc48-48cb-8bfb-f355f95bd249 | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003227 | 37b978b8-efa6-4d26-95e7-f322863fdacc | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003228 | cc216c78-a960-45ec-b0a8-7f4ae515c58b | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003229 | 2faa00f9-2964-4f78-bdfe-0de414ea9a6a | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003230 | 16f16a53-c628-498c-add5-2cde6af5614f | Pole | HFTD Tier 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003231 | 552207e6-75b8-457e-bd52-b416f5780f45 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003232 | 2a73b142-fce7-459b-b03c-3cc306567b45 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003233 | 408f30e8-6d9e-4f0d-88f6-f11a9f89dbc6 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003234 | 260619ef-6aad-4159-a461-1062dbb9ed12 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003235 | c6a77b7f-e804-4183-8913-475ea4635186 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003236 | 72c8b212-8d5b-4925-b63f-88ab55c0a1bc | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003237 | 4a93adc1-e7f3-4f81-9808-16b9b62a52ca | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003238 | 79d02709-cf05-4575-a30f-190b4f420571 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003239 | f56d600a-0a69-4468-aa43-2511b6ecd3fa | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003240 | 8db86714-7cd0-45a4-8838-b01231ed8491 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003241 | 07f7bef7-e317-4cae-a372-0bb3492bed6a | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003242 | 84826027-e0e4-4e4e-86dd-e09c269dfb50 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003243 | a349cab4-f321-487f-ae80-4e56731d67ab | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003244 | c500eb9a-3614-42cb-a1e6-1f63f4815c4d | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003245 | bfe9da00-69bc-4548-8219-ad57ae7eba4c | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003246 | 4998c980-b7fb-497c-a656-e76fe594a783 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003247 | 518b01b3-f0d1-412c-8fe8-597620965eb0 | Pole | HFTD Tier 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003248 | e5dc5cbb-8b70-4326-826e-a23fb01cba97 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003249 | 51dc9f81-f4da-4c03-a1b4-289c80803f41 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003250 | d76a10eb-13f4-4cfb-9a22-6aaa31a618a3 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003251 | 563682f3-9b98-4d5c-8687-5e85323f1ea3 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003252 | d507778b-7f2b-43ac-a5ba-548a999bb32a | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003253 | 55b091e8-0373-4266-ae34-a990caf18c71 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003254 | dc24ed84-4be8-492f-95c4-c286e84eba22 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003255 | 45eb5350-c97a-4f5a-a3b5-9ad2ab5dcd8b | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003256 | db8dda95-89d8-4d44-9c22-577164cd8c0d | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003257 | 4612ac93-3159-4bbc-aa74-44e409c85742 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003258 | b762f9ee-8b1f-493d-93ba-a5b1a423e7f7 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003259 | 4be75378-5f4a-459e-b458-0f1d1bbc600a | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003260 | e465f5d5-0d4e-45e7-8b49-d11c88f1c759 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003261 | 5a135d5e-5a13-4681-b7d7-0c68a78c303b | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003262 | faa36a05-6d01-427b-9b99-8c640ca26358 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003263 | 5c9472de-c4ea-409b-8b56-c7cefb2b086d | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003264 | 84740b3a-385b-4615-b2fd-0b49f99c79c9 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003265 | 63167f0c-f143-4fb9-a8f2-a780200c68ba | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003266 | 87a69f7b-e368-4bb8-a01b-bb63429d8fff | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003267 | a4c4ca2a-cc13-4985-91b1-0f395446db77 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003268 | 788f5ea1-9623-487a-9665-fd79e78b3c75 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003269 | a29d1750-c86c-418f-a254-44d62cd85908 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003270 | 97c6bb25-ce15-4cff-b3f1-b485ea909282 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003271 | aa2380d3-8eba-403f-b0c1-3f45abe71f18 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | 2021-04-16 | 2026-04-15 |  | Need to install split bolt at top of pole, pole ID installed 04/16/21 |  |  |  | Liberty | 2025 | 1
1130003272 | 963c12c9-7b0f-467d-9c58-cbf6e88b5f04 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003273 | 3fd0bfd6-afa6-41b5-9c84-60dc6a75914d | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003274 | a87a505c-9c20-4cdf-8222-b72d9dcf5755 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003275 | 42a95ff2-89a0-4cd9-9e15-e1938b7eded3 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003276 | a7a0b342-c6ed-4b27-8685-0438b78c4833 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003277 | 0169efcb-2ed4-46a6-938c-9355f405f29a | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003278 | b0d549f3-b255-42b5-a79e-09a0f619f941 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003279 | 02dd2efa-4a82-40e8-b0dc-a9bac672145c | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003280 | b01c07ed-d120-4b35-97ed-2bb63026fc1a | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003281 | eb13cd7a-4931-4ad0-8ff2-8fc8ba005ec0 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003282 | af40d29d-b24f-444d-a48c-12bf5593a315 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003283 | f25dc6da-ad0f-4012-9e9d-617087ec7230 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003284 | 9c0f69e4-5fc0-4a37-88c0-52f7e74af755 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003285 | f3b94888-8879-4bf2-8d5a-f37987967b66 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003286 | ad0a2c1c-4861-4356-97f4-cb11c9d6134a | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003287 | bbcb524b-b380-4a3d-922d-3975149be33f | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003288 | abc60e15-37a6-47f9-8211-e278b3351738 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003289 | d5385b7e-bf12-4cfd-944c-8ccc97c81c38 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003290 | 1a22c63e-20cf-4e46-b500-b518ba555114 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003291 | b3b74663-4b02-4240-9a7e-879cbff5357d | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003292 | 38c95a71-08e4-4b9e-81ec-db4c6fb63593 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003293 | e98f4df7-9ef2-402b-9bb1-ca2eea3e3701 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003294 | 20cb28f7-61d3-4784-a45b-710a7678a36f | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003295 | ce972377-fbf7-4a68-86b4-1ce8cd23b1b1 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003296 | 161a6279-0e70-4b64-84c2-ae4db8cde788 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003297 | eb4eb104-f56c-4363-98a0-528a4b632402 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003298 | 1481e906-fc04-42e5-950f-5c1bdd2515f1 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003299 | f3ede1de-0f44-4b95-8563-c50ffb570473 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003300 | 0f6d8585-c96b-4b2a-8505-2ae85c885aed | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003301 | c62b4dd9-4343-4492-83c1-667c5b157d80 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003302 | 0af720ed-a0ee-422b-8ee4-5b43c9d33bc7 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003303 | 7f1e6e8f-b861-45e8-b507-f2f42b9aeac0 | Pole | HFTD Tier 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003304 | 16e75a48-71d7-446b-be1f-c011067d8713 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003305 | 1b238d06-2938-44e0-a1f9-ae909ee178ff | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003306 | 144964b2-28c4-4443-abdb-1fd432bc0ed2 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003307 | cd3c3e79-6e00-455a-b805-7faa5e05d82e | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003308 | 38081f83-c28e-4b24-ac25-3d45d8cbd2ae | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003309 | c811748c-f3ed-4bca-8035-d2a263064ae5 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003310 | 2c7e8da3-493a-4221-a267-1f7825506d8a | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | 2022-05-27 | 2027-05-26 |  | Pole needs replacement |  |  |  | Liberty | 2025 | 1
1130003311 | d3a05c5c-8937-4030-a809-4a34d80200e4 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003312 | 1d549433-8f37-42e9-9f9d-1ba386aa5086 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003313 | 870336d2-780c-4d45-8f3a-9417175fa2c0 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003314 | 26964d70-51c6-4e86-a41c-f71119ecbe04 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003315 | 75d1fc85-7755-4b72-bb93-b309d8ea3930 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003316 | 282e9eb5-ae62-4c61-81e0-8b54c6631b9e | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003317 | 4e298a92-46c3-49d7-97ce-f85b1c05dc29 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003318 | af3e8268-2e81-48be-8ea7-bb83170a2faf | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003319 | b0e14802-6165-4f88-8981-1bf04ed23404 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003320 | d0552240-ad2d-41aa-99f2-ebc66d5e9463 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003321 | a7fccfc1-f161-452b-a740-090fe2e0d5c5 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003322 | d3609e1b-52f4-4f31-8fbe-b3ffbeb041c8 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003323 | 7f413600-9fea-49c3-b532-925067d40b87 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003324 | 280e46b9-6bb1-4010-9091-ffb217b83c58 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003325 | 381d8814-d3a6-49ac-9848-8e76e63b0524 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003326 | 72407f6f-3629-41ce-a150-e1fccc9ee5cf | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003327 | 3a3ac121-d4d6-4b9a-bc67-e354d823fd1d | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003328 | 71349818-7580-455a-91d0-048fd826e4c0 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003329 | 5eddef51-62f3-4b95-92f4-fd582d3511d4 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003330 | 725f8b5f-df3b-4b22-8c10-0a7eba33af26 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003331 | 131e8968-d1fa-4c1c-b968-a7793e30c812 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003332 | 7f718100-8722-49bc-a879-4a95d7106ba5 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003333 | 5f49e29a-51f0-45cc-9982-fb7d9fd98c68 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003334 | 7b282242-ebcf-4dfa-891a-b3538d922efc | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003335 | 4eda5d1e-d599-4a7a-a3ec-b02133a038d4 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003336 | dce02cab-2f64-464c-8787-ca752d541d8d | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003337 | ec5dc4ac-6a07-41b9-b61e-dad2c5c9e780 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003338 | d4740d9c-b482-466c-b338-3e22518f4a89 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003339 | f22e9fb5-b5d8-443c-ae18-be0d32f6fef7 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003340 | ebd4b750-cf76-43b6-a3eb-4b31c0f8a773 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003341 | f349b4b2-af6f-4d17-b93c-013a76e9ac07 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003342 | e39e9540-d75b-42a3-8022-d79d6285dc98 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003343 | e20d97f5-d335-4f0f-a319-b09e13407e07 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003344 | 93082e1b-e7e9-4ce1-89a3-2a9b1944771c | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003345 | eb8b3260-d6a5-4952-8cca-4c2a71e0f260 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003346 | fb46d411-5cc4-4e79-804f-728d4650d58b | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003347 | 02478bd8-57a8-4d1a-b6d8-c31b522adab2 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003348 | 064f086c-54e6-4007-944b-398f79d3713b | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003349 | 0c0994aa-3444-494a-a211-fca5f27b60a9 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003350 | 0d230900-2629-4e0b-8ef3-951fd826b2d1 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003351 | aaab666b-c2d6-4b26-ad9e-771fcb5536bb | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003352 | c3696ce8-4cc0-44db-a49a-6d1d31802eb4 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003353 | c1555915-83f2-4cd7-a767-425ab9a0e932 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003354 | 8c37726f-b365-498a-9805-ea90dee7df35 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003355 | bdae4cf3-59c7-4b0d-b646-d87e3150b3b8 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003356 | 67a26434-ecb7-41db-a708-04f4a2e0154f | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003357 | 5f641f14-f3dc-4074-8cfc-f0a209295355 | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003358 | 53f96c07-8016-463d-b808-94c49787328b | Pole | HFTD Tier 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003359 | e15d998b-37fe-4e12-9cd7-70b3452e2117 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003360 | 545fd7fd-e788-4d67-8c3c-2ef4dce14e1f | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003361 | e09a7e9d-ac55-4c4e-a5bd-0e14245c4336 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003362 | 46101885-50f2-45f8-b1e7-a692a1a9b0f8 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003363 | e04b4164-2aba-44a5-ae76-1a7a99b0ca8e | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003364 | 693a1f56-5104-42de-a179-77cfc44456fd | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003365 | d8a60def-06c9-4b60-8bc7-28f66a835e5d | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003366 | 64760a9a-780e-4e14-a944-fc8fb47f47b7 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003367 | de17cbb0-da00-46f3-9f93-90d2d5c86ed8 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003368 | 54c8cf7f-92b9-4e44-b7e8-f70dd7ccce8b | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003369 | fc9763da-5feb-4619-8e0a-5bbef2f0a77c | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003370 | c41c3d44-552f-4c17-970e-39011f68caba | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003371 | 82174148-0a5f-4b46-9191-5bb750438556 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | 2022-04-15 | 2027-04-14 |  | Pole needs replacement, rotten pole top |  |  |  | Liberty | 2025 | 1
1130003372 | aa8edd9c-7ee6-4212-9687-9bd38fabceea | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003373 | 71e617a2-e939-4499-85f5-9e7210963caf | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003374 | a24eb6f6-4d2e-4703-9556-06a97fa67214 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003375 | d17f322d-79ca-484e-92d4-de702ba0fdc6 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003376 | 73a70c41-d838-428c-b6b9-538bbf7b931c | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003377 | ab03f6ad-35b0-4485-8bf0-efd1aca3b486 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003378 | 1cefd6ff-8a39-4ba8-8f0d-813c43084c99 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003379 | 22b8e8d0-a4de-462f-a08f-6e54f5c46c1f | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003380 | c2c9d79b-7d35-4742-939b-0373d22e0fc9 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003381 | 1ea289ed-b6a2-4f3e-88f4-b140ea1499fe | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003382 | 0e740a7b-7d29-43cf-a0cc-eaa21602b720 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003383 | 2c99cbf7-7d26-411c-8af6-23b9e1158ebd | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003384 | 15e24b26-d177-4193-94ee-ad0e83155867 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003385 | 387cc8e2-2d3d-49f9-8841-99d9abb071d9 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003386 | 5a114bab-ad6e-40c0-a4ea-80e597da421e | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003387 | 3453d0d2-a655-49fb-9ad8-1810b75432ea | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003388 | b932e7be-4127-4738-b0a8-d3d1f11b1af2 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003389 | 1117d1f1-fe70-409c-83e0-ec926de681d3 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003390 | 4ba63b2f-5b79-4c38-8a14-fc6435dce7bd | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003391 | 14532269-d714-4010-bbcd-652cd9ae26d6 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003392 | b9f92c26-c72f-4180-ad0a-89742a7969e8 | Pole | HFTD Tier 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003393 | 2bd3bd95-1be1-4b54-a30b-5d48625870a4 | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003394 | 09e2028b-dd39-45e8-bb14-beeb43dba495 | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003395 | 967b71e5-a348-4d23-b76c-7ff17325523b | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003396 | c1a0303f-de68-4cca-b4fe-a1950f6f6cb8 | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003397 | 6d8a5646-6a38-4ee9-b4d8-ffce1f8eeabf | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003398 | 62b08ee9-a921-4a59-b178-59b0f9970b6f | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003399 | 8baf0207-8837-4fb0-8337-ef289fd5eba4 | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003400 | d2e96ea3-ab61-40ac-acdd-a06e0b5a4be5 | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003401 | c00852cf-094a-4399-8968-2ff75599306a | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003402 | c34be656-3015-4e8a-b974-b59edbd8ce1e | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003403 | ab061379-8e68-42ff-89e2-09a998aab300 | Pole | HFTD Tier 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003404 | 6e91be45-74f8-4cee-a80d-b729442d818f | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003405 | d9b8e866-edc7-4fcf-8651-68ded02b80f2 | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003406 | 0372d406-43ea-4d8b-916e-baa6b619a8d9 | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003407 | 83c76b50-c5e2-4c44-bc14-26eae6d45f25 | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003408 | 0b1fc06e-bb35-4fa0-94a6-407136e6821d | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003409 | 6d15505f-1c03-4442-87c5-e139ca184132 | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003410 | 16cb6f18-110e-47bf-bb21-2b49c863a980 | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003411 | 315893bc-8bf0-4169-9044-290fd14510ce | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003412 | f4622cbb-471d-4d00-9b02-87afe135a3e3 | Pole | Non-HFTD | Distribution | 2020-09-22 | 2025-09-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003413 | 75ac842b-131f-41aa-ac05-362e5fcb22e6 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003414 | f1dfba25-bb98-4aaa-bafa-22ab77ddf652 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003415 | 7b879260-8240-42ff-a819-d8237f735781 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003416 | 2a6febca-9650-4a16-b64c-981622ad12b3 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003417 | 90f9aff7-b2ef-404b-9b07-99a10d537107 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003418 | 26985cbf-f6df-47d7-bd12-5a9ced24f730 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003419 | 8eac32a1-3e4f-448a-8c52-9391a0b96aa7 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003420 | 286b3b1e-002b-4299-9b00-12b89fae14ed | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003421 | 69a6b781-5323-4678-8dce-296e4b8990a7 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003422 | 48c688de-4ac3-44e0-8eae-2028eaed4c5f | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003423 | 6a208164-8b29-4834-ba67-66f354dc6b2f | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003424 | 50ecd8b8-a11e-46d1-969c-127156a96abe | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003425 | 9cd04e7c-24b0-4d52-b0da-4de823c37a05 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003426 | 05dad096-127c-4b2d-b6eb-d4d799332779 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003427 | d466c7a7-3f54-423c-82f3-e7e454879774 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003428 | 40540f1a-ba90-415b-b62d-db6f03f4bcce | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003429 | d3e2c850-037d-4970-8e4e-2b76531ce32c | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003430 | 6008c623-14f8-411f-baba-30f99e57e83f | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003431 | fcca4c0c-971f-4d03-a6af-d299317a3ba2 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003432 | 9bde3b8e-b7a3-4337-82fe-645cfb8fdd7d | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003433 | c9b77d53-1992-4902-b026-1fa5f36365c1 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003434 | cac0e953-93eb-4e2b-b842-b7beb4e7fe30 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003435 | 899b4e46-63ff-4e11-8240-3528774fa842 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003436 | 725fcadf-d587-4187-8419-613508848c3e | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003437 | b336bae1-4de4-42f8-8342-a75ac26107bd | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003438 | 310c89e6-3d96-4994-9742-19fd1f80d49d | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003439 | 1dae268c-2c82-4f9d-b775-e99d9d9981df | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003440 | 183f7684-fa6d-4cee-bbfe-0815333cf09f | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003441 | 19e3ca7b-42df-445f-ad31-1cd727a30780 | Pole | Non-HFTD | Distribution | 2020-09-23 | 2025-09-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003442 | 45718d8b-01e1-4314-8080-fe3183110c39 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003443 | 1d4d29e3-ca10-4501-8219-0ce24e712dae | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003444 | 4b87c4eb-d3d3-4a08-a3f3-001395047364 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003445 | 2959c08b-2d61-4dd4-b84a-c430ced94c0e | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003446 | b415ca9a-f0eb-4100-b34e-163e1f51c9c9 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003447 | b2569ea7-8267-40f5-bca5-841c9c6ddb77 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003448 | 09d68a3f-e4ac-4b24-b4c6-b224611c70f8 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003449 | ab23d578-c5c6-4120-bb19-f10d6db7071a | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003450 | 0113187d-969a-487c-8333-f82ec1ab6ae9 | Pole | HFTD Tier 2 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003451 | a68f1ce3-f612-4e9b-adca-504d667a1a3d | Pole | HFTD Tier 2 | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003452 | 11b6d47c-3ee6-4cda-8a23-64c1336cacf3 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003453 | 963ea595-4ef4-4972-8113-5d0fe3facd00 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003454 | 0904baa1-e4c8-4efd-bab8-68769a47e986 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003455 | 8ed4feb7-2f41-40d8-9025-568fb267ac03 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003456 | 1d280027-04f6-47e4-80ac-48afe986e84f | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003457 | 704185da-3454-4160-989e-9fd85c65cac9 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003458 | 1832dc12-5ef5-49b7-a70f-a4e2725c6458 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003459 | 71ee2e78-4e14-4a2c-9dfb-96c1442394f5 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003460 | 494375ba-3253-4c92-b4ce-4f13bfa61d7a | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003461 | 6f2509b5-adf1-4d7d-b0c2-135b63ff7362 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003462 | 26c29f7a-590f-44ca-8869-c2c4b7b333e5 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003463 | cb5a1e7f-bd7f-4f71-a2bd-c0f2d2b84c54 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003464 | 4470a632-25d9-4396-a577-3a6886bf6ff0 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003465 | b957c8dc-03aa-4a21-9c89-65b3c3948462 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003466 | 408da581-b792-48ab-a4f3-51d0de8a106b | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003467 | 97b4e740-f17f-48db-ba20-487b5984f0a6 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003468 | f56bacf5-2d6b-44c5-a39a-7da8d192985e | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003469 | ada8989f-4023-4937-bc58-09c6f4260e01 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003470 | fbea8a5c-92f2-4a5d-a3d7-97eaaa819d7b | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003471 | a67a9c0a-fb0b-4c9f-ba60-057dfbe2e558 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003472 | a7317bc6-9766-4721-9b7f-28780f5efcb7 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003473 | f86916e6-3703-48d9-93fe-f3aa0b357368 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003474 | edc52a12-a097-4c4f-8b40-d08bbf974a6b | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003475 | f03bc64f-e118-4f33-9bc8-1d5c5ae7eb65 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003476 | dc170a4d-fb8b-42fd-9283-5f9b4fe35c83 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003477 | d84483d6-f80e-41b4-be8b-d718c0956194 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003478 | d6e906d6-5694-4e6c-9401-5ff6bd6bda82 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003479 | 863ee853-cd25-431c-8853-a1cd779a38d8 | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003480 | 7b2ef357-f3a4-483f-8008-1cd84f5b3a0a | Pole | Non-HFTD | Distribution | 2020-09-24 | 2025-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003481 | f8e5a2e5-27dc-41eb-81e0-ed47b9664c2b | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003482 | da2ad61b-7116-4fe9-bf8d-16631e499f5d | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003483 | f312b6d3-ca7a-49d4-bc2d-b0972f9bd4a5 | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003484 | ffa34a39-ef1f-4524-a636-595b49248c0f | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003485 | 97c109dc-80ed-4efc-ae8f-a930752a2d2c | Pole | HFTD Tier 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003486 | 8bbaf5b8-eed4-473c-a4c2-9c4a38c62059 | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003487 | ec92a2d0-7117-4ea8-88c3-58125ed00aee | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003488 | 855e5ef6-5b9f-4cbc-a685-611445b321bb | Pole | HFTD Tier 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003489 | e8198807-4624-4b13-b2c9-18813a90ea6f | Pole | HFTD Tier 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003490 | 7ee6f158-f093-45e7-897c-28564e0592ce | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003491 | bb10f092-94a3-4482-84bc-724b83061830 | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003492 | adf493ae-9310-4bee-8bc3-6c1ad88258ba | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003493 | 453ac828-a001-4bc5-992b-d2e535489cfd | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003494 | b2d8ee65-83c9-41f0-998a-316d649842bf | Pole | HFTD Tier 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003495 | 5e6bbac8-4251-4cf8-878f-4938327be4b0 | Pole | HFTD Tier 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003496 | 3048addc-d28a-48b6-991a-5eadd5fd03b7 | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003497 | 583a377f-3d93-472c-84c0-1727816b6837 | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003498 | 234b87d0-7609-4032-856c-432078f2e060 | Pole | HFTD Tier 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003499 | 63e3eaf1-827b-4499-853f-a9ec0b84e3c8 | Pole | Non-HFTD | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003500 | 12b3c0a0-1434-4a0d-9f64-f79b23cad13b | Pole | HFTD Tier 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003501 | 63b2eaf6-1c5f-4c86-9fb1-9a2007e4565d | Pole | HFTD Tier 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003502 | a78d19da-acfd-4a33-b7c6-dc81e657c7c4 | Pole | HFTD Tier 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003503 | 0c05e7be-3d32-4e62-bfb2-a81a1d2c3991 | Pole | Non-HFTD | Distribution | 2020-10-17 | 2025-10-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003504 | e36a2c59-9285-4e5b-9b41-916363ade87f | Pole | Non-HFTD | Distribution | 2020-10-17 | 2025-10-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003505 | 2db263e1-28d3-4ecb-8bd7-780d6408c6d2 | Pole | HFTD Tier 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003506 | ab75932b-2c78-43d1-902b-3cbf6c81e4a7 | Pole | Non-HFTD | Distribution | 2020-10-24 | 2025-10-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003507 | b75ad0ca-e0a0-469f-b3d5-f729f419cee1 | Pole | Non-HFTD | Distribution | 2020-10-24 | 2025-10-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003508 | f4685233-5388-4328-8e88-53d5e2f87c01 | Pole | Non-HFTD | Distribution | 2020-10-24 | 2025-10-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003509 | 7d8c80a0-cf74-4ab2-8108-1fbd84f60766 | Pole | Non-HFTD | Distribution | 2020-10-24 | 2025-10-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003510 | c66cebb7-58b5-460b-86ad-1da8d1f743c7 | Pole | Non-HFTD | Distribution | 2020-10-24 | 2025-10-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003511 | 5c28d58c-64ff-457b-a3af-be2a874f5acc | Pole | HFTD Tier 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003512 | 0f469cfe-371a-4e0f-b808-0eaae1d8f827 | Pole | HFTD Tier 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003513 | 576da134-1eab-4915-905d-2ee96edcd332 | Pole | HFTD Tier 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003514 | 3b8c4552-f17b-417f-8b5e-b5134f299bd7 | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003515 | 259f747d-cab9-450d-a73c-bc97decc887f | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2021-10-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003516 | 7451306b-464f-451e-a308-b8a879e2f521 | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003517 | 0fd03e2b-6cfc-4c28-82b7-04dafb7755fb | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003518 | 31efd5c0-35aa-432b-ba18-725735bb42af | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003519 | 35da62bb-89f0-4555-8c23-d6e82a91cd79 | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003520 | 68b79d80-623b-415a-bb8f-e39003edfc9e | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003521 | 045821c8-1666-49a5-a4bf-e757974e75ae | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003522 | 97da06a5-91c6-4200-99a3-80429c15eb49 | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003523 | 2d05026f-d6f7-424e-be09-0a53a38b5fbe | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003524 | 95ddb1f1-d32d-4242-8aa4-4fe7898c177e | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003525 | 6328891d-e2d5-47e8-9fce-5ad49d6939a9 | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003526 | 4a22d034-af5a-484a-80d0-d56cab2fc52a | Pole | HFTD Tier 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003527 | 4cbd9b67-e042-4eb6-acad-60eebb0ff06d | Pole | Non-HFTD | Distribution | 2020-11-02 | 2025-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003528 | 2ac66b2f-e929-4ae6-a6ae-2fcdb3a43704 | Pole | Non-HFTD | Distribution | 2020-11-02 | 2025-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003529 | fa93d64e-e449-40b9-a04c-47c9e3a5d44a | Pole | Non-HFTD | Distribution | 2020-11-02 | 2025-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003530 | 72f060b6-aee7-4276-97e9-17a602834e7d | Pole | HFTD Tier 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003531 | fa3a6a3f-da62-49f4-8cb0-b8cffda0ee3e | Pole | Non-HFTD | Distribution | 2020-11-02 | 2021-11-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003532 | 7f2ff55a-d4b4-467c-8390-8cde4f3d9ad9 | Pole | Non-HFTD | Distribution | 2020-11-02 | 2025-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003533 | b58728be-315c-4702-b333-4650a1252bd1 | Pole | HFTD Tier 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003534 | fc508bcb-835e-47fb-98fd-b217a0253225 | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003535 | 9e1c0331-0913-481a-b7f0-c3e55090b069 | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003536 | 5aa1f991-42e3-49f9-a448-314cacfe0558 | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003537 | 857011e7-17e7-4989-b5f7-d8855b094072 | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003538 | 8a7c6375-a2f8-47f1-b34e-fbf98195de7d | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003539 | 73c7aa1d-f3d3-4858-b5a4-7a30e63398cf | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003540 | 30188ccc-6c02-42a6-9593-d4bfab541819 | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003541 | 242938d9-ea14-48f9-a871-4b0fe2c56ce1 | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003542 | 18b83043-c444-4081-92e3-17f2e0fcc1ce | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003543 | 13e66b18-4646-4c68-ba09-2ecfbeea5295 | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003544 | 16c4fbfc-1b2d-4e48-9411-33aa38fd24fe | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003545 | fd7a2ddb-6dbe-478a-bfbe-09e4977c6baa | Pole | HFTD Tier 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003546 | 6cdb0dd6-58bb-4a1b-879e-c8c92d1f03b9 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003547 | 52a264de-d18c-4886-b22e-9e9bdbb46bf3 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003548 | 3fa3edb9-0223-4c2f-bf5c-93a4d1912192 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003549 | a2870148-6a38-491c-a2b3-c69849e44dfd | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003550 | 4006a461-8e7b-436a-9f94-3b80ffb7368d | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003551 | 10a46bdc-ff45-4cfb-b382-d32b53018fa3 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003552 | c67c4188-1292-440e-bd6a-91d3a40eeeb1 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003553 | 36c24442-95a7-46d7-b483-e43348955130 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003554 | 74da15fb-1dd5-4e5a-b57b-6230b4e7212b | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003555 | 89706162-b9c4-4b79-b1b8-3a5769d6ca25 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003556 | 8203fb0f-5e11-48ba-959b-050786096a80 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003557 | d2a06795-a4b5-4e0e-99e1-f6ba8276f609 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003558 | af45b8e6-2d8b-420a-ac23-d86959b0f453 | Pole | HFTD Tier 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003559 | c8213d31-66e3-4e5e-9621-c7d7695d96e2 | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003560 | a6f42990-a933-4e30-93da-5bbe8b784519 | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003561 | ce355eb1-8741-4b1e-aa45-4559704fbef4 | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003562 | a757e3f2-eeab-4dd3-b4d1-975da11a09a9 | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003563 | cd5019ab-cb16-4734-bbdd-2b9627301993 | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003564 | 6f2768e7-417e-436d-a182-1bede09d23b1 | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003565 | f05649f1-0061-4aa5-a97f-37b282cfe320 | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003566 | 51ed5513-539c-43e4-978d-a60c01ada391 | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003567 | 05abd4a0-3ad4-4c26-9ab6-96c44e02f66d | Pole | HFTD Tier 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003568 | d311405d-07ff-4d02-a01a-9aeafdd5e2ee | Pole | HFTD Tier 2 | Distribution | 2020-12-16 | 2025-12-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003569 | 059cd3f8-3f05-4f08-8ac0-2007b0349c85 | Pole | HFTD Tier 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003570 | 1dfba368-0f8b-4bc7-9ea6-13bef4ed3455 | Pole | HFTD Tier 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003571 | 42beeeb4-6d9f-45a3-8787-c8088dbace9d | Pole | HFTD Tier 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003572 | dcd9d11c-fca7-4ebc-b570-4d34ef118141 | Pole | HFTD Tier 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003573 | 3d7daa0b-97c7-4848-b2f3-7c1161854d38 | Pole | HFTD Tier 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003574 | e01786a2-1cbf-4fe9-a8a6-882b6f59dba2 | Pole | HFTD Tier 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003575 | 6bbfbf2e-0990-432c-9763-3453ed37c7ed | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003576 | 330852cd-9aae-48df-943e-96a15c57a544 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003577 | 31e90cb5-ce05-431d-92da-dce023a6746f | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003578 | 1132b68c-088b-41ba-a207-4b380e802cbd | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003579 | a21b8b30-d55d-471e-9127-7b6faed0a8f8 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003580 | d01164f6-447f-4225-b969-e271db983325 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003581 | 638d596e-8576-4ba0-876d-6c5e126ca05b | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003582 | d0de9407-1752-4628-a809-8de834351d41 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003583 | 9deeeaf6-b96b-42bb-ad8d-0556629dcd01 | Pole | HFTD Tier 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003584 | be3a6610-8ad3-4ae2-9c39-2372d418b8eb | Pole | HFTD Tier 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003585 | a73fee10-0e9d-47ba-937a-3f9687900e87 | Pole | HFTD Tier 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003586 | 8cf29a3a-1bcb-45d2-80e1-b792ad8fc960 | Pole | HFTD Tier 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003587 | 21cf93c0-8456-4c78-8f2f-da402b654f02 | Pole | HFTD Tier 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003588 | e7620f4c-5dde-4833-9dc3-0f86ba11b22d | Pole | HFTD Tier 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003589 | 3a34d26c-1b83-488e-b0db-cf3fcdcec3bf | Pole | HFTD Tier 2 | Distribution | 2021-04-28 | 2026-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003590 | 7809daac-a066-4b4c-80a6-50fef4685c4f | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003591 | 3ffb3f8e-f0c3-4551-907e-66e478986f1a | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003592 | af57562b-db22-48aa-9b36-d89583ac5f7e | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003593 | 2a07577f-b3f4-4ce8-ae72-5d1ad47185d9 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003594 | bec5e9e1-c8c5-46a8-96b7-ca73a130722b | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003595 | 22f64a95-b562-44aa-9537-65f936ce9654 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003596 | e30160df-4c83-49c6-9980-367734f7c1fe | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003597 | 18df15b7-dbcb-4eca-84d1-2be331080052 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003598 | e7bafe57-13cd-45e5-aba3-70bc50025290 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003599 | f5292a05-5d6f-4fd4-b118-08a7fc08a5ac | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003600 | fb58cdeb-97b8-478c-9abd-e449ac77695a | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003601 | 0c88dec1-27d0-44a2-9cac-edc4127bf2d1 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003602 | 1e9d1d0a-bb27-469e-b595-5ff300ff273a | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003603 | 35ce2f0d-a464-4c34-b1e8-086b90711db3 | Pole | HFTD Tier 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003604 | bf71822f-1fe7-4f1c-beb4-3cd0f71b0a31 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003605 | a829abaf-bbb8-4fe5-9c0e-f80fe4af51b6 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003606 | ba3c37c4-5184-4bab-8106-de6da6799464 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003607 | bb7d72a0-99f9-4841-b25c-90e8fd0e33f2 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003608 | 18b08b8c-1201-4f08-a90c-d91cab8251f1 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003609 | b2b532f3-0553-447e-a66d-3b730849b277 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003610 | 0061582a-773f-43b5-8863-245bc0d08fa2 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003611 | a91e7fd3-36a4-4083-857a-ad2a76aad36f | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003612 | 46c6109a-3376-435a-85fb-202def1b4017 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003613 | 94a68f8e-9954-4fea-a59d-acb8a0b712fb | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003614 | 5129bbb2-6cf7-4d34-aa5a-3b3795c0b3ce | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003615 | 8e6b4499-3622-4999-a502-77eb608cd385 | Pole | HFTD Tier 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003616 | 0f52bc9a-dedb-480d-9a2f-8be6e92238d4 | Pole | HFTD Tier 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003617 | 7ebd0501-4c69-46c3-a9b3-fc7c3005632f | Pole | HFTD Tier 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003618 | fb47b541-12d0-41ad-a428-5f7fc375958b | Pole | HFTD Tier 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003619 | 296bef50-d0da-4c12-b265-17e221248a61 | Pole | HFTD Tier 2 | Distribution | 2021-05-05 | 2026-05-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003620 | 37056221-fe6c-4de8-b617-a94feca8a471 | Pole | HFTD Tier 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003621 | c2c4fba6-8be8-4156-9ceb-38c84210ac45 | Pole | HFTD Tier 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003622 | b36ffc38-4d5e-4250-a769-c9e388fec444 | Pole | HFTD Tier 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003623 | 18a40d05-90fd-445f-819c-db748d984211 | Pole | HFTD Tier 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003624 | 5ab2c315-aff3-4fc1-af2b-b6ebd77be984 | Pole | HFTD Tier 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003625 | 7c56fffb-b9fe-4224-9fbf-f1c6a93c2bb8 | Pole | HFTD Tier 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003626 | d92a770c-1c52-415f-b5f0-faca8fc6011f | Pole | HFTD Tier 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003627 | cc953013-ddf2-4b47-b420-359eb93f1ffc | Pole | HFTD Tier 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003628 | 8c3a30b8-c7e5-4e1f-b099-b21d51181055 | Pole | HFTD Tier 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003629 | 8fdc8965-49d7-4753-bc91-051ed7b7cd59 | Pole | HFTD Tier 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003630 | 126788a7-aa86-4ec6-95a8-5380489b1b7c | Pole | HFTD Tier 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003631 | 63975c28-5e39-4be5-9e5a-366944612499 | Pole | HFTD Tier 2 | Distribution | 2021-06-14 | 2026-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003632 | d779e54a-a832-447f-b43e-c84d7b64f4aa | Pole | HFTD Tier 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003633 | ba196846-799d-4408-ad22-d2bbc1452d0a | Pole | HFTD Tier 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003634 | 839e7ee8-7c40-4c80-9f50-87d0160630ea | Pole | HFTD Tier 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003635 | 5b7c59f5-2241-4d5a-a61f-44619dc28cea | Pole | HFTD Tier 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003636 | 14ee7c33-3957-46b1-8042-10df52c595c2 | Pole | HFTD Tier 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003637 | 0e4e6094-7cc0-4cd4-8c93-c623e394cfd3 | Pole | HFTD Tier 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003638 | 1c3d0e1c-ba90-461d-b685-dce35d0cef47 | Pole | HFTD Tier 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003639 | af972b85-ef7e-4fab-b62d-63e311958fa5 | Pole | HFTD Tier 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003640 | fcf297d2-10a7-4bb0-977e-a28aa527aa50 | Pole | HFTD Tier 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003641 | 4a4474af-1995-41b4-9d01-f9405889bb78 | Pole | HFTD Tier 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003642 | 14219f68-abc9-47d6-9c31-f787b6450796 | Pole | HFTD Tier 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003643 | 34e3cfc8-e4d8-4bb8-8f9b-d73583d99c8d | Pole | HFTD Tier 2 | Distribution | 2021-07-09 | 2026-07-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003644 | c124d0af-8ed4-47b6-a135-dcf5e92c1360 | Pole | HFTD Tier 2 | Distribution | 2021-07-09 | 2026-07-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003645 | 75ea10ca-c63c-4e90-8a6b-97d7fb348fab | Vault/Box | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003646 | 282a7f03-51f0-4639-b6a4-fb5f21735e46 | Vault/Box | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003647 | a09553e3-7e4a-480e-837a-0161a44610c7 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003648 | 34d38710-c291-423f-bc5a-053b2f4338a4 | Vault/Box | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003649 | e3a8ee9e-1e0f-4bfe-b2e3-4587330ca0d2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003650 | 3607a411-9506-4dd9-bde5-6d417a28f4a0 | Vault/Box | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003651 | dfbf6508-3bc0-42d2-8ae7-1bcdab2f7041 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003652 | e9026147-f9d7-44a6-910e-71e0489624aa | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003653 | 208033da-57b1-4f97-8a6d-4f91d396e108 | Vault/Box | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003654 | 042e8926-2c53-44bd-b440-5088822e1078 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003655 | 813bcc20-84da-4843-b1fc-2a810be994ec | Vault/Box | HFTD Tier 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003656 | 26ee2dea-6b75-4afe-8159-a40882cf5d0b | Vault/Box | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003657 | ec44ca4f-a2ad-4dd4-83b0-03f3766314aa | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003658 | c03ddda7-3e08-4c55-b886-6f6d4d377ee5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003659 | 6f28aa38-21b4-4d1c-8e29-1f09c4daf840 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003660 | 64125ed6-bf79-4bd5-b24b-cfae85f50f67 | Vault/Box | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003661 | 59dcf11c-5afa-4e0f-b760-1f9f74e4ee29 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003662 | 168468f5-1a76-4702-a32c-68e40c8d4997 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2022-10-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003663 | 7da367c6-0a7d-4273-975f-8fd3299f27b3 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003664 | 2f502134-ee12-46db-b322-bd84040b8394 | Subsurface Transformer | Non-HFTD | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003665 | 948a5d2d-164b-4e9b-85a9-87574ea00e73 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003666 | f9c08220-3b95-456c-8660-2b98d8ac2897 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003667 | f3243f21-b472-48aa-b895-5759dc0954e3 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003668 | 067e54ae-6f41-4593-8219-f4b6caefbc14 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003669 | 0223c440-79de-4cc1-b6f3-3b99fbb4e611 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-26 | 2022-10-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003670 | 896c3455-6340-4bea-ba2c-3a2ebd063f10 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003671 | 698e8fb3-e5b1-42f4-95fc-055bb01c1e24 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003672 | 9593a78c-fcaa-4dfd-be17-45943eb14fb0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003673 | f833ecdf-bd46-4695-82f5-8a499459153b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003674 | 6df7862d-1a18-4493-8d17-5070bbd3807a | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003675 | 9d9bcdd6-28f2-43a1-a9ed-07e9161713d6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003676 | 4edde5ec-f06a-4d0d-a9e3-2ad0a2a16f9f | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003677 | d186e017-9afb-4ddb-8520-c7cbcdf14db2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003678 | b557800e-b205-4891-92b2-d173ce3c1667 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003679 | b97cc0c4-568a-4b1b-83cb-681dffc0ccc6 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003680 | 1226f38f-6372-4b38-8ebf-db2acc652f06 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003681 | 257cace0-d5f5-4006-9363-9058a66e4ceb | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003682 | f3f04387-269e-4300-8002-5ab516fc4df7 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003683 | 70475f39-c271-4181-b6c6-8f85749d583b | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003684 | 69c5f10d-8eff-470f-aedd-ab4db63e9967 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003685 | a9cbf5a1-fb57-4c92-8e76-664dcb70e241 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003686 | a9ae1d94-323b-4985-b0a8-208d43683390 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003687 | 7cfdedad-72e3-449c-8de1-0af0106c75e2 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003688 | b8c207f0-341f-45b2-a5dc-2f565c61c815 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003689 | 791e201f-de2a-4d61-9a7c-8117d626cef5 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003690 | 67eacf97-c032-4b3d-a1bd-be19fb824b78 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003691 | 2daa0614-4553-43b3-9a31-051a0e16b041 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003692 | b9ea6852-7497-44da-8f8b-d77c1b943033 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003693 | 705954ad-496e-4cc0-b6c7-10e0d1e5534f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003694 | d3de8ebe-423f-4820-9355-20ab83160314 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003695 | 3a9e766f-4355-48a6-a98c-26413c184e08 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003696 | ea278f9c-df96-4c88-90ab-79fd5f703f23 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003697 | c76a61c9-f3f7-47dd-9a91-409abc408bb0 | Padmount Transformer | HFTD Tier 3 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003698 | d9bd5f86-2789-47d1-95f2-8ef4e7546ecd | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003699 | 1662a1cd-5ceb-49b1-93fc-a780bc658dbf | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003700 | 289c8014-190f-47e9-ac2d-755d631fc1a4 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003701 | 6c746ba8-da7e-4ad8-8790-70a1250c36d4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003702 | cae5cd38-c6c4-455d-8ecf-babbbe45d76b | Padmount Switch | HFTD Tier 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003703 | ddcb61f1-817e-4f30-a5eb-1399cdeb7f15 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003704 | b95c5c5b-4dfb-4aa2-8956-8bcabdd6a8b5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003705 | 516d4ecf-2e7f-47ec-8b9e-cb0e6172279a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003706 | def94314-7bf1-4d50-a301-c1377311a40a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003707 | 60e1dc24-1694-476a-8035-f63d08c7a5de | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003708 | 69d7491f-b958-4eb5-9cd1-5435458de94c | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003709 | dda5488c-0c0e-422f-bdb9-d392e60854ca | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003710 | f752fed6-7947-407b-aaf2-bdd3a0357ef5 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003711 | 687bf21f-b12c-48bf-9870-c8de1c197818 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003712 | 860516a4-f107-40dc-8538-e90fa6a756de | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003713 | a06a1ad2-9562-4b09-8f02-4a154d17f877 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003714 | df7688d4-8313-4168-b7bf-a87b95666571 | Padmount Transformer | Non-HFTD | Distribution | 2021-11-01 | 2022-11-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003715 | d6b82dd1-a08b-4b83-82a5-d2bd032df7d2 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003716 | 6f28b315-0e58-4612-ad5a-2a3853b04416 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003717 | aeeb16c4-7b48-4227-8f43-0d4eee62ea2c | Other (Describe) | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003718 | 222913d1-64b2-4570-b54a-c92d197894b9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003719 | aaf28071-aeea-4c96-99df-6eab44cc2337 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003720 | 8eb42b9e-511f-4868-89ae-9d12db9fe120 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003721 | 9f691f93-53a5-43e5-b44b-baf83c2ef448 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003722 | cc851e0e-8d95-479b-a5a9-3d77768ae1be | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003723 | c8cc97f7-4d0f-448c-aebc-cebb7276f32b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003724 | 1f47a02a-b72a-4272-8e35-70c46eca8481 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003725 | b50b99a7-fb00-4311-a1d9-a3f89d7864d6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | 2021-11-01 | 2026-10-31 | [5 empty] | Liberty | 2025 | 1
1130003726 | 3759326a-470d-4c7d-8311-25a0e44e0f4e | Million riser with bridge switches | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003727 | 8a336278-04fd-44fa-9ed4-c5d71dde4123 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003728 | 667e43bc-507a-4413-8557-353f4a4898d3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003729 | e03311d5-420b-422e-a9ab-3d0fc1e77fda | Million dip pole with bridge switches | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003730 | 30e9ec4f-8a1b-4d9e-8532-c854b4e6b4bd | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003731 | 576f7b80-f2d2-4731-be05-70a5d29b13e9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003732 | 2194b38e-ecc9-42e7-ba81-98882a6802c5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003733 | 263d957b-b8ec-4459-99d4-708c8f4cb8e5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003734 | 899bc20c-4cb4-4be1-bf60-bc086ba5793b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003735 | 6f123e8a-3cb2-41b9-aa62-e23a93ef5b19 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003736 | 49820070-79e5-40a8-bf91-1519dd8ce439 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003737 | bc562ff2-9873-4067-beb1-2f2520203035 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003738 | 08424585-7ba5-4cff-b92e-801dd5235785 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003739 | 7d7a2c81-2e1f-444f-b157-e14dfcb1a344 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003740 | 202306af-3d29-4b76-9fc9-c92977c5c6fc | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003741 | a226c54b-8224-45f2-a698-f0c54751d210 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003742 | a01c768e-377a-42fd-9b04-e254799656e7 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003743 | ea54d99a-af5a-4ee7-b2af-fb88850a308c | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003744 | a16e8f1a-4a74-44d7-aac1-cd8b0e3e9a9f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003745 | 0d9ba3c0-2cbc-4ac0-888c-67a632acd0e0 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-02 | 2022-11-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003746 | b355d795-79e3-442c-8cf8-b69dfafbe192 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003747 | 2a17d956-d1d9-4688-8a05-e6366d70043f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003748 | 34c4977c-6c47-4c0a-98a3-d647a63042a9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003749 | 0fbb8efd-795b-47a9-844a-41c33711be26 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003750 | 2bcfa3c7-e207-4b2a-9fdb-162a328ebb25 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003751 | 40754894-3c03-4575-bdae-b16e8eda3e1d | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003752 | 70b2142d-8af5-4574-91a6-0d128404f305 | Regulator | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003753 | bebc84c7-06b8-40db-bbe1-f514f12a8092 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003754 | 3f89810f-aec4-4c11-9464-bba99e81c671 | REGULATOR | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003755 | fb3f036c-8876-42ba-ba67-aed8dbd22c2f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003756 | f7fb82af-30e1-4070-aced-8e7e8b00fabd | Regulator | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003757 | 2c2b9acc-bc63-4d8c-a8eb-5612c880af46 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003758 | 64d0c6e2-4180-4485-b091-665f21f54a1d | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003759 | f7a05631-3d06-42f7-886d-22c6ce62d088 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003760 | 4cf051ed-03c2-4b86-93ad-d36824c5d1b7 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003761 | 3034fb3c-80d5-46f5-b837-b356ff07d96a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003762 | 23cfefa2-b7ac-4d1d-a846-ea7217718faa | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003763 | 627e2ed8-2b7b-4ad5-9592-b2b9b1da2e03 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003764 | 0889c0ab-af53-4b52-966b-c7966de6c95e | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003765 | 663be561-e47d-4a4a-a947-9a6ed3226a13 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003766 | 93d7140b-c38d-4544-8943-d6f10f81c0d1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003767 | 62520226-2d13-44b5-98c4-39e513502843 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003768 | 2764ddfa-0b63-4c37-8cc2-a6629c2dd847 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003769 | 706064f3-6b86-46b4-a599-35b72f63b403 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003770 | 2aac781f-1042-4840-8cf2-cece4975881b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003771 | ebfa4c12-246b-49b1-9f0f-3763bc8403ec | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003772 | a0667eed-d8c1-4c75-b815-1d3ec28802f6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003773 | 4c547298-e4bd-485b-917b-51011cfbd4a1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003774 | a75e9ea7-3731-4bac-b931-04e78db08cf7 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003775 | c3a8e1af-bae3-4e0b-a94a-a90a8b1f5883 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003776 | e51f68ea-cec8-4452-a21a-c62a1982412f | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003777 | f889f99b-8348-4eae-9e52-0725d6ac6b52 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003778 | e2bb6d47-6f79-4d3c-ab96-0820c511eb40 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003779 | 73b7c453-abd5-4af7-9ffc-7b8156c492be | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003780 | 8a7c0559-9c60-453e-9fc8-7530b67dce88 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003781 | a0ea73a0-5f94-49b8-a85c-31731e089641 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003782 | fd0b4574-5ba1-4562-b59f-68fb630ea61c | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003783 | 341f0cc8-8c7f-4c87-8032-1f3a48f11e10 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003784 | 2dd3e7a8-fdf4-4d1e-8536-f017c5ceb505 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003785 | c0f1ca20-bbdf-4aa0-b0c9-1cb02cf1ed0a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003786 | e23e8807-3a89-4db3-8790-9130562e7746 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003787 | a5386803-b15c-4a6f-bf05-638df8393114 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003788 | 1f9260c7-52f3-4899-bb23-d50f0f10e731 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003789 | fe41d1c6-0e56-47e9-a73c-3040e69b2502 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003790 | c5b9339d-41e8-44b3-80bc-90d403e4634c | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003791 | cb93ed30-9033-443e-93f2-3bb708c9b8ea | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003792 | f9784fb5-d97f-44e6-aea9-2072689fe04d | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003793 | f36d7db6-0938-472d-b286-e7d76932d14d | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003794 | 3fd61d92-6f63-4b37-ba9a-b1b09c5ce596 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003795 | e974d547-3d45-4077-a1ef-ecea5dcef47d | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003796 | 27c06025-52ce-4196-b682-3a241787ae85 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003797 | bba9a32a-bb17-416c-aa4a-9af80ebfac5f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003798 | 46d022c9-680e-4e20-8f99-55002d0e7284 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003799 | bed65d66-1f64-4025-9500-e2f2ba549cc3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003800 | 577437d5-0a47-4e9c-a242-6670b40b3cfc | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003801 | 9affb1e5-9dbb-418c-920a-daeb0018f39e | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003802 | 69241977-9715-4fec-ad36-d67f66b5f906 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003803 | 6c3a4663-78f2-4816-81b3-95a91e27fb16 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003804 | b5057e47-e617-43af-a3cf-91b4802b90e5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003805 | 74c0b6b5-b8d2-40a1-85f9-4c74c64bbdd4 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003806 | 1875650d-24c7-4293-8782-8c6e3824b99f | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003807 | 2792c957-ee85-4f28-bab0-56c2e206c72b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003808 | f6c9f6e3-df6c-4084-8b5e-a695bebdf92a | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003809 | 66e0e874-4e13-4d2f-a3ec-f2e723fc496e | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003810 | 2dd09a9c-c660-4e43-8e11-029d8ae9e48b | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003811 | 18fcb6ea-fd22-445b-b0b4-e1c64f157c4d | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003812 | 9f401988-789d-4f66-80a9-765293f412af | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003813 | 7ad44b3b-d63c-4695-a1ef-4f86f9eadee0 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003814 | 56359f14-9ac2-4f85-9075-d22b8ecaab76 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003815 | 9a921048-7e6f-4db6-9494-62177420aec9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003816 | 97e9c61d-d22e-4545-9191-e249545e43e4 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003817 | b19740c6-82b3-4456-bc27-4dbc429cd91e | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003818 | f3353016-ac9f-4637-a0bc-487684cb63de | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003819 | 25f7629f-7d89-48d8-8852-a15c4657cc3f | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003820 | d664a045-7015-4ed1-b912-f92646a4c65b | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003821 | fd2d7187-2411-42ed-81b8-58a4d3d71abb | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003822 | 319c29e1-03ea-4d14-8610-01d22d6f36a5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003823 | fd37a7ff-ec5c-49d6-b940-190d7817b22f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003824 | bd07ebc9-d428-4687-95c6-9e045b4fadb3 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003825 | c2889f05-4510-4bf6-ab9b-3a4b66be74a3 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003826 | 00dc6f15-9045-4a19-93be-ce9de0c68255 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003827 | 719dbd3b-d751-45e9-87ab-af0d9109e15b | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003828 | 90c8650f-41e4-41aa-822c-fcf8ee06143a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003829 | d9d5b7f0-c1a6-493e-b2c6-e022dec25fd8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003830 | d33e239c-4582-4f45-bf1c-f22a3f9c29b5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003831 | 99265580-7cd9-4c07-b772-80aea4f639d1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003832 | 95541ad0-168f-41ca-bcb2-d0b547cfbacc | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003833 | d56b7971-beb4-49a9-8dfc-cc670246da33 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003834 | 51788ff7-bb37-4122-a2d6-7e4d6b7e172c | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003835 | a8ea1ae8-5656-4ce1-8b6f-08c89190871f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003836 | 4abace26-9b92-462c-a909-ec21b40f503a | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003837 | 6ff67d57-ab95-4cbc-883b-367c9e4cfc15 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003838 | 6098b3a4-42c1-45d9-a318-c394bae91b4f | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003839 | 06e4862b-57b0-4ee6-9c99-899fc65af24b | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003840 | 3ca8fda8-fcab-4e9c-8950-7876261c927f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003841 | e361cf1e-7e14-4baf-a0b8-3b432485a2cd | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003842 | 161128f5-5beb-464e-b4ed-b0cfb4d63550 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003843 | 2c1a70d9-e6ae-4d34-a193-e6787d5cd9d8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003844 | c556ac8e-a705-4d00-9b78-97b085f2af0f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003845 | 51ec8f6b-3653-493e-962e-330279c4d004 | Junction Enclosure | HFTD Tier 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003846 | 9f80bca3-d103-477c-9ec5-a389993ccd73 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003847 | 8edd9b0d-26e7-48a1-b66e-fac80750d58b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003848 | b822fca3-fd4c-47ea-9ddc-9167b560ad51 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003849 | 48698bf5-585c-4c57-b8de-ec5aa34a7970 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003850 | 154ab2c1-ae69-4121-a8de-166eaa9b3a14 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003851 | 70058380-feae-409b-b1e3-47d2ad9e6e77 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003852 | d00c121c-2471-4af9-8c17-3a79b2777da5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003853 | 21bc4f74-b34f-45f6-b29e-a2dd5aecd76e | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003854 | c094b4dd-1902-47ff-a385-e48c5e994a19 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003855 | cb1e5547-d2dd-4b55-8a09-be2dc3b60a6a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003856 | 70c962d7-6162-4a7f-94d4-ad9df67d6c07 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003857 | c7b2ac54-938e-4cf5-a26d-cd52ae3b1b42 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003858 | d9340227-da6e-4f44-bacb-51dceb365b6e | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003859 | 6618f0f8-ebb0-4295-a4c0-6bfc3488c21e | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003860 | a12c31c3-9ac8-4131-b5ea-77233fe0b020 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003861 | f8615808-3fd3-40bc-9370-4ea665f9e3f3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003862 | a040db75-035a-43d4-bec6-c13c38f64046 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003863 | 69a59481-aed4-4173-9712-9f08c91585fe | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003864 | e20eaa67-1091-4ce1-b285-a0e3f1931e75 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003865 | 304d7afb-bbed-456e-9ae8-f48dcb2304a2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003866 | 95ede16f-c88d-46c4-b310-16cf8354ec48 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003867 | 241ab08b-d97b-42a8-a97e-99c77a7d6f79 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2022-11-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003868 | c4928fcc-5509-493e-9b9a-2742942b5c46 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003869 | 9b024ff7-2807-44b3-9991-494a15a76622 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2022-11-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003870 | f48ff40f-4ce2-4846-b1ed-ac068f6235e2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003871 | cc61fa4b-8928-4590-a4d1-bd72247967e8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003872 | 36c17e5c-1cc8-421a-a50c-f67bb2d7ec7b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003873 | 4435fc26-76b4-4a0e-a46c-8dcbfbc84136 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003874 | 6b3a6260-7875-48dc-a1fd-33bbbb986312 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003875 | e5295df6-40db-4f53-89ce-ac6e73646e07 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003876 | c370e1cd-6580-40e7-91f9-db0eeca2b9ae | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003877 | 8d4a8de5-304f-4643-a28a-05dc0f673e86 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003878 | 8d2fe2d9-43de-4491-a056-9a97584d3eb4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003879 | 4da60e94-641b-423a-9dad-5c5c95c6de2f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003880 | f2859908-b0c1-49df-921c-ce5a60d0cbad | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003881 | b36ebc00-f57f-414f-afef-b60fdadd8779 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003882 | cc1f8089-8663-4abf-afb9-cb4b43c68fdb | Junction Enclosure | HFTD Tier 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003883 | 0b1f391b-32c2-4f14-92ab-711db48a41b7 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003884 | 4e8ef4c2-2c5e-4f71-bcfa-4845bc57d7da | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003885 | 97a720ee-e51b-46e1-88ab-58b6bfd08bc3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003886 | 1b253976-9c2d-4270-a34f-813ab66503a0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003887 | 8edfd2d7-e57e-4fe8-90ee-604aa24ac4a4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003888 | c4ece5b2-7e7c-44d0-9cea-67796624633b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003889 | ff964d7f-6d24-449c-b315-071cc9b78f34 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003890 | 7e1a7735-c75b-45e0-b5f7-42de67dcb4ad | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003891 | 00fb24bf-98fe-4101-8238-883b65fe9137 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003892 | f8f2dd25-e607-49f7-bc2a-a2d8ae51067e | Padmount Switch | HFTD Tier 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003893 | 855a23c1-8179-4082-8ca9-d7faeca7a793 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003894 | 9e52e1e2-97ec-4ddd-94f0-6eecd1d46ef0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003895 | 59dc15a0-980c-47bd-b5be-6d0074d4c738 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-01 | 2022-12-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003896 | d1bc89fd-6369-4743-97c7-3ec1c295fc98 | Junction Enclosure | HFTD Tier 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003897 | 3d4bdd58-28cb-4bc1-8ab5-24a2b45ebda5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003898 | a628d59a-f18b-4ad5-a2de-7b8ef81e545b | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003899 | da876f43-5eca-4b84-b449-92617ba3821e | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003900 | 28ae7b8f-a7fb-44e9-9bdf-bbe9ed769bf2 | Junction Enclosure | HFTD Tier 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003901 | 3431efa3-da78-4ad6-a734-9f8b13f762d9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003902 | f79316fc-f799-462c-aa1b-9da0ca30754a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003903 | c28aee0a-ceff-4572-bc48-2e5cb0a84e83 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003904 | 858ac9f1-67ea-4d93-b090-1448d44e0922 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003905 | 89dc8e3e-bbc0-46d8-93ef-8e076dbceb41 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003906 | 134b6581-1656-426b-8159-10bae2b929db | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003907 | 78f4a10a-4ad7-403d-85aa-6e1c501f5833 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003908 | 3fc33f72-480f-4986-b4d7-245969deafb7 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003909 | c589af83-02ef-467f-aeee-7d217f1e8f13 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003910 | 5094ee40-d750-4e30-acc0-72c09561e678 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003911 | 6f081616-2a6d-4b22-9142-b6696dcea656 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003912 | dc0f5871-0131-4f09-9527-17d704e73a1e | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003913 | 36be12e2-15f6-4ae7-8887-2f6823f3012c | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003914 | ca4cb178-f6a7-4484-816e-59b7c67fe56a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003915 | f17ccf5b-a1c4-4a0a-9532-3522a4767fcc | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003916 | 14d6eb9f-89f0-4b12-9036-a3f7b388f9fa | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003917 | e3a29ce1-e303-4930-a89d-e0a322d3acc9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003918 | cb869d06-bdaf-4ba4-a091-e77f580294ec | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003919 | 80aa210b-37b6-4f13-a74e-2710845afc9e | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003920 | 2c97498b-cd6e-4150-b31d-c40916a8e36e | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003921 | 243d7ee1-f943-4ef4-ba74-67b07dabec33 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003922 | 26b0dcfa-de42-40df-9903-179e832b48d8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003923 | caba6f74-2b89-45f8-a32c-90a52d5d8b28 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003924 | 0eb637ab-60cf-4b3b-b8ae-840ddb8b5cf1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003925 | e70af0a7-2aa0-41cf-8c43-6486ee763173 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003926 | 25ff2b77-ef21-4496-b38e-9a8111541a44 | Padmount Switch | HFTD Tier 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003927 | 9ae2ab3f-b422-4680-8c42-2921922e1c1f | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003928 | a719487e-a750-441b-b85f-04a822e554bd | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003929 | 7f028d2a-90c8-44d1-b2c5-70c6d9c66a4e | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003930 | 5ee1b427-c329-4379-8db0-a2052d7642cc | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003931 | 3d3a05a7-c603-4c90-bad2-0dcebecd2e53 | Junction Enclosure | HFTD Tier 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003932 | 11f778af-d1c3-469f-a294-ebb58f0efb19 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003933 | de7edbd5-f702-4c28-a3ca-d686c7e9311a | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-20 | 2022-12-20 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003934 | 43ab3ef7-b7d2-45a5-8fda-42eb651834c2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003935 | c32b12be-062f-4209-acce-3b56afc9ff2c | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003936 | 2d968f2b-c0c2-48ac-a981-41d4c4c06d4d | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003937 | 9bb99be4-599e-48de-a5a8-3adeb285894e | Junction Enclosure | HFTD Tier 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003938 | eba29318-c221-4eaf-b989-0ba7d80e26ab | Padmount Transformer | HFTD Tier 2 | Distribution | 2021-12-21 | 2022-12-21 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003939 | 4006d224-a3cd-41e1-bbf4-2f8e33663527 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-01-18 | 2027-01-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003940 | 98880d10-31ab-4fd3-bd11-918b54d50281 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-18 | 2027-01-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003941 | edc285b9-13e1-4d0b-b27b-8ac71239b037 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-18 | 2027-01-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003942 | b9d0b771-b60d-40b9-bdb6-3f6e28f4a8d0 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2027-01-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003943 | 1eb15c5c-161b-4a25-b21c-3dba971c1f6f | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003944 | 0277508f-0c50-4703-9be7-9125d4268361 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2027-01-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003945 | a5eee544-b786-4e61-a196-4bd701207d97 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2027-01-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003946 | 1e9a1327-0c87-46d3-bf4e-f7d4a57910f0 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003947 | dfcfdca6-6336-43ba-b883-e93be03864cf | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003948 | bf15e60a-78ab-448d-b152-b3a0481513e7 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003949 | 86c714dc-ffa8-4b1a-848f-e5d8b0e30c5e | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003950 | 7362db7c-3418-46b1-b363-050ebc6befd6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003951 | 3cf79ed8-740f-4afc-abb6-af5a8d24cf81 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003952 | 00ae7a6e-21ce-43f3-8e6a-e9c5360de7fd | Padmount Switch | Non-HFTD | Distribution | 2022-01-19 | 2027-01-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003953 | 85876347-5fe2-4ec0-a549-8c3ebe25f0a8 | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003954 | ebbebcd8-d748-458d-b72b-0b3cb3a8a81d | Padmount Transformer | Non-HFTD | Distribution | 2022-01-19 | 2023-01-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003955 | d26fd316-98a4-484a-b296-4ab7bd2d1fd5 | Pole | HFTD Tier 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003956 | 32eac4d9-d7a9-4d84-afbd-d62f0f2bc1fa | Pole | HFTD Tier 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003957 | b65d9914-75b7-42d7-87c2-3a1b5618bdb9 | Pole | HFTD Tier 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003958 | df04d907-f050-4e06-9ae5-67856b74cbd9 | Pole | HFTD Tier 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003959 | fc498a09-326d-4d63-9f85-0e58a10d54c1 | Pole | HFTD Tier 2 | Distribution | 2022-01-24 | 2023-01-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003960 | 2b5846ce-5add-4fb6-b30e-110f0be2516c | Pole | HFTD Tier 2 | Distribution | 2022-01-24 | 2027-01-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003961 | ede85024-0ed1-4881-a165-cae441895ca2 | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003962 | b646a044-212a-4883-b835-05df3135e9be | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003963 | 8dd8777f-cf04-4be3-b637-99cdbbccd3a6 | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003964 | 099b610b-3d59-4b76-957e-d75e3f85534a | Pole | Non-HFTD | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003965 | 222bee85-4956-4636-87b3-8d20690dc12e | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003966 | 1aa56628-a981-4cc2-9c27-8f81f0b0010e | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003967 | 900092a9-0d82-4ba2-8e68-2a871ec76873 | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003968 | ffdb08e1-3cda-4d70-b378-a29db53c941b | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003969 | 7a8cc998-e2c9-46f8-acc3-c1ce1ebd65ce | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003970 | dd4c6a5b-6280-461a-9307-7810ce4d656a | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003971 | 08977244-361d-49a6-a11d-b7ea84885b95 | Pole | Non-HFTD | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003972 | 89cff108-88f9-4315-9b45-e516a53c9b5f | Pole | Non-HFTD | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003973 | 4d986c89-524b-49a6-9c18-2c77865ba0b1 | Pole | Non-HFTD | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003974 | 79f94430-f7dd-4e43-b791-ac44b00b66bf | Pole | HFTD Tier 2 | Distribution | 2022-01-25 | 2027-01-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003975 | 6eed2db0-a166-431d-8bd6-c30d56d18c7c | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003976 | de0312a9-32dd-4e37-b7ea-5450062d4b14 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003977 | 468f2fdd-e8ea-4ee5-8a89-d9111ae6c9ea | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003978 | 228af172-de20-4126-8c9b-17f1104625e8 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003979 | 28a651f7-bf68-40a7-a7d4-87e2666f933b | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2023-01-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003980 | 71859952-679d-4912-8265-60faa7e2ef99 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003981 | b07a6841-ec72-4547-80db-57b6fb1ba967 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003982 | ed1f4cfe-c268-4216-abc5-e013378d3fef | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003983 | 5f2162e3-67aa-44a3-9117-68f66bec77ca | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003984 | 8bf623ee-ebef-4f63-a753-3af34c5f53f2 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003985 | 2de29661-84fd-42b7-9355-fdb668ede5d7 | Pole | HFTD Tier 2 | Distribution | 2022-01-26 | 2027-01-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003986 | 99eb7146-2303-4774-b479-2df14edf0fea | Pole | Non-HFTD | Distribution | 2022-01-26 | 2023-01-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003987 | 8bfd5005-be1f-41ac-8a4e-f257533a2c7e | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2023-01-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003988 | 8d86757a-3c9b-42af-adc7-06796d9d7a29 | Pole | Non-HFTD | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003989 | 043fae98-ccc9-44de-a7c0-fa93e21c647c | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003990 | 78e1a696-704a-4c47-bcee-1338dd0737c4 | Pole | Non-HFTD | Distribution | 2022-01-27 | 2023-01-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003991 | 854ae423-8952-4f95-b779-391c374b506b | Pole | Non-HFTD | Distribution | 2022-01-27 | 2023-01-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130003992 | 36db653b-49fa-4fff-a66e-f48cda801d8c | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003993 | 191884e9-eb33-4f6f-bf76-653a77eeefa4 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003994 | 8c70cf5e-777d-4e6a-a0e3-216ed425c4a3 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003995 | 6e1d1192-67d8-43df-8937-bd582eeac2d0 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003996 | 4170f2d8-a3b3-4fd9-892d-02c99aeff2c0 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003997 | 159e1a8c-1def-4adf-85dc-753639c85d4e | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003998 | af3c60aa-0c35-43c4-b18b-54a6a678f88d | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130003999 | 55163faa-a6bf-4846-a22a-43f45272dba0 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004000 | c55ae154-c776-4d22-8c01-d3618e007b92 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004001 | 5957e772-71c6-475b-a7b0-6c0c4f54115e | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004002 | b816cc8d-e397-44c2-b931-b1693beffc76 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | 2027-01-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004003 | 38ea6374-a530-4a97-8051-02e116fa36d8 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004004 | bf41e8c1-f20b-4868-bd31-488ffc926480 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004005 | 240dd5b0-bf4b-4d2b-9958-dd0349c52e71 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004006 | 6dd8d446-3ba3-4675-81d8-13aadcafe105 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004007 | 30e9314b-3fc7-4ef3-8a8f-8672f6471c83 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004008 | 32ecb370-1fe2-4223-9aa3-b3b344016ad4 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004009 | 64de3135-7326-462c-b984-7f93c432fe62 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004010 | 19034374-606f-44f0-bbca-bbc9c8e6c6d5 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004011 | 80b3a676-69ca-4447-8044-503c203f9f54 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004012 | 7b161d3f-c818-4639-a2bb-a97f1b8dc49e | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004013 | 310df571-c1f2-4150-b7d9-9590cc000ce0 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004014 | 9db076d1-85ab-4f7b-8fe6-cebe9e9e4372 | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004015 | 3e5aa20b-287f-4e65-8d89-20f2b57510ef | Pole | HFTD Tier 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004016 | 3863d8ff-96e3-4363-8e01-44bd64f1e23d | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004017 | ee8b96bf-0235-4a6d-b410-3adc36b03f94 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004018 | d53e934e-5450-43ab-981c-1a4c39321b26 | Pole | Non-HFTD | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004019 | 697dd3f0-21f1-48f0-bf87-f8c7b3d3a00a | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004020 | c4e018ac-38c8-4b21-a021-3434ef36aed7 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004021 | fee644bf-d820-47ff-84ef-ed0a8f4c90fe | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004022 | e7f8b7f3-8c67-4c62-a2d3-25de36bddacb | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004023 | 45272cd3-3f95-4a7b-bae8-62c8842024cf | Pole | Non-HFTD | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004024 | 5cfd89ec-b5bf-4403-a62b-7de5a991b46e | Pole | Non-HFTD | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004025 | 89554432-36cf-4421-a905-75d794760a16 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2023-01-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004026 | 0f04e37b-11c4-4417-839e-18c95bb58812 | Pole | Non-HFTD | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004027 | b2ae0f31-3cfd-41dc-9a14-e0695e2c3162 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004028 | 74d3df68-d906-4449-be83-d39385d41faf | Pole | Non-HFTD | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004029 | ec0ae177-610f-40dd-8840-854efb5ca0fc | Pole | Non-HFTD | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004030 | 79258e62-ee91-4690-9408-c165c6761acc | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004031 | 14a55c3d-7228-478b-9c15-e17f4b3f3dcc | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004032 | 79500704-6812-4c62-823b-ede8492e679d | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004033 | 453370c9-9491-4498-89a4-34d078f014b2 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | 2027-01-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004034 | 47a98e2f-f112-4294-9698-44510b7ddfe7 | Pole | HFTD Tier 2 | Distribution | 2022-02-01 | 2023-02-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004035 | cd06f12c-7067-4332-93c2-1bf2de1e0fac | Pole | Non-HFTD | Distribution | 2022-02-01 | 2023-02-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004036 | b66c6340-5f3a-4341-ac49-6bfce30c3977 | Pole | HFTD Tier 2 | Distribution | 2022-02-01 | 2023-02-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004037 | b5a819ee-8a32-44bd-9ab3-4557bc103c3d | Pole | HFTD Tier 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004038 | f9f147e9-2310-4fd9-8566-3b168ad678f2 | Pole | Non-HFTD | Distribution | 2022-02-01 | 2027-01-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004039 | 8e910bc3-7b15-4540-9482-fe25885e484c | Pole | HFTD Tier 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004040 | 673b2574-95cf-4487-b75a-9bd29aeba34f | Pole | HFTD Tier 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004041 | 40ed4c65-72dc-40e1-bb31-024a4eaeb42f | Pole | HFTD Tier 2 | Distribution | 2022-02-01 | 2027-01-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004042 | c683f763-e432-4ba1-9825-fd7bf223df28 | Pole | HFTD Tier 2 | Distribution | 2022-02-01 | 2023-02-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004043 | 1804e337-8682-4fa3-90af-ab5a106c71e5 | Pole | Non-HFTD | Distribution | 2022-02-01 | 2023-02-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004044 | 7a202396-2fa4-4d61-aba4-2c26ca013098 | Pole | HFTD Tier 2 | Distribution | 2022-02-02 | 2027-02-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004045 | eef9f8e3-0d94-48c5-8767-e524d5a51daf | Pole | HFTD Tier 2 | Distribution | 2022-02-02 | 2027-02-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004046 | 0616218b-bb19-4d87-99e1-0e825bcd16ea | Pole | HFTD Tier 2 | Distribution | 2022-02-02 | 2027-02-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004047 | db955333-1b48-44ff-a86f-eb29f060cb2d | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004048 | 0a5f34bb-89c6-4d6f-88e6-975684f2b44d | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004049 | 8e8cc5cf-35da-4c8b-8bba-06cfc398c5a3 | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004050 | ccfc32d6-007e-4975-aaf2-5b54592213bd | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004051 | 2ae45b42-6bdc-45a4-8c14-68dc424b9375 | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004052 | aaffcd1b-a947-42c5-b502-27c72cdab91b | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2023-02-03 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004053 | 1b830366-a6c7-4b26-ae93-86da0e17ae57 | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004054 | 3b411f7d-7f84-4058-aeeb-38aeb8b9ae3e | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004055 | eb0ee75f-54e1-4190-bbfc-c675345a4506 | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | 2027-02-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004056 | f00f17de-b84b-4d40-bccf-c6688a380e85 | Pole | HFTD Tier 2 | Distribution | 2022-02-04 | 2023-02-04 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004057 | 863da285-edbf-4295-b8c2-fe56458d6273 | Pole | HFTD Tier 2 | Distribution | 2022-02-04 | 2027-02-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004058 | 6f851d3c-aed8-43cb-83c7-ed251a712fb0 | Pole | HFTD Tier 2 | Distribution | 2022-02-04 | 2027-02-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004059 | 4caed8d0-3562-4ccf-8268-1666563489a4 | Pole | HFTD Tier 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004060 | 5557cf6e-722e-449a-b1c9-9d5b57bf62ed | Pole | HFTD Tier 2 | Distribution | 2022-02-04 | 2027-02-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004061 | 7ae3c14f-2dbc-4e6d-bd76-be4e2ded08fb | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004062 | 3246d659-6d77-4831-90b6-cea9af7d79c8 | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004063 | 5a44b1f9-daf3-47d2-9906-da650f080764 | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004064 | 2ef13931-0df6-425f-baae-b99d67aa692b | Pole | HFTD Tier 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004065 | 9b504635-8529-47ad-987c-e9c222dfaf87 | Pole | HFTD Tier 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004066 | 0f5d4677-fbd6-4d80-881f-e1aced3e76ba | Pole | HFTD Tier 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004067 | 59814633-5d78-46c3-98a6-d6a793ea0993 | Pole | HFTD Tier 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004068 | 73c23c0f-66aa-4389-a9e0-3c4e21a9372d | Pole | HFTD Tier 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004069 | 3cd8779a-dd4f-4a80-bd0f-da912a22a440 | Pole | HFTD Tier 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004070 | e491bab9-5918-49d5-910a-d85306c65fe7 | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004071 | 50eec48a-d4d0-451b-8f8d-7bf69be83d88 | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004072 | ca052ec3-6474-4b71-9760-46f14f99c04b | Pole | HFTD Tier 2 | Distribution | 2022-02-05 | 2027-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004073 | 689a9694-35c7-4e5d-8fd6-76093054c955 | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004074 | c8b0d519-5ed0-4d04-ad75-c9644ff6b414 | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004075 | 94c1c1f8-c648-4047-ab7b-42658c6e8c22 | Pole | HFTD Tier 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004076 | 024a504a-a708-47ea-a6e1-6aea8430b429 | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004077 | e755036b-b4b9-46e2-9efe-88413bcaceed | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004078 | 2ba86207-016f-4a6c-8374-f575e54bc4d0 | Pole | HFTD Tier 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004079 | 5e8d7c1c-19a9-4c15-bd56-e3877901be45 | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004080 | 26733d3c-41e1-4939-b0c9-974e9b7aed94 | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004081 | fdb754c7-0348-4e32-8e09-bf70bf37e73c | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004082 | c8948eb2-ee8e-4a7a-b39d-4d0fb33f4b2b | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004083 | bd2ecedf-a2b4-4298-b714-ea376549d553 | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004084 | 45d8b59e-b40d-437d-9a7c-2b9b922f4f0e | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004085 | 6fe1e808-51f9-4bbb-b36b-38c49894d5df | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004086 | c60090d2-1d60-416a-a60d-d31e4a6797b9 | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004087 | 9d4aeb38-6c02-4d0d-9d96-ecf2b02be560 | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2023-02-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004088 | 93088519-5600-44c8-b679-2de6d10b40fb | Pole | HFTD Tier 2 | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004089 | 74d3db50-2958-4ea3-aae7-6ec687c6f7f3 | Pole | Non-HFTD | Distribution | 2022-02-07 | 2027-02-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004090 | 829bc174-98ef-4def-b02c-c28427280eb9 | Pole | HFTD Tier 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004091 | 6541e1ef-582c-4724-abc1-27c4a5ff6ff1 | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004092 | 2f8b7c0e-9f64-40b0-9e06-c2e61b46ab5f | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004093 | 7867d964-1f89-4b8c-9e83-e87cc761370e | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004094 | 8fd2d194-0cc3-4236-b131-692a3f7afe6e | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004095 | 262258f9-4b4a-4482-ab78-5c5d251ff5d4 | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004096 | aab229c0-4d78-4d7d-ae92-e8778adf11b9 | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004097 | 3a508812-be8d-4175-855e-66a8a93c1e9f | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004098 | c5a11c96-f73a-4aa4-a8e8-9b0f66fc6d10 | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004099 | 6e920e41-7726-4669-b859-7885e6e5d4ff | Pole | Non-HFTD | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004100 | b1d99005-1e7a-4463-9842-bcd00c91afeb | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004101 | 361ad578-c9d1-44d6-83fd-a6171688612e | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2023-02-08 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004102 | a5cdc95e-52b2-4bbf-a91a-46e8ac3e68eb | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004103 | 24567a0a-842b-4466-8e30-ec5914884b87 | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004104 | 27a4e67d-0b6f-45b8-bda6-d421370b0101 | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004105 | 0d4d8486-686b-4e59-9502-cf8d8dec856d | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004106 | b5aa8e4f-995f-4832-8c9d-a0f0382225c0 | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2027-02-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004107 | 7b48c7b5-e511-40cf-9c07-908d5a0fcc4f | Pole | HFTD Tier 2 | Distribution | 2022-02-08 | 2023-02-08 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004108 | aee47510-2510-4c8a-866a-dfc1851e7622 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004109 | e62a2953-aa96-437a-adc0-6eca5113006a | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2023-02-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004110 | f5f3a27d-0f28-41e2-b904-041b5222c77f | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004111 | 9c8a0198-fe64-4ece-a649-80e87f783fdd | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004112 | 11b9b340-0f94-43dd-b4e7-f59a375faf5e | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004113 | 04d57a4f-0ec3-42b6-914f-a3469fd5f3a2 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004114 | e28837f0-09b3-4e71-a818-70bd5fb9c6fd | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004115 | f9deba75-bfe9-44f9-8b9b-6a996ee65564 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004116 | e94c659b-4d85-4b88-9972-6d2f0fc95a7b | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004117 | 4c4a84be-2c92-4176-b64c-03051d78995d | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004118 | 1418d789-7bc6-4a55-93a4-632676a3455d | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004119 | 409e354b-5e35-4b21-9f26-c5349fcaf695 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004120 | 8b77616c-e838-4a9d-9d19-43e258cce374 | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004121 | 8ebbf735-2967-43ce-a524-164f20cfb254 | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004122 | ad3fb623-0e83-4c5e-9c25-c81f37faa957 | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004123 | 3a211bc7-0824-48e7-ab31-826154608772 | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004124 | bbb0feb7-c394-4e1f-b724-67b7a5aa828d | Pole | Non-HFTD | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004125 | b164fc35-2500-44d9-9ece-ebfeb6b00cdf | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004126 | b82ee00e-e10b-462c-b893-fd1c6cf6c836 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004127 | 3377288b-7821-4177-8bf7-5452691c702b | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004128 | 65d2bf68-d300-4cd4-b5b8-897247934d06 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004129 | 3ecc3630-65b8-4cfa-b026-5aea84a78cc9 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004130 | dc0dde83-37dc-46dc-abf8-e909708acf89 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2023-02-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004131 | b4aff6f8-b0f6-4950-a3c5-64249790acc4 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004132 | 7838ca3b-97d3-41ed-864e-90337de4d2cb | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004133 | f5e435d2-8dcb-4ab3-8d2b-874bf6cfbc58 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004134 | 4e714cfe-6bfc-47c4-9d1d-9c79c9631560 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004135 | f4ed4a8c-c4a4-4a20-979c-921a00c4a32f | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2023-02-10 | Level 2 | 2022-03-01 | 2023-03-01 |  | Insulator broken on 7200 center phase |  |  |  | Liberty | 2025 | 1
1130004136 | b5369aa0-9d84-4889-8a25-ba2d224cabd7 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004137 | 347a3df6-003d-4e15-a10e-c538cc3aa9c2 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004138 | 92273650-5c8c-4b31-80fb-371286773c33 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004139 | 7ca72158-fca3-4608-963a-606b7090802f | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004140 | 84f38b4c-878d-4aab-8e63-f0fca525ea00 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004141 | 98e997d0-bb60-416e-9d8d-00e00d072fc6 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004142 | 336ffc13-c07a-4ce2-908b-b94223b4b313 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004143 | f8b26909-0c63-4bb4-a557-61764d582af3 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004144 | afc2c3c2-8cc4-4f9a-bf8b-acf9f7e7afec | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004145 | 8577e9c9-d067-43e7-b353-dabea63707cd | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004146 | 4ba7a9c4-396a-4e83-b196-597dc613f730 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004147 | 641c09cd-7df8-49c1-89fd-0c28e7ab180e | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004148 | ef2c5216-f05c-4c86-aa97-c358aa5d4da3 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004149 | fd25aefc-5092-45e8-8b3f-41191c2b6338 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004150 | e1bc3482-f8dd-45b3-9c5c-02021907d297 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004151 | 373081f1-43f4-43b3-9ac0-ac3005b9bc1c | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004152 | ea3ffd3d-76d1-472b-962c-05a5f788a14a | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004153 | 72180a74-92d1-4ee8-af48-47fe23503a02 | Pole | HFTD Tier 2 | Distribution | 2022-02-10 | 2027-02-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004154 | 5f3dff51-319e-46b0-98b6-e3656b60e743 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2023-02-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004155 | 5027ec82-9617-45c1-b457-2c865828a8a4 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004156 | 7975eba6-4ada-453f-9f75-5f0e06d525a9 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004157 | 3255b111-9ee4-4ea9-9911-131e79871f89 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004158 | 48cde3d7-c26e-4fee-b6f5-36d1b31c6894 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004159 | e8ea4709-8a1f-41fc-bd5e-022f9f4e755b | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004160 | 98797cd6-beba-4dd1-a582-96adbd90c85a | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004161 | ef0f6d13-2f30-42cf-a839-16c3b8bd0f84 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004162 | 85cf0826-67ef-469b-953f-fff1489e8e07 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004163 | 7889ba89-05dd-4b28-98b5-2c780633160b | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004164 | 640e56e0-8c5b-421e-ae26-999b8e6b038d | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004165 | 2203535d-0869-461c-ab49-ed472ad0a845 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004166 | 1048a037-c19e-4410-a822-f54a33a094e2 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2023-02-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004167 | f98781ca-7f80-4d10-9921-e9f3e33dfecf | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004168 | 5b5d578b-5cc4-49f1-909c-43d1aa697d7e | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004169 | 9eadc902-960d-462b-ae6a-85a890a2b9ed | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004170 | a91bcfcf-9eed-4f03-bb0b-5e5807b9a478 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004171 | 9a7e0f58-d901-472f-9d39-46d84a1deb44 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004172 | 27271a79-83ee-4590-bc95-201c162d2d62 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004173 | 0ed4b466-e953-4ed0-a059-eec179a89ccd | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004174 | f93c7ddc-36bf-4e1f-aab6-bcc9ca37f7b9 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004175 | 6eafa25b-0379-4a53-a155-a00da1809bdf | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004176 | 0096ef7a-d300-41bb-894d-8731d7d42a20 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004177 | 8fdd7ca0-48ee-48e5-8706-1e05f3dc29a1 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004178 | 90dbe23a-5b6a-4fe4-847e-069aa09a1b87 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004179 | 7fd32072-5cc8-40b7-87e8-a7b5b9a3db60 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004180 | 854a7074-a592-4f1a-8b28-994790628182 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004181 | a778c250-eeeb-44bb-81b9-94f18cf50bc8 | Pole | HFTD Tier 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004182 | d6b20f75-a2c2-431e-86ff-7afeed876eb2 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004183 | 74624c63-4d4d-485d-821d-65a1725e9c91 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004184 | 01f2f755-36c3-4cd8-85cb-6c5d1280b754 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004185 | 52bf416b-bc47-43d0-8ad9-ac88cbe69068 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004186 | daeaf391-654d-4291-aa01-3ff6de002d49 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004187 | d9e040c1-b18f-4b27-a4a8-b2008765546b | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004188 | 17407ecf-d6ae-4333-a45f-c72e0dd2f76f | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004189 | 35475c42-c6bb-4c3b-8f31-ecc9fafb1fc2 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004190 | 1cf59be6-c5e4-4755-aefd-924f11e06867 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004191 | b8daa9ae-7ca3-4e7b-b9d5-7b92c08e954c | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004192 | 3bfdd5a6-e333-4da7-a375-20004b5d6fc7 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004193 | 0b4dbea0-9aa1-4c2d-98af-0e14ef947e5b | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004194 | 5aff8b59-a6c4-4e8a-b3c1-87ab7457b5aa | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004195 | 90b0a8f3-97ea-48a5-b83b-b41ce2aba6e0 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004196 | 94d69d5e-b9c9-43e8-b57c-6b5f4214c313 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004197 | 29680063-05b2-4883-ae3e-bd1e250dd46c | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004198 | 36f334c7-a190-4f99-b45d-1e740329be2d | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004199 | a44c9641-1ef0-4d78-a32a-2fe5306a978e | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004200 | 9bfca67a-0300-4dbe-b484-7e9513d71de2 | Pole | HFTD Tier 2 | Distribution | 2022-02-14 | 2023-02-14 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004201 | b94ff1b6-54e0-4804-a8bd-29e125163ec3 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004202 | d890ee9a-0f14-4296-9bcb-cac84e5cb56a | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004203 | 3a89e89a-dd36-4b9e-a5ca-d48f3ac4ef29 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004204 | 3c6b65c4-c447-44ba-8b8d-39cb1b955f06 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004205 | 487ad8dc-134c-47ab-9b38-4b7772b7d179 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004206 | 65be6773-48df-42d0-8a6c-69c015e3152d | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004207 | c062b670-c241-4a35-b934-06669267a140 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004208 | a78cc53e-7923-4c2b-bb1e-6cf59d8a332e | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004209 | 039d6d2a-b43d-49d4-9bb3-875ca5452b3d | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004210 | ee4f3c52-702f-462c-8a6a-505e7d518d4b | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004211 | e090602f-3ae0-4894-8b91-6c55cfcc870d | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004212 | f80faefa-f6a3-4b7d-a0da-2c08a49e03df | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004213 | 18bd9e4c-5b55-47fb-801d-d163bfd77b96 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004214 | 87462660-e568-41cb-b54b-9a9c864adca1 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004215 | 38853420-36b3-4547-8e53-0b4f46fe2305 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004216 | 553f2862-4976-4606-b812-4a351c550645 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004217 | 6bffbf8f-5193-4989-9d4d-868158074cb2 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004218 | f7deaf33-5ee4-4c6b-a334-ec6c4138a5e6 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004219 | 248d43da-8321-4808-a946-7cabdb32c13b | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004220 | e3f6bb7e-bd0b-4d80-950a-097a99a868bb | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004221 | 7e07d202-73f1-4563-a420-00fb3f5d7ffa | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004222 | 947bc1d4-4b8f-4b81-a2f2-63d56c37edbe | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004223 | 7931be79-59c6-4093-8bf0-f35fff6cfba1 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004224 | 02796879-2d8e-48f0-8d61-19999923fd7b | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004225 | b22ee7ef-2188-4ff5-b4b3-c54bea5237be | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004226 | 3f6dd675-87dc-4253-ab19-28b711bb2c96 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2023-02-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004227 | 7da9e69c-245a-42ae-af6b-417204b8571d | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2023-02-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004228 | 438f01c7-4e93-4fed-899b-db83aa2f520b | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004229 | 55899d15-7725-4a37-b2ac-a02ae705d0ee | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004230 | da83ef42-52ad-42b2-b8c1-ec12b7d3294e | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004231 | df0e6db0-e95b-47ff-8728-3bae6646c39b | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004232 | 45ecfcbc-2389-4242-a5ce-de7064b1d746 | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004233 | 383aa520-ca8f-4e32-9b16-df1d4a27ed0d | Pole | HFTD Tier 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004234 | 2ec9f44d-2040-42a7-a15d-e49edf39d141 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004235 | b0f2f717-f4ab-499f-8053-20af695ded7c | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2023-02-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004236 | 9b33a883-46e6-4e44-a5fb-cb23af6f1daf | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004237 | 7f8b7030-ef5a-4aa9-a69b-48627e76fb78 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004238 | ba1957ca-b71b-44d6-928c-e08a6c85191c | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004239 | 9d022b08-baf9-4dc3-851c-5f875c872ae3 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004240 | c65a2464-72d2-4e03-b050-aa50e1bec388 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004241 | eeda8052-0c8c-45c1-b98f-525241ff9abd | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004242 | 691e566d-b98f-4afc-8531-bb44156b2843 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004243 | 5c4f95d1-d523-425e-9963-647e5a53c5fe | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004244 | efbee5aa-3981-42f1-92b4-a6e75952b7bf | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004245 | 0ed6137f-68ab-468e-9627-772310bca331 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004246 | 701d94bc-9812-47e0-8ac8-132e8531acae | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004247 | 70d32056-7851-4462-aa51-fa56955ad38a | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004248 | 8621246a-ca6c-4f4d-9c76-f902012c90a3 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004249 | 077c66c6-f44d-4523-b9e8-69a3c7cfa7b9 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004250 | 708ce6c9-1517-4ddc-a7be-264312b1ac38 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004251 | 74866de0-16c5-4b62-9d23-2b95b0ad037a | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004252 | 400aa66b-215c-4181-95ec-7b0e831f1bf7 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004253 | 9f3d9b3b-c7c8-4231-b897-17f0e3dcb676 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004254 | c0382428-dc2b-4b99-8042-c74090e94096 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004255 | 9443dcbc-54a3-49f4-bd68-6a4199c6044e | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004256 | f9e503a2-28d1-4614-9105-80b064f10829 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004257 | 0d0bbe7f-c4fc-4976-9fab-e6f5da0c688c | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004258 | 9dbdf0c5-a323-4342-af6d-5dad03f7cd5b | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004259 | d73ac0c0-0bce-472f-b676-a3d01dae965d | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004260 | 271138f7-5681-485c-a4ad-f1121977cc3a | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004261 | 724923f7-f34c-451b-9e8c-fe74dd568deb | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004262 | ea1fb652-0fd8-429d-80d0-084ea93c2976 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004263 | 99e20059-b9cc-4a3a-9f4b-b2912bf19144 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004264 | 9785ba76-1aba-41f1-864d-849a201fd1e3 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004265 | 49cc4cbe-ae3a-4e43-9dc4-6547476d1c7c | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004266 | 0b995957-56d6-443c-8bca-8201f2e469d0 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004267 | c759a3a6-d3ce-4df8-9543-3c2a63ed597b | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004268 | 5865ac4e-a73c-4af6-ad1b-2855f0e051fd | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004269 | 8d8d136e-295f-4bd5-a39e-370d80b33820 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004270 | 47ce586a-09a3-4662-99a2-8fff6187df98 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004271 | 44fe6654-06be-439c-887c-70312b9f1c44 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004272 | 4cffcaa4-5daf-41a9-8b4c-2a7062fe2ea1 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004273 | c1b5acd2-946f-4d5f-a591-52b40de913ff | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004274 | 22d303dd-6f3f-4495-869f-f550c3c1c990 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004275 | b0b78394-d538-4c74-bd45-fa3c8b5519d8 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2023-02-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004276 | 2dafe234-c350-4a22-b05a-4618d50078c3 | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004277 | ae116213-af5f-42cc-b484-d2d33bee6dee | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2023-02-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004278 | 20304509-bc34-492b-a313-18c2622fefdb | Pole | HFTD Tier 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004279 | 10f20064-542b-4830-af34-68bb174c67d5 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004280 | 8bd616ac-809a-4ef6-8ae4-aebb96ae6c54 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004281 | 877f8b4c-dc66-4311-908d-bbcea4e4d9be | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004282 | 7ae8bcc0-ff28-43ad-821f-34df53e64856 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004283 | 65a309c1-cf6b-4bed-bcae-32cb6208d3b2 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004284 | 6a4a1c51-02a6-4b74-b82f-3fcac6619351 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004285 | 5bebe5ff-2c01-4b56-a77f-80dcc59928a2 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004286 | ac5e64b7-acb8-4a6c-bb1e-19af91331589 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004287 | be5507f0-60d3-47e0-9691-1b65485e38c7 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004288 | 76bc5507-d5b8-4391-b358-fd12cb4faa44 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004289 | 67d30b97-97b0-4a62-84cd-7797cbc7b27a | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004290 | 20ebfdd9-851a-4144-ba77-0625426e7d2f | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004291 | e3510e28-1307-4d46-9454-ec5d1a1ec04c | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004292 | 244f07ff-8cae-43b4-9289-1cc2efb2b7c4 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004293 | 5ce7533d-3ee9-41e1-b22f-ae9f635c88b4 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004294 | d969d457-fe53-4ba4-b9e9-b87c641c08a8 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004295 | 9d0b1f07-aeca-4179-9c61-d5c19e29d82e | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004296 | ffd4779b-c0d9-4725-9b42-351f37b59c47 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004297 | 552f0a00-eef7-4833-8a3a-4c29ddbf7b79 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004298 | f063a576-c2b0-4457-b0f0-97e0cb588a4e | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004299 | e9c86fb0-6313-4803-b85e-72184bea0efe | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004300 | 4e389dee-70ea-4356-81fb-848fef83676e | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004301 | a4b3aed5-09f3-42d6-9182-f9fe12c38c47 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004302 | 0f36032e-a34f-4754-91dc-47ff2a73a780 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004303 | d8e7a254-8a3a-4de6-be80-3ae534416fe2 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004304 | 96ee963a-a3aa-4fe7-8aba-3a3c507240dd | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004305 | b5061134-142f-4342-8014-0a2d767e3bbc | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004306 | c46eeda5-e1b1-4d5b-b74f-77cffee8366d | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004307 | 283a6378-1bd6-4d04-9e97-f397374239cb | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004308 | 96ac7bc1-1d28-4af4-8a56-4082430c47f2 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004309 | ce444bd1-7843-4a24-97ce-db8d482edaf0 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004310 | 5e59230f-37cd-4b9b-9a74-00da4dfc6c55 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004311 | 1b3ce024-4b1d-422d-a0c3-3f9b51d9ee13 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004312 | 4fcae5b4-076c-4606-90eb-7451fcc61311 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004313 | 37bc1523-6a11-4ff1-86d9-7279f88c8d46 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004314 | 10ed8733-af37-4da6-92c8-9fd2f663e4d9 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004315 | f3cd9c1f-4c46-439e-8a76-2812b3465187 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004316 | b574719a-7966-4dfb-b4f3-c52cc84fb70f | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004317 | d422ad98-a166-4f00-b5c3-d0ffb783b6ff | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004318 | 54f4a338-1b7a-4e1f-a3df-9f70fe166300 | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004319 | 9ebdfd81-25dc-409d-8f99-287299a905da | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004320 | a1244c25-99ee-4524-b910-82767ebe789e | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004321 | f271782d-5511-4e1d-bdf3-28767b2d367d | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004322 | 78061a04-4fec-4305-93a4-7cfd7a4b02ae | Pole | HFTD Tier 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004323 | bbfbd9e5-2a43-4cf9-8d63-384354e6193b | Pole | HFTD Tier 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004324 | d6f3c386-d7a5-4808-b5dd-fd681b500b73 | Pole | HFTD Tier 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004325 | 859ba831-d0d3-4c11-84f3-8617d3494973 | Pole | HFTD Tier 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004326 | bc29ee4b-f7a0-4828-968d-3e0639b738ec | Pole | HFTD Tier 2 | Transmission | 2022-02-19 | 2023-02-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004327 | 10e876c6-2a1b-4a9c-bf84-44016aeb1892 | Pole | HFTD Tier 2 | Distribution | 2022-02-19 | 2027-02-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004328 | 5187767b-3cdd-4cdb-8f9f-10e4aa4480da | Pole | HFTD Tier 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004329 | e234c2b7-5a0f-487f-a649-9d28f00d1a91 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004330 | 37fa9bba-bcbd-412a-95af-4e2d9e84c822 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2023-02-21 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004331 | 3987970c-c1ce-46c6-b15e-53928aa69149 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004332 | 39633e0d-56ab-497f-8238-3a8df6bf0422 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004333 | 935fcf7b-57f0-4309-b78f-19e5b8f9afb3 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004334 | 27bf932c-cdd0-42fa-bae3-ffae46450035 | Pole | Non-HFTD | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004335 | 1d7adb21-0340-4c49-bdee-7f24895a2ca2 | Pole | Non-HFTD | Distribution | 2022-02-21 | 2023-02-21 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004336 | dd434e8d-f495-42ae-8a3c-fbc483fa85a6 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004337 | 77826756-5e17-4d26-b134-e37ade697d3d | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004338 | 89f49812-93ae-46ff-962f-b7b67ea85506 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004339 | c8f056ac-db16-40d8-8fa4-89a632372d17 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004340 | 02e2ef56-f561-4295-acac-ac41e9847395 | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004341 | e729f543-36a5-413d-b31c-4375990c69fc | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004342 | 4b4c7bc1-cefd-4e62-be59-d42b422ceb0b | Pole | HFTD Tier 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004343 | ba12ac90-f81c-4d8d-9070-2cff1aceae74 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004344 | 0cd63da1-526d-4da0-ac70-547f15f64ce0 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004345 | 6b61782c-fec9-4fae-bcdb-f8a67d3504f8 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004346 | c6096db7-aa5a-4245-a2c2-a96b032299cf | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004347 | 5afd6502-8f0f-4a16-bf57-2f2f56ceb31e | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004348 | bd5384c7-4bd1-4745-97a1-ac54117d1068 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004349 | 4909c102-847e-4b1b-b3b8-96117b2f076e | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004350 | ffe7051f-b693-481e-85a8-15ddc753f00a | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004351 | 0379701f-b44e-43d0-9341-899221cc2669 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004352 | 7494c47b-292c-48e2-88e2-df9f87ce0379 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2023-02-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004353 | 1c5378ec-3677-4013-b0b2-c329fd782dec | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004354 | 5a4c2575-d784-4717-a5b9-5b04aecb63fb | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004355 | 36069986-be44-4faa-8aa2-6eda045b2330 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004356 | 07c28662-ceac-4cd0-90ce-8232d672aabc | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004357 | be02f36a-9b3d-4e56-b48c-c3225cb948d4 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004358 | f785a383-b8c7-4949-92c5-a96f19b711ea | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004359 | f064449a-ebf4-4c12-8b30-c523861c16b0 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004360 | 7f527968-df73-49cc-9f05-cee645222c12 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004361 | cac1df23-bf75-4e0c-b092-534cadd6ed8e | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004362 | 372548d8-5d80-4e58-8835-e36b0f7f89e0 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004363 | c187a387-0679-4feb-ba14-1b09635120f3 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004364 | 8214c438-9985-4466-ae83-4df0a16e2e41 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004365 | 78875fd4-13a8-495b-85ed-64b32539bffa | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004366 | 8ea93489-bcfe-4f13-b958-deafc56beff1 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004367 | 3caf99d2-0abb-439c-9769-a4ff298a68f5 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004368 | 531a22fa-866b-4e53-ad53-89fd92e25d63 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004369 | 4b6d1296-b85e-48e6-a916-2b30cb4661b6 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004370 | 0140a406-6179-42b2-b2a0-71b36891e433 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004371 | 8623e559-0d0a-4e71-a711-b09f3f779f4f | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004372 | efbcf980-3eb9-4358-b4b4-fab2c7cbd84a | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004373 | 630fd4ac-7b24-4af2-8518-c56c321a5816 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004374 | 124dea7d-f27f-4eaf-b349-c1c7a50111de | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004375 | f43ef478-f816-4534-807e-30a5f1e2b999 | Pole | Non-HFTD | Distribution | 2022-02-23 | 2027-02-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004376 | ea66c5b7-9c80-4ad8-8e4f-c788116c06bd | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004377 | 16d8cd56-e13d-4341-9277-3a576765b208 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004378 | 5f74188c-7d0f-4654-903f-dd07b1ff2938 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004379 | d5049150-9b22-48c4-a7a7-a8b1ec4eb6b7 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004380 | 653e1c9d-7ae1-4705-8755-43c539383418 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004381 | ee11176b-3a19-4089-8484-06d7561fa353 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004382 | 6ba47bd8-a400-42ee-b779-bb1cc7941ed6 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004383 | 617233fe-4179-44f6-8e64-2079d1e94090 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004384 | bbef76b2-3d90-4a6b-b2a4-4a9c7b9a4934 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004385 | e7f729ce-ace2-4cd7-b676-9d4d161b25bd | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004386 | f1e8c6c2-4de8-412c-aa2b-e4963cdf9c0c | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004387 | 4f6414e8-2baf-48f5-b9d8-7b32a0de8f13 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004388 | 4707987d-5239-43ec-a193-afa0d31cd8d0 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004389 | a8b4ab2a-eb29-4e16-9782-63034f4d0465 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004390 | eae58e54-52f9-4ea4-995c-125da0f0f215 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004391 | 0c1fa858-08cd-4b10-b081-f06df53fe855 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004392 | 8be489ac-8429-4a28-87ab-64885de3e9df | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004393 | a0dd75d0-b4df-4f0f-b125-6856ded774d3 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004394 | 41d6a7ff-eb55-4d3b-adc1-f1ad1336eb34 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004395 | 0d0ce0e9-ab78-4daf-89f7-b341bd58b579 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004396 | fa420291-7268-418d-a286-ffc4591be4a5 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004397 | 7c3e3bb4-6a83-4dad-b9f8-7f3ed34fde94 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004398 | eb996fe9-c479-441a-9a73-d88a38ca7f49 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2023-02-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004399 | 688af7c8-9566-4874-b32b-950521a06c76 | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004400 | 50ec66bd-cf4a-43bd-86e2-f06446bbfb0e | Pole | Non-HFTD | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004401 | ff36785d-4895-4b39-bcfd-64f13737584a | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004402 | 2241ac4b-d0c8-4428-b8d5-dcc663a03eca | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004403 | d089bd9c-b2d7-4026-9d59-f64fc9a6ec5a | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004404 | 8020fb5f-2f00-4302-af7a-fef6bc43c26a | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004405 | e7a4df91-179a-4d39-b3ea-90d33d5661a7 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004406 | d5f16ab2-8a29-40b1-85ed-73ee67224e08 | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004407 | 592a28d7-5d44-4ec4-9df9-d4a543d9502b | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004408 | c8847889-53be-40b1-af9d-59ce98bc74ea | Pole | HFTD Tier 2 | Distribution | 2022-02-24 | 2023-02-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004409 | 193082a7-e68b-4ce4-8a3b-9b364ebc950c | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004410 | d3b213f5-43c0-4075-84c3-bd43f7297c41 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004411 | 356e602a-f24f-4c41-b98a-1b0be6e758a3 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004412 | fac502ae-f6d8-4080-92ee-301b5930cafb | Pole | Non-HFTD | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004413 | 2b6404e0-300e-4568-b19d-daeb5f1312ff | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004414 | 19e6c6d5-3a10-431c-bd3b-6269206237cd | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004415 | 007adb36-353c-4d60-9351-f01847004a89 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004416 | fcde8853-3f14-4a30-91b9-6e7d7e542ef6 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004417 | 9e1f1fbd-075e-437b-96ed-f2611da9d845 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004418 | ab3c6590-a4df-42c2-8121-9cf7647b2562 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004419 | 81eaa342-3487-479a-ba94-4d620a038329 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2023-02-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004420 | e3aff06e-22a7-4b19-9110-190114a77c6d | Pole | Non-HFTD | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004421 | 2bf7b5bb-b699-4a78-a386-b22cc4a00aa8 | Pole | Non-HFTD | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004422 | 1e4290a2-bf89-4ca7-b567-b0f90682ac45 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004423 | e7b213d0-3779-4907-b2d9-3f148b7206f4 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004424 | 87acbce1-183e-469f-89bb-f3aafed8179e | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004425 | 809af1d9-399a-47c9-8fb6-8efba13a0af5 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004426 | 7c10a9ac-4ea9-498f-b730-4b1065e51329 | Pole | HFTD Tier 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004427 | aaecfa6c-cfa5-43f6-8b5c-d38d2a748b99 | Pole | Non-HFTD | Distribution | 2022-02-25 | 2023-02-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004428 | 02287107-b5c9-47ad-a076-6b4080f37575 | Pole | Non-HFTD | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004429 | bb82f9b8-e802-473f-8a06-6d61c026f351 | Pole | Non-HFTD | Distribution | 2022-02-25 | 2027-02-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004430 | cbee412b-ea08-4e2e-8dd3-d840df3f1c60 | Pole | Non-HFTD | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004431 | 42f85533-e863-4a93-87e7-99415f5e27e5 | Pole | Non-HFTD | Distribution | 2022-02-26 | 2023-02-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004432 | 0d772885-a904-4855-a0e0-707a9fa963aa | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004433 | fd91963e-a2cc-43a3-a68b-18168ae3086a | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004434 | 16402208-3df6-430e-8b4e-ee80422b2254 | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004435 | a265bb57-349a-40eb-9932-c92587748cde | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004436 | 766c83e0-a3aa-4e77-b637-e8ecaf1b61ed | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004437 | 35e5c18b-0dec-4bfc-bf48-1f60948ebfaa | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004438 | 0b6fa2a9-15c2-4fb5-a732-95b67d772a09 | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004439 | a6107ee3-4637-4ff1-89f5-6e474a425c0a | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004440 | 62489f1b-d54a-41e2-a264-b7bafe0d0157 | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004441 | abecd5f2-eb6e-415a-9c75-aba7decef107 | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004442 | 528d45cb-0f42-4079-b4b8-49fa9b7b5315 | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004443 | b44346f8-e0ac-49ec-b4b8-4b41fbd05c58 | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004444 | 4de6ce0f-cb74-44fa-be5c-062afe46e7be | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004445 | e13607fb-4ea9-4e5a-914b-bb659cba38c7 | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004446 | 6c09af98-be98-4462-881f-f1d78def1e5c | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004447 | 83f5d058-7808-425a-b206-12cfdbffbee9 | Pole | HFTD Tier 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004448 | 6d074cf4-a17a-4fe5-bfe0-6de6cb56cce8 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004449 | ea17fc89-d740-4a5a-8096-ede5873481dc | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004450 | f31d21e5-944e-48ac-bcee-c29074c92159 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004451 | 4aa52295-2248-4da6-b326-9dd4b4f35a9b | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004452 | 122eb7be-1c77-4245-a809-e09c54b2adfa | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004453 | 1aca49f4-c0cc-4aef-a70e-09b25742eab9 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004454 | fe559a22-c1bd-4951-804f-41f2a2e465dd | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004455 | 727405c8-18bb-47d6-b2d6-6f98a423c685 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004456 | 2fa0521b-e61b-416a-8f2f-3c0c17fe21fc | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004457 | e0db64da-2c9d-4cdc-b766-f48469b85041 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004458 | 1e45b898-c7f2-435e-8349-fc7809bc9f55 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004459 | cb9757c8-d8a8-4991-8515-a062a28b9290 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004460 | abc16615-7808-45bd-8c70-2b5542d2bcc1 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004461 | a40c9abe-5c76-4fd4-a070-8f009638f197 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004462 | d117c99e-354c-49ac-b4d8-105333acd364 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004463 | 2b9f9207-d3aa-442d-b07f-39d280f770b2 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004464 | fc784963-eeb2-4201-822b-6048a528620f | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004465 | 16d48e85-5980-4fb0-80e5-af92cd8c0c12 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004466 | e55eebf1-bf37-4a9a-bd12-b1932e810128 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004467 | 4a28b787-6012-416f-8b40-7721bc6fcedf | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004468 | 25f2e63b-c85c-4234-9ffc-04de760a6776 | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004469 | 24618b52-1670-4e55-a09c-e2d1fb43c8cd | Pole | HFTD Tier 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004470 | 859fd0c2-8fa4-4bf2-9659-587b4e5732ba | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004471 | 1dcabb81-1f56-4fea-bca5-f7f19f9bf01f | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004472 | 3bbcdad2-e1dc-4fef-810a-019ee6ab95b1 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004473 | 72c4c84c-87b0-455e-851d-825e40159edb | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004474 | 2ceee83f-745a-4463-ab2d-78d3abdec0a1 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004475 | 62bce5c0-f588-45f9-8106-4ba0db955ef6 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004476 | d73636b1-e8b1-4abb-ba62-27cbdf69c45b | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004477 | 54c80c86-bda6-4faa-b364-0de74817354f | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004478 | 9eb1cdb7-024f-4897-ba8d-65150cefb10c | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004479 | 950a67c5-1730-4be5-b8f7-2437a7ad8fb3 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004480 | 0d16fe95-8650-4231-a428-68409e9a8f3a | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004481 | 9c4203c1-b39b-4541-b373-fa82aaacf2bd | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004482 | 68b18736-b7b4-4bca-8d46-59248f476a1c | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004483 | dc5d2b55-535a-4145-9186-3c2a0aa11515 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004484 | 2c55fe27-4cd1-4e2a-ae51-18a99ba78830 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004485 | 964f3cce-fe69-45c0-8bf0-5f65bfa42529 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004486 | d68284bd-a701-4957-a1b3-f3cb139f7a64 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004487 | 70944a0d-756d-494f-b125-25dabe12863d | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004488 | b772229f-97fe-48d9-b003-e5f11e0eb8dd | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004489 | 0e86a72c-b6bf-4b5b-8af1-ae60b9358040 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004490 | 680f696a-d323-4268-9363-35638b749d85 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004491 | 8bb2c126-9068-4690-ab94-4f64edd7f3ec | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004492 | 468e7a72-aac9-4875-b6c6-7ca17a809add | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004493 | fff10f7c-ed25-49bc-96de-64b2a069d9d6 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004494 | 8a979b76-6ec7-41fc-8585-4eefc8cf724d | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004495 | cba75e47-6f96-4558-9d85-e6d55a79ff4a | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004496 | af8dfd74-8f2c-4b62-9813-3fcb014ba1e9 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004497 | a36c39a2-d592-40bf-bb22-32899f3d83ba | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004498 | 19f71cb1-dbcd-4170-8ae6-25e7ed818a99 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004499 | 000345bd-beab-4323-b047-7f58ba23bfbe | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004500 | 5e33c42e-4c59-401e-9915-88db56c0ed59 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004501 | 3df0bec5-a624-49bb-bd69-1c3c07bc2706 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004502 | dfcf8a9d-eb91-4253-8590-a160c4caadd0 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004503 | fa6c7baa-32de-4b98-ab22-a0e03ab650da | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004504 | 75ecbeb3-bf64-4fa9-ae16-d7357816e3e0 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004505 | d1b72a86-f7be-4903-9054-deb205701c4f | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004506 | 2faa0286-4d2d-4802-a602-1c0e8b995b19 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004507 | 3659639d-9882-44da-bdbf-68aa293c1ee7 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004508 | 724d5e19-ee2c-46e8-b91e-82c5961309eb | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004509 | 3ef96de5-6e55-455d-9012-0c5a3bc12f1c | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004510 | f88c8f7c-92a9-43f3-bb9f-b123e322da59 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004511 | 122a807f-c7ec-4aed-928e-6b3d4f503e18 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004512 | 14b43334-4892-43f3-a1a6-aa38552380b5 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004513 | 1c2f1ab1-2d58-4c48-bb42-ecbfefa48e04 | Pole | HFTD Tier 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004514 | 118db6f3-3972-4377-b6ff-70f0658a1503 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004515 | b8834e72-d29b-4778-b42f-e2b80f7f191a | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004516 | c7863bf5-26e3-4ffb-8f1b-71b33ed22fc6 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004517 | 8d118ee1-dd6c-495d-b2cd-52df3a96953a | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004518 | e7f4af8e-02c8-44ad-a67e-14d3f4c94fbe | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004519 | 18e5b3be-284d-4902-a1ee-d6bb5ce2f183 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004520 | 0748d31d-9a0e-4785-9110-e2548baf68bf | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004521 | 2f111a29-6b32-457a-9820-681f39c0f7d4 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004522 | 6c215b98-b1b7-497e-8a66-3970d8a5494a | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004523 | 43ffd650-ff5c-466c-b1d9-bd4eae98c628 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004524 | 89657559-0bcb-4d5f-b8e3-84122ca68424 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004525 | 27c9ae21-8533-4ae8-9740-3318625968de | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004526 | b6260d5a-1901-4166-a6c1-b260bbeb57b6 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004527 | bac01e77-1f47-4cf2-8f25-54a526864b6e | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004528 | fcc1597a-45de-4181-b63d-34996c6ce1ff | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004529 | fd775da9-8175-45c0-8c64-c18753d96dbf | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004530 | 474acbbf-1f6b-40c5-ab4b-c83d0bf93411 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004531 | 72bb551f-6b47-4005-adea-85a9e259208e | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004532 | 8146167e-d080-4c28-8fe0-198b6e8a9165 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004533 | 7adc2332-94ef-496d-a96a-f6ec2947f265 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004534 | 7d018483-bba2-4200-9adc-8c381cc929e3 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004535 | 51708ac0-d11e-4bd3-8f62-d39b0431acc9 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004536 | b2336ecc-a1d2-43f8-b9b6-427b9730dd83 | Pole | HFTD Tier 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004537 | 9d132614-0aa3-494d-aac5-3e3d460483ed | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004538 | 1da73f04-c984-40a2-b8e6-9f9366d0df20 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004539 | 758290f2-01dd-4589-b57a-e87f0f5f5633 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004540 | dbd1372c-c638-40b0-a3db-cd5693d7c804 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004541 | 620954ff-355a-49c5-ab33-e6a060c052cd | Pole | HFTD Tier 2 | Transmission | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004542 | 7c1d2fd2-d98e-46eb-81a6-748860f7b50d | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004543 | b413799e-05fd-45c5-802e-338b566158e2 | Pole | HFTD Tier 2 | Transmission | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004544 | aba0429d-c04c-49af-99a8-cea2d2e7aff6 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004545 | 4ac35a51-82d1-4533-9529-2c6634d7ceb8 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004546 | 928bbc33-bdbe-438e-99a4-bea302d0435d | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004547 | 5c8cd669-43da-4290-bf9e-f9ac7d21bee8 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004548 | 2024979d-c021-487a-a2fa-a2e6d07a09c6 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004549 | c182d3be-fafd-4868-9269-acef9b47712b | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004550 | 9117be77-b5a9-4744-ac55-c52b5de5f09e | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004551 | ec42faca-dcdb-498a-8bf6-a60434c3b19a | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004552 | 96708bff-8bc3-4550-a2fb-20e3b30d5e52 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004553 | 35b4d4d0-2fc3-436e-96ad-81964433385a | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004554 | 025e007c-06ce-4b46-bbc8-5cabb0bd4861 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004555 | d500bc58-e23c-45c1-accd-4d30e52bc300 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004556 | 45db216a-e14e-45c7-a114-8075f729ddad | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004557 | 6d4e04e6-91fd-44ad-922e-62012c0d31a8 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004558 | 24d2edde-aeb0-4236-bc19-ba4362ad2f40 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004559 | bf515492-9cd1-4193-90d2-9bf157917115 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004560 | 7e19f252-101e-4b08-b6e8-824cb7ed7eb6 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004561 | 890ce002-3f41-4eb1-b37d-b6be1048d91b | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004562 | 819a3168-cac9-4bcd-a941-a3954609b813 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004563 | 2e409d41-287c-43f3-ac53-499d40a97fef | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004564 | 0f662efc-3ac0-4aa7-8a02-0ccfc133df98 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004565 | c06e8002-8e70-4553-8c1b-822d3e181b18 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004566 | 43a65242-1c7c-4286-9d19-7d97648a390f | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004567 | 7e3b28cd-1d10-47c2-84e4-8c62190a6099 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004568 | eff1c26a-66c2-4481-9297-519c502653d5 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004569 | e0b22470-e823-4b0a-94e5-b34563b87d3a | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2023-03-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004570 | fac6a3a0-75c0-4c0e-ad42-252501c6f847 | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004571 | 99fc7cda-66cb-4d16-9062-7493c69c22ed | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004572 | 9e2e4c11-0309-44e4-895a-2def76648e70 | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004573 | 47dd40eb-38a8-4772-aa88-a283ddcf0597 | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004574 | 4b093598-5e42-4a39-9233-e1fa149ee236 | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004575 | 7ed130d7-1186-4547-9330-9eaeda9697ad | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004576 | 194af122-7ba8-452d-92b4-2e945ff7b1bb | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004577 | 131a2118-e6cd-4620-b5f6-97f79bd425d6 | Pole | HFTD Tier 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004578 | 8eddc616-56e7-495f-bb7d-c5fe14e9b934 | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004579 | f0e1f223-0124-4ccf-bb14-f3bb9f41e348 | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004580 | 6e286861-2fe2-450a-8b00-e5f6fe613bf6 | Pole | HFTD Tier 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004581 | 0e8625a3-c494-412e-836c-1be5916e8639 | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004582 | 5e0722d8-69a2-407c-a314-57a8661cffea | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004583 | 2372f5c2-cc0a-49e6-ab1c-2dd7fcfc068f | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004584 | 9de101a5-29f0-4ef5-8b1d-7282e3de919a | Pole | HFTD Tier 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004585 | 26765015-9d89-4141-800e-c39046580bad | Pole | HFTD Tier 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004586 | dba0de0b-e910-4ad9-b9e6-2f78914fc9ae | Pole | HFTD Tier 2 | Transmission | 2022-03-07 | 2023-03-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004587 | c00c60ce-8573-4a4d-ba19-025391d89fbe | Pole | HFTD Tier 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004588 | 61ca8aa9-9f93-4772-b94a-3ed5add449ce | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004589 | 52b3bb82-a148-4fe7-9809-3d3e3af5559a | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004590 | a9167ffc-b364-4904-a8f5-90858cd97fe3 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2023-03-08 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004591 | f835e242-4b66-4e7c-aca2-3697a3f0e3a4 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004592 | 3f0c9acf-3bdb-4b70-b93b-c4aa35120ab6 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004593 | f789fc99-b2a4-4bb9-bac7-c403caed68ae | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004594 | e6c1721f-beb8-44ec-b219-19a1059a8b6d | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004595 | 2f2523e0-7813-45e4-8a58-ef81b4ccec88 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004596 | 8c01093e-fe1e-4abd-af6a-3558a3e369c8 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004597 | 96fda099-61e5-4a65-854a-88b07f5157d5 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004598 | 17c4164c-08cf-44c6-8260-4c22c1d562a8 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004599 | a97070f0-5eb5-4298-9b6c-ebac96bd5688 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004600 | c7fca155-0652-4ee4-aafd-7503a09ce007 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004601 | 061c8eba-3bb4-4ae2-b7f1-8549334a02f6 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004602 | 68836db5-75d8-4aad-a2be-cdcb197bb3e2 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004603 | ed0f6aea-7165-4fff-88d8-f9867587887d | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004604 | c35d1544-aa74-4417-8cdc-e81f255d8238 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004605 | 464b835f-a798-4131-8016-4c214f0e213c | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004606 | 846e663b-edf0-44f5-a7c8-537674ae3985 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004607 | 1df7f79b-a981-42fb-9ac5-455e1dd4b0b0 | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004608 | af0375a9-c7d2-4a90-8acc-34d85a7f13a4 | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004609 | b4476d03-25d1-4434-8c0c-a7902095b7d2 | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004610 | 23537b86-62b8-4250-b35d-034eaa1c1141 | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004611 | e3246536-3dcf-44ef-86b3-5c19328aaaac | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004612 | 605e7139-bc15-4384-80a0-e9de124b5015 | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004613 | 7d05c622-4a5e-4882-a671-a9fd262946b0 | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004614 | 1a7643da-9618-40e6-946a-8c2c2d56714b | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004615 | d113c1ba-623b-49e3-94e8-7bb9c3f45b3f | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004616 | 2372015e-64c0-44b8-82b4-73056cdde97f | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004617 | c20c1f1f-7462-4211-b5fe-e4148c16ef12 | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004618 | e7def9e7-d7af-4c6e-ad1d-d26eb717d698 | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004619 | 025c4b62-5b4b-41ee-9419-e27acc7063a6 | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004620 | 676714d5-68aa-4c9c-976e-ef813cfdd699 | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004621 | a7b864e5-96ad-4fcb-8fe0-2a97a37e631c | Pole | HFTD Tier 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004622 | f13d4655-f3b0-47bb-82d5-09c840a3b9a3 | Pole | HFTD Tier 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004623 | 279d1e14-2627-43da-8c7e-af99443f339f | Pole | HFTD Tier 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004624 | 3715d1fb-91fd-423d-afab-7c8bcae80623 | Pole | Non-HFTD | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004625 | 5bd81093-f232-47fd-af7e-68e5c0bf90d3 | Pole | Non-HFTD | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004626 | 5960d81e-af50-48d2-809b-ae69fa14be13 | Pole | HFTD Tier 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004627 | 4ffc6e7e-0a2e-467f-9c1d-9cf72424c2b4 | Pole | Non-HFTD | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004628 | eee6c825-8770-4f13-9298-273ba7da5e09 | Pole | HFTD Tier 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004629 | 033d17e9-55ab-4c53-818a-49b90ddc6cd6 | Pole | Non-HFTD | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004630 | b5c03242-7eaa-49c0-ae4e-6d9717f62e71 | Pole | Non-HFTD | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004631 | c22e7131-2579-48a3-ab97-aeb489c57316 | Pole | HFTD Tier 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004632 | f5b65d56-f626-44d4-8be2-369d271c7370 | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004633 | ff1e9233-01b3-495b-a602-4c463825dc1c | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004634 | bb7567a0-885b-4452-86d5-374a14e2e18e | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004635 | 94ace622-8c1a-4609-8a33-472cd42734ce | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004636 | e59ccf2e-acb0-4adf-a134-86a8d15c4b63 | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004637 | 4603d0bb-e271-4150-ac04-2241b42f860f | Pole | Non-HFTD | Distribution | 2022-03-14 | 2027-03-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004638 | e0259b07-0c21-497c-b08a-7ed5e2506f97 | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004639 | 5a6ed601-50b4-406f-923c-17ec889eb8d1 | Pole | Non-HFTD | Distribution | 2022-03-14 | 2027-03-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004640 | 1c6a1ff4-0a94-49aa-8583-8f3abe9d7f26 | Pole | HFTD Tier 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004641 | 482bc288-e8b7-4f39-88be-0a7740247e14 | Pole | HFTD Tier 2 | Distribution | 2022-03-15 | 2027-03-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004642 | 0478cc94-0f0e-48fb-9852-d500dc8bcf42 | Pole | HFTD Tier 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004643 | 5c3a802c-4785-4db0-94c5-f154d611ed32 | Pole | HFTD Tier 2 | Distribution | 2022-03-15 | 2027-03-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004644 | 2956fbb8-2b4d-4f3d-8950-2386873a3c59 | Pole | HFTD Tier 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004645 | ba8d0a27-5b02-48eb-9c07-b4b7aec6d00e | Pole | HFTD Tier 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004646 | 95e725ab-d539-4898-959c-e9efb0a6c79b | Pole | Non-HFTD | Distribution | 2022-03-18 | 2027-03-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004647 | 5ea6f806-94d2-45f8-afee-bfc21a9cbf00 | Pole | Non-HFTD | Distribution | 2022-03-18 | 2027-03-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004648 | 42b8af2d-2292-4e20-84f6-bd12843b48a1 | Pole | HFTD Tier 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004649 | c4f945aa-aab0-4a0f-bc6f-4f279b5f19a3 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004650 | a4681f11-8df9-4cab-9864-b15c560da8b8 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004651 | 3b57e49f-aed7-4e4a-88e2-06675e5e4418 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004652 | 9932d08c-9950-4b33-a9ee-87efe222a449 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004653 | 38ca824a-2abc-4ad6-975f-4110e77e4fd9 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004654 | 84ef54bc-3380-4333-a157-497a39da266e | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004655 | 79096de5-208d-4f60-a25b-925873503991 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004656 | af7de0d1-50fd-4fcd-a12a-e7c4a4a54ad7 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004657 | bc49c0ff-57c7-471f-92da-29a03735adc2 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004658 | 9743601d-a563-49a9-b989-53394adbcef1 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004659 | e56b0a19-d77c-434c-90c1-636d57a1142c | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004660 | 68d65041-18be-47ff-a2d8-0f37eb7854f0 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004661 | 48dd83f8-80a8-4950-aeee-27004f83fddb | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004662 | 30a5ebd3-baba-41ee-926c-6ac341664752 | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004663 | 9f148b51-c9aa-4630-bb30-0c5c88046c5e | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004664 | 373bf0b7-ba44-4850-b54c-41ea75be2660 | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004665 | af4e0761-fae5-457c-b4f1-9ec961b0f9ad | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004666 | 828b8419-e97d-445f-a054-db36bc5cfdbe | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004667 | 6b4ae72c-2ea7-4e35-8810-0ffaf2bb1ea1 | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004668 | e3db88c7-f89c-4738-8cdb-81fe55a72999 | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004669 | 1763ee4b-8321-454e-8bfc-b13cc1e079b6 | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004670 | 56166386-a26e-44c9-a6eb-d4262ef2a8d7 | Pole | HFTD Tier 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004671 | 7b5dee18-6d15-4e99-a3ae-8dfdabc965c4 | Pole | HFTD Tier 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004672 | 4acbd570-1d2d-4ffc-8438-a62d218c4ac4 | Pole | HFTD Tier 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004673 | a6bfd5ee-865a-4814-9e0e-1df0e7600bf9 | Pole | HFTD Tier 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004674 | 23774c31-0797-47d4-b0e9-8bdd8bd27e94 | Pole | HFTD Tier 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004675 | 3ff87b0b-e34b-457f-be4a-8695265fc19c | Pole | HFTD Tier 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004676 | ea9b8a76-f067-45f2-b25c-685d63c98253 | Pole | HFTD Tier 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004677 | 67b5eb10-2680-4429-9b60-994e45a85302 | Pole | HFTD Tier 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004678 | 5ca58bf3-0258-484b-bdc3-30ad06f4fdb7 | Pole | HFTD Tier 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004679 | 7e043f09-b91b-4d40-8029-d46cb83e6b84 | Pole | HFTD Tier 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004680 | 6dd3bb92-e7e5-4228-93a7-002478038549 | Pole | HFTD Tier 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004681 | 447ed10d-58ee-48d8-89a5-867fb454245c | Pole | HFTD Tier 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004682 | a2fb0a9c-6906-4fb9-900a-4fac4be7bb0a | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004683 | 53373121-98de-448e-8c85-35b9576a6869 | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004684 | 16c7a8ca-d294-4077-8444-0473df29aca3 | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004685 | 635f9fa8-3766-4c4c-9dbb-8ccf5eb329b5 | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004686 | 02f1711d-c3ca-4a27-9542-6712e192c178 | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004687 | 0a7892d0-e1cc-49fb-88f8-147c3111999c | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004688 | 38b8cda4-4c09-4873-abd9-113c145665bb | Pole | HFTD Tier 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004689 | 6699147a-6673-431d-830b-225a8877bb19 | Pole | HFTD Tier 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004690 | b4884129-3fd9-4d6f-b444-1c305127ca1f | Pole | HFTD Tier 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004691 | 69aaa11c-e5c6-419c-9c55-729a62cd0f23 | Pole | HFTD Tier 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004692 | 11243b97-53ab-4744-a034-24451762a977 | Pole | HFTD Tier 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004693 | 513fd5a0-de8c-41da-9d72-1424d6b94193 | Pole | HFTD Tier 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004694 | 30ebaf39-0ece-440a-9dda-b9718906fa0c | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004695 | 200ff739-41c9-4c5c-b5a6-d450709308b9 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004696 | 2f7fe449-2991-4db1-9ed4-233caefc8f61 | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004697 | a9e1c32c-16e2-4bf6-870f-594a27c27380 | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004698 | 3eba6a40-cc51-4e45-9881-f709b53de4cb | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004699 | 7113c053-0d5e-4b37-ac1a-e0d5289233dd | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004700 | ee0688f6-7625-4b66-8f99-be251eb47300 | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004701 | f9d49df4-00fb-497f-bfbf-417c02838a38 | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004702 | 4c7c8abc-f686-40b3-bd47-59270d8226ca | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004703 | f1796a26-08d3-4992-8b1d-64e4efe52a50 | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004704 | 4e889c56-a03f-4a27-b96d-b61e7750e2e0 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004705 | 7e9a6086-1a1e-4600-b621-64b022f371b6 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004706 | ad30b0b4-deb0-4522-8234-f90c5af20818 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004707 | 9caefccc-45ee-4908-b9b4-6bb22162fda4 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004708 | 0a09f7b4-a52b-4f94-ad95-54c10d0e50f1 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004709 | 8ee6f7c2-e248-4b75-813a-f29ff833a560 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004710 | 33765a7c-2407-42da-af75-23c078fcc578 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004711 | 576433c1-00d5-4142-ab60-574f73f8b481 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004712 | 088d6e8b-8dfc-4af1-8424-a7b20328ee6b | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004713 | f1eab8ff-b0b7-42cd-a2df-61ca5e145a62 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004714 | eb64b061-18b7-4d35-8d61-aa1c863c4a85 | Pole | HFTD Tier 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004715 | b2efeb4d-1763-4ae4-b9dc-f8deff9b794a | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004716 | 843ea2ba-a32b-45e7-b2d4-f9055a18cb86 | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004717 | f09b139c-1fd8-44b1-b6f8-f3886641beaf | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004718 | 3680f66d-8301-4e4c-8077-ed8fe78e3c7d | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004719 | db47ef52-d8ab-4a74-8543-6e9adc9515b8 | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004720 | dae60379-6f06-412c-b840-9ea6044082c9 | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004721 | 3e4d9860-54bc-4284-b86d-482d1087a4cf | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004722 | bed53dd8-e7b2-4f94-a8fc-2fd562ab41b2 | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004723 | 56dcb4a9-f149-4118-94a7-fb0ae769b8bb | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004724 | 82ee6174-3cb0-4c52-afa9-ebd956c2e838 | Pole | HFTD Tier 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004725 | 69ee62c8-ae3c-4c3f-9e09-4154c499eb66 | Pole | HFTD Tier 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004726 | a4eca477-882c-4782-8ea4-8de3006f2571 | Pole | HFTD Tier 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004727 | f8100800-b33b-45ea-932e-630f87eb3779 | Pole | HFTD Tier 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004728 | 3ebe0cbb-27eb-41e0-b609-e6202b6571b0 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004729 | 77da13f2-e51e-4343-84a8-8a2bbd21f480 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004730 | 371f7c92-04ec-4d25-9929-44772f4a543d | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004731 | f3b5b8b5-252a-4bfc-9474-f51b9a84c246 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004732 | 2a75247d-d462-4a28-92d0-6ee95d5eab4f | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004733 | c54573f5-0856-4cf8-88f2-d2c71b3747b9 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004734 | 09f1c01d-3812-4691-a333-c4f67703de98 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004735 | 158ff743-f443-4039-8f3b-147887272a04 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004736 | 80b7baf0-df49-479c-b1be-683135d89104 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004737 | a285c7f0-7141-4cab-b006-5ce892882fef | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004738 | 84b52372-589a-4d67-b45d-6df73a7fe2dd | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004739 | 467f7c03-befd-4a18-ba8f-0168f99f851d | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004740 | 40129d3b-7c9a-4e64-8341-5b5bac0bfe11 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004741 | 8d54dcdf-1a6c-49db-afda-98e99130de1d | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004742 | a9bfb66b-f162-4b34-98b5-7dda4204c231 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004743 | fb204016-655a-44a1-9307-fb449a10c57e | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004744 | 011ec3be-637c-4c53-8455-19bd724131e2 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004745 | 4c41728c-b3e3-48a1-9d54-839cac4e7513 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004746 | 78e82791-ec49-4494-9f03-0e875b4e68b1 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004747 | cd68c314-02ea-47f3-a18d-6f8eebcd2459 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004748 | fc83b659-098c-4bb4-81a2-adb559ab8f89 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004749 | 0433e635-6459-45c2-a96f-dcb378c21e73 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004750 | 4fab5f0d-3051-44dc-85a5-b019491ad3cc | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004751 | 2526366c-7d72-463d-b87a-572826383f6c | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004752 | 8b443ca0-7851-4a81-8ab8-8d63a71b476a | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004753 | f18805e4-d2db-40f3-8e7f-36fa9d0231fd | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004754 | 449a3fd9-6a15-4edb-adef-37eecac70186 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004755 | 80ae8e82-c16f-4a96-9269-1ae027ba6cb8 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004756 | b1aa0da5-f4a9-437c-90d0-ca0a246abe10 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004757 | 31a70705-7cad-4c98-ad1b-346a1a5fa69c | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2023-03-31 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004758 | c8bdab78-0c5b-4209-871e-e9ea2e4e3118 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004759 | ca4720c8-5ed2-4db6-a280-b55370cf589a | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004760 | db67ef23-5606-4962-88af-aa13d23541ee | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004761 | 88780bf0-6e73-41fe-9dff-845115867a46 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004762 | 54ccdac7-65e7-46aa-8772-7ac31e642101 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004763 | 3427a04e-af38-44c7-9dc0-03f25aea0c47 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004764 | 0d818849-b462-47b1-b64b-09034da53661 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004765 | a6325903-5690-4566-a643-a95167b5973d | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004766 | 7ce90122-c092-4e49-bccb-85440ed0b30d | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004767 | 53c60202-2fc4-4d0f-8eb0-64fad0838449 | Pole | HFTD Tier 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004768 | 57298da4-085e-4a72-9192-b84b02d621eb | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004769 | 9517ff8b-70eb-4a79-9c2c-13f5d37f6027 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004770 | 77a734b1-f825-4a0d-bfde-f8fef4f64205 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004771 | 3490a2ae-cf9d-443c-a876-3945b1a2ddd8 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004772 | b419a52d-bd16-45fa-92d9-24da7540126b | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004773 | ce7d0427-8658-41c9-9497-c0adce5ac409 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004774 | aeb3f051-68ce-4d17-b99c-3a30c040d614 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004775 | 771a1a54-c679-4232-8d62-bfebeeeba78c | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004776 | 6753f49f-78be-43e9-b0e1-7ad99d995a72 | Pole | HFTD Tier 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004777 | 66a36bd6-ddf1-4343-8ded-318b84afcc04 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004778 | 11951544-ac09-410e-9b67-787b49f3dfd5 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004779 | b749afa2-f60d-4b16-a6ab-c8c92391fb2b | Pole | HFTD Tier 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004780 | 9d54261b-583d-4de6-9a34-5a3bc96ee7c8 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004781 | c1d3a587-eb86-4aff-8eee-3859a1a8b293 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004782 | 9ddd52ad-27a2-4940-b3bc-9183c21d6be5 | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004783 | 60b388e9-9190-4be4-844d-0f31aed95a7e | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004784 | 70490651-8848-40de-b6b8-6db69485859e | Pole | HFTD Tier 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004785 | 88a46452-182b-40e8-a311-561508acf7cc | Pole | HFTD Tier 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004786 | e707e466-721c-4732-9532-a9f6cc279846 | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004787 | 42416bc3-b0fb-42c1-9961-e231d17186db | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004788 | 6490187f-9bae-4210-ace4-826a81fc03b8 | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004789 | 65aea2c3-65de-49ea-8c7b-da0da71d7c4c | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004790 | 6ddc633d-747c-438e-9737-1ba3a0a6dc06 | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004791 | d34f4cf2-e8c8-456a-8526-104005306e15 | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2023-04-04 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004792 | a514a183-210e-4d3d-9669-be29f8443e5a | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004793 | 536882ae-ee2d-4682-a30f-02f7efdd9622 | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004794 | 3e4167d9-5472-4774-854a-6b53e05d62a5 | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2023-04-04 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004795 | 891c7007-934c-4802-926b-c92f036b54f8 | Pole | HFTD Tier 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004796 | 4b8543b4-81d4-43a2-b8c9-a9d1ba053787 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004797 | 5e98754d-8e65-4817-b4ee-f93d0f3b5073 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004798 | 0ca8a859-b5cb-4f82-b0c5-f891d553eb89 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004799 | 1357eced-8afd-4479-b82c-152944c3f572 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004800 | c8d0333c-1ab8-4836-9766-032e21e4742d | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004801 | a39dd90a-6368-42a5-8bdf-ff9f0348990f | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004802 | 51fcd251-20d2-4d11-8ff0-5e3c30eaad34 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004803 | ef7fea55-987a-43d3-9f22-203f7c6236a6 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004804 | fad86c80-6615-4b44-8b56-5f6200dcffc0 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004805 | c41d3b73-5ace-40ad-8145-f8563c8d2a53 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004806 | c4998d00-7245-4eeb-bb67-208def1546f7 | Pole | HFTD Tier 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004807 | 04f67fff-4a65-4373-bdf0-ff776df5fe0f | Pole | HFTD Tier 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004808 | 0dba6e19-acb0-4b5d-bff5-f55abb94f985 | Pole | HFTD Tier 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004809 | b456e1ce-be9f-47fa-b2f9-6637c376e266 | Pole | HFTD Tier 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004810 | 406e13b0-2310-4f0e-93c3-465097c609c8 | Pole | HFTD Tier 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004811 | 759dd31a-a29e-47a2-acbf-3117e4dd7a3e | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004812 | 41ed7441-2394-478d-8c32-528aa9839a6a | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004813 | ec0e8d41-e7c9-428d-9be6-c293c45c8aa2 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004814 | 06fbe163-02ab-4510-b071-ab68098ccbf1 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004815 | f073a40d-ec75-4bb8-bc0c-bd0bbf1fd031 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004816 | f0a38a97-52b0-471b-ac55-f62e15c3613e | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004817 | 47ab9d43-bf03-4de6-9615-c79cd8e6f57e | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004818 | c3a29af3-8df4-4143-8864-b06a10d0f73e | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004819 | bd59abc6-3dd7-4d8f-9199-94f9be846fb5 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004820 | 3312cced-0c43-47c9-9268-33658a56b4ba | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004821 | ba31ea8c-07c5-4600-a7e5-0892d7adaa56 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004822 | 9dd4116d-078b-42f9-9b94-92ccf7f1ebd0 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004823 | ce61d46f-6e7f-4e8a-96ca-f5e12021aa28 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004824 | 93df7ac3-a101-49e7-a9a0-081db111c960 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004825 | ab44f8dc-89e3-4176-850f-793b3f19f46d | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004826 | 110e256e-ed09-42c0-977b-6ab387d4d360 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004827 | 989d3a22-55d6-4d04-be3e-072a0db3b5ab | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004828 | 7f5d4317-8e59-4210-8d36-86f829a70cf2 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004829 | 5c4e7dde-77b3-4613-a6e6-7e362b1c0e91 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004830 | 7f7458a2-d63f-4f1f-af4b-ead310ce806b | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004831 | 453e5e4a-a4bf-4062-9c16-7154c57a7647 | Pole | HFTD Tier 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004832 | 5f704f5b-9674-49fc-a084-041814e9145b | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004833 | ae8a5b56-5f09-49c5-879f-39a52004dce2 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004834 | 7458865c-ccb2-4f54-82a2-011af5d3522b | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004835 | dbde7c58-9f55-429b-8dd8-d36bb2fe4f06 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004836 | 1c918c01-a2cc-4e59-8a5d-7d05f9392d6a | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004837 | 4d2b8ecc-c3f7-41b2-8868-bda740cad8a8 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004838 | 752f7f4e-4f9c-4523-9d70-effcd4b9fae5 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004839 | f3c25928-8609-4651-a68b-3a65dcf43984 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004840 | cb3882a6-06d2-41ea-bad7-9ba7027598e6 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004841 | 31144e21-548e-437a-96b7-e0e1a0ca98f3 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004842 | 893d438e-38da-4a1c-8277-df8c921f331a | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004843 | a9077e38-0a8a-4f05-bb09-d2e748847190 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004844 | 6a56aa29-5d24-4179-ab69-2d8a5118ae4e | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004845 | 92ebab34-88d2-4e0e-af9f-1a54dee52310 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004846 | b18ac578-5674-49dd-a472-13aa899aedef | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004847 | 50b30623-87c5-49eb-826b-7fe81ce79572 | Pole | HFTD Tier 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004848 | 7f9f2bf2-b36a-4093-8a23-d04f9dc0d04d | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004849 | 5da1ffe8-e13c-4e1b-8d84-4f24e9a59222 | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004850 | cc00849c-8eb3-40fd-a6e7-ed38b13486ba | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004851 | 54b8461e-4806-4f58-bfa3-70ed626e1606 | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004852 | 1544ccbe-fbcc-477a-b0e7-85f33f0a08cb | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004853 | 25ff992f-3184-4b34-9463-ea896bb6ce19 | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004854 | fb2d214e-b91d-435f-9f3b-e2b0845207e1 | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004855 | ac825b42-2f9f-494f-8b6d-f2c0fbd2529e | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004856 | b4b229c7-0dd0-4a81-ae1b-3a1b4db8ba28 | Pole | HFTD Tier 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004857 | 802ae38c-43be-4b1e-80ae-be0a03e89114 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004858 | a0e8e8b4-792d-481e-aff5-af88c1ab75b6 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004859 | fcfb005b-5af5-44af-99dc-1f9859caa707 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004860 | 0f60ef12-9527-408a-a304-d1cd7f4d30b2 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004861 | 969808e2-e63f-4c96-8cad-34e50ca2ecc0 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004862 | 67c6b4e4-4d9c-456d-9889-c87907659f09 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004863 | 0a66d65a-3fa9-421a-a1f7-65d9dac49469 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004864 | 497d4a24-b574-49c4-b47b-d04eb2b34f0c | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004865 | 926910b6-22b4-4d03-8804-2453d9bf325e | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004866 | c335708a-9c1c-4f52-bf0a-372951cf6e28 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004867 | fee81b88-0170-40b1-ac9a-c7c944a7aa14 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004868 | ccbbf5d6-424a-4913-b12b-3ce684553850 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004869 | 4771aac8-e424-4297-a657-bb9d8165da26 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004870 | 51d941da-1ea2-4b06-b1cf-ec2c7b918d12 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004871 | 344dcb0b-06e1-412a-91e2-0174a804f168 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004872 | 089da26f-0a22-4ca1-a226-62a94e2cc3a9 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004873 | c3e0a445-ba3d-4db1-a5b6-2b7f678cdbf5 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004874 | 539206c6-785c-4360-a057-97571eb7e5e3 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004875 | 9441e91c-7b1d-4fae-8a31-5204036dc095 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004876 | ec7f82f8-4b5e-4598-9456-79c5cdfb747d | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004877 | 0255c325-77ac-4d86-bd16-8bfcf45f9eef | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004878 | f435a7b8-06f2-4b6b-9fdf-8eb65f08c292 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004879 | 91263e8a-96e5-4cef-a764-64a1dc400f17 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004880 | 69c465b0-603c-49e9-9907-7b1bf9244dbb | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004881 | e3342162-d6f8-46bc-b0ba-219d23c2d252 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004882 | a05159f4-3bdb-4c11-a05d-1e6c4436e9f4 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004883 | 04033804-b4c3-4d80-830b-a7a95b8a0527 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004884 | a1423266-f9b5-4b7d-8b63-98d7000c94dd | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004885 | c5fc0e98-f616-40d7-b78e-acd718d8ce1d | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004886 | 85c234cd-3fb1-428f-9e56-78e3f210c822 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004887 | 6cc8fef2-8517-4e54-a02f-d6c447c29159 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004888 | 8c5cb3bc-b7b1-47b7-9657-3e2f254bdcfe | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004889 | 9b7fa005-09f1-4e72-8f0e-2bb4c688d2a6 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004890 | 15a8510e-5caf-4f94-9c84-c23352144894 | Pole | HFTD Tier 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004891 | 2e3e75b5-cb8e-44b1-8231-10e37d7be6c1 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004892 | 43605e97-3ece-477a-b27e-5858505b3b50 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004893 | 37ced4df-2357-4c0d-b9bd-ac2b485fd4df | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004894 | 2303c569-23d0-4e2b-b11b-dc1230aac3f1 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004895 | 1b946904-148b-4bdf-bc48-70d5ea50b3db | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004896 | 6caa2c64-cc49-40f9-9e73-38d20bafa34f | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004897 | 46d1fafb-47ef-4b24-be4d-2d611d53b42f | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004898 | 38bfc3a2-e04e-48d1-86cc-97d661b1b849 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004899 | 95ade939-2538-4008-a08a-a823d6d34b66 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004900 | 74d9f9d2-5c33-48fc-98f1-f7de4db96d26 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004901 | 95aadd0c-83fe-45a7-a906-9627397d36a0 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004902 | a7978a0b-a636-40ac-a42b-2b214aee9077 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004903 | 543fd334-c0c7-4361-9569-153ef40dce9d | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004904 | 5d7d532b-9cac-49b0-85b7-43685b3ce849 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004905 | b8a3c1c3-60dc-49ee-8451-c633fa64a3a4 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004906 | 407180b4-8080-4c0f-a1c5-5c48ee428a7f | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004907 | 5149607e-d663-4d92-aeea-0b0e5e11edc0 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004908 | 58b1dc1a-2f93-45e5-a588-25d0000094be | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004909 | 4daae178-c498-4952-973e-9e2ca33f41f5 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004910 | 0cb11de0-c940-4107-85a0-a362719d60c1 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004911 | d670ffb7-afd5-4a68-983c-14c8a5e8e42f | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004912 | eccfd6d8-acf6-4758-a83c-65180e565fb4 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004913 | 3519c253-e12f-425c-9bd3-f0f540b08283 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004914 | 46fa10f8-a381-4ff6-bf27-65ad50a860fc | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004915 | b08889ee-cab6-4d1f-9820-0cbb0b6c1890 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004916 | d118a864-2860-4ba7-ba06-8da6829be47f | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004917 | a1d4f08a-129a-452f-9c9a-9d8b7e8e747c | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004918 | 7de8a9a8-846b-4e38-96e9-a4952b78d819 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004919 | 7cb83437-f6e7-4e3b-9150-24b9dff21a2f | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004920 | 5f9f2e8d-c191-46df-bda3-118d3523d4a2 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004921 | 22b5057e-3d76-4c55-8b83-048e78ea29a6 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004922 | 98219143-1471-4aaa-a415-ba60d1b34d14 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004923 | 3b25ab8d-845a-4f13-823a-e24707d3e252 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004924 | b0578be8-ff41-49f0-ba78-8b5266a06dee | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004925 | 8739f452-dbb5-4f7e-9b92-be33290ec8c0 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004926 | 34188dce-9593-4da6-a8d3-a23c78bdd2e5 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004927 | c117febe-713a-4a78-9ee8-5730bd8cd8ac | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004928 | eaf92ed2-82d7-4d73-926f-43b6498137f3 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004929 | a696cbf6-2311-4295-bb81-6ca5690ad502 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004930 | e51699d1-2083-41bf-969d-ab7f570dc789 | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004931 | 63639052-7d8a-4148-ba18-da2636ec976a | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004932 | 53e22257-d863-45aa-be5a-4b9ffeb2db7c | Pole | HFTD Tier 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004933 | 0bd4c211-2fa0-4ffc-a3a3-bcded4f6b868 | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004934 | e327c1cb-1cd4-4877-b74e-782d514eb4b8 | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004935 | 1b308e41-8eef-4f01-8695-2f778faf43f6 | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004936 | 4d7fbda5-e43c-46a5-b778-4afc68793f4f | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004937 | b332e4f1-6cde-41b0-86f4-7d0b268d74ce | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004938 | 84533a32-7b4d-4dc8-ae99-e970c426cddc | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004939 | 52403095-c006-4df4-bda1-0ef42303f754 | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2023-04-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004940 | 254b66a1-7352-4c51-9f61-8cac67d87333 | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004941 | 9406777b-4441-440a-9a39-08327bd49676 | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004942 | 98a38247-b04c-4ac1-a41a-1562fd198823 | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004943 | 56cf1067-2051-4971-8821-6c9641dd1a41 | Pole | HFTD Tier 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004944 | ab279528-8f1a-4ad8-b7c8-fea9d47704e1 | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004945 | 6cba7a52-ab89-45a4-94ad-9102f1a5e49e | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004946 | d091772c-f9c9-4cef-894a-56c98ff09b58 | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | 2023-04-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004947 | e05502a5-09c8-4f79-996c-f04ee625a61f | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004948 | 180dddd5-3a08-4127-80af-d0a2337d7d6e | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004949 | 56868fd5-9ff0-4f89-82d4-7be7a56e6942 | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004950 | 4e1d73d7-3d14-4f6a-9218-bfd869079ee8 | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004951 | 9772a723-2f64-42e1-8cc0-5f1f82b1178e | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004952 | 78d1ccd9-3911-4bd2-9c00-40f31eb4a38a | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004953 | 3abac912-64b6-4103-aabb-354e2cb0dae2 | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004954 | e7870a9e-d735-4842-a675-f0b52c9d1bc8 | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004955 | 97873176-0c76-4b9b-9c10-0f7645ee7bfb | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004956 | bc9af2ee-8b89-4018-b278-d05b9f6c55db | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004957 | 273ba082-00f7-4349-a975-b4e9df59307e | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004958 | a73c2a3c-debb-483e-b3a2-a01985a052e9 | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004959 | e0dc8417-b16e-4bff-b3d4-49214f604e2f | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004960 | db9b0309-2e8b-42ab-86d3-196ba68add20 | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004961 | 79a0ecdf-3fd3-4e45-8e16-323b372112cc | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004962 | f1b338dd-4222-4fb4-917c-e7faec94a149 | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004963 | a5ef761c-4fdf-43a0-95e4-cacbc7df56e4 | Pole | HFTD Tier 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004964 | 58bfd453-3669-4847-8464-c3906ea0539b | Pole | HFTD Tier 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004965 | b41acc02-a3cb-4116-bbe4-ed092a439a81 | Pole | HFTD Tier 2 | Distribution | 2022-04-21 | 2023-04-21 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004966 | 21cc9ccd-84a4-4e94-b033-832ca5e79404 | Pole | HFTD Tier 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004967 | af2931f1-1663-45ca-9442-79950f592897 | Pole | HFTD Tier 2 | Distribution | 2022-04-21 | 2023-04-21 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004968 | ee281a7a-954e-4279-8d5f-e3d4cdd508b5 | Pole | HFTD Tier 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004969 | 6dd093d7-4d98-417b-8966-989557e8e47a | Pole | HFTD Tier 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004970 | 0cdaa5f0-aa98-4c2f-a7d5-d704aec50ed6 | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004971 | 044cc782-1ed1-4432-9585-6b85bb948fbf | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004972 | 54c6c5c7-af47-4c91-92b2-813046992f50 | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004973 | 39247234-a6cf-497a-8401-46673d79b298 | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004974 | 23bd6e0d-7625-4a8e-a9f1-8b199e2a657c | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004975 | c48b42c7-d669-4c37-98ad-fe93558dfe71 | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004976 | 2a27cfc0-721c-433a-9041-b5969624522f | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004977 | 29b603ab-ec6d-44a9-8b96-6b949b6492d5 | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004978 | e79d5f6f-bec2-4403-b983-9f2af8015a75 | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004979 | 645df035-6d32-4acc-9e66-2e458f1374a3 | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004980 | a551285b-18dd-46b8-9be5-6324e3b5fb18 | Pole | HFTD Tier 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004981 | 51b1eadd-a6ed-4bb3-be36-c36e88e52843 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004982 | 502368bb-6d99-4105-bda3-8490f7be749e | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004983 | 2f243988-2fa6-48d8-abe0-8492a97c81c5 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004984 | 777597b1-ae99-42ef-8558-8ba002ddc946 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004985 | a7685d84-109d-4a27-b5ca-1deecf092af3 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004986 | 2406f9f3-e6fe-47e2-ae4a-d7416dd2b1c4 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004987 | 5d1cdcf7-cf77-4d35-ae7c-f4eabca8e997 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004988 | a008d37d-0cbd-4ee2-97f5-2d20d394eafb | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2023-04-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130004989 | 3dbebf98-ac14-4bee-9c02-e676adaf0872 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004990 | ef4075bd-e271-46ab-8913-3db49c6b78fb | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004991 | 0abf462f-4a89-4ad1-93a1-5c809be35dfa | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004992 | 31905159-7ab1-429b-8efc-06ae07dee55d | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004993 | 16a33b52-5c49-4a86-91c8-2c426afc256a | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004994 | 7df8c0c0-5b6a-4bd5-80e8-b7f7a98175c1 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004995 | 77b6f8ca-e4a6-4ef8-8e44-f9036fe953a1 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004996 | 04a9d646-9efd-4061-a678-7db7600e449a | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004997 | b54999a0-3cfd-4075-95d7-bc9c75a9d4f2 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004998 | 8015a689-bd64-48c2-a191-5a0f687408d8 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130004999 | d3e0b15a-ce35-4a71-811f-da58dc85a696 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005000 | 8bea342d-0196-48de-9f71-45cb08c431d5 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005001 | 710d83bb-840c-4a36-86a3-5a843c89ee4d | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005002 | 9639183e-8204-41fb-88ed-13a524577e27 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005003 | c65a0758-fb70-4012-8743-352dfe10f458 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005004 | c6a44c2d-b649-4509-ac88-16dff9f42731 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005005 | eab6a9b3-f84e-46ef-9457-61187b254332 | Pole | HFTD Tier 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005006 | 6a43f961-bb20-4849-907f-14538694b5e4 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005007 | 50bec5c4-71e5-4185-bf79-5361312f15b8 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005008 | 589ef09d-4c69-46b4-bd8e-274ab38f46bb | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005009 | 834a7a1e-47f1-41e2-b4e1-40aacdb85f78 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005010 | 0367aa0d-f46a-432e-959b-d3859b0a17bb | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005011 | 40f404f7-dc72-4dc7-8d67-686cfe847e3c | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005012 | d60e3007-fc96-476a-9381-ad3643717c56 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005013 | 038f91bd-8454-46a2-ae8a-e4908d660e69 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005014 | 9d29eb7a-6ea7-44e4-8ed6-023beb64f8d9 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005015 | 069ed871-507e-4c1e-846d-c92cc464c1c1 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005016 | f4a4f0d8-bb92-4f64-b3e3-79cd6479c452 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005017 | 7bfc2379-96f5-4571-8714-afb7ee873d07 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005018 | 07d834e7-8f2b-49bc-87d1-27a6fd4dc5a4 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005019 | cd37d0b4-ddbf-4d47-b6ad-43d58fdfce36 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005020 | 41b66920-69dd-48f1-b4b4-98ddbc999562 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005021 | ae7f8db5-b9c1-414b-91ed-49c90a051ce9 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005022 | fb283363-5592-4be7-9764-10b624714f82 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005023 | 758e15ff-a633-4495-b376-8b9a44799092 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005024 | 663f2b28-a649-46ef-ae1f-4bf5ae717110 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005025 | 07bfed0e-c746-4c8f-917a-4248316c2af2 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005026 | 01d92645-4777-4f1d-b242-0334b457dfb2 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005027 | 72b0d48b-eb88-4c83-9be2-ae4576358aea | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005028 | 0833051c-b789-492d-9806-12e8358f4344 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005029 | 17de24c2-dfd4-4fd5-98c5-57ccb2182bb5 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005030 | 61e83759-0271-443d-abff-525b6fd7e48c | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005031 | ef23f2bd-81ca-4be9-8160-d13efa8306c7 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005032 | e4499eb4-909f-47c5-bc44-525058e7f990 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005033 | beb398ae-2ae3-4eca-9999-c9c5570f9792 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005034 | b2606c75-08ed-491d-87b4-5d9f1cbfcce7 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005035 | 8ea913ab-45b6-42fb-afbe-cf977650b049 | Pole | HFTD Tier 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005036 | 0318d11f-2f87-450a-b603-43d888a89f72 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005037 | 8250d725-cc01-43cc-8f23-3254f0e72d0e | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005038 | 26768c99-8868-4ec8-b111-d76c648afdfb | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005039 | 3636c18b-c058-4485-8039-e34bec8cba11 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005040 | 212cb912-e24e-4343-bd3e-bfc6145ffcb9 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005041 | b6937104-4532-4756-93bf-b225d7135eb6 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005042 | b5780f2f-838e-4fdf-8b5d-df06ce8e5484 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005043 | 8eb424bf-e1e1-463f-9772-2cca597d3be0 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005044 | 54f86c39-892e-46d8-941c-f9ade22d4870 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005045 | 1fd43ccd-e5e4-4e3e-87df-4397fee6dc37 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005046 | d366d640-46a0-4f93-9247-7c19cb93fcbf | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005047 | 6ebf55f6-3536-4e8f-8754-927eaad90ecc | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005048 | 8b9d1e14-ace4-4f85-aba7-b989505dd28c | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005049 | b5ca188e-f899-4b0a-96de-c11d5246f427 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005050 | a985b574-9cde-45f0-8a41-e914321f1b1c | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005051 | cb5945f0-9be0-45d6-8bfe-5bd12f4dd4af | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005052 | 0a0bacef-9fc4-499e-8558-647fd2c0be1f | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005053 | 564a106d-0ae7-4e5d-aa4c-e1fb43ea2901 | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005054 | 8301bf99-a3a6-4415-82a0-5ad16bd85f1e | Pole | HFTD Tier 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005055 | 3aa036e9-1a77-4653-aa81-42b481a56beb | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005056 | 27e3db0d-9a6e-4c92-bdcb-60af8abe9e3d | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005057 | 198dbe61-54ae-406a-ac56-24a2c8805765 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005058 | fd946841-35c6-41e7-a1f7-55e477a766da | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005059 | e1c833bf-37ca-4e04-8d08-70a7ebee73b6 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005060 | 929101b3-b50a-4d44-84be-00e737994858 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005061 | 16a39b9b-e032-4f6a-a032-aa2a246c387c | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005062 | 3405dcee-99a7-426f-8fd8-bed4543525e9 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005063 | 0dda6f65-eb19-40b6-b945-4fd6ca182da7 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005064 | 4898f1f9-ca92-4abd-a39a-56c31bca5fcd | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005065 | 3f2d58af-39fd-41f0-bc76-431a4b0f6fce | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005066 | 2617f26d-02ce-4ab6-8fd0-91eff4d3c449 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005067 | 77e090c7-9e60-4cf1-a15d-ea403e60a9fd | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005068 | 17a215a7-a6cb-425c-9e29-130efbaf6fe5 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005069 | 89271cb7-de87-400b-b17a-4c0701d14603 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005070 | 82f7a0e2-0728-42d9-a38c-f0b89ecbc160 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005071 | 5e5568b1-4fd2-4063-89bf-358efa693e7f | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005072 | f0d50760-95a9-4cc3-a86f-8c427405f517 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005073 | a40b1cfd-b0af-4f5a-a559-507feb57f89a | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005074 | ec81eb58-86e6-4ebf-a94e-aa7e70ab80c8 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005075 | fdb9518d-3c84-4bbc-b469-0f43993ffffd | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005076 | 0234498d-ad8e-4b40-8afe-c0b403f2ac8b | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005077 | d6ab7c48-9bab-4fbe-9b4d-9d860a9c2e0c | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005078 | 5e027456-795e-4b81-a8d0-86d8c146ea5a | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005079 | 33a55016-349e-41fc-a0c6-e49767add75e | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005080 | 341b548c-ae42-4302-9ae5-3897ce9f0680 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005081 | e6494aea-47fa-482d-8648-15ab5747b169 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005082 | e1bc60cd-916d-4277-a384-2de9ebc1cd81 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005083 | 7aa47c82-9e5f-4760-8cf5-15e50e48708e | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005084 | da380639-a5b4-4d9d-a9c1-5cf6b88927ce | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005085 | 9349ea89-26e4-455b-9bd8-3d9f11f2317e | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005086 | 5bcb458e-9e6d-408c-a2be-98e3b88b0ec9 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005087 | bff92b25-2566-489f-a195-93767608bd67 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005088 | 8fa52884-10f0-4eb6-86ee-aa719caf9619 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005089 | 5f92a481-35f9-4857-b3f2-eb108755e8fc | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005090 | e203f001-da55-4f5c-8a55-2da7a8b35868 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005091 | a4fe59d9-672f-4c29-a3e8-738250b92127 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005092 | 246b2e48-94f1-4411-8a1c-d06c04444f16 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005093 | 594dd444-ca51-40d6-81a4-94385fd0dacf | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005094 | 24146a7b-51ee-4e81-931f-e2fd66909a79 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005095 | 1536684a-211c-40db-9af6-4199a916d950 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005096 | 1761b84e-f0c6-4206-ae56-3e9464a42f90 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005097 | 72db2865-e80d-4dad-898b-f9c98b309b2f | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005098 | 3d8bd53d-c6b2-49ae-b822-850928f81956 | Pole | HFTD Tier 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005099 | df68ef83-7e79-4448-be29-50a71572d360 | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005100 | a505d7a8-f7cd-4f25-a549-362868951d27 | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005101 | e2095962-bdf5-4afe-8797-0233055b99e8 | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005102 | 318c7b46-e673-4d1c-b4cd-7f033c31d376 | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005103 | 0c8e7d8e-9899-4ba7-9984-e99feba3ad6f | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005104 | ca695a36-c0f7-49e5-92eb-87e275d4e714 | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005105 | 6b025a29-d9b0-45eb-8b6a-ceb7dc88b186 | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005106 | 4e8d5dc1-856f-4046-805e-8a954648c489 | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005107 | 68ebfe06-637e-4f88-896d-96645b530d1b | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005108 | 7c473661-9e38-41b1-abcc-a26a97e1d21d | Pole | HFTD Tier 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005109 | 77182ab3-77f5-498f-beb5-85cc3deb90e0 | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005110 | 228d2cb7-d7a6-4a36-a73a-283efe271485 | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005111 | 076d4ef7-a837-4601-946a-029bef5e14ba | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005112 | 89cf2416-36ec-48b1-bb4c-9052cb4369fd | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005113 | bd894413-e933-4360-912d-a32f8fea01d7 | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005114 | 6c05f3e6-37bf-4168-b966-e1438fc2d73a | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005115 | eacb7d9c-4cba-425d-bed3-504356e99776 | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005116 | d7eb3ac1-6b18-4425-9cdd-373363321ecb | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005117 | d8032f20-9dea-48b3-914d-27c54b7f6925 | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005118 | e52e8fe8-90d7-45f9-b80f-3df0403efeb3 | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005119 | 8a7b2d40-9237-4655-a519-21efd6f22c7d | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005120 | a203d871-6590-4aec-8e96-ef991e36f81c | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005121 | 0c6f7350-a4ea-45fa-ab22-370ebbee41e7 | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005122 | 61173988-c7b1-48ad-b17a-2d1497dceaa6 | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005123 | 48518f1d-2595-40b5-8924-6b742fdcb17d | Pole | HFTD Tier 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005124 | 2d0208ab-1bdd-4532-a626-e644f08d8c7e | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005125 | 48c01278-af28-44e5-a26b-dd1d010abdf0 | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005126 | 34f2c261-e464-4c56-be2f-3610ddae6394 | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005127 | bf380df4-2c23-4518-80c6-9a6a4fb159d6 | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005128 | eddc312f-48a3-4918-837c-2a59bb177e38 | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005129 | 26e12f30-e2cf-4a51-ae6e-051856c267e4 | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005130 | b97f01d5-fa57-44cb-815b-daac957d9caf | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005131 | 92155074-1e9f-4f27-933a-53155c709102 | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005132 | a153e5b7-67ad-4956-af3f-21da2c6992aa | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005133 | 0f3a120b-7446-4255-8ec7-6c7f193af38e | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005134 | ad92c3c1-1c63-48c8-8684-e93fb0e004a2 | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005135 | 2dcec391-80df-4f4f-ad23-090ea3738b4f | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005136 | 7814f53c-c373-417c-a2d2-629c3ac77954 | Pole | HFTD Tier 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005137 | 500167d1-0ff0-4bba-bea2-7a5a742042af | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005138 | 723a343f-4e51-4bf7-a265-9242d90af7b1 | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005139 | 8c54cc1f-12be-43df-becf-bc441ce52540 | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005140 | ec320cce-d1a4-414b-957f-415718a43756 | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005141 | 13336123-cfb2-4bd8-81e7-16fbb24084fa | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005142 | 0d3a0903-4db9-4957-9ba4-337edfac3076 | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005143 | 5a163363-d9be-49d5-81cb-72b428b16110 | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005144 | df73a8da-26a1-42cf-98f3-2ee96cc3c1e9 | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005145 | 838dce41-ca2d-4d97-a272-98ca91f47122 | Pole | HFTD Tier 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005146 | e7e3c85a-f8db-45d5-8aec-09f48a3bb715 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005147 | f446b843-8afd-416b-821b-2148b5ec5c88 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005148 | 4392d768-0901-4ca6-9d77-2ed47f7efb4b | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005149 | b5f26494-e562-47e3-a3bc-d18e02851bef | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005150 | 026d47dc-553a-4ff9-a20f-23e44e64751b | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005151 | b605ea32-f156-4465-8b97-a49162316d92 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005152 | fe002313-099b-4a80-ac35-3a3fc9088b7c | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005153 | 5a5a41fb-162a-435d-937e-1b032e906c4c | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005154 | 0b1e0fe6-1291-41a8-9a1d-861417c02db4 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005155 | ad25fa49-2bb6-4179-8eda-e9ac9f8493ff | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005156 | 2737454e-4260-49eb-8111-875df1cb3b21 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005157 | 7f8d2fde-1755-4d97-91f0-eeb4f092bf32 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005158 | 866b2edb-b250-4424-96b6-c3b86a0976b8 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005159 | b0e440c5-168e-4668-8c38-693f00bd2aa7 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005160 | 352cd739-a6b4-4fb3-8e36-c3e93f22bb63 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005161 | 810f9668-2368-4863-98eb-093f7cf724fa | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005162 | 3ae6c5d3-c414-424d-a062-5333682d7029 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005163 | 8b29ee0d-724e-40bb-ba29-ac0ebe8559a9 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005164 | 93ada3f8-e853-4787-a2ed-f0b7870cd766 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005165 | fe2e481d-f037-4f69-82f4-c7a5c959308c | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005166 | 8a5a4df7-ccbc-4fe1-a564-d7c289f777c1 | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005167 | f13f49c2-aba6-4985-9435-eb679b8dad4a | Pole | HFTD Tier 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005168 | 9ea2fde5-4db6-4f90-a51b-174fcdb5e656 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2023-05-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005169 | 90783e95-7e39-4992-b4f8-71b3128a9482 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005170 | 63057f2e-0863-47c1-8d75-4a0eebe620af | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005171 | 1ccc9596-f125-47b2-ab94-951452106206 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005172 | e22f244a-0041-4546-b830-e561007ff366 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005173 | 56b1a033-198d-4bc1-a07f-0eb32b0ed58b | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005174 | ee2fd42a-3d23-4a9a-a0aa-58202834ac50 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005175 | a5003db8-217d-4336-9f3f-db97e213fea6 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005176 | a42f0493-0684-486d-8333-e2289e0c3161 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005177 | bf0aa8b5-a941-4939-a381-93910f7fc02e | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005178 | f5781dcd-e01d-40c4-b100-2d9f63e273a9 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005179 | f70d9920-31e0-487a-81d1-9d74e638dfb4 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005180 | 900da43b-04a7-45ae-81d1-de5f0af9f3b6 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005181 | dabed6aa-f8f0-4745-9501-28e7e84dcf8f | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005182 | dd6e61f7-a06b-466b-997a-a0a8649f4e58 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005183 | 30ac2746-26bb-46c5-87c6-acf4c25fb429 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005184 | f4506190-281a-465d-9d46-fd99a42d869f | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005185 | b6dded03-7c16-42f9-a8b5-82641a92bef8 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005186 | ec391e67-c3be-43a3-aec4-a087563f7ff6 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005187 | 73c34230-7354-4775-8ee6-23a6e3fa1583 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005188 | 108d34d8-4517-448c-be2a-1186078e302d | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005189 | 547a0952-2197-4b32-9bbb-36d7249a625e | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005190 | 4c453254-238b-4546-802a-dc8ebee7a6c9 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005191 | 0678f8a2-b3eb-4de3-8787-e17649350717 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005192 | e517c7dc-17cf-4c9b-8014-32d596d7b441 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005193 | 3fec7da1-48ae-4ce1-883c-83dd0f972d9a | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005194 | a3b2fc8a-8493-41d0-b4d3-8e0d75d04f29 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005195 | 99456af3-f563-4a5f-b6ae-8832e8654d17 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005196 | ab67e711-e865-4782-bd62-2d367eb475cb | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005197 | 2c011b87-f707-4c13-b9dc-4bfc441020af | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005198 | 41947854-6932-4f22-b900-f1f6a97a7688 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005199 | 7e35ce2a-9bd4-47f5-8e97-f4fedfda30ab | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005200 | 6ae0df42-bf1c-4842-83d3-fcb69c7acece | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005201 | cf9c32c9-ead5-430c-a5b3-d98b54e04c52 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005202 | edc9c05c-0227-461b-8f01-842471a3381d | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005203 | 61bcc74d-e717-4103-883b-297b3173ed70 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005204 | 3d9dac08-5e73-428a-9723-b3bcc0600b01 | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005205 | 33b79351-792d-4d2d-835b-6d7d670c416d | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005206 | 78d3cfd8-53ce-4ff8-bf20-fe77d7eae1e8 | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005207 | 220a05b6-c830-4ef5-a6da-fa4170b7b94f | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005208 | 972e7dbc-c100-486b-8177-670cb2803156 | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005209 | 32c6b6d6-cb5f-407c-878d-0985e5c5acc0 | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005210 | e9ae9ee6-2fc5-4b44-9733-cd5cfb8bb0d9 | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005211 | 7dc01b1c-02f4-4d88-ac33-1e5c9abc506b | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005212 | be154a97-5b53-4013-9a8e-4b8643bf52bf | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005213 | 505e633f-bce3-47aa-85fc-1234122e8ba7 | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005214 | 13100467-81e8-4d66-aa0b-f423075276be | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005215 | 9ed43638-b9d3-47f7-8d2b-087c225373ad | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005216 | 294674d8-d9f4-4e88-8461-86d97e46f4bb | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005217 | 49fb5ba0-64c5-4e38-b0f5-2a8c899d902f | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005218 | 6629aca7-8fd5-4d3e-a714-eee9437ad511 | Pole | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005219 | f724d32f-943c-4cdc-9711-87ce46c7939b | Pole | HFTD Tier 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005220 | 8fd1d9c4-bf77-49e7-9abf-b1012c4672fb | Pole | HFTD Tier 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005221 | 0204041b-1a77-41c7-9247-42c3b34be7aa | Pole | HFTD Tier 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005222 | 256b66b1-2ddb-43cb-ad76-83810c9f160e | Pole | HFTD Tier 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005223 | 194dc582-a29f-4dbc-a317-91b32acef012 | Pole | HFTD Tier 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005224 | 38683f2a-5adb-440c-a1c2-81f1288d9be0 | Pole | HFTD Tier 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005225 | d5aae43c-3c1e-4043-88d8-def61824f9db | Pole | HFTD Tier 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005226 | fa40f187-c389-41f5-9127-aa22ca5bfa94 | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005227 | afaad66e-9a9a-4bf5-afc2-7ee64c669dbb | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005228 | d833749e-0c56-48ca-a0fb-7beff27afedc | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005229 | f60dc076-11b1-4df4-b652-af532aea360c | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005230 | 637599e0-ec51-4add-9d1a-42663680cb5b | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005231 | b3bf5bcd-09cb-418d-9e4b-aa111694b225 | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005232 | 4f2a3573-f2d9-4ff3-b2a5-afe6de78150a | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005233 | e84f7c0b-e5e0-41ac-891a-c728f3990d34 | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005234 | d773336f-c1b1-4778-94e1-b32fa1bd9a10 | Pole | HFTD Tier 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005235 | 396e1662-d2d0-4286-95fc-d376b2e62559 | Pole | HFTD Tier 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005236 | d4ce3d9c-87c4-4ca5-8d17-dc551a99da55 | Pole | HFTD Tier 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005237 | 1ef8c973-b823-4a2f-a5d2-e06b849c4a90 | Pole | HFTD Tier 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005238 | 06da5821-f246-4f7d-9c6f-752a68a848f1 | Pole | HFTD Tier 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005239 | db5f8dc4-33e8-41e9-bb0f-0ad577f75c62 | Pole | HFTD Tier 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005240 | 47c89d3f-4265-4127-bae6-7ac6891e3a39 | Pole | HFTD Tier 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005241 | 9d666eb6-1b72-4bbd-ad54-88d2094f5c34 | Pole | HFTD Tier 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005242 | ccf999ef-e5d5-4a6d-9874-66232e53efb9 | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005243 | 5a6e5bd4-88bd-441a-a0ce-17c749ae2ce3 | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005244 | 519b67dd-89ac-4b6f-94f8-6e3f24d8e250 | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005245 | 1159c80e-4c3b-45d0-bba4-21f8f8f4d773 | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005246 | 6d6c1649-9610-420f-a93d-da286d9a99bc | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005247 | 9557e282-8f9d-4a1c-9f17-3c7931ec364d | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005248 | 22589855-1772-4d68-85af-91b3e958f9df | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005249 | 237dad7d-48a8-460e-8c48-89b67321a2aa | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005250 | e2c3e5e5-b4db-4e9b-b384-c3a5d7977276 | Pole | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005251 | cf4b55c9-5aba-43ca-b132-d30426043996 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005252 | 2b8bd0da-72b9-4866-a727-2242c6f6e6e6 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005253 | 8b93c3a2-edd4-44c4-bae6-07877af99f1e | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005254 | 62a80d46-8938-4e92-90dc-5cf6e3998b80 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005255 | c162c34b-39f3-4869-af08-224f7af9fee9 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005256 | f589bd31-b3c8-4344-ae97-b49df98d8913 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005257 | 97df6be5-a6ed-4314-abb9-e8e2e1270fa0 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005258 | a6ce0b2e-ac23-4aaf-a34b-558ac239c1f7 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005259 | 078072b0-71f3-49ad-bbfe-bf824f9b3cbf | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005260 | 876a7730-77be-4090-bc98-50db532e4141 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005261 | 1070bec3-2966-4e39-8354-b72b3d08757f | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005262 | 8346f35e-f234-47aa-9434-a2116b44bb26 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005263 | 6e168b59-7a0b-4bba-a899-81f7a92ad7f6 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005264 | f016d9cd-42e8-402d-9607-a374b1a1eacb | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005265 | 219e7cd2-12ca-4b13-a8b7-8621badafdeb | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005266 | 714a5bcf-804b-4038-a5d5-352eb694ab5e | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005267 | 76feba2b-2651-4f98-8bb7-bd8a7faa8b1f | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005268 | f2d4e6dc-2309-449c-b1a2-c556636c8fa4 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005269 | 4b62cb6e-b2d5-4723-ab9d-a64436a57b43 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005270 | c4055f7e-19e9-401c-8d65-1c7cfca7f892 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005271 | 0f070b41-15c3-4d82-b992-9d73209fa178 | Pole | HFTD Tier 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005272 | de823bc0-8d63-4926-a57d-7854fc53a55b | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005273 | 0d80419b-bf9f-4184-b4ae-4b27ae58c222 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005274 | c311b3f2-bf1e-4e29-b177-17934cda0ece | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005275 | 104950d2-0272-416f-8686-84215cf155b0 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005276 | 1864c947-254f-430d-811c-db73e773ef64 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005277 | 6b877e8d-8acc-4e10-b718-5eb75c248112 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005278 | aa65076f-4933-4807-b073-434bc9591816 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005279 | a1ea593c-b185-4196-b046-595f5ba05e97 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005280 | a43c9627-0d8d-43a5-bfc4-4cd8414b681c | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005281 | f8190310-fae6-4b2a-b517-ab1f4388407f | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005282 | e915edc4-9537-4dbc-9a78-47734a6ab98e | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005283 | 90b4f5e9-41c8-48c4-9322-70be8a13ca5a | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005284 | 3b773101-870e-4a08-ae20-b02ab96a33c6 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005285 | 0640b799-8f6a-4f11-8d18-dabb435fe145 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005286 | 2edafc4e-a5e2-4c3b-a0df-6a25975ca7b0 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005287 | 0486a58f-bdb6-45b7-ba7d-28240ba67d45 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005288 | 82a7526d-7a2f-4475-a870-68c09b9c835b | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005289 | c830a559-ab82-4815-92d3-c2386f52acad | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005290 | 175f420f-e847-4184-9998-fd23d168f48e | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005291 | 6bbf3f82-28f2-426e-9b71-1d50074026ce | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005292 | 35d43c75-e3ef-41a7-b070-4c6eac7d844b | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005293 | d0283dad-cc53-4d92-a7fe-42be13e315ea | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005294 | 32333d13-64fa-47a1-9e56-dca8e3eef442 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005295 | f89edeb2-c46a-49f4-8055-92bf361b8f29 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005296 | 0ad3329d-1306-423e-90dd-7b311f7760cd | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005297 | 4147ebb7-d785-437d-94f1-c63e15439295 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005298 | 662e0bfc-3131-4f47-8230-40fbc4fed84e | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005299 | b3ac1287-4de5-49ba-a161-efe7e47413b8 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005300 | c267a96e-9a05-4bd3-96de-095097d5e278 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005301 | 0707aaf2-c0ae-469f-88b0-3cb3981aa796 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005302 | 5ce1a4c8-5c74-4e61-8b60-a253f34df4b9 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005303 | a26810fc-68ac-457e-8ea7-9abaccd6588a | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005304 | 5903c963-16cb-4a0f-8e38-f800c9e244e8 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005305 | 6b04fb6a-31df-48d0-9fc0-334cd1a12725 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005306 | 46fa30e2-97c6-4a32-840b-7b3e9f31d2d8 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005307 | 8732133a-438e-4ded-ad8b-cec9ba855769 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005308 | 92424739-e331-4e40-a749-7a329c235006 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005309 | 7b89fcb4-3cd3-43fa-9592-c47b1ca957e4 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005310 | 5220555d-530b-45d6-b4bd-ee50b223879a | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005311 | 123a9e06-62e8-4afd-ab56-247195019dbf | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005312 | 571f0020-9591-4622-9474-2b8e91dfba03 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005313 | 3491b4d5-1c53-4b90-9947-3be1e233dfaa | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005314 | d542c0d8-df17-4f29-9ec2-fc934ca050d7 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005315 | f3b1c574-0fc6-4e8b-898f-170248306465 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005316 | 536d83ea-f364-426f-93a5-0a620ea9406e | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005317 | 6f2df028-03e9-4e56-b18a-2c4bfb112639 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005318 | 5c21b966-f6db-41a9-bf62-b3d9d2f34c3a | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005319 | 8460ce50-0b37-4933-ad25-95050f88c719 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005320 | 7d8414b7-ff9a-4d69-8992-df55ac0cbc62 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005321 | c8e5f9a6-ce7e-48f2-80b5-a5e0ba803450 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005322 | 50d35370-528c-423c-bd11-8da4b094cd89 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005323 | 9c438d86-726c-4e65-a203-d2bcac9d287f | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005324 | 50abee65-818f-40b3-8141-6948c17c2d94 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005325 | ec196a38-98dd-4e08-8eea-7c971650741f | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005326 | 304f1e88-33f1-48e3-ba34-7bbe004eb742 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005327 | 49e8d807-fce8-43c9-bceb-02bf5ed9d1f0 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005328 | 4e7fa2fa-8c1f-4f5f-bee2-8b6dbe927515 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005329 | 93a335ca-82cf-4835-a281-331b5e83b781 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005330 | 52f93104-8448-4fef-ae59-88653391c9d6 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005331 | 3e4d08e2-1296-4bc4-b3bf-81756346a887 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005332 | ade811e7-b55a-406e-bd85-e3cd30edb095 | Pole | HFTD Tier 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005333 | 314e7b35-7ea7-4eae-9c90-e028ea06a985 | Pole | HFTD Tier 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005334 | 4ad9da18-917b-4291-8884-271f04675abf | Pole | HFTD Tier 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005335 | 010e0020-c8cd-48fa-a80b-834f2967770e | Pole | HFTD Tier 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005336 | 82ea73e2-0efa-45ac-a8f9-98bf59bf105e | Pole | HFTD Tier 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005337 | 055dc2a9-be82-49c3-afb8-88fb39888a0c | Pole | HFTD Tier 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005338 | 09a260c3-77a5-4772-a258-5a1a5b66ea3a | Pole | HFTD Tier 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005339 | 449b87c6-5e53-40d2-8166-0665f7a1d879 | Pole | HFTD Tier 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005340 | 9c0e2499-44d6-4e31-aff9-74f207158bdb | Pole | HFTD Tier 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005341 | 6e368a25-af71-4924-bcbf-00c3c50baef5 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005342 | 46fa1606-63bc-41e6-9f34-efad31c5f0b9 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005343 | 17b25550-373d-4c9d-bbcd-882f32c45001 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005344 | 2e353a9f-445b-4240-8dbd-3236eb6e8d23 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005345 | 47c58d6f-9aee-45f0-ae9f-05b326bb32d6 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005346 | dc7877b6-a9b0-4fe9-8240-9ef7cc1dbfc9 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005347 | d3043195-c9c8-4020-b207-be73e2db89cc | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005348 | efc9b24c-0113-4f8d-8387-17679624b0db | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005349 | 3c50df41-b1cd-4c2b-97be-80611e16cbaa | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005350 | 71a4bc93-ed2c-485f-9823-2345f2cea45e | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005351 | abe60f95-1731-414e-b847-a507c4ea0969 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005352 | 2f152e79-307e-41cf-a830-5f5389eec106 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005353 | 3a855c2b-1857-42c8-8850-c51d01e2f481 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005354 | 9155a036-ddce-4153-a0d0-44c851a12fca | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005355 | 5a41558a-d04e-4c48-b213-1a82a99d62b8 | Pole | HFTD Tier 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005356 | 5d553ff7-ee75-4cde-9563-0da84159e678 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005357 | 76f37124-91df-4cbe-8964-13cf992f56b1 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005358 | 8aeb2d85-050e-477e-af90-c4ebaf7c42c2 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005359 | 961f2713-774c-471c-8f08-c3b9cf972127 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005360 | d5bb20d8-2408-45e9-b957-d2f5e1eba677 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005361 | ceea8410-f62f-416a-a7c4-b23e273cf619 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005362 | b5ab0eaa-c29c-4281-b77a-93d8b0114f33 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005363 | 9f99edc3-6bdf-40cf-910f-5f84dacab975 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005364 | 88fb5747-16b1-4f56-b066-ccb7fab27f4e | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005365 | 732c27b2-45de-4ed2-89e5-6e48a2bcfe04 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005366 | 0df625a4-db4e-4cee-a6cb-d4dadfd77d3a | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005367 | 3c50456e-25b7-4a83-b669-353187ff64f4 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005368 | ebb27f0e-7932-483f-81b3-afdc68154065 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005369 | fd340584-8b88-483b-bf90-26d3f8827736 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005370 | 60183bb6-6bcf-472c-8413-081fd6aac91d | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005371 | f4e22ffe-6b08-4517-85c6-75ca91aee3e9 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005372 | 13b0b3ca-53ee-43b9-923e-5b6356603705 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005373 | f160d08f-6a1e-46d9-ac66-d902a79b9ed2 | Pole | HFTD Tier 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005374 | d7aff897-46aa-4afe-b1d1-dfa8685cb22d | Pole | HFTD Tier 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005375 | 59455992-9461-48e4-97ec-f5f9c665ccc5 | Pole | HFTD Tier 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005376 | 22299901-0f59-4707-81b9-769ec8f650aa | Pole | HFTD Tier 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005377 | de4f3f45-d0d4-4ba2-a3c6-bf3836c2d426 | Pole | HFTD Tier 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005378 | 66115500-4bf0-4d9f-bc1c-b7d06e4bce20 | Pole | HFTD Tier 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005379 | 5072ce8d-9834-4add-a63d-e52acb103917 | Pole | HFTD Tier 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005380 | 22b4cbd1-3d67-415c-a47a-50cbd2b022e6 | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005381 | e526279b-ed7c-40eb-8099-3746fcdfec96 | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005382 | 7d2f1c1f-932e-488b-9765-49ad27882812 | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005383 | 3e92f47a-65e1-4e13-b072-7b1cb5e090e7 | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | 2023-05-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005384 | 1dc314d0-11c2-4f43-aa8a-a4131e7c003f | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005385 | f449ab15-e9ff-45fd-bfae-cfcf326b07d7 | Pole | HFTD Tier 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005386 | 63365578-58ff-46e9-8336-cf747e38cde3 | Pole | HFTD Tier 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005387 | 35209a0e-9b48-4506-87da-501a290bdbaf | Pole | HFTD Tier 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005388 | e0c988d9-a902-49c3-9c95-34d6067e3fda | Pole | HFTD Tier 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005389 | a2473792-ef56-427d-a95d-423999bf95c1 | Pole | HFTD Tier 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005390 | ac07bd03-ce8a-44be-bd89-d24904f5f391 | Pole | HFTD Tier 2 | Distribution | 2022-05-27 | 2023-05-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005391 | 9955d68a-5c5f-4d3f-ab30-f6c18feb4e1e | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005392 | 77332381-4f14-4eb1-b441-72c8b5b8e7b9 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005393 | 7493ed1a-00af-4355-a092-383cf7c0d111 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005394 | 9b5c75b5-ec13-4479-a57a-3d5eca35c05d | Pole | HFTD Tier 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005395 | a75dc238-4b55-4230-80b5-c570377e8fb5 | Pole | HFTD Tier 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005396 | 25b2e274-6aaa-450a-aa2a-c3ceaf205b75 | Pole | HFTD Tier 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005397 | ab349ebf-3f7b-4b3e-802a-1025bc172f19 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | 2027-06-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005398 | d9b309e3-a9ca-443d-925f-931b8c31be80 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005399 | a0e91ea1-20e1-4eed-b5c3-5408145d40c5 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005400 | 344540d6-aa77-49c6-87b8-ee89545406f9 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005401 | 544ea706-289a-48f0-8384-c72a8b6ab557 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | 2027-06-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005402 | a24df196-8d97-4a12-92e6-f5a8922fc6a0 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005403 | 641c7bd6-7e31-4005-b8e0-0e00bc1a38b5 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005404 | ba4ef147-96b6-4d55-9e4b-4fe01bf5a68f | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005405 | 0004ef32-55de-4796-a5d2-ef0815b5b4d5 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005406 | cd4a6116-442b-4d49-b794-8b71fd6785b8 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005407 | 1105f55c-a02b-4f8c-a1ab-ec093302f416 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005408 | 8b6b3e00-ee3e-48e7-a445-fce9cc685653 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005409 | 28ff136d-8274-48a8-83ba-c3f34a0bf1e1 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005410 | 8eb7d97e-fabf-429c-ac5f-4a8efc01a614 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005411 | 1dcc91c3-6439-4a25-b616-c0c3163c8238 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005412 | 43d4a2d2-071a-46c9-bb90-b2749196bc9f | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005413 | a9408bc8-7d43-408e-8ce0-21b554a0fa6f | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005414 | c72b6fa5-65cf-4ee6-b860-e9bbdd92d250 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005415 | 365ad973-8dea-4f3d-b539-c451969f6133 | Pole | HFTD Tier 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005416 | 143bbcb1-4bff-4433-84e3-d094e278d229 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005417 | 5a115124-8908-49a9-94a8-4fde1c0b83ff | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005418 | 5dbb384d-5ed2-4e9d-8243-c29615898e04 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005419 | 2a83371c-6805-483e-b8fa-115e4efd9845 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005420 | a7e4c324-e7d0-49ed-a931-d2e0f25d95a1 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005421 | c2b386f3-ff5b-4dd6-8cfe-eaba46a5655f | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005422 | 498bbc1e-87ed-402f-acaa-1e43184e88ef | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005423 | 89b7b56c-6ee6-4ea6-aa4f-c62b9e0b616c | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005424 | 6024e71a-260b-4ac9-96dc-e8be5c7a322d | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005425 | 17a22e5b-8b3d-4a7b-b9ef-36576707d486 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005426 | 75346032-5ffd-467a-a9dc-26765ebe63f9 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005427 | 6f69bad8-f7b3-456c-8901-297866b3168a | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005428 | c3b3a404-477c-439a-9ce5-65cd6e2437b8 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005429 | be5ece9f-9866-4eac-9334-2a0111a72dbd | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005430 | 8347da64-97a9-4a07-816e-f71c74c97c51 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005431 | d05e7b2e-80a6-4535-a5de-94064cea95bc | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005432 | bdfc1123-ca3e-424f-a172-c484daa01e15 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005433 | 1091024c-4583-41af-ac5f-c8132f98a92d | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005434 | 04d90c31-c6cf-40db-a291-c14c7c0d019b | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005435 | 79df62d4-4dd2-4508-ba7f-6016607cdb70 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005436 | 2628c265-f38d-47c8-91f4-c3b899afc407 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005437 | f0366e2f-3c13-4419-b8da-b0cb60dce6a2 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005438 | 5c7abca4-93ab-415f-aae6-894390258a8b | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005439 | 6164a3fd-2e5d-4854-a49c-e1ba315485f8 | Pole | HFTD Tier 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005440 | 89243e80-21b9-4c81-abb0-ac874c6aef31 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005441 | b53ba4da-4c50-41d4-83cb-4664dd6fe869 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005442 | e2af2c61-872f-43dd-ae6c-a1ffa0134aff | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005443 | 610a11c5-d848-4ba5-a3e9-4b9f049202c2 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005444 | d8a5981c-99a8-4882-bc7b-fe15da7e877c | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005445 | 10e75c0d-ef4b-4388-b340-0c723134601e | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005446 | 811c29aa-d1ab-4bc5-b0de-4dc6d53e7404 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005447 | 5e665a4a-1cfd-4b7c-b3c9-79ac17054773 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005448 | 46b3736e-d55a-4b84-86f5-89b1306ae357 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005449 | 7b4e4f45-4042-4bda-a3eb-93ddffa49b70 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005450 | d34c369e-0670-458f-9779-ec2eee716336 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005451 | c043bef2-8c25-4843-a6d7-4c57315b35ac | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005452 | 1c1a3677-ba9b-49d0-a429-8e1417474d26 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005453 | 6721eba9-26ee-4363-9e7d-f2baf93dfed9 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005454 | e99a5261-5b6c-451c-ad50-e048655028ee | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005455 | 6ff2103e-9b57-43e2-a8e2-6a016c8de0cb | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005456 | 00c6c0df-7ba4-46e4-9ca0-f596c6566e99 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005457 | 39c9cae9-f732-4d6e-9ce3-4fb4e0ad0de8 | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005458 | fd680597-8140-4f9e-afb9-d33fb48688eb | Pole | HFTD Tier 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005459 | 16736fa8-722d-4f1b-92db-821095e5fd60 | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005460 | b3382cfd-c86f-403d-bc3e-889a8fa63c5d | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005461 | 955f7bad-e0de-4d11-966e-c08488217d6b | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005462 | e1b9709a-344d-4b43-857c-0d6c316f2268 | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005463 | 7360a078-0a86-439d-a7c0-196dbda5fecc | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005464 | 2ae64c44-e90e-4ed1-81d0-6959f5fe1b3b | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005465 | fa02ba18-7868-4f64-87fd-aeb01f8e6926 | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005466 | 67afd26c-d3f6-4ce3-a851-501a1a857693 | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005467 | f94afe8d-cb88-42db-b43b-d702af3a8d7f | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005468 | 639521ae-05f0-4abd-b6c5-82b96a55caa1 | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005469 | a706e177-cd63-4ef9-984c-e27242f5da03 | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005470 | 8131c11a-f9e8-488e-82f9-892003027963 | Pole | HFTD Tier 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005471 | a3a973dc-676b-49d3-9567-b008c3465bdf | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005472 | 06b47d1d-c5fd-4fe8-b82d-dbd38ea8e0e2 | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005473 | 94e06f01-586d-4916-93b3-4858ba59a27d | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005474 | 6efafb16-b4b2-4eca-88a2-06a14c1ea4fa | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005475 | 9f5f4036-0b0c-4ae0-b953-e198ca5a87df | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005476 | 6e8efdb5-9225-4f0b-bdab-a9e86d23f028 | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005477 | bf041ecd-6b91-41f1-b71b-aceba9ac6631 | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005478 | a91b776b-9d8b-4edc-9a12-b7c48ed066f6 | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005479 | d206aedf-c741-47e4-8256-a93cd5b71298 | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005480 | d0672f7a-c10b-4a24-be37-c98d5566b47c | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005481 | 7a1111ea-8917-4aad-bf78-02a3f7e22a8c | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005482 | c7ea0d7b-8c7e-420b-abe5-83e7ab9e7429 | Pole | HFTD Tier 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005483 | a16e4a84-84a7-4f5d-9c1b-f86cf42893fb | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005484 | 7498583a-fd8a-499d-98db-67d2943192e0 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005485 | c2a855e3-f912-47da-a981-c5cb431607b0 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005486 | d21f36af-a788-41a6-a2f7-406f2ccf412a | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005487 | 5b15de2f-4970-41de-8235-aaaa4a3b6961 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005488 | 6734fe9d-87f6-4247-99ea-7163f41dc9a2 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005489 | 5182dca2-ef61-4303-b834-52684d6930ee | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005490 | 1bddce8b-51af-493f-8ff2-fac9ee93b34e | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005491 | a9cd4a66-b9b7-42ce-bc51-c7ced036d76f | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005492 | efab264e-d833-4984-8b68-4cffa4b0faa3 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005493 | 80e726dd-8693-4556-94ee-30918a08623d | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005494 | 9afc7767-cc86-497c-bb2e-b61316415c7b | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005495 | b5f6ae45-7962-4d58-b38a-06dcc5a2cd15 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005496 | 7e618191-a9e9-40e3-b7e0-2f90d7ee8142 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005497 | d3d5c8c5-5f12-4ef5-aa51-97ea57ecbb41 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005498 | 910c4810-263c-4616-93a4-af5bb4c194d5 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005499 | 8b8256dd-84d7-48a0-8da3-6a035abf43e0 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005500 | 3b53f5a8-10b0-4db1-a667-40d33a431ed7 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005501 | 356cd0ba-d898-4e07-907c-f35f19af5018 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005502 | eec0317c-6a48-4eec-9716-7ce75e49df66 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005503 | a34c196a-47ca-4983-bfaa-c8821936e298 | Pole | HFTD Tier 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005504 | 74c5dd60-f8d2-40d8-b606-4ac2f7096b0b | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005505 | 5d124e0b-77b2-48e7-9313-3f3db4224a4c | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005506 | 7a096404-c6db-401b-9c0e-6d69e51f83fc | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005507 | 5775a1e6-05d1-44b5-a543-7e4b7318f052 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005508 | 804502ca-24d1-400f-a84d-0e9a9eb097cc | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005509 | 91da5b98-7af5-4a4f-ab56-6f8195f33720 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005510 | 3f9e0f34-cd83-4ba3-a1d2-bffcbd1108e2 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005511 | e3eedb98-60df-4408-b15c-d986e8827147 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005512 | 0f30e4bf-789f-44d9-a930-8727944076c1 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005513 | 5b615b9c-ac4c-4d44-85a0-e409bb969a3c | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005514 | 699324da-bb0d-4487-a086-e86d128a785b | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005515 | dd57316a-83fc-4d6f-81a2-dbc163e2924b | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005516 | ab02603e-840a-43a7-9f4c-325968540c93 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005517 | f41478ee-683b-478b-b430-6641d9c61b4b | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005518 | fc47e68d-ad6c-4e62-b3f2-e4668ed6ca13 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005519 | d1a0409e-8058-4121-bcdd-874595064e6b | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005520 | c21ec53c-ef54-444b-b8ce-623927a779a0 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005521 | fc9d603a-221f-4c0e-aec3-1aa90c798efe | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005522 | 39c1dac9-e06a-4b8c-bd8a-4c93aeac0196 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005523 | 1170992b-ed45-41ac-93a7-032a54eb0ebb | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005524 | 408ead9d-8c47-452b-86ea-166c4a7d60fd | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005525 | 1de2c696-a2b7-4b7a-ac6e-39f87a4dc1e5 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005526 | d03823a5-9742-4526-a977-5a7534b82a18 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005527 | b2f9c999-a4e5-4b34-aa30-10c7ac927129 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005528 | 8d0e55ff-e064-484e-8b42-b5e0c78a2695 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005529 | 55c92808-b9d6-41c7-ace1-392949910923 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005530 | f0166268-2464-4c2c-9702-7aa32f362b69 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005531 | a62bae72-306b-4eae-832a-2129fad5a76f | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005532 | 3314c839-49fd-4c84-94f0-ff403a2bdffc | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005533 | db6af8c7-5e20-4e33-b1d9-7cd021bf3786 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005534 | 00b3fd56-db6c-41ff-a851-5eff8b2cacdb | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005535 | 3873a587-5e53-49e7-9d4a-2f9f5a677351 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005536 | 6b6cdbbe-fcf8-460c-9a52-178b96039102 | Pole | HFTD Tier 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005537 | 34575d69-e68f-4379-9637-d26f15c8b743 | Pole | HFTD Tier 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005538 | 2a57d8cb-f0cc-4d12-be65-ad767a431439 | Pole | HFTD Tier 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005539 | e63ee37c-9e77-4b4c-a390-1fe9daf492f7 | Pole | HFTD Tier 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005540 | 65afe448-4e5d-4267-aead-b056db2139d3 | Pole | HFTD Tier 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005541 | f6162a34-a159-4591-bdd0-9495d27962b4 | Pole | HFTD Tier 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005542 | ce749701-3e23-4323-9ee0-3daeba73ca6d | Pole | HFTD Tier 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005543 | 7d98426a-1568-40cf-99fb-d528cc8a41cf | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005544 | 43afcc3c-dc6b-40d9-b76d-b32e9627b339 | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005545 | b142c4c5-82cc-4937-a8e4-2befc07d782c | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005546 | f7b87618-6ab5-4a0c-9cd2-257dc9c646ce | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005547 | a9b0bcdb-a1bf-4a10-a4ea-dd20a4ac0b5a | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005548 | 53dec5b3-faa7-4bfc-a0c6-48c5cc985149 | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005549 | efcc95b5-2126-42ab-8708-b9881e78c60e | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005550 | b7809b28-bd3d-4e4f-85a8-8d71e13df508 | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005551 | 55ff8a66-62f9-4125-90f7-3fd21f8c442c | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005552 | 32e267c8-84fa-43f5-ae4a-81246921927b | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005553 | 45c74e7f-6f85-4b30-888b-4b7260c34cf6 | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005554 | 3c2024f3-3bfd-4964-985b-a8a6e4811a87 | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005555 | d1753f35-63fa-464c-b705-daf1cf8ac8bf | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005556 | bad390b3-c903-4be0-93e4-942920b6bb8d | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005557 | 49e7d3c1-4baa-481f-8b7a-99b53ecf6011 | Pole | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005558 | 8da15489-0c79-49d8-a2b5-d9657f001e25 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005559 | 6caa5d57-2859-42c4-b6a8-4aff7aea2a62 | Pole | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005560 | 01d772fd-37b6-4c2b-ba60-74b5953dc58e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005561 | 4cffdebe-6b28-4f95-8684-2ba580ee4cf0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005562 | 31bd0687-5047-4776-aeec-5a0e59630cc2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005563 | 4da1583a-09df-461d-98df-c52e9eef8c32 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2023-06-14 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005564 | 62f41e21-fd72-44c0-9e40-428dc67e40d7 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005565 | 4b047ca6-1b7e-4d8c-b79b-27fd2880956a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005566 | 0ede8458-fe64-4fe8-aa1f-1001484e6c23 | Padmount Transformer | Non-HFTD | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005567 | 2356a8df-bed8-4722-a538-a0e13afdd20f | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005568 | 9d931224-1b1d-4b0c-a10c-3146752be6b3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005569 | 41c771ad-a229-48d4-b6ce-833512e9406d | Pole | HFTD Tier 2 | Distribution | 2022-06-15 | 2023-06-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005570 | 2d41216f-eb07-4d47-8ac4-d361b2cc6657 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005571 | b7137f0b-e07e-4d6f-b28c-527d4970a1ed | Pole | HFTD Tier 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005572 | d5883e28-c8b9-4cfc-a5e6-3a6d407fd18c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005573 | 1b437797-e7da-4b7f-9f33-a2353b7a05cd | Pole | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005574 | bf32fec6-968c-4837-af4d-610d3f242349 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005575 | 1cf96f06-cc51-48f4-af3b-69bb6b81b81d | Pole | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005576 | 6ee10a26-a07e-405a-a205-dda0961b8089 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005577 | ef2b6b89-31e4-41f2-b08d-62fe967cd958 | Pole | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005578 | cd1d59a7-4fc4-4b0d-86dc-4f87bcede5d4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005579 | 3be1b787-56a8-460f-a934-283c82edd225 | Pole | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005580 | 3326eae9-8915-41ed-8c3a-ef82f50c8e29 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005581 | 18e8883c-5871-4d53-8b54-f822ff9b0bca | Pole | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005582 | 2ab9ebb6-a13e-455e-9d5d-eee2f3fc5415 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005583 | ac0a7736-89d2-4830-aca9-990ecbaee780 | Pole | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005584 | c968c4f0-659f-4de5-a1e6-f4e6889ab438 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005585 | e3c72cee-d094-433c-8f7d-e7b6adda54d7 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005586 | 13f53e72-f481-40ec-bc62-9184799269dc | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005587 | 36e9404f-b39d-459a-87b2-8a4451fc4f9d | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005588 | 0376c3be-b3c8-495b-957c-8b33413a41d1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005589 | 98989c5f-65de-46e5-80dd-aa56cb001af5 | Padmount Transformer | Non-HFTD | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005590 | 298880e0-5326-4328-ab84-29d25d0c3509 | Padmount Transformer | Non-HFTD | Distribution | 2022-06-16 | 2027-06-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005591 | 9fa3fb16-783e-439f-a137-d189d85edde6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005592 | a85af020-f1a8-4bb7-9b25-7d6ab1800b87 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005593 | 1e0436ed-acd5-4707-9e0d-4b9caf87169b | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005594 | 5130edae-bd79-4ba5-bb9a-0a3700ed4e69 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005595 | c29af4d0-15bc-4a57-af8c-9349b7329734 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005596 | 5a47bdef-e192-447a-908c-febf0d336eca | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005597 | 9fefda5a-c474-4c3b-b008-51ecf675b89b | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005598 | 94ead8eb-5256-4eec-9e73-cc55975f3aac | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005599 | 1cd58a7a-4a44-41f2-b43c-71405fb4fe55 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005600 | 4bcae9be-09ad-4b8e-9d80-4edc59cfa6a4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005601 | 3bab858e-5e11-40a5-8a19-325a0fe605b9 | Padmount Transformer | Non-HFTD | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005602 | d3c9cbf5-7f45-454c-b4b9-305dcb465d91 | Padmount Transformer | Non-HFTD | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005603 | b9dcc4c2-d986-4466-a298-b71daad4aed2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005604 | b4c67ffb-8e1b-4316-a2cb-13655371deb1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005605 | 8469ab74-35be-445a-ac3d-969d7431d8f4 | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005606 | 850c4a3c-16db-41c0-bd1c-7e4235e41cde | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005607 | 1f0ae53d-ed03-4fae-bad7-fed38ae00e9f | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005608 | e4856038-cb1a-451c-8a7b-c4ca6595cdcb | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005609 | c19fde90-5337-4ab8-b411-2b6c4af6ba3a | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005610 | 8a69389e-42e4-4bf2-8fc6-3e0a7062ef4a | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005611 | df52a1a8-0c31-44bf-8e75-6d7b9568ab17 | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005612 | e28a3cf3-c43f-442b-afcf-caff845f3b3e | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005613 | daed959a-4d21-4774-b0e0-a6f3204eda5c | Pole | HFTD Tier 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005614 | 32741ceb-896d-452b-96ba-e07359dffa68 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005615 | d9bf59df-21ac-4e4c-94d3-f737205c5a93 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005616 | 03e35072-a4be-4ccc-913d-6eb56020644d | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005617 | b9158da8-200b-408a-b0b3-fb24709ef9fd | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005618 | 9da46770-0fda-41c3-87c3-2dac72b9aedd | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005619 | 7e212068-3acf-47f4-9214-d7170a58f009 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005620 | edf775bc-9d7b-4a7c-b533-cec7cc2aeb91 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005621 | d7c209e0-3cd6-45ce-a082-cb48abee240d | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005622 | 9797b6a0-a6ce-484d-99ef-e7b1277772e3 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005623 | ed9fe677-fa14-4fc9-a972-79aa488a92e3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005624 | a183ea84-4574-42c4-83cf-160c72450850 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005625 | a13d0258-61f1-43b1-9228-dce5c58695ec | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005626 | cfa424be-1ade-43fa-b75e-5577b89676e5 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005627 | 5c779567-9f7b-4a49-bbb5-e3a9b15ce3aa | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005628 | c8b69eb6-aec6-48c1-9b49-bc58621544f4 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005629 | af878fdd-e739-454c-b83c-0d3c8a3da074 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005630 | de95aa96-8b3f-478f-ac18-01663b7bb0a6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-20 | 2027-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005631 | 4434c782-74d5-4f2c-a82c-96bddec5c6cf | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-20 | 2023-06-20 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005632 | 8e7c11bc-ab30-4a6a-bc20-03597152f93e | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-20 | 2027-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005633 | 83cb1b94-fe53-4233-ba65-b57df4a5f29c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005634 | b020aae7-2559-49d6-b69a-568c73d95411 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005635 | 2a6fc61d-ec28-49a9-a828-ac07c755ebe4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005636 | 73e61b9b-9c57-4cd1-b8a6-d973bd599f77 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005637 | 97f58b5d-8cef-4551-8b35-298f73685ad1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005638 | ecdaaf67-2f25-48e0-b1f1-17c861eee95e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005639 | c32741fe-cfac-41e6-8903-51d452f4222c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005640 | afbcdd41-9670-439b-9ffe-df89054667ae | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005641 | 6341d88c-4143-454a-8a88-a2c71eb74b70 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005642 | 2625c5b4-fb0e-4ad3-93fd-09e3dde8fc73 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005643 | c62a6fd3-3d2a-4738-83c5-9c116ff7d314 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005644 | 0506b8a3-464f-4898-b97d-fbd1adc9cbef | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005645 | 99d66450-6366-41fd-9cbd-ec5fc98f170e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005646 | 3b34f210-1300-4f76-97de-97cf73055ebe | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005647 | cd54d625-24a3-4554-831c-b03562412bb2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005648 | 1f3e2d0b-4465-4596-8775-db561b7ecb54 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005649 | a6ea84c3-f617-4943-93b4-b20a57622cff | Pole | Non-HFTD | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005650 | f57249bb-e0c6-4e31-b952-966facf30c04 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005651 | 86d0243f-c291-40c5-ac7b-cb1dbe150bfd | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005652 | 0f552bba-6a98-4f3f-bf4c-e1e6b54a2889 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005653 | 5ff51a71-1123-4167-a8f1-9b8cdb1bc2e2 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005654 | b5ecf54b-8f71-492e-b9ef-5fd482eaddc5 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005655 | 9e31fbe7-495e-410e-be28-838fb43b055a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005656 | 6b7360dd-d7ca-478d-a8f4-621faa5f32aa | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005657 | d13ec6ad-2fdf-41da-b0ea-8b8bcb119603 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005658 | 7dea3583-8a76-4701-bbff-0d76c1d40381 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005659 | b507717d-4fef-4b44-9fbf-7080fd933f3c | Subsurface Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005660 | fc00b21c-94d0-41e1-b78f-2da60c9f1c66 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005661 | da61a454-3b12-4842-b23f-f8ce9a5d9375 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005662 | 9fe80817-b76a-41b7-b99a-6e5982e7301c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2023-06-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005663 | f2144e7c-b2f0-4a5b-b261-25ea32aa872d | Other (Describe) | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005664 | 6c9aca1e-de70-4304-802d-23aac78d08b3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005665 | f3a74b06-ca89-44fc-9aa2-970b8f01b5ab | Other (Describe) | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005666 | 646e47e1-596b-4c18-9e99-e3b019554b14 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005667 | 873c3160-dc6f-4c6d-9cd5-907452cd4bab | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005668 | 983332d7-a2d7-4f4e-87fa-337b7aca6c24 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005669 | 3a916cab-3fa2-4352-8551-d7e195085c80 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005670 | b8daf1f6-1c7a-49ea-9f87-a5455520c5e2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005671 | 5bb253fb-2aba-44f5-b468-489eeeaba216 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-24 | 2023-06-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005672 | 70c03c5e-c0eb-43b5-9304-5b4b58c14e51 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005673 | c8a68e42-6db8-45f8-a73c-3b63e6a8d181 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005674 | c9e6a4a4-6892-431c-9c6e-9bff7f782e69 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005675 | 2876af88-cb1a-4ae9-a211-7396568f0ce7 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005676 | e88d3cef-d974-4f40-b969-eaed7156703a | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005677 | 9ab7f456-a2d7-4bac-b9d6-a22a4ae06fce | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005678 | 3ca1e1bb-6d6c-497f-9632-0c7bb1721885 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005679 | 0276fbd3-4b6d-4a0a-9b7d-f0d6a7d9d58a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005680 | ed42748d-cde4-4cea-8306-63913d379ec9 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005681 | 8eaa42d2-3c2a-43d8-868e-1c4607bea3cc | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005682 | 328f773a-3bbb-48cf-acf6-11c9c4514842 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005683 | 945759fd-7e64-461e-9003-579624b1b8a6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005684 | 417ba8ba-aff3-4c3c-a6ca-712c8d56501d | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005685 | 97333fea-8d0f-4cd7-b461-c7801cd23c3c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005686 | 57132dbf-b2ac-4061-a0c9-85a59e17da31 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005687 | 8bb83fdc-cf25-4ed3-a1b4-aaec1d4d16a1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005688 | c7091109-e6cb-4bd3-aeda-bc71f46805d1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005689 | 250fb58a-d59f-4e30-acdf-da04a8325175 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005690 | 1cdd61bb-40cc-4898-a072-83625893d433 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005691 | 158284ec-87b6-44ff-8d88-744610aef02c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005692 | 2e7582e2-17ba-40c1-b3f8-8230194c5720 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005693 | a7f44a4f-90ab-4f83-a5b9-d16942e0f474 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005694 | a045f6a4-5a5f-4005-a009-1d3e74085d87 | Riser | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005695 | a56054d6-e431-4b38-8102-c6340cd0a187 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005696 | 65a9971a-6362-4e5d-9cb4-3eaf1725e19f | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005697 | 3aa680e5-bc9e-4303-8983-379d6a5bcc86 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005698 | 46b5491d-a643-4ea0-9d7c-d7a875934113 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005699 | 652d85cd-7dca-4650-b09d-38be7c3593fa | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005700 | 039b0d1b-f16b-44e8-9c30-bef197d876ce | Padmount Switch | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005701 | 8b167cad-ced3-48d0-970e-6006b5a91556 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005702 | 3e50c77f-a7f2-4955-b0d0-5278041b75a2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005703 | cb46753c-69b2-4b62-bfa8-fd6e22d45485 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005704 | 3660f9c8-118f-4a67-a131-8be4912ccb05 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005705 | 0687ca96-0d7d-499a-b133-6232b6a7a83a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005706 | e6196d01-9922-43cd-81e6-ed765dfbaead | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005707 | 5f0f0f98-d7a8-4f7b-8e1c-9eed7eab2f85 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005708 | 5ee63644-9e79-4756-a201-1bf59accbe53 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005709 | d0248b90-8bf6-4a68-bff8-0331537d2212 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005710 | 7142821b-0126-4800-b5ed-30fe0d80526b | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005711 | 4211b33e-172d-45bd-9697-8a989f875f1e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005712 | ddf4c389-923c-467c-96b0-d0c119361cc2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005713 | 68d4db95-826e-4a41-99d6-adbacc591d9f | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005714 | ecad7c32-ba3f-452a-b4fc-8b8a34a72cfc | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005715 | dc8b62e1-29cd-4951-9234-3c9c888e7a7b | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005716 | 932cef69-6251-41a0-9c2b-d4e9c18b70b3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005717 | a24192c7-d0e0-4b59-a80e-4c1dfa603c19 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2023-06-30 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005718 | 3c6e3906-5dbc-47c0-ab98-7c06e5d5b54d | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005719 | b6a202cc-e85c-4595-9e38-5237c44102d4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005720 | 6a10e78d-e849-4d53-96ac-903f9d740ad9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005721 | 51d31739-f023-4f0a-af6b-356f3f09467a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005722 | 9b5f2d37-ff25-4842-8de1-153bd7b26a75 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005723 | 8f1cfaa6-fa5c-4bcd-8cac-67fb4803ad76 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005724 | 737883d5-c881-49dd-a4ba-11d018923726 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005725 | a748300e-ff2d-42dc-89a4-eb1d9a4dbf57 | Pole | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005726 | 9c1dd4ec-db04-49ac-8b38-729c84ad393f | Pole | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005727 | 705da63e-2ba7-43f7-acd8-8bbb9dc75726 | Pole | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005728 | c51783c2-eb7f-43dc-9154-9e496a6f7e5a | Pole | HFTD Tier 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005729 | 543bdd87-6ad5-4467-a96b-1817cdf1685c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005730 | cad96719-c1ad-4544-ba90-3d96d7c9daa5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005731 | 9027305d-5ca5-4d5a-9787-94edef7f4c3d | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005732 | 7b81f885-698b-40f4-bf70-872bdb3a84c2 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005733 | 0eaec015-d283-49a0-b937-bbdabba47018 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005734 | 866d4f8a-f536-4f2c-a15e-2fe3d47e28fe | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005735 | 35c0a14f-e71e-4039-93ba-c1c0a0e077a3 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005736 | af4a2120-e8a6-444a-8cf2-9f9173acc042 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005737 | 39df8bba-e3ec-4586-a4f4-e88ea4e81a39 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005738 | 7f1ff962-6326-4560-80e9-9bdc6059841a | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005739 | 68e1d5e5-eff0-424a-9140-d7a6c56d949c | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005740 | 96f35bd5-2d54-4ad3-887f-2982b4691c8c | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005741 | b79fbdf9-cd7d-4c21-b4da-2da62d78492e | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | 2027-07-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005742 | 92530485-8c67-4892-827b-293d16760fab | Riser | HFTD Tier 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005743 | d661365c-f23a-4424-b3a5-1608c055c038 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005744 | 32a90151-c9ff-402a-8e34-3d86e01a9052 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005745 | 60d3794a-6e91-440e-b84e-7ed56015b922 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005746 | f5bef563-93a4-4e5c-8152-864e6dd8f6b1 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-07-13 | 2027-07-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005747 | df73377f-8e16-4be6-a8e8-a831c9668a3f | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005748 | b36e2ca2-b169-4493-9b73-e845e21fd800 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005749 | 68a02437-a256-419e-a9d3-f894f99ad010 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005750 | 49c0182d-a1f1-46de-9431-6770c058615d | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005751 | 2c46a6b7-8e04-4748-afbe-a3cda8019211 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005752 | 365bee8d-1b6a-42a1-b2fc-77d25bdadf62 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005753 | 93f622d5-9481-4454-9711-a95cc62475c9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005754 | 7043c738-d041-43cf-9b14-2807c0406316 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005755 | b548237b-9408-400b-b565-8a28bf3d6739 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005756 | d6efa84d-31c2-4031-b7cb-6913f263534e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005757 | dc142e9c-5516-485e-8870-39690eb540fd | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005758 | 14d3fbec-cdea-436a-b506-902b9b425279 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005759 | 179aeb7c-a58f-4c01-94bf-2733a6069c87 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005760 | 0eaa605b-90e2-4dbc-aa23-f842abb4441a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005761 | 1e5b4693-4012-4541-94cf-5a10b67cf02c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005762 | 572a067d-dbe9-492e-9d01-d8016fec4e2f | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005763 | 0dcdac62-15c1-4b4d-8bb5-ae602fbde396 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-16 | 2023-07-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005764 | cd408b5f-a09a-485f-8f27-e6803a712d42 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-16 | 2027-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005765 | 615eb800-1974-438d-b5e5-b83e4e8b78d6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005766 | 39732bce-4537-47fc-a2a1-2444145d59fd | Padmount Transformer | Non-HFTD | Distribution | 2022-07-16 | 2023-07-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005767 | 436bff65-1e42-4cdf-b38d-9154e6ca75eb | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005768 | 9123d66e-a97f-433c-ab1d-0232923dacb8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005769 | ba98a25d-f5f8-492a-abb7-8c54732f1ef8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005770 | 5e15942c-10a5-499d-bc5e-5cf00d088373 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005771 | 4d85fbd3-0ecd-4729-be4a-8415b59a261a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005772 | 11deba5f-8923-4b68-b64f-fc0c83247e94 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005773 | ed9c0452-40c1-4795-88a2-77612647cc3f | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005774 | 503b2711-da55-4704-9f2a-7c2d6d4d528f | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005775 | 0e1bf72d-2512-4448-ae30-bb458d249f82 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005776 | 3cbd90aa-9655-4e4f-a4ec-802bedc5e9d5 | Riser | HFTD Tier 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005777 | c97c87ec-f115-42a9-9eb6-7efcdc14342c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005778 | ffc6ab46-5799-4009-924b-309c0bf5c4b0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005779 | 5621a3df-f5c6-4921-9d74-96aaac526093 | Riser | HFTD Tier 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005780 | 916aae83-4ce8-466a-b377-bd1a2df74ada | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005781 | f020a51a-b5df-4f16-a610-6fc66e8217e3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005782 | 915c9f2e-77c3-4454-b5d4-0816e8586cdf | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005783 | b4c00fa9-e2d6-467d-9da7-1477bf4ad733 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005784 | 91853f5b-ebfa-4c2d-802c-6777e74acc44 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005785 | 09b6a4c9-9d9a-4658-a262-ffae9d6a71f0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005786 | 87bf2d25-51f5-4eda-a819-3e4bc1b3e078 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005787 | 9d1360b0-d78b-4956-b9a7-c3cff338b71e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005788 | 1921a16a-9eb2-4a74-bd75-b59ed792a8d0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005789 | 7d1c1ce3-6f82-499d-9d0e-ac6a13a28378 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005790 | fdefdf95-fead-4925-b734-d1d13d0ac4ce | Padmount Transformer | HFTD Tier 3 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005791 | be65b7a9-0606-4a77-bc91-6909cacb4fe5 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005792 | 8778d3f4-313d-43a3-9601-be10799c26f9 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005793 | e29ddcdd-dcdc-466d-86d7-4baed185d2d4 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005794 | 2e3b666d-5a2a-4ebd-8ef5-c40eb21d0101 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005795 | d00f29c3-9cf1-469f-ac39-107417483492 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005796 | cdd81f99-0c1e-4117-bd49-8cc919fafbd3 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005797 | 30dcd263-f462-417a-85ba-1ed216a3cb18 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005798 | 830b5119-e30f-421b-985d-cacfda17d10b | Padmount Transformer | Non-HFTD | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005799 | ba8c44eb-52e6-42b9-a08e-023e286df4d2 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005800 | 6972277e-1219-4402-98b1-47968c05a7e4 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005801 | 1ce135df-0492-4f05-a54f-9bfd206d79cb | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005802 | e3b24731-f94d-4b5e-8a1b-25cf57a7e5f1 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005803 | 8afed30d-af2a-41f4-82e2-096f0182e553 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005804 | 956f4069-31b0-428d-8177-b463da41c82e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005805 | 31332b21-931a-44b4-956e-6993ef7ed5b5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005806 | 5321383c-e6de-4fff-a775-611f046675fa | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005807 | 4886971a-3471-44ca-a661-16449a1380a4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005808 | a911aff4-9c38-4ffe-965d-b093eb1a13f2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005809 | f503f765-03d2-4afe-8fb4-2de7d0fdb1d3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005810 | 0362e6ab-ce17-47fe-956a-9f771f25f8c8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005811 | 9075fa42-4c3d-487f-a422-210cffd4125d | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005812 | 294e7f47-d95b-497c-864a-d7d66db88130 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005813 | 1a27a9cf-dc7f-4bc3-b2e6-fbfe68a30b2c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005814 | 8dd3673d-4c38-4812-9032-9c7028bf5216 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005815 | 675e58bb-28dc-4e04-867a-1bd8b7207473 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005816 | 95d79daf-b3b6-46a7-95cf-761c5a74859a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005817 | d87e3694-0fc7-48a5-8c45-b29c3679e33c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005818 | 31813f44-b57a-4296-85b6-fd66ae276c82 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005819 | 69642a7e-84c4-4db3-90da-e2d9b776a952 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005820 | 0b50282c-7fd6-49fa-8b00-1f1305cab7f0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | 2022-07-26 | 2027-07-25 | [5 empty] | Liberty | 2025 | 1
1130005821 | 5a5bb1a4-1131-4fc2-8a5f-abb07ab05718 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005822 | 884194fe-1dee-4abe-9f39-1f907d53ada5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005823 | 77793559-5287-440e-8def-2d3f2ed3bd11 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005824 | d2a27a69-d475-4feb-8400-300c992ea1d1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005825 | 4f595da1-4354-4fb8-acba-fd9314f20b0c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005826 | 9e7ecdf4-4653-42ac-ad6d-850829b6f1d6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005827 | f55618a6-1f62-48fe-8bf2-1115e5f41d21 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005828 | 5ac12c6f-3ad7-463e-9239-feeed233a5f6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2023-07-27 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005829 | 341d56ad-4a32-4bb0-b9a9-8d3614f11eb2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005830 | 0a06ac16-598c-424e-b4eb-233e72e13620 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005831 | a8abaf8e-5bc4-4ba0-85c2-e9a5c7efdfae | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005832 | 6afb2566-bd9a-4ff9-8468-a7468a5268d8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005833 | 0b437a6f-992c-4b63-a4a0-8f63bd61e472 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005834 | a9397d43-0dcd-4c29-a948-40b7010d35e0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005835 | e5687798-66d1-40cd-91a7-d3da0ce5a4b4 | Riser | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005836 | 250c9c34-9c2e-45bd-af09-ab33a48ca98c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-29 | 2023-07-29 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005837 | 861b19f4-6d5c-4e9c-9ba3-2c6ccad098db | Riser | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005838 | ea9c69b8-d525-414d-8a95-f15e5cc68fc7 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005839 | b0268673-e6c0-4cb0-ab9a-6609cf887d27 | Pole | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005840 | 6cb5f3c7-bd45-459b-b014-f082c2b0ebb4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005841 | 65d3714c-1df3-4741-b98b-07d6a384ccbe | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005842 | c5e97d32-4cde-4060-9ba5-6b9dc2766f89 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005843 | b9a781ed-4ea7-4ce4-a8a3-f1a04afad7b8 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005844 | b50f0096-968c-48bf-9e26-a52003b046d3 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2023-07-30 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005845 | a6715506-e507-48ed-887e-83fadb3014a5 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-30 | 2023-07-30 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005846 | db1089c1-261e-4831-81da-48dfce9f5005 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005847 | 7410d3df-1fed-4cea-80d6-315c4022df64 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005848 | 8e4a5f9f-6632-4d4f-a9f5-1d80070e9d15 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005849 | ce38b17f-da91-472c-9395-7d1e3d7722cc | Padmount Transformer | Non-HFTD | Distribution | 2022-07-30 | 2023-07-30 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005850 | 69a96925-cc06-440c-9b2f-475fc55218d0 | Padmount Transformer | Non-HFTD | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005851 | 34676611-518b-4fea-ac97-e8d8543a0ac5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005852 | f4343387-4bdd-4505-b3cf-a4b09f7a2010 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005853 | 2e744b36-b962-4744-8d66-c2e62ba5bb58 | Junction Enclosure | HFTD Tier 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005854 | c12d6384-f464-4de5-95c3-64bddecf4c59 | Padmount Transformer | HFTD Tier 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005855 | b0d7d791-1408-4a03-997f-e76303f83691 | Subsurface Transformer | Non-HFTD | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005856 | f60c47f7-4dc0-485d-bd3e-bcf1fdf28e54 | Padmount Transformer | HFTD Tier 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005857 | 551d7049-3680-4d3c-b86a-8ab3c0b39a03 | Subsurface Transformer | Non-HFTD | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005858 | d5636e90-0e1a-44fd-8e2a-62427b08c5d7 | Padmount Transformer | HFTD Tier 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005859 | c61c9708-851f-4d07-b5e6-9688d560081a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005860 | 8932cfee-afd9-4c3a-a74a-1356c81f1554 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005861 | f181aca2-9243-4210-b20b-f296f4d959a0 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005862 | d5601299-ce56-48d1-a84b-0f66eca70bab | Subsurface Transformer | Non-HFTD | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005863 | 0be8bcc9-67f5-4258-b3dd-a5ae8079bebc | Subsurface Transformer | Non-HFTD | Distribution | 2022-08-01 | 2027-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005864 | 97469f90-6197-4c07-b313-b1e18fa4a873 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-11 | 2027-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005865 | 9455b029-8445-47d2-ae09-d8435a7339a0 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005866 | e8094d4f-dc0b-479d-a747-5b551348ddd3 | Subsurface Transformer | HFTD Tier 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005867 | 090d0960-c0bf-4243-a70d-952b018015c5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005868 | 68ff7442-50c4-42c1-957b-7353b5141e73 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005869 | 73b33a60-718e-45e1-be66-7665d45bbb94 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005870 | 0184cb9e-1316-4350-8fdc-49ad401c0bc9 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005871 | 22eb09b5-181a-41b7-878e-b93311d44e98 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005872 | 24468157-72e7-4e81-9a97-9131fea2a8aa | Padmount Switch | HFTD Tier 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005873 | 535c7cf6-0fe5-4998-b175-8c659de3f0e2 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005874 | d627965b-18e3-46f3-80c8-a090d628dd4d | Padmount Switch | HFTD Tier 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005875 | a71ef824-c2bc-4acd-9d39-bf5326eac1e6 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005876 | 60c7352e-e2ca-41e4-b777-9c66b20e6f58 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005877 | 024331a3-be90-425c-973c-6606c5e02e06 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005878 | f07da56a-f3cc-43de-9464-849917314445 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-18 | 2027-08-17 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005879 | 7aec2cde-0c8b-4373-ae05-963e468e25d8 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-20 | 2023-08-20 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005880 | b9023123-e78a-4574-8077-001d9a4529ba | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005881 | cfbef4e5-cbf9-40f4-9444-585ce549423a | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005882 | 3e4c6145-134c-4104-a579-0b4309f9c94f | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005883 | 41375cd6-eebc-43fd-b564-7cfbd63d5278 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005884 | 93e03673-6637-4894-913c-77f87a7eace4 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005885 | a28d12ef-69ed-41df-a1e7-c79e0bfaf05e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005886 | cc0a0498-0e59-4468-a87b-d5e286323e83 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005887 | e41871fe-103e-4997-94fd-40c37951a733 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005888 | 493f2e0d-d24c-493d-8e8f-1dc94a068fd1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005889 | 64e39d77-1867-4417-8e0c-e715fc4f932c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005890 | a767130c-dba3-4952-917f-3ecbef23df55 | Padmount Switch | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005891 | 87a165b5-ae73-4c59-bc68-0ac3fc94b44e | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005892 | af1cb5e4-d7c6-4250-ad1e-b0c8ba097f58 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005893 | 9871f144-207f-445a-83d2-e70b618e35f5 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005894 | 05424644-e141-48c3-b836-1e04f775c299 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005895 | 279b39fa-e1c9-4903-9c28-68043690652d | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005896 | 390e4d13-65ab-4011-90f0-4c9bfc1dbbe1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005897 | 7d8dd5db-5b95-4953-9214-71f4ea07b834 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005898 | f5f7f618-595e-458b-9551-fc38426e872c | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005899 | fa9a583e-e74f-4d93-9403-9463f183dc81 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005900 | 5a590a03-3348-42c7-a656-21ac9d10ae10 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005901 | 8029cc16-eaec-49cf-af10-4ec84ae103f1 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005902 | 6b1ae1a4-428b-4dba-97f2-a493b71f6c90 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005903 | 1183d39d-1dc9-4c4b-ad48-da44f6057a64 | Padmount Transformer | HFTD Tier 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005904 | 5bdf31cc-12ba-40bd-945b-df6d16365a4b | Pole | HFTD Tier 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005905 | 575f5753-2477-4b9b-a2e1-a7602258edfc | Pole | HFTD Tier 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005906 | bfde1b03-fd7c-428a-9801-45647e7f245d | Pole | HFTD Tier 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005907 | 986ff4b7-5132-4b0d-9221-aff00fb9ed4e | Pole | HFTD Tier 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005908 | 58942f1a-5036-44b2-91b6-f30a3ef7760f | Pole | HFTD Tier 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005909 | 3c855010-4141-4bd1-8816-7c7dd8e3e396 | Pole | HFTD Tier 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005910 | dd30c485-f732-48af-a419-c23e6af5be23 | Pole | HFTD Tier 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005911 | 889d3755-0ce9-4849-a53f-a410f3d60766 | Pole | HFTD Tier 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005912 | 2439f181-39ee-431e-89e9-0e27b0b4fb44 | Pole | HFTD Tier 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005913 | 4384139a-8914-4f69-898a-dcfc983d3606 | Pole | HFTD Tier 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005914 | d689b31a-dfb8-45a3-84d8-941810274be7 | Pole | HFTD Tier 2 | Distribution | 2022-11-23 | 2027-11-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005915 | 0e390fe4-c150-4bb1-bd86-8ee5d6a963ca | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005916 | e4d54697-90b4-4c0f-8054-564699302bad | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005917 | 89926fbb-cae6-49c3-b81a-361100e2f151 | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005918 | adef5ec6-94cb-4749-aa95-9a009b4f90c3 | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005919 | 6683fc71-8b48-4287-b7c9-05b6e14e884c | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005920 | 1d870439-b07c-4d3b-bd87-e32e995d0f1d | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005921 | 603c4036-e86a-4ab3-8508-2af5613496a9 | UG Transformer | HFTD Tier 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005922 | e4f3f827-471e-4a2a-b982-7f06b303bd95 | Pole | HFTD Tier 2 | Distribution | 2023-06-20 | 2024-06-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005923 | 7922db2e-c76c-48bf-a145-26f598dd418e | Pole | HFTD Tier 2 | Distribution | 2023-06-21 | 2028-06-19 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005924 | 25af01c1-9801-496b-90e4-e65b797d48ee | Pole | HFTD Tier 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005925 | 082bc590-82be-4263-a6ad-85ad8d9c7188 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005926 | 25af01c1-9801-496b-90e4-e65b797d48ee | Pole | HFTD Tier 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005927 | 082bc590-82be-4263-a6ad-85ad8d9c7188 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005928 | eb774b59-de36-441d-93d4-8c091737890c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005929 | 56a68e5b-2c48-43e3-a8da-16edf14cceb6 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-03 | 2028-08-01 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005930 | 5f7a055b-0b79-4eb7-ad9d-fcbc99612a1d | Pole | HFTD Tier 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005931 | 73a6df4e-5dbd-4be3-922f-33dbee3e7c57 | Pole | HFTD Tier 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005932 | 10ae7c58-8fa2-4cd7-a833-ef3d619c4ec5 | Pole | HFTD Tier 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005933 | 10ae7c58-8fa2-4cd7-a833-ef3d619c4ec5 | Pole | HFTD Tier 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005934 | 7870c4d6-8685-47ab-bd95-6728d82ca87a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005935 | 53bd6099-69d1-483e-a6cf-7b951353ec9e | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005936 | 90021dbd-8aca-4229-b8cc-b270799a24e3 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005937 | 59699ea0-8488-4955-9d2b-fdab627fef4a | Switch | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005938 | 91f4fd99-78af-4227-b5b7-031d0e4affd6 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005939 | 5d68e8d9-9a66-4b4b-844c-8223382e3a42 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005940 | e17fde17-4dd0-4c45-bcc3-702827eff6ac | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005941 | 88252c7e-6d45-470a-b69c-26eb176c7432 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005942 | e17fde17-4dd0-4c45-bcc3-702827eff6ac | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005943 | 88252c7e-6d45-470a-b69c-26eb176c7432 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005944 | 2ba08818-e9bf-422d-aaa7-ab5a3bab4546 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005945 | 7429ccf5-9ca6-43d7-b891-0fe7e19f2253 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005946 | 2ba08818-e9bf-422d-aaa7-ab5a3bab4546 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005947 | e4ff76a1-858f-401c-9a22-d3cff50d08b7 | Switch | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005948 | 1babbb9c-0c0f-4bd8-82d9-b572619de616 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005949 | 749cb7b6-ff3f-4210-972f-9933fde66bc7 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005950 | e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005951 | 7e885feb-4419-487c-91bb-27338a56f9a5 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005952 | e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005953 | 7e885feb-4419-487c-91bb-27338a56f9a5 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005954 | e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005955 | 82437ccc-2689-4506-ad18-0157147e699c | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005956 | fe5bfd0b-16da-41b5-987e-49529d383f01 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005957 | 0b64d76e-2543-4a3a-8a17-825bfe157b67 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005958 | b218a9e9-8a18-45c5-b10c-462d491586f3 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005959 | b218a9e9-8a18-45c5-b10c-462d491586f3 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005960 | b805ba8c-daf1-49e1-bdd8-1e25a7d47bde | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005961 | b805ba8c-daf1-49e1-bdd8-1e25a7d47bde | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005962 | da6c581b-31d0-40ba-9637-f04d7aff0249 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005963 | 95ae16f9-0c3f-4f76-9844-46551ff52b15 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005964 | cdb667a1-1ad6-4674-b6f1-603bb9edd36b | Pole | HFTD Tier 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005965 | a79307d7-546e-4597-a553-3f902306e604 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005966 | 9d2b8689-6f67-47d8-836e-22d1ab556f65 | Pole | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005967 | 4b0aea41-8804-4fb4-8a8a-08d0274b2831 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005968 | 3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005969 | 3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005970 | 3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005971 | 314ac0bd-372e-4280-9274-9b5ca92c9c61 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005972 | 314ac0bd-372e-4280-9274-9b5ca92c9c61 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005973 | 33312161-3410-46df-84e9-d1dd54121209 | Pole | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005974 | 3467600c-882b-4022-91be-fca076f96adf | Pole | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005975 | 093fa2a8-d25c-4951-9f25-66114e85a606 | Pole | HFTD Tier 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005976 | 093fa2a8-d25c-4951-9f25-66114e85a606 | Pole | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005977 | 0ceb50c6-05d1-42b3-906e-64786005e8a1 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005978 | ca5b3a34-133b-4062-ab26-c2695a6a7af5 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | 2023-11-15 | 2024-11-14 |  | Missing ground molding, stirrups, Grey wire |  |  |  | Liberty | 2025 | 1
1130005979 | 791f0da6-307c-4228-b721-3ee92d30b220 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005980 | ca5b3a34-133b-4062-ab26-c2695a6a7af5 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | 2023-11-15 | 2024-11-14 |  | Missing ground molding, stirrups, Grey wire |  |  |  | Liberty | 2025 | 1
1130005981 | 791f0da6-307c-4228-b721-3ee92d30b220 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005982 | db4777bf-e97f-425f-8bef-b4bba2f36e29 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005983 | a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005984 | fbf22393-af38-4629-9fab-fbb52ab7e6f5 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005985 | a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005986 | fbf22393-af38-4629-9fab-fbb52ab7e6f5 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005987 | a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005988 | 577fb3b6-ae0f-4dc3-b71d-18a1b8a0e27a | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005989 | db82a00c-8503-4cb5-9ccc-66e0785dc73b | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005990 | 0b2edd57-e419-4eeb-ad72-8c1b26ee7304 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005991 | d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005992 | 32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | Non-HFTD | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005993 | d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005994 | 32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | Non-HFTD | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005995 | d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005996 | 32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | Non-HFTD | Distribution | 2023-08-11 | 2028-08-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005997 | d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | HFTD Tier 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130005998 | af44782d-e74a-4eb5-b8c7-a9d5a0a793eb | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130005999 | d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006000 | d2aa4357-e6cb-49e9-8eda-18bc94d1aeaa | Pole | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006001 | d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006002 | d2aa4357-e6cb-49e9-8eda-18bc94d1aeaa | Pole | HFTD Tier 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006003 | d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006004 | ebc37288-97d0-4831-bf37-2bd2db97971a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006005 | 4ddf43cc-990a-4c97-9677-bb8dea4f69bc | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006006 | ebc37288-97d0-4831-bf37-2bd2db97971a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006007 | 85041ef2-c7b8-4a1c-8eb9-f44d77321aaf | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006008 | 74ccbbf1-373a-4547-9d92-8db63838cf50 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006009 | 880fb73d-b44a-4791-9c41-3ef1915f5d9a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | 2023-12-18 | 2028-12-16 |  | CouldnGÃ‡Ã–t open transformer, lock is a series pacific lock |  |  |  | Liberty | 2025 | 1
1130006010 | 1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006011 | 1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006012 | 1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006013 | 7003eb97-7f50-4bad-9bff-4f9eb93ec3c9 | Pole | HFTD Tier 2 | Distribution | 2023-08-15 | 2024-08-14 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006014 | 58fc35cb-6f1e-4dbb-9786-70e9d7ca44a4 | Switch | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006015 | b43a8611-d1a5-4101-8cec-3edd7f69d696 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-16 | 2024-08-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006016 | b52016fc-3acb-4e82-aa9d-96145b447b64 | Switch | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006017 | d22ee777-ac34-4da4-b5e4-5e2f8178894b | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006018 | d22ee777-ac34-4da4-b5e4-5e2f8178894b | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006019 | be95c557-170f-4528-b577-6b0ac7125401 | Regulator | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006020 | 3572f41a-64d5-40dd-9945-95f16d8538fd | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-16 | 2024-08-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006021 | 3572f41a-64d5-40dd-9945-95f16d8538fd | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006022 | 4bcfeaa3-a764-4a04-b3af-0a8d7fc7abc3 | Regulator | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006023 | fd043d17-f221-4afc-9ae2-eb78936e6e24 | Switch | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006024 | 5c223a31-d36f-4881-82a6-fe3ced9f3622 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006025 | cb9dd658-63b7-421c-b26f-7c3dd33b4280 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006026 | ab926a43-ca86-4277-92e0-3d020c7ef43c | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006027 | eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006028 | abee0617-1a2f-4b78-bf34-fbbda211f50a | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006029 | eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006030 | 4b67c191-306b-4682-b7c8-5f538566f82e | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006031 | eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2024-08-21 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006032 | 4b67c191-306b-4682-b7c8-5f538566f82e | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006033 | f1f0595e-0a49-4c17-98c9-c8c5db110fa1 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006034 | 1f01ba0a-da2a-4971-aeb1-ada765205f84 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006035 | bcf43e93-ebb3-4c85-b585-823195ae952b | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006036 | 1d97789e-38ac-4121-baf3-7b091231b6b1 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006037 | 1d97789e-38ac-4121-baf3-7b091231b6b1 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006038 | 4e022486-b6e0-4213-9f55-ecb5ab221f55 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006039 | 27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006040 | 3c98da15-44e3-41ae-b017-2c519209b370 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006041 | 27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006042 | 3c98da15-44e3-41ae-b017-2c519209b370 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006043 | 27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006044 | 3c98da15-44e3-41ae-b017-2c519209b370 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006045 | 3527813a-a393-4926-a21d-3f48666ded19 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006046 | 3c98da15-44e3-41ae-b017-2c519209b370 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006047 | a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006048 | 3c98da15-44e3-41ae-b017-2c519209b370 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006049 | a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006050 | 5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006051 | a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006052 | 5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006053 | 69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006054 | 5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006055 | 69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006056 | 67e41575-96fe-497d-b435-7995e89f775d | Pole | HFTD Tier 3 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006057 | 69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006058 | e0f03e02-e426-44f6-b5f7-8817feb70c65 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006059 | 69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006060 | c5376880-6048-4e10-947d-59f22e59a67c | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006061 | 69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | HFTD Tier 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006062 | c4d9e107-dfed-4445-baa4-4059dfa7169b | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006063 | 967ae741-4d1a-44db-afc7-09ef9c374019 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006064 | c4d9e107-dfed-4445-baa4-4059dfa7169b | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006065 | 967ae741-4d1a-44db-afc7-09ef9c374019 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006066 | 73ec8ebb-cf59-4ee3-bcc7-ed63994907d0 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006067 | 7558a656-f808-4736-b44a-666d0a6cc3d6 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006068 | ae387d68-5ba9-4ed3-b38c-45548ab67474 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006069 | 7558a656-f808-4736-b44a-666d0a6cc3d6 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006070 | ae387d68-5ba9-4ed3-b38c-45548ab67474 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006071 | 450c2c55-7a7d-4fb8-bc95-3a7ec2fe20ac | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006072 | 450c2c55-7a7d-4fb8-bc95-3a7ec2fe20ac | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006073 | c2a30b56-94ba-41ac-870b-2e2d90302857 | Pole | HFTD Tier 2 | Distribution | 2023-08-25 | 2024-08-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006074 | c2a30b56-94ba-41ac-870b-2e2d90302857 | Pole | HFTD Tier 2 | Distribution | 2023-08-25 | 2028-08-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006075 | 2693dc3e-af8b-4bd7-867e-45e1c3c67bcb | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006076 | 2693dc3e-af8b-4bd7-867e-45e1c3c67bcb | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006077 | 9fbe3716-89f7-470e-83ab-e7d6314272b3 | UG Transformer | HFTD Tier 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006078 | 454ceea3-c978-4c25-bd41-d6dba6c19948 | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006079 | 956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006080 | 3e326912-ac6a-4eaa-b012-d6d799777bd5 | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006081 | 956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006082 | 956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006083 | 28b2c850-2182-47ff-8508-2bae4904181c | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006084 | 451a8d6e-75fe-4e3c-a750-adb3a9f84d86 | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006085 | 451a8d6e-75fe-4e3c-a750-adb3a9f84d86 | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006086 | 3f76948d-08f8-4ecd-a084-d88560053acc | Pole | HFTD Tier 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006087 | bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006088 | 0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006089 | bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006090 | 0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006091 | bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006092 | 0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006093 | bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006094 | 0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006095 | 73bc6ea5-d236-43e1-a839-f9165107cb0c | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 | 2023-11-15 | 2028-11-13 |  | Pole in good shape needs stirrups |  |  |  | Liberty | 2025 | 1
1130006096 | 0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006097 | 73bc6ea5-d236-43e1-a839-f9165107cb0c | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 | 2023-11-15 | 2028-11-13 |  | Pole in good shape needs stirrups |  |  |  | Liberty | 2025 | 1
1130006098 | 0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006099 | f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006100 | bf590aa0-a752-4941-b813-c89467ba4baa | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006101 | f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006102 | f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006103 | f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006104 | f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | HFTD Tier 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006105 | cc8d5550-a21c-41f5-ac6f-c72f38125443 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | 2023-11-15 | 2028-11-13 |  | Not bolted down to pad |  |  |  | Liberty | 2025 | 1
1130006106 | da05f32c-ca4e-4a28-93d2-c3d362dde5a9 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006107 | ce1111e2-8fac-4ba8-88a7-65568b7cb270 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006108 | 06a9c6ff-20c6-4e52-ae0b-d1dc51eeab04 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | 2023-11-15 | 2028-11-13 |  | Transformer not bolted down |  |  |  | Liberty | 2025 | 1
1130006109 | b9f088c5-f33a-4df0-a65b-3ea2bc138839 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006110 | 65e0dc54-a129-47ad-8900-878ef9a2673f | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006111 | af631e78-0929-4686-9a6b-6190295ebaf6 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006112 | 65e0dc54-a129-47ad-8900-878ef9a2673f | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006113 | af631e78-0929-4686-9a6b-6190295ebaf6 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006114 | 0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006115 | 9da09cb6-02b1-4a88-8ff9-5a27491d333e | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006116 | 0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006117 | 721f0bad-bdc0-4009-b93c-0da5657c30d5 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006118 | 0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006119 | 721f0bad-bdc0-4009-b93c-0da5657c30d5 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006120 | 1081d5d3-15b3-4cb2-b489-94416ac1a91c | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006121 | 635cc53a-4aa4-44a1-9cde-e27e3770b3d6 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006122 | 12493a3a-71c6-4597-ab06-bc306445855b | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006123 | 48070ade-2503-4d1c-8c35-0d8de2eb81b7 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006124 | 48070ade-2503-4d1c-8c35-0d8de2eb81b7 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006125 | 49fa9a73-c609-4c81-ac09-04d2031aa554 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006126 | 2792b831-c0ae-4289-829a-1cff99e1ee30 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | 2023-11-15 | 2028-11-13 |  | Not bolted down, missing HV warning stickers |  |  |  | Liberty | 2025 | 1
1130006127 | 2792b831-c0ae-4289-829a-1cff99e1ee30 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3 | 2023-11-15 | 2028-11-13 |  | Not bolted down, missing HV warning stickers |  |  |  | Liberty | 2025 | 1
1130006128 | 288ac579-f6b2-4403-bbbd-b79504d89df8 | Switch | HFTD Tier 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006129 | af3dbaf5-db9f-4fa2-a3ed-4492bd352c94 | Switch | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-02 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006130 | 4298ab5f-2240-400d-b9f9-c93090400e23 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006131 | 01f1ae25-1fce-49eb-b04b-e5563c344c43 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006132 | 73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006133 | 73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2028-10-02 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006134 | 73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006135 | 73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | HFTD Tier 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006136 | b9da561a-be1f-4b06-9b72-41d54cf2060d | Pole | HFTD Tier 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006137 | ed94cc9b-ad66-4cbb-9bc9-2557f329cdd7 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006138 | 9b67dfee-4368-47cc-b862-6ea82e09b621 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006139 | ed94cc9b-ad66-4cbb-9bc9-2557f329cdd7 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006140 | 9b67dfee-4368-47cc-b862-6ea82e09b621 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006141 | f38d1b8e-ca13-40da-b5bf-e10b96a49c77 | Pole | HFTD Tier 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006142 | f38d1b8e-ca13-40da-b5bf-e10b96a49c77 | Pole | HFTD Tier 2 | Distribution | 2023-10-05 | 2024-10-04 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006143 | f941ba6b-a553-40c4-9c7f-bed3fa9860cf | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006144 | e40d9236-f6c0-4ad0-9875-9aa53573e7b7 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006145 | 3e7c9e46-6945-4a6a-b6b8-87aacbac709b | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006146 | f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006147 | f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006148 | f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006149 | f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006150 | f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006151 | a7d573e9-2a48-4bb2-b378-e5290a7f9a40 | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006152 | be4be738-c74c-43c7-9491-4da142e1c2d5 | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006153 | be4be738-c74c-43c7-9491-4da142e1c2d5 | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006154 | ae9bc4da-b916-4258-952e-8a9000986684 | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006155 | 50a11142-f99e-4a9b-884f-2a088221c9d4 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006156 | 50a11142-f99e-4a9b-884f-2a088221c9d4 | UG Transformer | HFTD Tier 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006157 | 2da4b3a5-6afc-42c2-9eb3-fdb0620d0cd2 | Pole | HFTD Tier 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006158 | 760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006159 | 2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 | 2023-12-18 | 2028-12-16 |  | Replace pole |  |  |  | Liberty | 2025 | 1
1130006160 | 760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006161 | 2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | 2023-12-18 | 2024-12-17 |  | Replace pole |  |  |  | Liberty | 2025 | 1
1130006162 | 760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006163 | 2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | 2023-12-18 | 2024-12-17 |  | Replace pole |  |  |  | Liberty | 2025 | 1
1130006164 | 760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006165 | 2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | 2023-12-18 | 2024-12-17 |  | Replace pole |  |  |  | Liberty | 2025 | 1
1130006166 | 8c88d310-3666-42b8-958a-60e712547a25 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | 2023-12-18 | 2024-12-17 |  | Replace pole |  |  |  | Liberty | 2025 | 1
1130006167 | 859eb4ab-bd5b-4954-96f4-76aef8b1990c | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006168 | 8c88d310-3666-42b8-958a-60e712547a25 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | 2023-12-18 | 2024-12-17 |  | Replace pole |  |  |  | Liberty | 2025 | 1
1130006169 | 8c88d310-3666-42b8-958a-60e712547a25 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2 | 2023-12-18 | 2024-12-17 |  | Replace pole |  |  |  | Liberty | 2025 | 1
1130006170 | 8c88d310-3666-42b8-958a-60e712547a25 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 | 2023-12-18 | 2028-12-16 |  | Replace pole |  |  |  | Liberty | 2025 | 1
1130006171 | f977c13d-1b5e-4a1b-bc1e-a8696300c618 | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006172 | e7ad16db-7eb9-4506-af8c-d4cdd950697e | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006173 | 15c83ebc-94ba-4f4b-88f7-50f451ff2dca | Pole | HFTD Tier 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006174 | 44863429-de7e-4008-be6c-31629eec6ef1 | Pole | HFTD Tier 2 | Distribution | 2023-12-29 | 2028-12-27 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006175 | 85631a97-d6d2-4b6e-a583-9e85d825b54a | Pole | HFTD Tier 2 | Distribution | 2023-12-29 | 2024-12-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006176 | d5f2100e-e1f0-4efa-8027-3f5dadd5d1a3 | Pole | HFTD Tier 2 | Distribution | 2023-12-29 | 2024-12-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006177 | a26490e1-c6be-4596-9b66-14fbc88ab3f5 | Pole | HFTD Tier 2 | Distribution | 2024-01-10 | 2029-01-08 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006178 | 3e30d935-8fe5-4e2a-b4d8-7f2085915154 | Pole | HFTD Tier 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006179 | ad0de065-8cf6-4cb1-9660-b3b917665ddc | Pole | HFTD Tier 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006180 | a3880147-5dc7-40f5-84c9-34ef098e1e47 | Pole | HFTD Tier 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006181 | 2da1ae28-2f23-4571-9820-32b5a63c0c2b | Pole | Non-HFTD | Distribution | 2024-01-10 | 2025-01-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006182 | a5befc16-47c5-47ca-ab71-944f89a76aad | Pole | HFTD Tier 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006183 | 32f36530-b6bf-4f75-9882-d9f09a6929c6 | Pole | HFTD Tier 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006184 | 27fb9d55-dc74-47ae-a07d-2465bc122ad6 | Pole | HFTD Tier 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006185 | 2bed610e-e932-4c0b-935f-c229000750d7 | Pole | HFTD Tier 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006186 | c791edf1-18b5-4988-8e6e-e0d23f99770a | Pole | HFTD Tier 2 | Distribution | 2024-01-11 | 2029-01-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006187 | d62e6a75-c027-43cf-8050-942c0ec6b8dc | Pole | HFTD Tier 2 | Distribution | 2024-01-11 | 2029-01-09 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130006188 | 8247efed-3828-49fa-8eac-7aef3d24a5fd | Pole | HFTD Tier 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006189 | 5bde5c22-0ebe-4658-b7bc-f536803f6a03 | Pole | HFTD Tier 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006190 | d861f6ee-166f-4c08-aeb0-8c4d72a55ca3 | Pole | HFTD Tier 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006191 | 4625aea7-8dba-4237-9316-bc1f3328ce92 | Pole | HFTD Tier 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130006192 | 176f00d7-d95a-4c7a-afc9-ee8c719e9d94 | Pole | HFTD Tier 2 | Distribution | 2024-02-13 | 2029-02-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006193 | f241ef45-461b-4a35-bd67-ef692afe5555 | Pole | HFTD Tier 3 | Distribution | 2024-02-13 | 2029-02-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006194 | a8ccc48d-709a-481f-8461-f6fc56ccf4fd | Pole | HFTD Tier 3 | Distribution | 2024-02-13 | 2029-02-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006195 | f35e4648-aef7-4cc9-88f0-e9eade8a1858 | Pole | HFTD Tier 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006196 | a8ccc48d-709a-481f-8461-f6fc56ccf4fd | Pole | HFTD Tier 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006197 | 7d68a3b9-c9e2-43db-a39d-c988564809d4 | Pole | HFTD Tier 2 | Distribution | 2024-02-13 | 2025-02-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006198 | e4ed1a34-9d6e-4fd4-bfe5-9fc78a15d05f | Pole | HFTD Tier 2 | Distribution | 2024-02-13 | 2025-02-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006199 | f68aacd1-1eb6-43eb-930c-f18c146ab1df | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006200 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006201 | 3f547d7f-c752-4412-8bc0-76c15d53d6e4 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006202 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006203 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006204 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006205 | 2b7ba891-f3a3-453a-8b70-9edce9e8db97 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006206 | 20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006207 | 2b7ba891-f3a3-453a-8b70-9edce9e8db97 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006208 | a0254dad-ff8a-4a9e-9f18-a4d42850d45a | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006209 | 95b93442-9eca-4ff0-b73c-0d3286d659ee | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006210 | a0254dad-ff8a-4a9e-9f18-a4d42850d45a | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006211 | 664ab5e5-34d5-428d-b9c9-548078ef2d3c | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006212 | 92a8e7c9-d186-4e55-b9f6-318472d9ca09 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006213 | b1d2ef54-7139-4685-8163-accee856723a | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006214 | 92a8e7c9-d186-4e55-b9f6-318472d9ca09 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006215 | 1ed8852d-d909-407c-9222-f51332a8e99a | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006216 | 2b7ba891-f3a3-453a-8b70-9edce9e8db97 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006217 | 1ed8852d-d909-407c-9222-f51332a8e99a | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006218 | ea89ee70-90ee-458d-a291-c72e6e29441c | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006219 | 1ed8852d-d909-407c-9222-f51332a8e99a | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006220 | b1d2ef54-7139-4685-8163-accee856723a | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006221 | 298df510-33f2-46e0-8d22-c368d5c4776b | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006222 | 1ed8852d-d909-407c-9222-f51332a8e99a | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006223 | 664ab5e5-34d5-428d-b9c9-548078ef2d3c | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006224 | 7df3e4b7-a8b1-438e-b011-0a9efc8f9d40 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006225 | 3035188a-3e25-484d-af79-3d19185e2b6a | Pole | HFTD Tier 3 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006226 | eec5f2f7-fc1c-4011-884d-e32a1db72c54 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006227 | 41457c93-b098-44c5-afa0-5139a62775bb | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006228 | 775fb11a-3fda-492e-a4d5-7d9f87078058 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006229 | 11405a2f-41ac-4e7f-987a-45667f405214 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006230 | bcfa7aa0-29c4-464b-9312-ac8df9f2bc28 | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006231 | ed6d4460-e20f-487e-9b8f-46ab9dc2caed | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006232 | e84261f5-f41b-4454-b502-cafb95749f2d | Pole | HFTD Tier 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006233 | 845b72a1-26fb-4819-9500-4085861146f7 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006234 | 845b72a1-26fb-4819-9500-4085861146f7 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006235 | 845b72a1-26fb-4819-9500-4085861146f7 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006236 | 1b9f3133-da71-4f86-8059-7e709fa520d9 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006237 | 845b72a1-26fb-4819-9500-4085861146f7 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006238 | 1b9f3133-da71-4f86-8059-7e709fa520d9 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006239 | 1b9f3133-da71-4f86-8059-7e709fa520d9 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2029-02-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006240 | 1b9f3133-da71-4f86-8059-7e709fa520d9 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006241 | 194839d4-de7f-4f6c-8c8b-bc82c26efbb4 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2029-02-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006242 | b6c91c8d-ee3f-4c4f-9bbc-29a3759b01e2 | Pole | HFTD Tier 2 | Distribution | 2024-02-16 | 2029-02-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006243 | 3118b7d2-5add-4642-b2b1-29b959ceb849 | Pole | HFTD Tier 2 | Distribution | 2024-02-16 | 2029-02-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006244 | bd841551-b843-40e1-9eb1-ea2c04c313b4 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006245 | 16605c0b-8ebd-4751-9d83-36f23f36af91 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006246 | ad29ab38-c95d-48a3-bfa1-98d707c7cb56 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2025-02-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006247 | 64d55888-b88e-4d17-bd44-99bf9aa76a80 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006248 | 1305dbb2-1ad1-4d78-8c02-0e1fad51ec31 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006249 | 64d55888-b88e-4d17-bd44-99bf9aa76a80 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006250 | 1305dbb2-1ad1-4d78-8c02-0e1fad51ec31 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006251 | ad29ab38-c95d-48a3-bfa1-98d707c7cb56 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2025-02-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006252 | eb0dbb3d-47b0-444f-8a7c-6b925c808b30 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006253 | 076444f5-7fdf-4d74-89de-4b328f514659 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006254 | 636795ba-90f8-4e20-ad7f-22889f5b6873 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006255 | 076444f5-7fdf-4d74-89de-4b328f514659 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006256 | 501b58fa-3085-48a4-ac38-da570208bb5a | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006257 | cd52c32c-2530-4859-83d8-4816e9be4f81 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006258 | 5f4df282-8de1-4cbe-b2a8-c3155750720c | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006259 | 0857b78f-6f5e-45b7-9123-40061e20957b | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006260 | b2f7b8ea-77c0-4abf-a2d6-7d4bc4a5753f | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006261 | 501b58fa-3085-48a4-ac38-da570208bb5a | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006262 | 1e92dcea-508e-4253-995c-db939f302bf1 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006263 | 501b58fa-3085-48a4-ac38-da570208bb5a | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006264 | 1e92dcea-508e-4253-995c-db939f302bf1 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006265 | 62c7429a-6560-4289-bbb7-bf47f5a0d95f | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006266 | 188dc025-7873-45d5-b698-8d33e5a6bc89 | Riser | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006267 | 62c7429a-6560-4289-bbb7-bf47f5a0d95f | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006268 | 64d55888-b88e-4d17-bd44-99bf9aa76a80 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006269 | fd3efeb9-b00e-47f1-bc32-5b236c612f1c | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006270 | 4c52a986-91d5-42ed-840a-e2a45299e2ba | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006271 | ef0d7626-593c-4c4e-a005-4b0bcf7eb222 | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006272 | 283a161d-9cc6-4609-be73-b6fd3eb8582d | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006273 | 6e53b0de-81c3-459c-b852-3e73a2c3914b | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006274 | db25654b-255e-4109-8eca-61413e73ea63 | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006275 | b89a9de6-5f59-42c1-83ae-942a4da3b604 | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006276 | fd9ee573-0d76-4a21-a490-62141b62ca8e | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006277 | e52abb1a-510c-45b8-92f4-80b6888bfee8 | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006278 | d065b46d-3120-44e8-8538-5984d1bf32f3 | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006279 | e52abb1a-510c-45b8-92f4-80b6888bfee8 | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006280 | 6e53b0de-81c3-459c-b852-3e73a2c3914b | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006281 | f38f4de5-ace3-4fc1-a27a-6f8fd359bd33 | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006282 | 6e53b0de-81c3-459c-b852-3e73a2c3914b | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006283 | 73381375-3274-48c7-8137-56e216796f2b | Pole | HFTD Tier 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006284 | c81b55e5-a404-4a68-aa81-004f0caf0567 | Pole | HFTD Tier 2 | Distribution | 2024-02-23 | 2025-02-22 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006285 | c81b55e5-a404-4a68-aa81-004f0caf0567 | Pole | HFTD Tier 2 | Distribution | 2024-02-23 | 2029-02-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006286 | c81b55e5-a404-4a68-aa81-004f0caf0567 | Pole | HFTD Tier 2 | Distribution | 2024-02-23 | 2029-02-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006287 | 10858027-00bc-4639-b757-07920fb02e12 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006288 | fea8f128-5102-4b99-88bd-57b57a48f76a | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006289 | fea8f128-5102-4b99-88bd-57b57a48f76a | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006290 | 275de8a0-d3ee-4bc3-a5c7-36442e2b9e82 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006291 | 599d888d-e1d2-447a-8a26-34df6bd7d61d | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006292 | 71fd52ed-7590-4532-bc76-bf16980569c1 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006293 | c21b4f59-4955-4024-858a-62e688f28464 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006294 | 03beb2a7-911d-4b32-9abe-b5644ed36cde | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006295 | d70048ad-942a-474e-85a4-02ec5487ad99 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006296 | 03beb2a7-911d-4b32-9abe-b5644ed36cde | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006297 | 350c6116-143e-4e60-a485-22ab28b5b51a | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006298 | 98a9a795-181c-44c0-9b94-2f554fb0957a | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006299 | 350c6116-143e-4e60-a485-22ab28b5b51a | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006300 | fd0e945b-5db7-47c6-acda-d035267da9c9 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006301 | 34e2601a-0fff-483d-9835-48c52e0e1617 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006302 | fd0e945b-5db7-47c6-acda-d035267da9c9 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006303 | 34e2601a-0fff-483d-9835-48c52e0e1617 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006304 | de39883f-bf09-4af8-809e-88a0a146e0d4 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006305 | fd0e945b-5db7-47c6-acda-d035267da9c9 | Pole | HFTD Tier 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006306 | c3599b9e-fddb-4889-b625-6fca66eefeaa | Pole | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006307 | b48530e5-bd30-47fb-8473-b4075f37b772 | Pole | HFTD Tier 3 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006308 | 28a9801a-d4da-4439-9520-19d221c562a7 | Pole | HFTD Tier 3 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006309 | c3599b9e-fddb-4889-b625-6fca66eefeaa | Pole | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006310 | 1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006311 | 1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006312 | 1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006313 | c7efe317-ec09-4cf1-8df1-eba14aef8c92 | Pole | HFTD Tier 3 | Distribution | 2024-02-27 | 2029-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006314 | 8be7f492-7ed2-4fa0-94c2-37e23b136ac5 | Pole | HFTD Tier 3 | Distribution | 2024-02-28 | 2029-02-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006315 | 380fa61b-d30a-4c68-b4ea-e65dfb919c74 | Pole | HFTD Tier 2 | Distribution | 2024-02-29 | 2029-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006316 | 08186b3b-154a-43c0-b189-d122f412d1c7 | Pole | HFTD Tier 2 | Distribution | 2024-02-29 | 2025-02-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006317 | 12755552-d927-491f-afce-2da810b382ba | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006318 | 4567186f-b1a9-4d69-818f-845b3a76e104 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006319 | f687f434-b62f-4ecf-a2ec-88f7f21a2d00 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006320 | d6ec854d-96d6-4d4e-be39-92f5799d120d | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006321 | c31bb5e9-66ad-484c-b6aa-59ff126b2066 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006322 | 148565cf-6988-42f5-8003-478d292c8159 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006323 | af46c94a-7ba4-43f5-b403-e48ce2229dc2 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006324 | 72311e7e-0cd0-40b7-84fe-a9358e811f86 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006325 | cc3d4551-a292-4149-bceb-8fda9a142625 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006326 | 69a4effb-f976-4aca-968f-82aa05104a1d | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006327 | 0dc316a5-2e37-48d0-9b06-648f0afeccd9 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006328 | 3a20ee58-57b3-474c-9d78-7d6668ff1a0b | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006329 | 078837ed-0297-4bfa-8ccb-b9cb5f9cab4e | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006330 | 1bd4c9ef-eccf-4384-85ec-4cccd4003092 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006331 | 7e940654-7e96-4e59-b50d-a3dfcaed60fe | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006332 | 9200b1f1-0fae-45aa-86f8-9f278a05e9d9 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006333 | 35b123cf-441d-4084-8f01-46e82a4f73f7 | Pole | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006334 | c0fe2780-0b51-4db3-93ec-2555a5b0319b | Pole | HFTD Tier 2 | Distribution | 2024-03-05 | 2029-03-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006335 | 0ea61359-570d-4ae7-b1ae-17008eeefa83 | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006336 | c4b929af-26a0-4633-99d0-5a066ce990e2 | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006337 | ecb6141c-4e89-4a42-a996-3cd7cf806d46 | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006338 | 0c58baa4-a3f4-4d8a-aa9f-d31c4608ba8b | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006339 | fd7c6e7c-8432-447d-985f-3578bb5e1334 | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006340 | 95c71cb9-4ef5-474b-8a4c-8197c67794ad | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006341 | 24334ed0-dff4-4f32-aedc-5bb4497d199a | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006342 | aa477842-7087-4932-9ef7-f58d33aa14ae | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006343 | 466efe1c-b899-4be3-98ac-19b69b87d983 | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006344 | 6f0336b9-9cd9-4d8e-b582-38a4f4f86c26 | Pole | Non-HFTD | Distribution | 2024-03-06 | 2025-03-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006345 | ed493cbb-15e5-45da-966a-7d9126f155cd | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006346 | 91929722-7fe8-4ba6-b99d-30a9b68b97c4 | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006347 | fd7c6e7c-8432-447d-985f-3578bb5e1334 | Pole | Non-HFTD | Distribution | 2024-03-06 | 2029-03-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006348 | 31c1b442-e018-46d0-a150-77a22a89a9e8 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006349 | 0f3e98f1-4d14-4ce9-946f-6ef1db4cfffc | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006350 | 3b768b55-ccb3-428a-a74f-85c044236ebe | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006351 | aaf9319c-d9d8-4712-98d5-9b3d513c0f07 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006352 | 49202a77-d54b-4c11-8a4e-651887284760 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006353 | 6b5bd890-11d5-41a7-a686-8e0925ebdbc0 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006354 | 6b5bd890-11d5-41a7-a686-8e0925ebdbc0 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006355 | 03aa88e9-5e8b-4a21-b0f8-9dc679130e24 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006356 | 03aa88e9-5e8b-4a21-b0f8-9dc679130e24 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006357 | 2618349d-f5f8-42a1-aa90-f445c584cf17 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006358 | 03aa88e9-5e8b-4a21-b0f8-9dc679130e24 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006359 | 31c1b442-e018-46d0-a150-77a22a89a9e8 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006360 | 5603c595-bfa1-44b6-8706-a85444ed5f3b | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006361 | d1d7fa17-fb61-4d4e-86fd-6fc1be7cec68 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006362 | 08bbf9cd-1247-420a-89af-0d99eb3ad7c9 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006363 | c2b0676a-62ea-4a5e-aa2b-03964cf50415 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006364 | a43a068e-eece-4418-801d-e4b92e8ccf9c | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006365 | b6e52144-8fe7-4c87-ae45-ce83f12869ae | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006366 | f0f5323d-3f93-4102-947f-ce44f2ab3755 | Pole | HFTD Tier 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006367 | d1a228bf-b1e9-4ab4-affc-11e8307ff20d | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006368 | c216ebf4-35cb-4029-9ceb-cfb93f3e5820 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006369 | c94467e6-d16a-4a54-8db2-6106b8f1a6d8 | Pole | HFTD Tier 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006370 | dd5a0d59-1230-4420-b5bc-96515de5e0d7 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006371 | 3b61d076-b890-4b34-94c8-a7c3a0f5d16f | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006372 | dd5a0d59-1230-4420-b5bc-96515de5e0d7 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006373 | c216ebf4-35cb-4029-9ceb-cfb93f3e5820 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006374 | 0cafef72-5301-41b1-ba25-b0c7bd91ee71 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2025-03-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006375 | ccb5b19f-0ac1-465b-b92c-334ef353cd26 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006376 | 0cafef72-5301-41b1-ba25-b0c7bd91ee71 | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006377 | ccb5b19f-0ac1-465b-b92c-334ef353cd26 | Pole | HFTD Tier 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006378 | 0ee1aa4f-b3d8-492d-b074-5bcf66825a2d | Pole | Non-HFTD | Distribution | 2024-03-07 | 2025-03-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006379 | 6f13c984-8130-46ab-a83e-a7de34113603 | Pole | HFTD Tier 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006380 | c37e24ea-3eb2-4a36-be5d-8419aa5a8daf | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006381 | 9073b083-b6fa-41bc-9456-3f28ad7fb70d | Pole | Non-HFTD | Distribution | 2024-03-07 | 2025-03-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006382 | 9073b083-b6fa-41bc-9456-3f28ad7fb70d | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006383 | 1ac901da-b9e1-4271-92c6-b08e544ca96a | Pole | Non-HFTD | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006384 | 9e79cc3b-790a-4ce6-b755-b2d7e8b754f8 | Pole | HFTD Tier 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006385 | b1ef0c83-bdc0-442a-87cb-9f2ed12dbefe | Pole | HFTD Tier 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006386 | 60634f10-915b-412f-86f1-ffe80636cafa | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006387 | a3dc23c7-095b-4ea9-b2a4-e9f7df5d5cfd | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006388 | b6f62fc1-a241-4f31-80ac-73c3a743d804 | Pole | HFTD Tier 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006389 | f6d01e62-8c71-4064-8175-46007b0cf106 | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006390 | b5324420-a776-467a-beea-8ccb212a3cc9 | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006391 | a6ace773-a1af-4353-a1e9-50bbf91fbbc3 | Pole | HFTD Tier 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006392 | d126760b-03ec-45c6-bdbe-91b9827656b6 | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006393 | 063fe1f0-7d4c-4600-ac04-0b30649fdfea | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006394 | 2c32b5ac-75a7-4144-9a27-fe13d7cdace6 | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006395 | 8dc80301-dfaf-4110-8d68-74a3ddc3a6af | Pole | HFTD Tier 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006396 | 8dc80301-dfaf-4110-8d68-74a3ddc3a6af | Pole | HFTD Tier 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006397 | 09e3c6c5-731c-4ef1-a0e7-83332ec8d02b | Pole | HFTD Tier 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006398 | e7e54f41-e05e-4ad3-977a-6f135e79943a | Pole | HFTD Tier 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006399 | 19466a1e-8d24-46a8-85ea-7f26968a1394 | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006400 | 73e21503-88be-4696-af29-77d892f36557 | Pole | HFTD Tier 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006401 | 6174cfca-1d17-4565-b940-3ed1242e364d | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006402 | 68d63cef-fd32-4dd8-a306-8189a5042194 | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006403 | 33cb1985-b383-4819-baed-02e03535b9f9 | Pole | Non-HFTD | Distribution | 2024-03-08 | 2029-03-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006404 | eab986d1-72dc-4425-885a-bbc36b208b77 | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006405 | 5de2faa2-a35c-4404-bf1a-db08b2abe8a4 | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006406 | eb885587-3a94-466a-a978-85a1da0ae610 | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006407 | 76a8b0fd-711c-4413-900e-ded0074ed862 | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006408 | eb885587-3a94-466a-a978-85a1da0ae610 | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006409 | 71a10a31-9234-48cf-8ea7-4cf857c1ac3c | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006410 | 71a10a31-9234-48cf-8ea7-4cf857c1ac3c | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006411 | f00129f7-0d53-47e1-8263-05891b037e6f | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006412 | 1b9c2306-3784-4477-852a-1b6d30bff078 | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006413 | 9ea965dc-3d90-4cd4-86e4-597e0c741dea | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006414 | 1b9c2306-3784-4477-852a-1b6d30bff078 | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006415 | bce8886b-c009-48aa-b9b4-84d94681378c | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006416 | 97de8504-fd39-4c3f-bc14-b1b54df9c7cd | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006417 | bce8886b-c009-48aa-b9b4-84d94681378c | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006418 | 9ad377f1-3d50-4082-aff0-76ef2ebf94a7 | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006419 | c4f200d3-2bca-4dc6-9620-11031254c290 | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006420 | 17c53b93-1598-41ad-be80-359cce421345 | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006421 | 9c4822fb-9c7f-467f-9795-7a31bd92248c | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006422 | db08b317-00f1-4690-bd87-629337143826 | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006423 | 0480007d-e095-4ed5-9879-84c2706e326d | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006424 | 8c4cd3fa-e0fa-45b9-860a-a84df24b8b62 | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006425 | ca861d4b-b6b8-4a9a-b610-3a7803d3330e | Pole | Non-HFTD | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006426 | 8ae604ba-27d2-4783-9b24-ee1af86e3ae0 | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006427 | 9ea965dc-3d90-4cd4-86e4-597e0c741dea | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006428 | 3037f421-e216-4aa3-b5d6-eb4b1ff737c1 | Pole | HFTD Tier 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006429 | ec09a040-7563-4c1e-a0ec-b466cd3f1fd0 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006430 | 35b541e8-8d98-45bb-963d-10f7886f47b8 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006431 | ccda2710-2a00-49ff-bf5a-e105cd05cbeb | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006432 | 6b79f5c2-2753-4f15-b91d-d8c43cc5c7bf | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006433 | 3978e39f-1a26-44b9-803f-31c0a0c49c74 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006434 | ccda2710-2a00-49ff-bf5a-e105cd05cbeb | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006435 | 5d2d4d98-907c-4264-bc6b-005b041d9a42 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006436 | ccda2710-2a00-49ff-bf5a-e105cd05cbeb | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006437 | 2546d8df-9301-483a-8eae-96eb9a7ead1e | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006438 | b32c4b9d-6c77-437f-bb92-f19c179eea5b | Pole | Non-HFTD | Distribution | 2024-03-12 | 2025-03-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006439 | fa33f759-6cdb-4317-a552-37d604cdc7d7 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006440 | b32c4b9d-6c77-437f-bb92-f19c179eea5b | Pole | Non-HFTD | Distribution | 2024-03-12 | 2025-03-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006441 | 8c7d26fa-a1fe-4958-941d-1bc3d9e2bb5b | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006442 | 8ee6371f-c940-48a3-ba62-2f23e4e82837 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006443 | e57b0b1d-7d5a-4966-9049-32c53588aafe | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006444 | 1026ccb6-e261-4d40-8855-9aad823c976d | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006445 | 2917fb9b-2a0c-4806-91af-80f91bbd428b | Pole | Non-HFTD | Distribution | 2024-03-12 | 2025-03-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006446 | ee2a6001-5a21-45f5-b666-1188492ceb88 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006447 | 2917fb9b-2a0c-4806-91af-80f91bbd428b | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006448 | 2e0f87d9-dbe7-4e52-b336-22347ffbbc71 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006449 | 4ed21ab4-189c-4d1d-94ef-572b2cdacc08 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006450 | 5c077e6d-0f17-45d5-991b-c4d774de9d19 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006451 | 28292332-8020-4055-883c-6bb760a99056 | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006452 | 0b2e686d-0fd3-4a6f-a5f5-b02cf0071a0b | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006453 | 0b2e686d-0fd3-4a6f-a5f5-b02cf0071a0b | Pole | Non-HFTD | Distribution | 2024-03-12 | 2029-03-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006454 | edc2f829-3290-4e13-91dc-01e6692bd68e | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006455 | 387d203a-d61e-4bc4-82ed-07ee986fa1b4 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006456 | edc2f829-3290-4e13-91dc-01e6692bd68e | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006457 | 255350d9-1de3-4c4b-9a49-5a4a04371a0f | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006458 | 070549e9-574c-487a-b5eb-e10e5c38a2fa | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006459 | 255350d9-1de3-4c4b-9a49-5a4a04371a0f | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006460 | 9835b7f9-09f6-402b-b537-c08396dfb26f | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006461 | 656716a8-8f6b-4b4e-bcf0-0f55444d67e7 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006462 | 99ef8eec-dba4-4b02-b684-2eabfcfa08e8 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006463 | 6d32cb47-eb6e-47f3-97d8-d2311a2cade3 | Pole | Non-HFTD | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006464 | c9a4b06b-def7-49ed-9dfd-28f9e822eefd | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006465 | e39191f7-e3df-4114-8897-c9ef1353a158 | Pole | Non-HFTD | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006466 | 613d0b2c-9d20-4454-8f55-e08ac74e678b | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006467 | 41d547ee-cd96-42dc-b2b9-2b0b9397d5b5 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006468 | 178b972f-f163-4382-822f-7648fdb5be01 | Pole | Non-HFTD | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006469 | caea4356-53f5-49dc-ac5f-3d968436a089 | Pole | Non-HFTD | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006470 | a48286ed-b7e2-4c1d-a13b-f95ca5129fc9 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006471 | b0f4c606-feb9-4204-976f-353fa9b80b10 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006472 | 06a0712e-c3c3-44fa-979b-ee9c216455b0 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006473 | f85c7d00-0b40-4291-bfe3-8fbb4ba7626c | Pole | Non-HFTD | Distribution | 2024-03-13 | 2029-03-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006474 | 4d307b47-2f22-41c1-a5ee-18926fc63cb8 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006475 | e598baa4-6661-45a7-a608-fa8b16f14b67 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006476 | 2c0a844e-c1d7-4c28-9e3b-15d94c887cde | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006477 | ff24349d-0e12-460b-9e42-f9aacb19313d | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006478 | 1ed64d66-c515-4d90-ad15-073e481ac805 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006479 | b3a1883d-cd23-4b3e-a2dc-8081c9029cdf | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006480 | 07826595-9403-4ece-9e3b-7855a13373b3 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2025-03-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006481 | b4ec6d68-155e-4b9a-8f6a-cea5b3145ed3 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2025-03-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006482 | 8c3a3394-2ea3-4911-873e-fe6330489d85 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006483 | 22678b77-17b5-4732-b06e-8845a2540d0c | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006484 | 8c3a3394-2ea3-4911-873e-fe6330489d85 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006485 | 1690a91a-1b12-4eed-9fff-59c7c7c29be8 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006486 | 671af8fe-d837-45f0-bc3e-775cef03a077 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006487 | 8531c9a7-ea4c-4e3c-b993-7bedd7b9d6ad | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006488 | 7a1b3cf5-4e25-47de-9d09-f4051dcb2b1b | Pole | Non-HFTD | Distribution | 2024-03-14 | 2025-03-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006489 | 671af8fe-d837-45f0-bc3e-775cef03a077 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006490 | 2ddde2ee-e860-4c50-b43a-d50bba6c0984 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006491 | 5a1a39d9-25c2-4213-a30d-2cad209cac55 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2025-03-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006492 | 3978e8d7-c54f-4d45-9eb4-4a6b900c0d9c | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006493 | 6c28ca20-e409-4a24-9e9a-5d008eb8b314 | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006494 | ff24349d-0e12-460b-9e42-f9aacb19313d | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006495 | 2b30b5af-88d3-474d-9d99-ea87c7fd5b80 | Pole | Non-HFTD | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006496 | 22678b77-17b5-4732-b06e-8845a2540d0c | Pole | Non-HFTD | Distribution | 2024-03-14 | 2025-03-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006497 | dc67055a-8a8e-441d-9179-75ace6d6ffbd | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006498 | 04f4d012-143b-4395-b60e-0b6101d9ddf7 | Pole | Non-HFTD | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006499 | 2f42eab6-9e41-4f1a-a470-7f1b41763b94 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006500 | 451ebfa4-b2f7-4b16-9476-0000c5a41fb8 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006501 | acd45106-2e48-4941-b30d-bfcdb1e20110 | Pole | Non-HFTD | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006502 | 46dc1da9-b06a-438b-b1c3-a80929ff6012 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006503 | ca77a8d2-4b9b-4281-908e-971acba65537 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006504 | 85a994ee-218a-4a63-9a51-21ec1db3c9b5 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006505 | 7d542951-a673-4186-91b2-23165a23f1c8 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006506 | 5b89e1cb-e006-4282-90a3-d8e8f38cd91f | Pole | Non-HFTD | Distribution | 2024-03-15 | 2025-03-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006507 | 81719855-bfbd-4fd9-80aa-f6c8649d370f | Pole | Non-HFTD | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006508 | 5b89e1cb-e006-4282-90a3-d8e8f38cd91f | Pole | Non-HFTD | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006509 | 3c341758-4271-4fed-9811-10f503ad4d11 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006510 | ca77a8d2-4b9b-4281-908e-971acba65537 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006511 | 75388b7f-b275-4da5-b320-be52785547ea | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006512 | 8d3e495b-2259-4360-8d30-97cc224149bd | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006513 | 5c520009-053d-44b0-bc48-0e24d1162b6a | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006514 | 873bec57-a3bc-486d-808b-953304dec26e | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006515 | 618d4b71-2d4f-4a66-9c36-bb4f93a37b7c | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006516 | 9233c06b-4391-4e5e-a127-2572d957f4c2 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006517 | a5b5bdd7-d799-4468-87bd-df8fd8f99927 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006518 | a99f53ce-11be-44f8-a145-6ddb818d2bfa | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006519 | 07c5e084-c33a-4f97-ae20-b4598b9a6f8a | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006520 | bae9418f-3727-40ca-b232-930da6564434 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006521 | 0cbb7e81-4142-48af-adbf-9d0d38b63be8 | Pole | Non-HFTD | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006522 | e14ca43b-d7b3-45fc-acc2-b90f84b76dd3 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006523 | 920c15f2-82fb-489f-94c2-486e824018a0 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006524 | b09fa20e-a7d1-47af-86d4-66d53310a772 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006525 | 81d8ef28-5319-47f3-b868-b5ab8ee21e52 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006526 | 2f42eab6-9e41-4f1a-a470-7f1b41763b94 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006527 | 94db60c7-d3ec-4d7a-8119-1cb5f2ffdf67 | Pole | Non-HFTD | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006528 | 6c9da36f-4613-433a-aa97-f76e50dd0c8f | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006529 | 6c9da36f-4613-433a-aa97-f76e50dd0c8f | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006530 | 626b915e-dfb8-48a9-b6f8-ab3835b17a73 | Pole | HFTD Tier 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006531 | 8eee6817-0611-4b74-961f-34f112221542 | Pole | HFTD Tier 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006532 | 448d965f-ab74-47be-b5f3-a9fbe1a1c69a | Pole | HFTD Tier 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006533 | 8a269a15-9eb7-4bca-aafa-8ee2d6195d9a | Pole | HFTD Tier 3 | Distribution | 2024-03-18 | 2024-09-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006534 | ec67a7ca-4c76-4298-a25d-7f99ec5d8a7b | Pole | HFTD Tier 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006535 | ec67a7ca-4c76-4298-a25d-7f99ec5d8a7b | Pole | HFTD Tier 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006536 | d855a00c-67fe-41f5-941b-dc9f6be92d53 | Pole | HFTD Tier 2 | Distribution | 2024-03-19 | 2029-03-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006537 | d855a00c-67fe-41f5-941b-dc9f6be92d53 | Pole | HFTD Tier 2 | Distribution | 2024-03-19 | 2029-03-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006538 | 305b8992-2005-452e-b1db-9ed04ceb5db8 | Pole | HFTD Tier 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006539 | 4cdbca96-ad2f-4657-9032-934c15f6630a | Pole | HFTD Tier 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006540 | 8c2c95a4-495b-4654-a1f8-daadfce3acd9 | Pole | HFTD Tier 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006541 | e58a30e9-909f-44a0-bf5e-b9398bec5e48 | Pole | HFTD Tier 2 | Distribution | 2024-03-20 | 2029-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006542 | 8c2c95a4-495b-4654-a1f8-daadfce3acd9 | Pole | HFTD Tier 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006543 | 7da6611b-5f78-4d37-9ee3-b63fb2907b8c | Pole | HFTD Tier 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006544 | b4b67759-1d9f-4321-adf1-65d6c4ae7dd7 | Pole | HFTD Tier 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006545 | ea60cde8-d125-4770-999a-8ffeae81d5ea | Pole | HFTD Tier 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006546 | 076f89b7-7432-4a4f-8808-17afc7a7570a | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006547 | bb2057e2-f77e-4948-8b02-28844880f609 | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006548 | 1316151e-84c4-4d0d-8160-99bfb51cd5b8 | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006549 | df3b2441-2766-48b7-885a-6341d6f1abd7 | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2025-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006550 | faaa79b8-0533-40a1-b55e-5be9f1dee2c9 | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006551 | 1c001f81-d803-4ad0-b36e-045ad791e3fa | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2025-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006552 | faaa79b8-0533-40a1-b55e-5be9f1dee2c9 | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006553 | 631c9364-656b-4c61-bf6c-3c1a85474ac6 | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006554 | e8293a8d-d8e5-46e6-be90-6bfaa5b58a78 | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2025-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006555 | 79bcaeb5-e20e-4355-a087-f82c42be58f8 | Pole | HFTD Tier 2 | Distribution | 2024-03-22 | 2029-03-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006556 | 79bcaeb5-e20e-4355-a087-f82c42be58f8 | Pole | HFTD Tier 2 | Distribution | 2024-03-22 | 2029-03-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006557 | 9f1fd254-cc24-4cfd-887d-c6f20dba28f1 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006558 | 28c0b09b-59eb-4bf1-904e-055ebdafa2d2 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006559 | b2c71ee3-47c1-42ee-b70f-dfde24749466 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006560 | 869b1d91-0739-46e0-bb69-f2076ffdbefd | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006561 | d7b9bb58-ceb3-401f-8b78-9e24b0393fd2 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006562 | 8a422453-d2f4-488d-b154-a639544d04d8 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006563 | 2504a978-48a9-456a-919e-c0050e2a0edf | Pole | Non-HFTD | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006564 | 8a422453-d2f4-488d-b154-a639544d04d8 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006565 | 69a27824-6010-4fb9-8d90-ff28a46393f8 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006566 | 06972e8f-7dc5-438f-b33f-35510119a835 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006567 | f541c835-4fb7-4925-8f12-b548445e8377 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006568 | 9d7cbc5a-d907-4533-81cb-a020d18481b5 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006569 | e803c6a8-09ff-4b35-98fe-050245e92993 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006570 | e0cdc8b5-1572-44ef-8f90-4d117dccea12 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006571 | d6eb1b6a-d6c5-4a46-a983-a18f24192be8 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006572 | 20105d19-eb20-480d-886b-605c7dff2ec7 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006573 | 54963d4b-5d80-4d7d-a999-7ebc87cfd053 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006574 | a14cf560-3e1d-4248-9940-b618c5d6a77d | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006575 | 77eb305c-4873-4f16-b29d-fe37a64b7d69 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006576 | 3d8cbdb6-dd42-4689-9599-f28f29adf4a2 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006577 | fd2c66a1-d430-461a-8d13-eaf41471acf8 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006578 | c3f1302f-9faa-447d-abb8-87d37ec135fe | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006579 | 3819d7e1-adc6-4475-8860-7bee70b023c5 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006580 | 9fd31c4c-560c-41c6-ae08-89f309938ffe | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006581 | 6c0fb2cd-ef45-4d1e-bec5-9da2390c28a0 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006582 | 77eb305c-4873-4f16-b29d-fe37a64b7d69 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006583 | 3506e123-6807-40ff-84fd-040a2f3b8510 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006584 | d13be912-32cb-4a9c-81f4-490a1ffc7eea | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006585 | bef47df3-f3df-43ad-9c0a-3b342fe827bd | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006586 | 9ff16f76-ca58-4874-a1dd-44f3a4e7be8e | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006587 | 9d7cbc5a-d907-4533-81cb-a020d18481b5 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006588 | 5ccaf539-35bf-4b3f-88cb-62c6bbc92c34 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006589 | 9d7cbc5a-d907-4533-81cb-a020d18481b5 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006590 | 8e46cf52-1148-4af0-a30e-d13f81904e12 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006591 | cc69dd27-a5d6-4458-b1d2-ebc40172c0c6 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006592 | 919465ea-efea-4261-9f5a-4f91cb3e8cf3 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006593 | cde1acd5-0220-4630-a455-50123ab05f68 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006594 | 2f8cf4cc-d5d6-4052-b31c-47b8001e58b7 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006595 | 92103ab7-e307-4022-8f61-883051ee656c | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006596 | eaa030f6-82ae-44fe-a346-8f8c57244f55 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006597 | 8e46cf52-1148-4af0-a30e-d13f81904e12 | Pole | Non-HFTD | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006598 | b3b06fc2-0ab1-4730-9545-a5a18e97def1 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006599 | ffdfce8d-25ee-4cd0-b253-ba08d6508dd4 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006600 | b3b06fc2-0ab1-4730-9545-a5a18e97def1 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006601 | 0f5be94a-869a-45e8-9f34-78c77392cafa | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006602 | cb26b583-44ae-49e2-a4b9-48bfd23f473a | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006603 | cb26b583-44ae-49e2-a4b9-48bfd23f473a | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006604 | d26758b8-a7f9-460c-b201-631234262042 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006605 | 407ebd9c-27d7-45a6-8b9a-e94d66953172 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006606 | 9c5d1905-b4c0-4d6a-b080-87b7eeb9d03f | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006607 | 5e966840-cb47-4bac-87d6-53c1b6ca6c97 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006608 | 9c5d1905-b4c0-4d6a-b080-87b7eeb9d03f | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006609 | 5ee3017b-ccbd-45f1-b2ee-1ce290e00175 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006610 | 4ee9864b-586a-466f-bde8-ac7bed6e047f | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006611 | 7ae52af0-668c-4ad3-abfb-e6d1057d3c75 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006612 | ba200718-345c-4a5d-ae57-05f298aa9a5a | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006613 | ef5f3d2c-86d5-4cea-a599-e9a8c84374ea | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006614 | b25361b5-5591-42c6-be07-534bc588a041 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006615 | c4d9a72f-e7e9-4791-9425-1ddbb14084d3 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006616 | 439f4f1a-ef34-4020-9d57-1cf73bc0bc7b | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006617 | 5aff294e-23de-4a7c-a2a7-9e7cbd0ecaea | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006618 | 5aff294e-23de-4a7c-a2a7-9e7cbd0ecaea | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006619 | 9606b5b1-db0c-44bf-a47b-46e1d94b7425 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006620 | c86a65e8-2708-4619-87ef-e406f467a518 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006621 | 547ae631-d4aa-4eb1-9c62-8b0c99827d59 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006622 | 5a897c18-9e93-43ab-9faa-1c2a139d9c51 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006623 | b43d0163-d0c0-4972-a52a-e3829f915d6b | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006624 | 5a897c18-9e93-43ab-9faa-1c2a139d9c51 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006625 | 43eefb5d-6dd3-4b20-a7f6-f3d394da8cb8 | Pole | HFTD Tier 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006626 | eaa09e16-2807-47e5-b21d-46aa16df96d8 | Pole | HFTD Tier 2 | Distribution | 2024-03-27 | 2029-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006627 | 35c8633a-c446-4c40-8153-99e855e157fe | Pole | HFTD Tier 2 | Distribution | 2024-03-27 | 2029-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006628 | 00383671-6b9f-4226-957e-2db7041ba9da | Pole | HFTD Tier 2 | Distribution | 2024-03-27 | 2029-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006629 | b32d724c-7de0-4811-86f7-6ab560e2bead | Pole | HFTD Tier 3 | Distribution | 2024-03-27 | 2024-09-23 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006630 | da91d30f-bd5f-46cd-be7c-c1a73e068c68 | Pole | HFTD Tier 3 | Distribution | 2024-03-27 | 2029-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006631 | 37f8d06a-f6b3-4f79-8b3a-e34fede2d630 | Pole | HFTD Tier 2 | Distribution | 2024-03-27 | 2029-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006632 | 29a83280-7a12-4e45-ac8a-36b7a3e13990 | Pole | HFTD Tier 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006633 | 00383671-6b9f-4226-957e-2db7041ba9da | Pole | HFTD Tier 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006634 | ed867b02-2786-4227-8336-47efa669032b | Pole | HFTD Tier 2 | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006635 | 40826a16-c983-4de8-bf86-8393f80b3dbe | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006636 | e76ebf8f-3586-4459-8d0f-228a4e8df366 | Pole | HFTD Tier 2 | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006637 | 5e76905f-23f0-4589-bbef-245daa4456ca | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006638 | f188f8a3-49d1-44fe-a043-7986326854fc | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006639 | 8f9f5d56-9ebe-4b36-a937-e9e6c457f2d6 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2025-03-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006640 | 11259963-4939-4c72-8c16-e0833ec09076 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006641 | fdb36ba8-1cfd-4924-9f09-2f9608aa69e7 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2025-03-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006642 | dfce73af-efd0-45dc-b099-86867272f1fc | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006643 | 05e5225f-da35-4ba2-bf98-15117c8072c6 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006644 | bef140bd-fdc4-490e-bc97-4f941805f85c | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006645 | 2519e6c2-4c77-492f-868d-3750d96795a1 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006646 | 978d82d2-2b18-4983-956f-269bb879bdf2 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006647 | 7ac2458b-dcd1-43ec-b7c1-765ca94bcc1f | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006648 | 2e8ed29e-70dd-478f-bbe1-0f83f0759243 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006649 | 9dab363d-ac1d-4ead-8508-3e1782d60067 | Pole | HFTD Tier 2 | Distribution | 2024-03-28 | 2025-03-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006650 | 31c6bd7f-b1f3-4074-bea0-40f036cdb7ed | Pole | HFTD Tier 2 | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006651 | 945fce7b-cfdd-40aa-aae1-0d47c3d51ee0 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006652 | 2bdf6cc7-69b1-485c-a41c-c499970e5057 | Pole | HFTD Tier 2 | Distribution | 2024-03-28 | 2029-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006653 | ad581a73-2d0d-41d7-8959-ef7f1a492d27 | Pole | Non-HFTD | Distribution | 2024-03-28 | 2025-03-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006654 | 5b7425b9-ec1f-44d6-a434-05e152179e04 | Pole | HFTD Tier 2 | Distribution | 2024-03-28 | 2025-03-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006655 | c088508e-259c-4315-8076-0ac742319634 | Pole | Non-HFTD | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006656 | 5db89488-50b0-431f-8e09-50930dce2e69 | Pole | Non-HFTD | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006657 | 9e0fc55b-c5b4-4425-a438-2be37a636ee5 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006658 | 4fc81fd9-a0cb-456a-a3ff-7728341a86a7 | Pole | Non-HFTD | Distribution | 2024-04-01 | 2025-04-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006659 | 11f6eaba-f401-4763-9551-7100de3a935c | Pole | Non-HFTD | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006660 | 9e0fc55b-c5b4-4425-a438-2be37a636ee5 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2025-04-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006661 | 11f6eaba-f401-4763-9551-7100de3a935c | Pole | Non-HFTD | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006662 | 14a43bb0-3ff9-45cb-9a27-73f069a23623 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2025-04-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006663 | f4d457f0-a87d-4413-9d26-7f60006415f4 | Pole | Non-HFTD | Distribution | 2024-04-01 | 2025-04-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006664 | 14a43bb0-3ff9-45cb-9a27-73f069a23623 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006665 | 6d58b5cd-ece2-4fa0-a593-b8aad67fba97 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006666 | 14a43bb0-3ff9-45cb-9a27-73f069a23623 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006667 | 4cc498c5-92d8-4c51-8e06-078ffba4eb62 | Pole | Non-HFTD | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006668 | f4da0ddf-2551-4329-8cd4-3da4fd0717f5 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2025-04-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006669 | 6d58b5cd-ece2-4fa0-a593-b8aad67fba97 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006670 | 0bf5b973-1b73-4830-9cf6-02cf5caa5851 | Pole | Non-HFTD | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006671 | 73a8e626-5de4-4eb6-98b2-c8cf173b9ae0 | Pole | HFTD Tier 2 | Distribution | 2024-04-01 | 2029-03-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006672 | dd98357f-61b2-4eb0-8f13-764dca80f012 | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2025-04-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006673 | dd98357f-61b2-4eb0-8f13-764dca80f012 | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2029-04-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006674 | ef8f1f0e-243b-4436-9177-c42b499d58bf | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2029-04-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006675 | 2cde91a4-9fcc-45e0-8444-b28273af62eb | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2025-04-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006676 | 96ec34ed-a9c9-42f5-9db0-5622776385f9 | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2029-04-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006677 | 2cde91a4-9fcc-45e0-8444-b28273af62eb | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2029-04-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006678 | f56804fc-3689-4a62-8033-60a06aaab1a0 | Pole | HFTD Tier 2 | Distribution | 2024-04-03 | 2025-04-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006679 | 9c48e29b-8eda-40da-904c-7d49621bedf3 | Pole | HFTD Tier 2 | Distribution | 2024-04-03 | 2025-04-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006680 | 139d70af-bad5-47fc-8a70-0312169234a1 | Pole | HFTD Tier 2 | Distribution | 2024-04-04 | 2029-04-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006681 | 60e7b89f-a117-4ef1-b1a7-3ed407130574 | Pole | HFTD Tier 2 | Distribution | 2024-04-04 | 2029-04-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006682 | d03630f3-5959-4c82-8761-939af74d07cc | Pole | HFTD Tier 2 | Distribution | 2024-04-04 | 2029-04-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006683 | 60e7b89f-a117-4ef1-b1a7-3ed407130574 | Pole | HFTD Tier 2 | Distribution | 2024-04-04 | 2029-04-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006684 | 9a079843-d426-4e9e-8e34-a0481853a430 | Pole | HFTD Tier 2 | Distribution | 2024-04-04 | 2029-04-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006685 | ad0c9bdc-62f8-499d-97b4-2dc743703d15 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006686 | c1359a59-ff03-4ee4-8d83-b0b7efce9bfc | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006687 | df4221a0-3b50-4083-8903-d662548cd015 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006688 | bb84cf7c-c478-435b-a8ed-382c93ad30aa | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006689 | 99ee6d33-8359-4119-9f4e-24fb9035d317 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006690 | bc9b46c6-6aeb-4909-b068-35331b542d05 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006691 | bc9b46c6-6aeb-4909-b068-35331b542d05 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006692 | 17b76e55-42d5-4a01-842e-349df46d3258 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006693 | 41fe3082-c57c-448b-9cae-559a68df01f8 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006694 | 1c712063-8174-4efe-97d5-0ed26232b82c | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2025-04-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006695 | 41fe3082-c57c-448b-9cae-559a68df01f8 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006696 | 1c712063-8174-4efe-97d5-0ed26232b82c | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006697 | f4b1bdd8-7609-497b-bc1e-9b86f12c98f4 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006698 | b1297ea4-f874-41dd-adb6-56089dff252c | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2025-04-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006699 | e415933e-db61-4b61-9f9e-ca30770a721f | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006700 | b1297ea4-f874-41dd-adb6-56089dff252c | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006701 | 47bd6bfe-1444-4c3c-8c70-92113bb07578 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006702 | cb0b459f-89d7-4bfb-810d-0ce685a0f680 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006703 | 4863b8cc-de62-4c98-8eed-eccd7887d849 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006704 | 64159d0d-7921-43c7-80c2-c9fa4ee32d2d | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006705 | 7447700b-dd6d-4e06-a345-86c4f0c26d53 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006706 | 7447700b-dd6d-4e06-a345-86c4f0c26d53 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006707 | 7447700b-dd6d-4e06-a345-86c4f0c26d53 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2025-04-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006708 | e415933e-db61-4b61-9f9e-ca30770a721f | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006709 | 6a5ef596-c07a-477b-892d-b896d7dccc05 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006710 | 1bca9513-aa59-495e-9289-2d15249cf957 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006711 | 2a9f629b-4b25-45de-8535-5b3231713bb8 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2029-04-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006712 | 58fe6693-23fc-4514-a659-cd6d3b87434b | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006713 | 3ef025fb-1dfc-4718-b179-9f9c274c1059 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006714 | 531b91d7-eb69-4156-9b85-fe2a352c0920 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006715 | 61edabc9-49b7-44bb-b2b3-677824fb89bb | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006716 | 1f47a65c-c391-42c0-af37-f1fadd13cf30 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006717 | 08294efb-08cb-4fa2-8468-d59dcfd56537 | Pole | Non-HFTD | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006718 | 2d844a88-0f49-4026-b614-6ef48dff6531 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006719 | 1a6ebf54-1445-427e-aac5-055e04ea7f27 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006720 | e4978102-d4cb-4586-abff-e3e28198a36b | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006721 | bd505ee7-4837-4efe-86d1-3f8e1df972bb | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006722 | 7be9c0f0-9e42-46f1-b0a9-5c81537c1b42 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006723 | 0ceeff65-0572-4ed1-97ce-245e19533840 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006724 | 71dee382-528b-4c29-8d27-9692cadd8c5c | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006725 | ea51014e-d4e3-4958-b088-9a6bcd983b98 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006726 | fb6962dc-8852-4c49-bd31-7e37aa542697 | Pole | Non-HFTD | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006727 | b5d5e32b-d3ca-4886-b058-9bdb83d50d38 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006728 | 1bfb5b29-bb03-4096-9134-ca77be79bc62 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2025-04-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006729 | 8860302e-7173-4cbe-8a91-bc68e45831ad | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2029-04-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006730 | 58391a71-f82a-43a8-8f84-d1a21051a6f1 | Pole | HFTD Tier 2 | Distribution | 2024-04-10 | 2029-04-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006731 | f081eec0-a506-4af0-a854-3fc093bb89dc | Pole | HFTD Tier 2 | Distribution | 2024-04-11 | 2025-04-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006732 | 21d7e080-7661-47aa-8c0c-2599d722b9f6 | Pole | HFTD Tier 2 | Distribution | 2024-04-11 | 2029-04-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006733 | 04b097fe-12bb-40e9-af69-37f040578a1c | Pole | HFTD Tier 2 | Distribution | 2024-04-11 | 2029-04-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006734 | 04b097fe-12bb-40e9-af69-37f040578a1c | Pole | HFTD Tier 2 | Distribution | 2024-04-11 | 2029-04-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006735 | 81031c96-fe20-47c8-be0d-97a360e79b2f | Pole | Non-HFTD | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006736 | 6e696b53-ebd6-45b0-a1a6-2879dc7449b8 | Pole | Non-HFTD | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006737 | 2124c400-61be-4cf8-a515-e2ea8e4a73df | Pole | HFTD Tier 2 | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006738 | cf3054da-1212-41d1-82ba-ebca9c75bab9 | Pole | HFTD Tier 2 | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006739 | 0e3e6319-7184-4e73-8f0f-d3e7fbeee194 | Pole | HFTD Tier 2 | Distribution | 2024-04-12 | 2025-04-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006740 | 04e29a53-390e-465b-9e53-29d405dcff16 | Pole | Non-HFTD | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006741 | c24624f8-e1fe-4d20-a9fc-81e64ce97adc | Pole | HFTD Tier 2 | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006742 | 943c45f9-d8bc-4502-bf2c-ea13f7cfb98f | Pole | HFTD Tier 2 | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006743 | f86ea6ed-a1a5-4814-aab1-dca517003c22 | Pole | Non-HFTD | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006744 | c26c2e84-ace9-421c-8885-29ec0db9a755 | Pole | HFTD Tier 2 | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006745 | c5e8e113-336f-435b-8c68-83a54a379a63 | Pole | Non-HFTD | Distribution | 2024-04-12 | 2025-04-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006746 | adea5487-6f3d-4516-aaa9-86270dfd9158 | Pole | Non-HFTD | Distribution | 2024-04-12 | 2029-04-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006747 | 653bb891-4f89-456e-a16b-4e845b6f8ad1 | Pole | HFTD Tier 2 | Distribution | 2024-04-15 | 2029-04-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006748 | b238880e-43f8-497d-8d01-a1bd856cea5f | Pole | HFTD Tier 2 | Distribution | 2024-04-15 | 2029-04-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006749 | 2ca96f70-8000-4ed1-a236-d5a17e4966d6 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2029-04-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006750 | 35fce8c5-bf28-4098-87d0-1123f5c01823 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2025-04-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006751 | e4baae82-77c6-4692-b7b3-11c2c5948d56 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2025-04-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006752 | 35fce8c5-bf28-4098-87d0-1123f5c01823 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2029-04-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006753 | 9495412e-9bdd-45eb-b8a1-324898697e02 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2029-04-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006754 | f6b9fe75-fb1f-475b-abb1-c9b7693a4c9b | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2025-04-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006755 | 3241456d-b2d8-4a6c-bb87-bd18dcce10ac | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2029-04-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006756 | 9495412e-9bdd-45eb-b8a1-324898697e02 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2025-04-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006757 | 9495412e-9bdd-45eb-b8a1-324898697e02 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2025-04-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006758 | 3241456d-b2d8-4a6c-bb87-bd18dcce10ac | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2029-04-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006759 | b3c45a90-b555-44bc-8b1b-989dc54ba934 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2029-04-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006760 | f988fccc-0d90-4f06-93a3-1a8f302aefe7 | Pole | HFTD Tier 2 | Distribution | 2024-04-17 | 2029-04-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006761 | c94467e6-d16a-4a54-8db2-6106b8f1a6d8 | Pole | HFTD Tier 2 | Distribution | 2024-04-17 | 2029-04-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006762 | 5b06aa64-7bde-4718-9752-6855f791b23f | Pole | HFTD Tier 2 | Distribution | 2024-04-17 | 2029-04-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006763 | 5b06aa64-7bde-4718-9752-6855f791b23f | Pole | HFTD Tier 2 | Distribution | 2024-04-17 | 2029-04-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006764 | 8e10f8fd-d05c-493a-b318-663208a5f125 | Pole | HFTD Tier 2 | Distribution | 2024-04-17 | 2029-04-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006765 | 5b06aa64-7bde-4718-9752-6855f791b23f | Pole | HFTD Tier 2 | Distribution | 2024-04-17 | 2025-04-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006766 | c94467e6-d16a-4a54-8db2-6106b8f1a6d8 | Pole | HFTD Tier 2 | Distribution | 2024-04-17 | 2029-04-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006767 | f61bf9d9-e273-43ac-8b33-ca390e2be8f0 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2025-04-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006768 | c9c67f46-e936-4c49-b643-decfdb68000e | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006769 | f61bf9d9-e273-43ac-8b33-ca390e2be8f0 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2025-04-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006770 | f61bf9d9-e273-43ac-8b33-ca390e2be8f0 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006771 | 415a137b-a1de-41f7-952d-5dff704db555 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006772 | 7db8e149-37f6-428e-b892-a52c34ad2704 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006773 | 415a137b-a1de-41f7-952d-5dff704db555 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006774 | e58e6e19-f5b9-4714-bb1f-66af8253d665 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006775 | c9c67f46-e936-4c49-b643-decfdb68000e | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006776 | e58e6e19-f5b9-4714-bb1f-66af8253d665 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2025-04-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006777 | c9c67f46-e936-4c49-b643-decfdb68000e | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006778 | e58e6e19-f5b9-4714-bb1f-66af8253d665 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2025-04-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006779 | 2207fa4a-654f-43b0-9657-7dc63f79e1c9 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006780 | 2207fa4a-654f-43b0-9657-7dc63f79e1c9 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006781 | 2207fa4a-654f-43b0-9657-7dc63f79e1c9 | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006782 | 97256a7e-c06d-4b9d-b0b9-c9c6580469fb | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006783 | a0d0aa50-b28e-459e-9617-25f7689a6ebf | Pole | HFTD Tier 2 | Distribution | 2024-04-18 | 2029-04-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006784 | a2704c3f-d4c3-4a87-99bf-1d0f9acf72c8 | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006785 | a2704c3f-d4c3-4a87-99bf-1d0f9acf72c8 | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006786 | 4e8b2df8-b343-43d0-919c-30b33ce47148 | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006787 | 5bbe6924-324b-4ce3-95ef-c7ddf95b1cb6 | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006788 | fbaff4c1-96e3-44c3-bb60-c466472bd1db | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006789 | fbaff4c1-96e3-44c3-bb60-c466472bd1db | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006790 | 89243e66-510e-44c1-ac35-b1adb28ae99f | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006791 | 0714200d-366d-464b-bf4a-8cf740fe383e | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006792 | 0714200d-366d-464b-bf4a-8cf740fe383e | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006793 | eb2f4621-499f-4eb5-a075-ce7cc9297c24 | UG Transformer | HFTD Tier 2 | Distribution | 2024-04-24 | 2029-04-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006794 | d8005513-12a9-4de2-9518-1d7a59466307 | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006795 | 858d666e-3913-476f-9e46-4752c1a5d7e4 | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006796 | efc47380-1ad0-45e0-9bbd-1129f51031df | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2025-04-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006797 | 0d4f9f30-79ed-44d5-950d-ded01495d4b3 | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006798 | fe12bca0-9462-428c-bb6d-ef5ba7750a0f | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2025-04-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006799 | d8005513-12a9-4de2-9518-1d7a59466307 | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006800 | 5b3094e0-f435-4cb5-8f11-ca51a45afdb9 | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006801 | 178b60a9-1fca-41da-a4e8-4443065e0e9d | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006802 | 5b3094e0-f435-4cb5-8f11-ca51a45afdb9 | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006803 | fe12bca0-9462-428c-bb6d-ef5ba7750a0f | Pole | HFTD Tier 2 | Distribution | 2024-04-26 | 2029-04-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006804 | 99d28f97-d0a5-4e8b-b037-10f667ae5cca | Pole | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006805 | 01fd8357-c2c0-4838-9c09-0164c5b0ef2c | Pole | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006806 | 0bba709a-bf6d-45be-a2d3-e0e1a4cf43eb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006807 | 162cd156-b460-45c7-82fc-4a859a70dd35 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006808 | ee24178a-9130-4ebb-bd7c-16150a8b5334 | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006809 | 162cd156-b460-45c7-82fc-4a859a70dd35 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006810 | e083317e-3e60-491f-af5d-7ebb15a16053 | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006811 | 0ad24e10-675c-4080-a534-2c6f7b04625e | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006812 | 24fbd4f8-4f61-4bd7-ae1a-90e1269a36fb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006813 | ee24178a-9130-4ebb-bd7c-16150a8b5334 | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006814 | c37e8ec4-3f8f-4784-aa09-ad802d7b6cce | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2025-04-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006815 | e88a415d-4325-4483-a077-428eca2efd38 | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006816 | 7a192bed-cdbc-4e0f-84ee-c24ee391894f | UG Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2025-04-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006817 | 162cd156-b460-45c7-82fc-4a859a70dd35 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006818 | da2002ff-f7d7-495e-b3c5-3a5eabc79a86 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-04-30 | 2025-04-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006819 | 43e6950a-a0a2-4d1c-bb2e-51de3911b8a4 | Pole | HFTD Tier 3 | Distribution | 2024-05-01 | 2029-04-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006820 | 7b8736b5-64fb-436f-9511-7b76d27cf325 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-01 | 2025-05-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006821 | 43e6950a-a0a2-4d1c-bb2e-51de3911b8a4 | Pole | HFTD Tier 3 | Distribution | 2024-05-01 | 2029-04-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006822 | 7b8736b5-64fb-436f-9511-7b76d27cf325 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-01 | 2025-05-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006823 | 3b8fe45a-d7c3-4f57-9d5d-fb8a6d10ca30 | Pole | HFTD Tier 3 | Distribution | 2024-05-01 | 2029-04-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006824 | 88b67910-252b-47db-9572-b364c4d23583 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-04-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006825 | 6a8493a7-c56f-489d-8f87-84cfe96541c2 | Pole | HFTD Tier 3 | Distribution | 2024-05-01 | 2029-04-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006826 | 3bcbc333-ef18-4428-ad36-11f3748c6436 | Pole | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-04-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006827 | 91433092-cdd7-47aa-bddd-c1753a880344 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006828 | e462fe93-0536-45f3-b8b6-77d80e7379fb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006829 | ce6db9c7-9922-4f25-ba5c-82e9a69c999a | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006830 | 1f86df81-c99f-45bb-aff3-c8ccfae8f79c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006831 | 7381c505-fbca-47bd-a3a4-bdb283602288 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006832 | 27abceee-78bf-4826-9569-cd913d05d6f4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006833 | 27abceee-78bf-4826-9569-cd913d05d6f4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006834 | 31981125-bff8-4478-8c0b-2c3f2aac2e1b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006835 | eb988988-9328-46c4-878f-dbf40fdd50d4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006836 | f7012d56-cc8a-4719-af8e-a442991fff35 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006837 | bd7404c6-999e-4cb0-a6e5-4bcf657155a5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006838 | a1d0a89d-7075-47d3-83bb-6289e795013e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006839 | bd7404c6-999e-4cb0-a6e5-4bcf657155a5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006840 | 0fd54a79-ea84-415c-83bf-91709f905767 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006841 | bd7404c6-999e-4cb0-a6e5-4bcf657155a5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2025-05-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006842 | f7012d56-cc8a-4719-af8e-a442991fff35 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006843 | e462fe93-0536-45f3-b8b6-77d80e7379fb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006844 | 8e96c690-980e-4383-8196-76e966498264 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006845 | a8f63a65-70de-4d88-8268-fd8ab69b72ce | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006846 | 8b01fc9e-cbcb-421a-ac22-1866ba2a6c3e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006847 | cb48ad7b-0587-4e0c-851c-5220410f5e2b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006848 | 8864d6dd-5a66-49fa-9f57-74c13da15119 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006849 | cb48ad7b-0587-4e0c-851c-5220410f5e2b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006850 | 41288d06-395b-40e5-9884-88069b02eb2e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006851 | 438a91d7-1656-4730-834a-4a8d3fe815a1 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006852 | d2bc90c3-a091-48e0-ac87-38c4c2f0b8d9 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006853 | 2d0254bf-5e99-4834-97bf-7e1339033db9 | Pole | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006854 | 58f81c81-198d-44c7-a443-53b97ac808e3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006855 | 0c96a9d8-c5f9-4b4e-afbb-265d8e13898b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006856 | e708c717-963f-4f49-ac0d-4f491a914a43 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006857 | 0c96a9d8-c5f9-4b4e-afbb-265d8e13898b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006858 | 5fdccde2-4ad8-4fed-8cf6-8b65435de3f1 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006859 | 8e96c690-980e-4383-8196-76e966498264 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006860 | 525c4a88-5f5f-45fd-b63d-c146305815ee | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006861 | b370b29e-ea08-4972-8507-a768eba4893d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006862 | 525c4a88-5f5f-45fd-b63d-c146305815ee | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006863 | b370b29e-ea08-4972-8507-a768eba4893d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006864 | 525c4a88-5f5f-45fd-b63d-c146305815ee | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006865 | b370b29e-ea08-4972-8507-a768eba4893d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006866 | 4bb3f2dd-894f-4e59-942b-b542b708b705 | Pole | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006867 | 30193e7b-473c-4846-8414-f73806a92b15 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006868 | a8f63a65-70de-4d88-8268-fd8ab69b72ce | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006869 | 45d2c245-5a4d-4cb8-a370-8ebb627301c5 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006870 | a8f63a65-70de-4d88-8268-fd8ab69b72ce | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006871 | 5c9cf1fa-36d2-4f91-8c8a-2e9a78e44f2b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006872 | 438a91d7-1656-4730-834a-4a8d3fe815a1 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006873 | 5c9cf1fa-36d2-4f91-8c8a-2e9a78e44f2b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006874 | 5c9cf1fa-36d2-4f91-8c8a-2e9a78e44f2b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006875 | 30193e7b-473c-4846-8414-f73806a92b15 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006876 | af8c0176-9495-4138-af30-00a7d7d5252a | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006877 | 8864d6dd-5a66-49fa-9f57-74c13da15119 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006878 | 7d69d156-5b8b-40ec-a025-feee69003cfb | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006879 | 7d69d156-5b8b-40ec-a025-feee69003cfb | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-03 | 2029-05-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006880 | 3f0c8a18-5dbc-4e26-ac37-8d6607ee18b0 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006881 | 587df27c-3151-4d8b-be65-f6edc8a1b7c5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006882 | 65da571b-46d4-484c-bac3-d7d531625821 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006883 | 8c6a1c97-97f0-4a7d-bf1c-4a5888657c56 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006884 | 7349fd96-e8c1-433f-bdf9-dbea94bf12cc | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006885 | 0df6a187-8fe9-4cc6-b514-ecc1761a5028 | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006886 | 85ee6927-4a1a-4943-bd9d-e5d6faa8c518 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006887 | 0df6a187-8fe9-4cc6-b514-ecc1761a5028 | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006888 | c07ffae7-69a5-49d9-8480-dd336783993a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006889 | 96122a3d-a10e-45eb-8cca-54aeb37423f4 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006890 | a8029143-cafb-422f-9059-54a477aaefca | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006891 | 96122a3d-a10e-45eb-8cca-54aeb37423f4 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006892 | a8029143-cafb-422f-9059-54a477aaefca | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006893 | 96122a3d-a10e-45eb-8cca-54aeb37423f4 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006894 | 859fa800-cb7c-4c47-9d58-e60f74ca69bf | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006895 | 49f88f71-c6fc-4d0d-993b-94a316a1401f | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006896 | 859fa800-cb7c-4c47-9d58-e60f74ca69bf | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006897 | 49f88f71-c6fc-4d0d-993b-94a316a1401f | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006898 | c4f76e2f-7407-4b9b-9b2a-75c3986c8511 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006899 | d6489d2b-2534-4eae-8f79-e8975e776ec6 | Padmount-Ã¡Switch | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006900 | fb446473-d0eb-4a9c-b1da-eb93b4747f3d | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006901 | 7349fd96-e8c1-433f-bdf9-dbea94bf12cc | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006902 | 3697255f-ab0f-4275-acdc-40cc96afc2d4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006903 | 8ab7eee5-ab5f-405f-9e84-456ecf618b62 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006904 | 3697255f-ab0f-4275-acdc-40cc96afc2d4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006905 | b9062607-6139-4575-b8cf-f2ead8fda325 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006906 | d8cdb439-0cf4-4e8c-9a71-d8d728c39108 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006907 | b9062607-6139-4575-b8cf-f2ead8fda325 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006908 | 8c6a1c97-97f0-4a7d-bf1c-4a5888657c56 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006909 | c07ffae7-69a5-49d9-8480-dd336783993a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006910 | 0df6a187-8fe9-4cc6-b514-ecc1761a5028 | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006911 | 5f770bfb-f698-4e16-82d6-19b05ff5155a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006912 | 099544bf-7087-4437-b430-a3d255139199 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006913 | 5a64b8de-0f9e-4d13-b4fd-5a510e11fd0d | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006914 | 0c8e0e3e-18bc-4890-b3ad-a9f8d37a22fb | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006915 | fb446473-d0eb-4a9c-b1da-eb93b4747f3d | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006916 | 96122a3d-a10e-45eb-8cca-54aeb37423f4 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006917 | fb446473-d0eb-4a9c-b1da-eb93b4747f3d | UG Transformer | Non-HFTD | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006918 | 6c86b983-0c97-4945-bc0e-3dce65026466 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006919 | 65da571b-46d4-484c-bac3-d7d531625821 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2025-05-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006920 | 65da571b-46d4-484c-bac3-d7d531625821 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006921 | d08c7e25-3434-48cf-b6ff-6f9f4fe522e7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006922 | c40329b1-ff35-4bf7-bf42-d8cebbb4dc7d | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006923 | a598b90a-436c-425b-9037-d6b629233318 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006924 | 4bc6e269-2dbc-4903-b165-fcb16daff69a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006925 | 6e070f51-923c-4e6a-9792-cff90a515767 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006926 | 53bab15b-cdcb-40b4-b078-cb183bbcb391 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006927 | 3c2403fa-08a1-4684-aecb-fb0e82847a13 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006928 | f133fda5-de76-4950-b6d0-d43dbfbcfd23 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006929 | 6a87a042-dccc-47e2-8f53-7622ced9f689 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006930 | b56f6120-337f-4610-aeba-89297bd68264 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006931 | 82d32094-74a2-4053-b496-8a48f4eb0e65 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006932 | 55be7bb6-5eac-429b-bf8c-69e564515658 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006933 | 043d6274-4743-4d9d-948a-80df7759f8d4 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006934 | 55be7bb6-5eac-429b-bf8c-69e564515658 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006935 | 97881f62-e364-46ad-a241-493e9e80408f | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006936 | d175c1fb-ed13-4876-be5e-9916dcb19f4f | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006937 | eff6ba75-99ac-4b47-9268-81d7d7e9c772 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006938 | 3c2403fa-08a1-4684-aecb-fb0e82847a13 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006939 | d175c1fb-ed13-4876-be5e-9916dcb19f4f | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006940 | 3c2403fa-08a1-4684-aecb-fb0e82847a13 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006941 | c40329b1-ff35-4bf7-bf42-d8cebbb4dc7d | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006942 | 6a87a042-dccc-47e2-8f53-7622ced9f689 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006943 | c40329b1-ff35-4bf7-bf42-d8cebbb4dc7d | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006944 | 043d6274-4743-4d9d-948a-80df7759f8d4 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006945 | f133fda5-de76-4950-b6d0-d43dbfbcfd23 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006946 | 97881f62-e364-46ad-a241-493e9e80408f | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006947 | 3a2a3497-ce7b-4f8c-b8b3-1ae68167ac87 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006948 | eff6ba75-99ac-4b47-9268-81d7d7e9c772 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006949 | 9a206726-1e50-4c7c-bdc3-75f7a973eff7 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006950 | 9a206726-1e50-4c7c-bdc3-75f7a973eff7 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006951 | b0d9b71f-09bf-49f7-87e1-02b1aec60a5a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006952 | eda0197a-475e-4e43-87be-980910d05520 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006953 | a598b90a-436c-425b-9037-d6b629233318 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2025-05-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006954 | 6e070f51-923c-4e6a-9792-cff90a515767 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-07 | 2029-05-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006955 | 8020b065-d4ca-450f-8d0d-306cba346663 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006956 | 50b35d34-8510-4508-b109-9ffb13c59a5e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006957 | c30ccbd0-f893-441e-9ce8-0a3ef94f4750 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006958 | 50b35d34-8510-4508-b109-9ffb13c59a5e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006959 | dd372591-863d-45a1-9cf7-1494f20ab365 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006960 | bdfa1737-2a84-43d9-a8c4-2f32b2beeea1 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006961 | d5d13e0b-9dbf-441a-bc5a-c2372a25f6fa | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006962 | d557d9af-846f-4742-a164-fa1138fd176f | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006963 | 02d81790-5348-4682-87c7-36b3f133b266 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2025-05-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006964 | 14fee142-172b-421c-8ea0-bd0296050cf7 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006965 | b72316b7-d835-4c84-820f-bd8200ff0f95 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006966 | dd372591-863d-45a1-9cf7-1494f20ab365 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2025-05-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006967 | d3cb28ff-6c8e-49d2-8c59-64e3d2298097 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2025-05-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006968 | d5d13e0b-9dbf-441a-bc5a-c2372a25f6fa | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006969 | e1b99598-3fa1-4d26-b0a5-1afe44b97b20 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006970 | b72316b7-d835-4c84-820f-bd8200ff0f95 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006971 | e1b99598-3fa1-4d26-b0a5-1afe44b97b20 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006972 | d3cb28ff-6c8e-49d2-8c59-64e3d2298097 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006973 | 69071d01-2ae3-4659-b036-b511219a3c7f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006974 | d3cb28ff-6c8e-49d2-8c59-64e3d2298097 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006975 | 6193e6e8-0175-44f8-bb2a-d273838c06c2 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006976 | f765ed55-f6ea-4444-bffc-1b951ed17615 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2025-05-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006977 | 930aab14-e88f-40aa-8185-05066a778ddf | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006978 | f765ed55-f6ea-4444-bffc-1b951ed17615 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006979 | 660fbb59-381a-47fa-bd7e-74e774bdec4f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006980 | c8769661-c570-47ed-bea7-9a1b840374e9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006981 | 7748dd36-8aa6-4b87-9359-d958686326f6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2025-05-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006982 | 7748dd36-8aa6-4b87-9359-d958686326f6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-08 | 2029-05-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006983 | b04f5436-a1a3-4b3a-848b-3fbe5488fa34 | UG Transformer | Non-HFTD | Distribution | 2024-05-09 | 2025-05-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006984 | a0d4cd2a-e440-4e96-8236-001c0c7026d1 | Pole | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006985 | b804b49e-8dd3-4d09-a293-ec688f87a293 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006986 | 4004a5ec-441b-42a1-b168-0d67cf8be243 | Pole | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006987 | b804b49e-8dd3-4d09-a293-ec688f87a293 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006988 | 4befb773-a209-42a1-b185-b1b9ab449006 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006989 | 1bd4494e-d439-42eb-a2a9-ce40f8edd4de | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006990 | 8f1430ac-290e-41b6-8ffc-3458f697aae3 | UG Transformer | Non-HFTD | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006991 | f1feb2be-6f8b-49d7-a916-abc37a6050ce | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006992 | 608ab463-29ba-40c0-a742-8f098213120c | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006993 | 605373af-2d15-4aaa-87f8-5ae421a34cc7 | Pole | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006994 | e671cf69-66a4-4634-b171-f0ec9b616d82 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006995 | 4befb773-a209-42a1-b185-b1b9ab449006 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006996 | c8d50956-d4ff-48e0-84fc-382f140128e5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2025-05-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130006997 | 9ab0d771-1097-41e5-b0cc-3d6c35a81ac2 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006998 | 1bd4494e-d439-42eb-a2a9-ce40f8edd4de | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130006999 | 4916ff0f-66e2-4922-a2f6-6027ccc81c79 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007000 | f1feb2be-6f8b-49d7-a916-abc37a6050ce | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007001 | feeb8506-eb8d-4b06-8363-abb6951be0c6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-09 | 2029-05-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007002 | 7e3ded4c-ce8a-45c1-a052-2bfe4ab645e6 | Pole | Non-HFTD | Distribution | 2024-05-10 | 2025-05-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007003 | 4106be3a-1bfd-4939-9714-8224bfba42bb | Pole | Non-HFTD | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007004 | 76d2215d-731c-4423-95aa-4033ae950c0e | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007005 | a238d16d-a14f-4871-98d9-07bbad7751d8 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007006 | e8cc5adb-fbef-4886-b464-565e71078362 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007007 | b548e4e1-688e-4c18-b388-0aa5bdbbaedb | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007008 | ee34ad01-9195-44e3-ba24-94bf95fba819 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007009 | 7c286cb4-3008-4cf2-ad1b-caf50d82483c | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007010 | 97ef3ccd-bd30-4e44-9ed0-912b8181944e | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-05-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007011 | 834c52d3-4976-4c48-8d4c-d2f6c5622bed | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007012 | 1dcd76be-0f21-4a37-93c7-f4aae2d5fd06 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007013 | b3c20874-324f-4a5d-b06b-68ce59747492 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007014 | c35e48c9-cb69-4aad-aac9-3e46e9aac686 | Pole | Non-HFTD | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007015 | 8391e02a-cb83-44dd-afd1-42511673febb | Pole | Non-HFTD | Distribution | 2024-05-10 | 2029-05-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007016 | 549a3ce3-af15-49b5-89af-5f5489c20268 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007017 | 81c37b41-519c-4af9-b229-0e0dbe70766f | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007018 | 549a3ce3-af15-49b5-89af-5f5489c20268 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007019 | 81c37b41-519c-4af9-b229-0e0dbe70766f | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007020 | 0fcb652e-e131-4a05-a123-292188b9930d | Pole | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007021 | 721bc90c-976f-4fd9-8ded-f81c8fb7d002 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007022 | a86ac48f-a691-4cb0-b15f-a5b76bd98cd6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007023 | 96f19cfa-a6eb-4f2e-95d1-b6d280f13566 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007024 | 0669ed1c-30f8-407f-b908-0afb52d0c465 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007025 | 9e36f5eb-8bd7-4a0b-b936-e444de99cfe7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007026 | 4941133f-fac2-4d43-a084-c3b0e2f2084f | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007027 | 7e3d4073-aa90-4ac0-916b-6a3d327e6c0a | Pole | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007028 | afada7be-14e0-48af-aae0-b1de79eb4e12 | Pole | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007029 | f933c2b1-3949-4b10-9c12-22d81d0db69e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007030 | 831ea914-350d-4601-a560-e400e747137a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007031 | bfbfe9de-1584-4fbf-95c7-38258e7df142 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007032 | 544d68b7-34ba-4f25-9ccf-e81a6a7a1a64 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007033 | 1dab73cb-9415-4d95-bc9b-f2e5308b8e33 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007034 | 9221e35a-edc8-47ef-8ca4-9542949c6dbb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2025-05-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007035 | 02ffe6c6-def9-4d77-a69d-0c19c33d1f0a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007036 | a2f886c3-6f99-4880-a1a0-a0500f597080 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007037 | 5a5c7af4-b01a-4428-94cd-4daebb3521d5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007038 | ebfb190c-7552-432e-912c-a03c0e8ba2c1 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2025-05-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007039 | 9844d650-974b-4eb4-a30b-cb146d59a3e9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2025-05-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007040 | c7b6b56c-f8b0-4a66-9df6-2d9ec781d19e | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007041 | c7b6b56c-f8b0-4a66-9df6-2d9ec781d19e | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-13 | 2029-05-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007042 | 771edbad-28f7-4a8f-97a8-f645a57e9177 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007043 | 771edbad-28f7-4a8f-97a8-f645a57e9177 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007044 | 589a71cf-f94b-4514-93a0-af1e5205c2c3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007045 | ee90b9e9-bb43-4e36-80a9-3c1f207bf38e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007046 | ee90b9e9-bb43-4e36-80a9-3c1f207bf38e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007047 | 5d4f22e0-2e84-4aa0-8477-eea15c303714 | UG Transformer | HFTD Tier 3 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007048 | 0d6211bd-f93f-4daa-a39e-03e9502ea114 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007049 | 0d6211bd-f93f-4daa-a39e-03e9502ea114 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007050 | 7209e22c-5cc3-4196-a9ef-342f18a6c70f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2025-05-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007051 | 7209e22c-5cc3-4196-a9ef-342f18a6c70f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007052 | b06bd0c5-8bbf-49b4-bd42-6f3b5a686af8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007053 | a8aefea2-8e7a-4cfe-a9e3-70873b922382 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007054 | 6f54ae50-4c93-484f-a329-7db3b91aa9a4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007055 | a8aefea2-8e7a-4cfe-a9e3-70873b922382 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007056 | f5b3ec57-3ec6-496c-84af-fbcb1b913560 | Padmount-Ã¡Transformer | HFTD Tier 3 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007057 | 85e9f6d9-d2c6-4674-bcde-9784cee426b3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007058 | 3cf9e2a6-cedf-4e63-8272-86fd0fd840d3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007059 | f5b3ec57-3ec6-496c-84af-fbcb1b913560 | Padmount-Ã¡Transformer | HFTD Tier 3 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007060 | 3cf9e2a6-cedf-4e63-8272-86fd0fd840d3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-14 | 2029-05-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007061 | f870a5bb-0694-48a2-92bb-987697265c56 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-15 | 2025-05-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007062 | f870a5bb-0694-48a2-92bb-987697265c56 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007063 | a207c352-d5cc-44c6-94b5-53e4e3cc1bc1 | Pole | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007064 | f870a5bb-0694-48a2-92bb-987697265c56 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007065 | d72dd533-5f50-4f93-be22-552cae077aff | Pole | Non-HFTD | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007066 | 82e75801-d7c7-417e-ae05-0d8c82105551 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007067 | 6fe9e18c-a593-4c1b-b3a2-e10dd1443c17 | Pole | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007068 | 82e75801-d7c7-417e-ae05-0d8c82105551 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007069 | 82dee2dc-0bbf-42c2-aa40-82a566e64c33 | Pole | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007070 | 247af2d1-7856-4935-9c72-908069489955 | Pole | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007071 | a207c352-d5cc-44c6-94b5-53e4e3cc1bc1 | Pole | HFTD Tier 2 | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007072 | 71f3b291-35d7-4583-9f16-031af88848b8 | Pole | Non-HFTD | Distribution | 2024-05-15 | 2029-05-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007073 | 5755766b-c47c-4b0a-8c67-6f8e7d22430c | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007074 | 51007c40-7a00-4fff-a876-d7fcb0d60758 | Pole | HFTD Tier 2 | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007075 | 5755766b-c47c-4b0a-8c67-6f8e7d22430c | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007076 | 192cfbdb-c3d8-4548-b8c3-1a315b44ca3f | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007077 | 01ab169f-be75-406f-b8c9-d519d33dec7e | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007078 | f5c436dd-5fd4-4f7d-916d-742e2d4af9d5 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007079 | d146c3f9-7585-45e6-bc51-4373ee7257ce | Pole | HFTD Tier 2 | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007080 | 25eaafc0-bbc1-4776-95c9-dc34d96dd049 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007081 | 9f6f2ed0-402b-4277-a1c4-954f22b4b166 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007082 | aba340f8-0208-4025-a6ec-7cfc0ff55384 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007083 | 9f6f2ed0-402b-4277-a1c4-954f22b4b166 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007084 | 15a584fc-5b2a-44a1-96a0-fab567dca7e8 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007085 | c1f685f8-c7ac-40df-8fcc-b2a0ffe02ecb | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007086 | f2995c75-e9fd-4704-b7e6-858d2e3eaf14 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007087 | a74e66e9-af39-41e6-849b-6ffa0d714c1c | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007088 | 9f6f2ed0-402b-4277-a1c4-954f22b4b166 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007089 | 699b2f57-528f-4b9e-93a4-f0898cf5bd48 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007090 | c1f685f8-c7ac-40df-8fcc-b2a0ffe02ecb | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007091 | 46c5f97d-4984-46e5-b092-01b3753d7df6 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007092 | c1f685f8-c7ac-40df-8fcc-b2a0ffe02ecb | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007093 | 51007c40-7a00-4fff-a876-d7fcb0d60758 | Pole | HFTD Tier 2 | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007094 | a74e66e9-af39-41e6-849b-6ffa0d714c1c | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007095 | 57f5e5aa-da65-4686-b202-03aeb8e0f4a0 | Pole | HFTD Tier 2 | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007096 | 8a2cc892-690c-40c5-ba62-c9cc25e6f529 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007097 | 23693063-2a90-4c11-a8b7-2fd9d2658f2d | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007098 | 8a2cc892-690c-40c5-ba62-c9cc25e6f529 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007099 | 3fcb7a6d-679c-44a6-90a2-6777311c250a | Pole | HFTD Tier 2 | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007100 | c0b45256-ab61-46b5-88af-5081f8885532 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007101 | 192cfbdb-c3d8-4548-b8c3-1a315b44ca3f | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007102 | 190cd3fb-e8ea-4ce0-9045-351f2cebda36 | Pole | Non-HFTD | Distribution | 2024-05-16 | 2029-05-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007103 | 79cc27d5-5d50-4178-939d-bef15abb3a22 | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007104 | 47dc81d3-0621-45f8-8665-8a74106312b1 | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007105 | 3d79ec0c-a2a9-4c1c-a6ad-bfcec9a6b22d | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007106 | fc9fca8b-9902-44b1-8b5c-8cb76045941e | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007107 | 079cd41a-eaa1-40d8-89c7-dddecf12c093 | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007108 | 88916860-4c62-4a32-aade-0677318bd6ce | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007109 | 4e4003f8-d16e-47fe-825a-ac990673df2f | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2025-05-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007110 | 6a44f1dc-a8e7-4940-924c-6da491ff70d2 | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2025-05-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007111 | 13289298-cbbe-4902-9d5d-ddd9d3a22e0b | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007112 | 6bb7811c-47ec-4d7d-b44d-5fae77327b7a | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007113 | adae0da2-dc7f-4cb2-b553-0e2bb92ce88e | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007114 | 63fbc24b-9493-437c-a85f-8081cd13f45f | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007115 | 411333ed-d66e-45fb-a97e-5373d524097d | Pole | HFTD Tier 2 | Distribution | 2024-05-20 | 2029-05-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007116 | f3f44cc4-d1ed-4369-86de-57e3a11e7549 | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007117 | b17a6f4d-20b6-4c01-a40d-bb67313d3436 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007118 | 6e53aac0-2f35-4ec6-a6b1-bffafa00c4dd | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007119 | b17a6f4d-20b6-4c01-a40d-bb67313d3436 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007120 | 6af30cc7-0867-41fc-80fa-3f3c16c478e7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007121 | bb76e9a2-3feb-497e-b68e-f9d5b4f3f691 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007122 | f34a0814-c59c-4cd4-b20b-dd592fedf143 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007123 | b0264223-8be9-466a-9093-fa6688e56aa3 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007124 | 04f41587-fe7b-44c9-80ec-4de2ebcce11e | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007125 | b0264223-8be9-466a-9093-fa6688e56aa3 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007126 | 5a1f3aae-eea7-4d80-9762-393cc5f871cf | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007127 | 843caf6f-6a1c-4dff-ac22-380e27948c08 | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007128 | aa4a4f2f-f11a-47c2-b3a0-4119f4a17a48 | Pole | HFTD Tier 2 | Distribution | 2024-05-21 | 2025-05-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007129 | aa4a4f2f-f11a-47c2-b3a0-4119f4a17a48 | Pole | HFTD Tier 2 | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007130 | 6e53aac0-2f35-4ec6-a6b1-bffafa00c4dd | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007131 | 8649bfe1-5dd6-4f7d-bcf4-214a36e8d1e7 | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007132 | 1d81795f-d60b-4617-9ce0-4034166bb21b | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007133 | 66276195-a208-4542-86ee-28ba7c6d545f | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007134 | 5a1f3aae-eea7-4d80-9762-393cc5f871cf | Pole | Non-HFTD | Distribution | 2024-05-21 | 2029-05-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007135 | ba8ef445-e99e-43fe-ae6c-5fc4292c0f47 | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007136 | 13148847-3fe6-4c01-9ecc-e77279fb92a1 | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007137 | 88758852-f9ca-4967-9e3f-23ffa85a4ff6 | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007138 | e055941b-238f-47c0-8ae8-0af569ed9a9b | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007139 | a9faf3a1-b867-4e3c-bdd6-8720f2c9b4ce | Pole | Non-HFTD | Distribution | 2024-06-12 | 2025-06-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007140 | 62c62937-0676-40d2-bfba-fd56eb75a607 | Pole | Non-HFTD | Distribution | 2024-06-12 | 2025-06-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007141 | cb40adb9-65d1-4b8d-9906-82467dc3de50 | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007142 | 3e25f299-f4f0-4b2b-831f-52556d2c9b90 | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007143 | 9cc8d493-d26e-43da-895b-720cd55ae53b | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007144 | 44531990-def1-4bc4-ad56-dfaf69dc102b | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007145 | 9cc8d493-d26e-43da-895b-720cd55ae53b | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007146 | 44531990-def1-4bc4-ad56-dfaf69dc102b | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007147 | 44531990-def1-4bc4-ad56-dfaf69dc102b | Pole | Non-HFTD | Distribution | 2024-06-12 | 2029-06-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007148 | 9dc51bb7-ed0f-4b38-a4a9-8e8450044b4a | Pole | HFTD Tier 2 | Distribution | 2024-06-13 | 2029-06-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007149 | 558bf5fd-c797-45b4-8817-bf2821c6072d | UG Transformer | HFTD Tier 2 | Distribution | 2024-06-13 | 2029-06-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007150 | ddc49c7d-a2c0-41c9-9860-d2c5ddfd6005 | UG Transformer | HFTD Tier 2 | Distribution | 2024-06-13 | 2029-06-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007151 | 4684ada2-254f-4353-b3ef-010637c90087 | Pole | HFTD Tier 2 | Distribution | 2024-06-13 | 2029-06-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007152 | 4684ada2-254f-4353-b3ef-010637c90087 | Pole | HFTD Tier 2 | Distribution | 2024-06-13 | 2029-06-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007153 | 3d44e95d-82b7-48c5-8680-6f190685f568 | UG Transformer | HFTD Tier 2 | Distribution | 2024-06-13 | 2029-06-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007154 | 8d2d4019-f21c-4130-b260-81d5d9ad5b9a | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007155 | 4021968e-a9ba-4455-ac77-3d9c94a642e8 | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007156 | 2061696a-c7a1-42fd-b432-222537520037 | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007157 | 9cdcd982-f65b-478c-bdca-06e1e6b9f584 | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007158 | e53bbab2-7890-442d-932d-e000041df083 | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007159 | 4d7a69d4-f2b5-4680-8814-126dfcb78bcc | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007160 | baea58ee-6a71-44ab-a230-493019d9483c | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007161 | baea58ee-6a71-44ab-a230-493019d9483c | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2025-06-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007162 | f485c6ac-4679-41a4-8af8-e1061a92e5ad | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2025-06-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007163 | 47795bbb-1265-4e50-a011-ef97bc283229 | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007164 | f7ad9557-4ba2-4382-ace6-6403f5529feb | Pole | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007165 | ec40e4ac-a319-4f7f-8e8c-3e4f2f045a37 | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2025-06-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007166 | b828e359-f2db-419a-beb1-fbc3af193b9e | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2029-06-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007167 | b828e359-f2db-419a-beb1-fbc3af193b9e | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2025-06-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007168 | 2bcc3727-1223-43b3-92ea-d2950704b24f | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2029-06-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007169 | 3e5d5e9a-7c10-4cbb-81b9-710aaa5cb7c7 | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2025-06-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007170 | 2dc42ec5-3264-478d-8207-5006cfaa9c49 | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2029-06-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007171 | 2dc42ec5-3264-478d-8207-5006cfaa9c49 | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2029-06-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007172 | 540cfb8b-538c-4b8c-87f5-52abf28f1079 | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2029-06-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007173 | 540cfb8b-538c-4b8c-87f5-52abf28f1079 | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2025-06-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007174 | 89f13320-4eca-4eb3-b20c-d12611f5aaa0 | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2029-06-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007175 | 89f13320-4eca-4eb3-b20c-d12611f5aaa0 | Pole | HFTD Tier 2 | Distribution | 2024-06-17 | 2029-06-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007176 | 2b079101-d70b-4687-b0db-02b3d997fa6c | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2029-06-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007177 | 2b079101-d70b-4687-b0db-02b3d997fa6c | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2029-06-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007178 | db7aa5da-dc94-48f5-9d9c-4ed3aab5ed97 | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2025-06-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007179 | 3cd9f898-b9fc-48fe-9ed1-7c7c069565c7 | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2025-06-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007180 | e4514c0f-5b25-4421-b497-2812e86488dc | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2025-06-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007181 | 44744ab6-6de4-4060-893c-e8d1204bf1bf | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2029-06-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007182 | d1fb83de-2b66-4f64-bb7c-7a20bece5e4f | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2029-06-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007183 | 340ad121-6d6f-4f4f-ae24-8db18a3edeac | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2029-06-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007184 | db7aa5da-dc94-48f5-9d9c-4ed3aab5ed97 | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2029-06-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007185 | 3b2c227f-3416-423c-89d9-8e414436bafd | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2025-06-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007186 | 70f91617-8cf1-452b-9f39-2bde4ade16aa | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007187 | c8d04886-2674-417f-9e09-b10d41de76a6 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007188 | e0cd2fe2-a32b-4b40-8054-33f6be44d3cf | UG Transformer | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007189 | 73e33d37-f3b9-4668-b444-d7c023e15981 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007190 | d3abef0d-7847-4c45-bb68-8f626fc6fea1 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007191 | 24b5d040-fdd3-4737-8f47-063bb41c00ef | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2025-06-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007192 | d3abef0d-7847-4c45-bb68-8f626fc6fea1 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007193 | d8955790-7649-48c2-9135-bdb41c7589e0 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007194 | 86c2f6c7-ba16-4115-a223-fc41d318704f | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007195 | 70f91617-8cf1-452b-9f39-2bde4ade16aa | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2025-06-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007196 | 86c2f6c7-ba16-4115-a223-fc41d318704f | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007197 | fb7fcf0c-9df2-403a-a7f3-aa0992a4e3e6 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007198 | 64defccf-e504-4e06-b1e3-be7cd65c968f | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007199 | eecfa70f-8f08-4c48-a753-8d8d775c5151 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007200 | 0a45574f-8700-4201-bd71-19a6cf0ed1e3 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007201 | b3c3c338-fe09-4171-b04b-52f83ace1388 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007202 | a61ded0a-6d33-45f6-9e83-921e4df9b03e | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007203 | 200bfd74-e459-4879-be7b-86357b5f6b8f | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007204 | 55273612-0cbd-4f37-833a-c6707443f248 | UG Transformer | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007205 | 6b5ad35a-cc47-49f6-9c15-538f33991091 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2025-06-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007206 | 30c28f85-3561-4a9b-a063-33a1cf71e4dd | UG Transformer | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007207 | beb033eb-1136-4939-b075-3872aae10e5e | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2025-06-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007208 | 80c52012-54aa-499b-992d-4cfd4ee26c9d | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2025-06-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007209 | a0b1993f-90b9-4119-95b3-b2d7c32684bf | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007210 | b618676e-8fbe-402c-8c62-573653e21803 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007211 | a0b1993f-90b9-4119-95b3-b2d7c32684bf | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007212 | 477ac6f0-989c-4234-a50e-0fa3a160f821 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007213 | ef7b2492-9625-4bcc-aa37-99a39fed24f1 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007214 | 700e57e9-fe16-497f-90c3-672a1b072da8 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007215 | ef7b2492-9625-4bcc-aa37-99a39fed24f1 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007216 | 360e1296-4534-49df-8be2-9f5cc277893e | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007217 | d71d5d1f-2606-4f27-9c06-5e4f05a2b1a3 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007218 | 200bfd74-e459-4879-be7b-86357b5f6b8f | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007219 | d71d5d1f-2606-4f27-9c06-5e4f05a2b1a3 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007220 | 071d1f9e-0db3-4111-a043-70e4a8820142 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007221 | c52ff267-e866-4edd-98d3-2b6fedb3d1e0 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2025-06-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007222 | ec5ba08f-6da4-49a0-94a2-7aa7015392b2 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2025-06-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007223 | 12132dc3-6b82-4c86-b6dd-41ec9a789211 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007224 | ec5ba08f-6da4-49a0-94a2-7aa7015392b2 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007225 | 2cff57be-cf91-4fe9-8f13-7aa20dce0cf2 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007226 | ec5ba08f-6da4-49a0-94a2-7aa7015392b2 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007227 | 3542e499-8338-425f-9e30-c046fc00a9ae | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007228 | 2cff57be-cf91-4fe9-8f13-7aa20dce0cf2 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007229 | 3542e499-8338-425f-9e30-c046fc00a9ae | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2025-06-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007230 | e85d09ec-50ac-46c9-9f20-155c44a348c1 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2025-06-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007231 | 1e7fb762-ea19-44da-99c4-26b9b2cbede7 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007232 | e85d09ec-50ac-46c9-9f20-155c44a348c1 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2025-06-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007233 | 01b8689b-d010-4f1d-83ea-eabb70873216 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007234 | e85d09ec-50ac-46c9-9f20-155c44a348c1 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007235 | 477ac6f0-989c-4234-a50e-0fa3a160f821 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007236 | 700e57e9-fe16-497f-90c3-672a1b072da8 | Pole | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007237 | 21146fa0-6daf-47ce-8b15-b9096c6bf25b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-06-20 | 2029-06-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007238 | 0c0974b8-5d93-4aff-b968-e98e00f9da85 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2025-06-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007239 | 7d78e208-28c3-43bf-883c-43a43d425917 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007240 | b6029ab2-b791-4fe8-8c2f-bf0405ef20bd | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007241 | 3d428473-6da7-4180-a2e1-9dd6d66afbcc | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007242 | c30517b4-54bc-4855-bde7-6fa4bf030c47 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007243 | 116af3d1-166b-4df6-b58b-3113a59b29e7 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007244 | c4744061-0cde-4f0e-ac9b-648e0b87a806 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007245 | 8f0059c0-f155-4ad3-91b9-cc20ab8376ce | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007246 | bf9ea3cd-fed7-4580-8e75-19fbc2b98b21 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007247 | 8f0059c0-f155-4ad3-91b9-cc20ab8376ce | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2025-06-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007248 | 0ef7fd1d-7a77-4162-a1a0-34716860b190 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007249 | 4b316754-2d38-4d13-92ad-42757587d1ab | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007250 | 9889f75f-9ad9-4580-92cd-b4b17d6932e0 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007251 | 6eafa96b-f7b8-464a-a650-852fa484915c | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007252 | 9889f75f-9ad9-4580-92cd-b4b17d6932e0 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007253 | c30517b4-54bc-4855-bde7-6fa4bf030c47 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007254 | 4ca2c65e-6c13-40c1-bb96-98b5dbf772d7 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007255 | 30d4bf07-c671-4d68-b59b-1d8a1c9dff46 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007256 | c4744061-0cde-4f0e-ac9b-648e0b87a806 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007257 | c4744061-0cde-4f0e-ac9b-648e0b87a806 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2029-06-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007258 | 1a2a8f72-5d11-458f-8ff5-519b4a4ea8b0 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007259 | fe08ef56-cf8e-41f8-8412-64b686d615af | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007260 | f3f53cd4-9fc2-4c34-8af7-ee36c8b603f7 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007261 | fe08ef56-cf8e-41f8-8412-64b686d615af | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007262 | 87bac6a0-8e82-4bb8-8b9b-f30de0010382 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007263 | eef4bf8f-32fc-4ff1-ab8a-cc695a730af2 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007264 | d0884ab1-5cff-4806-bdc6-02c655b421c2 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007265 | 493624e0-8a94-4a49-980d-d941388c8994 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2024-12-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007266 | 99a17907-2ffe-4c33-9644-eef208bf5142 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2024-12-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007267 | 86c71cfc-8312-47ce-b039-b12221b83c06 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007268 | 46a9fd68-e8c1-42ff-ae83-de7f8e34282a | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007269 | bc2c6791-61e0-4bad-b496-95784c10e72e | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007270 | 46a9fd68-e8c1-42ff-ae83-de7f8e34282a | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007271 | d614ba93-b67c-4858-a8a8-b904b0c5df97 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007272 | 35e4cc54-613b-4064-b7e0-81d496c6b04b | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007273 | dda13658-f048-49f4-a9b5-e4f77cc6d1d9 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2025-06-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007274 | b58a013c-804e-4844-a55b-14da0f94b8a0 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2024-12-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007275 | 55986f6f-a8b2-45e7-9f02-9f5d714433fe | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007276 | 9a39d7dd-e29f-4548-984f-6175b522ac5d | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007277 | 142ea652-1754-4a2c-8a40-9f6a2a0de9fc | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007278 | eef4bf8f-32fc-4ff1-ab8a-cc695a730af2 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2024-12-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007279 | 7239086e-c3a4-4bdb-8dc7-4520d0046be3 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007280 | ba085cdd-3183-4db5-ae30-1f350a847ca2 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007281 | 79efc97b-a504-4ec3-ae00-085b48bb466e | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007282 | 06dd0aec-9787-48dc-b355-1349b37437e1 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007283 | e5152ba9-4f6e-4fb7-afed-3b56698a8892 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007284 | 46999674-98e1-40e2-a1b2-754e84259d4a | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2024-12-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007285 | 46b33cdd-4ae2-4bb2-abe7-477772e602a6 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2025-06-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007286 | 55986f6f-a8b2-45e7-9f02-9f5d714433fe | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007287 | d0884ab1-5cff-4806-bdc6-02c655b421c2 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2024-12-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007288 | 85686d0e-ece8-4c3c-912e-1a4ab1faef9d | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007289 | 88da1a66-fd31-4d4e-8748-cc5aa3c88fb0 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007290 | 5dbdeab0-dab8-4a2a-9fc7-5cf68d73ef51 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007291 | 88da1a66-fd31-4d4e-8748-cc5aa3c88fb0 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007292 | 7d9063be-e925-47e5-b148-7111ea80cbe3 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007293 | a1dd7bb9-6438-46e9-bfaf-fd9b21b4c22d | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007294 | dc1044e3-d59f-4469-b512-0190dca2b122 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007295 | 35e4cc54-613b-4064-b7e0-81d496c6b04b | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007296 | 927536a3-4f12-4abb-b710-33579172935e | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007297 | 7aa9ddf8-a370-41a3-8869-4903a67dc3de | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007298 | 927536a3-4f12-4abb-b710-33579172935e | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007299 | 86faae2a-bb1c-46ac-8628-dbb4716ff70e | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007300 | 927536a3-4f12-4abb-b710-33579172935e | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007301 | b58a013c-804e-4844-a55b-14da0f94b8a0 | Pole | HFTD Tier 3 | Distribution | 2024-06-24 | 2024-12-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007302 | 09d28939-3493-479a-882e-52f3f5fc60e5 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007303 | b9465b9a-4868-4b97-9f3c-46e6aa843648 | Pole | HFTD Tier 2 | Distribution | 2024-06-24 | 2029-06-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007304 | 77ace6fa-b6c2-4173-9bab-45191874a14c | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007305 | 2677a5a3-05fb-4db1-8571-bebdea5fd17a | Pole | HFTD Tier 3 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007306 | 78221c67-3c75-4aca-90ad-142e2845970f | Pole | HFTD Tier 3 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007307 | 39a0a5e1-86af-4e94-8601-24f00d5b9117 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007308 | ae7287d2-c187-4d47-9f03-7ec37e08e7d4 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007309 | 39a0a5e1-86af-4e94-8601-24f00d5b9117 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007310 | 73706fca-1982-450e-9f8c-a5b4466637d6 | Pole | HFTD Tier 3 | Distribution | 2024-06-25 | 2024-12-22 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007311 | 39a0a5e1-86af-4e94-8601-24f00d5b9117 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007312 | 3c5ef2b8-5ee9-4116-871e-280e6be0dce9 | Pole | HFTD Tier 3 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007313 | c555bae9-5b0f-4c47-9609-5eadd936e88a | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007314 | 3a93f8d4-14ab-4dc0-a3f2-f1c795a19d49 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007315 | c555bae9-5b0f-4c47-9609-5eadd936e88a | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007316 | 76843465-6714-433e-81f0-aeca36fc981b | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007317 | 86a1a904-16f8-4cdb-8375-857d399a0e92 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007318 | 76843465-6714-433e-81f0-aeca36fc981b | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007319 | e9f0b3b9-9c18-4f57-9175-1dd1d64386b0 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007320 | 0b405660-acca-4348-a8cc-5727b4aa6c30 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007321 | 4d478bf9-d0b9-47f4-90a0-c97431c0a30c | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007322 | b6874927-6726-4969-a660-3282a0eb05cc | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007323 | 5ed9e4a5-93fe-47c6-afec-289ee6d2eacf | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007324 | 707557f6-b121-4b0b-98c3-070de29f703c | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007325 | 77ace6fa-b6c2-4173-9bab-45191874a14c | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007326 | 7f02375b-2e60-461c-a5ce-d6ec4a929c98 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007327 | 56eaa472-e6a4-4afe-ab54-e8870b637aaf | Pole | HFTD Tier 3 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007328 | e071ddc5-38b2-4c25-8754-9f08122e50fb | Pole | HFTD Tier 3 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007329 | 84e99b8c-c783-49a0-a3ef-b5080702dbdb | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007330 | 4a9ea315-1b1c-414d-96fe-07b99737c9a3 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007331 | 79387876-a594-40be-a373-a17785146bb5 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007332 | b653c500-e243-4e4d-815e-f5d630aa6646 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007333 | 76843465-6714-433e-81f0-aeca36fc981b | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007334 | 4b3e5d33-ddc7-40b4-9716-ad399f8b4b5b | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007335 | a013ced4-2fe7-479a-8cd6-c5f31b1ee1b8 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007336 | 4b3e5d33-ddc7-40b4-9716-ad399f8b4b5b | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007337 | e61ae870-aa73-45f7-a69c-de209b05ec42 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007338 | 39a0a5e1-86af-4e94-8601-24f00d5b9117 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007339 | c81cc607-92a6-4267-ac14-7a77e2e953d5 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007340 | 86a1a904-16f8-4cdb-8375-857d399a0e92 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007341 | 02dc7267-c881-4a2a-b68a-90f9089d50e5 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2025-06-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007342 | 94854d42-0c60-487a-8280-77cc55331838 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007343 | 02dc7267-c881-4a2a-b68a-90f9089d50e5 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007344 | 4298a310-1238-4af6-abf5-bd627d9b956b | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007345 | b6874927-6726-4969-a660-3282a0eb05cc | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007346 | f2343703-b80e-454c-bf43-c375dbd77aa8 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007347 | 707557f6-b121-4b0b-98c3-070de29f703c | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007348 | ed809408-b368-4b57-9a21-6ff964711263 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007349 | 7f02375b-2e60-461c-a5ce-d6ec4a929c98 | Pole | HFTD Tier 2 | Distribution | 2024-06-25 | 2029-06-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007350 | e700c8f5-758b-435c-830a-d9d8d8a381d9 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007351 | fe62bb7c-d6d3-4845-a881-1fb0519e5f8a | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007352 | 4956e2e5-764a-4eb6-bd82-338efef132b6 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007353 | b358b3ec-e38a-4da9-b4a9-359bb48b65ac | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007354 | 064e0681-ab18-4da5-9251-7b24d7e6cb09 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007355 | 8e1a98a8-270d-41ba-b4a7-2561ecfce642 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007356 | b358b3ec-e38a-4da9-b4a9-359bb48b65ac | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007357 | 69f2de45-db5c-47c9-9d8a-1ba853613ced | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007358 | 87274764-f32f-4a23-9a4a-67a198ba980a | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007359 | 4f66c4ea-4239-4a18-b551-6e1ffdd0e2ca | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007360 | 69f2de45-db5c-47c9-9d8a-1ba853613ced | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007361 | 4f66c4ea-4239-4a18-b551-6e1ffdd0e2ca | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007362 | 4ffc9c01-6a2e-4a79-97c6-fbe74d87a4b1 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007363 | df810e4a-eca1-4bc4-95fc-671a5f467a95 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007364 | 7e901f8b-2cda-4389-83b0-7eef0ae7afda | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007365 | 7ed765a6-2774-4657-808d-a0129c45c337 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2029-06-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007366 | ff229e7a-0f13-4cba-b74a-5ca3fb3fbbe2 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007367 | b32a339a-55b9-4c2b-a4c9-3e327f97714d | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007368 | cfee230c-e5a6-4f7e-bb21-057a94fae926 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2025-06-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007369 | b32a339a-55b9-4c2b-a4c9-3e327f97714d | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007370 | cfee230c-e5a6-4f7e-bb21-057a94fae926 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007371 | e1068c4b-a466-40cd-8cc7-111845877784 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007372 | 3b32507e-4299-40b2-bbd2-b7df5a3a9494 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007373 | 47d094fe-620a-4540-9e56-e0b6f81ef269 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007374 | ef693b42-1521-4bb2-8b81-6a0c0b6b204f | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2025-06-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007375 | 290262eb-949f-40e5-95db-13c2ab83618c | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007376 | 290262eb-949f-40e5-95db-13c2ab83618c | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007377 | 7f4b8f10-ae28-4c09-a670-5ce072a6c2db | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007378 | 11c00a5a-4d77-4fab-b5a5-2fc2a169256f | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007379 | 5f608a1c-f32c-4181-86c0-e27bc3a82d80 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007380 | 018e27b5-31ae-4a5f-951c-2220bc1822bf | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007381 | ace4830a-77ca-43c0-ac92-e62aefd4bc8f | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007382 | 8fc8ba60-e3a7-4a7e-ba6b-3a1539f55284 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2025-06-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007383 | 1803f3ad-b079-4094-a16f-77b4861688c1 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007384 | 8fc8ba60-e3a7-4a7e-ba6b-3a1539f55284 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007385 | 965c338b-03ac-44ec-a5ec-637edb1ddb84 | UG Transformer | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007386 | 5f608a1c-f32c-4181-86c0-e27bc3a82d80 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2025-06-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007387 | 5f608a1c-f32c-4181-86c0-e27bc3a82d80 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007388 | ace4830a-77ca-43c0-ac92-e62aefd4bc8f | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007389 | ace4830a-77ca-43c0-ac92-e62aefd4bc8f | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007390 | 1803f3ad-b079-4094-a16f-77b4861688c1 | Pole | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007391 | cd91f2c3-fd9c-4a71-bc4d-d5b40ecb8380 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007392 | 83162344-65b5-41fb-b352-3bd9f6851dec | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007393 | 5eeb4084-96d4-4f33-9648-42579d036773 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007394 | 83162344-65b5-41fb-b352-3bd9f6851dec | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007395 | 945d19e2-0f0c-4190-a5ec-14ae0467e5c3 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007396 | 18786433-fd0c-4715-ba98-2753340960f6 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007397 | 664d4f35-950d-4e73-b0d5-ef19ac9d77e8 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007398 | bd58e764-de5e-42ba-9dd4-978adbf94ca7 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007399 | f63a4c5a-36f8-4211-bcf5-79d40b7a0125 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007400 | cc554edc-478c-4856-accb-8f5a5d360a72 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007401 | 554b8123-6cd7-47d9-bb41-80ba1403106a | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007402 | f2860b60-ce7e-4c77-84c5-742dc0ba4130 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007403 | 0d5d9b57-b55d-4208-b8b0-784773aa7ae0 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007404 | 0d5d9b57-b55d-4208-b8b0-784773aa7ae0 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007405 | 208190b9-96e8-4d1d-bf40-280f247772a9 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007406 | 0c483d6c-fced-4dfb-89a2-b96e26c5d031 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007407 | 41c2467c-27c4-48c2-b3f8-68fec745b95a | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007408 | 0f186a31-262c-44c0-90e6-73cf476e85b1 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007409 | 1afd68f7-cc90-45bc-98ad-464051f54749 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007410 | cc554edc-478c-4856-accb-8f5a5d360a72 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2029-06-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007411 | 3d9d4296-b1f3-46f0-88e7-58335c15fa24 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007412 | ababda4c-c45b-4128-9e95-572cf871ae89 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007413 | 29c15402-8008-4c34-9003-7e7252237305 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007414 | bda94172-cdd9-4ced-9e6b-32037ec088ec | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007415 | 693ca94c-3b35-4eb3-9bab-e8f4c1480eb7 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007416 | 085da86e-a53e-4465-9f56-37dd9f17af90 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007417 | c72e7181-99ff-429a-aadc-76586dac72a8 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007418 | bfd4f6c4-2803-41bd-aeb1-b78ce23771af | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2025-07-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007419 | 39166c5d-0d84-4e77-b611-61e74e592195 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2025-07-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007420 | f5c05887-8dd7-4524-b321-5e7192f00fb5 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007421 | 6cbb0c82-d959-446a-8112-60728b5acca6 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007422 | a098dda8-d085-4582-ba82-5f394bb77166 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007423 | 6ff19ef5-92d3-463e-8870-11aeb40bcfe3 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007424 | 3747f1df-4a96-45ca-8b8e-43f130f5e6dc | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007425 | a098dda8-d085-4582-ba82-5f394bb77166 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007426 | e42300bb-b228-414b-99a3-69f3f8f44646 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2025-07-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007427 | c188be48-a5aa-41e0-8b54-5fce03825329 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007428 | e42300bb-b228-414b-99a3-69f3f8f44646 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007429 | 1a4269f5-cbcc-4313-a3c9-9460fd379930 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2025-07-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007430 | 9e39a6cd-9b0c-4b8b-a6e6-ac034f915b84 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007431 | fd3be72d-742a-4c7e-b9c9-d1109066e49d | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007432 | d84fbf71-3443-4187-b8d9-66b352946456 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007433 | 8eac64ed-9ad1-44d5-b631-d4d531aa8546 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007434 | c72e7181-99ff-429a-aadc-76586dac72a8 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007435 | 82e60072-487c-4d53-9ddf-7f164ea056b9 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007436 | 1a4269f5-cbcc-4313-a3c9-9460fd379930 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007437 | 085da86e-a53e-4465-9f56-37dd9f17af90 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2025-07-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007438 | aa25ee3d-fac2-4b47-80b7-7c3ce9d4401a | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007439 | bfd4f6c4-2803-41bd-aeb1-b78ce23771af | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2025-07-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007440 | a3e3b3ac-4469-4b88-b6af-616c7d3106db | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007441 | 94ec1b9b-94e0-4401-b191-e61072597462 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007442 | cc121b67-87bf-44ba-905c-7eae283c053d | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007443 | 554fbe6e-3a01-4887-b058-d6b01e263204 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007444 | b28d7754-2ebe-49a0-b7c8-d18f7a12398f | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007445 | d789bff0-f6a2-4634-ae17-9c00c1238b22 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007446 | 593b2383-2076-4c32-a2b0-182430c453db | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007447 | 5ec4f66d-ebed-4f3e-b493-7b80f6cf3756 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007448 | 331ea766-7e4d-46ad-b9b1-1f988606b999 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2025-07-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007449 | 593b2383-2076-4c32-a2b0-182430c453db | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2025-07-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007450 | a20404eb-4924-49ee-889d-02ec4a6d9693 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007451 | 56afe5c8-e52f-4428-9bd9-ba5cb6387a1b | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007452 | f6ae3e30-d096-4511-bf88-ff7d6eb84719 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007453 | 331ea766-7e4d-46ad-b9b1-1f988606b999 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007454 | 06f18c03-cc78-4925-9e9a-cbf2ddafc7e4 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007455 | f6f1a48f-1335-4a4b-90cd-2551456f1f84 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007456 | 13e2b00c-ccd8-48ec-83f3-317d9940cbb0 | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007457 | 889f4ac9-ae97-4196-9216-3411d3e839bb | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007458 | 889f4ac9-ae97-4196-9216-3411d3e839bb | Pole | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-06-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007459 | d714a95d-5a0d-4800-878b-6c3453429a0b | Pole | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007460 | bd89d1a8-7931-4cf2-b36b-25e4b4f4a560 | Pole | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007461 | 2164269b-954d-42f7-9792-92302948a9a4 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007462 | ade48442-015f-41e3-b1ae-0fbf17329556 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007463 | 3616e19f-cfd0-40c5-a215-696e9715537a | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007464 | 8b329659-8a64-44ec-a19a-34349badfca4 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007465 | 06ec18b8-9914-41b7-9e7c-b1d09b9c7328 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007466 | 126f2e3a-d1e5-4dba-a1da-3d04dc46d94e | Pole | HFTD Tier 2 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007467 | a7d7226c-d881-40be-a23a-ff2686fa0545 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007468 | d714a95d-5a0d-4800-878b-6c3453429a0b | Pole | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007469 | 192c2722-ec67-4e59-9f10-4c0bea1d987d | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007470 | d714a95d-5a0d-4800-878b-6c3453429a0b | Pole | HFTD Tier 2 | Distribution | 2024-07-02 | 2025-07-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007471 | 8cb11ab6-d5b1-4d63-85b0-dee3aecaa453 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007472 | efa3d9cc-8bc0-432c-88ef-7b85fe5c8c26 | Pole | HFTD Tier 2 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007473 | 4cf15d2e-7662-45b2-9a58-f384041a280d | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007474 | 140add64-a0b1-4edb-8452-e704c776c11a | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007475 | 585a1974-1125-49ab-b628-eb95af672f19 | Pole | HFTD Tier 2 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007476 | 12f62eb0-8676-4501-93bd-38e61ca1781d | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007477 | 1fa41337-bb6a-4262-bd6e-7b07db10d508 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007478 | 0f22279d-66a3-4588-92fa-a4acc6c81876 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007479 | 2c4a8893-b8db-4525-8913-66ac49ebfde6 | Pole | HFTD Tier 2 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007480 | 86e91040-aeb3-47ef-85f2-f6a8451bacd7 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007481 | 50061b87-8aad-46ab-b0b8-40056c9e9dc8 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007482 | 62a07bee-80fa-4514-bead-14d8e9f3b633 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007483 | 50061b87-8aad-46ab-b0b8-40056c9e9dc8 | Pole | HFTD Tier 3 | Transmission | 2024-07-02 | 2029-07-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007484 | 9a39b5a1-088c-49c0-9c1e-cd1d8cade4a0 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007485 | 27b5dded-e228-48eb-a390-90a5d2576e0f | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2025-07-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007486 | ac4d3815-f76b-4217-8160-20b4d0e2eb93 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007487 | b74581be-8da1-4db1-a9b4-e70926e11607 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2025-07-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007488 | b214acd9-6abe-43c6-be3e-e7918acae296 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007489 | e96599dc-f904-4ebf-b35e-22d173bc3ded | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2025-07-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007490 | 074aee67-5897-4b66-b291-7b03e366d9b2 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007491 | 006930a4-ff69-4550-85a0-3ceac5bb7f1a | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007492 | 074aee67-5897-4b66-b291-7b03e366d9b2 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007493 | 82bef7a5-06b9-4a2a-b749-3de995ceec99 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2025-07-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007494 | 2b4107c8-b685-4dc6-aa2d-4bdcbf5eb0d4 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007495 | 82bef7a5-06b9-4a2a-b749-3de995ceec99 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007496 | 7808dbc6-3d87-4738-a29e-057f952f2b5a | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007497 | a468b84b-639e-4f1b-956b-8a643882c43f | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007498 | 5f3828bf-5835-4a3b-9353-42577d1cbc21 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2025-07-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007499 | ac4d3815-f76b-4217-8160-20b4d0e2eb93 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007500 | 2dc59c9e-bc75-46ab-a550-7c3d13a255ca | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007501 | b214acd9-6abe-43c6-be3e-e7918acae296 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007502 | 27b5dded-e228-48eb-a390-90a5d2576e0f | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007503 | ac4cfa08-bbbe-4494-97bf-2b68daefc88d | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007504 | d7121ee0-a5f3-4bee-87ff-285ca49d08a5 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007505 | ac4cfa08-bbbe-4494-97bf-2b68daefc88d | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007506 | f6321919-385c-4f4a-a65e-7611c8beb1ad | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007507 | 2dc59c9e-bc75-46ab-a550-7c3d13a255ca | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007508 | a99b414a-6e14-490f-a65a-7bf10f09d28f | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007509 | d7121ee0-a5f3-4bee-87ff-285ca49d08a5 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007510 | 58c02d5c-fc76-466e-9ebd-1474de596cd3 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007511 | a99b414a-6e14-490f-a65a-7bf10f09d28f | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007512 | f3923078-178e-4cd3-b6ed-02a682b292e9 | Pole | HFTD Tier 2 | Distribution | 2024-07-03 | 2029-07-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007513 | 57e631f9-d66a-47a6-b88f-52540abc7d00 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007514 | 57e631f9-d66a-47a6-b88f-52540abc7d00 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007515 | 57e631f9-d66a-47a6-b88f-52540abc7d00 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007516 | 6caeffb3-7ca9-4c54-ae53-60176426c381 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007517 | c3edb75e-ee76-4f17-9c26-56ee63505524 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007518 | d3fc2d77-dc6d-4a88-b125-f73b13a9ff4d | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007519 | 3a90f9b0-82ff-4bdf-8af2-fc180b200aef | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007520 | 02a053b1-fbfb-4ea5-b197-91a85a498ca8 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2025-07-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007521 | 711dbb98-315c-412d-92ea-b2ed8539621b | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007522 | 3a90f9b0-82ff-4bdf-8af2-fc180b200aef | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007523 | 3e6baa81-4cdc-424b-8a04-7970dd33f977 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2025-07-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007524 | a97436f3-4c2c-4422-8211-e9cb09da50bc | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007525 | a97436f3-4c2c-4422-8211-e9cb09da50bc | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2025-07-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007526 | dd5e1b30-85af-458b-8471-15f98e969dc3 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2029-07-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007527 | 366f8155-2de3-4ccb-923c-98012989fe8e | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007528 | 1a1fc97e-b546-44b8-9fc4-fc9dbf62d939 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007529 | d72eeab0-69b9-40e2-b314-2bbef7c51c4f | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2025-07-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007530 | a1c55185-3ad2-44ad-895e-794116228c10 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007531 | 2203ac09-9dbc-45ac-8970-7cbe6b449ad3 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007532 | 0eee7066-4313-4f94-b807-5ddf298065a2 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007533 | d6fe64d3-7dd8-44ea-a7af-38c5b3377549 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007534 | bd4ddd51-69c1-4101-b06e-5e75e5643988 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007535 | 474152aa-7782-4174-b80c-bd88f4879cdc | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007536 | d72eeab0-69b9-40e2-b314-2bbef7c51c4f | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007537 | e70b1e56-2f74-433d-986d-7d2a10696851 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007538 | d6fe64d3-7dd8-44ea-a7af-38c5b3377549 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007539 | d48c77d4-f0f4-45bf-83c5-c6ffaa2e5f73 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007540 | d6fe64d3-7dd8-44ea-a7af-38c5b3377549 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007541 | 5e782cef-cfe8-4e99-beff-19d6399de820 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007542 | 1a26f0c4-8387-4c25-9535-0a60b998bb5b | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007543 | 9ffd8c29-ca9a-4c9e-8678-e2a5519f46b0 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007544 | 5e782cef-cfe8-4e99-beff-19d6399de820 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007545 | 0ecc4fe0-ca4e-4804-b8ff-fc255835883f | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007546 | 3bccaed5-42a4-4161-8287-505bae36f334 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007547 | 0ecc4fe0-ca4e-4804-b8ff-fc255835883f | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007548 | 85c7b76d-1228-42ba-b90e-05c8233aca47 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007549 | 88e6d832-3965-41f7-b283-531072ae26a8 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007550 | b5f88f79-2c8e-4d7b-9ce0-699b48089d31 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007551 | 88e6d832-3965-41f7-b283-531072ae26a8 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007552 | b5f88f79-2c8e-4d7b-9ce0-699b48089d31 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007553 | 09a1bbfb-0140-482e-9b34-486cd6e813d7 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007554 | 02438ed2-47c6-4206-979b-697c23fea2c2 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2025-07-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007555 | a1c55185-3ad2-44ad-895e-794116228c10 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007556 | de3cdd26-0b66-4753-9fbf-2fbbecd50bcf | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007557 | afb2fa38-c60c-4524-9ba1-c67a1015bcad | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007558 | afb2fa38-c60c-4524-9ba1-c67a1015bcad | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007559 | afb2fa38-c60c-4524-9ba1-c67a1015bcad | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007560 | 0d30bdfd-1859-4f88-93be-c183954cc810 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2025-07-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007561 | 0eee7066-4313-4f94-b807-5ddf298065a2 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007562 | fa1e1c3d-f9f2-48a9-ad39-7307157a08e7 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007563 | 7b8d0297-48d4-40c8-9f54-8029307cd60d | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2025-07-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007564 | 7b8d0297-48d4-40c8-9f54-8029307cd60d | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2025-07-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007565 | 85c7b76d-1228-42ba-b90e-05c8233aca47 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007566 | 9d118576-e91a-4f7d-98ab-a19e975a0e49 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007567 | 2c239d1c-baf1-408b-83bf-2e8628ed0753 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007568 | 41c43b62-c746-4521-b5c3-d878a88aca85 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007569 | 055b0785-f428-4d49-829e-ec59053502cd | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007570 | 4b7918ec-590c-4ced-b594-e0dc4a2305fb | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007571 | 14f710f4-4ca4-4f48-976e-765a30c0917e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007572 | 4b7918ec-590c-4ced-b594-e0dc4a2305fb | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007573 | 81620ee2-9a48-4105-86fc-5a2cc531cb3e | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007574 | 410c96b9-1d03-4557-ab41-c9de07bbf181 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007575 | 2dd7a658-ef51-4fda-9956-2454b2fcacea | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007576 | 410c96b9-1d03-4557-ab41-c9de07bbf181 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007577 | 2dd7a658-ef51-4fda-9956-2454b2fcacea | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007578 | 14f710f4-4ca4-4f48-976e-765a30c0917e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007579 | 5dc16a62-af7c-4523-9c37-332404aacab0 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007580 | 14f710f4-4ca4-4f48-976e-765a30c0917e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007581 | 5dc16a62-af7c-4523-9c37-332404aacab0 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007582 | 81620ee2-9a48-4105-86fc-5a2cc531cb3e | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007583 | 5dc16a62-af7c-4523-9c37-332404aacab0 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007584 | bea4e309-1329-48e1-a6df-b8a0abcca434 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007585 | dfbbb45d-92ef-429e-bc90-e8cb47e361dd | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007586 | d8dca262-bae6-4fcc-86ec-bfc205705e3f | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007587 | 76c8800b-0f85-437e-b389-2c07efd90d7c | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007588 | a9b2208f-8d56-45a1-a5cb-465e61f35ced | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007589 | 2eb8feba-5823-4587-b53c-816868e84526 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007590 | aaa1cdf4-42fd-46e5-a932-2f4758f628ac | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007591 | 9b021d0f-8282-45a9-8bcb-d8260074ea3e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007592 | 818f16fc-3640-46ef-938b-6d848fe3f253 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007593 | 9b021d0f-8282-45a9-8bcb-d8260074ea3e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007594 | 7527ffe5-80a7-4543-bf5c-7e79f3b4a854 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007595 | 9b021d0f-8282-45a9-8bcb-d8260074ea3e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007596 | adbabad3-577a-405f-a3a5-db8d3341619c | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007597 | 4b7918ec-590c-4ced-b594-e0dc4a2305fb | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007598 | adbabad3-577a-405f-a3a5-db8d3341619c | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007599 | b1fdffc8-acd9-43f3-9fd0-892dba5288e9 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007600 | d2bfa1c4-9ff0-4b77-9583-e5546134c349 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007601 | 7e5c3043-9c41-4935-9d06-3c71e42f0e7f | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007602 | 055b0785-f428-4d49-829e-ec59053502cd | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007603 | ad846840-fb00-4bbe-ae75-3df6b74a9e5a | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007604 | 2750fb51-f4df-46fe-be2f-fada05ab70be | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007605 | 2a833ae7-dd6e-47da-bb72-61f050278a45 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007606 | 2c239d1c-baf1-408b-83bf-2e8628ed0753 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2029-07-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007607 | 2c239d1c-baf1-408b-83bf-2e8628ed0753 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007608 | 45ad62c5-c513-491a-aa26-5b4c7ae979f7 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007609 | daac24fd-6f7a-4d5e-9762-b0e42594202e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007610 | 2aa46843-6d30-4aaa-bb88-833e04ebb660 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007611 | 753f2c42-e9e2-4e21-8362-ff68c91ccfca | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007612 | de220a65-1b17-4251-9523-b9ab3e59e4d0 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007613 | 0d31def1-e32f-4bcc-a982-fe54a534a119 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007614 | 9ed14aff-f0f8-44b9-a469-2d38e052de31 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007615 | d8f9be88-1241-4979-96c5-df346b3a6e55 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007616 | 6b8aedea-b828-4293-a502-9d5e92351a27 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007617 | d8f9be88-1241-4979-96c5-df346b3a6e55 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2025-07-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007618 | 32b3a7f9-1072-40e5-96db-b111c522ad75 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007619 | 14970b6a-d0ff-4a24-ab00-9e8daa2381ae | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007620 | 08d4a352-aaf9-4821-ae6f-b67f0502597b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007621 | de220a65-1b17-4251-9523-b9ab3e59e4d0 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007622 | 79e584f9-90fc-4048-87dc-71b20bbe7f01 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007623 | 6b8aedea-b828-4293-a502-9d5e92351a27 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2025-07-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007624 | daac24fd-6f7a-4d5e-9762-b0e42594202e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007625 | 9cfab621-7b61-401b-98a0-fb2e3a45e12b | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007626 | 753f2c42-e9e2-4e21-8362-ff68c91ccfca | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007627 | f6a96168-6a35-425a-b42c-84c25778557e | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007628 | f6a96168-6a35-425a-b42c-84c25778557e | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007629 | 32b3a7f9-1072-40e5-96db-b111c522ad75 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007630 | 08d4a352-aaf9-4821-ae6f-b67f0502597b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007631 | e83ac73b-3aa8-449d-99d1-10e221194020 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007632 | e83ac73b-3aa8-449d-99d1-10e221194020 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007633 | 6206f289-d7a8-41b7-9b55-96996bb28d29 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007634 | ae8faa09-454e-4c85-bef7-c0b1a5750392 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007635 | 45ad62c5-c513-491a-aa26-5b4c7ae979f7 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2025-07-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007636 | 384f2261-ed33-47f5-8599-2ee1bd034e98 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007637 | 384f2261-ed33-47f5-8599-2ee1bd034e98 | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007638 | 1e40938e-89fe-4ff9-b664-4eac8e0c17aa | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007639 | 1e40938e-89fe-4ff9-b664-4eac8e0c17aa | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007640 | 1e40938e-89fe-4ff9-b664-4eac8e0c17aa | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007641 | 1e40938e-89fe-4ff9-b664-4eac8e0c17aa | Pole | HFTD Tier 2 | Distribution | 2024-07-12 | 2029-07-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007642 | f8121124-7faf-4692-ba31-7a1ac77aec35 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2025-07-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007643 | 101b3959-e140-46f1-8101-531a8ec78ea6 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007644 | 8cba22a8-0b43-4edb-b95f-20e6b7703f45 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2025-01-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007645 | 6d8a7834-7714-4d38-8da5-1e24dcf0f3ee | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007646 | e2e1b9b9-f4dd-497c-ab9d-0e42b0cd3e6d | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007647 | 91176239-7db5-45b9-ae6c-608c6788b52a | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007648 | f65202c3-33bc-42ee-97ee-883e4714201c | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007649 | 47e13f85-c79d-4ba2-afe1-141e5c220003 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007650 | 91176239-7db5-45b9-ae6c-608c6788b52a | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007651 | cbe69c7b-cd54-4080-9385-7e0f1f9cc309 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007652 | 47e13f85-c79d-4ba2-afe1-141e5c220003 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007653 | 539dae35-a7d7-4c1f-82ae-e2f5801808f0 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007654 | cbe69c7b-cd54-4080-9385-7e0f1f9cc309 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007655 | 6a5aeed2-1a35-41ec-87dd-27480fe74f42 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007656 | 539dae35-a7d7-4c1f-82ae-e2f5801808f0 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007657 | 0b871fed-849f-4203-b08f-bf783be13cec | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007658 | 6a5aeed2-1a35-41ec-87dd-27480fe74f42 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007659 | 938c8ca4-67e7-4511-b217-6fde13cfd87a | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007660 | 0b871fed-849f-4203-b08f-bf783be13cec | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007661 | 8d1d2039-80e9-4b76-bdeb-f606803b1d41 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007662 | 938c8ca4-67e7-4511-b217-6fde13cfd87a | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007663 | 3290ae5c-786f-4348-998a-7256187181a7 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007664 | 4a312ea5-416b-40c2-bf94-2f3c19028cc3 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007665 | 008eed31-cb88-4554-9c52-ba9c72d02527 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007666 | c54d535e-24b9-4181-8c58-72dfb22c73e1 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007667 | f1829263-c3be-43aa-9e66-e3070fa12bee | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007668 | bf18a740-cf4c-4eec-97b4-e3a07ba4ebce | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007669 | 1807cfbb-6a8d-4000-ab03-d1f7b000f231 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007670 | df630516-142e-4dfa-89bc-8ac0d4252c9a | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007671 | e1711188-9b3d-4eb9-8a98-187dbadf1e05 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007672 | bb173e37-58a2-4e5c-a930-2d2f6ed639a2 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007673 | da85ccc1-4d7e-4486-b063-ff282201b6bc | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007674 | bb173e37-58a2-4e5c-a930-2d2f6ed639a2 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007675 | b818de26-4280-4482-acf5-b24e34bc21b7 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007676 | defb4b93-828f-461d-bbf0-96548d6493cd | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007677 | 9449c266-9474-4a6a-a45f-175ce66b2b52 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007678 | da85ccc1-4d7e-4486-b063-ff282201b6bc | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007679 | 9449c266-9474-4a6a-a45f-175ce66b2b52 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007680 | b8df0d59-9ce6-4cb6-9f58-df159c2da610 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007681 | defb4b93-828f-461d-bbf0-96548d6493cd | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007682 | b8df0d59-9ce6-4cb6-9f58-df159c2da610 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007683 | 09cd1c93-3485-4881-9869-53639fc44116 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007684 | b818de26-4280-4482-acf5-b24e34bc21b7 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007685 | 09cd1c93-3485-4881-9869-53639fc44116 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007686 | af962bac-9964-427a-9c74-0bd2b7801955 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007687 | f8121124-7faf-4692-ba31-7a1ac77aec35 | Pole | HFTD Tier 2 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007688 | 8cba22a8-0b43-4edb-b95f-20e6b7703f45 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2029-07-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007689 | 03c61afe-be04-442c-b61b-47712b944793 | Pole | HFTD Tier 3 | Transmission | 2024-07-16 | 2025-01-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007690 | bdb4a623-8720-4514-977b-c1222ac1fb97 | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007691 | d929c6ec-591d-4ef8-a996-6220b279bfef | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007692 | 38c4cc4d-903a-4f1c-8a9b-d2f9b1c600cc | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007693 | bdb4a623-8720-4514-977b-c1222ac1fb97 | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007694 | e9d95a06-c942-4d7b-9acf-9ae03731e232 | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007695 | c0a5ba7f-4137-4e0e-bd63-8e9e1449c14d | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007696 | 036a3e7f-fcba-4130-9385-b90e6cb0849b | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007697 | c0a5ba7f-4137-4e0e-bd63-8e9e1449c14d | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007698 | 72545532-2296-48dd-bba1-e6112b6c3b74 | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007699 | 09d5c577-9287-4f6e-ad67-a16aaeada326 | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007700 | 7ca0de63-0872-4866-8d5c-d5e573725747 | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007701 | fb989a85-a07e-4a6c-aa27-b0bc6aaf2b13 | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007702 | 76797465-345e-40f4-8408-184e127741cc | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007703 | c99a1c82-fed8-4771-a588-a860385e346a | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007704 | 76797465-345e-40f4-8408-184e127741cc | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007705 | 38c4cc4d-903a-4f1c-8a9b-d2f9b1c600cc | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007706 | 8b5b803d-0a17-4e49-9dc2-4d662c9f890b | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007707 | 036a3e7f-fcba-4130-9385-b90e6cb0849b | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007708 | c6038265-0c1a-485f-8172-773e50a97e8d | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007709 | 6cd48caa-3a4f-4c92-abff-7eda5818f755 | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007710 | 6cd48caa-3a4f-4c92-abff-7eda5818f755 | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007711 | 079dda7f-e0fe-4c23-9b84-5f732dd44d0a | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007712 | b7391d1f-343f-4f0f-a0a3-a4ed5cc71abc | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007713 | e821df61-d5c9-4c95-bc91-f272350dc11d | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007714 | 6b8d4d4c-19b5-4375-aebf-c0ebace28003 | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007715 | 6b8d4d4c-19b5-4375-aebf-c0ebace28003 | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007716 | 57024d4e-065c-4820-ae07-aefacb16436a | Pole | HFTD Tier 2 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007717 | c79912a8-e70e-4097-b929-503c1ee18f17 | Pole | HFTD Tier 3 | Transmission | 2024-07-17 | 2029-07-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007718 | c7acac1f-a371-41a3-8319-242d0fc9117f | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007719 | d2fd742d-feaf-46ed-bbb5-b4e5d3342861 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007720 | c7acac1f-a371-41a3-8319-242d0fc9117f | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007721 | be9b2a14-12b5-47e4-8ac7-886110552892 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007722 | e7dcd927-30b3-4c02-aa77-82fa703b7ca9 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007723 | 1a02130d-64e0-4606-9ff8-013e26adb2f8 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007724 | cb6a12bf-9090-4af3-a4cb-77ea01244531 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007725 | ad4533b6-a344-4871-968e-09c6dd4145d8 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007726 | cb6a12bf-9090-4af3-a4cb-77ea01244531 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007727 | 43586127-6935-4cc0-a042-b7cb7bc6f7a7 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007728 | 1ffb78d6-e903-46d7-b7f4-63fb4b31abfe | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007729 | 68212da4-2672-4fa3-904f-18c4e2ee8864 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007730 | dee55fa9-04be-4622-b9fc-c6fe29dbe1cc | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007731 | f7a1763f-1e37-40d1-8ea4-11f102911315 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007732 | dee55fa9-04be-4622-b9fc-c6fe29dbe1cc | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007733 | c7662110-bda9-4e2b-a3b9-ee2badd7c5be | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007734 | 74a9be43-7efe-408d-9805-d3f172f941ed | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007735 | a6f13dbb-f4a6-4abe-8b0d-a4a6b883a16c | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007736 | 5c0ec0d7-0e00-4336-851d-32f7d083c3f6 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007737 | c071b4ed-1315-4ae7-94b8-25c8101ca49b | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007738 | efdf1269-fa47-4d02-8278-fd92c77252f7 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007739 | 5fce6e63-3e8a-4c5b-b678-c103216964f0 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007740 | b216018a-0ecd-4f8a-a1b6-87954de7d97b | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2025-01-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007741 | e431d1a2-bdd8-463e-a859-c60265901272 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007742 | 3f3ef961-eece-4752-ab01-f3ff3f2bb0a9 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2025-01-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007743 | cf7bea5f-d673-4c41-a55e-f4a1371ed9ce | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007744 | 3f3ef961-eece-4752-ab01-f3ff3f2bb0a9 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007745 | 98090e08-7102-440c-8173-f1cc13a1f124 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007746 | 427a7120-5fe4-436b-a961-828562a28a39 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2025-01-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007747 | f5bf4487-9c26-4e8d-99c4-33485afbc426 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007748 | 427a7120-5fe4-436b-a961-828562a28a39 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007749 | e7dcd927-30b3-4c02-aa77-82fa703b7ca9 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007750 | 9f6a1a29-491e-4d94-a20c-8e49bac77d17 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2025-01-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007751 | 337e1679-089b-4193-840d-a04cb2e45d0e | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007752 | e3cafa74-9eb8-4128-9698-84aaeb201dfb | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2025-01-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007753 | f7bb08da-98fe-4fb9-80d6-3d9437d76332 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007754 | bbdf8521-d31d-41a7-88e6-f663496a041c | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2025-01-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007755 | b216018a-0ecd-4f8a-a1b6-87954de7d97b | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007756 | 0caccaa5-57da-4eea-8ab2-e4291d4e7af8 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007757 | 9f6a1a29-491e-4d94-a20c-8e49bac77d17 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007758 | ad4533b6-a344-4871-968e-09c6dd4145d8 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007759 | e3cafa74-9eb8-4128-9698-84aaeb201dfb | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007760 | 68212da4-2672-4fa3-904f-18c4e2ee8864 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007761 | bbdf8521-d31d-41a7-88e6-f663496a041c | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007762 | c98ca90a-0068-43ad-96f5-aff7e498ede7 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007763 | 0caccaa5-57da-4eea-8ab2-e4291d4e7af8 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2025-01-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007764 | 5de9bf1b-883e-4ace-b3f1-4426192484e8 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007765 | ebc5bb6b-ebc9-46ad-b9db-cd6446837c95 | Pole | HFTD Tier 3 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007766 | 6a7c2e9b-f394-4b6f-be51-b49a988e5914 | Pole | HFTD Tier 2 | Transmission | 2024-07-18 | 2029-07-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007767 | e2226c70-7ecc-471f-8c96-d33932791f51 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007768 | e7e9720e-a30c-49d2-b560-fe06328484ce | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007769 | e2226c70-7ecc-471f-8c96-d33932791f51 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007770 | e7e9720e-a30c-49d2-b560-fe06328484ce | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007771 | 957b0d6c-570d-4bf9-9fec-0c005889bf52 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007772 | 67d33fde-5979-4079-a0aa-d93dfb119ca2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007773 | 957b0d6c-570d-4bf9-9fec-0c005889bf52 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007774 | b66f98ac-de16-4a91-a4ab-d300e14fe889 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007775 | 66df40ee-ba98-4a1c-8640-a68749b64d9f | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007776 | 6298e6dc-1afa-4271-b28c-0923e6e55a73 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007777 | 67a8fa39-05ee-44ee-931e-7adda3885184 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007778 | 67a8fa39-05ee-44ee-931e-7adda3885184 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007779 | 012e98d7-a370-4d3f-8232-c290e9412d24 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007780 | 012e98d7-a370-4d3f-8232-c290e9412d24 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007781 | e7e9720e-a30c-49d2-b560-fe06328484ce | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007782 | 67d33fde-5979-4079-a0aa-d93dfb119ca2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007783 | 67d33fde-5979-4079-a0aa-d93dfb119ca2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007784 | b7b2921e-9f4e-4ee4-99ed-f890bd76c664 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-19 | 2029-07-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007785 | 63530295-9bb1-49e3-9aca-649554aa437a | Pole | HFTD Tier 2 | Distribution | 2024-07-19 | 2025-07-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007786 | b805b591-124c-4391-b5b6-c0178276a2c4 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007787 | 78b0353a-2e97-4799-b14d-718245e120c0 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007788 | a74a299b-0d71-49f5-a83d-985f095ee702 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007789 | 8e4fe346-b304-473d-b390-7214787744c8 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007790 | f09cdf3b-a392-4315-8e88-9895210f0404 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2025-07-22 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007791 | 8e4fe346-b304-473d-b390-7214787744c8 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007792 | 7e23338a-efd5-4759-a853-b7d85f7cfe3d | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007793 | 8e4fe346-b304-473d-b390-7214787744c8 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007794 | 3fe24ec8-1322-457f-80e0-d0295b342ab4 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007795 | a74a299b-0d71-49f5-a83d-985f095ee702 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007796 | 81d4210e-6901-47fc-a1b3-0723dc603f18 | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007797 | a1edf264-e908-410a-8202-7c66487d582b | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007798 | a4e843d9-64fa-40b2-b10c-c0112cdac7fc | Pole | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007799 | d2e7c0b3-e165-4c0c-ba21-a4c0ba7108ed | Pole | HFTD Tier 2 | Transmission | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007800 | 34aeef8a-c61b-467c-b810-0f7b3f2b6c5f | Pole | HFTD Tier 3 | Transmission | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007801 | 34aeef8a-c61b-467c-b810-0f7b3f2b6c5f | Pole | HFTD Tier 3 | Transmission | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007802 | aa91c2a0-c7a1-4b04-9e3c-8ed2691cc4ed | Pole | HFTD Tier 3 | Transmission | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007803 | 9989e535-e88b-4e13-a565-96ce165b3e39 | Pole | HFTD Tier 2 | Distribution | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007804 | 7c03634b-0500-4d69-842d-d8fc49921d9d | Pole | HFTD Tier 2 | Distribution | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007805 | ed840a13-392d-440b-ba7d-ce8a14f735ce | Pole | HFTD Tier 2 | Distribution | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007806 | ef8a5371-c5fb-416c-88a7-76246f30d31b | Pole | HFTD Tier 3 | Transmission | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007807 | d2e7c0b3-e165-4c0c-ba21-a4c0ba7108ed | Pole | HFTD Tier 2 | Transmission | 2024-07-23 | 2029-07-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007808 | 82fd1634-5f22-4a7a-add5-6051ea1c1afe | Pole | HFTD Tier 2 | Distribution | 2024-07-24 | 2029-07-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007809 | f49f31be-5186-475c-bc91-0b5ba2b3a818 | Pole | HFTD Tier 2 | Distribution | 2024-07-24 | 2025-07-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007810 | 8288bf7a-ec18-4954-86e3-91ec68112c69 | Pole | HFTD Tier 2 | Distribution | 2024-07-24 | 2025-07-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007811 | 641bd05a-6ac8-40a7-a1cb-d25cc22ae122 | Pole | HFTD Tier 2 | Distribution | 2024-07-24 | 2029-07-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007812 | 6d1a98a7-b384-48a5-994a-7347ed6e0cbc | Pole | HFTD Tier 2 | Distribution | 2024-07-24 | 2029-07-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007813 | 117eb034-d5c4-4a03-bbed-e177ea9a090d | Pole | HFTD Tier 3 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007814 | 6704c339-e926-48bd-ae79-44db1208f15e | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2025-07-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007815 | 420f064d-37ee-437c-8837-3763579b0450 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007816 | 5e32201c-d2da-4f0c-b9c4-6feae6635eb9 | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2025-07-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007817 | 70eac73c-8bee-408a-ad61-547d85475eba | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007818 | a92ccef7-98af-4702-94ab-9941cc8dd898 | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007819 | eb68e0c5-3221-4d77-b895-690c344cca2d | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2025-07-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007820 | 8fdf34ec-af3a-44ad-b875-c01fddb39c1e | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007821 | 058da625-ed9e-4925-82c4-d92b386addce | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007822 | 0b01dc6c-2c1f-4bf4-b454-7b99418220f9 | Pole | HFTD Tier 3 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007823 | ba356035-63fc-438b-b83d-f38dc732786a | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2025-07-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007824 | 117eb034-d5c4-4a03-bbed-e177ea9a090d | Pole | HFTD Tier 3 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007825 | 7d64a541-f30e-4499-ba3c-ae65c6a8e6c4 | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007826 | 420f064d-37ee-437c-8837-3763579b0450 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007827 | ffc75382-9705-4e6f-a041-fd2d619f9a89 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2025-07-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007828 | abb3b497-de12-44bd-8dbd-c2a9b5f8ae88 | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2025-07-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007829 | ffc75382-9705-4e6f-a041-fd2d619f9a89 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007830 | 04ad5ade-1eb7-45f0-bd48-c6ab53dfbd58 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2025-07-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007831 | 04ad5ade-1eb7-45f0-bd48-c6ab53dfbd58 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2029-07-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007832 | ffc75382-9705-4e6f-a041-fd2d619f9a89 | Pole | HFTD Tier 2 | Transmission | 2024-07-25 | 2025-07-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007833 | 1611ff50-1504-43e3-8c8c-103a2c315cf0 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2025-07-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007834 | 1611ff50-1504-43e3-8c8c-103a2c315cf0 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007835 | c21dc285-b441-4a29-a1ca-9af8f2135cf6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007836 | 6f841b88-5a4b-4e18-a1e9-30024b3895b0 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007837 | c21dc285-b441-4a29-a1ca-9af8f2135cf6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007838 | 24d251a3-14f9-4853-9bfa-4c2737012fe1 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007839 | f1bcd89b-dd96-49b0-99ed-7ee466059537 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007840 | 3c60c630-e170-4d6e-8254-40210f2307d7 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2025-07-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007841 | 088eab05-d496-4cb6-8c66-d8942a174fb8 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007842 | 4ec43c6a-0a6f-4e64-b328-b0c4111b7976 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007843 | a41d8aae-a14b-456e-b147-408245a343e3 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007844 | 4ec43c6a-0a6f-4e64-b328-b0c4111b7976 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007845 | 09e7a346-2288-41b8-b888-060b0b81befc | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007846 | 81196681-2942-44be-a8f6-b54bdebc1bee | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007847 | 09e7a346-2288-41b8-b888-060b0b81befc | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2025-07-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007848 | f86c78ad-9d48-4966-ba90-e8a3067cd442 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007849 | e4368eca-b0e9-42c1-9cb8-cc6aac7fdb46 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2025-07-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007850 | a3b092ec-843b-493c-81f6-3bd457c3d50c | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007851 | e026f1e9-713f-42de-bfd4-25bbe13b6080 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007852 | 0482aad2-58f6-4158-be89-e71dacecea18 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007853 | dc52c99d-3452-453b-87ce-2974a7aa6c8e | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007854 | e026f1e9-713f-42de-bfd4-25bbe13b6080 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2025-07-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007855 | dc52c99d-3452-453b-87ce-2974a7aa6c8e | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007856 | d1a056ed-305d-4aa6-9376-959caccd7cf1 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007857 | 5b83bf12-1961-42a9-be2e-5288e20805a0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007858 | 5b15c174-9ad7-496b-9ce1-780f346a99fc | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007859 | 5229cd95-3402-403f-a4eb-fb40821d0ae3 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2025-07-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007860 | a7ff3e93-7f49-4a92-be33-1c5f78c23a88 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007861 | a7ff3e93-7f49-4a92-be33-1c5f78c23a88 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007862 | 81196681-2942-44be-a8f6-b54bdebc1bee | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007863 | ef55ab36-ad55-4447-9b66-dfc89e720382 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007864 | af5cfe84-faaf-44c6-a063-04a5d82d24f8 | Pole | HFTD Tier 2 | Distribution | 2024-07-26 | 2029-07-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007865 | bf46f86b-63f8-4fca-8f50-50365503feab | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007866 | e6ef64e2-3aa4-44fb-9789-2cd35245f57f | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007867 | 2ddc0623-4827-496e-b9f9-bff794d4c011 | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007868 | b7455562-d8d1-4f68-9662-d23883f02f7f | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007869 | 70d271f3-8704-4d2d-98e9-026418c93a5e | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2025-07-29 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007870 | 691dde54-a90d-4dda-8f9c-005b8bc33c81 | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007871 | 36fed619-3887-4d1d-bb7a-7cbf9b5b76d9 | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007872 | 2a54715f-02ba-4a5f-acc9-172a44ec1c17 | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007873 | 3d66ffef-d356-4322-85c5-98fb365e903a | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2025-07-29 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007874 | 46026092-af0c-4774-a6f1-aac8bd81a2ff | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007875 | 5c1d0f00-ebf5-4a14-a5c1-893db1c42ffd | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2029-07-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007876 | d188e1e0-9309-44e5-9689-d40d29db3ed0 | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2029-07-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007877 | 416aa764-f0cd-4a45-a0d7-960d954b4b30 | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2029-07-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007878 | cb043f54-c80f-47b7-abe2-f5c8e0888c7c | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2029-07-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007879 | f50272b0-5dbd-4dee-8b7d-c4060a798d9a | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2025-07-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007880 | 386a66c6-f6ff-4f73-ad8b-ae49ca4c333a | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2029-07-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007881 | 4626ea5f-8d2b-4b06-9eec-1cd35d5bbc8f | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2029-07-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007882 | b597ea67-71a0-41b0-9f35-6f47e2e66489 | UG Transformer | HFTD Tier 2 | Distribution | 2024-07-31 | 2025-07-31 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007883 | 227c3e5a-3d61-484e-a428-ccf96f84b5d3 | Pole | HFTD Tier 2 | Distribution | 2024-07-31 | 2025-07-31 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007884 | 2796f3be-45a5-4718-90d6-605ec97698d0 | Pole | HFTD Tier 2 | Distribution | 2024-07-31 | 2029-07-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007885 | c4ad4e2d-72e7-4564-9f69-a4268186abf0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-31 | 2029-07-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007886 | 2796f3be-45a5-4718-90d6-605ec97698d0 | Pole | HFTD Tier 2 | Distribution | 2024-07-31 | 2029-07-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007887 | b375cc5a-f6d7-4e2d-b009-b1e826adcb58 | Pole | HFTD Tier 2 | Distribution | 2024-07-31 | 2029-07-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007888 | a899222c-837f-4738-aefe-0473bb1054da | Pole | HFTD Tier 2 | Distribution | 2024-07-31 | 2029-07-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007889 | a2c010c7-6663-4baa-834b-4366a77d8779 | Pole | HFTD Tier 2 | Distribution | 2024-07-31 | 2029-07-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007890 | 2fdc0030-4eda-4c0e-ba7a-cf2a446d0764 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-31 | 2029-07-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007891 | c4ad4e2d-72e7-4564-9f69-a4268186abf0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-07-31 | 2029-07-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007892 | dd15da4f-64fa-46ea-aa2d-e0a0d0738998 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007893 | 6c6f9cbb-1225-407b-8f82-b49594e6bbb9 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007894 | 5a0c1146-01b3-4891-a96a-4315c10654bb | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007895 | 6c6f9cbb-1225-407b-8f82-b49594e6bbb9 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007896 | b749dde7-d136-4568-8ced-2773716f4f63 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007897 | 4bd81305-7442-4a93-906d-3816d020c08d | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007898 | b5f4edd2-0287-4dc8-9286-b109886267b9 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007899 | e24b3eef-d164-4198-9988-cc9ecc2ddbfb | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007900 | 0597cc9e-7216-4cec-ba41-79209e7660f8 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007901 | e9622eb0-8a37-46af-8377-dc28278b53bf | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2029-07-31 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007902 | 123b6fcb-eec4-44bf-b683-11a2457c28c2 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007903 | ea8990db-fec6-49e3-82ee-45019682f9ec | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007904 | 2d85fe0f-c6e5-4e00-b8ba-8ff519525673 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007905 | 047dd912-6c71-4cf8-b96f-e575ea777e56 | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007906 | d082c49c-b01f-4e34-929a-8d171ee00dc7 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007907 | c5837ae8-c9fd-40a8-9f9c-dee9f430e56f | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007908 | 8ebd9775-e756-4509-bf12-014357bab20d | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007909 | 3320eaa7-1dcf-4f1f-a4fc-7469d06b2dc0 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007910 | cfc50978-362c-4deb-822f-799a1d4f65d1 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007911 | 5cfd5430-86bc-4399-b5fe-3a422edbcdcc | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007912 | 379941f4-71c5-447c-be67-c75837271cdb | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007913 | 221f05bf-7cfd-4fa5-adfd-2cd053d29688 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007914 | 5cfd5430-86bc-4399-b5fe-3a422edbcdcc | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007915 | 221f05bf-7cfd-4fa5-adfd-2cd053d29688 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007916 | dc4dec6d-9add-4264-aab9-53aad72a83eb | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007917 | 123b6fcb-eec4-44bf-b683-11a2457c28c2 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007918 | 7ece5e35-594d-450d-a780-3174a2c5507e | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-02 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007919 | 2d85fe0f-c6e5-4e00-b8ba-8ff519525673 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007920 | 19381fde-4a1f-4ac4-bbd6-2adda3726781 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007921 | fd07d373-6280-4c9a-b00e-5bb533a92cc4 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007922 | 36f5cb33-b386-4335-912a-9d8b08a1ed1c | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2029-08-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007923 | 0e5b21bd-8575-4e09-9bd1-ad0391fa72c5 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007924 | 0c8d6fa0-b305-4d5b-bbbf-43a2b4eead41 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007925 | f536559a-9831-447c-b184-5233adea7b57 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007926 | 0c8d6fa0-b305-4d5b-bbbf-43a2b4eead41 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007927 | 99a62d1a-5789-4d7e-8654-523e42f91cda | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007928 | a92b417c-cf0e-49df-a23b-ef6754ed973c | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007929 | dd95a965-9cc1-4ee5-82ac-cc4659a6e829 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007930 | 9528dab8-885b-4a8a-8de4-2a9eb0520649 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007931 | 2b483ddb-192c-4073-8a91-7c835f38d52d | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007932 | 01ab7c1b-8bf2-4639-9108-d4d64637ef22 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007933 | 9528dab8-885b-4a8a-8de4-2a9eb0520649 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007934 | be51aa5c-b3ca-49e3-b0b1-162a8821aa13 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007935 | be51aa5c-b3ca-49e3-b0b1-162a8821aa13 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007936 | be51aa5c-b3ca-49e3-b0b1-162a8821aa13 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007937 | 45aad611-5bc2-4d5e-a4fe-cba48f16bec3 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007938 | 96eb4924-db15-45bf-83c7-78509921346c | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007939 | d6144dc4-4290-4747-9ec7-af01ab7f0e68 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007940 | 92b21173-3f78-4ee8-a8e5-262be1363891 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007941 | 92b21173-3f78-4ee8-a8e5-262be1363891 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007942 | 92b21173-3f78-4ee8-a8e5-262be1363891 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007943 | 92676504-d865-4d08-a902-772480d2b12f | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007944 | bade7f56-7287-423e-83ff-ac5f1be3f4d8 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007945 | 5f94721c-a29a-439c-8b37-cfcc0844ae81 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007946 | dd95a965-9cc1-4ee5-82ac-cc4659a6e829 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007947 | 29d53bce-8e57-44d9-9764-53430f5efd4f | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007948 | 2d6bcbac-b24e-44d6-9947-329f5487f25d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-05 | 2029-08-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007949 | df9eb7fb-82a9-48cf-9509-3de7163000ee | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007950 | 23d60ae5-471a-4b8c-a067-7cfa3f7b60df | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007951 | 531ffadc-6ab0-4083-beb3-aae7ea51444c | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007952 | 22c5500e-5012-41ca-9292-9093a2c0a542 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007953 | 23d60ae5-471a-4b8c-a067-7cfa3f7b60df | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007954 | 6c05f561-c5e7-4fa5-bbaa-6b8efab5a1a5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-06 | 2025-08-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007955 | 1408e7b8-6aa6-4859-a536-2d73159eaa8b | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007956 | 6c05f561-c5e7-4fa5-bbaa-6b8efab5a1a5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007957 | 1408e7b8-6aa6-4859-a536-2d73159eaa8b | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007958 | 6c05f561-c5e7-4fa5-bbaa-6b8efab5a1a5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007959 | 22c5500e-5012-41ca-9292-9093a2c0a542 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007960 | 7a87532d-de27-489b-9bf8-882d191c6b3f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007961 | 68be8bd8-3f98-4e28-8489-a0b36d12335a | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007962 | 7c0ede32-ab3c-486e-b60b-5c47f7a1e4c7 | Pole | Non-HFTD | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007963 | 8c111c66-3676-487d-a538-4cc5de8507a7 | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007964 | bc58f3da-8826-471b-b741-34de5a9214aa | Pole | Non-HFTD | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007965 | 8d3896da-9e8b-41db-a3bf-a94bfbef65b2 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007966 | 317de1bb-d14a-4785-8309-060ffaf40f04 | Pole | HFTD Tier 2 | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007967 | 8d3896da-9e8b-41db-a3bf-a94bfbef65b2 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-08-06 | 2029-08-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007968 | 9a21a12c-1fed-40c8-8fa4-831e5c224657 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007969 | 9e814357-f48c-40c9-90e8-d224a02d7dc0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007970 | 35098ce8-f33b-4a6f-9530-1392a38000d9 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007971 | 9e814357-f48c-40c9-90e8-d224a02d7dc0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007972 | 27cf2e9e-4caf-4ec4-871b-1ca152bfe157 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007973 | 9e814357-f48c-40c9-90e8-d224a02d7dc0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2025-08-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007974 | 02b94e3f-6ec5-4db4-a668-6bee26da5429 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007975 | c276f6c9-8ff0-4285-ac31-a20a54fa3de6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007976 | c276f6c9-8ff0-4285-ac31-a20a54fa3de6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007977 | 9824cde2-9692-487e-b49d-c4bebe7c41b4 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007978 | c276f6c9-8ff0-4285-ac31-a20a54fa3de6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2025-08-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007979 | c40519e7-4395-41f5-9c87-b6b03b249249 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007980 | 9824cde2-9692-487e-b49d-c4bebe7c41b4 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007981 | f8c7de7c-c5c9-4cdd-b172-cecffd549fdb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007982 | a2d4536d-c0d0-4031-b2a6-6f8a7957cf9f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007983 | f8c7de7c-c5c9-4cdd-b172-cecffd549fdb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2025-08-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007984 | 68957be5-d01b-43c3-a446-033a39617147 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2025-08-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007985 | a865aa5f-6373-42f1-a0e5-3f49b16c54ad | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007986 | dcf667c7-64f0-431a-bbf4-87026d67193d | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007987 | 8a55ce91-a815-4f2b-bc9f-dfd434f39c59 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007988 | c40519e7-4395-41f5-9c87-b6b03b249249 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007989 | 8a55ce91-a815-4f2b-bc9f-dfd434f39c59 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2025-08-07 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007990 | f8c7de7c-c5c9-4cdd-b172-cecffd549fdb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007991 | 9da3e9d9-022a-4a3f-9279-9a4a8f0e2272 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007992 | 7b44a3ad-3571-42ce-8f50-587fd613f31c | Pole | HFTD Tier 2 | Distribution | 2024-08-08 | 2029-08-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007993 | 11c76924-a7e6-4f1c-a1e1-97e992643adb | Pole | HFTD Tier 2 | Distribution | 2024-08-08 | 2029-08-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007994 | f9ba5c67-2f73-4fdc-a926-d0609aa8886f | Pole | Non-HFTD | Distribution | 2024-08-08 | 2029-08-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007995 | 477dce3b-f593-45d1-9c03-864a7beba9da | Pole | Non-HFTD | Distribution | 2024-08-08 | 2029-08-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007996 | f9ba5c67-2f73-4fdc-a926-d0609aa8886f | Pole | Non-HFTD | Distribution | 2024-08-08 | 2025-08-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130007997 | 1e484413-3f76-4ba3-951b-525a136466a4 | Pole | HFTD Tier 2 | Distribution | 2024-08-08 | 2029-08-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007998 | f9ba5c67-2f73-4fdc-a926-d0609aa8886f | Pole | Non-HFTD | Distribution | 2024-08-08 | 2029-08-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130007999 | 411a909b-e890-4be3-876d-a4adb4cbbb3a | Pole | Non-HFTD | Distribution | 2024-08-08 | 2029-08-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008000 | 915fa0ff-a395-466c-99fd-e129ee660383 | Pole | Non-HFTD | Distribution | 2024-08-08 | 2025-08-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008001 | 10a2da1c-4317-4ef8-9989-78b39bb6ed2e | Pole | HFTD Tier 2 | Distribution | 2024-08-08 | 2025-08-08 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008002 | 2d89b1ef-71a2-46cd-9009-7273cf429d36 | Pole | Non-HFTD | Distribution | 2024-08-08 | 2029-08-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008003 | 6e13ac5e-9536-445e-9eae-dbaf787e1937 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008004 | 866927c0-16ff-44a1-bbcc-6d9bd7ab6be0 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008005 | 0739b7cc-de79-4aad-841f-e2cef6aada2f | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008006 | ea4e508e-0f2e-43e6-b2d6-ed257d7da4df | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008007 | 0739b7cc-de79-4aad-841f-e2cef6aada2f | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008008 | 4dd13f47-3faf-4553-982a-1869fc43fd07 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008009 | 182343ed-4997-4a83-a10e-d7236f17455c | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008010 | 328e45f2-f6e3-4109-9668-c0477b848562 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008011 | 1d472d17-1030-4828-8b02-504465ac8b96 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008012 | c7ad067c-5566-4528-9874-ae34e05af9e3 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008013 | 9170acb7-b3dc-4f40-84b8-3872e4486293 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008014 | f28c1a5b-556f-4e50-86d6-4f232f0598ff | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008015 | ca9a4803-da96-43db-be55-b7341ee0637d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008016 | 5289240d-3b7e-4f7a-accf-b7d360a8dfce | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008017 | aa915d21-6b3d-4b1a-b9ff-68cd57dda342 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008018 | 5944d893-687f-4061-8126-89aa2553ca89 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008019 | ea4e508e-0f2e-43e6-b2d6-ed257d7da4df | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008020 | ea4e508e-0f2e-43e6-b2d6-ed257d7da4df | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008021 | 4dd13f47-3faf-4553-982a-1869fc43fd07 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008022 | 777e74a9-97f6-4e2d-9b73-8d636aaff02b | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2029-08-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008023 | b8a3fdc8-efa3-4cd4-b287-ef7b2df953be | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008024 | 0d93b3f6-d6f6-45da-9e32-e019ae2be5b6 | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008025 | 63e69388-e33f-4ad1-97d2-ba89298bedb2 | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008026 | e89edb05-7973-496d-aeca-90c216731081 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008027 | e89edb05-7973-496d-aeca-90c216731081 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008028 | 83ac3794-4a42-4212-9a4a-092feb5c9d29 | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008029 | c828a331-a203-457f-b65e-a2318a19d5a0 | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008030 | c67eece9-46af-4d2a-bc5f-3597c81504c1 | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008031 | 806bdaad-1d63-461a-9c22-de7dcbe19e4f | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008032 | c67eece9-46af-4d2a-bc5f-3597c81504c1 | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008033 | aa9db7ea-2414-4315-b740-2eb376614cd3 | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008034 | f4d0a553-e770-4495-bc7a-c183d1c3c5fc | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008035 | 4e467aa8-09df-4841-a0f3-97a6289c10bd | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008036 | f114e322-c899-46de-9357-83a21a5640f3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008037 | f114e322-c899-46de-9357-83a21a5640f3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-12 | 2029-08-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008038 | cf51b366-f003-4694-b978-4498c17a31be | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008039 | 64081fdf-0206-4423-aacd-9840b31b6d92 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008040 | 66c6c047-d70b-4c8c-8a71-47c4b5ebd739 | Pole | Non-HFTD | Distribution | 2024-08-13 | 2025-08-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008041 | 24b97cdd-fb0a-46d1-831e-ba193fa8f6ca | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008042 | 2a7ea20a-2a43-48f1-93ed-afc6781e1408 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2025-08-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008043 | 00c5e728-236f-4c9d-b6b0-a2175c716be1 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2025-08-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008044 | ff5bf43f-3fc2-4575-bfc9-916a41e345d2 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008045 | a6deb3a0-7a58-4f4b-abe6-907dca1b0c4c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008046 | bd2a51fb-443e-4ff0-89da-f7f4c88e1c90 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2025-08-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008047 | cf51b366-f003-4694-b978-4498c17a31be | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2025-08-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008048 | 2758055d-f378-4cb2-a646-20dbc73ffa57 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008049 | cf51b366-f003-4694-b978-4498c17a31be | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008050 | de6a318c-334c-4d38-a451-a1a9fa185343 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008051 | 5a7417ed-b936-40cb-b832-7a7eb4ece94f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008052 | a90e2965-2580-4833-a55f-b57b249f6804 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008053 | ef228fca-b354-49da-aff9-c9bfd65715b6 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008054 | e488c90b-8931-40fe-9e30-3ac0b82850cf | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008055 | b946d227-13ca-42fe-a6f0-9356da7dceb3 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2029-08-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008056 | 1eb56c69-d6b7-4f71-83aa-e61e70744179 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008057 | 1eb56c69-d6b7-4f71-83aa-e61e70744179 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008058 | e930b169-e40f-4410-92e5-99e8ab7302fe | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008059 | af6f30b5-1a11-4e24-a7a5-bfa0fe89bb55 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008060 | 1a185a4c-3d50-4764-8914-7bac3d10b0c3 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008061 | af6f30b5-1a11-4e24-a7a5-bfa0fe89bb55 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008062 | fea59abf-6aa4-4355-9c3f-e5af4e057f99 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008063 | a2c22b53-0030-4e72-9dfb-256642c42c75 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008064 | cbe93841-c96a-4ce7-98ac-544a0996816c | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008065 | d89b3deb-1661-4d33-86ec-df8ad2c61e46 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008066 | 58045448-9a5e-4661-bb9a-69ebb36b0c44 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008067 | dc30b940-4c56-4455-b098-947eff56ebe9 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2029-08-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008068 | 58045448-9a5e-4661-bb9a-69ebb36b0c44 | Pole | HFTD Tier 2 | Distribution | 2024-08-14 | 2025-08-14 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008069 | a7daa290-19a6-462f-987c-8f4b0cfbf16a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008070 | 4eb31412-ae05-436d-bee9-79837a781a83 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008071 | 4ebe12f5-5150-4d88-8e4c-bc8de6af7cde | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008072 | 2d7f54b6-ec13-49d4-ad2e-13ea9f036365 | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008073 | 4eb31412-ae05-436d-bee9-79837a781a83 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008074 | 3204703e-70a5-4d6a-9308-a6a5586ac12e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008075 | 2d7f54b6-ec13-49d4-ad2e-13ea9f036365 | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008076 | 7f3616a8-a01d-42e9-be95-96b991ed0c4c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008077 | c968a6e0-8327-4c74-be17-b633aeb88752 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008078 | fefcf701-0536-4c12-9c1a-926deb8af5dc | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008079 | 3204703e-70a5-4d6a-9308-a6a5586ac12e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008080 | 5c971849-31d0-402c-8dee-d5063c09323a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008081 | 3204703e-70a5-4d6a-9308-a6a5586ac12e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2025-08-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008082 | 5c971849-31d0-402c-8dee-d5063c09323a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008083 | 05fb4b80-54b7-4384-aca2-87f0712adf6f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008084 | f4465848-7225-43b9-84ce-7b1ef95c5d04 | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008085 | 1d8b32e1-118d-4e52-baa0-d7a7384eb692 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008086 | a7daa290-19a6-462f-987c-8f4b0cfbf16a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008087 | 1d8b32e1-118d-4e52-baa0-d7a7384eb692 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008088 | cf036736-38c7-4659-aaae-6d1bdd6d7a38 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008089 | 7f3616a8-a01d-42e9-be95-96b991ed0c4c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008090 | f909cf9f-d5fb-4f46-9397-124c1201905c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008091 | f909cf9f-d5fb-4f46-9397-124c1201905c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008092 | b516ce67-6bdf-4c19-954a-5332fc33de7f | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2025-08-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008093 | abe063dd-d40d-4922-a6b0-6a2e06549ae9 | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008094 | abe063dd-d40d-4922-a6b0-6a2e06549ae9 | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008095 | 022d26b7-8b22-43cb-9db9-5288d3782091 | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008096 | b7b79708-67be-4b5a-8469-ca4618de803b | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008097 | e40baf70-788c-4753-acad-73a76f38c9fe | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008098 | 41ae1194-ba4a-4690-8a09-4690226153e0 | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2025-08-15 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008099 | e40baf70-788c-4753-acad-73a76f38c9fe | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008100 | 41ae1194-ba4a-4690-8a09-4690226153e0 | Pole | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008101 | 68cd602e-098b-45c6-8927-00a14e7a5405 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-15 | 2029-08-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008102 | bb599592-ddbe-452a-8d42-822cf531ee72 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008103 | bb599592-ddbe-452a-8d42-822cf531ee72 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008104 | 8460ebde-92f9-4455-a83e-948f9d3dae92 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008105 | 920ed3de-7714-44a7-ba30-45821c9bfce2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008106 | 4b642d70-9cdc-4e3a-9939-477f31847dea | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008107 | ca166e90-c815-403f-89ef-db0cd76aeb05 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008108 | ab2af6c1-41d2-4b15-bf71-b1808fde5768 | Pole | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008109 | 894dff3c-0490-4549-beb9-49039df01598 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2025-08-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008110 | 920ed3de-7714-44a7-ba30-45821c9bfce2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008111 | 62532762-36e2-4ab5-b0bb-2efec7ae26cb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008112 | 1c0a65e4-c2d9-41a4-89c5-ca7559720fbe | Pole | HFTD Tier 2 | Distribution | 2024-08-16 | 2025-08-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008113 | a7e88b44-34e4-4dee-adfb-0a7ec8091879 | Pole | HFTD Tier 2 | Distribution | 2024-08-16 | 2029-08-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008114 | 4f0ea774-eb47-4a0b-bafe-fac01893facd | Pole | HFTD Tier 2 | Distribution | 2024-08-19 | 2029-08-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008115 | 3469fa1f-61f1-4f8e-895a-402a2516c729 | Pole | HFTD Tier 2 | Distribution | 2024-08-19 | 2029-08-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008116 | 850681e8-77c4-4377-b037-10243481551b | Pole | HFTD Tier 2 | Distribution | 2024-08-19 | 2029-08-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008117 | 91d3218f-4de4-4d43-b77d-b185110bfd06 | Pole | HFTD Tier 2 | Distribution | 2024-08-19 | 2029-08-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008118 | 9aa565ad-b6e1-4fd9-a29f-22ea83a0f7b1 | Pole | HFTD Tier 2 | Distribution | 2024-08-19 | 2029-08-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008119 | 585e5b5b-b39c-4677-999c-200aee492b34 | Pole | HFTD Tier 2 | Distribution | 2024-08-19 | 2029-08-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008120 | 618ad268-fbf8-48be-9ce7-d57dc372c8f2 | Pole | HFTD Tier 2 | Distribution | 2024-08-19 | 2025-08-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008121 | 02046b06-9a07-41d6-8eff-aa93f8e993a9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008122 | 1c6fb414-48f5-4a24-bab9-53e0baa286f9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008123 | 02046b06-9a07-41d6-8eff-aa93f8e993a9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008124 | b56fa0b7-2dda-43b8-8228-403853b622e8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008125 | 8dcf29db-3601-46c2-901b-e02c6e030791 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008126 | 8b0a8e5e-b21e-4add-8a1f-26883e59559d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008127 | 42b2cc3a-a2bf-495e-8b85-5b5220c4e9cf | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008128 | ae8845dd-a941-4b21-85f2-af0065dce8f1 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008129 | 8f33ce1a-c81a-4cd2-9b74-d732b5d50f3b | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008130 | ae8845dd-a941-4b21-85f2-af0065dce8f1 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008131 | 9d2cc0c0-be0c-4f2c-9112-2497ae8f9e97 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008132 | ae8845dd-a941-4b21-85f2-af0065dce8f1 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008133 | 9d2cc0c0-be0c-4f2c-9112-2497ae8f9e97 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008134 | ae8845dd-a941-4b21-85f2-af0065dce8f1 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008135 | 3c6f1d56-8fb8-4321-96d8-008c36ce7dad | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008136 | 42b2cc3a-a2bf-495e-8b85-5b5220c4e9cf | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008137 | 731d133c-d80e-4ec4-ba10-0f3d0b9eb07a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008138 | 42b2cc3a-a2bf-495e-8b85-5b5220c4e9cf | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008139 | 4be62f04-90a5-4acf-af79-6580eaadada5 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008140 | 42b2cc3a-a2bf-495e-8b85-5b5220c4e9cf | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008141 | 58c196e2-7f9e-4445-b506-8c4ab47e919e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008142 | 42b2cc3a-a2bf-495e-8b85-5b5220c4e9cf | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008143 | d8079e76-9e31-41b5-8bc3-f1b7a1e9e344 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008144 | 2d9a6503-b4d7-44c2-9739-a1747ddd0985 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008145 | a3f58b97-fef7-46a0-bad6-7431c86fec0e | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008146 | 2d9a6503-b4d7-44c2-9739-a1747ddd0985 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008147 | 422b2fdc-33b4-44ad-820c-7358bd9db16b | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008148 | 2d9a6503-b4d7-44c2-9739-a1747ddd0985 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008149 | 0b7469de-dc1d-4bdd-aa1e-0cab39c489f8 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008150 | 4403f1a3-efdf-43f6-a61f-acd1f26c4807 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008151 | 0b7469de-dc1d-4bdd-aa1e-0cab39c489f8 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008152 | bb5c14ea-57d5-4f8a-9ed3-52c22deb6b97 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008153 | bb5c14ea-57d5-4f8a-9ed3-52c22deb6b97 | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008154 | 253ff7ba-3fe5-4300-b1a3-2060ba4cbf5e | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008155 | 253ff7ba-3fe5-4300-b1a3-2060ba4cbf5e | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008156 | e215fcb6-1138-4a4d-a159-425d8ecee0aa | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008157 | a3f58b97-fef7-46a0-bad6-7431c86fec0e | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008158 | a3f58b97-fef7-46a0-bad6-7431c86fec0e | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008159 | f5b898b8-a6db-4efa-a622-fee4687acc2d | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008160 | f5b898b8-a6db-4efa-a622-fee4687acc2d | Pole | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008161 | 58c196e2-7f9e-4445-b506-8c4ab47e919e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-20 | 2029-08-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008162 | b9fc63b7-3505-4165-b8d6-3c3fe82d363f | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008163 | 517acd47-9b87-4f37-9941-925ea87af023 | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008164 | a5d0b0d6-4da2-4f10-b834-7d36d85a2d64 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-08-21 | 2025-08-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008165 | bd3a4acb-c9be-4e87-8ad4-37c23687c2c8 | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2025-08-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008166 | aac693ab-dd80-4caa-9f24-b16bf5d936d6 | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008167 | ee5bf0b3-8a0c-4a8b-847b-d37ed8d28732 | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008168 | 2ccd50e0-70d4-4ef3-ae4c-bfda94d70998 | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008169 | dc093dce-79c3-4548-843d-1e42db79ea48 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008170 | cbd71303-4913-45ef-abf9-3b2662b5c7a6 | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008171 | 4e114290-e1f0-452e-aeb1-bd04a32f9a5e | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008172 | dd7ae483-c358-471b-a262-c27e797e6375 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008173 | dd7ae483-c358-471b-a262-c27e797e6375 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008174 | 0e28891a-d3dc-409c-b7f5-69e1bc37db2a | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008175 | 15918014-214e-4cdd-bf1e-9620f9cb06a1 | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008176 | 60568512-4c22-4efa-93ef-5f3edfa015f6 | Pole | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008177 | ba196bc6-106a-40b4-a5cb-e2e2f7836c60 | Pole | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008178 | af010bdc-c3e5-49a8-9980-17e1bb98eed2 | Pole | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008179 | e461ed9f-fe84-4bc5-a177-0b37ae2487f3 | Pole | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008180 | 0a158297-018d-4a8f-aa01-1da8984a1425 | Pole | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008181 | a6ad3dd8-ab75-4614-9424-b20ed91b81ef | Pole | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008182 | 1e599afc-0367-4e97-b59e-b284e322fa72 | Pole | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008183 | 6e6ad9b1-99ab-4b1d-9c54-6cd9e1e061c6 | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2025-08-23 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008184 | 56fc09c6-df8d-41e6-9589-10754863ee54 | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2029-08-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008185 | 0095b3a3-9bfa-4c88-8041-194496c56c22 | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2029-08-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008186 | 8fc6cc77-f1b2-4242-bc2e-37223f7e127a | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2029-08-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008187 | 93b639ff-af15-48db-a5f5-45aa53518bc2 | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2029-08-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008188 | 85bb58ae-1c9f-4d5b-b6be-a192e7050fc0 | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2029-08-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008189 | 02bd7fef-b72b-4640-ac49-a6ba9bc85910 | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2025-08-23 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008190 | 3efda570-0df8-4fbf-808d-0a993880a02e | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2025-08-23 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008191 | f6a48985-7b13-4b81-af0e-64332ab16587 | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2029-08-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008192 | 7db2c84b-f25d-4f96-ac0b-27d4f1092bad | Pole | HFTD Tier 2 | Distribution | 2024-08-23 | 2029-08-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008193 | dea4ee8c-6dbf-4fb0-9cc0-33550e0b86ac | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-08-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008194 | 72d823ed-e62e-49f8-91c9-ee906f30afa8 | Pole | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-08-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008195 | 60ba8991-f188-4926-9f96-2c00cfb39f7f | Pole | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008196 | edd3694a-b457-4d82-adae-44e41ca88cd6 | Pole | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008197 | 97eb9d87-42a6-4778-b82d-4bcd2fd15a81 | Pole | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008198 | 9bb506b7-f3a7-4004-b46a-0f18d0076ca1 | Pole | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-08-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008199 | d8277ab3-01b5-4d04-8e2d-ba33dde9845b | Pole | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008200 | ee6929e7-1663-48b5-b8bb-cd0bd9d44eb6 | Pole | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008201 | 6aafa712-7c6f-455b-b53a-c97836e1aaee | Pole | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008202 | 52d1e0a8-704b-49e3-809e-f06299d1b273 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008203 | a10ee937-6cec-4c68-aa61-1c96e0007db1 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008204 | 9b91fa0d-a7cf-49c3-9be7-fc46c86dd8c3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-27 | 2025-08-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008205 | 52d1e0a8-704b-49e3-809e-f06299d1b273 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008206 | 9b91fa0d-a7cf-49c3-9be7-fc46c86dd8c3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008207 | 6a46457f-ae18-4c2c-87a8-e43dccde9dc6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008208 | e2a773ce-09fa-4ab6-a9d8-faa267903519 | Pole | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008209 | 4a29cdce-e7a6-4b93-bf43-978d8475835d | Pole | Non-HFTD | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008210 | 79861150-8767-40ea-bac4-b3178f6bce6e | Pole | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008211 | 9b91fa0d-a7cf-49c3-9be7-fc46c86dd8c3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-27 | 2025-08-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008212 | 4735a001-50b9-4520-8daf-38d7efbc9327 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008213 | 3dbb73c7-abda-4e19-97a7-057754898280 | Pole | HFTD Tier 2 | Distribution | 2024-08-28 | 2025-08-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008214 | 4735a001-50b9-4520-8daf-38d7efbc9327 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-28 | 2025-08-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008215 | f22efe78-b1e4-4e06-ad76-bd7c3c640edc | Pole | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008216 | 897e2c40-da70-4820-bcf6-42272103b693 | Pole | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008217 | f19ed8fc-a211-44a3-a8a7-e982474195ed | Pole | HFTD Tier 2 | Distribution | 2024-08-28 | 2025-08-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008218 | 980c53f3-768a-4d05-8035-fd369f2990c8 | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008219 | f19ed8fc-a211-44a3-a8a7-e982474195ed | Pole | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008220 | 980c53f3-768a-4d05-8035-fd369f2990c8 | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008221 | 897e2c40-da70-4820-bcf6-42272103b693 | Pole | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008222 | 04a7c679-f1d8-4216-ae60-0d6bc13fedc4 | Pole | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008223 | f19ed8fc-a211-44a3-a8a7-e982474195ed | Pole | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008224 | 0a60ca57-05af-4411-9016-0d2b2e346d9e | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2025-08-29 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008225 | 95cf3268-72bd-48ae-95c2-62dad8eb76b2 | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008226 | 95cf3268-72bd-48ae-95c2-62dad8eb76b2 | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008227 | 113d2d12-c28e-40c5-922c-35f57589739e | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008228 | 3f9042fa-9a6e-4ada-b9cf-aa675b248a8e | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008229 | 4c5b9dc5-efa6-44b5-a8b7-53498f5fdcb5 | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008230 | d2d3e694-c4ca-4fe6-bbc9-b989dcdc38ba | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008231 | 4c5b9dc5-efa6-44b5-a8b7-53498f5fdcb5 | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2025-08-29 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008232 | 9b4a3daf-6ecb-4515-9771-6c3f175b2ad2 | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008233 | 3b148383-fac3-448e-a7a6-663efa94f4a1 | Pole | HFTD Tier 2 | Distribution | 2024-08-29 | 2029-08-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008234 | 3e014d7f-5e37-4e86-85cc-c905686c506b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008235 | 8f7d897c-0451-4f46-a11e-e1e01536b537 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008236 | e430b5cf-ccd6-4495-89c4-827443c1a91e | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008237 | 784cbe6f-27d4-4370-b960-5910cb286b1c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008238 | 97420605-2c4b-46ee-942a-308e15a5e4ab | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008239 | 25a5be80-0cba-4d78-8010-ad79b334c296 | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008240 | d57e036c-9b8e-4a1a-81dd-7f282694df7d | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008241 | 26887caf-d722-4a80-948f-dc947af8318e | UG Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2025-08-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008242 | d57e036c-9b8e-4a1a-81dd-7f282694df7d | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008243 | ef6341f5-a4b1-4b63-ae47-1b510a96d668 | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2025-08-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008244 | 4784d0f3-b5e0-4090-afcf-82d74daf8a3b | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008245 | 4784d0f3-b5e0-4090-afcf-82d74daf8a3b | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008246 | 03ae7ca2-e181-4865-a445-089f9ddd64d8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008247 | 3e014d7f-5e37-4e86-85cc-c905686c506b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008248 | 10ace6f9-3b5f-4024-bfda-b1671bb5e88b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008249 | 3e014d7f-5e37-4e86-85cc-c905686c506b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008250 | c9f83f49-f7a6-434e-b307-a9806ee4952f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008251 | ddcfbe57-d5c7-40ff-8a04-007aa614474e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008252 | c9f83f49-f7a6-434e-b307-a9806ee4952f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008253 | 60718a68-288b-4036-a653-b03e1a104af0 | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008254 | c9404292-4d5d-4262-8df8-e9aa57875dc9 | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008255 | 43d3198a-da8a-470e-a508-06310237536c | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008256 | 43d3198a-da8a-470e-a508-06310237536c | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2029-08-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008257 | 36386d3d-503f-4990-afb5-4385acc1a86c | Vault | Non-HFTD | Distribution | 2024-09-03 | 2025-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008258 | 9752c261-494a-410b-9fa7-d96d775575e7 | Pole | Non-HFTD | Distribution | 2024-09-03 | 2025-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008259 | c893e6ae-926c-4f8b-a2cd-53026b67d8a4 | Regulator | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008260 | 36c05ee7-e3a9-47f9-bfe9-d1371905c3d8 | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008261 | c893e6ae-926c-4f8b-a2cd-53026b67d8a4 | Regulator | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008262 | fdbc04ba-0cb6-4bd6-bba0-a2a3842beacd | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008263 | a6dc0ec0-2264-4dd8-8114-60bea90a57a8 | Pole | Non-HFTD | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008264 | 75e2e27b-0ced-474d-adfe-ebc730814ce9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008265 | a6dc0ec0-2264-4dd8-8114-60bea90a57a8 | Pole | Non-HFTD | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008266 | 75e2e27b-0ced-474d-adfe-ebc730814ce9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008267 | fdbc04ba-0cb6-4bd6-bba0-a2a3842beacd | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008268 | d3fcdd59-5e7c-4037-9850-c42d31770e06 | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008269 | f65813cc-09e0-429c-9b52-b6ce1717baaf | Pole | Non-HFTD | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008270 | f1ea5892-335c-44a8-a466-213f148a3aca | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008271 | 6f7a17fd-0406-401a-9cc4-94bf8ab22874 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008272 | 98df6b19-f784-4590-9c9c-877b6c1c6562 | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2025-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008273 | 6f7a17fd-0406-401a-9cc4-94bf8ab22874 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008274 | 98df6b19-f784-4590-9c9c-877b6c1c6562 | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008275 | 6f7a17fd-0406-401a-9cc4-94bf8ab22874 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-03 | 2025-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008276 | d91c6b95-10b4-4a43-b3db-3473bf58f7e8 | Pole | Non-HFTD | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008277 | fd0f2485-c363-4c31-8f60-5ab969e70705 | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2025-09-03 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008278 | b7462f9c-ff97-40e4-80f1-2675da7256d8 | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008279 | 87e5e68a-769f-47da-9fe2-4c510b9ac5a7 | Pole | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008280 | 0f6f2c08-d81f-493a-8544-67456633ca15 | Pole | Non-HFTD | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008281 | d91c6b95-10b4-4a43-b3db-3473bf58f7e8 | Pole | Non-HFTD | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008282 | 0f6f2c08-d81f-493a-8544-67456633ca15 | Pole | Non-HFTD | Distribution | 2024-09-03 | 2029-09-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008283 | 4bf69f74-13be-48d1-9d6b-61e6a0d02077 | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008284 | 45179ca9-b8e7-4285-9f6c-6686ccc6c1fa | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2025-09-04 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008285 | f939819f-47de-4e31-82fc-da55cd52e87a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008286 | 45179ca9-b8e7-4285-9f6c-6686ccc6c1fa | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008287 | 2a2aa738-96dd-42d0-9bd4-c0d01acd60e8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2025-09-04 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008288 | 64aa5118-9871-488d-b349-0de950d7c751 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008289 | b9a806ed-0f0c-4966-bd9e-793cfc198088 | Pole | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008290 | a1ccc85e-9664-47d5-9f44-c75cab20c498 | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008291 | 42706cf4-8db6-4a36-bac8-b0926dd77ca0 | Pole | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008292 | 55663507-cc45-495b-b8d3-9df183a7125d | Pole | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008293 | 248d4c34-d0a1-43db-a6c7-6067f91eff6d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008294 | 00fe60ff-f093-45f5-bcf2-4f0b8051acc0 | Pole | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008295 | ce2402a0-c1ad-4e6c-b24a-a6ce8966f49a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008296 | a5dbfee8-2236-488c-9b2f-53b3d1582f5d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008297 | 70e5e648-2836-499a-96dc-1ce87c3d6ba9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2025-09-04 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008298 | 9eb5cc44-e521-4931-8b01-e7a96b8f0e71 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008299 | 9eb5cc44-e521-4931-8b01-e7a96b8f0e71 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2025-09-04 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008300 | 2a2aa738-96dd-42d0-9bd4-c0d01acd60e8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008301 | 18824233-23ab-4de9-b882-60e331184aab | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008302 | 95097b56-7105-4335-b01f-7a51e050f596 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008303 | 95097b56-7105-4335-b01f-7a51e050f596 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008304 | c9b03c5d-a6e8-4be9-9e78-5e1e4049b26b | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2025-09-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008305 | b26aeaea-7a33-4ed7-974f-3103a554fc6b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008306 | 513a380e-c593-42be-b7a5-51a578cd18b4 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008307 | 513a380e-c593-42be-b7a5-51a578cd18b4 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2025-09-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008308 | 513a380e-c593-42be-b7a5-51a578cd18b4 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008309 | 00bfb561-d849-477f-9b49-af7b63141875 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008310 | f8fb9b64-176f-4c5f-82aa-b13c4f627146 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008311 | 88c30d26-df83-4c3c-b6ae-328ea4ddce50 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2025-09-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008312 | 284cc33e-fb45-45e1-9613-d45e8cc13ff5 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008313 | 5fef2ef5-b8c0-40af-b794-ba96bdcdd4d0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008314 | c679b097-ec2a-4273-90fe-fbb832bca1d9 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008315 | 10e4a74e-3127-4808-bcd6-b1abe3dda076 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008316 | 00bfb561-d849-477f-9b49-af7b63141875 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008317 | ec361fe0-dd2f-408c-866b-e347b13a04de | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008318 | 4c633712-9df8-4347-9516-eca1bd47ff60 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008319 | 430dd346-caa2-4f1d-93b7-1d5aafe993ce | Pole | HFTD Tier 3 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008320 | 88c30d26-df83-4c3c-b6ae-328ea4ddce50 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008321 | 539d5fe6-e28a-4e83-b94f-b5a8737f1a15 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008322 | 539d5fe6-e28a-4e83-b94f-b5a8737f1a15 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008323 | 284cc33e-fb45-45e1-9613-d45e8cc13ff5 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2025-09-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008324 | 284cc33e-fb45-45e1-9613-d45e8cc13ff5 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008325 | c679b097-ec2a-4273-90fe-fbb832bca1d9 | Pole | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008326 | 898ac8d5-697a-4a34-91b6-4ed5aac2f7ed | Padmount-Ã¡Transformer | HFTD Tier 3 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008327 | 898ac8d5-697a-4a34-91b6-4ed5aac2f7ed | Padmount-Ã¡Transformer | HFTD Tier 3 | Distribution | 2024-09-05 | 2029-09-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008328 | b77c7acc-0010-41fe-8a36-ad415b2d1dbc | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-06 | 2025-09-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008329 | 35a0559d-e418-405f-a50f-2664e38cc4c7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008330 | 0ecaaccd-81dd-4f54-83f1-246ccb0f9d2c | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008331 | 2b2e861c-8e5f-48f0-a4b9-e43ebadee05f | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008332 | e7d10817-71c0-47db-84f8-301b58adb44a | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008333 | d374c432-f55f-4f2b-99c5-d5efed76a500 | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008334 | e7d10817-71c0-47db-84f8-301b58adb44a | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008335 | ed23bff9-e665-4032-8365-e81d235272ae | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008336 | 1f0c9681-885a-45d1-b929-68213a6e6d6a | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008337 | 693d039e-a074-4638-8094-25ed5b3809d7 | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008338 | 1f0c9681-885a-45d1-b929-68213a6e6d6a | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008339 | 0bd7de10-4228-48d3-bf4d-1f552e3bcdb8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008340 | d374c432-f55f-4f2b-99c5-d5efed76a500 | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008341 | 71640dac-c5ae-49b7-8379-2599068ec6cf | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008342 | f7a0b853-f7d6-4eaf-be62-8ffb828ecfde | Pole | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008343 | 0bd7de10-4228-48d3-bf4d-1f552e3bcdb8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008344 | 0bd7de10-4228-48d3-bf4d-1f552e3bcdb8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-06 | 2029-09-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008345 | f4c4e1c9-3dd3-4273-b8a4-0ba62eccf51b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008346 | c216953f-e896-471b-a5ce-49af5b10d55c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008347 | 9b4c3d83-2463-4ae4-8942-c43555c831d2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008348 | c216953f-e896-471b-a5ce-49af5b10d55c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008349 | b4de29bd-d366-40d5-8d31-0c2cafa66726 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008350 | 89353253-51d1-4b8f-afb5-98263f8566bd | Pole | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008351 | b5b7600b-d46e-4dc2-9c94-df8af112cb8f | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008352 | 911ade34-c8b4-4669-a595-df6b9a0072bb | Pole | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008353 | 097412e0-3e53-4310-8900-9ef522481e03 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2025-09-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008354 | c0c329b6-7bc1-4c34-96a6-1ac3d9766d93 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008355 | a2859258-4b61-4ed0-9db0-17a289e02c27 | Pole | HFTD Tier 2 | Distribution | 2024-09-09 | 2025-09-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008356 | c0c329b6-7bc1-4c34-96a6-1ac3d9766d93 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008357 | 77a85b68-194d-4913-a691-0a64e85d8abd | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008358 | 77a85b68-194d-4913-a691-0a64e85d8abd | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008359 | 77a85b68-194d-4913-a691-0a64e85d8abd | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2025-09-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008360 | f5a9ddb7-f429-4572-89a1-1632da1a3920 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008361 | f5a9ddb7-f429-4572-89a1-1632da1a3920 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008362 | f5a9ddb7-f429-4572-89a1-1632da1a3920 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-09 | 2029-09-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008363 | f0c5d5bc-87e6-4559-bae7-05f5406f4430 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008364 | c11f256f-47b0-4fd3-b4c1-aa92b8ebecd1 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008365 | 80b34a8b-ff90-4ec8-a151-b9f0f6e08c35 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008366 | 5ba898ae-0e68-4baf-83a7-9831333ed980 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008367 | e1953949-f163-4b67-8ff0-1507173ad872 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-10 | 2025-09-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008368 | dd70452d-c855-4298-a420-84c9465f5771 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008369 | 924a094c-c072-42b8-b5a8-3840d971d118 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008370 | b06f52d5-6710-4cdf-af4d-df0ee2967cb8 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008371 | 72c21e5a-e20e-4864-b3c8-10d26a644dcb | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008372 | b06f52d5-6710-4cdf-af4d-df0ee2967cb8 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2025-09-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008373 | dc44779f-7b4e-4f16-baa8-39d59448a797 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008374 | 414b8e48-01ae-4bc4-affe-b6ddbb264229 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008375 | 4d58d2c4-07d8-4442-8bc5-42e9b1d22c1f | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008376 | f0c5d5bc-87e6-4559-bae7-05f5406f4430 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008377 | 4d58d2c4-07d8-4442-8bc5-42e9b1d22c1f | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008378 | f0c5d5bc-87e6-4559-bae7-05f5406f4430 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008379 | 4d58d2c4-07d8-4442-8bc5-42e9b1d22c1f | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008380 | 80b34a8b-ff90-4ec8-a151-b9f0f6e08c35 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008381 | a0a88d06-a48b-47d6-bac8-ff2527fc38e2 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008382 | 924a094c-c072-42b8-b5a8-3840d971d118 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008383 | 1d8c96a8-659e-4aa0-8aa3-1ee23a62b7f2 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008384 | 924a094c-c072-42b8-b5a8-3840d971d118 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008385 | 1d8c96a8-659e-4aa0-8aa3-1ee23a62b7f2 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008386 | 0c825709-f93f-4ca0-8e51-f1054c014cb0 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2029-09-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008387 | f0defdfd-0a74-41cc-82dc-71c0dd4bbde2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008388 | d571e7b4-404c-42e8-a7db-42beeee2cb5a | Pole | Non-HFTD | Distribution | 2024-09-11 | 2025-09-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008389 | 3a51b237-7289-42b8-81ff-dbb4c27cff08 | Pole | Non-HFTD | Distribution | 2024-09-11 | 2025-09-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008390 | f0defdfd-0a74-41cc-82dc-71c0dd4bbde2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008391 | 9a1dad77-3601-44a7-b986-79b6e2596cf4 | Pole | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008392 | 1130a881-5be0-4d92-b79b-0473f8890dbd | Pole | Non-HFTD | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008393 | 3a70867b-d7b4-445b-ba01-7f4c54e1c23d | Pole | Non-HFTD | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008394 | bf5e860f-cd3c-4262-99ec-0af9e410d2c1 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008395 | bf5e860f-cd3c-4262-99ec-0af9e410d2c1 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008396 | bf5e860f-cd3c-4262-99ec-0af9e410d2c1 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008397 | 6f176021-e74e-455d-a854-d9b085cdadb8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008398 | 6f176021-e74e-455d-a854-d9b085cdadb8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008399 | 5f86b496-e863-44d9-b3aa-52d4574b21d0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008400 | 8f80816b-3a75-4335-9db4-5b0cd02c74df | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2025-09-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008401 | e032e6a4-e8d9-472e-8991-b3c4b2a58119 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008402 | e032e6a4-e8d9-472e-8991-b3c4b2a58119 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008403 | d17716f3-0c16-4461-a387-b1e6de22d42d | UG Transformer | Non-HFTD | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008404 | d17716f3-0c16-4461-a387-b1e6de22d42d | UG Transformer | Non-HFTD | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008405 | f2701f3d-6cd7-4bc2-9a85-d02b5da82e03 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008406 | f2701f3d-6cd7-4bc2-9a85-d02b5da82e03 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008407 | 8f80816b-3a75-4335-9db4-5b0cd02c74df | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008408 | 4ee6c160-52a1-49aa-8e7a-68c0d6eeaab3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008409 | 8f80816b-3a75-4335-9db4-5b0cd02c74df | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-11 | 2029-09-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008410 | 8f082a70-ffa7-4330-ac6d-1b5b3b9636d7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008411 | 8f082a70-ffa7-4330-ac6d-1b5b3b9636d7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008412 | 031cd921-b172-4d56-b104-b8cfb8a57b22 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008413 | 031cd921-b172-4d56-b104-b8cfb8a57b22 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008414 | 031cd921-b172-4d56-b104-b8cfb8a57b22 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008415 | 35d9c21e-85e5-440d-8a62-7d6801930de6 | Pole | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008416 | c6740c73-912d-4352-ac24-f541feab8d4a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008417 | d03b49c7-bfee-4d4d-a888-f6d26b033c8c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008418 | efff9152-ae47-4345-beb1-e689dce9f2b5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2025-09-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008419 | 0541f9e5-ab4f-4e97-ac77-3093f244c390 | Pole | HFTD Tier 2 | Distribution | 2024-09-12 | 2025-09-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008420 | b1f41d8a-2b1b-4f3a-9daf-add645f296ae | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008421 | 045bbcdb-320d-4901-83fb-70a4d4a09408 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008422 | 045bbcdb-320d-4901-83fb-70a4d4a09408 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008423 | c6740c73-912d-4352-ac24-f541feab8d4a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008424 | 5bde19f2-16ac-450f-bcfd-59ab38c0ce24 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008425 | 8890cef5-4303-41bb-9c39-32eb271b34b7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008426 | b018ebbc-f7bd-441e-a8cf-bc91e18320e7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008427 | a85812cc-7557-4bcc-9fd2-1e7ef2412009 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008428 | 375d8217-1009-4b84-9509-da69e4df4b33 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008429 | 2cf3ae52-6bc9-41d8-b9ea-f684fd591569 | Pole | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008430 | 8890cef5-4303-41bb-9c39-32eb271b34b7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008431 | 5bde19f2-16ac-450f-bcfd-59ab38c0ce24 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008432 | a85812cc-7557-4bcc-9fd2-1e7ef2412009 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-09-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008433 | 22b06d7d-df49-4c48-beac-205d86e00b1e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008434 | da106805-3209-4ef1-a6d1-07adf8a093ad | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-09-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008435 | 22b06d7d-df49-4c48-beac-205d86e00b1e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008436 | 1bc8f556-3ed8-4aac-a3d7-57dd81fbd252 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-09-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008437 | da106805-3209-4ef1-a6d1-07adf8a093ad | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008438 | b4f25afd-19cb-4d87-8065-72689472daa4 | Pole | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008439 | 667b38d9-9801-4fef-a23f-d4b0366252ce | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008440 | b4f25afd-19cb-4d87-8065-72689472daa4 | Pole | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008441 | 1bc8f556-3ed8-4aac-a3d7-57dd81fbd252 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008442 | 48dac6d5-0ac4-46be-8089-e59c4f80afeb | Pole | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-09-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008443 | b4f25afd-19cb-4d87-8065-72689472daa4 | Pole | HFTD Tier 2 | Distribution | 2024-09-13 | 2029-09-12 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008444 | 48dac6d5-0ac4-46be-8089-e59c4f80afeb | Pole | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-09-13 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008445 | 666ae7e8-7c1f-44f3-98d9-9218624de691 | Pole | HFTD Tier 2 | Distribution | 2024-09-16 | 2029-09-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008446 | dbfb4d64-ab61-4b30-9d6a-d918aa99d51a | Pole | HFTD Tier 2 | Distribution | 2024-09-16 | 2029-09-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008447 | a293384e-2f2a-4004-a42c-fde162cc8db1 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-16 | 2029-09-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008448 | 8deb43ac-9beb-4f9d-9014-81c024399c88 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-16 | 2025-09-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008449 | 780ec16d-53f0-4330-9f4b-d8375b96cdf6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-16 | 2029-09-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008450 | 8deb43ac-9beb-4f9d-9014-81c024399c88 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-16 | 2029-09-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008451 | 258b0d67-5a5b-4089-9132-40754ba8e753 | Pole | HFTD Tier 2 | Distribution | 2024-09-16 | 2029-09-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008452 | ef8ca2e1-8f6b-487a-9c04-1af4af28ed68 | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008453 | 44cb1e4e-97a5-4330-b35c-3a339c240fe3 | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2025-09-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008454 | 04f4d665-90ac-48e0-8497-74080e4fbaec | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008455 | ea826e62-3185-4104-a307-41ab067922c0 | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008456 | e217976e-cb6d-40d6-9dc9-a95420ff798b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-17 | 2025-09-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008457 | d2dfd567-9fdb-4b9f-a05c-37bfb72dc57b | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008458 | 093c325f-5d17-4478-83ff-b90afd36b376 | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008459 | ef8ca2e1-8f6b-487a-9c04-1af4af28ed68 | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008460 | 7a798b57-e375-4f19-b64a-48bb8d7110ad | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008461 | ada1e453-68fe-4124-a348-b24bbbd7b21c | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008462 | 4702ccb5-077c-4732-9949-82a15f0d55e4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008463 | 1e1c8764-fef4-4795-93d3-3c77c6aa7749 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008464 | d2dfd567-9fdb-4b9f-a05c-37bfb72dc57b | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008465 | 1e1c8764-fef4-4795-93d3-3c77c6aa7749 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008466 | 729a4535-9628-4a35-88e2-ae02ea630f65 | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008467 | 4fb2eeba-2ef1-4676-99d7-a343a671362b | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008468 | b7a81c84-e4d8-45b6-9d76-81bc291f3525 | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008469 | 7a798b57-e375-4f19-b64a-48bb8d7110ad | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2025-09-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008470 | 25bccd6b-91db-4d64-9070-6578e8a92155 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-17 | 2025-09-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008471 | ba614ff9-2c7f-4255-9580-e03e6900035c | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008472 | 4314996b-c61b-47b6-b02c-875e96fae5ad | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008473 | d80ac435-5618-4a42-a267-cf6ec0c70e20 | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008474 | 1037f6c6-5d25-4fee-9b31-f52fe22cdccb | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2025-09-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008475 | 3e281911-ee7e-4344-aa26-72387afb487d | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2025-09-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008476 | 3e281911-ee7e-4344-aa26-72387afb487d | Pole | HFTD Tier 2 | Distribution | 2024-09-17 | 2029-09-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008477 | 32028755-7c3e-4713-8dab-fb16fe3a6ae0 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008478 | bde13681-61c5-4e76-9c75-339b759ccd11 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008479 | 32028755-7c3e-4713-8dab-fb16fe3a6ae0 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008480 | bde13681-61c5-4e76-9c75-339b759ccd11 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008481 | 32028755-7c3e-4713-8dab-fb16fe3a6ae0 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008482 | 691d582b-8c8f-412a-ac36-3f6c22df672a | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008483 | 0e5a9301-35c2-4637-8e22-d708e8724f1b | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008484 | d0b0cff4-84f5-491f-a283-c57ae0476fd3 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008485 | 20725215-60e9-4d78-929d-e8327f4962d7 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008486 | ab688ff8-3f48-44bc-abb0-8f0ea8809b98 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008487 | 1949efd1-f131-482a-bca3-3f7161ec7e8c | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008488 | 1949efd1-f131-482a-bca3-3f7161ec7e8c | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008489 | 878446b2-5ade-413e-ba81-802336b48ce3 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008490 | 22c8646b-a4f2-4ed5-a41e-b824672bbc1f | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008491 | 811edc8d-7b4c-42ae-940d-4c041d6756f9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008492 | dd5a69b4-f446-4194-bdbe-297373683036 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2025-09-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008493 | dd5a69b4-f446-4194-bdbe-297373683036 | Pole | HFTD Tier 2 | Distribution | 2024-09-18 | 2029-09-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008494 | 4ba5beb7-0690-4d6d-87bd-31d5d29fdb4b | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2029-09-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008495 | 498d6441-5d01-49a7-a349-615b525cdc6b | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2029-09-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008496 | 2bad614c-1a02-41c3-9ffe-76520d4fa0fa | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2029-09-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008497 | 15d8d022-3616-4351-b513-e767b8706c10 | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2025-09-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008498 | 3d442994-fbc9-440a-8ac4-98d338d625cd | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2029-09-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008499 | 7e062ead-54e6-42a2-aa0a-8e42fe3f0ac8 | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2029-09-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008500 | 7302dd1e-6b9c-4010-97e7-00f1be015818 | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2025-09-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008501 | 5f215efc-3b1a-4b19-8800-c1c50c95afee | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2029-09-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008502 | 5f215efc-3b1a-4b19-8800-c1c50c95afee | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2025-09-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008503 | 373b9596-0726-4921-b45c-7bee9bcaa0e4 | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2025-09-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130008504 | 9e4912f9-89af-441f-b7d9-31c0dfa8fe11 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008505 | ccd8240f-752d-42d5-9477-f19a37f0b5da | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008506 | 1c1c41dd-bdab-4a7e-af69-20304636e0e6 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008507 | ccd8240f-752d-42d5-9477-f19a37f0b5da | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008508 | 982c8f83-9ec8-4c18-a5cc-4cc344901ffd | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008509 | 0d03fb5d-ce63-4936-bf21-1a51d6758613 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2025-09-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008510 | 5ce7de4d-f762-4d1b-921b-a0c58b9e2061 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008511 | d912a9b5-0cec-4f3f-9f4f-bbee9506060e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008512 | ccd8240f-752d-42d5-9477-f19a37f0b5da | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008513 | d912a9b5-0cec-4f3f-9f4f-bbee9506060e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008514 | 4e462b09-aecb-4b86-a737-5aaf5c0f26cb | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008515 | 495b55f1-988d-4ffa-8336-db869c4ed609 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008516 | 90ac7f1c-e4cc-4424-9aa5-904650eb58f4 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008517 | 4f77adfa-3769-49b6-b3d2-331275825de3 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008518 | 4f77adfa-3769-49b6-b3d2-331275825de3 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008519 | 1050adb4-a432-4f61-8d7f-4cdceef651b5 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008520 | 490fe5d1-f046-46aa-bbfd-ed73c3671400 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008521 | 1050adb4-a432-4f61-8d7f-4cdceef651b5 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2025-09-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008522 | f34d7bf0-2849-4d73-81be-4ca53a83e41c | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2025-09-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008523 | 1050adb4-a432-4f61-8d7f-4cdceef651b5 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2025-09-20 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008524 | 45cff1a8-0a92-44d1-8d2c-ae7125517c4c | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008525 | a60ba85a-468d-49bc-bf2f-399e52d3376d | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008526 | 67f9a602-5b07-4ea9-99e4-fcc4615d2ce1 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008527 | 4917f07a-890d-4317-a8c2-2224dab84194 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008528 | f34d7bf0-2849-4d73-81be-4ca53a83e41c | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008529 | 45cff1a8-0a92-44d1-8d2c-ae7125517c4c | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008530 | 67f9a602-5b07-4ea9-99e4-fcc4615d2ce1 | Pole | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008531 | bb7e8be9-3e60-4ac9-8626-7bf59cb8c5eb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-20 | 2029-09-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008532 | 4fe4bd76-7b13-42ad-a8de-7ef2dfb23bc8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008533 | f3138c4e-5090-4f54-a3ab-457bfa537afc | Pole | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008534 | ca121bbf-5e5c-4a9d-ad7e-684192195c36 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008535 | 4fe4bd76-7b13-42ad-a8de-7ef2dfb23bc8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008536 | ca121bbf-5e5c-4a9d-ad7e-684192195c36 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2025-09-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008537 | 4fe4bd76-7b13-42ad-a8de-7ef2dfb23bc8 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2025-09-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008538 | 616b0213-ce3c-4099-b18b-c2649775bc54 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008539 | 616b0213-ce3c-4099-b18b-c2649775bc54 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008540 | 603d60b6-5957-4ce1-9546-e53194a8ac32 | Pole | HFTD Tier 2 | Distribution | 2024-09-24 | 2025-09-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008541 | 625bd66b-762a-4c3b-9c2d-e694347917aa | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008542 | 625bd66b-762a-4c3b-9c2d-e694347917aa | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008543 | 71894b0d-cb10-4460-8948-7680d703053b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008544 | d7266507-b4e9-4fd7-985c-1f5266f889d9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008545 | 71894b0d-cb10-4460-8948-7680d703053b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008546 | d7266507-b4e9-4fd7-985c-1f5266f889d9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008547 | 71894b0d-cb10-4460-8948-7680d703053b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2025-09-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008548 | a29f8ef9-e490-40a6-ad70-272b1d846599 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008549 | 943a068e-49ae-49ba-be04-cd7ace0f23f0 | Pole | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008550 | e46548fe-26c9-46d9-a457-f75b9b20e905 | Pole | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008551 | 1392a303-fa16-40db-9516-d9491920f833 | Pole | HFTD Tier 2 | Distribution | 2024-09-24 | 2029-09-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008552 | b83f15de-22bd-42c8-826f-8f2fe8a6b048 | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008553 | 6e1196d2-9c4c-4172-a5cf-1f2c1625cdd7 | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008554 | b83f15de-22bd-42c8-826f-8f2fe8a6b048 | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2025-09-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008555 | 6e1196d2-9c4c-4172-a5cf-1f2c1625cdd7 | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008556 | b83f15de-22bd-42c8-826f-8f2fe8a6b048 | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008557 | 0c6629f2-e6a0-48b2-bd9e-15e9e4821938 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008558 | 0c6629f2-e6a0-48b2-bd9e-15e9e4821938 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008559 | dcf512a8-2350-4306-a999-8bda830d7a7a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2025-09-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008560 | dcf512a8-2350-4306-a999-8bda830d7a7a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2025-09-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008561 | 40242096-005a-406e-a709-4b1cffb03ddf | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008562 | ef8f6506-f069-49db-aaa1-bb0603e83977 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008563 | f9698d70-4e85-4d17-9981-158a2c930642 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008564 | 40242096-005a-406e-a709-4b1cffb03ddf | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008565 | 8339bf41-6dff-47a1-8d04-103fe99994ed | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008566 | a59e60d3-d70b-465e-9090-b5b8aeceb967 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008567 | 8339bf41-6dff-47a1-8d04-103fe99994ed | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008568 | a59e60d3-d70b-465e-9090-b5b8aeceb967 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008569 | e1ecd1c9-69a3-4b2c-aa35-90fe941e0699 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008570 | a5b0b648-043d-4c4e-a80e-a263eb99cff2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008571 | bab13b6b-1f49-4b9d-82cc-861954e2eecd | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008572 | a5b0b648-043d-4c4e-a80e-a263eb99cff2 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008573 | 81de9156-a9e7-45e4-8b41-6b0f15e059bb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008574 | deb12a2d-3afb-4901-8998-700a11a9671e | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008575 | ec6e7566-9726-4e8e-b088-5b646e421310 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008576 | 7f839f12-270b-4002-8445-73932c6989ac | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008577 | e1915895-496e-4540-9e50-961ad0a86daa | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008578 | 7f839f12-270b-4002-8445-73932c6989ac | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008579 | 9b4a9be7-d8b4-473d-86a1-9c61794cb462 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008580 | 7f839f12-270b-4002-8445-73932c6989ac | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2025-09-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008581 | 9b4a9be7-d8b4-473d-86a1-9c61794cb462 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008582 | 9aa9fbf9-72ce-4ab7-ad16-ebbde0a0d7db | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008583 | 06fec07c-fb72-48f1-8e1e-f44bfc179d1f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008584 | 9aa9fbf9-72ce-4ab7-ad16-ebbde0a0d7db | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008585 | 05eac915-04b0-4990-bf81-a3ad0fbc52b4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008586 | 9aa9fbf9-72ce-4ab7-ad16-ebbde0a0d7db | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008587 | 05eac915-04b0-4990-bf81-a3ad0fbc52b4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008588 | 15993d1c-6199-4e10-a6a8-d21adb4e1cd9 | Pole | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008589 | e1ecd1c9-69a3-4b2c-aa35-90fe941e0699 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008590 | c650aabf-ee71-497e-91c9-ed4aefdea76e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008591 | c650aabf-ee71-497e-91c9-ed4aefdea76e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008592 | ec6e7566-9726-4e8e-b088-5b646e421310 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008593 | 06fec07c-fb72-48f1-8e1e-f44bfc179d1f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008594 | 05eac915-04b0-4990-bf81-a3ad0fbc52b4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008595 | 460dbf39-5bbf-4a44-869b-d6441006e399 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-25 | 2029-09-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008596 | 5e175530-feda-4bd7-8308-4eeaafb10b5b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008597 | 23a9b11c-4bd3-490e-a355-ddc69c8fa4f5 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2025-09-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008598 | 9df61872-f627-4f93-827e-c6a489ee69c3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008599 | b9d1284d-6773-4142-ba43-919acad42bb1 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008600 | b96076d4-570e-443b-b5f3-810ef3408016 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2025-09-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008601 | 604e91af-cdd9-4464-96be-3ac0b51743bd | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008602 | 8c7f96e7-fd52-4816-bf8b-ad48b9440032 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008603 | 1c080881-f66f-4cf4-8242-f1c87f8fbf44 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008604 | a706f29f-754b-4144-be72-9efca33ebe1a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008605 | 1c080881-f66f-4cf4-8242-f1c87f8fbf44 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008606 | a7352bd5-844f-46b3-82c7-e2da06bfe9e7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008607 | d75991ff-53c3-4cb2-a5ab-c216698abe7d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008608 | 36b0deac-50a5-4a3d-992b-2ddfc4e65f5f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008609 | aa421657-33dd-4aa3-9fbb-b6c44bba54d7 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008610 | 36b0deac-50a5-4a3d-992b-2ddfc4e65f5f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008611 | b96076d4-570e-443b-b5f3-810ef3408016 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008612 | 0b41e0b4-e3f7-46c5-8298-c99c7482e987 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008613 | b96076d4-570e-443b-b5f3-810ef3408016 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008614 | 0b41e0b4-e3f7-46c5-8298-c99c7482e987 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008615 | 8c7f96e7-fd52-4816-bf8b-ad48b9440032 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008616 | 8c06c43b-b8c7-4580-ad2b-7a428073a79d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008617 | a7352bd5-844f-46b3-82c7-e2da06bfe9e7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008618 | a8e07211-1b9f-466b-9785-89f05761ef5f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008619 | bf9efc98-26b7-4387-b982-824563a77c67 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008620 | 53e0d389-361f-4e27-84a1-ac6232ef139b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008621 | bf9efc98-26b7-4387-b982-824563a77c67 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008622 | 09a95b8c-e777-4c27-af37-e03d9aa372d6 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2025-09-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008623 | f73b8950-be91-49e0-954d-45da7ae066c2 | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008624 | 26f99798-d352-46f2-90c1-ebdf5c2e3fc9 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008625 | f73b8950-be91-49e0-954d-45da7ae066c2 | UG Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008626 | 5e562c17-ddf1-425a-970e-f34d2991642b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008627 | b4d660c5-afd8-46cd-97e4-0cc1ec8e6065 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008628 | f37fe851-cab7-4d69-8b34-912db647c774 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008629 | b4d660c5-afd8-46cd-97e4-0cc1ec8e6065 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008630 | 8c06c43b-b8c7-4580-ad2b-7a428073a79d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008631 | a8e07211-1b9f-466b-9785-89f05761ef5f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008632 | 53e0d389-361f-4e27-84a1-ac6232ef139b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008633 | 53e0d389-361f-4e27-84a1-ac6232ef139b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008634 | 26f99798-d352-46f2-90c1-ebdf5c2e3fc9 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2025-09-26 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008635 | 5e562c17-ddf1-425a-970e-f34d2991642b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008636 | f37fe851-cab7-4d69-8b34-912db647c774 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008637 | b6a24af7-d580-4a24-a63d-91388c185f68 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008638 | 45418583-7bf4-4b7c-b10b-4ab8e34cc158 | Pole | HFTD Tier 2 | Distribution | 2024-09-26 | 2029-09-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008639 | 64bab905-5eee-410c-bad9-20f7a1413c31 | Pole | HFTD Tier 2 | Distribution | 2024-09-27 | 2029-09-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008640 | c4baae82-2689-43e0-90cd-a9453402ebbc | Pole | HFTD Tier 2 | Distribution | 2024-09-27 | 2029-09-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008641 | c831b282-2bf0-40ec-bc22-408c39cd3c62 | Pole | HFTD Tier 2 | Distribution | 2024-09-27 | 2029-09-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008642 | aa25bc7b-7a31-45c7-b807-69ea0e966fb9 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008643 | 0664fe05-58cc-44c6-b7f0-7a8421dea284 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008644 | 7b8c650b-0ffa-4728-a061-81bef816f4bf | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008645 | 27af09af-6b2c-438e-b91a-9c6652489e96 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008646 | 27af09af-6b2c-438e-b91a-9c6652489e96 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008647 | 8c6b8e42-d2ab-456a-a43c-c47296ca8af8 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008648 | fef34a02-b872-47be-be95-f92460ed99b3 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008649 | 2463f4fe-15aa-4c9a-ad4a-a14e4c5df6e0 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008650 | fef34a02-b872-47be-be95-f92460ed99b3 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008651 | ed1dce4a-7c61-4004-b689-6eea8bbc5c98 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008652 | 2463f4fe-15aa-4c9a-ad4a-a14e4c5df6e0 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008653 | 5e0fb537-e921-4395-938c-619f927ebe38 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008654 | fc09bf81-4f9c-47ac-a245-ac242bdced9d | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008655 | 0fddf5cd-6bd7-4671-8e9d-98421022d214 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008656 | 867cdbad-cf69-4cd5-a59b-8974230f9ae3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008657 | fc2e2f9c-8f80-4cda-88b5-d3c39fef7cd4 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008658 | 0fddf5cd-6bd7-4671-8e9d-98421022d214 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008659 | f10f4b0d-2544-4398-b126-41267d989d11 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008660 | dad3948a-13d4-4499-926a-54eefcc0ac5e | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008661 | 996b7955-5e6c-4a24-a6b6-726a332f8141 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008662 | fc2e2f9c-8f80-4cda-88b5-d3c39fef7cd4 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008663 | e55eacd4-f818-48dd-83a1-88b6b3fdb396 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008664 | 7ff1b9b2-0f2b-43ad-87cc-e563f316740d | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008665 | 211e6678-dcd4-46a8-90df-b300dda220d7 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008666 | 684e208c-4e8a-46e2-a6da-8540c78fcc09 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008667 | 2c4c669a-6b25-464c-a565-6ccc66bebb3b | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008668 | 1c332e90-9ece-4065-b029-15ae3c9274f0 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008669 | 5d006ea9-3853-42f3-8eff-6b43d53b3538 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008670 | ca9b78cd-ac16-4723-8b08-f01f507bf529 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008671 | c83a711f-9c11-4559-904e-78a0a3336209 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008672 | 06978b98-3eb3-46f2-94a7-55725bdb5bde | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008673 | 543de849-be59-4d3f-94fe-dba90a6024a1 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2025-09-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008674 | 8f9fd481-bf77-46da-a06e-5bf59c21b4f0 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008675 | aa9ab962-eb8f-4c7b-af9e-8586d61b856c | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008676 | 2cd0bd79-b841-4f02-9be7-3d950a356f6c | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008677 | 3978392a-e985-4a26-83da-3f550633da02 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008678 | c83a711f-9c11-4559-904e-78a0a3336209 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008679 | b34923fc-9c83-4f2d-8b76-b0db83311a5a | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008680 | b34923fc-9c83-4f2d-8b76-b0db83311a5a | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008681 | d4d439ea-19d5-42ce-8d10-ec3989bb1293 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008682 | d4d439ea-19d5-42ce-8d10-ec3989bb1293 | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008683 | aa9ab962-eb8f-4c7b-af9e-8586d61b856c | Pole | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008684 | e6a1fcee-c29f-4e39-a610-646e50b4c9cb | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008685 | e6a1fcee-c29f-4e39-a610-646e50b4c9cb | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008686 | ff49e10d-0e6d-4313-897f-202da5dc8f6c | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2025-10-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008687 | d9e7b921-7806-4747-939e-5cc127ff0e34 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008688 | 56e8a309-d31f-4446-9f75-9abd91b83808 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008689 | 91ed88cf-0710-4d57-b19c-3ffcd1a2db34 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008690 | 56e8a309-d31f-4446-9f75-9abd91b83808 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008691 | 052648ff-a2d6-4839-81db-9f8ad42f85a6 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008692 | 9e207abc-a13a-4576-b3ed-9bb9a6a449a4 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2025-10-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008693 | 35f78f55-6da6-4551-aeac-0e6b627afa6c | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008694 | 811dde06-939f-48b1-b819-6dfbd0568e3c | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008695 | 35f78f55-6da6-4551-aeac-0e6b627afa6c | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008696 | 811dde06-939f-48b1-b819-6dfbd0568e3c | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008697 | ed8f095d-8b4d-4a8f-8f7a-95c761290807 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008698 | c242ff48-e8aa-4258-ad6c-8a841ef70db4 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2025-10-01 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008699 | ed8f095d-8b4d-4a8f-8f7a-95c761290807 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008700 | 91ed88cf-0710-4d57-b19c-3ffcd1a2db34 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008701 | ed8f095d-8b4d-4a8f-8f7a-95c761290807 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008702 | 93115026-d837-4122-b6b2-c0e39a894aaa | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008703 | ed683333-4da6-46e6-8c81-f5d89950dabb | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008704 | eb55ccb2-c091-4024-91a9-4fa3a10965bd | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008705 | cd994453-f9ae-4660-9a2e-c30ac7815b91 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008706 | 5ad75451-b97a-4b23-9f2b-93201ba02a0d | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008707 | c242ff48-e8aa-4258-ad6c-8a841ef70db4 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008708 | c242ff48-e8aa-4258-ad6c-8a841ef70db4 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008709 | dc2dfc77-1208-480f-b293-d91824198509 | Pole | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-09-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008710 | 696714b2-5def-479e-aabc-0bcc15f7bf15 | Pole | HFTD Tier 2 | Distribution | 2024-10-02 | 2029-10-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008711 | 9e76184e-15b3-4fcc-81a9-7e16123445a4 | Pole | HFTD Tier 2 | Distribution | 2024-10-02 | 2029-10-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008712 | eca5fac1-6bac-4006-b983-fbd9aa41b985 | Pole | HFTD Tier 2 | Distribution | 2024-10-02 | 2029-10-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008713 | 800fbd3a-a647-4570-9e93-e86dee3e2826 | Pole | HFTD Tier 2 | Distribution | 2024-10-02 | 2029-10-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008714 | f0f761ec-8021-4353-90ab-bfe190d74476 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-02 | 2029-10-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008715 | f0f761ec-8021-4353-90ab-bfe190d74476 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-02 | 2029-10-01 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008716 | fdbe831e-ddcc-4895-b9d0-c43fe3b9a9b6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008717 | 34320154-444a-4df7-99ff-2cd46a6adfd3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2025-10-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008718 | 2e3b7b5b-a4b5-41ee-b5ad-afde14445424 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2025-10-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008719 | 34320154-444a-4df7-99ff-2cd46a6adfd3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008720 | 2c8103d9-0715-4d1e-b7d0-55587cfcf289 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008721 | 09266f66-41db-4da7-a635-04b34449ce00 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008722 | 3f1fd076-4f1c-4280-96e9-1bea7bf1476a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008723 | 09266f66-41db-4da7-a635-04b34449ce00 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008724 | 508b450b-998b-4885-be47-df1849f218b1 | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008725 | 76dfde22-1c99-4935-b507-c61ca3b43ad9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008726 | 34320154-444a-4df7-99ff-2cd46a6adfd3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008727 | c388ec6a-7c9a-49c1-9c31-8317ae0202fe | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008728 | 9479b64d-c901-47d4-83f1-da12e9911470 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008729 | 189bcfca-b0c8-4985-a0e4-7645fbeb5892 | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008730 | 4c556401-9591-4465-936b-70a7b25f78c5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008731 | 2caeb9a5-9a6e-42f4-a91c-e2df66cef41f | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008732 | 80ea3861-b266-4550-8912-6baa7c8b740a | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008733 | 6ecb52ad-71a8-40d8-9a0c-e265a345711d | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008734 | b2b0f174-1681-45dd-9f1a-380d8137a13f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008735 | fdbe831e-ddcc-4895-b9d0-c43fe3b9a9b6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008736 | ff85515b-71c7-4e9f-a86e-ca1be81a9807 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008737 | c5192d9a-4442-4caa-860b-4813086eab88 | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008738 | 3f1fd076-4f1c-4280-96e9-1bea7bf1476a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008739 | 814c58b5-bed4-43a4-9b73-dbbc1ca97d3e | Pole | HFTD Tier 2 | Distribution | 2024-10-09 | 2029-10-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008740 | 0485412b-79dc-49de-87a6-0944c49a9889 | UG Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008741 | f53f9582-c167-4b67-89f2-46599dc5512a | Pole | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008742 | 0485412b-79dc-49de-87a6-0944c49a9889 | UG Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008743 | 71c9426b-d2ed-4ae8-93d1-38faab60ed77 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008744 | 60971553-fc01-4238-b6e1-ebd7d5d1c10c | Pole | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008745 | a76ea2f6-3581-4a3d-9f60-a4084d4331bc | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008746 | f78e1642-c85e-4d28-b925-7ecd57be58ed | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008747 | a76ea2f6-3581-4a3d-9f60-a4084d4331bc | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2025-10-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008748 | d174bece-7922-4591-bc77-f9e12d987d3d | Pole | HFTD Tier 2 | Distribution | 2024-10-10 | 2025-10-10 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008749 | a76ea2f6-3581-4a3d-9f60-a4084d4331bc | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008750 | d174bece-7922-4591-bc77-f9e12d987d3d | Pole | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008751 | ae004927-6548-4a0a-b555-193531262f56 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008752 | d174bece-7922-4591-bc77-f9e12d987d3d | Pole | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008753 | ce98d7a2-9fb4-4af3-890e-942f130b10ca | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008754 | d174bece-7922-4591-bc77-f9e12d987d3d | Pole | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008755 | ce98d7a2-9fb4-4af3-890e-942f130b10ca | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008756 | 4f18d760-953a-4375-b4e5-b76620c457e5 | Pole | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008757 | b2ea297a-42ab-452c-bb76-2725affd3c6a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008758 | 4dd8890e-9200-4e45-a7ea-94cf6e76c618 | Pole | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008759 | 650ced0d-cec0-41cf-a60c-d61bf8553803 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008760 | ae004927-6548-4a0a-b555-193531262f56 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008761 | 87cf50e5-3e5f-4c7d-9d3e-48171d969b3e | Pole | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008762 | 1322a05e-e1f2-49d4-bbae-8d5b385aeb66 | UG Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008763 | f78e1642-c85e-4d28-b925-7ecd57be58ed | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008764 | 1322a05e-e1f2-49d4-bbae-8d5b385aeb66 | UG Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008765 | 1407aab5-53b1-4a33-8b34-0ffbf36f387c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008766 | d10ff70c-88d1-4f1b-8932-53520bf050ba | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008767 | 1407aab5-53b1-4a33-8b34-0ffbf36f387c | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008768 | 09c2e1c9-8907-47d8-a471-c458c1a65812 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008769 | f80a5fca-6fa2-4b4b-bde2-483f43b2902f | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008770 | f80a5fca-6fa2-4b4b-bde2-483f43b2902f | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008771 | e15dc3aa-ee9b-4eef-9702-9fcc328cdd60 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-10 | 2029-10-09 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008772 | d9618ed7-060d-4d0c-ad0d-4387e1547058 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008773 | cc008f2d-435b-4e7f-8f99-3bf14fb5c639 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008774 | 4e58510b-63f8-4b43-ba40-129755beb438 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008775 | e5de71e9-d775-4df1-90e9-5442c450c4b9 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008776 | bd19429f-22b0-4cdb-871a-1272789f73f4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008777 | d9618ed7-060d-4d0c-ad0d-4387e1547058 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008778 | 215cdeaf-d308-4755-94c3-1be7a4fd2af3 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008779 | 99191574-3634-48cb-9390-9593d1d1be93 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008780 | 2e33b236-a7f8-43f7-89e8-a047a3f0684a | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008781 | 4e58510b-63f8-4b43-ba40-129755beb438 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008782 | 668093a5-d103-4f14-98fb-fc5594adb9a1 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008783 | f3eeb878-548d-422b-bdd0-8fe6686b3989 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008784 | 2fecfbb3-6524-40b7-b223-d3ea2e91be6b | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008785 | 1ce68c32-4675-4073-bce7-4cc9e365c524 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008786 | 7a327330-7866-486c-8def-b0303f47a9f0 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008787 | 1ce68c32-4675-4073-bce7-4cc9e365c524 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008788 | 9891bb22-60ef-4d5c-9806-d84bb80d2df4 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008789 | 9891bb22-60ef-4d5c-9806-d84bb80d2df4 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008790 | 871a68b5-4b06-46be-ad3b-0cdbf1f933ca | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008791 | 871a68b5-4b06-46be-ad3b-0cdbf1f933ca | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008792 | 6961199f-e550-474a-baef-36253aba8053 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2025-10-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008793 | 2535d8b5-3957-4497-82de-05c27ca4b107 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008794 | 5e6d6c68-0c9d-4b13-93a1-fd1fbd3a9e83 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008795 | 6961199f-e550-474a-baef-36253aba8053 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008796 | f0d23ea9-5c2b-433f-b17a-385c6a371bd9 | Pole | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008797 | 5e6d6c68-0c9d-4b13-93a1-fd1fbd3a9e83 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008798 | a531b7c3-9999-4182-a51a-ddb19352b4d0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008799 | a531b7c3-9999-4182-a51a-ddb19352b4d0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008800 | a531b7c3-9999-4182-a51a-ddb19352b4d0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008801 | 23d45562-8793-4d61-a245-655d5140d734 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2025-10-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008802 | a531b7c3-9999-4182-a51a-ddb19352b4d0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2025-10-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008803 | 08db2e62-6c88-4f03-9a40-91518b255098 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008804 | 23d45562-8793-4d61-a245-655d5140d734 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008805 | 08db2e62-6c88-4f03-9a40-91518b255098 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008806 | 23d45562-8793-4d61-a245-655d5140d734 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008807 | 58a1a6f7-e10d-42b4-80a4-c7a45ffb78c3 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008808 | 23d45562-8793-4d61-a245-655d5140d734 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2025-10-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008809 | 08db2e62-6c88-4f03-9a40-91518b255098 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-11 | 2025-10-11 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008810 | 58a1a6f7-e10d-42b4-80a4-c7a45ffb78c3 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-11 | 2029-10-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008811 | 322f97ab-7200-41bb-8f28-0e844c9d7c0b | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2025-10-12 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008812 | 8c18007d-4623-430f-8470-c4400e77cb83 | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008813 | 322f97ab-7200-41bb-8f28-0e844c9d7c0b | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008814 | b58101b8-8c8b-4995-b2b9-7c53cfda3dad | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008815 | 5778bbd9-65bf-4a10-b4ef-b035dd044096 | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008816 | 2a6725b0-7116-4af4-ba99-8191fdf978b3 | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008817 | 2a6725b0-7116-4af4-ba99-8191fdf978b3 | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008818 | dc9e993a-989b-45d0-872f-94f87b6fda55 | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008819 | eb0d74b2-0f5d-4cf5-9b74-b87782877e2b | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008820 | e9dcfa1a-f3c1-4f0a-879f-eb013b39f7e1 | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008821 | eb04b9ef-c7bd-4b92-a622-d9856930b3d3 | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008822 | b2e0e199-1cd9-453f-bcfc-d0d35b8b590c | Pole | Non-HFTD | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008823 | 9eb5a9de-ae33-4f52-b5dd-baa7b263d491 | Pole | Non-HFTD | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008824 | 19fc0a3b-0d5b-4851-a8a9-13c4b0149af2 | Pole | Non-HFTD | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008825 | 8ff1b1a0-5239-478b-a200-f0f630c96e6c | Pole | HFTD Tier 2 | Distribution | 2024-10-12 | 2029-10-11 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008826 | 819790b4-ccc8-44db-a679-12cd84dc736a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008827 | 5c01fba5-a42d-403c-8793-10acd12f9d1b | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008828 | c38a0d8b-f3bd-4282-99ad-415780b7278a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008829 | 39e4426e-0849-45f6-a108-7dba6fc0126b | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008830 | 96c89500-4e26-40b5-8fdd-6cf5e8362512 | Pole | HFTD Tier 2 | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008831 | 39e4426e-0849-45f6-a108-7dba6fc0126b | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008832 | 5c01fba5-a42d-403c-8793-10acd12f9d1b | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008833 | 7195baf8-8664-4afc-8ecb-e390bfee747e | Pole | HFTD Tier 2 | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008834 | a11cbb47-723c-42a9-b1af-0daf32481891 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008835 | 9f4b4e50-07ec-437f-8348-2223ea9fc705 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008836 | a11cbb47-723c-42a9-b1af-0daf32481891 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008837 | 819790b4-ccc8-44db-a679-12cd84dc736a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008838 | 7195baf8-8664-4afc-8ecb-e390bfee747e | Pole | HFTD Tier 2 | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008839 | c38a0d8b-f3bd-4282-99ad-415780b7278a | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008840 | 724aa0e8-e58d-4caa-a5a6-236f8b90886a | Pole | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008841 | 839d71da-5477-4da6-ac96-d3a5e3914ce3 | Pole | HFTD Tier 2 | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008842 | 724aa0e8-e58d-4caa-a5a6-236f8b90886a | Pole | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008843 | 53b33c26-3787-4f69-b9aa-aa5ad94f2e55 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008844 | 9f4b4e50-07ec-437f-8348-2223ea9fc705 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008845 | 296a6c42-6abd-4718-a1bb-54f867475045 | Pole | HFTD Tier 2 | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008846 | d8c8bdf3-8d10-4bfc-85c6-fe1bdba6d1c4 | UG Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008847 | f2daa8ca-b7fd-43fd-880d-6c314552dc8d | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008848 | f2daa8ca-b7fd-43fd-880d-6c314552dc8d | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008849 | 8717aabc-e929-4808-aa0f-886f22d7ce1c | Pole | HFTD Tier 2 | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008850 | 53b33c26-3787-4f69-b9aa-aa5ad94f2e55 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-14 | 2029-10-13 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008851 | d3f8ac3e-3eee-4034-a167-23191d079db4 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008852 | f6e03c59-241c-4014-b473-282aaa6c1b6e | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008853 | d3f8ac3e-3eee-4034-a167-23191d079db4 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008854 | f6e03c59-241c-4014-b473-282aaa6c1b6e | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008855 | 348b68a3-4eda-41d1-b2e8-9d50c6116f07 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008856 | d3f8ac3e-3eee-4034-a167-23191d079db4 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008857 | c119e41d-b00f-4642-80ab-6deb27fa258f | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008858 | 26ec0208-07d5-42ca-97c3-9aa745b0ca40 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008859 | 27e8d738-ce0a-4db0-a95a-395ba3a40366 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008860 | 341d0556-055c-42d5-a29b-13055737fca1 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008861 | 963644bf-f920-44db-8863-90ad7153acb6 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008862 | 27dfaa7c-28fd-4408-ae10-2ad1ed1582cf | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008863 | 963644bf-f920-44db-8863-90ad7153acb6 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008864 | 1a13512b-6fff-4794-a4bf-9496916467cc | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008865 | 058691a8-c181-4379-9cee-4d02635c8147 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008866 | 963644bf-f920-44db-8863-90ad7153acb6 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008867 | d3bd52a0-215f-4dcf-bd9d-1da58363a08e | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008868 | 76ba9b41-24f4-40a8-9cb9-638486a798f3 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008869 | de943325-c2e7-4e3c-b7fd-7041a7442554 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008870 | 43a49fe6-bf8e-4cb2-bc2d-89a491ef79c7 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008871 | 0567c9e0-942e-44b9-bb7d-e96c3ec8c5e7 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008872 | 536ae230-5451-42c8-8db0-26abd87fac07 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008873 | 953e4ef3-446d-4f7e-ab25-b0262e4d8aa0 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008874 | 86451e35-d8bb-4904-9836-71abf1a133dd | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008875 | 4aeb3774-e89a-4a18-8e05-4ab081ee4d59 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008876 | 9d8416aa-7bfc-490f-9bcf-6055996ead73 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008877 | 9d8416aa-7bfc-490f-9bcf-6055996ead73 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008878 | d75d531b-f681-4952-8566-c7a5badfe912 | Pole | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-14 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008879 | 1e5ca0c0-6c2a-45fe-afa4-aac8b7ff8781 | Padmount-Ã¡Switch | HFTD Tier 2 | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008880 | 1e5ca0c0-6c2a-45fe-afa4-aac8b7ff8781 | Padmount-Ã¡Switch | HFTD Tier 2 | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008881 | f2893eb8-f24a-4b06-8fd5-73d482b3d854 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008882 | 531087b5-3c4b-4bbb-bdcb-7ff2e9359764 | Pole | HFTD Tier 2 | Distribution | 2024-10-16 | 2025-10-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008883 | ba101026-bb63-4851-ab59-23e007003013 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-16 | 2025-10-16 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008884 | bee27026-6392-45c4-b385-93d45c3a80ea | Pole | HFTD Tier 2 | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008885 | ba101026-bb63-4851-ab59-23e007003013 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008886 | ba101026-bb63-4851-ab59-23e007003013 | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008887 | 129f06fe-c077-4c0d-94e4-749db0376ede | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008888 | 129f06fe-c077-4c0d-94e4-749db0376ede | Padmount-Ã¡Transformer | Non-HFTD | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008889 | d511cea1-8a7b-4d55-aaa9-7f2ad3328fc7 | Pole | Non-HFTD | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008890 | 82e1727c-9d9d-4216-9f5c-990ebcc913f0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-16 | 2029-10-15 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008891 | 4967dfa4-464e-43cc-8f11-b861a3b6704a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008892 | 61fb53a5-79bb-41aa-83a6-58c67092c6e8 | Pole | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008893 | 4967dfa4-464e-43cc-8f11-b861a3b6704a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2025-10-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008894 | 109ecc60-79de-4d82-9744-409fca45dda6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008895 | e1931c06-d883-4afc-b477-396f2a1a62bf | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008896 | 109ecc60-79de-4d82-9744-409fca45dda6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008897 | 720605ba-8096-450b-a754-4dbcc95983dc | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008898 | 54b1a1fe-84cf-408c-95ce-e1cd3516ff96 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008899 | 720605ba-8096-450b-a754-4dbcc95983dc | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2025-10-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008900 | 4967dfa4-464e-43cc-8f11-b861a3b6704a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008901 | 83417e27-3699-428f-89d8-6b6cbff9cd41 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008902 | 73c35a8c-54f6-47ea-9da5-6b2b299f3e81 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008903 | 74a49d09-70e3-4c43-8fa4-7ba862b51597 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008904 | 83417e27-3699-428f-89d8-6b6cbff9cd41 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008905 | 74a49d09-70e3-4c43-8fa4-7ba862b51597 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008906 | 9982c4c8-0c96-41cd-b6d4-ffb6d85f6b9a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008907 | 7db966f1-37ed-4e98-aa62-d4adf743cba9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008908 | 354ff82b-ded5-4aad-a65a-b3f61b54ad55 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008909 | 7db966f1-37ed-4e98-aa62-d4adf743cba9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2025-10-17 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008910 | ce62f005-e4db-426d-85ab-d82a757b35c9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008911 | 06eb7792-a968-48f7-9f5f-9b7d0d8117ad | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008912 | 720605ba-8096-450b-a754-4dbcc95983dc | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-17 | 2029-10-16 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008913 | 841378cc-89a1-499f-9d2d-db4d3f6945bd | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008914 | 2c146ad7-96b1-4365-95aa-e98ecce5bdf0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008915 | 551f78ab-3ced-4b2d-9bea-848524623773 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008916 | 2c146ad7-96b1-4365-95aa-e98ecce5bdf0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008917 | eda67a61-63ce-4c8d-9fc4-281db2ad09f0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008918 | 551f78ab-3ced-4b2d-9bea-848524623773 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008919 | eda67a61-63ce-4c8d-9fc4-281db2ad09f0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008920 | 18d6af9d-613a-4230-80ec-5ad8898321f6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008921 | c2a21166-74b2-4374-a529-bda800a102a7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008922 | 96400eda-ff92-44dc-96ef-f79e48ac6fbf | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008923 | 494ced9c-1ab1-453d-9330-c01b4435d4ba | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008924 | 412e7d61-5656-43a6-b955-f99c319cba9b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008925 | 18d6af9d-613a-4230-80ec-5ad8898321f6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008926 | 0bb287ac-1858-4c74-9f38-ee1eaf405fd3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008927 | 412e7d61-5656-43a6-b955-f99c319cba9b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008928 | 540b66ff-61e2-4431-b91a-11d9a7c29889 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008929 | 22b2f123-8d5c-4a1a-9721-33ea7c66f62f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008930 | 540b66ff-61e2-4431-b91a-11d9a7c29889 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008931 | 54181ace-95f2-48ab-9f09-9a22d354d8f7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2025-10-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008932 | 22b2f123-8d5c-4a1a-9721-33ea7c66f62f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008933 | 54181ace-95f2-48ab-9f09-9a22d354d8f7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008934 | a8df9444-8712-4dd8-b5c0-13f8e2153661 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008935 | 54181ace-95f2-48ab-9f09-9a22d354d8f7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2025-10-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008936 | 43dc4d83-651a-407b-b6a8-01d96bbe47d0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008937 | a8df9444-8712-4dd8-b5c0-13f8e2153661 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008938 | 43dc4d83-651a-407b-b6a8-01d96bbe47d0 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008939 | 47676014-5620-4f9a-b88f-25f33ab270fe | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008940 | af30613a-e3f0-483a-915b-5789b9e2f1e6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008941 | 47676014-5620-4f9a-b88f-25f33ab270fe | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008942 | 841378cc-89a1-499f-9d2d-db4d3f6945bd | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008943 | 945be714-dfbf-4cf5-bec6-efb1df7e7e3f | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008944 | 30520e9f-c799-4e9f-83ea-e3fa2b397cfc | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008945 | 945be714-dfbf-4cf5-bec6-efb1df7e7e3f | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008946 | 39e88e73-8810-40f9-8b6c-44681ab217d7 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008947 | e5a2efec-bbb5-4625-bfc2-ff18d21f0430 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008948 | 83d2e575-1471-4bf0-a0f8-3b55eecb367d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008949 | d94e3c31-f9e5-4c65-8722-e6553dc64bd1 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008950 | 83d2e575-1471-4bf0-a0f8-3b55eecb367d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008951 | 9dda1703-af52-46c0-a9cd-d499ac25f63f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008952 | 9dda1703-af52-46c0-a9cd-d499ac25f63f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008953 | 31705a33-6011-4689-be5f-941493161a75 | Pole | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008954 | 23da3e72-b0f1-442b-9b36-dd32a28b8dfe | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008955 | 1f3ebb24-8b99-4ba9-8262-3febaea3eedb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2025-10-18 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008956 | 1f3ebb24-8b99-4ba9-8262-3febaea3eedb | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008957 | 23da3e72-b0f1-442b-9b36-dd32a28b8dfe | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008958 | 0edeb0d1-cd2e-458f-a4d7-38a633d96570 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008959 | 0edeb0d1-cd2e-458f-a4d7-38a633d96570 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-18 | 2029-10-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008960 | 65f0d994-0906-4c6b-83b4-40ed2e967394 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008961 | 99d82cf4-c992-47bc-a244-9449b30f1e17 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008962 | 4849ce4d-24ad-4062-ba7b-ca3496554739 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008963 | e4111499-68b8-48c9-b5fc-be51d5ff8059 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008964 | cc32e59f-5a72-4ed4-b43a-294daa27db2e | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008965 | edff02c2-2da3-44ce-a17a-bd0b933719b3 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008966 | 053ba162-9050-4da2-a00e-94e4e36a679e | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008967 | 48cbdf3a-8e47-4a32-8622-e581b8bc0c4b | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008968 | 59d7c45b-02a2-4406-84a6-5d2a55c64bee | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008969 | 39dbd641-667e-4350-9cf3-c54310b2abf9 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008970 | 31715b47-834e-4008-af04-d601b53fe5bd | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008971 | 50ef5b8f-69bb-418c-b1b8-a5a37bd912eb | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008972 | 6403549f-56f9-4607-866d-27e66a20522b | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008973 | 7c1bd885-0a63-40bb-a5c0-9374364e689f | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008974 | 80b3bb02-0a39-4e2b-ad24-d31845fe8165 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008975 | 1fc174e1-b7a2-4380-a128-f180a9e28480 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008976 | 85befe17-f2ed-4b93-8c2e-c0895add0d44 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008977 | 9668a117-d19a-4aae-8815-3023b38ff73f | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008978 | fb93991c-2ad0-4be1-a71b-23d90600aaa9 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2025-10-19 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008979 | ed86bd5b-b83e-41fc-b71a-c932a214c165 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008980 | fb93991c-2ad0-4be1-a71b-23d90600aaa9 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008981 | d5719d9e-8f00-4f35-8512-ad890a2a73be | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008982 | 87bca81f-6f49-4a01-8ba1-ea7d569f2896 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008983 | d2d80b14-e4ab-4f08-8b4f-6b1ae4b82469 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008984 | 6f9225a5-64cb-4872-9dc6-44560526d842 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008985 | ddd8e9f8-d5bf-423d-abdf-049ce8bdae07 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008986 | 6f9225a5-64cb-4872-9dc6-44560526d842 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008987 | 6f612956-00ec-4bb9-a3a8-f4146cbbee60 | Pole | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008988 | 87bca81f-6f49-4a01-8ba1-ea7d569f2896 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008989 | 90fea085-52aa-442e-93bf-e1d56b4c3782 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-19 | 2029-10-18 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008990 | 7e00a582-8efc-49b2-a841-1d973c65fdcb | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008991 | 5e0f0757-11aa-486c-b9c1-4cd2d29ac5f6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008992 | 2547d664-b492-4a7c-9f2c-1ea77169f8a3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008993 | e45f61d7-b0cf-4137-8d5b-55af512e00dc | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008994 | 08366c3b-c69a-4b07-8b0a-a81f2ecaba42 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008995 | ccbd5e32-18de-4e51-967e-76de7fb605eb | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008996 | 08435365-2b50-40ab-a6cf-3542a002ebd6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2025-10-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130008997 | 9cde65a2-6686-401d-8ec1-9d7ccd84401e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008998 | 5e0f0757-11aa-486c-b9c1-4cd2d29ac5f6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130008999 | 32709514-58b6-44cf-9bdc-1965f9850d37 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009000 | 5dcc0208-a056-4210-af51-40957b643f44 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009001 | c019bea8-ced8-4e03-9b7c-7d6fd42db78d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009002 | 5dcc0208-a056-4210-af51-40957b643f44 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009003 | 5dcc0208-a056-4210-af51-40957b643f44 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009004 | 796c0b17-be1f-44cd-87d7-01fcfb722b54 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009005 | 2547d664-b492-4a7c-9f2c-1ea77169f8a3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009006 | 796c0b17-be1f-44cd-87d7-01fcfb722b54 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009007 | 79a4c9a9-96b8-4ef6-a3ce-725d348ad8cb | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009008 | 96b68241-e7a6-42ce-950e-67fce750d6bc | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009009 | 26173205-13ec-449a-b5b3-e6c69e08ea29 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009010 | 6d0289ce-619a-40b6-bfa8-3961a9d9ca80 | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009011 | 9df86d74-e19c-4772-b202-c91d91bb4c16 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009012 | dea32c44-6044-4378-a898-0d044fa7522f | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009013 | ae53f43a-8905-4275-b061-682ed0cd643b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009014 | 4a1a8291-6825-40f2-a4a6-c0a3198585d3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009015 | b83181a3-e28a-4e9b-bca6-aebdc06a6854 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009016 | ad89eb61-6587-442a-b8bd-48df87fdc998 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009017 | a5bee6b7-4955-4356-a066-3303a18e8f42 | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009018 | a5bee6b7-4955-4356-a066-3303a18e8f42 | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009019 | 4a1a8291-6825-40f2-a4a6-c0a3198585d3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009020 | a5bee6b7-4955-4356-a066-3303a18e8f42 | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009021 | 4a1a8291-6825-40f2-a4a6-c0a3198585d3 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009022 | 41aba0b6-53e3-4942-b23c-9321e811bb94 | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009023 | 64c3a23a-e86c-4c0d-bcb6-9b6c3ab0f59c | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2025-10-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009024 | cd8fbc58-a621-41a7-bf42-69d4fb29d74f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009025 | cd8fbc58-a621-41a7-bf42-69d4fb29d74f | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009026 | 45c3a7e8-10ca-4d93-9b2b-75a07c1f10fe | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009027 | 56912565-6188-4600-a634-d6e895f7ebd9 | Pole | HFTD Tier 2 | Distribution | 2024-10-21 | 2029-10-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009028 | da406d07-84fb-4e33-b77a-76c306313fe8 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009029 | 4de377c9-5191-43c3-8286-fdb4ca287931 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009030 | ada2008d-0908-4827-a59d-3c980cf6f6ac | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009031 | 3afb5d03-ad43-4aa0-9dce-805742744d26 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009032 | 41aba0b6-53e3-4942-b23c-9321e811bb94 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009033 | 1cf6c069-2c22-4ab4-8016-c2b452ce51aa | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009034 | 6492c510-8e88-45c0-8e2b-a5840c56e72c | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009035 | 8a09c499-6e27-4f15-98a2-43f07af25a2a | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009036 | 6711bf02-17be-480a-b94b-105e8ef07609 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009037 | da406d07-84fb-4e33-b77a-76c306313fe8 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009038 | 3afb5d03-ad43-4aa0-9dce-805742744d26 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2025-10-22 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009039 | 004e5bd4-a559-4f53-b4d7-1b37abb5d065 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009040 | 3afb5d03-ad43-4aa0-9dce-805742744d26 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009041 | 819f6840-a9b9-4f06-acc3-92cf33fa9c4d | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009042 | bdcd4f98-ad51-4daa-b9c3-8d1bd1d2cea2 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009043 | d15f3a78-b7dc-4b35-9b1c-9aa2ec134deb | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009044 | c58fef76-cd00-478d-979a-d2c16da4cc0e | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009045 | a5f10854-f02b-4a4a-86e7-20800380145b | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009046 | 019eef42-0239-428a-971c-4fee106a18ff | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009047 | 019eef42-0239-428a-971c-4fee106a18ff | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009048 | 819f6840-a9b9-4f06-acc3-92cf33fa9c4d | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2029-10-21 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009049 | 70b3e6d4-01ac-494c-b091-dd7244085da0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009050 | a2ba0198-b0cc-469a-ab5d-e16043a748d7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009051 | 3e88ae74-c096-427b-b161-e25b9c5e4d08 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009052 | 56d31827-5dfd-45cd-a818-c43742d324ec | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009053 | 8ee5f5e8-4030-425c-a661-31f2d79edb85 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009054 | e47b831d-af2c-4bcc-a38f-20fdedb6dac7 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009055 | 86c1c7fc-0ce3-42e6-bec0-148cf4f512ec | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009056 | 0e39d369-68ad-4851-9eb4-212c61b56174 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009057 | 160e5a50-7301-4290-be5a-db17d12c84cf | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009058 | 881aefd2-8bb6-4638-9d5d-8a7f03fdfbab | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009059 | a2ba0198-b0cc-469a-ab5d-e16043a748d7 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009060 | 33072e96-8f84-4738-804a-e971d935b57c | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009061 | e47b831d-af2c-4bcc-a38f-20fdedb6dac7 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009062 | 2f00c4ef-cb03-476f-b1ec-4915059c9cbd | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009063 | 56d31827-5dfd-45cd-a818-c43742d324ec | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009064 | 4235b473-bb75-4c55-b9eb-968d856e4d47 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009065 | 09db7738-a274-4426-9ae4-2f14f6f486a3 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009066 | 53b1e4df-fb6e-4e72-b85a-b8c89b992af5 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009067 | 33072e96-8f84-4738-804a-e971d935b57c | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009068 | fd763201-df6c-4631-ba1c-8bc67dfa49f9 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009069 | 86c1c7fc-0ce3-42e6-bec0-148cf4f512ec | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009070 | b8a39b06-8964-4ec5-ae7e-5674248b8cfd | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009071 | ee195894-4408-441c-a1c4-84bc67982891 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009072 | ee195894-4408-441c-a1c4-84bc67982891 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009073 | d553152f-96c9-4df9-a9ab-4ad776518f0a | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-23 | 2029-10-22 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009074 | 0c510104-c14d-463b-a931-07ed35313ada | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | 2025-10-23 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009075 | 7d19b434-96df-49f4-858c-e95ab05a5ebb | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009076 | 74ff18fd-8d5b-404b-87e5-c325654a4aea | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009077 | ee02e838-01df-40e3-9146-b9cf23df547d | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009078 | 6529e653-c5cb-41b3-b07b-6086e8cc8ec4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009079 | 268a2cd9-595f-4704-87b0-2f324ef375d0 | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009080 | 6529e653-c5cb-41b3-b07b-6086e8cc8ec4 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-10-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009081 | 1245648a-5fce-45e6-b498-e0d5a63c4217 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-10-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009082 | dcbba34e-7b16-4a47-ba86-5da432a735bd | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009083 | 0d6c76d7-9f2d-4d5e-87f7-dfbe881e94e3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009084 | a1c7c943-ae86-489d-a1aa-1e881b486495 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009085 | f6e786f3-f697-4a55-9c04-f68e3b4c855d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009086 | 02c269f9-dd60-48e9-bad3-472cf656e2b9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009087 | a966dba1-f317-4af3-8829-5d0475d6b15a | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009088 | 02c269f9-dd60-48e9-bad3-472cf656e2b9 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009089 | 0d6c76d7-9f2d-4d5e-87f7-dfbe881e94e3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-10-24 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009090 | 0d6c76d7-9f2d-4d5e-87f7-dfbe881e94e3 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009091 | cf49e877-3f97-41b7-8502-a4aa4367bd84 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009092 | 258b3228-4dc8-4131-af88-4cadd6762a53 | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009093 | 8aa2f0a4-e4d7-4a86-aa52-aa7543e9ea94 | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009094 | 0200e894-d8fa-47db-abf9-7fd2192225c9 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-24 | 2029-10-23 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009095 | ebd1e8e0-1f6f-42d3-ab6f-0960e3d2258f | Pole | HFTD Tier 2 | Distribution | 2024-10-26 | 2029-10-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009096 | 0b68f751-5024-4b30-ba6b-bb3d073fe08c | Pole | HFTD Tier 2 | Distribution | 2024-10-26 | 2029-10-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009097 | 306f0671-bc6b-48fe-bfc0-8e0930a81fa7 | Pole | HFTD Tier 2 | Distribution | 2024-10-26 | 2029-10-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009098 | cab94c0c-42ef-47d1-b2f1-6ceec79e5182 | Pole | HFTD Tier 2 | Distribution | 2024-10-26 | 2029-10-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009099 | 888aa292-e125-4af1-878e-a953702888d5 | Pole | HFTD Tier 2 | Distribution | 2024-10-26 | 2029-10-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009100 | 125a2d49-8b02-4f27-9e08-c6459e52dd15 | Pole | HFTD Tier 2 | Distribution | 2024-10-26 | 2029-10-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009101 | 6ad0fded-ad10-4bb0-8ff9-c04acd429123 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009102 | 2875683a-6278-4500-bebe-a52ca660a15b | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009103 | 6584af20-e1eb-4204-b5cb-4b96a30bde71 | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009104 | 7ce5aab6-ddc7-4e2f-9599-a557e0761efa | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009105 | 6eee4ad1-ae72-4341-b153-fd29ddb27ff0 | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009106 | 81e7706b-3d0c-4142-b277-659eaf7e1f65 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009107 | 0af12de2-b6cd-45fe-83dc-d8c8465c8a29 | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009108 | 258f1d89-dcaf-4929-a1b0-0ff981fed18a | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009109 | 3672467c-1d84-467d-9032-fbe28dc4b4c6 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009110 | e86a1a0e-bf60-4637-ac5f-e4bbcb4404fd | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009111 | 10f59f17-b2a2-4b60-af0e-a162ddff366c | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009112 | e0a35681-6d5e-4863-baf3-9c641449bf2e | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009113 | f8f00995-4770-48d5-8c18-8916f5ea68f7 | Pole | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009114 | 65ce50e1-81e3-48cb-af1d-b82062e96e6d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009115 | 65ce50e1-81e3-48cb-af1d-b82062e96e6d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009116 | 6ad0fded-ad10-4bb0-8ff9-c04acd429123 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-27 | 2029-10-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009117 | d97b485c-1efe-40ae-aab1-198c6333d032 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009118 | e1e373b7-f83f-4b17-9d65-0928e2fb4a39 | UG Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009119 | bc2d70ee-c471-44d4-a1f7-f4c21e958606 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009120 | dd0c5051-34af-40ec-9000-5e28b73dabc0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009121 | dd0c5051-34af-40ec-9000-5e28b73dabc0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009122 | 99df7004-7457-4296-85cd-9e2a5416ca9a | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009123 | 0cdd6527-19a0-4173-8576-80e1957db301 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009124 | 29792998-6084-4f44-937b-51e91dce967b | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009125 | b626e16e-11bb-4545-ba49-3859f5564750 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009126 | 5f8e83f4-3e53-45bb-805b-b4f087a8e146 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009127 | 9fd1fa18-fe83-474d-81ab-7c6137f34a27 | Pole | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009128 | d278f7d2-ef54-405f-ac42-07c00d1666be | Pole | HFTD Tier 2 | Distribution | 2024-10-28 | 2029-10-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009129 | cc5f04c8-0055-490a-b82c-55ed8d24c78e | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009130 | f7d0adee-52d6-4131-9740-6411ef7ec3ee | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009131 | 2062c56a-4166-4c6d-b19f-06dffd61f5c3 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009132 | 2d84b9de-10b7-436a-924b-d00700eea12c | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009133 | b1340f2b-2bb8-4fb0-941d-541ec2a913a2 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009134 | 2062c56a-4166-4c6d-b19f-06dffd61f5c3 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009135 | e323988a-f836-444d-a4bd-f768ddc7dc59 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009136 | 660f1795-9850-4425-982e-6020a39b9211 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009137 | 5d5a912d-8cd7-4ddd-a072-f971d75f11ff | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009138 | 1cf6a37a-a10e-47c0-b356-47798fabc4ef | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009139 | 55692e1c-6841-4c0a-8214-688717a074b0 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009140 | 53c979ac-a2cd-4991-9c1e-29a94711f812 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2025-10-29 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009141 | b6f53538-79ce-485d-9782-22a083382c6d | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009142 | 28ea2568-7530-4667-99ca-d77070bd2d2d | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-29 | 2025-10-29 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009143 | 660f1795-9850-4425-982e-6020a39b9211 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009144 | b6d4f3e4-d93c-41eb-a471-7d77bda12e8e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-29 | 2029-10-28 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009145 | f3ba627d-b144-485b-b574-3525c6679a15 | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | 2029-10-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009146 | 89067c2f-15a8-4f8a-8ca6-5cf2a2c20d1e | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-30 | 2025-10-30 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009147 | 613f8077-a037-4e53-8cee-bf676199936c | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | 2029-10-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009148 | 613f8077-a037-4e53-8cee-bf676199936c | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | 2029-10-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009149 | 1df1bbb1-3c64-4040-aed5-553787b258d0 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-30 | 2029-10-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009150 | 0bf271b0-8cab-413c-8d62-cab4d1c03884 | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | 2029-10-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009151 | fc731ad9-a623-4f1c-9ba7-6c04dd755afe | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | 2029-10-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009152 | 7c2eb508-89e6-4153-b6b5-5d0ad98c3f03 | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | 2029-10-29 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009153 | 51be79e0-e24e-46a4-a607-5120a951b051 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009154 | fca28332-892e-4670-bd64-f127a5c7cb14 | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009155 | 4dc0500b-0c3c-427f-a89d-7fc8076afb04 | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009156 | f9b1c445-e90d-45c0-a9b1-7bc28b4c56e8 | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009157 | f9b1c445-e90d-45c0-a9b1-7bc28b4c56e8 | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009158 | f962c14c-dddc-43de-b4e1-a4386a0a86f1 | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009159 | f187193e-4988-442b-991c-f34a383d6ba3 | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009160 | 1b09f168-b354-4e7e-99ee-112ec37faad7 | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009161 | 36577466-15c4-43ff-8a80-8e7031373a9e | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2025-10-31 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009162 | 4dc0500b-0c3c-427f-a89d-7fc8076afb04 | Pole | HFTD Tier 2 | Distribution | 2024-10-31 | 2029-10-30 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009163 | 4470b0ff-0864-4244-9552-589ff24993e5 | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009164 | 33f109e1-3e70-4e08-92a3-aa8e7dddd662 | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009165 | 7b979fb4-eef9-43b3-90a0-f0d4dbcd24c5 | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009166 | 33f109e1-3e70-4e08-92a3-aa8e7dddd662 | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009167 | 9f1874be-9248-4743-8614-2da744423da1 | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009168 | 7a231725-d1fb-4fcf-9518-3ad651342b6e | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009169 | 0aaad8ff-4be8-4a29-8fea-88929395824d | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009170 | f0010f27-817b-45c1-8f04-647c57600795 | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009171 | c99dace5-ab87-4b9c-9a6c-7fa33a325281 | Pole | HFTD Tier 2 | Distribution | 2024-11-03 | 2029-11-02 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009172 | 370cc27f-ead5-48bc-8f0d-d4d2d22d4736 | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009173 | 6a5777c4-33f5-4ee0-a1d3-f4299e61cc37 | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009174 | 4c1ab5d9-55a3-4129-a0c5-0073a56df3b6 | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009175 | bd0af5fa-24a0-40d8-bd41-715d0ed6cb7c | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009176 | 2c59ce64-2329-45fd-8af8-7c8f92c8fb30 | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009177 | 03dbda9b-fbc2-4fe3-91a7-50ea14690a19 | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009178 | 91db6059-a514-4f4e-a87f-2eec5729c474 | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009179 | c084f9b9-d8fd-44b8-be27-d32c979c358f | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009180 | c084f9b9-d8fd-44b8-be27-d32c979c358f | Pole | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009181 | 08e50229-03d6-483a-aeb1-34f7b3963862 | Padmount-Ã¡Transformer | HFTD Tier 2 | Distribution | 2024-11-04 | 2029-11-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009182 | 320a5f7d-d608-48a8-b26d-2c2be0afa951 | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | 2029-11-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009183 | 5f36c3cf-c848-4cd7-b117-c5326201488b | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | 2029-11-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009184 | 955e2426-dc04-4741-a378-f229fcb3f24c | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | 2029-11-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009185 | 5e4d3bff-2fb6-4bfb-9eea-6abf8338b292 | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | 2029-11-04 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009186 | 0fe96147-86b2-4d55-8968-028b1176a13f | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | 2025-11-05 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009187 | 3c367e31-21dd-4e4f-b3eb-61423817e4e2 | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2025-11-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009188 | ddfc27ed-7b42-4d61-8443-f7a81329d49a | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2025-11-06 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009189 | 0d26f128-3a3a-49ef-8fd9-f62318787ebb | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2029-11-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009190 | ddfc27ed-7b42-4d61-8443-f7a81329d49a | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2029-11-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009191 | db253e78-4e78-488b-a0f8-ba042d512d21 | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2029-11-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009192 | 5b322462-0f71-4e8a-b769-efdfa7421999 | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2029-11-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009193 | 4df6570c-a221-48c5-b4be-f87ed8b94a43 | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2029-11-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009194 | 6a47514c-ce80-4bfc-b3ff-44abfcefdd87 | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2029-11-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009195 | c44e6815-a2aa-4d73-a1a5-87556b9fcace | Pole | HFTD Tier 2 | Distribution | 2024-11-06 | 2029-11-05 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009196 | 9f1bf224-f042-499c-802c-8df58bb3752a | Pole | HFTD Tier 2 | Distribution | 2024-11-07 | 2029-11-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009197 | c6a1f51c-0f26-47b3-be9e-31b2ed9f22fe | Pole | HFTD Tier 2 | Distribution | 2024-11-07 | 2029-11-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009198 | ca527253-03b9-48a5-9399-257c5503807e | Pole | HFTD Tier 2 | Distribution | 2024-11-08 | 2029-11-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009199 | ca527253-03b9-48a5-9399-257c5503807e | Pole | HFTD Tier 2 | Distribution | 2024-11-08 | 2029-11-07 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009200 | 56a7b420-1a74-4d48-b25e-90f4ad2692b6 | Pole | HFTD Tier 2 | Distribution | 2024-11-09 | 2025-11-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009201 | 7b0fafc1-c67c-4bd5-9890-86ab43c2a0ae | Pole | HFTD Tier 2 | Distribution | 2024-11-09 | 2029-11-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009202 | 1323d8fe-0b09-4c67-be7a-4cc666f78011 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-09 | 2029-11-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009203 | 60226fdd-7df4-4381-809b-8847762872e2 | Pole | HFTD Tier 2 | Distribution | 2024-11-09 | 2029-11-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009204 | e74fdacb-7614-4e29-b18e-0a0026df388c | Pole | HFTD Tier 2 | Distribution | 2024-11-09 | 2029-11-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009205 | 709912ba-219d-46d4-908b-b3f9b4c6d811 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-09 | 2029-11-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009206 | b13e04ec-c05c-42a2-be1c-90132f247e9d | Pole | HFTD Tier 2 | Distribution | 2024-11-09 | 2029-11-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009207 | c802384c-9bd2-410b-97e2-d7a2a9618c20 | Pole | HFTD Tier 2 | Distribution | 2024-11-09 | 2025-11-09 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009208 | ff94d6fc-f660-45e7-9abc-ab79e89bb00c | Pole | HFTD Tier 2 | Distribution | 2024-11-09 | 2029-11-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009209 | af4a8fef-009d-4fba-b68a-659ccfdee203 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-09 | 2029-11-08 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009210 | 143f0332-dedb-41c7-b36b-dddd76196596 | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009211 | 740f81b5-445c-485b-993b-a2bc6683d520 | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009212 | 3e466d20-0c69-47c3-8755-4694f2458185 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009213 | e246363d-56c0-4f97-94ad-376204c6feb0 | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009214 | 0297e42b-326f-485a-a96c-284f4afa1400 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009215 | 43445246-e9c9-4f35-b6aa-4824927acd65 | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009216 | bb66a9bf-050d-4380-8436-5a7c9d0532a1 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009217 | e4300e6c-3023-45af-bc11-f73258baf50a | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009218 | abd956d5-9401-4256-a837-3ea4ed987b3f | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009219 | e4300e6c-3023-45af-bc11-f73258baf50a | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009220 | c59313c3-fe40-4596-8423-8a8c5e4c4a63 | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009221 | de84d0a1-54cb-409c-9404-b60fe53c68da | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009222 | 2b89969e-796a-4822-95d3-831ab86ec2cb | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009223 | de84d0a1-54cb-409c-9404-b60fe53c68da | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009224 | 3e67faca-c16e-46ac-9d3d-849067023a3b | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009225 | 0e8c086a-619b-448f-8e94-d7011bfdb8bc | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009226 | 6e80cdfb-7d56-4dfa-8483-ed68daaa5ecb | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009227 | 0297e42b-326f-485a-a96c-284f4afa1400 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009228 | 143f0332-dedb-41c7-b36b-dddd76196596 | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009229 | 53bfb8cd-0e83-49cf-ac95-1c5407f1f124 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009230 | 53bfb8cd-0e83-49cf-ac95-1c5407f1f124 | UG Transformer | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009231 | b2a34b42-9932-4130-8d65-2937b444b227 | Pole | HFTD Tier 2 | Distribution | 2024-11-11 | 2029-11-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009232 | 3afb5d03-ad43-4aa0-9dce-805742744d26 | Pole | HFTD Tier 2 | Distribution | 2025-01-23 | 2026-01-23 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009233 | 9983dfa2-d6a2-42f5-a8f0-decd21ac300b | Pole | Non-HFTD | Distribution | 2025-02-04 | 2030-02-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130009234 | 2ae58b12-178e-48ce-8666-b691b643c489 | Pole | HFTD Tier 2 | Distribution | 2025-02-05 | 2026-02-05 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009235 | dd98cc24-5a60-466e-b264-1ed94391468b | Pole | HFTD Tier 2 | Distribution | 2025-02-05 | 2030-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130009236 | 8a4fcf83-0a8e-4bdc-9217-d13c5533779f | Pole | Non-HFTD | Distribution | 2025-02-05 | 2026-02-05 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009237 | 16b9c22e-34ba-43cc-884d-4537fb8d84c1 | Pole | Non-HFTD | Distribution | 2025-02-05 | 2026-02-05 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009238 | 192cfbdb-c3d8-4548-b8c3-1a315b44ca3f | Pole | Non-HFTD | Distribution | 2025-02-05 | 2030-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130009239 | 8e4a4fe0-825a-45d6-8a7d-534134672cd6 | Pole | Non-HFTD | Distribution | 2025-02-05 | 2030-02-04 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130009240 | f546020f-d087-4464-b8f4-160f8dfd9de9 | Pole | Non-HFTD | Distribution | 2025-02-06 | 2026-02-06 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009241 | 845b72a1-26fb-4819-9500-4085861146f7 | Pole | HFTD Tier 2 | Distribution | 2025-02-12 | 2026-02-12 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009242 | b3f20024-c0ae-4467-aa91-75ba7d427f85 | Pole | HFTD Tier 2 | Distribution | 2025-02-19 | 2026-02-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009243 | 19ddd5a2-2b27-42d2-acb9-728a37443d61 | Pole | HFTD Tier 2 | Distribution | 2025-02-20 | 2030-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009244 | 63e39fd1-a166-47f4-8653-1409667b5d06 | Pole | HFTD Tier 3 | Distribution | 2025-02-20 | 2025-08-19 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009245 | 4bc18ee2-07d4-4ab7-ac9a-9c8a0f4cd16d | Pole | HFTD Tier 2 | Distribution | 2025-02-20 | 2030-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009246 | 9d4cace1-db14-4802-bb78-d5b884187aad | Pole | HFTD Tier 2 | Distribution | 2025-02-20 | 2030-02-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009247 | 033224a7-8eb3-4977-adbe-0ec6511c68e5 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009248 | 2291f61b-fa83-49b1-89fd-06ca292fa9f1 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009249 | 849ea042-aa18-4837-8ed8-d1696bf2f440 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009250 | 1f07c0e6-9e24-4812-a9e0-88e9e6f13b93 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009251 | dbe5c093-4843-4077-ae2f-8f8ec53c7159 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009252 | 7aad7942-d95f-4864-babe-20ea56721c75 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009253 | b88d0870-45d2-434f-871a-0ecc054b9df8 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009254 | 185844a8-b997-49ef-aed4-683186d9fcb9 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009255 | c9f89b71-e684-48d6-85e0-206ea8e26436 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2026-02-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009256 | 6273718e-0dfd-4c12-94ba-c6c5ff068d5f | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009257 | 6cceeafd-871f-4201-90c2-621d0c5fa9f0 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009258 | d10ba26e-9bb0-46e8-99b1-a35d3c0cb979 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009259 | c9819bc5-0af7-4fc0-baaf-c7afa51680ac | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009260 | ce38d17d-49f8-4f8a-bb7b-34fd89ba68f9 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009261 | c10f25b7-4181-485d-b8e8-aa39bc9c82bc | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009262 | 1a2eec75-269a-4efb-8c2f-d1023f41bee7 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009263 | daf93d99-09a6-48fa-89d6-3b727688c798 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009264 | 2b48e22f-e716-40fe-827d-c796a1d8bd87 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009265 | 3fb74fa6-dbf5-4525-8cb9-19eb3a77aa16 | Pole | HFTD Tier 2 | Distribution | 2025-02-21 | 2030-02-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009266 | d9c54737-42c2-4d91-936b-f67ec22f9337 | Pole | Non-HFTD | Distribution | 2025-02-25 | 2030-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009267 | 04463a67-6c24-433c-88ce-21208b881a0e | Pole | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009268 | 2626ed7c-d7e0-4452-b85e-715c5db7f70c | Pole | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009269 | 04463a67-6c24-433c-88ce-21208b881a0e | Pole | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009270 | 95ac786a-4538-464b-a6a1-92aed738d56e | Pole | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-25 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009271 | 3ab6c00a-099a-413e-80c5-82d1f07d6d3c | Pole | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009272 | ac81c9bc-0d98-462b-ab08-76ed4f0d4493 | Pole | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009273 | 65ba05e4-df32-4bd9-b04d-3fec4db659d2 | Pole | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009274 | f89d945a-9a47-41dc-af83-9bce8e9f70ca | Pole | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009275 | 342f77b9-e2fd-4c57-ba57-5eb78637c108 | Pole | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009276 | 112f9edf-eb31-4afd-acbb-d12436d157cd | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009277 | 5bc015a3-574b-480f-ac18-fc1db17145e2 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009278 | f6ddd8d7-d754-4b0d-99aa-b3dd9edb3233 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009279 | 4cbb4c68-141f-48bc-8438-ed9b50b45e48 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009280 | 4e799e20-0df3-4444-8801-9814566371eb | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009281 | dbe19199-7160-43e8-a3e4-6927cf03d92c | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009282 | 9f37860f-f3a7-4c4d-9f95-3a26b30fa09e | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009283 | 9518665f-4856-4edb-aa6e-d9865d050d82 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009284 | 546374bb-743e-4393-b361-e137ad85ab6a | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009285 | d673bacf-93fa-48cb-a381-dd13533dc77a | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009286 | fb0c63ba-91f8-44a7-9157-735ffd31220d | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009287 | a651bed1-ac0a-4895-a893-f194f8cf0e7c | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009288 | 71875d7c-38a3-4a36-aeeb-9a1d7ab2ccf2 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009289 | 546374bb-743e-4393-b361-e137ad85ab6a | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009290 | 9417c87c-abf0-4ae1-9c9e-49a92873082a | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009291 | 546374bb-743e-4393-b361-e137ad85ab6a | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009292 | fffddd42-6a29-4925-b436-f66561081014 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009293 | acff3f87-e96a-4245-979a-9d995e303824 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009294 | acff3f87-e96a-4245-979a-9d995e303824 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2026-02-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009295 | acff3f87-e96a-4245-979a-9d995e303824 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009296 | acff3f87-e96a-4245-979a-9d995e303824 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009297 | 02aaeb86-d9f5-4815-a2a1-73ac6d76ee7f | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009298 | cb5376bc-02bc-4543-b454-fdb1c3a53691 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009299 | 12542146-4753-4b98-85ff-1ca7f8e84a93 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009300 | 12542146-4753-4b98-85ff-1ca7f8e84a93 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009301 | c0276719-210d-4f71-84dd-d0b9f7d7f45e | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009302 | f1e773d7-6444-4fa5-9961-7cd2390bb2b5 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009303 | 3a7f2649-80e1-4bd4-82dd-d04c403593e0 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009304 | fffddd42-6a29-4925-b436-f66561081014 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009305 | 7f77bc38-cfb0-4b50-bec3-f6b3eb27a1ce | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009306 | 71875d7c-38a3-4a36-aeeb-9a1d7ab2ccf2 | Pole | HFTD Tier 2 | Distribution | 2025-02-28 | 2030-02-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009307 | f03f800f-5641-40ec-a7cd-8ea0e8c88749 | Pole | HFTD Tier 2 | Transmission | 2025-02-28 | 2026-02-28 | Level 2 | [7 empty] | Liberty | 2025 | 1
1130009308 | a4a39f38-f6b6-4870-b3d4-75be1cea2cec | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 | [7 empty] | Liberty | 2025 | 1
1130009309 | 8e8f78c1-523e-4374-919e-a3b36dece350 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009310 | 0ccc8acf-3476-481d-b528-09cd4fc07d15 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009311 | 88e95113-b1ab-4d72-8e77-74cf55f30c45 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009312 | 0ccc8acf-3476-481d-b528-09cd4fc07d15 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009313 | fb7c0a78-8db0-45ec-a54a-2e48de6a544c | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009314 | 3a9ca1cc-0b50-4fa4-8f60-cc7e0ff125d4 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009315 | fb7c0a78-8db0-45ec-a54a-2e48de6a544c | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009316 | 6863321c-b27f-49b7-9b9b-765881710f1b | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009317 | 39733793-5683-433a-adee-d0917d90ffa9 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2026-03-04 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009318 | 6c2b5f10-1d7f-436e-9ee6-f767876eec41 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009319 | 57f825bb-dd88-4d59-928e-fdc4e78bba2c | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009320 | 3ddbc701-4e5f-4d6c-8ef4-cbdb6cd7140a | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009321 | 9ba038f1-bebf-4e62-8e3d-0b198487a54c | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009322 | 3dacab4f-4c4f-4c6d-bcbb-037d8a3fcb56 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009323 | 50da1809-f59e-46df-be74-d618534160f2 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009324 | 95b7bcd6-1d11-4233-9fa1-aad784b1a8bf | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009325 | 57071b9b-29b4-44b4-8502-5a9f8dc12676 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009326 | 65991550-21b1-45c5-a9a5-9bd2175ba247 | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009327 | b9f7e966-7aa4-4ec1-b8e3-d27a5f7bd74b | Pole | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-03 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009328 | 8cfb2b9f-a10c-48be-a457-592293ed8c2d | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009329 | 6536af10-b041-4d3c-a55a-301ae3dc30ed | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009330 | daf8f2c2-eea0-413c-9aeb-93450134a0dc | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009331 | 6381231a-0638-42e0-a439-e66bcbbb6c06 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009332 | 6e15cd54-8aa6-41e1-833f-ed45fa386e68 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009333 | f4e5f669-9a06-4e8b-8f2d-8896839059f5 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009334 | 6df31a44-ed9e-424e-9b1b-260c144ea2d1 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009335 | fcce86c1-489b-4248-91a4-87d75a06fbff | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009336 | 34064f69-a35e-45ff-a16c-a35f17f23487 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009337 | 18350311-5e81-4e29-bd87-9ead83abf1a9 | Pole | HFTD Tier 2 | Distribution | 2025-03-07 | 2030-03-06 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009338 | f5856337-bcd1-42f6-aa36-495828066de9 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009339 | 06fdf389-b75f-4377-8d68-461125aac99a | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009340 | bcbbc8de-3b0e-4e8f-935e-3d1f2f9027c1 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009341 | 79713613-ef4e-4c80-b9b3-d9fa73a67ce3 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009342 | a8b1b111-af47-4d28-878d-9cd80e682c66 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009343 | fe647549-10f2-4474-84c5-0954eca1ac7f | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009344 | 1c71911b-8a42-4e7b-b19d-3ed402303b69 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009345 | 437e12d5-3064-4690-bc7c-164159bd7497 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009346 | 2640a118-7533-4eee-8aa6-c13e9ade6539 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009347 | 8e2c822a-bd81-4ce1-bcfb-3472e3411321 | Pole | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-10 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009348 | d7361257-5d6b-4b70-8a83-14bcecbdea19 | Pole | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-17 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009349 | c68d77a0-9ec9-42ce-81be-d8766018792f | Pole | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009350 | 316e3726-e6d3-4f0f-9d53-b3e401250bb3 | Pole | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009351 | c68d77a0-9ec9-42ce-81be-d8766018792f | Pole | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-19 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009352 | b5d2bf2a-5e8b-4351-8b6d-eb78533a31a2 | Pole | Non-HFTD | Distribution | 2025-03-21 | 2026-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009353 | 28499094-5eef-47b9-8118-34af7c3e6516 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2026-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009354 | b5d2bf2a-5e8b-4351-8b6d-eb78533a31a2 | Pole | Non-HFTD | Distribution | 2025-03-21 | 2026-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009355 | 28499094-5eef-47b9-8118-34af7c3e6516 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2026-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009356 | c3377fb7-35e5-4213-bf37-e25ba5e40071 | Pole | Non-HFTD | Distribution | 2025-03-21 | 2026-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009357 | 28499094-5eef-47b9-8118-34af7c3e6516 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2030-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009358 | c3377fb7-35e5-4213-bf37-e25ba5e40071 | Pole | Non-HFTD | Distribution | 2025-03-21 | 2026-03-21 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009359 | ecc179cf-6f0e-4254-b340-202123abfdf0 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2030-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009360 | ecc179cf-6f0e-4254-b340-202123abfdf0 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2030-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009361 | ecc179cf-6f0e-4254-b340-202123abfdf0 | Pole | HFTD Tier 2 | Distribution | 2025-03-21 | 2030-03-20 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009362 | 1afad64b-387f-46b0-99eb-df1f6a05c28c | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009363 | fa5a3228-72fb-4188-83b9-38f1d6e35858 | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009364 | 064a6ebe-62a7-464c-9d7d-3f7557fcda6c | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2026-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009365 | e49764df-0dd6-48ea-94fc-21c9bd9db534 | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2026-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009366 | e49764df-0dd6-48ea-94fc-21c9bd9db534 | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009367 | 36ab204a-dc7c-4fa7-b94e-bb595e22489e | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009368 | e49764df-0dd6-48ea-94fc-21c9bd9db534 | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009369 | 36d4433a-50b9-4ad5-b010-94bb286218ee | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2030-03-24 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009370 | 07502836-07df-4a5f-8d54-0ba0b755b4b9 | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2026-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009371 | 66d38341-5993-49e5-9897-9151da6a4ebb | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2026-03-25 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009372 | 4b391bf7-c054-4ad8-8490-030257192c45 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009373 | 957c43a0-7374-47cc-b6c2-1bbe1e909357 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009374 | 4b391bf7-c054-4ad8-8490-030257192c45 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009375 | 333c0654-50a8-43c7-90fd-42236fa1cdd2 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009376 | 7862145a-b779-45fe-b478-1325d91a2ebd | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009377 | 8c7a975b-05f7-449b-96f8-a8e31a0c14ce | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009378 | 8019d952-7a34-4a08-862a-3e08e4a04fb3 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009379 | 5f896831-ddb7-403f-a93e-712bb13be540 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009380 | aff8e811-4da9-4a87-b347-756628be1ed4 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009381 | 659b26a6-cb0f-4d9c-9484-ab52aeed8c41 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-26 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009382 | 8aaa6f5c-54fe-4be7-bce0-ac6e83755f47 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-27 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009383 | 4b6e7984-f3d3-417b-983b-78e12184f295 | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2030-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009384 | b239e7aa-4177-48e6-afbe-663ce3804a6c | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2026-03-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009385 | abb691fc-9ad8-4963-8652-6738bc94b260 | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2030-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009386 | c5ba39b5-8bf3-41d2-9676-cbcb8df33e3f | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2030-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1
1130009387 | ba4924ea-ced3-468f-af74-6441b6cfc9c8 | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2026-03-28 | Level 2 |  |  | Level 2 |  |  |  |  | Liberty | 2025 | 1
1130009388 | 4b6e7984-f3d3-417b-983b-78e12184f295 | Pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2030-03-27 | Level 3 |  |  | Level 3 |  |  |  |  | Liberty | 2025 | 1