## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | ANNUAL QUANTITATIVE TARGET | PROJECTED QUANTITATIVE PROGRESS Q1 | PROJECTED QUANTITATIVE PROGRESS Q1-2 | PROJECTED QUANTITATIVE PROGRESS Q1-3 | PROJECTED QUANTITATIVE PROGRESS Q1-4 | ANNUAL QUALITATIVE TARGET
2010000000 | Liberty | 2025-06-24 | Program |  |  | Covered conductor installation | See Column I | Reduce the risk of ignition from vegetation contact, wire slap during wind events, and wildlife interference. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.1 | WMP-GDOM-GH-01 | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-01_2026 | 117 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | No | Circuit Miles |  | 2026 | 3.9 |  |  |  | 3.9
2010000001 | Liberty | 2025-06-24 | Program |  |  | Undergrounding of electric lines and/or equipment | See Column I | Eliminate wildfire ignition risks. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.2 | WMP-GDOM-GH-02 | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-02_2026 | 119 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | No | Circuit Miles |  | 2026 | 0 |  |  |  | 0
2010000002 | Liberty | 2025-06-24 | Program |  |  | Distribution pole replacements and reinforcements | See Column I | Minimize the risk of faults due to pole and associated hardware failure and to maintain system reliability. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.3 | WMP-GDOM-GH-03 | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-03_2026 | 120 | Equipment ignition likelihood | No | Poles |  | 2026 | 400 |  |  |  | 400
2010000003 | Liberty | 2025-06-24 | Program |  |  | Traditional overhead hardening | See Column I | Support both wildfire risk reduction and system reliability improvements. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.5 | WMP-GDOM-GH-05 | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-05_2026 | 122 | Equipment ignition likelihood | No | Circuit Miles |  | 2026 | 1.1 |  |  |  | 1.1
2010000004 | Liberty | 2025-06-24 | Program |  |  | Microgrids | See Column I | Reduce wildfire risk and eliminate the possibility of infrastructure ignition events on lines that are removed or taken out of service. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.7 | WMP-GDOM-GH-07 | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-07_2026 | 124 | PSPS likelihood PSPS exposure potential | No | Microgrids |  | 2026 | 0 |  |  |  | 0
2010000005 | Liberty | 2025-06-24 | Program |  |  | Installation of system automation equipment | See Column I | Liberty installs reclosers to help with sectionalization, opportunities for distribution automation, and opportunities for grid topology improvement to reduce the size and number of customers affected by faults on the system. Reclosers also help Liberty more quickly identify and restore power to affected customers. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.8 | WMP-GDOM-GH-08 | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-08_2026 | 125 | Equipment ignition likelihood | No | Automatic Reclosers |  | 2026 | 0 |  |  |  | 0
2010000006 | Liberty | 2025-06-24 | Program |  |  | Line removal (in HFTD) | See Column I | Line removal eliminates the risk of infrastructure caused ignitions in the area where a line is removed. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.9 | WMP-GDOM-GH-09 | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-09_2026 | 126 | Equipment ignition likelihood | No | Circuit Miles |  | 2026 | 0 |  |  |  | 0
2010000007 | Liberty | 2025-06-24 | Program |  |  | Tree attachment removals | See Column I | Reduce wildfire ignition risk by eliminating the potential for conductor-tree contact, which can lead to faults, arcing, or fire during wind events or tree movement. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.12.1 | WMP-GDOM-GH-12a | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-12a_2026 | 126 | Equipment ignition likelihood | No | Tree Attachments |  | 2026 | 60 |  |  |  | 60
2010000008 | Liberty | 2025-06-24 | Program |  |  | Expulsion fuse replacement | See Column I | Reduce risk of ignition by limiting energy release. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.12.2 | WMP-GDOM-GH-12b | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-12b_2026 | 128 | Equipment ignition likelihood | No | Expulsion Fuses |  | 2026 | 500 |  |  |  | 500
2010000009 | Liberty | 2025-06-24 | Program |  |  | Animal guards | See Column I | Reduce risk of ignition by installing insulating animal guards on exposed substation equipment. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.12.3 | WMP-GDOM-GH-12c | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-12c_2026 | 129 | Equipment ignition likelihood Contact by object ignition likelihood | No | Animal Guards |  | 2026 | 0 |  |  |  | 0
2010000010 | Liberty | 2025-06-24 | Program |  |  | Open wire/grey wire | See Column I | Reduces the risk of ignition and service interruptions, particularly in wildland-urban interface areas where homes and vegetation are in close proximity to overhead infrastructure. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.12.5 | WMP-GDOM-GH-12e | Liberty_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP-GDOM-GH-12e_2026 | 129 | Equipment ignition likelihood | No | Circuit Miles |  | 2026 | 5.2 |  |  |  | 5.2
2010000011 | Liberty | 2025-06-24 | Program |  |  | Detailed inspections of distribution electric lines and equipment | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.1 | WMP-GDOM-AI-01 | Liberty_Grid Design, Operations, and Maintenance_Asset Inspections_WMP-GDOM-AI-01_2026 | 134 | Equipment ignition likelihood | Yes | Circuit Miles |  | 2026 | 207 | 20 | 50 | 150 | 207
2010000012 | Liberty | 2025-06-24 | Program |  |  | Intrusive pole inspections | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.2 | WMP-GDOM-AI-02 | Liberty_Grid Design, Operations, and Maintenance_Asset Inspections_WMP-GDOM-AI-02_2026 | 135 | Equipment ignition likelihood | Yes | Poles |  | 2026 | 2031 | 0 | 0 | 2031 | 2031
2010000013 | Liberty | 2025-06-24 | Program |  |  | Patrol inspections of distribution electric lines and equipment | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.3 | WMP-GDOM-AI-03 | Liberty_Grid Design, Operations, and Maintenance_Asset Inspections_WMP-GDOM-AI-03_2026 | 136 | Equipment ignition likelihood | Yes | Circuit Miles |  | 2026 | 553.4 | 200 | 553.4 | 553.4 | 553.4
2010000014 | Liberty | 2025-06-24 | Program |  |  | Other discretionary inspections of distribution electric lines and equipment | See Column I | Outage restoration. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.4 | WMP-GDOM-AI-04 | Liberty_Grid Design, Operations, and Maintenance_Asset Inspections_WMP-GDOM-AI-04_2026 | 137 | Equipment ignition likelihood | No | Circuit Miles |  | 2026 | 1 |  |  |  | 1
2010000015 | Liberty | 2025-06-24 | Program |  |  | Quality assurance / quality control of inspections | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.5 | WMP-GDOM-AI-05 | Liberty_Grid Design, Operations, and Maintenance_Asset Inspections_WMP-GDOM-AI-05_2026 | 143 | Equipment ignition likelihood | Yes | % of Detailed Inspections |  | 2026 | 12% | 0% | 0% | 0% | 12%
2010000016 | Liberty | 2025-06-24 | Program |  |  | Substation inspections | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.5 | WMP-GDOM-AI-06 | Liberty_Grid Design, Operations, and Maintenance_Asset Inspections_WMP-GDOM-AI-06_2026 | 138 | Equipment ignition likelihood | Yes | Substations |  | 2026 | 44 | 10 | 22 | 34 | 44
2010000017 | Liberty | 2025-06-24 | Program |  |  | Equipment maintenance and repair | See Column I | Reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | 8.4 | WMP-GDOM-MR-01 | Liberty_Grid Design, Operations, and Maintenance_Equipment Maintenance and Repair_WMP-GDOM-MR-01_2026 | 139 | Equipment ignition likelihood | No |  |  | 2026 | [5 empty] | All asset inspections and repairs recorded in Asset Tracking
2010000018 | Liberty | 2025-06-24 | Program |  |  | Equipment settings to reduce wildfire risk | See Column I | Utilize fast trip settings and add more fault indicators to reduce wildfire risk during high fire threat days. | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | 8.7.1 | WMP-GDOM-GO-01 | Liberty_Grid Design, Operations, and Maintenance_Grid Operations and Procedures_WMP-GDOM-GO-01_2026 | 153 | Equipment ignition likelihood | No | # of circuits with SRP |  | 2026 | 0 |  |  |  | 0
2010000019 | Liberty | 2025-06-24 | Program |  |  | Equipment settings to reduce wildfire risk | See Column I | Utilize fast trip settings and add more fault indicators to reduce wildfire risk during high fire threat days. | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | 8.7.1 | WMP-GDOM-GO-01 | Liberty_Grid Design, Operations, and Maintenance_Grid Operations and Procedures_WMP-GDOM-GO-01_2026 | 153 | Equipment ignition likelihood | No |  |  | 2026 | [5 empty] | Review settings of 1/3 of SRP circuits
2010000020 | Liberty | 2025-06-24 | Program |  |  | Vegetation Management Inspection Program - Detailed | See Column I | Prescribe pruning and removal of vegetation as a safeguard against grow‐ins or fall‐ins and to comply with required laws and regulations. | Vegetation Management & Inspections | Vegetation Management Inspections |  | 9.2.1 | WMP-VM-INSP-01 | Liberty_Vegetation Management & Inspections_Vegetation Management Inspections_WMP-VM-INSP-01_2026 | 166 | Contact from vegetation ignition likelihood | Yes | Line Miles |  | 2026 | 220 | 55 | 110 | 165 | 220
2010000021 | Liberty | 2025-06-24 | Program |  |  | Vegetation Management Inspection Program - Patrol | See Column I | Conduct as needed based on environmental conditions or other factors. | Vegetation Management & Inspections | Vegetation Management Inspections |  | 9.2.2 | WMP-VM-INSP-02 | Liberty_Vegetation Management & Inspections_Vegetation Management Inspections_WMP-VM-INSP-02_2026 | 171 | Contact from vegetation ignition likelihood | No | Line Miles |  | 2026 | 0 |  |  |  | 0
2010000022 | Liberty | 2025-06-24 | Program |  |  | Vegetation Management Inspection Program - LiDar | See Column I | Measure vegetation to conductor distances, tree height, and proximity to overhead lines. | Vegetation Management & Inspections | Vegetation Management Inspections |  | 9.2.3 | WMP-VM-INSP-03 | Liberty_Vegetation Management & Inspections_Vegetation Management Inspections_WMP-VM-INSP-03_2026 | 172 | Contact from vegetation ignition likelihood | Yes | Line Miles |  | 2026 | 700 | 0 | 0 | 700 | 700
2010000023 | Liberty | 2025-06-24 | Program |  |  | Pole Clearing | See Column I | Reduce wildfire risk by removing vegetation at base of poles. | Vegetation Management & Inspections | Pole Clearing |  | 9.4 | WMP-VM-VFM-01 | Liberty_Vegetation Management & Inspections_Pole Clearing_WMP-VM-VFM-01_2026 | 176 | Wildfire spread Wildfire hazard | No | Subject Poles |  | 2026 | 4900 | 0 | 1633 | 3266 | 4900
2010000024 | Liberty | 2025-06-24 | Program |  |  | Wood and Slash Management | See Column I | Reduce wildfire risks by removing wood and treating brush and slash after vegetation maintenance is performed. | Vegetation Management & Inspections | Wood and Slash Management |  | 9.5 | WMP-VM-VFM-02 | Liberty_Vegetation Management & Inspections_Wood and Slash Management_WMP-VM-VFM-02_2026 | 177 | Wildfire spread Wildfire hazard | No | Acres |  | 2026 | 280 |  |  |  | 280
2010000025 | Liberty | 2025-06-24 | Program |  |  | Substation Defensible Space | See Column I | Maintain accessibility, safety, and adherence to all appropriate governmental regulations and Liberty policies. | Vegetation Management & Inspections | Defensible Space |  | 9.6 | WMP-VM-VFM-03 | Liberty_Vegetation Management & Inspections_Defensible Space_WMP-VM-VFM-03_2026 | 179 | Wildfire spread Wildfire hazard | No | Substation Treatments |  | 2026 | 12 |  |  |  | 12
2010000026 | Liberty | 2025-06-24 | Program |  |  | Fire-Resilient Right-of-Ways | See Column I | Reduce future maintenance entries, protect infrastructure, increase fire-resiliency and are the initial step of the integrated vegetation management (“IVM”) program. | Vegetation Management & Inspections | Integrated Vegetation Management |  | 9.7 | WMP-VM-VFM-04 | Liberty_Vegetation Management & Inspections_Integrated Vegetation Management_WMP-VM-VFM-04_2026 | 181 | Wildfire spread Wildfire hazard | No | Line Miles |  | 2026 | [5 empty] | Maintain Tree Line USA
2010000027 | Liberty | 2025-06-24 | Program |  |  | Clearance | See Column I | Prescribe mitigation of vegetation encroachments. | Vegetation Management & Inspections | Clearance |  | 9.2 | WMP-VM-VFM-05 | Liberty_Vegetation Management & Inspections_Clearance_WMP-VM-VFM-05_2026 | 174 | Contact from vegetation ignition likelihood | No | Line Miles |  | 2026 | 700 |  |  |  | 700
2010000028 | Liberty | 2025-06-24 | Program |  |  | Fall-In Mitigation | See Column I | Identify trees that pose a high risk of failure. | Vegetation Management & Inspections | Fall-In Mitigation |  | 9.2 | WMP-VM-VFM-06 | Liberty_Vegetation Management & Inspections_Fall-In Mitigation_WMP-VM-VFM-06_2026 | 174 | Contact from vegetation ignition likelihood | No | Line Miles |  | 2026 | 220 |  |  |  | 220
2010000029 | Liberty | 2025-06-24 | Program |  |  | High-Risk Species | See Column I | Identify trees that pose a high risk of failure. | Vegetation Management & Inspections | High-Risk Species |  | 9.2 | WMP-VM-VFM-07 | Liberty_Vegetation Management & Inspections_High-Risk Species_WMP-VM-VFM-07_2026 | 174 | Contact from vegetation ignition likelihood | No | Line Miles |  | 2026 | 0 |  |  |  | 0
2010000030 | Liberty | 2025-06-24 | Program |  |  | Emergency Response Vegetation Management | See Column I | Identify and mitigate significantly damaged trees exhibiting 50% or more crown loss, severe trunk damage or scorching, and are an immediate or critical risk to restoration efforts or the repaired infrastructure. | Vegetation Management & Inspections | Emergency Response Vegetation Management |  | 9.1 | WMP-VM-VFM-08 | Liberty_Vegetation Management & Inspections_Emergency Response Vegetation Management_WMP-VM-VFM-08_2026 | 190 | Wildfire spread Wildfire hazard | No | Line Miles |  | 2026 | 0 |  |  |  | 0
2010000031 | Liberty | 2025-06-24 | Program |  |  | Quality Assurance and Quality Control | See Column I | Provides VM program oversight to provide reasonable assurance that vegetation inspection and maintenance work is being effectively performed. | Vegetation Management & Inspections | Quality Assurance and Quality Control |  | 9.11 | WMP-VM-QAQC-01 | Liberty_Vegetation Management & Inspections_Quality Assurance and Quality Control_WMP-VM-QAQC-01_2026 | 191 | Contact from vegetation ignition likelihood | No | Line Miles |  | 2026 | 228 |  |  |  | 228
2010000032 | Liberty | 2025-06-24 | Program |  |  | Environmental monitoring systems | See Column I | Monitor environmental conditions within service territory. | Situational Awareness & Forecasting | Environmental monitoring systems |  | 10.2 | WMP-SA-01 | Liberty_Situational Awareness & Forecasting_Environmental monitoring systems_WMP-SA-01_2026 | 211 | Wildfire exposure potential PSPS exposure potential | No | Weather Stations |  | 2026 | 0 |  |  |  | 0
2010000033 | Liberty | 2025-06-24 | Program |  |  | Grid monitoring systems | See Column I | Expedite power restoration during an outage by helping line crews locate the fault. | Situational Awareness & Forecasting | Grid monitoring systems |  | 10.3 | WMP-SA-02 | Liberty_Situational Awareness & Forecasting_Grid monitoring systems_WMP-SA-02_2026 | 218 | Equipment ignition likelihood | No | Circuits with Fault Indicators |  | 2026 | 0 |  |  |  | 0
2010000034 | Liberty | 2025-06-24 | Program |  |  | Collaboration and coordination with public safety partners | See Column I | Inform external public safety partners and other interconnected electrical corporation partners of wildfire, PSPS, and re-energization events as required by G.O. 166 and Public Utilities Code Section 768.6. | Emergency Preparedness | Collaboration and coordination with public safety partners |  | 11.3.1 | WMP-EP-02 | Liberty_Emergency Preparedness_Collaboration and coordination with public safety partners_WMP-EP-02_2026 | 249 | PSPS vulnerability Wildfire vulnerability | No |  |  | 2026 | [5 empty] | Conduct emergency drills; engagement with PSPs, meetings with community advisory boards.
2010000035 | Liberty | 2025-06-24 | Program |  |  | Customer support in wildfire and PSPS emergencies | See Column I | Increase awareness and community resiliency to wildfires and PSPS events. | Emergency Preparedness | Customer support in wildfire and PSPS emergencies |  | 11.5 | WMP-EP-05 | Liberty_Emergency Preparedness_Customer support in wildfire and PSPS emergencies_WMP-EP-05_2026 | 277 | PSPS vulnerability Wildfire vulnerability | No |  |  | 2026 | [5 empty] | Conduct IC training; hold tabletop PSPS exercise; implement AFN plan; maintain emergency response plans
2010000036 | Liberty | 2025-06-24 | Program |  |  | Learning after wildfire and PSPS events | See Column I | Increase awareness and community resiliency to wildfires and PSPS events. | Emergency Preparedness | Learning after wildfire and PSPS events |  | 7 | WMP-EP-06 | Liberty_Emergency Preparedness_Learning after wildfire and PSPS events_WMP-EP-06_2026 | 105 | PSPS vulnerability Wildfire vulnerability | No |  |  | 2026 | [5 empty] | Produce After Action Reports for each event
2010000037 | Liberty | 2025-06-24 | Program |  |  | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | See Column I | Increase awareness and community resiliency to wildfires and PSPS events. | Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management |  | 11.4.3 | WMP-CO-01 | Liberty_Community Outreach and Engagement_Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management_WMP-CO-01_2026 | 267 | PSPS vulnerability Wildfire vulnerability | No |  |  | 2026 | [5 empty] | Two wildfire and PSPS outreach surveys
2010000038 | Liberty | 2025-06-24 | Program |  |  | Engagement with AFN populations, local governments, and tribal communities | See Column I | Increase awareness and community resiliency to wildfires and PSPS events, including identification of AFN customers. | Community Outreach and Engagement | Engagement with AFN populations, local governments, and tribal communities |  | 11.4.4 | WMP-CO-03 | Liberty_Community Outreach and Engagement_Engagement with AFN populations, local governments, and tribal communities_WMP-CO-03_2026 | 272 | PSPS vulnerability Wildfire vulnerability | No |  |  | 2026 | [5 empty] | 9 Events
2010000039 | Liberty | 2025-06-24 | Program |  |  | Best practice sharing with other electrical corporations | See Column I | Share industry best practices | Community Outreach and Engagement | Best practice sharing with other electrical corporations |  | 11.4.4 | WMP-CO-05 | Liberty_Community Outreach and Engagement_Best practice sharing with other electrical corporations_WMP-CO-05_2026 | 272 | PSPS vulnerability Wildfire vulnerability | No |  |  | 2026 | [5 empty] | Participation in working groups and Joint IOU Councils

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2020000000 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | HFTD Tier 2 |  |  |  | Number of events |  |  | Liberty | 2026 | 2026 | 2 | 2 | 2
2020000001 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | HFTD Tier 3 |  |  |  | Number of events |  |  | Liberty | 2026 | 2026 | 0.3 | 0.3 | 0.3
2020000002 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | Non-HFTD |  |  |  | Number of events |  |  | Liberty | 2026 | 2026 | 0.3 | 0.3 | 0.3
2020000003 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | Liberty | 2026 | 2026 | 850 | 850 | 850
2020000004 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2020000005 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | Liberty | 2026 | 2026 | 5500 | 4950 | 4455
2020000006 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 18 | 18 | 18
2050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 2 | 2 | 2
2050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 3.6667 | 3.6667 | 3.6667
2050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 6 | 6 | 6
2050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1.6667 | 1.6667 | 1.6667
2050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 2 | 2 | 2
2050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 11 | 11 | 11
2050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 6 | 6 | 6
2050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 4.6667 | 4.6667 | 4.6667
2050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 63 | 63 | 63
2050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 5.6667 | 5.6667 | 5.6667
2050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 23.6667 | 23.6667 | 23.6667
2050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1.6667 | 1.6667 | 1.6667
2050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 11 | 11 | 11
2050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 3 | 3 | 3
2050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1.6667 | 1.6667 | 1.6667
2050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 11.3333 | 11.3333 | 11.3333
2050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 7.3333 | 7.3333 | 7.3333
2050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 4.6667 | 4.6667 | 4.6667
2050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 2 | 2 | 2
2050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 12.6667 | 12.6667 | 12.6667
2050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 6 | 6 | 6
2050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 9.6667 | 9.6667 | 9.6667
2050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1.6667 | 1.6667 | 1.6667
2050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 8 | 8 | 8
2050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 75.6667 | 75.6667 | 75.6667
2050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 4.6667 | 4.6667 | 4.6667
2050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 5.6667 | 5.6667 | 5.6667
2050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 4.6667 | 4.6667 | 4.6667
2050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 30.6667 | 30.6667 | 30.6667
2050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 2.6667 | 2.6667 | 2.6667
2050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 6.6667 | 6.6667 | 6.6667
2050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.1 | 0.1 | 0.1
2060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.4 | 0.4 | 0.4
2060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.3 | 0.3 | 0.3
2060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.1 | 0.1 | 0.1
2060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.1 | 0.1 | 0.1
2060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.1 | 0.1 | 0.1
2060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 4.59 | 4.59 | 4.59
2070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 1.04 | 1.04 | 1.04
2070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 12.73 | 12.73 | 12.73
2070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 5.41 | 5.41 | 5.41
2070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 52.54 | 52.54 | 52.54
2070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 15.99 | 15.99 | 15.99
2070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 307.65 | 307.65 | 307.65
2070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 17.95 | 17.95 | 17.95
2070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 582.93 | 582.93 | 582.93
2070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 165.32 | 165.32 | 165.32
2070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 114.41 | 114.41 | 114.41
2070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 72.62 | 72.62 | 72.62
2070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.03 | 0.03 | 0.03
2070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 109 | 109 | 109
2070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 15.71 | 15.71 | 15.71
2070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 1.46 | 1.46 | 1.46
2070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.39 | 0.39 | 0.39
2070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.1 | 0.1 | 0.1
2070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.16 | 0.16 | 0.16
2070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 1.57 | 1.57 | 1.57
2070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.18 | 0.18 | 0.18
2070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 5.69 | 5.69 | 5.69
2070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 20.68 | 20.68 | 20.68
2070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.29 | 0.29 | 0.29
2070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.03 | 0.03 | 0.03
2070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 2.32 | 2.32 | 2.32
2070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 21.7 | 21.7 | 21.7
2070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 1.05 | 1.05 | 1.05
2070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 3.42 | 3.42 | 3.42
2070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 1.52 | 1.52 | 1.52
2070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 8.84 | 8.84 | 8.84
2070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 1.84 | 1.84 | 1.84
2070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 103.76 | 103.76 | 103.76
2070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 11.88 | 11.88 | 11.88
2070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 297.61 | 297.61 | 297.61
2070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 77.48 | 77.48 | 77.48
2070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 35.42 | 35.42 | 35.42
2070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 10.52 | 10.52 | 10.52
2070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 8.76 | 8.76 | 8.76
2070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 1.46 | 1.46 | 1.46
2070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.06 | 0.06 | 0.06
2070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 1.09 | 1.09 | 1.09
2070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0.15 | 0.15 | 0.15
2070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 17.0312 | 17.0626 | 17.0939
2070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 2 | 2 | 2
2070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 18.5128 | 21.4203 | 24.7844
2070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 3.75 | 4.6875 | 5.8594
2070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 123.4522 | 149.4162 | 180.8408
2070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 22.706 | 27.135 | 32.4278
2070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 418.481 | 454.8736 | 494.4311
2070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 71.4643 | 81.0658 | 91.9573
2070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 538.3947 | 710.4628 | 937.5231
2070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 147.0985 | 208.0575 | 294.2783
2070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 79.4296 | 95.5918 | 115.0426
2070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 41.3269 | 48.7976 | 57.6187
2070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 63.0333 | 64.0839 | 65.152
2070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 6.0417 | 7.3003 | 8.8213
2070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 1002.5193 | 999.0506 | 995.5939
2070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 17 | 17 | 17
2070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 374.5341 | 377.0854 | 379.6541
2070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 20.1176 | 21.301 | 22.554
2070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 1454.4787 | 1444.033 | 1433.6624
2070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 38.0128 | 38.0256 | 38.0385
2070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 14483.3289 | 14619.9341 | 14757.8278
2070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 39 | 39 | 39
2070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 20289.2074 | 20446.6267 | 20605.2675
2070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 1075.5487 | 1102.7693 | 1130.6789
2070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 1786.907 | 1810.1116 | 1833.6174
2070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 199.8977 | 197.8172 | 195.7584
2070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 2826.7464 | 2843.5925 | 2860.5391
2070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 143.5244 | 144.0506 | 144.5788
2070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 99.7227 | 96.5497 | 93.4777
2070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 10.1538 | 9.3728 | 8.6518
2070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 75.544 | 75.0907 | 74.6401
2070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 87.7476 | 85.5515 | 83.4105
2070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 211.4522 | 206.0462 | 200.7785
2070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 86.8105 | 87.6286 | 88.4545
2070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 1775.396 | 1712.1299 | 1651.1182
2070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 258.2343 | 259.4746 | 260.7208
2070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 1501.2427 | 1494.5158 | 1487.8189
2070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 339.4082 | 334.8777 | 330.4077
2070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 136.7492 | 134.5348 | 132.3562
2070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 89.6671 | 90.3391 | 91.0162
2070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 62.8474 | 66.9456 | 71.3112
2070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 6.6 | 7.26 | 7.986
2070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 244.4314 | 295.7758 | 357.9055
2070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 4.5833 | 4.2014 | 3.8513
2070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 115.2363 | 135.5041 | 159.3365
2070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 3.0667 | 2.3511 | 1.8025
2070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 610.9887 | 633.7984 | 657.4596
2070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 22.4507 | 24.0015 | 25.6595
2070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 4949.0643 | 5772.6226 | 6733.2266
2070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 10.6944 | 11.4371 | 12.2314
2070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 4865.7636 | 6176.7949 | 7841.0706
2070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 257.3691 | 316.9323 | 390.2804
2070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 623.9244 | 688.994 | 760.8498
2070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 84.7 | 94.396 | 105.2019
2070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 794.9941 | 995.3001 | 1246.075
2070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 40.8583 | 47.6971 | 55.6806
2070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 2 | 2 | 2
2070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 5 | 5 | 5
2070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 2 | 2 | 2
2070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 4 | 4 | 4
2070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 2 | 2 | 2
2070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 8 | 8 | 8
2070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 11 | 11 | 11
2070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 5 | 5 | 5
2070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 7 | 7 | 7
2070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 1 | 1 | 1
2070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026 |  | 0.024
2090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026 |  | 3.11
2090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026 | 0.38
2090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026 | 5.06
2090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Liberty doesn't have project level information at this time. | Liberty | 2026 | 2026
2090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  | Not an initiative in Liberty's 2026-2028 WMP. | Liberty | 2026 | 2026
2090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0
2090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | Liberty | 2026 | 2026 | 0 | 0 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | All (regardless of WWS) | Number of events |  |  | Liberty | 2026 | 2026 | 3 | 3 | 3
2100000001 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | All (regardless of WWS) | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | Liberty | 2026 | 2026 | 6 | 6 | 6
2100000002 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | All (regardless of WWS) | Customer hours |  |  | Liberty | 2026 | 2026 | 46000 | 46000 | 46000
2100000003 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | All (regardless of WWS) | Number of events |  | N/A | Liberty | 2026 | 2026
2100000004 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | All (regardless of WWS) | Circuit mile days |  | N/A | Liberty | 2026 | 2026
2100000005 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  | N/A | Liberty | 2026 | 2026
2100000006 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  | N/A | Liberty | 2026 | 2026
2100000007 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  | N/A | Liberty | 2026 | 2026
2100000008 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  | N/A | Liberty | 2026 | 2026
2100000009 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  | N/A | Liberty | 2026 | 2026
2100000010 | 3. Critical infrastructure impacted by PSPS | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  | N/A | Liberty | 2026 | 2026
2100000011 | 4. Community outreach of PSPS metrics | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  | N/A | Liberty | 2026 | 2026
2100000012 | 4. Community outreach of PSPS metrics | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  | N/A | Liberty | 2026 | 2026
2100000013 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | Liberty | 2026 | 2026 | 3860 | 3860 | 3860
2100000014 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | N/A | Liberty | 2026 | 2026
2100000015 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | N/A | Liberty | 2026 | 2026
2100000016 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | N/A | Liberty | 2026 | 2026
2100000017 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | N/A | Liberty | 2026 | 2026
2100000018 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | N/A | Liberty | 2026 | 2026
2100000019 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  | N/A | Liberty | 2026 | 2026
2100000020 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  | N/A | Liberty | 2026 | 2026
2100000021 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  | N/A | Liberty | 2026 | 2026
2100000022 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  | N/A | Liberty | 2026 | 2026
2100000023 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  | N/A | Liberty | 2026 | 2026
2100000024 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  | N/A | Liberty | 2026 | 2026
2100000025 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  | N/A | Liberty | 2026 | 2026
2100000026 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  | N/A | Liberty | 2026 | 2026
2100000027 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  | N/A | Liberty | 2026 | 2026
2100000028 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  | N/A | Liberty | 2026 | 2026

## Table 11
METRIC NUMBER | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY (IF BLANK THIS REFERS TO ALL ACTIVITIES UNDER THE INITIATIVE) | EXPENSE TYPE | HFTD TIER | UNIT(S) | UTILITY MITIGATION ACTIVITY TRACKING IDS | PRIMARY DRIVER TARGETED | SECONDARY DRIVERS TARGETED | YEAR INITIATED | MOST RECENT PROCEEDING | MEMORANDUM ACCOUNT | CURRENT COMPLIANCE STATUS | ASSOCIATED RULES | OTHER SPEND CATEGORY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2110000000 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | CAPEX | Territory | $ Thousands | WMP-SA-06 |  |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000001 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | CAPEX | HFTD | $ Thousands | WMP-SA-06 |  |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000002 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | OPEX | Territory | $ Thousands | WMP-SA-06 |  |  | 2020 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 900 | 900 | 900
2110000003 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | OPEX | HFTD | $ Thousands | WMP-SA-06 |  |  | 2020 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 900 | 900 | 900
2110000004 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | CAPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000005 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000006 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | OPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000007 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | OPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000008 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-01 | Contact from vegetation ignition likelihood | Contact by object ignition likelihood | 2019 | 2025 WMP |  | In compliance | G.O. 95 |  |  |  | Liberty | 2026 | 2026 | 7081 | 6310 | 6695.5
2110000009 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-01 | Contact from vegetation ignition likelihood | Contact by object ignition likelihood | 2019 | 2025 WMP |  | In compliance | G.O. 95 |  |  |  | Liberty | 2026 | 2026 | 7081 | 6310 | 6695.5
2110000010 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | OPEX | Territory | $ Thousands | WMP-GDOM-GH-01 | Contact from vegetation ignition likelihood | Contact by object ignition likelihood | 2019 | 2025 WMP |  | In compliance | G.O. 95 |  |  | Not applicable | Liberty | 2026 | 2026
2110000011 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-01 | Contact from vegetation ignition likelihood | Contact by object ignition likelihood | 2019 | 2025 WMP |  | In compliance | G.O. 95 |  |  | Not applicable | Liberty | 2026 | 2026
2110000012 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-02 | Contact from vegetation ignition likelihood | Contact by object ignition likelihood |  | 2025 WMP |  | In compliance | G.O. 95 |  |  | Not applicable | Liberty | 2026 | 2026
2110000013 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-02 | Contact from vegetation ignition likelihood | Contact by object ignition likelihood |  | 2025 WMP |  | In compliance | G.O. 95 |  |  | Not applicable | Liberty | 2026 | 2026
2110000014 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | OPEX | Territory | $ Thousands | WMP-GDOM-GH-02 | Contact from vegetation ignition likelihood | Contact by object ignition likelihood |  | 2025 WMP |  | In compliance | G.O. 95 |  |  | Not applicable | Liberty | 2026 | 2026
2110000015 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-02 | Contact from vegetation ignition likelihood | Contact by object ignition likelihood |  | 2025 WMP |  | In compliance | G.O. 95 |  |  | Not applicable | Liberty | 2026 | 2026
2110000016 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-03 | Equipment ignition likelihood |  | 2011 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 8000 | 8000 | 8000
2110000017 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-03 | Equipment ignition likelihood |  | 2011 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 8000 | 8000 | 8000
2110000018 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | OPEX | Territory | $ Thousands | WMP-GDOM-GH-03 | Equipment ignition likelihood |  | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000019 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-03 | Equipment ignition likelihood |  | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000020 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-04 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000021 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-04 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000022 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | OPEX | Territory | $ Thousands | WMP-GDOM-GH-04 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000023 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-04 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000024 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-05 | Equipment ignition likelihood |  |  | 2025 WMP |  | In compliance | G.O. 95 |  |  |  | Liberty | 2026 | 2026 | 1000 | 1000 | 1000
2110000025 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-05 | Equipment ignition likelihood |  |  | 2025 WMP |  | In compliance | G.O. 95 |  |  |  | Liberty | 2026 | 2026 | 1000 | 1000 | 1000
2110000026 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | OPEX | Territory | $ Thousands | WMP-GDOM-GH-05 | Equipment ignition likelihood |  |  | 2025 WMP |  | In compliance | G.O. 95 |  |  | Not applicable | Liberty | 2026 | 2026
2110000027 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-05 | Equipment ignition likelihood |  |  | 2025 WMP |  | In compliance | G.O. 95 |  |  | Not applicable | Liberty | 2026 | 2026
2110000028 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-06 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000029 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-06 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000030 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | OPEX | Territory | $ Thousands | WMP-GDOM-GH-06 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000031 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-06 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000032 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-07 | PSPS likelihood | PSPS exposure potential | 2020 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000033 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-07 | PSPS likelihood | PSPS exposure potential | 2020 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000034 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | OPEX | Territory | $ Thousands | WMP-GDOM-GH-07 | PSPS likelihood | PSPS exposure potential | 2020 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000035 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-07 | PSPS likelihood | PSPS exposure potential | 2020 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000036 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-08 | Equipment ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000037 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-08 | Equipment ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000038 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | OPEX | Territory | $ Thousands | WMP-GDOM-GH-08 | Equipment ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000039 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-08 | Equipment ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000040 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-09 | Equipment ignition likelihood |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000041 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-09 | Equipment ignition likelihood |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000042 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | OPEX | Territory | $ Thousands | WMP-GDOM-GH-09 | Equipment ignition likelihood |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000043 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-09 | Equipment ignition likelihood |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000044 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-10 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000045 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-10 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000046 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | OPEX | Territory | $ Thousands | WMP-GDOM-GH-10 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000047 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-10 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000048 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-11 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000049 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-11 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000050 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | OPEX | Territory | $ Thousands | WMP-GDOM-GH-11 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000051 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-11 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000052 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | CAPEX | Territory | $ Thousands | WMP-GDOM-GH-12 | Equipment ignition likelihood |  | 2020 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 5132 | 5163 | 5195
2110000053 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | CAPEX | HFTD | $ Thousands | WMP-GDOM-GH-12 | Equipment ignition likelihood |  | 2020 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 5132 | 5163 | 5195
2110000054 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | OPEX | Territory | $ Thousands | WMP-GDOM-GH-12 | Equipment ignition likelihood |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000055 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | OPEX | HFTD | $ Thousands | WMP-GDOM-GH-12 | Equipment ignition likelihood |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000056 | Grid Design, Operations, and Maintenance | Asset Inspections |  | CAPEX | Territory | $ Thousands | WMP-GDOM-AI-01, WMP-GDOM-AI-02, WMP-GDOM-AI-03, WMP-GDOM-AI-04, WMP-GDOM-AI-06 | Equipment ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | G.O. 95;P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000057 | Grid Design, Operations, and Maintenance | Asset Inspections |  | CAPEX | HFTD | $ Thousands | WMP-GDOM-AI-01, WMP-GDOM-AI-02, WMP-GDOM-AI-03, WMP-GDOM-AI-04, WMP-GDOM-AI-06 | Equipment ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | G.O. 95;P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000058 | Grid Design, Operations, and Maintenance | Asset Inspections |  | OPEX | Territory | $ Thousands | WMP-GDOM-AI-01, WMP-GDOM-AI-02, WMP-GDOM-AI-03, WMP-GDOM-AI-04, WMP-GDOM-AI-06 | Equipment ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | G.O. 95;P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 1112.8 | 1209.312 | 1309.6845
2110000059 | Grid Design, Operations, and Maintenance | Asset Inspections |  | OPEX | HFTD | $ Thousands | WMP-GDOM-AI-01, WMP-GDOM-AI-02, WMP-GDOM-AI-03, WMP-GDOM-AI-04, WMP-GDOM-AI-06 | Equipment ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | G.O. 95;P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 1112.8 | 1209.312 | 1309.6845
2110000060 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | CAPEX | Territory | $ Thousands | WMP-GDOM-MR-01 | Equipment ignition likelihood |  | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000061 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | CAPEX | HFTD | $ Thousands | WMP-GDOM-MR-02 | Equipment ignition likelihood |  | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000062 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | OPEX | Territory | $ Thousands | WMP-GDOM-MR-03 | Equipment ignition likelihood |  | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000063 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | OPEX | HFTD | $ Thousands | WMP-GDOM-MR-04 | Equipment ignition likelihood |  | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000064 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | CAPEX | Territory | $ Thousands | WMP-GDOM-AI-05 | Equipment ignition likelihood |  | 2022 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000065 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | CAPEX | HFTD | $ Thousands | WMP-GDOM-AI-05 | Equipment ignition likelihood |  | 2022 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000066 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | OPEX | Territory | $ Thousands | WMP-GDOM-AI-05 | Equipment ignition likelihood |  | 2022 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 31.2 | 32.448 | 33.7459
2110000067 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | OPEX | HFTD | $ Thousands | WMP-GDOM-AI-05 | Equipment ignition likelihood |  | 2022 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 31.2 | 32.448 | 33.7459
2110000068 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | CAPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000069 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000070 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | OPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000071 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | OPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000072 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | CAPEX | Territory | $ Thousands | WMP-GDOM-GO-01 | Equipment ignition likelihood |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000073 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | CAPEX | HFTD | $ Thousands | WMP-GDOM-GO-01 | Equipment ignition likelihood |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000074 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | OPEX | Territory | $ Thousands | WMP-GDOM-GO-01 | Equipment ignition likelihood |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000075 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | OPEX | HFTD | $ Thousands | WMP-GDOM-GO-01 | Equipment ignition likelihood |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000076 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | CAPEX | Territory | $ Thousands | WMP-GDOM-GO-02 |  |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000077 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | CAPEX | HFTD | $ Thousands | WMP-GDOM-GO-02 |  |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000078 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | OPEX | Territory | $ Thousands | WMP-GDOM-GO-02 |  |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000079 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | OPEX | HFTD | $ Thousands | WMP-GDOM-GO-02 |  |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000080 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | CAPEX | Territory | $ Thousands | WMP-GDOM-GO-03 |  |  | 2019 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000081 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | CAPEX | HFTD | $ Thousands | WMP-GDOM-GO-03 |  |  | 2019 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000082 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | OPEX | Territory | $ Thousands | WMP-GDOM-GO-03 |  |  | 2019 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000083 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | OPEX | HFTD | $ Thousands | WMP-GDOM-GO-03 |  |  | 2019 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000084 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | CAPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000085 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | CAPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000086 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | OPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000087 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | OPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000088 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | CAPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000089 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000090 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | OPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000091 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | OPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000092 | Vegetation Management and Inspections | Vegetation Management Inspections |  | CAPEX | Territory | $ Thousands | WMP-VM-INSP-01, WMP-VM-INSP-02, WMP-VM-INSP-03 | Contact from vegetation ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | G.O. 95, Rule 35; Public Resources Code 4293; FAC-003-4 |  |  | Not applicable | Liberty | 2026 | 2026
2110000093 | Vegetation Management and Inspections | Vegetation Management Inspections |  | CAPEX | HFTD | $ Thousands | WMP-VM-INSP-01, WMP-VM-INSP-02, WMP-VM-INSP-03 | Contact from vegetation ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | G.O. 95, Rule 35; Public Resources Code 4293; FAC-003-4 |  |  | Not applicable | Liberty | 2026 | 2026
2110000094 | Vegetation Management and Inspections | Vegetation Management Inspections |  | OPEX | Territory | $ Thousands | WMP-VM-INSP-01, WMP-VM-INSP-02, WMP-VM-INSP-03 | Contact from vegetation ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | G.O. 95, Rule 35; Public Resources Code 4293; FAC-003-4 |  |  |  | Liberty | 2026 | 2026 | 2024.293 | 2085.022 | 2147.572
2110000095 | Vegetation Management and Inspections | Vegetation Management Inspections |  | OPEX | HFTD | $ Thousands | WMP-VM-INSP-01, WMP-VM-INSP-02, WMP-VM-INSP-03 | Contact from vegetation ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | G.O. 95, Rule 35; Public Resources Code 4293; FAC-003-4 |  |  |  | Liberty | 2026 | 2026 | 2024.293 | 2085.022 | 2147.572
2110000096 | Vegetation Management and Inspections | Pruning and Removal |  | CAPEX | Territory | $ Thousands | WMP-VM-VFM-05, WMP-VM-VFM-06 | Contact from vegetation ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000097 | Vegetation Management and Inspections | Pruning and Removal |  | CAPEX | HFTD | $ Thousands | WMP-VM-VFM-05, WMP-VM-VFM-06 | Contact from vegetation ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000098 | Vegetation Management and Inspections | Pruning and Removal |  | OPEX | Territory | $ Thousands | WMP-VM-VFM-05, WMP-VM-VFM-06 | Contact from vegetation ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 6110.059 | 6293.361 | 6482.162
2110000099 | Vegetation Management and Inspections | Pruning and Removal |  | OPEX | HFTD | $ Thousands | WMP-VM-VFM-05, WMP-VM-VFM-06 | Contact from vegetation ignition likelihood |  | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 6110.059 | 6293.361 | 6482.162
2110000100 | Vegetation Management and Inspections | Pole Clearing |  | CAPEX | Territory | $ Thousands | WMP-VM-VFM-01 | Wildfire spread | Wildfire hazard | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451; Public Resources Code 4292 |  |  | Not applicable | Liberty | 2026 | 2026
2110000101 | Vegetation Management and Inspections | Pole Clearing |  | CAPEX | HFTD | $ Thousands | WMP-VM-VFM-01 | Wildfire spread | Wildfire hazard | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451; Public Resources Code 4292 |  |  | Not applicable | Liberty | 2026 | 2026
2110000102 | Vegetation Management and Inspections | Pole Clearing |  | OPEX | Territory | $ Thousands | WMP-VM-VFM-01 | Wildfire spread | Wildfire hazard | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451; Public Resources Code 4292 |  |  |  | Liberty | 2026 | 2026 | 493.282 | 508.08 | 523.323
2110000103 | Vegetation Management and Inspections | Pole Clearing |  | OPEX | HFTD | $ Thousands | WMP-VM-VFM-01 | Wildfire spread | Wildfire hazard | 2011 | 2025 WMP |  | In compliance | P.U. Code § 451; Public Resources Code 4292 |  |  |  | Liberty | 2026 | 2026 | 493.282 | 508.08 | 523.323
2110000104 | Vegetation Management and Inspections | Wood and Slash Management |  | CAPEX | Territory | $ Thousands | WMP-VM-VFM-02 | Wildfire spread | Wildfire hazard | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000105 | Vegetation Management and Inspections | Wood and Slash Management |  | CAPEX | HFTD | $ Thousands | WMP-VM-VFM-02 | Wildfire spread | Wildfire hazard | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000106 | Vegetation Management and Inspections | Wood and Slash Management |  | OPEX | Territory | $ Thousands | WMP-VM-VFM-02 | Wildfire spread | Wildfire hazard | 2020 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 1381.311 | 1422.75 | 1465.433
2110000107 | Vegetation Management and Inspections | Wood and Slash Management |  | OPEX | HFTD | $ Thousands | WMP-VM-VFM-02 | Wildfire spread | Wildfire hazard | 2020 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 1381.311 | 1422.75 | 1465.433
2110000108 | Vegetation Management and Inspections | Defensible Space |  | CAPEX | Territory | $ Thousands | WMP-VM-VFM-03 | Wildfire spread | Wildfire hazard | 2013 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000109 | Vegetation Management and Inspections | Defensible Space |  | CAPEX | HFTD | $ Thousands | WMP-VM-VFM-03 | Wildfire spread | Wildfire hazard | 2013 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000110 | Vegetation Management and Inspections | Defensible Space |  | OPEX | Territory | $ Thousands | WMP-VM-VFM-03 | Wildfire spread | Wildfire hazard | 2013 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 45 | 46.35 | 47.741
2110000111 | Vegetation Management and Inspections | Defensible Space |  | OPEX | HFTD | $ Thousands | WMP-VM-VFM-03 | Wildfire spread | Wildfire hazard | 2013 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 45 | 46.35 | 47.741
2110000112 | Vegetation Management and Inspections | Integrated Vegetation Management |  | CAPEX | Territory | $ Thousands | WMP-VM-VFM-04 | Wildfire spread | Wildfire hazard | 2020 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000113 | Vegetation Management and Inspections | Integrated Vegetation Management |  | CAPEX | HFTD | $ Thousands | WMP-VM-VFM-04 | Wildfire spread | Wildfire hazard | 2020 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000114 | Vegetation Management and Inspections | Integrated Vegetation Management |  | OPEX | Territory | $ Thousands | WMP-VM-VFM-04 | Wildfire spread | Wildfire hazard | 2020 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 682.863 | 703.349 | 724.449
2110000115 | Vegetation Management and Inspections | Integrated Vegetation Management |  | OPEX | HFTD | $ Thousands | WMP-VM-VFM-04 | Wildfire spread | Wildfire hazard | 2020 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 682.863 | 703.349 | 724.449
2110000116 | Vegetation Management and Inspections | Partnerships |  | CAPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000117 | Vegetation Management and Inspections | Partnerships |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000118 | Vegetation Management and Inspections | Partnerships |  | OPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000119 | Vegetation Management and Inspections | Partnerships |  | OPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000120 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | CAPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000121 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000122 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | OPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000123 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | OPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000124 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | CAPEX | Territory | $ Thousands | WMP-VM-VFM-08 | Wildfire hazard |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000125 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | CAPEX | HFTD | $ Thousands | WMP-VM-VFM-08 | Wildfire hazard |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000126 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | OPEX | Territory | $ Thousands | WMP-VM-VFM-08 | Wildfire hazard |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000127 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | OPEX | HFTD | $ Thousands | WMP-VM-VFM-08 | Wildfire hazard |  | 2021 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000128 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | CAPEX | Territory | $ Thousands | WMP-VM-QAQC-01 | Contact from vegetation ignition likelihood |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000129 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | WMP-VM-QAQC-01 | Contact from vegetation ignition likelihood |  | 2020 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000130 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | OPEX | Territory | $ Thousands | WMP-VM-QAQC-01 | Contact from vegetation ignition likelihood |  | 2020 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 500 | 515 | 530.45
2110000131 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | OPEX | HFTD | $ Thousands | WMP-VM-QAQC-01 | Contact from vegetation ignition likelihood |  | 2020 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 500 | 515 | 530.45
2110000132 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | CAPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000133 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000134 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | OPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000135 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | OPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000136 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | CAPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000137 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000138 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | OPEX | Territory | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000139 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | OPEX | HFTD | $ Thousands | [10 empty] | Not applicable | Liberty | 2026 | 2026
2110000140 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | CAPEX | Territory | $ Thousands | WMP-SA-01 | Wildfire exposure potential | PSPS exposure potential | 2019 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000141 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | CAPEX | HFTD | $ Thousands | WMP-SA-01 | Wildfire exposure potential | PSPS exposure potential | 2019 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000142 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | OPEX | Territory | $ Thousands | WMP-SA-01 | Wildfire exposure potential | PSPS exposure potential | 2019 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 96 | 96 | 96
2110000143 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | OPEX | HFTD | $ Thousands | WMP-SA-01 | Wildfire exposure potential | PSPS exposure potential | 2019 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 96 | 96 | 96
2110000144 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | CAPEX | Territory | $ Thousands | WMP-SA-02 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000145 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | CAPEX | HFTD | $ Thousands | WMP-SA-02 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000146 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | OPEX | Territory | $ Thousands | WMP-SA-02 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000147 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | OPEX | HFTD | $ Thousands | WMP-SA-02 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000148 | Situational Awareness and Forecasting | Ignition Detection Systems |  | CAPEX | Territory | $ Thousands | WMP-SA-03 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000149 | Situational Awareness and Forecasting | Ignition Detection Systems |  | CAPEX | HFTD | $ Thousands | WMP-SA-03 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000150 | Situational Awareness and Forecasting | Ignition Detection Systems |  | OPEX | Territory | $ Thousands | WMP-SA-03 | [10 empty] | Liberty | 2026 | 2026 | 250 | 250 | 250
2110000151 | Situational Awareness and Forecasting | Ignition Detection Systems |  | OPEX | HFTD | $ Thousands | WMP-SA-03 | [10 empty] | Liberty | 2026 | 2026 | 250 | 250 | 250
2110000152 | Situational Awareness and Forecasting | Weather Forecasting |  | CAPEX | Territory | $ Thousands | WMP-SA-04 | [5 empty] | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000153 | Situational Awareness and Forecasting | Weather Forecasting |  | CAPEX | HFTD | $ Thousands | WMP-SA-04 | [5 empty] | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000154 | Situational Awareness and Forecasting | Weather Forecasting |  | OPEX | Territory | $ Thousands | WMP-SA-04 | [5 empty] | In compliance | P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 90 | 90 | 90
2110000155 | Situational Awareness and Forecasting | Weather Forecasting |  | OPEX | HFTD | $ Thousands | WMP-SA-04 | [5 empty] | In compliance | P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 90 | 90 | 90
2110000156 | Situational Awareness and Forecasting | Fire Potential Index |  | CAPEX | Territory | $ Thousands | WMP-SA-05 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000157 | Situational Awareness and Forecasting | Fire Potential Index |  | CAPEX | HFTD | $ Thousands | WMP-SA-05 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000158 | Situational Awareness and Forecasting | Fire Potential Index |  | OPEX | Territory | $ Thousands | WMP-SA-05 | [10 empty] | Liberty | 2026 | 2026 | 75 | 75 | 75
2110000159 | Situational Awareness and Forecasting | Fire Potential Index |  | OPEX | HFTD | $ Thousands | WMP-SA-05 | [10 empty] | Liberty | 2026 | 2026 | 75 | 75 | 75
2110000160 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | CAPEX | Territory | $ Thousands | WMP-EP-01, WMP-EP-04 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000161 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | CAPEX | HFTD | $ Thousands | WMP-EP-01, WMP-EP-04 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000162 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | OPEX | Territory | $ Thousands | WMP-EP-01, WMP-EP-04 | [10 empty] | Liberty | 2026 | 2026 | 425 | 425 | 425
2110000163 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | OPEX | HFTD | $ Thousands | WMP-EP-01, WMP-EP-04 | [10 empty] | Liberty | 2026 | 2026 | 425 | 425 | 425
2110000164 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | CAPEX | Territory | $ Thousands | WMP-EP-02 | PSPS vulnerability | Wildfire vulnerability | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000165 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | CAPEX | HFTD | $ Thousands | WMP-EP-02 | PSPS vulnerability | Wildfire vulnerability | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000166 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | OPEX | Territory | $ Thousands | WMP-EP-02 | PSPS vulnerability | Wildfire vulnerability | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000167 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | OPEX | HFTD | $ Thousands | WMP-EP-02 | PSPS vulnerability | Wildfire vulnerability | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000168 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | CAPEX | Territory | $ Thousands | WMP-CO-01 | PSPS vulnerability | Wildfire vulnerability | 2019 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000169 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | CAPEX | HFTD | $ Thousands | WMP-CO-01 | PSPS vulnerability | Wildfire vulnerability | 2019 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  | Not applicable | Liberty | 2026 | 2026
2110000170 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | OPEX | Territory | $ Thousands | WMP-CO-01 | PSPS vulnerability | Wildfire vulnerability | 2019 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 110 | 110 | 110
2110000171 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | OPEX | HFTD | $ Thousands | WMP-CO-01 | PSPS vulnerability | Wildfire vulnerability | 2019 | 2025 WMP |  | In compliance | P.U. Code § 451 |  |  |  | Liberty | 2026 | 2026 | 110 | 110 | 110
2110000172 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | CAPEX | Territory | $ Thousands | WMP-EP-05 | PSPS vulnerability | Wildfire vulnerability | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000173 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | CAPEX | HFTD | $ Thousands | WMP-EP-05 | PSPS vulnerability | Wildfire vulnerability | 2011 | 2025 WMP | [5 empty] | Not applicable | Liberty | 2026 | 2026
2110000174 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | OPEX | Territory | $ Thousands | WMP-EP-05 | PSPS vulnerability | Wildfire vulnerability | 2011 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 90 | 90 | 90
2110000175 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | OPEX | HFTD | $ Thousands | WMP-EP-05 | PSPS vulnerability | Wildfire vulnerability | 2011 | 2025 WMP | [6 empty] | Liberty | 2026 | 2026 | 90 | 90 | 90
2110000176 | Enterprise Systems | Enterprise Systems Development |  | CAPEX | Territory | $ Thousands | WMP-VM-ESG-01 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000177 | Enterprise Systems | Enterprise Systems Development |  | CAPEX | HFTD | $ Thousands | WMP-VM-ESG-01 | [9 empty] | Not applicable | Liberty | 2026 | 2026
2110000178 | Enterprise Systems | Enterprise Systems Development |  | OPEX | Territory | $ Thousands | WMP-VM-ESG-01 | [10 empty] | Liberty | 2026 | 2026 | 843.648 | 868.957 | 895.026
2110000179 | Enterprise Systems | Enterprise Systems Development |  | OPEX | HFTD | $ Thousands | WMP-VM-ESG-01 | [10 empty] | Liberty | 2026 | 2026 | 843.648 | 868.957 | 895.026

## Table 12
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP ACTIVITY NAME | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | UTILITY MITIGATION ACTIVITY TRACKING ID | TARGET TYPE | UNIT(S) | METHOD OF VERIFICATION | COMMENTS | REPORTING YEAR | CYCLE YEAR 1 | YTD TARGET - Y1 Q2 | YTD TARGET - Y1 Q3 | YTD TARGET - Y1 Q4 | YTD TARGET - Y2 Q2 | YTD TARGET - Y2 Q3 | YTD TARGET - Y2 Q4 | YTD TARGET - Y3 Q2 | YTD TARGET - Y3 Q3 | YTD TARGET - Y3 Q4
2120000000 | Liberty | 2025-06-24 | Covered conductor installation | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-01 | Quantitative | Circuit Miles | In addition to post-work verification of projects, Liberty reports completed projects in its QDR and quarterly GIS submissions to Energy Safety. Liberty utilizes the QDR and GIS data submissions to verify accuracy and consistency in its internal asset data updates (e.g., Fulcrum and GIS) capturing WMP initiative progress. |  | 2026 | 2026 |  |  | 3.9 |  |  | 3.5 |  |  | 3.7
2120000001 | Liberty | 2025-06-24 | Undergrounding of electric lines and/or equipment | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-02 | Quantitative | Circuit Miles | See Cell K2 |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000002 | Liberty | 2025-06-24 | Distribution pole replacements and reinforcements | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-03 | Quantitative | Poles | See Cell K2 |  | 2026 | 2026 |  |  | 400 |  |  | 400 |  |  | 400
2120000003 | Liberty | 2025-06-24 | Traditional overhead hardening | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-05 | Quantitative | Circuit Miles | See Cell K2 |  | 2026 | 2026 |  |  | 1.1 |  |  | 1.1 |  |  | 1.1
2120000004 | Liberty | 2025-06-24 | Microgrids | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-07 | Quantitative | Microgrids | See Cell K2 |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000005 | Liberty | 2025-06-24 | Installation of system automation equipment | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-08 | Quantitative | Automatic Reclosers | See Cell K2 |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000006 | Liberty | 2025-06-24 | Line removal (in HFTD) | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-09 | Quantitative | Circuit Miles | See Cell K2 |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000007 | Liberty | 2025-06-24 | Tree attachment removals | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-12a | Quantitative | Tree Attachments | See Cell K2 |  | 2026 | 2026 |  |  | 60 |  |  | 60 |  |  | 60
2120000008 | Liberty | 2025-06-24 | Expulsion fuse replacement | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-12b | Quantitative | Expulsion Fuses | See Cell K2 |  | 2026 | 2026 |  |  | 500 |  |  | 500 |  |  | 500
2120000009 | Liberty | 2025-06-24 | Animal guards | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-12c | Quantitative | Animal Guards | See Cell K2 |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000010 | Liberty | 2025-06-24 | Open wire/grey wire | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP-GDOM-GH-12e | Quantitative | Circuit Miles | See Cell K2 |  | 2026 | 2026 |  |  | 5.2 |  |  | 5.2 |  |  | 5.2
2120000011 | Liberty | 2025-06-24 | Detailed inspections of distribution electric lines and equipment | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP-GDOM-AI-01 | Quantitative | Circuit Miles | See Cell K2 |  | 2026 | 2026 | 50 | 150 | 207 | 50 | 150 | 198.5 | 50 | 150 | 219.5
2120000012 | Liberty | 2025-06-24 | Intrusive pole inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP-GDOM-AI-02 | Quantitative | Poles | See Cell K2 |  | 2026 | 2026 | 0 | 2031 | 2031 | 0 | 2389 | 2389 | 0 | 2860 | 2860
2120000013 | Liberty | 2025-06-24 | Patrol inspections of distribution electric lines and equipment | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP-GDOM-AI-03 | Quantitative | Circuit Miles | See Cell K2 |  | 2026 | 2026 | 553.4 | 553.4 | 553.4 | 568.8 | 568.8 | 568.8 | 542.8 | 542.8 | 542.8
2120000014 | Liberty | 2025-06-24 | Other discretionary inspections of distribution electric lines and equipment | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP-GDOM-AI-04 | Quantitative | Circuit Miles | See Cell K2 |  | 2026 | 2026 |  |  | 1 |  |  | 1 |  |  | 1
2120000015 | Liberty | 2025-06-24 | Quality assurance / quality control of inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP-GDOM-AI-05 | Quantitative | % of Detailed Inspections | See Cell K2 |  | 2026 | 2026 | 0% | 0% | 12% | 0% | 0% | 12% | 0% | 0% | 12%
2120000016 | Liberty | 2025-06-24 | Substation inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP-GDOM-AI-06 | Quantitative | Substations | See Cell K2 |  | 2026 | 2026 | 22 | 34 | 44 | 22 | 34 | 44 | 22 | 34 | 44
2120000017 | Liberty | 2025-06-24 | Equipment maintenance and repair | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | WMP-GDOM-MR-01 | Qualitative |  | See Cell K2 |  | 2026 | 2026 |  |  | All asset inspections and repairs recorded in Asset Tracking |  |  | All asset inspections and repairs recorded in Asset Tracking |  |  | All asset inspections and repairs recorded in Asset Tracking
2120000018 | Liberty | 2025-06-24 | Equipment settings to reduce wildfire risk | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | WMP-GDOM-GO-01 | Quantitative | # of circuits with SRP | See Cell K2 |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000019 | Liberty | 2025-06-24 | Equipment settings to reduce wildfire risk | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | WMP-GDOM-GO-01 | Qualitative |  | See Cell K2 |  | 2026 | 2026 |  |  | Review settings of 1/3 of SRP circuits |  |  | Review settings of 1/3 of SRP circuits |  |  | Review settings of 1/3 of SRP circuits
2120000020 | Liberty | 2025-06-24 | Asset Management and Inspection Enterprise System | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | WMP-GDOM-GO-05 | Qualitative |  | See Cell K2 |  | 2026 | 2026 | [8 empty] | All asset inspections and repairs recorded in Asset Tracking
2120000021 | Liberty | 2025-06-24 | Vegetation Management Inspection Program - Detailed | Vegetation Management & Inspections | Vegetation Management Inspections |  | WMP-VM-INSP-01 | Quantitative | Line Miles | Liberty utilizes QC of inspections, invoice review, documentation of span inspections, schedule and plan monitoring and tracking to verify. |  | 2026 | 2026 | 110 | 165 | 220 | 110 | 165 | 220 | 110 | 165 | 220
2120000022 | Liberty | 2025-06-24 | Vegetation Management Inspection Program - Patrol | Vegetation Management & Inspections | Vegetation Management Inspections |  | WMP-VM-INSP-02 | Quantitative | Line Miles | Liberty utilizes inspection data review to verify. |  | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2120000023 | Liberty | 2025-06-24 | Vegetation Management Inspection Program - LiDar | Vegetation Management & Inspections | Vegetation Management Inspections |  | WMP-VM-INSP-03 | Quantitative | Line Miles | Liberty utilizes inspection data review to verify. |  | 2026 | 2026 | 0 | 700 | 700 | 0 | 700 | 700 | 0 | 700 | 700
2120000024 | Liberty | 2025-06-24 | Pole Clearing | Vegetation Management & Inspections | Pole Clearing |  | WMP-VM-VFM-01 | Quantitative | Subject Poles | Liberty utilizes post-work verification, completed work orders, invoice review, GIS pole and asset data updates, and field verification of poles. |  | 2026 | 2026 | 1633 | 3266 | 4900 | 1633 | 3266 | 4900 | 1633 | 3266 | 4900
2120000025 | Liberty | 2025-06-24 | Wood and Slash Management | Vegetation Management & Inspections | Wood and Slash Management |  | WMP-VM-VFM-02 | Quantitative | Acres | Liberty utilizes post-work verification, completed work orders, invoice review, and load tag reports to verify. |  | 2026 | 2026 |  |  | 280 |  |  | 280 |  |  | 280
2120000026 | Liberty | 2025-06-24 | Substation Defensible Space | Vegetation Management & Inspections | Defensible Space |  | WMP-VM-VFM-03 | Quantitative | Substation Treatments | Liberty utilizes post-work verification, completed work orders, and invoice review to verify. |  | 2026 | 2026 |  |  | 12 |  |  | 12 |  |  | 12
2120000027 | Liberty | 2025-06-24 | Fire-Resilient Right-of-Ways | Vegetation Management & Inspections | Integrated Vegetation Management |  | WMP-VM-VFM-04 | Quantitative | Line Miles | Liberty utilizes post-work verification, completed work orders, and invoice review to verify. |  | 2026 | 2026
2120000028 | Liberty | 2025-06-24 | Clearance | Vegetation Management & Inspections | Clearance |  | WMP-VM-VFM-05 | Quantitative | Line Miles | Liberty utilizes post-work verification, completed work orders, and invoice review to verify. |  | 2026 | 2026 |  |  | 700 |  |  | 700 |  |  | 700
2120000029 | Liberty | 2025-06-24 | Fall-In Mitigation | Vegetation Management & Inspections | Fall-In Mitigation |  | WMP-VM-VFM-06 | Quantitative | Line Miles | Liberty utilizes post-work verification, completed work orders, and invoice review to verify. |  | 2026 | 2026 |  |  | 220 |  |  | 220 |  |  | 220
2120000030 | Liberty | 2025-06-24 | High-Risk Species | Vegetation Management & Inspections | High-Risk Species |  | WMP-VM-VFM-07 | Quantitative | Line Miles | Liberty utilizes post-work verification, completed work orders, and invoice review to verify. |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000031 | Liberty | 2025-06-24 | Emergency Response Vegetation Management | Vegetation Management & Inspections | Emergency Response Vegetation Management |  | WMP-VM-VFM-08 | Quantitative | Line Miles | Liberty utilizes post-work verification, completed work orders, and invoice review to verify. |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000032 | Liberty | 2025-06-24 | Vegetation Management Enterprise System | Vegetation Management & Inspections | Vegetation Management Enterprise System |  | WMP-VM-ESG-01 | Qualitative |  |  |  | 2026 | 2026 | [8 empty] | Automatic DQM Reporting on Liberty’s SQL database
2120000033 | Liberty | 2025-06-24 | Quality Assurance and Quality Control | Vegetation Management & Inspections | Quality Assurance and Quality Control |  | WMP-VM-QAQC-01 | Quantitative | Line Miles | Liberty utilizes QC inspection data, invoice review, scheduling of QC activities to align with maintenance work to verify. |  | 2026 | 2026 |  |  | 228 |  |  | 228 |  |  | 228
2120000034 | Liberty | 2025-06-24 | Environmental monitoring systems | Situational Awareness & Forecasting | Environmental monitoring systems |  | WMP-SA-01 | Quantitative | Weather Stations | See Cell K2 |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000035 | Liberty | 2025-06-24 | Grid monitoring systems | Situational Awareness & Forecasting | Grid monitoring systems |  | WMP-SA-02 | Quantitative | Circuits with Fault Indicators | See Cell K2 |  | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 0
2120000036 | Liberty | 2025-06-24 | Collaboration and coordination with public safety partners | Emergency Preparedness | Collaboration and coordination with public safety partners |  | WMP-EP-02 | Qualitative |  | Liberty utilizes a communications tracker to track all WMP outreach. |  | 2026 | 2026 |  |  | Conduct emergency drills; engagement with PSPs, meetings with community advisory boards. |  |  | Conduct emergency drills; engagement with PSPs, meetings with community advisory boards. |  |  | Conduct emergency drills; engagement with PSPs, meetings with community advisory boards.
2120000037 | Liberty | 2025-06-24 | Customer support in wildfire and PSPS emergencies | Emergency Preparedness | Customer support in wildfire and PSPS emergencies |  | WMP-EP-05 | Qualitative |  | Liberty utilizes after action reports to verify exercise and planning meetings. |  | 2026 | 2026 |  |  | Conduct IC training; hold tabletop PSPS exercise; implement AFN plan; maintain emergency response plans |  |  | Conduct IC training; hold tabletop PSPS exercise; implement AFN plan; maintain emergency response plans |  |  | Conduct IC training; hold tabletop PSPS exercise; implement AFN plan; maintain emergency response plans
2120000038 | Liberty | 2025-06-24 | Learning after wildfire and PSPS events | Emergency Preparedness | Learning after wildfire and PSPS events |  | WMP-EP-06 | Qualitative |  | Liberty utilizes after action reports to verify exercise and planning meetings. |  | 2026 | 2026 |  |  | Produce After Action Reports for each event |  |  | Produce After Action Reports for each event |  |  | Produce After Action Reports for each event
2120000039 | Liberty | 2025-06-24 | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management |  | WMP-CO-01 | Qualitative |  | Survey results. |  | 2026 | 2026 |  |  | Two wildfire and PSPS outreach surveys |  |  | Two wildfire and PSPS outreach surveys |  |  | Two wildfire and PSPS outreach surveys
2120000040 | Liberty | 2025-06-24 | Engagement with AFN populations, local governments, and tribal communities | Community Outreach and Engagement | Engagement with AFN populations, local governments, and tribal communities |  | WMP-CO-03 | Qualitative |  | Liberty utilizes a communications tracker to track all WMP outreach. |  | 2026 | 2026 |  |  | 9 Events |  |  | 9 Events |  |  | 9 Events
2120000041 | Liberty | 2025-06-24 | Best practice sharing with other electrical corporations | Community Outreach and Engagement | Best practice sharing with other electrical corporations |  | WMP-CO-05 | Qualitative |  | Liberty utilizes a communications tracker to track all WMP outreach. |  | 2026 | 2026 |  |  | Participation in working groups and Joint IOU Councils |  |  | Participation in working groups and Joint IOU Councils |  |  | Participation in working groups and Joint IOU Councils

## Table 14
METRIC NUMBER | HFTD TIER | LINE TYPE | OVERALL UTILITY RISK | WILDFIRE RISK | OUTAGE PROGRAM RISK | WILDFIRE LIKELIHOOD | IGNITION LIKELIHOOD | EQUIPMENT CAUSED LIKELIHOOD OF IGNITION | CONTACT FROM VEGETATION LIKELIHOOD OF IGNITION | CONTACT FROM OBJECT LIKELIHOOD OF IGNITION | BURN LIKELIHOOD | WILDFIRE CONSEQUENCE | WILDFIRE HAZARD INTENSITY | WILDFIRE EXPOSURE POTENTIAL | PSPS RISK | PSPS LIKELIHOOD | PSPS CONSEQUENCE | PSPS EXPOSURE POTENTIAL | PSPS VULNERABILITY | PEDS RISK | PEDS LIKELIHOOD | PEDS CONSEQUENCE | PEDS EXPOSURE POTENTIAL | PEDS VULNERABILITY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR
2140000000 | HFTD Tier 2 | Distribution | Calculated at circuit level | 0.00390659047639995 | Calculated at circuit level | 0.256657873652546 | 0.567442270054166 | pole | 1.76206467594147 | not in DRAT | 74.4456714408866 | 0.0111064672519403 | 1.17665764968749 | 4.92750630019244 | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level |  |  | Liberty | 2026
2140000001 | HFTD Tier 3 | Distribution | Calculated at circuit level | 0.0101827861751106 | Calculated at circuit level | 0.306806758532826 | 0.657265078956549 | conductor | 2 | not in DRAT | 48.6613980266299 | 0.0259310495124603 | 3.9923265724354 | 14.692581049335 | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level |  |  | Liberty | 2026
2140000002 | HFTD Tier 2 | Transmision | Calculated at circuit level | 0.00431822708760387 | Calculated at circuit level | 0.269184919741298 | 0.635241010754223 | pole | 1.86138807429125 | not in DRAT | 132.35319683773 | 0.0124352411633137 | 0.581173846041103 | 5.05033396871954 | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level |  |  | Liberty | 2026
2140000003 | HFTD Tier 3 | Transmision | Calculated at circuit level | 0.00439366101826431 | Calculated at circuit level | 0.341508268276633 | 0.649513449513455 | pole | 1.96507936507936 | not in DRAT | 92.8570861904766 | 0.0102361915040212 | 1.11040338095238 | 3.08455714285714 | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level |  |  | Liberty | 2026
2140000004 | Non-HFTD | Distribution | Calculated at circuit level | 0.00409103332026947 | Calculated at circuit level | 0.354682306660395 | 0.720929468620555 | pole | 1.70099490445792 | not in DRAT | 95.5759034872603 | 0.00936800679084409 | 0.712946219745242 | 3.17469976114648 | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level |  |  | Liberty | 2026
2140000005 | Non-HFTD | Transmision | Calculated at circuit level | 0.0126072607732662 | Calculated at circuit level | 0.42553000000002 | 0.6900574980575 | pole | 1.584 | not in DRAT | 224.00147219999 | 0.0204391670839383 | 1.43250099000001 | 6.43525 | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level | Calculated at circuit level |  |  | Liberty | 2026

## Table 15
METRIC NUMBER | TOP-RISK CIRCUIT / SEGMENT / SPAN ID | RISK GRANULARITY | LINE TYPE | CIRCUIT / SEGMENT / SPAN LENGTH (MI) | INCLUSION REASON | HFTD TIER | OVERALL UTILITY RISK | WILDFIRE RISK | OUTAGE PROGRAM RISK | WILDFIRE LIKELIHOOD | IGNITION LIKELIHOOD | EQUIPMENT CAUSED LIKELIHOOD OF IGNITION | CONTACT FROM VEGETATION LIKELIHOOD OF IGNITION | CONTACT FROM OBJECT LIKELIHOOD OF IGNITION | BURN LIKELIHOOD | WILDFIRE CONSEQUENCE | WILDFIRE HAZARD INTENSITY | WILDFIRE EXPOSURE POTENTIAL | PSPS RISK | PSPS LIKELIHOOD | PSPS CONSEQUENCE | PSPS EXPOSURE POTENTIAL | PSPS VULNERABILITY | PEDS RISK | PEDS LIKELIHOOD | PEDS CONSEQUENCE | PEDS EXPOSURE POTENTIAL | PEDS VULNERABILITY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR
2150000000 | CEM41 | Circuit | Distribution | 13.2 | Top 5% Overall Risk | 0, 2 | 0 | 3.3591e-06 | 0 | 0.00024158 | 0.742 | Pole | 1.7 | not in XY | 0.05 | 0.01 | 0.0050257 | 0.0026751 | 0.0016 | 0.04 | 0.04 | 48755.24 | 1.81 | 0 | 0.04 | 0.03 | 10272.95 | 0.38 |  |  | Liberty | 2026
2150000001 | MEY3400 | Circuit | Distribution | 143.6 | Top 5% Overall Risk | 0, 2, 3 | 0.11 | 4.9899e-06 | 0.21 | 0.00040013 | 0.61226 | Pole | 2 | not in XY | 0.01 | 0.01 | 0.016217 | 0.011199 | 0.22 | 0.38 | 0.57 | 600662.18 | 1653.09 | 0.21 | 0.38 | 0.56 | 134765.11 | 370.89 |  |  | Liberty | 2027
2150000002 | Muller1296 | Circuit | Distribution | 78.2 | Top 5% Overall Risk | 0, 2, 3 | 0.02 | 2.2592e-06 | 0.03 | 0.00048126 | 0.73964 | Pole | 1.65 | not in XY | 0.02 | 0 | 0.001526 | 0.00091187 | 0.04 | 0.46 | 0.09 | 110786.13 | 19.99 | 0.02 | 0.27 | 0.09 | 25024.29 | 4.51 |  |  | Liberty | 2028
2150000003 | Topaz1202 | Circuit | Distribution | 84 | Top 5% Overall Risk | 0, 2, 3 | 0.03 | 4.5306e-06 | 0.05 | 0.00051162 | 0.7824 | Pole | 1.35 | not in XY | 0.02 | 0.01 | 0.0058951 | 0.0033496 | 0.07 | 0.68 | 0.1 | 125450.48 | 31.11 | 0.02 | 0.26 | 0.09 | 27497.76 | 6.82 |  |  | Liberty | 2029