## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | ANNUAL QUANTITATIVE TARGET | PROJECTED QUANTITATIVE PROGRESS Q1 | PROJECTED QUANTITATIVE PROGRESS Q1-2 | PROJECTED QUANTITATIVE PROGRESS Q1-3 | PROJECTED QUANTITATIVE PROGRESS Q1-4 | ANNUAL QUALITATIVE TARGET
2010000000 | SDG&E | 2025-07-18 | Program |  |  | Risk Methodology and Assessment | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment (WiNGS) | Enhance WiNGS Visualization Platform | Risk Methodology and Assessment | Risk Methodology and Assessment |  | 05 | WMP.0442 | SDG&E_Risk Methodology and Assessment_Risk Methodology and Assessment_WMP.0442_2026 | 80 | Wildfire spread Wildfire hazard Wildfire exposure potential Wildfire vulnerability PSPS likelihood PSPS exposure potential PSPS vulnerability | No |  | WMP.0442-Risk Methodology and Assessment | 2026 | [5 empty] | By 12/31/2026: Continue enhancing the visualization platform to facilitate quick and easy access to reliable data to inform de-energization and mitigation investment planning decisions, faster initial loads and overall stability of the platform. Identify potential enhancements for existing features to elevate user experience and facilitate efficient risk information transfer.
2010000001 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Covered conductor installation | See Column I | Covered conductor utilizes conductors manufactured with an internal semiconducting layer and external insulating ultraviolet-resistant layer to provide incidental contact protection. The Covered Conductor program has the potential to raise the threshold for PSPS events to higher wind speeds compared to bare conductor. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.01 | WMP.0455 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0455_2026 | 149 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | No | Miles | WMP.0455-Combined Covered Conductor | 2026 | 50 |  |  |  | 50
2010000002 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Undergrounding of electric lines and/or equipment | See Column I | Strategic undergrounding converts overhead systems to underground, providing the dual benefits of nearly eliminating the risk of utility-caused wildfire and the need for PSPS events in these areas. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.02 | WMP.0473 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0473_2026 | 150 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition | No | Miles | WMP.0473-Strategic Undergrounding | 2026 | 0 |  |  |  | 0
2010000003 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Traditional overhead hardening | See Column I | Bare Conductor Hardening includes the replacement of wood poles with steel, replacement of conductor with high-strength bare conductor, and in some cases permanent removal of overhead facilities. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.05 | WMP.0475 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0475_2026 | 155 | Equipment ignition likelihood | No | Miles | WMP.0475-Distribution Overhead System Hardening | 2026 | 6.53 |  |  |  | 6.53
2010000004 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Traditional overhead hardening | See Column I | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.05 | WMP.0543 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0543_2026 | 156 | Equipment ignition likelihood | No | Miles | WMP.0543-Transmission Overhead Hardening | 2026 | 6.02 |  |  |  | 6.02
2010000005 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Traditional overhead hardening | See Column I | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.05 | WMP.0545 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0545_2026 | 156 | Equipment ignition likelihood | No | Miles | WMP.0545-Transmission Overhead Hardening (Distribution Underbuild) | 2026 | 1.2 |  |  |  | 1.2
2010000006 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Microgrids | See Column I | Microgrid backup generation and battery storage to reduce the impact of PSPS. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.07 | WMP.0462 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0462_2026 | 158 | PSPS vulnerability | No | Microgrids | WMP.0462-Microgrids | 2026 | 0 |  |  |  | 0
2010000007 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Installation of system automation equipment | See Column I | Advanced Protection creates higher visibility and situational awareness in fire-prone areas, and allow for the implementation of new relay and automation standards in locations where protection coordination is difficult due to lower fault currents attributed to high impedance faults. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.08 | WMP.0463 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0463_2026 | 159 | Equipment ignition likelihood | No | Nodes | WMP.0463-Advanced Protection | 2026 | 30 |  |  |  | 30
2010000008 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Other grid topology improvements to minimize risk of ignitions | See Column I | Strategic Pole Remediation targets high-risk poles located throughout the service territory that are gas treated (also known as Cellon treatment) and are set in concrete and steel reinforced, steel reinforced and set in soil, or set in soil, and are not being address by other programs such as Covered Conductor Hardening or Strategic Undergrounding. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.10 | WMP.1189 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.1189_2026 | 153 | Equipment ignition likelihood | No | Poles | WMP.1189-Strategic Pole Remediation | 2026 | 200 |  |  |  | 200
2010000009 | SDG&E | 2025-07-18 | Project | 2020-07-01 | 2028-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See Column I | Provide rebates on backup power solutions for eligible customers in the high fire threat district. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.11 | WMP.0467 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0467_2026 | 165 | PSPS vulnerability | No |  | WMP.0467-Generator Assistance Program | 2026 | [5 empty] | By 12/31/2026, enable rebates for backup power solutions for eligible customers.
2010000010 | SDG&E | 2025-07-18 | Project | 2020-07-01 | 2028-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See Column I | Assess and enable resiliency and backup power solutions for eligible non-residential customers in the high fire threat district. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.11 | WMP.0468 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0468_2026 | 164 | PSPS vulnerability | No | Generators | WMP.0468-Standby Power Program (Fixed Backup Power Commercial) | 2026 | [5 empty] | By 12/31/2026, enable backup power solutions of priority sites.
2010000011 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See Column I | PSPS Sectionalizing Enhancement Program installs switches in strategic locations, improving the ability to isolate high-risk areas for potential de energization. For example, switches are installed on circuits that have significant sections undergrounded, allowing customers with this lower-risk infrastructure to remain energized during weather events. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.11 | WMP.0461 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.0461_2026 | 162 | PSPS exposure potential PSPS vulnerability | No | Switches | WMP.0461-PSPS Sectionalizing Enhancements | 2026 | 7 |  |  |  | 7
2010000012 | SDG&E | 2025-07-18 | Project | 2026-01-01 | 2028-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See Column I | Assess and enable resiliency and backup power solutions for eligible residential customers in the high fire threat district. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 08.02.11 | WMP.1432 | SDG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_WMP.1432_2026 | 164 | PSPS vulnerability | No |  | WMP.1432-Customized Resiliancy Assessments | 2026 | [5 empty] | By 12/31/2026, offer resiliency support for eligible customers.
2010000013 | SDG&E | 2025-07-18 | Program |  |  | Distribution Overhead Detailed Inspections | See Column I | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.0478 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.0478_2026 | 171 | Equipment ignition likelihood | Yes | Structures | WMP.0478-Distribution Overhead Detailed Inspections | 2026 | 21924 | 5481 | 10962 | 16443 | 21924
2010000014 | SDG&E | 2025-07-18 | Program |  |  | Distribution Overhead Patrol Inspections | See Column I | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.0488 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.0488_2026 | 184 | Equipment ignition likelihood | Yes | Structures | WMP.0488-Distribution Overhead Patrol Inspections | 2026 | 84678 | 21170 | 42340 | 63510 | 84678
2010000015 | SDG&E | 2025-07-18 | Program |  |  | Distribution Wood Pole Intrusive Inspections | See Column I | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.0483 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.0483_2026 | 177 | Equipment ignition likelihood | Yes | Structures | WMP.0483-Distribution Wood Pole Intrusive Inspections | 2026 | 1214 | 303 | 606 | 909 | 1214
2010000016 | SDG&E | 2025-07-18 | Program |  |  | Risk-Informed Drone Inspections | See Column I | Perform drone inspections on highest risk structures in the HFTD and WUI areas. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.0552 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.0552_2026 | 180 | Equipment ignition likelihood | Yes | Structures | WMP.0552-Risk-Informed Drone Inspections | 2026 | 9000 | 2250 | 4500 | 6750 | 9000
2010000017 | SDG&E | 2025-07-18 | Program |  |  | Substation Patrol Inspections | See Column I | Perform substation patrols, as scheduled, to reduce the risk of equipment failure and to manage vegetation hazards within the substation. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.0492 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.0492_2026 | 188 | Equipment ignition likelihood | Yes | Substations | WMP.0492-Substation Patrol Inspections | 2026 | 381 | 90 | 192 | 282 | 381
2010000018 | SDG&E | 2025-07-18 | Program |  |  | Transmission Infrared Inspections | See Column I | Perform infrared inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.0482 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.0482_2026 | 175 | Equipment ignition likelihood | Yes | Structures | WMP.0482-Transmission Infrared Inspections | 2026 | 7294 | 0 | 0 | 7294 | 7294
2010000019 | SDG&E | 2025-07-18 | Program |  |  | Transmission Overhead Patrol Inspections | See Column I | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.0489 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.0489_2026 | 186 | Equipment ignition likelihood | Yes | Structures | WMP.0489-Transmission Overhead Patrol Inspections | 2026 | 7454 | 7121 | 7121 | 7121 | 7454
2010000020 | SDG&E | 2025-07-18 | Program |  |  | Transmission Wood Pole Intrusive Inspections | See Column I | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.1190 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.1190_2026 | 179 | Equipment ignition likelihood | Yes | Structures | WMP.1190-Transmission Wood Pole Intrusive Inspections | 2026 | 68 | 17 | 34 | 51 | 68
2010000021 | SDG&E | 2025-07-18 | Program |  |  | Transmisson Overhead Detailed Inspections | See Column I | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.0479 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.0479_2026 | 173 | Equipment ignition likelihood | Yes | Structures | WMP.0479-Transmisson Overhead Detailed Inspections | 2026 | 2447 | 433 | 917 | 1685 | 2447
2010000022 | SDG&E | 2025-07-18 | Program |  |  | Transmission Switch Inspections | See Column I | Evaluate transmission switches in the HFTD to verify functionality, identify potential issues, and determine if repair or replacement is needed | Grid Design, Operations, and Maintenance | Asset Inspections |  | 08.03 | WMP.1509 | SDG&E_Grid Design, Operations, and Maintenance_Asset Inspections_WMP.1509_2026 | 190 | Equipment ignition likelihood | Yes | Switches | WMP.1509-Transmission Switch Inspection | 2026 | 3 | 0 | 0 | 0 | 3
2010000023 | SDG&E | 2025-07-18 | Program |  |  | Transmission Asset Health | See Column I | Analyze asset heath for transmission shield wire, insulators, and hardware; explore proactive replacement strategies | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | 08.04 | WMP.1458 | SDG&E_Grid Design, Operations, and Maintenance_Equipment Maintenance and Repair_WMP.1458_2026 | 145 | Equipment ignition likelihood | No |  | WMP.1458-Transmission Asset Health | 2026 | [5 empty] | By 12/31/2026, begin data analysis of asset health, current condition, and outage history of transmission equipment
2010000024 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Transmission Inspections | See Column I | Ensure inspections are following SDG&E’s procedures for inspections | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1191 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1191_2026 | 200 | Equipment ignition likelihood | No | Findings | WMP.1191-Quality Assurance / Quality Control of Transmission Inspections | 2026 | 100% |  |  |  | 100%
2010000025 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Corrective Maintenance Program | See Column I | Ensure SDG&E repair procedures are being adhered to | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1434 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1434_2026 | 200 | Equipment ignition likelihood | No | OH Fire or Safety Related Corrective Actions | WMP.1434-Quality Assurance / Quality Control of Corrective Maintenance Program | 2026 | 1% |  |  |  | 1%
2010000026 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Distribution Detailed Inspections | See Column I | Ensure SDG&E inspection procedures are being adhered to | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.0491 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.0491_2026 | 200 | Equipment ignition likelihood | No | Findings | WMP.0491-Quality Assurance / Quality Control of Distribution Detailed Inspections | 2026 | 50% |  |  |  | 50%
2010000027 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of PSPS Sectionalizing Enhancement Program | See Column I | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1435 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1435_2026 | 200 | Equipment ignition likelihood | No | Switches | WMP.1435-Quality assurance/quality control of PSPS Sectionalizing Enhancement Program | 2026 | 95% |  |  |  | 95%
2010000028 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Advanced Protection Program | See Column I | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1496 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1496_2026 | 200 | Equipment ignition likelihood | No | Nodes | WMP.1496-Quality assurance/quality control of Advanced Protection Program | 2026 | 95% |  |  |  | 95%
2010000029 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Strategic Undergrounding Program | See Column I | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1497 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1497_2026 | 200 | Equipment ignition likelihood | No | Miles | WMP.1497-Quality assurance/quality control of Strategic Undergrounding Program | 2026 | 95% |  |  |  | 95%
2010000030 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Distribution Overhead System Hardening Program | See Column I | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1498 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1498_2026 | 200 | Equipment ignition likelihood | No | Miles | WMP.1498-Quality assurance/quality control of Distribution Overhead System Hardening Program | 2026 | 95% |  |  |  | 95%
2010000031 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Transmission Overhead Hardening | See Column I | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1499 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1499_2026 | 200 | Equipment ignition likelihood | No | Miles | WMP.1499-Quality assurance/quality control of Transmission Overhead Hardening | 2026 | 95% |  |  |  | 95%
2010000032 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild) | See Column I | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1500 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1500_2026 | 200 | Equipment ignition likelihood | No | Miles | WMP.1500-Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild) | 2026 | 95% |  |  |  | 95%
2010000033 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/ quality control of Combined Covered Conductor | See Column I | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1508 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1508_2026 | 200 | Equipment ignition likelihood | No | Miles | WMP.1508-Quality assurance/ quality control of Combined Covered Conductor | 2026 | 95% |  |  |  | 95%
2010000034 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Risk Informed Drone Inspections | See Column I | Ensure SDG&E inspection procedures are being adhered to | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1192 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1192_2026 | 200 | Equipment ignition likelihood | No | Drone Inspections | WMP.1192-Quality Assurance / Quality Control of Risk Informed Drone Inspections | 2026 | 15% |  |  |  | 15%
2010000035 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Substation Inspections | See Column I | Ensure SDG&E substation inspection procedures and checklists are being adhered to | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1194 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1194_2026 | 200 | Equipment ignition likelihood | No | Findings | WMP.1194-Quality Assurance / Quality Control of Substation Inspections | 2026 | 18 |  |  |  | 18
2010000036 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution) | See Column I | Ensure SDG&E inspection procedures are being adhered to | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1193 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1193_2026 | 200 | Equipment ignition likelihood | No | Intrusive Inspections | WMP.1193-Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution) | 2026 | 5% |  |  |  | 5%
2010000037 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Transmission Switch Inspections | See Column I | Ensure inspections are following SDG&E’s procedures for inspections | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 08.05 | WMP.1510 | SDG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_WMP.1510_2026 | 200 | Equipment ignition likelihood | No | Switch Function Inspections | WMP.1510-Quality Assurance / Quality Control of Transmission Switch Inspections | 2026 | 100% |  |  |  | 100%
2010000038 | SDG&E | 2025-07-18 | Program |  |  | Corrective Maintenance Program | See Column I | Repair wildfire-related conditions within established timeframes | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | 08.06 | WMP.1433 | SDG&E_Grid Design, Operations, and Maintenance_Work Orders (Asset Management)_WMP.1433_2026 | 167 | Equipment ignition likelihood | No |  | WMP.1433-Corrective Maintenance Program | 2026 | [5 empty] | By 12/31/2026, complete repairs within timeframes
2010000039 | SDG&E | 2025-07-18 | Program |  |  | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | See Column I | Examine electric line crew training and incorporate updates annually | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | 08.07.03 | WMP.1452 | SDG&E_Grid Design, Operations, and Maintenance_Grid Operations and Procedures_WMP.1452_2026 | 145 | Equipment ignition likelihood | No |  | WMP.1452-Personnel Training | 2026 | [5 empty] | By 12/31/2026, update electric line crew training
2010000040 | SDG&E | 2025-07-18 | Program |  |  | Workforce Planning (Asset Management) | See Column I | Consult with subject matter experts update the Storm and PSPS curriculum. | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | 08.08 | WMP.1453 | SDG&E_Grid Design, Operations, and Maintenance_Workforce Planning (Asset Management)_WMP.1453_2026 | 145 | Equipment ignition likelihood | No |  | WMP.1453-Workforce Planning (Asset Management) | 2026 | [5 empty] | By 12/31/2026, update Storm and PSPS training with lessons learned.
2010000041 | SDG&E | 2025-07-18 | Program |  |  | Detailed Inspections | See Column I | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation Management and Inspections | Vegetation Management Inspections |  | 09.02 | WMP.1502 | SDG&E_Vegetation Management and Inspections_Vegetation Management Inspections_WMP.1502_2026 | 236 | Wildfire hazard;Contact from vegetation ignition likelihood | No | Circuit Miles | WMP.1502-Detailed Inspections | 2026 | 10500 |  |  |  | 10500
2010000042 | SDG&E | 2025-07-18 | Program |  |  | Detailed Inspections | See Column I | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation Management and Inspections | Vegetation Management Inspections |  | 09.02 | WMP.0494 | SDG&E_Vegetation Management and Inspections_Vegetation Management Inspections_WMP.0494_2026 | 236 | Wildfire hazard;Contact from vegetation ignition likelihood | No | Trees | WMP.0494-Detailed Inspections | 2026 | 485500 |  |  |  | 485500
2010000043 | SDG&E | 2025-07-18 | Program |  |  | Off-Cycle Patrols | See Column I | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation Management and Inspections | Vegetation Management Inspections |  | 09.02 | WMP.1503 | SDG&E_Vegetation Management and Inspections_Vegetation Management Inspections_WMP.1503_2026 | 237 | Contact from vegetation ignition likelihood | No | Circuit Miles | WMP.1503-Off-Cycle Patrols | 2026 | 4850 |  |  |  | 4850
2010000044 | SDG&E | 2025-07-18 | Program |  |  | Off-Cycle Patrols | See Column I | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation Management and Inspections | Vegetation Management Inspections |  | 09.02 | WMP.0508 | SDG&E_Vegetation Management and Inspections_Vegetation Management Inspections_WMP.0508_2026 | 237 | Contact from vegetation ignition likelihood | No | VMAs | WMP.0508-Off-Cycle Patrols | 2026 | 106 |  |  |  | 106
2010000045 | SDG&E | 2025-07-18 | Program |  |  | Pole Clearing | See Column I | Pole brushing is a fire prevention measure involving the removal of vegetation at the base of poles that carry specific types of electrical hardware that could cause sparking or molten material to fall to the ground. | Vegetation Management and Inspections | Pole Clearing |  | 09.04 | WMP.1504 | SDG&E_Vegetation Management and Inspections_Pole Clearing_WMP.1504_2026 | 240 | Wildfire hazard;Contact from vegetation ignition likelihood | No | Circuit Miles | WMP.1504-Pole Clearing | 2026 | 1500 |  |  |  | 1500
2010000046 | SDG&E | 2025-07-18 | Program |  |  | Pole Clearing | See Column I | Pole brushing is a fire prevention measure involving the removal of vegetation at the base of poles that carry specific types of electrical hardware that could cause sparking or molten material to fall to the ground. | Vegetation Management and Inspections | Pole Clearing |  | 09.04 | WMP.0512 | SDG&E_Vegetation Management and Inspections_Pole Clearing_WMP.0512_2026 | 240 | Wildfire hazard;Contact from vegetation ignition likelihood | No | Poles Cleared | WMP.0512-Pole Clearing | 2026 | 22000 |  |  |  | 22000
2010000047 | SDG&E | 2025-07-18 | Project | 2026-01-01 | 2028-12-31 | Sustainability | See Column I | As part of the company sustainability goal, SDG&E will explore additional options of diverting green waste from landfills to recycling facilities. | Vegetation Management and Inspections | Wood and Slash Management |  | 09.05 | WMP.1460 | SDG&E_Vegetation Management and Inspections_Wood and Slash Management_WMP.1460_2026 | 241 | Contact from vegetation ignition likelihood | No |  | WMP.1460-Sustainability | 2026 | [5 empty] | By year end, engage Supply Management Department to research prospective recycling vendors.
2010000048 | SDG&E | 2025-07-18 | Program |  |  | Fuels Management | See Column I | Wildland fuel reduction involves the thinning, pruning, and in some cases, removal of vegetation for the purpose of minimizing source material that could ignite and propagate a wildfire. | Vegetation Management and Inspections | Integrated Vegetation Management |  | 09.07 | WMP.0497 | SDG&E_Vegetation Management and Inspections_Integrated Vegetation Management_WMP.0497_2026 | 242 | Contact from vegetation ignition likelihood | No | Poles Cleared | WMP.0497-Fuels Management | 2026 | 500 |  |  |  | 500
2010000049 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Vegetation Management | See Column I | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 09.11 | WMP.1493 | SDG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_WMP.1493_2026 | 250 | Contact from vegetation ignition likelihood | No | Circuit Miles | WMP.1493-Quality Assurance / Quality Control of Vegetation Management | 2026 | 2800 |  |  |  | 2800
2010000050 | SDG&E | 2025-07-18 | Program |  |  | Quality Assurance / Quality Control of Vegetation Management | See Column I | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 09.11 | WMP.1505 | SDG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_WMP.1505_2026 | 250 | Contact from vegetation ignition likelihood | No | Inspections | WMP.1505-Quality assurance/quality control of Vegetation Management | 2026 | 72825 |  |  |  | 72825
2010000051 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Prune and Removal | See Column I | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 09.11 | WMP.1494 | SDG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_WMP.1494_2026 | 250 | Contact from vegetation ignition likelihood | No | Circuit Miles | WMP.1494-Quality assurance/quality control of Prune and Removal | 2026 | 15% |  |  |  | 15%
2010000052 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Prune and Removal | See Column I | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 09.11 | WMP.1506 | SDG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_WMP.1506_2026 | 250 | Contact from vegetation ignition likelihood | No | Trees trimmed/removed | WMP.1506-Quality assurance/quality control of Prune and Removal | 2026 | 15% |  |  |  | 15%
2010000053 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Pole Clearing | See Column I | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 09.11 | WMP.1495 | SDG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_WMP.1495_2026 | 250 | Contact from vegetation ignition likelihood | No | Circuit Miles | WMP.1495-Quality assurance/quality control of Pole Clearing | 2026 | 350 |  |  |  | 350
2010000054 | SDG&E | 2025-07-18 | Program |  |  | Quality assurance/quality control of Pole Clearing | See Column I | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 09.11 | WMP.1507 | SDG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_WMP.1507_2026 | 250 | Contact from vegetation ignition likelihood | No | Poles Cleared | WMP.1507-Quality assurance/quality control of Pole Clearing | 2026 | 3300 |  |  |  | 3300
2010000055 | SDG&E | 2025-07-18 | Program |  |  | Workforce Planning (Vegetation Management) | See Column I | Manage vegetation management workforce through qualification and certification requirements. | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | 09.13 | WMP.0506 | SDG&E_Vegetation Management and Inspections_Workforce Planning (Vegetation Management)_WMP.0506_2026 | 258 | Contact from vegetation ignition likelihood | No |  | WMP.0506-Workforce Planning (Vegetation Management) | 2026 | [5 empty] | By year end, manage Vegetation Management workforce through the validation of required, annual contractor training including fire preparedness, hazard tree assessment, environmental, and customer service. Track training completion of internal staff for the Company’s Environmental & Safety Compliance Management Program (ESCMP) addressing compliance requirements, all applicable environmental, health and safety laws, rules, and regulations, and company standards. Validate internal and company workforce are compliant with required ISA-certification requirements of applicable job positions.
2010000056 | SDG&E | 2025-07-18 | Program |  |  | Air Quality Station Maintenance | See Column I | Air Quality Maintenance of the particulate sensors will include a scheduled monthly, quarterly, and annual inspection. Each visit will include a rigorous preventative maintenance to ensure accurate functioning of the sensors. | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | 10.02 | WMP.1431 | SDG&E_Situational Awareness and Forecasting_Environmental Monitoring Systems_WMP.1431_2026 | 266 | Wildfire exposure potential | No | Sensors | WMP.1431-Air Quality Station Maintenance | 2026 | 192 |  |  |  | 192
2010000057 | SDG&E | 2025-07-18 | Program |  |  | Weather Station Data | See Column I | Update 95th, 99th and max wind gust annually utilizing prior years weather station data. | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | 10.02 | WMP.1461 | SDG&E_Situational Awareness and Forecasting_Environmental Monitoring Systems_WMP.1461_2026 | 267 | Wildfire exposure potential | No |  | WMP.1461-Weather Station Data | 2026 | [5 empty] | By 12/31/2026, complete annual adjustments to max wind gust thresholds
2010000058 | SDG&E | 2025-07-18 | Program |  |  | Grid Monitoring Systems Data Integration | See Column I | Integrate power quality, fault data and smoke detection to enhance situational awareness and support grid reliability. | Situational Awareness and Forecasting | Grid Monitoring Systems |  | 10.03 | WMP.1444 | SDG&E_Situational Awareness and Forecasting_Grid Monitoring Systems_WMP.1444_2026 | 315 | Equipment ignition likelihood | No |  | WMP.1444-Grid Monitoring Systems Data Integration | 2026 | [5 empty] | By 12/31/2026, begin integration of power quality, fault data and smoke detection into a central monitoring system to enhance real-time monitoring, response, and prevention.
2010000059 | SDG&E | 2025-07-18 | Project | 2023-01-01 | 2028-12-31 | Early Fault Detection | See Column I | Early fault detection employs technologies such as Advance Radio Frequency Sensors (ARFS) and Power Quality (PQ) Meters to detect and prevent significant equipment failures before they occur. | Situational Awareness and Forecasting | Grid Monitoring Systems |  | 10.03 | WMP.1195 | SDG&E_Situational Awareness and Forecasting_Grid Monitoring Systems_WMP.1195_2026 | 264 | Equipment ignition likelihood | No | Nodes | WMP.1195-Early Fault Detection | 2026 | 60 |  |  |  | 60
2010000060 | SDG&E | 2025-07-18 | Program |  |  | Ignition Detection Systems - Cameras | See Column I | Ongoing review to identify camera communication network single points of failure to avoid interruption of camera imagery | Situational Awareness and Forecasting | Ignition Detection Systems |  | 10.04 | WMP.1343 | SDG&E_Situational Awareness and Forecasting_Ignition Detection Systems_WMP.1343_2026 | 273 | Wildfire vulnerability Wildfire exposure potential | No |  | WMP.1343-Ignition Detection Systems - Cameras | 2026 | [5 empty] | By 12/31/2026, complete annual monitoring of network
2010000061 | SDG&E | 2025-07-18 | Program |  |  | Quarterly validation of weekly uptime for Ignition Detection Cameras | See Column I | Quarterly validation of weekly uptime for Ignition Detection Cameras | Situational Awareness and Forecasting | Ignition Detection Systems |  | 10.04 | WMP.1467 | SDG&E_Situational Awareness and Forecasting_Ignition Detection Systems_WMP.1467_2026 | 265 | Wildfire vulnerability Wildfire exposure potential | No | Quarterly Validations | WMP.1467-Quarterly validation of weekly uptime for Ignition Detection Cameras | 2026 | 4 |  |  |  | 4
2010000062 | SDG&E | 2025-07-18 | Program |  |  | Post-processing success rate - WRF simulations | See Column I | Post-processing success rate - WRF simulations | Situational Awareness and Forecasting | Weather Forecasting |  | 10.05 | WMP.1465 | SDG&E_Situational Awareness and Forecasting_Weather Forecasting_WMP.1465_2026 | 265 | Wildfire vulnerability Wildfire exposure potential | No | Success rate | WMP.1465- Post-processing success rate - WRF simulations | 2026 | 97% |  |  |  | 97%
2010000063 | SDG&E | 2025-07-18 | Program |  |  | Weather Station Maintenance and Calibration | See Column I | Monitoring of communication success rate of weather stations | Situational Awareness and Forecasting | Weather Forecasting |  | 10.05.05 | WMP.1466 | SDG&E_Situational Awareness and Forecasting_Weather Forecasting_WMP.1466_2026 | 265 | Wildfire vulnerability Wildfire exposure potential | No |  | WMP.1466-Communication success rate of weather stations | 2026 | [5 empty] | By 12/31/2026, complete monitoring of communication success rate of weather stations
2010000064 | SDG&E | 2025-07-18 | Program |  |  | Weather Station Maintenance and Calibration | See Column I | Weather Station Maintenance and Calibration is dedicated to the maintenance and calibration of weather stations. The Weather Station Network strategically positions weather stations to transmit data on sustained wind speed, wind gust, wind direction, temperature, and humidity every 10 minutes using cellular and spread spectrum communications. | Situational Awareness and Forecasting | Weather Forecasting |  | 10.05.05 | WMP.1430 | SDG&E_Situational Awareness and Forecasting_Weather Forecasting_WMP.1430_2026 | 281 | Wildfire vulnerability Wildfire exposure potential | No | Weather Stations | WMP.1430-Weather Station Maintenance and Calibration | 2026 | 217 |  |  |  | 217
2010000065 | SDG&E | 2025-07-18 | Program |  |  | Fire potential index | See Column I | Ongoing analysis of FPI predictions versus observations to potentially improve FPI | Situational Awareness and Forecasting | Fire Potential Index |  | 10.06 | WMP.0450 | SDG&E_Situational Awareness and Forecasting_Fire Potential Index_WMP.0450_2026 | 281 | Wildfire vulnerability Wildfire exposure potential | No |  | WMP.0450-Fire potential index | 2026 | [5 empty] | By 12/31/2026, complete annual analysis
2010000066 | SDG&E | 2025-07-18 | Program |  |  | Emergency Preparedness and Recovery Plan | See Column I | Augment the CEADPP by incorporating detailed plans, concepts of operations (conops), and annexes tailored to specific identified risks. | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | 11.02 | WMP.1008 | SDG&E_Emergency Preparedness, Collaboration and Public Awareness_Emergency Preparedness and Recovery Plan_WMP.1008_2026 | 285 | PSPS exposure potential PSPS vulnerability Wildfire vulnerability Wildfire exposure potential | No |  | WMP.1008-Emergency Preparedness and Recovery Plan | 2026 | [5 empty] | By 12/31/2026 the CEADPP will be updated to incorporate applicable lessons learned from 2025 and include additional requirements as they are identified
2010000067 | SDG&E | 2025-07-18 | Program |  |  | External Collaboration and Coordination | See Column I | Enhance current collaborations and establish new ones with CBOs, public safety agencies, and government entities that deliver emergency preparedness education, response, and support services | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | 11.03 | WMP.1454 | SDG&E_Emergency Preparedness, Collaboration and Public Awareness_External Collaboration and Coordination_WMP.1454_2026 | 285 | PSPS exposure potential PSPS vulnerability Wildfire vulnerability Wildfire exposure potential | No |  | WMP.1454-External Collaboration and Coordination | 2026 | [5 empty] | By 12/13/2026, expand the CBO network to approximately 55 CBOs. Additional CBOs will target circuit segments in the HFTD that have a high number of individuals with AFN.
2010000068 | SDG&E | 2025-07-18 | Program |  |  | Public Outreach and Education Awareness | See Column I | Public Communication, Outreach, and Education - Focus on creating more meaningful and interactive engagements including proactive preparedness through community collaboration, Tribal feedback sessions, and a combination of Outreach and AFN engagement. Organize a series of Wildfire Safety Fairs and mini-Wildfire Safety Fairs aimed at educating, engaging, and preparing customers in rural communities for wildfires. Implement Wildfire/PSPS Public Education campaign leading up to when RFW are the highest. Solicit customer feedback on communications and messaging and use results to improve communications and notifications for the following year. | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | 11.04 | WMP.0527 | SDG&E_Emergency Preparedness, Collaboration and Public Awareness_Public Communication, Outreach, and Education Awareness_WMP.0527_2026 | 286 | PSPS exposure potential PSPS vulnerability Wildfire vulnerability Wildfire exposure potential | No |  | WMP.0527-Public Outreach and Education Awareness | 2026 | [5 empty] | By 12/31/2026 the Wildfire, PSPS and AFN Public Education campaigns will have concluded. Customer feedback will be gathered and used to improve communications for 2027. Host Tribal Nation learning sessions post PSPS to acquire level of satisfaction with communication and resiliency. Incorporate feedback where applicable. Continue partnerships with CBOs and AFN collaborative council for amplification of preparedness information by end of year. Host 4 Wildfire Safety Fairs and 65 mini-Wildfire Safety Fairs in key communities of concern.
2010000069 | SDG&E | 2025-07-18 | Program |  |  | Customer Support in Wildfire and PSPS Emergencies | See Column I | Enhance support and resources provided to impacted customers at Community Resource Centers. | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | 11.05 | WMP.1455 | SDG&E_Emergency Preparedness, Collaboration and Public Awareness_Customer Support in Wildfire and PSPS Emergencies_WMP.1455_2026 | 286 | PSPS exposure potential PSPS vulnerability | No |  | WMP.1455-Customer Support in Wildfire and PSPS Emergencies | 2026 | [5 empty] | By 12/31/2026 incorporate applicable lessons learned, and feedback received for Community Resource Centers.
2010000070 | SDG&E | 2025-07-18 | Program |  |  | Asset Management and Inspection Enterprise System | See Column I | Utilize advanced technology and analytics - including integrating Asset 360 and IIP data - to develop, enhance, expand risk-informed strategies, and enhance transparency for asset management | Enterprise Systems | Enterprise Systems Development |  | 12 | WMP.1457 | SDG&E_Enterprise Systems_Enterprise Systems Development_WMP.1457_2026 | 314 | Equipment ignition likelihood | No |  | WMP.1457-Asset Management and Inspection Enterprise System | 2026 | [5 empty] | By 12/31/2026, integrate advanced technology and analytics, including Asset 360 and IIP data, to develop risk-informed strategies for asset management.
2010000071 | SDG&E | 2025-07-18 | Program |  |  | Enterprise Data Foundation | See Column I | Migrate data from on-premise to the AWS Cloud | Enterprise Systems | Enterprise Systems Development |  | 12 | WMP.0519 | SDG&E_Enterprise Systems_Enterprise Systems Development_WMP.0519_2026 | 315 | Wildfire hazard | No |  | WMP.0519-Enterprise Data Foundation | 2026 | [5 empty] | By 12/31/2026: Establish data migration patterns, successfully migrate data sets including grid hardening, assets, and PSPS/risk events, and implement data validation, integrity, and governance processes to ensure quality and integrity throughout the migration journey.
2010000072 | SDG&E | 2025-07-18 | Program |  |  | Vegetation Management Enterprise System | See Column I | Enhance asset tracking, data analytics, and scheduling capabilities to more effectively manage and support Vegetation Management activities. | Enterprise Systems | Enterprise Systems Development |  | 12 | WMP.0511 | SDG&E_Enterprise Systems_Enterprise Systems Development_WMP.0511_2026 | 314 | Contact from vegetation ignition likelihood | No |  | WMP.0511-Vegetation Management Enterprise System | 2026 | [5 empty] | By mid-2026: Integrate historical meteorology data (e.g., wind gust) into PowerWorkz field application ("Epoch") as a GIS visualization tool for improved field situational awareness and decision-making. By 12/31/26: Complete update of new version of Powerworkz desktop work management application ("Cityworks") to enhance work order management and VM activity scheduling.
2010000073 | SDG&E | 2025-07-18 | Program |  |  | Vegetation Management Enterprise System - Advanced Analytics | See Column I | Advanced Analytics-Advanced analytics for proactive vegetation inspection | Enterprise Systems | Enterprise Systems Development |  | 12 | WMP.1464 | SDG&E_Enterprise Systems_Enterprise Systems Development_WMP.1464_2026 | 314 | Contact from vegetation ignition likelihood | No |  | WMP.1464-Vegetation Management Enterprise System - Advanced Analytics | 2026 | [5 empty] | By mid-2026: Complete and test v.2.0 of the Probability of Vegetation Contact (PoVC) model. Focus on model tuning and testing – including field-validation surveys with vegetation management subject matter experts.•By 12/31/2026: Test v.1.0 of the Probability of Hazard (POH) model. Focus on model tuning and testing – including field-validation surveys with vegetation management subject matter experts. •By 12/31/2026: Complete phase I of Vegetation Management data migration from PowerWorkz-Oracle to AWS.

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2020000000 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2026 | 5 | 5 | 5
2020000001 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2026 | 7 | 7 | 7
2020000002 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2020000003 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders | SDG&E's metric represents tree units since data is tracked as such |  | SDG&E | 2026 | 2026 | 15703 | 15703 | 15703
2020000004 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders | SDG&E's metric represents tree units since data is tracked as such |  | SDG&E | 2026 | 2026 | 637 | 637 | 637
2020000005 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2026 | 2026 | 4237 | 4237 | 4237
2020000006 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2026 | 2026 | 59 | 59 | 59

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2030000000 | Vegetation caused ignitions in the HFTD during FPI ratings of Elevated or higher | Vegetation caused ignitions in the HFTD during FPI ratings of Elevated or higher | Mornitor vegetation mitigation effectiveness | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions |  | Ignitions |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2030000001 | Vegetation caused ignitions in the HFTD during an RFW | Vegetation caused ignitions in the HFTD during an RFW | Mornitor vegetation mitigation effectiveness | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions |  | Ignitions |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2030000002 | Equipment caused ignitions in the HFTD during FPI ratings of Elevated or higher | Equipment caused ignitions in the HFTD during FPI ratings of Elevated or higher | Mornitor overhead asset related mitigation effectiveness during high fire condition | To evaluate the performance of risk reduction from asset inspection and grid hardening during fire-prone conditions |  | Ignitions |  |  | SDG&E | 2026 | 2026 | 5 | 5 | 5
2030000003 | Equipment caused ignitions in the HFTD during an RFW | Equipment caused ignitions in the HFTD during an RFW | Mornitor overhead asset related mitigation effectiveness during high fire condition | To evaluate the performance of risk reduction from asset inspection and grid hardening during fire-prone conditions |  | Ignitions |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2030000004 | Equipment caused ignition rate in the HFTD during a High FPI rating | Equipment caused ignition rate in the HFTD during a High FPI rating | Mornitor overhead asset related mitigation effectiveness during high fire condition | To evaluate the performance of risk reduction from asset inspection and grid hardening during fire-prone conditions |  | Ignition rate |  |  | SDG&E | 2026 | 2026 | 0.03 | 0.03 | 0.03
2030000005 | Vegetation caused outages in the HFTD during an Elevated FPI | Vegetation caused outages in the HFTD during an Elevated FPI | Mornitor vegetation mitigation effectiveness | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions |  | Outages |  |  | SDG&E | 2026 | 2026 | 4 | 4 | 4
2030000006 | Vegetation caused outages in the HFTD during an RFW | Vegetation caused outages in the HFTD during an RFW | Mornitor vegetation mitigation effectiveness | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions |  | Outages |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2030000007 | Overhead faults on circuits in the HFTD during an Elevated FPI | Overhead faults on circuits in the HFTD during an Elevated FPI | Mornitor overhead asset related mitigation effectiveness during high fire condition | To evaluate the performance of risk reduction from overall mitigations during fire-prone conditions |  | Outages |  |  | SDG&E | 2026 | 2026 | 135 | 135 | 135
2030000008 | Overhead faults on circuits in the HFTD during an RFW | Overhead faults on circuits in the HFTD during an RFW | Mornitor overhead asset related mitigation effectiveness during high fire condition | To evaluate the performance of risk reduction from overall mitigations during fire-prone conditions |  | Outages |  |  | SDG&E | 2026 | 2026 | 11 | 11 | 11
2030000009 | Energized wire down events in the HFTD during an FPI of Elevated or higher | Energized wire down events in the HFTD during an FPI of Elevated or higher | Mornitor overhead asset related mitigation effectiveness during high fire condition | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions |  | Outages |  |  | SDG&E | 2026 | 2026 | 9 | 9 | 9
2030000010 | Energized wire down events in the HFTD during an RFW | Energized wire down events in the HFTD during an RFW | Mornitor overhead asset related mitigation effectiveness during high fire condition | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions |  | Outages |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2030000011 | Overhead fault rate in the HFTD during a High FPI | Overhead fault rate in the HFTD during a High FPI | Mornitor overhead asset related mitigation effectiveness during high fire condition | To evaluate the performance of risk reduction from overall mitigations during fire-prone conditions |  | Outage Rate |  |  | SDG&E | 2026 | 2026 | 0.9 | 0.9 | 0.9

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.6 | 1.6 | 1.6
2050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.6 | 3.6 | 3.6
2050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.39925 | 0.39539 | 0.39101
2050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 19 | 19 | 19
2050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 8.2 | 8.2 | 8.1357
2050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2 | 2 | 1.9703
2050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.8 | 0.8 | 0.8
2050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.2 | 1.2 | 1.2
2050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0 | 0
2050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.8 | 2.8 | 2.8
2050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.79851 | 0.79079 | 0.78202
2050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.58944 | 0.58488 | 0.57119
2050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 9.8 | 9.8 | 9.8
2050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.1116 | 2.5891 | 2.4714
2050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.5644 | 1.5462 | 1.4792
2050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.16264 | 0.12268 | 0.084349
2050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 12.3264 | 12.246 | 12.2103
2050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 4.6498 | 3.6562 | 2.9292
2050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.5035 | 3.3067 | 2.6869
2050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 4.7859 | 3.9639 | 2.955
2050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.3352 | 0 | 0
2050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.68388 | 0.31259 | 0
2050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.5953 | 1.3213 | 0.98501
2050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.25446 | 0.17346 | 0.12257
2050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.19118 | 0.1886 | 0.18745
2050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.18404 | 0.16473 | 0.13929
2050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.38237 | 0.37719 | 0.37489
2050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.76474 | 0.75439 | 0.74978
2050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.418 | 1.418 | 1.1191
2050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.70025 | 0.66396 | 0.32795
2050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.50891 | 0.50891 | 0.40713
2050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.19118 | 0.19118 | 0.19003
2050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2026
2050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.19118 | 0.19118 | 0.19003
2050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.19734 | 0.19352 | 0.19219
2050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.19956 | 0.1963 | 0.19393
2050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.4 | 0.4
2050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.39907 | 0.39593
2050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.19703
2050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.4 | 0.4
2050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.59816 | 0.59345
2050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2026
2050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 38.4 | 38.4 | 38.4
2050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 21.2017 | 21.0376 | 20.5446
2050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.4 | 1.4 | 1.4
2050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.9601 | 2.8811 | 2.8612
2050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 90.8 | 90.8 | 90.8
2050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 8.9832 | 8.8964 | 8.7978
2050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.1613 | 2.1446 | 2.0944
2050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 10.6 | 10.6 | 10.6
2050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 7.8937 | 7.6829 | 7.6298
2050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 64.8 | 64.8 | 64.8
2050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 30.4 | 30.4 | 30.1614
2050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 13.8 | 13.8 | 13.5954
2050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.8 | 2.8 | 2.8
2050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.8 | 0.8 | 0.8
2050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.2 | 3.2 | 3.2
2050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.6 | 2.6 | 2.6
2050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3 | 3 | 3
2050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 15.8 | 15.8 | 15.8
2050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 5.3899 | 5.3378 | 5.2787
2050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.1437 | 3.1194 | 3.0463
2050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.6 | 0.6
2050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.59203 | 0.57622 | 0.57223
2050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 29.4 | 29.4 | 29.4
2050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 5.53 | 4.6 | 4.39
2050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 5.48 | 5.41 | 5.18
2050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.4 | 0.4
2050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.38 | 0.38 | 0.37
2050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.65 | 0.49 | 0.34
2050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 8.41 | 8.3 | 8.25
2050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.51 | 0.21 | 0
2050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.15 | 0.1 | 0.04
2050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 19.31 | 19.05 | 18.93
2050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 6.27 | 2.61 | 0
2050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 7.62 | 6.59 | 3.53
2050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.2 | 1.2 | 1.2
2050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 32.44 | 26.87 | 20.03
2050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 4.84 | 0 | 0
2050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.72 | 1.7 | 0
2050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 22.16 | 18.35 | 13.68
2050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 6.16 | 3.24 | 0.28
2050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 4.07 | 2.78 | 1.96
2050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 16.82 | 16.6 | 16.5
2050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.92 | 0.8 | 0
2050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.64 | 1.42 | 0.76
2050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 27.91 | 27.54 | 27.37
2050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.44 | 1.84 | 1.27
2050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.02 | 1.81 | 1.53
2050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.63 | 3.58 | 3.56
2050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.02 | 0.43 | 0
2050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.2 | 1.03 | 0.55
2050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 14.53 | 14.33 | 14.25
2050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.94 | 1.23 | 0
2050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.54 | 2.2 | 1.18
2050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 19.68 | 19.68 | 15.53
2050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 8.54 | 8.1 | 4
2050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 7.89 | 7.89 | 6.31
2050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.2 | 1.2 | 1.2
2050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.76 | 0.76 | 0.76
2050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.51 | 0.5 | 0.21
2050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.15 | 0.15 | 0.09
2050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2026 | 2026
2050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2026 | 2026
2050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2026 | 2026
2050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 14.15 | 14.15 | 14.06
2050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.26 | 0.1 | 0
2050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.15 | 0.15 | 0.09
2050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.4 | 0.4
2050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.39 | 0.37 | 0.37
2050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 18.72 | 14.96 | 10.31
2050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 5.79 | 0.67 | 0
2050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 4.01 | 2.55 | 0.2
2050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.19 | 0.19 | 0.19
2050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.81 | 0.81 | 0.62
2050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2026
2050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2026
2050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.38 | 0.38 | 0.38
2050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.13 | 0.12 | 0.05
2050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.15 | 0.15 | 0.09
2050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.6 | 0.6
2050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.58 | 1.55 | 1.54
2050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.8 | 2.8 | 2.8
2050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 0.98 | 0.97
2050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.57 | 1.57 | 1.53
2050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.2 | 2.2 | 2.2
2050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.33 | 0.32 | 0.25
2050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.16 | 0.16 | 0.12
2050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.6 | 0.6
2050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.4 | 0.4
2050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2 | 2 | 2
2050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.4 | 1.4 | 1.39
2050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 0.99
2050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 20.8 | 20.8 | 20.8
2050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 11 | 10.97 | 10.88
2050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 10.6 | 10.6 | 10.44
2050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.4 | 3.4 | 3.4
2050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2026
2050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 126.8 | 126.8 | 126.8
2050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 42.21 | 41.47 | 31.99
2050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 42.03 | 42.03 | 31.83
2050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1.8 | 1.8 | 1.8
2050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.6 | 0.6
2050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 3.8 | 3.8 | 3.8
2050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2.6 | 2.59 | 2.57
2050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 2 | 2 | 1.97
2050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.6 | 0.6
2050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2026
2060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.8 | 0.8 | 0.8
2060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 1.1912 | 1.1787 | 0.85262
2060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 1.6918 | 1.6024 | 1.1949
2060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.6 | 0.6
2060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.8 | 0.8 | 0.8
2060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.8 | 0.78749 | 0.46141
2060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.096734 | 0.0072538 | 0
2060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.6 | 0.6
2060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.082672
2060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.6 | 0.6 | 0.2464
2060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2026
2060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2026
2060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2026
2060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2026
2060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2026
2060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2026
2060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.18749 | 0
2060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.096734 | 0.0072538 | 0
2060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.4 | 0.4
2060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.13012 | 0.06024 | 0
2060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.081835 | 0 | 0
2060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.023153 | 0 | 0
2060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.19709 | 0.18455 | 0.17094
2060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.36333 | 0.34552 | 0.0080312
2060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.42964 | 0.31182 | 0
2060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.17849 | 0.15779 | 0.13129
2060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.053955 | 0 | 0
2060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 1.1609 | 0.94854 | 0.3983
2060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.19709 | 0.18455 | 0.17094
2060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.1378 | 0.10946 | 0.084989
2060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.19709 | 0.18455 | 0.17094
2060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.77212 | 0.76682 | 0.75541
2060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.7378 | 0.70946 | 0.68499
2060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.081835 | 0 | 0
2060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2026
2060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2026
2060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2026
2060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2026
2060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2026
2060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2026
2060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.37849 | 0.36069 | 0.34449
2060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.053955 | 0 | 0
2060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.17849 | 0.16069 | 0.14449
2060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.053955 | 0 | 0
2060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.57849 | 0.56069 | 0.54449
2060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.053955 | 0 | 0
2060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.4 | 0.4
2060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2026
2060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.082672
2060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2026
2060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.4 | 0.4 | 0.28267
2060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0.2 | 0.2 | 0.2
2060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 391.604 | 391.604 | 391.604
2070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 2066.158 | 2066.158 | 2066.158
2070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 175.7248 | 175.7248 | 175.7248
2070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 173.086 | 173.086 | 173.086
2070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 34.832 | 34.832 | 34.832
2070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 109.2259 | 109.2259 | 109.2259
2070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 91.2495 | 91.2495 | 91.2495
2070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 83.3956 | 83.3956 | 83.3956
2070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 842.2153 | 842.2153 | 842.2153
2070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 582.6491 | 582.6491 | 582.6491
2070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 19.1544 | 19.1544 | 15.0756
2070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 142.1457 | 142.1457 | 129.5621
2070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 5.204 | 5.204 | 5.204
2070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0.098864 | 0.098864 | 0.098864
2070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 633.6656 | 633.6656 | 618.9048
2070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 756.5021 | 756.5021 | 749.1983
2070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 25.4455 | 25.4455 | 25.4455
2070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 158.9778 | 158.9778 | 158.9778
2070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 135.2849 | 135.2849 | 135.2849
2070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 292.5894 | 292.5894 | 292.5894
2070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 54.1209 | 54.1209 | 54.1209
2070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 106.8933 | 106.8933 | 106.8933
2070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 22.8058 | 22.8058 | 22.8058
2070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 32.6186 | 32.6186 | 32.6186
2070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 66.6312 | 66.6312 | 66.6312
2070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 119.5887 | 119.5887 | 119.5887
2070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 435.9298 | 435.9298 | 435.9298
2070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 23.4249 | 23.4249 | 23.4249
2070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 21.3907 | 21.3907 | 21.3907
2070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 227.9576 | 227.9576 | 227.9576
2070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 2.7641 | 2.7641 | 2.7641
2070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 15.6528 | 15.6528 | 15.6528
2070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 1926.052 | 1926.052 | 1926.052
2070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 4931.1829 | 4931.1829 | 4931.1829
2070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 603.8646 | 603.8646 | 603.8646
2070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 885.1922 | 885.1922 | 885.1922
2070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 17.8589 | 17.8589 | 17.8589
2070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 56.6038 | 56.6038 | 56.6038
2070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 763.9408 | 763.9408 | 763.9408
2070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 160.8465 | 160.8465 | 160.8465
2070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 1038.09 | 1038.09 | 1038.09
2070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 368.6827 | 368.6827 | 368.6827
2070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 5.2425 | 5.2425 | 10.9929
2070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 23.5936 | 23.5936 | 40.6264
2070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 1.3741 | 1.3741 | 1.3741
2070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 363.3181 | 363.3181 | 382.6115
2070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 201.3352 | 201.3352 | 211.085
2070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 12.0066 | 12.0066 | 12.0066
2070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 35.1403 | 35.1403 | 35.1403
2070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 25.1734 | 25.1734 | 25.1734
2070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 68.38 | 68.38 | 68.38
2070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 13.6836 | 13.6836 | 13.6836
2070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 20.608 | 20.608 | 20.608
2070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 1.9388 | 1.9388 | 1.9388
2070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 12.476 | 12.476 | 12.476
2070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 1.47 | 1.47 | 1.47
2070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 13.5125 | 13.5125 | 13.5125
2070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 8.4841 | 8.4841 | 8.4841
2070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 2.192 | 2.192 | 2.192
2070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 3.2015 | 3.2015 | 3.2015
2070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 2.1501 | 2.1501 | 2.1501
2070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 3028 | 3028 | 3028
2070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 15216 | 15216 | 15216
2070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 719 | 719 | 719
2070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 2465 | 2465 | 2465
2070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 3 | 3 | 3
2070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 135 | 135 | 135
2070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 849 | 849 | 849
2070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 350 | 350 | 350
2070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 1055 | 1055 | 1055
2070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 966 | 966 | 966
2070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 11 | 11 | 11
2070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 85 | 85 | 85
2070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 5 | 5 | 5
2070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 483 | 483 | 483
2070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 788 | 788 | 788
2070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 42 | 42 | 42
2070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2026 | 91 | 91 | 91
2070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 203663 | 203663 | 203663
2070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 894986 | 894986 | 894986
2070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 37034 | 37034 | 37034
2070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 39403 | 39403 | 39403
2070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 1001 | 1001 | 1001
2070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 1674 | 1674 | 1674
2070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 67711 | 67711 | 67711
2070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 17344 | 17344 | 17344
2070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 58807 | 58807 | 58807
2070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 23262 | 23262 | 23262
2070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 260 | 260 | 260
2070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 495 | 495 | 495
2070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 102 | 102 | 102
2070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 3 | 3 | 3
2070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 18374 | 18374 | 18374
2070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 8106 | 8106 | 8106
2070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 932 | 932 | 932
2070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2026 | 889 | 889 | 889
2070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 14747 | 14747 | 14747
2070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 93739 | 93739 | 93739
2070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 4642 | 4642 | 4642
2070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 25008 | 25008 | 25008
2070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 101 | 101 | 101
2070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 519 | 519 | 519
2070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 4329 | 4329 | 4329
2070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 2470 | 2470 | 2470
2070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 5092 | 5092 | 5092
2070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 4203 | 4203 | 4203
2070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 34 | 34 | 34
2070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 222 | 222 | 222
2070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 17 | 17 | 17
2070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 2213 | 2213 | 2213
2070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 2549 | 2549 | 2549
2070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 146 | 146 | 146
2070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2026 | 387 | 387 | 387
2070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 44905 | 44905 | 44905
2070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 301191 | 301191 | 301191
2070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 7769 | 7769 | 7769
2070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 9316 | 9316 | 9316
2070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 299 | 299 | 299
2070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 444 | 444 | 444
2070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 14446 | 14446 | 14446
2070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 5217 | 5217 | 5217
2070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 11653 | 11653 | 11653
2070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 5119 | 5119 | 5119
2070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 92 | 92 | 92
2070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 173 | 173 | 173
2070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 29 | 29 | 29
2070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 5432 | 5432 | 5432
2070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 2148 | 2148 | 2148
2070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 242 | 242 | 242
2070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2026 | 197 | 197 | 197
2070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 12 | 12 | 12
2070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 66 | 66 | 66
2070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 4 | 4 | 4
2070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 26 | 26 | 26
2070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 3 | 3 | 3
2070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 5 | 5 | 5
2070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 5 | 5 | 5
2070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 21 | 21 | 21
2070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 11 | 11 | 11
2070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 3 | 3 | 3
2070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 13 | 13 | 13
2070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 4 | 4 | 4
2070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 2 | 2 | 2
2070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 2 | 2 | 2
2070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 4 | 4 | 4
2070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 16 | 16 | 16
2070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 52 | 52 | 52
2070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 1 | 1 | 1
2070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 7 | 7 | 7
2070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 12 | 12 | 12
2070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 84 | 84 | 84
2070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 3 | 3 | 3
2070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 17 | 17 | 17

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | -4.0788
2080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | -12.5835
2080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | -14.7608
2080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | -7.3038
2080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 5.7504
2080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 17.0327
2080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 19.2934
2080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 9.7498
2080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 1 | 0 | 0
2080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | -1 | 0
2080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 3.88 | 0
2090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0.7 | 0.14
2090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 9.78 | 8.01
2090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 3.61 | 1.47
2090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0.37 | 0 | 0
2090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 6.12 | 8.91 | 0.75
2090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 11.74 | 3.52 | 0.23
2090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 21.26 | 15.82 | 10.5
2090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 2.79 | 0 | 0.8
2090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 14.63 | 4.95 | 8.12
2090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0.39899 | 0
2090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 2.3354 | 0
2090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0.88401 | 1.2822 | 0
2090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 5.1699 | 1.3402 | 0
2090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 2.2958 | 6
2090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 1.0731 | 11.3874 | 0
2090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0.092972 | 0 | 0
2090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 2 | 1 | 0
2090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0
2090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2026 | 0 | 0 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | All (regardless of WWS) | Number of events |  |  | SDG&E | 2026 | 2026 | 3.3 | 3.3 | 3.3
2100000001 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | All (regardless of WWS) | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2026 | 2026 | 201.7 | 201.7 | 201.7
2100000002 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | All (regardless of WWS) | Customer hours |  |  | SDG&E | 2026 | 2026 | 1301430.0333 | 1301430.0333 | 1301430.0333
2100000003 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | All (regardless of WWS) | Number of events |  | not applicable | SDG&E | 2026 | 2026
2100000004 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | All (regardless of WWS) | Circuit mile days |  | not applicable | SDG&E | 2026 | 2026
2100000005 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  | not applicable | SDG&E | 2026 | 2026
2100000006 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  | not applicable | SDG&E | 2026 | 2026
2100000007 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  | not applicable | SDG&E | 2026 | 2026
2100000008 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  | not applicable | SDG&E | 2026 | 2026
2100000009 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  | not applicable | SDG&E | 2026 | 2026
2100000010 | 3. Critical infrastructure impacted by PSPS | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  | not applicable | SDG&E | 2026 | 2026
2100000011 | 4. Community outreach of PSPS metrics | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  | not applicable | SDG&E | 2026 | 2026
2100000012 | 4. Community outreach of PSPS metrics | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  | not applicable | SDG&E | 2026 | 2026
2100000013 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SDG&E | 2026 | 2026 | 42866 | 42866 | 42866
2100000014 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | not applicable | SDG&E | 2026 | 2026
2100000015 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | not applicable | SDG&E | 2026 | 2026
2100000016 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | not applicable | SDG&E | 2026 | 2026
2100000017 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | not applicable | SDG&E | 2026 | 2026
2100000018 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | not applicable | SDG&E | 2026 | 2026
2100000019 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  | not applicable | SDG&E | 2026 | 2026
2100000020 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  | not applicable | SDG&E | 2026 | 2026
2100000021 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  | not applicable | SDG&E | 2026 | 2026
2100000022 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  | not applicable | SDG&E | 2026 | 2026
2100000023 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  | not applicable | SDG&E | 2026 | 2026
2100000024 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  | not applicable | SDG&E | 2026 | 2026
2100000025 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  | not applicable | SDG&E | 2026 | 2026
2100000026 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  | not applicable | SDG&E | 2026 | 2026
2100000027 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  | not applicable | SDG&E | 2026 | 2026
2100000028 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  | not applicable | SDG&E | 2026 | 2026

## Table 11
METRIC NUMBER | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY (IF BLANK THIS REFERS TO ALL ACTIVITIES UNDER THE INITIATIVE) | EXPENSE TYPE | HFTD TIER | UNIT(S) | UTILITY MITIGATION ACTIVITY TRACKING IDS | PRIMARY DRIVER TARGETED | SECONDARY DRIVERS TARGETED | YEAR INITIATED | MOST RECENT PROCEEDING | MEMORANDUM ACCOUNT | CURRENT COMPLIANCE STATUS | ASSOCIATED RULES | OTHER SPEND CATEGORY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2110000000 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | CAPEX | Territory | $ Thousands | WMP.0442 |  |  |  | 2024 GRC | WMPMA |  |  |  | WMP.0442-Risk Methodology and Assessment |  | SDG&E | 2026 | 2026 | 3974 | 3974 | 3974
2110000001 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | CAPEX | HFTD | $ Thousands | WMP.0442 |  |  |  | 2024 GRC | WMPMA |  |  |  | WMP.0442-Risk Methodology and Assessment |  | SDG&E | 2026 | 2026 | 3974 | 3974 | 3974
2110000002 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | OPEX | Territory | $ Thousands | WMP.0442 |  |  |  | 2024 GRC | WMPMA |  |  |  | WMP.0442-Risk Methodology and Assessment |  | SDG&E | 2026 | 2026 | 5927 | 6104 | 6507.5512
2110000003 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | OPEX | HFTD | $ Thousands | WMP.0442 |  |  |  | 2024 GRC | WMPMA |  |  |  | WMP.0442-Risk Methodology and Assessment |  | SDG&E | 2026 | 2026 | 5927 | 6104 | 6507.5512
2110000004 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | CAPEX | Territory | $ Thousands | WMP.0523 |  |  |  | 2024 GRC | WMPMA |  |  |  | WMP.0523-Wildfire Mitigation Strategy Development | Not Applicable | SDG&E | 2026 | 2026
2110000005 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | CAPEX | HFTD | $ Thousands | WMP.0523 |  |  |  | 2024 GRC | WMPMA |  |  |  | WMP.0523-Wildfire Mitigation Strategy Development | Not Applicable | SDG&E | 2026 | 2026
2110000006 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | OPEX | Territory | $ Thousands | WMP.0523 |  |  |  | 2024 GRC | WMPMA |  |  |  | WMP.0523-Wildfire Mitigation Strategy Development |  | SDG&E | 2026 | 2026 | 5196 | 5352 | 5792.8077
2110000007 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | OPEX | HFTD | $ Thousands | WMP.0523 |  |  |  | 2024 GRC | WMPMA |  |  |  | WMP.0523-Wildfire Mitigation Strategy Development |  | SDG&E | 2026 | 2026 | 5196 | 5352 | 5792.8077
2110000008 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | CAPEX | Territory | $ Thousands | WMP.0455 | Other contact with object | Equipment failure | 2020 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0455-Combined Covered Conductor |  | SDG&E | 2026 | 2026 | 80000 | 60000 | 38961
2110000009 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | CAPEX | HFTD | $ Thousands | WMP.0455 | Other contact with object | Equipment failure | 2020 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0455-Combined Covered Conductor |  | SDG&E | 2026 | 2026 | 80000 | 60000 | 38961
2110000010 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | OPEX | Territory | $ Thousands | WMP.0455 | Other contact with object | Equipment failure | 2020 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0455-Combined Covered Conductor |  | SDG&E | 2026 | 2026 | 1832 | 1887 | 420
2110000011 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | OPEX | HFTD | $ Thousands | WMP.0455 | Other contact with object | Equipment failure | 2020 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0455-Combined Covered Conductor |  | SDG&E | 2026 | 2026 | 1832 | 1887 | 420
2110000012 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | CAPEX | Territory | $ Thousands | WMP.0473 | Other contact with object | Equipment failure | 2019 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0473-Strategic Undergrounding |  | SDG&E | 2026 | 2026 | 1520 | 23090 | 121200
2110000013 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | CAPEX | HFTD | $ Thousands | WMP.0473 | Other contact with object | Equipment failure | 2019 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0473-Strategic Undergrounding |  | SDG&E | 2026 | 2026 | 1520 | 23090 | 121200
2110000014 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | OPEX | Territory | $ Thousands | WMP.0473 | Other contact with object | Equipment failure | 2019 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0473-Strategic Undergrounding |  | SDG&E | 2026 | 2026 | 1634 | 1671 | 1708.855
2110000015 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | OPEX | HFTD | $ Thousands | WMP.0473 | Other contact with object | Equipment failure | 2019 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0473-Strategic Undergrounding |  | SDG&E | 2026 | 2026 | 1634 | 1671 | 1708.855
2110000016 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | CAPEX | Territory | $ Thousands |  | Equipment failure | [8 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000017 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | CAPEX | HFTD | $ Thousands |  | Equipment failure | [8 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000018 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | OPEX | Territory | $ Thousands |  | Equipment failure | [8 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000019 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | OPEX | HFTD | $ Thousands |  | Equipment failure | [8 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000020 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | CAPEX | Territory | $ Thousands |  | Equipment failure | [8 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000021 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | CAPEX | HFTD | $ Thousands |  | Equipment failure | [8 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000022 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | OPEX | Territory | $ Thousands |  | Equipment failure | [8 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000023 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | OPEX | HFTD | $ Thousands |  | Equipment failure | [8 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000024 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | CAPEX | Territory | $ Thousands | WMP.0475;WMP.0543;WMP.0545;WMP.1017 | Equipment failure | Other contact with object | 2009 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0475-Distribution Overhead System Hardening;WMP.0543-Transmission Overhead Hardening;WMP.0545-Transmission Overhead Hardening (Distribution Underbuild);WMP.1017-CNF(Distribution Overhead) |  | SDG&E | 2026 | 2026 | 15962 | 5573 | 3997.7728
2110000025 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | CAPEX | HFTD | $ Thousands | WMP.0475;WMP.0543;WMP.0545;WMP.1017 | Equipment failure | Other contact with object | 2009 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0475-Distribution Overhead System Hardening;WMP.0543-Transmission Overhead Hardening;WMP.0545-Transmission Overhead Hardening (Distribution Underbuild);WMP.1017-CNF(Distribution Overhead) |  | SDG&E | 2026 | 2026 | 15962 | 5573 | 3997.7728
2110000026 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | OPEX | Territory | $ Thousands | WMP.0475;WMP.0543;WMP.0545;WMP.1017 | Equipment failure | Other contact with object | 2009 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0475-Distribution Overhead System Hardening;WMP.0543-Transmission Overhead Hardening;WMP.0545-Transmission Overhead Hardening (Distribution Underbuild);WMP.1017-CNF(Distribution Overhead) |  | SDG&E | 2026 | 2026 | 1458 | 421 | 433.6927
2110000027 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | OPEX | HFTD | $ Thousands | WMP.0475;WMP.0543;WMP.0545;WMP.1017 | Equipment failure | Other contact with object | 2009 | 2024 GRC | WMPMA | Exceeds | G.O. 95 |  | WMP.0475-Distribution Overhead System Hardening;WMP.0543-Transmission Overhead Hardening;WMP.0545-Transmission Overhead Hardening (Distribution Underbuild);WMP.1017-CNF(Distribution Overhead) |  | SDG&E | 2026 | 2026 | 1458 | 421 | 433.6927
2110000028 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000029 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000030 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000031 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000032 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | CAPEX | Territory | $ Thousands | WMP.0462 | PSPS - for sectionalization, etc. |  | 2019 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0462-Microgrids |  | SDG&E | 2026 | 2026 | 0 | 0 | 910
2110000033 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | CAPEX | HFTD | $ Thousands | WMP.0462 | PSPS - for sectionalization, etc. |  | 2019 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0462-Microgrids |  | SDG&E | 2026 | 2026 | 0 | 0 | 910
2110000034 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | OPEX | Territory | $ Thousands | WMP.0462 | PSPS - for sectionalization, etc. |  | 2019 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0462-Microgrids |  | SDG&E | 2026 | 2026 | 1273 | 1311 | 1350.6106
2110000035 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | OPEX | HFTD | $ Thousands | WMP.0462 | PSPS - for sectionalization, etc. |  | 2019 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0462-Microgrids | Not Applicable | SDG&E | 2026 | 2026
2110000036 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | CAPEX | Territory | $ Thousands | WMP.0463 | PSPS - for sectionalization, etc.;Wildfire Exposure |  | 2011;2023 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0463-Advanced Protection |  | SDG&E | 2026 | 2026 | 2759 | 1808 | 1226
2110000037 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | CAPEX | HFTD | $ Thousands | WMP.0463 | PSPS - for sectionalization, etc.;Wildfire Exposure |  | 2011;2023 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0463-Advanced Protection |  | SDG&E | 2026 | 2026 | 2759 | 1808 | 1226
2110000038 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | OPEX | Territory | $ Thousands | WMP.0463;WMP.0549 | PSPS - for sectionalization, etc.;Wildfire Exposure |  | 2011;2023 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0463-Advanced Protection;WMP.0549-Distribution Communications Reliability Improvements |  | SDG&E | 2026 | 2026 | 2505 | 1220 | 1103.4454
2110000039 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | OPEX | HFTD | $ Thousands | WMP.0463;WMP.0549 | PSPS - for sectionalization, etc.;Wildfire Exposure |  | 2011;2023 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0463-Advanced Protection;WMP.0549-Distribution Communications Reliability Improvements |  | SDG&E | 2026 | 2026 | 2449 | 1194 | 1080.9454
2110000040 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000041 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000042 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000043 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000044 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | CAPEX | Territory | $ Thousands | WMP.1189 | Equipment failure |  | 2021 | 2024 GRC | WMPMA |  |  |  | WMP.1189-Strategic Pole Remediation |  | SDG&E | 2026 | 2026 | 7923 | 7923 | 7923
2110000045 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | CAPEX | HFTD | $ Thousands | WMP.1189 | Equipment failure |  | 2021 | 2024 GRC | WMPMA |  |  |  | WMP.1189-Strategic Pole Remediation |  | SDG&E | 2026 | 2026 | 7923 | 7923 | 7923
2110000046 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | OPEX | Territory | $ Thousands | WMP.1189 | Equipment failure |  | 2021 | 2024 GRC | WMPMA |  |  |  | WMP.1189-Strategic Pole Remediation |  | SDG&E | 2026 | 2026 | 168 | 173 | 178.2312
2110000047 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | OPEX | HFTD | $ Thousands | WMP.1189 | Equipment failure |  | 2021 | 2024 GRC | WMPMA |  |  |  | WMP.1189-Strategic Pole Remediation |  | SDG&E | 2026 | 2026 | 168 | 173 | 178.2312
2110000048 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | CAPEX | Territory | $ Thousands | WMP.0461;WMP.0467;WMP.0468;WMP.1432 | PSPS - for sectionalization, etc. |  | 2019;2020;2020;2026 | 2024 GRC | WMPMA | Exceeds | G.O. 95;P.U. Code § 451 |  | WMP.0461-PSPS Sectionalizing Enhancements;WMP.0467-Generator Assistance Program;WMP.0468-Standby Power Program (Fixed Backup Power Commercial);WMP.1432-Customized Resiliancy Assessments |  | SDG&E | 2026 | 2026 | 2205 | 1890 | 1575
2110000049 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | CAPEX | HFTD | $ Thousands | WMP.0461;WMP.0467;WMP.0468;WMP.1432 | PSPS - for sectionalization, etc. |  | 2019;2020;2020;2026 | 2024 GRC | WMPMA | Exceeds | G.O. 95;P.U. Code § 451 |  | WMP.0461-PSPS Sectionalizing Enhancements;WMP.0467-Generator Assistance Program;WMP.0468-Standby Power Program (Fixed Backup Power Commercial);WMP.1432-Customized Resiliancy Assessments |  | SDG&E | 2026 | 2026 | 1485 | 1485 | 1485
2110000050 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | OPEX | Territory | $ Thousands | WMP.0461;WMP.0467;WMP.0468;WMP.1432 | PSPS - for sectionalization, etc. |  | 2019;2020;2020;2026 | 2024 GRC | WMPMA | Exceeds | G.O. 95;P.U. Code § 451 |  | WMP.0461-PSPS Sectionalizing Enhancements;WMP.0467-Generator Assistance Program;WMP.0468-Standby Power Program (Fixed Backup Power Commercial);WMP.1432-Customized Resiliancy Assessments |  | SDG&E | 2026 | 2026 | 5610 | 5779 | 5952.084
2110000051 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | OPEX | HFTD | $ Thousands | WMP.0461;WMP.0467;WMP.0468;WMP.1432 | PSPS - for sectionalization, etc. |  | 2019;2020;2020;2026 | 2024 GRC | WMPMA | Exceeds | G.O. 95;P.U. Code § 451 |  | WMP.0461-PSPS Sectionalizing Enhancements;WMP.0467-Generator Assistance Program;WMP.0468-Standby Power Program (Fixed Backup Power Commercial);WMP.1432-Customized Resiliancy Assessments |  | SDG&E | 2026 | 2026 | 5610 | 5779 | 5952.084
2110000052 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000053 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000054 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000055 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000056 | Grid Design, Operations, and Maintenance | Asset Inspections |  | CAPEX | Territory | $ Thousands | WMP.0479;WMP.0481;WMP.0482;WMP.0489;WMP.0492;WMP.0552;WMP.0555;WMP.1190 | Equipment failure;Equipment ignition likelihood |  | 1997;2010;2011;2020;2023 | 2024 GRC | WMPMA | Exceeds | G.O. 95;P.U. Code § 451 |  | WMP.0478-Distribution Overhead Detailed Inspections;WMP.0479-Transmisson Overhead Detailed Inspections;WMP.0481-Distribution Infrared Inspections;WMP.0482-Transmission Infrared Inspections;WMP.0483-Distribution Wood Pole Intrusive Inspections;WMP.0488-Distribution Overhead Patrol Inspections;WMP.0489-Transmission Overhead Patrol Inspections;WMP.0492-Substation Patrol Inspections;WMP.0552-Risk-Informed Drone Inspections;WMP.0555-Transmission 69kV Tier 3 Visual Inspections;WMP.1190-Transmission Wood Pole Intrusive Inspections;WMP.1509-Transmission Switch Inspection |  | SDG&E | 2026 | 2026 | 24729.06 | 14677.4506 | 15122.1782
2110000057 | Grid Design, Operations, and Maintenance | Asset Inspections |  | CAPEX | HFTD | $ Thousands | WMP.0479;WMP.0481;WMP.0482;WMP.0489;WMP.0492;WMP.0552;WMP.0555;WMP.1190 | Equipment failure;Equipment ignition likelihood |  | 1997;2010;2011;2020;2023 | 2024 GRC | WMPMA | Exceeds | G.O. 95;P.U. Code § 451 |  | WMP.0478-Distribution Overhead Detailed Inspections;WMP.0479-Transmisson Overhead Detailed Inspections;WMP.0481-Distribution Infrared Inspections;WMP.0482-Transmission Infrared Inspections;WMP.0483-Distribution Wood Pole Intrusive Inspections;WMP.0488-Distribution Overhead Patrol Inspections;WMP.0489-Transmission Overhead Patrol Inspections;WMP.0492-Substation Patrol Inspections;WMP.0552-Risk-Informed Drone Inspections;WMP.0555-Transmission 69kV Tier 3 Visual Inspections;WMP.1190-Transmission Wood Pole Intrusive Inspections;WMP.1509-Transmission Switch Inspection |  | SDG&E | 2026 | 2026 | 24729.06 | 14677.4506 | 15122.1782
2110000058 | Grid Design, Operations, and Maintenance | Asset Inspections |  | OPEX | Territory | $ Thousands | WMP.0478;WMP.0479;WMP.0481;WMP.0482;WMP.0483;WMP.0488;WMP.0489;WMP.0492;WMP.0552;WMP.0555;WMP.1190 | Equipment failure;Equipment ignition likelihood |  | 1997;2010;2011;2020;2023 | 2024 GRC | WMPMA | Exceeds | G.O. 95;P.U. Code § 451 |  | WMP.0478-Distribution Overhead Detailed Inspections;WMP.0479-Transmisson Overhead Detailed Inspections;WMP.0481-Distribution Infrared Inspections;WMP.0482-Transmission Infrared Inspections;WMP.0483-Distribution Wood Pole Intrusive Inspections;WMP.0488-Distribution Overhead Patrol Inspections;WMP.0489-Transmission Overhead Patrol Inspections;WMP.0492-Substation Patrol Inspections;WMP.0552-Risk-Informed Drone Inspections;WMP.0555-Transmission 69kV Tier 3 Visual Inspections;WMP.1190-Transmission Wood Pole Intrusive Inspections;WMP.1509-Transmission Switch Inspection |  | SDG&E | 2026 | 2026 | 4848.91 | 5807.8162 | 6675.9407
2110000059 | Grid Design, Operations, and Maintenance | Asset Inspections |  | OPEX | HFTD | $ Thousands | WMP.0478;WMP.0479;WMP.0481;WMP.0482;WMP.0483;WMP.0488;WMP.0489;WMP.0492;WMP.0552;WMP.0555;WMP.1190 | Equipment failure;Equipment ignition likelihood |  | 1997;2010;2011;2020;2023 | 2024 GRC | WMPMA | Exceeds | G.O. 95;P.U. Code § 451 |  | WMP.0478-Distribution Overhead Detailed Inspections;WMP.0479-Transmisson Overhead Detailed Inspections;WMP.0481-Distribution Infrared Inspections;WMP.0482-Transmission Infrared Inspections;WMP.0483-Distribution Wood Pole Intrusive Inspections;WMP.0488-Distribution Overhead Patrol Inspections;WMP.0489-Transmission Overhead Patrol Inspections;WMP.0492-Substation Patrol Inspections;WMP.0552-Risk-Informed Drone Inspections;WMP.0555-Transmission 69kV Tier 3 Visual Inspections;WMP.1190-Transmission Wood Pole Intrusive Inspections;WMP.1509-Transmission Switch Inspection |  | SDG&E | 2026 | 2026 | 4848.91 | 5807.8162 | 6675.9407
2110000060 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | CAPEX | Territory | $ Thousands | WMP.1458 |  |  |  | 2024 GRC |  |  |  |  | WMP.1458-Transmission Asset Health | Not Applicable | SDG&E | 2026 | 2026
2110000061 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | CAPEX | HFTD | $ Thousands | WMP.1458 |  |  |  | 2024 GRC |  |  |  |  | WMP.1458-Transmission Asset Health | Not Applicable | SDG&E | 2026 | 2026
2110000062 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | OPEX | Territory | $ Thousands | WMP.1458 |  |  |  | 2024 GRC |  |  |  |  | WMP.1458-Transmission Asset Health | Not Applicable | SDG&E | 2026 | 2026
2110000063 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | OPEX | HFTD | $ Thousands | WMP.1458 | Equipment failure |  |  | 2024 GRC |  |  |  |  | WMP.1458-Transmission Asset Health | Not Applicable | SDG&E | 2026 | 2026
2110000064 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | CAPEX | Territory | $ Thousands | WMP.0491;WMP.1191;WMP.1192;WMP.1193;WMP.1194;WMP.1434;WMP.1435 | Equipment ignition likelihood |  | 2023;2026 | 2024 GRC |  |  |  |  | WMP.0491-Quality Assurance / Quality Control of Distribution Detailed Inspections;WMP.1191-Quality Assurance / Quality Control of Transmission Inspections;WMP.1192-Quality Assurance / Quality Control of Risk Informed Drone Inspections;WMP.1193-Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution);WMP.1194-Quality Assurance / Quality Control of Substation Inspections;WMP.1434-Quality Assurance / Quality Control of Corrective Maintenance Program;WMP.1510-Quality assurance / Quality control of Transmission Switch Inspections;WMP.1435-Quality assurance/quality control of PSPS Sectionalizing Enhancement Program;WMP.1496-Quality assurance/quality control of Advanced Protection Program;WMP.1497-Quality assurance/quality control of Strategic Undergrounding Program;WMP.1498-Quality assurance/quality control of Distribution Overhead System Hardening Program;WMP.1499-Quality assurance/quality control of Transmission Overhead Hardening;WMP.1500-Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild);WMP.1508-Quality assurance/ quality control of Combined Covered Conductor | Not Applicable | SDG&E | 2026 | 2026
2110000065 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | CAPEX | HFTD | $ Thousands | WMP.0491;WMP.1191;WMP.1192;WMP.1193;WMP.1194;WMP.1434;WMP.1435 | Equipment ignition likelihood |  | 2023;2026 | 2024 GRC |  |  |  |  | WMP.0491-Quality Assurance / Quality Control of Distribution Detailed Inspections;WMP.1191-Quality Assurance / Quality Control of Transmission Inspections;WMP.1192-Quality Assurance / Quality Control of Risk Informed Drone Inspections;WMP.1193-Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution);WMP.1194-Quality Assurance / Quality Control of Substation Inspections;WMP.1434-Quality Assurance / Quality Control of Corrective Maintenance Program;WMP.1510-Quality assurance / Quality control of Transmission Switch Inspections;WMP.1435-Quality assurance/quality control of PSPS Sectionalizing Enhancement Program;WMP.1496-Quality assurance/quality control of Advanced Protection Program;WMP.1497-Quality assurance/quality control of Strategic Undergrounding Program;WMP.1498-Quality assurance/quality control of Distribution Overhead System Hardening Program;WMP.1499-Quality assurance/quality control of Transmission Overhead Hardening;WMP.1500-Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild);WMP.1508-Quality assurance/ quality control of Combined Covered Conductor | Not Applicable | SDG&E | 2026 | 2026
2110000066 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | OPEX | Territory | $ Thousands | WMP.0491;WMP.1191;WMP.1192;WMP.1193;WMP.1194;WMP.1434;WMP.1435 | Equipment ignition likelihood |  | 2023;2026 | 2024 GRC |  |  |  |  | WMP.0491-Quality Assurance / Quality Control of Distribution Detailed Inspections;WMP.1191-Quality Assurance / Quality Control of Transmission Inspections;WMP.1192-Quality Assurance / Quality Control of Risk Informed Drone Inspections;WMP.1193-Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution);WMP.1194-Quality Assurance / Quality Control of Substation Inspections;WMP.1434-Quality Assurance / Quality Control of Corrective Maintenance Program;WMP.1510-Quality assurance / Quality control of Transmission Switch Inspections;WMP.1435-Quality assurance/quality control of PSPS Sectionalizing Enhancement Program;WMP.1496-Quality assurance/quality control of Advanced Protection Program;WMP.1497-Quality assurance/quality control of Strategic Undergrounding Program;WMP.1498-Quality assurance/quality control of Distribution Overhead System Hardening Program;WMP.1499-Quality assurance/quality control of Transmission Overhead Hardening;WMP.1500-Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild);WMP.1508-Quality assurance/ quality control of Combined Covered Conductor | Not Applicable | SDG&E | 2026 | 2026
2110000067 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | OPEX | HFTD | $ Thousands | WMP.0491;WMP.1191;WMP.1192;WMP.1193;WMP.1194;WMP.1434;WMP.1435 | Equipment ignition likelihood |  | 2023;2026 | 2024 GRC |  |  |  |  | WMP.0491-Quality Assurance / Quality Control of Distribution Detailed Inspections;WMP.1191-Quality Assurance / Quality Control of Transmission Inspections;WMP.1192-Quality Assurance / Quality Control of Risk Informed Drone Inspections;WMP.1193-Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution);WMP.1194-Quality Assurance / Quality Control of Substation Inspections;WMP.1434-Quality Assurance / Quality Control of Corrective Maintenance Program;WMP.1510-Quality assurance / Quality control of Transmission Switch Inspections;WMP.1435-Quality assurance/quality control of PSPS Sectionalizing Enhancement Program;WMP.1496-Quality assurance/quality control of Advanced Protection Program;WMP.1497-Quality assurance/quality control of Strategic Undergrounding Program;WMP.1498-Quality assurance/quality control of Distribution Overhead System Hardening Program;WMP.1499-Quality assurance/quality control of Transmission Overhead Hardening;WMP.1500-Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild);WMP.1508-Quality assurance/ quality control of Combined Covered Conductor | Not Applicable | SDG&E | 2026 | 2026
2110000068 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | CAPEX | Territory | $ Thousands | WMP.1433 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1433-Corrective Maintenance Program |  | SDG&E | 2026 | 2026 | 11033 | 11398 | 11775.8664
2110000069 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | CAPEX | HFTD | $ Thousands | WMP.1433 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1433-Corrective Maintenance Program |  | SDG&E | 2026 | 2026 | 11033 | 11398 | 11775.8664
2110000070 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | OPEX | Territory | $ Thousands | WMP.1433 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1433-Corrective Maintenance Program | Not Applicable | SDG&E | 2026 | 2026
2110000071 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | OPEX | HFTD | $ Thousands | WMP.1433 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1433-Corrective Maintenance Program | Not Applicable | SDG&E | 2026 | 2026
2110000072 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000073 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000074 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000075 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000076 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000077 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000078 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000079 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000080 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | CAPEX | Territory | $ Thousands | WMP.1452 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1452-Personnel Training | Not Applicable | SDG&E | 2026 | 2026
2110000081 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | CAPEX | HFTD | $ Thousands | WMP.1452 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1452-Personnel Training | Not Applicable | SDG&E | 2026 | 2026
2110000082 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | OPEX | Territory | $ Thousands | WMP.1452 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1452-Personnel Training | Not Applicable | SDG&E | 2026 | 2026
2110000083 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | OPEX | HFTD | $ Thousands | WMP.1452 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1452-Personnel Training | Not Applicable | SDG&E | 2026 | 2026
2110000084 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000085 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000086 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000087 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000088 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | CAPEX | Territory | $ Thousands | WMP.1453 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1453-Workforce Planning (Asset Management) | Not Applicable | SDG&E | 2026 | 2026
2110000089 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | CAPEX | HFTD | $ Thousands | WMP.1453 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1453-Workforce Planning (Asset Management) | Not Applicable | SDG&E | 2026 | 2026
2110000090 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | OPEX | Territory | $ Thousands | WMP.1453 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1453-Workforce Planning (Asset Management) | Not Applicable | SDG&E | 2026 | 2026
2110000091 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | OPEX | HFTD | $ Thousands | WMP.1453 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1453-Workforce Planning (Asset Management) | Not Applicable | SDG&E | 2026 | 2026
2110000092 | Vegetation Management and Inspections | Vegetation Management Inspections |  | CAPEX | Territory | $ Thousands | WMP.0494;WMP.0508 | Wildfire Exposure Potential |  | 1998 | 2024 GRC | VMBA |  | G.O. 95, Rule 35; Public Resources Code 4293; FAC-003-4 |  | WMP.1502-Detailed Inspections;WMP.0494-Detailed Inspections;WMP.1503-Off-Cycle Patrols;WMP.0508-Off-Cycle Patrols | Not Applicable | SDG&E | 2026 | 2026
2110000093 | Vegetation Management and Inspections | Vegetation Management Inspections |  | CAPEX | HFTD | $ Thousands | WMP.0494;WMP.0508 | Wildfire Exposure Potential |  | 1998 | 2024 GRC | VMBA |  | G.O. 95, Rule 35; Public Resources Code 4293; FAC-003-4 |  | WMP.1502-Detailed Inspections;WMP.0494-Detailed Inspections;WMP.1503-Off-Cycle Patrols;WMP.0508-Off-Cycle Patrols | Not Applicable | SDG&E | 2026 | 2026
2110000094 | Vegetation Management and Inspections | Vegetation Management Inspections |  | OPEX | Territory | $ Thousands | WMP.0494;WMP.0508 | Wildfire Exposure Potential |  | 1998 | 2024 GRC | VMBA |  | G.O. 95, Rule 35; Public Resources Code 4293; FAC-003-4 |  | WMP.1502-Detailed Inspections;WMP.0494-Detailed Inspections;WMP.1503-Off-Cycle Patrols;WMP.0508-Off-Cycle Patrols |  | SDG&E | 2026 | 2026 | 9477 | 9761.31 | 10054.1493
2110000095 | Vegetation Management and Inspections | Vegetation Management Inspections |  | OPEX | HFTD | $ Thousands | WMP.0494;WMP.0508 | Wildfire Exposure Potential |  | 1998 | 2024 GRC | VMBA |  | G.O. 95, Rule 35; Public Resources Code 4293; FAC-003-4 |  | WMP.1502-Detailed Inspections;WMP.0494-Detailed Inspections;WMP.1503-Off-Cycle Patrols;WMP.0508-Off-Cycle Patrols |  | SDG&E | 2026 | 2026 | 5131 | 5284.93 | 32638.9558
2110000096 | Vegetation Management and Inspections | Pruning and Removal |  | CAPEX | Territory | $ Thousands | WMP.0501 | Contact with vegetation |  | 2019 | 2024 GRC | VMBA | Exceeds | P.U. Code § 451 |  | WMP.1511-Prune and Removal;WMP.1492-Prune and Removal | Not Applicable | SDG&E | 2026 | 2026
2110000097 | Vegetation Management and Inspections | Pruning and Removal |  | CAPEX | HFTD | $ Thousands | WMP.0501 | Contact with vegetation |  | 2019 | 2024 GRC | VMBA | Exceeds | P.U. Code § 451 |  | WMP.1511-Prune and Removal;WMP.1492-Prune and Removal | Not Applicable | SDG&E | 2026 | 2026
2110000098 | Vegetation Management and Inspections | Pruning and Removal |  | OPEX | Territory | $ Thousands | WMP.0501 | Contact with vegetation |  | 2019 | 2024 GRC | VMBA | Exceeds | P.U. Code § 451 |  | WMP.1511-Prune and Removal;WMP.1492-Prune and Removal |  | SDG&E | 2026 | 2026 | 55392.445 | 57054.2184 | 58765.8449
2110000099 | Vegetation Management and Inspections | Pruning and Removal |  | OPEX | HFTD | $ Thousands | WMP.0501 | Contact with vegetation |  | 2019 | 2024 GRC | VMBA | Exceeds | P.U. Code § 451 |  | WMP.1511-Prune and Removal;WMP.1492-Prune and Removal |  | SDG&E | 2026 | 2026 | 27696 | 28526.88 | 29382.6864
2110000100 | Vegetation Management and Inspections | Pole Clearing |  | CAPEX | Territory | $ Thousands | WMP.0512 | Other contact with object |  | 1998 | 2024 GRC | VMBA | Meets | P.U. Code § 451; Public Resources Code 4292 |  | WMP.1504-Pole Clearing;WMP.0512-Pole Clearing | Not Applicable | SDG&E | 2026 | 2026
2110000101 | Vegetation Management and Inspections | Pole Clearing |  | CAPEX | HFTD | $ Thousands | WMP.0512 | Other contact with object |  | 1998 | 2024 GRC | VMBA | Meets | P.U. Code § 451; Public Resources Code 4292 |  | WMP.1504-Pole Clearing;WMP.0512-Pole Clearing | Not Applicable | SDG&E | 2026 | 2026
2110000102 | Vegetation Management and Inspections | Pole Clearing |  | OPEX | Territory | $ Thousands | WMP.0512 | Other contact with object |  | 1998 | 2024 GRC | VMBA | Meets | P.U. Code § 451; Public Resources Code 4292 |  | WMP.1504-Pole Clearing;WMP.0512-Pole Clearing |  | SDG&E | 2026 | 2026 | 6620 | 6818 | 7022.9564
2110000103 | Vegetation Management and Inspections | Pole Clearing |  | OPEX | HFTD | $ Thousands | WMP.0512 | Other contact with object |  | 1998 | 2024 GRC | VMBA | Meets | P.U. Code § 451; Public Resources Code 4292 |  | WMP.1504-Pole Clearing;WMP.0512-Pole Clearing |  | SDG&E | 2026 | 2026 | 5818 | 5992 | 6171.9469
2110000104 | Vegetation Management and Inspections | Wood and Slash Management |  | CAPEX | Territory | $ Thousands | WMP.1460 |  |  | 2026 | 2024 GRC | VMBA |  |  |  | WMP.1460-Sustainability | Not Applicable | SDG&E | 2026 | 2026
2110000105 | Vegetation Management and Inspections | Wood and Slash Management |  | CAPEX | HFTD | $ Thousands | WMP.1460 |  |  | 2026 | 2024 GRC | VMBA |  |  |  | WMP.1460-Sustainability | Not Applicable | SDG&E | 2026 | 2026
2110000106 | Vegetation Management and Inspections | Wood and Slash Management |  | OPEX | Territory | $ Thousands | WMP.1460 |  |  | 2026 | 2024 GRC | VMBA |  |  |  | WMP.1460-Sustainability | Not Applicable | SDG&E | 2026 | 2026
2110000107 | Vegetation Management and Inspections | Wood and Slash Management |  | OPEX | HFTD | $ Thousands | WMP.1460 |  |  | 2026 | 2024 GRC | VMBA |  |  |  | WMP.1460-Sustainability | Not Applicable | SDG&E | 2026 | 2026
2110000108 | Vegetation Management and Inspections | Defensible Space |  | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000109 | Vegetation Management and Inspections | Defensible Space |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000110 | Vegetation Management and Inspections | Defensible Space |  | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000111 | Vegetation Management and Inspections | Defensible Space |  | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000112 | Vegetation Management and Inspections | Integrated Vegetation Management |  | CAPEX | Territory | $ Thousands | WMP.0497 | Contact with vegetation |  | 2019 | 2024 GRC | VMBA | Exceeds | P.U. Code § 451 |  | WMP.0497-Fuels Management | Not Applicable | SDG&E | 2026 | 2026
2110000113 | Vegetation Management and Inspections | Integrated Vegetation Management |  | CAPEX | HFTD | $ Thousands | WMP.0497 | Contact with vegetation |  | 2019 | 2024 GRC | VMBA | Exceeds | P.U. Code § 451 |  | WMP.0497-Fuels Management | Not Applicable | SDG&E | 2026 | 2026
2110000114 | Vegetation Management and Inspections | Integrated Vegetation Management |  | OPEX | Territory | $ Thousands | WMP.0497 | Contact with vegetation |  | 2019 | 2024 GRC | VMBA | Exceeds | P.U. Code § 451 |  | WMP.0497-Fuels Management |  | SDG&E | 2026 | 2026 | 5608 | 5777 | 5949.8985
2110000115 | Vegetation Management and Inspections | Integrated Vegetation Management |  | OPEX | HFTD | $ Thousands | WMP.0497 | Contact with vegetation |  | 2019 | 2024 GRC | VMBA | Exceeds | P.U. Code § 451 |  | WMP.0497-Fuels Management |  | SDG&E | 2026 | 2026 | 5608 | 5777 | 5949.8985
2110000116 | Vegetation Management and Inspections | Partnerships |  | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000117 | Vegetation Management and Inspections | Partnerships |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000118 | Vegetation Management and Inspections | Partnerships |  | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000119 | Vegetation Management and Inspections | Partnerships |  | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000120 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000121 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000122 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000123 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000124 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000125 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000126 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000127 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000128 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | CAPEX | Territory | $ Thousands | WMP.0505 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1493-Quality assurance/quality control of Vegetation Management;WMP.1505-Quality assurance/quality control of Vegetation Management;WMP.1494-Quality assurance/quality control of Prune and Removal;WMP.1506-Quality assurance/quality control of Prune and Removal;WMP.1495-Quality assurance/quality control of Pole Clearing;WMP.1507-Quality assurance/quality control of Pole Clearing | Not Applicable | SDG&E | 2026 | 2026
2110000129 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | WMP.0505 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1493-Quality assurance/quality control of Vegetation Management;WMP.1505-Quality assurance/quality control of Vegetation Management;WMP.1494-Quality assurance/quality control of Prune and Removal;WMP.1506-Quality assurance/quality control of Prune and Removal;WMP.1495-Quality assurance/quality control of Pole Clearing;WMP.1507-Quality assurance/quality control of Pole Clearing | Not Applicable | SDG&E | 2026 | 2026
2110000130 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | OPEX | Territory | $ Thousands | WMP.0505 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1493-Quality assurance/quality control of Vegetation Management;WMP.1505-Quality assurance/quality control of Vegetation Management;WMP.1494-Quality assurance/quality control of Prune and Removal;WMP.1506-Quality assurance/quality control of Prune and Removal;WMP.1495-Quality assurance/quality control of Pole Clearing;WMP.1507-Quality assurance/quality control of Pole Clearing |  | SDG&E | 2026 | 2026 | 6246.807 | 6434.2112 | 6627.2375
2110000131 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | OPEX | HFTD | $ Thousands | WMP.0505 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1493-Quality assurance/quality control of Vegetation Management;WMP.1505-Quality assurance/quality control of Vegetation Management;WMP.1494-Quality assurance/quality control of Prune and Removal;WMP.1506-Quality assurance/quality control of Prune and Removal;WMP.1495-Quality assurance/quality control of Pole Clearing;WMP.1507-Quality assurance/quality control of Pole Clearing |  | SDG&E | 2026 | 2026 | 3123 | 3216.69 | 3313.1907
2110000132 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | CAPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000133 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000134 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | OPEX | Territory | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000135 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | OPEX | HFTD | $ Thousands | [10 empty] | Not Applicable | SDG&E | 2026 | 2026
2110000136 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | CAPEX | Territory | $ Thousands | WMP.0506 |  |  |  | 2024 GRC |  |  |  |  | WMP.0506-Workforce Planning (Vegetation Management) | Not Applicable | SDG&E | 2026 | 2026
2110000137 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | WMP.0506 |  |  |  | 2024 GRC |  |  |  |  | WMP.0506-Workforce Planning (Vegetation Management) | Not Applicable | SDG&E | 2026 | 2026
2110000138 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | OPEX | Territory | $ Thousands | WMP.0506 |  |  |  | 2024 GRC |  |  |  |  | WMP.0506-Workforce Planning (Vegetation Management) | Not Applicable | SDG&E | 2026 | 2026
2110000139 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | OPEX | HFTD | $ Thousands | WMP.0506 |  |  |  | 2024 GRC |  |  |  |  | WMP.0506-Workforce Planning (Vegetation Management) | Not Applicable | SDG&E | 2026 | 2026
2110000140 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | CAPEX | Territory | $ Thousands | WMP.1431;WMP.1461 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1431-Air Quality Station Maintenance;WMP.1461-Weather Station Data | Not Applicable | SDG&E | 2026 | 2026
2110000141 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | CAPEX | HFTD | $ Thousands | WMP.1431;WMP.1461 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1431-Air Quality Station Maintenance;WMP.1461-Weather Station Data | Not Applicable | SDG&E | 2026 | 2026
2110000142 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | OPEX | Territory | $ Thousands | WMP.1431;WMP.1461 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1431-Air Quality Station Maintenance;WMP.1461-Weather Station Data |  | SDG&E | 2026 | 2026 | 87 | 89 | 91.7891
2110000143 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | OPEX | HFTD | $ Thousands | WMP.1431;WMP.1461 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1431-Air Quality Station Maintenance;WMP.1461-Weather Station Data |  | SDG&E | 2026 | 2026 | 87 | 89 | 91.7891
2110000144 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | CAPEX | Territory | $ Thousands | WMP.1444;WMP.1195 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1444-Grid Monitoring Systems Data Integration |  | SDG&E | 2026 | 2026 | 2968 | 2868 | 1768
2110000145 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | CAPEX | HFTD | $ Thousands | WMP.1444;WMP.1195 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1444-Grid Monitoring Systems Data Integration |  | SDG&E | 2026 | 2026 | 2968 | 2868 | 1768
2110000146 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | OPEX | Territory | $ Thousands | WMP.1444;WMP.1195 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1444-Grid Monitoring Systems Data Integration |  | SDG&E | 2026 | 2026 | 131 | 135 | 139
2110000147 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | OPEX | HFTD | $ Thousands | WMP.1444;WMP.1195 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1444-Grid Monitoring Systems Data Integration |  | SDG&E | 2026 | 2026 | 131 | 135 | 139
2110000148 | Situational Awareness and Forecasting | Ignition Detection Systems |  | CAPEX | Territory | $ Thousands | WMP.1343 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1343-Ignition Detection Systems - Cameras | Not Applicable | SDG&E | 2026 | 2026
2110000149 | Situational Awareness and Forecasting | Ignition Detection Systems |  | CAPEX | HFTD | $ Thousands | WMP.1343 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1343-Ignition Detection Systems - Cameras | Not Applicable | SDG&E | 2026 | 2026
2110000150 | Situational Awareness and Forecasting | Ignition Detection Systems |  | OPEX | Territory | $ Thousands | WMP.1343 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1343-Ignition Detection Systems - Cameras | Not Applicable | SDG&E | 2026 | 2026
2110000151 | Situational Awareness and Forecasting | Ignition Detection Systems |  | OPEX | HFTD | $ Thousands | WMP.1343 |  |  | 2026 | 2024 GRC |  |  |  |  | WMP.1343-Ignition Detection Systems - Cameras | Not Applicable | SDG&E | 2026 | 2026
2110000152 | Situational Awareness and Forecasting | Weather Forecasting |  | CAPEX | Territory | $ Thousands | WMP.0540;WMP.1430 |  |  | 2010 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0540-SAWTI models;WMP.1430-Weather Station Maintenance and Calibration |  | SDG&E | 2026 | 2026 | 261 | 264 | 270
2110000153 | Situational Awareness and Forecasting | Weather Forecasting |  | CAPEX | HFTD | $ Thousands | WMP.0540;WMP.1430 |  |  | 2010 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0540-SAWTI models;WMP.1430-Weather Station Maintenance and Calibration | Not Applicable | SDG&E | 2026 | 2026
2110000154 | Situational Awareness and Forecasting | Weather Forecasting |  | OPEX | Territory | $ Thousands | WMP.0540;WMP.1430 |  |  | 2010 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0540-SAWTI models;WMP.1430-Weather Station Maintenance and Calibration | Not Applicable | SDG&E | 2026 | 2026
2110000155 | Situational Awareness and Forecasting | Weather Forecasting |  | OPEX | HFTD | $ Thousands | WMP.0540;WMP.1430 |  |  | 2010 | 2024 GRC | WMPMA | Exceeds | P.U. Code § 451 |  | WMP.0540-SAWTI models;WMP.1430-Weather Station Maintenance and Calibration | Not Applicable | SDG&E | 2026 | 2026
2110000156 | Situational Awareness and Forecasting | Fire Potential Index |  | CAPEX | Territory | $ Thousands | WMP.0450 | Wildfire Exposure Potential |  | 2012 | 2024 GRC |  |  |  |  | WMP.0450-Fire potential index | Not Applicable | SDG&E | 2026 | 2026
2110000157 | Situational Awareness and Forecasting | Fire Potential Index |  | CAPEX | HFTD | $ Thousands | WMP.0450 | Wildfire Exposure Potential |  | 2012 | 2024 GRC |  |  |  |  | WMP.0450-Fire potential index | Not Applicable | SDG&E | 2026 | 2026
2110000158 | Situational Awareness and Forecasting | Fire Potential Index |  | OPEX | Territory | $ Thousands | WMP.0450 | Wildfire Exposure Potential |  | 2012 | 2024 GRC |  |  |  |  | WMP.0450-Fire potential index |  | SDG&E | 2026 | 2026 | 5550 | 5717 | 5888.1435
2110000159 | Situational Awareness and Forecasting | Fire Potential Index |  | OPEX | HFTD | $ Thousands | WMP.0450 | Wildfire Exposure Potential |  | 2012 | 2024 GRC |  |  |  |  | WMP.0450-Fire potential index |  | SDG&E | 2026 | 2026 | 5550 | 5717 | 5888.1435
2110000160 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | CAPEX | Territory | $ Thousands | WMP.0514;WMP.0532;WMP.0557;WMP.1008 | PSPS Vulnerability |  | 2013 | 2024 GRC |  |  |  |  | WMP.0514-Wildfire Infrastructure Protection Teams;WMP.0532-Engagement with AFN Populations Total;WMP.0557-Aviation Firefighting Program;WMP.1008-Emergency Preparedness and Recovery Plan | Not Applicable | SDG&E | 2026 | 2026
2110000161 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | CAPEX | HFTD | $ Thousands | WMP.0514;WMP.0532;WMP.0557;WMP.1008 | PSPS Vulnerability |  | 2013 | 2024 GRC |  |  |  |  | WMP.0514-Wildfire Infrastructure Protection Teams;WMP.0532-Engagement with AFN Populations Total;WMP.0557-Aviation Firefighting Program;WMP.1008-Emergency Preparedness and Recovery Plan | Not Applicable | SDG&E | 2026 | 2026
2110000162 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | OPEX | Territory | $ Thousands | WMP.0514;WMP.0532;WMP.0557;WMP.1008 | PSPS Vulnerability |  | 2013 | 2024 GRC |  |  |  |  | WMP.0514-Wildfire Infrastructure Protection Teams;WMP.0532-Engagement with AFN Populations Total;WMP.0557-Aviation Firefighting Program;WMP.1008-Emergency Preparedness and Recovery Plan |  | SDG&E | 2026 | 2026 | 33265 | 34263 | 35290.5202
2110000163 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | OPEX | HFTD | $ Thousands | WMP.0514;WMP.0532;WMP.0557;WMP.1008 | PSPS Vulnerability |  | 2013 | 2024 GRC |  |  |  |  | WMP.0514-Wildfire Infrastructure Protection Teams;WMP.0532-Engagement with AFN Populations Total;WMP.0557-Aviation Firefighting Program;WMP.1008-Emergency Preparedness and Recovery Plan |  | SDG&E | 2026 | 2026 | 33265 | 34263 | 35290.5202
2110000164 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | CAPEX | Territory | $ Thousands | WMP.1337;WMP.1454 |  |  |  | 2024 GRC |  |  |  |  | WMP.1337-Community Engagement;WMP.1454-External Collaboration and Coordination | Not Applicable | SDG&E | 2026 | 2026
2110000165 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | CAPEX | HFTD | $ Thousands | WMP.1337;WMP.1454 |  |  |  | 2024 GRC |  |  |  |  | WMP.1337-Community Engagement;WMP.1454-External Collaboration and Coordination | Not Applicable | SDG&E | 2026 | 2026
2110000166 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | OPEX | Territory | $ Thousands | WMP.1337;WMP.1454 |  |  |  | 2024 GRC |  |  |  |  | WMP.1337-Community Engagement;WMP.1454-External Collaboration and Coordination | Not Applicable | SDG&E | 2026 | 2026
2110000167 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | OPEX | HFTD | $ Thousands | WMP.1337;WMP.1454 |  |  |  | 2024 GRC |  |  |  |  | WMP.1337-Community Engagement;WMP.1454-External Collaboration and Coordination | Not Applicable | SDG&E | 2026 | 2026
2110000168 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | CAPEX | Territory | $ Thousands | WMP.0527;WMP.0563 | PSPS Vulnerability |  | 2013 | 2024 GRC |  | Exceeds | P.U. Code § 451 |  | WMP.0527-Public Outreach and Education Awareness;WMP.0563-Public Emergency Communication Strategy | Not Applicable | SDG&E | 2026 | 2026
2110000169 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | CAPEX | HFTD | $ Thousands | WMP.0527;WMP.0563 | PSPS Vulnerability |  | 2013 | 2024 GRC |  | Exceeds | P.U. Code § 451 |  | WMP.0527-Public Outreach and Education Awareness;WMP.0563-Public Emergency Communication Strategy | Not Applicable | SDG&E | 2026 | 2026
2110000170 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | OPEX | Territory | $ Thousands | WMP.0527;WMP.0563 | PSPS Vulnerability |  | 2013 | 2024 GRC |  | Exceeds | P.U. Code § 451 |  | WMP.0527-Public Outreach and Education Awareness;WMP.0563-Public Emergency Communication Strategy |  | SDG&E | 2026 | 2026 | 10010 | 10310 | 10619.7681
2110000171 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | OPEX | HFTD | $ Thousands | WMP.0527;WMP.0563 | PSPS Vulnerability |  | 2013 | 2024 GRC |  | Exceeds | P.U. Code § 451 |  | WMP.0527-Public Outreach and Education Awareness;WMP.0563-Public Emergency Communication Strategy |  | SDG&E | 2026 | 2026 | 10010 | 10310 | 10619.7681
2110000172 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | CAPEX | Territory | $ Thousands | WMP.1455 |  |  |  | 2024 GRC |  |  |  |  | WMP.1455-Customer Support in Wildfire and PSPS Emergencies | Not Applicable | SDG&E | 2026 | 2026
2110000173 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | CAPEX | HFTD | $ Thousands | WMP.1455 |  |  |  | 2024 GRC |  |  |  |  | WMP.1455-Customer Support in Wildfire and PSPS Emergencies | Not Applicable | SDG&E | 2026 | 2026
2110000174 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | OPEX | Territory | $ Thousands | WMP.1455 |  |  |  | 2024 GRC |  |  |  |  | WMP.1455-Customer Support in Wildfire and PSPS Emergencies | Not Applicable | SDG&E | 2026 | 2026
2110000175 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | OPEX | HFTD | $ Thousands | WMP.1455 |  |  |  | 2024 GRC |  |  |  |  | WMP.1455-Customer Support in Wildfire and PSPS Emergencies | Not Applicable | SDG&E | 2026 | 2026
2110000176 | Enterprise Systems | Enterprise Systems Development |  | CAPEX | Territory | $ Thousands | WMP.0511;WMP.0519;WMP.1457;WMP.1464 |  |  | 2002 | 2024 GRC |  |  |  |  | WMP.0511-Vegetation Management Enterprise System;WMP.0519-Enterprise Data Foundation;WMP.1457-Asset Management and Inspection Enterprise System;WMP.1464-Vegetation Management Enterprise System - Advanced Analytics |  | SDG&E | 2026 | 2026 | 7397 | 6731 | 6425
2110000177 | Enterprise Systems | Enterprise Systems Development |  | CAPEX | HFTD | $ Thousands | WMP.0511;WMP.0519;WMP.1457;WMP.1464 |  |  | 2002 | 2024 GRC |  |  |  |  | WMP.0511-Vegetation Management Enterprise System;WMP.0519-Enterprise Data Foundation;WMP.1457-Asset Management and Inspection Enterprise System;WMP.1464-Vegetation Management Enterprise System - Advanced Analytics |  | SDG&E | 2026 | 2026 | 7397 | 6731 | 6425
2110000178 | Enterprise Systems | Enterprise Systems Development |  | OPEX | Territory | $ Thousands | WMP.0511;WMP.0519;WMP.1457;WMP.1464 |  |  | 2002 | 2024 GRC |  |  |  |  | WMP.0511-Vegetation Management Enterprise System;WMP.0519-Enterprise Data Foundation;WMP.1457-Asset Management and Inspection Enterprise System;WMP.1464-Vegetation Management Enterprise System - Advanced Analytics |  | SDG&E | 2026 | 2026 | 2169 | 2481 | 2555
2110000179 | Enterprise Systems | Enterprise Systems Development |  | OPEX | HFTD | $ Thousands | WMP.0511;WMP.0519;WMP.1457;WMP.1464 |  |  | 2002 | 2024 GRC |  |  |  |  | WMP.0511-Vegetation Management Enterprise System;WMP.0519-Enterprise Data Foundation;WMP.1457-Asset Management and Inspection Enterprise System;WMP.1464-Vegetation Management Enterprise System - Advanced Analytics |  | SDG&E | 2026 | 2026 | 2169 | 2481 | 2555

## Table 12
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP ACTIVITY NAME | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | UTILITY MITIGATION ACTIVITY TRACKING ID | TARGET TYPE | UNIT(S) | METHOD OF VERIFICATION | COMMENTS | REPORTING YEAR | CYCLE YEAR 1 | YTD TARGET - Y1 Q2 | YTD TARGET - Y1 Q3 | YTD TARGET - Y1 Q4 | YTD TARGET - Y2 Q2 | YTD TARGET - Y2 Q3 | YTD TARGET - Y2 Q4 | YTD TARGET - Y3 Q2 | YTD TARGET - Y3 Q3 | YTD TARGET - Y3 Q4
2120000000 | SDG&E | 2025-07-18 | Risk Methodology and Assessment | Risk Methodology and Assessment | Risk Methodology and Assessment |  | WMP.0442 | Qualitative |  | Quarterly Business Review and/or ADO delivery plan, and summary of actions taken in support of the qualitative target. | WMP.0442-Risk Methodology and Assessment | 2026 | 2026 |  |  | By 12/31/2026: Continue enhancing the visualization platform to facilitate quick and easy access to reliable data to inform de-energization and mitigation investment planning decisions, faster initial loads and overall stability of the platform. Identify potential enhancements for existing features to elevate user experience and facilitate efficient risk information transfer. |  |  | By 12/31/2027: Continue to integrate and deploy additional enhancements, bug fixes and features. Explore and expand additional use cases for risk modeling and visualization platform. |  |  | By 12/31/2028, Continue regular meetings with internal subject matter experts, visualization developers, and platform users to ensure the precision of displayed data and effective visualizations as well as pinpoint areas for improvement. Explore and expand additional use cases for risk modeling and visualization platform.
2120000001 | SDG&E | 2025-07-18 | Covered conductor installation | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0455 | Quantitative | Miles | Quantitative | WMP.0455-Combined Covered Conductor | 2026 | 2026 |  |  | 50 |  |  | 50 |  |  | 30
2120000002 | SDG&E | 2025-07-18 | Undergrounding of electric lines and/or equipment | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0473 | Quantitative | Miles | Quantitative | WMP.0473-Strategic Undergrounding | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 50
2120000003 | SDG&E | 2025-07-18 | Traditional overhead hardening | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0475 | Quantitative | Miles | Quantitative | WMP.0475-Distribution Overhead System Hardening | 2026 | 2026 |  |  | 6.53 |  |  | 0 |  |  | 0
2120000004 | SDG&E | 2025-07-18 | Traditional overhead hardening | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0543 | Quantitative | Miles | Quantitative | WMP.0543-Transmission Overhead Hardening | 2026 | 2026 |  |  | 6.02 |  |  | 11.94 |  |  | 3
2120000005 | SDG&E | 2025-07-18 | Traditional overhead hardening | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0545 | Quantitative | Miles | Quantitative | WMP.0545-Transmission Overhead Hardening (Distribution Underbuild) | 2026 | 2026 |  |  | 1.2 |  |  | 7.1 |  |  | 3
2120000006 | SDG&E | 2025-07-18 | Microgrids | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0462 | Quantitative | Microgrids | Quantitative | WMP.0462-Microgrids | 2026 | 2026 |  |  | 0 |  |  | 0 |  |  | 1
2120000007 | SDG&E | 2025-07-18 | Installation of system automation equipment | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0463 | Quantitative | Nodes | Quantitative | WMP.0463-Advanced Protection | 2026 | 2026 |  |  | 30 |  |  | 30 |  |  | 30
2120000008 | SDG&E | 2025-07-18 | Other grid topology improvements to minimize risk of ignitions | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.1189 | Quantitative | Poles | Quantitative | WMP.1189-Strategic Pole Remediation | 2026 | 2026 |  |  | 200 |  |  | 200 |  |  | 200
2120000009 | SDG&E | 2025-07-18 | Other grid topology improvements to mitigate or reduce PSPS events | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0467 | Qualitative |  | System of record (EECP) and summary of actions taken in support of the qualitative target. | WMP.0467-Generator Assistance Program | 2026 | 2026 |  |  | By 12/31/2026, enable rebates for backup power solutions for eligible customers. |  |  | By 12/31/2027, enable rebates for backup power solutions for eligible customers. |  |  | By 12/31/2028, enable rebates for backup power solutions for eligible customers.
2120000010 | SDG&E | 2025-07-18 | Other grid topology improvements to mitigate or reduce PSPS events | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0468 | Qualitative |  | System of record (EECP) and summary of actions taken in support of the qualitative target. | WMP.0468-Standby Power Program (Fixed Backup Power Commercial) | 2026 | 2026 |  |  | By 12/31/2026, enable backup power solutions of priority sites. |  |  | By 12/31/2027, enable backup power solutions of priority sites. |  |  | By 12/31/2028, enable backup power solutions of priority sites.
2120000011 | SDG&E | 2025-07-18 | Other grid topology improvements to mitigate or reduce PSPS events | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.0461 | Quantitative | Switches | Quantitative | WMP.0461-PSPS Sectionalizing Enhancements | 2026 | 2026 |  |  | 7 |  |  | 6 |  |  | 5
2120000012 | SDG&E | 2025-07-18 | Other grid topology improvements to mitigate or reduce PSPS events | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | WMP.1432 | Qualitative |  | System of record (EECP) and summary of actions taken in support of the qualitative target. | WMP.1432-Customized Resiliency Assessments | 2026 | 2026 |  |  | By 12/31/2026, offer resiliency support for eligible customers. |  |  | By 12/31/2027, offer resiliency support for eligible customers. |  |  | By 12/31/2028, offer resiliency support for eligible customers.
2120000013 | SDG&E | 2025-07-18 | Distribution Overhead Detailed Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.0478 | Quantitative | Structures | Quantitative | WMP.0478-Distribution Overhead Detailed Inspections | 2026 | 2026 | 10962 | 16443 | 21924 | 8888 | 13332 | 17779 | 5768 | 8652 | 11537
2120000014 | SDG&E | 2025-07-18 | Distribution Overhead Patrol Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.0488 | Quantitative | Structures | Quantitative | WMP.0488-Distribution Overhead Patrol Inspections | 2026 | 2026 | 42340 | 63510 | 84678 | 42340 | 63510 | 84678 | 42340 | 63510 | 84678
2120000015 | SDG&E | 2025-07-18 | Distribution Wood Pole Intrusive Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.0483 | Quantitative | Structures | Quantitative | WMP.0483-Distribution Wood Pole Intrusive Inspections | 2026 | 2026 | 606 | 909 | 1214 | 2738 | 4107 | 5477 | 6000 | 9000 | 11923
2120000016 | SDG&E | 2025-07-18 | Risk-Informed Drone Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.0552 | Quantitative | Structures | Quantitative | WMP.0552-Risk-Informed Drone Inspections | 2026 | 2026 | 4500 | 6750 | 9000 | 4500 | 6750 | 9000 | 4500 | 6750 | 9000
2120000017 | SDG&E | 2025-07-18 | Substation Patrol Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.0492 | Quantitative | Substations | Quantitative | WMP.0492-Substation Patrol Inspections | 2026 | 2026 | 192 | 282 | 381 | 192 | 282 | 381 | 192 | 282 | 381
2120000018 | SDG&E | 2025-07-18 | Transmission Infrared Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.0482 | Quantitative | Structures | Quantitative | WMP.0482-Transmission Infrared Inspections | 2026 | 2026 | 0 | 7294 | 7294 | 0 | 7294 | 7294 | 0 | 7294 | 7294
2120000019 | SDG&E | 2025-07-18 | Transmission Overhead Patrol Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.0489 | Quantitative | Structures | Quantitative | WMP.0489-Transmission Overhead Patrol Inspections | 2026 | 2026 | 7121 | 7121 | 7454 | 7121 | 7121 | 7454 | 7121 | 7121 | 7454
2120000020 | SDG&E | 2025-07-18 | Transmission Wood Pole Intrusive Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.1190 | Quantitative | Structures | Quantitative | WMP.1190-Transmission Wood Pole Intrusive Inspections | 2026 | 2026 | 34 | 51 | 68 | 98 | 147 | 196 | 12 | 18 | 24
2120000021 | SDG&E | 2025-07-18 | Transmisson Overhead Detailed Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.0479 | Quantitative | Structures | Quantitative | WMP.0479-Transmisson Overhead Detailed Inspections | 2026 | 2026 | 917 | 1685 | 2447 | 1437 | 2127 | 2524 | 1325 | 1980 | 2545
2120000022 | SDG&E | 2025-07-18 | Transmission Switch Inspections | Grid Design, Operations, and Maintenance | Asset Inspections |  | WMP.1509 | Quantitative | Switches | Quantitative | WMP.1509-Transmission Switch Inspection | 2026 | 2026 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 4
2120000023 | SDG&E | 2025-07-18 | Transmission Asset Health | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | WMP.1458 | Qualitative |  | Comprehensive asset strategy and summary of actions taken in support of the qualitative target. | WMP.1458-Transmission Asset Health | 2026 | 2026 |  |  | By 12/31/2026, begin data analysis of asset health, current condition, and outage history of transmission equipment |  |  | By 12/31/2027, continue analysis of transmission equipment, and review and adjust replacement strategies |  |  | By 12/31/2028, continue analysis of transmission equipment, and review and adjust replacement strategies
2120000024 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Transmission Inspections | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1191 | Quantitative | Findings | Quantitative | WMP.1191-Quality Assurance / Quality Control of Transmission Inspections | 2026 | 2026 |  |  | 100% |  |  | 100% |  |  | 100%
2120000025 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Corrective Maintenance Program | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1434 | Quantitative | OH Fire or Safety Related Corrective Actions | Quantitative | WMP.1434-Quality Assurance / Quality Control of Corrective Maintenance Program | 2026 | 2026 |  |  | 1% |  |  | 1% |  |  | 1%
2120000026 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Distribution Detailed Inspections | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.0491 | Quantitative | Findings | Quantitative | WMP.0491-Quality Assurance / Quality Control of Distribution Detailed Inspections | 2026 | 2026 |  |  | 50% |  |  | 50% |  |  | 50%
2120000027 | SDG&E | 2025-07-18 | Quality assurance/quality control of PSPS Sectionalizing Enhancement Program | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1435 | Quantitative | Switches | Quantitative | WMP.1435-Quality assurance/quality control of PSPS Sectionalizing Enhancement Program | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000028 | SDG&E | 2025-07-18 | Quality assurance/quality control of Advanced Protection Program | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1496 | Quantitative | Nodes | Quantitative | WMP.1496-Quality assurance/quality control of Advanced Protection Program | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000029 | SDG&E | 2025-07-18 | Quality assurance/quality control of Strategic Undergrounding Program | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1497 | Quantitative | Miles | Quantitative | WMP.1497-Quality assurance/quality control of Strategic Undergrounding Program | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000030 | SDG&E | 2025-07-18 | Quality assurance/quality control of Distribution Overhead System Hardening Program | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1498 | Quantitative | Miles | Quantitative | WMP.1498-Quality assurance/quality control of Distribution Overhead System Hardening Program | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000031 | SDG&E | 2025-07-18 | Quality assurance/quality control of Transmission Overhead Hardening | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1499 | Quantitative | Miles | Quantitative | WMP.1499-Quality assurance/quality control of Transmission Overhead Hardening | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000032 | SDG&E | 2025-07-18 | Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild) | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1500 | Quantitative | Miles | Quantitative | WMP.1500-Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild) | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000033 | SDG&E | 2025-07-18 | Quality assurance/ quality control of Combined Covered Conductor | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1508 | Quantitative | Miles | Quantitative | WMP.1508-Quality assurance/ quality control of Combined Covered Conductor | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000034 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Risk Informed Drone Inspections | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1192 | Quantitative | Drone Inspections | Quantitative | WMP.1192-Quality Assurance / Quality Control of Risk Informed Drone Inspections | 2026 | 2026 |  |  | 15% |  |  | 15% |  |  | 15%
2120000035 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Substation Inspections | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1194 | Quantitative | Findings | Quantitative | WMP.1194-Quality Assurance / Quality Control of Substation Inspections | 2026 | 2026 |  |  | 18 |  |  | 18 |  |  | 18
2120000036 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution) | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1193 | Quantitative | Intrusive Inspections | Quantitative | WMP.1193-Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution) | 2026 | 2026 |  |  | 5% |  |  | 5% |  |  | 5%
2120000037 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Transmission Switch Inspections | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | WMP.1510 | Quantitative | Switch Function Inspections | Quantitative | WMP.1510-Quality Assurance / Quality Control of Transmission Switch Inspections | 2026 | 2026 |  |  | 100% |  |  | 100% |  |  | 100%
2120000038 | SDG&E | 2025-07-18 | Corrective Maintenance Program | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | WMP.1433 | Qualitative |  | Asset Management System | WMP.1433-Corrective Maintenance Program | 2026 | 2026 |  |  | By 12/31/2026, complete repairs within timeframes |  |  | By 12/31/2027, complete repairs within timeframes |  |  | By 12/31/2028, complete repairs within timeframes
2120000039 | SDG&E | 2025-07-18 | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | WMP.1452 | Qualitative |  | Course curriculum guide to include course name, course description, training methodology, and the role of the personnel required to take each course. | WMP.1452-Personnel Training | 2026 | 2026 |  |  | By 12/31/2026, update electric line crew training |  |  | By 12/31/2027, update electric line crew training |  |  | By 12/31/2028, update electric line crew training
2120000040 | SDG&E | 2025-07-18 | Workforce Planning (Asset Management) | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | WMP.1453 | Qualitative |  | Training curriculum agenda/overview and summary of actions taken in support of the qualitative target. | WMP.1453-Workforce Planning (Asset Management) | 2026 | 2026 |  |  | By 12/31/2026, update Storm and PSPS training with lessons learned. |  |  | By 12/31/2027, update Storm and PSPS training with lessons learned. |  |  | By 12/31/2028, update Storm and PSPS training with lessons learned.
2120000041 | SDG&E | 2025-07-18 | Detailed Inspections | Vegetation Management and Inspections | Vegetation Management Inspections |  | WMP.1502 | Quantitative | Circuit Miles | Quantitative | WMP.1502-Detailed Inspections | 2026 | 2026 |  |  | 10500 |  |  | 10500 |  |  | 10500
2120000042 | SDG&E | 2025-07-18 | Detailed Inspections | Vegetation Management and Inspections | Vegetation Management Inspections |  | WMP.0494 | Quantitative | Trees | Quantitative | WMP.0494-Detailed Inspections | 2026 | 2026 |  |  | 485500 |  |  | 485500 |  |  | 485500
2120000043 | SDG&E | 2025-07-18 | Off-Cycle Patrols | Vegetation Management and Inspections | Vegetation Management Inspections |  | WMP.1503 | Quantitative | Circuit Miles | Quantitative | WMP.1503-Off-Cycle Patrols | 2026 | 2026 |  |  | 4850 |  |  | 4850 |  |  | 4850
2120000044 | SDG&E | 2025-07-18 | Off-Cycle Patrols | Vegetation Management and Inspections | Vegetation Management Inspections |  | WMP.0508 | Quantitative | VMAs | Quantitative | WMP.0508-Off-Cycle Patrols | 2026 | 2026 |  |  | 106 |  |  | 106 |  |  | 106
2120000045 | SDG&E | 2025-07-18 | Pole Clearing | Vegetation Management and Inspections | Pole Clearing |  | WMP.0512 | Quantitative | Circuit Miles | Quantitative | WMP.1504-Pole Clearing | 2026 | 2026 |  |  | 1500 |  |  | 1500 |  |  | 1500
2120000046 | SDG&E | 2025-07-18 | Pole Clearing | Vegetation Management and Inspections | Pole Clearing |  | WMP.0512 | Quantitative | Poles Cleared | Quantitative | WMP.0512-Pole Clearing | 2026 | 2026 |  |  | 22000 |  |  | 22000 |  |  | 22000
2120000047 | SDG&E | 2025-07-18 | Sustainability | Vegetation Management and Inspections | Wood and Slash Management |  | WMP.1460 | Qualitative |  | SDG&E's Supply Management's new vendor registration process (The Clearing House) and summary of actions taken in support of the qualitative target. | WMP.1460-Sustainability | 2026 | 2026 |  |  | By year end, engage Supply Management Department to research prospective recycling vendors. |  |  | By year end, enter service agreement with new recycling vendor(s) to divert green waste. |  |  | By year end, continue engaging additional vendor opportunities to reach company goal.
2120000048 | SDG&E | 2025-07-18 | Fuels Management | Vegetation Management and Inspections | Integrated Vegetation Management |  | WMP.0497 | Quantitative | Poles Cleared | Quantitative | WMP.0497-Fuels Management | 2026 | 2026 |  |  | 500 |  |  | 500 |  |  | 500
2120000049 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Vegetation Management | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | WMP.1493 | Quantitative | Circuit Miles | Quantitative | WMP.1493-Quality Assurance / Quality Control of Vegetation Management | 2026 | 2026 |  |  | 2800 |  |  | 2800 |  |  | 2800
2120000050 | SDG&E | 2025-07-18 | Quality Assurance / Quality Control of Vegetation Management | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | WMP.1505 | Quantitative | Inspections | Quantitative | WMP.1505-Quality assurance/quality control of Vegetation Management | 2026 | 2026 |  |  | 72825 |  |  | 72825 |  |  | 72825
2120000051 | SDG&E | 2025-07-18 | Quality assurance/quality control of Prune and Removal | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | WMP.1494 | Quantitative | Circuit Miles | Quantitative | WMP.1494-Quality assurance/quality control of Prune and Removal | 2026 | 2026 |  |  | 15% |  |  | 15% |  |  | 15%
2120000052 | SDG&E | 2025-07-18 | Quality assurance/quality control of Prune and Removal | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | WMP.1506 | Quantitative | Trees trimmed/removed | Quantitative | WMP.1506-Quality assurance/quality control of Prune and Removal | 2026 | 2026 |  |  | 15% |  |  | 15% |  |  | 15%
2120000053 | SDG&E | 2025-07-18 | Quality assurance/quality control of Pole Clearing | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | WMP.1495 | Quantitative | Circuit Miles | Quantitative | WMP.1495-Quality assurance/quality control of Pole Clearing | 2026 | 2026 |  |  | 350 |  |  | 350 |  |  | 350
2120000054 | SDG&E | 2025-07-18 | Quality assurance/quality control of Pole Clearing | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | WMP.1507 | Quantitative | Poles Cleared | Quantitative | WMP.1507-Quality assurance/quality control of Pole Clearing | 2026 | 2026 |  |  | 3300 |  |  | 3300 |  |  | 3300
2120000055 | SDG&E | 2025-07-18 | Workforce Planning (Vegetation Management) | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | WMP.0506 | Qualitative |  | International Society of Arboriculture (ISA) certification and summary of actions taken in support of the qualitative target | WMP.0506-Workforce Planning (Vegetation Management) | 2026 | 2026 |  |  | By year end, manage Vegetation Management workforce through the validation of required, annual contractor training including fire preparedness, hazard tree assessment, environmental, and customer service. Track training completion of internal staff for the Company’s Environmental & Safety Compliance Management Program (ESCMP) addressing compliance requirements, all applicable environmental, health and safety laws, rules, and regulations, and company standards. Validate internal and company workforce are compliant with required ISA-certification requirements of applicable job positions. |  |  | By year end, manage Vegetation Management workforce through the validation of required, annual contractor training including fire preparedness, hazard tree assessment, environmental, and customer service. Track training completion of internal staff for the Company’s ESCMP addressing compliance requirements, all applicable environmental, health and safety laws, rules, and regulations, and company standards. Validate internal and company workforce are compliant with required ISA-certification requirements of applicable job positions. |  |  | By year end, manage Vegetation Management workforce through the validation of required, annual contractor training including fire preparedness, hazard tree assessment, environmental, and customer service. Track training completion of internal staff for the Company’s ESCMP addressing compliance requirements, all applicable environmental, health and safety laws, rules, and regulations, and company standards. Validate internal and company workforce are compliant with required ISA-certification requirements of applicable job positions.
2120000056 | SDG&E | 2025-07-18 | Air Quality Station Maintenance | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | WMP.1431 | Quantitative | Sensors | Quantitative | WMP.1431-Air Quality Station Maintenance | 2026 | 2026 |  |  | 192 |  |  | 192 |  |  | 192
2120000057 | SDG&E | 2025-07-18 | Weather Station Data | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | WMP.1461 | Qualitative |  | Source system, https://synopticdata.com and a summary of actions taken in support of the qualitative target. | WMP.1461-Weather Station Data | 2026 | 2026 |  |  | By 12/31/2026, complete annual adjustments to max wind gust thresholds |  |  | By 12/31/2027, complete annual adjustments to max wind gust thresholds |  |  | By 12/31/2028, complete annual adjustments to max wind gust thresholds
2120000058 | SDG&E | 2025-07-18 | Grid Monitoring Systems Data Integration | Situational Awareness and Forecasting | Grid Monitoring Systems |  | WMP.1444 | Qualitative |  | Predictive Analytics Platform and summary of actions taken in support of the qualitative target | WMP.1444-Grid Monitoring Systems Data Integration | 2026 | 2026 |  |  | By 12/31/2026, begin integration of power quality, fault data and smoke detection into a central monitoring system to enhance real-time monitoring, response, and prevention. |  |  | By 12/31/2027, continue integration of power quality, fault data and smoke detection into a central monitoring system to enhance real-time monitoring, response, and prevention. |  |  | By 12/31/2028, continue integration of power quality, fault data and smoke detection into a central monitoring system to enhance real-time monitoring, response, and prevention.
2120000059 | SDG&E | 2025-07-18 | Early Fault Detection | Situational Awareness and Forecasting | Grid Monitoring Systems |  | WMP.1195 | Quantitative | Nodes | Quantitative | WMP.1195-Early Fault Detection | 2026 | 2026 |  |  | 60 |  |  | 60 |  |  | 60
2120000060 | SDG&E | 2025-07-18 | Ignition Detection Systems - Cameras | Situational Awareness and Forecasting | Ignition Detection Systems |  | WMP.1343 | Qualitative |  | Monitored through https://alertcalifornia.org and summary of actions taken in support of the qualitative target. | WMP.1343-Ignition Detection Systems - Cameras | 2026 | 2026 |  |  | By 12/31/2026, complete annual monitoring of network |  |  | By 12/31/2027, complete annual monitoring of network |  |  | By 12/31/2028, complete annual monitoring of network
2120000061 | SDG&E | 2025-07-18 | Quarterly validation of weekly uptime for Ignition Detection Cameras | Situational Awareness and Forecasting | Ignition Detection Systems |  | WMP.1467 | Quantitative | Quarterly Validations | Quantitative | WMP.1467-Quarterly validation of weekly uptime for Ignition Detection Cameras | 2026 | 2026 |  |  | 4 |  |  | 4 |  |  | 4
2120000062 | SDG&E | 2025-07-18 | Post-processing success rate - WRF simulations | Situational Awareness and Forecasting | Weather Forecasting |  | WMP.1465 | Quantitative | Success rate | Quantitative | WMP.1465- Post-processing success rate - WRF simulations | 2026 | 2026 |  |  | 0.97 |  |  | 0.97 |  |  | 0.97
2120000063 | SDG&E | 2025-07-18 | Weather Station Maintenance and Calibration | Situational Awareness and Forecasting | Weather Forecasting |  | WMP.1466 | Qualitative |  | Source system, https://app.westernwx.com and a summary of actions taken in support of the qualitative target. | WMP.1466-Communication success rate of weather stations | 2026 | 2026 |  |  | By 12/31/2026, complete monitoring of communication success rate of weather stations |  |  | By 12/31/2027, complete monitoring of communication success rate of weather stations |  |  | By 12/31/2028, complete monitoring of communication success rate of weather stations
2120000064 | SDG&E | 2025-07-18 | Weather Station Maintenance and Calibration | Situational Awareness and Forecasting | Weather Forecasting |  | WMP.1430 | Quantitative | Weather Stations | Quantitative | WMP.1430-Weather Station Maintenance and Calibration | 2026 | 2026 |  |  | 217 |  |  | 217 |  |  | 217
2120000065 | SDG&E | 2025-07-18 | Fire potential index | Situational Awareness and Forecasting | Fire Potential Index |  | WMP.0450 | Qualitative |  | Source system, https://mesowest.utah.edu/ and a summary of actions taken in support of the qualitative target. | WMP.0450-Fire potential index | 2026 | 2026 |  |  | By 12/31/2026, complete annual analysis |  |  | By 12/31/2027, complete annual analysis |  |  | By 12/31/2028, complete annual analysis
2120000066 | SDG&E | 2025-07-18 | Emergency Preparedness and Recovery Plan | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | WMP.1008 | Qualitative |  | Updated CEADPP and summary of actions taken in support of the qualitative target | WMP.1008-Emergency Preparedness and Recovery Plan | 2026 | 2026 |  |  | By 12/31/2026 the CEADPP will be updated to incorporate applicable lessons learned from 2025 and include additional requirements as they are identified |  |  | By 12/31/2027 the CEADPP will be updated to incorporate applicable lessons learned from 2026 and include additional requirements as they are identified |  |  | By 12/31/2028 the CEADPP will be updated to incorporate applicable lessons learned from 2027 and include additional requirements as they are identified
2120000067 | SDG&E | 2025-07-18 | External Collaboration and Coordination | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | WMP.1454 | Qualitative |  | SDG&E’s Outreach team’s SharePoint list of CBOs that are PSPS support partners and Memorandum of Understanding (MOU) that shows CBO is support PSPS outreach efforts. | WMP.1454-External Collaboration and Coordination | 2026 | 2026 |  |  | By 12/13/2026, expand the CBO network to approximately 55 CBOs. Additional CBOs will target circuit segments in the HFTD that have a high number of individuals with AFN. |  |  | By 12/31/2027, expand the CBO network to approximately 60 CBOs. Additional CBOs will target circuit segments in the HFTD that have a high number of individuals with AFN. |  |  | By 12/31/2028, expand the CBO network to approximately 65 CBOs. Additional CBOs will target circuit segments in the HFTD that have a high number of individuals with AFN.
2120000068 | SDG&E | 2025-07-18 | Public Outreach and Education Awareness | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | WMP.0527 | Qualitative |  | AFN Plan Quarterly Update and summary of actions taken in support of the qualitative target. | WMP.0527-Public Outreach and Education Awareness | 2026 | 2026 |  |  | By 12/31/2026 the Wildfire, PSPS and AFN Public Education campaigns will have concluded. Customer feedback will be gathered and used to improve communications for 2027. Host Tribal Nation learning sessions post PSPS to acquire level of satisfaction with communication and resiliency. Incorporate feedback where applicable. Continue partnerships with CBOs and AFN collaborative council for amplification of preparedness information by end of year. Host 4 Wildfire Safety Fairs and 65 mini-Wildfire Safety Fairs in key communities of concern. |  |  | By 12/31/2027 the Wildfire, PSPS and AFN Public Education campaigns will have concluded. Customer feedback will be gathered and used to improve communications for 2028. Host Tribal Nation learning sessions post PSPS to acquire level of satisfaction with communication and resiliency. Incorporate feedback where applicable. Continue partnerships with CBO's and AFN collaborative council for amplification of preparedness information by end of year. Host 4 Wildfire Safety Fairs and 70 mini-Wildfire Safety Fairs in key communities of concern. |  |  | By 12/31/2028 the Wildfire, PSPS and AFN Public Education campaigns will have concluded. Customer feedback will be gathered and used to improve communications for 2029. Host Tribal Nation learning sessions post PSPS to acquire level of satisfaction with communication and resiliency. Incorporate feedback where applicable. Continue parnerships with CBO's and AFN collaborative council for amplification of preparedness information by end of year. Host 4 Wildfire Safety Fairs and 75 mini-Wildfire Safety Fairs in key communities of concern.
2120000069 | SDG&E | 2025-07-18 | Customer Support in Wildfire and PSPS Emergencies | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | WMP.1455 | Qualitative |  | Survey results and meeting notes that contain CRC feedback, CRC post-event reports that include lessons learned and areas of opportunity, and summary of actions taken to support qualitative target. | WMP.1455-Customer Support in Wildfire and PSPS Emergencies | 2026 | 2026 |  |  | By 12/31/2026 incorporate applicable lessons learned, and feedback received for Community Resource Centers. |  |  | By 12/31/2027 incorporate applicable lessons learned, and feedback received for Community Resource Centers. |  |  | By 12/31/2028 incorporate applicable lessons learned, and feedback received for Community Resource Centers.
2120000070 | SDG&E | 2025-07-18 | Asset Management and Inspection Enterprise System | Enterprise Systems | Enterprise Systems Development |  | WMP.1457 | Qualitative |  | Asset Management and Inspection Enterprise System and summary of actions taken in support of the qualitative target | WMP.1457-Asset Management and Inspection Enterprise System | 2026 | 2026 |  |  | By 12/31/2026, integrate advanced technology and analytics, including Asset 360 and IIP data, to develop risk-informed strategies for asset management. |  |  | By 12/31/2027, continue enhancing and expanding these risk-informed strategies to improve transparency and efficiency in asset management. |  |  | By 12/31/2028, continue enhancing and expanding these risk-informed strategies to improve transparency and efficiency in asset management.
2120000071 | SDG&E | 2025-07-18 | Enterprise Data Foundation | Enterprise Systems | Enterprise Systems Development |  | WMP.0519 | Qualitative |  | WMP Central Data Repository and summary of actions taken in support of the qualitative target | WMP.0519-Enterprise Data Foundation | 2026 | 2026 |  |  | By 12/31/2026: Establish data migration patterns, successfully migrate data sets including grid hardening, assets, and PSPS/risk events, and implement data validation, integrity, and governance processes to ensure quality and integrity throughout the migration journey. |  |  | By 12/31/2027: Execute data integration from the upgraded SAP S/4 HANA platform for ERP, transitioning from the legacy SAP ECC system. Additionally, implement data ingestion processes for the new Transmission SAP S/4 HANA system while maintaining enterprise data quality standards. |  |  | By 12/31/2028: Integrate and ingest critical data from all newly implemented systems across the organization. This initiative will include establishing data pipelines, security protocols, and ETL processes. The integration will prioritize data quality and system compatibility while maintaining compliance standards.
2120000072 | SDG&E | 2025-07-18 | Vegetation Management Enterprise System | Enterprise Systems | Enterprise Systems Development |  | WMP.0511 | Qualitative |  | Vegetation Management Enterprise System (PowerWorkz) and summary of actions taken in support of the qualitative target | WMP.0511-Vegetation Management Enterprise System | 2026 | 2026 |  |  | By mid-2026: Integrate historical meteorology data (e.g., wind gust) into PowerWorkz field application ("Epoch") as a GIS visualization tool for improved field situational awareness and decision-making. By 12/31/26: Complete update of new version of Powerworkz desktop work management application ("Cityworks") to enhance work order management and VM activity scheduling. |  |  | By mid-2027: Complete migration of all VM data into AWS and the Cloud. By 12/31/27: Replace all current SSRS reporting with AWS-reporting capabilities and dashboarding to track, manage, and report on all Veg Mgmt activity status. |  |  | By mid-2028: Move from a Mobile Data Platform hardware tool used for data collection to a newer and more functional tool such as I-Pad to improve efficiency, functionality, and worker safety. By 12/31/28: Integrate data modeling and predictive analytics to improve VM activity scheduling, risk management, project scoping, etc.
2120000073 | SDG&E | 2025-07-18 | Vegetation Management Enterprise System - Advanced Analytics | Enterprise Systems | Enterprise Systems Development |  | WMP.1464 | Qualitative |  | Vegetation Management Work Management System (PowerWorkz) and summary of actions taken in support of the qualitative target | WMP.1464-Vegetation Management Enterprise System - Advanced Analytics | 2026 | 2026 |  |  | By mid-2026: Complete and test v.2.0 of the Probability of Vegetation Contact (PoVC) model. Focus on model tuning and testing – including field-validation surveys with vegetation management subject matter experts.•By 12/31/2026: Test v.1.0 of the Probability of Hazard (POH) model. Focus on model tuning and testing – including field-validation surveys with vegetation management subject matter experts. •By 12/31/2026: Complete phase I of Vegetation Management data migration from PowerWorkz-Oracle to AWS. |  |  | By early 2027: Begin AWS data-product developments (phase II) to streamline operational analytics, reporting, and future model developments. •By mid-2027: Begin design and exploratory data analysis for a Vegetation Growth (VG) model.•By 12/31/2027: Conduct proof-of-concept (POC) study(ies) with applicable vendor(s) to better understand the efficacy of remote sensing technologies for identifying non-compliant vegetation. |  |  | By early 2028: Complete v.1.0 of data-product developments and integrate with existing models and reporting systems where applicable.•By 12/31/2028: Where applicable, continue investigating and/or begin implementing remote sensing technologies identified during POC study(ies) in 2027.•By 12/31/2028: Test/utilize risk models to develop indices for prioritizing and conducting targeted Off-Cycle HFTD inspections.

## Table 14
METRIC NUMBER | HFTD TIER | LINE TYPE | OVERALL UTILITY RISK | WILDFIRE RISK | OUTAGE PROGRAM RISK | WILDFIRE LIKELIHOOD | IGNITION LIKELIHOOD | EQUIPMENT CAUSED LIKELIHOOD OF IGNITION | CONTACT FROM VEGETATION LIKELIHOOD OF IGNITION | CONTACT FROM OBJECT LIKELIHOOD OF IGNITION | BURN LIKELIHOOD | WILDFIRE CONSEQUENCE | WILDFIRE HAZARD INTENSITY | WILDFIRE EXPOSURE POTENTIAL | PSPS RISK | PSPS LIKELIHOOD | PSPS CONSEQUENCE | PSPS EXPOSURE POTENTIAL | PSPS VULNERABILITY | PEDS RISK | PEDS LIKELIHOOD | PEDS CONSEQUENCE | PEDS EXPOSURE POTENTIAL | PEDS VULNERABILITY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR
2140000000 | HFTD Tier 2 | Distribution | 991611273.8784 | 940601834.2962 | 51009439.5822 |  | 6.2066 | 0.00217 | 0.000516 | 0.003344 |  | 151549208.8951 |  |  | 49600929.9678 | 28.7264 | 1726669.2223 |  |  | 1408509.6144 | 1.9841 | 709895.137 |  |  | - Wildfire Likelihood - Ignition Likelihood is reported from the WiNGS-Planning output and the likelihood of that ignition turning into a wildfire is accounted for directly in the Monte Carlo risk event simulation, leveraging probabilistic sampling of fire impact simulation distributions associated to a assessed ignition event occurrence. - Burn Likelihood - Subject matter expertise is used to select a representation of the worst fire weather days in the service territory and simulated ignition events are probabilistically mapped to days that fall within the temporal span of the worst fire weather day dataset. The burn probability is assumed to be 100% for these days represented worst fire weather days. - Wildfire Hazard Intensity - It's captured in Wildfire Consequence, not captured separately. - Wildfire Exposure Potential - It's captured in Wildfire Consequence, not captured separately. - PSPS Exposure Potential - Field not reportable because intermediate risk metric is not broken out within the model and is instead embedded within PSPS Consequence calculation, including count and type of customers expected to be impacted. - PSPS Vulnerability - Field not reportable because intermediate risk metric is not broken out within the model and is instead embedded within PSPS Consequence calculation, including count and type of vulnerable customers expected to be impacted. - PEDS Exposure Potential - Field not reportable because intermediate risk metric is not broken out within the model and is instead embedded within PEDS Consequence calculation, including count and type of customers expected to be impacted. | not applicable | SDG&E | 2026
2140000001 | HFTD Tier 3 | Distribution | 1911755775.9084 | 1870251871.4851 | 41503904.4233 |  | 6.8279 | 0.00181 | 0.000305 | 0.00202 |  | 273914417.7956 |  |  | 40122207.6768 | 55.6371 | 721141.5867 |  |  | 1381696.7465 | 1.946 | 710001.2243 |  |  | see row 2 | not applicable | SDG&E | 2026
2140000002 | HFTD Tier 2 | Transmision | [23 empty] | not applicable | SDG&E | 2026
2140000003 | HFTD Tier 3 | Transmision | [23 empty] | not applicable | SDG&E | 2026
2140000004 | Non-HFTD | Distribution | 129113916.2444 | 80962274.6895 | 48151641.5549 |  | 9.4663 | 0.006725 | 0.001993 | 0.009963 |  | 8552716.7518 |  |  | 45046438.7535 | 11.8474 | 3802211.7229 |  |  | 3105202.8015 | 4.3739 | 709943.6841 |  |  | see row 2 | not applicable | SDG&E | 2026
2140000005 | Non-HFTD | Transmision | [23 empty] | not applicable | SDG&E | 2026

## Table 15
METRIC NUMBER | TOP-RISK CIRCUIT / SEGMENT / SPAN ID | RISK GRANULARITY | LINE TYPE | CIRCUIT / SEGMENT / SPAN LENGTH (MI) | INCLUSION REASON | HFTD TIER | OVERALL UTILITY RISK | WILDFIRE RISK | OUTAGE PROGRAM RISK | WILDFIRE LIKELIHOOD | IGNITION LIKELIHOOD | EQUIPMENT CAUSED LIKELIHOOD OF IGNITION | CONTACT FROM VEGETATION LIKELIHOOD OF IGNITION | CONTACT FROM OBJECT LIKELIHOOD OF IGNITION | BURN LIKELIHOOD | WILDFIRE CONSEQUENCE | WILDFIRE HAZARD INTENSITY | WILDFIRE EXPOSURE POTENTIAL | PSPS RISK | PSPS LIKELIHOOD | PSPS CONSEQUENCE | PSPS EXPOSURE POTENTIAL | PSPS VULNERABILITY | PEDS RISK | PEDS LIKELIHOOD | PEDS CONSEQUENCE | PEDS EXPOSURE POTENTIAL | PEDS VULNERABILITY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR
2150000000 | 222-1986R | Segment-level | Distribution | 21.2556 | Both >1% and Top 5% | HFTD TIER 3 | 79194348.7939 | 78602169.7569 | 592179.037 |  | 0.06916 | 0 | 0 | 0 |  | 1136523170.2179 |  |  | 578529.8095 | 0.32662 | 1771280.0123 |  |  | 13649.2275 | 0.019293 | 707463.1219 |  |  | - Wildfire Likelihood - Ignition Likelihood is reported from the WiNGS-Planning output and the likelihood of that ignition turning into a wildfire is accounted for directly in the Monte Carlo risk event simulation, leveraging probabilistic sampling of fire impact simulation distributions associated to a assessed ignition event occurrence. - Burn Likelihood - Subject matter expertise is used to select a representation of the worst fire weather days in the service territory and simulated ignition events are probabilistically mapped to days that fall within the temporal span of the worst fire weather day dataset. The burn probability is assumed to be 100% for these days represented worst fire weather days. - Wildfire Hazard Intensity - It's captured in Wildfire Consequence, not captured separately. - Wildfire Exposure Potential - It's captured in Wildfire Consequence, not captured separately. - PSPS Exposure Potential - Field not reportable because intermediate risk metric is not broken out within the model and is instead embedded within PSPS Consequence calculation, including count and type of customers expected to be impacted. - PSPS Vulnerability - Field not reportable because intermediate risk metric is not broken out within the model and is instead embedded within PSPS Consequence calculation, including count and type of vulnerable customers expected to be impacted. - PEDS Exposure Potential - Field not reportable because intermediate risk metric is not broken out within the model and is instead embedded within PEDS Consequence calculation, including count and type of customers expected to be impacted. | not applicable | SDG&E | 2026
2150000001 | 237-30R | Segment-level | Distribution | 33.4712 | Both >1% and Top 5% | HFTD TIER 3 | 65515491.9922 | 64815658.7441 | 699833.2481 |  | 0.10832 | 0.000149 | 0 | 0.000131 |  | 598354357.5535 |  |  | 680055.5135 | 0.35613 | 1909564.5467 |  |  | 19777.7346 | 0.028031 | 705571.5356 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000002 | 909-451 | Segment-level | Distribution | 20.5957 | Both >1% and Top 5% | HFTD TIER 3 | 55252374.6886 | 54850768.6606 | 401606.028 |  | 0.065456 | 0 | 0 | 0 |  | 837974111.9376 |  |  | 388366.8417 | 0.22712 | 1709930.0722 |  |  | 13239.1863 | 0.018541 | 714041.5007 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000003 | 222-1990R | Segment-level | Distribution | 14.2375 | Both >1% and Top 5% | HFTD TIER 3 | 45106640.152 | 44939414.3997 | 167225.7524 |  | 0.063955 | 0 | 0 | 0 |  | 702670219.1481 |  |  | 158286.7628 | 0.33553 | 471755.9456 |  |  | 8938.9896 | 0.01263 | 707780.893 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000004 | 908-2038R | Segment-level | Distribution | 17.9266 | Both >1% and Top 5% | HFTD TIER 2 | 41258574.2326 | 40800963.6338 | 457610.5988 |  | 0.053569 | 5.34e-05 | 0 | 7.25e-05 |  | 761646828.8568 |  |  | 444898.9658 | 0.15924 | 2793970.2214 |  |  | 12711.633 | 0.017728 | 717037.0621 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000005 | 524-69R | Segment-level | Distribution | 34.1718 | Both >1% and Top 5% | HFTD TIER 3 | 40375330.9497 | 39985024.927 | 390306.0227 |  | 0.10118 | 8.54e-05 | 0 | 0.000189 |  | 395174544.0641 |  |  | 367710.4494 | 0.13969 | 2632301.7946 |  |  | 22595.5733 | 0.031761 | 711420.643 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000006 | 358-682F | Segment-level | Distribution | 12.5079 | Both >1% and Top 5% | HFTD TIER 3 | 37602118.365 | 37073060.587 | 529057.778 |  | 0.050627 | 6.4e-05 | 4.42e-05 | 7.25e-05 |  | 732284225.8219 |  |  | 521206.7954 | 0.48064 | 1084412 |  |  | 7850.9826 | 0.011152 | 703972.4683 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000007 | 1458-601R | Segment-level | Distribution | 15.4477 | Both >1% and Top 5% | HFTD TIER 3 | 37077301.9797 | 36838604.201 | 238697.7787 |  | 0.051536 | 0 | 0 | 0 |  | 714807479.7821 |  |  | 228042.0393 | 0.13764 | 1656783.7825 |  |  | 10655.7393 | 0.015035 | 708719.4945 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000008 | 1021-1748F | Segment-level | Distribution | 17.727 | Both >1% and Top 5% | HFTD TIER 3 | 35156122.4002 | 34811510.8905 | 344611.5097 |  | 0.051371 | 7.47e-05 | 0 | 4.35e-05 |  | 677643803.5648 |  |  | 331735.5921 | 0.096065 | 3453255.3313 |  |  | 12875.9176 | 0.0182 | 707475.777 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000009 | 909-805R | Segment-level | Distribution | 13.4184 | Both >1% and Top 5% | HFTD TIER 2 | 32313161.0224 | 32075252.6475 | 237908.3748 |  | 0.038947 | 7.47e-05 | 2.21e-05 | 0.000116 |  | 823570033.0078 |  |  | 228761.1805 | 0.2374 | 963629.3733 |  |  | 9147.1943 | 0.012868 | 710826.0782 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000010 | 237-2R | Segment-level | Distribution | 16.7242 | Both >1% and Top 5% | HFTD TIER 3 | 30894123.4063 | 30619728.0088 | 274395.3975 |  | 0.046938 | 4.27e-05 | 0 | 0.000145 |  | 652338554.5491 |  |  | 262352.8253 | 0.11764 | 2230147.9887 |  |  | 12042.5722 | 0.01698 | 709212.6249 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000011 | 971-2050R | Segment-level | Distribution | 20.7013 | Top 5% highest risk | HFTD TIER 3 | 28484583.8082 | 28174790.2275 | 309793.5808 |  | 0.060319 | 0 | 0 | 0 |  | 467096441.0464 |  |  | 294674.2035 | 0.10307 | 2858910.5844 |  |  | 15119.3772 | 0.021251 | 711453.2328 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000012 | 1030-42R | Segment-level | Distribution | 16.7214 | Top 5% highest risk | HFTD TIER 3 | 28398789.4867 | 27971255.8292 | 427533.6574 |  | 0.048528 | 2.13e-05 | 0 | 5.8e-05 |  | 576391785.1732 |  |  | 416330.7729 | 0.21804 | 1909451.8581 |  |  | 11202.8845 | 0.015712 | 713032.6969 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000013 | 237-1765R | Segment-level | Distribution | 8.3421 | Top 5% highest risk | HFTD TIER 3 | 28249252.4704 | 28064039.1156 | 185213.3548 |  | 0.02585 | 4.27e-05 | 0 | 5.8e-05 |  | 1085666281.7071 |  |  | 179613.607 | 0.22538 | 796925.4454 |  |  | 5599.7477 | 0.0078522 | 713143.7951 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000014 | 237-17R | Segment-level | Distribution | 14.6369 | Top 5% highest risk | HFTD TIER 2 | 27080737.569 | 26780685.6631 | 300051.9059 |  | 0.034759 | 4.27e-05 | 2.21e-05 | 0.000131 |  | 770467667.7423 |  |  | 290058.8995 | 0.1066 | 2721120.2313 |  |  | 9993.0064 | 0.014037 | 711924.9982 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000015 | 907-1716R | Segment-level | Distribution | 12.7815 | Top 5% highest risk | HFTD TIER 3 | 27066455.1952 | 26848173.2279 | 218281.9673 |  | 0.03686 | 5.34e-05 | 0 | 2.9e-05 |  | 728374440.536 |  |  | 210320.852 | 0.039975 | 5261335.9407 |  |  | 7961.1153 | 0.011214 | 709926.4623 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000016 | 1030-989R | Segment-level | Distribution | 19.582 | Top 5% highest risk | HFTD TIER 3 | 26696216.0546 | 26471622.1415 | 224593.9132 |  | 0.068619 | 4.27e-05 | 0 | 2.9e-05 |  | 385779105.6866 |  |  | 212509.788 | 0.22133 | 960128.2222 |  |  | 12084.1251 | 0.017072 | 707824.7156 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000017 | 214-1122R | Segment-level | Distribution | 19.9074 | Top 5% highest risk | HFTD TIER 3 | 26281150.1655 | 25993614.3166 | 287535.8489 |  | 0.066356 | 6.4e-05 | 0 | 2.9e-05 |  | 391728494.3465 |  |  | 275469.895 | 0.18583 | 1482358.2509 |  |  | 12065.9539 | 0.016987 | 710288.4459 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000018 | 599-19R | Segment-level | Distribution | 27.9316 | Top 5% highest risk | HFTD TIER 2 | 25743456.0826 | 25588004.7565 | 155451.3261 |  | 0.079701 | 0.000171 | 2.21e-05 | 0.000131 |  | 321051595.0504 |  |  | 135218.1509 | 0.043361 | 3118427.8715 |  |  | 20233.1752 | 0.028552 | 708647.9731 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000019 | 1030-20R | Segment-level | Distribution | 15.7168 | Top 5% highest risk | HFTD TIER 3 | 25318461.9928 | 25101310.8982 | 217151.0946 |  | 0.049346 | 1.07e-05 | 0 | 0.000116 |  | 508679749.0822 |  |  | 206672.9701 | 0.22257 | 928590.9997 |  |  | 10478.1245 | 0.014767 | 709582.7383 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000020 | 235-899R | Segment-level | Distribution | 14.5858 | Top 5% highest risk | HFTD TIER 2 | 23678661.1441 | 23291809.548 | 386851.5961 |  | 0.034984 | 5.34e-05 | 0 | 5.8e-05 |  | 665780825.2869 |  |  | 377288.9261 | 0.10653 | 3541661.2793 |  |  | 9562.67 | 0.013452 | 710884.045 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000021 | 351-819R | Segment-level | Distribution | 12.622 | Top 5% highest risk | HFTD TIER 2 | 23517427.5477 | 23341044.154 | 176383.3936 |  | 0.035805 | 5.34e-05 | 2.21e-05 | 5.8e-05 |  | 651886144.3816 |  |  | 168384.291 | 0.096696 | 1741378.0405 |  |  | 7999.1026 | 0.011257 | 710576.5769 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000022 | 972-1590F | Segment-level | Distribution | 20.6608 | Top 5% highest risk | HFTD TIER 3 | 23409153.8603 | 23032887.7606 | 376266.0997 |  | 0.04905 | 0 | 0 | 1.45e-05 |  | 469581685.564 |  |  | 362302.0188 | 0.10726 | 3377886.9332 |  |  | 13964.0809 | 0.019725 | 707945.3739 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000023 | 972-32R | Segment-level | Distribution | 15.6835 | Top 5% highest risk | HFTD TIER 2 | 22914328.3826 | 22336491.2466 | 577837.136 |  | 0.042044 | 4.27e-05 | 2.21e-05 | 7.25e-05 |  | 531264657.1833 |  |  | 567712.7582 | 0.10987 | 5166990.6003 |  |  | 10124.3777 | 0.014154 | 715281.3078 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000024 | 908-2055F | Segment-level | Distribution | 11.56 | Top 5% highest risk | HFTD TIER 3 | 22564078.3354 | 22357448.5426 | 206629.7928 |  | 0.032573 | 3.2e-05 | 0 | 7.25e-05 |  | 686375564.6549 |  |  | 198388.4941 | 0.15939 | 1244657.7879 |  |  | 8241.2987 | 0.011582 | 711536.3559 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000025 | 214-647R | Segment-level | Distribution | 11.3022 | Top 5% highest risk | HFTD TIER 3 | 22354308.5327 | 22185077.5014 | 169231.0313 |  | 0.042459 | 4.27e-05 | 0 | 2.9e-05 |  | 522500965.6604 |  |  | 163192.3476 | 0.18745 | 870582.9851 |  |  | 6038.6837 | 0.0085248 | 708366.6116 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000026 | 236-1569R | Segment-level | Distribution | 16.0076 | Top 5% highest risk | HFTD TIER 3 | 21222913.1191 | 20875680.9896 | 347232.1295 |  | 0.043476 | 0 | 0 | 0 |  | 480165631.3726 |  |  | 336363.0898 | 0.1556 | 2161647.0536 |  |  | 10869.0397 | 0.015264 | 712060.8837 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000027 | 354-1706R | Segment-level | Distribution | 18.9327 | Top 5% highest risk | HFTD TIER 2 | 20510259.2469 | 20339348.0468 | 170911.2001 |  | 0.055314 | 0 | 0 | 0 |  | 367707055.1183 |  |  | 158498.2239 | 0.06656 | 2381283.4113 |  |  | 12412.9762 | 0.017515 | 708697.3715 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000028 | 79-808R | Segment-level | Distribution | 10.6674 | Top 5% highest risk | HFTD TIER 3 | 19978325.502 | 19824672.4607 | 153653.0413 |  | 0.041448 | 3.2e-05 | 0 | 2.9e-05 |  | 478302269.3676 |  |  | 146900.5349 | 0.39463 | 372252.3616 |  |  | 6752.5064 | 0.0095556 | 706654.3612 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000029 | 215-1534R | Segment-level | Distribution | 7.8127 | Top 5% highest risk | HFTD TIER 2 | 19489706.3687 | 19294168.695 | 195537.6737 |  | 0.022842 | 2.13e-05 | 0 | 1.45e-05 |  | 844672084.783 |  |  | 189765.6478 | 0.1672 | 1134934.8571 |  |  | 5772.0259 | 0.0081584 | 707494.8345 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000030 | 1021-25R | Segment-level | Distribution | 6.9741 | Top 5% highest risk | HFTD TIER 3 | 18825689.9208 | 18768978.8338 | 56711.087 |  | 0.020462 | 1.07e-05 | 0 | 0 |  | 917269195.9539 |  |  | 52369.3413 | 0.096999 | 539896.7951 |  |  | 4341.7458 | 0.0061486 | 706135.6656 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000031 | 79-785 | Segment-level | Distribution | 13.604 | Top 5% highest risk | HFTD TIER 3 | 18780928.5331 | 18244488.231 | 536440.3021 |  | 0.037654 | 2.13e-05 | 0 | 8.7e-05 |  | 484524736.312 |  |  | 528026.7206 | 0.33071 | 1596659.2823 |  |  | 8413.5815 | 0.011868 | 708918.0775 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000032 | 597-595 | Segment-level | Distribution | 17.4555 | Top 5% highest risk | HFTD TIER 2 | 18774393.9857 | 17938778.6421 | 835615.3436 |  | 0.050052 | 7.47e-05 | 2.21e-05 | 5.8e-05 |  | 358404266.0221 |  |  | 823747.1843 | 0.086229 | 9552973.6291 |  |  | 11868.1593 | 0.016785 | 707086.2186 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000033 | 157-81R | Segment-level | Distribution | 27.7907 | Top 5% highest risk | HFTD TIER 3 | 18749596.2803 | 18188039.2067 | 561557.0736 |  | 0.083238 | 7.47e-05 | 2.21e-05 | 7.25e-05 |  | 218505391.8226 |  |  | 543833.1499 | 0.27592 | 1971009.836 |  |  | 17723.9237 | 0.024981 | 709501.8452 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000034 | 352-27R | Segment-level | Distribution | 13.0331 | Top 5% highest risk | HFTD TIER 3 | 18614182.3412 | 18495148.8145 | 119033.5267 |  | 0.039108 | 2.13e-05 | 0 | 4.35e-05 |  | 472920109.6055 |  |  | 110352.5408 | 0.066819 | 1651519.3443 |  |  | 8680.986 | 0.012208 | 711089.9386 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000035 | 79-679R | Segment-level | Distribution | 7.3706 | Top 5% highest risk | HFTD TIER 3 | 18448582.7599 | 18245131.6107 | 203451.1492 |  | 0.025346 | 0 | 0 | 0 |  | 719836962.1763 |  |  | 198973.2731 | 0.36216 | 549411.6449 |  |  | 4477.8761 | 0.0063992 | 699755.6103 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000036 | 357-45R | Segment-level | Distribution | 11.815 | Top 5% highest risk | HFTD TIER 3 | 17696752.5099 | 17249773.4593 | 446979.0506 |  | 0.039295 | 6.4e-05 | 0 | 8.7e-05 |  | 438976914.837 |  |  | 438470.3008 | 0.13401 | 3271814.826 |  |  | 8508.7498 | 0.01207 | 704950.271 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000037 | 357-2049F | Segment-level | Distribution | 7.806 | Top 5% highest risk | HFTD TIER 3 | 16869708.0077 | 16664984.6208 | 204723.3869 |  | 0.020362 | 3.2e-05 | 4.42e-05 | 2.9e-05 |  | 818435547.6271 |  |  | 199776.3295 | 0.15549 | 1284799.6845 |  |  | 4947.0574 | 0.0070088 | 705835.1545 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000038 | 222-2085 | Segment-level | Distribution | 31.2755 | Top 5% highest risk | HFTD TIER 3 | 16772308.2179 | 16218058.7657 | 554249.4522 |  | 0.11419 | 0 | 0 | 0 |  | 142026215.518 |  |  | 533521.2809 | 0.20777 | 2567867.8493 |  |  | 20728.1713 | 0.029211 | 709611.2804 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000039 | 470-47R | Segment-level | Distribution | 24.3072 | Top 5% highest risk | HFTD TIER 3 | 16740391.1537 | 16634976.6647 | 105414.489 |  | 0.074311 | 0.000139 | 2.21e-05 | 0.000116 |  | 223857385.9547 |  |  | 89813.4696 | 0.066092 | 1358924.1242 |  |  | 15601.0193 | 0.021852 | 713953.1799 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000040 | 356-19R | Segment-level | Distribution | 24.1038 | Top 5% highest risk | HFTD TIER 3 | 16012786.3517 | 15654557.522 | 358228.8297 |  | 0.06528 | 4.27e-05 | 2.21e-05 | 7.25e-05 |  | 239805599.8913 |  |  | 343518.1164 | 0.081694 | 4204916.3275 |  |  | 14710.7133 | 0.02078 | 707940.1568 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000041 | 1458-1131R | Segment-level | Distribution | 6.1667 | Top 5% highest risk | HFTD TIER 3 | 15987426.5024 | 15842278.1898 | 145148.3126 |  | 0.017363 | 3.2e-05 | 0 | 4.35e-05 |  | 912436973.1389 |  |  | 142065.243 | 0.13775 | 1031359.5718 |  |  | 3083.0696 | 0.0043008 | 716859.5538 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000042 | 1039-13 | Segment-level | Distribution | 16.5898 | Top 5% highest risk | HFTD TIER 2 | 15957171.1285 | 15550885.1225 | 406286.006 |  | 0.047778 | 1.07e-05 | 6.63e-05 | 5.8e-05 |  | 325483490.7113 |  |  | 394286.4327 | 0.070461 | 5595842.6796 |  |  | 11999.5733 | 0.016862 | 711625.6041 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000043 | 908-1172R | Segment-level | Distribution | 10.1766 | Top 5% highest risk | HFTD TIER 2 | 15766518.7901 | 15502577.8274 | 263940.9627 |  | 0.030402 | 1.07e-05 | 0 | 8.7e-05 |  | 509923025.1972 |  |  | 256475.2349 | 0.16599 | 1545165.5743 |  |  | 7465.7277 | 0.010535 | 708659.4902 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000044 | 73-1163 | Segment-level | Distribution | 11.2661 | Top 5% highest risk | HFTD TIER 3 | 15337184.9109 | 15116478.9066 | 220706.0043 |  | 0.035859 | 0 | 0 | 0 |  | 421557977.9076 |  |  | 213658.0418 | 0.17934 | 1191330.8604 |  |  | 7047.9625 | 0.0098612 | 714716.515 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000045 | 971-1973R | Segment-level | Distribution | 10.9521 | Top 5% highest risk | HFTD TIER 3 | 15148796.1922 | 15005297.4007 | 143498.7915 |  | 0.032871 | 3.2e-05 | 0 | 2.9e-05 |  | 456490444.4845 |  |  | 135833.4004 | 0.10329 | 1315116.6414 |  |  | 7665.3911 | 0.010883 | 704345.408 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000046 | 971-383R | Segment-level | Distribution | 9.7066 | Top 5% highest risk | HFTD TIER 3 | 14770596.2279 | 14538988.9378 | 231607.2901 |  | 0.026 | 9.61e-05 | 0 | 0.000131 |  | 559196183.7318 |  |  | 225764.1919 | 0.1041 | 2168686.7269 |  |  | 5843.0982 | 0.0082674 | 706763.6994 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000047 | CB 351 | Segment-level | Distribution | 6.7335 | Top 5% highest risk | HFTD TIER 2 | 14599735.2229 | 14550361.9113 | 49373.3116 |  | 0.02064 | 1.07e-05 | 2.21e-05 | 0 |  | 704959394.928 |  |  | 44586.1651 | 0.097301 | 458229.2582 |  |  | 4787.1465 | 0.0066938 | 715161.2714 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000048 | 78-26R | Segment-level | Distribution | 6.3703 | Top 5% highest risk | HFTD TIER 3 | 14526726.8022 | 14317113.3624 | 209613.4398 |  | 0.019201 | 0 | 0 | 2.9e-05 |  | 745644151.9942 |  |  | 205179.4477 | 0.32027 | 640649.2302 |  |  | 4433.9921 | 0.0062056 | 714514.6484 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000049 | 216-1859F | Segment-level | Distribution | 8.4771 | Top 5% highest risk | HFTD TIER 3 | 14041287.7051 | 13926878.6549 | 114409.0502 |  | 0.024139 | 0 | 0 | 0 |  | 576935576.4799 |  |  | 108865.6056 | 0.12517 | 869735.0474 |  |  | 5543.4446 | 0.0077338 | 716781.4761 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000050 | 350-2192R | Segment-level | Distribution | 31.8811 | Top 5% highest risk | HFTD TIER 2 | 13871622.229 | 13613237.5993 | 258384.6298 |  | 0.090414 | 0.000139 | 2.21e-05 | 0.000131 |  | 150565926.875 |  |  | 235593.9222 | 0.066794 | 3527171.9341 |  |  | 22790.7076 | 0.032069 | 710681.6466 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000051 | 524-46R | Segment-level | Distribution | 12.3091 | Top 5% highest risk | HFTD TIER 3 | 13710953.333 | 13572074.1792 | 138879.1538 |  | 0.037121 | 3.2e-05 | 0 | 2.9e-05 |  | 365621088.539 |  |  | 131033.6277 | 0.14094 | 929716.0883 |  |  | 7845.5261 | 0.011096 | 707071.6974 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000052 | 353-904R | Segment-level | Distribution | 7.0653 | Top 5% highest risk | HFTD TIER 2 | 13534406.6532 | 13457602.2771 | 76804.3761 |  | 0.021143 | 3.2e-05 | 0 | 0 |  | 636509936.1043 |  |  | 71457.012 | 0.097148 | 735550.9762 |  |  | 5347.3641 | 0.0074806 | 714830.9066 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000053 | 350-2201R | Segment-level | Distribution | 14.5687 | Top 5% highest risk | HFTD TIER 3 | 13521745.4458 | 13424968.4125 | 96777.0333 |  | 0.043861 | 4.27e-05 | 0 | 4.35e-05 |  | 306079852.5461 |  |  | 87426.2339 | 0.067022 | 1304444.7321 |  |  | 9350.7993 | 0.013221 | 707290.0861 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000054 | 176-197F | Segment-level | Distribution | 13.767 | Top 5% highest risk | HFTD TIER 3 | 13172958.0173 | 12751842.4782 | 421115.5391 |  | 0.042242 | 5.34e-05 | 0 | 4.35e-05 |  | 301873058.3068 |  |  | 411525.6854 | 0.17673 | 2328529.5555 |  |  | 9589.8537 | 0.013442 | 713424.6185 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000055 | 970-1341R | Segment-level | Distribution | 4.3966 | Top 5% highest risk | HFTD TIER 3 | 12961613.4298 | 12917271.9445 | 44341.4853 |  | 0.013534 | 2.13e-05 | 0 | 2.9e-05 |  | 954402998.6211 |  |  | 41466.4897 | 0.10732 | 386366.6324 |  |  | 2874.9955 | 0.0041086 | 699750.6537 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000056 | CB 236 | Segment-level | Distribution | 9.3687 | Top 5% highest risk | HFTD TIER 2 | 12711187.7649 | 12408602.1726 | 302585.5923 |  | 0.02168 | 2.13e-05 | 0 | 8.7e-05 |  | 572352498.735 |  |  | 296581.1054 | 0.11179 | 2653105.4347 |  |  | 6004.487 | 0.0084302 | 712259.1362 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000057 | 215-1531R | Segment-level | Distribution | 8.4597 | Top 5% highest risk | HFTD TIER 2 | 12702411.9104 | 12475572.5359 | 226839.3745 |  | 0.026648 | 1.07e-05 | 0 | 5.8e-05 |  | 468161683.2733 |  |  | 220695.3654 | 0.16755 | 1317169.0681 |  |  | 6144.0091 | 0.00871 | 705397.1415 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000058 | 79-658R | Segment-level | Distribution | 9.5078 | Top 5% highest risk | HFTD TIER 3 | 12321075.9006 | 12230390.8778 | 90685.0227 |  | 0.034298 | 1.07e-05 | 0 | 0 |  | 356587796.4522 |  |  | 84071.8795 | 0.42302 | 198743.8767 |  |  | 6613.1432 | 0.0092374 | 715909.5901 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000059 | 521-32R | Segment-level | Distribution | 9.9971 | Top 5% highest risk | HFTD TIER 3 | 12241713.4625 | 12165680.2675 | 76033.1949 |  | 0.031334 | 4.27e-05 | 0 | 2.9e-05 |  | 388263087.1507 |  |  | 69068.987 | 0.10731 | 643655.3959 |  |  | 6964.2079 | 0.0097964 | 710894.6019 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000060 | 182-2240F | Segment-level | Distribution | 13.8138 | Top 5% highest risk | HFTD TIER 2 | 11917198.9064 | 11236831.9909 | 680366.9155 |  | 0.038653 | 2.13e-05 | 2.21e-05 | 5.8e-05 |  | 290707466.6365 |  |  | 673429.9826 | 0.097041 | 6939615.2837 |  |  | 6936.9329 | 0.0098096 | 707157.568 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000061 | 1030-1777 | Segment-level | Distribution | 5.7761 | Top 5% highest risk | HFTD TIER 3 | 11817577.2193 | 11650337.6053 | 167239.614 |  | 0.016484 | 0 | 0 | 0 |  | 706766416.2424 |  |  | 163206.4337 | 0.22414 | 728158.7041 |  |  | 4033.1803 | 0.0056742 | 710792.7681 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000062 | 908-1236 | Segment-level | Distribution | 5.4265 | Top 5% highest risk | HFTD TIER 2 | 11763931.114 | 11622998.1269 | 140932.9872 |  | 0.015917 | 0 | 0 | 1.45e-05 |  | 730207076.9634 |  |  | 137018.798 | 0.16628 | 824014.6139 |  |  | 3914.1891 | 0.005501 | 711541.3789 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000063 | 357-750R | Segment-level | Distribution | 8.4165 | Top 5% highest risk | HFTD TIER 2 | 11757625.4162 | 11499648.1899 | 257977.2263 |  | 0.027182 | 1.07e-05 | 4.42e-05 | 5.8e-05 |  | 423061150.3902 |  |  | 251929.878 | 0.13533 | 1861580.1679 |  |  | 6047.3483 | 0.0084898 | 712307.5056 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000064 | 1250-677R | Segment-level | Distribution | 9.4852 | Top 5% highest risk | HFTD TIER 2 | 11748908.7781 | 11662207.457 | 86701.321 |  | 0.029543 | 2.13e-05 | 0 | 2.9e-05 |  | 394756335.1151 |  |  | 80325.5814 | 0.078076 | 1028810.078 |  |  | 6375.7396 | 0.0089662 | 711086.0349 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000065 | 442-728R | Segment-level | Distribution | 22.2475 | Top 5% highest risk | HFTD TIER 3 | 11572220.9733 | 10238670.5132 | 1333550.46 |  | 0.077879 | 6.4e-05 | 8.84e-05 | 5.8e-05 |  | 131468614.3829 |  |  | 1319166.7287 | 0.25987 | 5076268.0357 |  |  | 14383.7313 | 0.020269 | 709627.8789 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000066 | 176-161R | Segment-level | Distribution | 10.6068 | Top 5% highest risk | HFTD TIER 3 | 11523304.9395 | 11381448.7362 | 141856.2032 |  | 0.033477 | 0.000117 | 0 | 4.35e-05 |  | 339976125.1312 |  |  | 135086.7031 | 0.18118 | 745579.0874 |  |  | 6769.5001 | 0.0095082 | 711964.416 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000067 | CB 971 | Segment-level | Distribution | 5.1074 | Top 5% highest risk | HFTD TIER 2 | 11456698.0576 | 11400370.6961 | 56327.3614 |  | 0.014194 | 2.13e-05 | 0 | 5.8e-05 |  | 803182379.6063 |  |  | 52343.6236 | 0.10551 | 496109.5304 |  |  | 3983.7379 | 0.0055742 | 714674.3737 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000068 | 521-14R | Segment-level | Distribution | 12.6964 | Top 5% highest risk | HFTD TIER 3 | 11350287.4351 | 10974724.5582 | 375562.877 |  | 0.038563 | 3.2e-05 | 0 | 2.9e-05 |  | 284595036.5942 |  |  | 366912.4365 | 0.22026 | 1665846.8766 |  |  | 8650.4405 | 0.012147 | 712146.2483 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000069 | 524-27R | Segment-level | Distribution | 14.5985 | Top 5% highest risk | HFTD TIER 3 | 11317694.2402 | 11291558.1537 | 26136.0865 |  | 0.040777 | 3.2e-05 | 0 | 0.000116 |  | 276909977.5296 |  |  | 16005.7023 | 0.0051862 | 3086210.0088 |  |  | 10130.3841 | 0.014244 | 711203.6038 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000070 | CB 355 | Segment-level | Distribution | 8.9743 | Top 5% highest risk | HFTD TIER 2 | 11288352.5173 | 11157038.9975 | 131313.5198 |  | 0.028263 | 6.4e-05 | 2.21e-05 | 2.9e-05 |  | 394752188.2543 |  |  | 125214.8711 | 0.068013 | 1841043.1998 |  |  | 6098.6487 | 0.008527 | 715216.2174 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000071 | 971-388R | Segment-level | Distribution | 17.9011 | Top 5% highest risk | HFTD TIER 3 | 11267961.0269 | 11152745.4958 | 115215.5311 |  | 0.05522 | 4.27e-05 | 0 | 5.8e-05 |  | 201969313.5785 |  |  | 104058.5439 | 0.10534 | 987814.4168 |  |  | 11156.9873 | 0.015858 | 703564.6358 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000072 | 350-41R | Segment-level | Distribution | 16.422 | Top 5% highest risk | HFTD TIER 2 | 11201388.8952 | 11075404.026 | 125984.8692 |  | 0.046008 | 3.2e-05 | 0 | 2.9e-05 |  | 240728833.5023 |  |  | 114551.2268 | 0.066869 | 1713074.3609 |  |  | 11433.6424 | 0.016086 | 710764.5218 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000073 | 217-835R | Segment-level | Distribution | 18.3176 | Top 5% highest risk | HFTD TIER 3 | 10686932.5847 | 10546229.7286 | 140702.8561 |  | 0.058771 | 3.2e-05 | 0 | 4.35e-05 |  | 179446150.7997 |  |  | 130572.3311 | 0.21117 | 618333.3055 |  |  | 10130.5249 | 0.014184 | 714242.1477 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000074 | 445-18R | Segment-level | Distribution | 24.8581 | Top 5% highest risk | HFTD TIER 2 | 10619796.7202 | 10161861.8372 | 457934.8829 |  | 0.1044 | 0 | 0 | 1.45e-05 |  | 97337892.5346 |  |  | 443951.1893 | 0.4807 | 923552.6178 |  |  | 13983.6937 | 0.019698 | 709904.2371 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000075 | 73-678R | Segment-level | Distribution | 14.1729 | Top 5% highest risk | HFTD TIER 3 | 10591376.886 | 10412424.065 | 178952.821 |  | 0.044606 | 2.13e-05 | 0 | 2.9e-05 |  | 233431019.7062 |  |  | 170038.0398 | 0.18066 | 941194.2735 |  |  | 8914.7812 | 0.012491 | 713684.929 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000076 | CB RA1 | Segment-level | Distribution | 9.6284 | Top 5% highest risk | HFTD TIER 2 | 10517062.3511 | 10338977.3236 | 178085.0275 |  | 0.023161 | 6.4e-05 | 2.21e-05 | 5.8e-05 |  | 446392126.6432 |  |  | 170320.8051 | 0.11319 | 1504792.1742 |  |  | 7764.2223 | 0.010915 | 711348.1093 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000077 | 357-50R | Segment-level | Distribution | 10.8632 | Top 5% highest risk | HFTD TIER 3 | 10432488.7437 | 10123494.7451 | 308993.9986 |  | 0.033132 | 1.07e-05 | 0 | 2.9e-05 |  | 305546677.7276 |  |  | 300831.8477 | 0.10455 | 2877424.4391 |  |  | 8162.1509 | 0.011445 | 713138.1076 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000078 | 1166-342R | Segment-level | Distribution | 11.5801 | Top 5% highest risk | HFTD TIER 3 | 10322641.9923 | 10227749.4926 | 94892.4997 |  | 0.037336 | 2.13e-05 | 2.21e-05 | 5.8e-05 |  | 273935073.8844 |  |  | 88974.2171 | 0.17309 | 514020.756 |  |  | 5918.2825 | 0.0083452 | 709184.0269 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000079 | 789-4R | Segment-level | Distribution | 12.3028 | Top 5% highest risk | HFTD TIER 2 | 10274005.9159 | 10265348.9348 | 8656.9811 |  | 0.038017 | 6.4e-05 | 0 | 0.000145 |  | 270022804.1123 |  |  | 0 | 0 | 0 |  |  | 8656.9811 | 0.012263 | 705954.6804 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000080 | 217-983R | Segment-level | Distribution | 6.8811 | Top 5% highest risk | HFTD TIER 3 | 10116962.9104 | 10020803.7313 | 96159.1791 |  | 0.025816 | 0 | 0 | 0 |  | 388156510.2518 |  |  | 92061.404 | 0.21217 | 433912.1445 |  |  | 4097.7751 | 0.0058128 | 704957.1734 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000081 | 1166-18R | Segment-level | Distribution | 7.5917 | Top 5% highest risk | HFTD TIER 3 | 10108490.1387 | 10085269.383 | 23220.7557 |  | 0.034692 | 2.13e-05 | 0 | 1.45e-05 |  | 290710467.1131 |  |  | 19839.3591 | 0.1742 | 113890.4909 |  |  | 3381.3966 | 0.004761 | 710228.2308 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000082 | 176-1834R | Segment-level | Distribution | 13.5415 | Top 5% highest risk | HFTD TIER 3 | 10068516.8214 | 9779526.9047 | 288989.9167 |  | 0.041194 | 4.27e-05 | 0 | 4.35e-05 |  | 237401730.9484 |  |  | 280260.2381 | 0.1786 | 1569230.8618 |  |  | 8729.6787 | 0.012255 | 712359.3328 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000083 | 1022-17F | Segment-level | Distribution | 4.5633 | Top 5% highest risk | HFTD TIER 3 | 9800679.2209 | 9763526.9192 | 37152.3017 |  | 0.014095 | 3.2e-05 | 0 | 0 |  | 692714012.4009 |  |  | 33870.5622 | 0.090782 | 373096.9534 |  |  | 3281.7394 | 0.0045734 | 717571.049 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000084 | 236-1535R | Segment-level | Distribution | 7.8693 | Top 5% highest risk | HFTD TIER 3 | 9719042.1331 | 9595870.9957 | 123171.1375 |  | 0.020791 | 0 | 0 | 0 |  | 461535216.6139 |  |  | 117498.9316 | 0.099676 | 1178806.2912 |  |  | 5672.2058 | 0.0080044 | 708635.9787 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000085 | 79-676R | Segment-level | Distribution | 4.5924 | Top 5% highest risk | HFTD TIER 3 | 9714146.4463 | 9547621.9773 | 166524.469 |  | 0.01407 | 3.2e-05 | 0 | 2.9e-05 |  | 678560806.8918 |  |  | 163732.4612 | 0.36609 | 447251.8483 |  |  | 2792.0078 | 0.003935 | 709531.8365 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000086 | 445-1311R | Segment-level | Distribution | 13.2995 | Top 5% highest risk | HFTD TIER 3 | 9632590.7157 | 9146838.7204 | 485751.9953 |  | 0.068253 | 2.13e-05 | 0 | 2.9e-05 |  | 134012938.8486 |  |  | 478216.1764 | 0.45906 | 1041725.0497 |  |  | 7535.8189 | 0.010607 | 710470.5371 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000087 | 222-1433R | Segment-level | Distribution | 6.2775 | Top 5% highest risk | HFTD TIER 3 | 9617971.1979 | 9578744.2722 | 39226.9257 |  | 0.023884 | 0 | 0 | 0 |  | 401059483.1679 |  |  | 35404.348 | 0.34341 | 103097.6996 |  |  | 3822.5777 | 0.0053688 | 711998.5221 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000088 | 1023-46AE | Segment-level | Distribution | 19.1678 | Top 5% highest risk | HFTD TIER 2 | 9469914.9237 | 9089006.5352 | 380908.3885 |  | 0.053269 | 4.27e-05 | 2.21e-05 | 0.000102 |  | 170623407.3451 |  |  | 367772.8429 | 0.06737 | 5459000.1915 |  |  | 13135.5456 | 0.018496 | 710190.7225 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000089 | RA1-402R | Segment-level | Distribution | 3.8122 | Top 5% highest risk | HFTD TIER 3 | 9339337.8204 | 9276378.8281 | 62958.9923 |  | 0.010942 | 1.07e-05 | 0 | 1.45e-05 |  | 847761768.9371 |  |  | 60319.6363 | 0.11483 | 525313.3988 |  |  | 2639.356 | 0.0037094 | 711531.7771 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000090 | 356-30AE | Segment-level | Distribution | 20.8132 | Top 5% highest risk | HFTD TIER 3 | 9294675.1195 | 8868205.8361 | 426469.2834 |  | 0.054258 | 1.07e-05 | 0 | 7.25e-05 |  | 163444527.0232 |  |  | 412482.4657 | 0.067045 | 6152304.2023 |  |  | 13986.8177 | 0.019755 | 708014.0571 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000091 | 73-683R | Segment-level | Distribution | 10.907 | Top 5% highest risk | HFTD TIER 3 | 9288032.8798 | 9142043.2186 | 145989.6612 |  | 0.035917 | 1.07e-05 | 0 | 2.9e-05 |  | 254535318.4502 |  |  | 138780.9856 | 0.18109 | 766380.7934 |  |  | 7208.6755 | 0.010155 | 709850.6698 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000092 | 353-1429R | Segment-level | Distribution | 5.9518 | Top 5% highest risk | HFTD TIER 2 | 9221802.1839 | 8990135.5043 | 231666.6796 |  | 0.017677 | 0 | 0 | 0 |  | 508572370.3038 |  |  | 226573.8474 | 0.096588 | 2345766.6488 |  |  | 5092.8322 | 0.0071466 | 712623.0958 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000093 | 972-942R | Segment-level | Distribution | 7.8388 | Top 5% highest risk | HFTD TIER 3 | 9149683.626 | 9068839.1214 | 80844.5047 |  | 0.022654 | 1.07e-05 | 0 | 7.25e-05 |  | 400312483.2864 |  |  | 75954.7616 | 0.11241 | 675721.6432 |  |  | 4889.7431 | 0.0068852 | 710181.7077 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000094 | 351-871R | Segment-level | Distribution | 4.4941 | Top 5% highest risk | HFTD TIER 3 | 9144312.3619 | 9119653.5616 | 24658.8003 |  | 0.013276 | 0 | 0 | 1.45e-05 |  | 686948504.1442 |  |  | 21681.8052 | 0.097253 | 222941.8183 |  |  | 2976.995 | 0.004152 | 717002.6551 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000095 | 788-34R | Segment-level | Distribution | 16.0985 | Top 5% highest risk | HFTD TIER 2 | 9132236.5922 | 8614677.8722 | 517558.72 |  | 0.043828 | 8.54e-05 | 2.21e-05 | 0.000174 |  | 196557387.5982 |  |  | 506521.4185 | 0.064673 | 7832038.3857 |  |  | 11037.3015 | 0.015543 | 710123.1125 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000096 | 448-744R | Segment-level | Distribution | 29.2157 | Top 5% highest risk | HFTD TIER 3 | 9104561.6318 | 8347199.644 | 757361.9878 |  | 0.091514 | 0 | 0 | 0 |  | 91211870.9619 |  |  | 739812.5409 | 0.37815 | 1956396.5808 |  |  | 17549.4469 | 0.024753 | 708982.6251 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000097 | 907-1702R | Segment-level | Distribution | 5.3095 | Top 5% highest risk | HFTD TIER 3 | 9100558.2495 | 9075653.9508 | 24904.2988 |  | 0.015464 | 5.34e-05 | 2.21e-05 | 0 |  | 586889158.7403 |  |  | 21331.0684 | 0.040564 | 525862.0548 |  |  | 3573.2304 | 0.0050506 | 707486.3107 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000098 | 521-700R | Segment-level | Distribution | 13.3513 | Top 5% highest risk | HFTD TIER 2 | 9012544.5994 | 8927133.7418 | 85410.8576 |  | 0.036793 | 7.47e-05 | 2.21e-05 | 4.35e-05 |  | 242629989.8305 |  |  | 75930.6611 | 0.024382 | 3114209.7075 |  |  | 9480.1965 | 0.013245 | 715735.0077 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000099 | 524-50R | Segment-level | Distribution | 10.5116 | Top 5% highest risk | HFTD TIER 3 | 8801876.9717 | 8643494.7957 | 158382.176 |  | 0.032024 | 5.34e-05 | 0 | 7.25e-05 |  | 269910153.6273 |  |  | 151173.6186 | 0.14094 | 1072580.8341 |  |  | 7208.5574 | 0.010167 | 709015.1873 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000100 | 521-18R | Segment-level | Distribution | 12.5093 | Top 5% highest risk | HFTD TIER 3 | 8713017.2766 | 8657405.5156 | 55611.761 |  | 0.035045 | 7.47e-05 | 2.21e-05 | 7.25e-05 |  | 247036824.5298 |  |  | 47262.4022 | 0.024471 | 1931347.9618 |  |  | 8349.3587 | 0.011805 | 707273.0799 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000101 | 1215-32R | Segment-level | Distribution | 12.1911 | Top 5% highest risk | HFTD TIER 3 | 8696504.1653 | 8389974.3077 | 306529.8576 |  | 0.056995 | 4.27e-05 | 0 | 4.35e-05 |  | 147205961.0291 |  |  | 299792.8752 | 0.61487 | 487574.484 |  |  | 6736.9824 | 0.0094616 | 712034.1605 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000102 | 973-1245R | Segment-level | Distribution | 3.3435 | Top 5% highest risk | HFTD TIER 3 | 8620110.617 | 8579827.5741 | 40283.0428 |  | 0.011048 | 3.2e-05 | 0 | 1.45e-05 |  | 776581486.0475 |  |  | 38325.9745 | 0.10661 | 359511.1574 |  |  | 1957.0683 | 0.0027324 | 716245.1603 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000103 | 859-42R | Segment-level | Distribution | 17.8147 | Top 5% highest risk | HFTD TIER 2 | 8606971.6622 | 8594825.5955 | 12146.0667 |  | 0.050053 | 0.000107 | 2.21e-05 | 0.000116 |  | 171714494.5451 |  |  | 0 | 0 | 0 |  |  | 12146.0667 | 0.017079 | 711177.9933 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000104 | CB 788 | Segment-level | Distribution | 21.0708 | Top 5% highest risk | HFTD TIER 2 | 8569068.0585 | 8146827.0651 | 422240.9934 |  | 0.05615 | 6.4e-05 | 2.21e-05 | 0.000203 |  | 145091453.2796 |  |  | 407466.3884 | 0.064889 | 6279475.7236 |  |  | 14774.6049 | 0.020772 | 711261.3344 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000105 | 521-1856R | Segment-level | Distribution | 12.1965 | Top 5% highest risk | HFTD TIER 3 | 8477861.6937 | 8290637.7323 | 187223.9614 |  | 0.034618 | 0 | 0 | 0 |  | 239491984.7802 |  |  | 178342.4023 | 0.10709 | 1665384.8737 |  |  | 8881.5591 | 0.012402 | 716139.2611 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000106 | 209-1769F | Segment-level | Distribution | 31.9017 | Top 5% highest risk | HFTD TIER 2 | 8462801.8216 | 8440861.3147 | 21940.507 |  | 0.08071 | 0.000128 | 0 | 0.00016 |  | 104582336.7393 |  |  | 0 | 0 | 0 |  |  | 21940.507 | 0.030983 | 708155.7697 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000107 | 907-1562AE | Segment-level | Distribution | 4.1122 | Top 5% highest risk | HFTD TIER 3 | 8439769.2215 | 8238563.7109 | 201205.5106 |  | 0.010825 | 1.07e-05 | 0 | 4.35e-05 |  | 761040119.6175 |  |  | 198305.696 | 0.039964 | 4962108.2983 |  |  | 2899.8146 | 0.0040772 | 711226.9635 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000108 | 450-1851F | Segment-level | Distribution | 7.0884 | Top 5% highest risk | HFTD TIER 2 | 8274122.4526 | 8210482.2612 | 63640.1913 |  | 0.022058 | 0 | 0 | 0 |  | 372219050.5682 |  |  | 59308.949 | 0.071222 | 832735.8905 |  |  | 4331.2423 | 0.006197 | 698925.6546 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000109 | 1458-565R | Segment-level | Distribution | 5.7011 | Top 5% highest risk | HFTD TIER 3 | 8159979.2875 | 8098401.0314 | 61578.256 |  | 0.017757 | 1.07e-05 | 0 | 2.9e-05 |  | 456078361.3662 |  |  | 58030.6786 | 0.13549 | 428290.9202 |  |  | 3547.5774 | 0.0049412 | 717958.6716 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000110 | 972-1582R | Segment-level | Distribution | 11.1522 | Top 5% highest risk | HFTD TIER 3 | 8019179.1907 | 7901674.2084 | 117504.9823 |  | 0.033479 | 6.4e-05 | 0 | 8.7e-05 |  | 236021643.9287 |  |  | 111015.7019 | 0.10812 | 1026769.0015 |  |  | 6489.2804 | 0.0090242 | 719097.5802 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000111 | 971-29R | Segment-level | Distribution | 3.8006 | Top 5% highest risk | HFTD TIER 3 | 8015406.5198 | 7972516.2609 | 42890.2589 |  | 0.011408 | 4.27e-05 | 0 | 4.35e-05 |  | 698877613.2467 |  |  | 40413.2039 | 0.10679 | 378423.463 |  |  | 2477.055 | 0.0035084 | 706035.5139 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000112 | 908-1372R | Segment-level | Distribution | 3.7273 | Top 5% highest risk | HFTD TIER 2 | 7960290.3283 | 7828738.2327 | 131552.0956 |  | 0.010694 | 2.13e-05 | 0 | 1.45e-05 |  | 732054593.3931 |  |  | 129010.0921 | 0.16274 | 792754.9837 |  |  | 2542.0035 | 0.0035764 | 710771.5897 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000113 | 355-41R | Segment-level | Distribution | 6.2962 | Top 5% highest risk | HFTD TIER 2 | 7500586.088 | 7388136.9365 | 112449.1515 |  | 0.018028 | 1.07e-05 | 2.21e-05 | 2.9e-05 |  | 409823655.7531 |  |  | 107958.6016 | 0.067904 | 1589875.7013 |  |  | 4490.5499 | 0.0063218 | 710327.735 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000114 | 222-2013R | Segment-level | Distribution | 13.7044 | Top 5% highest risk | HFTD TIER 3 | 7426975.8578 | 7133534.366 | 293441.4918 |  | 0.046653 | 6.4e-05 | 0 | 7.25e-05 |  | 152904919.3838 |  |  | 283167.7861 | 0.21814 | 1298104.726 |  |  | 10273.7057 | 0.014479 | 709578.6696 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000115 | 222-1523R | Segment-level | Distribution | 12.4352 | Top 5% highest risk | HFTD TIER 3 | 7406689.0243 | 7156613.2119 | 250075.8124 |  | 0.040774 | 6.4e-05 | 2.21e-05 | 0.000102 |  | 175518176.0013 |  |  | 240718.3378 | 0.215 | 1119639.965 |  |  | 9357.4746 | 0.013238 | 706864.6763 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000116 | CB 476 | Segment-level | Distribution | 18.0017 | Top 5% highest risk | HFTD TIER 2 | 7260321.7275 | 5346744.7833 | 1913576.9442 |  | 0.043529 | 3.2e-05 | 2.21e-05 | 5.8e-05 |  | 122830656.5985 |  |  | 1899954.8903 | 0.13862 | 13706249.9845 |  |  | 13622.0538 | 0.019105 | 713009.8838 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000117 | 445-1325F | Segment-level | Distribution | 11.7129 | Top 5% highest risk | HFTD TIER 2 | 7250722.8788 | 6968326.4254 | 282396.4534 |  | 0.050439 | 2.13e-05 | 0 | 8.7e-05 |  | 138153540.4229 |  |  | 275900.7801 | 0.51389 | 536887.6796 |  |  | 6495.6733 | 0.0092334 | 703497.4425 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000118 | 78-782R | Segment-level | Distribution | 1.7152 | Top 5% highest risk | HFTD TIER 3 | 7202315.8397 | 7167196.5439 | 35119.2958 |  | 0.0078748 | 1.07e-05 | 0 | 0 |  | 910143310.8007 |  |  | 33919.1162 | 0.32853 | 103244.7336 |  |  | 1200.1796 | 0.0016716 | 717982.5369 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000119 | 974-715R | Segment-level | Distribution | 8.7188 | Top 5% highest risk | HFTD TIER 3 | 7107169.6783 | 7075029.5845 | 32140.0938 |  | 0.029264 | 0 | 0 | 0 |  | 241765636.431 |  |  | 28293.2944 | 0.10598 | 266963.2048 |  |  | 3846.7994 | 0.005442 | 706872.3605 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000120 | 1021-1760R | Segment-level | Distribution | 2.9682 | Top 5% highest risk | HFTD TIER 3 | 7055715.6839 | 6926992.6786 | 128723.0053 |  | 0.0083966 | 2.13e-05 | 0 | 1.45e-05 |  | 824975904.3718 |  |  | 126531.8319 | 0.096787 | 1307319.8928 |  |  | 2191.1734 | 0.0031074 | 705146.8656 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000121 | 236-1573R | Segment-level | Distribution | 7.1517 | Top 5% highest risk | HFTD TIER 3 | 6927855.8046 | 6778519.8437 | 149335.9608 |  | 0.021156 | 3.2e-05 | 0 | 2.9e-05 |  | 320406496.6793 |  |  | 144709.0316 | 0.1572 | 920565.5087 |  |  | 4626.9292 | 0.0065236 | 709260.1052 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000122 | CB 470 | Segment-level | Distribution | 12.4373 | Top 5% highest risk | HFTD TIER 2 | 6922049.3159 | 6609552.2304 | 312497.0855 |  | 0.036263 | 8.54e-05 | 0 | 7.25e-05 |  | 182269121.0888 |  |  | 303721.2285 | 0.065298 | 4651309.8178 |  |  | 8775.857 | 0.012436 | 705692.9975 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000123 | RB1-427R | Segment-level | Distribution | 12.6949 | Top 5% highest risk | HFTD TIER 3 | 6920123.9655 | 6752264.4955 | 167859.47 |  | 0.035391 | 5.34e-05 | 0 | 0 |  | 190791519.1369 |  |  | 159587.4198 | 0.10679 | 1494432.1438 |  |  | 8272.0502 | 0.011626 | 711488.5297 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000124 | CB OK1 | Segment-level | Distribution | 7.3438 | Top 5% highest risk | HFTD TIER 3 | 6915681.9377 | 6846548.5064 | 69133.4313 |  | 0.027029 | 5.34e-05 | 0 | 2.9e-05 |  | 253307552.238 |  |  | 63662.4475 | 0.16783 | 379324.2706 |  |  | 5470.9838 | 0.0076898 | 711459.8303 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000125 | 1250-671R | Segment-level | Distribution | 2.001 | Top 5% highest risk | HFTD TIER 2 | 6815427.7597 | 6443060.7288 | 372367.0309 |  | 0.01265 | 3.2e-05 | 0 | 5.8e-05 |  | 509340916.758 |  |  | 370799.4193 | 0.077213 | 4802280.1704 |  |  | 1567.6116 | 0.002187 | 716786.2853 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000126 | 520-1527R | Segment-level | Distribution | 10.7038 | Top 5% highest risk | HFTD TIER 3 | 6763000.618 | 6541015.7388 | 221984.8792 |  | 0.033612 | 4.27e-05 | 0 | 2.9e-05 |  | 194602428.2499 |  |  | 214761.3737 | 0.22731 | 944775.1475 |  |  | 7223.5055 | 0.010119 | 713827.4508 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000127 | 449-13R | Segment-level | Distribution | 16.5478 | Top 5% highest risk | HFTD TIER 3 | 6729964.7304 | 6090025.9061 | 639938.8243 |  | 0.049545 | 5.34e-05 | 4.42e-05 | 4.35e-05 |  | 122918089.3911 |  |  | 628975.8541 | 0.21735 | 2893878.7012 |  |  | 10962.9702 | 0.015449 | 709641.6652 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000128 | 214-1135R | Segment-level | Distribution | 11.6815 | Top 5% highest risk | HFTD TIER 3 | 6666921.5731 | 6627374.3046 | 39547.2685 |  | 0.036405 | 2.13e-05 | 2.21e-05 | 2.9e-05 |  | 182045716.3742 |  |  | 31346.5489 | 0.042859 | 731391.1946 |  |  | 8200.7196 | 0.011513 | 712288.4659 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000129 | CB 1235 | Segment-level | Distribution | 20.7706 | Top 5% highest risk | HFTD TIER 2 | 6645571.9566 | 6585223.8253 | 60348.1313 |  | 0.056493 | 0.000107 | 2.21e-05 | 5.8e-05 |  | 116567076.0142 |  |  | 45643.4051 | 0.0056448 | 8085920.694 |  |  | 14704.7262 | 0.020687 | 710819.6527 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000130 | 1030-18R | Segment-level | Distribution | 3.5275 | Top 5% highest risk | HFTD TIER 3 | 6620909.8177 | 6532115.4055 | 88794.4122 |  | 0.010395 | 0 | 0 | 2.9e-05 |  | 628414311.8047 |  |  | 86685.2051 | 0.2251 | 385092.3185 |  |  | 2109.2071 | 0.0029306 | 719718.5189 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000131 | 973-626R | Segment-level | Distribution | 10.906 | Top 5% highest risk | HFTD TIER 3 | 6521723.6165 | 6393285.8327 | 128437.7837 |  | 0.036492 | 5.34e-05 | 0 | 1.45e-05 |  | 175195955.101 |  |  | 121568.7084 | 0.10603 | 1146545.787 |  |  | 6869.0753 | 0.0097772 | 702560.5807 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000132 | 474-22AE | Segment-level | Distribution | 9.6011 | Top 5% highest risk | Non-HFTD | 6435983.3722 | 6428609.8395 | 7373.5326 |  | 0.03621 | 2.21e-05 | 0 | 2.73e-05 |  | 177535883.2464 |  |  | 0 | 0 | 0 |  |  | 7373.5326 | 0.010425 | 707306.8667 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000133 | 1250-27R | Segment-level | Distribution | 4.6189 | Top 5% highest risk | HFTD TIER 2 | 6418508.1687 | 5971509.076 | 446999.0927 |  | 0.016583 | 0 | 0 | 0 |  | 360106923.8863 |  |  | 443953.3672 | 0.076513 | 5802341.1407 |  |  | 3045.7255 | 0.004274 | 712617.0984 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000134 | 975-22R | Segment-level | Distribution | 1.6544 | Top 5% highest risk | HFTD TIER 3 | 6417038.1128 | 5152704.553 | 1264333.5598 |  | 0.0055708 | 0 | 0 | 0 |  | 924948760.1477 |  |  | 1263248.1771 | 0.18961 | 6662293.7471 |  |  | 1085.3827 | 0.0015124 | 717655.8417 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000135 | 230-133AE | Segment-level | Distribution | 11.3506 | Top 5% highest risk | HFTD TIER 2 | 6388693.9467 | 6277695.8362 | 110998.1105 |  | 0.03163 | 5.34e-05 | 4.42e-05 | 5.8e-05 |  | 198471582.1016 |  |  | 103148.0092 | 0.05296 | 1947651.4293 |  |  | 7850.1013 | 0.010974 | 715323.3321 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000136 | 411-30R | Segment-level | Distribution | 24.6051 | Top 5% highest risk | HFTD TIER 3 | 6370041.441 | 6272317.8666 | 97723.5743 |  | 0.067932 | 5.34e-05 | 0 | 5.8e-05 |  | 92332300.9281 |  |  | 80399.7124 | 0.01073 | 7493262.7896 |  |  | 17323.8619 | 0.024431 | 709087.6384 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000137 | 907-2820R | Segment-level | Distribution | 2.4583 | Top 5% highest risk | HFTD TIER 3 | 6348475.522 | 6346945.6016 | 1529.9204 |  | 0.0088778 | 1.07e-05 | 0 | 1.45e-05 |  | 714923246.9252 |  |  | 509.5288 | 0.072148 | 7062.2919 |  |  | 1020.3916 | 0.0014532 | 702168.7196 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000138 | CB 1234 | Segment-level | Distribution | 17.3068 | Top 5% highest risk | HFTD TIER 3 | 6311491.8914 | 5319836.9588 | 991654.9326 |  | 0.051619 | 7.47e-05 | 2.21e-05 | 5.8e-05 |  | 103060066.465 |  |  | 980490.8067 | 0.052174 | 18792637.1027 |  |  | 11164.1258 | 0.015821 | 705652.3508 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000139 | 239-2215R | Segment-level | Distribution | 12.0589 | Top 5% highest risk | HFTD TIER 3 | 6268656.9491 | 6158320.4267 | 110336.5224 |  | 0.035052 | 0 | 0 | 0 |  | 175688980.6886 |  |  | 102173.5112 | 0.10761 | 949488.5302 |  |  | 8163.0111 | 0.011414 | 715150.2612 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000140 | 73-1130R | Segment-level | Distribution | 12.0339 | Top 5% highest risk | HFTD TIER 3 | 6201607.0003 | 6033465.8455 | 168141.1548 |  | 0.030024 | 1.07e-05 | 0 | 0 |  | 200954764.3732 |  |  | 161292.1004 | 0.1785 | 903618.4629 |  |  | 6849.0543 | 0.0096778 | 707707.7768 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000141 | 1215-12R | Segment-level | Distribution | 8.3178 | Top 5% highest risk | HFTD TIER 3 | 6147283.8671 | 6017063.678 | 130220.1891 |  | 0.040774 | 4.27e-05 | 0 | 1.45e-05 |  | 147571815.1844 |  |  | 125737.3971 | 0.65196 | 192859.8314 |  |  | 4482.792 | 0.0063332 | 707824.1692 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000142 | CB 357 | Segment-level | Distribution | 5.0178 | Top 5% highest risk | HFTD TIER 3 | 6110854.5999 | 5866848.8393 | 244005.7606 |  | 0.017951 | 3.2e-05 | 0 | 0 |  | 326822097.6493 |  |  | 240348.0184 | 0.10457 | 2298340.3084 |  |  | 3657.7422 | 0.0052066 | 702520.2956 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000143 | RB1-433R | Segment-level | Distribution | 6.3644 | Top 5% highest risk | HFTD TIER 3 | 5946507.5048 | 5905824.7081 | 40682.7967 |  | 0.02 | 3.2e-05 | 2.21e-05 | 0 |  | 295285329.6993 |  |  | 36655.7897 | 0.12719 | 288200.73 |  |  | 4027.0069 | 0.0056538 | 712265.5439 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000144 | 1090-73F | Segment-level | Distribution | 10.606 | Top 5% highest risk | HFTD TIER 3 | 5899045.3617 | 5876650.6475 | 22394.7142 |  | 0.030984 | 1.07e-05 | 0 | 0 |  | 189666044.226 |  |  | 14873.685 | 0.005206 | 2857027.4686 |  |  | 7521.0292 | 0.010563 | 711989.4361 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000145 | 175-90R | Segment-level | Distribution | 11.9254 | Top 5% highest risk | HFTD TIER 3 | 5741494.8572 | 5561271.4512 | 180223.406 |  | 0.03489 | 2.13e-05 | 0 | 2.9e-05 |  | 159395337.6416 |  |  | 171774.1421 | 0.15822 | 1085693.8745 |  |  | 8449.2639 | 0.011806 | 715663.2877 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000146 | 73-23R | Segment-level | Distribution | 8.2208 | Top 5% highest risk | HFTD TIER 3 | 5733790.742 | 5642495.3869 | 91295.3551 |  | 0.025077 | 6.4e-05 | 2.21e-05 | 4.35e-05 |  | 225008589.0898 |  |  | 86266.6494 | 0.18133 | 475733.9745 |  |  | 5028.7057 | 0.0070806 | 710208.9811 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000147 | 909-453R | Segment-level | Distribution | 2.3515 | Top 5% highest risk | HFTD TIER 2 | 5703040.2921 | 5701153.2251 | 1887.067 |  | 0.0071514 | 0 | 0 | 0 |  | 797207990.7605 |  |  | 0 | 0 | 0 |  |  | 1887.067 | 0.0026414 | 714419.2321 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000148 | 78-35R | Segment-level | Distribution | 1.532 | Top 5% highest risk | HFTD TIER 3 | 5696335.8077 | 5695326.8309 | 1008.9768 |  | 0.0067266 | 0 | 0 | 1.45e-05 |  | 846687305.7608 |  |  | 0 | 0 | 0 |  |  | 1008.9768 | 0.0014614 | 690417.9467 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000149 | 448-9R | Segment-level | Distribution | 17.7839 | Top 5% highest risk | HFTD TIER 3 | 5644810.8618 | 5273684.8346 | 371126.0272 |  | 0.055676 | 7.47e-05 | 0 | 4.35e-05 |  | 94720971.9552 |  |  | 360369.0586 | 0.47319 | 761575.6303 |  |  | 10756.9686 | 0.015075 | 713563.422 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000150 | 522-38R | Segment-level | Distribution | 17.4926 | Top 5% highest risk | HFTD TIER 2 | 5639841.4319 | 5439139.6424 | 200701.7896 |  | 0.046787 | 3.2e-05 | 4.42e-05 | 8.7e-05 |  | 116252231.2066 |  |  | 188304.5448 | 0.024207 | 7778800.896 |  |  | 12397.2448 | 0.017607 | 704092.8687 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000151 | 521-27R | Segment-level | Distribution | 10.1674 | Top 5% highest risk | HFTD TIER 2 | 5618622.9164 | 5550019.8098 | 68603.1066 |  | 0.029051 | 1.07e-05 | 4.42e-05 | 0.000116 |  | 191041389.0478 |  |  | 61335.2906 | 0.024453 | 2508252.0469 |  |  | 7267.816 | 0.010163 | 715139.1341 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000152 | 908-1368R | Segment-level | Distribution | 18.6854 | Top 5% highest risk | HFTD TIER 2 | 5570792.9034 | 5361811.1093 | 208981.7941 |  | 0.054917 | 7.47e-05 | 0 | 2.9e-05 |  | 97634814.5258 |  |  | 196688.6844 | 0.16418 | 1197969.8779 |  |  | 12293.1097 | 0.017342 | 708871.6085 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000153 | 350-2196R | Segment-level | Distribution | 34.4453 | Top 5% highest risk | HFTD TIER 2 | 5570685.7117 | 5402874.7346 | 167810.9771 |  | 0.098833 | 0.000139 | 0 | 0.000203 |  | 54666486.5782 |  |  | 144206.9831 | 0.066999 | 2152368.7314 |  |  | 23603.994 | 0.033314 | 708522.2615 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000154 | 79-714R | Segment-level | Distribution | 5.9877 | Top 5% highest risk | HFTD TIER 3 | 5536620.5341 | 5332550.5898 | 204069.9443 |  | 0.01796 | 5.34e-05 | 0 | 4.35e-05 |  | 296915922.7732 |  |  | 200312.3058 | 0.35443 | 565167.7873 |  |  | 3757.6385 | 0.0053262 | 705500.8203 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000155 | 157-189R | Segment-level | Distribution | 27.7167 | Top 5% highest risk | HFTD TIER 3 | 5507023.9246 | 5091861.4926 | 415162.432 |  | 0.089417 | 4.27e-05 | 0 | 0.00016 |  | 56944989.2476 |  |  | 398405.2954 | 0.25732 | 1548302.9729 |  |  | 16757.1366 | 0.023761 | 705225.1396 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000156 | 524-1782F | Segment-level | Distribution | 8.5739 | Top 5% highest risk | HFTD TIER 3 | 5468134.4802 | 5455868.3357 | 12266.1445 |  | 0.026739 | 0 | 0 | 0 |  | 204041599.7485 |  |  | 6254.5388 | 0.005199 | 1203027.2655 |  |  | 6011.6057 | 0.0084658 | 710104.8624 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000157 | 356-16R | Segment-level | Distribution | 5.9928 | Top 5% highest risk | HFTD TIER 2 | 5437437.5172 | 5336373.2739 | 101064.2433 |  | 0.016717 | 0 | 2.21e-05 | 4.35e-05 |  | 319210719.0062 |  |  | 96850.0673 | 0.068062 | 1422959.9204 |  |  | 4214.176 | 0.0059742 | 705395.8657 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000158 | 215-38R | Segment-level | Distribution | 6.4307 | Top 5% highest risk | HFTD TIER 3 | 5434815.4519 | 5375940.6103 | 58874.8416 |  | 0.020867 | 3.2e-05 | 0 | 5.8e-05 |  | 257628821.1206 |  |  | 54849.6154 | 0.098782 | 555256.9625 |  |  | 4025.2262 | 0.0056306 | 714884.0581 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000159 | 441-30R | Segment-level | Distribution | 5.7333 | Top 5% highest risk | HFTD TIER 3 | 5348877.3579 | 5272517.0957 | 76360.2622 |  | 0.033649 | 2.13e-05 | 0 | 4.35e-05 |  | 156690711.6864 |  |  | 72976.4139 | 0.5168 | 141207.5754 |  |  | 3383.8483 | 0.0047416 | 713651.1547 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000160 | 236-1567R | Segment-level | Distribution | 5.8553 | Top 5% highest risk | HFTD TIER 3 | 5332003.6622 | 5229333.7728 | 102669.8895 |  | 0.01797 | 4.27e-05 | 0 | 2.9e-05 |  | 291000310.1117 |  |  | 98148.246 | 0.15699 | 625185.4952 |  |  | 4521.6435 | 0.0063284 | 714500.2625 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000161 | 66-1213R | Segment-level | Distribution | 16.7053 | Top 5% highest risk | Non-HFTD | 5312267.5909 | 5193771.752 | 118495.8389 |  | 0.047062 | 2.84e-05 | 5.3e-05 | 4.09e-05 |  | 110360669.4174 |  |  | 106206.9301 | 0.010722 | 9905884.391 |  |  | 12288.9088 | 0.017361 | 707829.3678 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000162 | 283-55R | Segment-level | Distribution | 7.2309 | Top 5% highest risk | HFTD TIER 3 | 5299634.3657 | 5223022.4858 | 76611.8798 |  | 0.024145 | 0 | 0 | 0 |  | 216317217.7427 |  |  | 72583.4736 | 0.17173 | 422650.5738 |  |  | 4028.4062 | 0.0056924 | 707681.5063 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000163 | 470-40AE | Segment-level | Distribution | 6.1881 | Top 5% highest risk | HFTD TIER 2 | 5264968.8371 | 5176968.2697 | 88000.5674 |  | 0.019407 | 5.34e-05 | 2.21e-05 | 2.9e-05 |  | 266752283.65 |  |  | 84171.1392 | 0.066207 | 1271340.6099 |  |  | 3829.4282 | 0.00542 | 706536.5637 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000164 | 449-693R | Segment-level | Distribution | 8.4553 | Top 5% highest risk | HFTD TIER 3 | 5260705.5579 | 5196144.7106 | 64560.8473 |  | 0.02757 | 0 | 0 | 0 |  | 188473706.9325 |  |  | 60632.213 | 0.2279 | 266042.0762 |  |  | 3928.6343 | 0.005597 | 701917.8661 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000165 | CB RA2 | Segment-level | Distribution | 3.5953 | Top 5% highest risk | HFTD TIER 2 | 5229902.0724 | 5131211.4171 | 98690.6552 |  | 0.0091102 | 0 | 0 | 1.45e-05 |  | 563238064.7101 |  |  | 95774.9443 | 0.11389 | 840972.062 |  |  | 2915.711 | 0.004062 | 717801.8166 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000166 | 973-1226R | Segment-level | Distribution | 8.4832 | Top 5% highest risk | HFTD TIER 3 | 5177869.5988 | 5039261.7504 | 138607.8484 |  | 0.026938 | 1.07e-05 | 0 | 1.45e-05 |  | 187071667.4982 |  |  | 133846.6295 | 0.1063 | 1259190.1981 |  |  | 4761.219 | 0.0066614 | 714747.4961 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000167 | 231-1635R | Segment-level | Distribution | 29.745 | Top 5% highest risk | HFTD TIER 2 | 5142094.9811 | 5074261.8471 | 67833.134 |  | 0.080559 | 0.00016 | 0.000133 | 8.7e-05 |  | 62988143.4368 |  |  | 46327.9087 | 0.0056128 | 8253974.607 |  |  | 21505.2253 | 0.030305 | 709621.6274 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000168 | 1030-1728R | Segment-level | Distribution | 2.6777 | Top 5% highest risk | HFTD TIER 3 | 5124158.6734 | 5035020.7149 | 89137.9585 |  | 0.0075448 | 1.07e-05 | 0 | 0 |  | 667349792.5592 |  |  | 87660.8236 | 0.22578 | 388262.1714 |  |  | 1477.1349 | 0.0021176 | 697551.4225 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000169 | CB MOR1 | Segment-level | Distribution | 3.55 | Top 5% highest risk | HFTD TIER 2 | 5119714.0569 | 5045788.0578 | 73925.9991 |  | 0.009621 | 0 | 0 | 0 |  | 524455675.897 |  |  | 71304.005 | 0.11314 | 630218.0534 |  |  | 2621.9941 | 0.0037068 | 707347.0648 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000170 | 357-1299R | Segment-level | Distribution | 2.7532 | Top 5% highest risk | HFTD TIER 3 | 5098732.7905 | 5082456.8734 | 16275.9172 |  | 0.010791 | 1.07e-05 | 0 | 1.45e-05 |  | 470972892.6161 |  |  | 14745.3624 | 0.22795 | 64687.963 |  |  | 1530.5548 | 0.002167 | 706301.2255 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000171 | 1022-322R | Segment-level | Distribution | 3.6661 | Top 5% highest risk | HFTD TIER 3 | 5072199.4815 | 5029594.3965 | 42605.085 |  | 0.011253 | 3.2e-05 | 0 | 0 |  | 446963813.14 |  |  | 40132.4725 | 0.091155 | 440268.2096 |  |  | 2472.6125 | 0.0034584 | 714958.4962 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000172 | 1021-855 | Segment-level | Distribution | 2.9135 | Top 5% highest risk | HFTD TIER 3 | 5034375.2727 | 5009473.3713 | 24901.9014 |  | 0.0089948 | 1.07e-05 | 0 | 0 |  | 556929934.1058 |  |  | 22862.7294 | 0.097178 | 235265.5467 |  |  | 2039.172 | 0.0029158 | 699352.4859 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000173 | 520-35R | Segment-level | Distribution | 14.3572 | Top 5% highest risk | HFTD TIER 3 | 4997794.2437 | 4822590.9181 | 175203.3256 |  | 0.044456 | 3.2e-05 | 0 | 2.9e-05 |  | 108480090.8332 |  |  | 165559.9169 | 0.22732 | 728301.2525 |  |  | 9643.4087 | 0.013661 | 705887.2947 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000174 | 1090-74F | Segment-level | Distribution | 9.8927 | Top 5% highest risk | HFTD TIER 3 | 4990919.9691 | 4972118.9145 | 18801.0545 |  | 0.029392 | 3.2e-05 | 2.21e-05 | 8.7e-05 |  | 169168024.6917 |  |  | 10937.5089 | 0.0052052 | 2101265.8364 |  |  | 7863.5456 | 0.01114 | 705896.4807 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000175 | 234-48R | Segment-level | Distribution | 11.5796 | Top 5% highest risk | HFTD TIER 2 | 4939379.2504 | 4912538.7809 | 26840.4695 |  | 0.031747 | 3.2e-05 | 4.42e-05 | 7.25e-05 |  | 154742201.713 |  |  | 19343.3759 | 0.0056438 | 3427367.3551 |  |  | 7497.0936 | 0.010541 | 711231.7212 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000176 | 176-194R | Segment-level | Distribution | 9.0746 | Top 5% highest risk | HFTD TIER 3 | 4934160.3361 | 4820768.4196 | 113391.9164 |  | 0.026897 | 2.13e-05 | 0 | 1.45e-05 |  | 179228045.0765 |  |  | 107488.4773 | 0.18022 | 596414.6768 |  |  | 5903.4392 | 0.0082982 | 711412.0114 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000177 | 212-725R | Segment-level | Distribution | 11.8649 | Top 5% highest risk | HFTD TIER 3 | 4887826.6998 | 4846329.5478 | 41497.1521 |  | 0.043677 | 3.2e-05 | 0 | 2.9e-05 |  | 110959404.9855 |  |  | 35508.5272 | 0.087233 | 407055.7012 |  |  | 5988.6249 | 0.0084998 | 704560.6833 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000178 | 222-2063 | Segment-level | Distribution | 4.9145 | Top 5% highest risk | HFTD TIER 3 | 4859776.4656 | 4852517.2036 | 7259.262 |  | 0.017105 | 1.07e-05 | 0 | 0 |  | 283689985.593 |  |  | 4593.5252 | 0.21691 | 21177.3558 |  |  | 2665.7369 | 0.0037484 | 711166.5934 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000179 | 307-234R | Segment-level | Distribution | 4.6394 | Top 5% highest risk | HFTD TIER 2 | 4762848.0442 | 4550698.7421 | 212149.3021 |  | 0.01324 | 1.07e-05 | 0 | 5.8e-05 |  | 343713556.2544 |  |  | 208808.1126 | 0.092019 | 2269174.8979 |  |  | 3341.1895 | 0.0047476 | 703763.899 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000180 | 441-27R | Segment-level | Distribution | 7.3796 | Top 5% highest risk | HFTD TIER 3 | 4750126.7754 | 4655243.6145 | 94883.161 |  | 0.032668 | 1.07e-05 | 0 | 0.000102 |  | 142503386.06 |  |  | 91023.6797 | 0.51947 | 175224.6039 |  |  | 3859.4813 | 0.005385 | 716709.621 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000181 | 1138-6R | Segment-level | Distribution | 19.4272 | Top 5% highest risk | HFTD TIER 2 | 4663877.8673 | 4249838.818 | 414039.0493 |  | 0.048464 | 5.34e-05 | 0.00011 | 0.000102 |  | 87690994.474 |  |  | 399553.8585 | 0.10269 | 3890805.8721 |  |  | 14485.1909 | 0.02037 | 711104.1175 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000182 | 991-1206R | Segment-level | Distribution | 9.2129 | Top 5% highest risk | HFTD TIER 2 | 4576791.095 | 4566681.8556 | 10109.2395 |  | 0.025819 | 0 | 0 | 1.45e-05 |  | 176870177.2918 |  |  | 4519.9221 | 0.030104 | 150142.5753 |  |  | 5589.3174 | 0.0078618 | 710946.2664 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000183 | 353-901F | Segment-level | Distribution | 2.3892 | Top 5% highest risk | HFTD TIER 2 | 4555618.8657 | 4296048.7024 | 259570.1632 |  | 0.0069132 | 3.2e-05 | 0 | 4.35e-05 |  | 621426937.2244 |  |  | 257665.2243 | 0.09656 | 2668457.8676 |  |  | 1904.9389 | 0.0027098 | 702981.375 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000184 | 221-788 | Segment-level | Distribution | 3.6174 | Top 5% highest risk | HFTD TIER 3 | 4481914.2591 | 4457135.1181 | 24779.1411 |  | 0.019879 | 0 | 0 | 1.45e-05 |  | 224208734.5727 |  |  | 22835.2096 | 0.16714 | 136624.8823 |  |  | 1943.9315 | 0.002731 | 711802.0889 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000185 | 240-2004R | Segment-level | Distribution | 19.7983 | Top 5% highest risk | HFTD TIER 3 | 4437658.7596 | 4344911.7762 | 92746.9834 |  | 0.051336 | 3.2e-05 | 0 | 0.000145 |  | 84636082.315 |  |  | 78502.7252 | 0.024322 | 3227695.7586 |  |  | 14244.2583 | 0.020117 | 708056.6209 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000186 | 445-894R | Segment-level | Distribution | 26.8775 | Top 5% highest risk | HFTD TIER 2 | 4421002.3515 | 3895845.1495 | 525157.202 |  | 0.1094 | 9.61e-05 | 0 | 0.000131 |  | 35610104.5816 |  |  | 508789.1916 | 0.50288 | 1011744.2611 |  |  | 16368.0103 | 0.022971 | 712557.261 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000187 | 175-64R | Segment-level | Distribution | 10.35 | Top 5% highest risk | HFTD TIER 3 | 4385400.4311 | 4276794.127 | 108606.304 |  | 0.032071 | 3.2e-05 | 4.42e-05 | 4.35e-05 |  | 133353105.8089 |  |  | 101222.6408 | 0.15981 | 633384.9405 |  |  | 7383.6633 | 0.01044 | 707260.9869 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000188 | 235-897R | Segment-level | Distribution | 6.6053 | Top 5% highest risk | HFTD TIER 2 | 4375038.1439 | 3877449.0208 | 497589.1232 |  | 0.014436 | 3.2e-05 | 0 | 8.7e-05 |  | 268603246.1937 |  |  | 492961.9345 | 0.097015 | 5081316.9817 |  |  | 4627.1887 | 0.0064498 | 717415.8428 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000189 | 1458-1061 | Segment-level | Distribution | 2.3455 | Top 5% highest risk | HFTD TIER 2 | 4370098.6983 | 4312122.8435 | 57975.8547 |  | 0.0058536 | 0 | 0 | 1.45e-05 |  | 736661685.7158 |  |  | 56488.804 | 0.13434 | 420498.2066 |  |  | 1487.0508 | 0.002086 | 712871.8954 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000190 | 971-371R | Segment-level | Distribution | 2.4735 | Top 5% highest risk | HFTD TIER 3 | 4351506.2421 | 4330446.0988 | 21060.1433 |  | 0.0076008 | 0 | 0 | 0 |  | 569735567.1554 |  |  | 19464.057 | 0.10684 | 182182.5625 |  |  | 1596.0863 | 0.0022372 | 713430.2945 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000191 | CB 599 | Segment-level | Distribution | 11.4604 | Top 5% highest risk | HFTD TIER 2 | 4323244.1936 | 4315016.6286 | 8227.565 |  | 0.031497 | 5.34e-05 | 4.42e-05 | 0.000145 |  | 136996832.3709 |  |  | 0 | 0 | 0 |  |  | 8227.565 | 0.011597 | 709431.8589 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000192 | 1233-591R | Segment-level | Distribution | 6.4721 | Top 5% highest risk | HFTD TIER 3 | 4300183.7991 | 4242541.5206 | 57642.2785 |  | 0.019856 | 0 | 0 | 0 |  | 213663315.2665 |  |  | 52712.8052 | 0.10462 | 503858.8429 |  |  | 4929.4733 | 0.0069414 | 710155.4925 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000193 | 471-36F | Segment-level | Distribution | 3.9252 | Top 5% highest risk | HFTD TIER 2 | 4253667.121 | 4039168.3366 | 214498.7845 |  | 0.011797 | 1.07e-05 | 0 | 0 |  | 342383644.9797 |  |  | 211944.4864 | 0.077686 | 2728212.8147 |  |  | 2554.2981 | 0.0035954 | 710435.0261 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000194 | 305-32R | Segment-level | Distribution | 7.0648 | Top 5% highest risk | Non-HFTD | 4233866.5476 | 4103697.3678 | 130169.1798 |  | 0.020612 | 9.48e-06 | 6.62e-06 | 1.82e-05 |  | 199092633.7965 |  |  | 124613.0467 | 0.051829 | 2404329.786 |  |  | 5556.133 | 0.0077926 | 713001.1824 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000195 | 182-2252R | Segment-level | Distribution | 3.4226 | Top 5% highest risk | HFTD TIER 2 | 4229944.5723 | 4196758.1646 | 33186.4076 |  | 0.010686 | 0 | 0 | 2.9e-05 |  | 392748948.5499 |  |  | 30693.8966 | 0.098852 | 310504.1753 |  |  | 2492.511 | 0.0035338 | 705334.4823 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000196 | 1105-1479 | Segment-level | Distribution | 3.4339 | Top 5% highest risk | HFTD TIER 2 | 4228043.5461 | 4224870.7096 | 3172.8365 |  | 0.010576 | 0 | 0 | 1.45e-05 |  | 399462076.8504 |  |  | 1373.4345 | 0.092486 | 14850.1882 |  |  | 1799.402 | 0.0024988 | 720106.4481 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000197 | 1001-1820F | Segment-level | Distribution | 6.479 | Top 5% highest risk | HFTD TIER 2 | 4222247.108 | 3859583.2958 | 362663.8121 |  | 0.018664 | 5.34e-05 | 0 | 5.8e-05 |  | 206790716.7651 |  |  | 358314.2717 | 0.10374 | 3454037.6957 |  |  | 4349.5404 | 0.0060576 | 718030.315 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000198 | 176-164R | Segment-level | Distribution | 6.2526 | Top 5% highest risk | HFTD TIER 3 | 4184746.7473 | 4105075.4627 | 79671.2847 |  | 0.019734 | 4.27e-05 | 0 | 1.45e-05 |  | 208016228.6505 |  |  | 75288.4941 | 0.18132 | 415235.8829 |  |  | 4382.7905 | 0.0062214 | 704470.1426 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000199 | 67-34R | Segment-level | Distribution | 20.3065 | Top 5% highest risk | HFTD TIER 3 | 4180137.3859 | 3921083.9191 | 259053.4668 |  | 0.061507 | 3.2e-05 | 0 | 5.8e-05 |  | 63750620.5687 |  |  | 245326.3777 | 0.16659 | 1472658.6628 |  |  | 13727.0891 | 0.01934 | 709777.0978 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000200 | CB 233 | Segment-level | Distribution | 18.8384 | Top 5% highest risk | HFTD TIER 2 | 4127695.5357 | 4075589.0906 | 52106.4452 |  | 0.050248 | 0.000117 | 6.63e-05 | 0.000203 |  | 81110124.4748 |  |  | 38305.5831 | 0.0056584 | 6769684.5598 |  |  | 13800.862 | 0.019545 | 706099.8117 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000201 | CB 1250 | Segment-level | Distribution | 2.5689 | Top 5% highest risk | HFTD TIER 2 | 4075235.8936 | 4072563.6693 | 2672.2243 |  | 0.0084468 | 1.07e-05 | 0 | 1.45e-05 |  | 482142784.1697 |  |  | 1647.3021 | 0.078795 | 20906.2822 |  |  | 1024.9222 | 0.0014614 | 701328.9748 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000202 | 175-2024R | Segment-level | Distribution | 7.3674 | Top 5% highest risk | HFTD TIER 2 | 4029008.4568 | 3992843.5947 | 36164.8621 |  | 0.023973 | 1.07e-05 | 0 | 8.7e-05 |  | 166554468.9356 |  |  | 32825.1404 | 0.16247 | 202035.1791 |  |  | 3339.7217 | 0.0046958 | 711214.6389 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000203 | 1166-15R | Segment-level | Distribution | 5.0748 | Top 5% highest risk | HFTD TIER 3 | 3965221.7427 | 3896388.7437 | 68832.999 |  | 0.015585 | 2.13e-05 | 0 | 0 |  | 250005694.1035 |  |  | 65726.9864 | 0.17399 | 377765.6171 |  |  | 3106.0126 | 0.004392 | 707197.7582 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000204 | 221-37AE | Segment-level | Distribution | 7.7195 | Top 5% highest risk | HFTD TIER 3 | 3934773.2911 | 3817749.2995 | 117023.9916 |  | 0.025889 | 9.61e-05 | 0 | 0 |  | 147464939.028 |  |  | 111681.1543 | 0.16588 | 673254.9945 |  |  | 5342.8373 | 0.0074814 | 714149.3954 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000205 | 221-6R | Segment-level | Distribution | 6.0572 | Top 5% highest risk | HFTD TIER 2 | 3904259.0089 | 3899503.1774 | 4755.8315 |  | 0.043987 | 0 | 0 | 0 |  | 88650861.5562 |  |  | 1257.6822 | 0.1671 | 7526.5874 |  |  | 3498.1493 | 0.0049536 | 706183.231 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000206 | 157-204R | Segment-level | Distribution | 13.2184 | Top 5% highest risk | HFTD TIER 3 | 3876133.3857 | 3836813.9225 | 39319.4632 |  | 0.046093 | 1.07e-05 | 0 | 2.9e-05 |  | 83240707.3199 |  |  | 32325.7406 | 0.27181 | 118929.1091 |  |  | 6993.7226 | 0.0098664 | 708842.3971 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000207 | CB 471 | Segment-level | Distribution | 9.5888 | Top 5% highest risk | Non-HFTD | 3808732.8423 | 3802288.9453 | 6443.897 |  | 0.02141 | 9.48e-06 | 6.62e-06 | 4.54e-06 |  | 177590747.7359 |  |  | 0 | 0 | 0 |  |  | 6443.897 | 0.009157 | 703712.6741 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000208 | TM1-10R | Segment-level | Distribution | 3.3899 | Top 5% highest risk | HFTD TIER 3 | 3782856.7785 | 3763197.4906 | 19659.2879 |  | 0.010364 | 1.07e-05 | 0 | 0 |  | 363102806.8917 |  |  | 17162.436 | 0.079576 | 215672.4354 |  |  | 2496.8519 | 0.0034804 | 717403.7207 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000209 | 1023-48R | Segment-level | Distribution | 16.5267 | Top 5% highest risk | HFTD TIER 2 | 3773847.2966 | 3675353.5853 | 98493.7113 |  | 0.046087 | 0 | 2.21e-05 | 0 |  | 79748162.938 |  |  | 88211.5049 | 0.067662 | 1303700.5033 |  |  | 10282.2064 | 0.014413 | 713378.2712 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000210 | 249-24R | Segment-level | Distribution | 15.5693 | Top 5% highest risk | HFTD TIER 3 | 3753230.0343 | 3597511.4758 | 155718.5585 |  | 0.043458 | 7.47e-05 | 0 | 0.000131 |  | 82781721.0218 |  |  | 145470.9455 | 0.043014 | 3381975.5956 |  |  | 10247.613 | 0.014465 | 708422.3724 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000211 | 240-2006R | Segment-level | Distribution | 12.1512 | Top 5% highest risk | HFTD TIER 3 | 3742572.1436 | 3707607.3748 | 34964.7688 |  | 0.036178 | 5.34e-05 | 4.42e-05 | 8.7e-05 |  | 102483508.4373 |  |  | 28285.6294 | 0.024387 | 1159884.0937 |  |  | 6679.1393 | 0.009426 | 708586.8174 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000212 | CB RC1 | Segment-level | Distribution | 3.232 | Top 5% highest risk | HFTD TIER 2 | 3739874.8305 | 3707620.4941 | 32254.3364 |  | 0.0092964 | 1.07e-05 | 2.21e-05 | 0 |  | 398823253.524 |  |  | 30205.8517 | 0.072093 | 418983.3672 |  |  | 2048.4848 | 0.0028638 | 715303.0081 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000213 | DV1-3R | Segment-level | Distribution | 7.3926 | Top 5% highest risk | HFTD TIER 3 | 3719400.3806 | 3539616.4462 | 179783.9343 |  | 0.020835 | 1.07e-05 | 0 | 2.9e-05 |  | 169891260.0302 |  |  | 174475.2336 | 0.16594 | 1051455.9373 |  |  | 5308.7008 | 0.0074406 | 713477.5099 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000214 | 221-1230F | Segment-level | Distribution | 3.8686 | Top 5% highest risk | HFTD TIER 3 | 3690962.2783 | 3687572.8112 | 3389.4671 |  | 0.031093 | 0 | 0 | 0 |  | 118599692.8921 |  |  | 0 | 0 | 0 |  |  | 3389.4671 | 0.0047506 | 713481.8965 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000215 | 1250-8R | Segment-level | Distribution | 4.2055 | Top 5% highest risk | HFTD TIER 2 | 3684980.1605 | 3616964.705 | 68015.4556 |  | 0.010354 | 0 | 0 | 0 |  | 349336929.916 |  |  | 65291.9982 | 0.078089 | 836125.0044 |  |  | 2723.4573 | 0.003846 | 708127.2302 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000216 | 445-39R | Segment-level | Distribution | 8.4532 | Top 5% highest risk | HFTD TIER 2 | 3678580.6505 | 3220260.9918 | 458319.6587 |  | 0.037532 | 2.13e-05 | 0 | 7.25e-05 |  | 85799495.6829 |  |  | 453523.9109 | 0.44565 | 1017675.6815 |  |  | 4795.7478 | 0.006787 | 706607.9043 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000217 | 240-2032R | Segment-level | Distribution | 13.8096 | Top 5% highest risk | HFTD TIER 3 | 3665735.0887 | 3549053.9682 | 116681.1205 |  | 0.043791 | 2.13e-05 | 0 | 4.35e-05 |  | 81044542.2658 |  |  | 107379.2653 | 0.065853 | 1630585.3829 |  |  | 9301.8552 | 0.013132 | 708324.209 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000218 | 217-837R | Segment-level | Distribution | 12.6807 | Top 5% highest risk | HFTD TIER 3 | 3657183.3822 | 3461858.2787 | 195325.1034 |  | 0.038224 | 7.47e-05 | 0 | 0.000131 |  | 90568608.8895 |  |  | 187410.7511 | 0.093318 | 2008297.964 |  |  | 7914.3524 | 0.01115 | 709832.8536 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000219 | 354-24AE | Segment-level | Distribution | 3.6864 | Top 5% highest risk | HFTD TIER 2 | 3653653.987 | 3234791.8728 | 418862.1141 |  | 0.010941 | 2.13e-05 | 0 | 1.45e-05 |  | 295657789.3106 |  |  | 416154.1266 | 0.065871 | 6317713.8128 |  |  | 2707.9876 | 0.0037426 | 723557.8433 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000220 | 908-2040 | Segment-level | Distribution | 5.3209 | Top 5% highest risk | HFTD TIER 2 | 3646804.7891 | 3351774.2424 | 295030.5467 |  | 0.014493 | 5.34e-05 | 0 | 5.8e-05 |  | 231262108.4327 |  |  | 291221.4671 | 0.15948 | 1826064.3135 |  |  | 3809.0796 | 0.0053198 | 716019.3217 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000221 | 237-1761R | Segment-level | Distribution | 7.4915 | Top 5% highest risk | HFTD TIER 3 | 3634146.4134 | 3612196.0957 | 21950.3177 |  | 0.025622 | 1.07e-05 | 0 | 0 |  | 140981355.5513 |  |  | 17960.9578 | 0.1181 | 152089.0623 |  |  | 3989.3599 | 0.0056356 | 707885.5629 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000222 | 222-1988R | Segment-level | Distribution | 0.94526 | Top 5% highest risk | HFTD TIER 3 | 3619435.5667 | 3592933.5686 | 26501.9982 |  | 0.0034242 | 0 | 0 | 0 |  | 1049276785.4039 |  |  | 25896.588 | 0.34035 | 76087.9303 |  |  | 605.4102 | 0.0008364 | 723828.5532 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000223 | 350-2188R | Segment-level | Distribution | 22.0576 | Top 5% highest risk | HFTD TIER 2 | 3602011.8741 | 3439370.2131 | 162641.661 |  | 0.062025 | 8.54e-05 | 2.21e-05 | 5.8e-05 |  | 55451532.5021 |  |  | 147102.2415 | 0.067198 | 2189093.1179 |  |  | 15539.4195 | 0.021987 | 706742.0189 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000224 | 220-298R | Segment-level | Distribution | 33.1318 | Top 5% highest risk | HFTD TIER 3 | 3585631.4391 | 3204472.4076 | 381159.0315 |  | 0.090418 | 5.34e-05 | 0 | 0.000131 |  | 35440490.0724 |  |  | 360773.6342 | 0.38271 | 942688.3899 |  |  | 20385.3974 | 0.028642 | 711725.9625 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000225 | 1233-585R | Segment-level | Distribution | 6.2353 | Top 5% highest risk | HFTD TIER 3 | 3561958.681 | 3505652.5681 | 56306.1129 |  | 0.018499 | 0 | 0 | 0 |  | 189500879.3856 |  |  | 51908.639 | 0.10516 | 493621.4466 |  |  | 4397.4739 | 0.0062246 | 706466.9099 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000226 | 441-23R | Segment-level | Distribution | 5.1261 | Top 5% highest risk | HFTD TIER 3 | 3518020.3842 | 3428404.8814 | 89615.5027 |  | 0.021156 | 0 | 0 | 1.45e-05 |  | 162050485.0276 |  |  | 86815.4737 | 0.52271 | 166085.7388 |  |  | 2800.029 | 0.0039592 | 707220.9036 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000227 | 974-23R | Segment-level | Distribution | 16.0805 | Top 5% highest risk | HFTD TIER 3 | 3492862.6133 | 3272567.438 | 220295.1753 |  | 0.046051 | 4.27e-05 | 0 | 0.000102 |  | 71063364.8059 |  |  | 210871.8591 | 0.1054 | 2000621.0357 |  |  | 9423.3161 | 0.013266 | 710357.3235 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000228 | 230-2060R | Segment-level | Distribution | 9.1409 | Top 5% highest risk | HFTD TIER 2 | 3473455.3851 | 3392757.0341 | 80698.3511 |  | 0.025912 | 0 | 0 | 0 |  | 130933815.7643 |  |  | 74143.8925 | 0.053361 | 1389482.4002 |  |  | 6554.4586 | 0.0091416 | 716992.496 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000229 | 454-48F | Segment-level | Distribution | 3.4244 | Top 5% highest risk | HFTD TIER 2 | 3441166.132 | 3430799.5759 | 10366.5561 |  | 0.011469 | 0 | 0 | 0 |  | 299141983.1114 |  |  | 8747.5191 | 0.071728 | 121954.7168 |  |  | 1619.0369 | 0.0022904 | 706879.5468 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000230 | 520-1509R | Segment-level | Distribution | 15.3043 | Top 5% highest risk | HFTD TIER 2 | 3413911.7889 | 3165391.0031 | 248520.7858 |  | 0.043215 | 4.27e-05 | 0 | 0 |  | 73247845.718 |  |  | 238763.1895 | 0.22859 | 1044515.9686 |  |  | 9757.5962 | 0.013805 | 706826.3386 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000231 | 444-43R | Segment-level | Distribution | 20.6063 | Top 5% highest risk | HFTD TIER 2 | 3413813.7465 | 3334274.9115 | 79538.835 |  | 0.10918 | 4.27e-05 | 0 | 2.9e-05 |  | 30540141.4176 |  |  | 68095.9501 | 0.087106 | 781763.1719 |  |  | 11442.8848 | 0.01612 | 709838.7658 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000232 | 920-1342R | Segment-level | Distribution | 6.3664 | Top 5% highest risk | HFTD TIER 3 | 3406645.8369 | 3384146.9602 | 22498.8767 |  | 0.019161 | 3.2e-05 | 0 | 1.45e-05 |  | 176612719.334 |  |  | 18401.7954 | 0.043669 | 421394.5739 |  |  | 4097.0813 | 0.0057742 | 709549.6001 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000233 | 176-1845R | Segment-level | Distribution | 7.3522 | Top 5% highest risk | HFTD TIER 3 | 3401023.3781 | 3324151.4369 | 76871.9411 |  | 0.022022 | 0 | 0 | 0 |  | 150946845.7421 |  |  | 71858.0781 | 0.18066 | 397759.2819 |  |  | 5013.863 | 0.0070988 | 706297.2618 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000234 | 246-34R | Segment-level | Distribution | 12.821 | Top 5% highest risk | HFTD TIER 3 | 3387005.7991 | 3202236.9481 | 184768.851 |  | 0.033834 | 1.07e-05 | 4.42e-05 | 8.7e-05 |  | 94645532.5441 |  |  | 176039.3904 | 0.02429 | 7247342.156 |  |  | 8729.4605 | 0.012364 | 706049.9631 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000235 | CB SL1 | Segment-level | Distribution | 6.6007 | Top 5% highest risk | HFTD TIER 3 | 3361570.4894 | 3150269.9344 | 211300.5549 |  | 0.021049 | 3.2e-05 | 2.21e-05 | 0 |  | 149662216.8272 |  |  | 206030.4113 | 0.16692 | 1234288.5753 |  |  | 5270.1437 | 0.007302 | 721739.7497 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000236 | 791-419F | Segment-level | Distribution | 5.507 | Top 5% highest risk | HFTD TIER 2 | 3349759.3853 | 3101216.4739 | 248542.9114 |  | 0.02105 | 3.2e-05 | 0 | 1.45e-05 |  | 147328997.8874 |  |  | 244656.6803 | 0.0867 | 2821889.3774 |  |  | 3886.2311 | 0.0055036 | 706125.28 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000237 | CB 1023 | Segment-level | Distribution | 3.9246 | Top 5% highest risk | HFTD TIER 2 | 3332738.6224 | 3326464.9375 | 6273.685 |  | 0.012075 | 0 | 0 | 0 |  | 275492764.7686 |  |  | 3614.8923 | 0.066411 | 54431.9685 |  |  | 2658.7926 | 0.003781 | 703198.2596 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000238 | CB 234 | Segment-level | Distribution | 11.0316 | Top 5% highest risk | HFTD TIER 2 | 3294852.9726 | 3257846.8436 | 37006.1289 |  | 0.028907 | 8.54e-05 | 2.21e-05 | 0.000131 |  | 112699407.1983 |  |  | 29794.9831 | 0.0056612 | 5263015.464 |  |  | 7211.1458 | 0.010089 | 714724.9352 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000239 | 221-23R | Segment-level | Distribution | 7.9883 | Top 5% highest risk | HFTD TIER 3 | 3270237.5696 | 3013932.7368 | 256304.8328 |  | 0.026617 | 1.07e-05 | 0 | 1.45e-05 |  | 113232523.9625 |  |  | 250367.2007 | 0.16449 | 1522124.1566 |  |  | 5937.6321 | 0.0083448 | 711536.7759 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000240 | 157-232R | Segment-level | Distribution | 10.9006 | Top 5% highest risk | HFTD TIER 3 | 3160507.9457 | 3010962.3601 | 149545.5856 |  | 0.036403 | 5.34e-05 | 0 | 4.35e-05 |  | 82711474.8187 |  |  | 142243.2326 | 0.27502 | 517204.109 |  |  | 7302.353 | 0.010244 | 712869.7936 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000241 | 396-699R | Segment-level | Distribution | 20.4475 | Top 5% highest risk | HFTD TIER 2 | 3136951.6678 | 2766176.8265 | 370774.8413 |  | 0.048558 | 2.13e-05 | 2.21e-05 | 0.000102 |  | 56966448.9175 |  |  | 357592.253 | 0.089609 | 3990566.3135 |  |  | 13182.5882 | 0.01847 | 713745.1945 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000242 | 75-2259F | Segment-level | Distribution | 4.3521 | Top 5% highest risk | HFTD TIER 3 | 3135457.623 | 3128270.3011 | 7187.3219 |  | 0.011275 | 0 | 0 | 0 |  | 277446989.9495 |  |  | 4454.2562 | 0.0052 | 856587.7231 |  |  | 2733.0658 | 0.0038622 | 707644.8072 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000243 | 157-1928R | Segment-level | Distribution | 3.1864 | Top 5% highest risk | HFTD TIER 3 | 3052674.4598 | 3024212.5715 | 28461.8883 |  | 0.0095218 | 1.07e-05 | 0 | 0 |  | 317609335.5769 |  |  | 26568.0107 | 0.26902 | 98758.7167 |  |  | 1893.8776 | 0.0026628 | 711235.3783 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000244 | 233-123R | Segment-level | Distribution | 15.066 | Top 5% highest risk | HFTD TIER 2 | 3035804.5149 | 3000562.2494 | 35242.2655 |  | 0.041026 | 5.34e-05 | 2.21e-05 | 5.8e-05 |  | 73138777.9682 |  |  | 24952.003 | 0.005638 | 4425683.3989 |  |  | 10290.2625 | 0.014587 | 705450.3044 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000245 | 79-799R | Segment-level | Distribution | 6.7625 | Top 5% highest risk | HFTD TIER 3 | 3034823.4797 | 2947432.5106 | 87390.9691 |  | 0.035948 | 3.2e-05 | 0 | 2.9e-05 |  | 81991557.5453 |  |  | 83523.0373 | 0.72925 | 114532.2562 |  |  | 3867.9318 | 0.00548 | 705826.9771 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000246 | CB PE1 | Segment-level | Distribution | 6.7553 | Top 5% highest risk | HFTD TIER 3 | 3027547.9213 | 2867898.2114 | 159649.7099 |  | 0.020318 | 0 | 2.21e-05 | 0 |  | 141149226.3783 |  |  | 154685.5626 | 0.21434 | 721685.826 |  |  | 4964.1473 | 0.0070232 | 706821.2986 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000247 | 1233-587R | Segment-level | Distribution | 7.6085 | Top 5% highest risk | HFTD TIER 3 | 2983729.0544 | 2921127.9574 | 62601.0969 |  | 0.022854 | 0 | 0 | 0 |  | 127814685.8997 |  |  | 57541.4404 | 0.1049 | 548509.9889 |  |  | 5059.6565 | 0.0071282 | 709808.4419 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000248 | 520-1045R | Segment-level | Distribution | 8.7312 | Top 5% highest risk | HFTD TIER 2 | 2978813.9644 | 2899717.5924 | 79096.372 |  | 0.027405 | 0 | 0 | 1.45e-05 |  | 105811345.264 |  |  | 73616.8404 | 0.23313 | 315772.9409 |  |  | 5479.5316 | 0.007699 | 711719.9057 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000249 | 206-1817 | Segment-level | Distribution | 11.7296 | Top 5% highest risk | HFTD TIER 2 | 2976573.4131 | 2969126.7016 | 7446.7115 |  | 0.027806 | 5.34e-05 | 4.42e-05 | 0.000116 |  | 106780072.7026 |  |  | 0 | 0 | 0 |  |  | 7446.7115 | 0.010402 | 715906.0457 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000250 | 177-955 | Segment-level | Distribution | 4.7979 | Top 5% highest risk | HFTD TIER 2 | 2963405.8552 | 2318246.7809 | 645159.0743 |  | 0.014615 | 2.1e-05 | 0 | 4.4e-05 |  | 158623229.9407 |  |  | 641882.4257 | 0.098029 | 6547869.6728 |  |  | 3276.6486 | 0.004614 | 710153.5711 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000251 | 1023-200R | Segment-level | Distribution | 3.7841 | Top 5% highest risk | HFTD TIER 2 | 2889973.2177 | 2868050.8454 | 21922.3723 |  | 0.011031 | 0 | 0 | 1.45e-05 |  | 259989742.4993 |  |  | 19336.8689 | 0.068467 | 282426.1159 |  |  | 2585.5034 | 0.0036162 | 714978.0006 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000252 | 452-38AE | Segment-level | Distribution | 2.7653 | Top 5% highest risk | HFTD TIER 2 | 2823751.4759 | 2821884.1608 | 1867.3151 |  | 0.0087492 | 3.2e-05 | 0 | 0 |  | 322530535.4518 |  |  | 0 | 0 | 0 |  |  | 1867.3151 | 0.002646 | 705712.4296 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000253 | 236-1561R | Segment-level | Distribution | 5.1765 | Top 5% highest risk | HFTD TIER 3 | 2823578.0947 | 2746271.3929 | 77306.7018 |  | 0.015422 | 2.13e-05 | 0 | 1.45e-05 |  | 178072609.1513 |  |  | 73882.5515 | 0.15742 | 469339.9197 |  |  | 3424.1503 | 0.0048156 | 711053.7315 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000254 | CB 305 | Segment-level | Distribution | 5.6647 | Top 5% highest risk | Non-HFTD | 2786773.8569 | 2706155.2356 | 80618.6213 |  | 0.015532 | 9.48e-06 | 0 | 9.09e-06 |  | 174233201.2783 |  |  | 76146.1924 | 0.052098 | 1461595.3095 |  |  | 4472.4289 | 0.006319 | 707774.7902 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000255 | 212-773R | Segment-level | Distribution | 11.8401 | Top 5% highest risk | HFTD TIER 2 | 2758566.7114 | 2642067.3385 | 116499.3729 |  | 0.038893 | 1.07e-05 | 0 | 7.25e-05 |  | 67931693.0683 |  |  | 109237.1393 | 0.14975 | 729459.4708 |  |  | 7262.2336 | 0.010168 | 714238.4357 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000256 | 1001-1130R | Segment-level | Distribution | 3.7048 | Top 5% highest risk | HFTD TIER 2 | 2758282.9631 | 2661345.2595 | 96937.7036 |  | 0.010126 | 2.13e-05 | 6.63e-05 | 1.45e-05 |  | 262822956.6994 |  |  | 94204.2314 | 0.092166 | 1022112.5684 |  |  | 2733.4722 | 0.0038744 | 705521.4161 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000257 | CB 907 | Segment-level | Distribution | 1.375 | Top 5% highest risk | HFTD TIER 3 | 2742283.7877 | 2737736.2405 | 4547.5472 |  | 0.0041516 | 0 | 0 | 2.9e-05 |  | 659441237.2408 |  |  | 3493.5447 | 0.01806 | 193441.0136 |  |  | 1054.0025 | 0.0014568 | 723505.272 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000258 | 221-344R | Segment-level | Distribution | 11.5724 | Top 5% highest risk | HFTD TIER 3 | 2735928.315 | 2629449.2922 | 106479.0228 |  | 0.034505 | 6.4e-05 | 2.21e-05 | 2.9e-05 |  | 76205319.0341 |  |  | 98624.0236 | 0.16595 | 594283.8733 |  |  | 7854.9991 | 0.011042 | 711400.4438 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000259 | 231-1136R | Segment-level | Distribution | 13.2557 | Top 5% highest risk | HFTD TIER 2 | 2730917.723 | 2684541.5144 | 46376.2086 |  | 0.036478 | 0 | 0 | 0 |  | 73593036.7847 |  |  | 37502.001 | 0.0056314 | 6659445.4289 |  |  | 8874.2076 | 0.012545 | 707390.002 |  |  | see row 2 | not applicable | SDG&E | 2026
2150000260 | 217-48AE | Segment-level | Distribution | 15.1559 | Top 5% highest risk | HFTD TIER 2 | 2727584.5153 | 2396177.964 | 331406.5513 |  | 0.045211 | 3.2e-05 | 0 | 2.92e-05 |  | 52999888.6108 |  |  | 321334.4889 | 0.14291 | 2248493.7404 |  |  | 10072.0624 | 0.014237 | 707446.8554 |  |  | see row 2 | not applicable | SDG&E | 2026