## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | ANNUAL QUANTITATIVE TARGET | PROJECTED QUANTITATIVE PROGRESS Q1 | PROJECTED QUANTITATIVE PROGRESS Q1-2 | PROJECTED QUANTITATIVE PROGRESS Q1-3 | PROJECTED QUANTITATIVE PROGRESS Q1-4 | ANNUAL QUALITATIVE TARGET
2010000000 | PG&E | 2025-07-28 | Program |  |  | Detailed Inspection - Transmission | Complete detailed inspections on transmission structures in PG&E's asset registry as defined on the first business day of the target year. Please note that this projected target may require modification based on changes in the risk output. | Detailed inspections on transmission structures in PG&E's asset registry | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.1 | AI-04 | PG&E_Grid Design, Operations, and Maintenance_Asset Inspections_AI-04_2026 | 232 | Equipment ignition likelihood | Yes | Transmission Structures | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 22000 | 0 | 13200 | 22000 | 22000
2010000001 | PG&E | 2025-07-28 | Program |  |  | Infrared Inspections - Transmission | Infrared patrols will be performed on circuit miles of energized transmission line. Please note that the projected target may require modification based on changes in the risk output. | Infrared patrols on circuit miles of energized transmission line. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.3 | AI-06 | PG&E_Grid Design, Operations, and Maintenance_Asset Inspections_AI-06_2026 | 235 | Equipment ignition likelihood | Yes | Circuit miles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 2500 | 0 | 500 | 1500 | 2500
2010000002 | PG&E | 2025-07-28 | Program |  |  | Aerial Scan Inspections - Distribution | Complete aerial scan inspections on distribution poles, which will be identified in PG&E's asset registry at the time of work plan development and thus may require modification based on changes in the asset registry. | Detailed inspections on distribution poles in PG&E's asset registry. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.8 | AI-07A | PG&E_Grid Design, Operations, and Maintenance_Asset Inspections_AI-07A_2026 | 240 | Equipment ignition likelihood | Yes | Distribution Poles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 50000 | 0 | 30000 | 50000 | 50000
2010000003 | PG&E | 2025-07-28 | Program |  |  | Detailed Inspections - Distribution | Complete detailed inspections on distribution poles, which will be identified in PG&E's asset registry at the time of work plan development and thus may require modification based on changes in the asset registry. Inspections may be completed by either ground or aerial methods. | Detailed inspections on distribution poles in PG&E's asset registry. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.3.8 | AI-07D | PG&E_Grid Design, Operations, and Maintenance_Asset Inspections_AI-07D_2026 | 240 | Equipment ignition likelihood | Yes | Distribution Poles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 300000 | 0 | 90000 | 190000 | 300000
2010000004 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-09-30 | Community Engagement - Outreach to HFRA Infrastructure Customers | PG&E will perform annual outreach via email and/or phone to assigned Critical Infrastructure customers in the HFRA through Business Energy Solutions (assigned account managers). Outreach will cover the WMP, including potential PSPS and EPSS impacts, and updating contact information for critical accounts in the HFRA. | Annual outreach via email and/or phone to assigned Critical Infrastructure customers in the HFRA through Business Energy Solutions (assigned account managers). | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | 11.4.3 | CO-04 | PG&E_Emergency Preparedness, Collaboration and Public Awareness_Public Communication, Outreach, and Education Awareness_CO-04_2026 | 510 | Wildfire vulnerability | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Outreach to HFRA Infrastructure Customers
2010000005 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-09-30 | Community Engagement - Outage Preparedness Campaign | PG&E will conduct at least one direct-to-customer outage preparedness campaign annually via email and/or direct mail targeting residential customers within the PSPS and EPSS program scope. | Direct-to-customer outage preparedness campaign via email and/or direct mail targeting residential customers within the PSPS and EPSS program scope. | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | 11.4.3 | CO-05 | PG&E_Emergency Preparedness, Collaboration and Public Awareness_Public Communication, Outreach, and Education Awareness_CO-05_2026 | 510 | Wildfire vulnerability | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Outage Preparedness Campaign
2010000006 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-12-31 | Participate in Company Disaster Recovery Exercise | Meteorology Operations and Fire Science will participate in company disaster recovery exercise and test the failover capabilities of our AWS-cloud Meteorology Enterprise System. | Participate in company disaster recovery exercise and test the failover capabilities of our AWS-cloud Meteorology Enterprise System. | Enterprise Systems | Enterprise Systems Development |  | 12.1.1 | ES-04 | PG&E_Enterprise Systems_Enterprise Systems Development_ES-04_2026 | 542 | Wildfire exposure potential | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Participate in Company Disaster Recovery Exercise
2010000007 | PG&E | 2025-07-28 | Program |  |  | System Hardening - Undergrounding | Complete work associated with undergrounding for base system hardening work, fire rebuild work, and other (e.g. work requested by other, capacity, and rule 20A) undergrounding work. This commitment excludes community rebuild areas per revision notice RN-PG&E-26-05. | Undergrounding electric distribution system assets. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.2 | GH-04 | PG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_GH-04_2026 | 201 | Equipment ignition likelihood | No | Circuit Miles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 358 |  |  |  | 358
2010000008 | PG&E | 2025-07-28 | Program |  |  | System Hardening - Transmission Shunt Splices | Install shunt splice(s) on transmission lines. | Install shunt splice(s) on transmission lines. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.5.1 | GH-06 | PG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_GH-06_2026 | 208 | Equipment ignition likelihood | No | Shunt Splices | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 250 |  |  |  | 250
2010000009 | PG&E | 2025-07-28 | Program |  |  | System Hardening - Transmission Conductor Segment Replacement | Replace conductor segments on transmission lines traversing HFTD/HFRA areas.​ | Replace conductor segments on transmission lines. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.5.1 | GH-11 | PG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_GH-11_2026 | 208 | Equipment ignition likelihood | No | Conductor Segment | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 4 |  |  |  | 4
2010000010 | PG&E | 2025-07-28 | Program |  |  | Overhead Hardening - Distribution | Complete work associated with overhead hardening for base system hardening work, fire rebuild work, and other (e.g. work requested by other, capacity) overhead hardening work. This commitment excludes community rebuild areas per revision notice RN-PG&E-26-05. | Overhead system hardening | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.1 | GH-12 | PG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_GH-12_2026 | 184 | Equipment ignition likelihood | No | Circuit Miles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 294 |  |  |  | 294
2010000011 | PG&E | 2025-07-28 | Program |  |  | Line Removal Enabled by Remote Grid - Distribution | Complete line removal enabled by remote grid target, including work associated with line removal enabled by remote grid for base system hardening work, and fire rebuild work. This commitment excludes community rebuild areas per revision notice RN-PG&E-26-05. | Overhead line removal associated with remote grid installations | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.7.1 | GH-14 | PG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_GH-14_2026 | 211 | Equipment ignition likelihood | No | Circuit miles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 4 |  |  |  | 4
2010000012 | PG&E | 2025-07-28 | Program |  |  | Asset Inspections Distribution Quality Assurance | Achieve Quality Assurance Pass Rate for Asset Inspections Distribution. | Quality Assurance - Distribution | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.5.1 | GM-01D | PG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_GM-01D_2026 | 305 | Equipment ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 95% |  |  |  | 95%
2010000013 | PG&E | 2025-07-28 | Program |  |  | Asset Inspections Transmission Quality Assurance | Achieve Quality Assurance Pass Rate for Asset Inspections Transmission. | Quality Assurance - Transmission | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.5.1 | GM-01T | PG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_GM-01T_2026 | 305 | Equipment ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 95% |  |  |  | 95%
2010000014 | PG&E | 2025-07-28 | Program |  |  | Open Tag Reduction - Distribution Backlog | Close additional EC notifications on top of closing an equivalent number of EC notifications created in locations in 2025. | Close EC notifications and reduce wildfire risk. | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | 8.6.2 | GM-03 | PG&E_Grid Design, Operations, and Maintenance_Work Orders (Asset Management)_GM-03_2026 | 321 | Equipment ignition likelihood | No | Distribution EC Tags | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 134% |  |  |  | 134%
2010000015 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-02-15 | Updates on EPSS Reliability Study | Provide annually an updated Enhanced Powerline Safety Settings (EPSS) reliability impact study in alignment with prior WMP EPSS reliability studies and any associated ACIs. | Provide annually an updated Enhanced Powerline Safety Settings (EPSS) reliability impact study. | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | 8.7.1.1 | GM-07 | PG&E_Grid Design, Operations, and Maintenance_Grid Operations and Procedures_GM-07_2026 | 332 | Equipment ignition likelihood | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Updates on EPSS Reliability Study
2010000016 | PG&E | 2025-07-28 | Program |  |  | Asset Inspections Distribution Quality Control | Achieve Quality Control Pass Rate for Asset Inspections Distribution. | Quality Control - Distribution | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.5.1 | GM-09D | PG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_GM-09D_2026 | 305 | Equipment ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 95% |  |  |  | 95%
2010000017 | PG&E | 2025-07-28 | Program |  |  | Asset Inspection Transmission Quality Control | Achieve Quality Control Pass Rates for each Asset Inspection Transmission. | Quality Control - Transmission | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.5.1 | GM-09T | PG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_GM-09T_2026 | 305 | Equipment ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 95% |  |  |  | 95%
2010000018 | PG&E | 2025-07-28 | Program |  |  | System Hardening Distribution Quality Assurance | Achieve Quality Assurance pass rate for System Hardening Distribution. | Quality Assurance - System Hardening | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.5.1 | GM-10D | PG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_GM-10D_2026 | 305 | Equipment ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 88% |  |  |  | 88%
2010000019 | PG&E | 2025-07-28 | Program |  |  | System Hardening Distribution Quality Control | Achieve Quality Control Pass Rate for System Hardening Distribution. | Quality Control - System Hardening | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.5.1 | GM-11D | PG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_GM-11D_2026 | 305 | Equipment ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 80% |  |  |  | 80%
2010000020 | PG&E | 2025-07-28 | Program |  |  | Open Tag Reduction Distribution Backlog Quality Assurance | Achieve Quality Assurance Pass Rate for Open Tag Reduction Distribution Backlog | Quality Assurance - Distribution Tags | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.5.1 | GM-12D | PG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_GM-12D_2026 | 305 | Equipment ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 88% |  |  |  | 88%
2010000021 | PG&E | 2025-07-28 | Program |  |  | Open Tag Reduction Distribution Backlog Quality Control | Achieve Quality Control Pass Rate for Open Tag Reduction Distribution Backlog. | Quality Control - Distribution Tags | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.5.1 | GM-13D | PG&E_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control (Asset Management)_GM-13D_2026 | 305 | Equipment ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 80% |  |  |  | 80%
2010000022 | PG&E | 2025-07-28 | Program |  |  | Service Breakaway Connectors | Add OH service Breakaway Disconnects at service points. | Add OH service Breakaway Disconnects at service points. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.2.10.6 | GM-14 | PG&E_Grid Design, Operations, and Maintenance_Grid Design and System Hardening_GM-14_2026 | 223 | Equipment ignition likelihood | No | Service Breakaway Connectors | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 200 |  |  |  | 200
2010000023 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-05-01 | Workforce Planning - Distribution Asset Inspection | PG&E will continue our annual training program review for QCR workers focused on Distribution Inspections which supports wildfire mitigation. | Training program review for QCR workers focused on Distribution Inspections which supports wildfire mitigation. | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | 8.8.1 | GM-15 | PG&E_Grid Design, Operations, and Maintenance_Workforce Planning (Asset Management)_GM-15_2026 | 350 | Equipment ignition likelihood | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Workforce Planning
2010000024 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-12-31 | Continue sharing PSPS lessons learned | Continue sharing PSPS lessons learned and best practices with other IOUs in CA through monthly meetings focused on PSPS. | Continue sharing PSPS lessons learned and best practices with other IOUs in CA. | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | 11.3 | PS-10 | PG&E_Emergency Preparedness, Collaboration and Public Awareness_External Collaboration and Coordination_PS-10_2026 | 499 | PSPS likelihood | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Continue sharing PSPS lessons learned
2010000025 | PG&E | 2025-07-28 | Program |  |  | Line Sensor - Installations | Install Line Sensor devices on circuit locations. | Install Line Sensor devices on circuit locations. | Situational Awareness and Forecasting | Grid Monitoring Systems |  | 10.3.1 | SA-02 | PG&E_Situational Awareness and Forecasting_Grid Monitoring Systems_SA-02_2026 | 447 | Equipment ignition likelihood | No | Sensor Locations | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 240 |  |  |  | 240
2010000026 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-12-31 | Evaluate camera AI system performance and new functionalities. | In partnership with Digital Path, evaluate camera AI system performance and explore additional enhancements. | Evaluate camera AI system performance and explore additional enhancements. | Situational Awareness and Forecasting | Ignition Detection Systems |  | 10.4.1 | SA-08 | PG&E_Situational Awareness and Forecasting_Ignition Detection Systems_SA-08_2026 | 454 | Equipment ignition likelihood | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Evaluate camera AI system performance and new functionalities
2010000027 | PG&E | 2025-07-28 | Program |  |  | Distribution Fault Anticipation (DFA) Installations | Install Distribution Fault Anticipation (DFA) sensors on circuits. One sensor will be installed per circuit. | Install Distribution Fault Anticipation (DFA) sensors on circuits. | Situational Awareness and Forecasting | Grid Monitoring Systems |  | 10.3.1 | SA-10 | PG&E_Situational Awareness and Forecasting_Grid Monitoring Systems_SA-10_2026 | 447 | Equipment ignition likelihood | No | Sensor Locations | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 15 |  |  |  | 15
2010000028 | PG&E | 2025-07-28 | Program |  |  | Early Fault Detection (EFD) - Installations | Install Early Fault Detection (EFD) sensors on circuit locations. | Install Early Fault Detection (EFD) sensors on circuit locations. | Situational Awareness and Forecasting | Grid Monitoring Systems |  | 10.3.1 | SA-11 | PG&E_Situational Awareness and Forecasting_Grid Monitoring Systems_SA-11_2026 | 447 | Equipment ignition likelihood | No | Sensor Locations | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 180 |  |  |  | 180
2010000029 | PG&E | 2025-07-28 | Program |  |  | Live Fuel Moisture Data Collection | Collect and process live fuel moisture samples from May to November | Collect and process live fuel moisture samples | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | 10.2.1 / 10.2.4 | SA-12 | PG&E_Situational Awareness and Forecasting_Environmental Monitoring Systems_SA-12_2026 | 437 / 446 | Equipment ignition likelihood | No | Sample Locations | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 25 |  |  |  | 25
2010000030 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-12-31 | Weather Station Network Evaluation | Review weather station coverage annually to determine priority installation or optimization locations. | Determine priority installation or optimization locations. | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | 10.2.4 | SA-13 | PG&E_Situational Awareness and Forecasting_Environmental Monitoring Systems_SA-13_2026 | 446 | Equipment ignition likelihood | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Weather Station Network Evaluation
2010000031 | PG&E | 2025-07-28 | Program |  |  | Weekly uptime of Wildfire Cameras | Maintain weekly average uptime percentage of Wildfire Cameras during peak fire season (May 1 – November 30) | Maintain weekly average uptime percentage of Wildfire Cameras during peak fire season | Situational Awareness and Forecasting | Ignition Detection Systems |  | 10.4.1 | SA-15 | PG&E_Situational Awareness and Forecasting_Ignition Detection Systems_SA-15_2026 | 454 | Equipment ignition likelihood | No | Average weekly uptime percentage | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 90% |  |  |  | 90%
2010000032 | PG&E | 2025-07-28 | Program |  |  | Weather Model Verification Tool | Develop an in-house model verification tool to evaluate performance of multiple weather models. | Develop an in-house model verification tool | Situational Awareness and Forecasting | Weather Forecasting |  | 10.5.3 | SA-16 | PG&E_Situational Awareness and Forecasting_Weather Forecasting_SA-16_2026 | 467 | Equipment ignition likelihood | No | Weather Model Verification Tool | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 1 |  |  |  | 1
2010000033 | PG&E | 2025-07-28 | Program |  |  | Weather Station Network Health | By October 1 of each year, ensure weather stations are operational and within internal calibration guidance. | Ensure weather stations are operational and within internal calibration guidance. | Situational Awareness and Forecasting | Weather Forecasting |  | 10.5.5 | SA-18 | PG&E_Situational Awareness and Forecasting_Weather Forecasting_SA-18_2026 | 468 | Equipment ignition likelihood | No | Percent of Weather Stations | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 95% |  |  |  | 95%
2010000034 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-12-31 | Weather Station Network Optimization | Annually review stations that are no longer accessible or unsafe to determine opportunities to remove or optimize. | Remove or optimize stations that are no longer accessible or unsafe. | Situational Awareness and Forecasting | Weather Forecasting |  | 10.5.5 | SA-19 | PG&E_Situational Awareness and Forecasting_Weather Forecasting_SA-19_2026 | 468 | Equipment ignition likelihood | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Weather Station Network Optimization
2010000035 | PG&E | 2025-07-28 | Program |  |  | Pole Clearing Program - Compliance | Inspect and clear and maintain where necessary approximately distribution and transmission poles and structures, which will be identified by inspections in the previous year per Vegetation Control Standard TD-7112S. Note that this projected target may require modification based on equipment replacement and undergrounding. | Inspect and clear distribution poles and transmission structures | Vegetation Management and Inspections | Pole Clearing |  | 9.4 | VM-02C | PG&E_Vegetation Management and Inspections_Pole Clearing_VM-02C_2026 | 384 | Contact from vegetation ignition likelihood | Yes | Poles | Note: Table 1 includes commitments due in 2026 that are externally reported. This commitment includes Distribution and Transmission Poles and Structures. | 2026 | 45710 | 13668 | 30958 | 45710 | 45710
2010000036 | PG&E | 2025-07-28 | Program |  |  | Pole Clearing Program - Risk Reduction | Inspect and clear and maintain where necessary approximately distribution and transmission poles and structures, which will be identified by inspections in the previous year per Vegetation Control Standard TD-7112S. Note that this projected target may require modification based on equipment replacement and undergrounding. | Inspect and clear distribution poles and transmission structures | Vegetation Management and Inspections | Pole Clearing |  | 9.4 | VM-02R | PG&E_Vegetation Management and Inspections_Pole Clearing_VM-02R_2026 | 384 | Contact from vegetation ignition likelihood | Yes | Poles | Note: Table 1 includes commitments due in 2026 that are externally reported. This commitment includes Distribution and Transmission Poles and Structures. | 2026 | 24290 | 6820 | 16445 | 24290 | 24290
2010000037 | PG&E | 2025-07-28 | Program |  |  | Substation Inspections - Distribution | Complete defensible space inspections in alignment with the guidelines set forth in LAND-5201P-01 at distribution substations. Co-located power generation switchyards and Transmission & Distribution substations are counted separately as two distinct units. | Defensible space inspections - Distribution Substations | Vegetation Management and Inspections | Defensible Space |  | 9.6 | VM-05 | PG&E_Vegetation Management and Inspections_Defensible Space_VM-05_2026 | 388 | Wildfire exposure potential | Yes | Distribution Substations | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 130 | 58 | 122 | 130 | 130
2010000038 | PG&E | 2025-07-28 | Program |  |  | Substation Inspections - Transmission | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at transmission substations. Co-located power generation switchyards and Transmission & Distribution substations are counted separately as two distinct units. | Defensible space inspections - Transmission Substations | Vegetation Management and Inspections | Defensible Space |  | 9.6 | VM-06 | PG&E_Vegetation Management and Inspections_Defensible Space_VM-06_2026 | 388 | Wildfire exposure potential | Yes | Transmission Substations | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 55 | 0 | 53 | 55 | 55
2010000039 | PG&E | 2025-07-28 | Program |  |  | Substation Inspections - Power Generation | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at Power Generation Switchyards and Powerhouses. Co-located Power Generation switchyards and Transmission & Distribution substations are counted separately as two distinct units. | Defensible space inspections - Power Generation Switchyards and Powerhouses | Vegetation Management and Inspections | Defensible Space |  | 9.6 | VM-07 | PG&E_Vegetation Management and Inspections_Defensible Space_VM-07_2026 | 388 | Wildfire exposure potential | Yes | Power Generation Switchyards and Powerhouses | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 58 | 0 | 52 | 58 | 58
2010000040 | PG&E | 2025-07-28 | Program |  |  | Vegetation Management Quality Assurance - Distribution | Achieve Quality Assurance Pass Rate at Audit Locations for VM Distribution Routine program. | Quality Assurance - VM Distribution Routine | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 9.11 | VM-08D | PG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_VM-08D_2026 | 414 | Contact from vegetation ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 97% |  |  |  | 97%
2010000041 | PG&E | 2025-07-28 | Program |  |  | Vegetation Management Quality Assurance - Transmission | Achieve Quality Assurance Pass Rate at Audit Locations for the Transmission Routine program. | Quality Assurance - VM Transmission Routine | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 9.11 | VM-08T | PG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_VM-08T_2026 | 414 | Contact from vegetation ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 97% |  |  |  | 97%
2010000042 | PG&E | 2025-07-28 | Program |  |  | Routine Transmission - Ground | Complete Routine Transmission Ground Inspection as defined by Transmissions Routine LiDAR detection point data systemwide. | Routine Transmission Ground Inspection | Vegetation Management and Inspections | Vegetation Management Inspections |  | 9.2.3 | VM-13 | PG&E_Vegetation Management and Inspections_Vegetation Management Inspections_VM-13_2026 | 374 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 17500 | 1989 | 10000 | 15000 | 17500
2010000043 | PG&E | 2025-07-28 | Program |  |  | Transmission Hazard Patrol (Second Patrol, Tree Mortality) | Complete Transmission Second Patrol Inspection, dependent on remote sensing (ORTHO Imagery). | Transmission Second Patrol Inspection | Vegetation Management and Inspections | Vegetation Management Inspections |  | 9.2.4 | VM-14 | PG&E_Vegetation Management and Inspections_Vegetation Management Inspections_VM-14_2026 | 379 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 5625 | 0 | 0 | 0 | 5625
2010000044 | PG&E | 2025-07-28 | Program |  |  | Distribution Routine Patrol | Complete Distribution Routine Annual Patrol Inspection of overhead circuit miles system wide. | VM Distribution Routine Annual Patrol Inspection | Vegetation Management and Inspections | Vegetation Management Inspections |  | 9.2.1 | VM-16 | PG&E_Vegetation Management and Inspections_Vegetation Management Inspections_VM-16_2026 | 365 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 78200 | 11500 | 31500 | 50500 | 78200
2010000045 | PG&E | 2025-07-28 | Program |  |  | Distribution Hazard Patrol | Complete Distribution Hazard Patrol Inspection in HFTD and HFRA locations categorized by risk. | VM Distribution Hazard Patrol Inspection | Vegetation Management and Inspections | Vegetation Management Inspections |  | 9.2.2 | VM-17 | PG&E_Vegetation Management and Inspections_Vegetation Management Inspections_VM-17_2026 | 370 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 10000 | 1500 | 4000 | 6500 | 10000
2010000046 | PG&E | 2025-07-28 | Program |  |  | Vegetation Management Quality Control - Distribution Routine | Achieve Quality Control Pass Rate at Audit Locations for the VM Distribution Routine program. | Quality Control - VM Distribution Routine | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 9.11 | VM-22D | PG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_VM-22D_2026 | 414 | Contact from vegetation ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 95% |  |  |  | 95%
2010000047 | PG&E | 2025-07-28 | Program |  |  | Vegetation Management Quality Control - Pole Clearing | Achieve Quality Control Pass Rate at Audit Locations for the VM Pole Clearing program. | Quality Control - VM Pole Clearing | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 9.11 | VM-22P | PG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_VM-22P_2026 | 414 | Contact from vegetation ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 95% |  |  |  | 95%
2010000048 | PG&E | 2025-07-28 | Program |  |  | Vegetation Management Quality Control - Transmission Routine | Achieve Quality Control Pass Rate at Audit Locations for the VM Transmission Routine program. | Quality Control - VM Transmission Routine | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 9.11 | VM-22T | PG&E_Vegetation Management and Inspections_Quality Assurance and Quality Control (Vegetation Management)_VM-22T_2026 | 414 | Contact from vegetation ignition likelihood | No | % Pass Rate | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 95% |  |  |  | 95%
2010000049 | PG&E | 2025-07-28 | Project | 2026-01-01 | 2026-12-31 | ​​Workforce Planning - Vegetation Management​ | Continue annually the execution of planned recruitment, retention, training of vegetation management, inspections personnel and partners. | Recruitment, retention, training of vegetation management and inspections personnel and partnerships. | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | 9.13 | VM-24 | PG&E_Vegetation Management and Inspections_Workforce Planning (Vegetation Management)_VM-24_2026 | 425 | Contact from vegetation ignition likelihood | No |  | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | [5 empty] | Execution of planned recruitment, retention, and training of vegetation management and inspections personnel and partnerships.
2010000050 | PG&E | 2025-07-28 | Program |  |  | Mitigation of Legacy Tree Removal Inventory (TRI) | Mitigate 135,000 trees from the legacy Tree Removal Inventory (cumulative) between 2026-2028. | Tree Removal Inventory | Vegetation Management and Inspections | Vegetation Management Inspections |  | 9.2.1 | VM-26 | PG&E_Vegetation Management and Inspections_Vegetation Management Inspections_VM-26_2026 | 365 | Contact from vegetation ignition likelihood | No | Trees | Note: Table 1 includes commitments due in 2026 that are externally reported. | 2026 | 40000 | 0 | 0 | 0 | 40000

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2020000000 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2026 | 943.6667 | 943.6667 | 943.6667
2020000001 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2026 | 335.3333 | 335.3333 | 335.3333
2020000002 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of WWS) | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2026 | 1244.3333 | 1244.3333 | 1244.3333
2020000003 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | PG&E | 2026 | 2026 | 275000 | 275000 | 275000
2020000004 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | PG&E | 2026 | 2026 | 100 | 100 | 100
2020000005 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | PG&E | 2026 | 2026 | 983117 | 986329 | 998868
2020000006 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | PG&E | 2026 | 2026 | 839774 | 852657 | 870497

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2030000000 | Weather-Normalized CPUC-Reportable Fire Ignitions Rate in R3+ Conditions (Rolling 365 days) | The metric measures the rate of Distribution and Transmission ignition incidents occurring in high-risk weather conditions normalized by 100,000 circuit miles and meeting the following criteria: Occur within PG&E’s High Fire Threat District (HFTD) and High Fire Risk Area (HFRA) Occur in high-risk weather conditions defined as meeting the criteria of Fire Potential Index (FPI) of R3, R4, R5 or R5+ Reportable to the CPUC per Decision 14-02-015. A reportable fire incident includes all the following: 1) Ignition is associated with PG&E’s electric assets, 2) something other than PG&E facilities burned, and 3) the resulting fire travelled more than one meter from the ignition point. The metric is reported as a YTD indicator for a rolling 365-day period. In case of a leap year, the metric will be reported for a rolling 366-day period. | This lagging metric enabled PG&E to assess its performance relative to the scale of the infrastructure and elevated risk conditions and directly supports the overarching goal of reducing wildfire risk. | (1) The metric focuses on ignitions occurring in elevated wildfire risk conditions as measured by the FPI of R3 and above; historical ignitions occurring in R3+ conditions result in the most consequential fires; (2) The rolling metric addresses the issue of considerable swings during the first half of the year when the number of R3 days is low (often 0) | The metric performance is validated quarterly by PG&E’s Internal Audit. | Count of CPUC Reportable Ignitions in HFTD or HFRA occurring in high-risk weather conditions *100,000 / cumulative count of circuit miles in Fire Index Areas (FIA) exposed to high-risk weather conditions, calculated for a rolling 365-day period. |  | Due to the annual target-setting process for this metric which relies on the historical 3-year actual performance, we are unable to provide targets beyond 2025. | PG&E | 2026 | 2026

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 27.3333 | 27.3333 | 27.3333
2050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 73 | 73 | 73
2050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.6667 | 2.6667 | 2.6667
2050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 21.3333 | 21.3333 | 21.3333
2050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 511.3333 | 511.3333 | 511.3333
2050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 32.6667 | 32.6667 | 32.6667
2050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 15.3333 | 15.3333 | 15.3333
2050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 7.3333 | 7.3333 | 7.3333
2050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 101.6667 | 101.6667 | 101.6667
2050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 13.6667 | 13.6667 | 13.6667
2050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5.3333 | 5.3333 | 5.3333
2050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 51 | 51 | 51
2050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5.3333 | 5.3333 | 5.3333
2050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 7.3333 | 7.3333 | 7.3333
2050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1739 | 1739 | 1739
2050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 398.3333 | 398.3333 | 398.3333
2050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 315.6667 | 315.6667 | 315.6667
2050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.3333 | 4.3333 | 4.3333
2050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3.3333 | 3.3333 | 3.3333
2050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 712.6667 | 712.6667 | 712.6667
2050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 62 | 62 | 62
2050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 28.6667 | 28.6667 | 28.6667
2050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6.3333 | 6.3333 | 6.3333
2050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.6667 | 2.6667 | 2.6667
2050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 44.3333 | 44.3333 | 44.3333
2050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 10.6667 | 10.6667 | 10.6667
2050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1.6667 | 1.6667 | 1.6667
2050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 180.3333 | 180.3333 | 180.3333
2050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 13.6667 | 13.6667 | 13.6667
2050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5.3333 | 5.3333 | 5.3333
2050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.6667 | 4.6667 | 4.6667
2050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 167 | 167 | 167
2050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 19.3333 | 19.3333 | 19.3333
2050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3.6667 | 3.6667 | 3.6667
2050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.3333 | 4.3333 | 4.3333
2050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6 | 6 | 6
2050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 13.3333 | 13.3333 | 13.3333
2050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 19 | 19 | 19
2050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 68.3333 | 68.3333 | 68.3333
2050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 56 | 56 | 56
2050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 36.3333 | 36.3333 | 36.3333
2050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5 | 5 | 5
2050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.3333 | 4.3333 | 4.3333
2050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5.3333 | 5.3333 | 5.3333
2050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 75.3333 | 75.3333 | 75.3333
2050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.3333 | 4.3333 | 4.3333
2050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5.3333 | 5.3333 | 5.3333
2050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 73.6667 | 73.6667 | 73.6667
2050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 8.6667 | 8.6667 | 8.6667
2050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 239 | 239 | 239
2050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 16 | 16 | 16
2050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6 | 6 | 6
2050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 13.3333 | 13.3333 | 13.3333
2050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 12.3333 | 12.3333 | 12.3333
2050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1789.3333 | 1789.3333 | 1789.3333
2050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 286.3333 | 286.3333 | 286.3333
2050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 86.3333 | 86.3333 | 86.3333
2050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 38 | 38 | 38
2050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 11.3333 | 11.3333 | 11.3333
2050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 403.3333 | 403.3333 | 403.3333
2050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 8.3333 | 8.3333 | 8.3333
2050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1679.6667 | 1679.6667 | 1679.6667
2050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 140.6667 | 140.6667 | 140.6667
2050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 64 | 64 | 64
2050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 55.3333 | 55.3333 | 55.3333
2050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3.3333 | 3.3333 | 3.3333
2050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 7 | 7 | 7
2050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 191 | 191 | 191
2050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 35 | 35 | 35
2050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 17.3333 | 17.3333 | 17.3333
2050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 14 | 14 | 14
2050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1.6667 | 1.6667 | 1.6667
2050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 183.3333 | 183.3333 | 183.3333
2050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 28.6667 | 28.6667 | 28.6667
2050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 7.6667 | 7.6667 | 7.6667
2050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 10.6667 | 10.6667 | 10.6667
2050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4326.6667 | 4326.6667 | 4326.6667
2050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1004 | 1004 | 1004
2050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 892.6667 | 892.6667 | 892.6667
2050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 15 | 15 | 15
2050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 14.6667 | 14.6667 | 14.6667
2050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 7.6667 | 7.6667 | 7.6667
2050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 54.3333 | 54.3333 | 54.3333
2050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3.6667 | 3.6667 | 3.6667
2050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 53.6667 | 53.6667 | 53.6667
2050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2399 | 2399 | 2399
2050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 260.3333 | 260.3333 | 260.3333
2050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 120.3333 | 120.3333 | 120.3333
2050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 9.3333 | 9.3333 | 9.3333
2050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.6667 | 4.6667 | 4.6667
2050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3.3333 | 3.3333 | 3.3333
2050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 568 | 568 | 568
2050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 44 | 44 | 44
2050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 17.6667 | 17.6667 | 17.6667
2050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 9.6667 | 9.6667 | 9.6667
2050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 871.6667 | 871.6667 | 871.6667
2050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 120.3333 | 120.3333 | 120.3333
2050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 49.6667 | 49.6667 | 49.6667
2050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 971.6667 | 971.6667 | 971.6667
2050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 92.3333 | 92.3333 | 92.3333
2050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 47.3333 | 47.3333 | 47.3333
2050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 149.3333 | 149.3333 | 149.3333
2050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 19.6667 | 19.6667 | 19.6667
2050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 8 | 8 | 8
2050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 249.6667 | 249.6667 | 249.6667
2050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 71 | 71 | 71
2050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 41.3333 | 41.3333 | 41.3333
2050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 30 | 30 | 30
2050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.3333 | 4.3333 | 4.3333
2050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1.3333 | 1.3333 | 1.3333
2050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 110 | 110 | 110
2050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 19.6667 | 19.6667 | 19.6667
2050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 10 | 10 | 10
2050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.6667 | 4.6667 | 4.6667
2050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1370.3333 | 1370.3333 | 1370.3333
2050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 273.6667 | 273.6667 | 273.6667
2050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 111.3333 | 111.3333 | 111.3333
2050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 23.6667 | 23.6667 | 23.6667
2050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 87.3333 | 87.3333 | 87.3333
2050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 25.6667 | 25.6667 | 25.6667
2050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 9.3333 | 9.3333 | 9.3333
2050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5.3333 | 5.3333 | 5.3333
2050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 26.3333 | 26.3333 | 26.3333
2050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.6667 | 2.6667 | 2.6667
2050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 753.6667 | 753.6667 | 753.6667
2050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 80.6667 | 80.6667 | 80.6667
2050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 28.3333 | 28.3333 | 28.3333
2050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 191 | 191 | 191
2050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 9.6667 | 9.6667 | 9.6667
2050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3.6667 | 3.6667 | 3.6667
2050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 29 | 29 | 29
2050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3878.3333 | 3878.3333 | 3878.3333
2050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 513.3333 | 513.3333 | 513.3333
2050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 218 | 218 | 218
2050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6.3333 | 6.3333 | 6.3333
2050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 52.3333 | 52.3333 | 52.3333
2050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 11.6667 | 11.6667 | 11.6667
2050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5 | 5 | 5
2050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 444 | 444 | 444
2050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 67.3333 | 67.3333 | 67.3333
2050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 26.6667 | 26.6667 | 26.6667
2050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 43.3333 | 43.3333 | 43.3333
2050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.3333 | 4.3333 | 4.3333
2050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3932.3333 | 3932.3333 | 3932.3333
2050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 657 | 657 | 657
2050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 305 | 305 | 305
2050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 23 | 23 | 23
2050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2.3333 | 2.3333 | 2.3333
2050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 18.3333 | 18.3333 | 18.3333
2050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5.3333 | 5.3333 | 5.3333
2050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 115 | 115 | 115
2050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6.3333 | 6.3333 | 6.3333
2050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1.6667 | 1.6667 | 1.6667
2050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5.6667 | 5.6667 | 5.6667
2050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 300.6667 | 300.6667 | 300.6667
2050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 98.3333 | 98.3333 | 98.3333
2050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 56.3333 | 56.3333 | 56.3333
2050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 43 | 43 | 43
2050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 20 | 20 | 20
2050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.66667 | 0.66667 | 0.66667
2050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 27 | 27 | 27
2050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 15 | 15 | 15
2050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4.3333 | 4.3333 | 4.3333
2050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 14 | 14 | 14
2050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0.33333 | 0.33333 | 0.33333
2050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 150 | 150 | 150
2050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 42 | 42 | 42
2050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 10.3333 | 10.3333 | 10.3333
2050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 11903 | 11903 | 11903
2050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2011.6667 | 2011.6667 | 2011.6667
2050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 901 | 901 | 901
2050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 166.3333 | 166.3333 | 166.3333
2050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 83.3333 | 83.3333 | 83.3333
2050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 45 | 45 | 45
2050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 805.6667 | 805.6667 | 805.6667
2050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 260 | 260 | 260
2050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 97 | 97 | 97
2050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 149.6667 | 149.6667 | 149.6667
2050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 58 | 58 | 58
2050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 19.6667 | 19.6667 | 19.6667

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 54 | 54 | 54
2060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 16 | 16 | 16
2060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 49 | 49 | 49
2060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5 | 5 | 5
2060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 10 | 10 | 10
2060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 57 | 57 | 57
2060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 24 | 24 | 24
2060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 14 | 14 | 14
2060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6 | 6 | 6
2060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 40 | 40 | 40
2060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 25 | 25 | 25
2060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5 | 5 | 5
2060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 7 | 7 | 7
2060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6 | 6 | 6
2060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6 | 6 | 6
2060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5 | 5 | 5
2060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 14 | 14 | 14
2060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 10 | 10 | 10
2060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 2 | 2 | 2
2060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 9 | 9 | 9
2060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 5 | 5 | 5
2060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | No | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 6 | 6 | 6
2060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 9 | 9 | 9
2060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 11 | 11 | 11
2060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 3 | 3 | 3
2060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 1 | 1 | 1
2060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions | Yes | Projected values are based on a 3 year average. |  | PG&E | 2026 | 2026 | 0 | 0 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 4626.8 | 4626.8 | 4626.8
2070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 9427.8 | 9427.8 | 9427.8
2070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 6964.3 | 6964.3 | 6964.3
2070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 28916.6 | 28916.6 | 28916.6
2070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 412.5 | 412.5 | 412.5
2070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 4850.5 | 4850.5 | 4850.5
2070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 670.6 | 669.4 | 667.8
2070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 110.2 | 110.2 | 110.2
2070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 8399 | 8369.6 | 8331.3
2070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 5355.5 | 5342.9 | 5326.5
2070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 768.1 | 765.5 | 762.1
2070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 2306.5 | 2290.8 | 2270.3
2070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 259.8 | 259.1 | 258.2
2070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 31.7 | 31.7 | 31.7
2070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 3771.4 | 3641.3 | 3471.8
2070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 1606.3 | 1572.9 | 1529.4
2070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 313.1 | 301.5 | 286.4
2070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 313.4 | 305.3 | 294.6
2070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 574.3635 | 574.3635 | 574.3635
2070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1604.3793 | 1604.3793 | 1604.3793
2070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 875.423 | 875.423 | 875.423
2070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 7747.3875 | 7747.3875 | 7747.3875
2070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 47.3271 | 47.3271 | 47.3271
2070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1580.6756 | 1580.6756 | 1580.6756
2070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 100.6399 | 100.6399 | 100.6399
2070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 116.2407 | 116.2407 | 116.2407
2070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 851.8958 | 851.8958 | 851.8958
2070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 2054.2698 | 2054.2698 | 2054.2698
2070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 67.1669 | 67.1669 | 67.1669
2070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 958.3237 | 958.3237 | 958.3237
2070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 35.002 | 35.002 | 35.002
2070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 23.1582 | 23.1582 | 23.1582
2070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 300.9987 | 300.9987 | 300.9987
2070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 753.7378 | 753.7378 | 753.7378
2070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 27.054 | 27.054 | 27.054
2070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 133.1446 | 133.1446 | 133.1446
2070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 6476.2 | 6476.2 | 6476.2
2070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 12097.9 | 12097.9 | 12097.9
2070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 2805.5 | 2805.5 | 2805.5
2070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 3402.4 | 3402.4 | 3402.4
2070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 68 | 68 | 68
2070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 166.4 | 166.4 | 166.4
2070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 347.7 | 349.2 | 351.1
2070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 51.4 | 51.4 | 51.4
2070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 1317 | 1353.8 | 1401.8
2070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 502.8 | 518.5 | 539
2070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 100.5 | 103.8 | 108.1
2070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 249.4 | 269.1 | 294.7
2070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 130 | 130.9 | 132.1
2070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 9.9 | 9.9 | 9.9
2070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 1009 | 1171.7 | 1383.6
2070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 297.5 | 339.2 | 393.6
2070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 40.8 | 55.4 | 74.3
2070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 7 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 67.3 | 77.5 | 90.8
2070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 23.521 | 23.521 | 23.521
2070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 100.4945 | 100.4945 | 100.4945
2070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 10.8743 | 10.8743 | 10.8743
2070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 36.3053 | 36.3053 | 36.3053
2070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1.6534 | 1.6534 | 1.6534
2070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0.14894 | 0.14894 | 0.14894
2070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1.1211 | 1.1211 | 1.1211
2070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 7.8692 | 7.8692 | 7.8692
2070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0.58353 | 0.58353 | 0.58353
2070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0.35051 | 0.35051 | 0.35051
2070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 13127 | 13127 | 13127
2070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 30667 | 30667 | 30667
2070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 6502 | 6502 | 6502
2070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 8474 | 8474 | 8474
2070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 231 | 231 | 231
2070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 679 | 679 | 679
2070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 988 | 988 | 988
2070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 180 | 180 | 180
2070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 3018 | 3018 | 3018
2070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1434 | 1434 | 1434
2070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 314 | 314 | 314
2070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 411 | 411 | 411
2070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 361 | 361 | 361
2070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 50 | 50 | 50
2070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1675 | 1675 | 1675
2070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 592 | 592 | 592
2070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 159 | 159 | 159
2070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 115 | 115 | 115
2070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1240123 | 1240123 | 1240123
2070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 2598093 | 2598093 | 2598093
2070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 411369 | 411369 | 411369
2070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 321627 | 321627 | 321627
2070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 10100 | 10100 | 10100
2070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 12808 | 12808 | 12808
2070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 69605 | 69605 | 69605
2070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 3751 | 3751 | 3751
2070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 190988 | 190988 | 190988
2070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 32715 | 32715 | 32715
2070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 16457 | 16457 | 16457
2070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 10266 | 10266 | 10266
2070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 27309 | 27309 | 27309
2070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1803 | 1803 | 1803
2070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 104584 | 104584 | 104584
2070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 11426 | 11426 | 11426
2070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 9131 | 9131 | 9131
2070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 2553 | 2553 | 2553
2070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 98101 | 98101 | 98101
2070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 307607 | 307607 | 307607
2070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 53802 | 53802 | 53802
2070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 156200 | 156200 | 156200
2070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1822 | 1822 | 1822
2070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 13390 | 13390 | 13390
2070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 3258 | 3258 | 3258
2070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 771 | 771 | 771
2070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 17969 | 17969 | 17969
2070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 10870 | 10870 | 10870
2070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1682 | 1682 | 1682
2070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 3366 | 3366 | 3366
2070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1296 | 1296 | 1296
2070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 175 | 175 | 175
2070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 7875 | 7875 | 7875
2070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 3346 | 3346 | 3346
2070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 678 | 678 | 678
2070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 564 | 564 | 564
2070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 334709 | 334709 | 334709
2070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 861178 | 861178 | 861178
2070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 113088 | 113088 | 113088
2070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 118389 | 118389 | 118389
2070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 2938 | 2938 | 2938
2070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 3901 | 3901 | 3901
2070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 12330 | 12330 | 12330
2070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 658 | 658 | 658
2070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 54386 | 54386 | 54386
2070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 8079 | 8079 | 8079
2070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 4570 | 4570 | 4570
2070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 2600 | 2600 | 2600
2070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 4394 | 4394 | 4394
2070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 343 | 343 | 343
2070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 28136 | 28136 | 28136
2070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 2592 | 2592 | 2592
2070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 1780 | 1780 | 1780
2070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 617 | 617 | 617
2070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 96 | 96 | 96
2070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 202 | 202 | 202
2070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 59 | 59 | 59
2070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 286 | 286 | 286
2070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 6 | 6 | 6
2070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 61 | 61 | 61
2070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 14 | 14 | 14
2070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 41 | 41 | 41
2070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 69 | 69 | 69
2070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 14 | 14 | 14
2070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 49 | 49 | 49
2070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 23 | 23 | 23
2070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 22 | 22 | 22
2070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 5 | 5 | 5
2070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 19 | 19 | 19
2070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 22 | 22 | 22
2070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 35 | 35 | 35
2070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 73 | 73 | 73
2070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 187 | 187 | 187
2070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 8 | 8 | 8
2070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 70 | 70 | 70
2070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 9 | 9 | 9
2070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 7 | 7 | 7
2070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 189 | 189 | 189
2070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 381 | 381 | 381
2070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 34 | 34 | 34
2070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 240 | 240 | 240
2070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 9 | 9 | 9
2070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 5 | 5 | 5
2070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 106 | 106 | 106
2070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 158 | 158 | 158
2070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 15 | 15 | 15
2070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | For Projected data, PG&E used Q4 2024 metrics and projecting it to be flat delta |  | PG&E | 2026 | 2026 | 37 | 37 | 37

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -1.4 | -1.2 | -1.6
2080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -34.5 | -29.4 | -38.3
2080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -15.7 | -12.6 | -16.4
2080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -3.1 | -2.6 | -3.4
2080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -18.5 | -15.7 | -20.5
2080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -0.8 | -0.7 | -0.9
2080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -152.6 | -130.1 | -169.5
2080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -40.5 | -33.4 | -43.5
2080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -13.6 | -11.6 | -15.1
2080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | The projected net change in overhead circuit miles is based on the target undergrounding circuit miles to be installed according to the 2026-2028 WMP initiative GH-04, and the target line removal circuit miles to be removed per WMP initiative GH-12. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | -11.2 | -8.2 | -10.6
2080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 1.8 | 1.5 | 2
2080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 43.1 | 36.8 | 47.9
2080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 18.5 | 15.7 | 20.5
2080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 3.9 | 3.3 | 4.3
2080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 23.1 | 19.7 | 25.6
2080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 1.1 | 0.9 | 1.2
2080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 190.7 | 162.7 | 211.9
2080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 48.9 | 41.7 | 54.3
2080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 17 | 14.5 | 18.9
2080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 8 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 12 | 10.2 | 13.3
2080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | There are no 2026 - 2028 WMP commitments related to this metric. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | Substation net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | Weather Stations net addition or removal is subject to funding and strategic planning and cannot be projected at this time. |  | PG&E | 2026 | 2026 | 0 | 0 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. Planned miles for 2027-2028 are currently forecasted at the circuit segment level and have not yet been divided into subprojects. The forecasts in Table 9 for 2027-2028 are based on the proportions of the 2026 HFTD tier, area type, and WUI status using the annual 2027-2028 WMP targets. Once subprojects are scoped, the forecasts for 2027 and 2028 can be recalculated. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 3.5 | 2.6 | 3.1
2090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 99.1 | 74.8 | 88.8
2090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 107.1 | 80.9 | 96.1
2090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 11.1 | 8.4 | 10
2090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 52.7 | 39.8 | 47.3
2090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 2.4 | 1.8 | 2.1
2090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 251.6 | 190 | 225.6
2090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 69.3 | 52.3 | 62.1
2090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 36.7 | 27.7 | 32.9
2090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | PG&E is using GH-04 and GH-12 targeted miles to determine the number of overhead circuit miles upgraded. 2027 - 2028 planned miles are currently forecasted at the circuit segment level and not yet into subprojects. 2027-2028 Table 7 forecasts are based on the 2026 HFTD tier, area type, and WUI status proportions and 2027 and 2028 mileage targets that will be filed in the 2026-2028 WMP. Once subprojects are scoped, forecasts can be recalculated for 2027 and 2028. |  | PG&E | 2026 | 2026 | 24.6 | 18.6 | 22.1
2090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission line. | PG&E | 2026 | 2026
2090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | Substation upgrade projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future updates. |  | PG&E | 2026 | 2026 | 0 | 0 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | All (regardless of WWS) | Number of events | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. This is based on the Q4 2024 QDR 2025 Projected Value. |  | PG&E | 2026 | 2026 | 4 | 4 | 4
2100000001 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | All (regardless of WWS) | Circuit-events, measured in number of events multiplied by number of circuits de-energized | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. This is based on the Q4 2024 QDR 2025 Projected Value. |  | PG&E | 2026 | 2026 | 459 | 459 | 459
2100000002 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | All (regardless of WWS) | Customer hours | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. This is based on the Q4 2024 QDR 2025 Projected Value. |  | PG&E | 2026 | 2026 | 12012165 | 12012165 | 12012165
2100000003 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | All (regardless of WWS) | Number of events | These forecasts are based on an estimated annual decrease of 2%. |  | PG&E | 2026 | 2026 | 2205 | 2161 | 2118
2100000004 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | All (regardless of WWS) | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; The forecasts are based on a 3-year historical average (2022-2024). |  | PG&E | 2026 | 2026 | 5813549.82 | 5813549.82 | 5813549.82
2100000005 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | PG&E | 2026 | 2026 | 4883085.1223 | 4883085.1223 | 4883085.1223
2100000006 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | PG&E | 2026 | 2026 | 38355177.8668 | 38355177.8668 | 38355177.8668
2100000007 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | PG&E | 2026 | 2026 | 6167645.8332 | 6167645.8332 | 6167645.8332
2100000008 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | PG&E | 2026 | 2026 | 518.5667 | 518.5667 | 518.5667
2100000009 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | PG&E | 2026 | 2026 | 512.3 | 512.3 | 512.3
2100000010 | 3. Critical infrastructure impacted by PSPS | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PG&E | 2026 | 2026 | 2.093 | 2.093 | 2.093
2100000011 | 4. Community outreach of PSPS metrics | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PG&E | 2026 | 2026 | 2.0897 | 2.0897 | 2.0897
2100000012 | 4. Community outreach of PSPS metrics | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | PG&E | 2026 | 2026
2100000013 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. This is based on the Q4 2024 QDR 2025 Projected Value. |  | PG&E | 2026 | 2026 | 309138 | 309138 | 309138
2100000014 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2026
2100000015 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2026
2100000016 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2026
2100000017 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2026
2100000018 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2026
2100000019 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | PG&E | 2026 | 2026
2100000020 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | PG&E | 2026 | 2026
2100000021 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | PG&E | 2026 | 2026
2100000022 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | PG&E | 2026 | 2026
2100000023 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | PG&E | 2026 | 2026
2100000024 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PG&E | 2026 | 2026
2100000025 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PG&E | 2026 | 2026
2100000026 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | The forecasts are based on a 3-year historical average (2022-2024). |  | PG&E | 2026 | 2026 | 0.35 | 0.35 | 0.35
2100000027 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | The forecasts are based on a 3-year historical average (2022-2024). |  | PG&E | 2026 | 2026 | 0.73 | 0.73 | 0.73
2100000028 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | PG&E | 2026 | 2026

## Table 11
METRIC NUMBER | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY (IF BLANK THIS REFERS TO ALL ACTIVITIES UNDER THE INITIATIVE) | EXPENSE TYPE | HFTD TIER | UNIT(S) | UTILITY MITIGATION ACTIVITY TRACKING IDS | PRIMARY DRIVER TARGETED | SECONDARY DRIVERS TARGETED | YEAR INITIATED | MOST RECENT PROCEEDING | MEMORANDUM ACCOUNT | CURRENT COMPLIANCE STATUS | ASSOCIATED RULES | OTHER SPEND CATEGORY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | WMP CYCLE START YEAR | PROJECTED CYCLE YEAR 1 VALUE | PROJECTED CYCLE YEAR 2 VALUE | PROJECTED CYCLE YEAR 3 VALUE
2110000000 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | CAPEX | Territory | $ Thousands | 5 | Foundational | Foundational | 2019 | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 8329.6578 | 8392.9543 | 8488.8487
2110000001 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | CAPEX | HFTD | $ Thousands | 5 | Foundational | Foundational | 2019 | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 8329.6578 | 8392.9543 | 8488.8487
2110000002 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | OPEX | Territory | $ Thousands | 5 | Foundational | Foundational | 2019 | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 2501.07 | 2386.028 | 2367.866
2110000003 | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | OPEX | HFTD | $ Thousands | 5 | Foundational | Foundational | 2019 | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 691.8744 | 691.8744 | 691.8744
2110000004 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | CAPEX | Territory | $ Thousands | 6 | Foundational | All Drivers, All Consequences | n/a | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000005 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | CAPEX | HFTD | $ Thousands | 6 | Foundational | All Drivers, All Consequences | n/a | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000006 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | OPEX | Territory | $ Thousands | 6 | Foundational | All Drivers, All Consequences | n/a | 2023 GRC |  | In Compliance | n/a | Costs partially in Risk Methodology and Assessment |  | Costs partially in Risk Methodology and Assessment | PG&E | 2026 | 2026 | 13201.5926 | 13536.913 | 0
2110000007 | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | OPEX | HFTD | $ Thousands | 6 | Foundational | All Drivers, All Consequences | n/a | 2023 GRC |  | In Compliance | n/a | Costs partially in Risk Methodology and Assessment |  | Costs partially in Risk Methodology and Assessment | PG&E | 2026 | 2026 | 13201.5926 | 13536.913 | 0
2110000008 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | CAPEX | Territory | $ Thousands | 8.2.1; GH-12 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2018 | 2023 GRC |  | In Compliance | TD-9001M CH 15 "Fire Area Design Guidance" |  |  |  | PG&E | 2026 | 2026 | 284906.4599 | 197264.9474 | 197500.838
2110000009 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | CAPEX | HFTD | $ Thousands | 8.2.1; GH-12 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2018 | 2023 GRC |  | In Compliance | TD-9001M CH 15 "Fire Area Design Guidance" |  |  |  | PG&E | 2026 | 2026 | 284906.4598 | 197264.9474 | 197500.838
2110000010 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | OPEX | Territory | $ Thousands | 8.2.1 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2018 | 2023 GRC |  | In Compliance | TD-9001M CH 15 "Fire Area Design Guidance" |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000011 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation | OPEX | HFTD | $ Thousands | 8.2.1 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2018 | 2023 GRC |  | In Compliance | TD-9001M CH 15 "Fire Area Design Guidance" |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000012 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | CAPEX | Territory | $ Thousands | 8.2.2; GH-04 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC |  | In Compliance | UG Design and Construction Standards |  |  |  | PG&E | 2026 | 2026 | 1116073.7027 | 1021123.7039 | 1191464.1884
2110000013 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | CAPEX | HFTD | $ Thousands | 8.2.2; GH-04 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC |  | In Compliance | UG Design and Construction Standards |  |  |  | PG&E | 2026 | 2026 | 1116073.7027 | 1021123.7039 | 1191464.1884
2110000014 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | OPEX | Territory | $ Thousands | 8.2.2 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC |  | In Compliance | UG Design and Construction Standards |  |  |  | PG&E | 2026 | 2026 | 875.4529 | 580 | 562
2110000015 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment | OPEX | HFTD | $ Thousands | 8.2.2 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC |  | In Compliance | UG Design and Construction Standards |  |  |  | PG&E | 2026 | 2026 | 875.4529 | 400 | 400
2110000016 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | CAPEX | Territory | $ Thousands | 8.2.3 | Equipment / facility failure |  | <2018 | 2023 GRC |  | Not in Compliance | GO 95 Rule 18 |  |  |  | PG&E | 2026 | 2026 | 441458.695 | 615919.527 | 609209.374
2110000017 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | CAPEX | HFTD | $ Thousands | 8.2.3 | Equipment / facility failure |  | <2018 | 2023 GRC |  | Not in Compliance | GO 95 Rule 18 |  |  |  | PG&E | 2026 | 2026 | 316974.664 | 320393.621 | 319805.196
2110000018 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | OPEX | Territory | $ Thousands | 8.2.3 | Equipment / facility failure |  | <2018 | 2023 GRC |  | Not in Compliance | GO 95 Rule 18 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000019 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution pole replacements and reinforcements | OPEX | HFTD | $ Thousands | 8.2.3 | Equipment / facility failure |  | <2018 | 2023 GRC |  | Not in Compliance | GO 95 Rule 18 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000020 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | CAPEX | Territory | $ Thousands | 8.2.4 | Equipment / facility failure |  | <2018 | TO Rate Case |  |  | GO 95 Rule 18 |  |  |  | PG&E | 2026 | 2026 | 211229.76 | 220749.942 | 207431.105
2110000021 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | CAPEX | HFTD | $ Thousands | 8.2.4 | Equipment / facility failure |  | <2018 | TO Rate Case |  |  | GO 95 Rule 18 |  |  |  | PG&E | 2026 | 2026 | 102330.485 | 89094.16 | 70289.45
2110000022 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | OPEX | Territory | $ Thousands | 8.2.4 | Equipment / facility failure |  | <2018 | TO Rate Case |  |  | GO 95 Rule 18 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000023 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission pole/tower replacements and reinforcements | OPEX | HFTD | $ Thousands | 8.2.4 | Equipment / facility failure |  | <2018 | TO Rate Case |  |  | GO 95 Rule 18 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000024 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | CAPEX | Territory | $ Thousands | 8.2.5; GH-06; GH-11 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution: refer to Maintenance program in 8.4; Transmission: <2018 | 2023 GRC; TO Rate Case |  |  | Distribution - refer to Maintenance program in 8.4; Transmission - n/a |  |  |  | PG&E | 2026 | 2026 | 41819.237 | 32795.8456 | 27694.202
2110000025 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | CAPEX | HFTD | $ Thousands | 8.2.5; GH-06; GH-11 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution: refer to Maintenance program in 8.4; Transmission: <2018 | 2023 GRC; TO Rate Case |  |  | Distribution - refer to Maintenance program in 8.4; Transmission - n/a |  |  |  | PG&E | 2026 | 2026 | 41819.237 | 32795.8456 | 27694.202
2110000026 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | OPEX | Territory | $ Thousands | 8.2.5 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution: refer to Maintenance program in 8.4; Transmission: <2018 | 2023 GRC; TO Rate Case |  |  | Distribution - refer to Maintenance program in 8.4; Transmission - n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000027 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening | OPEX | HFTD | $ Thousands | 8.2.5 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution: refer to Maintenance program in 8.4; Transmission: <2018 | 2023 GRC; TO Rate Case |  |  | Distribution - refer to Maintenance program in 8.4; Transmission - n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000028 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | CAPEX | Territory | $ Thousands | 8.2.6 | Equipment / facility failure |  | 2020 | 2023 GRC; TO Rate Case |  | Not in Compliance | Cal Fire Power Line Fire Prevention Field Guide; TD-9100P-09 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000029 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | CAPEX | HFTD | $ Thousands | 8.2.6 | Equipment / facility failure |  | 2020 | 2023 GRC; TO Rate Case |  | Not in Compliance | Cal Fire Power Line Fire Prevention Field Guide; TD-9100P-09 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000030 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | OPEX | Territory | $ Thousands | 8.2.6 | Equipment / facility failure |  | 2020 | 2023 GRC; TO Rate Case |  | Not in Compliance | Cal Fire Power Line Fire Prevention Field Guide; TD-9100P-09 |  |  |  | PG&E | 2026 | 2026 | 475.825 | 490.708 | 511.49
2110000031 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Emerging grid hardening technology installations and pilots | OPEX | HFTD | $ Thousands | 8.2.6 | Equipment / facility failure |  | 2020 | 2023 GRC; TO Rate Case |  | Not in Compliance | Cal Fire Power Line Fire Prevention Field Guide; TD-9100P-09 |  |  |  | PG&E | 2026 | 2026 | 400.825 | 415.708 | 436.49
2110000032 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | CAPEX | Territory | $ Thousands | 8.2.7; GH-14 | Consequence - PSPS |  | 2019 | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 2005.732 | 68 | 0
2110000033 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | CAPEX | HFTD | $ Thousands | 8.2.7; GH-14 | Consequence - PSPS |  | 2019 | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 2005.732 | 68 | 0
2110000034 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | OPEX | Territory | $ Thousands | 8.2.7; GH-14 | Consequence - PSPS |  | 2019 | 2023 GRC | Partially in WMPMA | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 16938.4711 | 15216.9522 | 14992.526
2110000035 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids | OPEX | HFTD | $ Thousands | 8.2.7; GH-14 | Consequence - PSPS |  | 2019 | 2023 GRC | Partially in WMPMA | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 16938.4711 | 15216.9522 | 14992.526
2110000036 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | CAPEX | Territory | $ Thousands | 8.2.8 | Foundational | Foundational | 2019 | n/a - no forecast |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000037 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | CAPEX | HFTD | $ Thousands | 8.2.8 | Foundational | Foundational | 2019 | n/a - no forecast |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000038 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | OPEX | Territory | $ Thousands | 8.2.8 | Foundational | Foundational | 2019 | n/a - no forecast |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000039 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment | OPEX | HFTD | $ Thousands | 8.2.8 | Foundational | Foundational | 2019 | n/a - no forecast |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000040 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | CAPEX | Territory | $ Thousands | 8.2.9 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution: 2019; Transmission: <2018 | 2023 GRC |  | In Compliance | TD-2495P-01 - Idle Facility Program; GO-95 Rule 31.6 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000041 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | CAPEX | HFTD | $ Thousands | 8.2.9 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution: 2019; Transmission: <2018 | 2023 GRC |  | In Compliance | TD-2495P-01 - Idle Facility Program; GO-95 Rule 31.6 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000042 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | OPEX | Territory | $ Thousands | 8.2.9 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution: 2019; Transmission: <2018 | 2023 GRC |  | In Compliance | TD-2495P-01 - Idle Facility Program; GO-95 Rule 31.6 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000043 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line removals (in HFTD) | OPEX | HFTD | $ Thousands | 8.2.9 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution: 2019; Transmission: <2018 | 2023 GRC |  | In Compliance | TD-2495P-01 - Idle Facility Program; GO-95 Rule 31.6 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000044 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | CAPEX | Territory | $ Thousands | 8.2.10; GM-14 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC |  | Not in Compliance | Cal Fire Power Line Fire Prevention Field Guide; TD-9100P-09 |  |  |  | PG&E | 2026 | 2026 | 11106.44 | 17753.439 | 18402.432
2110000045 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | CAPEX | HFTD | $ Thousands | 8.2.10; GM-14 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC |  | Not in Compliance | Cal Fire Power Line Fire Prevention Field Guide; TD-9100P-09 |  |  |  | PG&E | 2026 | 2026 | 10706.44 | 17753.439 | 18402.432
2110000046 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | OPEX | Territory | $ Thousands | 8.2.10 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC |  | Not in Compliance | Cal Fire Power Line Fire Prevention Field Guide; TD-9100P-09 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000047 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions | OPEX | HFTD | $ Thousands | 8.2.10 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC |  | Not in Compliance | Cal Fire Power Line Fire Prevention Field Guide; TD-9100P-09 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000048 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | CAPEX | Territory | $ Thousands | 8.2.11 | Consequence - PSPS |  | Distribution: 2019; Transmission: 2019/2020 | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000049 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | CAPEX | HFTD | $ Thousands | 8.2.11 | Consequence - PSPS |  | Distribution: 2019; Transmission: 2019/2020 | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000050 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | OPEX | Territory | $ Thousands | 8.2.11 | Consequence - PSPS |  | Distribution: 2019; Transmission: 2019/2020 | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000051 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events | OPEX | HFTD | $ Thousands | 8.2.11 | Consequence - PSPS |  | Distribution: 2019; Transmission: 2019/2020 | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000052 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | CAPEX | Territory | $ Thousands | 8.2.12 | Contact from object |  | Pertaining to Substation Animal Abatement: 2019 - Wildfire Safety Plan | 2023 GRC |  | Exceeding Compliance | Pertaining to Substation Animal Abatement: GO 174 |  |  |  | PG&E | 2026 | 2026 | 4938.4698 | 5941.5705 | 6059.3417
2110000053 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | CAPEX | HFTD | $ Thousands | 8.2.12 | Contact from object |  | Pertaining to Substation Animal Abatement: 2019 - Wildfire Safety Plan | 2023 GRC |  | Exceeding Compliance | Pertaining to Substation Animal Abatement: GO 174 |  |  |  | PG&E | 2026 | 2026 | 1841.621 | 1847.682 | 1917.674
2110000054 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | OPEX | Territory | $ Thousands | 8.2.12 | Contact from object |  | Pertaining to Substation Animal Abatement: 2019 - Wildfire Safety Plan | 2023 GRC |  | Exceeding Compliance | Pertaining to Substation Animal Abatement: GO 174 |  |  |  | PG&E | 2026 | 2026 | 5312.222 | 17255.6958 | 18092.6986
2110000055 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other technologies and systems not listed above | OPEX | HFTD | $ Thousands | 8.2.12 | Contact from object |  | Pertaining to Substation Animal Abatement: 2019 - Wildfire Safety Plan | 2023 GRC |  | Exceeding Compliance | Pertaining to Substation Animal Abatement: GO 174 |  |  |  | PG&E | 2026 | 2026 | 1188.3782 | 1118.6368 | 1122.9928
2110000056 | Grid Design, Operations, and Maintenance | Asset Inspections |  | CAPEX | Territory | $ Thousands | 8.3 | Equipment / facility failure |  | Distribution: 2016 (focused on WMP work); Transmission: 2019 (when WSIP program started in full); Substation: 2019 Wildfire Safety Plan | 2023 GRC; TO Rate Case |  | Exceeding Compliance | GO 95; GO 165; GO 165 IV; GO 95; Rule 18B; Rule 31.2; GO 174 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000057 | Grid Design, Operations, and Maintenance | Asset Inspections |  | CAPEX | HFTD | $ Thousands | 8.3 | Equipment / facility failure |  | Distribution: 2016 (focused on WMP work); Transmission: 2019 (when WSIP program started in full); Substation: 2019 Wildfire Safety Plan | 2023 GRC; TO Rate Case |  | Exceeding Compliance | GO 95; GO 165; GO 165 IV; GO 95; Rule 18B; Rule 31.2; GO 174 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000058 | Grid Design, Operations, and Maintenance | Asset Inspections |  | OPEX | Territory | $ Thousands | 8.3; AI-04; AI-06; AI-07A; AI-07D | Equipment / facility failure |  | Distribution: 2016 (focused on WMP work); Transmission: 2019 (when WSIP program started in full); Substation: 2019 Wildfire Safety Plan | 2023 GRC; TO Rate Case |  | Exceeding Compliance | GO 95; GO 165; GO 165 IV; GO 95; Rule 18B; Rule 31.2; GO 174 |  |  |  | PG&E | 2026 | 2026 | 137729.0833 | 151310.956 | 149584.8981
2110000059 | Grid Design, Operations, and Maintenance | Asset Inspections |  | OPEX | HFTD | $ Thousands | 8.3; AI-04; AI-06; AI-07A; AI-07D | Equipment / facility failure |  | Distribution: 2016 (focused on WMP work); Transmission: 2019 (when WSIP program started in full); Substation: 2019 Wildfire Safety Plan | 2023 GRC; TO Rate Case |  | Exceeding Compliance | GO 95; GO 165; GO 165 IV; GO 95; Rule 18B; Rule 31.2; GO 174 |  |  |  | PG&E | 2026 | 2026 | 101340.5541 | 113482.7327 | 112452.538
2110000060 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | CAPEX | Territory | $ Thousands | 8.4; GM-03 | Equipment / facility failure |  | Distribution: <2018; Transmission: <2018; Substation: Circuit breaker maintenance and installation initiative was introduced in the 2020 WMP. | 2023 GRC; TO Rate Case | Partially in WMPMA | Not in Compliance | GO 95 Rule 18; CPUC General Order 174; WECC-FAC-501 |  |  |  | PG&E | 2026 | 2026 | 977218.906 | 1903709.5373 | 2278746.7815
2110000061 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | CAPEX | HFTD | $ Thousands | 8.4; GM-03 | Equipment / facility failure |  | Distribution: <2018; Transmission: <2018; Substation: Circuit breaker maintenance and installation initiative was introduced in the 2020 WMP. | 2023 GRC; TO Rate Case | Partially in WMPMA | Not in Compliance | GO 95 Rule 18; CPUC General Order 174; WECC-FAC-501 |  |  |  | PG&E | 2026 | 2026 | 415101.858 | 1022307.605 | 1032792.188
2110000062 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | OPEX | Territory | $ Thousands | 8.4; GM-03 | Equipment / facility failure |  | Distribution: <2018; Transmission: <2018; Substation: Circuit breaker maintenance and installation initiative was introduced in the 2020 WMP. | 2023 GRC; TO Rate Case | Partially in WMPMA | Not in Compliance | GO 95 Rule 18; CPUC General Order 174; WECC-FAC-501 |  |  |  | PG&E | 2026 | 2026 | 269061.2922 | 278134.5124 | 304433.9583
2110000063 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | OPEX | HFTD | $ Thousands | 8.4; GM-03 | Equipment / facility failure |  | Distribution: <2018; Transmission: <2018; Substation: Circuit breaker maintenance and installation initiative was introduced in the 2020 WMP. | 2023 GRC; TO Rate Case | Partially in WMPMA | Not in Compliance | GO 95 Rule 18; CPUC General Order 174; WECC-FAC-501 |  |  |  | PG&E | 2026 | 2026 | 188802.8747 | 186285.8989 | 182207.1897
2110000064 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | CAPEX | Territory | $ Thousands | 8.5 | Foundational | Foundational | 2020 | 2023 GRC; TO Rate Case |  | In Compliance | GO 95; GO 128; GO 165 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000065 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | CAPEX | HFTD | $ Thousands | 8.5 | Foundational | Foundational | 2020 | 2023 GRC; TO Rate Case |  | In Compliance | GO 95; GO 128; GO 165 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000066 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | OPEX | Territory | $ Thousands | 8.5; GM-01D; GM-09D; GM-10D; GM-11D; GM-12; GM-13 | Foundational | Foundational | 2020 | 2023 GRC; TO Rate Case |  | In Compliance | GO 95; GO 128; GO 165 |  |  |  | PG&E | 2026 | 2026 | 35727.9951 | 35521.1285 | 35343.8985
2110000067 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | OPEX | HFTD | $ Thousands | 8.5; GM-01D; GM-09D; GM-10D; GM-11D; GM-12; GM-13 | Foundational | Foundational | 2020 | 2023 GRC; TO Rate Case |  | In Compliance | GO 95; GO 128; GO 165 |  |  |  | PG&E | 2026 | 2026 | 22108.621 | 22036.1125 | 21965.0541
2110000068 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | CAPEX | Territory | $ Thousands | 8.6 | Equipment / facility failure |  | Distribution: <2018; Transmission: <2018; Substation: Circuit breaker maintenance and installation initiative was introduced in the 2020 WMP. | n/a - no forecast |  |  | refer to 8.4 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000069 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | CAPEX | HFTD | $ Thousands | 8.6 | Equipment / facility failure |  | Distribution: <2018; Transmission: <2018; Substation: Circuit breaker maintenance and installation initiative was introduced in the 2020 WMP. | n/a - no forecast |  |  | refer to 8.4 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000070 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | OPEX | Territory | $ Thousands | 8.6 | Equipment / facility failure |  | Distribution: <2018; Transmission: <2018; Substation: Circuit breaker maintenance and installation initiative was introduced in the 2020 WMP. | n/a - no forecast |  |  | refer to 8.4 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000071 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | OPEX | HFTD | $ Thousands | 8.6 | Equipment / facility failure |  | Distribution: <2018; Transmission: <2018; Substation: Circuit breaker maintenance and installation initiative was introduced in the 2020 WMP. | n/a - no forecast |  |  | refer to 8.4 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000072 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | CAPEX | Territory | $ Thousands | 8.7.1 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC; TO Rate Case |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 61682.8839 | 67925.3762 | 66289.5498
2110000073 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | CAPEX | HFTD | $ Thousands | 8.7.1 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC; TO Rate Case |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 45382.8839 | 46425.3762 | 44789.5498
2110000074 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | OPEX | Territory | $ Thousands | 8.7.1; GM-07 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC; TO Rate Case |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 61638.1153 | 58402.1752 | 58098.6339
2110000075 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk | OPEX | HFTD | $ Thousands | 8.7.1; GM-07 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC; TO Rate Case |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 61558.4703 | 58331.4122 | 58029.2019
2110000076 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | CAPEX | Territory | $ Thousands | 8.7.2 | Foundational | Foundational | n/a - refer to other sections (8.7.1 - EPSS, for example) | n/a - no forecast |  |  | n/a - refer to other sections (8.7.1 - EPSS, for example) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000077 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | CAPEX | HFTD | $ Thousands | 8.7.2 | Foundational | Foundational | n/a - refer to other sections (8.7.1 - EPSS, for example) | n/a - no forecast |  |  | n/a - refer to other sections (8.7.1 - EPSS, for example) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000078 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | OPEX | Territory | $ Thousands | 8.7.2 | Foundational | Foundational | n/a - refer to other sections (8.7.1 - EPSS, for example) | n/a - no forecast |  |  | n/a - refer to other sections (8.7.1 - EPSS, for example) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000079 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications | OPEX | HFTD | $ Thousands | 8.7.2 | Foundational | Foundational | n/a - refer to other sections (8.7.1 - EPSS, for example) | n/a - no forecast |  |  | n/a - refer to other sections (8.7.1 - EPSS, for example) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000080 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | CAPEX | Territory | $ Thousands | 8.7.3 | Foundational | Foundational | <2018 | 2023 GRC |  | In Compliance | 2021 California Code Public Resources Code - PRC, sections 4427, 4428, 4431 |  |  |  | PG&E | 2026 | 2026 | 2278.939 | 4276.675 | 4303.064
2110000081 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | CAPEX | HFTD | $ Thousands | 8.7.3 | Foundational | Foundational | <2018 | 2023 GRC |  | In Compliance | 2021 California Code Public Resources Code - PRC, sections 4427, 4428, 4431 |  |  |  | PG&E | 2026 | 2026 | 1060.9767 | 3059.9226 | 3066.7837
2110000082 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | OPEX | Territory | $ Thousands | 8.7.3 | Foundational | Foundational | <2018 | 2023 GRC |  | In Compliance | 2021 California Code Public Resources Code - PRC, sections 4427, 4428, 4431 |  |  |  | PG&E | 2026 | 2026 | 37590.2246 | 53867.371 | 53900.9847
2110000083 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | OPEX | HFTD | $ Thousands | 8.7.3 | Foundational | Foundational | <2018 | 2023 GRC |  | In Compliance | 2021 California Code Public Resources Code - PRC, sections 4427, 4428, 4431 |  |  |  | PG&E | 2026 | 2026 | 36858.7905 | 50181.3444 | 50153.4944
2110000084 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | CAPEX | Territory | $ Thousands |  | Foundational | Foundational |  | n/a - no forecast | [6 empty] | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000085 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | CAPEX | HFTD | $ Thousands |  | Foundational | Foundational |  | n/a - no forecast | [6 empty] | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000086 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | OPEX | Territory | $ Thousands |  | Foundational | Foundational |  | n/a - no forecast | [6 empty] | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000087 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Other Grid Operations and Procedures not listed above | OPEX | HFTD | $ Thousands |  | Foundational | Foundational |  | n/a - no forecast | [6 empty] | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000088 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | CAPEX | Territory | $ Thousands | 8.8 | Foundational | Foundational | <2018 | n/a - no forecast |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000089 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | CAPEX | HFTD | $ Thousands | 8.8 | Foundational | Foundational | <2018 | n/a - no forecast |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000090 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | OPEX | Territory | $ Thousands | 8.8; GM-15 | Foundational | Foundational | <2018 | n/a - no forecast |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000091 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) |  | OPEX | HFTD | $ Thousands | 8.8; GM-15 | Foundational | Foundational | <2018 | n/a - no forecast |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000092 | Vegetation Management and Inspections | Vegetation Management Inspections |  | CAPEX | Territory | $ Thousands | 9.2 | Vegetation Contact |  | Non-Substation: <2018. Substation: 2019 Wildfire Safety Plan | 2023 GRC; TO Rate Case |  | In Compliance | GO Rule 95; PRC 4292; PRC 4293; Distribution Routine Patrol Procedure (TD-7102P-01); Distribution Vegetation Management Standard (DVMS) (TD-7102S); ESRB-4; GO 95 Rule 18; Vegetation Management Second Patrol Procedure (TD-7102P-23); GO 174 (Substation); NERC Standard FAC-003-04; GO 95 Rule 35; Transmission Non-Orchard Routine Patrol Procedure (TD-7103P-01) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000093 | Vegetation Management and Inspections | Vegetation Management Inspections |  | CAPEX | HFTD | $ Thousands | 9.2 | Vegetation Contact |  | Non-Substation: <2018. Substation: 2019 Wildfire Safety Plan | 2023 GRC; TO Rate Case |  | In Compliance | GO Rule 95; PRC 4292; PRC 4293; Distribution Routine Patrol Procedure (TD-7102P-01); Distribution Vegetation Management Standard (DVMS) (TD-7102S); ESRB-4; GO 95 Rule 18; Vegetation Management Second Patrol Procedure (TD-7102P-23); GO 174 (Substation); NERC Standard FAC-003-04; GO 95 Rule 35; Transmission Non-Orchard Routine Patrol Procedure (TD-7103P-01) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000094 | Vegetation Management and Inspections | Vegetation Management Inspections |  | OPEX | Territory | $ Thousands | 9.2; VM-13; VM-14; VM-16; VM-17; VM-26 | Vegetation Contact |  | Non-Substation: <2018. Substation: 2019 Wildfire Safety Plan | 2023 GRC; TO Rate Case |  | In Compliance | GO Rule 95; PRC 4292; PRC 4293; Distribution Routine Patrol Procedure (TD-7102P-01); Distribution Vegetation Management Standard (DVMS) (TD-7102S); ESRB-4; GO 95 Rule 18; Vegetation Management Second Patrol Procedure (TD-7102P-23); GO 174 (Substation); NERC Standard FAC-003-04; GO 95 Rule 35; Transmission Non-Orchard Routine Patrol Procedure (TD-7103P-01) |  |  |  | PG&E | 2026 | 2026 | 211742.857 | 169322.0113 | 167881.1775
2110000095 | Vegetation Management and Inspections | Vegetation Management Inspections |  | OPEX | HFTD | $ Thousands | 9.2; VM-13; VM-14; VM-16; VM-17; VM-26 | Vegetation Contact |  | Non-Substation: <2018. Substation: 2019 Wildfire Safety Plan | 2023 GRC; TO Rate Case |  | In Compliance | GO Rule 95; PRC 4292; PRC 4293; Distribution Routine Patrol Procedure (TD-7102P-01); Distribution Vegetation Management Standard (DVMS) (TD-7102S); ESRB-4; GO 95 Rule 18; Vegetation Management Second Patrol Procedure (TD-7102P-23); GO 174 (Substation); NERC Standard FAC-003-04; GO 95 Rule 35; Transmission Non-Orchard Routine Patrol Procedure (TD-7103P-01) |  |  |  | PG&E | 2026 | 2026 | 92365.6878 | 67313.0207 | 66819.1646
2110000096 | Vegetation Management and Inspections | Pruning and Removal |  | CAPEX | Territory | $ Thousands | 9.3 | Vegetation Contact |  | <2018 | 2023 GRC; TO Rate Case |  | In Compliance | Distribution Vegetation Management Program (TD-7102S); Vegetation Management Distribution Inspection Procedure (TD-7102P-01); Vegetation Management Transmission Program (TD-7103S); Vegetation Management Transmission Inspection (TD-7103P-01); Transmission Vegetation Management Imminent Threat and Hazard Notification (TD-7103P-09); Vegetation Management Priority Tag (TD-7102P-17) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000097 | Vegetation Management and Inspections | Pruning and Removal |  | CAPEX | HFTD | $ Thousands | 9.3 | Vegetation Contact |  | <2018 | 2023 GRC; TO Rate Case |  | In Compliance | Distribution Vegetation Management Program (TD-7102S); Vegetation Management Distribution Inspection Procedure (TD-7102P-01); Vegetation Management Transmission Program (TD-7103S); Vegetation Management Transmission Inspection (TD-7103P-01); Transmission Vegetation Management Imminent Threat and Hazard Notification (TD-7103P-09); Vegetation Management Priority Tag (TD-7102P-17) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000098 | Vegetation Management and Inspections | Pruning and Removal |  | OPEX | Territory | $ Thousands | 9.3 | Vegetation Contact |  | <2018 | 2023 GRC; TO Rate Case | Partially in FRMMA | In Compliance | Distribution Vegetation Management Program (TD-7102S); Vegetation Management Distribution Inspection Procedure (TD-7102P-01); Vegetation Management Transmission Program (TD-7103S); Vegetation Management Transmission Inspection (TD-7103P-01); Transmission Vegetation Management Imminent Threat and Hazard Notification (TD-7103P-09); Vegetation Management Priority Tag (TD-7102P-17) |  |  |  | PG&E | 2026 | 2026 | 940420.1695 | 817620.6625 | 807174.7594
2110000099 | Vegetation Management and Inspections | Pruning and Removal |  | OPEX | HFTD | $ Thousands | 9.3 | Vegetation Contact |  | <2018 | 2023 GRC; TO Rate Case | Partially in FRMMA | In Compliance | Distribution Vegetation Management Program (TD-7102S); Vegetation Management Distribution Inspection Procedure (TD-7102P-01); Vegetation Management Transmission Program (TD-7103S); Vegetation Management Transmission Inspection (TD-7103P-01); Transmission Vegetation Management Imminent Threat and Hazard Notification (TD-7103P-09); Vegetation Management Priority Tag (TD-7102P-17) |  |  |  | PG&E | 2026 | 2026 | 470905.8209 | 391241.7051 | 388897.8452
2110000100 | Vegetation Management and Inspections | Pole Clearing |  | CAPEX | Territory | $ Thousands | 9.4 | Vegetation Contact |  | <2018 | 2023 GRC |  | In Compliance | PRC 4292; Vegetation Control Program Standard (TD-7112S); Vegetation Control Procedure (TD-7112P-01); Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000101 | Vegetation Management and Inspections | Pole Clearing |  | CAPEX | HFTD | $ Thousands | 9.4 | Vegetation Contact |  | <2018 | 2023 GRC |  | In Compliance | PRC 4292; Vegetation Control Program Standard (TD-7112S); Vegetation Control Procedure (TD-7112P-01); Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000102 | Vegetation Management and Inspections | Pole Clearing |  | OPEX | Territory | $ Thousands | 9.4; VM-02C; VM-02R | Vegetation Contact |  | <2018 | 2023 GRC |  | In Compliance | PRC 4292; Vegetation Control Program Standard (TD-7112S); Vegetation Control Procedure (TD-7112P-01); Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  |  | PG&E | 2026 | 2026 | 17707.5497 | 23251.5497 | 23251.5497
2110000103 | Vegetation Management and Inspections | Pole Clearing |  | OPEX | HFTD | $ Thousands | 9.4; VM-02C; VM-02R | Vegetation Contact |  | <2018 | 2023 GRC |  | In Compliance | PRC 4292; Vegetation Control Program Standard (TD-7112S); Vegetation Control Procedure (TD-7112P-01); Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  |  | PG&E | 2026 | 2026 | 17707.5497 | 23251.5497 | 23251.5497
2110000104 | Vegetation Management and Inspections | Wood and Slash Management |  | CAPEX | Territory | $ Thousands | 9.5 | Vegetation Contact |  | <2018 | 2023 GRC |  | In Compliance | TD-7116S Vegetation Management Wood Management Program; TD-7116P-01 Vegetation Management Wood Management Inspection and Prescription |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000105 | Vegetation Management and Inspections | Wood and Slash Management |  | CAPEX | HFTD | $ Thousands | 9.5 | Vegetation Contact |  | <2018 | 2023 GRC |  | In Compliance | TD-7116S Vegetation Management Wood Management Program; TD-7116P-01 Vegetation Management Wood Management Inspection and Prescription |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000106 | Vegetation Management and Inspections | Wood and Slash Management |  | OPEX | Territory | $ Thousands | 9.5; VM-23 | Vegetation Contact |  | <2018 | 2023 GRC |  | In Compliance | TD-7116S Vegetation Management Wood Management Program; TD-7116P-01 Vegetation Management Wood Management Inspection and Prescription |  |  |  | PG&E | 2026 | 2026 | 69715.4317 | 63128.6493 | 62848.9749
2110000107 | Vegetation Management and Inspections | Wood and Slash Management |  | OPEX | HFTD | $ Thousands | 9.5; VM-23 | Vegetation Contact |  | <2018 | 2023 GRC |  | In Compliance | TD-7116S Vegetation Management Wood Management Program; TD-7116P-01 Vegetation Management Wood Management Inspection and Prescription |  |  |  | PG&E | 2026 | 2026 | 69082.538 | 62440.5355 | 62171.0285
2110000108 | Vegetation Management and Inspections | Defensible Space |  | CAPEX | Territory | $ Thousands | 9.6 | Vegetation Contact |  | 2019 | 2023 GRC |  | In Compliance | Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000109 | Vegetation Management and Inspections | Defensible Space |  | CAPEX | HFTD | $ Thousands | 9.6 | Vegetation Contact |  | 2019 | 2023 GRC |  | In Compliance | Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000110 | Vegetation Management and Inspections | Defensible Space |  | OPEX | Territory | $ Thousands | 9.6; VM-05; VM-06; VM-07 | Vegetation Contact |  | 2019 | 2023 GRC | Partially in WMPMA | In Compliance | Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  |  | PG&E | 2026 | 2026 | 19428.8927 | 18355.4406 | 17830.4175
2110000111 | Vegetation Management and Inspections | Defensible Space |  | OPEX | HFTD | $ Thousands | 9.6; VM-05; VM-06; VM-07 | Vegetation Contact |  | 2019 | 2023 GRC | Partially in WMPMA | In Compliance | Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  |  | PG&E | 2026 | 2026 | 9162.5158 | 7711.4309 | 7670.9924
2110000112 | Vegetation Management and Inspections | Integrated Vegetation Management |  | CAPEX | Territory | $ Thousands | 9.7 | Vegetation Contact |  | 2023 | 2023 GRC; TO Rate Case |  | In Compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO);ANSI A300 (Part 7)-2018 Integrated Vegetation Management |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000113 | Vegetation Management and Inspections | Integrated Vegetation Management |  | CAPEX | HFTD | $ Thousands | 9.7 | Vegetation Contact |  | 2023 | 2023 GRC; TO Rate Case |  | In Compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO);ANSI A300 (Part 7)-2018 Integrated Vegetation Management |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000114 | Vegetation Management and Inspections | Integrated Vegetation Management |  | OPEX | Territory | $ Thousands | 9.7; VM-25 | Vegetation Contact |  | 2023 | 2023 GRC; TO Rate Case |  | In Compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO);ANSI A300 (Part 7)-2018 Integrated Vegetation Management |  |  |  | PG&E | 2026 | 2026 | 16745.497 | 16851.364 | 16831.872
2110000115 | Vegetation Management and Inspections | Integrated Vegetation Management |  | OPEX | HFTD | $ Thousands | 9.7; VM-25 | Vegetation Contact |  | 2023 | 2023 GRC; TO Rate Case |  | In Compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO);ANSI A300 (Part 7)-2018 Integrated Vegetation Management |  |  |  | PG&E | 2026 | 2026 | 7621.6694 | 7672.4856 | 7663.1294
2110000116 | Vegetation Management and Inspections | Partnerships |  | CAPEX | Territory | $ Thousands | 9.8 | Foundational | Foundational | <2018 | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000117 | Vegetation Management and Inspections | Partnerships |  | CAPEX | HFTD | $ Thousands | 9.8 | Foundational | Foundational | <2018 | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000118 | Vegetation Management and Inspections | Partnerships |  | OPEX | Territory | $ Thousands | 9.8 | Foundational | Foundational | <2018 | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 2755.0575 | 1945.9664 | 1945.9664
2110000119 | Vegetation Management and Inspections | Partnerships |  | OPEX | HFTD | $ Thousands | 9.8 | Foundational | Foundational | <2018 | 2023 GRC |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 1739.1646 | 1510.8278 | 1510.8278
2110000120 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | CAPEX | Territory | $ Thousands | 9.9 | Vegetation Contact |  | <2018 | n/a - no forecast |  | In Compliance | Vegetation Management Priority Tag Procedure (TD-7120P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000121 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | CAPEX | HFTD | $ Thousands | 9.9 | Vegetation Contact |  | <2018 | n/a - no forecast |  | In Compliance | Vegetation Management Priority Tag Procedure (TD-7120P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000122 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | OPEX | Territory | $ Thousands | 9.9 | Vegetation Contact |  | <2018 | n/a - no forecast |  | In Compliance | Vegetation Management Priority Tag Procedure (TD-7120P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000123 | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | OPEX | HFTD | $ Thousands | 9.9 | Vegetation Contact |  | <2018 | n/a - no forecast |  | In Compliance | Vegetation Management Priority Tag Procedure (TD-7120P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000124 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | CAPEX | Territory | $ Thousands | 9.10 | Vegetation Contact |  | <2018 | n/a - no forecast | CEMA | In Compliance | Vegetation Management Priority Tag Procedure (TD-7120P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000125 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | CAPEX | HFTD | $ Thousands | 9.10 | Vegetation Contact |  | <2018 | n/a - no forecast | CEMA | In Compliance | Vegetation Management Priority Tag Procedure (TD-7120P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000126 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | OPEX | Territory | $ Thousands | 9.10 | Vegetation Contact |  | <2018 | n/a - no forecast | CEMA | In Compliance | Vegetation Management Priority Tag Procedure (TD-7120P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000127 | Vegetation Management and Inspections | Post-Fire Service Restoration |  | OPEX | HFTD | $ Thousands | 9.10 | Vegetation Contact |  | <2018 | n/a - no forecast | CEMA | In Compliance | Vegetation Management Priority Tag Procedure (TD-7120P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000128 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | CAPEX | Territory | $ Thousands | 9.11 | Foundational | Foundational | <2018,2019,2021 | 2023 GRC; TO Rate Case |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000129 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | 9.11 | Foundational | Foundational | <2018,2019,2021 | 2023 GRC; TO Rate Case |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000130 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | OPEX | Territory | $ Thousands | 9.11; VM-08D; VM-08T; VM-22D; VM-22P; VM-22T | Foundational | Foundational | <2018,2019,2021 | 2023 GRC; TO Rate Case |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 99445.1674 | 59423.2939 | 58839.8265
2110000131 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | OPEX | HFTD | $ Thousands | 9.11; VM-08D; VM-08T; VM-22D; VM-22P; VM-22T | Foundational | Foundational | <2018,2019,2021 | 2023 GRC; TO Rate Case |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 93178.835 | 53842.017 | 53300.1164
2110000132 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | CAPEX | Territory | $ Thousands | 9.12 | Vegetation Contact |  | n/a | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000133 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | 9.12 | Vegetation Contact |  | n/a | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000134 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | OPEX | Territory | $ Thousands | 9.12 | Vegetation Contact |  | n/a | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000135 | Vegetation Management and Inspections | Work Orders (Vegetation Management) |  | OPEX | HFTD | $ Thousands | 9.12 | Vegetation Contact |  | n/a | n/a - no forecast |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000136 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | CAPEX | Territory | $ Thousands | 9.13 | Foundational | Foundational | n/a | 2023 GRC; TO Rate Case |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000137 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | CAPEX | HFTD | $ Thousands | 9.13 | Foundational | Foundational | n/a | 2023 GRC; TO Rate Case |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000138 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | OPEX | Territory | $ Thousands | 9.13; VM-24 | Foundational | Foundational | n/a | 2023 GRC; TO Rate Case |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 5846.7377 | 2777.45 | 2750.1064
2110000139 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) |  | OPEX | HFTD | $ Thousands | 9.13; VM-24 | Foundational | Foundational | n/a | 2023 GRC; TO Rate Case |  | In Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 1812.4887 | 861.0095 | 852.533
2110000140 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | CAPEX | Territory | $ Thousands | 10.2 | Foundational | Foundational | 2018 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 1205.033 | 1203.836 | 1223.156
2110000141 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | CAPEX | HFTD | $ Thousands | 10.2 | Foundational | Foundational | 2018 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 1205.033 | 1203.836 | 1223.156
2110000142 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | OPEX | Territory | $ Thousands | 10.2; SA-12; SA-13 | Foundational | Foundational | 2018 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 1104.4122 | 984.5127 | 965.5832
2110000143 | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | OPEX | HFTD | $ Thousands | 10.2; SA-12; SA-13 | Foundational | Foundational | 2018 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 1104.4122 | 984.5127 | 965.5832
2110000144 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | CAPEX | Territory | $ Thousands | 10.3; SA-02; SA-10; SA-11 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC |  |  | GO 95 |  |  |  | PG&E | 2026 | 2026 | 10845.746 | 54526.766 | 68710.83
2110000145 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | CAPEX | HFTD | $ Thousands | 10.3; SA-02; SA-10; SA-11 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC |  |  | GO 95 |  |  |  | PG&E | 2026 | 2026 | 10045.746 | 10035.766 | 10196.83
2110000146 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | OPEX | Territory | $ Thousands | 10.3; SA-14 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC |  |  | GO 95 |  |  |  | PG&E | 2026 | 2026 | 1925.988 | 8228 | 7458
2110000147 | Situational Awareness and Forecasting | Grid Monitoring Systems |  | OPEX | HFTD | $ Thousands | 10.3; SA-14 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC |  |  | GO 95 |  |  |  | PG&E | 2026 | 2026 | 1665.988 | 5700 | 5700
2110000148 | Situational Awareness and Forecasting | Ignition Detection Systems |  | CAPEX | Territory | $ Thousands | 10.4; SA-15 | Foundational | Foundational | 2017 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000149 | Situational Awareness and Forecasting | Ignition Detection Systems |  | CAPEX | HFTD | $ Thousands | 10.4; SA-15 | Foundational | Foundational | 2017 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000150 | Situational Awareness and Forecasting | Ignition Detection Systems |  | OPEX | Territory | $ Thousands | 10.4; SA-08; SA-15 | Foundational | Foundational | 2017 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 11635.211 | 11777.085 | 14246.886
2110000151 | Situational Awareness and Forecasting | Ignition Detection Systems |  | OPEX | HFTD | $ Thousands | 10.4; SA-08; SA-15 | Foundational | Foundational | 2017 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 11635.211 | 11527.425 | 13997.226
2110000152 | Situational Awareness and Forecasting | Weather Forecasting |  | CAPEX | Territory | $ Thousands | 10.5 | Foundational | Foundational | 2014 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 1492.968 | 1491.485 | 1515.422
2110000153 | Situational Awareness and Forecasting | Weather Forecasting |  | CAPEX | HFTD | $ Thousands | 10.5 | Foundational | Foundational | 2014 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 1492.968 | 1491.485 | 1515.422
2110000154 | Situational Awareness and Forecasting | Weather Forecasting |  | OPEX | Territory | $ Thousands | 10.5; SA-16; SA-17; SA-18; SA-19 | Foundational | Foundational | 2014 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 7457.9604 | 8456.8153 | 8745.9264
2110000155 | Situational Awareness and Forecasting | Weather Forecasting |  | OPEX | HFTD | $ Thousands | 10.5; SA-16; SA-17; SA-18; SA-19 | Foundational | Foundational | 2014 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 7457.9604 | 1027.405 | 1041.7272
2110000156 | Situational Awareness and Forecasting | Fire Potential Index |  | CAPEX | Territory | $ Thousands | 10.6 | Foundational | Foundational | 2015 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000157 | Situational Awareness and Forecasting | Fire Potential Index |  | CAPEX | HFTD | $ Thousands | 10.6 | Foundational | Foundational | 2015 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000158 | Situational Awareness and Forecasting | Fire Potential Index |  | OPEX | Territory | $ Thousands | 10.6 | Foundational | Foundational | 2015 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 7219.1154 | 7489.8834 | 7700.893
2110000159 | Situational Awareness and Forecasting | Fire Potential Index |  | OPEX | HFTD | $ Thousands | 10.6 | Foundational | Foundational | 2015 | 2023 GRC |  | Exceeding Compliance | n/a |  |  |  | PG&E | 2026 | 2026 | 7219.1154 | 7489.8834 | 7700.893
2110000160 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | CAPEX | Territory | $ Thousands | 11.2; EP-07 | All Consequences |  | <2018 | 2023 GRC |  | In Compliance | GO 166; R.96-11-004; R.18-12-005 |  |  |  | PG&E | 2026 | 2026 | 70.9004 | 70.83 | 71.9668
2110000161 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | CAPEX | HFTD | $ Thousands | 11.2; EP-07 | All Consequences |  | <2018 | 2023 GRC |  | In Compliance | GO 166; R.96-11-004; R.18-12-005 |  |  |  | PG&E | 2026 | 2026 | 17.0161 | 16.9992 | 17.272
2110000162 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | OPEX | Territory | $ Thousands | 11.2; EP-07 | All Consequences |  | <2018 | 2023 GRC |  | In Compliance | GO 166; R.96-11-004; R.18-12-005 |  |  |  | PG&E | 2026 | 2026 | 50974.8514 | 69013.0142 | 69218.6821
2110000163 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | OPEX | HFTD | $ Thousands | 11.2; EP-07 | All Consequences |  | <2018 | 2023 GRC |  | In Compliance | GO 166; R.96-11-004; R.18-12-005 |  |  |  | PG&E | 2026 | 2026 | 43216.0664 | 60113.9685 | 60174.9934
2110000164 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | CAPEX | Territory | $ Thousands | 11.3 | All Consequences |  | 2018 | 2023 GRC |  | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000165 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | CAPEX | HFTD | $ Thousands | 11.3 | All Consequences |  | 2018 | 2023 GRC |  | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 0 | 0 | 0
2110000166 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | OPEX | Territory | $ Thousands | 11.3 | All Consequences |  | 2018 | 2023 GRC |  | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 7567.0669 | 7587.0669 | 7617.0669
2110000167 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | OPEX | HFTD | $ Thousands | 11.3 | All Consequences |  | 2018 | 2023 GRC |  | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 1967.4374 | 1972.6374 | 1980.4374
2110000168 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | CAPEX | Territory | $ Thousands | 11.4; CO-04; CO-05 | Foundational | Foundational | 2018 | 2023 GRC |  | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 114.46 | 120.673 | 123.587
2110000169 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | CAPEX | HFTD | $ Thousands | 11.4; CO-04; CO-05 | Foundational | Foundational | 2018 | 2023 GRC |  | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 114.46 | 120.673 | 123.587
2110000170 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | OPEX | Territory | $ Thousands | 11.4; CO-04; CO-05 | Foundational | Foundational | 2018 | 2023 GRC | Partially in WMPMA | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 20866.1655 | 21198.6386 | 8413.7831
2110000171 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | OPEX | HFTD | $ Thousands | 11.4; CO-04; CO-05 | Foundational | Foundational | 2018 | 2023 GRC | Partially in WMPMA | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 19416.217 | 19763.1078 | 6955.2746
2110000172 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | CAPEX | Territory | $ Thousands | 11.5 | All Consequences |  | 2018 | 2023 GRC | Partially in WMPMA | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 6500 | 24319.104 | 42646.026
2110000173 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | CAPEX | HFTD | $ Thousands | 11.5 | All Consequences |  | 2018 | 2023 GRC | Partially in WMPMA | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 1690 | 15942.967 | 30327.9668
2110000174 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | OPEX | Territory | $ Thousands | 11.5 | All Consequences |  | 2018 | 2023 GRC |  | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 77290.044 | 91820.758 | 52048.127
2110000175 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | OPEX | HFTD | $ Thousands | 11.5 | All Consequences |  | 2018 | 2023 GRC |  | In Compliance | De-energization OIR - Phase 3 |  |  |  | PG&E | 2026 | 2026 | 77290.044 | 91820.758 | 52048.127
2110000176 | Enterprise Systems | Enterprise Systems Development |  | CAPEX | Territory | $ Thousands | 12; ES-01; ES-02; ES-03; ES-04; ES-05 | Foundational | Foundational | 2021 (VM) | 2023 GRC |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 31514 | 56014 | 40350
2110000177 | Enterprise Systems | Enterprise Systems Development |  | CAPEX | HFTD | $ Thousands | 12; ES-01; ES-02; ES-03; ES-04; ES-05 | Foundational | Foundational | 2021 (VM) | 2023 GRC |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 31514 | 56014 | 40350
2110000178 | Enterprise Systems | Enterprise Systems Development |  | OPEX | Territory | $ Thousands | 12; ES-01; ES-02; ES-03; ES-04; ES-05 | Foundational | Foundational | 2021 (VM) | 2023 GRC |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 44204.011 | 39053.338 | 35211.968
2110000179 | Enterprise Systems | Enterprise Systems Development |  | OPEX | HFTD | $ Thousands | 12; ES-01; ES-02; ES-03; ES-04; ES-05 | Foundational | Foundational | 2021 (VM) | 2023 GRC |  |  | n/a |  |  |  | PG&E | 2026 | 2026 | 44124.121 | 38982.121 | 35142.121

## Table 12
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP ACTIVITY NAME | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | UTILITY MITIGATION ACTIVITY TRACKING ID | TARGET TYPE | UNIT(S) | METHOD OF VERIFICATION | COMMENTS | REPORTING YEAR | CYCLE YEAR 1 | YTD TARGET - Y1 Q2 | YTD TARGET - Y1 Q3 | YTD TARGET - Y1 Q4 | YTD TARGET - Y2 Q2 | YTD TARGET - Y2 Q3 | YTD TARGET - Y2 Q4 | YTD TARGET - Y3 Q2 | YTD TARGET - Y3 Q3 | YTD TARGET - Y3 Q4
2120000000 | PG&E | 2025-07-28 | Detailed Inspection - Transmission | Grid Design, Operations, and Maintenance | Asset Inspections |  | AI-04 | Quantitative | Transmission Structures | Attainment Report |  | 2026 | 2026 | 13200 | 22000 | 22000 | 13200 | 22000 | 22000 | 13200 | 22000 | 22000
2120000001 | PG&E | 2025-07-28 | Infrared Inspections - Transmission | Grid Design, Operations, and Maintenance | Asset Inspections |  | AI-06 | Quantitative | Circuit miles | Completed SAP Work Orders |  | 2026 | 2026 | 500 | 1500 | 2500 | 500 | 1500 | 2500 | 500 | 1500 | 2500
2120000002 | PG&E | 2025-07-28 | Aerial Scan Inspections - Distribution | Grid Design, Operations, and Maintenance | Asset Inspections |  | AI-07A | Quantitative | Distribution Poles | Attainment Report |  | 2026 | 2026 | 30000 | 50000 | 50000 | 12000 | 20000 | 20000 | 12000 | 20000 | 20000
2120000003 | PG&E | 2025-07-28 | Detailed Inspections - Distribution | Grid Design, Operations, and Maintenance | Asset Inspections |  | AI-07D | Quantitative | Distribution Poles | Attainment Report |  | 2026 | 2026 | 90000 | 190000 | 300000 | 90000 | 190000 | 305000 | 60000 | 160000 | 215000
2120000004 | PG&E | 2025-07-28 | System Hardening - Undergrounding | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | GH-04 | Quantitative | Circuit Miles | As-built job packages and design construction drawing |  | 2026 | 2026 |  |  | 360 |  |  | 307 |  |  | 400
2120000005 | PG&E | 2025-07-28 | System Hardening - Transmission Shunt Splices | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | GH-06 | Quantitative | Shunt Splices | Closed Work Orders |  | 2026 | 2026 |  |  | 250 |  |  | 250 |  |  | 250
2120000006 | PG&E | 2025-07-28 | System Hardening - Transmission Conductor Segment Replacement | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | GH-11 | Quantitative | Conductor Segment | As-built job package |  | 2026 | 2026 |  |  | 4 |  |  | 5 |  |  | 6
2120000007 | PG&E | 2025-07-28 | Overhead Hardening - Distribution | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | GH-12 | Quantitative | Circuit Miles | As-built job packages and design construction drawing |  | 2026 | 2026 |  |  | 294 |  |  | 190 |  |  | 190
2120000008 | PG&E | 2025-07-28 | Line Removal Enabled by Remote Grid - Distribution | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | GH-14 | Quantitative | Circuit Miles | As-built job packages and design construction drawing |  | 2026 | 2026 |  |  | 4 |  |  | 0 |  |  | 0
2120000009 | PG&E | 2025-07-28 | Asset Inspections Distribution Quality Assurance | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | GM-01D | Quantitative | % Pass Rate | Audit Checklists and Final Reports for All Audits |  | 2026 | 2026 |  |  | 95% |  |  | 96% |  |  | 97%
2120000010 | PG&E | 2025-07-28 | Asset Inspections Transmission Quality Assurance | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | GM-01T | Quantitative | % Pass Rate | Audit Checklists and Final Reports for All Audits |  | 2026 | 2026 |  |  | 95% |  |  | 96% |  |  | 97%
2120000011 | PG&E | 2025-07-28 | Open Tag Reduction - Distribution Backlog | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) |  | GM-03 | Quantitative | Distribution EC Tags | Closed Work Orders |  | 2026 | 2026 |  |  | 134% |  |  | 153% |  |  | 160%
2120000012 | PG&E | 2025-07-28 | Asset Inspections Distribution Quality Control | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | GM-09D | Quantitative | % Pass Rate | Audit Checklists and Final Reports for All Audits |  | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000013 | PG&E | 2025-07-28 | Asset Inspection Transmission Quality Control | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | GM-09T | Quantitative | % Pass Rate | Audit Checklists and Final Reports for All Audits |  | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000014 | PG&E | 2025-07-28 | System Hardening Distribution Quality Assurance | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | GM-10D | Quantitative | % Pass Rate | Audit Checklists and Final Reports for All Audits |  | 2026 | 2026 |  |  | 88% |  |  | 92% |  |  | 95%
2120000015 | PG&E | 2025-07-28 | System Hardening Distribution Quality Control | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | GM-11D | Quantitative | % Pass Rate | Audit Checklists and Final Reports for All Audits |  | 2026 | 2026 |  |  | 80% |  |  | 88% |  |  | 95%
2120000016 | PG&E | 2025-07-28 | Open Tag Reduction Distribution Backlog Quality Assurance | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | GM-12D | Quantitative | % Pass Rate | Audit Checklists and Final Reports for All Audits |  | 2026 | 2026 |  |  | 88% |  |  | 92% |  |  | 95%
2120000017 | PG&E | 2025-07-28 | Open Tag Reduction Distribution Backlog Quality Control | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | GM-13D | Quantitative | % Pass Rate | Audit Checklists and Final Reports for All Audits |  | 2026 | 2026 |  |  | 80% |  |  | 88% |  |  | 95%
2120000018 | PG&E | 2025-07-28 | Service Breakaway Connectors | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | GM-14 | Quantitative | Service Breakaway Connectors | Closed Work Orders |  | 2026 | 2026 |  |  | 200 |  |  | 1400 |  |  | 1400
2120000019 | PG&E | 2025-07-28 | Line Sensor - Installations | Situational Awareness and Forecasting | Grid Monitoring Systems |  | SA-02 | Quantitative | Sensor Locations | Closed notifications |  | 2026 | 2026 |  |  | 240 |  |  | 240 |  |  | 240
2120000020 | PG&E | 2025-07-28 | Distribution Fault Anticipation (DFA) Installations | Situational Awareness and Forecasting | Grid Monitoring Systems |  | SA-10 | Quantitative | Sensor Locations | Report demonstrating the first communication between the sensor and the Headend software. |  | 2026 | 2026 |  |  | 15 |  |  | 15 |  |  | 15
2120000021 | PG&E | 2025-07-28 | Early Fault Detection (EFD) - Installations | Situational Awareness and Forecasting | Grid Monitoring Systems |  | SA-11 | Quantitative | Sensor Locations | SAP Report showing notification completions. |  | 2026 | 2026 |  |  | 180 |  |  | 180 |  |  | 180
2120000022 | PG&E | 2025-07-28 | Live Fuel Moisture Data Collection | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | SA-12 | Quantitative | Sample Locations | Table of measured values. |  | 2026 | 2026 |  |  | 25 |  |  | 25 |  |  | 25
2120000023 | PG&E | 2025-07-28 | Weekly uptime of Wildfire Cameras | Situational Awareness and Forecasting | Ignition Detection Systems |  | SA-15 | Quantitative | Average weekly uptime percentage | Vendor report that demonstrates the average weekly uptime percentage of wildfire cameras during peak fire season (May 1 – November 30). |  | 2026 | 2026 |  |  | 90% |  |  | 90% |  |  | 90%
2120000024 | PG&E | 2025-07-28 | Weather Model Verification Tool | Situational Awareness and Forecasting | Weather Forecasting |  | SA-16 | Quantitative | Weather Model Verification Tool | Screen shots as well as numerical output from the tool showing quantitative skill scores based on observed values versus forecast from each weather model input. |  | 2026 | 2026 |  |  | 1 |  |  | 0 |  |  | 0
2120000025 | PG&E | 2025-07-28 | Weather Station Network Health | Situational Awareness and Forecasting | Weather Forecasting |  | SA-18 | Quantitative | Percent of Weather Stations | Export from the internal weather station calibration and maintenance database |  | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000026 | PG&E | 2025-07-28 | Pole Clearing Program - Compliance | Vegetation Management and Inspections | Pole Clearing |  | VM-02C | Quantitative | Poles | List of all distribution and transmission poles and structures in VM database as of October 1, with work status (end of program annual cycle) |  | 2026 | 2026 | 30958 | 45710 | 45710 | 30958 | 45710 | 45710 | 30958 | 45710 | 45710
2120000027 | PG&E | 2025-07-28 | Pole Clearing Program - Risk Reduction | Vegetation Management and Inspections | Pole Clearing |  | VM-02R | Quantitative | Poles | List of all distribution and transmission poles and structures in VM database as of October 1, with work status (end of program annual cycle) |  | 2026 | 2026 | 16445 | 24290 | 24290 | 16445 | 24290 | 24290 | 16445 | 24290 | 24290
2120000028 | PG&E | 2025-07-28 | Substation Inspections - Distribution | Vegetation Management and Inspections | Defensible Space |  | VM-05 | Quantitative | Distribution Substations | Closed notifications |  | 2026 | 2026 | 122 | 130 | 130 | 58 | 122 | 130 | 58 | 122 | 130
2120000029 | PG&E | 2025-07-28 | Substation Inspections - Transmission | Vegetation Management and Inspections | Defensible Space |  | VM-06 | Quantitative | Transmission Substations | Closed notifications |  | 2026 | 2026 | 53 | 55 | 55 | 53 | 55 | 55 | 53 | 55 | 55
2120000030 | PG&E | 2025-07-28 | Substation Inspections - Power Generation | Vegetation Management and Inspections | Defensible Space |  | VM-07 | Quantitative | Power Generation Switchyards and Powerhouses | Closed notifications |  | 2026 | 2026 | 52 | 58 | 58 | 52 | 58 | 58 | 52 | 58 | 58
2120000031 | PG&E | 2025-07-28 | Vegetation Management Quality Assurance - Distribution | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | VM-08D | Quantitative | % Pass Rate | Final Reports and Field Guides for All Audits. |  | 2026 | 2026 |  |  | 97% |  |  | 97% |  |  | 97%
2120000032 | PG&E | 2025-07-28 | Vegetation Management Quality Assurance - Transmission | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | VM-08T | Quantitative | % Pass Rate | Final Reports and Field Guides for All Audits. |  | 2026 | 2026 |  |  | 97% |  |  | 97% |  |  | 97%
2120000033 | PG&E | 2025-07-28 | Routine Transmission - Ground | Vegetation Management and Inspections | Vegetation Management Inspections |  | VM-13 | Quantitative | Circuit Miles | Report from VM database reflecting completed work. |  | 2026 | 2026 | 10000 | 15000 | 17500 | 10000 | 15000 | 17500 | 10000 | 15000 | 17500
2120000034 | PG&E | 2025-07-28 | Transmission Hazard Patrol (Second Patrol, Tree Mortality) | Vegetation Management and Inspections | Vegetation Management Inspections |  | VM-14 | Quantitative | Circuit Miles | Report from VM database reflecting completed work. |  | 2026 | 2026 | 0 | 0 | 5625 | 0 | 0 | 5625 | 0 | 0 | 5625
2120000035 | PG&E | 2025-07-28 | Distribution Routine Patrol | Vegetation Management and Inspections | Vegetation Management Inspections |  | VM-16 | Quantitative | Circuit Miles | Report from VM database reflecting completed work. |  | 2026 | 2026 | 31500 | 50500 | 78200 | 31000 | 50000 | 77800 | 31000 | 50000 | 77500
2120000036 | PG&E | 2025-07-28 | Distribution Hazard Patrol | Vegetation Management and Inspections | Vegetation Management Inspections |  | VM-17 | Quantitative | Circuit Miles | Report from VM database reflecting completed work. |  | 2026 | 2026 | 4000 | 6500 | 10000 | 4000 | 6500 | 10000 | 4000 | 6500 | 10000
2120000037 | PG&E | 2025-07-28 | Vegetation Management Quality Control - Distribution Routine | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | VM-22D | Quantitative | % Pass Rate | Final reports and field guides for all audits. |  | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000038 | PG&E | 2025-07-28 | Vegetation Management Quality Control - Pole Clearing | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | VM-22P | Quantitative | % Pass Rate | Final reports and field guides for all audits. |  | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000039 | PG&E | 2025-07-28 | Vegetation Management Quality Control - Transmission Routine | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | VM-22T | Quantitative | % Pass Rate | Final reports and field guides for all audits. |  | 2026 | 2026 |  |  | 95% |  |  | 95% |  |  | 95%
2120000040 | PG&E | 2025-07-28 | Mitigation of Legacy Tree Removal Inventory (TRI) | Vegetation Management and Inspections | Vegetation Management Inspections |  | VM-26 | Quantitative | Trees | Report from VM database reflecting hazard no longer present. |  | 2026 | 2026 |  |  | 40000 |  |  | 85000 |  |  | 135000

## Table 14
METRIC NUMBER | HFTD TIER | LINE TYPE | OVERALL UTILITY RISK | WILDFIRE RISK | OUTAGE PROGRAM RISK | WILDFIRE LIKELIHOOD | IGNITION LIKELIHOOD | EQUIPMENT CAUSED LIKELIHOOD OF IGNITION | CONTACT FROM VEGETATION LIKELIHOOD OF IGNITION | CONTACT FROM OBJECT LIKELIHOOD OF IGNITION | BURN LIKELIHOOD | WILDFIRE CONSEQUENCE | WILDFIRE HAZARD INTENSITY | WILDFIRE EXPOSURE POTENTIAL | PSPS RISK | PSPS LIKELIHOOD | PSPS CONSEQUENCE | PSPS EXPOSURE POTENTIAL | PSPS VULNERABILITY | PEDS RISK | PEDS LIKELIHOOD | PEDS CONSEQUENCE | PEDS EXPOSURE POTENTIAL | PEDS VULNERABILITY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR
2140000000 | HFTD Tier 2 | Distribution | 17716.8176 | 14993.3944 | 2723.4232 |  | 184.9835 | 79.3867 | 71.7813 | 33.8156 |  | 22712.6596 |  |  | 1702.0184 |  |  |  |  | 1021.4048 | [5 empty] | The data presented in this table are based on the best knowledge that PG&E has as of April 1, 2025. Note 1: Ignition Likelihood Metric: Ignition Risk scaled from WDRM v4 to historical CPUC reportable risks. Note 2: The WTRM currently does not output results in the categories defined in this table. While the WTRM is used to represent risk across PG&E's Transmission System, the WTRM is not currently calibrated with the WDRM and is not fit for use for comparison of risks across multiple domains. This applies to Transmission Line Metric or Metric Number: 2140000002, 2140000003 & 2140000005. Note 3: PSPS Likelihood Metric: PSPS likelihood is aggregated at the number of annual PSPS events and is represented as the same value for both HFTD and non-HFTD. Note 4: PG&E's risk models does not uniquely differentiate HFTD Tier 2 vs Tier 3 in its results, as PG&E sees a wide range of risk consequence in Tier 2 and Tier3. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. Per note 4, PG&E has provided its data in HFTD 2 Distribution row but note that the results also include HFTD 3 Distribution. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. This applies to Distribution HFTD Tier 3 or Metric Number: 2140000001. Note 5: For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2140000001 | HFTD Tier 3 | Distribution | [23 empty] | The data presented in this table are based on the best knowledge that PG&E has as of April 1, 2025. Note 1: Ignition Likelihood Metric: Ignition Risk scaled from WDRM v4 to historical CPUC reportable risks. Note 2: The WTRM currently does not output results in the categories defined in this table. While the WTRM is used to represent risk across PG&E's Transmission System, the WTRM is not currently calibrated with the WDRM and is not fit for use for comparison of risks across multiple domains. This applies to Transmission Line Metric or Metric Number: 2140000002, 2140000003 & 2140000005. Note 3: PSPS Likelihood Metric: PSPS likelihood is aggregated at the number of annual PSPS events and is represented as the same value for both HFTD and non-HFTD. Note 4: PG&E's risk models does not uniquely differentiate HFTD Tier 2 vs Tier 3 in its results, as PG&E sees a wide range of risk consequence in Tier 2 and Tier3. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. Per note 4, PG&E has provided its data in HFTD 2 Distribution row but note that the results also include HFTD 3 Distribution. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. This applies to Distribution HFTD Tier 3 or Metric Number: 2140000001. Note 5: For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2140000002 | HFTD Tier 2 | Transmision | [23 empty] | The data presented in this table are based on the best knowledge that PG&E has as of April 1, 2025. Note 1: Ignition Likelihood Metric: Ignition Risk scaled from WDRM v4 to historical CPUC reportable risks. Note 2: The WTRM currently does not output results in the categories defined in this table. While the WTRM is used to represent risk across PG&E's Transmission System, the WTRM is not currently calibrated with the WDRM and is not fit for use for comparison of risks across multiple domains. This applies to Transmission Line Metric or Metric Number: 2140000002, 2140000003 & 2140000005. Note 3: PSPS Likelihood Metric: PSPS likelihood is aggregated at the number of annual PSPS events and is represented as the same value for both HFTD and non-HFTD. Note 4: PG&E's risk models does not uniquely differentiate HFTD Tier 2 vs Tier 3 in its results, as PG&E sees a wide range of risk consequence in Tier 2 and Tier3. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. Per note 4, PG&E has provided its data in HFTD 2 Distribution row but note that the results also include HFTD 3 Distribution. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. This applies to Distribution HFTD Tier 3 or Metric Number: 2140000001. Note 5: For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2140000003 | HFTD Tier 3 | Transmision | [23 empty] | The data presented in this table are based on the best knowledge that PG&E has as of April 1, 2025. Note 1: Ignition Likelihood Metric: Ignition Risk scaled from WDRM v4 to historical CPUC reportable risks. Note 2: The WTRM currently does not output results in the categories defined in this table. While the WTRM is used to represent risk across PG&E's Transmission System, the WTRM is not currently calibrated with the WDRM and is not fit for use for comparison of risks across multiple domains. This applies to Transmission Line Metric or Metric Number: 2140000002, 2140000003 & 2140000005. Note 3: PSPS Likelihood Metric: PSPS likelihood is aggregated at the number of annual PSPS events and is represented as the same value for both HFTD and non-HFTD. Note 4: PG&E's risk models does not uniquely differentiate HFTD Tier 2 vs Tier 3 in its results, as PG&E sees a wide range of risk consequence in Tier 2 and Tier3. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. Per note 4, PG&E has provided its data in HFTD 2 Distribution row but note that the results also include HFTD 3 Distribution. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. This applies to Distribution HFTD Tier 3 or Metric Number: 2140000001. Note 5: For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2140000004 | Non-HFTD | Distribution | 2298.5679 | 2080.6056 | 217.9623 |  | 341.9987 | 199.3551 | 52.589 | 90.0545 |  | 3326.3728 |  |  | 190.8271 |  |  |  |  | 27.1352 | [5 empty] | The data presented in this table are based on the best knowledge that PG&E has as of April 1, 2025. Note 1: Ignition Likelihood Metric: Ignition Risk scaled from WDRM v4 to historical CPUC reportable risks. Note 2: The WTRM currently does not output results in the categories defined in this table. While the WTRM is used to represent risk across PG&E's Transmission System, the WTRM is not currently calibrated with the WDRM and is not fit for use for comparison of risks across multiple domains. This applies to Transmission Line Metric or Metric Number: 2140000002, 2140000003 & 2140000005. Note 3: PSPS Likelihood Metric: PSPS likelihood is aggregated at the number of annual PSPS events and is represented as the same value for both HFTD and non-HFTD. Note 4: PG&E's risk models does not uniquely differentiate HFTD Tier 2 vs Tier 3 in its results, as PG&E sees a wide range of risk consequence in Tier 2 and Tier3. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. Per note 4, PG&E has provided its data in HFTD 2 Distribution row but note that the results also include HFTD 3 Distribution. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. This applies to Distribution HFTD Tier 3 or Metric Number: 2140000001. Note 5: For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2140000005 | Non-HFTD | Transmision | [23 empty] | The data presented in this table are based on the best knowledge that PG&E has as of April 1, 2025. Note 1: Ignition Likelihood Metric: Ignition Risk scaled from WDRM v4 to historical CPUC reportable risks. Note 2: The WTRM currently does not output results in the categories defined in this table. While the WTRM is used to represent risk across PG&E's Transmission System, the WTRM is not currently calibrated with the WDRM and is not fit for use for comparison of risks across multiple domains. This applies to Transmission Line Metric or Metric Number: 2140000002, 2140000003 & 2140000005. Note 3: PSPS Likelihood Metric: PSPS likelihood is aggregated at the number of annual PSPS events and is represented as the same value for both HFTD and non-HFTD. Note 4: PG&E's risk models does not uniquely differentiate HFTD Tier 2 vs Tier 3 in its results, as PG&E sees a wide range of risk consequence in Tier 2 and Tier3. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. Per note 4, PG&E has provided its data in HFTD 2 Distribution row but note that the results also include HFTD 3 Distribution. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. This applies to Distribution HFTD Tier 3 or Metric Number: 2140000001. Note 5: For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026

## Table 15
METRIC NUMBER | TOP-RISK CIRCUIT / SEGMENT / SPAN ID | RISK GRANULARITY | LINE TYPE | CIRCUIT / SEGMENT / SPAN LENGTH (MI) | INCLUSION REASON | HFTD TIER | OVERALL UTILITY RISK | WILDFIRE RISK | OUTAGE PROGRAM RISK | WILDFIRE LIKELIHOOD | IGNITION LIKELIHOOD | EQUIPMENT CAUSED LIKELIHOOD OF IGNITION | CONTACT FROM VEGETATION LIKELIHOOD OF IGNITION | CONTACT FROM OBJECT LIKELIHOOD OF IGNITION | BURN LIKELIHOOD | WILDFIRE CONSEQUENCE | WILDFIRE HAZARD INTENSITY | WILDFIRE EXPOSURE POTENTIAL | PSPS RISK | PSPS LIKELIHOOD | PSPS CONSEQUENCE | PSPS EXPOSURE POTENTIAL | PSPS VULNERABILITY | PEDS RISK | PEDS LIKELIHOOD | PEDS CONSEQUENCE | PEDS EXPOSURE POTENTIAL | PEDS VULNERABILITY | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR
2150000000 | CLAYTON 2212681608 | Circuit Segment | Distribution | 35.4168 | Top 20% | Tier 2 | 99.7013 | 92.6037 | 7.0976 |  | 0.13611 | 0.063237 | 0.046244 | 0.026633 |  | 43.7216 |  |  | 6.1997 |  |  |  |  | 0.89786 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000001 | BALCH NO 1 1101105414 | Circuit Segment | Distribution | 7.6231 | Top 20% | Tier 2 | 91.5229 | 91.5131 | 0.0098458 |  | 0.024374 | 0.0086115 | 0.0092063 | 0.0065563 |  | 241.2813 |  |  | 0 |  |  |  |  | 0.0098458 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000002 | CLOVERDALE 1102672 | Circuit Segment | Distribution | 23.3732 | Top 20% | Tier 2 | 80.9024 | 78.7264 | 2.176 |  | 0.058839 | 0.018553 | 0.030624 | 0.0096617 |  | 85.986 |  |  | 2.0231 |  |  |  |  | 0.15291 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000003 | PLACERVILLE 21067522 | Circuit Segment | Distribution | 75.656 | Top 20% | Tier 2 | 72.8321 | 67.696 | 5.1361 |  | 0.385 | 0.11568 | 0.2105 | 0.058814 |  | 11.2999 |  |  | 4.0717 |  |  |  |  | 1.0644 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000004 | PLACERVILLE 210611132 | Circuit Segment | Distribution | 46.9606 | Top 20% | Tier 2 | 67.324 | 62.2574 | 5.0666 |  | 0.18299 | 0.058076 | 0.093408 | 0.031511 |  | 21.8636 |  |  | 1.4525 |  |  |  |  | 3.614 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000005 | MIDDLETOWN 1101644756 | Circuit Segment | Distribution | 20.3553 | Top 20% | Tier 2 | 66.8951 | 65.0459 | 1.8492 |  | 0.077249 | 0.022512 | 0.045453 | 0.0092835 |  | 54.1125 |  |  | 1.6808 |  |  |  |  | 0.16837 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000006 | STANISLAUS 1701CB | Circuit Segment | Distribution | 43.596 | Top 20% | Tier 2 | 64.2834 | 62.1173 | 2.1661 |  | 0.13461 | 0.052727 | 0.034377 | 0.04751 |  | 29.6545 |  |  | 0.53509 |  |  |  |  | 1.631 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000007 | EL DORADO PH 210119752 | Circuit Segment | Distribution | 52.401 | Top 20% | Tier 2 | 61.3359 | 55.4086 | 5.9273 |  | 0.20347 | 0.062625 | 0.1064 | 0.034444 |  | 17.5003 |  |  | 5.0835 |  |  |  |  | 0.84382 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000008 | CALPINE 1144CB | Circuit Segment | Distribution | 27.2585 | Top 20% | Tier 2 | 60.6956 | 58.9532 | 1.7424 |  | 0.048353 | 0.013749 | 0.016475 | 0.018129 |  | 78.3526 |  |  | 1.7424 |  |  |  |  | 0 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000009 | ALLEGHANY 1102CB | Circuit Segment | Distribution | 19.4996 | Top 20% | Tier 2 | 60.0599 | 59.7834 | 0.27645 |  | 0.079255 | 0.027332 | 0.041508 | 0.010416 |  | 48.4754 |  |  | 0.15542 |  |  |  |  | 0.12102 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000010 | MARIPOSA 210237282 | Circuit Segment | Distribution | 62.7085 | Top 20% | Tier 2 | 59.3946 | 57.7906 | 1.604 |  | 0.20758 | 0.077918 | 0.083705 | 0.045953 |  | 17.8916 |  |  | 0 |  |  |  |  | 1.604 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000011 | BIG BEND 1101CB | Circuit Segment | Distribution | 23.609 | Top 20% | Tier 2 | 57.5444 | 51.6681 | 5.8763 |  | 0.05666 | 0.023075 | 0.026154 | 0.0074312 |  | 58.6022 |  |  | 5.7313 |  |  |  |  | 0.145 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000012 | WEST POINT 11024788 | Circuit Segment | Distribution | 75.8544 | Top 20% | Tier 2 | 57.4156 | 54.6136 | 2.8021 |  | 0.16676 | 0.076021 | 0.062502 | 0.028239 |  | 21.0462 |  |  | 2.2061 |  |  |  |  | 0.59599 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000013 | CALAVERAS CEMENT 1101544800 | Circuit Segment | Distribution | 23.6165 | Top 20% | Tier 2 | 57.3184 | 57.0604 | 0.25802 |  | 0.040149 | 0.020534 | 0.011907 | 0.0077075 |  | 91.3337 |  |  | 0.21182 |  |  |  |  | 0.046205 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000014 | CALAVERAS CEMENT 1101502 | Circuit Segment | Distribution | 43.3366 | Top 20% | Tier 2 | 56.1338 | 54.458 | 1.6758 |  | 0.12629 | 0.053666 | 0.043409 | 0.029216 |  | 27.7113 |  |  | 0.34326 |  |  |  |  | 1.3325 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000015 | CORNING 110185152 | Circuit Segment | Distribution | 25.5307 | Top 20% | Tier 2 | 54.4345 | 48.2352 | 6.1993 |  | 0.1089 | 0.046822 | 0.040529 | 0.021549 |  | 28.4645 |  |  | 6.015 |  |  |  |  | 0.18428 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000016 | CURTIS 17048140 | Circuit Segment | Distribution | 38.453 | Top 20% | Tier 2 | 54.0429 | 51.7497 | 2.2932 |  | 0.11627 | 0.050045 | 0.044665 | 0.021558 |  | 28.6032 |  |  | 1.241 |  |  |  |  | 1.0523 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000017 | COLUMBIA HILL 1101CB | Circuit Segment | Distribution | 51.5966 | Top 20% | Tier 2 | 53.4681 | 50.684 | 2.784 |  | 0.16327 | 0.056241 | 0.084031 | 0.022996 |  | 19.9498 |  |  | 0.96326 |  |  |  |  | 1.8208 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000018 | TEMPLETON 2113A12 | Circuit Segment | Distribution | 41.5125 | Top 20% | Tier 2 | 53.4192 | 53.0356 | 0.38359 |  | 0.091532 | 0.03792 | 0.024195 | 0.029417 |  | 37.2361 |  |  | 0.23292 |  |  |  |  | 0.15067 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000019 | FORT ROSS 112170288 | Circuit Segment | Distribution | 25.2158 | Top 20% | Tier 2 | 52.9255 | 52.6791 | 0.24643 |  | 0.19931 | 0.030951 | 0.16126 | 0.0071058 |  | 16.9851 |  |  | 0.12827 |  |  |  |  | 0.11817 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000020 | BIG BEND 1101641808 | Circuit Segment | Distribution | 30.4748 | Top 20% | Tier 2 | 52.57 | 47.0195 | 5.5505 |  | 0.065293 | 0.035274 | 0.021822 | 0.0081979 |  | 46.2785 |  |  | 5.4214 |  |  |  |  | 0.12906 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000021 | MARIPOSA 2101752630 | Circuit Segment | Distribution | 19.3001 | Top 20% | Tier 2 | 51.4021 | 51.3695 | 0.032589 |  | 0.044686 | 0.02144 | 0.016406 | 0.0068402 |  | 73.8765 |  |  | 0 |  |  |  |  | 0.032589 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000022 | SILVERADO 2104633600 | Circuit Segment | Distribution | 38.4142 | Top 20% | Tier 2 | 50.5596 | 44.9826 | 5.577 |  | 0.12429 | 0.051605 | 0.036784 | 0.035902 |  | 23.258 |  |  | 5.242 |  |  |  |  | 0.33499 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000023 | VACAVILLE 110838316 | Circuit Segment | Distribution | 24.831 | Top 20% | Tier 2 | 49.3106 | 47.764 | 1.5466 |  | 0.082862 | 0.035522 | 0.034679 | 0.012661 |  | 37.0439 |  |  | 1.1272 |  |  |  |  | 0.41938 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000024 | APPLE HILL 110497086 | Circuit Segment | Distribution | 31.1463 | Top 20% | Tier 2 | 49.1966 | 46.843 | 2.3536 |  | 0.099401 | 0.031617 | 0.058211 | 0.0095738 |  | 30.2847 |  |  | 2.2142 |  |  |  |  | 0.13941 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000025 | APPLE HILL 21029722 | Circuit Segment | Distribution | 40.284 | Top 20% | Tier 2 | 48.5389 | 46.5058 | 2.0331 |  | 0.14042 | 0.047394 | 0.069193 | 0.023831 |  | 21.2841 |  |  | 1.3069 |  |  |  |  | 0.72622 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000026 | MIDDLETOWN 1101548 | Circuit Segment | Distribution | 55.4704 | Top 20% | Tier 2 | 48.4984 | 41.3425 | 7.1559 |  | 0.15762 | 0.063641 | 0.070346 | 0.02363 |  | 16.8563 |  |  | 5.8623 |  |  |  |  | 1.2936 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000027 | PINE GROVE 11026080 | Circuit Segment | Distribution | 36.1724 | Top 20% | Tier 2 | 48.1154 | 46.5222 | 1.5931 |  | 0.11847 | 0.034357 | 0.068772 | 0.015345 |  | 25.2353 |  |  | 1.4599 |  |  |  |  | 0.13321 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000028 | HIGHLANDS 1102628 | Circuit Segment | Distribution | 21.9791 | Top 20% | Tier 2 | 46.8557 | 46.5809 | 0.27478 |  | 0.049214 | 0.020183 | 0.0060569 | 0.022974 |  | 60.8259 |  |  | 0.25621 |  |  |  |  | 0.018563 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000029 | PLACERVILLE 21069712 | Circuit Segment | Distribution | 27.8279 | Top 20% | Tier 2 | 46.2948 | 43.8896 | 2.4052 |  | 0.11139 | 0.027599 | 0.069322 | 0.014469 |  | 25.3213 |  |  | 0.62618 |  |  |  |  | 1.7791 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000030 | HARTLEY 1101698 | Circuit Segment | Distribution | 34.9538 | Top 20% | Tier 2 | 46.1802 | 45.9563 | 0.22392 |  | 0.11607 | 0.043326 | 0.042357 | 0.030388 |  | 25.4442 |  |  | 0 |  |  |  |  | 0.22392 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000031 | PUEBLO 2103678 | Circuit Segment | Distribution | 37.8073 | Top 20% | Tier 2 | 45.963 | 42.0971 | 3.8658 |  | 0.20238 | 0.053764 | 0.13077 | 0.017838 |  | 13.3679 |  |  | 2.9464 |  |  |  |  | 0.9194 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000032 | MARTELL 110191216 | Circuit Segment | Distribution | 42.5694 | Top 20% | Tier 2 | 45.6481 | 45.3977 | 0.25043 |  | 0.17854 | 0.045181 | 0.11349 | 0.019868 |  | 16.3405 |  |  | 0 |  |  |  |  | 0.25043 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000033 | REDBUD 1101323962 | Circuit Segment | Distribution | 27.7774 | Top 20% | Tier 2 | 45.5277 | 36.441 | 9.0867 |  | 0.11119 | 0.045251 | 0.036131 | 0.029812 |  | 21.0609 |  |  | 8.6579 |  |  |  |  | 0.4288 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000034 | MOLINO 1102318 | Circuit Segment | Distribution | 29.5017 | Top 20% | Tier 2 | 45.412 | 44.6383 | 0.77372 |  | 0.26334 | 0.046125 | 0.21003 | 0.0071901 |  | 10.8933 |  |  | 0.60801 |  |  |  |  | 0.16571 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000035 | HIGHLANDS 1103520 | Circuit Segment | Distribution | 48.9336 | Top 20% | Tier 2 | 44.295 | 41.366 | 2.929 |  | 0.17704 | 0.073004 | 0.073294 | 0.030738 |  | 15.0159 |  |  | 2.5212 |  |  |  |  | 0.40774 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000036 | COARSEGOLD 210410110 | Circuit Segment | Distribution | 56.3809 | Top 20% | Tier 2 | 43.9578 | 41.5037 | 2.4541 |  | 0.16647 | 0.066672 | 0.0722 | 0.027595 |  | 16.0223 |  |  | 1.434 |  |  |  |  | 1.0201 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000037 | AUBERRY 1101R2578 | Circuit Segment | Distribution | 48.6037 | Top 20% | Tier 2 | 43.6409 | 40.7536 | 2.8873 |  | 0.14805 | 0.083057 | 0.040157 | 0.024833 |  | 17.6903 |  |  | 1.722 |  |  |  |  | 1.1653 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000038 | MARIPOSA 210237288 | Circuit Segment | Distribution | 87.3656 | Top 20% | Tier 2 | 43.5691 | 42.7023 | 0.86674 |  | 0.21901 | 0.081372 | 0.097741 | 0.039896 |  | 12.5302 |  |  | 0 |  |  |  |  | 0.86674 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000039 | FROGTOWN 170113412 | Circuit Segment | Distribution | 54.0948 | Top 20% | Tier 2 | 43.5543 | 37.8631 | 5.6911 |  | 0.1502 | 0.062128 | 0.049366 | 0.038701 |  | 16.2006 |  |  | 2.818 |  |  |  |  | 2.8732 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000040 | ELECTRA 1101CB | Circuit Segment | Distribution | 25.4619 | Top 20% | Tier 2 | 43.215 | 41.7064 | 1.5086 |  | 0.079933 | 0.031496 | 0.03447 | 0.013967 |  | 33.5311 |  |  | 0.42173 |  |  |  |  | 1.0869 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000041 | CORNING 11021622 | Circuit Segment | Distribution | 35.385 | Top 20% | Tier 2 | 42.7053 | 41.3156 | 1.3897 |  | 0.057258 | 0.025699 | 0.014721 | 0.016838 |  | 46.371 |  |  | 1.3315 |  |  |  |  | 0.058175 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000042 | DIAMOND SPRINGS 110676088 | Circuit Segment | Distribution | 35.0127 | Top 20% | Tier 2 | 42.3199 | 41.9075 | 0.4124 |  | 0.094289 | 0.033429 | 0.052275 | 0.0085845 |  | 28.5628 |  |  | 0.28979 |  |  |  |  | 0.12261 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000043 | BONNIE NOOK 1102CB | Circuit Segment | Distribution | 34.8434 | Top 20% | Tier 2 | 41.8552 | 35.1003 | 6.7549 |  | 0.15144 | 0.041004 | 0.091728 | 0.018704 |  | 14.8953 |  |  | 5.5218 |  |  |  |  | 1.2332 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000044 | BRUNSWICK 11021010 | Circuit Segment | Distribution | 50.4723 | Top 20% | Tier 2 | 41.6777 | 40.6525 | 1.0252 |  | 0.19266 | 0.057329 | 0.1123 | 0.023035 |  | 13.5602 |  |  | 0.50855 |  |  |  |  | 0.51663 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000045 | CURTIS 170390320 | Circuit Segment | Distribution | 32.6469 | Top 20% | Tier 2 | 41.0182 | 39.6973 | 1.3209 |  | 0.10586 | 0.041724 | 0.039249 | 0.024884 |  | 24.0998 |  |  | 0.81835 |  |  |  |  | 0.50253 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000046 | MARIPOSA 210110070 | Circuit Segment | Distribution | 26.4071 | Top 20% | Tier 2 | 40.9066 | 40.8295 | 0.077089 |  | 0.075969 | 0.035472 | 0.028069 | 0.012428 |  | 34.5387 |  |  | 0 |  |  |  |  | 0.077089 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000047 | GIRVAN 11011330 | Circuit Segment | Distribution | 26.4545 | Top 20% | Tier 2 | 40.5343 | 35.9333 | 4.601 |  | 0.097704 | 0.034017 | 0.045967 | 0.01772 |  | 23.6349 |  |  | 4.3222 |  |  |  |  | 0.27885 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000048 | APPLE HILL 110413512 | Circuit Segment | Distribution | 34.9362 | Top 20% | Tier 2 | 40.3039 | 32.9483 | 7.3557 |  | 0.17086 | 0.05237 | 0.090642 | 0.027851 |  | 12.3924 |  |  | 5.7972 |  |  |  |  | 1.5584 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000049 | DIAMOND SPRINGS 11057722 | Circuit Segment | Distribution | 67.1467 | Top 20% | Tier 2 | 40.1837 | 39.017 | 1.1667 |  | 0.21238 | 0.076078 | 0.094685 | 0.041612 |  | 11.8065 |  |  | 0 |  |  |  |  | 1.1667 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000050 | BALCH NO 1 1101406582 | Circuit Segment | Distribution | 3.7849 | Top 20% | Tier 2 | 40.1094 | 40.1094 | 0 |  | 0.0093633 | 0.0047782 | 0.0020065 | 0.0025786 |  | 275.2873 |  |  | 0 |  |  |  |  | 0 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000051 | MOUNTAIN QUARRIES 21011130 | Circuit Segment | Distribution | 23.1739 | Top 20% | Tier 2 | 39.6503 | 38.0279 | 1.6224 |  | 0.11605 | 0.030195 | 0.07681 | 0.0090458 |  | 21.0583 |  |  | 1.5487 |  |  |  |  | 0.073701 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000052 | APPLE HILL 2102836878 | Circuit Segment | Distribution | 45.221 | Top 20% | Tier 2 | 39.4699 | 30.2953 | 9.1746 |  | 0.15723 | 0.057234 | 0.07022 | 0.029775 |  | 12.3826 |  |  | 2.3416 |  |  |  |  | 6.8331 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000053 | COALINGA NO 2 11059260 | Circuit Segment | Distribution | 19.5983 | Top 20% | Non-HFTD | 39.3637 | 39.1603 | 0.20346 |  | 0.037265 | 0.017713 | 0.003974 | 0.015577 |  | 67.5332 |  |  | 0.20346 |  |  |  |  | 0 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000054 | LAYTONVILLE 1101518 | Circuit Segment | Distribution | 22.9002 | Top 20% | Tier 2 | 38.8951 | 38.1141 | 0.78099 |  | 0.11357 | 0.025802 | 0.079474 | 0.0082907 |  | 21.5678 |  |  | 0.47054 |  |  |  |  | 0.31044 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000055 | APPLE HILL 21028372 | Circuit Segment | Distribution | 67.8945 | Top 20% | Tier 2 | 38.7665 | 34.2702 | 4.4963 |  | 0.21575 | 0.075313 | 0.10119 | 0.039255 |  | 10.2076 |  |  | 2.3587 |  |  |  |  | 2.1376 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000056 | LOS OSITOS 21037014 | Circuit Segment | Distribution | 40.7498 | Top 20% | Non-HFTD | 38.7165 | 38.6357 | 0.080815 |  | 0.08994 | 0.041143 | 0.01465 | 0.034147 |  | 27.606 |  |  | 0.080815 |  |  |  |  | 0 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000057 | STILLWATER 11021466 | Circuit Segment | Distribution | 23.3806 | Top 20% | Tier 2 | 38.3929 | 34.3774 | 4.0155 |  | 0.059258 | 0.027049 | 0.022635 | 0.0095751 |  | 37.2814 |  |  | 3.8751 |  |  |  |  | 0.1404 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000058 | PIT NO 3 21011482 | Circuit Segment | Distribution | 15.2143 | Top 20% | Tier 2 | 37.308 | 37.1846 | 0.12347 |  | 0.049215 | 0.013084 | 0.029559 | 0.0065721 |  | 48.5554 |  |  | 0.11655 |  |  |  |  | 0.0069235 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000059 | GEYSERVILLE 1102904170 | Circuit Segment | Distribution | 23.5742 | Top 20% | Tier 2 | 36.9939 | 34.3796 | 2.6142 |  | 0.049465 | 0.019995 | 0.018524 | 0.010946 |  | 44.6653 |  |  | 2.5059 |  |  |  |  | 0.10833 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000060 | FORESTHILL 11011802 | Circuit Segment | Distribution | 30.2054 | Top 20% | Tier 2 | 36.4406 | 30.8293 | 5.6113 |  | 0.16344 | 0.045694 | 0.098248 | 0.019497 |  | 12.1221 |  |  | 4.8255 |  |  |  |  | 0.78582 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000061 | FITCH MOUNTAIN 111324918 | Circuit Segment | Distribution | 25.752 | Top 20% | Tier 2 | 36.4262 | 35.8264 | 0.59982 |  | 0.15764 | 0.021202 | 0.13028 | 0.0061534 |  | 14.6055 |  |  | 0.39278 |  |  |  |  | 0.20705 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000062 | MARIPOSA 2101439030 | Circuit Segment | Distribution | 21.2147 | Top 20% | Tier 2 | 36.0716 | 35.9859 | 0.085693 |  | 0.067417 | 0.023849 | 0.036056 | 0.007511 |  | 34.3032 |  |  | 0 |  |  |  |  | 0.085693 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000063 | CLAYTON 221296224 | Circuit Segment | Distribution | 11.284 | Top 20% | Tier 2 | 35.9806 | 35.4507 | 0.52991 |  | 0.046568 | 0.021833 | 0.015603 | 0.0091324 |  | 48.9217 |  |  | 0.49709 |  |  |  |  | 0.032818 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000064 | PEORIA 170190090 | Circuit Segment | Distribution | 31.2401 | Top 20% | Tier 2 | 35.8543 | 33.1277 | 2.7266 |  | 0.11004 | 0.043929 | 0.021347 | 0.044767 |  | 19.3464 |  |  | 0.48969 |  |  |  |  | 2.2369 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000065 | HOPLAND 11014626 | Circuit Segment | Distribution | 34.8809 | Top 20% | Tier 2 | 35.6066 | 34.6606 | 0.94602 |  | 0.097139 | 0.039756 | 0.035941 | 0.021442 |  | 22.9303 |  |  | 0 |  |  |  |  | 0.94602 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000066 | SILVERADO 2104632 | Circuit Segment | Distribution | 20.6928 | Top 20% | Tier 2 | 35.5808 | 32.1845 | 3.3963 |  | 0.10997 | 0.025477 | 0.073616 | 0.010876 |  | 18.8081 |  |  | 2.6824 |  |  |  |  | 0.71395 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000067 | PLACERVILLE 2106935216 | Circuit Segment | Distribution | 22.2061 | Top 20% | Tier 2 | 35.4512 | 34.222 | 1.2292 |  | 0.072958 | 0.025842 | 0.033935 | 0.013181 |  | 30.1442 |  |  | 1.0988 |  |  |  |  | 0.13036 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000068 | APPLE HILL 2102186912 | Circuit Segment | Distribution | 66.3958 | Top 20% | Tier 2 | 34.9302 | 30.6161 | 4.3141 |  | 0.20513 | 0.067594 | 0.10245 | 0.035084 |  | 9.5917 |  |  | 2.6329 |  |  |  |  | 1.6813 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000069 | SHADY GLEN 1101941844 | Circuit Segment | Distribution | 22.045 | Top 20% | Tier 2 | 34.5974 | 29.2227 | 5.3747 |  | 0.11588 | 0.032269 | 0.069197 | 0.014418 |  | 16.2056 |  |  | 5.0009 |  |  |  |  | 0.37383 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000070 | PINE GROVE 1102269286 | Circuit Segment | Distribution | 39.4734 | Top 20% | Tier 2 | 34.1506 | 26.1142 | 8.0364 |  | 0.18696 | 0.060873 | 0.098634 | 0.02745 |  | 8.9764 |  |  | 4.7919 |  |  |  |  | 3.2445 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000071 | ORO FINO 110239154 | Circuit Segment | Distribution | 48.2517 | Top 20% | Tier 2 | 34.0841 | 28.7396 | 5.3445 |  | 0.18321 | 0.058536 | 0.11024 | 0.014435 |  | 10.0811 |  |  | 4.8406 |  |  |  |  | 0.50388 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000072 | WEST POINT 110234416 | Circuit Segment | Distribution | 27.7683 | Top 20% | Tier 2 | 33.9065 | 32.2029 | 1.7036 |  | 0.10398 | 0.030661 | 0.061247 | 0.012073 |  | 19.9026 |  |  | 1.5426 |  |  |  |  | 0.16097 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000073 | CEDAR CREEK 1101CB | Circuit Segment | Distribution | 50.4966 | Top 20% | Tier 2 | 33.7551 | 29.4514 | 4.3038 |  | 0.10487 | 0.039742 | 0.049724 | 0.015404 |  | 18.0476 |  |  | 3.7364 |  |  |  |  | 0.56738 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000074 | SISQUOC 1102M52 | Circuit Segment | Distribution | 36.24 | Top 20% | Tier 2 | 33.4088 | 33.1637 | 0.24506 |  | 0.074935 | 0.029168 | 0.020849 | 0.024918 |  | 28.4412 |  |  | 0.13334 |  |  |  |  | 0.11172 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000075 | TEMPLETON 2113641367 | Circuit Segment | Distribution | 41.7005 | Top 20% | Tier 2 | 33.3923 | 32.9903 | 0.40202 |  | 0.088437 | 0.038841 | 0.027803 | 0.021794 |  | 23.9728 |  |  | 0.15967 |  |  |  |  | 0.24235 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000076 | MARIPOSA 21019400 | Circuit Segment | Distribution | 64.9749 | Top 20% | Tier 2 | 33.2984 | 31.1666 | 2.1319 |  | 0.17249 | 0.074105 | 0.076059 | 0.022324 |  | 11.6118 |  |  | 0 |  |  |  |  | 2.1319 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000077 | FORESTHILL 1102359542 | Circuit Segment | Distribution | 26.2066 | Top 20% | Tier 2 | 32.7979 | 30.1772 | 2.6207 |  | 0.090421 | 0.02365 | 0.053858 | 0.012913 |  | 21.4476 |  |  | 2.5431 |  |  |  |  | 0.077682 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000078 | CALAVERAS CEMENT 11011419 | Circuit Segment | Distribution | 16.8179 | Top 20% | Tier 2 | 32.6283 | 32.0933 | 0.53505 |  | 0.037272 | 0.016106 | 0.014487 | 0.0066787 |  | 55.3346 |  |  | 0.23297 |  |  |  |  | 0.30208 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000079 | BRUNSWICK 110651486 | Circuit Segment | Distribution | 65.0758 | Top 20% | Tier 2 | 32.0751 | 30.4848 | 1.5903 |  | 0.26515 | 0.072643 | 0.1658 | 0.026705 |  | 7.3886 |  |  | 0.88165 |  |  |  |  | 0.70861 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000080 | SHINGLE SPRINGS 210913322 | Circuit Segment | Distribution | 46.0385 | Top 20% | Tier 2 | 32.0191 | 31.847 | 0.17212 |  | 0.15997 | 0.056183 | 0.079468 | 0.024322 |  | 12.7936 |  |  | 0 |  |  |  |  | 0.17212 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000081 | PINE GROVE 11013170 | Circuit Segment | Distribution | 44.1726 | Top 20% | Tier 2 | 32.0008 | 30.8997 | 1.101 |  | 0.21226 | 0.073439 | 0.10191 | 0.036911 |  | 9.3554 |  |  | 0.73713 |  |  |  |  | 0.36391 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000082 | WEST POINT 110236676 | Circuit Segment | Distribution | 17.6111 | Top 20% | Tier 2 | 31.795 | 30.7184 | 1.0766 |  | 0.05121 | 0.018142 | 0.02695 | 0.0061179 |  | 38.5489 |  |  | 1.0236 |  |  |  |  | 0.052994 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000083 | APPLE HILL 21021532 | Circuit Segment | Distribution | 46.0637 | Top 20% | Tier 2 | 31.4372 | 26.2948 | 5.1423 |  | 0.16376 | 0.060503 | 0.074967 | 0.028285 |  | 10.3192 |  |  | 2.0803 |  |  |  |  | 3.062 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000084 | CALAVERAS CEMENT 110147968 | Circuit Segment | Distribution | 17.4847 | Top 20% | Tier 2 | 30.7825 | 30.4048 | 0.37764 |  | 0.040766 | 0.02144 | 0.011659 | 0.0076668 |  | 47.9307 |  |  | 0.29887 |  |  |  |  | 0.078774 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000085 | WILDWOOD 1101384582 | Circuit Segment | Distribution | 4.5387 | Top 20% | Tier 2 | 30.7606 | 30.7594 | 0.0012027 |  | 0.01155 | 0.0019628 | 0.0067979 | 0.0027893 |  | 171.1448 |  |  | 0.00096625 |  |  |  |  | 0.00023647 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000086 | SANTA YNEZ 1102320270 | Circuit Segment | Distribution | 21.2284 | Top 20% | Tier 2 | 30.7321 | 30.3443 | 0.38784 |  | 0.077777 | 0.043202 | 0.016673 | 0.017902 |  | 25.0723 |  |  | 0 |  |  |  |  | 0.38784 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000087 | FRENCH GULCH 11022902 | Circuit Segment | Distribution | 7.1023 | Top 20% | Tier 2 | 30.5736 | 30.5621 | 0.011534 |  | 0.024194 | 0.0077904 | 0.012194 | 0.00421 |  | 81.1784 |  |  | 0.0062473 |  |  |  |  | 0.0052866 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000088 | STANISLAUS 17011812 | Circuit Segment | Distribution | 23.3869 | Top 20% | Tier 2 | 30.5553 | 28.5064 | 2.0489 |  | 0.12244 | 0.046829 | 0.053344 | 0.022269 |  | 14.9618 |  |  | 0.88048 |  |  |  |  | 1.1684 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026
2150000089 | PERRY 110179696 | Circuit Segment | Distribution | 34.0965 | Top 20% | Tier 2 | 30.4315 | 30.2638 | 0.16767 |  | 0.091464 | 0.041426 | 0.035089 | 0.014949 |  | 21.2639 |  |  | 0 |  |  |  |  | 0.16767 | [5 empty] | Notes: 1) Column Header: BURN LIKELIHOOD - As described in Section 5 Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately 2) Column Header: WILDFIRE HAZARD INTENSITY - PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4. 3) Column Header: WILDFIRE EXPOSURE POTENTIAL, PSPS EXPOSURE POTENTIAL. PSPS VULNERABILITY- PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS. 4) Column Header: IGNITION LIKELIHOOD is scaled from WDRM v4 to historical CPUC reportable probabilities 5) Column Header: TOP-RISK CIRCUIT / SEGMENT / SPAN ID - Circuit segment HFTD mileage only 6) Column Header: WILDFIRE CONSEQUENCE - Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk 7) Column Header: INCLUSION REASON - PG&E reports out Top 20% which aligns with the 2026 – 2028 WMP. 8)For other columns not mentioned above, we are still developing capabilities to perform the analysis for these Headers. | PG&E | 2026