## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | REPORTING QUARTER | QUANTITATIVE ACTUAL PROGRESS Q1 | QUANTITATIVE ACTUAL PROGRESS Q1-2 | QUANTITATIVE ACTUAL PROGRESS Q1-3 | QUANTITATIVE ACTUAL PROGRESS Q1-4 | QUALITATIVE ACTUAL PROGRESS Q1 | QUALITATIVE ACTUAL PROGRESS Q1-2 | QUALITATIVE ACTUAL PROGRESS Q1-3 | QUALITATIVE ACTUAL PROGRESS Q1-4 | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Covered conductor installation | See coulumn I | Covered conductor utilizes conductors manufactured with an internal semiconducting layer and external insulating ultraviolet-resistant layer to provide incidental contact protection. The Covered Conductor program has the potential to raise the threshold for PSPS events to higher wind speeds compared to bare conductor. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.1 | WMP.455 | SDGE_Grid Design, Operations, and Maintainence_Covered Conductor Installation _WMP.455_2025 | 151 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | No | Miles |  | 2025 | 1 | 3.84 | [7 empty] | In Progress
1010000001 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Undergrounding of electric lines and/or equipment | See coulumn I | Strategic undergrounding converts overhead systems to underground, providing the dual benefits of nearly eliminating the risk of utility-caused wildfire and the need for PSPS events in these areas. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.2 | WMP.473 | SDGE_Grid Design, Operations, and Maintainence_Undergrounding of Electric Lines and/or Equipment _WMP.473_2025 | 153 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition | No | Miles |  | 2025 | 1 | 9.42 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000002 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Traditional overhead hardening | See coulumn I | Bare Conductor Hardening includes the replacement of wood poles with steel, replacement of conductor with high-strength bare conductor, and in some cases permanent removal of overhead facilities. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution overhead system hardening | 8.1.2.5.1 | WMP.475 | SDGE_Grid Design, Operations, and Maintainence_Traditional Overhead Hardening (Distribution) _WMP.475_2025 | 157 | Equipment ignition likelihood | No | Miles |  | 2025 | 1 | 0.11 | [7 empty] | In Progress
1010000003 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Traditional overhead hardening | See coulumn I | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission overhead hardening | 8.1.2.5.2 | WMP.543 | SDGE_Grid Design, Operations, and Maintainence_Traditional Overhead Hardening (Transmission) _WMP.543_2025 | 159 | Equipment ignition likelihood | No | Miles |  | 2025 | 1 | 0 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000004 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Traditional overhead hardening | See coulumn I | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission overhead hardening (distribution underbuild) | 8.1.2.5.2 | WMP.545 | SDGE_Grid Design, Operations, and Maintainence_Traditional Overhead Hardening (Distribution Underbuilt)_WMP.545_2025 | 159 | Equipment ignition likelihood | No | Miles |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000005 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Installation of system automation equipment | See coulumn I | Advanced Protection creates higher visibility and situational awareness in fire-prone areas, and allow for the implementation of new relay and automation standards in locations where protection coordination is difficult due to lower fault currents attributed to high impedance faults. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Advanced protection | 8.1.2.8.1 | WMP.463 | SDGE_Grid Design, Operations, and Maintainence_Installation of System Automation Equipment (Advanced Protection)_WMP.463_2025 | 163 | Equipment ignition likelihood | No | Circuits |  | 2025 | 1 | 2 | [7 empty] | In Progress
1010000006 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Installation of system automation equipment | See coulumn I | Early fault detection employs technologies such as Advance Radio Frequency Sensors (ARFS) and Power Quality (PQ) Meters to detect and prevent significant equipment failures before they occur. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Early fault detection | 8.1.2.8.2 | WMP.1195 | SDGE_Grid Design, Operations, and Maintainence_Installation of System Automation Equipment (EFD) _WMP.1195_2025 | 166 | Equipment ignition likelihood | No | Nodes |  | 2025 | 1 | 39 | [7 empty] | In Progress
1010000007 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Installation of system automation equipment | See coulumn I | The Distribution Communications Reliability Improvement (DCRI) program enables APP and EFD technologies as a reliable communication network is necessary for initiatives that require continuous communication. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution communications reliability improvements | 8.1.2.8.3 | WMP.549 | SDGE_Grid Design, Operations, and Maintainence_Installation of System Automation Equipment (LTE)_WMP.549_2025 | 170 | Wildfire hazard PSPS exposure potential | No | Base Stations |  | 2025 | 1 | 1 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000008 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | The SCADA Capacitors Maintenance and Replacement Program will detect and isolate issues before a capacitor rupture occurs, reducing the failure mode most likely to lead to an ignition. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Capacitor maintenance and replacement program (SCADA) | 8.1.4.3 | WMP.453 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (SCADA) _WMP.453_2025 | 213 | Equipment ignition likelihood | No | Capacitors |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000009 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | The Expulsion Fuse Replacement Program replaces existing expulsion fuses with new, more fire safe expulsion fuses that are approved by CAL FIRE. These new expulsion fuses reduce the discharge expelled into the atmosphere, reducing the chance of a fuse operation leading to an ignition. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Expulsion fuse replacement | 8.1.4.4 | WMP.459 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Expulsion Fuse Replacement) _WMP.459_2025 | 214 | Equipment ignition likelihood | No | Fuses |  | 2025 | 1 | 164 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000010 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | The Hotline Clamps (HLC) Replacement Program replaces HLC connections that are connected directly onto the overhead primary conductors with compression connections to eliminate the risk of the wire down failure and the associated wildfire risk. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Maintenance, repair, and replacement of connectors, including hotline clamps | 8.1.4.5 | WMP.464 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (HLC)_WMP.464_2025 | 216 | Equipment ignition likelihood | No | HLCs |  | 2025 | 1 | 90 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000011 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | Lightning Arrestors Replacement Program installs CAL FIRE-approved lightning arrestors to mitigate the impact of transient overvoltage on the electric system. CAL FIRE-approved lightning arrestors are equipped with an external device that operates prior to the arrestor overloading, dramatically reducing the potential of becoming an ignition source. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Lightning arrester removal and replacement | 8.1.4.6 | WMP.550 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Arrestors)_WMP.550_2025 | 218 | Equipment ignition likelihood | No | Arrestors |  | 2025 | 1 | 348 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000012 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | Avian Protection is aimed at improving reliability and reducing the risk of faults and wire-down events associated with avian contact that can lead to ignitions. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Avian protection | 8.1.2.10.1 | WMP.972 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Avian)_WMP.972_2025 | 171 | Contact by object ignition | No | Poles |  | 2025 | 1 | 270 | [7 empty] | Completed
1010000013 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | Wireless fault indicator technology is deployed to narrow the location of detected issues on the system. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Wireless Fault Indicators | 8.1.8.2 | WMP.449 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Wireless fault indicators)_WMP.449_2025 | 277 | Equipment ignition likelihood | No | WFIs |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000014 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | Strategic Pole Replacement targets high-risk poles located throughout the service territory that are gas treated (also known as Cellon treatment) and are set in concrete and steel reinforced, steel reinforced and set in soil, or set in soil, and are not being address by other programs such as Covered Conductor Hardening or Strategic Undergrounding. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Strategic pole replacement program | 8.1.2.10.2 | WMP.1189 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Pole Replacements)_WMP.1189_2025 | 173 | Equipment ignition likelihood | No | Poles |  | 2025 | 1 | 70 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000015 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See coulumn I | PSPS Sectionalizing Enhancement Program installs switches in strategic locations, improving the ability to isolate high-risk areas for potential de energization. For example, switches are installed on circuits that have significant sections undergrounded, allowing customers with this lower-risk infrastructure to remain energized during weather events. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | PSPS sectionalizing enhancements | 8.1.2.11.1 | WMP.461 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to mitigate or reduce PSPS events (PSPS Sectionalizing Enhancements)_WMP.461_2025 | 175 | PSPS exposure potential PSPS vulnerability | No | Switches |  | 2025 | 1 | 3 | [7 empty] | In Progress
1010000016 | SDG&E | 2025-05-01 | Project | 2023-01-01 | 2025-12-31 | Microgrids | See coulumn I | Microgrid backup generation and battery storage to reduce the impact of PSPS. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.7 | WMP.462 | SDGE_Grid Design & System Hardening_Microgrids_WMP.462_2025 | 161 | PSPS vulnerability | No | Microgrid |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000017 | SDG&E | 2025-05-01 | Project | 2020-07-01 | 2025-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See coulumn I | This program assists backcountry residences, businesses, and local communities in the HFTD by providing a fixed installation backup generator, or a solar panel and battery backup system to keep customers energized during PSPS. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Standby power (fixed power backup) | 8.1.2.11.2 | WMP.468 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to mitigate or reduce PSPS events (Standby Power)_WMP.468_2025 | 175 | PSPS vulnerability | No | Generators |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000018 | SDG&E | 2025-05-01 | Project | 2020-07-01 | 2025-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See coulumn I | The Resiliency Grant Programs offer portable battery units with solar charging capacity to provide vulnerable customers with a means to keep small devices and appliances charged and powered during PSPS events. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Generator grant program | 8.1.2.11.3 | WMP.466 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to mitigate or reduce PSPS events (Generator Grant Program)_WMP.466_2025 | 177 | PSPS vulnerability | No | Generators |  | 2025 | 1 |  |  |  |  | Vendor continued to deliver batteries and provide emergency deliveries to qualifying impacted customers during January PSPS events. Finalized 2025 pricing and updated scope of work. Eligible customer list generated for 2025. 2025 system configuration updates currently in process for completion in early Q2. |  |  |  | In Progress
1010000019 | SDG&E | 2025-05-01 | Project | 2020-07-01 | 2025-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See coulumn I | The Resiliency Assistance Programs focus on enhancing resiliency for customers who reside in the HFTD and may be impacted by PSPS events. The program offers a rebate to customers providing a 70-to-90 percent discount on average portable generator models to mitigate the impacts of PSPS. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Generator assistance program | 8.1.2.11.4 | WMP.467 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to mitigate or reduce PSPS events (Generator Assistance Program)_WMP.467_2025 | 179 | PSPS vulnerability | No | Generators |  | 2025 | 1 |  |  |  |  | Completed analysis for Qualified Product List and update. Launched marketing and outreach communications. Generated customer eligibility lists based on data parameters. Program go-live - systems and processes active for customer participation. |  |  |  | In Progress
1010000020 | SDG&E | 2025-05-01 | Program |  |  | Distribution overhead detailed inspections | See coulumn I | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.1 | WMP.478 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Detailed Inspections of Distribution Electric Lines and Equipment)_WMP.478_2025 | 182 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 6327 | [7 empty] | In Progress
1010000021 | SDG&E | 2025-05-01 | Program |  |  | Transmission overhead detailed inspections | See coulumn I | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.2 | WMP.479 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Detailed Inspections of Transmission Electric Lines and Equipment) _WMP.479_2025 | 185 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 349 | [7 empty] | In Progress
1010000022 | SDG&E | 2025-05-01 | Program |  |  | Distribution infrared inspections | See coulumn I | Perform infrared inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.3 | WMP.481 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Infrared Inspections of Distribution Electric Lines and Equipment)_WMP.481_2025 | 188 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000023 | SDG&E | 2025-05-01 | Program |  |  | Transmission infrared inspections | See coulumn I | Perform infrared inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.4 | WMP.482 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Infrared Inspections of Transmission Electric Lines and Equipment)_WMP.482_2025 | 189 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000024 | SDG&E | 2025-05-01 | Program |  |  | Distribution wood pole intrusive inspections | See coulumn I | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.5 | WMP.483 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Distribution Wood Pole Intrusive Pole Inspections)_WMP.483_2025 | 192 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 215 | [7 empty] | In Progress
1010000025 | SDG&E | 2025-05-01 | Program |  |  | Transmission wood pole intrusive inspections | See coulumn I | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.6 | WMP.1190 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Wood Pole Trans)_WMP.1190_2025 | 194 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 21 | [7 empty] | In Progress
1010000026 | SDG&E | 2025-05-01 | Program |  |  | Drone assessments | See coulumn I | Perform drone inspections on highest risk structures in the HFTD and WUI areas. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.7 | WMP.552 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Distribution Drone Assessments)_WMP.552_2025 | 194 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 0 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000027 | SDG&E | 2025-05-01 | Program |  |  | Distribution overhead patrol inspections | See coulumn I | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.8 | WMP.488 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Distribution overhead Patrol Inspections)_WMP.488_2025 | 200 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 35253 | [7 empty] | In Progress
1010000028 | SDG&E | 2025-05-01 | Program |  |  | Transmission overhead patrol inspections | See coulumn I | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.9 | WMP.489 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Transmission Overhead Patrol)_WMP.489_2025 | 202 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 6935 | [7 empty] | In Progress
1010000029 | SDG&E | 2025-05-01 | Program |  |  | Transmission 69kV tier 3 visual inspections | See coulumn I | Perform supplemental inspections on all 69kV tielines in Tier 3 prior to wildfire season | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.10 | WMP.555 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Transmission 69kV Tier 3)_WMP.555_2025 | 206 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000030 | SDG&E | 2025-05-01 | Program |  |  | Substation patrol inspections | See coulumn I | Perform substation patrols, as scheduled, to reduce the risk of equipment failure and to manage vegetation hazards within the substation. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.11 | WMP.492 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Substation Patrol)_WMP.492_2025 | 207 | Equipment ignition likelihood | No | Substations |  | 2025 | 1 | 94 | [7 empty] | In Progress
1010000031 | SDG&E | 2025-05-01 | Program |  |  | Quality assurance / quality control of transmission inspections | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.1 | WMP.1191 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Secondary Trans)_WMP.1191_2025 | 226 | Equipment ignition likelihood | Yes | Findings |  | 2025 | 1 | 100% | [7 empty] | In Progress
1010000032 | SDG&E | 2025-05-01 | Program |  |  | Quality assurance / quality control of distribution detailed inspections | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.2 | WMP.491 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Distribution Detailed)_WMP.491_2025 | 226 | Equipment ignition likelihood | No | Structures |  | 2025 | 1 | 9 | [7 empty] | In Progress
1010000033 | SDG&E | 2025-05-01 | Program |  |  | Quality assurance / quality control of distribution drone assessments | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.3 | WMP.1192 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Distribution Drone)_WMP.1192_2025 | 227 | Equipment ignition likelihood | No | Structures |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000034 | SDG&E | 2025-05-01 | Program |  |  | Quality assurance / quality control of wood pole intrusive (transmission and distribution) | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.4 | WMP.1193 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Wood Pole Dist &Trans)_WMP.1193_2025 | 227 | Equipment ignition likelihood | No | Structures |  | 2025 | 1 | 871 | [7 empty] | Completed
1010000035 | SDG&E | 2025-05-01 | Program |  |  | Quality assurance / quality control of substation inspections | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.5 | WMP.1194 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Periodic Review)_WMP.1194_2025 | 227 | Equipment ignition likelihood | No | Structures |  | 2025 | 1 | 5 | [7 empty] | Planned
1010000036 | SDG&E | 2025-05-01 | Program |  |  | Detailed inspections | See coulumn I | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation Management and Inspections | Vegetation Management Inspections |  | 8.2.2.1 | WMP.494 | SDGE_Vegetation Management and Inspection_Vegetation Management Inspection Program (Detailed inspections of vegetation around distribution electric lines and equipment)_WMP.494_2025 | 260 | Wildfire hazard | No | Inspections |  | 2025 | 1 | 136645 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000037 | SDG&E | 2025-05-01 | Program |  |  | Off-cycle patrol | See coulumn I | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation Management and Inspections | Vegetation Management Inspections |  | 8.2.2.2 | WMP.508 | SDGE_Vegetation Management and Inspection_Vegetation Management Inspection Program (Off-Cycle)_WMP.508_2025 | 265 | Contact from vegetation ignition likelihood | No | VMAs |  | 2025 | 1 | 31 | [7 empty] | In Progress
1010000038 | SDG&E | 2025-05-01 | Program |  |  | Fuels management | See coulumn I | Wildland fuel reduction involves the thinning, pruning, and in some cases, removal of vegetation for the purpose of minimizing source material that could ignite and propagate a wildfire. | Vegetation Management and Inspections | Integrated Vegetation Management |  | 8.2.3 | WMP.497 | SDGE_Vegetation Management and Inspection_Fuel Management (slash) _WMP.497_2025 | 273 | Contact from vegetation ignition likelihood | No | Poles Cleared |  | 2025 | 1 | 62 | [7 empty] | In Progress
1010000039 | SDG&E | 2025-05-01 | Program |  |  | Pole clearing (brushing) | See coulumn I | Pole brushing is a fire prevention measure involving the removal of vegetation at the base of poles that carry specific types of electrical hardware that could cause sparking or molten material to fall to the ground. | Vegetation Management and Inspections | Pole Clearing |  | 8.2.3.1 | WMP.512 | SDGE_Vegetation Management and Inspection_Pole Clearing (Brushing)_WMP.501_2025 | 270 | Wildfire hazard | No | Poles Brushed |  | 2025 | 1 | 12710 | [7 empty] | Delayed | Requested target change in Petition to Amend, submitted on April 10, 2025.
1010000040 | SDG&E | 2025-05-01 | Program |  |  | Clearance | See coulumn I | Vegetation Management defines enhanced clearances as greater than or equal to 12 feet at time of trim, which is the CPUC-recommended post-trim clearance for distribution voltages in the HFTD. SDG&E aims to achieve clearances up to 25 feet, where feasible, to achieve the optimal risk mitigation. | Vegetation Management and Inspections | Pruning and Removal |  | 8.2.3.3 | WMP.501 | SDGE_Vegetation Management and Inspection_Clearance (Achieve clearances around electric lines and equipment) _WMP.512_2025 | 274 | Wildfire hazard | No | Trees Trimmed or Removed |  | 2025 | 1 | 1462 | [7 empty] | In Progress
1010000041 | SDG&E | 2025-05-01 | Program |  |  | Quality assurance / quality control vegetation management | See coulumn I | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 8.2.5 | WMP.505 | SDGE_Vegetation Management and Inspection_Quality assurance / quality control_WMP.505_2025 | 280 | Contact from vegetation ignition likelihood | No | Inspections |  | 2025 | 1 | 27% | [7 empty] | In Progress
1010000042 | SDG&E | 2025-05-01 | Program |  |  | Weather Station Maintenance and Calibration | See coulumn I | Weather Station Maintenance and Calibration is dedicated to the maintenance and calibration of weather stations. The Weather Station Network strategically positions weather stations to transmit data on sustained wind speed, wind gust, wind direction, temperature, and humidity every 10 minutes using cellular and spread spectrum communications. | Situational Awareness and Forecasting | Weather Forecasting |  | 8.3.2.4.1 | WMP.1430 | SDGE_Situational Awareness and Forecasting_Weather Station Maintenance and Calibration_WMP.1430_2025 | 248 | Wildfire vulnerability Wildfire exposure potential | No | Weather Stations |  | 2025 | 1 | 53 | [7 empty] | In Progress
1010000043 | SDG&E | 2025-05-01 | Program |  |  | Air Quality Station Maintenance | See coulumn I | Air Quality Maintenance of the particulate sensors will include a scheduled monthly, quarterly, and annual inspection. Each visit will include a rigorous preventative maintenance to ensure accurate functioning of the sensors. | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | 8.3.2.1.3 | WMP.1431 | SDGE_Situational Awareness and Forecasting_Air Quality Station Maintenance_WMP.1431_2025 | 298 | Wildfire exposure potential | No | Sensors |  | 2025 | 1 | 48 | [7 empty] | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 4
1020000001 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 2
1020000002 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000003 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 35
1020000004 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 3
1020000005 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000006 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000007 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 28
1020000008 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000009 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000010 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 2
1020000011 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 164
1020000012 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000013 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000014 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000015 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 3
1020000016 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000017 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000018 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000019 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000020 | 1. Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000021 | 1. Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000022 | 1. Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 2
1020000023 | 1. Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 12
1020000024 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 4
1020000025 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 2
1020000026 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000027 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 34
1020000028 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 3
1020000029 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000030 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000031 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 28
1020000032 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000033 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000034 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 2
1020000035 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 152
1020000036 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000037 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000038 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000039 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000040 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000041 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000042 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000043 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000044 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000045 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000046 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000047 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 12
1020000048 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000049 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000050 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 2
1020000051 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000052 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000053 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000054 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000055 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000056 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 1
1020000057 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000058 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000059 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1020000060 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SDG&E | 2025 | 1 | 83
1020000061 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SDG&E | 2025 | 1 | 123
1020000062 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SDG&E | 2025 | 1 | 86
1020000063 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SDG&E | 2025 | 1 | 122
1020000064 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | SDG&E | 2025 | 1 | 77
1020000065 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | SDG&E | 2025 | 1 | 118
1020000066 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SDG&E | 2025 | 1 | 84
1020000067 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SDG&E | 2025 | 1 | 120
1020000068 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SDG&E | 2025 | 1 | 81
1020000069 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SDG&E | 2025 | 1 | 104
1020000070 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  |  | SDG&E | 2025 | 1 | 91
1020000071 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  |  | SDG&E | 2025 | 1 | 115
1020000072 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000073 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000074 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 3
1020000075 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 3
1020000076 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000077 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 3
1020000078 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000079 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000080 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000081 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000082 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000083 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000084 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 545
1020000085 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 1259
1020000086 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 122
1020000087 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 408
1020000088 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 318
1020000089 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 510
1020000090 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 315
1020000091 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 504
1020000092 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 378
1020000093 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 416
1020000094 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 313
1020000095 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 429
1020000096 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 1
1020000097 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 1
1020000098 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 1
1020000099 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 1
1020000100 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 1
1020000101 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 1
1020000102 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 416
1020000103 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 416
1020000104 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000105 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 0
1020000106 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 105
1020000107 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 1 | 105
1020000108 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2025 | 1 | 13603
1020000109 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2025 | 1 | 54
1020000110 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2025 | 1 | 2895
1020000111 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2025 | 1 | 90
1020000112 | 8. Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  |  | SDG&E | 2025 | 1 | 7.9
1020000113 | 9. Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | SDG&E | 2025 | 1 | 0
1020000114 | 9. Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | SDG&E | 2025 | 1 | 0
1020000115 | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | SDG&E | 2025 | 1 | 0
1020000116 | 11. Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | SDG&E | 2025 | 1 | 0
1020000117 | 11. Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | SDG&E | 2025 | 1 | 0
1020000118 | 12. Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | SDG&E | 2025 | 1 | 0.08
1020000119 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000120 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000121 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000122 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000123 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000124 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000125 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000126 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000127 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000128 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000129 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 0
1020000130 | 13. Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 1 | 3
1020000131 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000132 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 7211
1020000133 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000134 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 10785
1020000135 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000136 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000137 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000138 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 4189
1020000139 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000140 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000141 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000142 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 163
1020000143 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000144 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 310.4085
1020000145 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000146 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 442.1583
1020000147 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000148 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000149 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000150 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 165.718
1020000151 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000152 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000153 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000154 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000155 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000156 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000157 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000158 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000159 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000160 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000161 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000162 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000163 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000164 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000165 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000166 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000167 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000168 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000169 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000170 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 7
1020000171 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000172 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000173 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000174 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 99
1020000175 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000176 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000177 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000178 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 1
1020000179 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000180 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000181 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000182 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000183 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000184 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000185 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000186 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000187 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000188 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000189 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000190 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000191 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000192 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 8056
1020000193 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000194 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 9201
1020000195 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000196 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000197 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000198 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 2138
1020000199 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000200 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000201 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000202 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 52
1020000203 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000204 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 340.0688
1020000205 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000206 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 330.1534
1020000207 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000208 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000209 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000210 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 99.3348
1020000211 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000212 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000213 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000214 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000215 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000216 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000217 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000218 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000219 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000220 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000221 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000222 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 1
1020000223 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000224 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000225 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000226 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000227 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000228 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000229 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000230 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 10
1020000231 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000232 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000233 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000234 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 43
1020000235 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000236 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000237 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000238 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 2
1020000239 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000240 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000241 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000242 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000243 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000244 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000245 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000246 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000247 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000248 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000249 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000250 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000251 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000252 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 734
1020000253 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000254 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 33186
1020000255 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000256 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000257 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000258 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 6154
1020000259 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000260 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000261 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000262 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 4061
1020000263 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000264 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 39.2193
1020000265 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000266 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 722.5945
1020000267 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000268 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000269 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000270 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 110.7896
1020000271 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000272 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000273 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000274 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000275 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000276 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000277 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000278 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 5
1020000279 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000280 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000281 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000282 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 28
1020000283 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000284 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000285 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000286 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000287 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000288 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000289 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000290 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 91
1020000291 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000292 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000293 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000294 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 656
1020000295 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000296 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000297 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000298 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 55
1020000299 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000300 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000301 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000302 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000303 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000304 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000305 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000306 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000307 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000308 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000309 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000310 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000311 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000312 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 4059
1020000313 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000314 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000315 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000316 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000317 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000318 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 198
1020000319 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000320 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000321 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000322 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 11
1020000323 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000324 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 564.6035
1020000325 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000326 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000327 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000328 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000329 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000330 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 28.9733
1020000331 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000332 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000333 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000334 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000335 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000336 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000337 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000338 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000339 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000340 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000341 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000342 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000343 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000344 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000345 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000346 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000347 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000348 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 2
1020000349 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000350 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000351 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000352 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000353 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000354 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 5
1020000355 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000356 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000357 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000358 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000359 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000360 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000361 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000362 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000363 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000364 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000365 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000366 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 3
1020000367 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000368 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000369 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000370 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000371 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000372 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 1724
1020000373 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000374 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000375 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000376 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000377 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000378 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 72
1020000379 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000380 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000381 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000382 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000383 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000384 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 190.6186
1020000385 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000386 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000387 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000388 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000389 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000390 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 17.6328
1020000391 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000392 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000393 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000394 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000395 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000396 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000397 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000398 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000399 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000400 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000401 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000402 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000403 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000404 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000405 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000406 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000407 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000408 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000409 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000410 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000411 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000412 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000413 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000414 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 7
1020000415 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000416 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000417 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000418 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000419 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000420 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000421 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000422 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000423 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000424 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000425 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000426 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000427 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000428 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000429 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000430 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000431 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000432 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 5972
1020000433 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000434 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 14
1020000435 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000436 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 9
1020000437 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000438 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 767
1020000439 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000440 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000441 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000442 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 1 | 80
1020000443 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000444 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 491.779
1020000445 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000446 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 26.2456
1020000447 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000448 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 1.699
1020000449 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000450 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 120.8097
1020000451 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000452 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000453 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 1
1020000454 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 1 | 0
1020000455 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000456 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000457 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000458 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000459 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000460 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000461 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000462 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 1
1020000463 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000464 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000465 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000466 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000467 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000468 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 3
1020000469 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000470 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000471 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000472 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 3
1020000473 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000474 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 118
1020000475 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000476 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000477 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000478 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000479 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000480 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000481 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000482 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000483 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000484 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 1
1020000485 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000486 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 2
1020000487 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000488 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000489 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 1
1020000490 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 1 | 0
1020000491 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000492 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000493 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000494 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000495 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000496 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000497 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000498 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000499 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000500 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000501 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000502 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000503 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000504 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000505 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000506 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 42
1020000507 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000508 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000509 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000510 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 66
1020000511 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 170
1020000512 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000513 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000514 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 2
1020000515 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000516 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000517 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000518 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000519 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000520 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000521 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000522 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000523 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000524 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000525 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000526 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000527 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000528 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000529 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000530 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000531 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000532 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000533 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000534 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 1
1020000535 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000536 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000537 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000538 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000539 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000540 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000541 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000542 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 8
1020000543 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000544 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000545 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000546 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 32
1020000547 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 135
1020000548 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000549 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000550 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 1
1020000551 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000552 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000553 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000554 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000555 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000556 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000557 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000558 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000559 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000560 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000561 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000562 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000563 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000564 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000565 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000566 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 5
1020000567 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000568 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000569 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000570 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 28
1020000571 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000572 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000573 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000574 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000575 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000576 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000577 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000578 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 142
1020000579 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000580 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000581 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000582 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 330
1020000583 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 5
1020000584 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000585 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000586 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 68
1020000587 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000588 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000589 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000590 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000591 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000592 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000593 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000594 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000595 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000596 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000597 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000598 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000599 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000600 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000601 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000602 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000603 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000604 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000605 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000606 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000607 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000608 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000609 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000610 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000611 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000612 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 2
1020000613 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000614 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000615 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000616 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000617 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000618 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 19
1020000619 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000620 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000621 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000622 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000623 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000624 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000625 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000626 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000627 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000628 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000629 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000630 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 2
1020000631 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000632 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000633 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000634 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000635 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000636 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000637 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000638 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000639 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000640 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000641 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000642 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000643 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000644 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000645 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000646 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000647 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000648 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000649 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000650 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000651 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000652 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000653 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000654 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 4
1020000655 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000656 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000657 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000658 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000659 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000660 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000661 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000662 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000663 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000664 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000665 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000666 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000667 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000668 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000669 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000670 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000671 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000672 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000673 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000674 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000675 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000676 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000677 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000678 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000679 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000680 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000681 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000682 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000683 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000684 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000685 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000686 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000687 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000688 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000689 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000690 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 63
1020000691 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000692 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000693 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000694 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000695 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000696 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000697 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000698 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000699 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000700 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000701 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000702 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 1
1020000703 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000704 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000705 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 1
1020000706 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 1 | 0
1020000707 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000708 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000709 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000710 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 45905
1020000711 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000712 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000713 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000714 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 48751
1020000715 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000716 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000717 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000718 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000719 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000720 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000721 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000722 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 233
1020000723 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000724 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000725 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000726 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 34615
1020000727 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000728 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000729 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000730 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 22167
1020000731 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000732 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000733 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000734 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000735 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000736 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000737 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000738 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 145
1020000739 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000740 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000741 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000742 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 53848
1020000743 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000744 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000745 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000746 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000747 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000748 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000749 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000750 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000751 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000752 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000753 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000754 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000755 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000756 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000757 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000758 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 643
1020000759 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000760 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000761 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000762 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 1672
1020000763 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000764 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000765 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000766 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000767 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000768 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000769 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000770 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000771 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000772 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000773 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000774 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 98
1020000775 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000776 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000777 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000778 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 54
1020000779 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000780 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000781 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000782 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000783 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000784 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000785 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000786 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000787 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000788 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000789 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000790 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 1 | 1536
1020000791 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000792 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000793 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000794 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 1 | 0
1020000795 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000796 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000797 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000798 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000799 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000800 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000801 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000802 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 1
1020000803 | 17. Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | Not Applicable | SDG&E | 2025 | 1

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | Number of High FPI days (elevated or extreme FPI) | Number of High FPI days (elevated or extreme FPI) | To track the number of days that wildfire weather conditions observed | To evaluate the frequency of the risk event and normalize it for comparison over historical years to quantify the performance | No | Days |  |  | SDG&E | 2025 | 1 | 24
1030000001 | Number of RFW days | Number of RFW days | To track the number of days that wildfire weather conditions observed | To evaluate the frequency of the risk event and normalize it for comparison over historical years to quantify the performance | No | Days |  |  | SDG&E | 2025 | 1 | 15
1030000002 | Vegetation caused ignitons in HFTD with elevated or higher FPI | Vegetation caused ignitons in HFTD with elevated or higher FPI | To track the number of vegetation caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000003 | Vegetation caused ignitons in HFTD with RFW | Vegetation caused ignitons in HFTD with RFW | To track the number of vegetation caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000004 | Equipment caused ignitions in HFTD with elevated or higher FPI | Equipment caused ignitions in HFTD with elevated or higher FPI | To track the number of equipment caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000005 | Equipment caused ignitions in HFTD with RFW | Equipment caused ignitions in HFTD with RFW | To track the number of equipment caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000006 | Balloons caused ignitions in HFTD with elevated or higher FPI | Balloons caused ignitions in HFTD with elevated or higher FPI | To track the number of bolloon caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000007 | Balloons caused ignitions in HFTD with RFW | Balloons caused ignitions in HFTD with RFW | To track the number of balloon caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000008 | Vehicles caused ignitions in HFTD with elevated or higher FPI | Vehicles caused ignitions in HFTD with elevated or higher FPI | To track the number of vehicles caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000009 | Vehicles caused ignitions in HFTD with RFW | Vehicles caused ignitions in HFTD with RFW | To track the number of vehicles caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000010 | Equipment caused ignition rate in HFTD during high FPI | Equipment caused ignition rate in HFTD during high FPI | To track ignition rate during elevated or extreme wildfire weather condition | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions per high FPI day |  |  | SDG&E | 2025 | 1 | 0
1030000011 | CPUC reportable secondary igntions | CPUC reportable secondary igntions | To correctly categorize and count the ignitions that are not transmission or distribution related | n/a | No | Ignitions |  |  | SDG&E | 2025 | 1 | 0
1030000012 | Vegetation caused outages in HFTD with Elevated FPI | Vegetation caused outages in HFTD with Elevated FPI | To track the number of vegetation caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 1 | 0
1030000013 | Vegetation caused outages in HFTD with RFW | Vegetation caused outages in HFTD with RFW | To track the number of vegetation caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 1 | 0
1030000014 | Overhead faults on circuits in HFTD with Elevated or higher FPI | Overhead faults on circuits in HFTD with Elevated or higher FPI | To track the number of all overhead faults that are controllable during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 1 | 0
1030000015 | Overhead faults on circuits in HFTD with RFW | Overhead faults on circuits in HFTD with RFW | To track the number of all overhead faults that are controllable during RFW wildfire weather conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 1 | 0
1030000016 | Energized wire down events in HFTD with Elevated or higher FPI | Energized wire down events in HFTD with Elevated or higher FPI | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 1 | 0
1030000017 | Energized wire down events in HFTD with RFW | Energized wire down events in HFTD with RFW | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 1 | 0
1030000018 | Number of non-CALFIRE rated fuse operations in HFTD with Elevated or higher FPI | Number of non-CALFIRE rated fuse operations in HFTD with Elevated or higher FPI | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 1 | 0
1030000019 | Number of non-CALFIRE rated fuse operations in HFTD with RFW | Number of non-CALFIRE rated fuse operations in HFTD with RFW | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 1 | 0
1030000020 | Overhead fault rate in HFTD during High FPI | Overhead fault rate in HFTD during High FPI | To evaluate the performance of risk reduction from overall mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Overhead faults per high FPI day |  |  | SDG&E | 2025 | 1 | 1.13
1030000021 | Near Miss Reporting | Near Miss Reporting | Track safety related incidents | To evaluate and assess the safety culture | No | Near miss events reported |  |  | SDG&E | 2025 | 1 | 96
1030000022 | Safety Observations | Safety Observations | Track safety related incidents | To evaluate and assess the safety culture | No | Observations performed |  |  | SDG&E | 2025 | 1 | 4221
1030000023 | Percent of customers being de-energized on PSPS circuits | Percent of customers being de-energized on PSPS circuits | To track the scope of PSPS events | To evaluate the isolation of the de-energization given weather events | No | percent |  |  | SDG&E | 2025 | 1 | 58.03%
1030000024 | Number of circuits de-engergized | Number of circuits de-engergized | To track the scale of PSPS events | To evaluate the scale of the de-energization given weather events | No | circuits |  |  | SDG&E | 2025 | 1 | 64
1030000025 | Communication success rate of weather stations | Communication success rate of weather stations | To track the weather station performance | To ensure the effectiveness of situational awareness tools | Yes | percent |  |  | SDG&E | 2025 | 1 | 99.14
1030000026 | Post processing success rate - WRF simulations | Post processing success rate - WRF simulations | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | Yes | percent |  |  | SDG&E | 2025 | 1 | 100
1030000027 | Post processing success rate - ML gust model | Post processing success rate - ML gust model | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | No | percent |  |  | SDG&E | 2025 | 1 | 100
1030000028 | Post processing success rate - SAWTI | Post processing success rate - SAWTI | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | No | percent |  |  | SDG&E | 2025 | 1 | 93.2
1030000029 | Post processing success rate - FPI | Post processing success rate - FPI | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | No | percent |  |  | SDG&E | 2025 | 1 | 99.4
1030000030 | Post processing success rate - OPI | Post processing success rate - OPI | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | No | percent |  |  | SDG&E | 2025 | 1 | 100
1030000031 | Percentage of community partners participating in local wildfire mitigation planning (in territory) | Percentage of community partners participating in local wildfire mitigation planning (in territory) | To track engagement and preparedness for PSPS activation | To ensure the effectiveness of preparedness of external partners | No | percent |  |  | SDG&E | 2025 | 1 | 100
1030000032 | Percentage of Wildfire/PSPS events followed by an After-Action Review or feedback process | Percentage of Wildfire/PSPS events followed by an After-Action Review or feedback process | To track the after action review and feedback | To ensure the effectiveness of preparedness | No | percent |  |  | SDG&E | 2025 | 1 | 100
1030000033 | Percentage of individuals with AFN who were aware of what support and resources were available to them during a PSPS event. | Percentage of individuals with AFN who were aware of what support and resources were available to them during a PSPS event. | To track engagement and preparedness for PSPS activation | To ensure the effectiveness of preparedness | No | percent |  |  | SDG&E | 2025 | 1 | 60
1030000034 | Percentage of individuals with AFN who were able to use necessary medical equipment to maintain necessary life functions for the duration of any PSPS event that affected them | Percentage of individuals with AFN who were able to use necessary medical equipment to maintain necessary life functions for the duration of any PSPS event that affected them | To track engagement and preparedness for PSPS activation | To ensure the effectiveness of preparedness | No | percent |  |  | SDG&E | 2025 | 1 | 58
1030000035 | Percentage of individuals who utilized mitigation services and reported they were satisfied with the level of support | Percentage of individuals who utilized mitigation services and reported they were satisfied with the level of support | To track engagement and preparedness for PSPS activation | To ensure the effectiveness of preparedness | No | percent |  |  | SDG&E | 2025 | 1 | 91
1030000036 | Percentage of customers notified prior to a PSPS event impacting them | Percentage of customers notified prior to a PSPS event impacting them | To track the performance of notifications for PSPS activation | To ensure the effectiveness of preparedness | No | percent |  |  | SDG&E | 2025 | 1 | 97

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 2708024
1040000001 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 2618201
1040000002 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 2100634
1040000003 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 771817
1040000004 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 439790
1040000005 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 343239
1040000006 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 1209272
1040000007 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 1258728
1040000008 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 970323
1040000009 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 344186
1040000010 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 218498
1040000011 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 166896
1040000012 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 286554
1040000013 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 329718
1040000014 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 124766
1040000015 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 76860
1040000016 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 59200
1040000017 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 19975
1040000018 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 39711.79
1040000019 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 37497.9
1040000020 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 54086
1040000021 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 13670.93
1040000022 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 7718.54
1040000023 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 1 | 10662.05

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 5
1050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 3
1050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 1
1050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 1
1050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 5
1050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 6
1050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 12
1050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 16
1050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 5
1050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 7
1050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 3
1050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 12
1050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 5
1050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 6
1050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 8
1050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 2
1050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 12
1050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 5
1050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 9
1050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 4
1050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 4
1050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 8
1050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 4
1050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2025 | 1
1050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2025 | 1
1050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2025 | 1
1050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 7
1050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 5
1050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 4
1050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 1
1050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 1
1050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 4
1050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 1
1050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 32
1050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 9
1050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 10
1050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 8
1050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 5
1050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  |  | SDG&E | 2025 | 1 | 0
1050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  |  | SDG&E | 2025 | 1 | 1
1050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  |  | SDG&E | 2025 | 1 | 0

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 1
1060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 1
1060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 1
1060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 1
1060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 1
1060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 1
1060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 1
1060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 1
1060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 1
1060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 1
1060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 1
1060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 1
1060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 1
1060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 1
1060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 1
1060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 1
1060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 1
1060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 1
1060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0
1060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  |  |  | SDG&E | 2025 | 1 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 429.8464
1070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 2100.2731
1070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 137.0936
1070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 136.858
1070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 34.832
1070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 109.2259
1070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 98.4797
1070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 87.8951
1070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 835.5487
1070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 579.8877
1070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 20.3169
1070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 151.9375
1070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 5.3559
1070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.098864
1070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 651.065
1070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 804.4352
1070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 10.4462
1070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 109.1578
1070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 150.9227
1070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 308.1589
1070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 38.4715
1070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 91.3159
1070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 22.8058
1070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 45.5332
1070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 79.5692
1070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 106.6742
1070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 422.9918
1070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 23.4249
1070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 23.8494
1070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 232.0983
1070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.3053
1070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 11.5121
1070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 2090.7962
1070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 5131.7987
1070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 440.3305
1070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 711.4644
1070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 17.8589
1070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 35.6517
1070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 937.1089
1070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 218.8013
1070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 865.4354
1070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 309.64
1070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 3.6754
1070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 9.8407
1070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 1.3741
1070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 363.4934
1070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 206.9763
1070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 6.7146
1070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 24.9259
1070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 24.5908
1070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 70.1184
1070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 14.282
1070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 20.7046
1070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.10379
1070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 13.4377
1070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 2.0636
1070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 12.2184
1070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 7.8905
1070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 1.5518
1070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 3.8419
1070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 2.1501
1070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 3025
1070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 15216
1070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 736
1070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 2449
1070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 3
1070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 136
1070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 849
1070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 350
1070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 1049
1070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 955
1070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 11
1070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 85
1070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 5
1070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 0
1070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 471
1070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 803
1070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 42
1070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 1 | 90
1070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 203864
1070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 896283
1070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 37003
1070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 39479
1070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 1002
1070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 1672
1070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 67960
1070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 17338
1070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 58729
1070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 23107
1070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 259
1070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 493
1070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 102
1070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 3
1070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 18230
1070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 8146
1070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 924
1070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 1 | 891
1070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 14849
1070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 94925
1070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 4702
1070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 24960
1070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 101
1070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 525
1070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 4353
1070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 2478
1070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 5180
1070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 4243
1070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 34
1070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 221
1070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 17
1070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 0
1070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 2260
1070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 2657
1070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 150
1070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 1 | 384
1070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 48351
1070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 307022
1070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 4586
1070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 4018
1070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 298
1070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 435
1070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 16589
1070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 6778
1070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 9680
1070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 3612
1070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 96
1070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 173
1070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 28
1070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 1
1070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 5652
1070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 2230
1070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 39
1070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 1 | 151
1070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 12
1070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 69
1070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 4
1070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 23
1070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 3
1070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 2
1070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 7
1070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 4
1070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 18
1070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 1
1070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 11
1070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 1
1070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 3
1070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 14
1070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 3
1070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 2
1070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 2
1070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 6
1070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 16
1070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 50
1070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 1
1070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 7
1070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 12
1070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 95
1070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 3
1070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 7

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 37.9263
1080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 34.0042
1080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -38.6312
1080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -36.228
1080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -4.2425e-09
1080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -3.0304e-08
1080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 6.8939
1080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 4.4907
1080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -6.8123
1080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -4.625
1080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 6.06e-10
1080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -0.0024621
1080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.15189
1080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 3.6364e-10
1080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 12.4362
1080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 43.2208
1080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -14.9992
1080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -49.8201
1080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 15.6377
1080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 15.5695
1080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -15.6494
1080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -15.5774
1080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -2.4243e-09
1080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 12.9146
1080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 12.9381
1080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -12.9146
1080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -12.9381
1080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 4.5454e-09
1080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 2.4587
1080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 4.1407
1080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -2.4587
1080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -4.1407
1080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 165.2288
1080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 200.7744
1080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -163.5341
1080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -173.7278
1080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -4.8485e-09
1080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -20.9521
1080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 173.5763
1080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 57.9667
1080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -172.4983
1080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -56.4225
1080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -1.2122e-10
1080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.1053
1080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 3.0303e-10
1080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 6.1513
1080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 11.985
1080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -5.292
1080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -10.2144
1080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -0.58263
1080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 1.7385
1080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.59835
1080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.096566
1080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -1.835
1080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.96174
1080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.59364
1080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -1.2942
1080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -0.59364
1080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | -0.64016
1080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.64035
1080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 4.5454e-10
1080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 1.3305
1090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 1.093
1090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.75106
1090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0.77712
1090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 1 | 0
1090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 1 | 0
1090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0
1090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 1 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | SDG&E | 2025 | 1 | 0
1100000001 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | SDG&E | 2025 | 1 | 0
1100000002 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | SDG&E | 2025 | 1 | 2
1100000003 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | SDG&E | 2025 | 1 | 0
1100000004 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2025 | 1 | 0
1100000005 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2025 | 1 | 0
1100000006 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2025 | 1 | 76
1100000007 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2025 | 1 | 0
1100000008 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | SDG&E | 2025 | 1 | 987213.2667
1100000009 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | SDG&E | 2025 | 1 | 230850.05
1100000010 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | SDG&E | 2025 | 1 | 454814.9833
1100000011 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | SDG&E | 2025 | 1 | 139277.3333
1100000012 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | SDG&E | 2025 | 1 | 2
1100000013 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | SDG&E | 2025 | 1 | 0
1100000014 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | SDG&E | 2025 | 1 | 2
1100000015 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | SDG&E | 2025 | 1 | 1
1100000016 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | SDG&E | 2025 | 1 | 3961.67
1100000017 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | SDG&E | 2025 | 1 | 0
1100000018 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | SDG&E | 2025 | 1 | 16172
1100000019 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | SDG&E | 2025 | 1 | 99.74
1100000020 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | SDG&E | 2025 | 1 | 2156357.77
1100000021 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | SDG&E | 2025 | 1 | 385580
1100000022 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | SDG&E | 2025 | 1 | 76284.37
1100000023 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | SDG&E | 2025 | 1 | 80.06
1100000024 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | SDG&E | 2025 | 1 | 15.85
1100000025 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | SDG&E | 2025 | 1 | 0.1422
1100000026 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | SDG&E | 2025 | 1 | 0.1113
1100000027 | 3. Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | SDG&E | 2025 | 1 | 2528
1100000028 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SDG&E | 2025 | 1 | 51488
1100000029 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SDG&E | 2025 | 1 | 3078
1100000030 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SDG&E | 2025 | 1 | 158277
1100000031 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SDG&E | 2025 | 1 | 11149
1100000032 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SDG&E | 2025 | 1 | 51371
1100000033 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SDG&E | 2025 | 1 | 3076
1100000034 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | SDG&E | 2025 | 1 | 0
1100000035 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | SDG&E | 2025 | 1 | 1142
1100000036 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | SDG&E | 2025 | 1 | 0.22186
1100000037 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | SDG&E | 2025 | 1 | 0.4336
1100000038 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | SDG&E | 2025 | 1 | 13.8021
1100000039 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | SDG&E | 2025 | 1 | 2.87
1100000040 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | SDG&E | 2025 | 1 | 8.79
1100000041 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | SDG&E | 2025 | 1 | 6.18
1100000042 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | SDG&E | 2025 | 1 | 23.4
1100000043 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | SDG&E | 2025 | 1 | 2

## Table 13
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED OR MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1130000000 | 130700 | Area Around Footer(s) | HFTD Tier 2 | Transmission | 2023-05-17 | 2025-05-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000001 | 133378 | Damper (Complete) | HFTD Tier 2 | Transmission | 2024-04-26 | 2025-04-25 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000002 | 130556 | Footings (Complete) | HFTD Tier 2 | Transmission | 2023-05-11 | 2025-05-10 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000003 | 136093 | Shoe (Complete) | HFTD Tier 2 | Transmission | 2024-08-07 | 2025-08-06 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000004 | 133531 | Bolt(s) | HFTD Tier 3 | Transmission | 2023-12-18 | 2025-12-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000005 | 137081 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2024-09-18 | 2025-09-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000006 | 136711 | Hardware | HFTD Tier 2 | Transmission | 2024-09-18 | 2025-09-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000007 | 136713 | Sign Warning (With Man) | HFTD Tier 2 | Transmission | 2024-09-18 | 2025-09-18 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000008 | 136725 | Other(Specify) | HFTD Tier 2 | Transmission | 2025-03-17 | 2026-03-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000009 | 132539 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000010 | 132858 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2023-12-18 | 2025-06-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000011 | 137273 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2024-12-07 | 2025-12-06 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000012 | 134451 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-04 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000013 | 134452 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2024-06-05 | 2025-06-04 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000014 | 138172 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-01-29 | 2026-01-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000015 | 131117 | Armor Rod - Shieldwire | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-08 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000016 | 132412 | Cold End Cotter Key(s) | HFTD Tier 3 | Transmission | 2023-12-29 | 2025-12-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000017 | 135728 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2024-11-14 | 2025-11-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000018 | 132311 | Shoe Pin-Bolt | HFTD Tier 3 | Transmission | 2023-12-29 | 2025-12-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000019 | 132502 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000020 | 132536 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000021 | 136702 | Other(Specify) | HFTD Tier 2 | Transmission | 2025-03-17 | 2026-03-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000022 | 133947 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2024-04-06 | 2026-04-04 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000023 | 137292 | Ground Connection | HFTD Tier 2 | Transmission | 2025-03-15 | 2026-03-15 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000024 | 137565 | Pole Top | HFTD Tier 2 | Transmission | 2025-01-29 | 2026-01-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000025 | 136726 | Other(Specify) | HFTD Tier 2 | Transmission | 2025-03-17 | 2026-03-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000026 | 132616 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000027 | 133152 | Footings (Complete) | HFTD Tier 3 | Transmission | 2023-10-29 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000028 | 134692 | Bond Wire | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000029 | 134634 | Pole Top | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000030 | 134635 | Bolt(s) | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000031 | 132517 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000032 | 137208 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2024-12-07 | 2025-12-06 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000033 | 132534 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000034 | 132481 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000035 | 137214 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2024-12-07 | 2025-12-06 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000036 | 132325 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000037 | 137225 | Guy Wire - OH | HFTD Tier 2 | Transmission | 2025-01-13 | 2026-01-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000038 | 132504 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000039 | 134777 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000040 | 134780 | Bond Wire | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000041 | 134779 | Pole Butt | HFTD Tier 2 | Transmission | 2024-05-31 | 2025-05-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000042 | 136698 | Other(Specify) | HFTD Tier 2 | Transmission | 2025-01-17 | 2026-01-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000043 | 132343 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000044 | 132345 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000045 | 130574 | Footings (Complete) | HFTD Tier 2 | Transmission | 2023-05-17 | 2025-05-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000046 | 132857 | Cold End Cotter Key(s) | HFTD Tier 3 | Transmission | 2023-12-18 | 2025-06-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000047 | 132873 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2023-12-15 | 2025-12-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000048 | 133565 | Footings (Complete) | HFTD Tier 2 | Transmission | 2023-12-13 | 2025-12-12 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000049 | 134748 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2024-06-21 | 2025-06-20 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000050 | 132596 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000051 | 132503 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000052 | 137832 | Complete Tower | HFTD Tier 2 | Transmission | 2025-03-03 | 2026-03-03 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000053 | 130991 | Bolted Spacer | HFTD Tier 2 | Transmission | 2023-10-08 | 2025-10-07 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000054 | 130990 | Aerial Marker Sphere(s) | HFTD Tier 2 | Transmission | 2023-10-08 | 2025-10-07 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000055 | 121727 | Insulators-Ceramic, Standard, 50K | HFTD Tier 3 | Transmission | 2020-12-15 | 2025-08-05 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000056 | 132587 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000057 | 136229 | Member (Steel Tower) | HFTD Tier 2 | Transmission | 2023-12-15 | 2025-06-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000058 | 132871 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2023-12-15 | 2025-06-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000059 | 132535 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000060 | 138171 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-01-29 | 2026-01-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000061 | 132624 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000062 | 134436 | Anchor Rods | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000063 | 134454 | Pole Butt | HFTD Tier 2 | Transmission | 2025-02-27 | 2026-02-27 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000064 | 132361 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000065 | 133412 | Footings (Complete) | HFTD Tier 2 | Transmission | 2024-01-29 | 2026-01-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000066 | 134415 | Bond Wire | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000067 | 137035 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2025-03-10 | 2026-03-09 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000068 | 133382 | Fiberglass Rod | HFTD Tier 3 | Transmission | 2024-01-20 | 2025-06-12 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000069 | 135729 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2024-11-14 | 2025-11-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000070 | 134693 | Guy Wire - OH | HFTD Tier 2 | Transmission | 2024-05-24 | 2025-05-23 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000071 | 134403 | Complete Steel Pole | HFTD Tier 2 | Transmission | 2024-07-09 | 2026-07-09 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000072 | 132480 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000073 | 134447 | Armor Rod Strand(s) | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000074 | 134637 | Shoe Pin-Bolt | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000075 | 130986 | Anti-Climb Barrier | HFTD Tier 2 | Transmission | 2024-04-25 | 2025-04-24 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000076 | 133377 | Bolt(s) | HFTD Tier 2 | Transmission | 2024-09-10 | 2025-09-09 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000077 | 133376 | Signs-Danger | HFTD Tier 2 | Transmission | 2024-09-10 | 2025-09-09 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000078 | 134154 | Aerial Light(s) | HFTD Tier 2 | Transmission | 2024-08-21 | 2025-08-20 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000079 | 138007 | Bond Wire | HFTD Tier 2 | Transmission | 2024-05-21 | 2025-05-21 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000080 | 132976 | Cold End Cotter Key(s) | HFTD Tier 3 | Transmission | 2023-12-18 | 2025-12-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000081 | 136918 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2025-02-21 | 2026-02-21 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000082 | 134974 | Insulators-Ceramic, Standard, 20K | HFTD Tier 2 | Transmission | 2024-10-17 | 2025-10-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000083 | 132362 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000084 | 133554 | Cold End Cotter Key(s) | HFTD Tier 3 | Transmission | 2023-12-18 | 2025-12-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000085 | 132516 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000086 | 137090 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2024-09-18 | 2025-09-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000087 | 136710 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2024-09-18 | 2025-09-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000088 | 136709 | Sign Warning (With Man) | HFTD Tier 2 | Transmission | 2024-09-18 | 2025-09-18 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000089 | 134503 | Complete Tower | HFTD Tier 2 | Transmission | 2025-03-04 | 2026-03-04 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000090 | 132329 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000091 | 136998 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2024-06-25 | 2025-06-25 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000092 | 136868 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2024-11-08 | 2025-11-07 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000093 | 137498 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000094 | 132520 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000095 | 136723 | Other(Specify) | HFTD Tier 2 | Transmission | 2025-03-17 | 2026-03-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000096 | 134622 | Shoe Pin-Bolt | HFTD Tier 2 | Transmission | 2024-06-18 | 2025-06-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000097 | 135531 | Conductor Strand(s) | HFTD Tier 2 | Transmission | 2024-08-21 | 2025-08-20 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000098 | 136667 | Other(Specify) | HFTD Tier 2 | Transmission | 2024-10-07 | 2025-10-06 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000099 | 134429 | Cross Arms | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000100 | 134431 | Pole Ground (Wire) | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000101 | 134430 | Fiberglass Rod | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000102 | 134432 | Jumper Strand(s) | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000103 | 134428 | Anchor Rods | HFTD Tier 2 | Transmission | 2024-05-29 | 2025-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000104 | 131178 | Shoe Nut(s) | HFTD Tier 2 | Transmission | 2023-10-08 | 2025-10-07 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000105 | 132336 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000106 | 132344 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000107 | 133153 | Nuts | HFTD Tier 3 | Transmission | 2023-12-18 | 2025-12-15 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000108 | 133521 | Shoe Nut(s) | HFTD Tier 2 | Transmission | 2023-12-15 | 2025-06-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000109 | 133523 | Cold End Clevis-Shackle | HFTD Tier 2 | Transmission | 2023-12-15 | 2025-06-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000110 | 133522 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2023-12-15 | 2025-06-13 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000111 | 135965 | Pole Butt | HFTD Tier 2 | Transmission | 2024-09-04 | 2025-09-04 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000112 | 136832 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2024-09-04 | 2025-09-04 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000113 | 136688 | Other(Specify) | HFTD Tier 2 | Transmission | 2024-10-15 | 2025-10-14 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000114 | 137576 | FAA Light(s) | HFTD Tier 2 | Transmission | 2025-02-04 | 2026-02-04 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000115 | 134397 | Complete Steel Pole | HFTD Tier 2 | Transmission | 2025-02-24 | 2026-02-24 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000116 | 132326 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000117 | 134973 | Insulators-Ceramic, Standard, 20K | HFTD Tier 2 | Transmission | 2024-10-17 | 2025-10-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000118 | 136999 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2024-06-25 | 2025-06-25 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000119 | 125650 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2021-09-01 | 2025-04-07 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000120 | 138169 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-01-29 | 2026-01-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000121 | 136869 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2024-11-08 | 2025-11-07 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000122 | 132482 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000123 | 133397 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2024-09-10 | 2025-09-09 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000124 | 132537 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000125 | 132623 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000126 | 134188 | Other(Specify) | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000127 | 132519 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000128 | 133970 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2024-04-29 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000129 | 136707 | Other(Specify) | HFTD Tier 2 | Transmission | 2024-10-15 | 2025-10-14 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000130 | 132328 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000131 | 132613 | Complete Wood Pole | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000132 | 132601 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000133 | 132600 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000134 | 134521 | Armor Rod - Shieldwire | HFTD Tier 2 | Transmission | 2024-05-09 | 2025-05-08 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000135 | 133295 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000136 | 133294 | Bolt(s) | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000137 | 133293 | Insulators-Ceramic, Standard, 30K | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000138 | 132360 | Signs-High Voltage-At Top | HFTD Tier 3 | Transmission | 2024-08-02 | 2025-08-01 | Level 3 | [7 empty] | SDG&E | 2025 | 1
1130000139 | 132538 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000140 | 136699 | Other(Specify) | HFTD Tier 2 | Transmission | 2025-01-17 | 2026-01-17 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000141 | 132855 | Jumper (Complete) | HFTD Tier 3 | Transmission | 2023-12-18 | 2025-12-16 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000142 | 134417 | Insulators-NCI, 69kv | HFTD Tier 2 | Transmission | 2024-09-03 | 2025-09-02 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000143 | 134418 | Cross Arms | HFTD Tier 2 | Transmission | 2024-09-03 | 2025-09-02 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000144 | 132394 | Shoe Pin-Bolt | HFTD Tier 3 | Transmission | 2023-12-29 | 2025-06-26 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000145 | 137010 | Area Underneath Span | HFTD Tier 2 | Transmission | 2024-11-25 | 2025-11-25 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000146 | 136917 | Suspension Shoe (Complete) | HFTD Tier 2 | Transmission | 2025-02-21 | 2026-02-21 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000147 | 134420 | Hardware | HFTD Tier 2 | Transmission | 2024-05-30 | 2025-05-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000148 | 138170 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-01-29 | 2026-01-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000149 | 136645 | Guy Wire - OH | HFTD Tier 2 | Transmission | 2024-10-07 | 2025-10-06 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000150 | 136150 | Pole Butt | HFTD Tier 2 | Transmission | 2024-12-10 | 2025-12-09 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000151 | 137548 | Pole Top | HFTD Tier 2 | Transmission | 2025-01-29 | 2026-01-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000152 | 133298 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000153 | 133297 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000154 | 133296 | Insulators-Ceramic, Standard, 30K | HFTD Tier 2 | Transmission | 2024-04-19 | 2025-04-18 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000155 | 136581 | Anchor Rod Ground Wire | HFTD Tier 2 | Transmission | 2025-01-29 | 2026-01-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000156 | 137560 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-01-29 | 2026-01-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000157 | 130573 | Footings (Complete) | HFTD Tier 2 | Transmission | 2023-04-10 | 2026-04-09 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000158 | 135931 | Footings (Complete) | HFTD Tier 2 | Transmission | 2023-01-10 | 2025-05-09 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000159 | 135930 | Concrete | HFTD Tier 2 | Transmission | 2023-01-10 | 2025-05-09 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000160 | 132614 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000161 | 100025613304 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000162 | 100025472514 | Pole | HFTD Tier 3 | Distribution | 2024-02-04 | 2024-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000163 | 100025711862 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-22 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000164 | 100025711863 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-22 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000165 | 100025596658 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-02-29 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000166 | 100025469240 | Pole | HFTD Tier 2 | Distribution | 2024-02-02 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000167 | 100025663846 | Pole | HFTD Tier 3 | Distribution | 2024-03-13 | 2024-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000168 | 100025692199 | Pole | HFTD Tier 3 | Distribution | 2024-03-19 | 2024-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000169 | 100025692240 | Pole | HFTD Tier 3 | Distribution | 2024-03-19 | 2024-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000170 | 100026603996 | Conductor | HFTD Tier 3 | Distribution | 2024-07-17 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000171 | 100026558716 | Pole | HFTD Tier 3 | Distribution | 2024-09-04 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000172 | 100026577215 | Conductor | HFTD Tier 3 | Distribution | 2024-09-11 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000173 | 100026555434 | Cross Arm | HFTD Tier 3 | Distribution | 2024-09-03 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000174 | 100026555435 | Cross Arm | HFTD Tier 3 | Distribution | 2024-09-03 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000175 | 100025489608 | Other | HFTD Tier 2 | Distribution | 2024-02-05 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000176 | 100023095820 | Other | HFTD Tier 2 | Distribution | 2022-12-28 | 2023-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000177 | 100023693412 | Pole | HFTD Tier 2 | Distribution | 2023-04-17 | 2024-04-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000178 | 100023762351 | Pole | HFTD Tier 2 | Distribution | 2023-04-27 | 2024-04-29 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000179 | 100023851910 | Pole | HFTD Tier 2 | Distribution | 2023-05-16 | 2024-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000180 | 100023822497 | Anchor/Guy | HFTD Tier 2 | Distribution | 2023-05-09 | 2024-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000181 | 100023598897 | Other | HFTD Tier 2 | Distribution | 2023-03-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000182 | 100023644150 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-04-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000183 | 100023644152 | Other | HFTD Tier 2 | Distribution | 2023-04-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000184 | 100023653912 | Cross Arm | HFTD Tier 2 | Distribution | 2023-04-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000185 | 100023653914 | Other | HFTD Tier 2 | Distribution | 2023-04-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000186 | 100023653916 | Pole | HFTD Tier 2 | Distribution | 2023-04-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000187 | 100023653919 | Cross Arm | HFTD Tier 2 | Distribution | 2023-04-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000188 | 100023722111 | Cross Arm | HFTD Tier 2 | Distribution | 2023-04-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000189 | 100023761863 | Pole | HFTD Tier 2 | Distribution | 2023-04-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000190 | 100023761872 | Cross Arm | HFTD Tier 2 | Distribution | 2023-04-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000191 | 100023820119 | Pole | HFTD Tier 2 | Distribution | 2023-05-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000192 | 100023885018 | Other | HFTD Tier 2 | Distribution | 2023-05-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000193 | 100023885059 | Cross Arm | HFTD Tier 2 | Distribution | 2023-05-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000194 | 100023885062 | Anchor/Guy | HFTD Tier 2 | Distribution | 2023-05-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000195 | 100023885064 | Pole | HFTD Tier 2 | Distribution | 2023-05-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000196 | 100023885083 | Other | HFTD Tier 2 | Distribution | 2023-05-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000197 | 100023885084 | Pole | HFTD Tier 2 | Distribution | 2023-05-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000198 | 100023885134 | Other | HFTD Tier 2 | Distribution | 2023-05-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000199 | 100024607654 | Pole | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000200 | 100024607655 | Pole | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000201 | 100023910982 | Pole | HFTD Tier 2 | Distribution | 2023-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000202 | 100023925581 | Other | HFTD Tier 2 | Distribution | 2023-05-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000203 | 100023931625 | Other | HFTD Tier 2 | Distribution | 2023-05-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000204 | 100023932259 | Other | HFTD Tier 2 | Distribution | 2023-05-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000205 | 100023932301 | Cross Arm | HFTD Tier 2 | Distribution | 2023-05-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000206 | 100023965246 | Pole | HFTD Tier 2 | Distribution | 2023-06-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000207 | 100023985707 | Pole | HFTD Tier 3 | Distribution | 2023-06-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000208 | 100023985705 | Other | HFTD Tier 3 | Distribution | 2023-06-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000209 | 100024009478 | Pole | HFTD Tier 2 | Distribution | 2023-06-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000210 | 100024044729 | Other | HFTD Tier 2 | Distribution | 2023-06-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000211 | 100024168167 | Cross Arm | HFTD Tier 3 | Distribution | 2023-07-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000212 | 100024168166 | Other | HFTD Tier 3 | Distribution | 2023-07-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000213 | 100024168168 | Cross Arm | HFTD Tier 3 | Distribution | 2023-07-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000214 | 100024173429 | Cross Arm | HFTD Tier 3 | Distribution | 2023-07-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000215 | 100024173440 | Cross Arm | HFTD Tier 3 | Distribution | 2023-07-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000216 | 100024173463 | Other | HFTD Tier 2 | Distribution | 2023-07-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000217 | 100024173462 | Other | HFTD Tier 2 | Distribution | 2023-07-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000218 | 100024173465 | Pole | HFTD Tier 2 | Distribution | 2023-07-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000219 | 100024173469 | Other | HFTD Tier 2 | Distribution | 2023-07-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000220 | 100024226059 | Pole | HFTD Tier 2 | Distribution | 2023-07-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000221 | 100024226061 | Pole | HFTD Tier 2 | Distribution | 2023-07-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000222 | 100024226069 | Pole | HFTD Tier 2 | Distribution | 2023-07-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000223 | 100024226087 | Other | HFTD Tier 3 | Distribution | 2023-07-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000224 | 100024226090 | Pole | HFTD Tier 3 | Distribution | 2023-07-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000225 | 100024552866 | Cross Arm | HFTD Tier 2 | Distribution | 2023-09-22 | 2024-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000226 | 100024243901 | Pole | HFTD Tier 2 | Distribution | 2023-07-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000227 | 100024892056 | Other | HFTD Tier 2 | Distribution | 2023-11-20 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000228 | 100024315851 | Pole | HFTD Tier 2 | Distribution | 2023-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000229 | 100024315854 | Pole | HFTD Tier 2 | Distribution | 2023-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000230 | 100024315856 | Cross Arm | HFTD Tier 2 | Distribution | 2023-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000231 | 100024334163 | Other | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000232 | 100024334171 | Other | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000233 | 100024334175 | Other | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000234 | 100024334174 | Other | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000235 | 100024334173 | Other | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000236 | 100024334178 | Pole | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000237 | 100024334180 | Pole | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000238 | 100024335233 | Cross Arm | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000239 | 100024335234 | Other | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000240 | 100024351583 | Pole | HFTD Tier 2 | Distribution | 2023-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000241 | 100024351584 | Other | HFTD Tier 2 | Distribution | 2023-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000242 | 100024351591 | Pole | HFTD Tier 2 | Distribution | 2023-08-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000243 | 100024351592 | Other | HFTD Tier 2 | Distribution | 2023-08-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000244 | 100024351595 | Other | HFTD Tier 2 | Distribution | 2023-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000245 | 100024364160 | Other | HFTD Tier 2 | Distribution | 2023-08-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000246 | 100024364235 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-08-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000247 | 100024369061 | Other | HFTD Tier 2 | Distribution | 2023-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000248 | 100024369067 | Other | HFTD Tier 2 | Distribution | 2023-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000249 | 100024369066 | Cross Arm | HFTD Tier 2 | Distribution | 2023-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000250 | 100024369068 | Other | HFTD Tier 2 | Distribution | 2023-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000251 | 100024369072 | Cross Arm | HFTD Tier 2 | Distribution | 2023-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000252 | 100024380231 | Anchor/Guy | HFTD Tier 2 | Distribution | 2023-08-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000253 | 100024396591 | Cross Arm | HFTD Tier 2 | Distribution | 2023-08-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000254 | 100024607586 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000255 | 100024607587 | Cross Arm | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000256 | 100024607585 | Pole | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000257 | 100024409671 | Anchor/Guy | HFTD Tier 2 | Distribution | 2023-08-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000258 | 100024409672 | Anchor/Guy | HFTD Tier 2 | Distribution | 2023-08-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000259 | 100024434897 | Other | HFTD Tier 2 | Distribution | 2023-08-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000260 | 100024445375 | Cross Arm | HFTD Tier 2 | Distribution | 2023-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000261 | 100024482165 | Other | HFTD Tier 2 | Distribution | 2023-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000262 | 100024482166 | Other | HFTD Tier 2 | Distribution | 2023-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000263 | 100024497217 | Pole | HFTD Tier 2 | Distribution | 2023-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000264 | 100024497216 | Other | HFTD Tier 2 | Distribution | 2023-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000265 | 100024512473 | Cross Arm | HFTD Tier 2 | Distribution | 2023-09-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000266 | 100024521070 | Pole | HFTD Tier 2 | Distribution | 2023-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000267 | 100024533342 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000268 | 100024533341 | Other | HFTD Tier 2 | Distribution | 2023-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000269 | 100024533354 | Other | HFTD Tier 2 | Distribution | 2023-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000270 | 100024533355 | Cross Arm | HFTD Tier 2 | Distribution | 2023-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000271 | 100024533359 | Other | HFTD Tier 2 | Distribution | 2023-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000272 | 100024539847 | Cross Arm | HFTD Tier 2 | Distribution | 2023-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000273 | 100024545146 | Cross Arm | HFTD Tier 2 | Distribution | 2023-09-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000274 | 100024892414 | Other | HFTD Tier 3 | Distribution | 2023-11-06 | 2024-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000275 | 100025686576 | Conductor | HFTD Tier 2 | Distribution | 2024-03-18 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000276 | 100025691725 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-19 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000277 | 100025690362 | Pole | HFTD Tier 2 | Distribution | 2024-03-19 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000278 | 100025670714 | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000279 | 100025670718 | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000280 | 100025673672 | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000281 | 100025673673 | Other | HFTD Tier 2 | Distribution | 2024-03-14 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000282 | 100025673674 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-14 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000283 | 100025673675 | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000284 | 100025704444 | Cross Arm | HFTD Tier 3 | Distribution | 2024-03-20 | 2024-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000285 | 100025367649 | Pole | HFTD Tier 3 | Distribution | 2024-01-23 | 2024-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000286 | 100025656487 | Pole | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000287 | 100025656501 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000288 | 100025656507 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000289 | 100025522942 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000290 | 100025521543 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000291 | 100025521546 | Pole | HFTD Tier 2 | Distribution | 2024-02-15 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000292 | 100025707253 | Pole | HFTD Tier 2 | Distribution | 2024-03-21 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000293 | 100025398738 | Cross Arm | HFTD Tier 3 | Distribution | 2024-01-24 | 2024-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000294 | 100025398740 | Pole | HFTD Tier 3 | Distribution | 2024-01-24 | 2024-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000295 | 100025807232 | Pole | HFTD Tier 3 | Distribution | 2024-04-08 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000296 | 100025465847 | Cross Arm | HFTD Tier 2 | Distribution | 2024-02-02 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000297 | 100025707503 | Other | HFTD Tier 3 | Distribution | 2024-03-21 | 2024-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000298 | 100025643246 | Other | HFTD Tier 2 | Distribution | 2024-03-08 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000299 | 100025544918 | Pole | HFTD Tier 2 | Distribution | 2024-02-21 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000300 | 100025544917 | Cross Arm | HFTD Tier 2 | Distribution | 2024-02-21 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000301 | 100025679978 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000302 | 100025680173 | Pole | HFTD Tier 2 | Distribution | 2024-03-15 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000303 | 100025670568 | Pole | HFTD Tier 2 | Distribution | 2024-03-14 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000304 | 100025526925 | Pole | HFTD Tier 3 | Distribution | 2024-02-16 | 2024-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000305 | 100025664757 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000306 | 100025664759 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000307 | 100025664760 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000308 | 100025664762 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000309 | 100025684401 | Pole | HFTD Tier 2 | Distribution | 2024-03-18 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000310 | 100025684407 | Pole | HFTD Tier 2 | Distribution | 2024-03-18 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000311 | 100025762540 | Other | HFTD Tier 2 | Distribution | 2024-03-28 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000312 | 100025614393 | Other | HFTD Tier 2 | Distribution | 2024-03-01 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000313 | 100025598865 | Pole | HFTD Tier 2 | Distribution | 2024-02-29 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000314 | 100025964998 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000315 | 100025745386 | Pole | HFTD Tier 3 | Distribution | 2024-03-25 | 2024-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000316 | 100025760519 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-28 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000317 | 100025759599 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-28 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000318 | 100025760031 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-28 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000319 | 100025760034 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-03-28 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000320 | 100025925903 | Cross Arm | HFTD Tier 3 | Distribution | 2024-04-30 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000321 | 100025750812 | Other | HFTD Tier 2 | Distribution | 2024-03-26 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000322 | 100025743996 | Pole | HFTD Tier 2 | Distribution | 2024-03-25 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000323 | 100025743998 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-25 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000324 | 100026252252 | Pole | HFTD Tier 3 | Distribution | 2024-06-25 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000325 | 100026252253 | Cross Arm | HFTD Tier 3 | Distribution | 2024-06-25 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000326 | 100026252256 | Pole | HFTD Tier 3 | Distribution | 2024-06-25 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000327 | 100026252260 | Cross Arm | HFTD Tier 3 | Distribution | 2024-06-25 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000328 | 100026257677 | Cross Arm | HFTD Tier 3 | Distribution | 2024-06-26 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000329 | 100026257678 | Pole | HFTD Tier 3 | Distribution | 2024-06-26 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000330 | 100026184432 | Pole | HFTD Tier 3 | Distribution | 2024-06-13 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000331 | 100026184431 | Pole | HFTD Tier 3 | Distribution | 2024-06-13 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000332 | 100026184433 | Pole | HFTD Tier 3 | Distribution | 2024-06-13 | 2024-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000333 | 100025964194 | Pole | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000334 | 100025964350 | Pole | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000335 | 100025964351 | Pole | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000336 | 100025837776 | Other | HFTD Tier 3 | Distribution | 2024-04-16 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000337 | 100026638959 | Other | HFTD Tier 3 | Distribution | 2024-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000338 | 100026638963 | Pole | HFTD Tier 3 | Distribution | 2024-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000339 | 100026649474 | Pole | HFTD Tier 3 | Distribution | 2024-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000340 | 100026649476 | Other | HFTD Tier 3 | Distribution | 2024-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000341 | 100026649479 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000342 | 100026107812 | Pole | HFTD Tier 2 | Distribution | 2024-05-30 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000343 | 100026049946 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-21 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000344 | 100025942071 | Pole | HFTD Tier 2 | Distribution | 2024-05-01 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000345 | 100026049947 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-21 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000346 | 100026049944 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-21 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000347 | 100026049945 | Pole | HFTD Tier 2 | Distribution | 2024-05-21 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000348 | 100026049943 | Pole | HFTD Tier 2 | Distribution | 2024-05-21 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000349 | 100025798712 | Pole | HFTD Tier 2 | Distribution | 2024-04-04 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000350 | 100026381509 | Pole | HFTD Tier 2 | Distribution | 2024-07-25 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000351 | 100025811298 | Pole | HFTD Tier 2 | Distribution | 2024-04-09 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000352 | 100025806180 | Pole | HFTD Tier 2 | Distribution | 2024-04-08 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000353 | 100026492778 | Other | HFTD Tier 2 | Distribution | 2024-08-21 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000354 | 100026519492 | Pole | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000355 | 100026519491 | Other | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000356 | 100026523245 | Other | HFTD Tier 2 | Distribution | 2024-08-27 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000357 | 100026436706 | Conductor | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000358 | 100026495821 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-22 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000359 | 100026479115 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-16 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000360 | 100026404803 | Pole | HFTD Tier 2 | Distribution | 2024-07-29 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000361 | 100026404802 | Cross Arm | HFTD Tier 2 | Distribution | 2024-07-29 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000362 | 100026518733 | Pole | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000363 | 100026518961 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000364 | 100026451225 | Pole | HFTD Tier 2 | Distribution | 2024-08-08 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000365 | 100026452806 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-08 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000366 | 100026428955 | Other | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000367 | 100026456480 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000368 | 100026428950 | Other | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000369 | 100026455704 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000370 | 100026455703 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000371 | 100026428954 | Other | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000372 | 100026490194 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000373 | 100026456007 | Other | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000374 | 100026436242 | Other | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000375 | 100026436241 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000376 | 100026436139 | Other | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000377 | 100026479327 | Other | HFTD Tier 2 | Distribution | 2024-08-16 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000378 | 100026456328 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000379 | 100026456329 | Pole | HFTD Tier 2 | Distribution | 2024-08-09 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000380 | 100026445090 | Pole | HFTD Tier 2 | Distribution | 2024-08-07 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000381 | 100026492777 | Other | HFTD Tier 2 | Distribution | 2024-08-21 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000382 | 100026492974 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-21 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000383 | 100026492973 | Pole | HFTD Tier 2 | Distribution | 2024-08-21 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000384 | 100026474695 | Other | HFTD Tier 2 | Distribution | 2024-08-15 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000385 | 100026205988 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000386 | 100026489237 | Other | HFTD Tier 2 | Distribution | 2024-08-20 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000387 | 100026429845 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000388 | 100026413199 | Pole | HFTD Tier 2 | Distribution | 2024-07-31 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000389 | 100026436707 | Other | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000390 | 100026523692 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-08-27 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000391 | 100026482756 | Other | HFTD Tier 2 | Distribution | 2024-08-19 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000392 | 100026524682 | Other | HFTD Tier 2 | Distribution | 2024-08-27 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000393 | 100026524684 | Other | HFTD Tier 2 | Distribution | 2024-08-27 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000394 | 100026432911 | Other | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000395 | 100026451966 | Pole | HFTD Tier 2 | Distribution | 2024-08-08 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000396 | 100026437473 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000397 | 100026408976 | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000398 | 100026409620 | Pole | HFTD Tier 2 | Distribution | 2024-07-30 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000399 | 100026140134 | Pole | HFTD Tier 2 | Distribution | 2024-06-04 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000400 | 100026572963 | Pole | HFTD Tier 2 | Distribution | 2024-09-10 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000401 | 100026373060 | Cross Arm | HFTD Tier 2 | Distribution | 2024-07-24 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000402 | 100026534984 | Other | HFTD Tier 2 | Distribution | 2024-08-29 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000403 | 100026373571 | Pole | HFTD Tier 2 | Distribution | 2024-07-24 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000404 | 100026137885 | Pole | HFTD Tier 2 | Distribution | 2024-06-04 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000405 | 100026200870 | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000406 | 100026538350 | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000407 | 100026565829 | Conductor | HFTD Tier 2 | Distribution | 2024-09-06 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000408 | 100026539464 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-30 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000409 | 100026539465 | Pole | HFTD Tier 2 | Distribution | 2024-08-30 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000410 | 100026582099 | Pole | HFTD Tier 2 | Distribution | 2024-09-12 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000411 | 100026572750 | Cross Arm | HFTD Tier 2 | Distribution | 2024-09-10 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000412 | 100026572708 | Other | HFTD Tier 2 | Distribution | 2024-09-10 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000413 | 100026207104 | Pole | HFTD Tier 2 | Distribution | 2024-06-19 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000414 | 100026176883 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-12 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000415 | 100026205394 | Conductor | HFTD Tier 2 | Distribution | 2024-06-19 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000416 | 100026591812 | Other | HFTD Tier 2 | Distribution | 2024-09-16 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000417 | 100026499041 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-23 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000418 | 100026601298 | Other | HFTD Tier 2 | Distribution | 2024-09-19 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000419 | 100026601387 | Pole | HFTD Tier 2 | Distribution | 2024-09-19 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000420 | 100026289760 | Pole | HFTD Tier 2 | Distribution | 2024-07-02 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000421 | 100026591506 | Pole | HFTD Tier 2 | Distribution | 2024-09-16 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000422 | 100026625664 | Cross Arm | HFTD Tier 2 | Distribution | 2024-09-24 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000423 | 100026430344 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000424 | 100026464839 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000425 | 100026743589 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000426 | 100026743587 | Pole | HFTD Tier 2 | Distribution | 2024-10-29 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000427 | 100026434089 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000428 | 100026430231 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000429 | 100026743586 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-29 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000430 | 100026434088 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000431 | 100026685741 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-14 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000432 | 100026720506 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000433 | 100026460815 | Pole | HFTD Tier 2 | Distribution | 2024-08-12 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000434 | 100026430323 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000435 | 100026729769 | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000436 | 100026451224 | Pole | HFTD Tier 2 | Distribution | 2024-08-08 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000437 | 100026464838 | Pole | HFTD Tier 2 | Distribution | 2024-08-13 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000438 | 100026430341 | Pole | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000439 | 100026431617 | Pole | HFTD Tier 2 | Distribution | 2024-08-02 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000440 | 100026715323 | Other | HFTD Tier 2 | Distribution | 2024-10-21 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000441 | 100026743610 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-29 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000442 | 100026585051 | Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000443 | 100027243404 | Pole | HFTD Tier 2 | Distribution | 2025-01-07 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000444 | 100027397576 | Conductor | HFTD Tier 3 | Distribution | 2025-03-20 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000445 | 100027397365 | Conductor | HFTD Tier 3 | Distribution | 2025-03-20 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000446 | 100027358099 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-03-05 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000447 | 100027243413 | Pole | HFTD Tier 3 | Distribution | 2025-01-07 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000448 | 100027397364 | Pole | HFTD Tier 3 | Distribution | 2025-03-20 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000449 | 100027397363 | Conductor | HFTD Tier 3 | Distribution | 2025-03-20 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000450 | 100027243432 | Cross Arm | HFTD Tier 3 | Distribution | 2025-01-29 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000451 | 100027242346 | Conductor | HFTD Tier 2 | Distribution | 2025-01-13 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000452 | 100027243433 | Pole | HFTD Tier 2 | Distribution | 2025-02-05 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000453 | 100027437704 | Pole | HFTD Tier 3 | Distribution | 2025-03-26 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000454 | 100027437704 | Pole | HFTD Tier 3 | Distribution | 2025-03-26 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000455 | 100027243459 | Pole | HFTD Tier 2 | Distribution | 2025-02-03 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000456 | 100027405056 | Other | HFTD Tier 2 | Distribution | 2025-03-24 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000457 | 100027405709 | Pole | HFTD Tier 2 | Distribution | 2025-03-24 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000458 | 100027405057 | Other | HFTD Tier 2 | Distribution | 2025-03-24 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000459 | 100025910559 | Other | HFTD Tier 2 | Distribution | 2024-04-09 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000460 | 100026979036 | Other | HFTD Tier 3 | Distribution | 2024-10-02 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000461 | 100026374171 | Other | HFTD Tier 2 | Distribution | 2024-07-23 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000462 | 100025801256 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000463 | 100025792759 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-04-03 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000464 | 100026053659 | Pole | HFTD Tier 2 | Distribution | 2024-05-23 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000465 | 100025911585 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-04-26 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000466 | 100025911586 | Conductor | HFTD Tier 2 | Distribution | 2024-04-26 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000467 | 100025883031 | Other | HFTD Tier 2 | Distribution | 2024-04-24 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000468 | 100026104581 | Other | HFTD Tier 2 | Distribution | 2024-05-29 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000469 | 100025787909 | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000470 | 100025788080 | Cross Arm | HFTD Tier 2 | Distribution | 2024-04-02 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000471 | 100025788081 | Cross Arm | HFTD Tier 2 | Distribution | 2024-04-02 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000472 | 100025788082 | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000473 | 100025790810 | Pole | HFTD Tier 2 | Distribution | 2024-04-02 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000474 | 100025838456 | Pole | HFTD Tier 2 | Distribution | 2024-04-16 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000475 | 100025783683 | Cross Arm | HFTD Tier 2 | Distribution | 2024-04-01 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000476 | 100025845314 | Pole | HFTD Tier 2 | Distribution | 2024-04-17 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000477 | 100025793757 | Other | HFTD Tier 2 | Distribution | 2024-04-03 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000478 | 100025799012 | Pole | HFTD Tier 2 | Distribution | 2024-04-04 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000479 | 100025835331 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-04-15 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000480 | 100026144331 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-05 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000481 | 100026144333 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-05 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000482 | 100026138089 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-04 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000483 | 100026138091 | Pole | HFTD Tier 2 | Distribution | 2024-06-04 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000484 | 100025959603 | Pole | HFTD Tier 2 | Distribution | 2024-05-06 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000485 | 100026108720 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-05-30 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000486 | 100025996124 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-14 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000487 | 100026110102 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-30 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000488 | 100026110101 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-05-30 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000489 | 100026110106 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-30 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000490 | 100026132409 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-03 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000491 | 100026132564 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-03 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000492 | 100026018163 | Pole | HFTD Tier 2 | Distribution | 2024-05-16 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000493 | 100025996630 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-14 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000494 | 100025996636 | Conductor | HFTD Tier 2 | Distribution | 2024-05-14 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000495 | 100026267786 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000496 | 100026267708 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000497 | 100026267781 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000498 | 100026267784 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000499 | 100026267790 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000500 | 100026267791 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000501 | 100026267793 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000502 | 100026267796 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000503 | 100026267799 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000504 | 100025979542 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000505 | 100025979543 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000506 | 100025979544 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000507 | 100025979546 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000508 | 100025926874 | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000509 | 100025953145 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000510 | 100026034806 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-05-20 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000511 | 100026185289 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-06-13 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000512 | 100026185361 | Other | HFTD Tier 2 | Distribution | 2024-06-13 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000513 | 100026185369 | Other | HFTD Tier 2 | Distribution | 2024-06-13 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000514 | 100026185360 | Pole | HFTD Tier 2 | Distribution | 2024-06-13 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000515 | 100025871214 | Cross Arm | HFTD Tier 2 | Distribution | 2024-04-22 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000516 | 100026181577 | Pole | HFTD Tier 2 | Distribution | 2024-06-12 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000517 | 100025869686 | Pole | HFTD Tier 2 | Distribution | 2024-04-22 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000518 | 100026174776 | Pole | HFTD Tier 2 | Distribution | 2024-06-12 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000519 | 100026174777 | Pole | HFTD Tier 2 | Distribution | 2024-06-12 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000520 | 100026175279 | Pole | HFTD Tier 2 | Distribution | 2024-06-12 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000521 | 100026175680 | Pole | HFTD Tier 2 | Distribution | 2024-06-12 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000522 | 100026181578 | Pole | HFTD Tier 2 | Distribution | 2024-06-12 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000523 | 100026322603 | Other | HFTD Tier 2 | Distribution | 2024-07-12 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000524 | 100025871297 | Pole | HFTD Tier 2 | Distribution | 2024-04-22 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000525 | 100025882090 | Pole | HFTD Tier 2 | Distribution | 2024-04-24 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000526 | 100025904486 | Pole | HFTD Tier 2 | Distribution | 2024-04-25 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000527 | 100025904432 | Pole | HFTD Tier 2 | Distribution | 2024-04-25 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000528 | 100025904433 | Pole | HFTD Tier 2 | Distribution | 2024-04-25 | 2025-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000529 | 100026176880 | Other | HFTD Tier 2 | Distribution | 2024-06-12 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000530 | 100026312945 | Pole | HFTD Tier 2 | Distribution | 2024-07-10 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000531 | 100026312950 | Other | HFTD Tier 2 | Distribution | 2024-07-10 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000532 | 100026200701 | Pole | HFTD Tier 2 | Distribution | 2024-06-18 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000533 | 100026219997 | Pole | HFTD Tier 2 | Distribution | 2024-06-21 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000534 | 100025993153 | Pole | HFTD Tier 2 | Distribution | 2024-05-13 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000535 | 100025990639 | Other | HFTD Tier 2 | Distribution | 2024-05-13 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000536 | 100025959623 | Other | HFTD Tier 2 | Distribution | 2024-05-06 | 2025-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000537 | 100026407664 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-07-30 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000538 | 100027317991 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000539 | 100026428237 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000540 | 100026429749 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000541 | 100026429750 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000542 | 100026429751 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-08-01 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000543 | 100026329591 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-07-15 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000544 | 100027345636 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000545 | 100026435947 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000546 | 100026435946 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000547 | 100026437295 | Conductor | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000548 | 100026428384 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-07-15 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000549 | 100026318150 | Pole | HFTD Tier 2 | Distribution | 2024-07-11 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000550 | 100026334900 | Other | HFTD Tier 2 | Distribution | 2024-07-16 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000551 | 100026362230 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-07-22 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000552 | 100026362232 | Cross Arm | HFTD Tier 2 | Distribution | 2024-07-22 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000553 | 100026266358 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000554 | 100026258598 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000555 | 100026257679 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000556 | 100026258073 | Pole | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000557 | 100026258072 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-26 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000558 | 100026373190 | Pole | HFTD Tier 2 | Distribution | 2024-07-24 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000559 | 100026372669 | Cross Arm | HFTD Tier 2 | Distribution | 2024-07-24 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000560 | 100026334307 | Pole | HFTD Tier 2 | Distribution | 2024-07-16 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000561 | 100026334744 | Cross Arm | HFTD Tier 2 | Distribution | 2024-07-16 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000562 | 100026339019 | Other | HFTD Tier 2 | Distribution | 2024-07-17 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000563 | 100026309825 | Pole | HFTD Tier 2 | Distribution | 2024-07-09 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000564 | 100026437414 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000565 | 100026437297 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000566 | 100026437105 | Pole | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000567 | 100026577338 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-09-11 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000568 | 100026667007 | Pole | HFTD Tier 2 | Distribution | 2024-10-07 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000569 | 100026666846 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-10-07 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000570 | 100026952509 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-10-31 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000571 | 100026664914 | Other | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000572 | 100026664917 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000573 | 100026665280 | Pole | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000574 | 100026664919 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000575 | 100026665281 | Pole | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000576 | 100026665285 | Other | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000577 | 100026665284 | Other | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000578 | 100026665287 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000579 | 100026665289 | Other | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000580 | 100026665288 | Other | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000581 | 100026665290 | Pole | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000582 | 100026665291 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000583 | 100026665305 | Other | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000584 | 100026665307 | Other | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000585 | 100026665310 | Other | HFTD Tier 3 | Distribution | 2024-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000586 | 100026665722 | Pole | HFTD Tier 3 | Distribution | 2024-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000587 | 100026665721 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000588 | 100026665723 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000589 | 100026665724 | Conductor | HFTD Tier 3 | Distribution | 2024-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000590 | 100026665725 | Pole | HFTD Tier 3 | Distribution | 2024-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000591 | 100026670098 | Pole | HFTD Tier 3 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000592 | 100026670100 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000593 | 100026670102 | Pole | HFTD Tier 3 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000594 | 100026670103 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000595 | 100026670108 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000596 | 100026670107 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000597 | 100026670109 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000598 | 100026670114 | Pole | HFTD Tier 2 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000599 | 100026670117 | Pole | HFTD Tier 2 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000600 | 100026670118 | Pole | HFTD Tier 2 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000601 | 100026670120 | Pole | HFTD Tier 3 | Distribution | 2024-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000602 | 100026673658 | Pole | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000603 | 100026673657 | Other | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000604 | 100026673659 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000605 | 100026673660 | Pole | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000606 | 100026673663 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000607 | 100026673664 | Pole | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000608 | 100026673666 | Pole | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000609 | 100026673668 | Pole | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000610 | 100026673669 | Pole | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000611 | 100026673670 | Other | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000612 | 100026673672 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000613 | 100026673674 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000614 | 100026673678 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000615 | 100026673680 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000616 | 100026680269 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000617 | 100026680411 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000618 | 100026680412 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000619 | 100026680413 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000620 | 100026680419 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000621 | 100026682969 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000622 | 100026683213 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000623 | 100026683215 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000624 | 100026683216 | Other | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000625 | 100026683217 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000626 | 100026683222 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000627 | 100026683223 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000628 | 100026683226 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000629 | 100026683227 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000630 | 100026690432 | Pole | HFTD Tier 3 | Distribution | 2024-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000631 | 100026690581 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000632 | 100026690582 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000633 | 100026695918 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000634 | 100026695919 | Pole | HFTD Tier 3 | Distribution | 2024-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000635 | 100026695921 | Pole | HFTD Tier 3 | Distribution | 2024-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000636 | 100026695920 | Other | HFTD Tier 3 | Distribution | 2024-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000637 | 100026699882 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000638 | 100026699883 | Other | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000639 | 100026699888 | Conductor | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000640 | 100026699892 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000641 | 100026699895 | Pole | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000642 | 100026699897 | Pole | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000643 | 100026699898 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000644 | 100026699899 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000645 | 100026699900 | Pole | HFTD Tier 3 | Distribution | 2024-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000646 | 100026703103 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-10-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000647 | 100026718313 | Other | HFTD Tier 2 | Distribution | 2024-10-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000648 | 100026718314 | Pole | HFTD Tier 3 | Distribution | 2024-10-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000649 | 100026722079 | Transformer | HFTD Tier 2 | Distribution | 2024-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000650 | 100026722220 | Pole | HFTD Tier 2 | Distribution | 2024-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000651 | 100026726324 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000652 | 100026726326 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000653 | 100026726329 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000654 | 100026726330 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000655 | 100026726332 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000656 | 100026726336 | Pole | HFTD Tier 3 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000657 | 100026726338 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000658 | 100026726339 | Pole | HFTD Tier 2 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000659 | 100026734480 | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000660 | 100026734482 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000661 | 100026734483 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000662 | 100026734484 | Conductor | HFTD Tier 2 | Distribution | 2024-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000663 | 100026741705 | Pole | HFTD Tier 2 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000664 | 100026741707 | Pole | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000665 | 100026741708 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000666 | 100026741734 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000667 | 100026741735 | Pole | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000668 | 100026741738 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000669 | 100026741739 | Pole | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000670 | 100026741740 | Pole | HFTD Tier 2 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000671 | 100026741741 | Pole | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000672 | 100026741742 | Pole | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000673 | 100026741744 | Pole | HFTD Tier 3 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000674 | 100026741745 | Pole | HFTD Tier 2 | Distribution | 2024-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000675 | 100026750548 | Pole | HFTD Tier 3 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000676 | 100026750547 | Other | HFTD Tier 3 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000677 | 100026751043 | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000678 | 100026751044 | Other | HFTD Tier 2 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000679 | 100026751045 | Other | HFTD Tier 3 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000680 | 100026751049 | Pole | HFTD Tier 3 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000681 | 100026751050 | Cross Arm | HFTD Tier 3 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000682 | 100026751051 | Other | HFTD Tier 3 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000683 | 100026751057 | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000684 | 100026751060 | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000685 | 100026751058 | Other | HFTD Tier 2 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000686 | 100026751059 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000687 | 100026751061 | Pole | HFTD Tier 2 | Distribution | 2024-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000688 | 100026765440 | Pole | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000689 | 100026765441 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000690 | 100026765442 | Other | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000691 | 100026765443 | Other | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000692 | 100026765444 | Pole | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000693 | 100026765445 | Pole | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000694 | 100026765446 | Pole | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000695 | 100026765449 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000696 | 100026765452 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000697 | 100026765457 | Other | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000698 | 100026765458 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000699 | 100026765465 | Other | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000700 | 100026765466 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000701 | 100026769270 | Other | HFTD Tier 3 | Distribution | 2024-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000702 | 100026769271 | Other | HFTD Tier 3 | Distribution | 2024-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000703 | 100026769275 | Pole | HFTD Tier 3 | Distribution | 2024-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000704 | 100026769277 | Transformer | HFTD Tier 3 | Distribution | 2024-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000705 | 100026777739 | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000706 | 100026777930 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000707 | 100026777932 | Other | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000708 | 100026777934 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000709 | 100026777935 | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000710 | 100026777936 | Other | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000711 | 100026777937 | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000712 | 100026777938 | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000713 | 100026777939 | Pole | HFTD Tier 2 | Distribution | 2024-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000714 | 100026784976 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000715 | 100026784979 | Pole | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000716 | 100026785280 | Pole | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000717 | 100026785283 | Pole | HFTD Tier 2 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000718 | 100026785286 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000719 | 100026785287 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000720 | 100026785288 | Conductor | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000721 | 100026785292 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000722 | 100026785293 | Pole | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000723 | 100026785294 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000724 | 100026785295 | Conductor | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000725 | 100026785299 | Pole | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000726 | 100026785301 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000727 | 100026785302 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000728 | 100026789299 | Other | HFTD Tier 2 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000729 | 100026789750 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000730 | 100026789752 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000731 | 100026789753 | Transformer | HFTD Tier 2 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000732 | 100026789754 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000733 | 100026789755 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000734 | 100026789756 | Pole | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000735 | 100026789757 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000736 | 100026789758 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000737 | 100026789759 | Pole | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000738 | 100026789760 | Pole | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000739 | 100026789761 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000740 | 100026789762 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000741 | 100026789763 | Pole | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000742 | 100026789764 | Other | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000743 | 100026789765 | Pole | HFTD Tier 3 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000744 | 100026792046 | Pole | HFTD Tier 3 | Distribution | 2024-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000745 | 100026792047 | Pole | HFTD Tier 3 | Distribution | 2024-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000746 | 100026792048 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000747 | 100026792049 | Pole | HFTD Tier 3 | Distribution | 2024-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000748 | 100026792460 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000749 | 100026792462 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000750 | 100026792463 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000751 | 100026792464 | Pole | HFTD Tier 3 | Distribution | 2024-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000752 | 100026797325 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000753 | 100026797326 | Other | HFTD Tier 2 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000754 | 100026797327 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000755 | 100026797328 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000756 | 100026797329 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000757 | 100026797450 | Other | HFTD Tier 2 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000758 | 100026797453 | Pole | HFTD Tier 3 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000759 | 100026797454 | Pole | HFTD Tier 3 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000760 | 100026797456 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000761 | 100026803848 | Other | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000762 | 100026803849 | Transformer | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000763 | 100026804272 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000764 | 100026804273 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000765 | 100026804274 | Other | HFTD Tier 3 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000766 | 100026804275 | Pole | HFTD Tier 3 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000767 | 100026804276 | Pole | HFTD Tier 3 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000768 | 100026804278 | Pole | HFTD Tier 3 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000769 | 100026804279 | Pole | HFTD Tier 3 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000770 | 100026804280 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000771 | 100026804281 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000772 | 100026804283 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000773 | 100026804284 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000774 | 100026804285 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000775 | 100026804286 | Conductor | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000776 | 100026804287 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000777 | 100026804288 | Pole | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000778 | 100026808919 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000779 | 100026809030 | Other | HFTD Tier 2 | Distribution | 2024-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000780 | 100026809031 | Other | HFTD Tier 2 | Distribution | 2024-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000781 | 100026809033 | Pole | HFTD Tier 2 | Distribution | 2024-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000782 | 100026809034 | Conductor | HFTD Tier 2 | Distribution | 2024-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000783 | 100026812834 | Pole | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000784 | 100026812835 | Pole | HFTD Tier 3 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000785 | 100026812837 | Pole | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000786 | 100026813443 | Other | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000787 | 100026813444 | Other | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000788 | 100026813445 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000789 | 100026813447 | Pole | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000790 | 100026813449 | Pole | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000791 | 100026813450 | Pole | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000792 | 100026818328 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000793 | 100026818580 | Other | HFTD Tier 3 | Distribution | 2024-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000794 | 100026818584 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000795 | 100026818587 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000796 | 100026818588 | Pole | HFTD Tier 3 | Distribution | 2024-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000797 | 100026822527 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000798 | 100026822528 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000799 | 100026828250 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000800 | 100026828253 | Conductor | HFTD Tier 3 | Distribution | 2024-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000801 | 100026828255 | Pole | HFTD Tier 3 | Distribution | 2024-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000802 | 100026828256 | Pole | HFTD Tier 3 | Distribution | 2024-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000803 | 100026908884 | Other | HFTD Tier 2 | Distribution | 2024-11-27 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000804 | 100026835593 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000805 | 100026835594 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000806 | 100026835595 | Other | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000807 | 100026835598 | Pole | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000808 | 100026835741 | Pole | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000809 | 100026835744 | Pole | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000810 | 100026835743 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000811 | 100026835745 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000812 | 100026835751 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000813 | 100026842838 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000814 | 100026842839 | Pole | HFTD Tier 3 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000815 | 100026843221 | Other | HFTD Tier 3 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000816 | 100026843223 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000817 | 100026843225 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000818 | 100026843226 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000819 | 100026843227 | Pole | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000820 | 100026843228 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000821 | 100026843229 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000822 | 100026843230 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000823 | 100026843231 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000824 | 100026843232 | Anchor/Guy | HFTD Tier 3 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000825 | 100026843236 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000826 | 100026843238 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000827 | 100027098353 | Pole | HFTD Tier 2 | Distribution | 2025-01-09 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000828 | 100027098354 | Pole | HFTD Tier 2 | Distribution | 2025-01-09 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000829 | 100027250359 | Pole | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000830 | 100027250370 | Pole | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000831 | 100027126843 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-01-17 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000832 | 100027250802 | Pole | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000833 | 100027250803 | Cross Arm | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000834 | 100027250804 | Pole | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000835 | 100027358860 | Conductor | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000836 | 100027358861 | Conductor | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000837 | 100027358495 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000838 | 100027358496 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000839 | 100027358497 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000840 | 100027347894 | Pole | HFTD Tier 2 | Distribution | 2025-03-03 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000841 | 100027277878 | Pole | HFTD Tier 2 | Distribution | 2025-02-20 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000842 | 100027283383 | Other | HFTD Tier 2 | Distribution | 2025-02-21 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000843 | 100027122983 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-01-16 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000844 | 100027283386 | Conductor | HFTD Tier 2 | Distribution | 2025-02-21 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000845 | 100027283387 | Conductor | HFTD Tier 2 | Distribution | 2025-02-21 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000846 | 100027397850 | Pole | HFTD Tier 2 | Distribution | 2025-03-20 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000847 | 100027102078 | Pole | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000848 | 100027102079 | Conductor | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000849 | 100027201303 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-01-31 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000850 | 100027201767 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-01-31 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000851 | 100027278179 | Other | HFTD Tier 2 | Distribution | 2025-02-20 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000852 | 100027357037 | Pole | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000853 | 100027271401 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-02-19 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000854 | 100027178944 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-01-22 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000855 | 100027178946 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-01-22 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000856 | 100027081258 | Pole | HFTD Tier 3 | Distribution | 2025-01-03 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000857 | 100027107000 | Cross Arm | HFTD Tier 2 | Distribution | 2025-01-13 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000858 | 100027077528 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000859 | 100027078212 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000860 | 100027078213 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000861 | 100027078214 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000862 | 100027077695 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000863 | 100027196951 | Other | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000864 | 100027196950 | Cross Arm | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000865 | 100027196952 | Cross Arm | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000866 | 100027196953 | Other | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000867 | 100027196954 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000868 | 100027196955 | Other | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000869 | 100027196956 | Other | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000870 | 100027197017 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000871 | 100027197018 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000872 | 100027197019 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000873 | 100027197086 | Other | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000874 | 100027197087 | Other | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000875 | 100027197088 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000876 | 100027197203 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000877 | 100027197206 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000878 | 100027196897 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000879 | 100027196912 | Cross Arm | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000880 | 100027196911 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000881 | 100027196913 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000882 | 100027196914 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000883 | 100027196915 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000884 | 100027101588 | Other | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000885 | 100027101579 | Other | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000886 | 100027101580 | Other | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000887 | 100027101581 | Other | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000888 | 100027224636 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-02-03 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000889 | 100027185333 | Cross Arm | HFTD Tier 3 | Distribution | 2025-01-28 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000890 | 100027187532 | Pole | HFTD Tier 2 | Distribution | 2025-01-29 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000891 | 100027187125 | Pole | HFTD Tier 2 | Distribution | 2025-01-29 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000892 | 100027186780 | Conductor | HFTD Tier 2 | Distribution | 2025-01-29 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000893 | 100027187252 | Cross Arm | HFTD Tier 2 | Distribution | 2025-01-29 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000894 | 100027187238 | Pole | HFTD Tier 3 | Distribution | 2025-01-29 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000895 | 100027187237 | Cross Arm | HFTD Tier 3 | Distribution | 2025-01-29 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000896 | 100027361010 | Pole | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000897 | 100027361011 | Cross Arm | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000898 | 100027361012 | Pole | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000899 | 100027361013 | Other | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000900 | 100027157925 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-01-23 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000901 | 100027196218 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-01-24 | 2026-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000902 | 100027247775 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-02-10 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000903 | 100027247778 | Conductor | HFTD Tier 2 | Distribution | 2025-02-10 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000904 | 100027247779 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-02-10 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000905 | 100027247781 | Conductor | HFTD Tier 2 | Distribution | 2025-02-10 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000906 | 100027078130 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-01-02 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000907 | 100027242478 | Conductor | HFTD Tier 3 | Distribution | 2025-02-06 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000908 | 100027269739 | Pole | HFTD Tier 3 | Distribution | 2025-02-18 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000909 | 100026912513 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-12-03 | 2025-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130000910 | 100026878265 | Other | HFTD Tier 2 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000911 | 100026878267 | Other | HFTD Tier 2 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000912 | 100026878268 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000913 | 100026878269 | Other | HFTD Tier 2 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000914 | 100026878730 | Pole | HFTD Tier 2 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000915 | 100026878731 | Other | HFTD Tier 2 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000916 | 100026878733 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000917 | 100026878735 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000918 | 100026878737 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000919 | 100026878738 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000920 | 100026881570 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000921 | 100026881571 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000922 | 100026881572 | Pole | HFTD Tier 2 | Distribution | 2024-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000923 | 100026881574 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000924 | 100026881575 | Other | HFTD Tier 2 | Distribution | 2024-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000925 | 100026881576 | Pole | HFTD Tier 2 | Distribution | 2024-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000926 | 100026885040 | Other | HFTD Tier 3 | Distribution | 2024-11-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000927 | 100026885041 | Cross Arm | HFTD Tier 3 | Distribution | 2024-11-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000928 | 100026885043 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000929 | 100026885046 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-11-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000930 | 100026885047 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000931 | 100026886090 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000932 | 100026914208 | Pole | HFTD Tier 2 | Distribution | 2024-12-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000933 | 100026914320 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000934 | 100026914321 | Other | HFTD Tier 2 | Distribution | 2024-12-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000935 | 100026914323 | Other | HFTD Tier 3 | Distribution | 2024-12-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000936 | 100026918031 | Other | HFTD Tier 2 | Distribution | 2024-12-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000937 | 100026918033 | Pole | HFTD Tier 3 | Distribution | 2024-12-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000938 | 100026918035 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000939 | 100026918036 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000940 | 100026918037 | Pole | HFTD Tier 3 | Distribution | 2024-12-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000941 | 100026922430 | Other | HFTD Tier 2 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000942 | 100026922431 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000943 | 100026922432 | Conductor | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000944 | 100026922433 | Pole | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000945 | 100026922434 | Pole | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000946 | 100026922435 | Pole | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000947 | 100026922436 | Pole | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000948 | 100026922438 | Pole | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000949 | 100026922439 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000950 | 100026922440 | Pole | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000951 | 100026922446 | Pole | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000952 | 100026922448 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000953 | 100026922449 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000954 | 100026925808 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000955 | 100026925810 | Pole | HFTD Tier 3 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000956 | 100026925809 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000957 | 100026925811 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000958 | 100026925812 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000959 | 100026925813 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000960 | 100026925814 | Pole | HFTD Tier 2 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000961 | 100026925815 | Other | HFTD Tier 2 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000962 | 100026925816 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000963 | 100026925818 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000964 | 100026925817 | Other | HFTD Tier 2 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000965 | 100026925824 | Other | HFTD Tier 3 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000966 | 100026925825 | Other | HFTD Tier 3 | Distribution | 2024-12-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000967 | 100026929156 | Pole | HFTD Tier 3 | Distribution | 2024-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000968 | 100026929158 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000969 | 100026929157 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000970 | 100026929159 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000971 | 100026935312 | Pole | HFTD Tier 2 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000972 | 100026935313 | Pole | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000973 | 100026935314 | Pole | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000974 | 100026935316 | Pole | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000975 | 100026935317 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000976 | 100026935318 | Pole | HFTD Tier 2 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000977 | 100026935319 | Other | HFTD Tier 2 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000978 | 100026935320 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000979 | 100026935321 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000980 | 100026935322 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000981 | 100026935323 | Other | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000982 | 100026935325 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000983 | 100026935326 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000984 | 100026939794 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000985 | 100026939795 | Conductor | HFTD Tier 2 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000986 | 100026939796 | Pole | HFTD Tier 2 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000987 | 100026939797 | Pole | HFTD Tier 2 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000988 | 100026939798 | Other | HFTD Tier 3 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000989 | 100026939799 | Other | HFTD Tier 3 | Distribution | 2024-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000990 | 100026939811 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000991 | 100026939815 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000992 | 100026939816 | Other | HFTD Tier 3 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000993 | 100026944517 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000994 | 100026944518 | Pole | HFTD Tier 2 | Distribution | 2024-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000995 | 100026944710 | Pole | HFTD Tier 3 | Distribution | 2024-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000996 | 100026944519 | Other | HFTD Tier 3 | Distribution | 2024-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000997 | 100026944711 | Conductor | HFTD Tier 3 | Distribution | 2024-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000998 | 100026944713 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130000999 | 100026949967 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001000 | 100026949968 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001001 | 100026949969 | Other | HFTD Tier 2 | Distribution | 2024-12-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001002 | 100026950473 | Transformer | HFTD Tier 2 | Distribution | 2024-12-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001003 | 100026950474 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001004 | 100026950475 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001005 | 100026950476 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-12-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001006 | 100026960034 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001007 | 100026960035 | Pole | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001008 | 100026960321 | Pole | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001009 | 100026960322 | Pole | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001010 | 100026960324 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001011 | 100026960326 | Pole | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001012 | 100026960327 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001013 | 100026960328 | Pole | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001014 | 100026960332 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001015 | 100026969910 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001016 | 100026969912 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001017 | 100027464472 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001018 | 100027464472 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001019 | 100026969917 | Conductor | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001020 | 100026969918 | Other | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001021 | 100026969919 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001022 | 100026969920 | Other | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001023 | 100026969921 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001024 | 100026969922 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001025 | 100026969923 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001026 | 100026969924 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001027 | 100026969926 | Pole | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001028 | 100026969927 | Pole | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001029 | 100026969929 | Conductor | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001030 | 100026969933 | Pole | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001031 | 100026969934 | Other | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001032 | 100026969935 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001033 | 100026976244 | Other | HFTD Tier 2 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001034 | 100026976249 | Pole | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001035 | 100026976248 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001036 | 100026976356 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001037 | 100026976359 | Pole | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001038 | 100026976362 | Other | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001039 | 100026976363 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001040 | 100026976364 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001041 | 100026976365 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001042 | 100026976366 | Pole | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001043 | 100026976367 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001044 | 100026976368 | Pole | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001045 | 100026976369 | Other | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001046 | 100026976371 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001047 | 100026976370 | Pole | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001048 | 100026976373 | Anchor/Guy | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001049 | 100026976374 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001050 | 100026976376 | Pole | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001051 | 100026976375 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001052 | 100026976378 | Pole | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001053 | 100026976377 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001054 | 100026976383 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001055 | 100026976384 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001056 | 100026976385 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001057 | 100027012941 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001058 | 100027012942 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001059 | 100027012943 | Other | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001060 | 100027012945 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001061 | 100027012944 | Other | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001062 | 100027012946 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001063 | 100027012948 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001064 | 100027012949 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001065 | 100027013160 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001066 | 100027013161 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001067 | 100027013162 | Pole | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001068 | 100027013163 | Pole | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001069 | 100027013164 | Pole | HFTD Tier 2 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001070 | 100027013166 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001071 | 100027016356 | Other | HFTD Tier 2 | Distribution | 2024-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001072 | 100027016358 | Conductor | HFTD Tier 3 | Distribution | 2024-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001073 | 100027016359 | Conductor | HFTD Tier 2 | Distribution | 2024-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001074 | 100027016955 | Pole | HFTD Tier 3 | Distribution | 2024-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001075 | 100027016954 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001076 | 100027016956 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001077 | 100027016957 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001078 | 100027016959 | Pole | HFTD Tier 2 | Distribution | 2024-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001079 | 100027231801 | Other | HFTD Tier 2 | Distribution | 2025-02-05 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001080 | 100027315516 | Pole | HFTD Tier 2 | Distribution | 2025-02-25 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001081 | 100027313270 | Conductor | HFTD Tier 2 | Distribution | 2025-02-24 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001082 | 100027310345 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-02-24 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001083 | 100027310392 | Other | HFTD Tier 2 | Distribution | 2025-02-24 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001084 | 100027310391 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-02-24 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001085 | 100027243740 | Other | HFTD Tier 2 | Distribution | 2025-02-07 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001086 | 100027328890 | Other | HFTD Tier 2 | Distribution | 2025-02-28 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001087 | 100027329454 | Cross Arm | HFTD Tier 3 | Distribution | 2025-02-28 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001088 | 100027234333 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-05 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001089 | 100027232785 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-05 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001090 | 100027232787 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-05 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001091 | 100027330427 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-28 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001092 | 100027330428 | Pole | HFTD Tier 3 | Distribution | 2025-02-28 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001093 | 100027346574 | Pole | HFTD Tier 3 | Distribution | 2025-03-03 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001094 | 100027251827 | Cross Arm | HFTD Tier 3 | Distribution | 2025-02-11 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001095 | 100027245065 | Cross Arm | HFTD Tier 3 | Distribution | 2025-02-07 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001096 | 100027254603 | Pole | HFTD Tier 3 | Distribution | 2025-02-12 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001097 | 100027254164 | Cross Arm | HFTD Tier 3 | Distribution | 2025-02-12 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001098 | 100027324423 | Conductor | HFTD Tier 2 | Distribution | 2025-02-27 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001099 | 100027324425 | Conductor | HFTD Tier 2 | Distribution | 2025-02-27 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001100 | 100027268525 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-18 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001101 | 100027242474 | Pole | HFTD Tier 3 | Distribution | 2025-02-06 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001102 | 100027241743 | Pole | HFTD Tier 3 | Distribution | 2025-02-06 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001103 | 100027241744 | Pole | HFTD Tier 3 | Distribution | 2025-02-06 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001104 | 100027248002 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-10 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001105 | 100027248004 | Conductor | HFTD Tier 3 | Distribution | 2025-02-10 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001106 | 100027248003 | Pole | HFTD Tier 3 | Distribution | 2025-02-10 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001107 | 100027240481 | Cross Arm | HFTD Tier 3 | Distribution | 2025-02-06 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001108 | 100027240230 | Pole | HFTD Tier 3 | Distribution | 2025-02-06 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001109 | 100027229958 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-04 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001110 | 100027229957 | Cross Arm | HFTD Tier 3 | Distribution | 2025-02-04 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001111 | 100027229608 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-04 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001112 | 100027229607 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-02-04 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001113 | 100027229610 | Pole | HFTD Tier 3 | Distribution | 2025-02-04 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001114 | 100027388957 | Cross Arm | HFTD Tier 3 | Distribution | 2025-03-18 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001115 | 100027053566 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001116 | 100027053567 | Pole | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001117 | 100027053569 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001118 | 100027053940 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001119 | 100027053942 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001120 | 100027053943 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001121 | 100027053944 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001122 | 100027053947 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001123 | 100027053946 | Other | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001124 | 100027053948 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001125 | 100027053949 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001126 | 100027053951 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001127 | 100027053950 | Other | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001128 | 100027056887 | Pole | HFTD Tier 2 | Distribution | 2024-12-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001129 | 100027056888 | Pole | HFTD Tier 2 | Distribution | 2024-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001130 | 100027060239 | Conductor | HFTD Tier 2 | Distribution | 2024-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001131 | 100027060310 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001132 | 100027060313 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001133 | 100027060314 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001134 | 100027060315 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001135 | 100027060316 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001136 | 100027060317 | Pole | HFTD Tier 2 | Distribution | 2024-12-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001137 | 100027060318 | Other | HFTD Tier 2 | Distribution | 2024-12-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001138 | 100027247155 | Other | HFTD Tier 3 | Distribution | 2025-02-05 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001139 | 100027247156 | Other | HFTD Tier 2 | Distribution | 2025-02-06 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001140 | 100027357273 | Other | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001141 | 100027357274 | Other | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001142 | 100027357361 | Other | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001143 | 100027346082 | Pole | HFTD Tier 2 | Distribution | 2025-03-03 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001144 | 100027359974 | Other | HFTD Tier 3 | Distribution | 2025-03-06 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001145 | 100027375609 | Pole | HFTD Tier 3 | Distribution | 2025-03-12 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001146 | 100027436893 | Pole | HFTD Tier 2 | Distribution | 2025-03-26 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001147 | 100027436894 | Pole | HFTD Tier 2 | Distribution | 2025-03-26 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001148 | 100027435599 | Cross Arm | HFTD Tier 2 | Distribution | 2025-03-26 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001149 | 100027390655 | Pole | HFTD Tier 2 | Distribution | 2025-03-19 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001150 | 100027440013 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001151 | 100027439146 | Other | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001152 | 100027439058 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001153 | 100027439041 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001154 | 100027439040 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001155 | 100027425652 | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001156 | 100027389825 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-03-19 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001157 | 100027390758 | Pole | HFTD Tier 2 | Distribution | 2025-03-19 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001158 | 100027366287 | Pole | HFTD Tier 3 | Distribution | 2025-03-07 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001159 | 100027447482 | Pole | HFTD Tier 2 | Distribution | 2025-03-31 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001160 | 100027477277 | Other | HFTD Tier 3 | Distribution | 2025-03-27 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 1
1130001161 | P100609 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001162 | P101614 | Pole | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001163 | P102518 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001164 | P102519 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001165 | P103249 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-10-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001166 | P10341 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001167 | P104982 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-07-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001168 | P104982 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001169 | P104982 | Other | HFTD Tier 2 | Distribution | 2021-07-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001170 | P106547 | Pole | HFTD Tier 2 | Distribution | 2021-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001171 | P108381 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001172 | P110394 | Pole | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001173 | P110433 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001174 | P110609 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001175 | P111956 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001176 | P112067 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001177 | P112072 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001178 | P112081 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001179 | P112085 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001180 | P112086 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001181 | P112306 | Pole | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001182 | P113386 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001183 | P113400 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001184 | P113400 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001185 | P113400 | Other | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001186 | P113566 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001187 | P113566 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001188 | P114906 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001189 | P114906 | Other | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001190 | P114906 | Other | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001191 | P115355 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001192 | P115355 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001193 | P115355 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001194 | P115622 | Pole | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001195 | P115849 | Pole | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001196 | P116331 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001197 | P116548 | Pole | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001198 | P117154 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001199 | P117257 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001200 | P117257 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001201 | P117257 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001202 | P117257 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001203 | P117257 | Transformer | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001204 | P117587 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001205 | P117588 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001206 | P118555 | Other | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001207 | P118961 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001208 | P119447 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001209 | P119519 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001210 | P119728 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001211 | P119728 | Other | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001212 | P128871 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001213 | P130439 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001214 | P130711 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001215 | P130711 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001216 | P130773 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001217 | P130773 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001218 | P130943 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001219 | P130943 | Pole | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001220 | P13101 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-08-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001221 | P13102 | Other | HFTD Tier 2 | Distribution | 2021-08-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001222 | P131177 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001223 | P131178 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001224 | P13145 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001225 | P13145 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001226 | P13145 | Other | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001227 | P13145 | Other | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001228 | P13145 | Other | HFTD Tier 2 | Distribution | 2021-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001229 | P13145 | Other | HFTD Tier 2 | Distribution | 2021-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001230 | P13156 | Other | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001231 | P13175 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001232 | P133456 | Other | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001233 | P13465 | Pole | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001234 | P134687 | Other | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001235 | P134687 | Other | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001236 | P135067 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001237 | P135075 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001238 | P136166 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001239 | P136166 | Other | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001240 | P139091 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001241 | P139135 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001242 | P14985 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001243 | P15285 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001244 | P15460 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001245 | P15461 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001246 | P15462 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001247 | P15463 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001248 | P160114 | Pole | HFTD Tier 2 | Distribution | 2021-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001249 | P16131 | Pole | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001250 | P161457 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001251 | P16163 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001252 | P16163 | Pole | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001253 | P16173 | Other | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001254 | P16174 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001255 | P16174 | Pole | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001256 | P162577 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001257 | P163400 | Pole | HFTD Tier 2 | Distribution | 2021-07-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001258 | P164100 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001259 | P164112 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001260 | P164188 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001261 | P164218 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001262 | P164218 | Other | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001263 | P164263 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001264 | P164263 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001265 | P164936 | Pole | HFTD Tier 2 | Distribution | 2021-10-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001266 | P165189 | Pole | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001267 | P165190 | Pole | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001268 | P165201 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001269 | P165216 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001270 | P165224 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001271 | P165225 | Other | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001272 | P165225 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001273 | P165236 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001274 | P165724 | Pole | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001275 | P168743 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001276 | P168904 | Pole | HFTD Tier 2 | Distribution | 2021-08-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001277 | P169385 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001278 | P16938 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001279 | P16938 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001280 | P16938 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001281 | P171426 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001282 | P172470 | Other | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001283 | P172470 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001284 | P172498 | Other | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001285 | P172499 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001286 | P172499 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001287 | P172514 | Pole | HFTD Tier 2 | Distribution | 2021-12-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001288 | P172516 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001289 | P17396 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001290 | P175198 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001291 | P175199 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001292 | P17561 | Pole | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001293 | P176074 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001294 | P177248 | Pole | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001295 | P177248 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001296 | P177248 | Other | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001297 | P177251 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001298 | P177251 | Pole | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001299 | P177251 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001300 | P177251 | Other | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001301 | P177251 | Other | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001302 | P177252 | Pole | HFTD Tier 2 | Distribution | 2021-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001303 | P178595 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001304 | P179876 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001305 | P18734 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001306 | P18734 | Other | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001307 | P190007 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001308 | P190977 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001309 | P190981 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001310 | P190982 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001311 | P192111 | Pole | HFTD Tier 2 | Distribution | 2021-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001312 | P192111 | Other | HFTD Tier 2 | Distribution | 2021-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001313 | P192115 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001314 | P194136 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001315 | P194136 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001316 | P194136 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001317 | P196531 | Other | HFTD Tier 2 | Distribution | 2021-08-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001318 | P196531 | Pole | HFTD Tier 2 | Distribution | 2021-08-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001319 | P196545 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001320 | P196546 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001321 | P196549 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001322 | P196551 | Other | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001323 | P198453 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001324 | P199111 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001325 | P199399 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001326 | P199831 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001327 | P200143 | Pole | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001328 | P200150 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001329 | P200225 | Pole | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001330 | P202593 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001331 | P202593 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001332 | P205443 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001333 | P206096 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001334 | P206096 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001335 | P206918 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001336 | P206918 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001337 | P206967 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001338 | P206967 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001339 | P206967 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001340 | P207282 | Other | HFTD Tier 2 | Distribution | 2021-08-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001341 | P207282 | Pole | HFTD Tier 2 | Distribution | 2021-08-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001342 | P209041 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001343 | P209042 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001344 | P210771 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001345 | P210776 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001346 | P210777 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001347 | P211289 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001348 | P211567 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001349 | P211730 | Pole | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001350 | P212353 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001351 | P212497 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001352 | P212498 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001353 | P212546 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001354 | P213118 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001355 | P213119 | Other | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001356 | P213119 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001357 | P213126 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001358 | P213445 | Other | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001359 | P213445 | Pole | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001360 | P213850 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001361 | P214000 | Other | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001362 | P214135 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001363 | P214757 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001364 | P214767 | Pole | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001365 | P214952 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001366 | P214952 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001367 | P216205 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001368 | P216205 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001369 | P216391 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001370 | P216620 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001371 | P216698 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001372 | P216698 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001373 | P217016 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001374 | P217304 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001375 | P217319 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001376 | P217319 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001377 | P217319 | Other | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001378 | P217320 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001379 | P218186 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001380 | P218187 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001381 | P218262 | Pole | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001382 | P218266 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001383 | P218461 | Pole | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001384 | P218684 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001385 | P218689 | Pole | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001386 | P218879 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001387 | P218879 | Pole | HFTD Tier 2 | Distribution | 2021-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001388 | P224242 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001389 | P225174 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001390 | P233816 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001391 | P238774 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001392 | P238774 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001393 | P238929 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001394 | P238929 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001395 | P238975 | Pole | HFTD Tier 2 | Distribution | 2021-08-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001396 | P239111 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001397 | P239111 | Pole | HFTD Tier 2 | Distribution | 2021-08-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001398 | P239218 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001399 | P239785 | Other | HFTD Tier 2 | Distribution | 2021-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001400 | P245499 | Pole | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001401 | P247434 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001402 | P254677 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001403 | P274146 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001404 | P274677 | Pole | HFTD Tier 2 | Distribution | 2021-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001405 | P274848 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001406 | P275125 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001407 | P276969 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001408 | P278270 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001409 | P278871 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001410 | P30244 | Pole | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001411 | P30307 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001412 | P310605 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001413 | P311360 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001414 | P311360 | Pole | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001415 | P311361 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001416 | P311384 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001417 | P311384 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001418 | P311618 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001419 | P311619 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001420 | P311619 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001421 | P311621 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001422 | P311621 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001423 | P311811 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001424 | P311817 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001425 | P311818 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001426 | P311823 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001427 | P311823 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001428 | P311828 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001429 | P312057 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001430 | P312334 | Pole | HFTD Tier 2 | Distribution | 2021-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001431 | P312334 | Other | HFTD Tier 2 | Distribution | 2021-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001432 | P313564 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001433 | P313564 | Other | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001434 | P316603 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001435 | P317760 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001436 | P317762 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001437 | P318079 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001438 | P318087 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001439 | P318805 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001440 | P319272 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001441 | P32785 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001442 | P32813 | Other | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001443 | P32813 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001444 | P33611 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001445 | P33813 | Pole | HFTD Tier 2 | Distribution | 2021-07-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001446 | P36794 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001447 | P370037 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001448 | P370044 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001449 | P370057 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001450 | P371202 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001451 | P371202 | Conductor | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001452 | P371202 | Conductor | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001453 | P371204 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001454 | P373013 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001455 | P373107 | Transformer | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001456 | P373713 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001457 | P375248 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001458 | P375272 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001459 | P375273 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001460 | P376255 | Other | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001461 | P376280 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001462 | P376280 | Conductor | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001463 | P376920 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001464 | P377349 | Transformer | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001465 | P377349 | Other | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001466 | P40754 | Other | HFTD Tier 2 | Distribution | 2021-07-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001467 | P40757 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001468 | P40759 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001469 | P410119 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001470 | P41044 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001471 | P411160 | Other | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001472 | P411164 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001473 | P412368 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001474 | P412368 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001475 | P412373 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001476 | P412699 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001477 | P412699 | Other | HFTD Tier 2 | Distribution | 2021-08-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001478 | P412996 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001479 | P413502 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001480 | P413502 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001481 | P413724 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001482 | P413724 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001483 | P413981 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001484 | P414326 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001485 | P414858 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001486 | P41518 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001487 | P41518 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001488 | P41520 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001489 | P415228 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001490 | P415228 | Other | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001491 | P41522 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001492 | P41525 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001493 | P41526 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001494 | P41526 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001495 | P41527 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001496 | P415334 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001497 | P41535 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001498 | P41539 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001499 | P416002 | Pole | HFTD Tier 2 | Distribution | 2021-11-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001500 | P416448 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001501 | P417006 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001502 | P417177 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001503 | P417177 | Other | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001504 | P417177 | Other | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001505 | P41728 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001506 | P41729 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001507 | P41729 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001508 | P41733 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001509 | P41733 | Pole | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001510 | P41755 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001511 | P41755 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001512 | P41759 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001513 | P41759 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001514 | P41759 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001515 | P41761 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001516 | P41925 | Pole | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001517 | P42000 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001518 | P42001 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001519 | P42001 | Pole | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001520 | P42269 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001521 | P42270 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001522 | P42272 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001523 | P42560 | Other | HFTD Tier 3 | Distribution | 2020-05-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001524 | P44311 | Pole | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001525 | P44637 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001526 | P44647 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001527 | P44816 | Other | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001528 | P44836 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001529 | P44870 | Pole | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001530 | P44874 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001531 | P44874 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001532 | P44879 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001533 | P44879 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001534 | P44884 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001535 | P44884 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001536 | P44884 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001537 | P44907 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001538 | P44911 | Other | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001539 | P44911 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001540 | P44914 | Other | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001541 | P44914 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001542 | P44922 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001543 | P44922 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001544 | P44930 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001545 | P44938 | Pole | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001546 | P44942 | Pole | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001547 | P44946 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001548 | P44946 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001549 | P44947 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001550 | P45006 | Pole | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001551 | P45008 | Pole | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001552 | P45011 | Pole | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001553 | P45012 | Pole | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001554 | P45014 | Other | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001555 | P45014 | Other | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001556 | P45014 | Pole | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001557 | P45014 | Other | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001558 | P45034 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001559 | P45034 | Other | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001560 | P45034 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001561 | P45035 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001562 | P45035 | Other | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001563 | P45035 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001564 | P45135 | Pole | HFTD Tier 2 | Distribution | 2021-08-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001565 | P45153 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001566 | P45153 | Pole | HFTD Tier 2 | Distribution | 2021-08-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001567 | P45154 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001568 | P45189 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001569 | P45333 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001570 | P45333 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001571 | P45334 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001572 | P45336 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001573 | P45336 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001574 | P45429 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001575 | P45460 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001576 | P45460 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001577 | P45681 | Pole | HFTD Tier 2 | Distribution | 2021-08-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001578 | P45726 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001579 | P45740 | Other | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001580 | P45740 | Pole | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001581 | P45740 | Other | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001582 | P45866 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001583 | P45866 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001584 | P45893 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001585 | P45918 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001586 | P45931 | Pole | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001587 | P46002 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001588 | P46003 | Other | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001589 | P46074 | Cross Arm | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001590 | P46075 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001591 | P46075 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001592 | P46077 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001593 | P46077 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001594 | P46078 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001595 | P46078 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001596 | P46079 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001597 | P46080 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001598 | P46082 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001599 | P46083 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001600 | P46083 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001601 | P46084 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001602 | P46084 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001603 | P46086 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001604 | P46088 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001605 | P46088 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001606 | P46089 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001607 | P46089 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001608 | P46089 | Other | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001609 | P46089 | Pole | HFTD Tier 2 | Distribution | 2021-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001610 | P46094 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001611 | P46132 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001612 | P46137 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001613 | P46139 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001614 | P46141 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001615 | P46141 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001616 | P46143 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001617 | P46144 | Other | HFTD Tier 2 | Distribution | 2021-07-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001618 | P46176 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001619 | P46213 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001620 | P46213 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001621 | P46543 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001622 | P470088 | Pole | HFTD Tier 2 | Distribution | 2021-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001623 | P471261 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001624 | P471261 | Other | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001625 | P471899 | Pole | HFTD Tier 3 | Distribution | 2021-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001626 | P473840 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001627 | P474084 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001628 | P474084 | Other | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001629 | P474095 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001630 | P474171 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001631 | P474485 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001632 | P475572 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001633 | P476188 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001634 | P510934 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001635 | P511334 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001636 | P511335 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001637 | P511428 | Other | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001638 | P511856 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001639 | P512003 | Other | HFTD Tier 2 | Distribution | 2021-10-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001640 | P512472 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001641 | P513106 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001642 | P513106 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001643 | P513148 | Pole | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001644 | P513148 | Other | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001645 | P513454 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001646 | P514449 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001647 | P514713 | Pole | HFTD Tier 2 | Distribution | 2021-11-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001648 | P514787 | Transformer | HFTD Tier 2 | Distribution | 2021-11-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001649 | P516145 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001650 | P516145 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001651 | P516145 | Other | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001652 | P516887 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001653 | P516911 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001654 | P516911 | Other | HFTD Tier 2 | Distribution | 2021-10-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001655 | P517183 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001656 | P518158 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001657 | P518158 | Conductor | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001658 | P518780 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001659 | P518781 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001660 | P518799 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001661 | P518889 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001662 | P519456 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001663 | P519456 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001664 | P519456 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001665 | P519941 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001666 | P519941 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001667 | P570135 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001668 | P570135 | Transformer | HFTD Tier 2 | Distribution | 2021-12-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001669 | P570171 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001670 | P570546 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001671 | P570928 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001672 | P570928 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001673 | P570928 | Other | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001674 | P572015 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001675 | P572179 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001676 | P572974 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001677 | P575428 | Pole | HFTD Tier 2 | Distribution | 2021-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001678 | P577067 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001679 | P578769 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001680 | P578769 | Other | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001681 | P610381 | Other | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001682 | P610381 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001683 | P610382 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001684 | P610786 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001685 | P610786 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001686 | P610912 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001687 | P611479 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001688 | P611480 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001689 | P611872 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001690 | P612489 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001691 | P612772 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001692 | P613321 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001693 | P613994 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001694 | P614170 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001695 | P615216 | Pole | HFTD Tier 2 | Distribution | 2021-10-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001696 | P615235 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001697 | P615501 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001698 | P615501 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001699 | P615609 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001700 | P616235 | Pole | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001701 | P616769 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001702 | P616877 | Pole | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001703 | P617898 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001704 | P617964 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001705 | P617966 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001706 | P618293 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001707 | P618293 | Pole | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001708 | P618519 | Pole | HFTD Tier 2 | Distribution | 2021-10-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001709 | P618522 | Pole | HFTD Tier 2 | Distribution | 2021-10-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001710 | P618736 | Pole | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001711 | P618736 | Other | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001712 | P618739 | Pole | HFTD Tier 2 | Distribution | 2021-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001713 | P618838 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001714 | P618987 | Pole | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001715 | P619319 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001716 | P619319 | Other | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001717 | P619321 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001718 | P619578 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001719 | P671410 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001720 | P672676 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001721 | P674283 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001722 | P674283 | Conductor | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001723 | P675047 | Transformer | HFTD Tier 2 | Distribution | 2021-12-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001724 | P676869 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001725 | P676870 | Conductor | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001726 | P677097 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001727 | P677546 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001728 | P678679 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001729 | P710270 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001730 | P710270 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001731 | P710330 | Pole | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001732 | P710333 | Transformer | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001733 | P710543 | Transformer | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001734 | P710702 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001735 | P710702 | Other | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001736 | P710896 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001737 | P711354 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001738 | P711355 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001739 | P711445 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001740 | P711777 | Pole | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001741 | P711808 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001742 | P711972 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001743 | P711974 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001744 | P712344 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001745 | P712344 | Other | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001746 | P712344 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001747 | P712742 | Other | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001748 | P712742 | Pole | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001749 | P713162 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001750 | P713162 | Other | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001751 | P713270 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001752 | P713271 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001753 | P713379 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001754 | P713379 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001755 | P713811 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001756 | P713811 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001757 | P713971 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001758 | P713971 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001759 | P714026 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001760 | P714216 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001761 | P714238 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001762 | P714566 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001763 | P714566 | Other | HFTD Tier 2 | Distribution | 2021-10-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001764 | P716364 | Pole | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001765 | P716746 | Other | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001766 | P716746 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001767 | P716827 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001768 | P716961 | Pole | HFTD Tier 2 | Distribution | 2021-11-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001769 | P717218 | Other | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001770 | P717480 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001771 | P717884 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001772 | P717885 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001773 | P718039 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001774 | P718107 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001775 | P718781 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001776 | P719072 | Other | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001777 | P719072 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001778 | P719365 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001779 | P719365 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001780 | P719400 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001781 | P719401 | Other | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001782 | P719479 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001783 | P719479 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001784 | P719778 | Other | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001785 | P719778 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001786 | P719779 | Pole | HFTD Tier 2 | Distribution | 2021-08-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001787 | P719902 | Pole | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001788 | P719902 | Other | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001789 | P73879 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001790 | P74169 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001791 | P74314 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001792 | P74315 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001793 | P771923 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001794 | P771941 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001795 | P771942 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001796 | P774385 | Other | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001797 | P774385 | Conductor | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001798 | P776191 | Other | HFTD Tier 2 | Distribution | 2021-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001799 | P776191 | Other | HFTD Tier 2 | Distribution | 2021-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001800 | P777477 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001801 | P778741 | Pole | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001802 | P810654 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001803 | P811995 | Other | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001804 | P811995 | Other | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001805 | P811995 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001806 | P812348 | Pole | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001807 | P812368 | Pole | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001808 | P812541 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001809 | P812915 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001810 | P812960 | Pole | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001811 | P812960 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001812 | P812960 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001813 | P813513 | Pole | HFTD Tier 2 | Distribution | 2021-08-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001814 | P813699 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001815 | P814344 | Other | HFTD Tier 2 | Distribution | 2021-10-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001816 | P814364 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001817 | P814364 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001818 | P814404 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001819 | P814404 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001820 | P814488 | Pole | HFTD Tier 2 | Distribution | 2021-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001821 | P814488 | Other | HFTD Tier 2 | Distribution | 2021-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001822 | P814636 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001823 | P815142 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001824 | P815144 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001825 | P815145 | Pole | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001826 | P815203 | Pole | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001827 | P815206 | Pole | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001828 | P815293 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001829 | P815295 | Pole | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001830 | P815433 | Other | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001831 | P815433 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001832 | P815739 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001833 | P815766 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001834 | P815987 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001835 | P815987 | Other | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001836 | P816245 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001837 | P816370 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001838 | P816510 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001839 | P816510 | Other | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001840 | P817218 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001841 | P817254 | Pole | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001842 | P817583 | Pole | HFTD Tier 2 | Distribution | 2021-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001843 | P817591 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001844 | P819071 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001845 | P819071 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001846 | P86056 | Other | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001847 | P870520 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001848 | P870522 | Pole | HFTD Tier 2 | Distribution | 2021-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001849 | P871189 | Pole | HFTD Tier 2 | Distribution | 2021-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001850 | P871560 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001851 | P872004 | Pole | HFTD Tier 2 | Distribution | 2021-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001852 | P872498 | Pole | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001853 | P872532 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001854 | P873282 | Pole | HFTD Tier 2 | Distribution | 2021-11-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001855 | P873539 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001856 | P873591 | Pole | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001857 | P873787 | Anchor/Guy | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001858 | P874046 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001859 | P874538 | Other | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001860 | P875411 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001861 | P875520 | Pole | HFTD Tier 2 | Distribution | 2021-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001862 | P875622 | Pole | HFTD Tier 2 | Distribution | 2021-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001863 | P875779 | Pole | HFTD Tier 2 | Distribution | 2021-11-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001864 | P876243 | Pole | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001865 | P876244 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001866 | P876424 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001867 | P876729 | Pole | HFTD Tier 2 | Distribution | 2021-11-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001868 | P877036 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001869 | P970419 | Pole | HFTD Tier 2 | Distribution | 2021-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001870 | P970419 | Other | HFTD Tier 2 | Distribution | 2021-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001871 | P970731 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001872 | P971211 | Pole | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001873 | P971559 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001874 | P972342 | Pole | HFTD Tier 2 | Distribution | 2021-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001875 | Z10216 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001876 | Z118300 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001877 | Z16579 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001878 | Z181660 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001879 | P109812 | Pole | HFTD Tier 2 | Distribution | 2022-03-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001880 | P212073 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001881 | P614790 | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001882 | P517781 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001883 | P719324 | Pole | HFTD Tier 2 | Distribution | 2022-03-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001884 | P719327 | Pole | HFTD Tier 2 | Distribution | 2022-03-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001885 | P719327 | Other | HFTD Tier 2 | Distribution | 2022-03-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001886 | P102142 | Pole | HFTD Tier 2 | Distribution | 2022-03-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001887 | P117119 | Pole | HFTD Tier 2 | Distribution | 2022-03-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001888 | P719302 | Other | HFTD Tier 2 | Distribution | 2022-03-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001889 | P712144 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001890 | P712144 | Other | HFTD Tier 2 | Distribution | 2022-03-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001891 | P816465 | Pole | HFTD Tier 2 | Distribution | 2022-03-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001892 | P816465 | Other | HFTD Tier 2 | Distribution | 2022-03-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001893 | P816465 | Other | HFTD Tier 2 | Distribution | 2022-03-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001894 | P219453 | Fuse | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001895 | P235901 | Conductor | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001896 | P219452 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001897 | P418351 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001898 | P712058 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001899 | P813904 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001900 | P418732 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001901 | P517453 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001902 | P517448 | Pole | HFTD Tier 2 | Distribution | 2022-03-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001903 | P715289 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001904 | P812767 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001905 | P117145 | Pole | HFTD Tier 2 | Distribution | 2022-03-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001906 | P233617 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001907 | P318243 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001908 | P516638 | Pole | HFTD Tier 2 | Distribution | 2022-03-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001909 | P716012 | Pole | HFTD Tier 2 | Distribution | 2022-03-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001910 | P718078 | Pole | HFTD Tier 2 | Distribution | 2022-03-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001911 | P814809 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001912 | P816471 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001913 | P233518 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001914 | P233517 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001915 | P132977 | Transformer | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001916 | P204384 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001917 | P210344 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001918 | P210344 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001919 | P215879 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001920 | P215879 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001921 | P411024 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001922 | P416246 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001923 | P513415 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001924 | P519838 | Other | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001925 | P519838 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001926 | P111113 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001927 | P111113 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001928 | P193139 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001929 | P199888 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001930 | P15804 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001931 | P160512 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001932 | P162131 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001933 | P162131 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001934 | P162131 | Other | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001935 | P138693 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001936 | P168057 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001937 | P226793 | Conductor | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001938 | P217909 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001939 | P217909 | Other | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001940 | P221603 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001941 | P239281 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001942 | P31177 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001943 | P36715 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001944 | P36715 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001945 | P31169 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001946 | P31169 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001947 | P31123 | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001948 | P31174 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001949 | P323123 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001950 | P310648 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001951 | P31171 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001952 | P11683 | Cross Arm | HFTD Tier 3 | Distribution | 2022-10-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001953 | P11683 | Other | HFTD Tier 3 | Distribution | 2022-10-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001954 | P414971 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001955 | P419379 | Transformer | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001956 | P516958 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001957 | P516962 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001958 | P516957 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001959 | P516959 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001960 | P707069 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001961 | P707069 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001962 | P715532 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001963 | P619276 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001964 | P619276 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001965 | P811648 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001966 | P814118 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001967 | P814118 | Other | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001968 | P814594 | Transformer | HFTD Tier 2 | Distribution | 2022-02-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001969 | P814594 | Other | HFTD Tier 2 | Distribution | 2022-02-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001970 | P715526 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001971 | P715534 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001972 | P811169 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001973 | P715531 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001974 | P810583 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001975 | P812202 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001976 | P812202 | Other | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001977 | P812214 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001978 | P813228 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001979 | P814295 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001980 | P811447 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001981 | P816708 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001982 | P819435 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001983 | P813231 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001984 | P813231 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001985 | P202813 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001986 | P120814 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001987 | P122212 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001988 | P122211 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001989 | P211153 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001990 | P221407 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001991 | P221407 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001992 | P193245 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001993 | P225932 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001994 | P24981 | Transformer | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001995 | P25068 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001996 | P38961 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001997 | P318870 | Other | HFTD Tier 2 | Distribution | 2022-04-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001998 | P183607 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130001999 | P183607 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002000 | P814624 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002001 | P831226 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002002 | P16872 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002003 | P107564 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002004 | P280407 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002005 | P33763 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002006 | P776416 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-02-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002007 | P108139 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002008 | P108153 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002009 | P518783 | Other | HFTD Tier 2 | Distribution | 2022-03-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002010 | P518783 | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002011 | P518787 | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002012 | P518785 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002013 | P518785 | Other | HFTD Tier 2 | Distribution | 2022-03-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002014 | P518785 | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002015 | P518786 | Pole | HFTD Tier 2 | Distribution | 2022-03-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002016 | P670057 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002017 | P675330 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002018 | P675328 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002019 | P770282 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002020 | P103630 | Other | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002021 | P21284 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002022 | P21284 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002023 | P228276 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002024 | P228274 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002025 | P100383 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002026 | P100383 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002027 | P100380 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002028 | P165163 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002029 | P179870 | Other | HFTD Tier 2 | Distribution | 2022-03-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002030 | P165158 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002031 | P165166 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002032 | P410124 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002033 | P710353 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002034 | P411426 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002035 | P18411 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002036 | P117878 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002037 | P169550 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002038 | P13160 | Other | HFTD Tier 2 | Distribution | 2022-03-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002039 | P13160 | Pole | HFTD Tier 2 | Distribution | 2022-03-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002040 | P13310 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002041 | P137972 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002042 | P213296 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002043 | P14901 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002044 | P515862 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002045 | P714801 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002046 | P619893 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002047 | P717622 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002048 | P715872 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002049 | P877901 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002050 | P877901 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002051 | P238759 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002052 | P18401 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002053 | P19655 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002054 | P318633 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002055 | P411475 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002056 | P610054 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002057 | P610054 | Other | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002058 | P613542 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002059 | P719336 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002060 | P719336 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002061 | P714778 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002062 | P410558 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002063 | P132979 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002064 | P14743 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002065 | P14742 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002066 | P213454 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002067 | P214765 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002068 | P237969 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002069 | P35036 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002070 | P316893 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002071 | P414490 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002072 | P414490 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002073 | P415938 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002074 | P417062 | Transformer | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002075 | P417062 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002076 | P615526 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002077 | P615526 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002078 | P511327 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002079 | P514368 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002080 | P514368 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002081 | P514368 | Other | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002082 | P519495 | Transformer | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002083 | P610038 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002084 | P514843 | Other | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002085 | P615527 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002086 | P710590 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002087 | P711449 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002088 | P811625 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002089 | P711450 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002090 | P414495 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002091 | P514535 | Pole | HFTD Tier 2 | Distribution | 2022-03-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002092 | P25308 | Pole | HFTD Tier 2 | Distribution | 2022-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002093 | P109000 | Pole | HFTD Tier 2 | Distribution | 2022-03-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002094 | P107875 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002095 | P617979 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002096 | P617980 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002097 | P839764 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002098 | P86045 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002099 | P86042 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002100 | P86051 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002101 | P119492 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002102 | P119492 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002103 | P228082 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002104 | P219611 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002105 | P35982 | Other | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002106 | P310970 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002107 | P312569 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002108 | P510640 | Transformer | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002109 | P518670 | Transformer | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002110 | P714030 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002111 | P811740 | Transformer | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002112 | P613182 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002113 | P514696 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002114 | P815557 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002115 | P116900 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002116 | P511099 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002117 | P109459 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002118 | P162793 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002119 | P214015 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002120 | P417782 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002121 | P25319 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002122 | P225930 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002123 | P25315 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002124 | P25323 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002125 | P710767 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002126 | P710762 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002127 | P710766 | Other | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002128 | P710764 | Pole | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002129 | P710764 | Other | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002130 | P101331 | Pole | HFTD Tier 2 | Distribution | 2022-03-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002131 | Z31761 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002132 | Z31762 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002133 | Z31759 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002134 | Z31760 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002135 | Z219792 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002136 | Z219781 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002137 | Z188630 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002138 | Z188630 | Other | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002139 | P108130 | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002140 | P108134 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002141 | P128451 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002142 | P128463 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002143 | P128463 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002144 | P324293 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002145 | P253370 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002146 | P27896 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002147 | P324144 | Other | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002148 | P184755 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002149 | P107327 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002150 | P126063 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002151 | P167953 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002152 | P132945 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002153 | P132945 | Pole | HFTD Tier 2 | Distribution | 2022-02-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002154 | P220530 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002155 | P108919 | Pole | HFTD Tier 2 | Distribution | 2022-03-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002156 | P25303 | Other | HFTD Tier 2 | Distribution | 2022-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002157 | P812374 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002158 | P128403 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002159 | P28301 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002160 | P13285 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002161 | P319473 | Pole | HFTD Tier 2 | Distribution | 2022-03-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002162 | P515212 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002163 | P220951 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002164 | P220951 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002165 | P220984 | Transformer | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002166 | P13081 | Other | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002167 | P13081 | Transformer | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002168 | P13309 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002169 | P116046 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002170 | P511122 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002171 | P515604 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002172 | P515604 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002173 | P238758 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002174 | P270022 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002175 | P270022 | Pole | HFTD Tier 2 | Distribution | 2022-02-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002176 | P713708 | Pole | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002177 | P217259 | Other | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002178 | P311027 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002179 | P271013 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002180 | P878342 | Pole | HFTD Tier 2 | Distribution | 2022-02-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002181 | P128456 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002182 | P128456 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002183 | P224884 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002184 | P175296 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002185 | P175296 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002186 | P237856 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002187 | P237856 | Other | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002188 | P34174 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002189 | P470601 | Transformer | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002190 | P816974 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002191 | P121060 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002192 | P121060 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002193 | P127214 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002194 | P121934 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002195 | P220600 | Conductor | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002196 | P205387 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002197 | P25224 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002198 | P27088 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002199 | P27302 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002200 | P27902 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002201 | P26011 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002202 | P294291 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002203 | P28314 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002204 | P27912 | Transformer | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002205 | P18083 | Transformer | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002206 | P514435 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002207 | P514434 | Cross Arm | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002208 | P516901 | Pole | HFTD Tier 2 | Distribution | 2022-02-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002209 | P616416 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002210 | P616416 | Other | HFTD Tier 2 | Distribution | 2022-03-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002211 | P16975 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002212 | P16947 | Other | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002213 | P511897 | Fuse | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002214 | P412941 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002215 | P511324 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002216 | P616886 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002217 | P110320 | Pole | HFTD Tier 2 | Distribution | 2022-03-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002218 | P112951 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002219 | P172246 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002220 | P172246 | Pole | HFTD Tier 2 | Distribution | 2022-03-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002221 | P719301 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002222 | P719301 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002223 | P816093 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002224 | P816093 | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002225 | P219035 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002226 | P219035 | Transformer | HFTD Tier 3 | Distribution | 2022-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002227 | P219035 | Other | HFTD Tier 3 | Distribution | 2022-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002228 | P198942 | Pole | HFTD Tier 3 | Distribution | 2022-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002229 | P198942 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002230 | P200319 | Pole | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002231 | P273631 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002232 | P273631 | Other | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002233 | P278079 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002234 | P278079 | Pole | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002235 | P273634 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002236 | P200317 | Pole | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002237 | P772523 | Pole | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002238 | P198865 | Pole | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002239 | P273635 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002240 | P772524 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002241 | P772524 | Pole | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002242 | P311024 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002243 | P273638 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002244 | P273638 | Pole | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002245 | P273637 | Cross Arm | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002246 | P200284 | Pole | HFTD Tier 3 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002247 | P191121 | Cross Arm | HFTD Tier 2 | Distribution | 2022-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002248 | P770474 | Pole | HFTD Tier 3 | Distribution | 2022-12-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002249 | P198919 | Pole | HFTD Tier 3 | Distribution | 2022-12-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002250 | P273629 | Cross Arm | HFTD Tier 3 | Distribution | 2022-12-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002251 | P273623 | Pole | HFTD Tier 3 | Distribution | 2022-12-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002252 | P273622 | Cross Arm | HFTD Tier 3 | Distribution | 2022-12-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002253 | P273622 | Other | HFTD Tier 3 | Distribution | 2022-12-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002254 | P273625 | Cross Arm | HFTD Tier 3 | Distribution | 2022-12-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002255 | P277753 | Cross Arm | HFTD Tier 3 | Distribution | 2022-12-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002256 | P277753 | Conductor | HFTD Tier 3 | Distribution | 2022-12-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002257 | P273626 | Pole | HFTD Tier 3 | Distribution | 2022-12-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002258 | P38992 | Pole | HFTD Tier 2 | Distribution | 2022-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002259 | P18389 | Other | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002260 | P200533 | Pole | HFTD Tier 3 | Distribution | 2022-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002261 | P478388 | Other | HFTD Tier 2 | Distribution | 2022-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002262 | P312638 | Cross Arm | HFTD Tier 2 | Distribution | 2022-12-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002263 | P512420 | Pole | HFTD Tier 2 | Distribution | 2022-12-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002264 | P218736 | Other | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002265 | P15479 | Other | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002266 | P618261 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002267 | P618261 | Other | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002268 | P217728 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002269 | P213049 | Transformer | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002270 | P717780 | Transformer | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002271 | P416382 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002272 | P214104 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002273 | P214104 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002274 | P214104 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002275 | P118972 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002276 | P118972 | Transformer | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002277 | P162131 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002278 | P162131 | Pole | HFTD Tier 2 | Distribution | 2022-06-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002279 | P162131 | Other | HFTD Tier 2 | Distribution | 2022-06-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002280 | P17081 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002281 | P17081 | Conductor | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002282 | P17081 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002283 | P712282 | Transformer | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002284 | P15548 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002285 | P15548 | Other | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002286 | P10394 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002287 | P10394 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002288 | P10394 | Fuse | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002289 | P10394 | Transformer | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002290 | P617551 | Other | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002291 | P617551 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002292 | P617551 | Conductor | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002293 | P312587 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002294 | P312587 | Transformer | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002295 | P816642 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002296 | P612541 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002297 | P612541 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002298 | P612541 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002299 | P812762 | Transformer | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002300 | P216400 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002301 | P216400 | Transformer | HFTD Tier 2 | Distribution | 2022-04-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002302 | P812214 | Pole | HFTD Tier 2 | Distribution | 2022-06-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002303 | P818474 | Other | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002304 | P818474 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002305 | P818474 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002306 | P518546 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002307 | P30792 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002308 | P118940 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002309 | P13165 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002310 | P318871 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002311 | P813635 | Other | HFTD Tier 2 | Distribution | 2022-04-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002312 | P813635 | Pole | HFTD Tier 2 | Distribution | 2022-04-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002313 | P15375 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002314 | P516325 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002315 | P516325 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002316 | P114668 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002317 | P114668 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002318 | P115792 | Other | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002319 | P115792 | Other | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002320 | P410782 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002321 | P410782 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002322 | P215948 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002323 | P618785 | Other | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002324 | P17067 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002325 | P17067 | Other | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002326 | P253649 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002327 | P211547 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002328 | P124119 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002329 | P165821 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002330 | P165821 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002331 | P112107 | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002332 | P112107 | Other | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002333 | P619546 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002334 | P716461 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002335 | P111245 | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002336 | P219492 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002337 | P112183 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002338 | P164469 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002339 | P199815 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002340 | P511862 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002341 | P211336 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002342 | P512300 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002343 | P617546 | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002344 | P119686 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002345 | P119686 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002346 | P510914 | Conductor | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002347 | P816544 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002348 | P518213 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002349 | P518213 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002350 | P15570 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002351 | P16703 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002352 | P16703 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002353 | P212691 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002354 | P31171 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002355 | P715097 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002356 | P17493 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002357 | P610106 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002358 | P15569 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002359 | P161528 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002360 | P13992 | Other | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002361 | P518211 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002362 | P518211 | Other | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002363 | P131402 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002364 | P610841 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002365 | P610841 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002366 | P716089 | Other | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002367 | P218848 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002368 | P218848 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002369 | P510310 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002370 | P510310 | Other | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002371 | P19655 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002372 | P316199 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002373 | P132911 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002374 | P217400 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002375 | P217400 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002376 | P18614 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002377 | P813013 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002378 | P216761 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002379 | P712384 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002380 | P118754 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002381 | P712382 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002382 | P14792 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002383 | P210457 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002384 | P719616 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002385 | P414839 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002386 | P418443 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002387 | P210406 | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002388 | P211076 | Pole | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002389 | P213799 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002390 | P17059 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002391 | P239114 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002392 | P17057 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002393 | P210456 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002394 | P239257 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002395 | P518012 | Pole | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002396 | P114203 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002397 | P716309 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002398 | P716309 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002399 | P169516 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002400 | P518210 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002401 | P610497 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002402 | P312447 | Pole | HFTD Tier 2 | Distribution | 2022-05-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002403 | P14771 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002404 | P819678 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002405 | P417723 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002406 | P210488 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002407 | P212822 | Conductor | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002408 | P319633 | Pole | HFTD Tier 2 | Distribution | 2022-06-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002409 | P712704 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002410 | P113356 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002411 | P516958 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002412 | P419059 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002413 | P14791 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002414 | P418442 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002415 | P214282 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002416 | P18642 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002417 | P117952 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002418 | P319634 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002419 | P117486 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002420 | P14766 | Other | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002421 | P112115 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002422 | P318073 | Other | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002423 | P318073 | Other | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002424 | P713535 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002425 | P717781 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002426 | P15477 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002427 | P714995 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002428 | P713412 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002429 | P16699 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002430 | P16699 | Other | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002431 | P712887 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002432 | P417916 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002433 | P31169 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002434 | P31169 | Pole | HFTD Tier 2 | Distribution | 2022-06-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002435 | P511281 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002436 | P118973 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002437 | P10182 | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002438 | P30815 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002439 | P816916 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002440 | P810392 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002441 | P516959 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002442 | P211073 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002443 | P814410 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002444 | P215516 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002445 | P15480 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002446 | P419549 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002447 | P161948 | Other | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002448 | P217218 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002449 | P710336 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002450 | P514761 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002451 | P113491 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002452 | P239196 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002453 | P36208 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002454 | P618753 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002455 | P812612 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002456 | P812612 | Pole | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002457 | P811934 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002458 | P714994 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002459 | P36625 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002460 | P516957 | Cross Arm | HFTD Tier 2 | Distribution | 2022-06-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002461 | P818045 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002462 | P818045 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002463 | P317008 | Cross Arm | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002464 | P710731 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002465 | P215041 | Other | HFTD Tier 2 | Distribution | 2022-04-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002466 | P117521 | Pole | HFTD Tier 2 | Distribution | 2022-04-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002467 | P101106 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002468 | P212651 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002469 | P117641 | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002470 | P196251 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002471 | P36015 | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002472 | P412378 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002473 | P110414 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002474 | P110414 | Other | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002475 | P116712 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002476 | P116712 | Other | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002477 | P116887 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002478 | P116887 | Other | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002479 | P16027 | Fuse | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002480 | P16027 | Other | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002481 | P168137 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002482 | P168137 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002483 | P173315 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002484 | P173315 | Other | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002485 | P174808 | Other | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002486 | P17540 | Other | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002487 | P212398 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002488 | P212398 | Other | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002489 | P30234 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002490 | P30234 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002491 | P30234 | Transformer | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002492 | P413938 | Other | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002493 | P516523 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002494 | P516523 | Other | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002495 | P618052 | Other | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002496 | P618052 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002497 | P618052 | Other | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002498 | P771533 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002499 | P773213 | Other | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002500 | P773225 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002501 | P773969 | Other | HFTD Tier 2 | Distribution | 2022-09-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002502 | P816181 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002503 | P816181 | Other | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002504 | P818754 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002505 | P818754 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002506 | P871970 | Other | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002507 | P872511 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002508 | P872511 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002509 | P872530 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002510 | P874795 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002511 | P875166 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002512 | P875166 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002513 | P876562 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002514 | P876562 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002515 | P878938 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002516 | P878938 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002517 | P970809 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002518 | P977008 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002519 | P977008 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002520 | P119144 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002521 | P515371 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002522 | P515371 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002523 | P875374 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002524 | P875374 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002525 | P876445 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002526 | P876854 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002527 | P116894 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002528 | P212014 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002529 | P216153 | Other | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002530 | P478022 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002531 | P515037 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002532 | P516522 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002533 | P519854 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002534 | P576749 | Pole | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002535 | P710361 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002536 | P712573 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002537 | P715308 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002538 | P773644 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002539 | P816414 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002540 | P816414 | Pole | HFTD Tier 2 | Distribution | 2022-08-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002541 | P474936 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002542 | P119255 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002543 | P119255 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002544 | P13212 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002545 | P13212 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002546 | P167863 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002547 | P167863 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002548 | P173316 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002549 | P173316 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002550 | P173316 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002551 | P214576 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002552 | P214576 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002553 | P215262 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002554 | P215262 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002555 | P254174 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002556 | P254174 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002557 | P417290 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002558 | P417290 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002559 | P419160 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002560 | P419160 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002561 | P576745 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002562 | P870060 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002563 | P90093 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002564 | P90093 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002565 | P90093 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002566 | P90093 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002567 | P90147 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002568 | P90147 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002569 | P972699 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002570 | P111470 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002571 | P111470 | Transformer | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002572 | P116891 | Transformer | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002573 | P134865 | Transformer | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002574 | P172255 | Transformer | HFTD Tier 2 | Distribution | 2022-09-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002575 | P30163 | Transformer | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002576 | P319010 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002577 | P319010 | Transformer | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002578 | P319283 | Transformer | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002579 | P515161 | Transformer | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002580 | P515368 | Transformer | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002581 | P713267 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002582 | P713267 | Transformer | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002583 | P713719 | Transformer | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002584 | P971176 | Transformer | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002585 | P101230 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002586 | P102597 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002587 | P107652 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002588 | P107714 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002589 | P107716 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002590 | P107716 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002591 | P111345 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002592 | P111378 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002593 | P111474 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002594 | P111482 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002595 | P111486 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002596 | P111809 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002597 | P112539 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002598 | P113017 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002599 | P113126 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002600 | P119155 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002601 | P119155 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002602 | P119258 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002603 | P121647 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002604 | P121649 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002605 | P134864 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002606 | P15137 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002607 | P15137 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002608 | P170883 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002609 | P172263 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002610 | P173722 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002611 | P173722 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002612 | P173856 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002613 | P174255 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002614 | P175013 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002615 | P177857 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002616 | P178320 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002617 | P178521 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002618 | P212011 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002619 | P213041 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002620 | P216152 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002621 | P216692 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002622 | P219683 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002623 | P237475 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002624 | P270547 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002625 | P270547 | Pole | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002626 | P271392 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002627 | P271400 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002628 | P276283 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002629 | P276284 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002630 | P276432 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002631 | P277807 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002632 | P277808 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002633 | P310171 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002634 | P319047 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002635 | P320776 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002636 | P321097 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002637 | P32842 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002638 | P32842 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002639 | P376165 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002640 | P412989 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002641 | P418157 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002642 | P418873 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002643 | P418873 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002644 | P474535 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002645 | P475568 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002646 | P511046 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002647 | P511046 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002648 | P513187 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002649 | P513187 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002650 | P514022 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002651 | P514044 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002652 | P515372 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002653 | P519365 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002654 | P575216 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002655 | P576747 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002656 | P610256 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002657 | P611754 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002658 | P613643 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002659 | P613643 | Pole | HFTD Tier 2 | Distribution | 2022-08-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002660 | P615074 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002661 | P618053 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002662 | P619915 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002663 | P710305 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002664 | P712001 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002665 | P712966 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002666 | P713175 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002667 | P713175 | Other | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002668 | P714034 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002669 | P714975 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002670 | P716371 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002671 | P718033 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002672 | P718573 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002673 | P719599 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002674 | P719599 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002675 | P719814 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002676 | P773645 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002677 | P774391 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002678 | P775414 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002679 | P811017 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002680 | P811950 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002681 | P811951 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002682 | P813298 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002683 | P813298 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002684 | P813312 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002685 | P816615 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002686 | P816615 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002687 | P816615 | Other | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002688 | P816654 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002689 | P819187 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002690 | P873898 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002691 | P873898 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002692 | P874596 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002693 | P878117 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002694 | P91438 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002695 | P972009 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002696 | P21786 | Switch | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002697 | P103782 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002698 | P10412 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002699 | P107655 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002700 | P107659 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002701 | P107715 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002702 | P107719 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002703 | P107728 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002704 | P109851 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002705 | P111380 | Pole | HFTD Tier 2 | Distribution | 2022-08-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002706 | P111477 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002707 | P111625 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002708 | P112028 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002709 | P112542 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002710 | P113443 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002711 | P113699 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002712 | P113700 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002713 | P117559 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002714 | P117859 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002715 | P13087 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002716 | P134836 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002717 | P134856 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002718 | P134858 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002719 | P139511 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002720 | P15084 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002721 | P161347 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002722 | P163362 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002723 | P163566 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002724 | P165272 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002725 | P165603 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002726 | P165961 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002727 | P166116 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002728 | P167223 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002729 | P167224 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002730 | P167719 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002731 | P169126 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002732 | P175384 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002733 | P175399 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002734 | P175417 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002735 | P191636 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002736 | P191636 | Anchor/Guy | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002737 | P194228 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002738 | P208524 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002739 | P210433 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002740 | P211047 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002741 | P212124 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002742 | P213461 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002743 | P216156 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002744 | P219485 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002745 | P228888 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002746 | P237729 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002747 | P245093 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002748 | P245111 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002749 | P25589 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002750 | P26442 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002751 | P273802 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002752 | P277300 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002753 | P27996 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002754 | P311436 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002755 | P33794 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002756 | P36982 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002757 | P370804 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002758 | P370806 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002759 | P374930 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002760 | P410104 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002761 | P410104 | Conductor | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002762 | P410105 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002763 | P414198 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002764 | P510609 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002765 | P512420 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002766 | P513788 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002767 | P518783 | Other | HFTD Tier 2 | Distribution | 2022-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002768 | P518783 | Pole | HFTD Tier 2 | Distribution | 2022-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002769 | P574572 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002770 | P576675 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002771 | P611522 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002772 | P612426 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002773 | P618195 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002774 | P619756 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002775 | P619863 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002776 | P679762 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002777 | P712734 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002778 | P716353 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002779 | P716989 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002780 | P718230 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002781 | P718796 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002782 | P770269 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002783 | P772394 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002784 | P773295 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002785 | P775020 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002786 | P775097 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002787 | P775097 | Conductor | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002788 | P775652 | Pole | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002789 | P777027 | Pole | HFTD Tier 2 | Distribution | 2022-09-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002790 | P810710 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002791 | P812323 | Pole | HFTD Tier 2 | Distribution | 2022-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002792 | P819188 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002793 | P870041 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002794 | P870946 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002795 | P872866 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002796 | P873021 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002797 | P873551 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002798 | P874034 | Pole | HFTD Tier 2 | Distribution | 2022-09-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002799 | P874648 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002800 | P875488 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002801 | P875645 | Pole | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002802 | P876355 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002803 | P876636 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002804 | P876682 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002805 | P876928 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002806 | P877083 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002807 | P877447 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002808 | P877655 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002809 | P878939 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002810 | P90098 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002811 | P91442 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002812 | P970147 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002813 | P970786 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002814 | P972386 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002815 | P972740 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002816 | P977085 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002817 | P977152 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002818 | P977153 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002819 | P111778 | Other | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002820 | P122573 | Other | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002821 | P130839 | Other | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002822 | P172048 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002823 | P172268 | Other | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002824 | P21806 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002825 | P474537 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002826 | P518409 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002827 | P679565 | Other | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002828 | P873370 | Other | HFTD Tier 2 | Distribution | 2022-08-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002829 | P111381 | Other | HFTD Tier 2 | Distribution | 2022-08-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002830 | P111483 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002831 | P112394 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002832 | P112547 | Pole | HFTD Tier 2 | Distribution | 2022-07-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002833 | P168809 | Pole | HFTD Tier 2 | Distribution | 2022-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002834 | P178522 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002835 | P198176 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002836 | P214250 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002837 | P245667 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002838 | P370805 | Other | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002839 | P38798 | Pole | HFTD Tier 2 | Distribution | 2022-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002840 | P38992 | Pole | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002841 | P411475 | Pole | HFTD Tier 2 | Distribution | 2022-08-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002842 | P513918 | Pole | HFTD Tier 2 | Distribution | 2022-07-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002843 | P518785 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002844 | P518785 | Other | HFTD Tier 2 | Distribution | 2022-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002845 | P518785 | Pole | HFTD Tier 2 | Distribution | 2022-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002846 | P518786 | Pole | HFTD Tier 2 | Distribution | 2022-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002847 | P518787 | Pole | HFTD Tier 2 | Distribution | 2022-08-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002848 | P579767 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002849 | P613900 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002850 | P712471 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002851 | P713268 | Other | HFTD Tier 2 | Distribution | 2022-08-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002852 | P819845 | Other | HFTD Tier 2 | Distribution | 2022-07-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002853 | P109611 | Pole | HFTD Tier 2 | Distribution | 2022-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002854 | P112080 | Pole | HFTD Tier 2 | Distribution | 2022-06-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002855 | P113385 | Pole | HFTD Tier 2 | Distribution | 2022-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002856 | P128871J | Pole | HFTD Tier 2 | Distribution | 2022-05-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002857 | P134684 | Cross Arm | HFTD Tier 2 | Distribution | 2022-07-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002858 | P134687 | Pole | HFTD Tier 2 | Distribution | 2022-08-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002859 | P172508 | Pole | HFTD Tier 2 | Distribution | 2022-05-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002860 | P177886J | Pole | HFTD Tier 2 | Distribution | 2022-03-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002861 | P190927 | Pole | HFTD Tier 2 | Distribution | 2022-03-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002862 | P205491 | Pole | HFTD Tier 2 | Distribution | 2022-11-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002863 | P210299 | Pole | HFTD Tier 2 | Distribution | 2022-05-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002864 | P218242 | Pole | HFTD Tier 2 | Distribution | 2022-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002865 | P218267 | Pole | HFTD Tier 2 | Distribution | 2022-10-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002866 | P25307 | Pole | HFTD Tier 2 | Distribution | 2022-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002867 | P253754 | Pole | HFTD Tier 2 | Distribution | 2022-05-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002868 | P311620 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002869 | P36794 | Pole | HFTD Tier 2 | Distribution | 2022-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002870 | P41528 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002871 | P41530 | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002872 | P41532 | Pole | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002873 | P416447 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002874 | P41756 | Pole | HFTD Tier 2 | Distribution | 2022-05-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002875 | P42268 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002876 | P44849 | Pole | HFTD Tier 2 | Distribution | 2022-04-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002877 | P46003 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002878 | P471274J | Pole | HFTD Tier 2 | Distribution | 2022-04-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002879 | P517981J | Pole | HFTD Tier 2 | Distribution | 2022-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002880 | P518023 | Pole | HFTD Tier 2 | Distribution | 2022-04-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002881 | P571595 | Pole | HFTD Tier 2 | Distribution | 2022-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002882 | P614520J | Pole | HFTD Tier 2 | Distribution | 2022-05-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002883 | P615234 | Pole | HFTD Tier 2 | Distribution | 2022-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002884 | P618278 | Pole | HFTD Tier 2 | Distribution | 2022-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002885 | P672639 | Other | HFTD Tier 2 | Distribution | 2022-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002886 | P672640 | Other | HFTD Tier 2 | Distribution | 2022-10-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002887 | P712243 | Pole | HFTD Tier 2 | Distribution | 2022-06-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002888 | P713378 | Pole | HFTD Tier 2 | Distribution | 2022-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002889 | P719899 | Other | HFTD Tier 2 | Distribution | 2022-05-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002890 | P719900 | Other | HFTD Tier 2 | Distribution | 2022-05-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002891 | P719901 | Other | HFTD Tier 2 | Distribution | 2022-05-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002892 | P74312 | Pole | HFTD Tier 2 | Distribution | 2022-03-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002893 | P775612J | Pole | HFTD Tier 2 | Distribution | 2022-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 1
1130002894 | P875924 | Pole | HFTD Tier 2 | Distribution | 2022-11-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 1