## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | REPORTING QUARTER | QUANTITATIVE ACTUAL PROGRESS Q1 | QUANTITATIVE ACTUAL PROGRESS Q1-2 | QUANTITATIVE ACTUAL PROGRESS Q1-3 | QUANTITATIVE ACTUAL PROGRESS Q1-4 | QUALITATIVE ACTUAL PROGRESS Q1 | QUALITATIVE ACTUAL PROGRESS Q1-2 | QUALITATIVE ACTUAL PROGRESS Q1-3 | QUALITATIVE ACTUAL PROGRESS Q1-4 | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | BV | 2023-05-01 | Program |  |  | Public outreach and education awareness program | Development and deployment of public outreach and education awareness program(s) for wildfires; outages due to wildfires, PSPS events, and protective equipment and device settings; service restoration before, during, and after the incidents and vegetation management. | Development and deployment of public outreach and education awareness program(s) for wildfires; outages due to wildfires, PSPS events, and protective equipment and device settings; service restoration before, during, and after the incidents and vegetation management. | Community Outreach and Engagement | Public outreach and education awareness program |  | 8.5.2 | COE_1 | BV_Community Outreach and Engagement_Public outreach and education awareness program_COE_1_2023 | 321 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | No | Number of Public Outreach and Education Events |  | 2025 | 3 | 310 | 572 | 851 | [5 empty] | Completed
1010000001 | BV | 2023-05-01 | Program |  |  | Engagement with access and functional needs populations | Actions taken understand, evaluate, design, and implement wildfire and PSPS risk mitigation strategies, policies, and procedures specific to access and functional needs customers. | Actions taken understand, evaluate, design, and implement wildfire and PSPS risk mitigation strategies, policies, and procedures specific to access and functional needs customers. | Community Outreach and Engagement | Engagement with access and functional needs populations |  | 8.5.3 | COE_2 | BV_Community Outreach and Engagement_Engagement with access and functional needs populations_COE_2_2023 | 339 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | No | AFN Customer Needs Verifications |  | 2025 | 3 | 6 | 12 | 18 | [5 empty] | Completed
1010000002 | BV | 2023-05-01 | Program |  |  | Collaboration on local wildfire mitigation planning | Development and integration of plans, programs, and/or policies for collaborating with communities on local wildfire mitigation planning, such as wildfire safety elements in general plans, community wildfire protection plans, and local multi-hazard mitigation plans. | Development and integration of plans, programs, and/or policies for collaborating with communities on local wildfire mitigation planning, such as wildfire safety elements in general plans, community wildfire protection plans, and local multi-hazard mitigation plans. | Community Outreach and Engagement | Collaboration on local wildfire mitigation planning |  | 8.5.4 | COE_3 | BV_Community Outreach and Engagement_Collaboration on local wildfire mitigation planning_COE_3_2023 | 354 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | No |  |  | 2025 | 3 |  |  |  |  | Completed | Completed | Completed |  | Completed
1010000003 | BV | 2023-05-01 | Program |  |  | Best practice sharing with other utilities | Development and integration of an electrical corporation’s policy for sharing best practices and collaborating with other electrical corporations on technical and programmatic aspects of its WMP program. | Development and integration of an electrical corporation’s policy for sharing best practices and collaborating with other electrical corporations on technical and programmatic aspects of its WMP program. | Community Outreach and Engagement | Best practice sharing with other utilities |  | 8.5.5 | COE_4 | BV_Community Outreach and Engagement_Best practice sharing with other utilities_COE_4_2023 | 354 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | No | Working Groups, Conferences |  | 2025 | 3 | 25 | 62 | 96 | [5 empty] | Completed
1010000004 | BV | 2023-05-01 | Program |  |  | Emergency preparedness plan | Development and integration of wildfire- and PSPS-specific emergency strategies, practices, policies, and procedures into the electrical corporation’s overall emergency plan based on the minimum standards described in GO 166. | Development and integration of wildfire- and PSPS-specific emergency strategies, practices, policies, and procedures into the electrical corporation’s overall emergency plan based on the minimum standards described in GO 166. | Emergency Preparedness | Emergency preparedness plan |  | 8.4.2 | EP_1 | BV_Emergency Preparedness_Emergency preparedness plan_EP_1_2023 | 274 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000005 | BV | 2023-05-01 | Program |  |  | External collaboration and coordination | Actions taken to coordinate wildfire and PSPS emergency preparedness with relevant public safety partners including the state, cities, counties, and tribes. | Actions taken to coordinate wildfire and PSPS emergency preparedness with relevant public safety partners including the state, cities, counties, and tribes. | Emergency Preparedness | External collaboration and coordination |  | 8.4.3 | EP_2 | BV_Emergency Preparedness_External collaboration and coordination_EP_2_2023 | 303 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000006 | BV | 2023-05-01 | Program |  |  | Public emergency communication strategy | Development and integration of a comprehensive communication strategy to inform essential customers and other stakeholder groups of wildfires, outages due to wildfires, and PSPS and service restoration, as required by Public Utilities Code section 768.6. | Development and integration of a comprehensive communication strategy to inform essential customers and other stakeholder groups of wildfires, outages due to wildfires, and PSPS and service restoration, as required by Public Utilities Code section 768.6. | Emergency Preparedness | Public emergency communication strategy |  | 8.4.4 | EP_3 | BV_Emergency Preparedness_Public emergency communication strategy_EP_3_2023 | 336 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000007 | BV | 2023-05-01 | Program |  |  | Preparedness and planning for service restoration | Development and integration of the electrical corporation’s plan to restore service after an outage due to a wildfire or PSPS event. | Development and integration of the electrical corporation’s plan to restore service after an outage due to a wildfire or PSPS event. | Emergency Preparedness | Preparedness and planning for service restoration |  | 8.4.5 | EP_4 | BV_Emergency Preparedness_Preparedness and planning for service restoration_EP_4_2023 | 345 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000008 | BV | 2023-05-01 | Program |  |  | Customer support in wildfire and PSPS emergencies | Development and deployment of programs, systems, and protocols to support residential and non- residential customers in wildfire emergencies and PSPS events. | Development and deployment of programs, systems, and protocols to support residential and non- residential customers in wildfire emergencies and PSPS events. | Emergency Preparedness | Customer support in wildfire and PSPS emergencies |  | 8.4.6 | EP_5 | BV_Emergency Preparedness_Customer support in wildfire and PSPS emergencies_EP_5_2023 | 354 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000009 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Covered Conductor Replacement Project | BVES plans to cover all overhead bare sub-transmission lines (34.5 kV) in the High Fire-Threat District (HFTD) Tiers 2 and 3 covering approximately 4.3 circuit miles per year. This action will result in the entire 34.5 kV system in the HFTD being underground or covered; thereby, reducing the risk of sub-transmission lines contacting vegetation or other debris and causing an ignition to near zero. BVES also plans to cover all overhead bare distribution lines (4 kV) in the High Fire-Threat District (HFTD) Tiers 2 and 3 over a 20-year period. The focus of the first 10 years of the project are the highest risk areas and will result in covering approximately 8.6 circuit miles per year. This action will eventually result in the entire 4 kV system in the HFTD being underground or covered; thereby, reducing the risk of distribution lines contacting vegetation or other debris and causing an ignition to near zero. | Installation of covered or insulated conductors to replace standard bare or unprotected conductors (defined in accordance with GO 95 as supply conductors, including but not limited to lead wires, not enclosed in a grounded metal pole or not covered by: a “suitable protective covering” (in accordance with Rule 22.8), grounded metal conduit, or grounded metal sheath or shield). In accordance with GO 95, conductor is defined as a material suitable for: (1) carrying electric current, usually in the form of a wire, cable or bus bar, or (2) transmitting light in the case of fiber optics; insulated conductors as those which are surrounded by an insulating material (in accordance with Rule 21.6), the dielectric strength of which is sufficient to withstand the maximum difference of potential at normal operating voltages of the circuit without breakdown or puncture; and suitable protective covering as a covering of wood or other non-conductive material having the electrical insulating efficiency (12kV/in. dry) and impact strength (20ft.-lbs) of 1.5 inches of redwood or other material meeting the requirements of Rule 22.8-A, 22.8-B, 22.8-C or 22.8-D. | Grid Design, Operations, and Maintenance | Covered conductor installation |  | 8.1.2.1 | GD_1 | BV_Grid Design, Operations, and Maintenance_Covered conductor installation_GD_1_2023 | 131 | Wildfire exposure potential Wildfire vulnerability | No | Circuit Miles of Line Replaced |  | 2025 | 3 | 0 | 3 | 7.73 | [5 empty] | Completed
1010000010 | BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | Bear Valley Solar Energy Project | BVES proposes an Energy Storage (seperate project) and Solar Generating Facility Project that are designed to reduce the likelihood and consequences of disruptive events and provide many of the benefits outlined the Grid Resilience and Innovation Partnerships (GRIP) program. The proposed projects enhance safety, reliability and quality of service. The projects are designed to significantly mitigate the potential of ignitions by removing the need to expand sub-transmission supply lines to Bear Valley’s service area, which may cause wildfires with catastrophic loss of life and enormous loss of property. These projects significantly reduce the need for Public Safety Power Shut-off (PSPS) and the impact of Southern California Edison (SCE) initiating a PSPS event affecting the supply lines to Bear Valley. BVES proposes to construct the Bear Valley Solar Energy Project (BVSEP), 5 MW alternating current single-axis tracker solar generation facility, to be constructed on a 21-acre site within the BVES service territory. This system will directly feed the distribution system benefiting all customers. One of the purposes of the solar energy project is to minimize the impact of the loss of all SCE energy imports to the BVES service area due to a SCE-directed PSPS of the SCE supply lines to BVES. BVES energy imports from SCE are subject to PSPS and while these lines may be required to be de-energized by SCE, the BVES service area may not require PSPS. This project will be submitted to the CPUC and the County of San Bernardino in 2023. If the proposed project is approved it will allow BVES to internally supply energy to most of its customers by utilizing its existing peaking power plant (8.4 MW), along with the BVSEP and the energy storage battery to minimize the effects of any PSPS event. | Development and deployment of microgrids that may reduce the risk of ignition, risk from PSPS, and wildfire consequence. “Microgrid” is defined by Public Utilities Code section 8370(d). | Grid Design, Operations, and Maintenance | Microgrids |  | 8.1.2.7 | GD_10 | BV_Grid Design, Operations, and Maintenance_Microgrids_GD_10_2023 | 139 | PSPS exposure potential PSPS vulnerability | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | Delayed | BVES is pursuing regulatory approval from the CPUC. Project complletion is expected in 2027 and has been updated in BVES's 2026-2028 WMP.
1010000011 | BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | Energy Storage Project | BVES proposes an Energy Storage and Solar Generating Facility Project (seperate project) that are designed to reduce the likelihood and consequences of disruptive events and provide many of the benefits outlined the Grid Resilience and Innovation Partnerships (GRIP) program. The proposed projects enhance safety, reliability and quality of service. The projects are designed to significantly mitigate the potential of ignitions by removing the need to expand sub-transmission supply lines to Bear Valley’s service area, which may cause wildfires with catastrophic loss of life and enormous loss of property. These projects significantly reduce the need for Public Safety Power Shut-off (PSPS) and the impact of Southern California Edison (SCE) initiating a PSPS event affecting the supply lines to Bear Valley. BVES proposes to construct an energy storage project of approximately 5 MW/20 MWh (four-hour) Lithium-Ion NMC utility-grade battery located in the BVES maintenance yard. This project will complement the Bear Valley Solar Energy Project (BVSEP), 5 MW alternating current single-axis tracker solar generation facility, to be constructed on a 21-acre site within the BVES service territory. This system will directly feed the distribution system benefiting all customers. One of the purposes of the storage project is to minimize the impact of the loss of all SCE energy imports to the BVES service area due to a SCE-directed PSPS of the SCE supply lines to BVES. BVES energy imports from SCE are subject to PSPS and while these lines may be required to be de-energized by SCE, the BVES service area may not require PSPS. The project will be submitted to the CPUC and the County of San Bernardino in 2023. If the project is approved it will allow BVES to internally supply energy to most of its customers by utilizing its existing peaking power plant (8.4 MW), along with the BVSEP and the energy storage battery to minimize the effects of any PSPS event. | Development and deployment of microgrids that may reduce the risk of ignition, risk from PSPS, and wildfire consequence. “Microgrid” is defined by Public Utilities Code section 8370(d). | Grid Design, Operations, and Maintenance | Microgrids |  | 8.1.2.7 | GD_11 | Grid Design, Operations, and Maintenance_Microgrids_GD_11_2023 | 139 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | Delayed | BVES is pursuing regulatory approval from the CPUC. Project complletion is expected in 2027 and has been updated in BVES's 2026-2028 WMP.
1010000012 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Substation Automation | The project aims to connect 9 substations to Bear Valley’s SCADA network in order to allow remote real-time monitoring, reporting, and documenting key substation parameters over 3 years. The project involves the following elements: installing SCADA enabled control equipment, enhancing telemetry, and creating the capability to collect and modify settings remotely. This project will establish a robust and secure IP communications network across the distribution system to fully enable monitoring and control of critical equipment at the substations throughout the distribution system. Critical switches at substations will be automated and connected to SCADA in a phased approach. Connectivity to SCADA will be via the BVES service area fiber optic network. Additionally, sensors will be placed throughout the substations to continuously monitor volt-ampere reactive (VAR) performance and power quality. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | 8.1.2.8 | GD_12 | Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_12_2023 | 140 | PSPS exposure potential PSPS vulnerability | No | Number of Substations Automated and Connected to SCADA |  | 2025 | 3 | 0 | 1 | 2 | [5 empty] | In Progress
1010000013 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Switch and Field Device Automation | This project aims to automate and connect to Bear Valley’s SCADA network 28 sub-transmission (34 kV) switches and distribution switches over the next 4 years (2023 to 2026) in order to allow remote real-time monitoring, reporting, and documenting key 16 switch parameters and enable remote operation of the switches. The project involves the following elements: installing SCADA enabled control equipment, enhancing telemetry, and creating the capability to collect and modify settings remotely. This project will establish a robust and secure IP communications network across the sub-transmission and distribution systems to fully enable monitoring and control of critical switches throughout the sub-transmission and distribution systems. Critical switches in the system will be automated and connected to SCADA in a phased approach. Connectivity to SCADA will be via the BVES service area fiber optic network and in some cases via radio/cellular data transfer equipment. This project will mitigate and/or reduce PSPS events in terms of geographic scope and number of customers affected not covered by another initiative. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | 8.1.2.8 | GD_13 | Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_13_2023 | 142 | PSPS exposure potential PSPS vulnerability | No | Number of Field Switches Automated and Connected to SCADA |  | 2025 | 3 | 3 | 5 | 10 | [5 empty] | In Progress
1010000014 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Capacitor Bank Upgrade Project | The Capacitor Bank Upgrade Project aims to replace 24 aging capacitor banks from 2023 – 2026 with updated SCADA enabled capacitor banks. 23 of the capacitor banks are overhead type and 1 is underground pad mounted type. The existing capacitor banks are manually operated units, are nearing the end of their useful life (all greater than 40 years old), and are showing the telltale signs of near-term failure both in electronic performance and structurally, which may lead to the potential for fire and explosion hazards (catastrophic failure). The project will study the locations to ensure that they are optimal for providing the necessary voltage support and control in the distribution system such that customers receive the proper voltage at their connecting points. The capacitors will be replaced with 450KVAR 3Phase units that are fully capable of being connected to SCADA for remote control and monitoring. Connectivity to SCADA will be via radio/cellular data transfer equipment and the BVES service area fiber optic network. This will allow Bear Valley to control voltage by placing or removing the capacitor banks from service as needed without having to send a crew to manually operate the capacitor banks. Additionally, the capacitor banks will be continuously monitored to ensure the banks do not overheat or have excessive voltage which may lead to catastrophic failure. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | 8.1.2.8 | GD_14 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_14_2023 | 140 | PSPS exposure potential PSPS vulnerability | No | Number of Capacitor Banks Replaced and Connected to SCADA |  | 2025 | 3 | 0 | 0 | 5 | [5 empty] | In Progress
1010000015 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Fuse TripSaver Automation | This project aims to connect and automate 160 Fuse TripSaver®’s to Bear Valley’s SCADA network over 4 years. A Fuse TripSaver is a device used in lieu of fuse cutouts on laterals, feeders, or circuit sections. The TripSaver improves system reliability by eliminating the permanent outages caused when lateral fuses respond to temporary faults. When the device is in “automatic” mode, the device keeps the power on and avoids truck rolls since power is restored automatically for transient faults similar to the way a re-closer would restore power. During high fire threat weather, the TripSavers are placed in “manual”; such that when a fault is detected, the device drops out and requires crew response similar to conventional fuses. Unlike a conventional fuse, there is no expulsion of metal slag that could cause an ignition. The advantage of the TripSaver is that in addition to having an “automatic re-close” or “manual” one shot mode of operation, it is programmable with various selectable protection curves (time vs. current curves) and it will behave like a conventional fuse. The setting may be optimized for reliability during a storm or ignition prevention during high fire threat weather. By connecting the TripSavers to the SCADA network, they can be monitored and operators would be alerted when a TripSaver actuates on fault. This provides prompt notification of a potential fault and ignition as well as localizing information; thereby, vastly improving response times. Additionally, by connecting the TripSavers to the SCADA network, they can be remotely programmed allowing the utility to rapidly optimize the TripSavers for fire prevention during high fire threat weather. Currently, Bear Valley crews must drive to each TripSaver and change their program operation, which takes several days. Therefore, Bear Valley operates the TripSavers in “manual” one-shot mode from April to November/December depending on the weather outlook. This project will establish a robust and secure IP communications network across the sub-transmission and distribution systems to fully enable monitoring of the TripSavers. Connectivity to SCADA will be via the BVES service area fiber optic network and via radio/cellular data transfer equipment. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | 8.1.2.8 | GD_15 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_15_2023 | 143 | Equipment ignition likelihood PSPS exposure potential PSPS vulnerability | No | Number of Fuse TripSavers Automated and Connected to SCADA |  | 2025 | 3 | 50 | 50 | 50 | [5 empty] | Completed
1010000016 | BV | 2023-05-01 | Project | 2023-01-01 | 2024-01-01 | Server Room | The Server Room Project is designed to expand, upgrade, and improve security and reliability of the current computer server room capabilities. In the past four years, Bear Valley has installed a fiber network in the BVES service area, began automating substations and certain field devices, installed a server-based circuit metering system, migrated the Bear Valley Power Plant control system to Bear Valley’s current SCADA software application, and fully developed a GIS database with asset and inspection applications that fully support data schema requirements directed by the Office of Energy Infrastructure Safety (OEIS). Looking ahead, it is clear that Bear Valley will need to continue to significantly expand the automation of substations and field devices, eventually install Advanced Metering Infrastructure (AMI), and grow the GIS database and associated applications. The current server room is becoming inadequate and will eventually not be able to support the ever-growing information technology (IT) systems. The Server Room is currently 10 feet by 4.9 feet (47.5 square feet). This project will enlarge it to 10 feet by 9 feet (180 square feet) and install a properly rated and redundant environmental control system to ensure system safety and reliability. According to North American Electric Reliability Corporation (NERC) standards and best practices for industrial control systems, the SCADA system is required to operate independently from the other server racks. This requirement necessitates the enlargement of the current Server Room. This upgrade also allows for future expansion on the server racks. This project includes the design and installation of the servers for the SCADA system. The Server Room Project is a component of the significant grid automation efforts taken to date and being planned, which will enable Bear Valley to provide safer, more reliable, more resilient, and higher quality service to its customers and the communities it serves. In order to achieve Bear Valley’s grid automation goals, it is essential to install a robust and secure server room for the Internet Protocol (IP) network and SCADA system. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | 8.1.2.8 | GD_16 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_16_2023 | 137 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | Completed | Completed | Completed |  | Completed
1010000017 | BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | Distribution Management Center | The Distribution Management Center Project is intended to establish a control room to interface with the applications designed to monitor and control the entire sub-transmission and distribution network efficiently and reliably. Improving the safety, reliability, resiliency and quality of service in terms of mitigating ignitions, preventing wildfires, reducing outages, minimizing outage time, maintaining acceptable frequency and voltage levels are the key deliverables of the Distribution Management Center. The project specifically establishes a small two operator control room located adjacent to Bear Valley’s Emergency Operations Center equipped with the following capabilities: (1) Monitor and operate the SCADA system; (2) Monitor the Outage Management System; (3) Monitor Bear Valley’s network of weather stations; (4) Access the Customer Information System (CIS) as needed; (5) Monitor Geographical Information System (GIS) applications as applicable; (6) Monitor security systems installed to provide physical security; (7) Update the Interactive Voice Response System (IVRS), TextPower system, and Bear Valley’s website and social media; (8) Communicate with Management, Field Operations crews, key stakeholders, and customers; and (9) When installed, monitor and operate the AMI system. In the past four years, Bear Valley has installed a fiber network in the BVES service area, began automating substations and certain field devices, installed a server-based circuit metering system, migrated the Bear Valley Power Plant control system to Bear Valley’s current SCADA software application, and fully developed a GIS database with asset and inspection applications that fully support data schema requirements directed by the Office of Energy Infrastructure Safety (OEIS). Looking ahead, it is clear that Bear Valley will need to continue to significantly expand the automation substations and field devices, eventually install AMI, and grow the GIS database and associated applications. Therefore, establishing a control room to access, process, and act upon the information provided by these information technology (IT) systems is an important component necessary to truly reap their benefit. Bear Valley currently does not have a single control room to provide the situational awareness in one location that these systems offer. Currently, staff access these applications at specific controlled locations as in the case of SCADA and through various other devices such as desktop computers, workbooks and other mobile devices. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | 8.1.2.8 | GD_17 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_17_2023 | 140 | Equipment ignition likelihood PSPS exposure potential PSPS vulnerability | No |  |  | 2025 | 3 |  |  |  |  | Completed | Completed | Completed |  | Completed
1010000018 | BV | 2023-05-01 | Program |  |  | Line removals (in HFTD) | BVES does not have any line removel projects planned. | Removal of overhead lines to minimize the risk of ignition due to the design, location, or configuration of electric equipment in HFTDs. | Grid Design, Operations, and Maintenance | Line removals (in HFTD) |  | 8.1.2.9 | GD_18 | BV_Grid Design, Operations, and Maintenance_Line removals (in HFTD)_GD_18_2023 | 145 | Equipment ignition likelihood PSPS exposure potential PSPS vulnerability | No |  |  | 2025 | 3 |  |  |  |  | Completed | Completed | Completed |  | Completed
1010000019 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Tree Attachment Removal Project | This project is dedicated to the removal of existing distribution line tree attachments in BVES’s distribution system and it includes costs for replacing tree attachments with poles as necessary to safely and reliably route distribution lines and service lines to customers. BVES has been proactively removing tree attachments, which will improve system reliability and safety and reduce potential fire hazards. Since 2018 when this initiative started, BVES removed 642 tree attachments and has 565 tree attachments remaining in the system. | Actions taken to minimize the risk of ignition due to the design, location, or configuration of electric equipment in HFTDs not covered by another initiative. | Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | GD_19 | BV_Grid Design, Operations, and Maintenance_Other grid topology improvements to minimize risk of ignitions_GD_19_2023 | 145 | Contact from vegetation ignition likelihood | No | Number of Tree Attachments Removed |  | 2025 | 3 | 1 | 106 | 106 | [5 empty] | Completed
1010000020 | BV | 2023-05-01 | Program |  |  | Other grid topology improvements to mitigate or reduce PSPS events | The objectives of this initiative are achieved through BVES's installation of system automation equipment initiatives. | Actions taken to mitigate or reduce PSPS events in terms of geographic scope and number of customers affected not covered by another initiative. | Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | GD_20 | BV_Grid Design, Operations, and Maintenance_Other grid topology improvements to mitigate or reduce PSPS events_GD_20_2023 | 146 | PSPS likelihood PSPS exposure potential PSPS vulnerability | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000021 | BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | BVPP Phase 4 Upgrade Project | The BVPP Reliability Upgrades Project is aimed at reducing the impacts of power outages from proactive de-energization and preserving essential services by improving the reliability of the BVPP. The project includes installing updated engine controls on all seven natural gas engines to a current controls system that will allow efficient start/stop functions, consolidated controls, and synchronization monitoring. Also, the project replaces the Detonation Sensing Module (DSM) Controls on all engines with a detonation controller (DetCon) system that will allow for visual DSM monitoring. DSM modules will also be wired to prevent any fire hazards or failure. Lastly, the project is scheduled to replace the governor speed control systems on all engines with a ProActTM engine speed control system and an EX Gen excitation control system. This upgraded system will be used to fine tune emissions, allow monitoring on the engine control unit, and eliminate all mechanical linkage. The proposed upgrade package is designed to provide improved performance through modifications which translate into better response, lower emissions, reduced downtime, maintenance costs savings, and single source control over the engine and emissions system performance. | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design, Operations, and Maintenance | Other technologies and systems not listed above |  | 8.1.2.12 | GD_21 | BV_Grid Design, Operations, and Maintenance_Other technologies and systems not listed above_GD_21_2023 | 147 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | Completed | Completed | Completed |  | Completed
1010000022 | BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | Partial Safety and Technical Upgrades to Maltby Substation | This project replaces overhead regulators with pad mounted regulators, installs pad mounted IntelliRupter switches, converts substation to be fully underground and updates substation controls. The substation is located in one of the more densely populated residential areas of Big Bear City on the East end of the BVES service area. This two 3.75 MVA transformer substation converts 34.5 kV sub-transmission to two 4.160 kV distribution circuits (Paradise and Erwin Lake circuits). These circuits also provide power to small businesses in the area. These circuits are located in high wind areas. The IntelliRupter switches will significantly (1) Improve the ability of the circuits to be rapidly de-energized when fault conditions are detected. (2) The IntelliRupter when in automatic mode will test at approximately 10% power when a fault is detected, thereby significantly reducing the possibility of causing an ignition. The equipment will be SCADA enabled with remote monitoring and operation capability. The regulators and switches at Maltby Substation are aged and approaching their maximum useful life which makes the equipment more prone to failure and requires costly heightened monitoring and maintenance. Maintaining compliance with GO-174 standards has also been very difficult and costly. As substation equipment further ages, catastrophic failure of the equipment is more likely. Such a failure could potentially cause an ignition event that could lead to a wildfire. Maltby Substation was partially upgraded in 2012 resulting in the feeds on both the sub-transmission and distribution sides being undergrounded and the transformers being pad mounted. The re-closers and regulators are of the overhead design. This project would complete the conversion of the substation to be completely underground with pad mounted equipment. At the completion of the project there would be no exposed bare wire or bus work. The Maltby Substation is heavily loaded making voltage regulation an important issue. The aging regulators are struggling to maintain proper voltage and will need to be replaced. There are safety concerns with the exposed wiring configuration at the substation. These concerns are reduced through increased worker protections, including additional personal protective equipment, additional protective covers, increased safety processes and enhanced safety reviews and briefing prior to entering the substation. These enhanced safety precautions are costly but are necessary to reduce the potential safety exposure to workers and the public. The heightened but costly safety measures are not acceptable as a long-term solution to the safety concerns that exist at the substation. | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design, Operations, and Maintenance | Other technologies and systems not listed above |  | 8.1.2.12 | GD_22 | BV_Grid Design, Operations, and Maintenance_Other technologies and systems not listed above_GD_22_2023 | 147 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000023 | BV | 2023-05-01 | Project | 2025-01-01 | 2026-01-01 | Safety and Technical Upgrades to Lake Substation | The existing Lake Substation is to be converted from an overhead-type to an underground pad-mounted design. This single 2.0 MVA transformer substation converts 34.5 kV sub-transmission to one 4.160 kV distribution circuit (Pump House circuit). The project will improve the safety, reliability and efficiency of the substation by eliminating a wiring configuration that is a potential safety issue, and replacing all aged substation equipment with more efficient and enclosed pad mount transformers, voltage regulators, circuit re-closers, and bus work. The transformation capability would be increased to 5 MVA to accommodate load growth and allow the Pump House circuit to pick up other circuits’ loads for maintenance considerations and during faulted conditions, to improve system reliability and resiliency. The equipment will be SCADA enabled with remote monitoring and operation capability. Advanced metering will be installed to provide real-time, high-quality circuit load data as well as reliability data. The transformer in the Lake Substation is approaching its maximum useful life. In the event of a major transformer failure at the Lake Substation, Bear Valley would not be able to restore the substation until a new or refurbished transformer is procured and delivered, which at a minimum would take a week but more likely several weeks due to supply chain issues and the logistics of trucking such a transformer up the mountain roads to Big Bear Lake. The substation equipment is over 33 years old, which makes the equipment more prone to failure and requiring costly, heightened monitoring and maintenance. Maintaining compliance with GO-174 standards has been very difficult and costly. As substation equipment further ages, catastrophic failure of the equipment is more likely. Such a failure could potentially cause an ignition event that could lead to a wildfire. Replacing the substation would also permit BVES to improve and strengthen the existing oil spill prevention systems. This should avoid increases in the ongoing maintenance costs of complying with the San Bernardino County Fire Department and the Environmental Protection Agency’s requirements regarding oil spill prevention and countermeasures. The substation is located less than 1,000 ft. from Big Bear Lake and therefore, a catastrophic failure of oil-filled equipment (transformer, regulator, and circuit breaker) may pose a threat of contaminating the lake. The Lake Substation is heavily loaded. Circuit loads are often at a high load condition, which makes the likelihood of a circuit trip very likely due to even small current spikes. Circuit trips reduce reliability of service. Additionally, due to load limitations, combining other circuits with circuits originating from this substation is not feasible except during the summer months when load is reduced. Being so heavily loaded reduces overall service reliability in the event of unplanned outages. It also increases maintenance costs because it limits the flexibility of planned maintenance activities. There are safety concerns with the exposed wiring configuration at the substation. These concerns are reduced through increased worker protections, including additional personal protective equipment, additional protective covers, increased safety processes and enhanced safety reviews and briefing prior to entering the substation. These enhanced safety precautions are costly but are necessary to reduce the potential safety exposure to workers and the public. The heightened but costly safety measures are not acceptable as a long-term solution to the safety concerns that exist at the station. | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design, Operations, and Maintenance | Other technologies and systems not listed above |  | 8.1.2.12 | GD_23 | BV_Grid Design, Operations, and Maintenance_Other technologies and systems not listed above_GD_23_2023 | 157 | Equipment ignition likelihood Contact by object ignition | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000024 | BV | 2023-05-01 | Project | 2025-01-01 | 2026-01-01 | Partial Safety and Technical Upgrades to Village Substation | This project replaces overhead enclosed regulators with pad mounted regulators, installs pad mounted IntelliRupter switches, and updates substation controls. The substation is located in one of the more densely populated commercial and residential areas of Big Bear Lake. This 2 3.75 MVA transformer substation converts 34.5 kV sub-transmission to three 4.160 kV distribution circuits (Boulder, Harnish, and Lagonita circuits). These circuits also provide power to critical infrastructure and small businesses in the area. The reliability and safety of this substation is crucial to providing reliable and safe service to a substantial portion of BVES’s customers. Two of the distribution circuits traverse high wind and high vegetation areas. The IntelliRupter switches will significantly improve the ability of the circuits to be rapidly de-energized when fault conditions are detected. The IntelliRupter when in automatic mode will test at approximately 10% power when a fault is detected, thereby significantly reducing the possibility of causing an ignition. The equipment will be SCADA enabled with remote monitoring and operation capability. The regulators and switches at Village Substation are over 23 years old and approaching their maximum useful life, which makes the equipment more prone to failure and requires costly, heightened monitoring and maintenance. Maintaining compliance with GO-174 standards has been very difficult and costly. As substation equipment further ages, catastrophic failure of the equipment is more likely. Such a failure could potentially cause an ignition event that could lead to a wildfire. Village Substation was partially upgraded in 2012 resulting in the feeds on both the sub-transmission and distribution sides being underground and the transformers being pad mounted. The re-closers and regulators are of the overhead design. This project would complete the conversion of the substation to be completely underground with pad mounted equipment. At the completion of the project there would be no exposed bare wire or bus work. The Village Substation is heavily loaded making voltage regulation an important issue. The aging regulators are struggling to maintain proper voltage and will need to be replaced. There are safety concerns with the exposed wiring configuration at the substation. These concerns are reduced through increased worker protections, including additional personal protective equipment, additional protective covers, increased safety processes and enhanced safety reviews and briefing prior to entering the substation. These enhanced safety precautions are costly but are necessary to reduce the potential safety exposure to workers and the public. The heightened but costly safety measures are not acceptable as a long-term solution to the safety concerns that exist at the station. | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design, Operations, and Maintenance | Other technologies and systems not listed above |  | 8.1.2.12 | GD_24 | BV_Grid Design, Operations, and Maintenance_Other technologies and systems not listed above_GD_24_2023 | 147 | Equipment ignition likelihood Contact by object ignition | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | Delayed | BVES has move this target to 2028 and has been updated in BVES's 2026-2028 WMP.
1010000025 | BV | 2023-05-01 | Program |  |  | Detailed Inspections | In accordance with GO 165, careful visual inspections of overhead electric distribution lines and equipment where individual pieces of equipment and structures are carefully examined, visually and through use of routine diagnostic test, as appropriate, and (if practical and if useful information can be so gathered) opened, and the condition of each rated and recorded. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | Asset inspections |  | 8.1.3.1 | GD_25 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_25_2023 | 151 | Equipment ignition likelihood | No | Circuit Miles Inspected |  | 2025 | 3 | 12 | 49 | 49 | [5 empty] | In Progress
1010000026 | BV | 2023-05-01 | Program |  |  | Patrol Inspections | In accordance with GO 165, simple visual inspections of overhead electric distribution lines and equipment that is designed to identify obvious structural problems and hazards. Patrol inspections may be carried out in the course of other company business. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | Asset inspections |  | 8.1.3.1 | GD_26 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_26_2023 | 151 | Equipment ignition likelihood Contact by object ignition | No | Circuit Miles Inspected |  | 2025 | 3 | 56 | 107 | 168 | [5 empty] | In Progress
1010000027 | BV | 2023-05-01 | Program |  |  | UAV Thermography | Inspections of overhead electric distribution lines, equipment, and right-of-way using infrared (heat-sensing) technology and cameras that can identify "hot spots", or conditions that indicate deterioration or potential equipment failures, of electrical equipment. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | Asset inspections |  | 8.1.3.1 | GD_27 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_27_2023 | 152 | Equipment ignition likelihood Contact by object ignition | No | Circuit Miles Inspected |  | 2025 | 3 | 0 | 0 | 205 | [5 empty] | Completed
1010000028 | BV | 2023-05-01 | Program |  |  | UAV HD Photography/Videography | Inspections of overhead electric distribution lines, equipment, and right-of-way using high definition (HD) photography and video cameras that can identify conditions that indicate deterioration or potential equipment failures, of electrical equipment. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | Asset inspections |  | 8.1.3.1 | GD_28 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_28_2023 | 152 | Equipment ignition likelihood Contact by object ignition | No | Circuit Miles Inspected |  | 2025 | 3 | 0 | 0 | 205 | [5 empty] | Completed
1010000029 | BV | 2023-05-01 | Program |  |  | LiDAR Inspection | Inspections of overhead electric distribution lines, equipment, and right-of-way using LiDAR (Light Detection and Ranging, a remote sensing method that uses light in the form of a pulsed laser to measure variable distances). | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | Asset inspections |  | 8.1.3.1 | GD_29 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_29_2023 | 153 | Equipment ignition likelihood PSPS Likelihood | No | Circuit Miles Inspected |  | 2025 | 3 | 0 | 0 | 205 | [5 empty] | Completed
1010000030 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Minor Undergrounding Upgrades Projects | Actions taken to convert overhead electric lines and/or equipment to underground electric lines and/or equipment (i.e., located underground and in accordance with GO 128). | Actions taken to convert overhead electric lines and/or equipment to underground electric lines and/or equipment (i.e., located underground and in accordance with GO 128). | Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | GD_3 | BV_Grid Design, Operations, and Maintenance_Undergrounding of electric lines and/or equipment_GD_3_2023 | 134 | Equipment ignition likelihood Contact by object ignition | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000031 | BV | 2023-05-01 | Program |  |  | 3rd Party Ground Patrol | In accordance with GO 165, simple visual inspections of overhead electric distribution lines and equipment that is designed to identify obvious structural problems and hazards. Patrol inspections may be carried out in the course of other company business. This inspection is performed by an independent 3rd Party. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | Asset inspections |  | 8.1.3.1 | GD_30 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_30_2023 | 154 | Equipment ignition likelihood | No | Circuit Miles Inspected |  | 2025 | 3 | 0 | 0 | 205 | [5 empty] | Completed
1010000032 | BV | 2023-05-01 | Program |  |  | Intrussive Pole Inspections | In accordance with GO 165, intrusive inspections involve movement of soil, taking samples for analysis, and/or using more sophisticated diagnostic tools beyond visual inspections or instrument reading. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | Asset inspections |  | 8.1.3.1 | GD_31 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_31_2023 | 154 | Equipment ignition likelihood | No | Number of Poles Intrusively Inspected |  | 2025 | 3 | 0 | 0 | 850 | [5 empty] | Completed
1010000033 | BV | 2023-05-01 | Program |  |  | Substation inspections | In accordance with GO 174, inspection of substations performed by qualified persons and according to the frequency established by the utility, including record-keeping. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | Asset inspections |  | 8.1.3.1 | GD_32 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_32_2023 | 155 | Equipment ignition likelihood | No | Number of Substations Inspected |  | 2025 | 3 | 39 | 78 | 117 | [5 empty] | In Progress
1010000034 | BV | 2023-05-01 | Program |  |  | Equipment maintenance and repair | Remediation, adjustments, or installations of new equipment to improve or replace existing connector equipment, such as hotline clamps. | Remediation, adjustments, or installations of new equipment to improve or replace existing connector equipment, such as hotline clamps. | Grid Design, Operations, and Maintenance | Equipment maintenance and repair |  | 8.1.4 | GD_33 | BV_Grid Design, Operations, and Maintenance_Equipment maintenance and repair_GD_33_2023 | 158 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000035 | BV | 2023-05-01 | Program |  |  | Asset management and inspection enterprise system(s) | Operation of and support for centralized asset management and inspection enterprise system(s) updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | Operation of and support for centralized asset management and inspection enterprise system(s) updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | Grid Design, Operations, and Maintenance | Asset management and inspection enterprise system(s) |  | 8.1.5 | GD_34 | BV_Grid Design, Operations, and Maintenance_Asset management and inspection enterprise system(s)_GD_34_2023 | 161 | Equipment ignition likelihood Contact by object ignition | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000036 | BV | 2023-05-01 | Program |  |  | Asset Quality assurance / quality control | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | Grid Design, Operations, and Maintenance | Quality assurance / quality control |  | 8.1.6 | GD_35 | BV_Grid Design, Operations, and Maintenance_Quality assurance / quality control_GD_35_2023 | 164 | Equipment ignition likelihood Contact by object ignition | No | Number of Asset QCs on WMP Work |  | 2025 | 3 | 5 | 10 | 15 | [5 empty] | In Progress
1010000037 | BV | 2023-05-01 | Program |  |  | Asset Open work orders | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe asset management activities. | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe asset management activities. | Grid Design, Operations, and Maintenance | Open work orders |  | 8.1.7 | GD_36 | BV_Grid Design, Operations, and Maintenance_Open work orders_GD_36_2023 | 166 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000038 | BV | 2023-05-01 | Program |  |  | Equipment Settings to Reduce Wildfire Risk | The electrical corporation’s procedures for adjusting the sensitivity of grid elements to reduce wildfire risk. | The electrical corporation’s procedures for adjusting the sensitivity of grid elements to reduce wildfire risk. | Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk |  | 8.1.8.1 | GD_37 | BV_Grid Design, Operations, and Maintenance_Equipment Settings to Reduce Wildfire Risk_GD_37_2023 | 169 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000039 | BV | 2023-05-01 | Program |  |  | Grid Response Procedures and Notifications | The electrical corporation’s procedures it uses to respond to faults, ignitions, or other issues detected on its grid that may result in a wildfire. | The electrical corporation’s procedures it uses to respond to faults, ignitions, or other issues detected on its grid that may result in a wildfire. | Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications |  | 8.1.8.2 | GD_38 | BV_Grid Design, Operations, and Maintenance_Grid Response Procedures and Notifications_GD_38_2023 | 172 | Wildfire spread Wildfire hazard PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000040 | BV | 2023-05-01 | Program |  |  | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | Work activity guidelines that designate what type of work can be performed during operating conditions of different levels of wildfire risk. Training for personnel on these guidelines and the procedures they prescribe, from normal operating procedures to increased mitigation measures to constraints on work performed. | Work activity guidelines that designate what type of work can be performed during operating conditions of different levels of wildfire risk. Training for personnel on these guidelines and the procedures they prescribe, from normal operating procedures to increased mitigation measures to constraints on work performed. | Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk |  | 8.1.8.3 | GD_39 | BV_Grid Design, Operations, and Maintenance_Personnel Work Procedures and Training in Conditions of Elevated Fire Risk_GD_39_2023 | 173 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000041 | BV | 2023-05-01 | Project | 2023-01-01 | 2025-01-01 | Covered Conductor Replacement Project | In conducting the Covered Conductor Preplacement Project, existing poles are assessed (3-D stress loading, GO-95 discrepancies, intrussive testing) and are remediated or replaced to ensure they are able to support covered conductor. | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. | Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements |  | 8.1.2.3 | GD_4 | BV_Grid Design, Operations, and Maintenance_Distribution pole replacements and reinforcements_GD_4_2023 | 159 | Equipment ignition likelihood Contact from vegetation ignition likelihood | No | Number of Poles Replaced |  | 2025 | 3 | 0 | 78 | 115 | [5 empty] | Completed
1010000042 | BV | 2023-05-01 | Program |  |  | Asset Workforce Planning | Programs to ensure that the electrical corporation has qualified asset personnel and to ensure that both employees and contractors tasked with asset management responsibilities are adequately trained to perform relevant work. | Programs to ensure that the electrical corporation has qualified asset personnel and to ensure that both employees and contractors tasked with asset management responsibilities are adequately trained to perform relevant work. | Grid Design, Operations, and Maintenance | Workforce Planning |  | 8.1.9 | GD_40 | BV_Grid Design, Operations, and Maintenance_Workforce Planning_GD_40_2023 | 174 | Wildfire hazard Equipment ignition likelihood Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000043 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Radford Line Replacement Project | Radford Line Replacement Project replaces fire resistant (ductile iron) poles because it is located in an area designated as High Fire Threat District Tier 3 (“extreme fire risk”) by the CPUC. BVES believes that this approach will provide the greatest protection and significantly enhance public safety. | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. | Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements |  | 8.1.2.3 | GD_5 | BV_Grid Design, Operations, and Maintenance_Distribution pole replacements and reinforcements_GD_6_2023 | 159 | Equipment ignition likelihood | No | Number of Poles Replaced |  | 2025 | 3 | 0 | 0 | 0 | [5 empty] | Completed
1010000044 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Evacuation Route Hardening Project | This project aims to build upon the work that Bear Valley previously accomplished in the area of hardening evacuation routes. In 2021 and 2022, Bear Valley completed the hardening of primary evacuation routes to its service area. This project is aimed at hardening electrical assets along secondary roads that lead to the primary evacuation routes. The hardening of BVES electrical assets (poles, wires, equipment) along the evacuation routes and secondary roads that lead to primary evacuation routes is important to ensure they do not fail during a wildfire, which would limit mobility along the evacuation routes required to safely perform an evacuation. Lessons learned from past wildfires and most notably the Camp Fire indicate hardening of utility assets along evacuation routes is critical to public safety for the following reasons: (1) To allow the safe evacuation of the public in the event of a wildfire; and (2) To allow the mobility for First Responders to move assets in and out of the wildfire areas to allow them to actively fight the wildfire, save lives, protect property, and minimize environmental damage. BVES plans to install wire wrap mesh on 500 wood poles per year in selected high-risk areas along secondary roads leading to the primary evacuation routes from 2023 to 2026. | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. | Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements |  | 8.1.2.3 | GD_6 | BV_Grid Design, Operations, and Maintenance_Distribution pole replacements and reinforcements_GD_6_2023 | 159 | Wildfire hazard | No | Number of Poles that had Wire Mesh Installed on them. |  | 2025 | 3 | 500 | 586 | 595 | [5 empty] | Completed
1010000045 | BV | 2023-05-01 | Program |  |  | Transmission pole/tower replacements and reinforcements | BVES does not own or operate any transmission lines. | Remediation, adjustments, or installations of new equipment to improve or replace existing transmission towers (e.g., structures such as lattice steel towers or tubular steel poles that support lines at or above 65kV). | Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements |  | 8.1.2.4 | GD_7 | BV_Grid Design, Operations, and Maintenance_Transmission pole/tower replacements and reinforcements_GD_7_2023 | 138 | Wildfire spread Wildfire hazard PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | Completed | Completed | Completed |  | Completed
1010000046 | BV | 2023-05-01 | Program |  |  | Traditional overhead hardening | Maintenance, repair, and replacement of capacitors, circuit breakers, cross-arms, transformers, fuses, and connectors (e.g., hot line clamps) with the intention of minimizing the risk of ignition. | Maintenance, repair, and replacement of capacitors, circuit breakers, cross-arms, transformers, fuses, and connectors (e.g., hot line clamps) with the intention of minimizing the risk of ignition. | Grid Design, Operations, and Maintenance | Traditional overhead hardening |  | 8.1.2.5 | GD_8 | BV_Grid Design, Operations, and Maintenance_Traditional overhead hardening_GD_8_2023 | 156 | Wildfire spread Wildfire hazard PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000047 | BV | 2023-05-01 | Program |  |  | Emerging grid hardening technology installations and pilots | BVES does not have any pilot projects or programs for novel grid hardening technology. BVES is following what other larger electric utilties are doing regarding grid hardening technology as well as participating in industry conferences and trade shows to keep current on any emerging grid hardening technologies. BVES will certainly pilot any promising grid hardening technologies that would work well in BVES's service area and system. | Development, deployment, and piloting of novel grid hardening technology. | Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots |  | 8.1.2.6 | GD_9 | BV_Grid Design, Operations, and Maintenance_Emerging grid hardening technology installations and pilots_GD_9_2023 | 138 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000048 | BV | 2023-05-01 | Program |  |  | Technosylva Contractor. Program implemented and ongoing. | Development and use of tools and processes to assess the risk of wildfire and PSPS across an electrical corporation’s service territory. | Development and use of tools and processes to assess the risk of wildfire and PSPS across an electrical corporation’s service territory. | Risk Methodology and Assessment | Risk Methodology and Assessment |  | 6 | RMA_1 | BV_Risk Methodology and Assessment_Risk Methodology and Assessment_RMA_1_2023 | 259 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000049 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Advanced weather monitoring and weather stations | Project installs and maintains 20 weather stations. | Development and deployment of systems which measure environmental characteristics, such as fuel moisture, air temperature, and velocity. | Situational Awareness and Forecasting | Environmental monitoring systems |  | 8.3.2 | SAF_1 | Situational Awareness and Forecasting_Environmental monitoring systems_SAF_1_2023 | 244 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000050 | BV | 2023-05-01 | Project | 2023-01-01 | 2024-01-01 | Install Fault Indicators | The project aims to install an additional 129 fault indicators (FIs) at 43 locations in Bear Valley’s sub-transmission and distribution system. FIs are devices installed on overhead power lines in electric power distribution systems to detect and indicate the occurrence of faults. They are installed at specific distances along a circuit and at major branch lines so that when a fault occurs, the fault zone (where the fault occurred) is minimized, thereby reducing time to locate and identify the fault and, therefore, restore service to affected customers. FIs provide a visual indicator on which side of the FI the fault occurred. Therefore, responding crews look for the portion of the circuit in which the FIs have “sandwiched” the fault. Some FIs, in addition to providing a visual indicator, have the capability to be connected to the Supervisory Control and Data Acquisition (SCADA) network which allows remote identification of the fault zone. This further reduces response time in localizing a fault since the crews would be directed to roll their truck directly to the fault zone rather than the faulted circuit. This project will install the SCADA capable FI devices. This project will establish a robust and secure IP communications network across the sub-transmission and distribution systems to fully enable monitoring of the FIs. Connectivity to SCADA will be via the BVES service area fiber optic network and via radio/cellular data transfer equipment. FIs allow crews to locate and arrive at the fault location significantly faster and are more likely to identify a faulted situation and ignition with greater opportunity to reduce the risks of a wildfire. | Development and deployment of systems that checks the operational conditions of electrical facilities and equipment and detects such things as faults, failures, and recloser operations. | Situational Awareness and Forecasting | Grid monitoring systems |  | 8.3.3 | SAF_2 | BV_Situational Awareness and Forecasting_Grid monitoring systems_SAF_2_2023 | 240 | Contact from vegetation ignition likelihood | No | Number of Fis installed. |  | 2025 | 3 | 0 | 0 | 0 | [5 empty] | Completed
1010000051 | BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Online Diagnostic System | Project installs continuous monitor sensors to provide usable grid insight information that is measured, reported, and documented. Analytics enable the ability to identify and correct current and future irregularities before a problem arises. This will enhance safety, reliability, cost control, and customer satisfaction. Designed to pinpoint irregularities, which may be due to degrading/imminent hardware failures, as well as identify objects such as vegetation contacting the lines. Enables BVES to rapidly inspect potential problems before they develop into an ignition source. | Development and deployment of systems that checks the operational conditions of electrical facilities and equipment and detects such things as faults, failures, and recloser operations. | Situational Awareness and Forecasting | Grid monitoring systems |  | 8.3.3 | SAF_3 | BV_Situational Awareness and Forecasting_Grid monitoring systems_SAF_3_2023 | 241 | Contact from vegetation ignition likelihood | No | Number of circuits installed on per year. |  | 2025 | 3 | 0 | 0 | 0 | [5 empty] | In Progress
1010000052 | BV | 2023-05-01 | Program |  |  | HD ALERTWildfire Cameras | Project installs 15 HD ALERTWildfire Cameras to provide complete coverage of the BVES Service Area. | Development and deployment of systems which discover or identify the presence or existence of an ignition, such as cameras. | Situational Awareness and Forecasting | Ignition detection systems |  | 8.3.4 | SAF_4 | BV_Situational Awareness and Forecasting_Ignition detection systems_SAF_4_2023 | 240 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | Completed | Completed | Completed |  | Completed
1010000053 | BV | 2023-05-01 | Program |  |  | Weather forecasting | Program leverages Technosylva’s software capabilities and solutions, which have been implemented across California in other electric utilities, to provide: (1) On-demand, real time wildfire behavior modeling, predictive spread conditions, and derivation of potential impacts analysis; (2)Ability to conduct simulations on-demand, to reflect changing conditions or local data observations, including proactive “what if” scenarios; and (3) Weather and wildfire risk forecasting for BVES’s assets and the service territory using daily weather prediction integration to support PSPS activation calls and response operations. Also, program engages an expert weather consultant to provide BVES specific weather forecasts at least weekly and more frequently during fire threat weather conditions. This information, along with the information gained from Technosylva fire threat analysis applications allows BVES to evalaute weather impacts on electric lines and equipment and the potential for ignitions and wildfire. | Development methodology for forecast of weather conditions relevant to electrical corporation operations, forecasting weather conditions and conducting analysis to incorporate into utility decision- making, learning and updates to reduce false positives and false negatives of forecast PSPS conditions. | Situational Awareness and Forecasting | Weather forecasting |  | 8.3.5 | SAF_5 | Situational Awareness and Forecasting_Weather forecasting_SAF_5_2023 | 241 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000054 | BV | 2023-05-01 | Program |  |  | Fire potential index | Calculation and application of a landscape scale index used as a proxy for assessing real-time risk of a wildfire under current and forecasted weather conditions. | Calculation and application of a landscape scale index used as a proxy for assessing real-time risk of a wildfire under current and forecasted weather conditions. | Situational Awareness and Forecasting | Fire potential index |  | 8.3.6 | SAF_6 | BV_Situational Awareness and Forecasting_Fire potential index_SAF_6_2023 | 242 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000055 | BV | 2023-05-01 | Project | 2025-01-01 | 2026-01-01 | GreenGrid iSIU | The iSIU System is a camera-based inspection and monitoring device. The device consists of a camera, optical sensors, communication module, processor and power module in one integrated unit. The devices have been strategically placed on poles on the Boulder and North Shore Circuits and allow for autonomous monitoring of the power line infrastructures and advise the remote maintenance, inspections, or operations crews on potentially hazardous events automatically, thus saving operational cost and reducing risks to humans and the environment. | Continuous circuit monitoring | Situational Awareness and Forecasting | Grid monitoring systems |  | 8.3.6 | SAF_7 | BV_Situational Awareness and Forecasting_Grid monitoring systems_SAF_7_2023 | 250 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000056 | BV | 2023-05-01 | Program |  |  | Environmental compliance and permitting | Development and implementation of process and procedures to ensure compliance with applicable environmental laws, regulations, and permitting related to the implementation of the WMP. | Development and implementation of process and procedures to ensure compliance with applicable environmental laws, regulations, and permitting related to the implementation of the WMP. | Overview of the Service Territory | Environmental compliance and permitting |  | 5.4.5 | ST_1 | BV_Overview of the Service Territory_Environmental compliance and permitting_ST_1_2023 | 42 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000057 | BV | 2023-05-01 | Program |  |  | Detailed Inspections | Careful visual inspections and maintenance of vegetation around the distribution right-of-way, where individual trees are carefully examined, visually, and the condition of each rated and recorded. Describe the frequency of inspection and maintenance programs. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | Vegetation inspections |  | 8.2.2.1 | VM_1 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_1_2023 | 151 | Wildfire exposure potential | No | Circuit Miles Inspected |  | 2025 | 3 | 12 | 49 | 49 | [5 empty] | In Progress
1010000058 | BV | 2023-05-01 | Program |  |  | Fall-in mitigation | Actions taken to identify and remove or otherwise remediate trees that pose a high risk of failure or fracture that could potentially strike electrical equipment. | Actions taken to identify and remove or otherwise remediate trees that pose a high risk of failure or fracture that could potentially strike electrical equipment. | Vegetation Management and Inspection | Fall-in mitigation |  | 8.2.3.4 | VM_10 | BV_Vegetation Management and Inspection_Fall-in mitigation_VM_10_2023 | 218 | Contact from vegetation ignition likelihood | No | Number of trees remediated or removed to prevent fall-in |  | 2025 | 3 | 25 | 73 | 116 | [5 empty] | Completed
1010000059 | BV | 2023-05-01 | Program |  |  | Substation defensible space | Actions taken to reduce ignition probability and wildfire consequence due to contact with substation equipment. | Actions taken to reduce ignition probability and wildfire consequence due to contact with substation equipment. | Vegetation Management and Inspection | Substation defensible space |  | 8.2.3.5 | VM_11 | BV_Vegetation Management and Inspection_Substation defensible space_VM_11_2023 | 218 | Contact from vegetation ignition likelihood | No | Substations inspected and cleared |  | 2025 | 3 | 0 | 0 | 13 | [5 empty] | Completed
1010000060 | BV | 2023-05-01 | Program |  |  | High-risk species | Actions taken to reduce the ignition probability and wildfire consequence attributable to high-risk species of vegetation. | Actions taken to reduce the ignition probability and wildfire consequence attributable to high- risk species of vegetation. | Vegetation Management and Inspection | High-risk species |  | 8.2.3.6 | VM_12 | BV_Vegetation Management and Inspection_High-risk species_VM_12_2023 | 219 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000061 | BV | 2023-05-01 | Program |  |  | Fire-resilient rights-of-way | Actions taken to promote vegetation communities that are sustainable, fire-resilient, and compatible with the use of the land as an electrical corporation right-of-way. | Actions taken to promote vegetation communities that are sustainable, fire-resilient, and compatible with the use of the land as an electrical corporation right-of-way. | Vegetation Management and Inspection | Fire-resilient rights-of-way |  | 8.2.3.7 | VM_13 | BV_Vegetation Management and Inspection_Fire-resilient rights-of-way_VM_13_2023 | 219 | Wildfire vulnerability | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000062 | BV | 2023-05-01 | Program |  |  | Emergency response vegetation management | Planning and execution of vegetation activities in response to emergency situations including weather conditions that indicate an elevated fire threat and post-wildfire service restoration. | Planning and execution of vegetation activities in response to emergency situations including weather conditions that indicate an elevated fire threat and post-wildfire service restoration. | Vegetation Management and Inspection | Emergency response vegetation management |  | 8.2.3.8 | VM_14 | BV_Vegetation Management and Inspection_Emergency response vegetation management_VM_14_2023 | 220 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000063 | BV | 2023-05-01 | Program |  |  | Vegetation management enterprise system | Operation of and support for centralized vegetation management and inspection enterprise system(s) updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | Operation of and support for centralized vegetation management and inspection enterprise system(s) updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | Vegetation Management and Inspection | Vegetation management enterprise system |  | 8.2.4 | VM_15 | BV_Vegetation Management and Inspection_Vegetation management enterprise system_VM_15_2023 | 221 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000064 | BV | 2023-05-01 | Program |  |  | Vegetation Management Quality assurance / quality control | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | Vegetation Management and Inspection | Quality assurance / quality control |  | 8.2.5 | VM_16 | BV_Vegetation Management and Inspection_Quality assurance / quality control_VM_16_2023 | 22 | Contact from vegetation ignition likelihood | No | Number of Vegetation Management Audits |  | 2025 | 3 | 26 | 69 | 123 | [5 empty] | Completed
1010000065 | BV | 2023-05-01 | Program |  |  | Vegetation Management Open work orders | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe vegetation management activities. | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe vegetation management activities. | Vegetation Management and Inspection | Open work orders |  | 8.2.6 | VM_17 | BV_Vegetation Management and Inspection_Open work orders_VM_17_2023 | 226 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000066 | BV | 2023-05-01 | Program |  |  | Vegetation Management Workforce planning | Programs to ensure that the electrical corporation has qualified vegetation management personnel and to ensure that both employees and contractors tasked with vegetation management responsibilities are adequately trained to perform relevant work. | Programs to ensure that the electrical corporation has qualified vegetation management personnel and to ensure that both employees and contractors tasked with vegetation management responsibilities are adequately trained to perform relevant work. | Vegetation Management and Inspection | Workforce planning |  | 8.2.7 | VM_18 | BV_Vegetation Management and Inspection_Workforce planning_VM_18_2023 | 217 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000067 | BV | 2023-05-01 | Project | 2025-01-01 | 2026-01-01 | AiDash | AiDash software uses satellite imagining providing a rapid assessment of BVES’s service territory and insight into whether vegetation should be assessed or moved up in priority for upcoming patrol, detailed, or third-party ground inspections. The AiDash assessment allows BVES to gain a comprehensive understanding of its service territory at a glance. AiDash also provides a complementary review of BVES’s vegetation management program. | The AiDash assessment allows BVES to gain a comprehensive understanding of its service territory at a glance. AiDash also provides a complementary review of BVES’s vegetation management program. | Vegetation Management and Inspection | Vegetation inspections |  | 8.2.2.7 | VM_19 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_19_2023 | 229 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000068 | BV | 2023-05-01 | Program |  |  | Patrol Inspections | Visual inspections of vegetation along rights-of- way that is designed to identify obvious hazards. Patrol inspections may be carried out in the course of other company business. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | Vegetation inspections |  | 8.2.2.1 | VM_2 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_2_2023 | 151 | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected |  | 2025 | 3 | 56 | 107 | 168 | [5 empty] | In Progress
1010000069 | BV | 2023-05-01 | Program |  |  | UAV HD Photography/Videography | Inspections of right-of-way using aerial (UAV) HD photography and vido cameras. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | Vegetation inspections |  | 8.2.2.1 | VM_3 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_3_2023 | 152 | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected |  | 2025 | 3 | 0 | 0 | 205 | [5 empty] | Completed
1010000070 | BV | 2023-05-01 | Program |  |  | LiDAR Inspection | Inspections of right-of-way using LiDAR. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | Vegetation inspections |  | 8.2.2.1 | VM_4 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_4_2023 | 153 | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected |  | 2025 | 3 | 0 | 0 | 205 | [5 empty] | Completed
1010000071 | BV | 2023-05-01 | Program |  |  | 3rd Party Ground Patrol | Visual inspections of vegetation along rights-of- way that is designed to identify obvious hazards. Patrol inspections may be carried out in the course of other company business. This inspection is performed by an independent 3rd Party. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | Vegetation inspections |  | 8.2.2.1 | VM_5 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_5_2023 | 154 | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected |  | 2025 | 3 | 0 | 0 | 205 | [5 empty] | Completed
1010000072 | BV | 2023-05-01 | Program |  |  | Substation inspections | Inspection of vegetation surrounding substations, performed by qualified persons and according to the frequency established by the utility, including record-keeping. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | Vegetation inspections |  | 8.2.2.1 | VM_6 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_6_2023 | 155 | Contact from vegetation ignition likelihood | No | Number of Substations Inspected |  | 2025 | 3 | 39 | 78 | 117 | [5 empty] | In Progress
1010000073 | BV | 2023-05-01 | Program |  |  | Pole clearing | Plan and execution of vegetation removal around poles per Public Resources Code section 4292 and outside the requirements of Public Resources Code section 4292 (e.g., pole clearing performed outside of the State Responsibility Area). | Plan and execution of vegetation removal around poles per Public Resources Code section 4292 and outside the requirements of Public Resources Code section 4292 (e.g., pole clearing performed outside of the State Responsibility Area). | Vegetation Management and Inspection | Pole clearing |  | 8.2.3.1 | VM_7 | BV_Vegetation Management and Inspection_Pole clearing_VM_7_2023 | 214 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000074 | BV | 2023-05-01 | Program |  |  | Wood and slash management | Actions taken to manage all downed wood and “slash” generated from vegetation management activities. | Actions taken to manage all downed wood and “slash” generated from vegetation management activities. | Vegetation Management and Inspection | Wood and slash management |  | 8.2.3.2 | VM_8 | BV_Vegetation Management and Inspection_Wood and slash management_VM_8_2023 | 214 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Progress | In Progress | In Progress |  | In Progress
1010000075 | BV | 2023-05-01 | Program |  |  | Clearance | Actions taken after inspection to ensure that vegetation does not encroach upon electrical equipment and facilities, such as tree trimming. | Actions taken after inspection to ensure that vegetation does not encroach upon electrical equipment and facilities, such as tree trimming. | Vegetation Management and Inspection | Clearance |  | 8.2.3.3 | VM_9 | BV_Vegetation Management and Inspection_Clearance_VM_9_2023 | 215 | Contact from vegetation ignition likelihood | No | Circuit Miles Cleared |  | 2025 | 3 | 25 | 49 | 59 | [5 empty] | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000001 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000002 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000003 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000004 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000005 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000006 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000007 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000008 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000009 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000010 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000011 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000012 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000013 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000014 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000015 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 1
1020000016 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000017 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000018 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000019 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000020 | 1. Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000021 | 1. Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000022 | 1. Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000023 | 1. Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000024 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000025 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000026 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000027 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 5
1020000028 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000029 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000030 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000031 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000032 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000033 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000034 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000035 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000036 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000037 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000038 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000039 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000040 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000041 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000042 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000043 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000044 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000045 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000046 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000047 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000048 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000049 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000050 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000051 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000052 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000053 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000054 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000055 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BV | 2025 | 3 | 0
1020000056 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000057 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000058 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000059 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000060 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  | BV does not currently record this data | BV | 2025 | 3
1020000061 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  | BV does not currently record this data | BV | 2025 | 3
1020000062 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  | BV does not currently record this data | BV | 2025 | 3
1020000063 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  | BV does not currently record this data | BV | 2025 | 3
1020000064 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000065 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000066 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  | BV does not have any transmission lines | BV | 2025 | 3
1020000067 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  | BV does not have any transmission lines | BV | 2025 | 3
1020000068 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  | BV does not have any transmission lines | BV | 2025 | 3
1020000069 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  | BV does not have any transmission lines | BV | 2025 | 3
1020000070 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  | BV does not have any transmission lines | BV | 2025 | 3
1020000071 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  | BV does not have any transmission lines | BV | 2025 | 3
1020000072 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000073 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000074 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000075 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000076 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000077 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000078 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000079 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000080 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000081 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000082 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000083 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000084 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000085 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000086 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000087 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000088 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000089 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000090 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000091 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000092 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000093 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000094 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000095 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000096 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000097 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000098 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000099 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BV | 2025 | 3
1020000100 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000101 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000102 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000103 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000104 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000105 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000106 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000107 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BV | 2025 | 3
1020000108 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | BV | 2025 | 3 | 0
1020000109 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | BV | 2025 | 3 | 0
1020000110 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | BV | 2025 | 3 | 4
1020000111 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | BV | 2025 | 3 | 0
1020000112 | 8. Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  |  | BV | 2025 | 3 | 0
1020000113 | 9. Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | BV | 2025 | 3 | 0
1020000114 | 9. Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | BV | 2025 | 3 | 0
1020000115 | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | BV | 2025 | 3 | 0
1020000116 | 11. Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | BV | 2025 | 3 | 0
1020000117 | 11. Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | BV | 2025 | 3 | 0
1020000118 | 12. Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | BV | 2025 | 3 | 0
1020000119 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | BV | 2025 | 3 | 0
1020000120 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | BV | 2025 | 3 | 0
1020000121 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | BV | 2025 | 3 | 0
1020000122 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | BV | 2025 | 3 | 0
1020000123 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | BV | 2025 | 3 | 0
1020000124 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | BV | 2025 | 3 | 0
1020000125 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | BV | 2025 | 3 | 0
1020000126 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | BV | 2025 | 3 | 0
1020000127 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000128 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000129 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000130 | 13. Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000131 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000132 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000133 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000134 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000135 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000136 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000137 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000138 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000139 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000140 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000141 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000142 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000143 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000144 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000145 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000146 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 263
1020000147 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 203
1020000148 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000149 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 203
1020000150 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000151 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000152 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000153 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000154 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000155 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000156 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000157 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000158 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000159 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000160 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000161 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000162 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000163 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000164 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000165 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000166 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000167 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000168 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000169 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000170 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000171 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000172 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000173 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000174 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 1
1020000175 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000176 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000177 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000178 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000179 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000180 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000181 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000182 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000183 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000184 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000185 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000186 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000187 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000188 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000189 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000190 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000191 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000192 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000193 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000194 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000195 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000196 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000197 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000198 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000199 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000200 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000201 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000202 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BV | 2025 | 3
1020000203 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000204 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000205 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000206 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 4
1020000207 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 2
1020000208 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000209 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 2
1020000210 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000211 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000212 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000213 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000214 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | BV | 2025 | 3 | 0
1020000215 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000216 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000217 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000218 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000219 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000220 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000221 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000222 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000223 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000224 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000225 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000226 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000227 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000228 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000229 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000230 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000231 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000232 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000233 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000234 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000235 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000236 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000237 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000238 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000239 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000240 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000241 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000242 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000243 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000244 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000245 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000246 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000247 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000248 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000249 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000250 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BV | 2025 | 3 | 0
1020000251 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000252 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000253 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000254 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000255 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000256 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000257 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000258 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000259 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000260 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000261 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000262 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000263 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000264 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000265 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000266 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000267 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000268 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000269 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000270 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000271 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000272 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000273 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000274 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000275 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000276 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000277 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000278 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000279 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000280 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000281 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000282 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000283 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000284 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000285 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000286 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000287 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000288 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000289 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000290 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000291 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000292 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000293 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000294 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000295 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000296 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000297 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000298 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000299 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000300 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000301 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000302 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000303 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000304 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000305 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000306 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000307 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000308 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000309 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000310 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000311 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000312 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000313 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000314 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000315 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000316 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000317 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000318 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000319 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000320 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000321 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000322 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000323 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000324 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000325 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000326 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000327 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000328 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000329 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000330 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000331 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000332 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000333 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000334 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000335 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000336 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000337 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000338 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000339 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000340 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000341 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000342 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000343 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000344 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000345 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000346 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000347 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000348 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000349 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000350 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000351 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000352 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000353 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000354 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000355 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000356 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000357 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000358 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000359 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000360 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000361 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000362 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000363 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000364 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000365 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000366 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000367 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000368 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000369 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000370 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000371 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000372 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000373 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000374 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000375 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000376 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000377 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000378 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000379 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000380 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000381 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000382 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000383 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000384 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000385 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000386 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000387 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000388 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000389 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000390 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000391 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000392 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000393 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000394 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000395 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000396 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000397 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000398 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000399 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000400 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000401 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000402 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000403 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000404 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000405 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000406 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000407 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000408 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000409 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000410 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000411 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000412 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000413 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000414 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000415 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000416 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000417 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000418 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000419 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000420 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000421 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000422 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000423 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000424 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000425 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000426 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000427 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000428 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000429 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000430 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000431 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000432 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000433 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000434 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000435 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000436 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000437 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000438 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000439 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000440 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000441 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000442 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000443 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000444 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000445 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000446 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000447 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000448 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000449 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000450 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000451 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000452 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000453 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000454 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BV | 2025 | 3
1020000455 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000456 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000457 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000458 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000459 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000460 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000461 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000462 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000463 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000464 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000465 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000466 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000467 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000468 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000469 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000470 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000471 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000472 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000473 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000474 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000475 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000476 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000477 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000478 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000479 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000480 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000481 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000482 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000483 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000484 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000485 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000486 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000487 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000488 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000489 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000490 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BV | 2025 | 3
1020000491 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000492 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000493 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000494 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000495 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000496 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000497 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000498 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000499 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000500 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000501 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000502 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000503 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000504 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000505 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000506 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000507 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000508 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000509 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000510 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 13
1020000511 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000512 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000513 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000514 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000515 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000516 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000517 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000518 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000519 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000520 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000521 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000522 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000523 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000524 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000525 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000526 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000527 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000528 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000529 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000530 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000531 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000532 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000533 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000534 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000535 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000536 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000537 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000538 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000539 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000540 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000541 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000542 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000543 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000544 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000545 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000546 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000547 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000548 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000549 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000550 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000551 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000552 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000553 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000554 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000555 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000556 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000557 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000558 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000559 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000560 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000561 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000562 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BV | 2025 | 3 | 0
1020000563 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000564 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000565 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000566 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000567 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000568 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000569 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000570 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000571 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000572 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000573 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000574 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000575 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000576 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000577 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000578 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000579 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000580 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000581 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000582 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000583 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000584 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000585 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000586 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000587 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000588 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000589 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000590 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000591 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000592 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000593 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000594 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000595 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000596 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000597 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000598 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000599 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000600 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000601 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000602 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000603 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000604 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000605 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000606 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000607 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000608 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000609 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000610 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000611 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000612 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000613 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000614 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000615 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000616 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000617 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000618 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000619 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000620 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000621 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000622 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000623 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000624 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000625 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000626 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000627 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000628 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000629 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000630 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000631 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000632 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000633 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000634 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000635 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000636 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000637 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000638 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000639 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000640 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000641 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000642 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000643 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000644 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000645 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000646 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000647 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000648 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000649 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000650 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000651 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000652 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000653 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000654 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000655 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000656 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000657 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000658 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000659 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000660 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000661 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000662 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000663 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000664 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000665 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000666 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000667 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000668 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000669 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000670 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000671 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000672 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000673 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000674 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000675 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000676 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000677 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000678 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000679 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000680 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000681 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000682 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000683 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000684 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000685 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000686 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000687 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000688 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000689 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000690 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000691 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000692 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000693 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000694 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000695 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000696 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000697 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000698 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000699 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000700 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000701 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000702 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000703 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000704 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000705 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000706 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BV | 2025 | 3
1020000707 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000708 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000709 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000710 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000711 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000712 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000713 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000714 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 1358
1020000715 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000716 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000717 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000718 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000719 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000720 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000721 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000722 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000723 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000724 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000725 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000726 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000727 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000728 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000729 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000730 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000731 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000732 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000733 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000734 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BV | 2025 | 3 | 0
1020000735 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000736 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000737 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000738 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BV | 2025 | 3 | 0
1020000739 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000740 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000741 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000742 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000743 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000744 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000745 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000746 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000747 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000748 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000749 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000750 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000751 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000752 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000753 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000754 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1020000755 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000756 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000757 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000758 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000759 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000760 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000761 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000762 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000763 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000764 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000765 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000766 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000767 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000768 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000769 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000770 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000771 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000772 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000773 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000774 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000775 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000776 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000777 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000778 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000779 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000780 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000781 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000782 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000783 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000784 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000785 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000786 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000787 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000788 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000789 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000790 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000791 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000792 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000793 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000794 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000795 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000796 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000797 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000798 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000799 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000800 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000801 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000802 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BV | 2025 | 3
1020000803 | 17. Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  |  | BV | 2025 | 3 | 0

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | Number of poles assessed | Count of poles assessed | Identify # of inspected poles to reduce the number of pole failures & possibility of fire | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of poles assessed |  |  | BV | 2025 | 3 | 253
1030000001 | Number of poles that failed assessment (wind loading, age, deterioraton, unfixable GO-95 violation) | Count of poles that fail assessment | Identify proper pole replacement periodicty, lifespan, etc. and reduce possibility of fire | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of poles that fail assessment |  |  | BV | 2025 | 3 | 103
1030000002 | Number of poles replaced as a result of failed assessments | Count of poles replaced | Demonstrates progress of fire resilience efforts | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of poles replaced |  |  | BV | 2025 | 3 | 33
1030000003 | Number of poles remediated as a result of failed assessments | Count of poles remediated as a result of failed assessment | Demonstrates progress of fire resilience efforts | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of poles remediated as a result of failed assessment |  |  | BV | 2025 | 3 | 51
1030000004 | Number of Tree Attachments Removed | Count of tree attachments removed | Demonstrates progress toward goal of zero tree attachment and reduce possibility of fire | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of tree attachments removed |  |  | BV | 2025 | 3 | 0
1030000005 | Number of new poles installed as a result of Tree Attachments Removed | Count of poles installed to replace wiring attachment from prior tree attachment | Demonstrates progress in reducing direct vegetation contact risk and installing more resilient poles in place of the prior attachment. | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of poles installed to replace wiring attachment from prior tree attachment |  |  | BV | 2025 | 3 | 0
1030000006 | Length of Covered Bare Wire (Circuit Miles) | Miles of covered bare wire | Demonstrates progress in covering bare wire | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Miles of covered bare wire |  |  | BV | 2025 | 3 | 0
1030000007 | Percent of 34.5 kV System that is Overhead Bare Wire | Percent of 34.5 kV System that is Overhead Bare Wire | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Percent of 34.5 kV System that is Overhead Bare Wire |  |  | BV | 2025 | 3 | 0
1030000008 | Percent of 34.5 kV System that is Underground | Percent of 34.5 kV System that is underground | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Percent of 34.5 kV System that is underground |  |  | BV | 2025 | 3 | 0.11
1030000009 | Percent of 34.5 kV System that is Covered Wire | Percent of 34.5 kV System that is covered wire | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Percent of 34.5 kV System that is covered wire |  |  | BV | 2025 | 3 | 0.89
1030000010 | Percent of 4 kV System that is Overhead Bare Wire | Percent of 4 kV System that is Overhead Bare Wire | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Percent of 4 kV System that is Overhead Bare Wire |  |  | BV | 2025 | 3 | 0.53
1030000011 | Percent of 4 kV System that is Underground | Percent of 4 kV System that is underground | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Percent of 4 kV System that is underground |  |  | BV | 2025 | 3 | 0.25
1030000012 | Percent of 4 kV System that is Covered Wire | Percent of 4 kV System that is covered wire | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Percent of 34.5 kV System that is underground |  |  | BV | 2025 | 3 | 0.21
1030000013 | Number of Tree Attachments Remaining in System | Count of tree attachments | Demonstrates progress toward goal of zero tree attachment and reduce possibility of fire | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of tree attachments |  |  | BV | 2025 | 3 | 240
1030000014 | Number of Trees Trimmed | Count of trees trimmed as part of veg mgmt work | Inventory and identify trends | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of trees trimmed as part of veg mgmt work |  |  | BV | 2025 | 3 | 1238
1030000015 | Number of Trees Removed | Count of trees removed as part of veg mgmt work | Inventory and identify trends | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of trees removed as part of veg mgmt work |  |  | BV | 2025 | 3 | 43
1030000016 | Circuit Miles Trimmed | Number of Circuit Miles with VM trimming | Account for circuit miles that receive tree trimming activities per quarter | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Number of Circuit Miles with VM trimming |  |  | BV | 2025 | 3 | 10
1030000017 | VM QCs | Number of VM QCs performed | Include metrics for the number of quality checks performed on vegtation management activities | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Number of VM QCs performed |  |  | BV | 2025 | 3 | 34
1030000018 | Number of Substations Inspected | Number of Substations Inspected | Accounting record for number of substations inspected quarterly | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Number of Substations Inspected |  |  | BV | 2025 | 3 | 39
1030000019 | Number of Poles Intrusively Inspected | Number of Poles Intrusively Inspected | Inventory and identify performance trends | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Number of Poles Intrusively Inspected |  |  | BV | 2025 | 3 | 850
1030000020 | Number of Poles Failing Instrusive Inspection | Number of Poles Failing Intrusively Inspection | Inventory and identify trends | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Number of Poles Failing Intrusively Inspection |  |  | BV | 2025 | 3 | 15
1030000021 | Number of Customer Service Calls about Tree Trimming | Number of Customer Service Calls about Tree Trimming | Inventory and identify trends | Monitor changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Number of Customer Service Calls about Tree Trimming |  |  | BV | 2025 | 3 | 91
1030000022 | Number of Customer Engagements in Community Outreach for PSPS and WMP | Count of Engagements | Record of outreach performed each quarter related to WMP activities or PSPS preparedness | Monitor customer and community outreach activities | No third-party validation necessary | Number of outreach performed |  |  | BV | 2025 | 3 | 279
1030000023 | SAIDI due to PSPS | SAIDI Reliability Performance impacts due to PSPS | Identify impacts to SAIDI performance from PSPS events | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | SAIDI Reliability Performance impacts due to PSPS |  |  | BV | 2025 | 3 | 0
1030000024 | Number of NFDRS “Very Dry” and “Dry” Days | Count of NFDRS "very dry" and "dry" days | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of NFDRS "very dry" and "dry" days |  |  | BV | 2025 | 3 | 62
1030000025 | Number of PSPS Events | Count of PSPS events | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Count of PSPS events |  |  | BV | 2025 | 3 | 0
1030000026 | Maximum recorded sustained winds Recorded | Highest recorded sutained wind speed recorded | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Highest recorded sutained wind speed recorded |  |  | BV | 2025 | 3 | 28
1030000027 | Maximum recorded wind gusts Recorded | Highest recorded sutained wind gust recorded | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | Highest recorded sutained wind gust recorded |  |  | BV | 2025 | 3 | 41
1030000028 | Frequency of sustained high winds (number of days sustained wind > 50 mph) | Count of sustained high wind days recorded | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Data obtained from BVES owned weather stations | Count of sustained high wind days recorded |  |  | BV | 2025 | 3 | 0
1030000029 | Frequency of high wind gusts (number of days wind gusts > 50 mph) recorded | Count of days with high wind gusts recorded | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Data obtained from BVES owned weather stations | Count of days with high wind gusts recorded |  |  | BV | 2025 | 3 | 0

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | BV | 2025 | 3 | 0
1040000001 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | BV | 2025 | 3 | 0
1040000002 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1040000003 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000004 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000005 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000006 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | BV | 2025 | 3 | 0
1040000007 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | BV | 2025 | 3 | 0
1040000008 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1040000009 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000010 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000011 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000012 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | BV | 2025 | 3 | 0
1040000013 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | BV | 2025 | 3 | 0
1040000014 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1040000015 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000016 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000017 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000018 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not currently have this data but is working on a solution. | BV | 2025 | 3
1040000019 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not currently have this data but is working on a solution. | BV | 2025 | 3
1040000020 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1040000021 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000022 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3
1040000023 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not have any transmission lines | BV | 2025 | 3

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 1
1050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 1
1050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 1
1050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 1
1050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 1
1050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 1
1050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  |  | BV | 2025 | 3 | 0
1050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3
1050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | BV does not have any transmission lines | BV | 2025 | 3

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions | No |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | BV | 2025 | 3 | 0
1060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3
1060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions | No |  | BV does not have any transmission lines | BV | 2025 | 3

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 452.79
1070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 121.99
1070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 1.27
1070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 103.96
1070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 37.87
1070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 12
1070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 2
1070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | BV | 2025 | 3 | 0
1070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | BV | 2025 | 3 | 19245
1070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | BV | 2025 | 3 | 3282
1070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | BV | 2025 | 3 | 0
1070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 1301
1070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 177
1070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | BV | 2025 | 3 | 0
1070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 627
1070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 102
1070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BV | 2025 | 3 | 0
1070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | BV | 2025 | 3 | 8
1070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 6
1070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 9
1070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 9
1070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 2
1070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 1.17
1080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 1
1080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0.85
1090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 4.24
1090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BV | 2025 | 3 | 0
1090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BV | 2025 | 3
1090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 1
1090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | BV | 2025 | 3 | 0
1090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BV | 2025 | 3
1090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0
1090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | BV | 2025 | 3 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | BV | 2025 | 3 | 0
1100000001 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | BV | 2025 | 3 | 0
1100000002 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | BV | 2025 | 3 | 0
1100000003 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | BV | 2025 | 3 | 0
1100000004 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | BV | 2025 | 3 | 0
1100000005 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | BV | 2025 | 3 | 0
1100000006 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | BV | 2025 | 3 | 0
1100000007 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | BV | 2025 | 3 | 0
1100000008 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | BV | 2025 | 3 | 0
1100000009 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | BV | 2025 | 3 | 0
1100000010 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | BV | 2025 | 3 | 0
1100000011 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | BV | 2025 | 3 | 0
1100000012 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | BV | 2025 | 3 | 0
1100000013 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | BV | 2025 | 3 | 0
1100000014 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | BV | 2025 | 3 | 0
1100000015 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | BV | 2025 | 3 | 0
1100000016 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | BV | 2025 | 3 | 0
1100000017 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | BV | 2025 | 3 | 0
1100000018 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | BV | 2025 | 3 | 0
1100000019 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | BV | 2025 | 3 | 0
1100000020 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | BV | 2025 | 3 | 0
1100000021 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | BV | 2025 | 3 | 118178.2333
1100000022 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | BV | 2025 | 3 | 118178.2333
1100000023 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | BV | 2025 | 3 | 284.5954
1100000024 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | BV | 2025 | 3 | 284.5954
1100000025 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | BV | 2025 | 3 | 0.96075
1100000026 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | BV | 2025 | 3 | 0.96075
1100000027 | 3. Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | BV | 2025 | 3 | 0
1100000028 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BV | 2025 | 3 | 0
1100000029 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BV | 2025 | 3 | 0
1100000030 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BV | 2025 | 3 | 0
1100000031 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BV | 2025 | 3 | 0
1100000032 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BV | 2025 | 3 | 0
1100000033 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BV | 2025 | 3 | 0
1100000034 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | BV | 2025 | 3 | 0
1100000035 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | BV | 2025 | 3 | 0
1100000036 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | BV | 2025 | 3 | 0
1100000037 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | BV | 2025 | 3 | 0
1100000038 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | BV | 2025 | 3 | 0
1100000039 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | BV | 2025 | 3 | 0
1100000040 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | BV | 2025 | 3 | 0
1100000041 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | BV | 2025 | 3 | 0
1100000042 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | BV | 2025 | 3 | 0
1100000043 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | BV | 2025 | 3 | 0

## Table 13
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED OR MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1130000000 | T4835BV_20240614091250 | crossarm | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-14 | 3 | [7 empty] | BV | 2025 | 3
1130000001 | 8974BV_20250216080326 | pole | HFTD Tier 2 | Distribution | 2025-02-16 | 2026-02-15 | 2 | [7 empty] | BV | 2025 | 3
1130000002 | 62911CTC_20250328102339 | pole | HFTD Tier 2 | Distribution | 2025-03-28 | 2026-03-27 | 2 | [7 empty] | BV | 2025 | 3
1130000003 | 5720BV_20250429090326 | pole | HFTD Tier 2 | Distribution | 2025-04-29 | 2026-04-28 | 2 | [7 empty] | BV | 2025 | 3