## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | REPORTING QUARTER | QUANTITATIVE ACTUAL PROGRESS Q1 | QUANTITATIVE ACTUAL PROGRESS Q1-2 | QUANTITATIVE ACTUAL PROGRESS Q1-3 | QUANTITATIVE ACTUAL PROGRESS Q1-4 | QUALITATIVE ACTUAL PROGRESS Q1 | QUALITATIVE ACTUAL PROGRESS Q1-2 | QUALITATIVE ACTUAL PROGRESS Q1-3 | QUALITATIVE ACTUAL PROGRESS Q1-4 | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | LS Power | 2025-05-01 | Program |  |  | LSP-01 | Implement Hot Work Programs during construction and maintenance activities | Improve Safety and wildfire prevention in HFTD areas | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.8.3 | LSP-01 | LS Power_Grid Design, Operations, and Maintenance_Grid Design, Operations, and Maintenance_LSP-01_2025 | 102 | equipment ignition likelihood | No | Implementation of hot work program |  | 2025 | 4 | 2 | 2 | 2 | 2 |  |  |  |  | Completed
1010000001 | LS Power | 2025-05-01 | Program |  |  | LSP-02 | Implement Substation Inspection Program | Safely transition from construction to operating utility. | Vegetation Management and inspections | Vegetation Management and inspections |  | 8.2 | LSP-02 | LS Power_Vegetation Management and inspections_Vegetation Management and inspections_LSP-02_2025 | 102 | Contact from vegetation ignition likelihood | No | inspections done |  | 2025 | 4 | 1 | 4 | 7 | 10 |  |  |  |  | Completed
1010000002 | LS Power | 2025-05-01 | Project | 2024-06-01 | 2026-01-01 | LSP-03 | Enhance use of Computer Maintenance Management Systems (CMMS)/automation into LSPG-CA maintenance work orders | Ensure system reliability and public safety | Grid Design, Operations, and Maintenance | Grid Design, Operations, and Maintenance |  | 8.1.7 | LSP-03 | LS Power_Grid Design, Operations, and Maintenance_Grid Design, Operations, and Maintenance_LSP-03_2025 | 102 | equipment ignition likelihood | No | Percentage Integration |  | 2025 | 4 | 0 | 100 | 100 | 100 |  |  |  |  | Completed
1010000003 | LS Power | 2025-05-01 | Program |  |  | LSP-04 | Establish risk-based buffer zones and implement monthly substation inspection program once operational | Reduce risk of vegetation contact and potential wildfire spread | Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy |  | 7.2.1 | LSP-04 | LS Power_Wildfire Mitigation Strategy Development_Wildfire Mitigation Strategy_LSP-04_2025 | 120 | Contact from vegetation ignition likelihood | No | Vegetation inspections done |  | 2025 | 4 | 1 | 4 | 7 | 10 |  |  |  |  | Completed
1010000004 | LS Power | 2025-05-01 | Project | 2024-06-01 | 2024-12-01 | LSP-05 | Integrate StormGeo into decision-making and safety practices | Establish and maintain an environmental monitoring and weather forecasting program to reduce the risk of wildfires from environmental or weather-related conditions. | Situational Awareness and Forecasting | Situational Awareness and Forecasting |  | 8.3.2 | LSP-05 | LS Power_Situational Awareness and Forecasting_Situational Awareness and Forecasting_LSP-05_2025 | 132 | Wildfire spread | No | Integration % | Intergration was completed in 2024 and since has been used in daily operations. | 2025 | 4 | 0 | 0 | 0 | 0 |  |  |  |  | Completed
1010000005 | LS Power | 2025-05-01 | Project | 2024-06-01 | 2024-12-01 | LSP-06 | Implement 24/7 video security surveillance at substation locations | Increase awareness of incidents at facilities and improve wildfire detection | Situational Awareness and Forecasting | Situational Awareness and Forecasting |  | 8.3.2 | LSP-06 | LS Power_Situational Awareness and Forecasting_Situational Awareness and Forecasting_LSP-06_2025 | 132 | Wildfire spread | No | Cameras Installed |  | 2025 | 4 | 29 | 29 | 29 | 29 |  |  |  |  | Completed
1010000006 | LS Power | 2025-05-01 | Pilot |  |  | LSP-07 | Evaluate and enhance use of live video | Increase awareness of incident at facilities and improve wildfire detection | Situational Awareness and Forecasting | Situational Awareness and Forecasting |  | 8.3.2 | LSP-07 | LS Power_Situational Awareness and Forecasting_Situational Awareness and Forecasting_LSP-07_2025 | 132 | Wildfire spread | No | Camera Live Feed Analysis | Since LSP asest was energized in March, we will keep maturing situational awareness | 2025 | 4 | 0 | 0 | 0 | 1 |  |  |  |  | In Progress
1010000007 | LS Power | 2025-05-01 | Project | 2023-06-01 | 2028-12-01 | LSP-08 | Establish and ensure integration into Local Public Safety Computer dispatch systems. | Verify site locations and access information are integrated into relevant dispatch systems to improve response time and safety | Emergency Preparedness | Emergency Preparedness |  | 8.4.3 | LSP-08 | LS Power_Emergency Preparedness_Emergency Preparedness_LSP-08_2025 | 142 | Wildfire spread | No | Integration into dispatch systems | Completed in 2024 | 2025 | 4 | 0 | 0 | 0 | 0 |  |  |  |  | Completed
1010000008 | LS Power | 2025-05-01 | Program |  |  | LSP-09 | Work to build relationships with local fire agencies and conduct annual visits | Improve local response times and communication efficacy | Community outreach and engagement | Community outreach and engagement |  | 8.5.4 | LSP-09 | LS Power_Community outreach and engagement_Community outreach and engagement_LSP-09_2025 | 142 | Wildfire spread | Yes | Number of meetings |  | 2025 | 4 | 0 | 1 | 2 | 2 |  |  |  |  | Completed
1010000009 | LS Power | 2025-05-01 | Program |  |  | LSP-10 | Establish continuous improvement of emergency plan and procedures | Improve emergency preparedness | Emergency Preparedness | Emergency Preparedness |  | 8.4.2 | LSP-10 | LS Power_Emergency Preparedness_Emergency Preparedness_LSP-10_2025 | 142 | Wildfire hazard | No | Drafting of Emergency preparedness plan |  | 2025 | 4 | 1 | 1 | 2 | 2 |  |  |  |  | Completed
1010000010 | LS Power | 2025-05-01 | Program |  |  | LSP-11 | Formalize mechanisms to share lessons learned among ITO peers | Improve collaboration and best practices with other utilities | Community outreach and engagement | Community outreach and engagement |  | 8.5.5 | LSP-11 | LS Power_Community outreach and engagement_Community outreach and engagement_LSP-11_2025 | 175 | Wildfire hazard | No | Instances of Collaboration |  | 2025 | 4 | 3 | 4 | 5 | 8 |  |  |  |  | Completed

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000001 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000002 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000003 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000004 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000005 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000006 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000007 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000008 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000009 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000010 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000011 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000012 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000013 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000014 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000015 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000016 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000017 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000018 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000019 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000020 | 1. Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000021 | 1. Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000022 | 1. Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000023 | 1. Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000024 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000025 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000026 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000027 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000028 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000029 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000030 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000031 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000032 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000033 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000034 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000035 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000036 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000037 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000038 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000039 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000040 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000041 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000042 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000043 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000044 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000045 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000046 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000047 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000048 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000049 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000050 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000051 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000052 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000053 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000054 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000055 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000056 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000057 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000058 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000059 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LS Power | 2025 | 4
1020000060 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000061 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000062 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000063 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000064 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000065 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000066 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000067 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000068 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000069 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000070 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000071 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  | Not Applicable | LS Power | 2025 | 4
1020000072 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000073 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000074 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000075 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000076 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000077 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000078 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000079 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000080 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000081 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000082 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000083 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000084 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000085 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000086 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000087 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000088 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000089 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000090 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000091 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000092 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000093 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000094 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000095 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000096 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000097 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000098 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000099 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000100 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000101 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000102 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000103 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000104 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000105 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000106 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000107 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LS Power | 2025 | 4
1020000108 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  | Not Applicable | LS Power | 2025 | 4 | 0
1020000109 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  | Not Applicable | LS Power | 2025 | 4
1020000110 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  | Not Applicable | LS Power | 2025 | 4
1020000111 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  | Not Applicable | LS Power | 2025 | 4
1020000112 | 8. Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  | Not Applicable | LS Power | 2025 | 4
1020000113 | 9. Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  | Not Applicable | LS Power | 2025 | 4
1020000114 | 9. Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  | Not Applicable | LS Power | 2025 | 4
1020000115 | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  | Not Applicable | LS Power | 2025 | 4
1020000116 | 11. Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  | Not Applicable | LS Power | 2025 | 4
1020000117 | 11. Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  | Not Applicable | LS Power | 2025 | 4
1020000118 | 12. Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  | Not Applicable | LS Power | 2025 | 4
1020000119 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000120 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000121 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000122 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000123 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000124 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000125 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000126 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000127 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000128 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000129 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000130 | 13. Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  | Not Applicable | LS Power | 2025 | 4
1020000131 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000132 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000133 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000134 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000135 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000136 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000137 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000138 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000139 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000140 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000141 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000142 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000143 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000144 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000145 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000146 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000147 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000148 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000149 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000150 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000151 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000152 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000153 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000154 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000155 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000156 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000157 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000158 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000159 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000160 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000161 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000162 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000163 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000164 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000165 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000166 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000167 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000168 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000169 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000170 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000171 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000172 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000173 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000174 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000175 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000176 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000177 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000178 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000179 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000180 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000181 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000182 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000183 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000184 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000185 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000186 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000187 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000188 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000189 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000190 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000191 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000192 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000193 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000194 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000195 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000196 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000197 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000198 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000199 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000200 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000201 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000202 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000203 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000204 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000205 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000206 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000207 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000208 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000209 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000210 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000211 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000212 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000213 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000214 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000215 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000216 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000217 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000218 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000219 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000220 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000221 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000222 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000223 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000224 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000225 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000226 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000227 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000228 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000229 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000230 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000231 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000232 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000233 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000234 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000235 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000236 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000237 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000238 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000239 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000240 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000241 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000242 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000243 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000244 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000245 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000246 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000247 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000248 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000249 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000250 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000251 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000252 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000253 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000254 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000255 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000256 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000257 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000258 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000259 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000260 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000261 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000262 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000263 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000264 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000265 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000266 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000267 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000268 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000269 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000270 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000271 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000272 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000273 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000274 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000275 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000276 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000277 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000278 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000279 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000280 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000281 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000282 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000283 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000284 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000285 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000286 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000287 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000288 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000289 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000290 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000291 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000292 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000293 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000294 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000295 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000296 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000297 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000298 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000299 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000300 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000301 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000302 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000303 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000304 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000305 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000306 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000307 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000308 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000309 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000310 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000311 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000312 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000313 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000314 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000315 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000316 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000317 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000318 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000319 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000320 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000321 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000322 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000323 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000324 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000325 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000326 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000327 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000328 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000329 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000330 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000331 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000332 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000333 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000334 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000335 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000336 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000337 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000338 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000339 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000340 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000341 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000342 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000343 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000344 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000345 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000346 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000347 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000348 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000349 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000350 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000351 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000352 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000353 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000354 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000355 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000356 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000357 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000358 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000359 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000360 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000361 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000362 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000363 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000364 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000365 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000366 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000367 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000368 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000369 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000370 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000371 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000372 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000373 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000374 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000375 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000376 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000377 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000378 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000379 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000380 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000381 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000382 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000383 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000384 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000385 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000386 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000387 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000388 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000389 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000390 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000391 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000392 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000393 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000394 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000395 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000396 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000397 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000398 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000399 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000400 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000401 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000402 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000403 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000404 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000405 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000406 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000407 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000408 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000409 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000410 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000411 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000412 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000413 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000414 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000415 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000416 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000417 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000418 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000419 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000420 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000421 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000422 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000423 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000424 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000425 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000426 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000427 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000428 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000429 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000430 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000431 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000432 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000433 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000434 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4 | 210
1020000435 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000436 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000437 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000438 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000439 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000440 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000441 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000442 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000443 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000444 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000445 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000446 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000447 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000448 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000449 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000450 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000451 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000452 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000453 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000454 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LS Power | 2025 | 4
1020000455 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000456 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000457 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000458 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000459 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000460 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000461 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000462 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000463 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000464 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000465 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000466 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000467 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000468 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000469 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000470 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000471 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000472 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000473 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000474 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000475 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000476 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000477 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000478 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000479 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000480 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000481 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000482 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4 | 1
1020000483 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000484 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000485 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000486 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000487 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000488 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000489 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000490 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LS Power | 2025 | 4
1020000491 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000492 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000493 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000494 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000495 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000496 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000497 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000498 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000499 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000500 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000501 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000502 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000503 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000504 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000505 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000506 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000507 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000508 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000509 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000510 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000511 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000512 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000513 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000514 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000515 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000516 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000517 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000518 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000519 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000520 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000521 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000522 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000523 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000524 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000525 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000526 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000527 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000528 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000529 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000530 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000531 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000532 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000533 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000534 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000535 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000536 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000537 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000538 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000539 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000540 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000541 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000542 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000543 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000544 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000545 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000546 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000547 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000548 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000549 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000550 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000551 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000552 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000553 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000554 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000555 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000556 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000557 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000558 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000559 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000560 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000561 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000562 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000563 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000564 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000565 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000566 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000567 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000568 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000569 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000570 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000571 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000572 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000573 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000574 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000575 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000576 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000577 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000578 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000579 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000580 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000581 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000582 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000583 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000584 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000585 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000586 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000587 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000588 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000589 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000590 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000591 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000592 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000593 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000594 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000595 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000596 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000597 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000598 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000599 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000600 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000601 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000602 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000603 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000604 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000605 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000606 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000607 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000608 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000609 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000610 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000611 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000612 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000613 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000614 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000615 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000616 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000617 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000618 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000619 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000620 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000621 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000622 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000623 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000624 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000625 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000626 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000627 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000628 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000629 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000630 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000631 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000632 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000633 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000634 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000635 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000636 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000637 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000638 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000639 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000640 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000641 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000642 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000643 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000644 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000645 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000646 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000647 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000648 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000649 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000650 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000651 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000652 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000653 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000654 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000655 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000656 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000657 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000658 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000659 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000660 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000661 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000662 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000663 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000664 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000665 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000666 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000667 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000668 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000669 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000670 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000671 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000672 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000673 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000674 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000675 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000676 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000677 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000678 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000679 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000680 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000681 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000682 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000683 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000684 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000685 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000686 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000687 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000688 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000689 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000690 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000691 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000692 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000693 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000694 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000695 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000696 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000697 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000698 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000699 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000700 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000701 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000702 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000703 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000704 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000705 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000706 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LS Power | 2025 | 4
1020000707 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000708 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000709 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000710 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000711 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000712 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000713 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000714 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000715 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000716 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000717 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000718 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000719 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000720 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000721 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000722 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000723 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000724 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000725 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000726 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000727 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000728 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000729 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000730 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000731 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000732 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000733 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000734 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000735 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000736 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000737 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000738 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000739 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000740 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000741 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000742 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000743 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000744 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000745 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000746 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000747 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000748 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000749 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000750 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000751 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000752 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000753 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000754 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000755 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000756 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000757 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000758 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000759 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000760 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000761 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000762 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000763 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000764 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000765 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000766 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000767 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000768 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000769 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000770 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000771 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000772 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000773 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000774 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000775 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000776 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000777 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000778 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000779 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000780 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000781 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000782 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000783 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000784 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000785 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000786 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000787 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000788 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000789 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000790 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000791 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000792 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000793 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000794 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000795 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000796 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000797 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000798 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000799 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000800 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000801 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000802 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LS Power | 2025 | 4
1020000803 | 17. Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | Not Applicable | LS Power | 2025 | 4

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | Camera Installation | Quantity of substation cameras installed | Count of cameras installed for initiative tracking | Installation of cameras |  | Number of Cameras | 29 Cameras were installed in 2024 | Not applicable | LS Power | 2025 | 4 | 29
1030000001 | Total Integration % | Percentage of integration of weather forecasting tool into decision making | Improve weather safety and awareness | improved decision making based off of forecasts |  | Percentage integration | Completed in 2024 | Not applicable | LS Power | 2025 | 4 | 1

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000001 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000002 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000003 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000004 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000005 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000006 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000007 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000008 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000009 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000010 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000011 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000012 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000013 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000014 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000015 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000016 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000017 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000018 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000019 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000020 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000021 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000022 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4
1040000023 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LS Power | 2025 | 4

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4
1050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | Not Applicable | LS Power | 2025 | 4

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4
1060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  |  | Not Applicable | LS Power | 2025 | 4

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  | Not Applicable | LS Power | 2025 | 4
1070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  | Not Applicable | LS Power | 2025 | 4
1070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  | Not Applicable | LS Power | 2025 | 4
1070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LS Power | 2025 | 4
1070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4 | 1
1070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4 | 1
1070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LS Power | 2025 | 4
1090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LS Power | 2025 | 4
1090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4
1090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LS Power | 2025 | 4

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000001 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000002 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000003 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000004 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  | Not applicable | LS Power | 2025 | 4
1100000005 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  | Not applicable | LS Power | 2025 | 4
1100000006 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  | Not applicable | LS Power | 2025 | 4
1100000007 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  | Not applicable | LS Power | 2025 | 4
1100000008 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  | Not applicable | LS Power | 2025 | 4
1100000009 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  | Not applicable | LS Power | 2025 | 4
1100000010 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  | Not applicable | LS Power | 2025 | 4
1100000011 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  | Not applicable | LS Power | 2025 | 4
1100000012 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000013 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000014 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000015 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000016 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  | Not applicable | LS Power | 2025 | 4
1100000017 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  | Not applicable | LS Power | 2025 | 4
1100000018 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  | Not applicable | LS Power | 2025 | 4
1100000019 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  | Not applicable | LS Power | 2025 | 4
1100000020 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  | Not applicable | LS Power | 2025 | 4
1100000021 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  | Not applicable | LS Power | 2025 | 4
1100000022 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  | Not applicable | LS Power | 2025 | 4
1100000023 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  | Not applicable | LS Power | 2025 | 4
1100000024 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  | Not applicable | LS Power | 2025 | 4
1100000025 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  | Not applicable | LS Power | 2025 | 4
1100000026 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  | Not applicable | LS Power | 2025 | 4
1100000027 | 3. Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  | Not applicable | LS Power | 2025 | 4
1100000028 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not applicable | LS Power | 2025 | 4
1100000029 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not applicable | LS Power | 2025 | 4
1100000030 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not applicable | LS Power | 2025 | 4
1100000031 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not applicable | LS Power | 2025 | 4
1100000032 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not applicable | LS Power | 2025 | 4
1100000033 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not applicable | LS Power | 2025 | 4
1100000034 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  | Not applicable | LS Power | 2025 | 4
1100000035 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  | Not applicable | LS Power | 2025 | 4
1100000036 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  | Not applicable | LS Power | 2025 | 4
1100000037 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  | Not applicable | LS Power | 2025 | 4
1100000038 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  | Not applicable | LS Power | 2025 | 4
1100000039 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  | Not applicable | LS Power | 2025 | 4
1100000040 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  | Not applicable | LS Power | 2025 | 4
1100000041 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  | Not applicable | LS Power | 2025 | 4
1100000042 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  | Not applicable | LS Power | 2025 | 4
1100000043 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  | Not applicable | LS Power | 2025 | 4

## Table 13
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED OR MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1130000000 | [13 empty] | Not applicable | LS Power | 2025 | 4