## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | REPORTING QUARTER | QUANTITATIVE ACTUAL PROGRESS Q1 | QUANTITATIVE ACTUAL PROGRESS Q1-2 | QUANTITATIVE ACTUAL PROGRESS Q1-3 | QUANTITATIVE ACTUAL PROGRESS Q1-4 | QUALITATIVE ACTUAL PROGRESS Q1 | QUALITATIVE ACTUAL PROGRESS Q1-2 | QUALITATIVE ACTUAL PROGRESS Q1-3 | QUALITATIVE ACTUAL PROGRESS Q1-4 | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Retainment of Inspectors and Internal Workforce Development | Develop a plan to increase retention over time for trained and qualified inspectors. Develop a plan to focus on increasing and sustaining a consistent, year-over-year internal workforce that builds on existing experience and mentors new employees for asset inspections. | This initiative will assist in maintaining a consistent workforce | Grid Design, Operations and Maintenance | Retainment of Inspectors and Internal Workforce Development |  | 8.1.1.1 | AI-01 | PG&E_Grid Design, Operations and Maintenance_Retainment of Inspectors and Internal Workforce Development_AI-01_2025 | 589 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | In Q1 2025, System Inspection officially closed out this commitment. This initiative has increased our permanent compliance inspector headcount in our organization by 74 inspectors and increased employee tenure. | In Q1 2025, System Inspection officially closed out this commitment. This initiative has increased our permanent compliance inspector headcount in our organization by 74 inspectors and increased employee tenure. | In Q1 2025, System Inspection officially closed out this commitment. This initiative has increased our permanent compliance inspector headcount in our organization by 74 inspectors and increased employee tenure. |  | Completed
1010000001 | PG&E | 2025-11-03 | Program |  |  | Detailed Inspection Transmission – Ground | Complete detailed aerial inspections on approximately 22,000 transmission structures in PG&E’s asset registry as of January 1, 2025. | This initiative includes detailed inspections (ground) of transmission poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Ground |  | 8.1.1.2 | AI-02 | PG&E_Grid Design, Operations and Maintenance_Detailed Inspection Transmission – Ground_AI-02_2025 | 477 | Equipment ignition likelihood | Yes | Transmission Structures | Please note that Q1 value has changed from 12,384 to 12,428 and Q2 value has changed from 22,350 to 22,991.The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis is due to asset re-inspection, tier type change and removed, replaced or de-activated. | 2025 | 3 | 12428 | 22991 | 24025 | [5 empty] | Completed
1010000002 | PG&E | 2025-11-03 | Program |  |  | Detailed Inspection Transmission – Aerial | Complete detailed aerial inspections on approximately 19,000 transmission structures in PG&E’s asset registry as of January 1, 2025. | This initiative includes detailed inspections (aerial) of transmission poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Aerial |  | 8.1.1.2 | AI-04 | PG&E_Grid Design, Operations and Maintenance_Detailed Inspection Transmission – Aerial_AI-04_2025 | 478 | Equipment ignition likelihood | Yes | Transmission Structures | Please note that Q1 value has changed from 6,964 to 6,975 and Q2 value has changed from 20,439 to 20,554.The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis is due to asset re-inspection, tier type change and removed, replaced or de-activated. | 2025 | 3 | 6975 | 20554 | 23489 | [5 empty] | Completed
1010000003 | PG&E | 2025-11-03 | Program |  |  | Detailed Inspection Transmission – Climbing | Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2025. | This initiative includes detailed inspections (climbing) of transmission poles which can reduce the potential for equipment failure which could case a potential wildfire ignition. | Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Climbing |  | 8.1.1.2 | AI-05 | PG&E_Grid Design, Operations and Maintenance_Detailed Inspection Transmission – Climbing_AI-05_2025 | 479 | Equipment ignition likelihood | Yes | Transmission Structures | Please note that Q1 value has changed from 423 to 555 and Q2 value has changed from 1,253 to 1,462. The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis is due to asset re-inspection, tier type change and removed, replaced or de-activated. | 2025 | 3 | 555 | 1462 | 1873 | [5 empty] | Completed
1010000004 | PG&E | 2025-11-03 | Program |  |  | Perform transmission IR inspections | Infrared patrols will be performed on 3,500 circuit miles of energized transmission line. | This initiative includes transmission infrared inspections which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | Perform transmission IR inspections |  | 8.1.1.2 | AI-06 | PG&E_Grid Design, Operations and Maintenance_Perform transmission IR inspections_AI-06_2025 | 480 | Equipment ignition likelihood | Yes | Miles | The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis is due to asset re-inspection, tier type change and removed, replaced or de-activated. | 2025 | 3 | 1025.47 | 2322.55 | 3629.09 | [5 empty] | Completed
1010000005 | PG&E | 2025-11-03 | Program |  |  | Detailed Ground and Aerial Inspections – Distribution | Complete detailed inspections on approximately 244,000 distribution poles, which will be identified in PG&E’s asset registry as of December 27, 2022. | This initiative includes detailed inspections of distribution poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | Detailed Ground and Aerial Inspections – Distribution |  | 8.1.1.2 | AI-07 | PG&E_Grid Design, Operations and Maintenance_Detailed Ground and Aerial Inspections – Distribution_AI-07_2025 | 487 | Equipment ignition likelihood | Yes | Distribution Poles | Please note that Q1 value has changed from 53,564 to 57,580 and Q2 value has changed from 109,025 to 129,887.The quarterly data we provide is a snapshot in time and given the dynamic nature of our portfolio, the actual may shift after the data is provided to Energy Safety on a quarterly basis is due to asset re-inspection, tier type change and removed, replaced or de-activated. | 2025 | 3 | 57580 | 129887 | 225069 | [5 empty] | In Progress
1010000006 | PG&E | 2025-11-03 | Program |  |  | Supplemental Inspections – Substation Distribution | Complete supplemental inspections on 78 distribution substations. | This initiative provides for supplemental distribution substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | Supplemental Inspections – Substation Distribution |  | 8.1.1.2 | AI-08 | PG&E_Grid Design, Operations and Maintenance_Supplemental Inspections – Substation Distribution_AI-08_2025 | 498 | Equipment ignition likelihood | Yes | Distribution Substations | The Substation Inspection Process Flow Figure 8.1.3-6 located in PG&E’s 2023-2025 WMP is incorrect regarding Emergency issues. The yes and no values for the Emergency issue decision point are incorrect and should be reversed. If it is not an emergency, then a decision needs to be made on if the work can be completed as minor work. If it is an emergency, we need to create emergency LC and follow emergency procedures. Note this mistake was presented to Energy Safety for their awareness. They will inform us if there are actions that we need to take. | 2025 | 3 | 0 | 78 | 78 | [5 empty] | Completed
1010000007 | PG&E | 2025-11-03 | Program |  |  | Supplemental Inspections – Substation Transmission | Complete supplemental inspections on 41 transmission substations. | This initiative provides for supplemental transmission substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | Supplemental Inspections – Substation Transmission |  | 8.1.1.2 | AI-09 | PG&E_Grid Design, Operations and Maintenance_Supplemental Inspections – Substation Transmission_AI-09_2025 | 498 | Equipment ignition likelihood | Yes | Transmission Substations | The Substation Inspection Process Flow Figure 8.1.3-6 located in PG&E’s 2023-2025 WMP is incorrect regarding Emergency issues. The yes and no values for the Emergency issue decision point are incorrect and should be reversed. If it is not an emergency, then a decision needs to be made on if the work can be completed as minor work. If it is an emergency, we need to create emergency LC and follow emergency procedures. Note this mistake was presented to Energy Safety for their awareness. They will inform us if there are actions that we need to take. | 2025 | 3 | 0 | 41 | 41 | [5 empty] | Completed
1010000008 | PG&E | 2025-11-03 | Program |  |  | Supplemental Inspections – Hydroelectric Substations and Powerhouses | Complete supplemental inspections on 40 Hydroelectric Generation Substations and Powerhouses. | This initiative provides for supplemental hydroelectric substation and powerhouse inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | Supplemental Inspections – Hydroelectric Substations and Powerhouses |  | 8.1.1.2 | AI-10 | PG&E_Grid Design, Operations and Maintenance_Supplemental Inspections – Hydroelectric Substations and Powerhouses_AI-10_2025 | 498 | Equipment ignition likelihood | Yes | Hydroelectric Substations and Powerhouse | The Substation Inspection Process Flow Figure 8.1.3-6 located in PG&E’s 2023-2025 WMP is incorrect regarding Emergency issues. The yes and no values for the Emergency issue decision point are incorrect and should be reversed. If it is not an emergency, then a decision needs to be made on if the work can be completed as minor work. If it is an emergency, we need to create emergency LC and follow emergency procedures. Note this mistake was presented to Energy Safety for their awareness. They will inform us if there are actions that we need to take. | 2025 | 3 | 0 | 40 | 42 | [5 empty] | Completed
1010000009 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Filling Asset Inventory Data Gaps | Populate missing age data in the Asset Registry (using “Installation Date” data element as a proxy) to 90 percent weighted average across risk prioritized distribution and transmission equipment. | This initiative will populate missing age data in the Asset Registry | Grid Design, Operations and Maintenance | Filling Asset Inventory Data Gaps |  | 8.1.1.1 | AI-11 | PG&E_Grid Design, Operations and Maintenance_Filling Asset Inventory Data Gaps_AI-11_2025 | 521 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | This objective is on track. In Q1, the estimated age model that had undergone development in 2024 was formally published for the in-scope risk-prioritized distribution and transmission equipment types. This estimated age model produces high-confidence data-derived installation years for the targeted equipment types by identifying age proxies by equipment type, statistically ranking these methods, and then applying the highest-ranked available age proxy to assets that do not have an installation date recorded in the system of record. | This objective is on track. In Q2, the GIS AI-11 project team worked with the asset owners of the in-scope equipment types to secure their approval of the thresholds that will be applied to the estimated age model output. The thresholds determine which methods of estimating an age will be considered approved for the purposes of this AI-11 WMP objective and which will not — in other words, the thresholds determine which estimated ages will be counted in the completion metrics for the AI-11 objective and which will not. The AI-11 project team also began to compile the necessary records of evidence (both internal & external) to close out the AI-11 objective once threshold approval is secured from asset owners. The project team anticipates completing the AI-11 objective of reaching a 90% fill rate by the end of Q3 2025. | This objective remains on track. In Q3, we reached the 90% fill rate. The record of evidence is pending internal review which will take place in Q4 2025. The objective will be completed by the end of the year. |  | In Progress
1010000010 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-09-30 | Community Outreach and Engagement – Meetings | PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. | This initiative concerns customer and community events to further awareness of WMP activities. | Community Outreach and Engagement | Community Outreach and Engagement – Meetings |  | 8.5.1.1 | CO-01 | PG&E_Community Outreach and Engagement_Community Outreach and Engagement – Meetings_CO-01_2025 | 895 | Wildfire vulnerability | No |  |  | 2025 | 3 |  |  |  |  | This objective is on track. In Q1 of 2025, a total of five Regional Town Halls were conducted. These five Regional Town Halls conducted count toward the CO-01 commitment, as they were CWSP-specific. | In Q2 of 2025, a total of 10 Wildfire Safety Webinars were conducted. The 10 Wildfire Safety Webinars conducted count toward the CO-01 commitment, as they were CWSP-specific. This objective is on track with a YTD total of 15 events. | This objective was completed on September 10, 2025. This objective required PG&E to hold a total of 22 community engagement meetings annually within its five regions of service, which would include, but not be limited to, a mix of webinars, open houses, and town halls. In Q1 of 2025, 5 CWSP-specific regional town halls were completed. In Q2 2025, a total of 10 CWSP-specific events were completed, comprising 9 regional webinars and 1 in-person open house. In Q3 of 2025, a total of 7 CWSP-specific events were completed, consisting of 5 regional town halls, 1 regional webinar and 1 in-person open house. |  | Completed
1010000011 | PG&E | 2025-11-03 | Program |  |  | Community Engagement – Surveys | PG&E will complete two PSPS education and outreach surveys. | This initiative concerns customer and community events to further awareness of WMP activities focusing on PSPS events. | Community Outreach and Engagement | Community Engagement – Surveys |  | 8.5.1.2 | CO-02 | PG&E_Community Outreach and Engagement_Community Engagement – Surveys_CO-02_2025 | 895 | Wildfire vulnerability | No | Survey |  | 2025 | 3 | 1 | 1 | 1 | [5 empty] | In Progress
1010000012 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-11-30 | Complete PSPS and Wildfire Tabletop and Functional Exercises | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP). | This initiative will complete the PSPS and Wildfire Tabletop and Functional Exercise to assist with our response to emergency activations, including wildfires. | Emergency Preparedness Plan | Complete PSPS and Wildfire Tabletop and Functional Exercises |  | 8.4.1.1 | EP-01 | PG&E_Emergency Preparedness Plan_Complete PSPS and Wildfire Tabletop and Functional Exercises_EP-01_2025 | 829 | PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | This commitment is on track. The Wildfire and PSPS tabletop exercise was held on 3/27/25. The Wildfire and PSPS FSE is scheduled for 4/28/25 to 5/2/25. | This commitment is on track. PSPS and Wildfire tabletop exercise was completed on March 27, 2025 and the PSPS and Wildfire full-scale exercise was completed on May 2, 2025. | This commitment is now completed. The Wildfire and PSPS tabletop exercise was held on March 27, 2025. The Wildfire and PSPS Full-Scale Exercise was held from April 28, 2025 to May 2, 2025. The PSPS Seminar was completed on September 3, 2025. |  | Completed
1010000013 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Maintain all hazards planning and preparedness program | Maintain the All Hazards Planning and Preparedness Program to provide emergency response and safely and expeditiously restore service. | This initiative will review and update the All Hazards Planning and Preparedness procedures, to assist with our response to emergency activations, including wildfires. | Emergency Preparedness Plan | Maintain all hazards planning and preparedness program |  | 8.4.1.1 | EP-02 | PG&E_Emergency Preparedness Plan_Maintain all hazards planning and preparedness program_EP-02_2025 | 846 | PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | This program is on track. The Wildfire, Volcano and Disaster Rebuild annexes were completed in Q1. | The Emergency Communications, Information Technology, and Physical Threat annexes were completed in Q2 and this program remains on track for 2025. | The Electric, Infectious Disease and Pandemic Response, Public Safety Power Shutoff and Capacity Shortage annexes were completed in Q3 and this program remains on track for 2025. |  | In Progress
1010000014 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Expand all hazards planning to include additional threats and scenarios | Expand the All Hazards Planning and Preparedness Program to include additional threats and scenarios. | This initiative will review and update the All Hazards Planning and Preparedness procedures focused on threats and scenarios, to assist with our response to emergency activations, including wildfires. | Emergency Preparedness Plan | Expand all hazards planning to include additional threats and scenarios |  | 8.4.1.1 | EP-04 | PG&E_Emergency Preparedness Plan_Expand all hazards planning to include additional threats and scenarios_EP-04_2025 | 846 | PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | This work is on track. The Volcano Annex was completed in Q1. | This work remains on track. The CERP and Wildfire Annex were published and the PSPS Annex will be completed in Q3. | This objective is on track. The PSPS Annex was published in Q3 the CERP will be published in Q4. |  | In Progress
1010000015 | PG&E | 2025-11-03 | Program |  |  | Annually review, and revise if appropriate, the Company Emergency Response Plan (CERP) and the two wildfire-related annexes (the Wildfire Annex and the PSPS Annex) | 3 documents (1 CERP and 2 wildfire-related annexes) | This initiative will review, and revise the CERP and 2 Wildfire Related Annexes to provide emergency response safely and expeditiously restore service, including during wildfires. | Emergency Preparedness Plan | Annually review, and revise if appropriate, the Company Emergency Response Plan (CERP) and the two wildfire-related annexes (the Wildfire Annex and the PSPS Annex) |  | 8.4.1.2 | EP-06 | PG&E_Emergency Preparedness Plan_Annually review, and revise if appropriate, the Company Emergency Response Plan (CERP) and the two wildfire-related annexes (the Wildfire Annex and the PSPS Annex)_EP-06_2025 | 846 | PSPS likelihood | No | 1 CERP and 2 wildfire related annexes |  | 2025 | 3 | 1 | 1 | 2 | [5 empty] | In Progress
1010000016 | PG&E | 2025-11-03 | Program |  |  | System Hardening – Distribution | Complete 520 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. | This initiative will harden distribution circuit miles through overhead system hardening, undergrounding, and the removal of overhead lines to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | System Hardening – Distribution |  | 8.1.1.2 | GH-01 | PG&E_Grid Design, Operations and Maintenance_System Hardening – Distribution_GH-01_2025 | 400 | Equipment ignition likelihood | No | Circuit Miles |  | 2025 | 3 | 50.12 | 187.92 | 347.97 | [5 empty] | In Progress
1010000017 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-03-31 | Evaluate Covered Conductor Effectiveness | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. | This initiative will calculate the covered conductor effective using pervious year's outage data on the lines that have covered conductors for consideration in future system hardening workplans. | Grid Design, Operations and Maintenance | Evaluate Covered Conductor Effectiveness |  | 8.1.1.1 | GH-02 | PG&E_Grid Design, Operations and Maintenance_Evaluate Covered Conductor Effectiveness_GH-02_2025 | 400 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | The team updated the covered conductor effectiveness by reviewing all outage data from 2024, updated the white-paper with the refreshed analysis, and informed the WRGSC of the results. All tasks for this initiative are now complete. | The initiative was completed in Q1. | This commitment was completed in Q1 of 2025. |  | Completed
1010000018 | PG&E | 2025-11-03 | Program |  |  | 10K Undergrounding | Complete 330 circuit miles of undergrounding work. The 330-circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. | This initiative will underground electrical facilities to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 10K Undergrounding |  | 8.1.1.2 | GH-04 | PG&E_Grid Design, Operations and Maintenance_10K Undergrounding_GH-04_2025 | 404 | Equipment ignition likelihood | No | Circuit Miles |  | 2025 | 3 | 23.88 | 55.49 | 152.98 | [5 empty] | In Progress
1010000019 | PG&E | 2025-11-03 | Program |  |  | System Hardening – Transmission | Remove or replace 5 circuit miles of transmission conductor. | This initiative will remove or replace 5 circuit miles of transmission conductor. | Grid Design, Operations and Maintenance | System Hardening – Transmission |  | 8.1.1.2 | GH-05 | PG&E_Grid Design, Operations and Maintenance_System Hardening – Transmission_GH-05_2025 | 441 | Equipment ignition likelihood | No | Circuit Miles |  | 2025 | 3 | 0 | 19.4 | 19.4 | [5 empty] | Completed
1010000020 | PG&E | 2025-11-03 | Program |  |  | System Hardening – Transmission Shunt Splices | Install shunt splice(s) on 25 transmission lines. | This initiative will install shunt splice(s) on transmission lines to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | System Hardening – Transmission Shunt Splices |  | 8.1.1.2 | GH-06 | PG&E_Grid Design, Operations and Maintenance_System Hardening – Transmission Shunt Splices_GH-06_2025 | 441 | Equipment ignition likelihood | No | Transmission Lines |  | 2025 | 3 | 3 | 8 | 19 | [5 empty] | In Progress
1010000021 | PG&E | 2025-11-03 | Program |  |  | Non-Exempt Expulsion Fuse – Removal | Remove non-exempt expulsion fuses/ cutouts from approximately 1,400 fuse locations (based on known population as of 1/26/23) identified on distribution poles. | This initiative will remove non-exempt equipment that may generate electrical arcs, sparks, or hot material during its normal operation. | Grid Design, Operations and Maintenance | Non-Exempt Expulsion Fuse – Removal |  | 8.1.1.2 | GH-10 | PG&E_Grid Design, Operations and Maintenance_Non-Exempt Expulsion Fuse – Removal_GH-10_2025 | 467 | Equipment ignition likelihood | No | Fuses | Please note that Q1 value has changed from 112 to 118 and Q2 value has changed from 462 to 472. In our last report, we signaled that we would not meet the 2025 WMP target of 1,400 non-exempt line fuse removals. This was due to overperformance in previous years, and replacements through other programs, which left the remaining population at the start of 2025 with only 848 line fuses. In efforts to honor our original WMP target of replacing 1,400 non-exempt line fuses in 2025, we are now going to meet the 1,400 WMP target with a combination of 848 line fuse removals and 552 equipment fuse removals. | 2025 | 3 | 118 | 472 | 882 | [5 empty] | In Progress
1010000022 | PG&E | 2025-11-03 | Program |  |  | System Hardening – Transmission Conductor Segment Replacement | Replace conductor segments on 2 transmission lines | This initiative will replace conductor segments on 2 transmission lines. | Grid Design, Operations and Maintenance | System Hardening – Transmission Conductor Segment Replacement |  | 8.1.1.2 | GH-11 | PG&E_Grid Design, Operations and Maintenance_System Hardening – Transmission Conductor Segment Replacement_GH-11_2025 | 441 | Equipment ignition likelihood | No | Transmission Lines |  | 2025 | 3 | 1 | 2 | 2 | [5 empty] | Completed
1010000023 | PG&E | 2025-11-03 | Program |  |  | Asset Inspections – Quality Assurance | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Inspection – HFTD/HFRA: 500 audit locations*; 95% pass rate Distribution Inspections – HFTD/HFRA: 1,500 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative audits the quality of transmission and distribution system inspections, which can help identify gaps and implement improvements for inspections. | Grid Design, Operations and Maintenance | Asset Inspections – Quality Assurance |  | 8.1.1.2 | GM-01 | PG&E_Grid Design, Operations and Maintenance_Asset Inspections – Quality Assurance_GM-01_2025 | 529 | Equipment ignition likelihood | No | Pass Rate | QA System Inspection Transmission Pass Rate: Total # of Locations Passed / Total # of Locations Audited Year to Date (01/01/2025 – 09/30/2025): Pass Rate -> 100.0% Total # of Locations Passed -> 1285 Total # of Locations Failed -> 0 Total # of Locations Audited -> 1285 07/01/2025 – 09/30/2025: Pass Rate -> 100.0% Total # of Locations Passed -> 282 Total # of Locations Failed -> 0 Total # of Locations Audited -> 282 QA System Inspection Distribution Pass Rate: Total # of Locations Passed / Total # of Locations Audited Year to Date (01/01/2025 – 09/30/2025): Pass Rate -> 99.81% Total # of Locations Passed -> 1541 Total # of Locations Failed -> 3 Total # of Locations Audited -> 1544 07/01/2025 – 09/30/2025: Pass Rate -> 99.78% Total # of Locations Passed -> 452 Total # of Locations Failed -> 1 Total # of Locations Audited -> 453 | 2025 | 3 | 100% | 99.91% | 99.91% | [5 empty] | In Progress
1010000024 | PG&E | 2025-11-03 | Program |  |  | HFTD/HFRA Open Tag Reduction – Distribution Backlog | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2025. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 92,000 EC notifications. Of these EC notifications, we expect to close out 63,747 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 77 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 3-year period (2023 to 2025), from 151.1 risk units—as of January 1, 2023—by 116.3 risk units (77 percent). | This initiative is focused on closing out open E maintenance tags for distribution facilities in HFTD and HFRA areas. | Grid Design, Operations and Maintenance | HFTD/HFRA Open Tag Reduction – Distribution Backlog |  | 8.1.1.2 | GM-03 | PG&E_Grid Design, Operations and Maintenance_HFTD/HFRA Open Tag Reduction – Distribution Backlog_GM-03_2025 | 538 | Equipment ignition likelihood | No | Percent Risk Reduction | As of Q3 2025, the following items remain on track: (1) 86.09% backlog ignition risk reduction, exceeding the interim target of 76.97%. (2) 98,904 HFTD/HFRA units closed, exceeding the interim target of 79,321 HFTD/HFRA unit closures. However, the backlog volume component of this work is delayed with 47,457 distribution backlog ignition risk units closed, short of the Q3 YTD target of 48,546 distribution backlog ignition risk, leaving a gap to target of 1,089 units. we have implemented a corrective action plan, and this commitment is still on track to be completed by end of year. Given that this is an annual target, with no quarterly targets, and that we anticipate that it will be completed by the end of the year, we are marking this initiative as 'In Progress'. | 2025 | 3 | 76.64% | 81.21% | 86.09% | [5 empty] | In Progress
1010000025 | PG&E | 2025-11-03 | Program |  |  | EPSS – Down Conductor Detection (DCD) | Make capable for DCD 250 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | This initiative will make capable for Down Conductor Detection (DCD) protective device controllers or relays to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | EPSS – Down Conductor Detection (DCD) |  | 8.1.1.2 | GM-06 | PG&E_Grid Design, Operations and Maintenance_EPSS – Down Conductor Detection (DCD)_GM-06_2025 | 461 | Equipment ignition likelihood | No | Protective Device Controllers or Relays that are DCD capable |  | 2025 | 3 | 97 | 256 | 404 | [5 empty] | Completed
1010000026 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2026-02-15 | Updates on EPSS Reliability Study | Provide annually an updated Enhanced Powerline Safety Settings (EPSS) reliability impact study per ACI PG&E-22-32 | This initiative provides updates on the EPSS reliability study. | Grid Design, Operations and Maintenance | Updates on EPSS Reliability Study |  | 8.1.1.1 | GM-07 | PG&E_Grid Design, Operations and Maintenance_Updates on EPSS Reliability Study_GM-07_2025 | 568 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | This commitment was completed in Q1 of 2025. The report was Completed and submitted to Energy Safety and the CPUC. | This commitment was completed in Q1 of 2025. | This commitment was completed in Q1 of 2025. |  | Completed
1010000027 | PG&E | 2025-11-03 | Program |  |  | Asset Inspection – Quality Control | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD/HFRA: 17,450 audit locations*; 95% pass rate System Inspection Distribution – HFTD/HFRA: 170,000 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative will perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program, to gain insight to improve asset inspection work on the field. | Grid Design, Operations and Maintenance | Asset Inspection – Quality Control |  | 8.1.1.2 | GM-09 | PG&E_Grid Design, Operations and Maintenance_Asset Inspection – Quality Control_GM-09_2025 | 531 | Equipment ignition likelihood | No | Pass Rate | QC System Inspection Transmission Pass Rate: Total # of Locations Passed / Total # of Locations Audited Year to Date (01/01/2025 – 09/30/2025): Pass Rate -> 99.99% Total # of Locations Passed -> 19840 Total # of Locations Failed -> 2 Total # of Locations Audited -> 19842 07/01/2025 – 09/30/2025: Pass Rate -> N/A Total # of Locations Passed -> 0 Total # of Locations Failed -> 0 Total # of Locations Audited -> 0 QC System Inspection Distribution Pass Rate: Total # of Locations Passed / Total # of Locations Audited Year to Date (01/01/2025 – 09/30/2025): Pass Rate -> 99.91% Total # of Locations Passed -> 142773 Total # of Locations Failed -> 132 Total # of Locations Audited -> 142905 07/01/2025 – 09/30/2025: Pass Rate -> 99.92% Total # of Locations Passed -> 63859 Total # of Locations Failed -> 50 Total # of Locations Audited -> 63909 | 2025 | 3 | 99.97% | 99.95% | 99.95% | [5 empty] | In Progress
1010000028 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Evaluate enhancements for the PSPS Transmission guidance | Evaluate enhancements for the PSPS Transmission guidance to enhance focus of PSPS events. | This initiative will evaluate the PSPS Transmission guidance to enhance focus of PSPS events. | Public Safety Power Shutoff | Evaluate enhancements for the PSPS Transmission guidance |  | 9.1.3 | PS-01 | PG&E_Public Safety Power Shutoff_Evaluate enhancements for the PSPS Transmission guidance_PS-01_2025 | 915 | PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | This program is on track with the evaluation phase planned to begin in Q2. | This program is on track and expected to start the evaluation phase in mid-July | This objective is completed. The evaluation of the changes to the PSPS input models has been accomplished and was approved by the Wildfire Risk Governance Steering Committee. |  | Completed
1010000029 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance to enhance focus of PSPS events. | This initiative will evaluate the incorporation of IPW enhancements into the PSPS Distribution guidance to enhance focus of PSPS events. | Public Safety Power Shutoff | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance |  | 9.1.3 | PS-02 | PG&E_Public Safety Power Shutoff_Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance_PS-02_2025 | 915 | PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | This program is on track with the evaluation phase planned to begin in Q2. | This objective is on track. Models assessment has been completed and will be presenting out to the WRSGC in Q3 for approval. | This objective has been completed. The evaluation of the changes to the PSPS input models has been accomplished and was approved by the Wildfire Risk Governance Steering Committee. |  | Completed
1010000030 | PG&E | 2025-11-03 | Program |  |  | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | Provide 3,300 cumulative new or replacement portable batteries to PG&E customers | This initiative will provide new or replacement portable batteries to PG&E customers to assist them during emergency events, including wildfires. | Public Safety Power Shutoff | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations |  | 9.1.4 | PS-06 | PG&E_Public Safety Power Shutoff_Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations_PS-06_2025 | 915 | PSPS likelihood | No | # of batteries | Please note that the Q2 value has changed from 1,953 to 1,964. Our 2025 target for PS-06 is to provide 3,300 new or replacement portable batteries to PG&E customers. Our estimate for portable batteries is 2,000 with a gap to target of 1,300. PG&E plans to fill this gap by distributing 1,300 permanent batteries to reach the WMP target of 3,300. This change was not eligible as determined in Energy Safety’s Decision on PG&E’s 2024 Change Order request. | 2025 | 3 | 368 | 1964 | 3469 | [5 empty] | Completed
1010000031 | PG&E | 2025-11-03 | Program |  |  | Reduce PSPS impacts by ~38k customer events (2.4%) (j) for 2023-2025 period by completing planned Wildfire mitigation projects including, but not limited to, MSO switch replacements and undergrounding | 13,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2025. | This initiative will focus on the reduction of customer events based on Wildfire mitigation projects and help improve PG&E's response to wildfires. | Public Safety Power Shutoff | Reduce PSPS impacts by ~38k customer events (2.4%) (j) for 2023-2025 period by completing planned Wildfire mitigation projects including, but not limited to, MSO switch replacements and undergrounding |  | 9.1.4 | PS-07 | PG&E_Public Safety Power Shutoff_Reduce PSPS impacts by ~38k customer events (2.4%) (j) for 2023-2025 period by completing planned Wildfire mitigation projects including, but not limited to, MSO switch replacements and undergrounding_PS-07_2025 | 915 | PSPS likelihood | No | # of Customer events | Based on 152.98 miles UG completed | 2025 | 3 | 954 | 2217 | 6109 | [5 empty] | In Progress
1010000032 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Continue sharing PSPS lessons learned | Continue sharing PSPS lessons learned and best practices with CA IOUs through monthly meetings focused on PSPS. | This initiative will share PSPS lessons learned and best practices with CA IOUs to enhance focus of PSPS events. | Public Safety Power Shutoff | Continue sharing PSPS lessons learned |  | 9.1.3 | PS-10 | PG&E_Public Safety Power Shutoff_Continue sharing PSPS lessons learned_PS-10_2025 | 915 | PSPS likelihood | No |  |  | 2025 | 3 |  |  |  |  | This work is on track, Joint IOU notes are submitted to the CPUC within 14 days following each scheduled monthly meeting. | This work is on track, Joint IOU notes continue to be submitted to the CPUC within 14 days following each scheduled monthly meeting. | This work remains on track. Joint IOU notes continue to be submitted to the CPUC within 14 days following each scheduled monthly meeting. |  | In Progress
1010000033 | PG&E | 2025-11-03 | Program |  |  | Line Sensor – Installations | Install Line Sensor devices on 40 circuits. | This initiative will install line sensor devices on 40 circuits | Situational Awareness and Forecasting | Line Sensor – Installations |  | 8.3.1.2 | SA-02 | PG&E_Situational Awareness and Forecasting_Line Sensor – Installations_SA-02_2025 | 747 | Equipment ignition likelihood | No | Circuits |  | 2025 | 3 | 5 | 8 | 38 | [5 empty] | In Progress
1010000034 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Evaluate FPI and IPW Modeling enhancements | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in 2023. This involves testing new features and types of model configurations that could improve model skill. For example, one of the features that will be evaluated for IPW is covered conductor and EPSS on the system. If covered conductor, EPSS, or other model enhancements, do not improve model skill, it will not be deployed as a part of the model improvement. | This initiative will evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model to improve the overall model accuracy. | Situational Awareness and Forecasting | Evaluate FPI and IPW Modeling enhancements |  | 8.3.1.1 | SA-05 | PG&E_Situational Awareness and Forecasting_Evaluate FPI and IPW Modeling enhancements_SA-05_2025 | 781 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | This objective is on track. New FPI and OPW models were evaluated and built in 2023 into 2024 and approved for operations in 2024 by the wildfire governance steering committee. These models were operationalized on August 1, 2024 and are currently operational. | New FPI and OPW models were evaluated and built in 2023 into 2024 and approved for operations in 2024 by the wildfire governance steering committee. These models were operationalized on August 1, 2024 and are currently operational. This Objective is now complete | This objective was completed in Q2 of 2025. |  | Completed
1010000035 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Monitor and evaluate the Cameras AI system’s performance | In partnership with Digital Path (the AI vendor that works with us and other agencies on the broader camera network) monitor and evaluate the AI system’s performance. Explore additional features and inputs to further enhance the system. At present we do not know what these enhancements will be specifically, however we will look for opportunities to explore best practices and incorporate enhancements with the vendor. | This initiative will monitor and evaluate the AI system’s performance to enhance the overall functionality. | Situational Awareness and Forecasting | Monitor and evaluate the Cameras AI system’s performance |  | 8.3.1.1 | SA-07 | PG&E_Situational Awareness and Forecasting_Monitor and evaluate the Cameras AI system’s performance_SA-07_2025 | 745 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | This objective is currently on track. Our AI vendor has successfully provided metrics evaluating AI system performance over the first quarter. The vendor has also sufficiently shared additional AI system enhancements that were being explored and/or implemented. For example, the vendor recently deployed a full AI-driven fire propagation algorithm before the end of the quarter that provides better performance, risk analysis, and alert filtering for end users. | This objective remains on track. We successfully collected all required documentation from the vendor over the last quarter. The fire propagation model that was deployed earlier in the year has been fine-tuned by the vendor and they are now looking at adding additional features to it. | This objective remains on track. We have successfully collected all required documentation from the vendor over the last quarter. The vendor has also completed efforts to retrain their fire propagation model and released a second version. As part of these efforts, the vendor is also exploring their ability to move towards fully autonomous calibration within their model and projecting camera imagery onto terrain to assist with location accuracy. |  | In Progress
1010000036 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | EFD and DFA Reporting | Perform a feasibility study on the use of EFD/DFA technologies to successfully identify incipient failures as a supplement to field inspections. If feasible, complete a data driven proposal for integrating sensor findings into the inspection program. | This initiative will perform a feasibility study on the use of EFD/DFA technologies to successfully identify incipient failures as a supplement to field inspections. | Situational Awareness and Forecasting | EFD and DFA Reporting |  | 8.3.1.1 | SA-09 | PG&E_Situational Awareness and Forecasting_EFD and DFA Reporting_SA-09_2025 | 747 | Equipment ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | This initiative is on track. For DFA, 1 installation was completed in Q1 2025. We are on track for Q3 installations as planned in the WMP operating period targets. For EFD, we completed installations at 4 locations and are on track for operating period targets in Q4 2025. | This objective is on track. Completion of co-relation studies between sensor findings and overhead/aerial inspections was completed in Q2. | This initiative is on track. For DFA, nine installations were completed in Q3 2025. We are on track for Q4 2025 installations as planned in the WMP operating period targets. For EFD, we completed 134 installations for Q3 2025 and are on track for operating period targets in Q4 2025. |  | In Progress
1010000037 | PG&E | 2025-11-03 | Program |  |  | Distribution Fault Anticipation (DFA) - Installations | Install 15 Distribution Fault Anticipation (DFA) sensors on circuits. One sensor will be installed per circuit at the initiating substation. | This initiative will install Distribution Fault Anticipation (DFA) sensors on circuits to allow better detection and assistance in locating faults, abnormal power flow events, and categorization of events. | Situational Awareness and Forecasting | Distribution Fault Anticipation (DFA) - Installations |  | 8.3.1.2 | SA-10 | PG&E_Situational Awareness and Forecasting_Distribution Fault Anticipation (DFA) - Installations_SA-10_2025 | 747 | Equipment ignition likelihood | No | DFA Sensors |  | 2025 | 3 | 1 | 1 | 10 | [5 empty] | In Progress
1010000038 | PG&E | 2025-11-03 | Program |  |  | Early Fault Detection (EFD) - Installations | Install Early Fault Detection (EFD) sensors on 4 circuits. | This initiative will install Early Fault Detection (EFD) sensors on circuits to detect failing equipment early and detect vegetation encroachment. | Situational Awareness and Forecasting | Early Fault Detection (EFD) - Installations |  | 8.3.1.2 | SA-11 | PG&E_Situational Awareness and Forecasting_Early Fault Detection (EFD) - Installations_SA-11_2025 | 747 | Equipment ignition likelihood | No | EFD circuits |  | 2025 | 3 | 0 | 0 | 0 | [5 empty] | In Progress
1010000039 | PG&E | 2025-11-03 | Program |  |  | LiDAR Data Collection – Transmission | Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HFTD Transmission circuit miles. | This initiative includes the collection of LiDAR data for the Transmission System which informs inspection work that can reduce the potential for asset-caused ignitions and wildfires. | Vegetation Management and Inspection | LiDAR Data Collection – Transmission |  | 8.2.1.2 | VM-01 | PG&E_Vegetation Management and Inspection_LiDAR Data Collection – Transmission_VM-01_2025 | 663 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | Please note that Q1 value has changed from 9,744 to 9,745 and Q2 value has changed from 17,942 to 17,943 . | 2025 | 3 | 9745 | 17943 | 17950 | [5 empty] | Completed
1010000040 | PG&E | 2025-11-03 | Program |  |  | Pole Clearing Program | 2025 pole count to be adjusted by the ending pole population in the previous year (2024) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. | This initiative performs pole clearing inspections and mitigation work (where needed) for poles in HFTD and HFRA areas where clearance is not required by PRC Section 4292. Pole clearing can reduce the potential for a wildfire ignition. | Vegetation Management and Inspection | Pole Clearing Program |  | 8.2.1.2 | VM-02 | PG&E_Vegetation Management and Inspection_Pole Clearing Program_VM-02_2025 | 687 | Contact from vegetation ignition likelihood | Yes | Distribution poles | For this Commitment as of Q3 2025 we have completed pole clearing on 81,255 poles. This count includes constrained units. We are working internally to obtain the accurate count of poles completed for this commitment. We will provide the final count in our Q4 2025 QDR and 2025 ARC. | 2025 | 3 | 57666 | 81220 | 81255 | [5 empty] | Completed
1010000041 | PG&E | 2025-11-03 | Program |  |  | Focused Tree Inspection (FTI) | Within Areas of Concern (AOC) locations complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. | This initiative will identify the Areas of Concern (AOC) and implement guidelines to reduce the risk associated with vegetation contact that could cause a potential ignition. | Vegetation Management and Inspection | Focused Tree Inspection (FTI) |  | 8.2.1.2 | VM-03 | PG&E_Vegetation Management and Inspection_Focused Tree Inspection (FTI)_VM-03_2025 | 681 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | Please note that Q1 value has changed from 529.89 to 525.74 and Q2 value has changed from 1,241.28 to 1,229.96. | 2025 | 3 | 525.74 | 1229.96 | 1539.71 | [5 empty] | Completed
1010000042 | PG&E | 2025-11-03 | Program |  |  | Tree Removal Inventory (TRI) | Mitigate 25,000 trees identified from the legacy EVM program. | This initiative will remove trees identified from the legacy EVM program to reduce the risk associated with vegetation contact causing a potential ignition. | Vegetation Management and Inspection | Tree Removal Inventory (TRI) |  | 8.2.1.2 | VM-04 | PG&E_Vegetation Management and Inspection_Tree Removal Inventory (TRI)_VM-04_2025 | 680 | Contact from vegetation ignition likelihood | Yes | Trees | Please note that Q1 value has changed from 7,927 to 7,785 and Q2 value has changed from 18,179 to 18,118 . | 2025 | 3 | 7785 | 18118 | 28502 | [5 empty] | Completed
1010000043 | PG&E | 2025-11-03 | Program |  |  | Defensible Space Inspections – Distribution Substation | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around distribution substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | Defensible Space Inspections – Distribution Substation |  | 8.2.1.2 | VM-05 | PG&E_Vegetation Management and Inspection_Defensible Space Inspections – Distribution Substation_VM-05_2025 | 683 | Wildfire exposure potential | Yes | Distribution poles | We completed inspections at 130 substations compared to the WMP target of 131. The gap to target of one is due to the decommissioning of the North Branch substation. 100% of the scope for this commitment has been achieved, thus, we are marking this initiative as complete. We will provide the decommissioning documentation during the compliance process | 2025 | 3 | 76 | 130 | 130 | [5 empty] | Completed
1010000044 | PG&E | 2025-11-03 | Program |  |  | Defensible Space Inspections – Transmission Substation | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around transmission substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | Defensible Space Inspections – Transmission Substation |  | 8.2.1.2 | VM-06 | PG&E_Vegetation Management and Inspection_Defensible Space Inspections – Transmission Substation_VM-06_2025 | 683 | Wildfire exposure potential | Yes | Transmission Substations |  | 2025 | 3 | 23 | 55 | 55 | [5 empty] | Completed
1010000045 | PG&E | 2025-11-03 | Program |  |  | Defensible Space Inspections – Hydroelectric Substations and Powerhouses | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around hydroelectric substations and powerhouses to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | Defensible Space Inspections – Hydroelectric Substations and Powerhouses |  | 8.2.1.2 | VM-07 | PG&E_Vegetation Management and Inspection_Defensible Space Inspections – Hydroelectric Substations and Powerhouses_VM-07_2025 | 683 | Wildfire exposure potential | Yes | Hydroelectric Substations and Powerhouses | We completed inspections at 58 substations compared to the WMP target of 61. The gap to target is the result of the transfer in ownership of three substations. 100% of the scope for this commitment has been achieved, thus, we are marking this initiative as complete. We will provide the transfer documentation during the compliance process. | 2025 | 3 | 43 | 58 | 58 | [5 empty] | Completed
1010000046 | PG&E | 2025-11-03 | Program |  |  | Vegetation Management – Quality Assurance | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,862 audit locations*; 95% pass rate Transmission VM – HFTD: 1,374 audit locations*; 95% pass rate Vegetation Control Pole Clearing – HFTD: 2,061 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative performs Quality Assurance and Quality Verification audits and reviews of various aspects of our Vegetation Management program to identify gaps and areas of improvement. | Vegetation Management and Inspection | Vegetation Management – Quality Assurance |  | 8.2.1.2 | VM-08 | PG&E_Vegetation Management and Inspection_Vegetation Management – Quality Assurance_VM-08_2025 | 701 | Contact from vegetation ignition likelihood | No | Pass Rate | QA Vegetation Management Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 99.91% Location Inspected - 1476 Total # of Audit Trees Inspected - 6,741 Total # of Audit Trees Passed - 6,735 Total # of Audit Trees Failed - 6 YTD: Pass Rate -> 99.92% Location Inspected - 4101 Total # of Audit Trees Inspected - 19,777 Total # of Audit Trees Passed - 19,762 Total # of Audit Trees Failed - 15 QA Vegetation Management Transmission Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 100.00% Location Inspected - 150 Total # of Audit Trees Inspected - 450 Total # of Audit Trees Passed - 450 Total # of Audit Trees Failed - 0 YTD: Pass Rate -> 99.99% Location Inspected - 2042 Total # of Audit Trees Inspected - 6,816 Total # of Audit Trees Passed - 6,815 Total # of Audit Trees Failed - 1 QA VC Pole Clearing Pass Rate: Total # of Poles Passed / Total # of Poles Audited Quarter 3: Pass Rate -> 100.00% Total # of Poles Inspected - 937 Total # of Poles Passed - 937 Total # of Poles Failed - 0 YTD: Pass Rate -> 100.00% Total # of Poles Inspected - 2,647 Total # of Poles Passed - 2,647 Total # of Poles Failed - 0 | 2025 | 3 | 100% | 99.97% | 99.97% | [5 empty] | Completed
1010000047 | PG&E | 2025-11-03 | Project | 2025-01-01 | 2025-12-31 | Constraint Resolution Procedural Guideline | Develop a process of centralizing constraints resolution. As part of the build out of the centralized constraints team, three major categories will be addressed: customer constraints, environmental constraints (including internal PG&E procedures required to perform work) and permitting constraints (including both Land and Environmental permits). | This initiative will develop a process of centralizing constraints resolution with the intent to reduce the overall number of constrains. | Vegetation Management and Inspection | Constraint Resolution Procedural Guideline |  | 8.2.1.1 | VM-09 | PG&E_Vegetation Management and Inspection_Constraint Resolution Procedural Guideline_VM-09_2025 | 713 | Contact from vegetation ignition likelihood | No |  |  | 2025 | 3 |  |  |  |  | This Objective is on track. We have produced documentation of Constraint Thresholds by constraint type. Documentation is added to VM-09 record of evidence tracking and is available in Constraints Management reporting. We also met with stakeholder group to discuss constraint thresholds and get input on any gaps to meet the commitment. Midstream validation for the objective is set to take place in Q2. | This Objective remains on track. Procedures have been created/updated and published in support of three major constraints categories (Customer, Environmental, Permitting). Additionally, internal targets have been established for each constraint type and PowerBI reporting enables tracking. Lastly, VM re-launched our Right Tree, Right Place program in 2024 and have continued it into 2025. Midstream validation for the objective was completed in Q2. We are on track to complete this objective by the end of the year | This objective remains on track. We are actively working with the appropriate internal partners to close this objective by the end of year, as planned. |  | In Progress
1010000048 | PG&E | 2025-11-03 | Program |  |  | Routine Ground -Transmission | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | Routine Ground -Transmission |  | 8.2.1.2 | VM-13 | PG&E_Vegetation Management and Inspection_Routine Ground -Transmission_VM-13_2025 | 663 | Contact from vegetation ignition likelihood | Yes | Circuit Miles |  | 2025 | 3 | 8471 | 16287 | 17797 | [5 empty] | In Progress
1010000049 | PG&E | 2025-11-03 | Program |  |  | Second Patrol – Transmission | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | Second Patrol – Transmission |  | 8.2.1.2 | VM-14 | PG&E_Vegetation Management and Inspection_Second Patrol – Transmission_VM-14_2025 | 666 | Contact from vegetation ignition likelihood | Yes | Circuit Miles |  | 2025 | 3 | 0 | 0 | 5898 | [5 empty] | Completed
1010000050 | PG&E | 2025-11-03 | Program |  |  | Integrated Vegetation Management – Transmission | Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work | Vegetation Management and Inspection | Integrated Vegetation Management – Transmission |  | 8.2.1.2 | VM-15 | PG&E_Vegetation Management and Inspection_Integrated Vegetation Management – Transmission_VM-15_2025 | 668 | Contact from vegetation ignition likelihood | Yes | Acres | Please note that Q1 value has changed from 1,410 to 1,448 and Q2 value has changed from 2,837 to 2,838. | 2025 | 3 | 1448 | 2838 | 6660 | [5 empty] | Completed
1010000051 | PG&E | 2025-11-03 | Program |  |  | Routine Patrol – Distribution | Complete Distribution Routine Annual Patrol Inspection of 78,200 overhead circuit miles system wide | This initiative will identify vegetation contact that could cause a potential ignition around Distribution equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | Routine Patrol – Distribution |  | 8.2.1.2 | VM-16 | PG&E_Vegetation Management and Inspection_Routine Patrol – Distribution_VM-16_2025 | 672 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | Please note that Q1 value has changed from 24,480.21 to 22,810.86 and Q2 value has changed from 48,543.06 to 47,890.89. | 2025 | 3 | 22810.859 | 47890.889 | 68018.17 | [5 empty] | In Progress
1010000052 | PG&E | 2025-11-03 | Program |  |  | Second Patrol – Distribution | Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. | This initiative will identify vegetation contact that could cause a potential ignition around Distribution equipment and aid in prescribing any needed vegetation mitigation work | Vegetation Management and Inspection | Second Patrol – Distribution |  | 8.2.1.2 | VM-17 | PG&E_Vegetation Management and Inspection_Second Patrol – Distribution_VM-17_2025 | 675 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | Please note that Q1 value has changed from 7,509.53 to 6,919.9 and Q2 value has changed from 12,925.59 to 12,873.77. | 2025 | 3 | 6919.9 | 12873.77 | 20444.62 | [5 empty] | In Progress
1010000053 | PG&E | 2025-11-03 | Program |  |  | VM for Operational Mitigations (VMOM) | Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year’s carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year’s EPSS outage data analysis. | This initiative will mitigate trees under the VM for Operational Mitigations program, on EPSS capable circuits. | Vegetation Management and Inspection | VM for Operational Mitigations (VMOM) |  | 8.2.1.2 | VM-18 | PG&E_Vegetation Management and Inspection_VM for Operational Mitigations (VMOM)_VM-18_2025 | 678 | Contact from vegetation ignition likelihood | Yes | Trees |  | 2025 | 3 | 2649 | 5720 | 7866 | [5 empty] | Completed
1010000054 | PG&E | 2025-11-03 | Program |  |  | Vegetation Management - Quality Control | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM –HFTD: 85,000 audit locations*; 95% pass rate Transmission VM – HFTD: 14,500 audit locations*; 95% pass rate Vegetation Control Pole Clearing – HFTD: 12,500 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative performs Quality Control and Quality Verification audits and reviews of various aspects of our Vegetation Management program to identify gaps and areas of improvement. | Vegetation Management and Inspection | Vegetation Management - Quality Control |  | 8.2.1.2 | VM-22 | PG&E_Vegetation Management and Inspection_Vegetation Management - Quality Control_VM-22_2025 | 706 | Contact from vegetation ignition likelihood | No | Pass Rate | QC Vegetation Management Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 98.95% Spans Inspected – 30,753 Total # of Audit Trees Inspected – 186,420 Total # of Audit Trees Passed – 184,458 Total # of Audit Trees Failed – 1,962 YTD (01/01/25 – 09/30/2025): Pass Rate -> 99.27% Spans Audited -> 82,309 Total Trees Audited -> 452,341 Total # of Trees Passed -> 449,060 Total # of Trees Failed -> 3,281 QC Vegetation Management Transmission Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 99.79% Location Inspected – 4,077 Total # of Audit Trees Inspected – 12,510 Total # of Audit Trees Passed – 12,484 Total # of Audit Trees Failed – 26 YTD (01/01/25 - 09/30/2025): Pass Rate -> 99.79% Location Inspected – 14,510 Total # of Audit Trees Inspected – 41,129 Total # of Audit Trees Passed – 41,041 Total # of Audit Trees Failed – 88 QC Pole Clearing Pass Rate: Total # of Poles Passed / Total # of Poles Audited Quarter 3: Pass Rate – 99.69% Total # of Poles Audited – 5,497 Total # of Poles Passed – 5,480 Total # of Poles Failed – 17 YTD (01/01/25 - 09/30/2025): Pass Rate – 99.45% Total # of Poles Audited – 13,312 Total # of Poles Passed – 13,239 Total # of Poles Failed – 73 | 2025 | 3 | 99.58% | 99.52% | 99.5% | [5 empty] | In Progress
Note on D2: Author: Select cells for dropdown list.
Note on D11: Author: Select cells for dropdown list.
Note on D12: Author: Select cells for dropdown list.
Note on D14: Author: Select cells for dropdown list.
Note on D15: Author: Select cells for dropdown list.
Note on D16: Author: Select cells for dropdown list.
Note on D19: Author: Select cells for dropdown list.
Note on D28: Author: Select cells for dropdown list.
Note on D30: Author: Select cells for dropdown list.
Note on D31: Author: Select cells for dropdown list.
Note on D34: Author: Select cells for dropdown list.
Note on D36: Author: Select cells for dropdown list.
Note on D38: Author: Select cells for dropdown list.
Note on D49: Author: Select cells for dropdown list.

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 5
1020000001 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000002 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000003 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 1556
1020000004 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 1
1020000005 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000006 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000007 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 671
1020000008 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 3
1020000009 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000010 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000011 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 8086
1020000012 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 1
1020000013 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000014 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000015 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 70
1020000016 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000017 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000018 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000019 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 33
1020000020 | 1. Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000021 | 1. Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000022 | 1. Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000023 | 1. Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 463
1020000024 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 4
1020000025 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000026 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000027 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 1482
1020000028 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 1
1020000029 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000030 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000031 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 623
1020000032 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 3
1020000033 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000034 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000035 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 7836
1020000036 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 1
1020000037 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000038 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000039 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 74
1020000040 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000041 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000042 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000043 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 48
1020000044 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000045 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000046 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000047 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 250
1020000048 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 4
1020000049 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000050 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000051 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 543
1020000052 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 1
1020000053 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000054 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000055 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 183
1020000056 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 1
1020000057 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000058 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1020000059 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2025 | 3 | 752
1020000060 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | PG&E | 2025 | 3 | 88.8333
1020000061 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | PG&E | 2025 | 3 | 385.2083
1020000062 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | PG&E | 2025 | 3 | 84.9167
1020000063 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | PG&E | 2025 | 3 | 363.9583
1020000064 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | PG&E | 2025 | 3 | 116.2917
1020000065 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | PG&E | 2025 | 3 | 357.75
1020000066 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2025 | 3 | 105.5833
1020000067 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2025 | 3 | 396.4604
1020000068 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2025 | 3 | 151.5417
1020000069 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2025 | 3 | 449.8229
1020000070 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2025 | 3 | 89.4583
1020000071 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2025 | 3 | 384.3333
1020000072 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 0
1020000073 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1
1020000074 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 0
1020000075 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1
1020000076 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 0
1020000077 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1
1020000078 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1
1020000079 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 7
1020000080 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 7.5
1020000081 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 8
1020000082 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1
1020000083 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 6
1020000084 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 829
1020000085 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 2316
1020000086 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1164
1020000087 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 2315
1020000088 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 182
1020000089 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1936
1020000090 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 341.5
1020000091 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 874
1020000092 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 150
1020000093 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 846
1020000094 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1034
1020000095 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1835
1020000096 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1170
1020000097 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 3055
1020000098 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1500
1020000099 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 2981
1020000100 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 3590
1020000101 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 3655
1020000102 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 496
1020000103 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1188
1020000104 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 491
1020000105 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1508
1020000106 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 643
1020000107 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2025 | 3 | 1857
1020000108 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders | Data is in total number of trees.​ This data includes Legacy (Distribution and Transmission) and One VM data. |  | PG&E | 2025 | 3 | 96353
1020000109 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders | Data is in total number of trees and is based off P1/P2 and Second Patrol numbers. These numbers do not include constrained trees. |  | PG&E | 2025 | 3 | 5
1020000110 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | PG&E | 2025 | 3 | 934907
1020000111 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | PG&E | 2025 | 3 | 624883
1020000112 | 8. Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  | For metric 8, data for crew response time to a locked circuit breaker incident is only readily available for instances involving hazard conditions such as 911 or wire down calls. PG&E will continue to review the available information in its outage systems to provide this information in a future filing, although we anticipate creating a system to capture this data could take many months. Currently, any quarterly data would reflect only 911 and wire down events and is not a good representation of our overall response time. | PG&E | 2025 | 3
1020000113 | 9. Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000114 | 9. Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000115 | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | PG&E | 2025 | 3 | 0
1020000116 | 11. Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000117 | 11. Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000118 | 12. Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 439.85
1020000119 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000120 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000121 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000122 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 1
1020000123 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000124 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000125 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000126 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000127 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000128 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000129 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 0
1020000130 | 13. Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2025 | 3 | 7
1020000131 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000132 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000133 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000134 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 86263
1020000135 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000136 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial". |  | PG&E | 2025 | 3 | 45584
1020000137 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000138 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2025 | 3 | 170
1020000139 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000140 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000141 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000142 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000143 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000144 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000145 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000146 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 3234.8625
1020000147 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000148 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 1709.4
1020000149 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000150 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2025 | 3 | 6.375
1020000151 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000152 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000153 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000154 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000155 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000156 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000157 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000158 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 8
1020000159 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000160 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 123
1020000161 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000162 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 13
1020000163 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000164 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000165 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000166 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 658
1020000167 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000168 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000169 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000170 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 32
1020000171 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000172 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 7076
1020000173 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000174 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 68
1020000175 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000176 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000177 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000178 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 2014
1020000179 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000180 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000181 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000182 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000183 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000184 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 27
1020000185 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000186 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 3
1020000187 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000188 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000189 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000190 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 84
1020000191 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000192 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000193 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000194 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 45244
1020000195 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000196 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial". |  | PG&E | 2025 | 3 | 48109
1020000197 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000198 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. Detailed ground inspections in HFTD Tier 3. |  | PG&E | 2025 | 3 | 78
1020000199 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000200 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000201 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000202 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000203 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000204 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000205 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000206 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 1696.65
1020000207 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000208 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 1804.0875
1020000209 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000210 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2025 | 3 | 2.925
1020000211 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000212 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000213 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000214 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000215 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000216 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000217 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000218 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1
1020000219 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000220 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 132
1020000221 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000222 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 5
1020000223 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000224 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000225 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000226 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 312
1020000227 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000228 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000229 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000230 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 21
1020000231 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000232 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 7887
1020000233 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000234 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 43
1020000235 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000236 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000237 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000238 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1511
1020000239 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000240 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000241 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000242 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000243 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000244 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 52
1020000245 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000246 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 7
1020000247 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000248 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000249 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000250 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 44
1020000251 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000252 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000253 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000254 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 325096
1020000255 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000256 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial". |  | PG&E | 2025 | 3 | 23
1020000257 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000258 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2025 | 3 | 94674
1020000259 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000260 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000261 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000262 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000263 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000264 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000265 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000266 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 12191.1
1020000267 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000268 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 0.8625
1020000269 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000270 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 3550.275
1020000271 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000272 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000273 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000274 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000275 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000276 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000277 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000278 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 117
1020000279 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000280 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 10
1020000281 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000282 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 619
1020000283 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000284 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000285 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000286 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 3661
1020000287 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000288 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000289 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000290 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 174
1020000291 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000292 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 209
1020000293 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000294 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 9991
1020000295 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000296 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000297 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000298 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 3649
1020000299 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000300 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000301 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000302 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1
1020000303 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000304 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000305 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000306 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 2411
1020000307 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000308 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000309 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000310 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 365
1020000311 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000312 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000313 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000314 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 2438
1020000315 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000316 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 707
1020000317 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000318 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 211
1020000319 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000320 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000321 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000322 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000323 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000324 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000325 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000326 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 91.425
1020000327 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000328 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 26.5125
1020000329 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000330 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 7.9125
1020000331 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000332 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000333 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000334 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000335 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000336 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 8
1020000337 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000338 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 17
1020000339 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000340 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1
1020000341 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000342 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1
1020000343 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000344 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000345 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000346 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 21
1020000347 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000348 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 2
1020000349 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000350 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 12
1020000351 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000352 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 93
1020000353 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000354 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 12
1020000355 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000356 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000357 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000358 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 78
1020000359 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000360 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000361 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000362 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000363 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000364 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 100
1020000365 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000366 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 9
1020000367 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000368 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000369 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000370 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 13
1020000371 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000372 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000373 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000374 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 2612
1020000375 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000376 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 244
1020000377 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000378 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 174
1020000379 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000380 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000381 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000382 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000383 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000384 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000385 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000386 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 97.95
1020000387 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000388 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 9.15
1020000389 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000390 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 6.525
1020000391 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000392 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000393 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000394 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000395 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000396 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000397 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000398 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1
1020000399 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000400 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000401 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000402 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000403 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000404 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000405 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000406 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1
1020000407 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000408 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000409 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000410 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 5
1020000411 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000412 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 25
1020000413 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000414 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 3
1020000415 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000416 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000417 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000418 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 9
1020000419 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000420 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000421 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000422 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 0
1020000423 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000424 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 17
1020000425 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000426 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 6
1020000427 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000428 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000429 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000430 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 9
1020000431 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000432 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000433 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000434 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 14310
1020000435 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000436 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 8760
1020000437 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000438 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2025 | 3 | 6355
1020000439 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000440 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000441 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000442 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000443 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000444 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000445 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000446 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 536.625
1020000447 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000448 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 328.5
1020000449 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000450 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2025 | 3 | 238.3125
1020000451 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000452 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000453 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000454 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000455 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000456 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 9
1020000457 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000458 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 65
1020000459 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000460 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 16
1020000461 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000462 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 10
1020000463 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000464 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000465 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000466 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 33
1020000467 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000468 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 7
1020000469 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000470 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 34
1020000471 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000472 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1456
1020000473 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000474 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 359
1020000475 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000476 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000477 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000478 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 141
1020000479 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000480 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1
1020000481 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000482 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 4
1020000483 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000484 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 1272
1020000485 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000486 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 335
1020000487 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000488 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000489 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000490 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2025 | 3 | 101
1020000491 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000492 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000493 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000494 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 8
1020000495 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000496 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 123
1020000497 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000498 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 14
1020000499 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000500 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000501 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000502 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 636
1020000503 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000504 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000505 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000506 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 43
1020000507 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000508 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2549
1020000509 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000510 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 13093
1020000511 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000512 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000513 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000514 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 6710
1020000515 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000516 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000517 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000518 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 5
1020000519 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000520 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 70
1020000521 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000522 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2739
1020000523 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000524 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000525 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000526 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 921
1020000527 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000528 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000529 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000530 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1
1020000531 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000532 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 128
1020000533 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000534 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 5
1020000535 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000536 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000537 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000538 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 308
1020000539 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000540 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000541 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000542 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 23
1020000543 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000544 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1879
1020000545 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000546 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 4359
1020000547 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000548 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000549 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000550 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2472
1020000551 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000552 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000553 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000554 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2
1020000555 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000556 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 37
1020000557 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000558 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1562
1020000559 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000560 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000561 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000562 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 452
1020000563 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000564 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000565 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000566 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 118
1020000567 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000568 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 10
1020000569 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000570 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 607
1020000571 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000572 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000573 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000574 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 3612
1020000575 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000576 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000577 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000578 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 176
1020000579 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000580 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 122
1020000581 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000582 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 6106
1020000583 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000584 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000585 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000586 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 3464
1020000587 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000588 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000589 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000590 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2
1020000591 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000592 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 3
1020000593 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000594 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1976
1020000595 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000596 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000597 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2025 | 3
1020000598 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1107
1020000599 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000600 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 8
1020000601 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000602 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 16
1020000603 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000604 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1
1020000605 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000606 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1
1020000607 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000608 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000609 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000610 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 17
1020000611 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000612 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2
1020000613 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000614 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 9
1020000615 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000616 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 759
1020000617 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000618 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 457
1020000619 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000620 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000621 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000622 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 255
1020000623 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000624 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 4
1020000625 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000626 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 0
1020000627 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000628 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 776
1020000629 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000630 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 402
1020000631 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000632 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000633 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000634 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 178
1020000635 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000636 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 0
1020000637 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000638 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1
1020000639 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000640 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 0
1020000641 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000642 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 0
1020000643 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000644 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000645 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000646 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2
1020000647 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000648 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 4
1020000649 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000650 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2
1020000651 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000652 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 298
1020000653 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000654 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 100
1020000655 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000656 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000657 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000658 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 59
1020000659 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000660 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 0
1020000661 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000662 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2
1020000663 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000664 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 275
1020000665 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000666 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 102
1020000667 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000668 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000669 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000670 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 42
1020000671 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000672 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 9
1020000673 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000674 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 61
1020000675 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000676 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 15
1020000677 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000678 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 8
1020000679 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000680 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000681 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000682 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 31
1020000683 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000684 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 55
1020000685 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000686 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 43
1020000687 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000688 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 2060
1020000689 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000690 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 1187
1020000691 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000692 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000693 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000694 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 443
1020000695 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000696 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 6
1020000697 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000698 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 16
1020000699 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000700 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 839
1020000701 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000702 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 447
1020000703 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000704 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000705 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2025 | 3
1020000706 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2025 | 3 | 274
1020000707 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000708 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000709 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 0
1020000710 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 101293
1020000711 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000712 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | PG&E | 2025 | 3 | 8
1020000713 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000714 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 23162
1020000715 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000716 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3 | 0
1020000717 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000718 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 3835
1020000719 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000720 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000721 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 0
1020000722 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 6667
1020000723 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000724 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000725 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 0
1020000726 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 57946
1020000727 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000728 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | PG&E | 2025 | 3 | 0
1020000729 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000730 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 19090
1020000731 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000732 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3 | 0
1020000733 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000734 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 3561
1020000735 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000736 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000737 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 0
1020000738 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 6452
1020000739 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000740 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000741 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 0
1020000742 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 179705
1020000743 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000744 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | PG&E | 2025 | 3 | 0
1020000745 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000746 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 2314
1020000747 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000748 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3 | 0
1020000749 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000750 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 703
1020000751 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000752 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000753 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 0
1020000754 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 18222
1020000755 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000756 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000757 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2025 | 3 | 2832
1020000758 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 3347
1020000759 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000760 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000761 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000762 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000763 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000764 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000765 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000766 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000767 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000768 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000769 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2025 | 3 | 0
1020000770 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 0
1020000771 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000772 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000773 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2025 | 3 | 544
1020000774 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 1460
1020000775 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000776 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000777 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000778 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000779 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000780 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000781 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000782 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000783 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000784 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000785 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2025 | 3 | 0
1020000786 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 0
1020000787 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000788 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000789 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2025 | 3 | 4431
1020000790 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2025 | 3 | 6040
1020000791 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000792 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000793 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000794 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000795 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000796 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000797 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000798 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000799 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000800 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2025 | 3
1020000801 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2025 | 3 | 0
1020000802 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2025 | 3 | 0
1020000803 | 17. Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | PG&E does not issue wildfire evacuation notices to customers and does not maintain metrics on the number of customers in an evacuation zone or the number of customers notified of evacuation orders. Because of this, PG&E is unable to report on evacuation related requirements in this table. PG&E anticipates this to be a recurring challenge going forward. | PG&E | 2025 | 3

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | Customer Hours of PSPS per RFW OH Circuit Mile Day |  |  |  |  | Customer hours per RFW OH circuit mile day in time period |  |  | PG&E | 2025 | 3 | 0

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 2873.4752
1040000001 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 970.7416
1040000002 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 2815.0018
1040000003 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 1424.1795
1040000004 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 258.8085
1040000005 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 604.6204
1040000006 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 0
1040000007 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 0
1040000008 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 0
1040000009 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 0
1040000010 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 0
1040000011 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 0
1040000012 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 2873.4752
1040000013 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 970.7416
1040000014 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 2815.0018
1040000015 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 1424.1795
1040000016 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 258.8085
1040000017 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2025 | 3 | 604.6204
1040000018 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2025 | 3 | 880213.104
1040000019 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2025 | 3 | 320572.2641
1040000020 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2025 | 3 | 190097.3879
1040000021 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2025 | 3 | 206988.5942
1040000022 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2025 | 3 | 61621.1988
1040000023 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2025 | 3 | 33308.5648

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 25
1050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 140
1050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 10
1050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 4
1050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 9
1050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 6
1050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 7
1050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 62
1050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 32
1050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 16
1050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 90
1050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 7
1050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 7
1050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 25
1050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 26
1050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 4
1050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 10
1050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 20
1050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 24
1050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 10
1050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 7
1050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 4
1050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 32
1050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 1
1050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 1
1050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 26
1050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 7
1050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 8
1050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 6
1050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 1
1050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 591
1050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 102
1050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 33
1050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 16
1050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 7
1050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 92
1050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 428
1050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 44
1050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 17
1050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 26
1050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 27
1050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 7
1050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 12
1050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 6
1050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 49
1050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 14
1050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 261
1050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 79
1050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 59
1050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 13
1050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 12
1050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 600
1050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 73
1050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 41
1050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 4
1050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 118
1050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 6
1050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 8
1050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 301
1050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 39
1050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 31
1050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 211
1050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 14
1050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 59
1050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 19
1050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 11
1050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 9
1050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 5
1050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 19
1050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 6
1050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 572
1050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 186
1050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 84
1050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 5
1050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 24
1050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 4
1050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 7
1050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 3
1050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 148
1050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 15
1050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 8
1050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 65
1050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 4
1050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 19
1050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1082
1050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 182
1050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 115
1050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 2
1050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 17
1050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 172
1050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 25
1050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 13
1050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 8
1050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 10
1050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 5
1050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 50
1050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 1
1050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 393
1050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 129
1050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 39
1050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 73
1050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 36
1050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 3
1050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 9
1050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 0
1050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 3
1050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 2
1050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 0
1050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 2021
1050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 307
1050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 104
1050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 15
1050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 8
1050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 3
1050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | PG&E | 2025 | 3 | 448
1050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 194
1050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PG&E | 2025 | 3 | 67
1050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events | No |  |  | PG&E | 2025 | 3 | 15
1050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events | No |  |  | PG&E | 2025 | 3 | 11
1050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events | No |  |  | PG&E | 2025 | 3 | 3

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 20
1060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 5
1060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 17
1060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 3
1060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | No | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | No | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | No | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | No | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | No | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | No | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 21
1060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 10
1060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 15
1060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 15
1060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 3
1060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | Yes | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database. |  | PG&E | 2025 | 3 | 2
1060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | Yes | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database. |  | PG&E | 2025 | 3 | 0
1060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | Yes | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database. |  | PG&E | 2025 | 3 | 0
1060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | Yes | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database. |  | PG&E | 2025 | 3 | 0
1060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | Yes | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database. |  | PG&E | 2025 | 3 | 0
1060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | Yes | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database. |  | PG&E | 2025 | 3 | 0
1060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | Yes | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type 4. Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2025 | 3 | 2
1060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | Yes | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type 4. Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2025 | 3 | 2
1060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | Yes | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type 4. Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2025 | 3 | 0
1060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | Yes | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type 4. Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2025 | 3 | 0
1060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | Yes | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type 4. Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2025 | 3 | 0
1060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | Yes | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type 4. Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2025 | 3 | 0
1060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | No | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | No | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | No | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | No | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | No | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | No | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: 2. Contact from object, Ignition Driver: Other (contact from object) or Metric Type: 10. Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2025 | 3 | 0
1060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 9
1060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 1
1060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 6
1060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | No |  |  | PG&E | 2025 | 3 | 0
1060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 6
1060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 8
1060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 3
1060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 2
1060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 3
1060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0
1060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PG&E | 2025 | 3 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 4628.9
1070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 9506.821
1070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 6961.456
1070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 28498.68
1070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 421.9803
1070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 5213.388
1070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 684.7565
1070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 114.9884
1070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 8425.172
1070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 5336.361
1070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 818.919
1070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 2336.895
1070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 255.9076
1070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 34.1075
1070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 4055.28
1070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 1668.069
1070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 344.1593
1070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 344.2442
1070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 574.3062
1070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 1607.153
1070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 874.5088
1070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 7738.04
1070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 47.3163
1070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 1580.734
1070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 100.665
1070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 116.2213
1070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 852.8567
1070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 2046.137
1070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 67.2025
1070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 958.2312
1070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 35.002
1070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 23.1551
1070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 300.9932
1070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 753.0241
1070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 27.0564
1070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 137.1739
1070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 6521.42
1070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 12453.49
1070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 2911.681
1070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 3634.262
1070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 64.6159
1070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 169.0499
1070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 356.6961
1070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 54.9315
1070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 1301.581
1070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 543.1439
1070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 92.387
1070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 216.1897
1070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 116.871
1070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 7.2741
1070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 697.1354
1070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 216.3768
1070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 31.4641
1070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 47.8616
1070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 23.5289
1070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 100.4943
1070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 10.8744
1070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 36.3053
1070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 1.6534
1070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0.14894
1070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 1.1211
1070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 7.8692
1070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0.58353
1070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0.35051
1070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 12977
1070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 30338
1070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 6442
1070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 8392
1070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 227
1070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 669
1070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 982
1070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 178
1070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 3018
1070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 1426
1070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 315
1070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 422
1070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 362
1070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 50
1070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 1673
1070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 592
1070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 158
1070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2025 | 3 | 118
1070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 1244232
1070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 2611214
1070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 413139
1070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 326755
1070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 10263
1070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 13058
1070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 69766
1070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 3784
1070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 191436
1070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 32880
1070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 16465
1070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 10281
1070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 27392
1070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 1808
1070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 105075
1070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 11457
1070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 9146
1070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | PG&E | 2025 | 3 | 2561
1070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 98528
1070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 308608
1070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 54008
1070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 156748
1070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 1818
1070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 13461
1070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 3273
1070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 776
1070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 17973
1070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 10891
1070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 1686
1070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 3358
1070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 1279
1070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 175
1070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 7828
1070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 3336
1070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 679
1070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2025 | 3 | 568
1070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 327479
1070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 861031
1070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 109368
1070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 117903
1070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 2835
1070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 3769
1070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 10846
1070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 600
1070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 50652
1070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 7608
1070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 4279
1070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 2421
1070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 3875
1070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 282
1070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 26273
1070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 2409
1070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 1612
1070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2025 | 3 | 521
1070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 96
1070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 204
1070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 62
1070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 294
1070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 6
1070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 61
1070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 14
1070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 4
1070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 41
1070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 67
1070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 13
1070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 49
1070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 21
1070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 22
1070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 5
1070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 19
1070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 22
1070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 38
1070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 73
1070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 201
1070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 8
1070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 73
1070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 10
1070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 7
1070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 190
1070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 386
1070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 34
1070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 244
1070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 9
1070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 5
1070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 107
1070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 160
1070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 15
1070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 38

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.64868
1080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -3.5311
1080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.74471
1080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.11193
1080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.23676
1080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.67375
1080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.35381
1080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.01379
1080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -18.9041
1080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 1.189
1080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -1.7252
1080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -8.1903
1080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -4.8558
1080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.069332
1080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -17.4521
1080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -6.9861
1080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.26675
1080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 2.5938
1080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -5.5e-05
1080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.20145
1080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.10291
1080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 1.5285
1080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.010751
1080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.089423
1080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -9.2e-05
1080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 7.6e-05
1080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.24074
1080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.20434
1080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.032241
1080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.032197
1080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 6e-06
1080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.000819
1080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.01447
1080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -3e-06
1080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0.060546
1080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 7.5082
1080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 43.9632
1080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 12.0598
1080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 52.9253
1080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 4.3225
1080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 3.7095
1080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 2.9937
1080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 3.2329
1080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 37.48
1080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 4.7382
1080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 2.8141
1080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 6.4447
1080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 4.2291
1080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.006651
1080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 27.8184
1080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 7.374
1080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.083384
1080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -0.033516
1080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 3.2e-05
1080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -4.5e-05
1080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -2e-06
1080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 1.4e-05
1080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 1e-06
1080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -1e-06
1080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 4e-06
1080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -1e-06
1080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -1
1080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | -1
1080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 1
1080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 4
1080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 3
1080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 1
1080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 3
1080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 0
1080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2025 is the variance between Q1 2025 and Q4 2024. |  | PG&E | 2025 | 3 | 1

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 0
1090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 0
1090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 0
1090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 0.17
1090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 4.08
1090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 0.05
1090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 4.11
1090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 0
1090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 116.8
1090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 57.15
1090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 25.89
1090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 32.33
1090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 7.93
1090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 0
1090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 89.91
1090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 21.91
1090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 0.65
1090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | The 2025 actual values reported here represent work completed from 2023-2025 WMP Initiatives GH-01 and GH-04. Miles reported in Non-HFTD areas represent work selected because they are within the Tier 1 Buffer Zone, PG&E’s High Fire Risk Area (HFRA), or part of our Community Rebuild program. |  | PG&E | 2025 | 3 | 1.92
1090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2025 | 3 | 0
1090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2025 | 3 | 0
1090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0
1090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2025 | 3 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | PG&E | 2025 | 3 | 0
1100000001 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | PG&E | 2025 | 3 | 0
1100000002 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | PG&E | 2025 | 3 | 0
1100000003 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | PG&E | 2025 | 3 | 0
1100000004 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PG&E | 2025 | 3 | 0
1100000005 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PG&E | 2025 | 3 | 0
1100000006 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PG&E | 2025 | 3 | 0
1100000007 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PG&E | 2025 | 3 | 0
1100000008 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | PG&E | 2025 | 3 | 0
1100000009 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | PG&E | 2025 | 3 | 0
1100000010 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | PG&E | 2025 | 3 | 0
1100000011 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | PG&E | 2025 | 3 | 0
1100000012 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | PG&E | 2025 | 3 | 5
1100000013 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | PG&E | 2025 | 3 | 0
1100000014 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | PG&E | 2025 | 3 | 0
1100000015 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | PG&E | 2025 | 3 | 1437
1100000016 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | PG&E | 2025 | 3 | 55109
1100000017 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | PG&E | 2025 | 3 | 0
1100000018 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | PG&E | 2025 | 3 | 0
1100000019 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | PG&E | 2025 | 3 | 1498697.9
1100000020 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | PG&E | 2025 | 3 | 906184
1100000021 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | PG&E | 2025 | 3 | 3472471
1100000022 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | PG&E | 2025 | 3 | 2437137
1100000023 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Data is reported in minutes. |  | PG&E | 2025 | 3 | 73.2
1100000024 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Data is reported in minutes. |  | PG&E | 2025 | 3 | 73.2
1100000025 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PG&E | 2025 | 3 | 0.519
1100000026 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PG&E | 2025 | 3 | 0.519
1100000027 | 3. Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | PG&E | 2025 | 3 | 0
1100000028 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2025 | 3 | 0
1100000029 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2025 | 3 | 0
1100000030 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2025 | 3 | 0
1100000031 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2025 | 3 | 0
1100000032 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2025 | 3 | 0
1100000033 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2025 | 3 | 0
1100000034 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | PG&E | 2025 | 3 | 0
1100000035 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | PG&E | 2025 | 3 | 0
1100000036 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | PG&E | 2025 | 3 | 0
1100000037 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | PG&E | 2025 | 3 | 0
1100000038 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | PG&E | 2025 | 3 | 0
1100000039 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PG&E | 2025 | 3 | 0
1100000040 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PG&E | 2025 | 3 | 0
1100000041 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | PG&E | 2025 | 3 | 0.52
1100000042 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | PG&E | 2025 | 3 | 1.25
1100000043 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | PG&E | 2025 | 3 | 0