## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | REPORTING QUARTER | QUANTITATIVE ACTUAL PROGRESS Q1 | QUANTITATIVE ACTUAL PROGRESS Q1-2 | QUANTITATIVE ACTUAL PROGRESS Q1-3 | QUANTITATIVE ACTUAL PROGRESS Q1-4 | QUALITATIVE ACTUAL PROGRESS Q1 | QUALITATIVE ACTUAL PROGRESS Q1-2 | QUALITATIVE ACTUAL PROGRESS Q1-3 | QUALITATIVE ACTUAL PROGRESS Q1-4 | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Covered conductor installation | See coulumn I | Covered conductor utilizes conductors manufactured with an internal semiconducting layer and external insulating ultraviolet-resistant layer to provide incidental contact protection. The Covered Conductor program has the potential to raise the threshold for PSPS events to higher wind speeds compared to bare conductor. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.1 | WMP.455 | SDGE_Grid Design, Operations, and Maintainence_Covered Conductor Installation _WMP.455_2025 | 156 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | No | Miles |  | 2025 | 4 | 3.84 | 8.92 | 25.49 | 52.03 |  |  |  |  | Completed
1010000001 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Undergrounding of electric lines and/or equipment | See coulumn I | Strategic undergrounding converts overhead systems to underground, providing the dual benefits of nearly eliminating the risk of utility-caused wildfire and the need for PSPS events in these areas. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.2 | WMP.473 | SDGE_Grid Design, Operations, and Maintainence_Undergrounding of Electric Lines and/or Equipment _WMP.473_2025 | 158 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition | No | Miles |  | 2025 | 4 | 1.67 | 2.77 | 23.81 | 32.56 |  |  |  |  | Completed
1010000002 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Traditional overhead hardening | See coulumn I | Bare Conductor Hardening includes the replacement of wood poles with steel, replacement of conductor with high-strength bare conductor, and in some cases permanent removal of overhead facilities. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution overhead system hardening | 8.1.2.5.1 | WMP.475 | SDGE_Grid Design, Operations, and Maintainence_Traditional Overhead Hardening (Distribution) _WMP.475_2025 | 157 | Equipment ignition likelihood | No | Miles |  | 2025 | 4 | 0.11 | 0.11 | 0.11 | 0.11 |  |  |  |  | Completed
1010000003 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Traditional overhead hardening | See coulumn I | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission overhead hardening | 8.1.2.5.2 | WMP.543 | SDGE_Grid Design, Operations, and Maintainence_Traditional Overhead Hardening (Transmission) _WMP.543_2025 | 163 | Equipment ignition likelihood | No | Miles |  | 2025 | 4 | 0 | 0 | 0 | 2 |  |  |  |  | Completed
1010000004 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Traditional overhead hardening | See coulumn I | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission overhead hardening (distribution underbuild) | 8.1.2.5.2 | WMP.545 | SDGE_Grid Design, Operations, and Maintainence_Traditional Overhead Hardening (Distribution Underbuilt)_WMP.545_2025 | 160 | Equipment ignition likelihood | No | Miles |  | 2025 | 4 | 0 | 0 | 0 | 0 |  |  |  |  | Delayed | No corrective actions required. 3yr target scope exceeded by 14.5mi. 3yr scope completion is 248%
1010000005 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Installation of system automation equipment | See coulumn I | Advanced Protection creates higher visibility and situational awareness in fire-prone areas, and allow for the implementation of new relay and automation standards in locations where protection coordination is difficult due to lower fault currents attributed to high impedance faults. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Advanced protection | 8.1.2.8.1 | WMP.463 | SDGE_Grid Design, Operations, and Maintainence_Installation of System Automation Equipment (Advanced Protection)_WMP.463_2025 | 163 | Equipment ignition likelihood | No | Circuits |  | 2025 | 4 | 2 | 5.9989 | 7 | 7 |  |  |  |  | Delayed | Required permits were delayed and not issued until Jan 2026. SMEs reviewing scope for 2026 inclusion.
1010000006 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Installation of system automation equipment | See coulumn I | Early fault detection employs technologies such as Advance Radio Frequency Sensors (ARFS) and Power Quality (PQ) Meters to detect and prevent significant equipment failures before they occur. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Early fault detection | 8.1.2.8.2 | WMP.1195 | SDGE_Grid Design, Operations, and Maintainence_Installation of System Automation Equipment (EFD) _WMP.1195_2025 | 172 | Equipment ignition likelihood | No | Nodes |  | 2025 | 4 | 39 | 68 | 89 | 125 |  |  |  |  | Completed
1010000007 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Installation of system automation equipment | See coulumn I | The Distribution Communications Reliability Improvement (DCRI) program enables APP and EFD technologies as a reliable communication network is necessary for initiatives that require continuous communication. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution communications reliability improvements | 8.1.2.8.3 | WMP.549 | SDGE_Grid Design, Operations, and Maintainence_Installation of System Automation Equipment (LTE)_WMP.549_2025 | 175 | Wildfire hazard PSPS exposure potential | No | Base Stations |  | 2025 | 4 | 1 | 1 | 2 | 4 |  |  |  |  | Delayed | Delay due to field change order for unknown facilities discovered below grid. Remaining base station in construction for early 2026 delivery.
1010000008 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | The SCADA Capacitors Maintenance and Replacement Program will detect and isolate issues before a capacitor rupture occurs, reducing the failure mode most likely to lead to an ignition. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Capacitor maintenance and replacement program (SCADA) | 8.1.4.3 | WMP.453 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (SCADA) _WMP.453_2025 | 213 | Equipment ignition likelihood | No | Capacitors |  | 2025 | 4 | 0 | 0 | 0 | 0 |  |  |  |  | Cancelled
1010000009 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | The Expulsion Fuse Replacement Program replaces existing expulsion fuses with new, more fire safe expulsion fuses that are approved by CAL FIRE. These new expulsion fuses reduce the discharge expelled into the atmosphere, reducing the chance of a fuse operation leading to an ignition. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Expulsion fuse replacement | 8.1.4.4 | WMP.459 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Expulsion Fuse Replacement) _WMP.459_2025 | 222 | Equipment ignition likelihood | No | Fuses |  | 2025 | 4 | 164 | 250 | 316 | 503 |  |  |  |  | Delayed | Petition to Amend submitted for reduced target due to GRC decision, so work scoped for 2025 was rolled back. Restarted program when Petition to Amend was denied, but unable to reach full target due to pause in program.
1010000010 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | The Hotline Clamps (HLC) Replacement Program replaces HLC connections that are connected directly onto the overhead primary conductors with compression connections to eliminate the risk of the wire down failure and the associated wildfire risk. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Maintenance, repair, and replacement of connectors, including hotline clamps | 8.1.4.5 | WMP.464 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (HLC)_WMP.464_2025 | 224 | Equipment ignition likelihood | No | HLCs |  | 2025 | 4 | 90 | 106 | 107 | 110 |  |  |  |  | Delayed | No corrective actions required. 3yr target scope exceeded by 297 HLC installs. 3yr scope completion is 120%.
1010000011 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | Lightning Arrestors Replacement Program installs CAL FIRE-approved lightning arrestors to mitigate the impact of transient overvoltage on the electric system. CAL FIRE-approved lightning arrestors are equipped with an external device that operates prior to the arrestor overloading, dramatically reducing the potential of becoming an ignition source. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Lightning arrester removal and replacement | 8.1.4.6 | WMP.550 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Arrestors)_WMP.550_2025 | 226 | Equipment ignition likelihood | No | Arrestors |  | 2025 | 4 | 344 | 507 | 656 | 1015 |  |  |  |  | Completed
1010000012 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | Avian Protection is aimed at improving reliability and reducing the risk of faults and wire-down events associated with avian contact that can lead to ignitions. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Avian protection | 8.1.2.10.1 | WMP.972 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Avian)_WMP.972_2025 | 171 | Contact by object ignition | No | Poles |  | 2025 | 4 | 269 | 353 | 507 | 724 |  |  |  |  | Completed
1010000013 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | Wireless fault indicator technology is deployed to narrow the location of detected issues on the system. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Wireless Fault Indicators | 8.1.8.2 | WMP.449 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Wireless fault indicators)_WMP.449_2025 | 277 | Equipment ignition likelihood | No | WFIs |  | 2025 | 4 | 0 | 0 | 0 | 0 |  |  |  |  | Cancelled
1010000014 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to minimize risk of ignitions | See coulumn I | Strategic Pole Replacement targets high-risk poles located throughout the service territory that are gas treated (also known as Cellon treatment) and are set in concrete and steel reinforced, steel reinforced and set in soil, or set in soil, and are not being address by other programs such as Covered Conductor Hardening or Strategic Undergrounding. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Strategic pole replacement program | 8.1.2.10.2 | WMP.1189 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to minimize risk of ignitions (Pole Replacements)_WMP.1189_2025 | 179 | Equipment ignition likelihood | No | Poles |  | 2025 | 4 | 68 | 110 | 198 | 228 |  |  |  |  | Completed
1010000015 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See coulumn I | PSPS Sectionalizing Enhancement Program installs switches in strategic locations, improving the ability to isolate high-risk areas for potential de energization. For example, switches are installed on circuits that have significant sections undergrounded, allowing customers with this lower-risk infrastructure to remain energized during weather events. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | PSPS sectionalizing enhancements | 8.1.2.11.1 | WMP.461 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to mitigate or reduce PSPS events (PSPS Sectionalizing Enhancements)_WMP.461_2025 | 175 | PSPS exposure potential PSPS vulnerability | No | Switches |  | 2025 | 4 | 5 | 5 | 7 | 9 |  |  |  |  | Completed
1010000016 | SDG&E | 2025-11-01 | Project | 2023-01-01 | 2025-12-31 | Microgrids | See coulumn I | Microgrid backup generation and battery storage to reduce the impact of PSPS. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.7 | WMP.462 | SDGE_Grid Design & System Hardening_Microgrids_WMP.462_2025 | 161 | PSPS vulnerability | No | Microgrid |  | 2025 | 4 | 0 | 0 | 0 | 0 |  |  |  |  | Cancelled
1010000017 | SDG&E | 2025-11-01 | Project | 2020-07-01 | 2025-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See coulumn I | This program assists backcountry residences, businesses, and local communities in the HFTD by providing a fixed installation backup generator, or a solar panel and battery backup system to keep customers energized during PSPS. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Standby power (fixed power backup) | 8.1.2.11.2 | WMP.468 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to mitigate or reduce PSPS events (Standby Power)_WMP.468_2025 | 175 | PSPS vulnerability | No | Generators |  | 2025 | 4 | 0 | 8 | 26 | 88 |  |  |  |  | Completed
1010000018 | SDG&E | 2025-11-01 | Project | 2020-07-01 | 2025-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See coulumn I | The Resiliency Grant Programs offer portable battery units with solar charging capacity to provide vulnerable customers with a means to keep small devices and appliances charged and powered during PSPS events. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Generator grant program | 8.1.2.11.3 | WMP.466 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to mitigate or reduce PSPS events (Generator Grant Program)_WMP.466_2025 | 177 | PSPS vulnerability | No | Generators |  | 2025 | 4 |  |  |  |  | Vendor continued to deliver batteries and provide emergency deliveries to qualifying impacted customers during January PSPS events. Finalized 2025 pricing and updated scope of work. Eligible customer list generated for 2025. 2025 system configuration updates currently in process for completion in early Q2. | Vendor partner agreements for 2025 have been executed. 2025 customer notification communications have been mailed to newly qualified customers, websited updates have been completed, and outreach materials have been updated. Program has officially launched for the 2025 program year. 2025 procedure updates have been finalized and are in the process of being updated in the Access and Functional Needs active PSPS procedure documentation. | Customer eligibility lists were updated. Outreach communications were mailed out and the implementer began performing outreach phone calls to customers. The program was promoted to interested customers during all Wildfire Safety Fairs. The implementer continued to perform outreach, delivery, and education services. | Customer eligibility lists are updated and provided to vendors monthly. Contractor conducted scheduling, delivery, and product training to all eligible customers who enrolled in the program. End-of-year report has been finalized and will be received from vendor in Q1 2026. End-of-year customer survey is being finalized and will be distributed to 2025 participating customers in Q1 2026. | Completed
1010000019 | SDG&E | 2025-11-01 | Project | 2020-07-01 | 2025-12-31 | Other grid topology improvements to mitigate or reduce PSPS events | See coulumn I | The Resiliency Assistance Programs focus on enhancing resiliency for customers who reside in the HFTD and may be impacted by PSPS events. The program offers a rebate to customers providing a 70-to-90 percent discount on average portable generator models to mitigate the impacts of PSPS. | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Generator assistance program | 8.1.2.11.4 | WMP.467 | SDGE_Grid Design, Operations, and Maintainence_Other grid topology improvements to mitigate or reduce PSPS events (Generator Assistance Program)_WMP.467_2025 | 179 | PSPS vulnerability | No | Generators |  | 2025 | 4 |  |  |  |  | Completed analysis for Qualified Product List and update. Launched marketing and outreach communications. Generated customer eligibility lists based on data parameters. Program go-live - systems and processes active for customer participation. | System configuration completed 2/21/2025. Website updates completed 3/1/25. Customer invitiations have been sent 6/18/25. Customer facing portal updated on 3/3/2025. Processes and procedures updated on 2/28/2025. | SDG&E has been processing rebates since program went live on 3/1/2025. Attended four Wildfire Safety Fairs and provided customer education to more than 2,000 customers. Customer eligibility lists are updated and provided to the vendor monthly. | Customer eligibility lists are updated and provided to vendors monthly. Final year-end marketing communications were distributed on December 16, 2025. End-of-year survey was finalized and will be distributed in Q1 2026. End-of-year participation report was finalized and will be received from vendor in Q1 2026. | Completed
1010000020 | SDG&E | 2025-11-01 | Program |  |  | Distribution overhead detailed inspections | See coulumn I | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.1 | WMP.478 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Detailed Inspections of Distribution Electric Lines and Equipment)_WMP.478_2025 | 182 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 6327 | 14143 | 17180 | 17950 |  |  |  |  | Completed
1010000021 | SDG&E | 2025-11-01 | Program |  |  | Transmission overhead detailed inspections | See coulumn I | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.2 | WMP.479 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Detailed Inspections of Transmission Electric Lines and Equipment) _WMP.479_2025 | 185 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 349 | 732 | 1927 | 2184 |  |  |  |  | Delayed | No corrective actions required. 3yr target scope exceeded by 210 inspections. 3yr scope completion is 103%. All remaining inspections remain current under CAISO's 3yr inspection cycle requirement.
1010000022 | SDG&E | 2025-11-01 | Program |  |  | Distribution infrared inspections | See coulumn I | Perform infrared inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.3 | WMP.481 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Infrared Inspections of Distribution Electric Lines and Equipment)_WMP.481_2025 | 188 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 0 | 88 | 211 | 302 |  |  |  |  | Completed
1010000023 | SDG&E | 2025-11-01 | Program |  |  | Transmission infrared inspections | See coulumn I | Perform infrared inspections, as scheduled, to reduce the risk of equipment failure. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.4 | WMP.482 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Infrared Inspections of Transmission Electric Lines and Equipment)_WMP.482_2025 | 189 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 0 | 0 | 6976 | 6976 |  |  |  |  | Completed
1010000024 | SDG&E | 2025-11-01 | Program |  |  | Distribution wood pole intrusive inspections | See coulumn I | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.5 | WMP.483 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Distribution Wood Pole Intrusive Pole Inspections)_WMP.483_2025 | 192 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 215 | 1013 | 1228 | 1478 |  |  |  |  | Completed
1010000025 | SDG&E | 2025-11-01 | Program |  |  | Transmission wood pole intrusive inspections | See coulumn I | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.6 | WMP.1190 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Wood Pole Trans)_WMP.1190_2025 | 194 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 21 | 44 | 75 | 163 |  |  |  |  | Completed
1010000026 | SDG&E | 2025-11-01 | Program |  |  | Drone assessments | See coulumn I | Perform drone inspections on highest risk structures in the HFTD and WUI areas. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.7 | WMP.552 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Distribution Drone Assessments)_WMP.552_2025 | 194 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 0 | 0 | 5254 | 13500 |  |  |  |  | Completed
1010000027 | SDG&E | 2025-11-01 | Program |  |  | Distribution overhead patrol inspections | See coulumn I | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.8 | WMP.488 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Distribution overhead Patrol Inspections)_WMP.488_2025 | 200 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 35253 | 60502 | 83769 | 86040 |  |  |  |  | Completed
1010000028 | SDG&E | 2025-11-01 | Program |  |  | Transmission overhead patrol inspections | See coulumn I | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.9 | WMP.489 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Transmission Overhead Patrol)_WMP.489_2025 | 202 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 6935 | 6935 | 7263 | 7263 |  |  |  |  | Completed
1010000029 | SDG&E | 2025-11-01 | Program |  |  | Transmission 69kV tier 3 visual inspections | See coulumn I | Perform supplemental inspections on all 69kV tielines in Tier 3 prior to wildfire season | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.10 | WMP.555 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Transmission 69kV Tier 3)_WMP.555_2025 | 206 | Equipment ignition likelihood | Yes | Structures |  | 2025 | 4 | 0 | 1 | 1601 | 1601 |  |  |  |  | Completed
1010000030 | SDG&E | 2025-11-01 | Program |  |  | Substation patrol inspections | See coulumn I | Perform substation patrols, as scheduled, to reduce the risk of equipment failure and to manage vegetation hazards within the substation. | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.11 | WMP.492 | SDGE_Grid Design, Operations, and Maintainence_Asset inspections (Substation Patrol)_WMP.492_2025 | 207 | Equipment ignition likelihood | No | Substations |  | 2025 | 4 | 94 | 196 | 287 | 391 |  |  |  |  | Completed
1010000031 | SDG&E | 2025-11-01 | Program |  |  | Quality assurance / quality control of transmission inspections | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.1 | WMP.1191 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Secondary Trans)_WMP.1191_2025 | 226 | Equipment ignition likelihood | Yes | Findings |  | 2025 | 4 | 100% | 100% | 100% | 100% |  |  |  |  | Completed
1010000032 | SDG&E | 2025-11-01 | Program |  |  | Quality assurance / quality control of distribution detailed inspections | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.2 | WMP.491 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Distribution Detailed)_WMP.491_2025 | 226 | Equipment ignition likelihood | No | Structures |  | 2025 | 4 | 202 | 645 | 982 | 1078 |  |  |  |  | Completed
1010000033 | SDG&E | 2025-11-01 | Program |  |  | Quality assurance / quality control of distribution drone assessments | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.3 | WMP.1192 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Distribution Drone)_WMP.1192_2025 | 227 | Equipment ignition likelihood | No | Structures |  | 2025 | 4 | 0 | 0 | 5254 | 13500 |  |  |  |  | Completed
1010000034 | SDG&E | 2025-11-01 | Program |  |  | Quality assurance / quality control of wood pole intrusive (transmission and distribution) | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.4 | WMP.1193 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Wood Pole Dist &Trans)_WMP.1193_2025 | 227 | Equipment ignition likelihood | No | Structures |  | 2025 | 4 | 871 | 1263 | 1329 | 1381 |  |  |  |  | Completed
1010000035 | SDG&E | 2025-11-01 | Program |  |  | Quality assurance / quality control of substation inspections | See coulumn I | Perform Quality assurance / quality control of inspections to validate inspection results, either by field or desktop validation | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) |  | 8.1.6.5 | WMP.1194 | SDGE_Grid Design, Operations, and Maintainence_Quality assurance / quality control (Periodic Review)_WMP.1194_2025 | 227 | Equipment ignition likelihood | No | Structures |  | 2025 | 4 | 5 | 9 | 18 | 18 |  |  |  |  | Completed
1010000036 | SDG&E | 2025-11-01 | Program |  |  | Detailed inspections | See coulumn I | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation Management and Inspections | Vegetation Management Inspections |  | 8.2.2.1 | WMP.494 | SDGE_Vegetation Management and Inspection_Vegetation Management Inspection Program (Detailed inspections of vegetation around distribution electric lines and equipment)_WMP.494_2025 | 260 | Wildfire hazard | No | Inspections |  | 2025 | 4 | 136645 | 275667 | 386310 | 511150 |  |  |  |  | Completed
1010000037 | SDG&E | 2025-11-01 | Program |  |  | Off-cycle patrol | See coulumn I | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation Management and Inspections | Vegetation Management Inspections |  | 8.2.2.2 | WMP.508 | SDGE_Vegetation Management and Inspection_Vegetation Management Inspection Program (Off-Cycle)_WMP.508_2025 | 265 | Contact from vegetation ignition likelihood | No | VMAs |  | 2025 | 4 | 31 | 62 | 106 | 106 |  |  |  |  | Completed
1010000038 | SDG&E | 2025-11-01 | Program |  |  | Fuels management | See coulumn I | Wildland fuel reduction involves the thinning, pruning, and in some cases, removal of vegetation for the purpose of minimizing source material that could ignite and propagate a wildfire. | Vegetation Management and Inspections | Integrated Vegetation Management |  | 8.2.3 | WMP.497 | SDGE_Vegetation Management and Inspection_Fuel Management (slash) _WMP.497_2025 | 273 | Contact from vegetation ignition likelihood | No | Poles Cleared |  | 2025 | 4 | 62 | 341 | 452 | 500 |  |  |  |  | Completed
1010000039 | SDG&E | 2025-11-01 | Program |  |  | Pole clearing (brushing) | See coulumn I | Pole brushing is a fire prevention measure involving the removal of vegetation at the base of poles that carry specific types of electrical hardware that could cause sparking or molten material to fall to the ground. | Vegetation Management and Inspections | Pole Clearing |  | 8.2.3.1 | WMP.512 | SDGE_Vegetation Management and Inspection_Pole Clearing (Brushing)_WMP.501_2025 | 270 | Wildfire hazard | No | Poles Brushed |  | 2025 | 4 | 12710 | 20003 | 23865 | 33250 |  |  |  |  | Completed
1010000040 | SDG&E | 2025-11-01 | Program |  |  | Clearance | See coulumn I | Vegetation Management defines enhanced clearances as greater than or equal to 12 feet at time of trim, which is the CPUC-recommended post-trim clearance for distribution voltages in the HFTD. SDG&E aims to achieve clearances up to 25 feet, where feasible, to achieve the optimal risk mitigation. | Vegetation Management and Inspections | Pruning and Removal |  | 8.2.3.3 | WMP.501 | SDGE_Vegetation Management and Inspection_Clearance (Achieve clearances around electric lines and equipment) _WMP.512_2025 | 274 | Wildfire hazard | No | Trees Trimmed or Removed |  | 2025 | 4 | 2211 | 3945 | 8554 | 11921 |  |  |  |  | Completed
1010000041 | SDG&E | 2025-11-01 | Program |  |  | Quality assurance / quality control vegetation management | See coulumn I | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) |  | 8.2.5 | WMP.505 | SDGE_Vegetation Management and Inspection_Quality assurance / quality control_WMP.505_2025 | 280 | Contact from vegetation ignition likelihood | No | Inspections |  | 2025 | 4 | 26% | 34% | 29% | 27% |  |  |  |  | Completed
1010000042 | SDG&E | 2025-11-01 | Program |  |  | Weather Station Maintenance and Calibration | See coulumn I | Weather Station Maintenance and Calibration is dedicated to the maintenance and calibration of weather stations. The Weather Station Network strategically positions weather stations to transmit data on sustained wind speed, wind gust, wind direction, temperature, and humidity every 10 minutes using cellular and spread spectrum communications. | Situational Awareness and Forecasting | Weather Forecasting |  | 8.3.2.1.1 | WMP.1430 | SDGE_Situational Awareness and Forecasting_Weather Station Maintenance and Calibration_WMP.1430_2025 | 305 | Wildfire vulnerability Wildfire exposure potential | No | Weather Stations |  | 2025 | 4 | 53 | 208 | 216 | 216 |  |  |  |  | Completed
1010000043 | SDG&E | 2025-11-01 | Program |  |  | Air Quality Station Maintenance | See coulumn I | Air Quality Maintenance of the particulate sensors will include a scheduled monthly, quarterly, and annual inspection. Each visit will include a rigorous preventative maintenance to ensure accurate functioning of the sensors. | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | 8.3.2.1.3 | WMP.1431 | SDGE_Situational Awareness and Forecasting_Air Quality Station Maintenance_WMP.1431_2025 | 307 | Wildfire exposure potential | No | Sensors |  | 2025 | 4 | 48 | 95 | 143 | 194 |  |  |  |  | Completed

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000001 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000002 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000003 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 37
1020000004 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000005 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000006 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000007 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 38
1020000008 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000009 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000010 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000011 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 155
1020000012 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000013 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000014 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000015 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 5
1020000016 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000017 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000018 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000019 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 2
1020000020 | 1. Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000021 | 1. Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000022 | 1. Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000023 | 1. Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 16
1020000024 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000025 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000026 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000027 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 37
1020000028 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000029 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000030 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000031 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 38
1020000032 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000033 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000034 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000035 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 122
1020000036 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000037 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000038 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000039 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000040 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000041 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000042 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000043 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000044 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000045 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000046 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000047 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 33
1020000048 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000049 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000050 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000051 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000052 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000053 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000054 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000055 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000056 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000057 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000058 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000059 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2025 | 4 | 0
1020000060 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SDG&E | 2025 | 4 | 120
1020000061 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SDG&E | 2025 | 4 | 169
1020000062 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SDG&E | 2025 | 4 | 128
1020000063 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SDG&E | 2025 | 4 | 309
1020000064 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | SDG&E | 2025 | 4 | 118
1020000065 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | SDG&E | 2025 | 4 | 161
1020000066 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SDG&E | 2025 | 4 | 121.5
1020000067 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SDG&E | 2025 | 4 | 154
1020000068 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SDG&E | 2025 | 4 | 113
1020000069 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SDG&E | 2025 | 4 | 140
1020000070 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  |  | SDG&E | 2025 | 4 | 117
1020000071 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  |  | SDG&E | 2025 | 4 | 155
1020000072 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000073 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000074 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 1
1020000075 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 1
1020000076 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 2
1020000077 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 3.75
1020000078 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000079 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000080 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000081 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000082 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000083 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000084 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 1115
1020000085 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 1548
1020000086 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 103
1020000087 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 500
1020000088 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 253
1020000089 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 588
1020000090 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 246
1020000091 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 394
1020000092 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 23
1020000093 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 150
1020000094 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 249
1020000095 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 766
1020000096 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 4
1020000097 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 4
1020000098 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 4
1020000099 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 4
1020000100 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 4
1020000101 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit | Not Applicable | SDG&E | 2025 | 4
1020000102 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000103 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000104 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000105 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000106 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000107 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2025 | 4 | 0
1020000108 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2025 | 4 | 15547
1020000109 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2025 | 4 | 1150
1020000110 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2025 | 4 | 1675
1020000111 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2025 | 4 | 78
1020000112 | 8. Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  |  | SDG&E | 2025 | 4 | 1.16
1020000113 | 9. Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | SDG&E | 2025 | 4 | 0
1020000114 | 9. Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | SDG&E | 2025 | 4 | 0
1020000115 | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | SDG&E | 2025 | 4 | 0
1020000116 | 11. Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | SDG&E | 2025 | 4 | 0
1020000117 | 11. Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | SDG&E | 2025 | 4 | 0
1020000118 | 12. Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | SDG&E | 2025 | 4 | 0.25
1020000119 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000120 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000121 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000122 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000123 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000124 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000125 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000126 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000127 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000128 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000129 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000130 | 13. Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2025 | 4 | 0
1020000131 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000132 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000133 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000134 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 2104
1020000135 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000136 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000137 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000138 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 676
1020000139 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 3279
1020000140 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000141 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000142 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 149
1020000143 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000144 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000145 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000146 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 90.4947
1020000147 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000148 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000149 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000150 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 33.0987
1020000151 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 168.6388
1020000152 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000153 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000154 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 4.2451
1020000155 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000156 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000157 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000158 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000159 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000160 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000161 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000162 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000163 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 2
1020000164 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000165 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000166 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000167 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000168 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000169 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000170 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 1
1020000171 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000172 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000173 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000174 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 10
1020000175 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 225
1020000176 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000177 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000178 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 2
1020000179 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000180 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000181 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000182 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000183 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000184 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000185 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000186 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000187 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000188 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000189 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000190 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000191 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000192 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000193 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000194 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 167
1020000195 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000196 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000197 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000198 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 94
1020000199 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 4875
1020000200 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000201 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000202 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 101
1020000203 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000204 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000205 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000206 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 8.286
1020000207 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000208 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000209 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000210 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 3.3483
1020000211 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 252.5241
1020000212 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000213 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000214 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000215 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000216 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000217 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000218 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000219 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000220 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000221 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000222 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000223 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 3
1020000224 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000225 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000226 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000227 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000228 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000229 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000230 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000231 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000232 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000233 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000234 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 8
1020000235 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 494
1020000236 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000237 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000238 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000239 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000240 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000241 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000242 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000243 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000244 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000245 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000246 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000247 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000248 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000249 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000250 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000251 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000252 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000253 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000254 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 15867
1020000255 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000256 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000257 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000258 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 3462
1020000259 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 92
1020000260 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000261 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000262 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 2060
1020000263 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000264 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000265 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000266 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 345.4483
1020000267 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000268 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000269 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000270 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 97.9305
1020000271 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 5.1617
1020000272 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000273 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000274 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0.098295
1020000275 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000276 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000277 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000278 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 1
1020000279 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000280 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000281 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000282 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 4
1020000283 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000284 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000285 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000286 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 2
1020000287 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000288 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000289 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000290 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 63
1020000291 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000292 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000293 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000294 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 204
1020000295 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 8
1020000296 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000297 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000298 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 28
1020000299 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000300 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000301 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000302 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000303 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000304 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000305 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000306 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000307 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000308 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000309 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000310 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000311 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000312 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000313 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000314 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000315 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000316 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000317 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000318 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 220
1020000319 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000320 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000321 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000322 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 41
1020000323 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000324 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000325 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000326 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000327 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000328 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000329 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000330 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 18.1146
1020000331 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000332 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000333 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000334 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000335 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000336 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000337 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000338 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000339 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000340 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000341 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000342 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000343 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000344 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000345 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000346 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000347 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000348 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000349 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000350 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000351 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000352 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000353 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000354 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 12
1020000355 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000356 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000357 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000358 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000359 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000360 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000361 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000362 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000363 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000364 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000365 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000366 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000367 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000368 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000369 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000370 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000371 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000372 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000373 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000374 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000375 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000376 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000377 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000378 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 4
1020000379 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000380 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000381 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000382 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000383 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000384 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000385 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000386 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000387 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000388 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000389 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000390 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0.36465
1020000391 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000392 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000393 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000394 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000395 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000396 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000397 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000398 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000399 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000400 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000401 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000402 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000403 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000404 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000405 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000406 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000407 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000408 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000409 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000410 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000411 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000412 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000413 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000414 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000415 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000416 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000417 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000418 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000419 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000420 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000421 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000422 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000423 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000424 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000425 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000426 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000427 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000428 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000429 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000430 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000431 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000432 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000433 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000434 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000435 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000436 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000437 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000438 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 251
1020000439 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000440 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000441 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000442 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2025 | 4 | 430
1020000443 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000444 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000445 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000446 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000447 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000448 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000449 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000450 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 15.9585
1020000451 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000452 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000453 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2025 | 4
1020000454 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2025 | 4 | 0
1020000455 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000456 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000457 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000458 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000459 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000460 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000461 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000462 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000463 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000464 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000465 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000466 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000467 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000468 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000469 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000470 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000471 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000472 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000473 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000474 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 80
1020000475 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000476 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000477 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000478 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000479 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000480 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000481 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000482 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000483 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000484 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000485 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000486 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000487 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000488 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000489 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2025 | 4
1020000490 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2025 | 4 | 0
1020000491 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000492 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000493 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000494 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000495 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000496 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000497 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000498 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000499 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 2
1020000500 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000501 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000502 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000503 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000504 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000505 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000506 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 10
1020000507 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000508 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000509 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000510 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 28
1020000511 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 162
1020000512 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000513 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000514 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 1
1020000515 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000516 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000517 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000518 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000519 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000520 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000521 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000522 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000523 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000524 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000525 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000526 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000527 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000528 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000529 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000530 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000531 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000532 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000533 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000534 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000535 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 2
1020000536 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000537 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000538 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000539 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000540 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000541 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000542 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 10
1020000543 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000544 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000545 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000546 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 79
1020000547 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 111
1020000548 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000549 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000550 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 3
1020000551 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000552 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000553 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000554 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000555 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000556 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000557 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000558 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000559 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000560 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000561 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000562 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000563 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000564 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000565 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000566 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 1
1020000567 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000568 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000569 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000570 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 4
1020000571 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000572 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000573 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000574 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 2
1020000575 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000576 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000577 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000578 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 64
1020000579 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000580 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000581 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000582 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 195
1020000583 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 8
1020000584 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000585 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000586 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 14
1020000587 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000588 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000589 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000590 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000591 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000592 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000593 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000594 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000595 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000596 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000597 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000598 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000599 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000600 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000601 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000602 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000603 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000604 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000605 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000606 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000607 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000608 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000609 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000610 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000611 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000612 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000613 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000614 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000615 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000616 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 2
1020000617 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000618 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 28
1020000619 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000620 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000621 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000622 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000623 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000624 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000625 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000626 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000627 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000628 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000629 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000630 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000631 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000632 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000633 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000634 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000635 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000636 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000637 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000638 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000639 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000640 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000641 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000642 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000643 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000644 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000645 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000646 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000647 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000648 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000649 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000650 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000651 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000652 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000653 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000654 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 7
1020000655 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000656 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000657 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000658 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000659 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000660 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000661 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000662 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000663 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000664 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000665 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000666 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000667 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000668 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000669 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000670 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000671 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000672 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000673 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000674 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000675 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000676 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000677 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000678 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000679 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000680 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000681 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000682 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000683 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000684 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 2
1020000685 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000686 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000687 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000688 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 4
1020000689 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000690 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 122
1020000691 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000692 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000693 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000694 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 1
1020000695 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000696 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000697 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000698 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000699 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000700 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000701 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000702 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000703 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000704 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000705 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2025 | 4
1020000706 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2025 | 4 | 0
1020000707 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000708 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000709 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000710 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 23356
1020000711 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000712 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000713 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000714 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000715 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 2
1020000716 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000717 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000718 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000719 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000720 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000721 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000722 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 394
1020000723 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000724 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000725 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000726 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 18848
1020000727 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000728 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000729 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000730 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000731 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 4
1020000732 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000733 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000734 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000735 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000736 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000737 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000738 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 81
1020000739 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000740 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000741 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000742 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 78585
1020000743 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000744 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000745 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000746 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000747 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000748 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000749 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000750 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000751 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000752 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000753 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000754 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 1408
1020000755 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000756 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000757 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000758 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 1670
1020000759 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000760 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000761 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000762 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000763 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000764 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000765 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000766 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000767 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000768 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000769 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000770 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000771 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000772 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000773 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000774 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 120
1020000775 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000776 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000777 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000778 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000779 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000780 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000781 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000782 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000783 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000784 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000785 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000786 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000787 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000788 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000789 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000790 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 2261
1020000791 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000792 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000793 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000794 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2025 | 4 | 0
1020000795 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000796 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000797 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000798 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000799 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000800 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000801 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2025 | 4
1020000802 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2025 | 4 | 1
1020000803 | 17. Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | Not Applicable | SDG&E | 2025 | 4

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | Number of High FPI days (elevated or extreme FPI) | Number of High FPI days (elevated or extreme FPI) | To track the number of days that wildfire weather conditions observed | To evaluate the frequency of the risk event and normalize it for comparison over historical years to quantify the performance | No | Days |  |  | SDG&E | 2025 | 4 | 28
1030000001 | Number of RFW days | Number of RFW days | To track the number of days that wildfire weather conditions observed | To evaluate the frequency of the risk event and normalize it for comparison over historical years to quantify the performance | No | Days |  |  | SDG&E | 2025 | 4 | 0
1030000002 | Vegetation caused ignitons in HFTD with elevated or higher FPI | Vegetation caused ignitons in HFTD with elevated or higher FPI | To track the number of vegetation caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 4 | 0
1030000003 | Vegetation caused ignitons in HFTD with RFW | Vegetation caused ignitons in HFTD with RFW | To track the number of vegetation caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 4 | 0
1030000004 | Equipment caused ignitions in HFTD with elevated or higher FPI | Equipment caused ignitions in HFTD with elevated or higher FPI | To track the number of equipment caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 4 | 0
1030000005 | Equipment caused ignitions in HFTD with RFW | Equipment caused ignitions in HFTD with RFW | To track the number of equipment caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 4 | 0
1030000006 | Balloons caused ignitions in HFTD with elevated or higher FPI | Balloons caused ignitions in HFTD with elevated or higher FPI | To track the number of bolloon caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 4 | 0
1030000007 | Balloons caused ignitions in HFTD with RFW | Balloons caused ignitions in HFTD with RFW | To track the number of balloon caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 4 | 0
1030000008 | Vehicles caused ignitions in HFTD with elevated or higher FPI | Vehicles caused ignitions in HFTD with elevated or higher FPI | To track the number of vehicles caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 4 | 0
1030000009 | Vehicles caused ignitions in HFTD with RFW | Vehicles caused ignitions in HFTD with RFW | To track the number of vehicles caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2025 | 4 | 0
1030000010 | Equipment caused ignition rate in HFTD during high FPI | Equipment caused ignition rate in HFTD during high FPI | To track ignition rate during elevated or extreme wildfire weather condition | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions per high FPI day |  |  | SDG&E | 2025 | 4 | 0
1030000011 | CPUC reportable secondary igntions | CPUC reportable secondary igntions | To correctly categorize and count the ignitions that are not transmission or distribution related | n/a | No | Ignitions |  |  | SDG&E | 2025 | 4 | 1
1030000012 | Vegetation caused outages in HFTD with Elevated FPI | Vegetation caused outages in HFTD with Elevated FPI | To track the number of vegetation caused risk events during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 4 | 0
1030000013 | Vegetation caused outages in HFTD with RFW | Vegetation caused outages in HFTD with RFW | To track the number of vegetation caused risk events during RFW wildfire weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 4 | 0
1030000014 | Overhead faults on circuits in HFTD with Elevated or higher FPI | Overhead faults on circuits in HFTD with Elevated or higher FPI | To track the number of all overhead faults that are controllable during elelvated and extreme wildfire weather conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 4 | 14
1030000015 | Overhead faults on circuits in HFTD with RFW | Overhead faults on circuits in HFTD with RFW | To track the number of all overhead faults that are controllable during RFW wildfire weather conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 4 | 0
1030000016 | Energized wire down events in HFTD with Elevated or higher FPI | Energized wire down events in HFTD with Elevated or higher FPI | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 4 | 0
1030000017 | Energized wire down events in HFTD with RFW | Energized wire down events in HFTD with RFW | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 4 | 0
1030000018 | Number of non-CALFIRE rated fuse operations in HFTD with Elevated or higher FPI | Number of non-CALFIRE rated fuse operations in HFTD with Elevated or higher FPI | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 4 | 0
1030000019 | Number of non-CALFIRE rated fuse operations in HFTD with RFW | Number of non-CALFIRE rated fuse operations in HFTD with RFW | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2025 | 4 | 0
1030000020 | Overhead fault rate in HFTD during High FPI | Overhead fault rate in HFTD during High FPI | To evaluate the performance of risk reduction from overall mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Overhead faults per high FPI day |  |  | SDG&E | 2025 | 4 | 0.5
1030000021 | Near Miss Reporting | Near Miss Reporting | Track safety related incidents | To evaluate and assess the safety culture | No | Near miss events reported |  |  | SDG&E | 2025 | 4 | 445
1030000022 | Safety Observations | Safety Observations | Track safety related incidents | To evaluate and assess the safety culture | No | Observations performed |  |  | SDG&E | 2025 | 4 | 14097
1030000023 | Percent of customers being de-energized on PSPS circuits | Percent of customers being de-energized on PSPS circuits | To track the scope of PSPS events | To evaluate the isolation of the de-energization given weather events | No | percent | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1030000024 | Number of circuits de-engergized | Number of circuits de-engergized | To track the scale of PSPS events | To evaluate the scale of the de-energization given weather events | No | circuits | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1030000025 | Communication success rate of weather stations | Communication success rate of weather stations | To track the weather station performance | To ensure the effectiveness of situational awareness tools | Yes | percent |  |  | SDG&E | 2025 | 4 | 98.66%
1030000026 | Post processing success rate - WRF simulations | Post processing success rate - WRF simulations | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | Yes | percent |  |  | SDG&E | 2025 | 4 | 100%
1030000027 | Post processing success rate - ML gust model | Post processing success rate - ML gust model | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | No | percent |  |  | SDG&E | 2025 | 4 | 100%
1030000028 | Post processing success rate - SAWTI | Post processing success rate - SAWTI | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | No | percent |  |  | SDG&E | 2025 | 4 | 96.4%
1030000029 | Post processing success rate - FPI | Post processing success rate - FPI | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | No | percent |  |  | SDG&E | 2025 | 4 | 100%
1030000030 | Post processing success rate - OPI | Post processing success rate - OPI | To track the weather data processing performance | To ensure the effectiveness of situational awareness tools | No | percent |  |  | SDG&E | 2025 | 4 | 100%
1030000031 | Percentage of community partners participating in local wildfire mitigation planning (in territory) | Percentage of community partners participating in local wildfire mitigation planning (in territory) | To track engagement and preparedness for PSPS activation | To ensure the effectiveness of preparedness of external partners | No | percent |  |  | SDG&E | 2025 | 4 | 100
1030000032 | Percentage of Wildfire/PSPS events followed by an After-Action Review or feedback process | Percentage of Wildfire/PSPS events followed by an After-Action Review or feedback process | To track the after action review and feedback | To ensure the effectiveness of preparedness | No | percent | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1030000033 | Percentage of individuals with AFN who were aware of what support and resources were available to them during a PSPS event. | Percentage of individuals with AFN who were aware of what support and resources were available to them during a PSPS event. | To track engagement and preparedness for PSPS activation | To ensure the effectiveness of preparedness | No | percent | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1030000034 | Percentage of individuals with AFN who were able to use necessary medical equipment to maintain necessary life functions for the duration of any PSPS event that affected them | Percentage of individuals with AFN who were able to use necessary medical equipment to maintain necessary life functions for the duration of any PSPS event that affected them | To track engagement and preparedness for PSPS activation | To ensure the effectiveness of preparedness | No | percent | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1030000035 | Percentage of individuals who utilized mitigation services and reported they were satisfied with the level of support | Percentage of individuals who utilized mitigation services and reported they were satisfied with the level of support | To track engagement and preparedness for PSPS activation | To ensure the effectiveness of preparedness | No | percent | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1030000036 | Percentage of customers notified prior to a PSPS event impacting them | Percentage of customers notified prior to a PSPS event impacting them | To track the performance of notifications for PSPS activation | To ensure the effectiveness of preparedness | No | percent | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000001 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000002 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000003 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000004 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000005 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000006 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000007 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000008 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000009 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000010 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000011 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000012 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000013 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000014 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000015 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000016 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000017 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1040000018 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 41327.14
1040000019 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 42236.13
1040000020 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 38959.64
1040000021 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 11741.21
1040000022 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 7679.52
1040000023 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2025 | 4 | 6740.34

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 3
1050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | No | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | No | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | No | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | No | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | No | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | No | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 4
1050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 4
1050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 3
1050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2025 | 4
1050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | No | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | No | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2025 | 4
1050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 9
1050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 2
1050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 8
1050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 10
1050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 2
1050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 16
1050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 3
1050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 7
1050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 2
1050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 4
1050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | No | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | No | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 31
1050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 8
1050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 4
1050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 8
1050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 4
1050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 6
1050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 2
1050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 5
1050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 8
1050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 5
1050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 3
1050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 4
1050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events | No | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2025 | 4
1050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2025 | 4
1050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2025 | 4
1050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 3
1050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 4
1050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 3
1050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | No | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2025 | 4
1050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | No | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | No | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2025 | 4
1050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events | No | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2025 | 4
1050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 21
1050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 5
1050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 10
1050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 12
1050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 4
1050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 1
1050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0
1050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SDG&E | 2025 | 4 | 0

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2025 | 4
1060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | No | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 4
1060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | No | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 4
1060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | No | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 4
1060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | No | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 4
1060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | No | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 4
1060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | No | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2025 | 4
1060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | No | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 4
1060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 4
1060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 4
1060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | No | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 4
1060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 4
1060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2025 | 4
1060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E does not currently track this driver | not applicable | SDG&E | 2025 | 4
1060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | No | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2025 | 4
1060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0
1060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SDG&E | 2025 | 4 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 368.3988
1070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 2164.6477
1070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 122.2122
1070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 146.956
1070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 26.093
1070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 117.7509
1070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 87.5245
1070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 96.1281
1070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 730.6155
1070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 674.3399
1070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 12.8813
1070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 151.3328
1070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 4.9792
1070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.37957
1070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 541.3986
1070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 890.3577
1070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 7.7435
1070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 110.3865
1070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 99.7389
1070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 452.9512
1070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 25.1634
1070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 123.8845
1070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 22.8575
1070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 27.1016
1070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 110.3454
1070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 67.1165
1070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 514.0107
1070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 23.4248
1070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.66539
1070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.56946
1070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 16.0867
1070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 246.6929
1070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.20164
1070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 11.8542
1070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 1735.3228
1070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 5224.3156
1070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 372.3424
1070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 763.6592
1070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 11.8625
1070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 39.7467
1070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 845.4946
1070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 283.7643
1070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 731.3485
1070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 409.08
1070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 4.1249
1070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 9.5659
1070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 5.5881
1070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 1.6835
1070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 315.7326
1070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 253.1076
1070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 4.8752
1070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 29.7047
1070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 14.3222
1070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 86.895
1070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 5.3869
1070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 22.7881
1070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.092242
1070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 10.6668
1070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 4.9604
1070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 8.64
1070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 16.9733
1070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 1.761
1070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.65012
1070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 3.5073
1070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 3.4685
1070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 3249
1070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 15666
1070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 497
1070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 2074
1070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 3
1070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 66
1070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 986
1070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 397
1070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 916
1070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 915
1070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 12
1070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 88
1070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 2
1070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 0
1070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 504
1070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 862
1070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 13
1070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2025 | 4 | 69
1070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 217821
1070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 913531
1070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 23142
1070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 20403
1070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 1003
1070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 1663
1070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 80023
1070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 23574
1070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 46173
1070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 16740
1070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 256
1070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 493
1070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 102
1070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 3
1070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 18917
1070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 8463
1070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 156
1070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2025 | 4 | 547
1070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 16143
1070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 95881
1070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 2686
1070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 20111
1070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 98
1070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 381
1070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 4740
1070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 2647
1070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 4254
1070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 3859
1070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 34
1070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 216
1070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 14
1070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 0
1070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 2197
1070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 2600
1070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 50
1070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2025 | 4 | 236
1070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 47014
1070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 296674
1070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 4466
1070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 3966
1070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 404
1070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 314
1070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 16231
1070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 6608
1070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 9506
1070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 3620
1070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 100
1070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 169
1070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 26
1070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 1
1070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 5579
1070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 2150
1070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 37
1070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2025 | 4 | 158
1070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 12
1070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 71
1070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 4
1070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 23
1070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 3
1070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 2
1070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 7
1070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 4
1070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 18
1070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 1
1070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 11
1070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 1
1070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 3
1070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 14
1070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 3
1070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 2
1070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 2
1070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 6
1070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 17
1070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 49
1070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 1
1070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 7
1070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 13
1070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 93
1070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 3
1070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 7

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 2.8422e-14
1080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.55336
1090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 2.8861
1090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 2.0749
1090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 6.2669
1090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 8.909
1090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 5.8489
1090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.18015
1090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 1.6169
1090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0.17035
1090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2025 | 4 | 0
1090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2025 | 4 | 0
1090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0
1090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2025 | 4 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | SDG&E | 2025 | 4 | 0
1100000001 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | SDG&E | 2025 | 4 | 0
1100000002 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | SDG&E | 2025 | 4 | 0
1100000003 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | SDG&E | 2025 | 4 | 0
1100000004 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2025 | 4 | 0
1100000005 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2025 | 4 | 0
1100000006 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2025 | 4 | 0
1100000007 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | SDG&E | 2025 | 4 | 0
1100000008 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | SDG&E | 2025 | 4 | 0
1100000009 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | SDG&E | 2025 | 4 | 0
1100000010 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | SDG&E | 2025 | 4 | 0
1100000011 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | SDG&E | 2025 | 4 | 0
1100000012 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | SDG&E | 2025 | 4 | 0
1100000013 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | SDG&E | 2025 | 4 | 0
1100000014 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | SDG&E | 2025 | 4 | 0
1100000015 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | SDG&E | 2025 | 4 | 0
1100000016 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1100000017 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1100000018 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1100000019 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | SDG&E | 2025 | 4 | 0
1100000020 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | SDG&E | 2025 | 4 | 464356.0167
1100000021 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | SDG&E | 2025 | 4 | 363641.18
1100000022 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | SDG&E | 2025 | 4 | 0
1100000023 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | SDG&E | 2025 | 4 | 14.16
1100000024 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | SDG&E | 2025 | 4 | 14.16
1100000025 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | SDG&E | 2025 | 4 | 0.133
1100000026 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | SDG&E | 2025 | 4 | 0.133
1100000027 | 3. Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000028 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000029 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000030 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000031 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000032 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000033 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000034 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000035 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000036 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000037 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000038 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000039 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000040 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000041 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000042 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4
1100000043 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events | No PSPS events in 2025 Q4 | Not Applicable | SDG&E | 2025 | 4

## Table 13
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED OR MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1130000000 | 140338 | Complete Tower | HFTD Tier 2 | Transmission | 2025-03-04 | 2026-03-04 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000001 | 137823 | Guy Wire - OH | Non-HFTD | Transmission | 2025-06-24 | 2026-06-23 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000002 | 137831 | Complete Tower | HFTD Tier 2 | Transmission | 2025-04-10 | 2026-04-09 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000003 | 137832 | Complete Tower | HFTD Tier 2 | Transmission | 2025-04-10 | 2026-04-09 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000004 | 136194 | Guy Wire - Anchor | Non-HFTD | Transmission | 2025-06-25 | 2026-06-24 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000005 | 139200 | Guy Wire - OH | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000006 | 137966 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-08-07 | 2026-08-07 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000007 | 137221 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2025-04-16 | 2026-04-15 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000008 | 137574 | Pole Butt | Non-HFTD | Transmission | 2025-10-29 | 2026-10-29 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000009 | 138546 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2025-10-10 | 2026-10-10 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000010 | 138354 | Insulators-Ceramic, Standard, 50K | HFTD Tier 3 | Transmission | 2025-08-23 | 2026-08-22 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000011 | 140865 | Footings (Complete) | HFTD Tier 3 | Transmission | 2025-04-15 | 2026-04-14 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000012 | 137216 | Ground Grid Taps | HFTD Tier 2 | Transmission | 2025-10-08 | 2026-10-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000013 | 138868 | Anchor Rods | HFTD Tier 2 | Transmission | 2025-10-31 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000014 | 138870 | Anchor Rod Ground Wire | HFTD Tier 2 | Transmission | 2025-10-31 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000015 | 138087 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-08-13 | 2026-08-13 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000016 | 138088 | Guy Wire - OH | Non-HFTD | Transmission | 2025-08-13 | 2026-08-13 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000017 | 139152 | Insulators-NCI, 69kv | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000018 | 140287 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000019 | 140284 | Pole Top | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000020 | 140285 | Pole Top | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000021 | 137964 | Insulators-Ceramic, Post, 69kv | Non-HFTD | Transmission | 2025-08-04 | 2026-08-04 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000022 | 132539 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000023 | 137810 | Area Around Structure | HFTD Tier 3 | Transmission | 2025-06-25 | 2026-06-25 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000024 | 139671 | Pole Butt | Non-HFTD | Transmission | 2025-08-05 | 2026-08-05 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000025 | 139669 | Pole Top | Non-HFTD | Transmission | 2025-08-05 | 2026-08-05 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000026 | 135931 | Footings (Complete) | HFTD Tier 2 | Transmission | 2023-01-10 | 2026-08-09 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000027 | 135930 | Concrete | HFTD Tier 2 | Transmission | 2023-01-10 | 2026-08-09 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000028 | 132614 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000029 | 140182 | Other(Specify) | HFTD Tier 2 | Transmission | 2025-11-24 | 2026-11-24 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000030 | 132502 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000031 | 132536 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000032 | 140721 | Pole Butt | HFTD Tier 2 | Transmission | 2025-08-13 | 2026-08-13 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000033 | 133947 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2024-04-06 | 2026-04-04 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000034 | 139182 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000035 | 139150 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000036 | 132616 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000037 | 141112 | Complete Wood Pole | Non-HFTD | Transmission | 2025-04-17 | 2026-04-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000038 | 141111 | Pole Butt | Non-HFTD | Transmission | 2025-04-17 | 2026-04-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000039 | 139148 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-16 | 2026-12-16 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000040 | 138613 | Insulators-Ceramic, Standard, 40K | HFTD Tier 2 | Transmission | 2025-11-08 | 2026-11-07 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000041 | 140608 | Footings (Complete) | HFTD Tier 2 | Transmission | 2025-05-28 | 2026-05-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000042 | 137967 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-08-07 | 2026-08-07 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000043 | 137576 | FAA Light(s) | HFTD Tier 2 | Transmission | 2025-02-04 | 2026-02-03 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000044 | 140073 | Insulators-Post, NCI, 69kv, Long | HFTD Tier 2 | Transmission | 2025-10-06 | 2026-10-05 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000045 | 138588 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2025-10-23 | 2026-10-22 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000046 | 140981 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-27 | 2026-12-27 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000047 | 138155 | Complete Wood Pole | Non-HFTD | Transmission | 2025-03-11 | 2026-03-11 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000048 | 139205 | Shoe (Complete) | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000049 | 139201 | Pole Top | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000050 | 139206 | Guy Wire - OH | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000051 | 139203 | Insulators-Ceramic, Standard, 30K | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000052 | 140120 | Insulators-Ceramic, Standard, 40K | HFTD Tier 2 | Transmission | 2025-11-24 | 2026-11-24 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000053 | 139175 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000054 | 132517 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000055 | 139323 | Conduit | HFTD Tier 2 | Transmission | 2025-07-29 | 2026-07-29 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000056 | 139367 | Bolt(s) | Non-HFTD | Transmission | 2025-10-13 | 2026-10-13 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000057 | 139368 | Insulators-Post, NCI, 69kv, Long | Non-HFTD | Transmission | 2025-10-13 | 2026-10-13 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000058 | 138348 | Cold End Cotter Key(s) | HFTD Tier 3 | Transmission | 2025-08-23 | 2026-02-21 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000059 | 132516 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000060 | 138146 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2025-07-31 | 2026-07-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000061 | 132613 | Complete Wood Pole | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000062 | 132600 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000063 | 132601 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000064 | 139149 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-16 | 2026-12-16 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000065 | 136522 | Anchor Rod Ground Wire | HFTD Tier 2 | Transmission | 2025-07-26 | 2026-07-25 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000066 | 139178 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000067 | 132504 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000068 | 137928 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-07-28 | 2026-07-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000069 | 138192 | Aerial Number(s) | HFTD Tier 3 | Transmission | 2025-08-23 | 2026-08-22 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000070 | 132534 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000071 | 132481 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000072 | 134747 | Insulators-Post, NCI, 69kv, Long | Non-HFTD | Transmission | 2024-06-21 | 2026-06-19 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000073 | 136207 | Anchor Rods | Non-HFTD | Transmission | 2025-06-24 | 2026-06-23 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000074 | 139251 | Pole Top | HFTD Tier 2 | Transmission | 2025-07-29 | 2026-07-29 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000075 | 138472 | Insulators-Ceramic, Standard, 50K | HFTD Tier 3 | Transmission | 2025-08-23 | 2026-02-21 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000076 | 138470 | Stub Angles | HFTD Tier 3 | Transmission | 2025-08-21 | 2026-06-19 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000077 | 138471 | Hot End Cotter Key(s) | HFTD Tier 3 | Transmission | 2025-08-23 | 2026-02-21 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000078 | 140790 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-11-29 | 2026-11-29 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000079 | 140980 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-27 | 2026-12-27 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000080 | 140972 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-12-27 | 2026-12-27 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000081 | 132596 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000082 | 132503 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000083 | 139179 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000084 | 138548 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2025-10-10 | 2026-10-10 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000085 | 139183 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000086 | 139764 | Complete Wood Pole | Non-HFTD | Transmission | 2025-08-05 | 2026-08-05 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000087 | 130991 | Bolted Spacer | HFTD Tier 2 | Transmission | 2023-10-08 | 2026-10-07 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000088 | 136589 | Anchor Rods | HFTD Tier 2 | Transmission | 2025-07-29 | 2026-07-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000089 | 140989 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-16 | 2026-12-16 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000090 | 132587 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000091 | 140864 | Footings (Complete) | HFTD Tier 3 | Transmission | 2025-04-15 | 2026-04-14 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000092 | 137825 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-14 | 2026-12-14 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000093 | 139012 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-06-10 | 2026-06-10 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000094 | 136042 | Bolt(s) | HFTD Tier 2 | Transmission | 2025-06-10 | 2026-06-10 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000095 | 139181 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000096 | 138614 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2025-11-08 | 2026-11-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000097 | 137380 | Area Around Structure | HFTD Tier 3 | Transmission | 2025-10-25 | 2026-10-25 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000098 | 132520 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000099 | 139259 | Jumper Bolt(S)-Nut(s) | HFTD Tier 2 | Transmission | 2025-12-30 | 2026-12-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000100 | 137188 | Area Around Footer(s) | HFTD Tier 2 | Transmission | 2025-04-10 | 2026-04-10 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000101 | 132535 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000102 | 138489 | Complete Wood Pole | Non-HFTD | Transmission | 2025-04-22 | 2026-04-22 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000103 | 138115 | Hardware | HFTD Tier 2 | Transmission | 2025-08-28 | 2026-08-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000104 | 132624 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000105 | 137677 | Other(Specify) | HFTD Tier 2 | Transmission | 2025-11-21 | 2026-11-21 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000106 | 131897 | Cold End Clevis-Shackle | Non-HFTD | Transmission | 2023-12-18 | 2026-06-15 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000107 | 132482 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000108 | 139193 | Guy Wire - OH | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000109 | 139194 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000110 | 132537 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000111 | 134188 | Other(Specify) | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000112 | 132623 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000113 | 136600 | Pole Butt | HFTD Tier 2 | Transmission | 2025-08-01 | 2026-08-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000114 | 132519 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000115 | 137826 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-14 | 2026-12-14 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000116 | 138021 | Anchor Rods | Non-HFTD | Transmission | 2025-08-14 | 2026-08-14 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000117 | 138019 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-08-14 | 2026-08-14 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000118 | 134403 | Complete Steel Pole | HFTD Tier 2 | Transmission | 2024-07-09 | 2026-07-09 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000119 | 132480 | Pole Butt | HFTD Tier 3 | Transmission | 2024-03-01 | 2026-03-01 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000120 | 139177 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000121 | 136450 | Brace(s) | Non-HFTD | Transmission | 2025-07-21 | 2026-07-20 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000122 | 138867 | Hardware | HFTD Tier 2 | Transmission | 2025-10-31 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000123 | 125650 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2021-09-01 | 2027-08-25 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000124 | 139174 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-16 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000125 | 139151 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000126 | 137941 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-08-02 | 2026-08-02 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000127 | 140513 | Aerial Marker Sphere(s) | HFTD Tier 3 | Transmission | 2025-07-10 | 2026-05-07 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000128 | 139198 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000129 | 140863 | Footings (Complete) | HFTD Tier 3 | Transmission | 2025-04-16 | 2026-04-15 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000130 | 138590 | Hairpin Strand(s) | HFTD Tier 2 | Transmission | 2025-08-02 | 2026-08-02 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000131 | 132538 | Pole Butt | HFTD Tier 3 | Transmission | 2024-02-29 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000132 | 132855 | Jumper (Complete) | HFTD Tier 3 | Transmission | 2023-12-18 | 2026-12-15 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000133 | 137811 | Pole Top | HFTD Tier 3 | Transmission | 2025-12-23 | 2026-12-23 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000134 | 100023693412 | Pole | HFTD Tier 2 | Distribution | 2023-04-17 | 2024-04-29 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000135 | 100024607585 | Pole | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000136 | 100024607586 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000137 | 100024607587 | Cross Arm | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000138 | 100024892414 | Wood Pole | HFTD Tier 3 | Distribution | 2023-11-06 | 2024-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000139 | 100025465847 | Cross Arm | HFTD Tier 2 | Distribution | 2024-02-02 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000140 | 100025472514 | Pole | HFTD Tier 3 | Distribution | 2024-02-04 | 2024-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000141 | 100025526925 | Pole | HFTD Tier 3 | Distribution | 2024-02-16 | 2024-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000142 | 100025596658 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-02-29 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000143 | 100025598865 | Pole | HFTD Tier 2 | Distribution | 2024-02-29 | 2025-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000144 | 100025656487 | Pole | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000145 | 100025656501 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000146 | 100025656507 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000147 | 100025664759 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000148 | 100025664760 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000149 | 100025664762 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000150 | 100025684401 | Pole | HFTD Tier 2 | Distribution | 2024-03-18 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000151 | 100025684407 | Pole | HFTD Tier 2 | Distribution | 2024-03-18 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000152 | 100025690362 | Pole | HFTD Tier 2 | Distribution | 2024-03-19 | 2025-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000153 | 100025801256 | Pole | HFTD Tier 2 | Distribution | 2024-04-05 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000154 | 100025883031 | Avian Protection | HFTD Tier 2 | Distribution | 2024-04-24 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000155 | 100025905418 | Other | HFTD Tier 2 | Distribution | 2024-04-25 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000156 | 100025905419 | Transformer | HFTD Tier 2 | Distribution | 2024-04-25 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000157 | 100025911585 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-04-26 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000158 | 100025911586 | Conductor | HFTD Tier 2 | Distribution | 2024-04-26 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000159 | 100025926874 | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2025-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000160 | 100025953145 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-03 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000161 | 100025964194 | Pole | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000162 | 100025964350 | Pole | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000163 | 100025964351 | Pole | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000164 | 100025964998 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000165 | 100025979542 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000166 | 100025979543 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000167 | 100025979544 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000168 | 100025979546 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000169 | 100025996630 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-14 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000170 | 100026018163 | Pole | HFTD Tier 2 | Distribution | 2024-05-16 | 2025-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000171 | 100026132409 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-03 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000172 | 100026132564 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-03 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000173 | 100026138089 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-04 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000174 | 100026138091 | Pole | HFTD Tier 2 | Distribution | 2024-06-04 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000175 | 100026267708 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000176 | 100026267781 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000177 | 100026267784 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000178 | 100026267786 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000179 | 100026267790 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000180 | 100026267793 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000181 | 100026267796 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000182 | 100026267799 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000183 | 100026289760 | Pole | HFTD Tier 2 | Distribution | 2024-07-02 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000184 | 100026323167 | Insulator and Bushing | Non-HFTD | Distribution | 2024-07-01 | 2027-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000185 | 100026334307 | Pole | HFTD Tier 2 | Distribution | 2024-07-16 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000186 | 100026334744 | Cross Arm | HFTD Tier 2 | Distribution | 2024-07-16 | 2025-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000187 | 100026374171 | Wood Pole | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000188 | 100026403049 | Pole | Non-HFTD | Distribution | 2024-07-23 | 2027-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000189 | 100026433704 | Conductor | Non-HFTD | Distribution | 2024-07-30 | 2027-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000190 | 100026433705 | Switch | Non-HFTD | Distribution | 2024-07-30 | 2027-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000191 | 100026437295 | Conductor - Veg | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000192 | 100026437414 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000193 | 100026495821 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-22 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000194 | 100026519491 | Other | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000195 | 100026519492 | Pole | HFTD Tier 2 | Distribution | 2024-08-26 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000196 | 100026585051 | Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000197 | 100026591812 | Other | HFTD Tier 2 | Distribution | 2024-09-16 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000198 | 100026672795 | Switch | Non-HFTD | Distribution | 2024-09-30 | 2027-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000199 | 100026701250 | Cross Arm | Non-HFTD | Distribution | 2024-10-11 | 2027-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000200 | 100026729769 | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000201 | 100026766313 | Cross Arm | Non-HFTD | Distribution | 2024-09-05 | 2028-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000202 | 100026768781 | Cross Arm | Non-HFTD | Distribution | 2024-11-01 | 2028-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000203 | 100026768782 | Cross Arm | Non-HFTD | Distribution | 2024-11-01 | 2028-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000204 | 100026788856 | Insulator and Bushing | Non-HFTD | Distribution | 2024-11-04 | 2028-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000205 | 100026788858 | Cross Arm | Non-HFTD | Distribution | 2024-11-05 | 2028-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000206 | 100027016345 | Cross Arm | Non-HFTD | Distribution | 2024-12-16 | 2028-02-29 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000207 | 100027077528 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000208 | 100027077695 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000209 | 100027077696 | Other | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000210 | 100027077697 | Transformer | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000211 | 100027077698 | Transformer | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000212 | 100027077699 | Transformer | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000213 | 100027078212 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000214 | 100027078213 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000215 | 100027078214 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000216 | 100027101579 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000217 | 100027101580 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000218 | 100027101581 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000219 | 100027101588 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000220 | 100027157833 | Switch | HFTD Tier 2 | Distribution | 2025-01-23 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000221 | 100027196897 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000222 | 100027196913 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000223 | 100027196915 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000224 | 100027196950 | Cross Arm | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000225 | 100027196951 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000226 | 100027196952 | Cross Arm | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000227 | 100027196953 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000228 | 100027196954 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000229 | 100027196955 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000230 | 100027197017 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000231 | 100027197018 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000232 | 100027197086 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000233 | 100027197088 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000234 | 100027197203 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000235 | 100027197206 | Pole | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000236 | 100027224636 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-02-03 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000237 | 100027242478 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-02-06 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000238 | 100027248003 | Pole | HFTD Tier 3 | Distribution | 2025-02-10 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000239 | 100027248004 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-02-10 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000240 | 100027250359 | Pole | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000241 | 100027250370 | Pole | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000242 | 100027250802 | Pole | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000243 | 100027250803 | Cross Arm | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000244 | 100027250804 | Pole | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000245 | 100027251827 | Cross Arm | HFTD Tier 3 | Distribution | 2025-02-11 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000246 | 100027254164 | Cross Arm | HFTD Tier 3 | Distribution | 2025-02-12 | 2025-08-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000247 | 100027283386 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-02-21 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000248 | 100027315516 | Pole | HFTD Tier 2 | Distribution | 2025-02-25 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000249 | 100027324423 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-02-27 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000250 | 100027324425 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-02-27 | 2026-04-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000251 | 100027357037 | Pole | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000252 | 100027357273 | Pole | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000253 | 100027357274 | Pole | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000254 | 100027357361 | Pole | HFTD Tier 2 | Distribution | 2025-03-05 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000255 | 100027361011 | Cross Arm | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000256 | 100027390655 | Pole | HFTD Tier 2 | Distribution | 2025-03-19 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000257 | 100027390758 | Pole | HFTD Tier 2 | Distribution | 2025-03-19 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000258 | 100027397850 | Pole | HFTD Tier 2 | Distribution | 2025-03-20 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000259 | 100027405709 | Pole | HFTD Tier 2 | Distribution | 2025-03-24 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000260 | 100027425652 | Pole | HFTD Tier 2 | Distribution | 2025-03-25 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000261 | 100027435599 | Cross Arm | HFTD Tier 2 | Distribution | 2025-03-26 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000262 | 100027436893 | Pole | HFTD Tier 2 | Distribution | 2025-03-26 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000263 | 100027436894 | Pole | HFTD Tier 2 | Distribution | 2025-03-26 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000264 | 100027439040 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000265 | 100027439041 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000266 | 100027439058 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000267 | 100027440013 | Pole | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-05-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000268 | 100027466521 | Pole | HFTD Tier 2 | Distribution | 2025-04-02 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000269 | 100027468753 | Cross Arm | HFTD Tier 3 | Distribution | 2025-04-03 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000270 | 100027475468 | Pole | HFTD Tier 2 | Distribution | 2025-04-07 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000271 | 100027498762 | Pole | HFTD Tier 2 | Distribution | 2025-04-14 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000272 | 100027501981 | Pole | HFTD Tier 2 | Distribution | 2025-04-15 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000273 | 100027504716 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000274 | 100027505505 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000275 | 100027505506 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000276 | 100027505809 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000277 | 100027505820 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000278 | 100027505821 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000279 | 100027505825 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000280 | 100027508733 | Avian Protection | HFTD Tier 2 | Distribution | 2025-04-17 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000281 | 100027519390 | Pole | HFTD Tier 2 | Distribution | 2025-04-21 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000282 | 100027523251 | Pole | HFTD Tier 2 | Distribution | 2025-04-22 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000283 | 100027570380 | Pole | HFTD Tier 2 | Distribution | 2025-04-30 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000284 | 100027583241 | Pole | HFTD Tier 2 | Distribution | 2025-05-01 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000285 | 100027584165 | Pole | HFTD Tier 2 | Distribution | 2025-04-30 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000286 | 100027584166 | Cross Arm | HFTD Tier 2 | Distribution | 2025-04-30 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000287 | 100027584167 | Pole | HFTD Tier 2 | Distribution | 2025-04-30 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000288 | 100027591056 | Pole | HFTD Tier 3 | Distribution | 2025-05-05 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000289 | 100027591057 | Pole | HFTD Tier 3 | Distribution | 2025-05-05 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000290 | 100027591131 | Pole | HFTD Tier 3 | Distribution | 2025-05-05 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000291 | 100027591364 | Pole | HFTD Tier 2 | Distribution | 2025-05-05 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000292 | 100027591991 | Pole | HFTD Tier 2 | Distribution | 2025-05-05 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000293 | 100027597911 | Cross Arm | HFTD Tier 3 | Distribution | 2025-05-06 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000294 | 100027604697 | Pole | HFTD Tier 2 | Distribution | 2025-05-08 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000295 | 100027605564 | Pole | HFTD Tier 3 | Distribution | 2025-05-08 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000296 | 100027607201 | Wood Pole | HFTD Tier 2 | Distribution | 2025-05-08 | 2028-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000297 | 100027616866 | Pole | HFTD Tier 3 | Distribution | 2025-05-13 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000298 | 100027617034 | Pole | HFTD Tier 3 | Distribution | 2025-05-13 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000299 | 100027643132 | Pole | HFTD Tier 3 | Distribution | 2025-05-21 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000300 | 100027643133 | Pole | HFTD Tier 3 | Distribution | 2025-05-21 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000301 | 100027676087 | Pole | HFTD Tier 3 | Distribution | 2025-05-27 | 2025-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000302 | 100027705673 | Other | HFTD Tier 2 | Distribution | 2025-06-04 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000303 | 100027708225 | Conductor | HFTD Tier 2 | Distribution | 2025-06-05 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000304 | 100027708839 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2025-06-05 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000305 | 100027708930 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-06-05 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000306 | 100027711899 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-06-06 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000307 | 100027711900 | Pole | HFTD Tier 2 | Distribution | 2025-06-06 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000308 | 100027711901 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-06-06 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000309 | 100027712864 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-06 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000310 | 100027713989 | Pole | HFTD Tier 2 | Distribution | 2025-06-09 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000311 | 100027717479 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000312 | 100027717530 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000313 | 100027717531 | Transformer | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000314 | 100027717532 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000315 | 100027717558 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000316 | 100027717559 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000317 | 100027717593 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000318 | 100027717594 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000319 | 100027717595 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000320 | 100027717596 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000321 | 100027717597 | Transformer | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000322 | 100027718000 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000323 | 100027718503 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000324 | 100027718504 | Transformer | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000325 | 100027720460 | Pole | HFTD Tier 2 | Distribution | 2025-06-10 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000326 | 100027722978 | Pole | HFTD Tier 2 | Distribution | 2025-06-11 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000327 | 100027726780 | Pole | HFTD Tier 2 | Distribution | 2025-06-13 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000328 | 100027727243 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-13 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000329 | 100027729814 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-06-16 | 2025-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000330 | 100027733628 | Pole | HFTD Tier 2 | Distribution | 2025-06-17 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000331 | 100027743744 | Switch | Non-HFTD | Distribution | 2025-06-13 | 2028-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000332 | 100027751612 | Other | HFTD Tier 2 | Distribution | 2025-06-24 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000333 | 100027772263 | Pole | HFTD Tier 2 | Distribution | 2025-06-25 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000334 | 100027786799 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000335 | 100027786830 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000336 | 100027786831 | Pole | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000337 | 100027786919 | Pole | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000338 | 100027787130 | Pole | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000339 | 100027787131 | Pole | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000340 | 100027787132 | Pole | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000341 | 100027787133 | Pole | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000342 | 100027787767 | Pole | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000343 | 100027787768 | Pole | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000344 | 100027787769 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-27 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000345 | 100027802659 | Cross Arm | HFTD Tier 2 | Distribution | 2025-05-13 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000346 | 100027803029 | Insulator and Bushing | Non-HFTD | Distribution | 2025-05-30 | 2028-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000347 | 100027805293 | Pole | HFTD Tier 2 | Distribution | 2025-07-02 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000348 | 100027805436 | Insulator and Bushing | Non-HFTD | Distribution | 2025-05-30 | 2028-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000349 | 100027805654 | Other | Non-HFTD | Distribution | 2025-05-30 | 2028-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000350 | 100027806765 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-07-03 | 2026-01-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000351 | 100027812090 | Pole | HFTD Tier 3 | Distribution | 2025-07-08 | 2026-01-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000352 | 100027815722 | Pole | HFTD Tier 2 | Distribution | 2025-07-09 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000353 | 100027815785 | Other | Non-HFTD | Distribution | 2025-07-09 | 2028-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000354 | 100027823367 | Pole | HFTD Tier 2 | Distribution | 2025-07-14 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000355 | 100027902972 | Ground Wire | HFTD Tier 3 | Distribution | 2025-08-01 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000356 | 100027902973 | Pole | HFTD Tier 3 | Distribution | 2025-08-01 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000357 | 100027902974 | Pole | HFTD Tier 3 | Distribution | 2025-08-01 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000358 | 100027907497 | Pole | HFTD Tier 3 | Distribution | 2025-08-01 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000359 | 100027907498 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-01 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000360 | 100027907990 | Pole | HFTD Tier 2 | Distribution | 2025-08-05 | 2030-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000361 | 100027907991 | Pole | HFTD Tier 2 | Distribution | 2025-08-05 | 2030-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000362 | 100027908149 | Pole | HFTD Tier 2 | Distribution | 2025-08-05 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000363 | 100027914798 | Cross Arm | HFTD Tier 2 | Distribution | 2025-08-07 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000364 | 100027917131 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000365 | 100027917132 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000366 | 100027917135 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000367 | 100027917136 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000368 | 100027918059 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000369 | 100027918260 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000370 | 100027918263 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000371 | 100027918264 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000372 | 100027924879 | Other | Non-HFTD | Distribution | 2025-08-07 | 2028-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000373 | 100027927979 | Pole | HFTD Tier 3 | Distribution | 2025-08-13 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000374 | 100027928168 | Pole | HFTD Tier 3 | Distribution | 2025-08-13 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000375 | 100027929519 | Avian Protection | HFTD Tier 3 | Distribution | 2025-08-13 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000376 | 100027929660 | Avian Protection | HFTD Tier 3 | Distribution | 2025-08-13 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000377 | 100027932034 | Pole | HFTD Tier 3 | Distribution | 2025-08-14 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000378 | 100027932292 | Pole | HFTD Tier 3 | Distribution | 2025-08-14 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000379 | 100027936873 | Pole | HFTD Tier 3 | Distribution | 2025-08-18 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000380 | 100027936988 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000381 | 100027979455 | Pole | HFTD Tier 3 | Distribution | 2025-08-26 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000382 | 100027979498 | Pole | HFTD Tier 3 | Distribution | 2025-08-26 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000383 | 100027979499 | Pole | HFTD Tier 3 | Distribution | 2025-08-26 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000384 | 100027979541 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-26 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000385 | 100027979542 | Pole | HFTD Tier 3 | Distribution | 2025-08-26 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000386 | 100027979543 | Transformer | HFTD Tier 3 | Distribution | 2025-08-26 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000387 | 100027979544 | Pole | HFTD Tier 3 | Distribution | 2025-08-26 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000388 | 100027981211 | Pole | HFTD Tier 3 | Distribution | 2025-08-27 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000389 | 100027981212 | Transformer | HFTD Tier 3 | Distribution | 2025-08-27 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000390 | 100027981219 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-08-27 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000391 | 100027981260 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-08-27 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000392 | 100027983203 | Pole | HFTD Tier 2 | Distribution | 2025-07-31 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000393 | 100027983211 | Pole | HFTD Tier 2 | Distribution | 2025-08-14 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000394 | 100027983212 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000395 | 100027983214 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2025-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000396 | 100027983215 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000397 | 100027983216 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000398 | 100027983217 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000399 | 100027983218 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000400 | 100027983219 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-25 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000401 | 100027983227 | Cross Arm | HFTD Tier 2 | Distribution | 2025-07-31 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000402 | 100027983240 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000403 | 100027983243 | Cross Arm | HFTD Tier 2 | Distribution | 2025-08-06 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000404 | 100027983247 | Cross Arm | HFTD Tier 2 | Distribution | 2025-07-22 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000405 | 100027983248 | Cross Arm | HFTD Tier 2 | Distribution | 2025-07-16 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000406 | 100027983251 | Pole | HFTD Tier 2 | Distribution | 2025-08-01 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000407 | 100027983256 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000408 | 100027983275 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-15 | 2026-02-28 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000409 | 100027983276 | Pole | HFTD Tier 2 | Distribution | 2025-08-08 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000410 | 100027999801 | Other | Non-HFTD | Distribution | 2025-08-29 | 2028-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000411 | 100028000172 | Other | Non-HFTD | Distribution | 2025-08-29 | 2028-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000412 | 100028008019 | Insulator and Bushing | Non-HFTD | Distribution | 2025-09-04 | 2028-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000413 | 100028009642 | Insulator and Bushing | Non-HFTD | Distribution | 2025-09-04 | 2028-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000414 | 100028009643 | Switch | Non-HFTD | Distribution | 2025-09-04 | 2028-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000415 | 100028015420 | Pole | HFTD Tier 3 | Distribution | 2025-09-08 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000416 | 100028015421 | Pole | HFTD Tier 3 | Distribution | 2025-09-08 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000417 | 100028029792 | Pole | HFTD Tier 2 | Distribution | 2025-09-14 | 2026-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000418 | 100028035552 | Wood Pole | HFTD Tier 3 | Distribution | 2025-09-11 | 2026-03-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000419 | 100028040972 | Switch | Non-HFTD | Distribution | 2025-09-05 | 2028-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000420 | 100028041030 | Switch | Non-HFTD | Distribution | 2025-09-12 | 2028-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000421 | 100028062548 | Other | Non-HFTD | Distribution | 2025-09-12 | 2028-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000422 | 100028073627 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2026-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000423 | 100028077292 | Conductor | HFTD Tier 2 | Distribution | 2025-09-30 | 2026-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000424 | 100028077661 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-30 | 2026-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000425 | 100028077662 | Pole | HFTD Tier 2 | Distribution | 2025-09-30 | 2026-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000426 | 100028095624 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000427 | 100028095931 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000428 | 100028095933 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000429 | 100028096210 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | 2030-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000430 | 100028096432 | Other | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000431 | 100028096522 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000432 | 100028096583 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | 2030-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000433 | 100028096584 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000434 | 100028116494 | Avian Protection | HFTD Tier 2 | Distribution | 2025-10-13 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000435 | 100028122186 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-15 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000436 | 100028122187 | Pole | HFTD Tier 2 | Distribution | 2025-10-15 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000437 | 100028122369 | Conductor | HFTD Tier 2 | Distribution | 2025-10-15 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000438 | 100028122510 | Other | HFTD Tier 2 | Distribution | 2025-10-15 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000439 | 100028122511 | Pole | HFTD Tier 2 | Distribution | 2025-10-15 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000440 | 100028125082 | Other | HFTD Tier 2 | Distribution | 2025-09-02 | 2026-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000441 | 100028125087 | Pole | HFTD Tier 2 | Distribution | 2025-06-17 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000442 | 100028125089 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-06-17 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000443 | 100028125274 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000444 | 100028125275 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000445 | 100028125276 | Pole | HFTD Tier 2 | Distribution | 2025-04-09 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000446 | 100028125584 | Pole | HFTD Tier 2 | Distribution | 2025-04-08 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000447 | 100028125587 | Pole | HFTD Tier 2 | Distribution | 2025-04-10 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000448 | 100028125634 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000449 | 100028125720 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2026-11-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000450 | 100028125884 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-08-04 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000451 | 100028125885 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-08-04 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000452 | 100028125886 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-08-04 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000453 | 100028125900 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-08-06 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000454 | 100028125907 | Pole | HFTD Tier 2 | Distribution | 2025-07-30 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000455 | 100028125908 | Cross Arm | HFTD Tier 2 | Distribution | 2025-08-11 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000456 | 100028125932 | Other | HFTD Tier 2 | Distribution | 2025-08-13 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000457 | 100028125941 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-08-11 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000458 | 100028125956 | Pole | HFTD Tier 2 | Distribution | 2025-08-05 | 2026-10-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000459 | 100028126032 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-04-30 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000460 | 100028126117 | Switch | HFTD Tier 2 | Distribution | 2025-05-14 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000461 | 100028126159 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-05-30 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000462 | 100028126166 | Pole | HFTD Tier 2 | Distribution | 2025-06-11 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000463 | 100028126184 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-05-15 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000464 | 100028126191 | Pole | HFTD Tier 2 | Distribution | 2025-04-29 | 2026-07-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000465 | 100028126192 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-04-29 | 2026-06-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000466 | 100028126206 | Conductor | HFTD Tier 2 | Distribution | 2025-06-04 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000467 | 100028126248 | Pole | HFTD Tier 2 | Distribution | 2025-08-05 | 2026-08-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000468 | 100028136178 | Other | HFTD Tier 2 | Distribution | 2025-10-20 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000469 | 100028138532 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000470 | 100028138655 | Conductor | Non-HFTD | Distribution | 2025-10-16 | 2028-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000471 | 100028139098 | Other | HFTD Tier 2 | Distribution | 2025-10-20 | 2026-12-31 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000472 | 100028187874 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2027-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000473 | 100028208828 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-11-10 | 2027-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000474 | 100028278013 | Other | HFTD Tier 2 | Distribution | 2025-07-30 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000475 | 100028278014 | Other | HFTD Tier 2 | Distribution | 2025-07-30 | 2026-09-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000476 | 100028293743 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-26 | 2027-01-30 | Level 2 | [7 empty] | SDG&E | 2025 | 4
1130000477 | 100023598897 | Other | HFTD Tier 2 | Distribution | 2023-03-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000478 | 100023644150 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-04-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000479 | 100023644152 | Other | HFTD Tier 2 | Distribution | 2023-04-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000480 | 100023931625 | Avian Protection | HFTD Tier 2 | Distribution | 2023-05-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000481 | 100023965246 | Pole | HFTD Tier 2 | Distribution | 2023-06-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000482 | 100024173429 | Cross Arm | HFTD Tier 3 | Distribution | 2023-07-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000483 | 100024173440 | Cross Arm | HFTD Tier 3 | Distribution | 2023-07-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000484 | 100024226059 | Pole | HFTD Tier 2 | Distribution | 2023-07-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000485 | 100024226061 | Pole | HFTD Tier 2 | Distribution | 2023-07-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000486 | 100024226069 | Pole | HFTD Tier 2 | Distribution | 2023-07-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000487 | 100024243901 | Pole | HFTD Tier 2 | Distribution | 2023-07-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000488 | 100024335233 | Cross Arm | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000489 | 100024335234 | Other | HFTD Tier 2 | Distribution | 2023-08-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000490 | 100024351591 | Pole | HFTD Tier 2 | Distribution | 2023-08-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000491 | 100024351592 | Avian Protection | HFTD Tier 2 | Distribution | 2023-08-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000492 | 100024364235 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-08-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000493 | 100024533359 | Other | HFTD Tier 2 | Distribution | 2023-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000494 | 100024545430 | Pole | Non-HFTD | Distribution | 2023-09-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000495 | 100026683215 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000496 | 100026683216 | Other | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000497 | 100026683217 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000498 | 100026726329 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000499 | 100026789750 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000500 | 100026789753 | Transformer | HFTD Tier 2 | Distribution | 2024-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000501 | 100026797453 | Pole | HFTD Tier 3 | Distribution | 2024-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000502 | 100026804274 | Other | HFTD Tier 3 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000503 | 100026804275 | Pole | HFTD Tier 3 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000504 | 100026809033 | Pole | HFTD Tier 2 | Distribution | 2024-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000505 | 100026812834 | Pole | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000506 | 100026813443 | Other | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000507 | 100026813444 | Other | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000508 | 100026813445 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000509 | 100026843228 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000510 | 100026918033 | Pole | HFTD Tier 3 | Distribution | 2024-12-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000511 | 100026922431 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000512 | 100026935312 | Pole | HFTD Tier 2 | Distribution | 2024-12-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000513 | 100026939815 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000514 | 100027012941 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000515 | 100027012942 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000516 | 100027012943 | Other | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000517 | 100027012944 | Other | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000518 | 100027012945 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000519 | 100027012946 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000520 | 100027013160 | Cross Arm | HFTD Tier 3 | Distribution | 2024-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000521 | 100027016356 | Other | HFTD Tier 2 | Distribution | 2024-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000522 | 100027053944 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000523 | 100027053948 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000524 | 100027053949 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000525 | 100027053950 | Other | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000526 | 100027053951 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000527 | 100027060310 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000528 | 100027963437 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-08-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000529 | 100027963438 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000530 | 100027963439 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000531 | 100027978120 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000532 | 100027978125 | Pole | HFTD Tier 3 | Distribution | 2025-08-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000533 | 100027978126 | Pole | HFTD Tier 3 | Distribution | 2025-08-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000534 | 100027980876 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000535 | 100027980878 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000536 | 100027980879 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000537 | 100027981052 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000538 | 100027981053 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000539 | 100027981054 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000540 | 100027981055 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000541 | 100027981056 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000542 | 100027981057 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000543 | 100027981058 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000544 | 100027981059 | Other | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000545 | 100027983564 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000546 | 100027983567 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000547 | 100027983568 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000548 | 100027983791 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000549 | 100027983792 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000550 | 100027983794 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000551 | 100027983795 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000552 | 100027983796 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000553 | 100027983797 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000554 | 100027983799 | Other | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000555 | 100027983800 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000556 | 100027986301 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-08-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000557 | 100027986307 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000558 | 100027989609 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000559 | 100027989694 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000560 | 100027989695 | Pole | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000561 | 100027989699 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000562 | 100027989970 | Pole | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000563 | 100027989971 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000564 | 100027989972 | Pole | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000565 | 100027989974 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000566 | 100027990110 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000567 | 100028002790 | Pole | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000568 | 100028002791 | Pole | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000569 | 100028002794 | Pole | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000570 | 100028002795 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000571 | 100028002798 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000572 | 100028002803 | Other | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000573 | 100028002807 | Transformer | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000574 | 100028002808 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000575 | 100028002809 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000576 | 100028002815 | Anchor/Guy - Veg | HFTD Tier 3 | Distribution | 2025-09-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000577 | 100028010202 | Other | HFTD Tier 3 | Distribution | 2025-09-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000578 | 100028010203 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000579 | 100028010205 | Pole | HFTD Tier 3 | Distribution | 2025-09-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000580 | 100028010207 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000581 | 100028012287 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000582 | 100028012289 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000583 | 100028012960 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000584 | 100028012965 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000585 | 100028012966 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000586 | 100028012968 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000587 | 100028012971 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000588 | 100028012975 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000589 | 100028012976 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000590 | 100028012977 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000591 | 100028012978 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000592 | 100028012985 | Other | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000593 | 100028012986 | Other | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000594 | 100028012987 | Other | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000595 | 100028012988 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000596 | 100028012989 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000597 | 100028012990 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000598 | 100028012991 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000599 | 100028012993 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000600 | 100028012995 | Other | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000601 | 100028012996 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000602 | 100028015757 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000603 | 100028015760 | Pole | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000604 | 100028015762 | Other | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000605 | 100028015763 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000606 | 100028015764 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000607 | 100028015765 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000608 | 100028015766 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000609 | 100028015771 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000610 | 100028015773 | Pole | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000611 | 100028015774 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000612 | 100028015777 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000613 | 100028015778 | Other | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000614 | 100028015779 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000615 | 100028015780 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000616 | 100028015781 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000617 | 100028015782 | Pole | HFTD Tier 3 | Distribution | 2025-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000618 | 100028017935 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000619 | 100028017937 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000620 | 100028018481 | Other | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000621 | 100028018483 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000622 | 100028018485 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000623 | 100028018486 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000624 | 100028018487 | Ground Wire | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000625 | 100028018489 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000626 | 100028018490 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000627 | 100028018491 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000628 | 100028018492 | Other | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000629 | 100028018493 | Other | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000630 | 100028018494 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000631 | 100028018498 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000632 | 100028018499 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000633 | 100028018500 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000634 | 100028018501 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000635 | 100028018502 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000636 | 100028018503 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000637 | 100028018504 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000638 | 100028018505 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000639 | 100028018506 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000640 | 100028018507 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000641 | 100028018508 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000642 | 100028018510 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000643 | 100028018511 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000644 | 100028018512 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000645 | 100028018513 | Other | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000646 | 100028018515 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000647 | 100028021197 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000648 | 100028021199 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000649 | 100028021200 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000650 | 100028021201 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000651 | 100028021202 | Pole | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000652 | 100028021203 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000653 | 100028021208 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000654 | 100028021209 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000655 | 100028021212 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000656 | 100028021213 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000657 | 100028021214 | Other | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000658 | 100028021215 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000659 | 100028021216 | Other | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000660 | 100028021218 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000661 | 100028021219 | Pole | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000662 | 100028021220 | Other | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000663 | 100028021221 | Other | HFTD Tier 3 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000664 | 100028021222 | Transformer | HFTD Tier 2 | Distribution | 2025-09-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000665 | 100028025163 | Pole | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000666 | 100028025165 | Pole | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000667 | 100028025665 | Other | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000668 | 100028025667 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000669 | 100028025668 | Conductor | HFTD Tier 2 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000670 | 100028025672 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000671 | 100028025673 | Pole | HFTD Tier 2 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000672 | 100028025674 | Pole | HFTD Tier 2 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000673 | 100028025675 | Pole | HFTD Tier 2 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000674 | 100028025680 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000675 | 100028025683 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000676 | 100028025684 | Pole | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000677 | 100028025688 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000678 | 100028025692 | Pole | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000679 | 100028025693 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000680 | 100028025694 | Pole | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000681 | 100028025695 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000682 | 100028025696 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000683 | 100028025697 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000684 | 100028025698 | Pole | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000685 | 100028025701 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000686 | 100028025702 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000687 | 100028029125 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000688 | 100028029126 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000689 | 100028029127 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000690 | 100028029128 | Other | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000691 | 100028029129 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000692 | 100028029620 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000693 | 100028029621 | Other | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000694 | 100028029622 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000695 | 100028029623 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000696 | 100028029624 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000697 | 100028029628 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000698 | 100028029630 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000699 | 100028029631 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000700 | 100028029632 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000701 | 100028029633 | Other | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000702 | 100028029634 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000703 | 100028029635 | Pole | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000704 | 100028029637 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000705 | 100028029638 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000706 | 100028029641 | Other | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000707 | 100028029643 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000708 | 100028029650 | Other | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000709 | 100028029651 | Pole | HFTD Tier 3 | Distribution | 2025-09-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000710 | 100028033915 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000711 | 100028033917 | Pole | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000712 | 100028033918 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000713 | 100028033919 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000714 | 100028034442 | Other | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000715 | 100028034443 | Pole | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000716 | 100028034446 | Pole | HFTD Tier 2 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000717 | 100028034447 | Other | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000718 | 100028034456 | Pole | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000719 | 100028034457 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000720 | 100028034458 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000721 | 100028034460 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000722 | 100028034461 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000723 | 100028034462 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000724 | 100028034463 | Pole | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000725 | 100028034464 | Other | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000726 | 100028034465 | Pole | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000727 | 100028034466 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000728 | 100028034469 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000729 | 100028034471 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000730 | 100028034472 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000731 | 100028037423 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000732 | 100028037424 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000733 | 100028037426 | Pole | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000734 | 100028037427 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000735 | 100028037428 | Other | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000736 | 100028037429 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000737 | 100028037680 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000738 | 100028037682 | Pole | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000739 | 100028037687 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000740 | 100028037688 | Other | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000741 | 100028037691 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000742 | 100028037692 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000743 | 100028037693 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000744 | 100028037694 | Pole | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000745 | 100028037695 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000746 | 100028037696 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000747 | 100028037697 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000748 | 100028037698 | Other | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000749 | 100028037700 | Pole | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000750 | 100028037701 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000751 | 100028037704 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000752 | 100028037705 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000753 | 100028037706 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000754 | 100028037707 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000755 | 100028037709 | Other | HFTD Tier 2 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000756 | 100028037710 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000757 | 100028037711 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000758 | 100028040319 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000759 | 100028040322 | Other | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000760 | 100028040324 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000761 | 100028040326 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000762 | 100028040328 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000763 | 100028040332 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000764 | 100028040335 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000765 | 100028040336 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000766 | 100028040337 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000767 | 100028040338 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000768 | 100028040342 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000769 | 100028042487 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000770 | 100028042488 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000771 | 100028043100 | Pole | HFTD Tier 2 | Distribution | 2025-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000772 | 100028043101 | Pole | HFTD Tier 2 | Distribution | 2025-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000773 | 100028043102 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000774 | 100028043107 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000775 | 100028046391 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000776 | 100028046393 | Pole | HFTD Tier 3 | Distribution | 2025-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000777 | 100028046395 | Other | HFTD Tier 3 | Distribution | 2025-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000778 | 100028046396 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000779 | 100028046397 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000780 | 100028046660 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000781 | 100028046663 | Pole | HFTD Tier 3 | Distribution | 2025-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000782 | 100028050950 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000783 | 100028050952 | Other | HFTD Tier 2 | Distribution | 2025-09-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000784 | 100028050955 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000785 | 100028050957 | Capacitor Bank | Non-HFTD | Distribution | 2025-09-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000786 | 100028050958 | Insulator and Bushing | Non-HFTD | Distribution | 2025-09-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000787 | 100028050959 | Cross Arm | Non-HFTD | Distribution | 2025-09-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000788 | 100028050960 | Pole | Non-HFTD | Distribution | 2025-09-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000789 | 100028053612 | Other | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000790 | 100028053613 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000791 | 100028053614 | Pole | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000792 | 100028053615 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000793 | 100028053616 | Pole | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000794 | 100028053782 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000795 | 100028053785 | Other | Non-HFTD | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000796 | 100028053786 | Other | Non-HFTD | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000797 | 100028053787 | Other | Non-HFTD | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000798 | 100028053788 | Other | Non-HFTD | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000799 | 100028053789 | Other | Non-HFTD | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000800 | 100028053790 | Pole | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000801 | 100028053791 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000802 | 100028053793 | Pole | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000803 | 100028053794 | Pole | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000804 | 100028053796 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000805 | 100028053798 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000806 | 100028053799 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000807 | 100028060351 | Pole | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000808 | 100028060356 | Cross Arm | Non-HFTD | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000809 | 100028060357 | Insulator and Bushing | Non-HFTD | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000810 | 100028060358 | Cross Arm | Non-HFTD | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000811 | 100028060359 | Insulator and Bushing | Non-HFTD | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000812 | 100028060591 | Transformer | Non-HFTD | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000813 | 100028060592 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000814 | 100028060593 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000815 | 100028060594 | Pole | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000816 | 100028060597 | Pole | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000817 | 100028060604 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000818 | 100028060605 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000819 | 100028060606 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000820 | 100028060607 | Pole | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000821 | 100028060608 | Pole | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000822 | 100028060610 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000823 | 100028060612 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000824 | 100028060613 | Pole | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000825 | 100028060614 | Other | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000826 | 100028060616 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000827 | 100028068716 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000828 | 100028068717 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000829 | 100028068718 | Pole | HFTD Tier 3 | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000830 | 100028068719 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000831 | 100028068720 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000832 | 100028068721 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000833 | 100028068722 | Pole | HFTD Tier 3 | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000834 | 100028068723 | Cross Arm | Non-HFTD | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000835 | 100028068724 | Pole | Non-HFTD | Distribution | 2025-09-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000836 | 100028071595 | Pole | HFTD Tier 2 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000837 | 100028071598 | Other | HFTD Tier 2 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000838 | 100028071599 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000839 | 100028071920 | Pole | HFTD Tier 2 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000840 | 100028071922 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000841 | 100028071926 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000842 | 100028071927 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000843 | 100028071928 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000844 | 100028071929 | Pole | HFTD Tier 3 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000845 | 100028071932 | Pole | HFTD Tier 3 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000846 | 100028071934 | Conductor | HFTD Tier 3 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000847 | 100028071935 | Pole | HFTD Tier 3 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000848 | 100028071936 | Pole | HFTD Tier 3 | Distribution | 2025-09-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000849 | 100028074817 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000850 | 100028074818 | Pole | HFTD Tier 3 | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000851 | 100028075100 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000852 | 100028075101 | Other | HFTD Tier 2 | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000853 | 100028075103 | Pole | HFTD Tier 3 | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000854 | 100028075107 | Cross Arm | Non-HFTD | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000855 | 100028075108 | Cross Arm | Non-HFTD | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000856 | 100028075109 | Other | Non-HFTD | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000857 | 100028075110 | Anchor/Guy | Non-HFTD | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000858 | 100028075111 | Anchor/Guy | Non-HFTD | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000859 | 100028075112 | Pole | Non-HFTD | Distribution | 2025-09-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000860 | 100028085947 | Other | HFTD Tier 3 | Distribution | 2025-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000861 | 100028085950 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000862 | 100028085951 | Pole | HFTD Tier 3 | Distribution | 2025-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000863 | 100028085954 | Cross Arm | Non-HFTD | Distribution | 2025-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000864 | 100028085956 | Cross Arm | Non-HFTD | Distribution | 2025-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000865 | 100028085957 | Conductor - Veg | Non-HFTD | Distribution | 2025-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000866 | 100028085958 | Cross Arm | Non-HFTD | Distribution | 2025-09-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000867 | 100028088250 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000868 | 100028088251 | Other | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000869 | 100028088252 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000870 | 100028088253 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000871 | 100028088254 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000872 | 100028088255 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000873 | 100028088256 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000874 | 100028088257 | Other | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000875 | 100028088258 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000876 | 100028088259 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000877 | 100028088260 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000878 | 100028088261 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000879 | 100028088262 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000880 | 100028088264 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000881 | 100028088265 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000882 | 100028088266 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000883 | 100028088267 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000884 | 100028088268 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000885 | 100028088269 | Other | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000886 | 100028088270 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000887 | 100028088271 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000888 | 100028091693 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000889 | 100028091694 | Other | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000890 | 100028091695 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000891 | 100028091696 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000892 | 100028091698 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000893 | 100028091699 | Other | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000894 | 100028091822 | Pole | HFTD Tier 3 | Distribution | 2025-10-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000895 | 100028094845 | Other | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000896 | 100028094846 | Pole | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000897 | 100028094848 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000898 | 100028094849 | Pole | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000899 | 100028095150 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000900 | 100028095151 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000901 | 100028095152 | Other | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000902 | 100028095153 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000903 | 100028095155 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000904 | 100028095156 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000905 | 100028095157 | Pole | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000906 | 100028095158 | Pole | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000907 | 100028095159 | Other | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000908 | 100028098464 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000909 | 100028098465 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000910 | 100028098467 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000911 | 100028098469 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000912 | 100028098470 | Other | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000913 | 100028098471 | Other | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000914 | 100028098474 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000915 | 100028098475 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000916 | 100028098476 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000917 | 100028098477 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000918 | 100028098478 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000919 | 100028098479 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000920 | 100028098480 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000921 | 100028098482 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000922 | 100028098483 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000923 | 100028101025 | Pole | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000924 | 100028101026 | Pole | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000925 | 100028101028 | Ground Wire | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000926 | 100028101029 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000927 | 100028101300 | Pole | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000928 | 100028101301 | Other | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000929 | 100028101303 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000930 | 100028101304 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000931 | 100028101305 | Pole | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000932 | 100028101306 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000933 | 100028101307 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000934 | 100028101308 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000935 | 100028101309 | Pole | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000936 | 100028101316 | Pole | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000937 | 100028101317 | Other | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000938 | 100028101318 | Pole | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000939 | 100028101319 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000940 | 100028101325 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000941 | 100028103011 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000942 | 100028104727 | Pole | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000943 | 100028104728 | Pole | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000944 | 100028104729 | Pole | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000945 | 100028104910 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000946 | 100028104911 | Pole | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000947 | 100028104913 | Pole | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000948 | 100028104914 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000949 | 100028104916 | Pole | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000950 | 100028104918 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000951 | 100028104919 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000952 | 100028104921 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000953 | 100028104922 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000954 | 100028104923 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000955 | 100028104925 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000956 | 100028104927 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000957 | 100028104928 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000958 | 100028104931 | Pole | HFTD Tier 3 | Distribution | 2025-10-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000959 | 100028108550 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000960 | 100028108552 | Pole | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000961 | 100028108558 | Other | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000962 | 100028108559 | Pole | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000963 | 100028108560 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000964 | 100028108561 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000965 | 100028108562 | Other | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000966 | 100028108563 | Transformer | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000967 | 100028108564 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000968 | 100028108565 | Pole | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000969 | 100028108568 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000970 | 100028108569 | Pole | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000971 | 100028108571 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000972 | 100028108572 | Pole | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000973 | 100028108573 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000974 | 100028108574 | Pole | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000975 | 100028108575 | Pole | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000976 | 100028108577 | Pole | HFTD Tier 2 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000977 | 100028108581 | Other | HFTD Tier 3 | Distribution | 2025-10-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000978 | 100028111408 | Other | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000979 | 100028111409 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000980 | 100028111730 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000981 | 100028111731 | Pole | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000982 | 100028111735 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000983 | 100028111737 | Other | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000984 | 100028111739 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000985 | 100028111740 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000986 | 100028111741 | Pole | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000987 | 100028111742 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000988 | 100028111743 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000989 | 100028111744 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000990 | 100028111745 | Pole | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000991 | 100028111746 | Pole | HFTD Tier 3 | Distribution | 2025-10-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000992 | 100028116948 | Other | HFTD Tier 2 | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000993 | 100028117861 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000994 | 100028117862 | Other | HFTD Tier 2 | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000995 | 100028117863 | Pole | HFTD Tier 3 | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000996 | 100028117867 | Pole | Non-HFTD | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000997 | 100028117869 | Pole | Non-HFTD | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000998 | 100028117870 | Cross Arm | Non-HFTD | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130000999 | 100028117871 | Other | Non-HFTD | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001000 | 100028117872 | Insulator and Bushing | Non-HFTD | Distribution | 2025-10-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001001 | 100028119705 | Other | Non-HFTD | Distribution | 2025-10-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001002 | 100028119708 | Pole | HFTD Tier 3 | Distribution | 2025-10-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001003 | 100028119816 | Other | Non-HFTD | Distribution | 2025-10-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001004 | 100028123581 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001005 | 100028123582 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001006 | 100028123583 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001007 | 100028123585 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001008 | 100028123586 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001009 | 100028123587 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001010 | 100028123588 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001011 | 100028123589 | Ground Wire | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001012 | 100028123780 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001013 | 100028123784 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001014 | 100028123785 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001015 | 100028123786 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001016 | 100028123787 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001017 | 100028123788 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001018 | 100028123790 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001019 | 100028123791 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001020 | 100028123792 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001021 | 100028123793 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001022 | 100028123794 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001023 | 100028123795 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001024 | 100028123796 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001025 | 100028123797 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001026 | 100028123798 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001027 | 100028123799 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001028 | 100028123800 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001029 | 100028128374 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001030 | 100028128376 | Pole | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001031 | 100028128377 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001032 | 100028128650 | Pole | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001033 | 100028128651 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001034 | 100028128653 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001035 | 100028128654 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001036 | 100028128655 | Pole | HFTD Tier 3 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001037 | 100028128657 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001038 | 100028128659 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001039 | 100028128660 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001040 | 100028128661 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001041 | 100028128662 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001042 | 100028128666 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001043 | 100028128667 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001044 | 100028128668 | Pole | HFTD Tier 3 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001045 | 100028128669 | Pole | HFTD Tier 3 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001046 | 100028128670 | Pole | HFTD Tier 3 | Distribution | 2025-10-16 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001047 | 100028131482 | Other | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001048 | 100028131483 | Pole | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001049 | 100028131484 | Pole | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001050 | 100028131485 | Other | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001051 | 100028131486 | Pole | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001052 | 100028131487 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001053 | 100028131488 | Other | HFTD Tier 2 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001054 | 100028131490 | Other | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001055 | 100028131491 | Other | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001056 | 100028131492 | Pole | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001057 | 100028131493 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001058 | 100028131494 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001059 | 100028131497 | Pole | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001060 | 100028131498 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001061 | 100028131499 | Pole | HFTD Tier 3 | Distribution | 2025-10-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001062 | 100028137985 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001063 | 100028137986 | Transformer | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001064 | 100028137988 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001065 | 100028138190 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001066 | 100028138191 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001067 | 100028138192 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001068 | 100028138193 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001069 | 100028138194 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001070 | 100028138196 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001071 | 100028138198 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001072 | 100028138199 | Other | HFTD Tier 2 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001073 | 100028138200 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001074 | 100028138202 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001075 | 100028138203 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001076 | 100028146078 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001077 | 100028146090 | Pole | HFTD Tier 3 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001078 | 100028146091 | Pole | HFTD Tier 3 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001079 | 100028146093 | Other | HFTD Tier 3 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001080 | 100028146095 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001081 | 100028146097 | Other | HFTD Tier 3 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001082 | 100028146098 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001083 | 100028146103 | Pole | HFTD Tier 2 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001084 | 100028146104 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001085 | 100028146105 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001086 | 100028146106 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001087 | 100028146107 | Conductor - Veg | HFTD Tier 2 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001088 | 100028146108 | Pole | HFTD Tier 2 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001089 | 100028146112 | Pole | HFTD Tier 3 | Distribution | 2025-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001090 | 100028149210 | Other | HFTD Tier 3 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001091 | 100028149214 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001092 | 100028149215 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001093 | 100028149217 | Other | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001094 | 100028149218 | Pole | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001095 | 100028149219 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001096 | 100028149220 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001097 | 100028149221 | Pole | HFTD Tier 3 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001098 | 100028149222 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001099 | 100028149225 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001100 | 100028149226 | Other | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001101 | 100028149228 | Pole | HFTD Tier 3 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001102 | 100028149229 | Other | HFTD Tier 3 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001103 | 100028149230 | Pole | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001104 | 100028149231 | Pole | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001105 | 100028149232 | Transformer | HFTD Tier 2 | Distribution | 2025-10-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001106 | 100028158973 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001107 | 100028158974 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001108 | 100028158975 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001109 | 100028158976 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001110 | 100028158977 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001111 | 100028158978 | Other | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001112 | 100028160370 | Transformer | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001113 | 100028160371 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001114 | 100028160372 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001115 | 100028160373 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001116 | 100028160374 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001117 | 100028160375 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001118 | 100028160376 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001119 | 100028160377 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001120 | 100028160378 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001121 | 100028160379 | Other | HFTD Tier 3 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001122 | 100028160380 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001123 | 100028160381 | Pole | HFTD Tier 2 | Distribution | 2025-10-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001124 | 100028165574 | Other | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001125 | 100028165575 | Pole | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001126 | 100028165578 | Pole | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001127 | 100028165579 | Pole | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001128 | 100028166000 | Pole | HFTD Tier 2 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001129 | 100028166001 | Pole | HFTD Tier 2 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001130 | 100028166003 | Pole | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001131 | 100028166005 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001132 | 100028166006 | Other | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001133 | 100028166007 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001134 | 100028166008 | Pole | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001135 | 100028166009 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001136 | 100028166010 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001137 | 100028166012 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001138 | 100028166013 | Other | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001139 | 100028166015 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001140 | 100028166017 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001141 | 100028166018 | Other | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001142 | 100028166022 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001143 | 100028166023 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001144 | 100028166024 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001145 | 100028166025 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001146 | 100028169105 | Anchor/Guy - Veg | HFTD Tier 3 | Distribution | 2025-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001147 | 100028169106 | Other | HFTD Tier 3 | Distribution | 2025-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001148 | 100028169108 | Pole | HFTD Tier 3 | Distribution | 2025-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001149 | 100028169593 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001150 | 100028169594 | Other | HFTD Tier 2 | Distribution | 2025-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001151 | 100028169595 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001152 | 100028172029 | Pole | HFTD Tier 2 | Distribution | 2025-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001153 | 100028172120 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001154 | 100028176337 | Pole | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001155 | 100028176338 | Pole | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001156 | 100028176590 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001157 | 100028176591 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001158 | 100028176592 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001159 | 100028176593 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001160 | 100028176595 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001161 | 100028176596 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001162 | 100028176598 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001163 | 100028176599 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001164 | 100028176600 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001165 | 100028176601 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001166 | 100028176602 | Pole | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001167 | 100028176603 | Pole | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001168 | 100028176605 | Pole | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001169 | 100028176606 | Other | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001170 | 100028176607 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001171 | 100028176608 | Pole | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001172 | 100028176613 | Pole | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001173 | 100028176614 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001174 | 100028176617 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001175 | 100028176618 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001176 | 100028176619 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001177 | 100028176620 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001178 | 100028176621 | Other | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001179 | 100028176622 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001180 | 100028176623 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-30 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001181 | 100028183224 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001182 | 100028183225 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001183 | 100028183226 | Other | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001184 | 100028183228 | Other | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001185 | 100028184300 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001186 | 100028184303 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001187 | 100028184304 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001188 | 100028184305 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001189 | 100028184306 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001190 | 100028184307 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001191 | 100028184309 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001192 | 100028184310 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001193 | 100028184311 | Other | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001194 | 100028184313 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001195 | 100028184314 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001196 | 100028184315 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001197 | 100028184316 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001198 | 100028184317 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001199 | 100028184318 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001200 | 100028184319 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001201 | 100028184320 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001202 | 100028184321 | Other | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001203 | 100028184322 | Other | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001204 | 100028184323 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001205 | 100028184324 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001206 | 100028184325 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001207 | 100028188482 | Pole | HFTD Tier 3 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001208 | 100028188483 | Other | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001209 | 100028188484 | Other | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001210 | 100028188486 | Pole | HFTD Tier 3 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001211 | 100028188489 | Pole | HFTD Tier 3 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001212 | 100028188681 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001213 | 100028188682 | Pole | HFTD Tier 3 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001214 | 100028188685 | Pole | HFTD Tier 3 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001215 | 100028188686 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001216 | 100028188688 | Other | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001217 | 100028188689 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001218 | 100028188690 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001219 | 100028188691 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001220 | 100028188692 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001221 | 100028188693 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001222 | 100028188694 | Other | HFTD Tier 2 | Distribution | 2025-11-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001223 | 100028193061 | Other | HFTD Tier 2 | Distribution | 2025-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001224 | 100028193062 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001225 | 100028193063 | Other | HFTD Tier 3 | Distribution | 2025-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001226 | 100028193065 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001227 | 100028193068 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001228 | 100028193080 | Other | HFTD Tier 2 | Distribution | 2025-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001229 | 100028193082 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001230 | 100028197467 | Ground Wire | HFTD Tier 2 | Distribution | 2025-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001231 | 100028197468 | Transformer | HFTD Tier 2 | Distribution | 2025-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001232 | 100028197469 | Pole | HFTD Tier 3 | Distribution | 2025-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001233 | 100028198090 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001234 | 100028198091 | Pole | HFTD Tier 3 | Distribution | 2025-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001235 | 100028198094 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001236 | 100028198096 | Pole | HFTD Tier 3 | Distribution | 2025-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001237 | 100028198097 | Pole | HFTD Tier 3 | Distribution | 2025-11-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001238 | 100028201503 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001239 | 100028201504 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001240 | 100028201506 | Other | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001241 | 100028201507 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001242 | 100028201508 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001243 | 100028201509 | Transformer | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001244 | 100028201750 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001245 | 100028201753 | Other | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001246 | 100028201754 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001247 | 100028201755 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001248 | 100028201756 | Pole | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001249 | 100028201758 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001250 | 100028201759 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001251 | 100028201760 | Other | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001252 | 100028201761 | Other | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001253 | 100028201763 | Other | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001254 | 100028201764 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001255 | 100028207527 | Other | HFTD Tier 2 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001256 | 100028208040 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001257 | 100028208041 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001258 | 100028208042 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001259 | 100028208043 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001260 | 100028208044 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001261 | 100028208048 | Other | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001262 | 100028208050 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001263 | 100028208051 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001264 | 100028208053 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001265 | 100028208054 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-07 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001266 | 100028212010 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001267 | 100028212013 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001268 | 100028212014 | Other | HFTD Tier 2 | Distribution | 2025-11-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001269 | 100028212015 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-11-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001270 | 100028212017 | Other | HFTD Tier 3 | Distribution | 2025-11-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001271 | 100028212018 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-11-10 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001272 | 100028212726 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001273 | 100028212727 | Pole | HFTD Tier 3 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001274 | 100028212728 | Pole | HFTD Tier 3 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001275 | 100028212729 | Pole | HFTD Tier 3 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001276 | 100028213260 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001277 | 100028213262 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001278 | 100028213263 | Other | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001279 | 100028213264 | Pole | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001280 | 100028213265 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001281 | 100028213267 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001282 | 100028213271 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001283 | 100028213274 | Ground Wire | HFTD Tier 3 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001284 | 100028213275 | Other | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001285 | 100028213276 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001286 | 100028213277 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001287 | 100028213280 | Other | HFTD Tier 3 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001288 | 100028213281 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-11-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001289 | 100028216062 | Other | HFTD Tier 3 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001290 | 100028216063 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001291 | 100028216065 | Other | HFTD Tier 2 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001292 | 100028216068 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001293 | 100028216069 | Pole | HFTD Tier 2 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001294 | 100028216070 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001295 | 100028216071 | Pole | HFTD Tier 2 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001296 | 100028216072 | Other | HFTD Tier 2 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001297 | 100028216073 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001298 | 100028216074 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001299 | 100028218870 | Pole | HFTD Tier 3 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001300 | 100028218871 | Other | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001301 | 100028218872 | Other | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001302 | 100028218873 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001303 | 100028218874 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001304 | 100028218877 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001305 | 100028218879 | Transformer | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001306 | 100028218880 | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001307 | 100028218886 | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001308 | 100028218887 | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001309 | 100028218890 | Ground Wire | HFTD Tier 2 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001310 | 100028218891 | Pole | HFTD Tier 3 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001311 | 100028218892 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001312 | 100028218893 | Pole | HFTD Tier 3 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001313 | 100028218894 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001314 | 100028218895 | Pole | HFTD Tier 3 | Distribution | 2025-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001315 | 100028220303 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001316 | 100028220304 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001317 | 100028220305 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001318 | 100028220306 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001319 | 100028220307 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001320 | 100028220308 | Other | HFTD Tier 2 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001321 | 100028220309 | Other | HFTD Tier 2 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001322 | 100028220995 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001323 | 100028220996 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001324 | 100028220997 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001325 | 100028220998 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001326 | 100028220999 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001327 | 100028221000 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001328 | 100028221001 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001329 | 100028221002 | Ground Wire | HFTD Tier 2 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001330 | 100028221003 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001331 | 100028221004 | Pole | HFTD Tier 2 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001332 | 100028221005 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001333 | 100028225837 | Other | HFTD Tier 2 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001334 | 100028225838 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001335 | 100028226270 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001336 | 100028226272 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001337 | 100028226273 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001338 | 100028226275 | Other | HFTD Tier 2 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001339 | 100028226276 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001340 | 100028226277 | Other | HFTD Tier 3 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001341 | 100028226278 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001342 | 100028226280 | Other | HFTD Tier 3 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001343 | 100028226281 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001344 | 100028226283 | Other | HFTD Tier 2 | Distribution | 2025-11-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001345 | 100028228698 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001346 | 100028228699 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001347 | 100028228991 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001348 | 100028228992 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001349 | 100028228993 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001350 | 100028228994 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001351 | 100028228995 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001352 | 100028228996 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001353 | 100028228997 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001354 | 100028228998 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001355 | 100028228999 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001356 | 100028229000 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001357 | 100028229001 | Pole | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001358 | 100028229002 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001359 | 100028229003 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001360 | 100028229004 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001361 | 100028229005 | Pole | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001362 | 100028229008 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001363 | 100028229009 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001364 | 100028229010 | Other | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001365 | 100028229011 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001366 | 100028229012 | Pole | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001367 | 100028229013 | Pole | HFTD Tier 3 | Distribution | 2025-11-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001368 | 100028233165 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001369 | 100028233167 | Transformer | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001370 | 100028233168 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001371 | 100028233169 | Pole | HFTD Tier 2 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001372 | 100028234410 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001373 | 100028234411 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001374 | 100028234412 | Other | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001375 | 100028234414 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001376 | 100028234415 | Pole | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001377 | 100028234416 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001378 | 100028234417 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001379 | 100028234418 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001380 | 100028234419 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001381 | 100028234420 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001382 | 100028234421 | Pole | HFTD Tier 3 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001383 | 100028234422 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001384 | 100028234423 | Other | HFTD Tier 2 | Distribution | 2025-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001385 | 100028236778 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001386 | 100028236779 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001387 | 100028237010 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001388 | 100028237011 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001389 | 100028237012 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001390 | 100028237013 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001391 | 100028237014 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001392 | 100028237018 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001393 | 100028237021 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001394 | 100028237022 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001395 | 100028237023 | Pole | HFTD Tier 3 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001396 | 100028237024 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001397 | 100028237026 | Other | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001398 | 100028237029 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001399 | 100028237030 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001400 | 100028237031 | Other | HFTD Tier 3 | Distribution | 2025-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001401 | 100028239259 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001402 | 100028239583 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001403 | 100028239584 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001404 | 100028239585 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001405 | 100028239586 | Pole | HFTD Tier 2 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001406 | 100028239587 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001407 | 100028239588 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001408 | 100028239589 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001409 | 100028239590 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001410 | 100028239591 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001411 | 100028239593 | Other | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001412 | 100028239594 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001413 | 100028239598 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001414 | 100028239599 | Pole | HFTD Tier 2 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001415 | 100028239600 | Transformer | HFTD Tier 2 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001416 | 100028239603 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001417 | 100028239604 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001418 | 100028244356 | Pole | Non-HFTD | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001419 | 100028244357 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001420 | 100028259064 | Other | HFTD Tier 3 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001421 | 100028259066 | Other | HFTD Tier 3 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001422 | 100028259067 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001423 | 100028259069 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001424 | 100028259091 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001425 | 100028259092 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001426 | 100028259094 | Pole | HFTD Tier 3 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001427 | 100028259095 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001428 | 100028259098 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001429 | 100028259099 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001430 | 100028259100 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001431 | 100028259102 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001432 | 100028259103 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001433 | 100028259104 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001434 | 100028289561 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001435 | 100028289562 | Transformer | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001436 | 100028289563 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001437 | 100028289564 | Pole | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001438 | 100028289565 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001439 | 100028289566 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001440 | 100028289567 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001441 | 100028289568 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001442 | 100028289580 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001443 | 100028289581 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001444 | 100028289582 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001445 | 100028289583 | Other | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001446 | 100028289585 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001447 | 100028289586 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001448 | 100028289587 | Pole | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001449 | 100028289592 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001450 | 100028289593 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001451 | 100028289595 | Ground Wire | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001452 | 100028289597 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001453 | 100028289598 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001454 | 100028289599 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001455 | 100028293791 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001456 | 100028293794 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001457 | 100028293795 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001458 | 100028293796 | Pole | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001459 | 100028293797 | Pole | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001460 | 100028293798 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001461 | 100028293799 | Other | HFTD Tier 2 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001462 | 100028293940 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001463 | 100028293942 | Other | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001464 | 100028293943 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001465 | 100028293944 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001466 | 100028293946 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001467 | 100028293947 | Pole | HFTD Tier 3 | Distribution | 2025-11-26 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001468 | 100028316616 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001469 | 100028316617 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001470 | 100028316618 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001471 | 100028316619 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001472 | 100028316780 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001473 | 100028316781 | Pole | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001474 | 100028316783 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001475 | 100028316784 | Pole | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001476 | 100028316785 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001477 | 100028316786 | Ground Wire | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001478 | 100028316787 | Other | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001479 | 100028316788 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001480 | 100028316789 | Pole | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001481 | 100028316790 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001482 | 100028316791 | Other | HFTD Tier 3 | Distribution | 2025-12-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001483 | 100028329135 | Other | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001484 | 100028329136 | Pole | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001485 | 100028329137 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001486 | 100028329138 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001487 | 100028329139 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001488 | 100028329450 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001489 | 100028329452 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001490 | 100028329455 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001491 | 100028329456 | Other | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001492 | 100028329457 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001493 | 100028329458 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001494 | 100028329461 | Other | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001495 | 100028329462 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001496 | 100028329463 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001497 | 100028329465 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001498 | 100028329466 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001499 | 100028329467 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001500 | 100028329470 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001501 | 100028329472 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001502 | 100028329473 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001503 | 100028329475 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001504 | 100028329476 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001505 | 100028329477 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001506 | 100028329478 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001507 | 100028329480 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001508 | 100028329481 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001509 | 100028329482 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001510 | 100028329483 | Other | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001511 | 100028329484 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001512 | 100028329487 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001513 | 100028329488 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-05 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001514 | 100028332852 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001515 | 100028332853 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001516 | 100028332854 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001517 | 100028332855 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001518 | 100028332856 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001519 | 100028332857 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001520 | 100028332858 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001521 | 100028332859 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001522 | 100028333205 | Other | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001523 | 100028333208 | Conductor - Veg | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001524 | 100028333209 | Other | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001525 | 100028333210 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001526 | 100028333211 | Pole | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001527 | 100028333212 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001528 | 100028333213 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001529 | 100028333214 | Other | HFTD Tier 2 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001530 | 100028333215 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001531 | 100028333216 | Other | HFTD Tier 2 | Distribution | 2025-12-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001532 | 100028338129 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001533 | 100028338530 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001534 | 100028338532 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001535 | 100028338533 | Pole | HFTD Tier 3 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001536 | 100028338534 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001537 | 100028338539 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001538 | 100028338540 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001539 | 100028338541 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001540 | 100028338542 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001541 | 100028338543 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001542 | 100028338544 | Other | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001543 | 100028338545 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001544 | 100028338547 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001545 | 100028338549 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001546 | 100028338550 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001547 | 100028338551 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001548 | 100028338552 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-12-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001549 | 100028345844 | Pole | HFTD Tier 3 | Distribution | 2025-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001550 | 100028345846 | Other | HFTD Tier 3 | Distribution | 2025-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001551 | 100028345847 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001552 | 100028345848 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001553 | 100028345849 | Pole | HFTD Tier 3 | Distribution | 2025-12-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001554 | 100028396727 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001555 | 100028396728 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001556 | 100028396729 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001557 | 100028396830 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001558 | 100028396831 | Other | HFTD Tier 2 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001559 | 100028396832 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001560 | 100028396833 | Pole | HFTD Tier 2 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001561 | 100028396834 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001562 | 100028396835 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001563 | 100028396836 | Other | HFTD Tier 2 | Distribution | 2025-12-17 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001564 | 100028401899 | Other | HFTD Tier 2 | Distribution | 2025-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001565 | 100028402140 | Pole | HFTD Tier 2 | Distribution | 2025-12-18 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001566 | 100028404846 | Pole | HFTD Tier 2 | Distribution | 2025-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001567 | 100028404847 | Other | HFTD Tier 2 | Distribution | 2025-12-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001568 | P100380 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001569 | P100383 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001570 | P100383 | Pole | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001571 | P103782 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001572 | P10412 | Pole | HFTD Tier 2 | Distribution | 2022-07-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001573 | P111956 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001574 | P11541 | Cross Arm | Non-HFTD | Distribution | 2022-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001575 | P115849 | Pole | HFTD Tier 2 | Distribution | 2021-09-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001576 | P116900 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-01 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001577 | P117588 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001578 | P118555 | Other | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001579 | P119447 | Other | HFTD Tier 2 | Distribution | 2021-10-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001580 | P119492 | Other | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001581 | P119492 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001582 | P119686 | Other | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001583 | P119686 | Pole | HFTD Tier 2 | Distribution | 2022-05-31 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001584 | P128463 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001585 | P128463 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001586 | P13156 | Other | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001587 | P13285 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001588 | P165158 | Cross Arm | HFTD Tier 2 | Distribution | 2022-03-23 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001589 | P165224 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001590 | P165225 | Other | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001591 | P165225 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001592 | P165236 | Pole | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001593 | P175399 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001594 | P175417 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001595 | P190981 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001596 | P190982 | Pole | HFTD Tier 2 | Distribution | 2021-12-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001597 | P196358 | Cross Arm | Non-HFTD | Distribution | 2022-11-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001598 | P200150 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001599 | P210776 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001600 | P210777 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001601 | P214757 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001602 | P2157472131 | Insulator and Bushing | Non-HFTD | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001603 | P216391 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001604 | P217016 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001605 | P218684 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001606 | P218689 | Pole | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001607 | P233517 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001608 | P233518 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001609 | P271400 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001610 | P280407 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001611 | P28301 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001612 | P310970 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001613 | P311360 | Cross Arm | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001614 | P311360 | Pole | HFTD Tier 2 | Distribution | 2021-09-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001615 | P311811 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001616 | P311817 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001617 | P311818 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001618 | P311823 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001619 | P311823 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001620 | P311828 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001621 | P324293 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001622 | P371204 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001623 | P410119 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001624 | P41759 | Pole | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001625 | P41759 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001626 | P41759 | Other | HFTD Tier 2 | Distribution | 2021-07-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001627 | P417916 | Pole | HFTD Tier 2 | Distribution | 2022-06-22 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001628 | P42268 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001629 | P42269 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001630 | P42270 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001631 | P42272 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001632 | P42560 | Other | HFTD Tier 3 | Distribution | 2020-05-11 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001633 | P44922 | Cross Arm | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001634 | P44922 | Pole | HFTD Tier 2 | Distribution | 2021-08-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001635 | P45008 | Pole | HFTD Tier 2 | Distribution | 2021-07-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001636 | P46141 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001637 | P46141 | Pole | HFTD Tier 2 | Distribution | 2021-10-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001638 | P470088 | Pole | HFTD Tier 2 | Distribution | 2021-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001639 | P471899 | Pole | HFTD Tier 3 | Distribution | 2021-12-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001640 | P516887 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001641 | P576675 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001642 | P611872 | Cross Arm | HFTD Tier 2 | Distribution | 2021-12-29 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001643 | P618278 | Pole | HFTD Tier 2 | Distribution | 2022-11-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001644 | P618987 | Pole | HFTD Tier 2 | Distribution | 2021-09-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001645 | P62303 | Cross Arm | Non-HFTD | Distribution | 2022-10-12 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001646 | P678679 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001647 | P710353 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001648 | P710731 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-25 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001649 | P711449 | Pole | HFTD Tier 2 | Distribution | 2022-01-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001650 | P714801 | Pole | HFTD Tier 2 | Distribution | 2022-01-04 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001651 | P714994 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-14 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001652 | P776416 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-02-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001653 | P811934 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-19 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001654 | P812915 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-12-28 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001655 | P813699 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001656 | P815433 | Pole | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001657 | P815433 | Other | HFTD Tier 2 | Distribution | 2021-09-02 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001658 | P816370 | Pole | HFTD Tier 2 | Distribution | 2021-08-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001659 | P819071 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001660 | P819071 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001661 | P836813 | Cross Arm | Non-HFTD | Distribution | 2022-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001662 | P836813 | Cross Arm | Non-HFTD | Distribution | 2022-10-03 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001663 | P86042 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001664 | P86045 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001665 | P86051 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001666 | P86056 | Other | HFTD Tier 2 | Distribution | 2021-11-13 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001667 | P870522 | Pole | HFTD Tier 2 | Distribution | 2021-11-20 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001668 | P876928 | Pole | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001669 | P90093 | Cross Arm | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001670 | P90093 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001671 | P90093 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001672 | P90093 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2022-09-27 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001673 | P970731 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [8 empty] | Not Applicable | SDG&E | 2025 | 4
1130001674 | P972009 | Cross Arm | HFTD Tier 2 | Distribution | 2022-08-08 | [8 empty] | Not Applicable | SDG&E | 2025 | 4