## Q3 Removals
Correction | IaID | InitiativeFeature | InitiativeID | UMATID | AuditDate | ActivityDate | Result | Description | PerformedBy | Confidential | BusinessID | ProgramName | QuarterlyProgress | CumulativeProgress | ActivityInitiativeTrackingID | HFTDClass | WMPInitiativeActivity | ActivityProgramName | AssetID | WUI | CensusTract
Removed | WMP.505-{24C5B5E6-19FB-4A06-96C5-25365BEE367C} | Vegetation Management Project Point | 653-RY4356-TT | WMP.505 | 2025-09-18 | 2025-09-08 | Issues identified | Insufficient clearance obtained | Contractor | No | RY4356 | Quality assurance / quality control vegetation management | 1 | 32 | WMP.501 | Tier 2 | Quality assurance / quality control vegetation management | Clearance | {24C5B5E6-19FB-4A06-96C5-25365BEE367C} | Non-WUI | Rural
Removed | WMP.505-{3AC3032C-6154-405D-BE77-329CE9B1FDF6} | Vegetation Management Project Point | 387-FM10669-TT | WMP.505 | 2025-08-21 | 2025-06-13 | Issues identified | Insufficient clearance obtained | Contractor | No | FM10669 | Quality assurance / quality control vegetation management | 1 | 32 | WMP.501 | Tier 2 | Quality assurance / quality control vegetation management | Clearance | {3AC3032C-6154-405D-BE77-329CE9B1FDF6} | WUI | Rural
Removed | WMP.505-{5C6129E0-26E5-4B1E-A38F-F195F1D5A56B} | Vegetation Management Project Point | 653-AS1244-TT | WMP.505 | 2025-09-18 | 2025-09-08 | Issues identified | Poor Trimming Practices | Contractor | No | AS1244 | Quality assurance / quality control vegetation management | 1 | 32 | WMP.501 | Tier 2 | Quality assurance / quality control vegetation management | Clearance | {5C6129E0-26E5-4B1E-A38F-F195F1D5A56B} | Non-WUI | Rural
Removed | WMP.505-{A321956E-2792-48A0-8A89-3149F4E24E0B} | Vegetation Management Project Point | 380-JF3534-TT | WMP.505 | 2025-08-25 | 2025-07-24 | Issues identified | Poor Trimming Practices | Contractor | No | JF3534 | Quality assurance / quality control vegetation management | 1 | 32 | WMP.501 | Tier 2 | Quality assurance / quality control vegetation management | Clearance | {A321956E-2792-48A0-8A89-3149F4E24E0B} | WUI | Rural
Removed | WMP.505-{F0625EE6-3676-4664-8C8B-57B6EFC9152D} | Vegetation Management Project Point | 387-FM10728-TT | WMP.505 | 2025-08-21 | 2025-06-12 | Issues identified | Poor Trimming Practices | Contractor | No | FM10728 | Quality assurance / quality control vegetation management | 1 | 32 | WMP.501 | Tier 2 | Quality assurance / quality control vegetation management | Clearance | {F0625EE6-3676-4664-8C8B-57B6EFC9152D} | WUI | Rural