## 2025 FINAL AIR
Expense & Capital 2025 WMP Forecast vs Actual Overview
WMP CapEx / OpEx Category | WMP Category | WMP Initiative Activity | Utility Initiative Tracking ID | WMP Initiative Name | HFTD - 2025 Actual Expenditure (in 1,000s) | NHFTD - 2025 Actual Expenditure (in 1,000s) | Total 2025 Actual Expenditure (in 1,000s) | HFTD 2025 Planned Budget (in 1,000s) | NHFTD 2025 Planned Budget (in 1,000s) | Total 2025 Planned Budget (in 1,000s) | Variance % (Budget vs Actual) | Variance Threshold (+-10%) | Variance Explanation
Expense | Grid Design, Operations, and Maintenance | Asset Inspections | AI-02 | Detailed Inspection Transmission – Ground | 5801.474 | 0 | 5801.474 | 8499.97 | 0 | 8499.97 | -31.75% | Yes | Early training completions and favorable weather allowed for inspections to take place earlier in the year than anticipated. This allowed for resource optimization and a lower unit cost. In addition, the 2025 workplan was updated throughout the year, resulting in fewer units completed than planned.
Expense | Grid Design, Operations, and Maintenance | Asset Inspections | AI-04 | Detailed Inspection Transmission – Aerial | 16584.4499 | 0 | 16584.4499 | 22590.87 | 0 | 22590.87 | -26.59% | Yes | Favorability due to savings from renegotiating contract terms from hourly rates to unit-based rates.
Expense | Grid Design, Operations, and Maintenance | Asset Inspections | AI-05 | Detailed Inspection Transmission – Climbing | 3033.2903 | 0 | 3033.2903 | 1751.4 | 0 | 1751.4 | 73.19% | Yes | Operational circumstances required adding units to the workplan after budget-setting. Completing the incremental units entailed engaging more resources which resulted in higher unit costs as well.
Expense | Grid Design, Operations, and Maintenance | Asset Inspections | AI-06 | Perform transmission infrared inspections | 1398.7789 | 0 | 1398.7789 | 1549.38 | 0 | 1549.38 | -9.72% | No | Target met, work completed.
Expense | Grid Design, Operations, and Maintenance | Asset Inspections | AI-07 | Detailed Ground Inspections - Distribution | 36278.6294 | 0 | 36278.6294 | 40228.25 | 0 | 40228.25 | -9.818% | No | Target met, work completed.
Expense | Grid Design, Operations, and Maintenance | Asset Inspections | AI-08 | Supplemental Inspections - Substation Distribution | 1853.9554 | 0 | 1853.9554 | 2702.31 | 0 | 2702.31 | -31.39% | Yes | Process improvements reduced the need for overtime, double-time, travel and lodging, and fulltime employees.
Expense | Grid Design, Operations, and Maintenance | Asset Inspections | AI-09 | Supplemental Inspections - Substation Transmission | 2660.3538 | 0 | 2660.3538 | 1700.54 | 0 | 1700.54 | 56.44% | Yes | PG&E erroneously underfunded this activity during budget-setting. However, the Company identified the error in January and continued to execute the work in alignment with its WMP commitment.
Expense | Grid Design, Operations, and Maintenance | Asset Inspections | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 1036.5438 | 0 | 1036.5438 | 2150 | 0 | 2150 | -51.79% | Yes | Process improvements drove efficiencies in scheduling and inspection tool use. This allowed for more efficient execution of inspections and reduced overtime charges.
Expense | Enterprise Systems | Enterprise Systems Development | AI-11 | Filling Asset Inventory Data Gaps | 275.9482 | 409.6792 | 685.6274 | 375 | 2125 | 2500 | -72.57% | Yes | PG&E pivoted from utilizing manual install date collection methods (e.g. field collection, review of as built records) to using estimated ages. This resulted in significant cost savings.
Expense | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | GM-01 | Asset Inspections - Quality Assurance | 4527.069 | 0 | 4527.069 | 5067.58 | 0 | 5067.58 | -10.67% | Yes | Through resource optimization and early scheduling, PG&E reduced overtime, doubletime, and contractor costs.
Expense | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) | GM-02 | HFTD-HFRA Open Tag Reduction - Transmission | 654.5788 | 0 | 654.5788 | 838.53 | 0 | 838.53 | -21.94% | Yes | PG&E completed this work with fewer hours of labor than planned.
Expense | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) | GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | 532.14 | 0 | 532.14 | 600 | 0 | 600 | -11.31% | Yes | PG&E completed this work with lower unit costs than planned.
Expense | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | GM-09 | Asset Inspection – Quality Control | 17373.1837 | 0 | 17373.1837 | 21250.45 | 0 | 21250.45 | -18.25% | Yes | Through resource optimization and early scheduling, PG&E reduced overtime, doubletime, and contractor costs.
Expense | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | 5043.2165 | 0 | 5043.2165 | 12795 | 0 | 12795 | -60.58% | Yes | Generator Rebate Program variance is driven due to lower-than-anticipated application volume. The budget was developed with expectation that activity would remain consistent or exceed prior year levels.
Expense | Situational Awareness and Forecasting | Weather Forecasting | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | 1124.0885 | 0 | 1124.0885 | 3095.19 | 0 | 3095.19 | -63.68% | Yes | In-year changes of capital accounting guidance shifted actuals to capital orders which caused an underrun relative to the expense budget.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-01 | LiDAR Data Collection - Transmission | 3495.2995 | 7548.3007 | 11043.6002 | 2028.506 | 4380.6757 | 6409.1816 | 72.31% | Yes | PG&E recorded costs for LiDAR used in Second Patrol, Substation, and Integrated Vegetation Management to the orders supporting this initiative. In addition, costs for processing and analytic support were higher than planned.
Expense | Vegetation Management and Inspections | Pole Clearing | VM-02 | Pole Clearing Program | 20123.2862 | 12727.5115 | 32850.7976 | 16761.5492 | 10601.2908 | 27362.84 | 20.06% | Yes | The overrun for this activity was driven by increased units completed, additional focus on completion of 1254C work, and increased inspection volumes throughout the year compared to plan.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-03 | Focused Tree Inspection (FTI) | 99944.4727 | 1955.1263 | 101899.599 | 180434.1348 | 3529.6752 | 183963.81 | -44.61% | Yes | PG&E realized efficiencies for this program resulting in lower unit costs than planned. This allowed PG&E to balance overruns in the Distribution Routine and Second Patrol programs.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-04 | Tree Removal Inventory (TRI) | 29428.7792 | 0 | 29428.7792 | 70385.93 | 0 | 70385.93 | -58.19% | Yes | PG&E rebalanced its Vegetation Management work plan to align with areas with existing volumes of marked tree inventory. Underruns in the TRI program offset overruns in the Distribution Routine and Second Patrol programs.
Expense | Vegetation Management and Inspections | Defensible Space | VM-05 | Defensible Space Inspections - Distribution Substation | 2113.2315 | 0 | 2113.2315 | 2199.89 | 0 | 2199.89 | -3.939% | No | Target met, work completed.
Expense | Vegetation Management and Inspections | Defensible Space | VM-06 | Defensible Space Inspections - Transmission Substation | 1270.8048 | 0 | 1270.8048 | 1211.49 | 0 | 1211.49 | 4.896% | No | Target met, work completed.
Expense | Vegetation Management and Inspections | Defensible Space | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 1503.2022 | 0.14298 | 1503.3452 | 1550 | 0 | 1550 | -3.01% | No | Target met, work completed.
Expense | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | VM-08 | Vegetation Management – Quality Assurance | 9495.0043 | 0 | 9495.0043 | 10283.04 | 0 | 10283.04 | -7.663% | No | Target met, work completed.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-13 | Routine Ground - Transmission | 8720.49 | 18832.401 | 27552.8911 | 7848.2613 | 16948.7727 | 24797.034 | 11.11% | Yes | An increased contract presence for Vegetation Management Oversight Services, who perform safety observations and work competency assessments, caused an overrun in this program.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-14 | Transmission Second Patrol | 1871.9485 | 0 | 1871.9485 | 1151.8769 | 0 | 1151.8769 | 62.51% | Yes | To meet our target for the Transmission Second Patrol program, PG&E required LiDAR contracts that were incremental to its planned budget.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-15 | Integrated Vegetation Management - Transmission | 6593.2724 | 7088.5546 | 13681.827 | 7481.1815 | 8043.1628 | 15524.3443 | -11.87% | Yes | Unit cost efficiencies drove the underrun in this program.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-16 | Distribution Routine Patrol | 400002.321 | 485990.0534 | 885992.3744 | 336484.5911 | 408818.0389 | 745302.63 | 18.88% | Yes | The overrun for this activity was driven by increased units completed, increased pre-inspection work, and Blitz reliability work.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-17 | Distribution Second Patrol | 134103.0152 | 9283.7065 | 143386.7216 | 116462.2966 | 7577.8234 | 124040.12 | 15.6% | Yes | PG&E rebalanced its Vegetation Management work plan to align with areas with existing volumes of marked tree inventory. Underruns in other VM programs offset overruns in the Distribution Second Patrol program.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections | VM-18 | VM for Operational Mitigations (VMOM) | 10144.999 | 1183.3427 | 11328.3417 | 8785.1046 | 895.4514 | 9680.556 | 17.02% | Yes | Increased unit costs relative to plan caused an overrun in this program.
Expense | Enterprise Systems | Enterprise Systems Development | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | 4179.4743 | 11895.4269 | 16074.9012 | 7019.9948 | 19979.9852 | 26999.98 | -40.46% | Yes | Changes to capital accounting shifted planned OpEx to CapEx.
Expense | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | VM-22 | Vegetation Management - Quality Control | 24482.9524 | 0 | 24482.9524 | 26601.8 | 0 | 26601.8 | -7.965% | No | Target met, work completed.
Expense | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | Customer Support in Wildfire and PSPS Emergencies | 28411.8239 | 22547.6046 | 50959.4285 | 40232.7768 | 25266.8338 | 65499.6106 | -22.2% | Yes | Lower contract costs than planned reduced the overall spend for this activity.
Expense | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan |  | Emergency Preparedness and Recovery Plan | 3065.2325 | 8724.1231 | 11789.3556 | 2876.9156 | 8188.1444 | 11065.06 | 6.546% | No | Target met, work completed.
Expense | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination |  | External Collaboration and Coordination | 6832.382 | 19446.0102 | 26278.3922 | 6685.3258 | 19027.4656 | 25712.7914 | 2.2% | No | Target met, work completed.
Expense | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness |  | Public Communication, Outreach, and Education Awareness | 5840.4491 | 17107.6031 | 22948.0522 | 5997.0913 | 17704.5706 | 23701.6619 | -3.18% | No | Target met, work completed.
Expense | Grid Design, Operations, and Maintenance | Asset Inspections |  | Asset Inspections | 12314.7127 | 3551.0145 | 15865.7272 | 11597.391 | 2930.8422 | 14528.2332 | 9.206% | No | Target met, work completed.
Expense | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | Equipment Maintenance and Repair | 161534.9746 | 129281.2042 | 290816.1788 | 140463.533 | 157612.177 | 298075.71 | -2.435% | No | Target met, work completed.
Expense | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | Grid Design and System Hardening | 58209.9363 | 33297.3317 | 91507.268 | 51415.8822 | 37349.9978 | 88765.88 | 3.088% | No | Target met, work completed.
Expense | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | Grid Operations and Procedures | 91512.4318 | 19977.5703 | 111490.0021 | 113428.2736 | 33082.7764 | 146511.05 | -23.9% | Yes | Favorable weather and fewer outage events reduced helicopter standby, patrol, and SIPT costs. Additionally, PG&E received a credit from Los Angeles county for wildfire support.
Expense | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | Environmental Monitoring Systems | 3014.0093 | 753.5023 | 3767.5116 | 3231.472 | 807.868 | 4039.34 | -6.73% | No | Target met, work completed.
Expense | Situational Awareness and Forecasting | Fire Potential Index |  | Fire Potential Index | 145.5461 | 0 | 145.5461 | 173.72 | 0 | 173.72 | -16.22% | Yes | Internal efficiencies resulted in a small ($28k) variance relative to plan.
Expense | Situational Awareness and Forecasting | Ignition Detection Systems |  | Ignition Detection Systems | 13187.7467 | 14068.796 | 27256.5427 | 12310.2472 | 12912.9928 | 25223.24 | 8.061% | No | Target met, work completed.
Expense | Vegetation Management and Inspections | Activities Based on Weather Conditions |  | Activities Based on Weather Conditions | 1253.8526 | 1523.3909 | 2777.2435 | 0 | 0 | 0 |  | Yes | PG&E did not prepare a separate budget line item for Activities Based on Weather Conditions, but funds this work through the Routine Vegetation Management program.
Expense | Vegetation Management and Inspections | Vegetation Management Inspections |  | Vegetation Management Inspections | 0 | 3313.5043 | 3313.5043 | 0 | 3633.01 | 3633.01 | -8.795% | No | Target met, work completed.
Expense | Vegetation Management and Inspections | Wood and Slash Management |  | Wood and Slash Management | 27321.1998 | 2158.6546 | 29479.8545 | 29439.9059 | 2326.0541 | 31765.96 | -7.197% | No | Target met, work completed.
Expense | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | Wildfire Mitigation Strategy Development | 120688.6092 | 53048.2128 | 173736.822 | 102384.2972 | 50830.4868 | 153214.784 | 13.39% | Yes | Due to the structure of PG&E's accounting framework, there are certain wildfire-related costs that PG&E incurred, but which do not fit cleanly into other activities. Examples include miscellaneous EP&R costs, regulatory engagement costs, support from Aviation, our internal supply chain program, and corporate real estate. These are included here. Generally though, the overruns were driven by an increased need for support for equipment failure and extent of condition analyses, including Watch Duty professional licenses available for use in other internal organizations. California also entered a highly active wildfire season earlier than prior years and activated a task force to unify actions to address ignitions in high fire risk locations and exposure. PG&E also pursued incremental wildfire resilience efforts including grants and partnerships.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | GH-01 | System Hardening - Distribution | 283952.0136 | 0 | 283952.0136 | 248939.5443 | 0 | 248939.5443 | 14.06% | Yes | PG&E hardened a greater number of overhead circuit miles than it had budgeted.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | GH-04 | 10K Undergrounding | 1191461.3071 | 19065.412 | 1210526.7191 | 1206822.1924 | 6000.0026 | 1212822.195 | -0.1893% | No | Target met, work completed.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | GH-05 | System Hardening - Transmission | 9331.2192 | 0 | 9331.2192 | 21516.6 | 0 | 21516.6 | -56.63% | Yes | PG&E significantly reduced costs for work at Foresthill Substation by eliminating the need for approximately $10M of primary generation.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | GH-06 | System Hardening - Transmission Shunt Splices | 3572.7085 | 0 | 3572.7085 | 4673.554 | 0 | 4673.554 | -23.55% | Yes | Transitioning to internal M&C crews from contractors resulted in savings for this work.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | GH-08 | Surge Arrestor - Removals | 1868.0001 | 0 | 1868.0001 | 800 | 0 | 800 | 133.5% | Yes | PG&E exceeded its planned budget for this activity because a population of surge arrester installations required quality assurance and documentation remediation. Significant rework by field and clerical teams was necessary to ensure auditable and accurate records.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | GH-10 | Non-Exempt Expulsion Fuse - Removal | 8199.5857 | 0 | 8199.5857 | 5484.8923 | 0 | 5484.8923 | 49.49% | Yes | PG&E needed to add additional units to its workplan post-budget-setting to meet its WMP commitment.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | GH-11 | System Hardening – Transmission Conductor Segment Replacement | 1031.1696 | 0 | 1031.1696 | 1111.908 | 0 | 1111.908 | -7.261% | No | Target met, work completed.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | GM-06 | EPSS - Down Conductor Detection (DCD) | 33977.4162 | 0 | 33977.4162 | 31258.68 | 0 | 31258.68 | 8.698% | No | Target met, work completed.
Capital | Situational Awareness and Forecasting | Grid Monitoring Systems | SA-02 | Line Sensor - Installations | 1834.0009 | 0 | 1834.0009 | 2349.25 | 0 | 2349.25 | -21.93% | Yes | PG&E met its WMP commitment to install line sensors on 40 circuits with fewer installations than originally forecasted.
Capital | Situational Awareness and Forecasting | Weather Forecasting | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | 2506.4596 | 0 | 2506.4596 | 1765.8 | 0 | 1765.8 | 41.94% | Yes | To reduce the unit cost of 2026 installations, PG&E pre-ordered additional weather station kits resulting in higher spend than planned for this activity.
Capital | Situational Awareness and Forecasting | Grid Monitoring Systems | SA-10 | Distribution Fault Anticipation (DFA) Installations | 3153.9303 | 0 | 3153.9303 | 2861.3 | 0 | 2861.3 | 10.23% | Yes | PG&E required additional units to achieve its Eyes-on-Risk target.
Capital | Situational Awareness and Forecasting | Grid Monitoring Systems | SA-11 | Early Fault Detection (EFD) Installations | 7346.9185 | 0 | 7346.9185 | 6676.62 | 0 | 6676.62 | 10.04% | Yes | PG&E erroneously underfunded this activity during budget-setting. However, the Company identified the error and executed the work in alignment with its WMP commitment.
Capital | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies |  | Customer Support in Wildfire and PSPS Emergencies | 7787.4984 | 995.6894 | 8783.1877 | 6959.5044 | 169.3856 | 7128.89 | 23.21% | Yes | Target met, work completed.
Capital | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair |  | Equipment Maintenance and Repair | 437625.0907 | 815116.3107 | 1252741.4014 | 435139.9013 | 580518.1187 | 1015658.02 | 23.34% | Yes | PG&E utilized prior-year spending trends to forecast for this category of work, but inspection findings and constraints in outage scheduling resulted in higher spend.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | Grid Design and System Hardening | 823224.7529 | 371989.6089 | 1195214.3618 | 922548.8466 | 138763.7928 | 1061312.6395 | 12.62% | Yes | PG&E completed additional units in support of the GM-03 Commitment to eliminate backlog tags.
Capital | Grid Design, Operations, and Maintenance | Grid Operations and Procedures |  | Grid Operations and Procedures | 35449.1817 | 330.4066 | 35779.5883 | 62072.5248 | 165.7552 | 62238.28 | -42.51% | Yes | Material delays and resource constraints caused work deferrals.
Capital | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | Risk Methodology and Assessment (Initiative) | 2804.5073 | 7982.0592 | 10786.5665 | 1849.367 | 5263.583 | 7112.95 | 51.65% | Yes | Overrun driven by increased internal labor and associated overheads for the WMP Risk Modeling team.
Capital | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | Environmental Monitoring Systems | 1717.8082 | 429.452 | 2147.2602 | 1141.376 | 285.344 | 1426.72 | 50.5% | Yes | To reduce the unit cost of 2026 installations, PG&E pre-ordered additional weather station kits resulting in higher spend than planned for this activity.
Capital | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | Covered conductor installation | 1546.5119 | 1703.7551 | 3250.267 | 649.9922 | 1849.9778 | 2499.97 | 30.01% | Yes | PG&E completed a volume of overhead miles completed relative to plan.
Expense | Vegetation Management and Inspections | Defensible Space |  | Defensible space | 690.7853 | 0 | 690.7853 | 495.01 | 0 | 495.01 | 39.55% | Yes | Due to internal controls on recording costs to certain memorandum accounts such as the Fire Risk Mitigation Memorandum Account (FRMMA), budget for this work could not be established until a governance panel approved the accounting treatment. This occurred in 2025 after budget-setting.
Expense | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | Covered conductor installation | 106.3401 | 302.6604 | 409.0005 | 0 | 0 | 0 |  | No
Expense | Situational Awareness and Forecasting | Grid Monitoring Systems |  | Grid Monitoring Systems | 5418.297 | 0 | 5418.297 | 36317.9 | 0 | 36317.9 | -16.35% | Yes | Favorability in PG&E's contracts for this work reduced spending relative to plan.
Capital | Situational Awareness and Forecasting | Grid Monitoring Systems |  | Grid Monitoring Systems | 25862.4199 | 0 | 25862.4199 | 0 | 0 | 0 |  | No | New Continuous Monitoring work that was not part of original Planned Budget
Expense | Risk Methodology and Assessment | Risk Methodology and Assessment (Initiative) |  | Risk Methodology and Assessment (Initiative) | 17.0887 | 48.6372 | 65.7259 | 0 | 0 | 0 |  | No | Target met, work completed.
Capital | Wildfire Mitigation Strategy | Wildfire Mitigation Strategy Development |  | Wildfire Mitigation Strategy Development | 2387.9142 | 10293.8106 | 12681.7248 | 10667.9541 | 1474.0504 | 12142.0045 | 4.445% | No | Target met, work completed.
Capital | Enterprise Systems | Enterprise Systems Development |  | Enterprise Systems Development | 44792.138 | 0 | 44792.138 | 42433.3165 | 0 | 42433.3165 | 5.559% | No | Target met, work completed.