## Tab 1 - Overview tab
IE ARC Attachments
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | LS Power Grid
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted
Tab 5 | List of Failed-to-Fund Initiatives - All initiatives funded less than 100%

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | LS Power Grid
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC ARC) | EC-Claimed Progress | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | Initiative Validation Rate (%) | IE Finding on Initiative | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | LSP-01 | 8.3.4 | Implement Hot Work Programs | Focus & non-field verifiable | Implement Hot Work Programs for Consruction and Maintenance operations | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | Training Documents & Logs (DR006) | N/A | N/A | 0 | 0 | 0% |  | N/A | N/A | N/A
Grid Design Operations and Maintenance | LSP-02 | 8.2 | Implement Substation Inspection Programs | Focus & non-field verifiable | Implement a monthly Substation Inspection program | N/A | N/A | N/A | N/A | Target not met | Delayed due to Construction Timeline | N/A | N/A | LSPG Written Response (DR007) | N/A | N/A | 0 | 0 | 0% |  | N/A | N/A | N/A
Grid Design Operations and Maintenance | LSP-03 | 8.1.7 | Enhance Use of Computer Management Systems (CMMS) | Focus & non-field verifiable | Review and enhance Computer Management Systems | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% |  | N/A | N/A | N/A
Vegetation Management and Inspections | LSP-04 | 7.2.1 | Establish Risk Based Buffer Zones & Implement Monthly Substation Inspections | Focus & non-field verifiable | Implement monthly Substation Inspections and establish/maintain risk-based vegetation buffer zones | N/A | N/A | N/A | N/A | Target not met | Delayed due to Construction Timeline | N/A | N/A | N/A | N/A | N/A | 0 | 6125 |  | Overspend | Weed Abatement at the Orchard Substation | N/A | N/A
Situational Awareness and Forecasting | LSP-05 | 7.2.1 | Integrate StormGeo | Focus & non-field verifiable | Utilize StormGeo as a real-time weatherm monitoring and forecasting system | N/A | N/A | N/A | N/A | Target met | N/A | N/A | N/A | Purchase Order & Operation Plan (DR010) | N/A | N/A | 10000 | 1082.5 | -89% | Underspend | Less to implement than anticipated | N/A | N/A
Situational Awareness and Forecasting | LSP-06 | 8.3.2 | Install Substation Cameras | Focus & non-field verifiable | Install 24/7 cameras at Orchard and Fern Substation | 64 | 29 | 29 | 29 |  | N/A | N/A | N/A | LSPG Written Response & Purchase Orders (DR011) | N/A | Initiative Validated | 0 | 0 | 0% |  | N/A | N/A | N/A
Situational Awareness and Forecasting | LSP-07 | 8.3.2 | Evaluate and Enhance Use of Live Video | Focus & non-field verifiable | Review and enhance practices related to the use of video capability | N/A | N/A | N/A | N/A | Target not met | Delayed due to Construction Timeline | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% |  | N/A | N/A | N/A
Emergency Preparedness | LSP-08 | 8.4.3 | Integrate Into Local Dispatch Systems | Focus & non-field verifiable | Establish contact with local fire and safety agencies to ensure site location access information are integrated into relevant dispatch systems | Integrate into Local dispatch system | N/A | N/A | N/A | Target met | N/A | N/A | N/A | LSPG Written Response & Email Correspondence (DR013) | N/A | Initiative Validated | 20000 | 2416.2 | -87% | Underspend | Less to implement than anticipated | N/A | N/A
Emergency Preparedness | LSP-09 | 8.5.4 | Establish Annual Contact with Local Fire Agencies | Focus & non-field verifiable | Conduct annual visits with fire agencies to each site | 2 | 6 | 6 | 6 |  | N/A | N/A | N/A | LSPG Written Response & Email Correspondence (DR014) | N/A | Initiative Validated | 0 | 0 | 0% |  | N/A | N/A | N/A
Emergency Preparedness | LSP-10 | 8.4.2 | Formalized Review with Benchmarking | Focus & non-field verifiable | Conduct a formalized review of emergency procedures with benchmarking | 1 | 1 | 1 | 1 |  | N/A | N/A | N/A | LSPG Written Response, Emergency Operation Plan, and Plan Review Checklist (DR015) | N/A | Initiative Validated | 0 | 0 | 0% |  | N/A | N/A | N/A
Community Outreach and Engagement | LSP-11 | 8.5.5 | Best Practice Sharing | Focus & non-field verifiable | Share best practices with other utilities and local fire and safety agencies | 2 | N/A | N/A | N/A |  | N/A | N/A | N/A | Wildfire Conference PPT, Notes, and LSPG Written Response (DR016) | N/A | Initiative Validated | 20000 | 3522.38 | -82% | Underspend | Less to implement than anticipated | N/A | N/A
Note on K11: Number of "actuals" from which samples are selected

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | LS Power Grid
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2025-04-23 | 2025-04-30 | QA/QC Docs. | LSP_DR001 | LSP_DR0001 Ampirical EPC QA-QC Plan TTR QA QC Manual Siemens_LS Power_Fern Rd_Qualty Plan Siemens_LS Power_Orchard_Qualty Plan
2025-04-23 | 2025-05-05 | QA/QC SME Requests | LSP_DR002 | LSP_DR0002
2025-04-23 | 2025-04-30 | Financial Docs./ SME Request | LSP_DR003 | LSP_DR0003 WMP Financial Evaluation
2025-04-28 | 2025-05-05 | SME Interviews Questions | LSP_DR004 | LSPGC_DR004 LS_Power_SME_Role_Mapping
2025-06-10 | 2025-06-18 | LSP-01; LSP-05: LSP-06 | LSP_DR005 | LSP_DR005 Response Rev1 06.18.25
2025-04-23 | 2025-04-30 | LSP-01 | LSP_DR006 | LSP_DR006 1-Gates_WEAP Training_09122022 2-220909 Orchard Substation_CFPP 3-TTRS Orchard Fire Prevention Plan 4-Fern Road Sub WEAP 5-Fern Rd-Round Mountain_CFPP_20230616 6-TTR Substations Fire Prevention Plan Fern Road Substation 4.12.2024 7-TTR Substations Fire Prevention Plan Fern Road Substation 6.14.2024 8-TTR Welding, Cutting, and Hot Work 9-Orchard Sub_WEAP Logs_2024_Scanned Docs 10-Fern Road Sub_WEAP Logs_2024_Scanned Docs
2025-04-23 | 2025-04-30 | LSP-02 | LSP_DR007 | LSP_DR007
2025-04-23 | 2025-04-30 | LSP-05 | LSP_DR010 | LSP_DR010 LSPGC EOP-011 Emergency Operations Plan v.1 PO 3546
2025-04-23 | 2025-04-30 | LSP-06 | LSP_DR011 | LSP_DR011 LSP10116 LSP10121
2025-04-23 | 2025-04-30 | LSP-08 | LSP_DR013 | LSP_DR013 _ext_ Re_ Fern Road Project - File 96_90_12 - 01112024 - Correspondence - External - CAL Fire Access Coordination.msg FW_ Fresno County Fire Huron station 93.msg
2025-04-23 | 2025-04-30 | LSP-09 | LSP_DR014 | LSP_DR014 Fire Agency Visit Log Orchard Substation Public Safety Outreach_Training.msg RE_ Ls-Power Public Safety Outreach.msg _ext_ RE_ BCOM23-0011 + BCOM23-0012.msg _ext_ Re_ Fern Road Project - File 96_90_12 - 01112024 - Correspondence - External - CAL Fire Access Coordination.msg Fern Road Project - File 96_90_12 - 09092024 - Correspondence - External - Transformer Deliveries.msg
2025-04-23 | 2025-04-30 | LSP-10 | LSP_DR015 | LSP_DR015 LSPGC EOP-011 Emergency Operations Plan v.1 RC0410A
2025-04-23 | 2025-04-30 | LSP-11 | LSP_DR016 | LSP_DR016 SDGE Shaun Gahagan EUCI 020624 EUCI Conference 2_6_24 - SDGE PSPS - Nisha Menon DRAFT_PGE_10K UG Program_2024 Wildfire Mitigation for Utilities Conference_20240130 LSP_DR016

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | LS Power Grid
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2024-05-01 | 8.1.2.1 - GH-01 | SME001 | Director of Wildfire Mitigation | Overview of funding verification with slide presentation covering financial assumptions; cost model assmption; major elements of cost models; planning order fields; and overview of 2023 spend high-level drivers | <-- Example

## Tab 5 - List of "Fail-to-Fund"
List of Failed-to-Fund Initiatives
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | LS Power Grid
WMP Category | WMP Section Number | WMP Page Number | Initiative Tracking ID | Initiative Name | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%)
Situational Awareness and Forecasting | 7.2.1 | 94 | LSP-05 | Integrate StormGeo | 10000 | 1082.5 | -89%
Emergency Preparedness | 8.4.3 | 155 | LSP-08 | Integrate Into Local Dispatch Systems | 20000 | 2416.2 | -87%
Community Outreach and Engagement | 8.5.5 | 178 | LSP-11 | Best Practice Sharing | 20000 | 3522.38 | -82%
Note on E11: Kopunova, Sara: If applicable since some commitments occur outside of initiatives