## Tab 1 - Overview tab
IE ARC Attachments
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Trans Bay Cable
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted
Tab 5 | List of Failed-to-Fund Initiatives - All initiatives funded less than 100%

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Trans Bay Cable
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC ARC) | EC-Claimed Progress | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | Initiative Validation Rate (%) | IE Finding on Initiative | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | 002 | 8.1.2 | Compressed Gas Cylinder Housing | Focus & field verifiable | Complete Compressed Gas Cylinder Housing project | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Initiative validated | 27200 | 35800 |  | Overspend | Spillover costs from 2023 to close out project | N/A | N/A
Grid Design Operations and Maintenance | 007 | 8.1.2 | Spare Parts Building Suppression System | Focus & field verifiable | Complete the Spare Parts Building Suppressions System | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | Initiative validated | 27200 | N/A | N/A | N/A | N/A | N/A | N/A
Note on K11: Number of "actuals" from which samples are selected

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Trans Bay Cable
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2025-04-23 | 2025-05-07 | QA/QC Documents | TBC_DR001 | Compressed Gas Cylinder Cage.jpg System Record of Completion - Spare Parts Building Suppression
2025-06-12 | 2025-06-20 | Financials | TBC_DR002 | TBC - Response to TBC_DR002.pdf TBC-HS-200_Emergency_Action_Plan_R6_2020-12-02 Confidential.pdf TBC-OP-04_Emergency_Operations_R13.1_2021-07-01 Confidential.pdf
2025-04-30 | 2025-05-07 | GM/Finances/VM | TBC_DR004 | 2024-01-31 PI MIOW; 2024-02-26 PI MIOW; 2024-03-28 PI MIOW; 2024-04-30 PI MIOW; 2024-05-21 PI MIOW; 2024-06-26 PI MIOW; 2024-07-22 PI MIOW; 2024-08-21 PI MIOW ; 2024-09-30 PI MIOW; 2024-10-23 PI MIOW; 2024-11-25 PI MIOW; 2024-12-30 PI MIOW; 2024-04-12 PI IOW; 2024-04-12 PI IOW; 2024-04-18 PI IOW; 2024-04-23 PI IOW; 2024-04-30 PI IOW; 2024-05-06 PI IOW; 2024-05-14 PI IOW; 2024-05-21 PI IOW; 2024-05-28 PI IOW; 2024-06-04 PI IOW; 2024-06-14 PI IOW; 2024-06-18 PI IOW; 2024-06-26 PI IOW; 2024-07-03 PI IOW; 2024-07-09 PI IOW; 2024-07-15 PI IOW; 2024-07-22 PI IOW; 2024-07-29 PI IOW; 2024-08-08 PI IOW; 2024-08-14 PI IOW; 2024-08-19 PI IOW; 2024-08-29 PI IOW; 2024-09-06 PI IOW; 2024-09-13 PI IOW; 2024-09-19 PI IOW; 2024-09-24 PI IOW; 2024-10-02 PI IOW; 2024-10-08 PI IOW; 2024-10-16 PI IOW; 2024-10-23 PI IOW; 2024-10-28 PI IOW; 2024-11-06 PI IOW; 2024-11-11 PI IOW; 2024-11-18 PI IOW; 2024-11-25 PI IOW; 2024-12-04 PI IOW; 2024-12-12 PI IOW; 2024-12-17 PI IOW; 2024-12-27 PI IOW; 2024-12-30 PI IOW Trans Bay Cable - Response to BV DR_004 Item #2 2024-03-06 PI VEGETATION QUARTERLY; 2024-05-28 PI VEGETATION QUARTERLY; 2024-08-16 PI VEGETATION QUARTERLY; 2024-10-28 PI VEGETATION QUARTERLY
2025-04-30 | 2025-05-01 | SA/EP/CO | TBC_DR005 | Trans Bay Cable - Response to BV DR_005 Item #1 TBC-HS-200_Emergency_Action_Plan_R6_2020-12-02 TBC-OP-022_Extreme_Weather_Earthquake_Procedure_R1_05_30_2024 TBC_EOP-005 Approval Letter 2024-05 TBC-OP-004_Emergency_Operations_R14_EOP-011_05_03_2024 TBC-OP-008_System_Restoration_R3.4_2024-07-01_EOP005
2025-04-23 | 2025-05-01 | 002 | TBC_DR006 | Image (3)
2025-04-23 | 2025-05-01 | 007 | TBC_DR007 | System Record of Completion - Spare Parts Building Suppression
2025-05-05 | 2025-05-08 | SME Questions | TBC_DR008 | TBC_SME_Interview_Questions_QAQC_DR008

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Trans Bay Cable
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2024-05-01 | 8.1.2.1 - GH-01 | SME001 | Director of Wildfire Mitigation | Overview of funding verification with slide presentation covering financial assumptions; cost model assmption; major elements of cost models; planning order fields; and overview of 2023 spend high-level drivers | <-- Example

## Tab 5 - List of "Fail-to-Fund"
List of Failed-to-Fund Initiatives
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Trans Bay Cable
WMP Category | WMP Section Number | WMP Page Number | Initiative Tracking ID | Initiative Name | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%)
Grid Design Operations and Maintenance | 8.1.2.3 | 87 | SH-01 | Pole replacement | 10000 | 9000 | 10% | <-- Example
Note on E11: Kopunova, Sara: If applicable since some commitments occur outside of initiatives