## Tab 1 - Overview tab
IE ARC Attachments
Independent Evaluator: | NV5 / Guidehouse / JH Land Consultants
Electrical Corporation: | PacifiCorp
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted
Tab 5 | List of Failed-to-Fund Initiatives - All initiatives funded less than 100%

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: | NV5 / Guidehouse / JH Land Consultants
Electrical Corporation: | PacifiCorp
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC ARC) | EC-Claimed Progress | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | Initiative Validation Rate (%) | IE Finding on Initiative | WMP - Planned Spend (Thousands $) | EC-Claimed Actual Spend (Thousands $) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | GH-01 | 8.1.2.1 | Line Rebuild - Covered Conductor Installation | Focus & field verifiable | Count of line-miles of covered conductor installed in 2024 | 80 | 72 | 72 | 72 | Target not met | Project delays | 31 | 100% | Field & Desktop | 90% | Initiative not validated | 62313 | 115739 | 85.74% | Overspend | Costs increased due to bringing on a construction project management company to manage the system hardening projects. Incremental costs include field engineering support, post construction inspections, extended warranty, etc. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | GH-02 | 8.1.2.3 | Distribution Pole Replacement | Focus & field verifiable | Count of distribution pole replacements in 2024 | 1600 | 1608 | 1608 | 1608 | Target met | Target met | 69 | 96.5% | Field & Desktop | 96.98% | Initiative validated | Not separately tracked | Not separately tracked | Not separately tracked | No discrepancy | Spend for this initiative is included in GH-01 | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | GH-03 | 8.1.2.4 | Transmission Pole Replacement | Focus & field verifiable | Count of transmission pole replacements in 2024 | 160 | 204 | 204 | 204 | Target met | Target met | 54 | 100% | Field & Desktop | 127.5% | Initiative validated | Not separately tracked | Not separately tracked | Not separately tracked | No discrepancy | Spend for this initiative is included in GH-01 | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | GH-04 | 8.1.2.8 | Installation of System Automation Equipment | Focus & field verifiable | Count of system automation equipment installed in 2024 | 20 | 11 | 11 | 11 | Target not met | Issues with technician availability | 11 | 100% | Field & Desktop | 55% | Initiative not validated | 5000 | 12796 | 155.9% | Overspend | Costs increased due to bringing on a construction project management company to manage the system hardening projects. Additionally, project work in 2024 included higher costs to extend communications to field devices increasing the cost per unit completed. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | GH-05 | 8.1.2.12 | Expulsion Fuse Replacement | Focus & field verifiable | Count of expulsion fuse replacements conducted in 2024 | 500 | 2673 | 2673 | 2673 | Target met | Target met but reported actual is not accurate. The correct actual value is 2,531, and PacifiCorp has started formal QA/QC process to correct. | 70 | 96.6% | Field & Desktop | 516.4% | Initiative validated | 1000 | 5324 | 432.4% | Overspend | Increase in expulsion fuses replaced due to Pacific Power establishing a High Fire Risk Area (HFRA). Consistent with the Company's approach to replacing expulsion fuses in the Tier 2 and Tier 3 High Fire Threat Districts, the company replaced the expulsion fuses in the HFRA. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-01 | 8.1.3.1 | Transmission Patrol Inspections | Non-focus & non-field verifiable | Count of transmission patrol inspections conducted in 2024 | 12034 | 12261 | 12261 | 12261 | Target met | Target met | 18 | 100% | Desktop | 101.9% | Initiative validated | 93 | 63 | -32.26% | Underspend | Actual costs to complete the planned work was less than anticipated when the 2024 plan was projected prior to 2023. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-02 | 8.1.3.1 | Distribution Patrol Inspections | Non-focus & non-field verifiable | Count of distribution patrol inspections conducted in 2024 | 46276 | 48403 | 48403 | 48403 | Target met | Target met | 18 | 100% | Desktop | 104.6% | Initiative validated | 308 | 266 | -13.64% | Underspend | Actual costs to complete the planned work was less than anticipated when the 2024 plan was projected prior to 2023. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-03 | 8.1.3.2 | Transmission Detail Inspections | Focus & non-field verifiable | Count of transmission detail inspections conducted in 2024 | 1631 | 1631 | 1631 | 1631 | Target met | Target met | 69 | 100% | Desktop | 100% | Initiative validated | 137 | 57 | -58.39% | Underspend | Actual costs to complete the planned work was less than anticipated when the 2024 plan was projected prior to 2023. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-04 | 8.1.3.2 | Distribution Detail Inspections | Focus & non-field verifiable | Count of distribution detail inspections conducted in 2024 | 8672 | 8628 | 8628 | 8628 | Target met | Target considered met because shortfall was due to retirements and incorrect labeling of facility points that did not meet the criteria for inspection. | 72 | 100% | Desktop | 99.49% | Initiative validated | 203 | 231 | 13.79% | Overspend | Actual costs to complete the planned work was higher than anticipated when the 2024 plan was projected prior to 2023. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-05 | 8.1.3.3 | Transmission Intrusive Pole Inspections | Focus & non-field verifiable | Count of transmission intrusive inspections conducted in 2024 | 783 | 780 | 780 | 780 | Target met | Target considered met because shortfall was due to retired facility points that did not meet the criteria for inspection. | 66 | 100% | Desktop | 99.62% | Initiative validated | 171 | 95 | -44.44% | Underspend | Actual costs to complete the planned work was less than anticipated when the 2024 plan was projected prior to 2023. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-06 | 8.1.3.3 | Distribution Intrusive Pole Inspections | Focus & non-field verifiable | Count of distribution intrusive inspections conducted in 2024 | 2523 | 2517 | 2517 | 2517 | Target met | Target considered met because shortfall was due to retirements and incorrect labeling of facility points that did not meet the criteria for inspection. | 70 | 100% | Desktop | 99.76% | Initiative validated | 90 | 103 | 14.44% | Overspend | Actual costs to complete the planned work was higher than anticipated when the 2024 plan was projected prior to 2023. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-07 | 8.1.3.6 | Enhanced (Infrared) Inspections in Transmission Lines | Non-focus & non-field verifiable | Count of transmission line-miles undergoing an enhanced (infrared) inspection in 2024 | 700 | 700 | 700 | 693 | Target met | Lines accounting for seven line-miles decommissioned prior to inspection. Target considered met, but progress misreported in ARC and QDR | 18 | 100% | Desktop | 99% | Initiative validated | 90 | 85 | -5.556% | No discrepancy | Within 10% of plan | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-08 | 8.1.3.5 | Enhanced (Infrared) Inspections in Distribution Lines | Non-focus & non-field verifiable | Count of distribution line-miles undergoing an enhanced (infrared) inspection in 2024 | 810 | 810 | 810 | 810 | Target met | Target met | 18 | 100% | Desktop | 100% | Initiative validated | 130 | 129 | -0.7692% | No discrepancy | Within 10% of plan | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-11 | 8.1.3.4 | Substation Inspections | Non-focus & non-field verifiable | Count of substation inspections conducted in 2024 | 451 | 443 | 443 | 443 | Target met | Substation accounting for eight planned inspections decommissioned. Target considered met | 17 | 100% | Desktop | 98.23% | Initiative validated | 179 | 181 | 1.117% | No discrepancy | Within 10% of plan | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | AI-12 | 8.1.6 | Quality Assurance and Quality Control | Non-focus & non-field verifiable | Count of QA/QC of asset inspections conducted in 2024 | No target | 826 | Not reported | 826 | Target met | Actual verified progress was 825 but no target was set hence there was no missed target. | 18 | 100% | Desktop | N/A - no target | Initiative validated | 36 | 0 | -100% | Underspend | Asset inspection QA/QC costs were not charged out to work orders for 2024 and the actuals for this initiative were not tracked separately. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | GO-01 | 8.1.8.1 | Equipment Settings to Reduce Wildfire Risk (Grid Ops): EFR and Fault Indicators | Non-focus & non-field verifiable | Implementation of equipment settings to reduce wildfire risk | No target | Not reported | Pacific Power continues to deploy ESS on capable devices in the service territory. | Pacific Power continues to deploy ESS on capable devices in the service territory. | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 0 | 482 | N/A - no planned spend to compare with actuals | No discrepancy | Equipment settings and spend for this initiative was not projected for 2024 at the time of the creation of the base 2023-2025 WMP. PacifiCorp was still determining scope for this initiative for 2024 based on 2023 results. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | GO-02 | 8.1.8.3 | Grid Response Procedures and Notifications (Grid Ops): Patrols | Non-focus & non-field verifiable | Grid response procedures and notifications | Continue to deploy Elevated Fire Risk (EFR) settings [now known as Enhanced Safety Settings (ESS)] | Not reported | Pacific Power continues to deploy ESS on capable devices in the service territory. | Pacific Power continues to deploy ESS on capable devices in the service territory. | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 600 | 3751 | 525.2% | Overspend | Encroachment patrols was not originally included in the 2024 plan when this initiative was forecasted back in 2023. | N/A - see note in header row | N/A - see note in header row
Grid Design Operations and Maintenance | MA-01 | 8.1.4 | Equipment Maintenance and Repair | Non-focus & non-field verifiable | Weather station maintenance | - Continue planned transmission and distribution wires maintenance - Continue planned substation apparatus maintenance programs | 108 | All weather stations in service by end of year 2023 were maintained in 2024. | 108 | Target met | Target met | 16 | 100% | Desktop | N/A - no target | Initiative validated | 285 | 387 | 35.79% | Overspend | The original forecast for this initiative did not include the costs associated with the weather station data plans. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-01 | 8.2.2.1 | Detailed Inspection – Distribution | Non-focus & non-field verifiable | Count of distribution line-miles undergoing detailed vegetation inspections in 2024 | 874 | 875 | Target met | 875 | Target met | Target met | 875 | 100% | Desktop | 100.1% | Initiative validated | 294 | 492 | 67.35% | Overspend | Pacific Power increased vegetation management activity for 2024 due to the establishment of the High Fire Risk Area (HFRA) for which the plan did not originally account. The Company's approach to vegetation management in the HFRA is consistent with vegetation management in the Tier 2 and Tier 3 High Fire Threat Districts for which the plan did not originally account. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-02 | 8.2.2.2 | Detailed Inspection - Transmission | Non-focus & non-field verifiable | Count of transmission line-miles undergoing detailed vegetation inspections in 2024 | 602 | 599 | Target met | 599 | Target met | Target met | 602 | 100% | Desktop | 99.5% | Initiative validated | 157 | 201 | 28.03% | Overspend | Pacific Power increased vegetation management activity for 2024 due to establishment of the High Fire Risk Area (HFRA) for which the plan did not originally account. The Company's approach to vegetation management in the HFRA is consistent with vegetation management in the Tier 2 and Tier 3 High Fire Threat Districts. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-03 | 8.2.2.3 | Patrol Inspection - Distribution | Non-focus & non-field verifiable | Count of distribution line-miles undergoing vegetation patrol inspections in 2024 | 865 | 1037 | Target met | 1037 | Target met | Target met | 1037 | 100% | Desktop | 119.9% | Initiative validated | 316 | 333 | 5.38% | No discrepancy | Within 10% of plan | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-04 | 8.2.2.4 | Patrol Inspection - Transmission | Non-focus & non-field verifiable | Count of transmission line-miles undergoing vegetation patrol inspections in 2024 | 99 | 119 | Target met | 119 | Target met | Target met | 119 | 100% | Desktop | 120.2% | Initiative validated | 20 | 25 | 25% | Overspend | Pacific Power had increased vegetation management activity for 2024 due to the establishment of the High Fire Risk Area (HFRA) for which the plan did not originally account. The Company's approach to vegetation management in the HFRA is consistent with vegetation management in the Tier 2 and Tier 3 High Fire Threat Districts. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-05 | 8.2.3.1.2 | Pole Clearing | Focus & field verifiable | Pole clearing work | 3126 | 3192 | Target met | 3192 | Target met | Target met | 71 | 76% | Field & Desktop | 77.6% | Initiative not validated | 374 | 413 | 10.43% | No discrepancy | Pacific Power increased vegetation management activity for 2024 due to the establishment of the High Fire Risk Area (HFRA) for which the plan did not originally account. The Company's approach to vegetation management in the HFRA is consistent with vegetation management in the Tier 2 and Tier 3 High Fire Threat Districts. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-06 | 8.2.2.2 | Clearance - Distribution | Non-focus & non-field verifiable | Distribution clearance work | No target | Not reported | Not reported | Not reported | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 15087 | 18295 | 21.26% | Overspend | Pacific Power increased vegetation management activity for 2024 due to the establishment of the High Fire Risk Area (HFRA)for which the plan did not originally account for. The Company's approach to vegetation management in the HFRA is consistent with vegetation management in the Tier 2 and Tier 3 High Fire Threat Districts. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-07 | 8.2.2.2 | Clearance - Transmission | Non-focus & non-field verifiable | Transmission clearance work | No target | Not reported | Not reported | Not reported | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 1904 | 2498 | 31.2% | Overspend | Pacific Power increased vegetation management activity for 2024 due to the High Fire Risk Area (HFRA) for which the plan did not originally account for. The Company's approach to vegetation management in the HFRA is consistent with vegetation management in the Tier 2 and Tier 3 High Fire Threat Districts. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-08 | 8.2.3.3 | Fall-in Mitigation | Non-focus & non-field verifiable | Fall-in mitigation pilot | 2024: Tree condition will be reviewed to determine the impact of enhanced overhang reduction/crown removal. Trees will be assessed for dieback or other defects. | Not reported | Pacific Power continues to evaluate the enhanced overhang reduction pilot by inspecting trees that were treated under the project in 2023 and 2024. | Pacific Power continues to evaluate the enhanced overhang reduction pilot by inspecting trees that were treated under the project in 2023 and 2024. | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 30 | 0 | -100% | Underspend | Budget was provided in case a third-party contractor was needed to conduct or augment PacifiCorp’s follow-up work, assessments, or inspections following implementation of the expanded overhang specification. Follow-up reviews of completed work did not require a third-party contractor and reviews were completed by PacifiCorp internal staff. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-11 | 8.2.5 | Quality Assurance / Quality Control (Post-Audit Distribution) | Non-focus & non-field verifiable | Count of distribution line-miles undergoing vegetation post-audits in 2024 | 865 | 1037 | Target met | 1037 | Target met | Target met | 1037 | 100% | Desktop | 119.9% | Initiative validated | 135 | 171 | 26.67% | Overspend | Pacific Power increased vegetation management activity for 2024 due to the High Fire Risk Area (HFRA) for which the plan did not originally account for. The Company's approach to vegetation management in the HFRA is consistent with vegetation management in the Tier 2 and Tier 3 High Fire Threat Districts. | N/A - see note in header row | N/A - see note in header row
Vegetation Management and Inspections | VM-11 | 8.2.5 | Quality Assurance / Quality Control (Post-Audit Transmission) | Non-focus & non-field verifiable | Count of transmission line-miles undergoing vegetation post-audits in 2024 | 99 | 119 | Target met | 119 | Target met | Target met | 119 | 100% | Desktop | 120.2% | Initiative validated | 135 | 171 | 26.67% | Overspend | Pacific Power increased vegetation management activity for 2024 due to the High Fire Risk Area (HFRA) for which the plan did not originally account for. The Company's approach to vegetation management in the HFRA is consistent with vegetation management in the Tier 2 and Tier 3 High Fire Threat Districts. | N/A - see note in header row | N/A - see note in header row
Situational Awareness and Forecasting | SA-01 | 8.3.2.1 | Environmental Monitoring Systems | Non-focus & non-field verifiable | Count of environmental monitoring systems installed in 2024 | 8 | 10 | 10 | 10 | Target met | Target met | 10 | 100% | Desktop | 125% | Initiative validated | 160 | 209 | 30.63% | Overspend | Pacific Power installed two stations more than were originally planned for 2024 and presented in the 2023-2025 Base WMP. | N/A - see note in header row | N/A - see note in header row
Situational Awareness and Forecasting | SA-02 | 8.3.3.1 | Grid Monitoring Systems | Focus & non-field verifiable | Implementation of grid monitoring systems | No target | Not reported | PacifiCorp completed pilot of this initiative in 2024 and does not plan on future utilization of distribution fault anticipators. | PacifiCorp completed pilot of this initiative in 2024 and does not plan on future utilization of distribution fault anticipators. | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 39 | 108 | 176.9% | Overspend | The original forecast for this initiative did not include the costs associated with the data connections for the DFAs. | N/A - see note in header row | N/A - see note in header row
Situational Awareness and Forecasting | SA-03 | 8.3.4.1 | Smoke and Air Quality Sensors | Non-focus & non-field verifiable | Smoke and air quality sensors pilot | No target | Not reported | Initiative discontinued | Initiative discontinued | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 15 | 14 | -6.667% | No discrepancy | Within 10% of plan | N/A - see note in header row | N/A - see note in header row
Situational Awareness and Forecasting | SA-04 | 8.3.4.1 | Ignition Detection Systems | Focus & non-field verifiable | Count of wildfire detection cameras installed in 2024 | 6 | 6 | 6 | 6 | Target met | Target met | 6 | 100% | Desktop | 100% | Initiative validated | 1065 | 1031 | -3.192% | No discrepancy | Within 10% of plan | N/A - see note in header row | N/A - see note in header row
Situational Awareness and Forecasting | SA-05 | 8.3.5.3 | Weather Forecasting | Non-focus & non-field verifiable | Weather forecasting efforts | No target | - Completed (QDR target): Extend historic 30-year weather data reanalysis through 2023 - Completed (QDR target): Build Machine Learning (ML) gridded grassland Normalized Difference Vegetation Index (NDVI) product - Completed (QDR target): Develop detailed technical requirements for multi-member Weather Research and Forecast (WRF) ensemble implementation | Not reported | All QDR targets completed | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 115 | 267 | 132.2% | Overspend | The original forecast was for a limited scope and the domain expansion costs were not included in Pacific Power’s original forecast. | N/A - see note in header row | N/A - see note in header row
Situational Awareness and Forecasting | SA-06 | 8.3.6.1 | Fire Potential Index | Non-focus & non-field verifiable | Implementation of Fire Potential Index | Scheduled for completion in 2023 | Not reported | Not reported | Completed | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 97 | 0 | -100% | Underspend | The actual costs for this initiative were included in the actuals for the SA-05 initiative. | N/A - see note in header row | N/A - see note in header row
Emergency Preparedness | EP-01 | 8.4.2 | Emergency Preparedness Plan | Non-focus & non-field verifiable | Internal staff Emergency Coordination Center (ECC) and Department Operations Center (DOC) three- year training program | Continued progress on three-year training program | Not reported | Continued progress on three-year training program | Continued progress on three-year training program | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 50 | 253 | 406% | Overspend | Original projections did not include all related emergency management and meteorology personnel for 2024 when the plan was created prior to 2023. | N/A - see note in header row | N/A - see note in header row
Emergency Preparedness | EP-02 | 8.4.2.3 | External Collaboration and Coordination | Non-focus & non-field verifiable | Efforts to enhance awareness of PSPS plan and understanding of roles and responsibilities | - 1 Functional Exercise (FE) - 1 Table Top Exercise (TTX) - 1 Workshop | - 1 Functional Exercise (FE) - 1 Table Top Exercise (TTX) - 1 Workshop - 1 Preparedness Fair/ CRC Demo (QDR target) | - 1 Functional Exercise (FE) - 1 Table Top Exercise (TTX) - 1 Workshop | - 1 Functional Exercise (FE) - 1 Table Top Exercise (TTX) - 1 Workshop - 1 Preparedness Fair/ CRC Demo | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 30 | 7 | -76.67% | Underspend | Pacific Power did not require as much funding for this initiative as originally forecasted prior to 2023 for the 2024 year. | N/A - see note in header row | N/A - see note in header row
Emergency Preparedness | EP-03 | 8.4.4.2 | Public Emergency Communication Strategy | Non-focus & non-field verifiable | Development of a web-based portal for Public Safety Partners with critical facility/infrastructure data for use during PSPS events | Implement improvements to the Public Safety Partner Portal and deliver a dashboard for situational awareness during PSPS reponses | Completed | Continued improvements to Public Safety Partner Portal | Completed | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 0 | 2.5 | N/A - no planned spend to compare with actuals | No discrepancy | No projected spend was included for 2024. The spend is associated with the annual upkeep of the portal that was not accounted for in the original forecast. | N/A - see note in header row | N/A - see note in header row
Emergency Preparedness | EP-05 | 8.4.6 | Customer Support in Wildfire and PSPS Emergencies | Non-focus & non-field verifiable | Customer support in wildfire and PSPS emergencies | No target | Not reported | Not reported | Not reported | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 0 | 140 | N/A - no planned spend to compare with actuals | No discrepancy | No projected spend was included for 2024. The portable battery and rebate program was in a pilot phase and spend was not forecasted for 2024 because results from 2023 were still being evaluated. | N/A - see note in header row | N/A - see note in header row
Community Outreach and Engagement | CO-01 | 8.5.2 | Public Outreach and Education Awareness Program | Non-focus & non-field verifiable | Public outreach and education awareness program | - Perform Pre- and Post-fire season customer survey: In Q2 and Q4, respectively - Pre-fire season survey: 55% or more of the sample survey are aware of wildfire safety communications - Pre-fire season survey: PacifiCorp remains the most mentioned source of communication about wildfire preparedness - Access and Functional Needs (AFN) resources on the website: One additional language for the medical certificate | -Completed: Pre-fire season survey: 55% or more of the sample survey are aware of wildfire safety communications -QDR did not report on other targets. | -Completed: Perform Pre- and Post-fire season customer survey -Completed: AFN resources on the website: One additional language for the medical certificate | - Completed: Perform Pre- and Post-fire season customer survey: In Q2 and Q4, respectively - Completed: Pre-fire season survey: 55% or more of the sample survey are aware of wildfire safety communications - Completed: Access and Functional Needs (AFN) resources on the website: One additional language for the medical certificate | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative not validated | 90 | 100 | 11.11% | Overspend | Pacific Power did more outreach in 2024 then what was originally forecasted prior to 2023. The actual costs for 2024 are more aligned with actual costs from 2023. | N/A - see note in header row | N/A - see note in header row
Risk Methodology and Assessment | RA-01 | 6.2.2 | Risk and Risk Components Calculation | Non-focus & non-field verifiable | Efforts to calculate risk and risk components | No target | - Completed (QDR target): Updated wildfire risk at the circuit level as part of annual FireSight planning model updates - In progress (QDR target): Updated PSPS risk at the circuit level | Not reported | No WMP target. Met first QDR target in Q1. Second QDR target in progress | Target not met | Missed second QDR target due to shifting priorities and staffing limitations | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative not validated | 130 | 368 | 183.1% | Overspend | The spend for initiative includes the spend for RA-03 and the original forecast did not include the work for calculating risk reduction. | N/A - see note in header row | N/A - see note in header row
Risk Methodology and Assessment | RA-02 | 6.4.1 | Top Risk Areas within the HFRA | Non-focus & non-field verifiable | Designation of top risk areas within the FHRA | No target | Completed (QDR target): Updated and approved FHCA | Not reported | No WMP target. Met QDR target in Q2 | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 0 | 6.5 | N/A - no planned spend to compare with actuals | No discrepancy | Spend for this initiative was not projected for 2024 at the time of the creation of the base 2023-2025 WMP. Spend for this initiative was the maintenance done to updates to the FHCA and were not originally included in forecasts. | N/A - see note in header row | N/A - see note in header row
Risk Methodology and Assessment | RA-03 | 6.4.3 | Other Key Metrics | Non-focus & non-field verifiable | Efforts to calculate other key metrics | No target | In progress (QDR target): Effectiveness measures for select mitigations | Not reported | No WMP target. Per QDR target, initiated discovery and benchmarking for effectiveness of undergrounding and covered conductor. Began developing internal effectiveness modeling for undergrounding | Target not met | None provided for missing QDR target | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative not validated | 40 | 0 | -100% | Underspend | The work break down structure for this work was originally planned to be separated to RA- 03 when forecasted in 2023 for 2024. It has since changed and is now being captured in spend for RA-01. | N/A - see note in header row | N/A - see note in header row
Risk Methodology and Assessment | RA-04 | 6.5 | Enterprise System for Risk Assessment | Non-focus & non-field verifiable | Implementation of enterprise system for risk assessment | No target | Not reported | Not reported | Not reported | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 157 | 157 | 0% | No discrepancy | Within 10% of plan | N/A - see note in header row | N/A - see note in header row
Public Safety Power Shutoff | PS-01 | 9.1.6 | Protocols on PSPS | Non-focus & non-field verifiable | Protocols on PSPS | No target | Not reported | Pacific Power did not have any PSPS events in 2024. | Pacific Power did not have any PSPS events in 2024. | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 800 | 0 | -100% | Underspend | Pacific Power did not have any PSPS events in 2024. | N/A - see note in header row | N/A - see note in header row
Wildfire Mitigation Plan Strategy Development | WP-01 | 7.1.2 | Wildfire Mitigation Strategy Development | Non-focus & non-field verifiable | Wildfire Mitigation Strategy development | No target | Not reported | Not reported | Not reported | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 520 | 949 | 82.5% | Overspend | The costs for independent evaluation were not included in Pacific Power’s plan for 2024 when it was originally forecasted in 2023. | N/A - see note in header row | N/A - see note in header row
Wildfire Mitigation Plan Strategy Development | WP-02 | 7.1.4.1 | Identifying and Evaluating Mitigation Initiatives | Non-focus & non-field verifiable | Identifying and evaluating mitigation initiatives | No target | Not reported | Not reported | Not reported | Target met | Target met | Sampling not utilized | Sampling not utilized | Desktop | Sampling not utilized | Initiative validated | 100 | 666 | 566% | Overspend | The grant study included in this initiative was not included for the 2024 plan when it was originally forecasted in 2023. | N/A - see note in header row | N/A - see note in header row
Note on X11: PacifiCorp did not capture risk reduction goals in its 2023-2025 WMP. Thus the IE could not validate if a goal was met.
Note on Y11: PacifiCorp did not capture risk reduction goals in its 2023-2025 WMP. Thus the IE could not validate if a goal was met.

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | NV5 / Guidehouse / JH Land Consultants
Electrical Corporation: | PacifiCorp
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2025-04-07 | 2025-04-10 | All initiatives under Asset Management & Inspections and Vegetation Management & Inspections | DR1 | PC_2024_Q1_Tables1-15_R0.xlsx PC_2024_Q2_Tables1-15_R0.xlsx PC_2024_Q3_Tables1-15_R0.xlsx PC_2024_Q4_Tables1-15_R0.xlsx PC_2024_Q1_SpatialDataStatusReport.xlsx PC_2024_Q2_SpatialDataStatusReport.xlsx PC_2024_Q3_SpatialDataStatusReport.xlsx PC_2024_Q4_SpatialDataStatusReport.xlsx PC_2024_Q1_rev.gdb.zip PC_2024_Q2.gdb.zip PC_2024_Q3.gdb.zip PC_2024_Q4.gdb.zip PC_2024_ARC_20250331.pdf SOP_08292024.pdf Policy 001.xlsx 009-Detailed Inspections.pdf 011-Safety Patrol Inspections.pdf 013-Intrusive Testing (Pole Test And Treat).pdf 203-Enhanced Inspections.pdf 292-Timeframe Correction Policy Policy 034_R5.pdf Form 3274F.xlsx Form 3274S-PP.xlsx Procedure 069.xlsx 2025 GO95 Training Manual_12162024.pdf 2025 GO95 Transmission Training Guide.pdf Overhead Detailed Inspection Program Audit Process (May 2021).pdf Policy No. 123-PP.pdf
2025-04-21 | 2025-04-24 | VM-11 | DR2 | PG&E and PacifiCorp Vegetation Management Collaboration.pdf PacifiCorp_QAQC_Program_030420251_v1.docx
2025-04-29 | 2025-05-02 | WMP Section Questions | DR3 | No Files
2025-04-29 | 2025-05-02 | AI-01, AI-02, AI-03, AI-04, AI-05, AI-06, AI-07, AI-08, AI-11, AI-12, GH-01, GH-02, GH-03, GH-04, GH-05, MA-01, SA-01, SA-04, VM-01, VM-02, VM-03, VM-04, VM-05, VM-11 | DR4 | CA_2024_AI-01_INSPECTIONS.xlsx CA_2024_AI-02_INSPECTIONS.xlsx CA_2024_AI-03_INSPECTIONS.xlsx CA_2024_AI-04_INSPECTIONS.xlsx CA_2024_AI-05_INSPECTIONS.xlsx CA_2024_AI-06_INSPECTIONS.xlsx AI-07_2024 Transmission IR Information.xlsx CA_2024_ENHANCED_INSPECTIONS.xlsx AI-08_Distribution Infrared Inspection.xlsx AI-11_CA 2024 Substation Inspections.xlsx CA_2024_AI-12_INSPECTIONS.xlsx Item 11 covered conductor.xlsx Item 12 distribution poles.xlsx Item 13 transmission poles.xlsx Item 14 system automation 2024.xlsx Item 15 expulsion fuse replacements.xlsx A-01_Weather Station Information.xlsx Item 17 weather stations 2024.xlsx DR4_250429_Cameras.xlsx CA_Miles_Units_Tracker_2024.xlsx PpNotificationPoleClearing_2024_LRA.xlsx PpPoleTreatmentDetail_2024_LRA.xlsx MASTER_2024_POST AUDIT Tracker_CA
2025-05-05 | 2025-05-08 | VM-05 | DR5 | PpPoleTreatmentDetail_2024_LRA.xlsx PpNotificationPoleClearing_2024_LRA.xlsx
2025-05-08 | 2025-05-13 | AI-01, AI-02, AI-03, AI-04, AI-05, AI-06, AI-07, AI-08, AI-11, AI-12, MA-01, SA-01, SA-04, VM-01, VM-02, VM-03, VM-04, VM-05, VM-11, EP-02 | DR6 | AI-01_CA_2024_RANDOM_SAMPLE_RESULTS.zip AI-02_CA_2024_RANDOM_SAMPLE_RESULTS.zip AI-03_CA_2024_RANDOM_SAMPLE_RESULTS.zip AI-04_CA_2024_RANDOM_SAMPLE_RESULTS.zip AI-05_CA_2024_RANDOM_SAMPLE_RESULTS.zip AI-06_CA_2024_RANDOM_SAMPLE_RESULTS.zip AI-07_CA_2024_RANDOM_SAMPLE_RESULTS.xlsx AI-08_CA_2024_RANDOM_SAMPLE_RESULTS.zip AI-11_CA 2024 Sample Inspection Results.xlsx AI-12_CA_2024_RANDOM_SAMPLE_RESULTS.zip MA-01_CA_2024_RANDOM_SAMPLE-RESULTS.zip SA-01 10 weather station 2024 CA documents.zip DR6_250508_Cameras.xlsx Item 15 & 16 Attachments.zip Item 17 Attachments.zip
2025-05-13 | 2025-05-16 | CO-01, EP-01, EP-03, EP-05, GO-01, GO-02, RA-01, RA-02, RA-03, SA-05, VM-05, VM-08 | DR7 | Spring 2024 California Wildfire Survey Results.pptx Fall 2024 California Wildfire Survey Results.pptx Item 2 Attachment.xlsx DR7.03.pdf PacifiCorp_ESS_EMS Record_2024_05-15-25.xlsx PacifiCorp_DR 7_Issuance_250513_Q8.docx PacifiCorp_DR7_11.zip Historical Reanalysis WRF.csv TSVA_ENSEMBLE STATEMENT OF WORK.docx NDVI_Modeling_Final_Report.pdf Item 14 Attachments.zip
2025-05-14 | 2025-05-19 | VM-05 | DR8 | No Files Note - PacifiCorp does not have any vegetation agreements with landowners.
2025-05-15 | 2025-05-20 | GH-01, GH-02, GH-03, GH-04, GH-05 | DR9 | Covered Conductor.zip Distribution Pole Replace.zip Transmission Pole Replace.zip System Automation.zip Item 3 Attachment - Expulsion Fuses.xlsx
2025-05-21 | 2025-05-27 | VM-01, VM-02, VM-03, VM-04 | DR10 | DNT Folder TNT_MGI Folder FIN Folder FIT_FMT Folder Vegetation Management Reporting Disclosure.pdf
2025-05-23 | 2025-05-27 | AI-07 | DR11 | CA_RANDOM_SAMPLE_DR11.zip
2025-05-27 | 2025-05-30 | VM-05 | DR12 | Pole Clearing Audit Tracker_2024.xlsx PpAuditException_2024_LRA.xlsx
2025-05-29 | 6/3/25 (Items 1 and 2); 6/4/25 (Item 3) | VM-11 | DR13 | Item 1.zip Item 2.zip Item 3.zip
2025-06-06 | 6/11/25; 6/23/25 | GH-01, GH-05, MA-01, EP-02 | DR14 | DR14 Item 1.docx DR14 Item 2.xlsx DR14 Item 3.xlsx DR14 Item 4.zip Item 5_MA-01 Wires Equipment Maintenance_2024.xlsx May 1 2024 Preparedness Fair.pdf May 1 2024 Press Release.pdf May 1 2024 Social Media.pdf

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | NV5 / Guidehouse / JH Land Consultants
Electrical Corporation: | PacifiCorp
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2025-05-21 | 8.2.2 - VM-01, VM-02, VM-03, VM-04 | SME001 |  | Discussion of verification method for covered initiatives.
2025-05-22 | 8.1.3 - AI-07, AI-08 | SME002 |  | Discussion of verification method for AI-07 and IE questions following review of AI-08 evidence.
2025-05-27 | 8.3.2.1 - SA-01 | SME003 |  | Discussion of IE questions following review of SA-01 evidence.
2025-05-29 | 8.2.5 - VM-11 | SME004 |  | Discussion of IE questions following review of VM-11 evidence.
2025-05-30 | 8.2.2 - VM-01, VM-02, VM-03, VM-04 | SME005 |  | Discussion of IE questions following review of covered initiatives.
2025-06-02 | 6.2.2, 6.4.1, 6.4.3 - RA-01, RA-02, RA-03 | SME006 |  | Discussion of IE questions following review of covered initiatives.
2025-06-06 | 8.1.2.1, 8.1.2.12 - GH-01, GH-05 | SME007 |  | Discussion of IE questions following review of covered initiatives.

## Tab 5 - List of "Fail-to-Fund"
List of Failed-to-Fund Initiatives
Independent Evaluator: | NV5 / Guidehouse / JH Land Consultants
Electrical Corporation: | PacifiCorp
WMP Category | WMP Section Number | WMP Page Number | Initiative Tracking ID | Initiative Name | WMP - Planned Spend (Thousand $) | EC-Claimed Actual Spend (Thousand $) | Variance (%)
Grid Design Operations and Maintenance | 8.1.3.1 |  | AI-01 | Transmission Patrol Inspections | 93 | 63 | -32.26%
Grid Design Operations and Maintenance | 8.1.3.1 |  | AI-02 | Distribution Patrol Inspections | 308 | 266 | -13.64%
Grid Design Operations and Maintenance | 8.1.3.2 |  | AI-03 | Transmission Detail Inspections | 137 | 57 | -58.39%
Grid Design Operations and Maintenance | 8.1.3.3 |  | AI-05 | Transmission Intrusive Pole Inspections | 171 | 95 | -44.44%
Grid Design Operations and Maintenance | 8.1.3.6 |  | AI-07 | Enhanced (Infrared) Inspections in Transmission Lines | 90 | 85 | -5.556%
Grid Design Operations and Maintenance | 8.1.3.5 |  | AI-08 | Enhanced (Infrared) Inspections in Distribution Lines | 130 | 129 | -0.7692%
Grid Design Operations and Maintenance | 8.1.6 |  | AI-12 | Quality Assurance and Quality Control | 36 | 0 | -100%
Emergency Preparedness | 8.4.2.3 |  | EP-02 | External Collaboration and Coordination | 30 | 7 | -76.67%
Public Safety Power Shutoff | 9.1.6 |  | PS-01 | Protocols on PSPS | 800 | 0 | -100%
Risk Methodology and Assessment | 6.4.3 |  | RA-03 | Other Key Metrics | 40 | 0 | -100%
Situational Awareness and Forecasting | 8.3.4.1 |  | SA-03 | Smoke and Air Quality Sensors | 15 | 14 | -6.667%
Situational Awareness and Forecasting | 8.3.4.1 |  | SA-04 | Ignition Detection Systems | 1065 | 1031 | -3.192%
Situational Awareness and Forecasting | 8.3.6.1 |  | SA-06 | Fire Potential Index | 97 | 0 | -100%
Vegetation Management and Inspections | 8.2.3.3 |  | VM-08 | Fall-in Mitigation | 30 | 0 | -100%
Note on E11: Kopunova, Sara: If applicable since some commitments occur outside of initiatives