## Tab 1 - Overview tab
IE ARC Attachments
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Liberty
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted
Tab 5 | List of Failed-to-Fund Initiatives - All initiatives funded less than 100%

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: |  | Bureau Veritas
Electrical Corporation: |  | Liberty
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC ARC) | EC-Claimed Progress | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | Initiative Validation Rate (%) | IE Finding on Initiative | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | WMP-GDOM-AI-01 | 8.1.3.1 | Detailed inspections of distribution electric lines and equipment | Focus & non-field verifiable | 264.2 Circuit Miles | 264.2 | 363.45 | 363.45 | 363.45 | Target met | N/A | 61 | 100% | List of Distribution Inspections (DR018) Inspection Reports (DR018.b) | 137% | Initiative validated | 125000 | 536670.12 | 329.3% | Overspend | Liberty's initial projections for its 2024 asset inspection initiatives were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-AI-02 | 8.1.3.2 | Intrusive pole inspections | Non-focus & non-field verifiable | 2302 Poles | 2302 | 2641 | 2641 | 2641 | Target met | N/A | 18 | 100% | List of Intrusive Pole Inspections (DR019/.b) | 144% | Initiative validated | 0 | 147641.5 | 100% | Overspend | Liberty erroneously did not project costs for intrusive pole inspections in 2024. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-AI-03 | 8.1.3.1 | Patrol inspections of distribution electric lines and equipment | Focus & non-field verifiable | 589 Circuit Miles | 589 | 476.9 | 476.9 | 476.9 | Target not met | that Liberty has completed the 476.9 claimed amount of inspection mileage, however, this initiative is not validated due to not inspecting the remaining 12.8 (adjusted per WMP-GDOM-AI-01 over completion) circuit miles and ultimately not meeting their 2024 target. | 65 | 100% | List of Patrol Inspections (DR020) Inspection Reports (DR020.b) | 81% | Initiative not validated | 125000 | 536670.12 | 329.3% | Overspend | Liberty's initial projections for its 2024 asset inspection initiatives were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-AI-04 | 8.1.3.4 | Other discretionary inspections of distribution electric lines and equipment | Non-focus & non-field verifiable | No Target Circuit Miles | No Target | 1 | 1 | 1 | Target met | N/A | 1.33 | 100% | Records of drone inspections completion (DR039) | 100% | Initiative validated | 1000000 | 363867.33 | -63.61% | Underspend | Liberty's initial projections for its 2024 asset inspection initiatives were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-AI-05 | 8.1.3.5 | Quality assurance / quality control of inspections | Non-focus & non-field verifiable | 0.12 % of Detailed Inspections | 0.12 | 0.12 | 0.12 | 0.12 | Target met | N/A | 17 | 100% | Records of QA completion (DR040) Records of asset inspections completion (DR018) | 105% | Initiative validated | 10000 | 212985.81 | 2030% | Overspend | Liberty's initial projections for its 2024 asset inspection initiatives were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-AI-06 | 8.1.3.6 | Substation inspections | Non-focus & non-field verifiable | 42 Substations | 42 | 71 | 71 | 71 | Target met | N/A | 15 | 100% | List of Substation Inspections (DR021.b) | 121% | Initiative validated | 10000 | 0 | -100% | Underspend | Liberty's initial projections for its 2024 asset inspection initiatives were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-01 | 8.1.2.1 | Covered conductor installation | Focus & field verifiable | 5.61 Circuit Miles | 5.61 | 3.9 | 3.9 | 3.9 | Target not met | The IE field validated the 4.06 circuit miles of Covered Conductor completion but Liberty did not meet the goal of 5.61 circuit miles. | 4.06 | 100% | Project Shapefiles (DR041) Project As-Builts (DR041) | 72.37% | Initiative not validated | 8627427 | 8312596.19 | -3.649% | Underspend | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-02 | 8.1.2.2 | Undergrounding of electric lines and/or equipment | Non-focus & field verifiable | 1.25 Circuit Miles | 1.25 | 0 | 0 | 0 | Target not met | Because no undergrounding was completed, the IE did not perform field verification. Based on the review of documentation and the absence of completed work, Liberty did not meet its 2024 target, and this initiative is not validated. | 0 | N/A | N/A | 0% | Initiative not validated | 8482680 | 46066.92 | -99.46% | Underspend | Liberty did not complete its initial 2024 WMP target for undergrounding. Refer to Section B of this report and Liberty's 2024 WMP Change Order Request. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-03 | 8.1.2.3 | Distribution pole replacements and reinforcements | Focus & field verifiable | 400 Poles | 400 | 823 | 823 | 823 | Target met | N/A | 82 | 100% | Records of pole replacements (DR043) | 205.8% | Initiative validated | 7413000 | 20147051.05 | 171.8% | Overspend | Liberty exceeded its 2024 WMP target for pole replacements by 106%. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-04 | 8.1.2.4 | Transmission pole/tower replacements and reinforcements | Non-focus & field verifiable |  | 0 | 0 | 0 | 0 | Target met | N/A | 1 | 100% | Records of pole replacements (DR043) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-05 | 8.1.2.5 | Traditional overhead hardening | Focus & field verifiable | 3.5 Circuit Miles | 3.5 | 3.5 | 3.5 | 3.5 | Target met | N/A | 3.63 | 100% | Project Shapefiles (DR045) Project As-Builts (DR045) | 104% | Initiative validated | 3500000 | 1863709.28 | -46.75% | Underspend | Liberty completed its 2024 WMP target for traditional overheard hardening at a lower cost than initially projected. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-06 | 8.1.2.6 | Emerging grid hardening technology installations and pilot progress | Non-focus & non-field verifiable | Implement SRP Program | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Liberty Written Response UNR Fire Mitigation Study (DR022) | 100% | Initiative validated | 3050000 | 0 | -100% | Underspend | Liberty captured costs associated with implementing its SRP Program in WMP initiatives: WMP-GDOM-GH-08 and WMP-SA-02. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-07 | 8.1.2.7 | Microgrids | Non-focus & non-field verifiable | 1 Microgrids | 1 | 0 | 0 | 0 | Target not met | The utility cited high costs and shifting priorities as the rationale for deferring the microgrid project, leading to a missed target. | 0 | 0% | Liberty Written Response (DR023) 2024 WMP Update Change Order Report (DR023.b) | 0% | Initiative not validated | 1500000 | 0 | -100% | Underspend | Liberty did not complete its initial 2024 WMP target for microgrids. Refer to Section B of this report and Liberty's 2024 WMP Change Order Request. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-08 | 8.1.2.8 | Installation of system automation equipment | Focus & field verifiable | 8 Automatic Reclosers | 8 | 2 | 2 | 2 | Target not met | The IE field validated the completion of 2 automatic recloser installations but but Liberty did not meet the goal of 8. | 2 | 100% | Records of automatic recloser installation (DR024) | 25% | Initiative not validated | 1200000 | 1300520.31 | 8.377% | Overspend | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-09 | 8.1.2.9 | Line removal (in HFTD) | Non-focus & non-field verifiable | 1.1 Circuit Miles | 1.1 | 0 | 0 | 0 | Target not met | Liberty communicated a strategic shift in 2024, opting to focus on a covered conductor project instead of the originally planned 1.1 miles of microgrid-enabled line removal under the initiative, leading to a missed target. | 1 | 0% | Liberty Written Response (DR025) 2024 WMP Update Change Order Report (DR025.b) | 0% | Initiative not validated | 500000 | 0 | -100% | Underspend | Liberty did not complete its initial 2024 WMP target for line removal. Refer to Section B of this report and Liberty's 2024 WMP Change Order Request. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-10 | 8.1.2.10 | Other grid topology improvements to minimize risk of ignitions | Non-focus & non-field verifiable |  | 0 | 0 | 0 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-11 | 8.1.2.11 | Other grid topology improvements to mitigate or reduce PSPS events | Non-focus & non-field verifiable |  | 0 | 0 | 0 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-12 | 8.1.2.12 | Other technologies and systems not listed above: | Non-focus & non-field verifiable |  | 0 | 0 | 0 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-12a | 8.1.2.12 | Tree attachment removals | Non-focus & non-field verifiable | 60 Tree Attachments | 60 | 98 | 98 | 98 | Target met | N/A | 20 | 100% | Records of tree attachment removal completion (DR048) | 163% | Initiative validated | 720392 | 928830.84 | 28.93% | Overspend | Liberty exceeded its 2024 WMP target for tree attachment removals by 63%. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-12b | 8.1.2.12 | Expulsion fuse replacement | Focus & field verifiable | 500 Expulsion Fuses | 500 | 750 | 750 | 750 | Target met | N/A | 87 | 100% | Records of expulsion fuse replacement completion (DR049) | 136.2% | Initiative validated | 0 | 699266.23 | 100% | Overspend | Liberty's projected expenditures for its 2024 expulsion fuse replacements was TBD at time of WMP submission. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-12c | 8.1.2.12 | Animal guards | Non-focus & non-field verifiable | 2 Animal Guards | 2 | 0 | 0 | 0 | Target not met | According to Liberty’s 2024 Q4 QDR and DR050, no animal guards were installed by the end of 2024, due to issues with material procurement. | 0 | N/A | Confirmation of no installation (DR050) | 0% | Initiative not validated | 100000 | 0 | -100% | Underspend | Liberty did not complete its 2024 WMP target for animal guards. Refer to Section B of this report. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-12d | 8.1.2.12 | CalFIRE exempt hardware | Non-focus & non-field verifiable | CalFIRE Exempt Hardware | 0 | 0 | 0 | 0 |  | N/A | N/A | N/A | Liberty Written Response (DR027) | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-12e | 8.1.2.12 | Open wire/grey wire | Non-focus & non-field verifiable | 5.09602387739369 Circuit Miles | 5.096 | 7.36 | 7.36 | 7.36 | Target met | N/A | 7 | 100% | List of Grey Wire Replacements Inspection Reports (DR028) | 145% | Initiative validated | 2000000 | 1754772.88 | -12.26% | Underspend | Liberty completed its 2024 WMP target for open wire/grey wire at a lower cost than initially projected. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GH-12f | 8.1.2.12 | Substation Equipment Replacement | Non-focus & non-field verifiable | 1 Substations | 1 | 1 | 1 | 1 | Target met | N/A | 1 | 100% | Outage Correspondence to Cutover from Old to New Substation Equipment Old/New Substation Photos (DR029) | 100% | Initiative validated | 0 | 415204.29 | 100% | Overspend | Liberty did not project costs for substation equipment replacement as the work associated with this WMP initiative is determined by the results of substation inspections in the WMP compliance year. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GO-01 | 8.1.8.1 | Equipment settings to reduce wildfire risk | Non-focus & non-field verifiable | 15 # of circuits with SRP | 15 | 15 | 15 | 15 | Target met | N/A | 15 | 100% | Records of SRP enabled circuits (DR051) | 100% | Initiative validated | 800000 | 0 | -100% | Underspend | Liberty captured costs associated with implementing its SRP Program in WMP initiatives: WMP-GDOM-GH-08 and WMP-SA-02. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GO-02 | 8.1.8.2 | Grid response procedures and notifications | Non-focus & non-field verifiable | No Target | 0 | 0 | 0 | 0 | Target met | N/A | Overview of operational procedures | 100% | Documentation of operational procedures (DR052) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GO-03 | 8.1.8.3 | Personnel work procedures and training in conditions of elevated fire risk | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Annual FPP Sign-In Sheet Annual FPP Training Smoke & Field Training Sign-In Sheet Liberty Fire Refresher 24 VM Training Fire Prevention Plan Refresher (DR030) | 100% | Initiative validated | 298088.4375 | 0 | -100% | Underspend | Liberty did not track costs in this WMP initiative in 2024. | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GO-04 | 8.1.8.1 | Automatic recloser operations | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-GO-05 | 8.1.5 | Asset Management and Inspection Enterprise System | Non-focus & non-field verifiable | No Target | 0 | 0 | 0 | 0 | Target met | N/A | Overview of enterprise system | 100% | SME Interview (DR054) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Grid Design Operations and Maintenance | WMP-GDOM-MR-01 | 8.1.4 | Equipment maintenance and repair | Non-focus & non-field verifiable | No Target | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Records of maintenance and repairs documentation (DR055) | 100% | Initiative validated | 500000 | 0 | -100% | Underspend | Liberty did not track costs in this WMP initiative in 2024. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-ESG-01 | 8.2.4 | Vegetation Management Enterprise System | Non-focus & non-field verifiable | No Target | 0 | 0 | 0 | 0 | Target met | N/A | Overview of enterprise system | 100% | SME Interview (DR056) | 100% | Initiative validated | 418185.15 | 577570.4 | 38.11% | Overspend | Liberty's initial projections for 2024 Enterprise System were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-INSP-01 | 8.2.2.1 | Vegetation Management Inspection Program - Detailed | Focus & non-field verifiable | 220 Line Miles | 220 | 258 | 258 | 258 | Target met | N/A | 72 | 100% | Records of detailed VM inspections (DR057) | 117.9% | Initiative validated | 813514.6 | 763520.33 | -6.145% | Underspend | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-INSP-02 | 8.2.2.2 | Vegetation Management Inspection Program - Patrol | Non-focus & non-field verifiable | Line Miles | 0 | 136.4 | 136.4 | 136.4 | Target met | N/A | 20 | 100% | Records of VM patrol inspections (DR058) | 100% | Initiative validated | 257500 | 595415.18 | 131.2% | Overspend | More patrol inspection work was performed than anticipated due to tree mortality. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-INSP-03 | 8.2.2.3 | Vegetation Management Inspection Program - LiDar | Non-focus & non-field verifiable | 700 Line Miles | 700 | 700 | 700 | 700 | Target met | N/A | 23 | 100% | Records of VM LiDAR inspections (DR058) | 100% | Initiative validated | 721000 | 563341.53 | -21.87% | Underspend | Liberty worked with its vendor to develop specifications for deliverables that resulted in cost savings. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-QAQC-01 | 8.2.5 | Quality Assurance and Quality Control | Non-focus & non-field verifiable | 229 Line Miles | 229 | 234.3 | 234.3 | 234.3 | Target met | N/A | 22 | 100% | Records of QA completion (DR060) | 102.3% | Initiative validated | 515000 | 542652.7 | 5.369% | Overspend | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-VFM-01 | 8.2.3.1 | Pole Clearing | Non-focus & non-field verifiable | 4960 Subject Poles | 4960 | 5084 | 5084 | 5084 | Target met | N/A | 23 | 100% | Records of pole clearing completion (DR061) | 102.5% | Initiative validated | 494400 | 565771.28 | 14.44% | Overspend | Liberty utilized a second vendor to complete pole clearing work which resulted in increased cost. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-VFM-02 | 8.2.3.2 | Wood and Slash Management | Non-focus & non-field verifiable | 280 Acres | 280 | 349.54 | 349.54 | 349.54 | Target met | N/A | 17 | 100% | 2024 Fuel Management List 2024 Fuel Management Tracking Project Summaries (DR038) | 124% | Initiative validated | 1545000 | 1267477.93 | -17.96% | Underspend | Liberty's initial projections for its 2024 Wood and Slash Management Program were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-VFM-03 | 8.2.3.5 | Substation Defensible Space | Non-focus & non-field verifiable | No Target | 0 | 23 | 23 | 23 | Target met | N/A | 13 | 100% | Records of substation clearing completion (DR062) | 100% | Initiative validated | 20600 | 62320.96 | 202.5% | Overspend | Liberty's initial projections for its 2024 Substation Defensible Space were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-VFM-04 | 8.2.3.7 | Fire-Resilient Right-of-Ways | Non-focus & non-field verifiable | No Target | 0 | 13.2 | 13.2 | 13.2 | Target met | N/A | 13.2 | 100% | Records of right-of-way clearing completion (DR063) | 100% | Initiative validated | 262650 | 821204.93 | 212.7% | Overspend | Liberty's initial projections for Fire Resilient ROWS were inaccurate. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-VFM-05 | 8.2.3.3 | Clearance | Focus & non-field verifiable | No Target | 0 | 702.1 | 702.1 | 702.1 | Target met | N/A | 83 | 100% | Records of VM inspections and maintenance completion (DR064) | 100% | Initiative validated | 913507 | 996356.88 | 9.069% | Overspend | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-VFM-06 | 8.2.3.4 | Fall-In Mitigation | Focus & field verifiable | 220 Line Miles | 220 | 364 | 364 | 364 | Target met | N/A | 88.4 | 100% | Field Inspections Records of fall-in mitigation completion (DR065.c) | 165.5% | Initiative validated | 7982500 | 3254922.15 | -59.22% | Underspend | Liberty's initial projections for 2024 Fall-In Mitigation were inaccurate. Spend is dependent on work required in the field found from inspections. Liberty is maintaining targets for vegetation inspections, but mitigation work was lower than anticipated. | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-VFM-07 | 8.2.3.6 | High-Risk Species | Non-focus & non-field verifiable | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Vegetation Management and Inspections | WMP-VM-VFM-08 | 8.2.3.8 | Emergency Response Vegetation Management | Non-focus & non-field verifiable | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 6444.72 | 100% | Overspend | Liberty does not project costs for this WMP initiative as work is uncertain at the time of WMP submission. | N/A | No risk reduction goal was identified for this initiative
Situational Awareness and Forecasting | WMP-SA-01 | 8.3.2 | Environmental monitoring systems | Non-focus & non-field verifiable | Unknown | 0 | 0 | 0 | 0 |  | N/A | N/A | N/A | Liberty Written Response (DR031) | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Situational Awareness and Forecasting | WMP-SA-02 | 8.3.3 | Grid monitoring systems | Focus & non-field verifiable | 10 Circuits with Fault Indicators | 10 | 15 | 15 | 15 | Target met | N/A | 15 | 100% | FI Installation List (DR032) FI Past Orders FI 2024 PO NLT FI Install Work Order 2024 (DR032.b) | 150% | Initiative validated | 150000 | 421609.56 | 181.1% | Overspend | Liberty exceeded its 2024 WMP target for fault indicators by 50% and costs were higher than expected. | N/A | No risk reduction goal was identified for this initiative
Situational Awareness and Forecasting | WMP-SA-03 | 8.3.4 | Fire detection and alarm systems | Non-focus & non-field verifiable | Unknown | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Liberty Written Response (DR033) | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Situational Awareness and Forecasting | WMP-SA-04 | 8.3.5 | Weather forecasting | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 331988.73 | 100% | Overspend | Liberty incurred costs not forecasted for 2024, including weather station maintenance and calibration costs and implementations costs for Liberty's weather dashboard. | N/A | No risk reduction goal was identified for this initiative
Situational Awareness and Forecasting | WMP-SA-05 | 8.3.6 | Fire Potential Index | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Situational Awareness and Forecasting | WMP-SA-06 | 6.2.2.1 | Ignition likelihood calculation | Non-focus & non-field verifiable | Model Enhancements | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | WMP Model Documentation Reax Liberty PSPS Threshold Exceedance Analysis Phase 2 Risk Preliminary Risk Circuits (DR036) | 100% | Initiative validated | 683807 | 1224799.47 | 79.11% | Overspend | Costs were higher than projected due to increase in wildfire and PSPS risk modeling efforts. | N/A | No risk reduction goal was identified for this initiative
Situational Awareness and Forecasting | WMP-SA-07 | 6.2.2.2 | Ignition consequence calculation | Non-focus & non-field verifiable | Model Enhancements | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Emergency Preparedness | WMP-EP-01 | 8.4.2 | Wildfire and PSPS emergency preparedness plan | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | CERP Fireland Incident Response Guide PSPS Playbook (DR011) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Emergency Preparedness | WMP-EP-02 | 8.4.3 | Collaboration and coordination with public safety partners | Non-focus & non-field verifiable | Conduct emergency drills. Continue engagement with local stakeholders, meet with Community Advisor Board | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Meeting Notes (DR012) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Emergency Preparedness | WMP-EP-03 | 8.4.4 | Public notification and communication strategy | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Liberty WCAB Attendance PSPS Playbook (DR013) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Emergency Preparedness | WMP-EP-04 | 8.4.5 | Preparedness and planning for service restoration | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Corporate Emergency Management Plan (DR014) | 100% | Initiative validated | 1437734.4739 | 426082.45 | -70.36% | Underspend | Liberty's costs for this initiative were lower than projected for 2024 because all projected costs were not incurred. | N/A | No risk reduction goal was identified for this initiative
Emergency Preparedness | WMP-EP-05 | 8.4.6 | Customer support in wildfire and PSPS emergencies | Non-focus & non-field verifiable | Conduct incident command training, hold a virtual PSPS tabletop exercise. Continue implementation of AFN Plan. | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | 2024 Liberty ICS Training 2024 Functional Exercise Folder 2024 Tabletop Exercise Folder (DR015) | 100% | Initiative validated | 105000 | 122974.29 | 17.12% | Overspend | Liberty experienced its first actual PSPS event in 2024 and thus had higher than projected costs in 2024. | N/A | No risk reduction goal was identified for this initiative
Emergency Preparedness | WMP-EP-06 | 0 | Learning after wildfire and PSPS events | Non-focus & non-field verifiable | After action report for each event | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | De-Energization Improvement Items PSPS Meeting Events for Nov. (DR016) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Community Outreach and Engagement | WMP-CO-01 | 8.5.2 | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | Non-focus & non-field verifiable | 2 Wildfire & PSPS Outreach Surveys | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | June ’24 Summary Report December ’24 Summary Report Liberty 2025 Plan to Address AFN Pop. (DR006) | 100% | Initiative validated | 90000 | 112302.64 | 24.78% | Overspend | Liberty included additional labor costs not initially forecasted in its 2024 WMP. | N/A | No risk reduction goal was identified for this initiative
Community Outreach and Engagement | WMP-CO-02 | 0 | Public engagement in WMP decision-making process | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Liberty Written Response (DR007) | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Community Outreach and Engagement | WMP-CO-03 | 8.5.3 | Engagement with AFN populations, local governments, and tribal communities | Non-focus & non-field verifiable | Target Not Set | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | June ’24 Summary Report December ’24 Summary Report Liberty 2025 Plan to Address AFN Pop. (DR008) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Community Outreach and Engagement | WMP-CO-04 | 8.5.4 | Collaboration on local wildfire mitigation and planning | Non-focus & non-field verifiable | N/A | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Liberty Written Response (DR009) | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Community Outreach and Engagement | WMP-CO-05 | 8.5.5 | Best practice sharing with other electrical corporations | Non-focus & non-field verifiable | Participation in Working Groups and Joint IOU Councils | 0 | 0 | 0 | 0 | Target met | N/A | N/A | N/A | Statewide Council Meeting Notes Collab Council Meeting Notes Q2 Joint IOU AFN Meeting Notes Q2 Joint IOU AFN Statewide Council Meeting Notes Q3 Joint IOU AFN Collaborative Council Meeting Q3 Joint IOU AFN Statewide Council Meeting Q4 Statewide Council Meeting Notes Q4 Collaborative Council Notes (DR010) | 100% | Initiative validated | 0 | 0 | 0% | No Variance | Less than 10% variance | N/A | No risk reduction goal was identified for this initiative
Note on K11: Number of "actuals" from which samples are selected

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Liberty Utilities
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2025-05-20 | 2025-06-02 | QAQC Questions | LU_DR001 | LU_DR001_QAQC Questions_20250602 Asset_Inspection_QA-QC_2023-Final VM-04_Post_Work_Verification_2.0
2025-05-21 | 2025-06-03 | Funding Verification | LU_DR005 | Liberty Response_LU_DR005
2025-04-22 | 2025-04-28 | WMP-CO-01 | LU_DR006 | R1812005-Liberty 2025 Plan to Address AFN Populations During De-Energization Events {B} 240248 - Liberty - Wildfire Messaging Awareness December 2024 Summary Report {B} 240111 - Liberty - Wildfire Messaging Awareness June 2024 Summary Report
2025-04-22 | 2025-04-28 | WMP-CO-02 | LU_DR007 | Liberty Response_LU_DR007
2025-04-22 | 2025-04-28 | WMP-CO-03 | LU_DR008 | R1812005-Liberty 2025 Plan to Address AFN Populations During De-Energization Events {B} 240111 - Liberty - Wildfire Messaging Awareness June 2024 Summary Report {B} 240248 - Liberty - Wildfire Messaging Awareness December 2024 Summary Report Final MOU TCPUD PSPS_5.22.23_tcpud signed
2025-04-22 | 2025-04-28 | WMP-CO-04 | LU_DR009 | Liberty Response_LU_DR009
2025-04-22 | 2025-04-28 | WMP-CO-05 | LU_DR010 | 2024 03-20 Statewide Council Meeting Notes 2024 03-27 Collab Council Meeting Notes FINAL_Meeting Notes_Q2 Joint IOU AFN Collaborative Council Meeting_20240610 Final_Q2 Joint IOU AFN Statewide Council Meeting Notes_20240624 FINAL_Q4 Collaborative Council Notes_20250115 NOTES_Q3 Joint IOU AFN Collaborative Council Meeting Notes_Q3 Joint IOU AFN Statewide Council Meeting_20240917 Q4 Statewide Council Meeting Notes_20250115
2025-04-22 | 2025-04-28 | WMP-EP-01 | LU_DR011 | Corporate Emergency Management Plan Liberty Post-Event Report on November 11 2024 PSPS Event Liberty Post-Event Report on November 13 2024 Potential PSPS Event Liberty Post-Event Report on November 20 2024 PSPS Event Liberty Post-Event Report on November 22 2024 PSPS Event Liberty Wildland-Fire-Incident Response Guide Final PSPS Playbook_9.21.2023 R1812005-Liberty CalPeco 2024 Post Season Rpt
2025-05-23 | 2025-06-03 | EP-02 | LU_DR012 | FINAL_Meeting Notes_Q2 Joint IOU AFN Collaborative Council Meeting_20240610 File 1 - Q4 Statewide Council Meeting Notes (1 document) File 2 - Dec. El Dorado CAC Minutes (1 document) File 3 - Jan. El Dorado CAC Minutes (1 document) File 4 - May El Dorado CAC Minutes (1 document) File 5 - Oct. El Dorado CAC Minutes (1 document) File 6 - Q1 Collaborative Council Meeting Notes (1 document) File 7 - Q1 Statewide Council Meeting Notes (1 document) File 8 - Q2 Statewide Council Meeting Notes (1 document) File 9 - Q3 Collaborative Council Meeting Notes (1 document) File 10 - Q3 Statewide Council Meeting Notes (1 document) File 11 - LU_DR012 Subfile 1 - Mar. El Dorado CAC Minutes (1 document) Subfile 2 - Q4 Collaborative Council Meeting Notes (1 document)
2025-04-22 | 2025-04-28 | WMP-EP-03 | LU_DR013 | Liberty_WCAB_Attendance PSPS Playbook_9.21.2023
2025-05-23 | 2025-06-02 | EP-04 | LU_DR014 | Corporate Emergency Management Plan
2025-04-22 | 2025-04-28 | WMP-EP-05 | LU_DR015 | 2024 Liberty ICS Training 2024 Functional Exercise folder: Evaluation of PSPS Exercise June 27, 2024, Liberty Utilities 2024 PSPS Functional Exercise Agenda, PSPS Functional Exercise June 27, 2024, PSPS Functional Exercise Recording Document 2024 Tabletop Exercise folder: Evaluation of TTX May 23, 2024, Liberty Utilities 2024 PSPS Table Top Exercise Agenda, PSPS Tabletop Exercise Recording Document, Table Top PSPS Exercise May 2024
2025-04-22 | 2025-04-28 | WMP-EP-06 | LU_DR016 | After Action Review Meeting PSPS Events Nov 11, 13, 20 and 22, 2024 Attachment 3-POSTR1 Section IV.5 - DRAFT2
2025-04-22 | 2025-04-28 | WMP-GDOM-AI-01 | LU_DR018 | LU_DR018_Response
2025-05-06 | 2025-05-16 | WMP-GDOM-AI-01 | LU_DR018.b | File 1: LU_DR018.b_AI-01 Sample Request.xlx LU_DR018.B.xlx 155685_Sierra_Brooks_51_Pole.pdf 205130_Meyers_3300_Pole.pdf 224188_Glenshire_7400_Pole.pdf 269561_Tahoe_City_7200_Pole.pdf 295462_Muller_1296_Pole.pdf 295479_Topaz_1202_Pole.pdf 296944_111_Pole.pdf 51820_Portola_3100_Padmount_Transformer.pdf 66637_Meyers_3500_Pole.pdf 80868_Meyers_3200_Pole.pdf 98764_Stateline_3501_Pole.pdf 98802_640_Pole.pdf 511463_Tahoe_City_5201_Padmount_Transformer.pdf Kingsbury_2800_Padmount_Transformer.pdf File 2: LU_DR018.B.xlx.csv
2025-04-22 | 2025-04-28 | WMP-GDOM-AI-02 | LU_DR019 | 2024 Liberty Intrusive Inspections Data
2025-05-13 | 2025-05-16 | WMP-GDOM-AI-02 | LU_DR019.b | Liberty Response_LU_DR019.b.doc
2025-04-22 | 2025-04-28 | WMP-GDOM-AI-03 | LU_DR020 | LU_DR020_Response
2025-05-06 | 2025-05-16 | WMP-GDOM-AI-03 | LU_DR020.b | File 1: LU_DR020.B.xlx File 2: LU_DR020.B.xlx LU_DR010.b_AI-03 Sample Request.xlx 35133_Kings_Beach_5200_Pole.pdf 45096_Stateline_3101_Pole.pdf 61302_Kings_Beach_5200_Pole.pdf 85740_Kings_Beach_5200_Pole.pdf 94926_Stateline_3101_Pole.pdf 206927_Cemetery_42_Pole.pdf 248901_Russell_Valley_7900_Pole.pdf 294738_Meyers_3100_Pole.pdf
2025-04-22 | 2025-04-28 | WMP-GDOM-AI-06 | LU_DR021 | Substation Inspections 2023
2025-05-13 | 2025-05-16 | WMP-GDOM-AI-06 | LU_DR021.b | Liberty Response_LU_DR021.b.word Substation Inspections 2023_updated.xlx 21.b.2024 Substation Inspection w HFTD.xlsx
2025-04-22 | 2025-04-28 | WMP-GDOM-GH-06 | LU_DR022 | Liberty Response_LU_DR022 Appendix B - UNR Liberty Fire Mitigation Study
2025-04-22 | 2025-04-28 | WMP-GDOM-GH-07 | LU_DR023 | Liberty Response_LU_DR023
2025-05-02 | 2025-05-07 | WMP-GDOM-GH-07 | LU_DR023.b | Liberty 2024 WMP Update Change Order Report_05282024
2025-04-22 | 2025-04-28 | WMP-GDOM-GH-08 | LU_DR024 | Recloser Installs 2022-2025 Test Report - CEM_41CB_SEL-651RA Test Report - CEM_42CB_SEL-651RA Test Report - MEY_3400-R1_SEL-651RA Test Report - TAH_7300-R1_SEL-651RA Test Report - TPZ_1261-R1_SEL-651RA
2025-05-02 | 05.07.25 | WMP-GDOM-GH-08 | LU_DR024.b | Liberty Response_LU_DR024.b SRB_51-CB_SEL-651RA_TEST-RESULTS_20250123
2025-04-22 | 2025-04-28 | WMP-GDOM-GH-09 | LU_DR025 | Liberty Response_LU_DR025
2025-05-02 | 2025-05-07 | WMP-GDOM-GH-09 | LU_DR025.b | Liberty 2024 WMP Update Change Order Report_05282024
2025-04-22 | 2025-04-28 | WMP-GDOM-GH-12d | LU_DR027 | Liberty Response_LU_DR027
2025-04-22 | 2025-04-28 | WMP-GDOM-GH-12e | LU_DR028 | LU_DR028_Response _Example_Grey_Open_Wire_QAQC Reports folder: (55 items for Tahoe City)
2025-04-22 | 2025-04-28 | WMP-GDOM-GH-12f | LU_DR029 | Portola In-Service Portola Streetview - New (photo) Portola Streetview - Old (photo) Portola Substation - New (photo)
2025-04-22 | 2025-04-28 | WMP-GDOM-GO-03 | LU_DR030 | 2024-05-14 Annual FPP Sign-in Sheet 2024-05-14 Annual FPP Training FPP_Smoke_FieldServicesTraining_SignIn_072524 Liberty Fire Refresher 24 LU Fire Prevention Plan 10-9-2020 tailboard_briefing_checklist-days FPP Operating Policy was implemented VM Training_Fire_Prevention_Plan_refresher_09.03.24
2025-04-22 | 2025-04-28 | WMP-SA-01 | LU_DR031 | Liberty Response_LU_DR031
2025-04-22 | 2025-04-28 | WMP-SA-02 | LU_DR032 | FI doc - Sept 2024
2025-05-13 | 2025-05-20 | WMP-SA-02 | LU_DR032.b | Fault Indicator Past Orders.xlsx Fault Indicators Purchase Order_2024.png Liberty Response_LU_DR032.b.doc NLT Fault Indicator Install Work Order 2024.png Purchase Order_4500003366.pdf
2025-04-22 | 2025-04-28 | WMP-SA-03 | LU_DR033 | Liberty Response_LU_DR033
2025-04-22 | 2025-04-28 | WMP-SA-04 | LU_DR034 | 2024 CloudFire Weather Forecasting 2024 Fuel Moisture Sampling 2024 Technosylva Weather Forecasting 2024 Weather Forecast Meeting Notes
2025-04-22 | 2025-04-28 | WMP-SA-05 | LU_DR035 | 2024 CloudFire Weather Forecasting 2024 Fuel Moisture Sampling 2024 Technosylva Weather Forecasting
2025-05-13 | 2025-05-16 | SA-06/SA-07 | LU_DR036 | B1 - WMP Model Documentation_TSYL_2024_Appendix.pdf B5 - Reax Liberty PSPS Threshold Exceedance Frequency Analysis.word IMLB - Phase 2 – Risk.pdf Preliminary Risk Circuits.xl
2025-04-22 | 2025-04-28 | WMP-VM-VFM-02 | LU_DR038 | 2024_Fuel_Management 2024_Fuel_Management_Tracking Angora PH 1 Wood Removals Angora Ridge - Helicopter Logging, Vegetation Management Hobart Fuel Management Project Summary and Report Martis Peak Rd Buffer Project Summary Report
2025-05-01 | 2025-05-06 | WMP-GDOM-AI-04 | LU_DR039 | Liberty Data Request LU_DR039 - WMP-GDOM-AI-04
2025-05-27 | 2025-06-02 | WMP-GDOM-AI-04 | LU_DR039.b | Liberty Response_LU_DR039.b
2025-05-01 | 2025-05-06 | WMP-GDOM-AI-05 | LU_DR040 | LU_DR040_Detailed_Reinspection
2025-05-27 | 2025-06-02 | WMP-GDOM-AI-05 | LU_DR040.b | LU_DR40b
2025-05-01 | 2025-05-06 | WMP-GDOM-GH-01 | LU_DR041 | Liberty_Covered_Conductor.gdb 100% Design-DCA.0000048.CE.0015-Angora Lateral 100% Design-DCA.0000048.CE.0015-Angora Ridge 100% DESIGN-DCA.0000048.CE.0018-7300 Phase 9-WMP Cover Cond FALLEN LEAF C_AS-BUILTS AND XFMR CUT SHEETS Liberty Data Request LU_DR041 - WMP-GDOM-GH-01
2025-05-01 | 2025-05-06 | WMP-DGOM-GH-03 | LU_DR043 | LU_DR043_Pole_Replacements
2025-05-01 | 2025-05-06 | WMP-GDOM-GH-05 | LU_DR045 | Liberty_TraditionalHardening_2024.gdb Copy of Liberty Data Request LU_DR045 - WMP-GDOM-GH-05 DCA.TPZLNP1.CE.0001-Topaz Lane Tap Rbld Ph1-REV1-signed DCA.TPZLNP2.CE.0001-Topaz Lane Tap Rbld Ph2-REV 1-signed
2025-05-01 | 2025-05-06 | WMP-GDOM-GH-12a | LU_DR048 | LU_DR048_Tree_attachment_removals
2025-05-27 | 2025-06-02 | WMP-GDOM-GH-12a | LU_DR048.b | LU_DR48b
2025-05-01 | 2025-05-06 | WMP-GDOM-GH-12b | LU_DR049 | LU_DR049_Expulsion_Fuse_replacements
2025-05-05 | 2025-05-08 | WMP-GDOM-GH-12c | LU_DR050 | Liberty Response_LU_DR050
2025-05-01 | 2025-05-08 | WMP-GDOM-GO-01 | LU_DR051 | FI doc - Sept 2024 fi doc hob7700 and gls7600 fi doc
2025-05-27 | 2025-06-02 | WMP-GDOM-GO-01 | LU_DR051.b | Liberty Response_LU_DR051.b File 1 - EFS Testing.zip (25 items)
2025-05-05 | 2025-05-08 | WMP-GDOM-GO-02 | LU_DR052 | Liberty Response_LU_DR052 Outage Process Flow
2025-05-05 | 2025-05-12 | WMP-GDOM-GO-05 | LU_DR054 | SME Interview scheduled 5/15
2025-05-05 | 2025-05-08 | WMP-GDOM-MR-01 | LU_DR055 | LU_DR055_Repairs
2025-05-27 | 2025-06-02 | WMP-GDOM-MR-01 | LU_DR055.b | Liberty Response_LU_DR055.b
2025-05-05 | 2025-05-12 | WMP-VM-ESG-01 | LU_DR056 | SME Interview scheduled 5/14
2025-05-01 | 2025-05-06 | WMP-VM-INSP-01 | LU_DR057 | LU_DR057
2025-05-27 | 2025-05-30 | WMP-GDOM-INSP-01 | LU_DR057.b | Liberty Responses_IE DR_05302025
2025-05-01 | 2025-05-06 | WMP-VM-INSP-02 | LU_DR058 | LU_DR058
2025-05-27 | 2025-05-30 | WMP-GDOM-INSP-02 | LU_DR058.b | Liberty Responses_IE DR_05302025
2025-05-01 | 2025-05-06 | WMP-VM-INSP-03 | LU_DR059 | LU_DR059 LiDAR Span Inspections 2024
2025-05-27 | 2025-05-30 | WMP-GDOM-INSP-03 | LU_DR059.b | Liberty Responses_IE DR_05302025
2025-05-01 | 2025-05-06 | WMP-VM-QAQC-01 | LU_DR060 | LU_DR060 QC photo reports (70 photos) LU_DR060 2024_liberty_work_complete_qc
2025-05-27 | 2025-05-29 | WMP-GDOM-QAQC-01 | LU_DR060.b | Liberty Response_LU_DR060.b 2024_VM_QC_All_Data 2024 QC of Completed Tree Work Projects
2025-05-01 | 2025-05-06 | WMP-VM-VFM-01 | LU_DR061 | LU_DR061_Pole_Clearing
2025-05-27 | 2025-05-30 | WMP-GDOM-VFM-01 | LU_DR061.b | Liberty Responses_IE DR_05302025
2025-05-01 | 2025-05-06 | WMP-VM-VFM-03 | LU_DR062 | Liberty Sub Footprints Final.kmz Liberty_Substations Liberty Fall 2024 Pre-Emergent Applciation Data Liberty Jobsheets Fall 2024 Liberty Spring 2024 Cycle 2 Job Sheets Liberty Spring 2024 Chemical Use Reports
2025-05-01 | 2025-05-06 | WMP-VM-VFM-04 | LU_DR063 | LU_DR063 TCS Project Tracker _ Martis Peak Roadside Fuelbreak _ Project Detail LU_DR063 Martis Peak Rd Buffer Project Summary Report LU_DR063 Martis Peak Project Span Data LU_DR063_2024 Fire Resilient ROW Project List LU_DR063_Fallen_Leaf_And_Angora_Projects
2025-05-27 | 2025-05-30 | WMP-GDOM-VFM-04 | LU_DR063.b | Liberty Responses_IE DR_05302025
2025-05-01 | 2025-05-06 | WMP-VM-VFM-05 | LU_DR064 | LU_DR064_Clearance_Miles LU_DR064_Clearance_Work
2025-05-27 | 2025-05-30 | WMP-GDOM-VFM-05 | LU_DR064.b | Liberty Responses_IE DR_05302025
2025-05-01 | 2025-05-06 | WMP-VM-VFM-06 | LU_DR065 | LU_DR065 Fall-In Mitigation Completed Work LU_DR065_Fall_In_Mitigation_Mileage
2025-05-15 | 2025-05-20 | WMP-VM-VFM-06 | LU_DR065.b | LU_DR065.b.xlsx
2025-05-27 | 2025-05-28 | WMP-GDOM-VFM-06 | LU_DR065.c | Liberty Response_LU_DR065.c.word 2024 Fallin Agg.xlsx
2025-05-01 | 2025-05-06 | WMP-VM-VFM-07 | LU_DR066 | Liberty Response_LU_DR066
2025-05-01 | 2025-05-06 | WMP-VM-VFM-08 | LU_DR067 | VM-02-3_Vegetation Management Plan VM-03_Hazard_Tree_Plan_1.0 VM-05.2_Vegetation Threat Procedure VM-07_Vegetation_Inspection_Manual_1.0
2025-05-27 | 2025-05-30 | WMP-GDOM-VFM-08 | LU_DR067.b | Liberty Responses_IE DR_05302025

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Liberty Utilities
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2025-05-14 | VM-ESG-01 - DR056 | SME001 | Data Analyst; Sr. Mgr. Willdfire Prevention; Manager, Vegetation Management | Overview of Veg. Management Enterprise System and 2024 upgrades; field data collected (inspections, LiDAR, tree work, pole clearning, etc.) imported into SQL database; streamlined manual efforts, improved data accuracy and provide Energy Safety updates and quarterly compliance reports; QAQC enforced through mandatory form and vendor confirms exports; dashboards alert any anomalies in real time.
2025-05-15 | GDOM-GO-05 | SME002 | Data Analyst | Overview of Asset Management Enterprise System implemented in 2024; data collected in Fulcrum App; everything consolidted into one program vs. multiple programs previously used; can provide layered filters and appy pins; deep dive into pictures and pole information, inventory and parts for build out events; event types, codes for inspections, priorities, levels of repairs etc. codes to red for repairs.
2025-06-06 | Financial | SME003 | Manager, Regulatory Affairs & Sr. Manager, Wildfire Prevention | Understanding of Q4 ADR and recent ARC report involving process for creating and estimating WMP budgets and reasons behind variances greater than 10% between planned and and actual spend across various initiatives. The projections were developed prior to filing and 2024 was a unique year where there was not a process for WMP updates and a change order was submitted to Energy Safey that was denied based on criteria. The accounting system is a large factor contributing to the variances. A new SAP tracking system went live in Q4 2023. The old system and the new system were designed to report the granular reporting required for initiative levels. This created changes in mapping projections and how costs were recorded in 2024. Other factors contributing to variances were permit delays, backlog of pole replacmetns, staffing or system limitations, findings scope adjustment, contractor and vendor changes, and costs for program developments.

## Tab 5 - List of "Fail-to-Fund"
List of Failed-to-Fund Initiatives
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Liberty
WMP Category | WMP Section Number | WMP Page Number | Initiative Tracking ID | Initiative Name | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%)
Grid Design Operations and Maintenance | 8.1.3.4 | 177 | WMP-GDOM-AI-04 | Other discretionary inspections of distribution electric lines and equipment | 1000000 | 363867 | 63.61%
Grid Design Operations and Maintenance | 8.1.3.6 | 178 | WMP-GDOM-AI-06 | Substation inspections | 10000 | 0 | 100%
Grid Design Operations and Maintenance | 8.1.2.1 | 154 | WMP-GDOM-GH-01 | Covered conductor installation | 8627427 | 8312596 | 3.649%
Grid Design Operations and Maintenance | 8.1.2.2 | 160 | WMP-GDOM-GH-02 | Undergrounding of electric lines and/or equipment | 8482680 | 46067 | 99.46%
Grid Design Operations and Maintenance | 8.1.2.5 | 162 | WMP-GDOM-GH-05 | Traditional overhead hardening | 3500000 | 1863709 | 46.75%
Grid Design Operations and Maintenance | 8.1.2.6 | 163 | WMP-GDOM-GH-06 | Emerging grid hardening technology installations and pilot progress | 3050000 | 0 | 100%
Grid Design Operations and Maintenance | 8.1.2.7 | 165 | WMP-GDOM-GH-07 | Microgrids | 1500000 | 0 | 100%
Grid Design Operations and Maintenance | 8.1.2.9 | 167 | WMP-GDOM-GH-09 | Line removal (in HFTD) | 500000 | 0 | 100%
Grid Design Operations and Maintenance | 8.1.2.12 | 168 | WMP-GDOM-GH-12c | Animal guards | 100000 | 0 | 100%
Grid Design Operations and Maintenance | 8.1.2.12 | 168 | WMP-GDOM-GH-12e | Open wire/grey wire | 2000000 | 1754773 | 12.26%
Grid Design Operations and Maintenance | 8.1.8.1 | 190 | WMP-GDOM-GO-01 | Equipment settings to reduce wildfire risk | 800000 | 0 | 100%
Grid Design Operations and Maintenance | 8.1.8.3 | 193 | WMP-GDOM-GO-03 | Personnel work procedures and training in conditions of elevated fire risk | 298088 | 0 | 100%
Grid Design Operations and Maintenance | 8.1.4 | 179 | WMP-GDOM-MR-01 | Equipment maintenance and repair | 500000 | 0 | 100%
Vegetation Management and Inspections | 8.2.2.1 | 219 | WMP-VM-INSP-01 | Vegetation Management Inspection Program - Detailed | 813515 | 763520 | 6.146%
Vegetation Management and Inspections | 8.2.2.3 | 221 | WMP-VM-INSP-03 | Vegetation Management Inspection Program - LiDar | 721000 | 563342 | 21.87%
Vegetation Management and Inspections | 8.2.3.2 | 223 | WMP-VM-VFM-02 | Wood and Slash Management | 1545000 | 1267478 | 17.96%
Vegetation Management and Inspections | 8.2.3.4 | 227 | WMP-VM-VFM-06 | Fall-In Mitigation | 7982500 | 3254922 | 59.22%
Emergency Preparedness | 8.4.5 | 337 | WMP-EP-04 | Preparedness and planning for service restoration | 1437734 | 426082 | 70.36%
Note on E11: Kopunova, Sara: If applicable since some commitments occur outside of initiatives