## Tab 1 - Overview tab
IE ARC Attachments
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Horizon West Transmission
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted
Tab 5 | List of Failed-to-Fund Initiatives - All initiatives funded less than 100%

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: |  | Bureau Veritas
Electrical Corporation: |  | Horizon West Transmission
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC ARC) | EC-Claimed Progress | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | Initiative Validation Rate (%) | IE Finding on Initiative | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | 001 | 8.1.3.1 | Asset Inspection | Focus & non-field verifiable | Monthly inspections | Monthly inspections | Monthly inspections | Monthly inspections | Monthly inspections | Target met | N/A | 12 | 100% | Monthly Asset Condition Assessment Reports (DR001) | 100% | Initiative validated | 66 | 225.9 | 242.3% | Overspend | HWT continued its cadence of monthly asset inspections and monitoring. Costs were higher than plan due to reclassification of employee time spent on these activities. Additionally, HWT had minor carryover costs from project(s) completed in 2023 which were paid in 2024 and identifies those cost in this initiative category. | N/A | No risk reduction goal identified for this initiative.
Vegetation Management and Inspections | 002 | 8.2.2.1 | Vegetation Inspections | Focus & non-field verifiable | Monthly inspections | Monthly inspections | Monthly inspections | Monthly inspections | Monthly inspections | Target met | N/A | 12 | 100% | Monthly Wildfire Condition Assessment Reports (DR002) | 100% | Initiative validated | 17 | 8.3 | 51.18% | Underspend | HWT engaged a third-party vendor to provide vegetation management services in 2024 which entailed weed abatement and management of the defensible space surrounding the Suncrest facility. Additionally, vegetation is inspected during the monthly asset inspections. Actual WMP spend is lower than planned spend primarily because of lower costs associated with asset inspections and vegetation management/inspections. | N/A | No risk reduction goal identified for this initiative.

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Horizon West Transmission
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2025-05-01 | 2025-05-06 | 001 - 8.1.3.1 - Asset Inspection | DR001 | Monthly Asset Condition Assessments - 2024, AMP Task - Annual Review of Monthly Inspection Reports, HWT NEET_Com60DaysAheadRpt 20240914
2025-05-01 | 2025-05-06 | 002 - 8.2.2.1 - Vegetation Inspections | DR002 | Monthly Wildfire Condition Assessments - 2024, AMP Task - Annual Review of Monthly Inspection Reports HWT NEET_Com60DaysAheadRpt 20240914

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Horizon West Transmission
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
N/A

## Tab 5 - List of "Fail-to-Fund"
List of Failed-to-Fund Initiatives
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | Horizon West Transmission
WMP Category | WMP Section Number | WMP Page Number | Initiative Tracking ID | Initiative Name | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%)
Grid Design Operations and Maintenance | 8.1.3.1 | 80 | 001 | Asset Inspection | 66 | 225.9 | 242.3%
Vegetation Management and Inspections | 8.2.2.1 | 103 | 002 | Vegetation Inspections | 17 | 8.3 | 51.18%
Emergency Preparedness | 8.4 | 89 | N/A | Third-party fire brigade support services | 70 | 68 | 2.857%
Note on E11: Kopunova, Sara: If applicable since some commitments occur outside of initiatives