## Tab 1 - Overview tab
IE ARC Attachments
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | BVES
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted
Tab 5 | List of Failed-to-Fund Initiatives - All initiatives funded less than 100%

## Tab 2 - Catalog of Initiati
Catalog of Initiatives
Independent Evaluator: |  | Bureau Veritas
Electrical Corporation: |  | BVES
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC ARC) | EC-Claimed Progress | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | Initiative Validation Rate (%) | IE Finding on Initiative | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | GD_1 | 8.1.2.1 | Covered Conductor Replacement Project | Focus & non-field verifiable | Covered Conductor Replacement Project | 12.9 Circuit Miles | 13.32 Circuit Miles | 13.32 Circuit Miles | 13.32 Circuit Miles | Complete | N/A | 13.32 Circuit Miles | 100% | Field Inspections Project Completion Data (DR046) Project As-Builts (DR046b) | 103% | Initiative Validated | 4737300 | 4595400 | 2.995% | Underspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_2 | 8.1.2.1 | Radford Line Replacement Project | Focus & non-field verifiable | Radford Line Replacement Project | 2.7 Circuit Miles | 2.8 Circuit Miles | 3.1 Circuit Miles | 2.8 Circuit Miles | Complete | N/A | 2.8 Circuit Miles | 100% | Field Inspections Project Completion Data (DR047) Project As-Builts (DR047b) | 104% | Initiative Validated | 3633600 | 5865300 | 61.42% | Overspend | CAPEX overrun. The project was estimated in 2020. Due to the significant time required to obtain a permit from the USFS, estimated costs were significantly less as labor and equipment costs increase over the 4 year period. Additionally, there were significant costs associated with environmental studies to support the permit, increase helicopter fees to support construction, delays resulting in additional demobilizations/mobilizations due to encountering an endangered species and the Line Fire. Other cost drivers were overtime needed to complete the before the winter season once access granted following the Line Fire and additional fiber optic cable work scope. | Yes | N/A
Grid Design Operations and Maintenance | GD_3 | 8.1.2.2 | Minor Undergrounding Upgrades Projects | Non-focus & non-field verifiable | Minor Undergrounding Upgrades Projects | No Target | N/A | N/A | N/A | Ongoing | N/A | 1 Project | 100% | Field Inspections Project Completion Data (DR052) | 100% | Initiative Validated | 303700 | 95300 | 68.62% | Underspend | CAPEX underrun. UG projects that BVES engages in are generally driven by the customer or local government and are generally new facilities. In 2024, they were less than budget. In 2023, minor UG projects was overrun by $524.9 thousand. Year-to-year variations are high due to the projects being customer and local government driven. | Yes | N/A
Grid Design Operations and Maintenance | GD_4 | 8.1.2.3 | Covered Conductor Replacement Project | Focus & non-field verifiable | Covered Conductor Replacement Project | 200 Poles | 262 Poles | 262 Poles | 262 Poles | Complete | N/A | 72 Poles | 100% | Field Inspections Project Completion Data (DR055) | 134% | Initiative Validated | 2030300 | 1969500 | 2.995% | Underspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_5 | 8.1.2.3 | Radford Line Replacement Project | Focus & non-field verifiable | Radford Line Replacement Project | 70 Poles | 83 Poles | 83 Poles | 83 Poles | Complete | N/A | 49 Poles | 100% | Field Inspections Project Completion Data (DR057) | 126% | Initiative Validated | 1557300 | 2513700 | 61.41% | Overspend | CAPEX overrun. The project was estimated in 2020. Due to the significant time required to obtain a permit from the USFS, estimated costs were significantly less as labor and equipment costs increase over the 4 year period. Additionally, there were significant costs associated with environmental studies to support the permit, increase helicopter fees to support construction, delays resulting in additional demobilizations/mobilizations due to encountering an endangered species and the Line Fire. Other cost drivers were overtime needed to complete the before the winter season once access granted following the Line Fire and additional fiber optic cable work scope. | Yes | N/A
Grid Design Operations and Maintenance | GD_6 | 8.1.2.3 | Evacuation Route Hardening Project | Focus & non-field verifiable | Evacuation Route Hardening Project | 500 Poles | 1,095 Poles | 1,095 Poles | 1,095 Poles | Complete | N/A | 85 Poles | 100% | Field Inspections Project Completion Data (DR058) | 186% | Initiative Validated | 808000 | 541300 | 33.01% | Underspend | CAPEX underrun. Annual target for 2024 was achieved (actually exceeded) at lower than budgeted. Labor was less than originally estimated. | Yes | N/A
Grid Design Operations and Maintenance | GD_7 | 8.1.2.4 | Transmission pole/tower replacements and reinforcements | Non-focus & non-field verifiable | Transmission pole/tower replacements and reinforcements | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance. | N/A | N/A
Grid Design Operations and Maintenance | GD_8 | 8.1.2.5 | Traditional overhead hardening | Non-focus & non-field verifiable | Traditional overhead hardening | No Target | N/A | N/A | N/A | Ongoing | N/A | 9 Maintenance Activities | 100% | Field Inspections Project Completion Data (060) | 100% | Initiative Validated | 809800 | 1669600 | 106.2% | Overspend | CAPEX overrun. CPAEX Overrun was due to additional overhead hardening work being conducted than estimated. In addition to resolving asset inspection findings, BVES has been proactively replacing non-exempt equipment (e.g. arresters) and splices. | Yes | N/A
Grid Design Operations and Maintenance | GD_9 | 8.1.2.6 | Emerging grid hardening technology installations and pilots | Non-focus & non-field verifiable | Emerging grid hardening technology installations and pilots | N/A | N/A | N/A | N/A | Not Started in 2024 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance. | N/A | N/A
Grid Design Operations and Maintenance | GD_10 | 8.1.2.7 | Bear Valley Solar Energy Project | Non-focus & non-field verifiable | Bear Valley Solar Energy Project | Perform Necessary Project Action | N/A | N/A | N/A | Not Started in 2024 | N/A | N/A | N/A | Battery & Solar Ruling BVES Testimony BVES Solar & Storage Application (DR014) | 100% | Initiative Validated | 0 | 0 | 0% | No Variance | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_11 | 8.1.2.7 | Energy Storage Project | Non-focus & non-field verifiable | Energy Storage Project | Perform Necessary Project Action | N/A | N/A | N/A | Not Started in 2024 | N/A | N/A | N/A | Battery & Solar Ruling BVES Testimony BVES Solar & Storage Application (DR015) | 100% | Initiative Validated | 0 | 0 | 0% | No Variance | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_12 | 8.1.2.8 | Substation Automation | Focus & non-field verifiable | Substation Automation | 3 Substations | 3 Substations | 3 Substations | 3 Substations | Complete | N/A | 3 Substations | 100% | Field Inspections Project Location Data (DR016) | 100% | Initiative Validated | 655900 | 1114300 | 69.89% | Overspend | CAPEX overrun. Overrun was due to higher labor costs than estimated to achieve proper connectivity with the three substations. Additionally, one of the substations had an underground fiber optic cable that needed to be repaired before the station could be connected to SCADA. Also, equipment related to automation was more expensive than estimated. | Yes | N/A
Grid Design Operations and Maintenance | GD_13 | 8.1.2.8 | Switch and Field Device Automation | Focus & non-field verifiable | Switch and Field Device Automation | 10 Switches | 10 Switches | 10 Switches | 10 Switches | Complete | N/A | 10 Switches | 100% | Field Inspections Project Completion Data (DR017) | 100% | Initiative Validated | 673600 | 1200300 | 78.19% | Overspend | CAPEX overrun. Overrun was due to higher costs than estimated for the switches and communications equipment and higher labor costs (more labor hours) than estimated to achieve proper connectivity with the switches to the SCADA system. Additionally, BVES hired a 3rd party to test the switches once received from the vendor prior to installing the switches as necessary quality control step; this had not be planned in the original budget. | Yes | N/A
Grid Design Operations and Maintenance | GD_14 | 8.1.2.8 | Capacitor Bank Upgrade Project | Focus & non-field verifiable | Capacitor Bank Upgrade Project | 6 Capacitor Banks | 4 Capacitor Banks | 4 Capacitor Banks | 4 Capacitor Banks | Missed Target | BVES installed 4 out of the 6 targeted capacitor banks | 4 Capacitor Banks | 100% | Field Inspections Project Completion Data (DR018) | 67% | Initiative Not Validated | 319100 | 692500 | 117% | Overspend | CAPEX overrun. Overrun was due to higher costs than estimated for the capacitor banks and communications equipment and higher labor costs (more labor hours) than estimated to achieve proper connectivity with the capacitor banks to the SCADA system. Additionally, BVES hired a 3rd party to test the capacitor banks once received from the vendor prior to installing the capacitor banks as necessary quality control step; this had not be planned in the original budget. | No | BVES installed 4 out of the 6 targeted capacitor banks
Grid Design Operations and Maintenance | GD_15 | 8.1.2.8 | Fuse TripSaver Automation | Focus & non-field verifiable | Fuse TripSaver Automation | 50 Fuse TripSavers | 27 Fuse TripSavers | 27 Fuse TripSavers | 27 Fuse TripSavers | Missed Target | The 2024 ARC, cites that while 50 Fuse TripSavers were installed, 23 devices could not be connected before year‑end due to connectivity issues even though those 23 units were installed and operational. | 27 FuseTripSavers | 100% | Field Inspections Project Completion Data (DR019) | 54% | Initiative Not Validated | 136900 | 297700 | 117.5% | Overspend | CAPEX overrun. Overrun was due to higher costs than estimated for the communications equipment and higher labor costs (more BVES and contracted labor hours) than estimated to achieve proper connectivity with the Fuse TripSavers to the SCADA system. | No | The 2024 ARC, cites that while 50 Fuse TripSavers were installed, 23 devices could not be connected before year‑end due to connectivity issues even though those 23 units were installed and operational.
Grid Design Operations and Maintenance | GD_16 | 8.1.2.8 | Server Room | Non-focus & non-field verifiable | Server Room | Project Milestone for Server Installation | Yearly Target Met | Yearly Target Met | Yearly Target Met | Complete | N/A | 1 Server Room | 100% | Field Inspections Project Completion Data (DR020) | 100% | Initiative Validated | 103200 | 61400 | 40.5% | Underspend | CAPEX underrun. The server room was completed under budget to the project specification. The decreased costs was driven by lower than anticipated costs to conduct modifications to the server room. | Yes | N/A
Grid Design Operations and Maintenance | GD_17 | 8.1.2.8 | Distribution Management Center | Non-focus & non-field verifiable | Distribution Management Center | Project Milestone for Distribution Management Center | Initiative Complete | Initiative Complete | Initiative Complete | Complete | N/A | 1 Distribution Management Center | 100% | Field Inspections Project Completion Data (DR047) | 100% | Initiative Validated | 37400 | 65300 | 74.6% | Overspend | CAPEX overrun. Costs for this project were higher than expected due to increase equipment costs and construction costs. | Yes | N/A
Grid Design Operations and Maintenance | GD_18 | 8.1.2.9 | Line removals (in HFTD) | Non-focus & non-field verifiable | Line removals (in HFTD) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | NA | N/A | N/A
Grid Design Operations and Maintenance | GD_19 | 8.1.2.10 | Tree Attachment Removal Project | Focus & non-field verifiable | Tree Attachment Removal Project | 100 Tree Attachments | 104 Tree Attachments | 104 Tree Attachments | 104 Tree Attachments | Complete | N/A | 54 | 100% | Field Inspections Project Completion Data (DR048) | 104% | Initiative Validated | 607200 | 699300 | 15.17% | Overspend | CAPEX overrun. Higher labor costs resulted in the CAPEX spend being higher than projected. | Yes | N/A
Grid Design Operations and Maintenance | GD_20 | 8.1.2.11 | Other grid topology improvements to mitigate or reduce PSPS events | Non-focus & non-field verifiable | Other grid topology improvements to mitigate or reduce PSPS events | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | Less than 10% variance. | N/A | N/A
Grid Design Operations and Maintenance | GD_21 | 8.1.2.12 | BVPP Phase 4 Upgrade Project | Non-focus & non-field verifiable | BVPP Phase 4 Upgrade Project | Project Milestone | N/A | N/A | N/A | Complete | N/A | N/A | N/A | -Executed Budget -Phase 4 PSPS Risk -Power Plant 2024 Timeline -SDP Invoice for Phase 3 (DR023) | 100% | Initiative Validated | 561600 | 594400 | 5.84% | Overspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_22 | 8.1.2.12 | Partial Safety and Technical Upgrades to Maltby Substation | Non-focus & non-field verifiable | Partial Safety and Technical Upgrades to Maltby Substation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 795000 | 794700 | 0.03774% | Underspend | Less than 10% variance. | N/A | N/A
Grid Design Operations and Maintenance | GD_23 | 8.1.2.12 | Safety and Technical Upgrades to Lake Substation | Non-focus & non-field verifiable | Safety and Technical Upgrades to Lake Substation | 64% of Project Completion | N/A | N/A | N/A | Not Started in 2024 | No progress has been made on the project and BVES did not meet 64% project completion | N/A | N/A | -QDR4 Table 1 -BVES 2024 WMP Updates R2 | 0% | Initiative Not Validated | 0 | 0 | 0% | Program Not Started in 2024 | #N/A | No | No progress has been made on the project and BVES did not meet 64% project completion
Grid Design Operations and Maintenance | GD_24 | 8.1.2.12 | Partial Safety and Technical Upgrades to Village Substation | Non-focus & non-field verifiable | Partial Safety and Technical Upgrades to Village Substation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | Program Not Started in 2024 | #N/A | N/A | N/A
Grid Design Operations and Maintenance | GD_25 | 8.1.3.1 | Detailed Inspections | Non-focus & non-field verifiable | Detailed Inspections | 51 Inspections | 51 Inspections | 51 Inspections | 51 Inspections | Complete | N/A | 14 Inspections | 100% | -Detailed Inspection Circuits (DR025) -Detailed Inspection Reports (DR025.b) | 100% | Initiative Validated | 13900 | 25300 | 82.01% | Overspend | OPEX overrun. Labor hours dedicated to this initiative were higher than forecasted. Annual was target achieved. | Yes | N/A
Grid Design Operations and Maintenance | GD_26 | 8.1.3.1 | Patrol Inspections | Non-focus & non-field verifiable | Patrol Inspections | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | Complete | N/A | 17 Circuit Miles | 100% | -Patrol Inspection Record (DR026) -Patrol Inspections (DR026.b) | 100% | Initiative Validated | 32400 | 58900 | 81.79% | Overspend | OPEX overrun. Labor hours dedicated to this initiative were higher than forecasted. Annual was target achieved. | Yes | N/A
Grid Design Operations and Maintenance | GD_27 | 8.1.3.1 | UAV Thermography | Non-focus & non-field verifiable | UAV Thermography | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | Complete | N/A | 17 Circuit Miles | 100% | -2024 UAV Report (DR027) -DR27.b Explanation -Pages From Big Bear City (DR027.b) | 100% | Initiative Validated | 77500 | 65200 | 15.87% | Underspend | OPEX underrun. BVES was able to contract the work for lower cost than projected. Intended scope of work and annual target was achieved. | Yes | N/A
Grid Design Operations and Maintenance | GD_28 | 8.1.3.1 | UAV HD Photography/Videography | Non-focus & non-field verifiable | UAV HD Photography/Videography | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | Complete | N/A | 17 Circuit Miles | 100% | -2024 UAV Report (DR028) | 100% | Initiative Validated | 77500 | 65200 | 15.87% | Underspend | OPEX underrun. BVES was able to contract the work for lower cost than projected. Intended scope of work and annual target was achieved. | Yes | N/A
Grid Design Operations and Maintenance | GD_29 | 8.1.3.1 | LiDAR Inspection | Non-focus & non-field verifiable | LiDAR Inspection | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | Complete | N/A | 17 Circuit Miles | 100% | -Mobile LiDAR Data (DR029) -Encroachments KMZ (DR029.b) | 100% | Initiative Validated | 79600 | 71800 | 9.799% | Underspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_30 | 8.1.3.1 | 3rd Party Ground Patrol | Non-focus & non-field verifiable | 3rd Party Ground Patrol | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | 205 Circuit Miles | Complete | N/A | 17 Circuit Miles | 100% | -Ground Inspection Log (DR030) | 100% | Initiative Validated | 64300 | 21400 | 66.72% | Underspend | OPEX underrun. BVES was able to contract the work for lower cost than projected. Intended scope of work and annual target was achieved. | Yes | N/A
Grid Design Operations and Maintenance | GD_31 | 8.1.3.1 | Intrussive Pole Inspections | Non-focus & non-field verifiable | Intrussive Pole Inspections | 850 Poles | 850 Poles | 850 Poles | 850 Poles | Complete | N/A | 18 Circuit Miles | 100% | -Intrusive Testing Results (DR031) -Intrusive Testing Follow-Up Procedure (DR031.b) | 100% | Initiative Validated | 19100 | 19300 | 1.047% | Overspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_32 | 8.1.3.1 | Substation inspections | Non-focus & non-field verifiable | Substation inspections | 144 Inspections | 156 Inspections | 156 Inspections | 156 Inspections | Complete | N/A | 16 Inspections | 100% | -Inspection Reports (DR032) | 108% | Initiative Validated | 283300 | 110500 | 61% | Underspend | OPEX underrun. The contracted portion of substation inspections (equipment testing) was achieved at a lower cost than estimated. Annual target was achieved. | Yes | N/A
Grid Design Operations and Maintenance | GD_33 | 8.1.4 | Equipment maintenance and repair | Non-focus & non-field verifiable | Equipment maintenance and repair | N/A | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -2024 QDR4 Table 11 (DR033) -Budget Breakdown (DR033.b) | 100% | Initiative Validated | 1073200 | 1440900 | 34.26% | Overspend | CAPEX overrun. Costs were higher than estimated to due more labor hours dedicated to conducting equipment maintenance and repair in response to inspection findings and storm damage. | Yes | N/A
Grid Design Operations and Maintenance | GD_34 | 8.1.5 | Asset management and inspection enterprise system(s) | Non-focus & non-field verifiable | Asset management and inspection enterprise system(s) | 1 | N/A | N/A | N/A | Ongoing | N/A | N/A | N/A | -Executed Contract -Meter Inspection Portal Response (DR034) | 100% | Initiative Validated | 57700 | 42800 | 25.82% | Underspend | OPEX underrun. Costs associated with updating and maintaining the asset management and inspection enterprise systems(s) were lower than forecasted due to lower than estimated labor costs. | Yes | N/A
Grid Design Operations and Maintenance | GD_35 | 8.1.6 | Asset Quality assurance / quality control | Non-focus & non-field verifiable | Asset Quality assurance / quality control | 20 Asset QCs | 20 Asset QCs | 20 Asset QCs | 20 Asset QCs | Complete | N/A | 13 Asset QCs | 100% | Asset QC Documentation (DR053, DR053.b) | 100% | Initiative Validated | 20300 | 22100 | 8.867% | Overspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_36 | 8.1.7 | Asset Open work orders | Non-focus & non-field verifiable | Asset Open work orders | All WO Resolved | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -BVES GO165 Procedures -BVES Inspection Schedule (DR035) | 100% | Initiative Validated | 17800 | 19300 | 8.427% | Overspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_37 | 8.1.8.1 | Equipment Settings to Reduce Wildfire Risk | Non-focus & non-field verifiable | Equipment Settings to Reduce Wildfire Risk | Review & Evaluate System Settings | Quarterly target Met | Quarterly target Met | Quarterly target Met | Ongoing | N/A | N/A | N/A | -Emergency Response & Disaster Plan -PSPS Procedures -Recloser Settings Clarification (DR036) | 100% | Initiative Validated | 5100 | 7100 | 39.22% | Overspend | OPEX overrun. Labor was less than estimated. All necessary activities planned for 2024 were achieved. This budget item is small ($5 thousand); therefore, it does not take much expense to significantly cause a cost variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_38 | 8.1.8.2 | Grid Response Procedures and Notifications | Non-focus & non-field verifiable | Grid Response Procedures and Notifications | Review & Update Procedure Annually | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Complete | N/A | N/A | N/A | -Firefighting Coordination Protocols (DR037) -Firefight Coordination Response -Emergency Response & Disaster Plan (DR037.b) | 100% | Initiative Validated | 8900 | 9700 | 8.989% | Overspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_39 | 8.1.8.3 | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | Non-focus & non-field verifiable | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | Review & Update Procedure Annually | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Complete | N/A | N/A | N/A | -PSPS Procedures -QAQC Personnel Work Procedures -PSPS Post Season Report 2024 -PSPS Procedure Review (DR054) | 100% | Initiative Validated | 3800 | 4100 | 7.895% | Overspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | GD_40 | 8.1.9 | Asset Workforce Planning | Non-focus & non-field verifiable | Asset Workforce Planning | Staffing Level Verified | Staffing Levels Verified | Staffing Levels Verified | Staffing Levels Verified | Complete | N/A | N/A | N/A | -Executed Outsource Contracts -Executed Work Change Orders -QAQC Asset Workforce Planning (DR056) | 100% | Initiative Validated | 6400 | 6900 | 7.812% | Overspend | Less than 10% variance. | Yes | N/A
Grid Design Operations and Maintenance | ST_1 | 5.4.5 | Environmental compliance and permitting | Non-focus & non-field verifiable | Environmental compliance and permitting | Annual Review & Update | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -Big Bear Power Line Biology Report (DR041) -Radford Survey Requirement (DR041.b) | 100% | Initiative Validated | 25400 | 31300 | 23.23% | Overspend | OPEX overrun. Permitting costs were higher than anticipated, which was related to the overall increase project work conducted in 2024. | Yes | N/A
Vegetation Management and Inspections | VM_1 | 8.2.2.1 | Detailed Inspections | Non-focus & non-field verifiable | Detailed Inspections | 51 Circuit Miles | 51 Circuit Miles | 51 Circuit Miles | 51 Circuit Miles | Complete | N/A | 20.74 Circuit Miles | 100% | Detailed Inspection Documentation (DR067, DR067.b) | 100% | Initiative Validated | 13900 | 25300 | 82.01% | Overspend | OPEX overrun. Labor hours dedicated to this initiative were higher than forecasted. Annual was target achieved. | Yes | N/A
Vegetation Management and Inspections | VM_2 | 8.2.2.1 | Patrol Inspections | Focus & non-field verifiable | Patrol Inspections | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | Complete | N/A | 69.9 Circuit Miles | 100% | Patrol Inspection Logs (DR069, DR069.b) | 100% | Initiative Validated | 32400 | 58900 | 81.79% | Overspend | OPEX overrun. Labor hours dedicated to this initiative were higher than forecasted. Annual was target achieved. | Yes | N/A
Vegetation Management and Inspections | VM_3 | 8.2.2.1 | UAV HD Photography/Videography | Non-focus & non-field verifiable | UAV HD Photography/Videography | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | Complete | N/A | 22 Circuit Miles | 100% | UAV HD Photography/Videography Documentation (DR077, DR077.b) | 100% | Initiative Validated | 77500 | 67200 | 13.29% | Underspend | OPEX underrun. BVES was able to contract the work for lower cost than projected. Intended scope of work and annual target was achieved. | Yes | N/A
Vegetation Management and Inspections | VM_4 | 8.2.2.1 | LiDAR Inspection | Non-focus & non-field verifiable | LiDAR Inspection | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | Complete | N/A | 22 Circuit Miles | 100% | Lidar Shapefiles (DR078) | 100% | Initiative Validated | 79600 | 71800 | 9.799% | Underspend | Less than 10% variance. | Yes | N/A
Vegetation Management and Inspections | VM_5 | 8.2.2.1 | 3rd Party Ground Patrol | Non-focus & non-field verifiable | 3rd Party Ground Patrol | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | 205 Circuit Miles Inspected | Complete | N/A | 22 Circuit Miles | 100% | 3rd Party Ground Patrol Inspection Records (DR079) | 100% | Initiative Validated | 64300 | 21400 | 66.72% | Underspend | OPEX underrun. BVES was able to contract the work for lower cost than projected. Intended scope of work and annual target was achieved. | Yes | N/A
Vegetation Management and Inspections | VM_6 | 8.2.2.1 | Substation inspections | Non-focus & non-field verifiable | Substation inspections | 144 Substations Inspected | 156 Substations Inspected | 156 Substations Inspected | 156 Substations Inspected | Complete | N/A | 20 Substations | 100% | Substation Inspection Records (DR080) | 108% | Initiative Validated | 4400 | 15000 | 240.9% | Overspend | OPEX overrun. Labor hours dedicated to this initiative were higher than forecasted. Annual was target achieved. | Yes | N/A
Vegetation Management and Inspections | VM_7 | 8.2.3.1 | Pole clearing | Non-focus & non-field verifiable | Pole clearing | Review and Update Procedure | Needs Met | Needs Met | Needs Met | Ongoing | N/A | N/A | 100% | BVES Written Response (DR081) Vegetation Management QC Policy and Procedure (DR081) WMP Planning Meeting Invite (DR081) | 100% | Initiative Validated | 0 | 0 | 0% | No Variance | Less than 10% variance. | Yes | N/A
Vegetation Management and Inspections | VM_8 | 8.2.3.2 | Wood and slash management | Non-focus & non-field verifiable | Wood and slash management | Contractor Adhere to Waste Removal | Contractor Met Requirements | Contractor Met Requirements | Contractor Met Requirements | Ongoing | N/A | N/A | 100% | BVES Written Response (DR082) Vegetation Management Contract (DR082) WMP Planning Meeting Invite (DR082) | 100% | Initiative Validated | 520400 | 453800 | 12.8% | Underspend | OPEX underrun. BVES was able to contract the work for lower cost than projected. All wood and slash was properly removed per BVES's vegetation management contract. | Yes | N/A
Vegetation Management and Inspections | VM_9 | 8.2.3.3 | Clearance | Focus & non-field verifiable | Clearance | 72 Circuit Miles | 100 Circuit Miles | 100 Circuit Miles | 100 Circuit Miles | Complete | N/A | 53 Circuit Miles | 100% | Clearance Shapefiles (DR083) | 139% | Initiative Validated | 2212800 | 1935400 | 12.54% | Underspend | OPEX underrun. BVES was able to contract the work for lower cost than projected. Intended scope of work and annual target was achieved for vegetation clearance activities. | Yes | N/A
Vegetation Management and Inspections | VM_10 | 8.2.3.4 | Fall-in mitigation | Focus & non-field verifiable | Fall-in mitigation | 88 Trees | 182 Trees | 182 Trees | 182 Trees | Complete | N/A | 65 Trees | 100% | Field Inspections Fall-In Mitigation Completion Log (DR068) | 206% | Initiative Validated | 351100 | 328800 | 6.351% | Underspend | Less than 10% variance. | Yes | N/A
Vegetation Management and Inspections | VM_11 | 8.2.3.5 | Substation defensible space | Non-focus & non-field verifiable | Substation defensible space | 13 Substations | 13 Substations | 13 Substations | 13 Substations | Complete | N/A | 13 Substations | 100% | Substation Clearing Logs (DR069) | 100% | Initiative Validated | 15500 | 14300 | 7.742% | Underspend | Less than 10% variance. | Yes | N/A
Vegetation Management and Inspections | VM_12 | 8.2.3.6 | High-risk species | Non-focus & non-field verifiable | High-risk species | No Target | N/A | N/A | N/A | Ongoing | N/A | 31 | 100% | High-Risk Species Documentation (DR070) | 100% | Initiative Validated | 351100 | 328800 | 6.351% | Underspend | Less than 10% variance. | Yes | N/A
Vegetation Management and Inspections | VM_13 | 8.2.3.7 | Fire-resilient rights-of-way | Non-focus & non-field verifiable | Fire-resilient rights-of-way | No Target | Work Completed on High Risk Right-of-Way | Work Completed on High Risk Right-of-Way | Work Completed on High Risk Right-of-Way | Complete | N/A | N/A | N/A | Project KMZ (DR044) | 100% | Initiative Validated | 14400 | 16300 | 13.19% | Overspend | OPEX overrun. Costs were less than estimated. All necessary activities planned for 2024 were achieved. This budget item is small ($14.4 thousand); therefore, it does not take much expense to significantly cause a cost variance. | Yes | N/A
Vegetation Management and Inspections | VM_14 | 8.2.3.8 | Emergency response vegetation management | Non-focus & non-field verifiable | Emergency response vegetation management | Review and update emergency response procedures | Quarterly target met | Quarterly target met | Quarterly target met | Ongoing | N/A | N/A | N/A | Procedures for VM_14 Emergency Response Vegetation Management (DR071) | 100% | Initiative Validated | 28800 | 37900 | 31.6% | Overspend | OPEX overrun. Costs were lower than estimated due to lower than normal emergency response activities. | Yes | N/A
Vegetation Management and Inspections | VM_15 | 8.2.4 | Vegetation management enterprise system | Non-focus & non-field verifiable | Vegetation management enterprise system | Review and update VM Enterprise Procedures | Quarterly target met | Quarterly target met | Quarterly target met | Ongoing | N/A | N/A | N/A | Records of meetings, draft VM enterprise system procedures (DR072) | 100% | Initiative Validated | 21600 | 18300 | 15.28% | Underspend | OPEX underrun. Costs associated with updating and maintaining the vegetation management enterprise systems(s) were lower than forecasted due to lower than estimated labor costs. | Yes | N/A
Vegetation Management and Inspections | VM_16 | 8.2.5 | Vegetation Management Quality assurance / quality control | Focus & non-field verifiable | Vegetation Management Quality assurance / quality control | 72 QC Reviews, 5 Program Audits | 5 Program Audits | 5 Program Audits | 5 Program Audits | Complete | N/A | 5 Program Audits | 100% | Records of QC review log, audit reports (DR073) | 100% | Initiative Validated | 50900 | 66100 | 29.86% | Overspend | OPEX overrun. Costs were higher than estimated to due more labor hours dedicated to this effort. | Yes | N/A
Vegetation Management and Inspections | VM_17 | 8.2.6 | Vegetation Management Open work orders | Non-focus & non-field verifiable | Vegetation Management Open work orders | Maintain compliance with open workorders | N/A | N/A | N/A | Ongoing | N/A | N/A | N/A | Records of vegetation management workorder completion for 2024 (DR074) | 100% | Initiative Validated | 35700 | 41900 | 17.37% | Overspend | OPEX overrun. Costs were higher than estimated to due more labor hours dedicated to this effort. | Yes | N/A
Vegetation Management and Inspections | VM_18 | 8.2.7 | Vegetation Management Workforce planning | Non-focus & non-field verifiable | Vegetation Management Workforce planning | Verification Current Staffing Level (Internal & Contractors) Meets Need | Needs Met | Needs Met | Needs Met | Ongoing | N/A | N/A | N/A | Weekly staff log-in (DR075) | 100% | Initiative Validated | 6400 | 7800 | 21.87% | Overspend | OPEX overrun. Costs were higher than estimated to due more labor hours dedicated to this effort. This budget item is small ($6.4 thousand); therefore, it does not take much expense to significantly cause a cost variance. | Yes | N/A
Vegetation Management and Inspections | VM_19 | 8.2.2.1 | AiDash | Non-focus & non-field verifiable | AiDash | Annual Review | Target Met | Target Met | Target Met | Ongoing | N/A | N/A | N/A | -BVES Response -AiDash Proof (DR042) | N/A | N/A | 40000 | 40000 | 0% | No Variance | Less than 10% variance. | N/A | N/A
Situational Awareness and Forecasting | SAF_1 | 8.3.2 | Advanced weather monitoring and weather stations | Non-focus & non-field verifiable | Advanced weather monitoring and weather stations | N/A | N/A | N/A | N/A | Complete | N/A | 20 Weather Stations | 100% | Weather station maintenance records (DR061) | 100% | Initiative Validated | 7300 | 8600 | 17.81% | Overspend | OPEX overrun. Labor and replacement parts to maintain the weather stations was higher than estimated. All weather stations were properly serviced. | Yes | N/A
Situational Awareness and Forecasting | SAF_2 | 8.3.3 | Install Fault Indicators | Focus & non-field verifiable | Install Fault Indicators | N/A | 30 FIs | 30 FIs | 30 FIs | Complete | N/A | 30 FIs | 100% | Records of FI installation (DR062) | 100% | Initiative Validated | 260000 | 270700 | 4.115% | Overspend | Less than 10% variance. | Yes | N/A
Situational Awareness and Forecasting | SAF_3 | 8.3.3 | Online Diagnostic System | Non-focus & non-field verifiable | Online Diagnostic System | 1 Circuit | 1 Circuit | 1 Circuit | 1 Circuit | Complete | N/A | 1 Circuit | 100% | Installation records of completion (DR063) | 100% | Initiative Validated | 77300 | 17200 | 77.75% | Underspend | CAPEX underrun. Annual target for 2024 was achieve at lower than budgeted. Contractor costs were less than originally estimated. | Yes | N/A
Situational Awareness and Forecasting | SAF_4 | 8.3.4 | HD ALERTWildfire Cameras | Non-focus & non-field verifiable | HD ALERTWildfire Cameras | N/A | N/A | N/A | N/A | Complete | N/A | N/A | N/A | Statement of record from BVES | 100% | Initiative Validated | 0 | 0 | 0% | No Variance | Less than 10% variance. | Yes | N/A
Situational Awareness and Forecasting | SAF_5 | 8.3.5 | Weather forecasting | Non-focus & non-field verifiable | Weather forecasting | Ongoing Monitoring & Maintenance | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -Weather Forecasting Maintenance Response (DR065) -Staff Training Notes -Technosylva Forecast Correspondence (DR065.b) | 100% | Initiative Validated | 70600 | 82200 | 16.43% | Overspend | OPEX overrun. Contracted expenses were higher than initially planned. | Yes | N/A
Situational Awareness and Forecasting | SAF_6 | 8.3.6 | Fire potential index | Non-focus & non-field verifiable | Fire potential index | Ongoing Monitoring & Maintenance | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -FPI Maintenance Response (DR066) | 100% | Initiative Validated | 53200 | 57700 | 8.459% | Overspend | Less than 10% variance. | Yes | N/A
Situational Awareness and Forecasting | SAF_7 | 8.3.3 | GreenGrid iSIU | Non-focus & non-field verifiable | GreenGrid iSIU | Ongoing Monitoring & Maintenance | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No Variance | #N/A | N/A | N/A
Situational Awareness and Forecasting | RMA_1 | 6 | Technosylva Contractor. Program implemented and ongoing. | Non-focus & non-field verifiable | Technosylva Contractor. Program implemented and ongoing. | Maintain Realtime Risk Mapping | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -2023v2022 FireSight Training -Technosylva Meeting Notes -TSYL Model Documentation (DR039) | 100% | Initiative Validated | 88600 | 180400 | 103.6% | Overspend | OPEX overrun. Additional contracted expenses were higher than initially planned due to BVES working with contractor (Direxyon) to further develop Utility Risk Model. | Yes | N/A
Emergency Preparedness | EP_1 | 8.4.2 | Emergency preparedness plan | Non-focus & non-field verifiable | Emergency preparedness plan | Review & Evaluate Emergency Plan | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -PSPS Procedure Review (DR045) -EDRP Review for Changes -QAQC Preparedness Plan Procedures (DR045.b) | 100% | Initiative Validated | 4800 | 5200 | 8.333% | Overspend | Less than 10% variance. | Yes | N/A
Emergency Preparedness | EP_2 | 8.4.3 | External collaboration and coordination | Non-focus & non-field verifiable | External collaboration and coordination | Meetings with Community Partners | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -Emergency Response & Disaster Plan (DR010) -PSPS & WMP Collab Log (DR009) | 100% | Initiative Validated | 22000 | 31600 | 43.64% | Overspend | OPEX overrun. Costs for attending Joint IOU workshops and wildfire mitigation related conferences were higher than estimated. This budget item is small ($22 thousand); therefore, it does not take much expense to significantly cause a cost variance. | Yes | N/A
Emergency Preparedness | EP_3 | 8.4.4 | Public emergency communication strategy | Non-focus & non-field verifiable | Public emergency communication strategy | Review and Evaluate Emergency Communication Program | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -Emergency Response & Disaster Plan (DR011) -Emergency Communication Review (DR011.b) | 100% | Initiative Validated | 4300 | 4700 | 9.302% | Overspend | Less than 10% variance. | Yes | N/A
Emergency Preparedness | EP_4 | 8.4.5 | Preparedness and planning for service restoration | Non-focus & non-field verifiable | Preparedness and planning for service restoration | Update Service Restoration Plan | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -PSPS Service Restoration Meetings (DR012) | 100% | Initiative Validated | 5800 | 6300 | 8.621% | Overspend | Less than 10% variance. | Yes | N/A
Emergency Preparedness | EP_5 | 8.4.6 | Customer support in wildfire and PSPS emergencies | Non-focus & non-field verifiable | Customer support in wildfire and PSPS emergencies | Review & Evaluate PSPS Program | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Ongoing | N/A | N/A | N/A | -Customer Outreach Planning Program (DR013) | 100% | Initiative Validated | 3600 | 3900 | 8.333% | Overspend | Less than 10% variance. | Yes | N/A
Community Outreach and Engagement | COE_1 | 8.5.2 | Public Outreach and Education Awareness Program | Non-focus & non-field verifiable | Public Outreach and Education Awareness Program | 360 | 1013 | 1013 | 1013 | Complete | N/A | 17 | 100% | -PSPS Tracking 2024 (DR006) | 281% | Initiative Validated | 92700 | 148300 | 59.98% | Overspend | OPEX overrun. Higher than estimated costs of advertising and contracted public relations services drove this cost higher than forecasted. | Yes | N/A
Community Outreach and Engagement | COE_2 | 8.5.3 | Engagement With Access and Functional Needs Populations | Non-focus & non-field verifiable | Engagement With Access and Functional Needs Populations | 12 | 26 | 26 | 26 | Complete | N/A | 12 | 100% | -AFN Date Tracker 2024 (DR007) | 216% | Initiative Validated | 30900 | 59900 | 93.85% | Overspend | OPEX overrun. Higher than estimated costs of advertising and contracted public relations services drove this cost higher than forecasted. | Yes | N/A
Community Outreach and Engagement | COE_3 | 8.5.4 | Collaboration on Local Wildfire Mitigation Planning | Non-focus & non-field verifiable | Collaboration on Local Wildfire Mitigation Planning | Engage with Local Support | Target Met | Target Met | Target Met | Ongoing | N/A | N/A | N/A | -2024 Collaboration (DR008) | 100% | Initiative Validated | 23300 | 31300 | 34.33% | Overspend | OPEX overrun. Costs were higher than estimated to due more labor hours dedicated to this effort. This budget item is small ($23.3 thousand); therefore, it does not take much expense to significantly cause a cost variance. | Yes | N/A
Community Outreach and Engagement | COE_4 | 8.5.5 | Best Practice Sharing With Other Utilities | Non-focus & non-field verifiable | Best Practice Sharing With Other Utilities | 15 | 135 | 135 | 135 | Complete | N/A | 15 | 100% | -PSPS and WMP Collaboration Log (DR009) | 900% | Initiative Validated | 15200 | 16600 | 9.211% | Overspend | Less than 10% variance. | Yes | N/A
Note on K11: Number of "actuals" from which samples are selected

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | BVES
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2025-05-20 | 2025-05-23 | QA/QC | BVES_DR001 | BVES INC Quality Management Plan Rev0.pdf BVES_DR001_QAQC Questions Response.word
2025-06-03 | 2025-06-06 | SME Interview ResourceKeeper | BVES_DR002 | Document Confirmation.word BVES GD_27; 28; 30 SME Interview 06.03.25.pdf
2025-05-21 | 2025-05-27 | Financials | BVES_DR005 | BVES_DR005_Attachment Response
2025-04-22 | 2025-04-29 | COE_1 | BVES_DR006 | DR 6 WMP-PSPS tracking 2025.xlsx
2025-06-10 | 2025-06-13 | COE_1 | BVES_DR006.b | WMP Post Confirmation
2025-04-22 | 2025-04-29 | COE_2 | BVES_DR007 | DR 7 AFN Date Tracker 2024.xlsx
2025-06-10 | 2025-06-13 | COE_2 | BVES_DR007.b | AFN Confirmationxlsx
2025-04-22 | 2025-04-25 | COE_3 | BVES_DR008 | 2024 Collaboration.xlsx
2025-04-22 | 2025-04-25 | COE_4 | BVES_DR009 | BVES PSPS and WMP Collaboration Log 2024.xlsx
2025-06-10 | 2025-06-13 | COE_4 | BVES_DR009.b | BVES PSPS and WMP Collaboration Log 2024_Documents Update.xlx File 1 - Q1: 03-13-2024 IEFSA Agenda 0224-wildfire-mitigation FINAL_Joint IOU AFN Q1 Statewide Council_March 2024 Q1 2024 Joint IOU AFN Collaborative Council_March 2024 File 2 - Q2: TN13898_20240415T124117_Notice_of_2025_WMP_Update_Workshop__Group_1 WMAC April 16 Meeting Minutes WMAC June 13 Meeting Minutes WMAC May 21 Meeting Minutes File 3 - Q3: 07-10-2024 IEFSA Agenda CPUC Slide Deck for PSPS Workshop Day 1 872024 Joint IOU AFN Q3 Collaborative Council Meeting Agenda WMP Joint IOU Monthly Meeting Agenda Sept.2024 File 4 - Q4 11-13-2024 IEFSA Agenda Copy Q4 2024 PSPS Working Group Meeting + Microgrid Workshop - Central Region - Q4 Joint IOU AFN Collaborative Council Meeting_20241202 Utility Agenda_Dec 12
2025-04-22 | 2025-04-25 | EP_2 | BVES_DR010 | BVERS INC EmergencyResponseAndDisasterPlan Rev2.pdf
2025-04-22 | 2025-04-29 | EP_3 | BVES_DR011 | BVES INC Emergency Response and Disaster Plan Rev2.pdf
2025-05-14 | 2025-05-19 | EP_3 | BVES_DR011.b | Emergency Communication Review
2025-04-22 | 2025-04-29 | EP_4 | BVES_DR012 | PSPS Service Restoration Meetings.xlsx
2025-04-22 | 2025-04-29 | EP_5 | BVES_DR013 | Customer Outreach Program Planning.xlsx
2025-04-30 | 2025-05-06 | GD_10 | BVES_DR014 | A.24-05-___BVES Matlock_Linam Testimony - Chapter 1 - 3 (05.17.2024) (Public Version) A.24-05-___BVES Solar and Storage Application_Public Version_FINAL 05172024 Battery and Solar Ruling - 4.18.25
2025-04-30 | 2025-05-06 | GD_11 | BVES_DR015 | A.24-05-___BVES Matlock_Linam Testimony - Chapter 1 - 3 (05.17.2024) (Public Version) A.24-05-___BVES Solar and Storage Application_Public Version_FINAL 05172024 Battery and Solar Ruling - 4.18.25
2025-04-22 | 2025-04-25 | GD_12 | BVES_DR016 | Substation Automation 2024.xlsx
2025-04-30 | 2025-05-06 | GD_12 | BVES_DR016.b | Bear Mountain SCADA Screen.JPEG Division SCADA Screen.JPEG Maple SCADA Screen.JPEG Fiber Install Invoice
2025-04-22 | 2025-04-25 | GD_13 | BVES_DR017 | Switch and Field 2024.xlsx
2025-04-30 | 2025-05-06 | GD_13 | BVES_DR017.b | AR102 Install Record; AR105 Install Record; AR145 Install Record; AR405 Install Record; PS104 Install Record; PS106 Install Record; PS406 Install Record; PS407 Install Record; PS802 Install Record; PS3464IR Install Record; AR405 SCADA Screen.jpeg
2025-04-22 | 2025-04-25 | GD_14 | BVES_DR018 | 2024 Capacitor Bank Locations.xlsx
2025-04-22 | 2025-04-29 | GD_15 | BVES_DR019 | DR 19 Fuse and Trip Savers 2024.xlsx
2025-04-22 | 2025-04-25 | GD_16 | BVES_DR020 | Server Room 2024.xlsx
2025-04-22 | 2025-04-29 | GD_21 | BVES_DR023 | C#20288-007 - OS -FULLY EXECUTED_ProjectBudget.pdf Phase 4 PSPS Risk.word Power Plant 2024 Timeline.xlsx SDP invoice for phase 3_Confirmation of Phase 3 Completion.pdf
2025-04-22 | 2025-04-25 | GD_25 | BVES_DR025 | DR 25 Detailed Inspection Circuits.xlsx
2025-05-05 | 2025-05-08 | GD_25 | BVES_DR025.b | Detailed Inspection Reports
2025-04-22 | 2025-04-25 | GD_26 | BVES_DR026 | Patrol Inspection Record 2024.xlsx
2025-04-30 | 2025-05-06 | GD_26 | BVES_DR026.b | patrol inspections
2025-04-22 | 2025-04-25 | GD_27 | BVES_DR027 | DR 27 and 28 2024 UAV Report.xlsx
2025-05-02 | 2025-05-07 | GD_27 | BVES_DR027.b | DR27B Explanation Pages from 2024_WMP_BIG BEAR CITY_20204SEPT24
2025-04-22 | 2025-04-25 | GD_28 | BVES_DR028 | DR 27 and 28 2024 UAV Report.xlsx
2025-04-22 | 2025-04-25 | GD_29 | BVES_DR029 | DR 29 2024_BVES_MobileLiDAR.zip
2025-05-02 | 2025-05-07 | GD_29 | BVES_DR029.b | Encroachments2024.kmz
2025-04-22 | 2025-04-25 | GD_30 | BVES_DR030 | DR 30 20240815_Ground_inspection.xlsx
2025-04-22 | 2025-04-25 | GD_31 | BVES_DR031 | Intrusive Testing Results.xlsx
2025-05-02 | 2025-05-07 | GD_31 | BVES_DR031.b | Intrusive Testing Followup Procedure
2025-04-22 | 2025-04-25 | GD_32 | BVES_DR032 | 2024 Bear City Substation.pdf; 2024 Bear Mountain Substation.pdf; 2024 Division Substation.pdf; 2024 Fawnskin Substation.pdf; 2024 Lake Substation.pdf; 2024 Maltby Substation.pdf; 2024 Maple Substation.pdf; 2024 Meadow Substation.pdf; 2024 Moonridge Substation.pdf; 2024 Palomino Substation.pdf; 2024 Pineknot Substation.pdf; 2024 Summit Substation.pdf; 2024 Village Substation.pdf
2025-04-22 | 2025-04-25 | GD_33 | BVES_DR033 | 2024 QDR Table 11.xlsx
2025-05-05 | 2025-05-08 | GD_33 | BVES_DR033.b | Budget Breakdown po 120540
2025-05-06 | 2025-05-09 | GD_34 | BVES_DR034 | C_3127-000 Fully Executed Meter Inspection Portal Response
2025-04-22 | 2025-04-25 | GD_36 | BVES_DR035 | BVES GO 165 Procedures.pdf; BVES Inspection Schedule Rev01
2025-04-22 | 2025-04-25 | GD_37 | BVES_DR036 | BVES INC Emergency Response and Disaster Plan Rev2.pdf; BVES INC PSPS Procedures Rev3.pdf; Recloser Settings Clarification.doc
2025-04-22 | 2025-04-25 | GD_38 | BVES_DR037 | Firefighting Coordination Protocols.doc
2025-05-05 | 2025-05-08 | GD_38 | BVES_DR037.b | Firefighting Coordination Response BVERS INC EmergencyResponseAndDisasterPlan Rev2
2025-04-22 | 2025-04-25 | RMA_1 | BVES_DR039 | 2023 vs 2022 FireSight Training.doc; 2024_10_1_BVES_Technosylva_Meeting_Notes_Documentation of training.doc; WMP Model Documentation_TSYL_2024_AppendixVersion_compressed.pdf
2025-04-22 | 2025-04-25 | ST_1 | BVES_DR041 | Big Bear Power Line Biology Report.pdf
2025-05-05 | 2025-05-08 | ST_1 | BVES_DR041.b | Radford Survey Requirment
2025-05-06 | 2025-05-09 | VM_19 | BVES_DR042 | BVES_DR042- VM-19 VM-19 AiDash proof
2025-04-22 | 2025-04-25 | WMSD_1 | BVES_DR043 | 2024_10_1_BVES_Technoslyva_Meeting_Notes.doc; BVES Responses.doc
2025-05-01 | 2025-05-06 | VM_13 | BVES_DR044 | BVES_DR044 - VM_13 BVES Veg Mgt 9.27.2024.kmz
2025-05-27 | 2025-05-29 | VM_13 | BVES_DR044.b | Document Confirmation.word
2025-05-01 | 2025-05-06 | EP_1 | BVES_DR045 | PSPS Procedure Review
2025-05-07 | 2025-05-12 | EP_1 | BVES_DR045.b | EDRP Review for Changes EP_1 QAQC Emergenccy Preparednes Plan Procedures R0
2025-05-01 | 2025-05-06 | GD_1 | BVES_DR046 | 2024 Covered Conductor
2025-05-21 | 2025-05-27 | GD_1 | BVES_DR046.b | Copy of DR046b Covered Conductor Replacement Project Attachment Rev 01.xlsx 2024_WMP_BIG BEAR CITY_20204SEPT24.pdf 2024_WMP_RECONDUCTOR_ BALDWIN LAKE_20JUNE2023.pdf 2024_WMP_BIG BEAR CITY_20204SEPT24.pdf
2025-05-01 | 2025-05-06 | GD_17 | BVES_DR047 | Distribuition Management Center Final
2025-05-01 | 2025-05-06 | GD_19 | BVES_DR048 | TARP 2024
2025-05-01 | 2025-05-06 | GD_2 | BVES_DR049 | Radford Mileage
2025-05-21 | 2025-05-27 | GD_2 | BVES_DR049.b | RADFORD 34.5KV-FOREST-INSTALL.pdf RADFORD 34.5KV-FOREST-REMOVE.pdf RADFORD 34.5KV-KNICKERBOCKER.pdf
2025-05-05 | 2025-05-08 | GD_3 | BVES_DR052 | Minor Underground Upgrades
2025-05-01 | 2025-05-06 | GD_35 | BVES_DR053 | QC Locations
2025-05-27 | 2025-05-29 | GD_35 | BVES_DR053.b | Document Confirmation.word
2025-05-01 | 2025-05-06 | GD_39 | BVES_DR054 | PSPS Procedure Review BVES INC PSPS Procedures Rev3 GD_39 QAQC Personnel Work Procedures and Training in Conditions of Elevated Fire Risk Procedures R0 PSPS Post Season Report 2024
2025-05-01 | 2025-05-06 | GD_4 | BVES_DR055 | Replacment Reframes 2024
2025-05-01 | 2025-05-06 | GD_40 | BVES_DR056 | GD_40 QAQC Asset Workforce Planning Procedures R0; C#2967-008-Amendment #1 - FULLY EXECUTED; C#2968-016 - Amendment #1 -FULLY EXECUTED; C#2967-007 FULLY EXECUTED; C#2968-014 - FULLY EXECUTED; C#2967-006 FULLY EXECUTED; C#2968-000 For Outsource Signed; C#2967-004 FULLY EXECUTED; C#2967-000 For Outsource Signed
2025-05-01 | 2025-05-06 | GD_5 | BVES_DR057 | Radford Pole Data
2025-05-01 | 2025-05-06 | GD_6 | BVES_DR058 | Fire Wrap 2024
2025-05-01 | 2025-05-06 | GD_8 | BVES_DR060 | Maintenance Repair
2025-05-01 | 2025-05-06 | SAF_1 | BVES_DR061 | Weather Stations 2024
2025-05-01 | 2025-05-06 | SAF_2 | BVES_DR062 | Fault Indicators 2024
2025-05-27 | 2025-05-29 | SAF_2 | BVES_DR062.b | Document Confirmation.word
2025-05-01 | 2025-05-07 | SAF_3 | BVES_DR063 | Output Monitoring Response; Online Diagnostic System; Events; Boulder Voltages-Dynamic 1440M-from 09_48_10.340 Tue, May 06, 25-till 09_48_10.340 Wed, May 07, 25; Boulder Environmentals-Dynamic 1440M-from 09_48_10.346 Tue, May 06, 25-till 09_48_10.346 Wed, May 07, 25; Boulder (4kV) Load-Dynamic 1440M-Zoomed-from 09_44_23.950 Tue, May 06, 25-till 09_44_23.950 Wed, May 07, 25; Baldwin Voltages-Dynamic 1440M-from 09_47_09.33 Tue, May 06, 25-till 09_47_09.33 Wed, May 07, 25; Baldwin Load-Dynamic 1440M-from 09_44_23.892 Tue, May 06, 25-till 09_44_23.892 Wed, May 07, 25; Baldwin Environmental-Dynamic 1440M-from 09_49_33.399 Tue, May 06, 25-till 09_49_33.399 Wed, May 07, 25
2025-05-01 | 2025-05-06 | SAF_4 | BVES_DR064 | Camera Maintenance Response
2025-05-27 | 2025-05-29 | SAF_4 | BVES_DR064.b | Camera Coverage.word
2025-05-01 | 2025-05-06 | SAF_5 | BVES_DR065 | Weather Forecasting Maintenance Response
2025-05-07 | 2025-05-12 | SAF_5 | BVES_DR065.b | 2024_1_17_BVES_Staff_Training_Notes Technosylva forecast for 8_26_2024 - email
2025-05-01 | 2025-05-06 | SAF_6 | BVES_DR066 | FPI Maintenance Response
2025-05-01 | 2025-05-06 | VM_1 | BVES_DR067 | VM 1 Detailed Inspection Circuits
2025-05-22 | 2025-05-28 | VM_1 | BVES_DR067.b | DR067b VM_1 - Detailed Inspections Attachment.xlsx Detailed Inspection Reports.pdf
2025-05-01 | 2025-05-06 | VM_10 | BVES_DR068 | VM-10 2024 Removals
2025-05-01 | 2025-05-06 | VM_11 | BVES_DR069 | VM-11 Substation Defensible Space
2025-05-27 | 2025-05-29 | VM_11 | BVES_DR069.b | Document Confirmation.word
2025-05-01 | 2025-05-06 | VM_12 | BVES_DR070 | VM-12 High Risk Species Removals
2025-05-27 | 2025-05-29 | VM_12 | BVES_DR070.b | Document Confirmation.word
2025-05-01 | 2025-05-06 | VM_14 | BVES_DR071 | PSPS Procedure Review; VM_14 Emergency Response Vegetation Management QAQC Procedures R0; PSPS Post Season Report 2024; BVES INC PSPS Procedures Rev3
2025-05-01 | 2025-05-06 | VM_15 | BVES_DR072 | BVES_DR072 - VM_15; Vegetation Management Contract; VM-15 VM Enterprise System Meeting Dates
2025-05-01 | 2025-05-06 | VM_16 | BVES_DR073 | BVES_DR073 - VM_16; VM-16 QA.QC Record; Vegetation Management Program Annual Audit 2023; Vegetation Management Quarterly Update Q1 2024; Vegetation Management Quarterly Update Q2 2024; Vegetation Management Quarterly Update Q3 2024; Vegetation Management Quarterly Update Q4 2024
2025-05-27 | 2025-05-29 | VM_16 | BVES_DR073.b | Document Confirmation.word
2025-05-01 | 2025-05-06 | VM_17 | BVES_DR074 | BVES_DR074 - VM_17; VM-17 Open Work Orders
2025-05-01 | 2025-05-06 | VM_18 | BVES_DR075 | BVES_DR075 - VM_18 BVES Master Logout
2025-05-01 | 2025-05-06 | VF_2 | BVES_DR076 | Patrol Inspection Record 2024
2025-05-22 | 2025-05-28 | VM_2 | BVES_DR076.b | DR076b - Patrol Inspections Attachment.xlsx patrol inspections.pdf
2025-05-01 | 2025-05-06 | VF_3 | BVES_DR077 | 2024 UAV Report
2025-05-27 | 2025-05-29 | VM_3 | BVES_DR077.b | Document Confirmation.word
2025-05-01 | 2025-05-06 | VF_4 | BVES_DR078 | 2024_BVES_MobileLiDAR.zip
2025-05-27 | 2025-05-29 | VM_4 | BVES_DR078.b | Document Confirmation.word
2025-05-01 | 2025-05-06 | VF_5 | BVES_DR079 | VM 5 20240815_Ground_inspection
2025-05-27 | 2025-05-29 | VM_5 | BVES_DR079.b | Document Confirmation.word
2025-05-01 | 2025-05-06 | VF_6 | BVES_DR080 | 2024 Bear City Substation; 2024 Bear Mountain Substation; 2024 Division Substation; 2024 Fawnskin Substation; 2024 Lake Substation; 2024 Maltby Substation; 2024 Maple Substation; 2024 Meadow Substation; 2024 Moonridge Substation; 2024 Palomino Substation; 2024 Pineknot Substation; 2024 Summit Substation; 2024 Village Substation
2025-05-01 | 2025-05-06 | VF_7 | BVES_DR081 | BVES_DR081 - VM_7 Response Initial WMP Planning Meeting BVES INC Vegetation Management and Vegetation Management QC Programs Policy and Procedures Rev1
2025-05-01 | 2025-05-06 | VF_8 | BVES_DR082 | BVES_DR082 - VM_8 Response; BVES Data Request BVES_DR082 - VM_8; BVES INC Vegetation Management and Vegetation Management QC Programs Policy and Procedures Rev1; Initial WMP Planning Meeting
2025-05-21 | 2025-05-27 | VM_8 | BVES_DR082.b | Vegetation Management Contract.pdf
2025-05-01 | 2025-05-06 | VF_9 | BVES_DR083 | VM-9 VEG_2024 Milage. Zip
2025-05-27 | 2025-05-29 | VM_9 | BVES_DR083.b | Document Confirmation.word

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | BVES
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2025-05-30 | QA/QC | SME001 | Wildfire Mitigation & Reliability Engineer Utility Engineer & Wildfire Mitigation Supervisor | Follow-up SME interview from DR001 to gather more data related to QA/QC Processes. Discussions around frequency, additional triggers, QA/QC implementation, databases, and general clarifications on QA/QC processes.
2025-06-03 | GD_27; GD_28; GD_30 | SME002 | Wildfire Mitigation & Reliability Engineer | Overview of ResourceKeeper platform in response to DR027, DR028, and DR030. Run by Davey, 3rd party ground control, do UAV, pole detail, ShapeFiles and KMZ files reflect total number of circuit miles; requested access to program.

## Tab 5 - List of "Fail-to-Fund"
List of Failed-to-Fund Initiatives
Independent Evaluator: | Bureau Veritas
Electrical Corporation: | BVES
WMP Category | WMP Section Number | WMP Page Number | Initiative Tracking ID | Initiative Name | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%)
Grid Design Operations and Maintenance | 8.1.2.1 | 133 | GD_1 | Covered Conductor Replacement Project | 4737300 | 4595400 | 2.995%
Grid Design Operations and Maintenance | 8.1.2.2 | 136 | GD_3 | Minor Undergrounding Upgrades Projects | 303700 | 95300 | 68.62%
Grid Design Operations and Maintenance | 8.1.2.3 | 137 | GD_4 | Covered Conductor Replacement Project | 2030300 | 1969500 | 2.995%
Grid Design Operations and Maintenance | 8.1.2.3 | 137 | GD_6 | Evacuation Route Hardening Project | 808000 | 541300 | 33.01%
Grid Design Operations and Maintenance | 8.1.2.8 | 142 | GD_16 | Server Room | 103200 | 61400 | 40.5%
Grid Design Operations and Maintenance | 8.1.2.12 | 149 | GD_22 | Partial Safety and Technical Upgrades to Maltby Substation | 795000 | 794700 | 0.03774%
Grid Design Operations and Maintenance | 8.1.3.1 | 154 | GD_27 | UAV Thermography | 77500 | 65200 | 15.87%
Grid Design Operations and Maintenance | 8.1.3.1 | 155 | GD_28 | UAV HD Photography/Videography | 77500 | 65200 | 15.87%
Grid Design Operations and Maintenance | 8.1.3.1 | 155 | GD_29 | LiDAR Inspection | 79600 | 71800 | 9.799%
Grid Design Operations and Maintenance | 8.1.3.1 | 156 | GD_30 | 3rd Party Ground Patrol | 64300 | 21400 | 66.72%
Grid Design Operations and Maintenance | 8.1.3.1 | 214 | GD_32 | Substation inspections | 283300 | 110500 | 61%
Grid Design Operations and Maintenance | 8.1.5 | 164 | GD_34 | Asset management and inspection enterprise system(s) | 57700 | 42800 | 25.82%
Vegetation Management and Inspections | 8.2.2.1 | 212 | VM_3 | UAV HD Photography/Videography | 77500 | 67200 | 13.29%
Vegetation Management and Inspections | 8.2.2.1 | 212 | VM_4 | LiDAR Inspection | 79600 | 71800 | 9.799%
Vegetation Management and Inspections | 8.2.2.1 | 213 | VM_5 | 3rd Party Ground Patrol | 64300 | 21400 | 66.72%
Vegetation Management and Inspections | 8.2.3.2 | 217 | VM_8 | Wood and slash management | 520400 | 453800 | 12.8%
Vegetation Management and Inspections | 8.2.3.3 | 218 | VM_9 | Clearance | 2212800 | 1935400 | 12.54%
Vegetation Management and Inspections | 8.2.3.4 | 221 | VM_10 | Fall-in mitigation | 351100 | 328800 | 6.351%
Vegetation Management and Inspections | 8.2.3.5 | 221 | VM_11 | Substation defensible space | 15500 | 14300 | 7.742%
Vegetation Management and Inspections | 8.2.3.6 | 222 | VM_12 | High-risk species | 351100 | 328800 | 6.351%
Vegetation Management and Inspections | 8.2.4 | 224 | VM_15 | Vegetation management enterprise system | 21600 | 18300 | 15.28%
Situational Awareness and Forecasting | 8.3.3 | 242 | SAF_3 | Online Diagnostic System | 77300 | 17200 | 77.75%
Note on E11: Kopunova, Sara: If applicable since some commitments occur outside of initiatives