## Detailed implementation steps
Last update:
[5 empty] | Q1 |  |  | Q2 |  |  | Q3 | Q4 | 2025-02-18 | Objective Outcome/status
Priority | Objective | Intended outcome | Action | Who | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. - May 2025 | Jun. - Aug. 2025 | Action Status
Priority 1: Actualizing Our Mission in Collaboration with the Office of Energy Infrastructure Safety Priority Steward: Chris Porter | Develop in-person engagement with Energy Safety. | Both sides feel communication is satisfactory | Establish monthly calls between Executive Committee and Energy Safety Program Manager | Mark | Establish calls | [5 empty] | Transfer to day-to-day portfolio |  | Complete | Monthly calls established
|  |  | Establish quarterly calls between Chair and Energy Safety Director | Dina; Mark to track |  |  | Establish recurring series |  |  | Hold first call | Transfer to day-to-day portfolio |  | Complete | First call held 2/4/25
| Delegate administrative authority to WSAB. | WSAB has input into the resources available to it | Agree with Energy Safety on process to make budget requests | Executive Committee | Agreed on process | [7 empty] | Complete | Executive Committee agreed with ESPD Program Manger to make request at March meeting
|  |  | Adopt request to Energy Safety for resources | Executive Committee |  |  |  |  | Develop budget request |  | At March Board meeting, adopt request to Energy Safety |  | In progress
| Discover Energy Safety needs / wants for setting WSAB Priorities. | WSAB improves the impact of its recommendations by understanding where Energy Safety most welcomes input | For September 2024 Work Plan: Staff ask Energy Safety for input | Mark | Staff present work plan with Energy Safety input | [7 empty] | Complete | Energy Safety gave informal input to staff
|  |  | For March 2025 Work Plan update: Staff to ask Energy Safety for input | Mark |  |  |  | Staff ask Energy Safety for update | Receive any request and incorporate into work plan |  |  |  | In progress | Energy Safety is developing request letter
| Share WSAB priorities and expertise with Energy Safety. | WSAB improves the impact of its recommendations by ensuring they are disseminated to Energy Safety staff | Staff to introduce WSAB, its priorities and areas of expertise to other Energy Safety divisions |  | Present to Compliance Division meeting | Presented WSAB at all-hands Summit breakouts | [6 empty] | Complete | All Energy Safety staff at all-hands Summit saw WSAB presentation
|  |  | Staff work to better understand Energy Safety work and priorities | [9 empty] | Ongoing | Collaboration begun; more to do
Priority 2: Building Collaborative Relationships with External Partners Priority Steward: Jessica Block | Establish meaningful, mutually beneficial, and consistent practices for communicating with key partners. | WSAB improves the impact of its recommendations, by increasing familiarity of utilities and other stakeholders with Board outputs, and improving inputs into Board consideration. | Identify key partners |  | POUs identified as key partners | Staff had initial contact with three large IOUs |  | Each Board Member to add to list of "key partners" |  |  |  |  | Complete | All Board members were asked for input
|  |  | Set regular cadence of internal review of communication with each key partner | [6 empty] | Policy Committee to set cadence |  |  | In progress | Proposed cadence sent to Policy Committee; review at a future committee meeting
|  |  | Meet with key partners and communicate key messages |  |  | POU Committee restarts POU Working Group | Staff presents to CMUA WMP Forum | POU Working Group | POU Working Group | Set cadence |  |  | In progress | Proposed cadence sent to Policy Committee; review at a future committee meeting
| Develop clear priorities for mission related collaborative efforts. | WSAB improves the efficiency of communication for both itself and partners | Develop messages for key partners |  |  |  | Staff develops messages; reviews with Executive, Policy, and POU Committees | Refine messages based on feedback from Members and public | Review and refine messages; tie to cadence of internal review and external contact |  |  |  | Behind | Behind; waiting for confirmation of key partners
| Create communication practices and calendar interaction activities to support relationship development and collaboration | WSAB deploys staff resources to this objective, and key partners develop confidence in WSAB as a partner | Where appropriate, set regular cadence of meetings and follow-up with key partners |  |  | POU Committee restarts POU Working Group |  |  | Make initial contact with additional key partners |  |  |  | Ongoing | Contact ongoing; minimum cadence to be set by Policy Committee
Priority 3: Retaining and Developing Staff Priority Steward: Mark | Develop improved employee retention practices. | WSAB staff remain for an average of at least 3 years. | Provide each staffer with one or more projects on which they are the lead |  | Use work plan to identify discrete projects; assign projects | [7 empty] | Complete | Each staffer is lead on one or more projects
|  |  | Build sense of teamwork among staff |  |  |  | Site visit | [5 empty] | Ongoing
|  |  | Recognize individual contributions |  | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | Ongoing
| Create opportunities for career development for WSAB staff members. | WSAB staff improve skills to support Board, their own interests, and future career options. | Hold initial discussions of career development |  |  |  | Hold initial discussion | [5 empty] | Complete | Supervisor looking for opportunities to help develop staff
|  |  | Develop annual individual development plans | [5 empty] | Each WSAB staffer develops IDP |  |  |  | In progress | Will be complete in February 2025
|  |  | Staffers complete formal training |  |  |  | Sang's CPI continuing education | AI class |  |  |  |  | Ongoing | For 2025, will follow IDPs
|  |  | Include staff in meetings with Board Members and key partners |  |  | Staff included in POU Committee meetings to prep for Working Group | Staff included in POU Committee meetings to prep for Working Group | Staff included in POU Committee meetings to prep for Working Group; Staff in Director briefing on POU Advisory Opinion; staff in Committee meetings on workstreams |  |  |  |  | Ongoing
| Create work practices that support staff members' work success and allow for work life balance. | Staff feel that workload is sustainable and that the WSAB branch is a welcoming and supportive place to work. | Encourage and allow time off for vacation and family responsibilities | [9 empty] | Ongoing
|  |  | Maximize benefits of agency RTO policies |  |  | Establish common in-office day for Branch |  |  |  | Plan activities that maximize benefits of in-person time | Plan and execute activities that maximize benefits of in-person time |  | Ongoing
Priority 4: Creating the Structures and Practices for Successful Implementation Priority Steward: Mark | WSAB has established and consistently applies effective project management practices. | Products are delivered in a timely manner, meeting legislative deadlines, meeting Board expectations for scope and quality, and balancing workload | Develop project plans for major work products |  | Develop project plans for top 4 workstreams |  |  | Maintain and update project plans |  |  |  |  | Ongoing
|  |  | Establish schedule of Board meetings, and associated deadlines such as agenda posting, well in advance | [9 empty] | Complete | Board meetings scheduled through 2025; Excel calculator for associated deadlines
|  |  | Schedule Committee meetings for Board Member input into key work products |  |  |  | Schedule Scientific, Grid, and Veg Management Committee calls | [5 empty] | Behind | Scheduled scientific and grid call; veg management to come
|  |  | Develop staff guide and checklists for recurring processes |  | Update checklists after each Board meeting |  | Update checklists after each Board meeting | Complete Staff Guide |  |  | Update checklists after each Board meeting; Complete staff guide | Update checklists after each Board meeting | Behind | Staff guide/SOPs slightly behind schedule
| Plan and facilitate open meetings to allow for appropriate strategic collaboration. | Board meetings meet statutory requirement for frequency, and are well planned and structured to provide information to Board Members and support collaboration and communication with key partners | Develop Board meeting topics and speakers to provide information and support collaboration |  |  |  | Board workshop on vegetation management | Board meeting |  |  | Board meeting | Board meeting | Ongoing
|  |  | Promote Board meetings through media outreach; website development; use of email lists; individual invitations |  |  |  | Board meeting | Board meeting |  |  | Board meeting | Board meeting | Ongoing
| Establish cohesive vision and roles and responsibilities. | A cohesive vision that supports Board decision-making, direction to staff, and the priorities of the Strategic Plan | Develop and propose vision to Board |  |  |  |  | Develop vision | Socialize with individual Board Members |  | Present as part of updated work plan/strategic plan to Board |  | Behind | Draft principles will be part of Board discusion. Will reset actions as outcome of March 2025 Board strategic planning discussion
| Ensure current activities are sufficiently resourced. | Products are delivered in a timely manner, meeting legislative deadlines, meeting Board expectations for scope and quality, and balancing workload | Develop work plan |  | Work plan presented to Board | [7 empty] | Complete | Work plan execution underway
|  |  | Update work plan | [6 empty] | Update work plan | Present updated work plan to Board |  | In progress
| Create sufficient cadence of communication between Board and staff. | Board Members are informed and provide direction to staff. | Establish recurring Committee meetings |  |  |  | Schedule Scientific, Grid, and Veg Management Committee calls | [5 empty] | Behind | Staff will propose revised Committee structure at March 2025 Board meeting

## KPIs
|  | Status check at end of Q1 (December Board meeting) | Status check at end of Q2 (March Board meeting) | Status check at end of Q3 (June Board meeting)
Priority 1: Actualizing Our Mission in Collaboration with the Office of Energy Infrastructure Safety Priority Steward: Chris Porter | Ensure affected stakeholders are aware of WSAB recommendations and advisory opinions through recognized preferred channels and that comments are openly considered. | Staff restarted use of email subscription lists to announce Board meetings and availability of documents for public comment. POU Advisory Opinion posted for 2-week public comment period. POU Working Group meetings underway. Three-week public comment period scheduled for recommendations to Energy Safety by June 30, 2025. | Staff is updating dockets and email lists to continue to improve communication with stakeholders. Recommendations to Energy Safety will be published for public comment.
| Board Members, Committees, and staff meet with partner organizations at least once per quarter. | POU Committee meeting with POU associations and representatives in regularly scheduled meetings. Staff met with representatives of each of the three large IOUs in October 2024. | POU Committee met regularly with POU associations; working to schedule additional meetings. Staff met with each of the Large IOUs in Q1 2025.
| Perform two site visits per year. | Completed site visit with Trinity PUD on 11/6/24. | Site visit to PG&E Hazard Awareness and Warning Center scheduled for March 4.
Priority 2: Building Collaborative Relationships with External Partners Priority Steward: Jessica Block | Setting clear expectations for WSAB Members and WSAB Branch staff of the division of responsibilities between WSAB and Energy Safety. | Executive Committee met with Energy Safety management. | Executive Committee meets monthly with Energy Safety management.
| Identifying Energy Safety requests for “other advice and recommendations related to wildfire safety.” | Staff worked with Energy Safety to understand needs; incorporated into work plan presented 9/2024. Process for identifying requests in 2025 begun. | Energy Safety is developing a request letter.
| Participating in emerging collaborations. | No update | No update
| Holding regular meetings with WSAB Chair/Vice Chair and Energy Safety leadership. Keeping each other informed of activities and evolving topic interests. | Executive Committee meets monthly with Energy Safety management. | Executive Committee meets monthly with Energy Safety management.
| The WSAB has set annual budget discussions and participates in the budgeting process as appropriate. | Budget discussion set for March meeting. | Budget discussion set for March meeting.
Priority 3: Retaining and Developing Staff Priority Steward: Mark | Set a benchmark for employee satisfaction levels. | Scheduled for Q1 2025 | Electrical Safety Policy Division is developing a broader organizational culture assessment and discussion. Employee satisfaction within WSAB branch will be incorporated into that effort.
| Define opportunities for staff to engage in topics of interest and contribute their expertise. | Work plan includes meaningful projects for staff. | Work plan includes meaningful projects for staff.
| Each employee has clear roles and responsibilities. | Staff supervisor has set project roles for staff. | Staff supervisor has set project roles for staff.
| Each employee has an annual individual development plan developed with the supervisor to improve relevant skills and knowledge. | Scheduled for Q1 2025 | Will be complete in Q1 2025.
Priority 4: Creating the Structures and Practices for Successful Implementation Priority Steward: Mark | Maintain an updated staff guide as a living document. | Staff guide sections identified; first section under review. Staff coordinating with Electrical Safety Policy Division on standard operating procedures. | One section complete, 5 under review. Staff coordinating with Electrical Safety Policy Division on standard operating procedures.
| Initiate a project management system by December 2024. | Project management system in place, using work plan, Microsoft Planner, and a Microsoft Excel spreadsheet. | Project management system in place.
| Every initiative has clear deadlines, assigned team members, and measurements. | Project plans in place for first four workstreams, with assigned team members. Measurements to be developed. | Assignments set for team members. Supervisor will continue to update and revise, especially as new Senior Policy Advisor joins.