## WSAB 2025-2027 Strategic Plan
Priority | Objective | KPI | Action | Who | Milestones | [5 empty] | Last update: | 2025-05-14
[5 empty] | Q1 |  |  | Q2 | Q3 | Q4 |  | Objective Outcome/status
[5 empty] | Jun. | Jul. | Aug. | Sep. - Nov. 2025 | Dec. '25 - Feb. '26 | Mar. - May 2026 | Action Status
Priority 1: Actualizing Our Mission in Collaboration with the Office of Energy Infrastructure Safety Priority Steward: Chris Porter | Board Members and Energy Safety leadership and management are deepening collaboration and are satisfied with frequency and depth of communication. | Survey of Board Members and Energy Safety leadership | Participate in monthly and quarterly meetings, share information, bring questions | Executive Committee | Monthly meeting | Monthly meeting | Monthly & quarterly meetings | Monthly & quarterly meetings | Monthly & quarterly meetings | Monthly & quarterly meetings | In progress
| Board recommendations are informed by Energy Safety’s approach, timing, and constraints. | Board recommendations are delivered in sync with Energy Safety timelines | Collaborate with Energy Safety staff to understand their processes | Branch Staff | Participate in all-hands and management meetings; track WMP, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP, SCA, and compliance processes | In progress
Priority 2: Building Collaborative Relationships with External Partners Priority Steward: Jessica Block | Board Members and staff have network of partners key to success. | Staff members add contacts to their networks | Staffers attend 4 conferences per year | Branch Staff |  |  |  | Attend NCPA and SCPPA annual conferences, and CMUA WMP workshop |  | Attend CMUA annual conference | In progress | Supervisor attended EUCI conference Feb. 2025
|  | Board makes 4 site visits per year | Staff develops site visits | Branch Staff | Site visit associated with June Board meeting (ArborWorks) |  |  | Site visit associated with September Board meeting (Eaton fire) | Site visit associated with December Board meeting | Site visit associated with March Board meeting | In progress
| Board recommendations are informed by expert advice. | Board makes 4 site visits per year | Board Members attend site visits | Board Members | Site visit associated with June Board meeting (ArborWorks) |  |  | Site visit associated with September Board meeting (Eaton fire) | Site visit associated with December Board meeting | Site visit associated with March Board meeting | In progress
|  | Board presents 4 topical presentations/workshops per year | Board Members contribute contacts and expertise | Board Members |  | Committees work with staff to develop presentation for September Board meeting |  | Committees work with staff to develop presentations for Board meetings | Committees work with staff to develop presentations for Board meetings | Committees work with staff to develop presentations for Board meetings | Not started
|  |  | Staff organize presentations | Branch Staff |  |  |  | Expert presentation to Board at quarterly meeting | Expert presentation to Board at quarterly meeting | Expert presentation to Board at quarterly meeting | In progress
| Board Committees and staff have established and are deepening relationships with external partners. | Branch staff review of relationships | Staff meet with key partners on cadence set by Committees | Branch Staff | Meet as scheduled (monthly or quarterly) with key partners | Meet as scheduled (monthly or quarterly) with key partners | Meet as scheduled (monthly or quarterly) with key partners | Meet as scheduled (monthly or quarterly) with key partners | Meet as scheduled (monthly or quarterly) with key partners | Meet as scheduled (monthly or quarterly) with key partners | In progress
|  |  | Staff review relationships and report to Board | Branch Staff |  | Staff and Committees review relationships | Staff and Committees review relationships | Staff report to Board on external partner relationships | Staff and Committees review relationships | Report to Board on external partner relationships | Not started
| Board and staff have clear priorities for collaborative efforts. | There are clear priorities (and messages where appropriate) for interaction with key partners | Committees identify and review key partners and messages for their workstreams | Workstream Committees |  | Staff and Committees review relationships | Staff and Committees review relationships | Staff report to Board on external partner relationships | Staff and Committees review relationships | Report to Board on external partner relationships | Not started
Priority 3: Retaining and Developing Staff Priority Steward: Mark | Staff are satisfied with their work, work-life balance, recognition, and professional development. | Results of staff survey on work, work-life balance, recognition, and professional development | Provide each staffer with one or more projects on which they are the lead | Branch Supervisor | Onboard new staffer; identify and reassign projects |  |  | Update assignments based on Board discussion of workstreams |  |  | In progress
|  |  | Build sense of teamwork among staff | Branch Supervisor, Branch Staff | Onboard new staffer; plan teambuilding exercises; collaborate | Use POU WMP review cross-assignments to build team |  |  |  |  | In progress
|  |  | Recognize individual contributions | Branch Supervisor, Branch Staff | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | Ongoing
|  |  | Encourage and allow time off for vacation and family responsibilities | Branch Supervisor | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Ongoing
|  |  | Maximize benefits of agency RTO policies | Branch Supervisor, Branch Staff | Communicate opportunities and challenges; plan activities | Work through transition to 4 days/week; plan activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | In progress
|  |  | Survey staff semiannually | Branch Supervisor |  | Semiannual survey |  |  | Semiannual survey |  | Not started
| Board Members support staff development. | Results of staff survey | Board members introduce staff to members of their networks | Board Members | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Not started
|  |  | Board members use committee meetings and products as staff development opportunities, in collaboration with supervisor | Board Members, Branch Supervisor | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Not started
| Branch staff develops in capacity to support increased Board effectiveness. | Staffers complete majority of trainings in individual development plans | Staffers identify training goals and opportunities | Branch Staff | Review progress on 2025 IDPs |  |  |  | Develop annual IDP |  | Not started
|  |  | Staffers complete training that aligns with their job responsibilities and career development goals | Branch Staff |  |  |  | Complete training |  |  | In progress
Priority 4: Creating the Structures and Practices for Successful Implementation Priority Steward: Mark | Branch has and follows up-to-date processes, including project management, recordkeeping, and standard operating procedures. | Staff meets product deadlines, positioning Board to meet its statutory deadlines | Develop and follow project plans for major work products | Branch Supervisor, Branch Staff | Finalize POU WMP review process and assignments | Execute project plans | Execute project plans | Finalize project plan for 2026 Recommendations to Energy Safety | Execute project plans | Execute project plans | In progress
|  | Website and internal files are clearly organized and up to date | Establish, review, and revise Branch processes, Standard Operating Procedures, and checklists | Branch Supervisor, Branch Staff | Onboard new staffer with SOPs |  |  |  | Review all SOPs; revise as needed |  | Not started
|  | Staff efficiency | Communicate and follow standard processes | Branch Supervisor, Branch Staff | Onboard new staffer with SOPs | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Ongoing
| Board focuses attention and resources on clear priorities. | Priorities are reflected in Strategic Plan and Work Plans | Board members and staff establish clear priorities | Board, Branch Staff |  |  |  | Review Priorities semiannually at March and September Board meetings |  | Review Priorities semiannually at March and September Board meetings | Not started
|  | Staff resources are aligned with priorities | Supervisor plans staff resources to align with priorities and meet deadlines | Branch Supervisor | Develop annual work plan | Revise work plan as needed with new information | Revise work plan as needed with new information | Update Board on work plan at March and September meetings | Revise work plan as needed with new information | Update Board on work plan at March and September meetings | In progress
|  | Board Member input is focused, clear, and timely | Board members participate in Committee calls | Board Members | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
|  |  | Board members review and provide feedback on documents | Board Members |  |  |  | Board member review of POU Advisory Opinion | Board member review of draft Recommendations to Energy Safety | Board member review of draft Recommendations to Energy Safety | Not started
| Board members are satisfied with frequency and depth of communication with staff. | Results of Board Member survey | Staff communicate regular updates to Board and schedule Committee and Board Member briefings | Branch Staff | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
|  |  | Supervisor conducts survey | Branch Supervisor |  | Semiannual survey |  |  | Semiannual survey |  | Not started