## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID (UMAT) | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | REPORTING YEAR | REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | BVES | 2026-08-03 | Emergency Preparedness and Community Outreach | Emergency preparedness and recovery plan | Emergency preparedness and recovery plan |  | EP_1 | Program | Development and integration of wildfire- and PSPS-specific emergency strategies, practices, policies, and procedures into the electrical corporation’s overall emergency plan based on the minimum standards described in GO 166. | To provide standardized wildfire and PSPS emergency response that meet GO 166 standards and incorporate lessons and recommendations from local government and agencies. | 11.2 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000001 | BVES | 2026-08-03 | Emergency Preparedness and Community Outreach | External collaboration and coordination | External collaboration and coordination |  | EP_2 | Program | • Actions taken to coordinate wildfire and PSPS emergency preparedness with relevant public safety partners including the state, cities, counties, and tribes. • Development and integration of plans, programs, and/or policies for collaborating with communities on local wildfire mitigation planning, such as wildfire safety elements in general plans, community wildfire protection plans, and local multi-hazard mitigation plans. | To ensure wildfire and PSPS emergency preparedness is coordinated and integrated with relevant public safety partners and local communities wildfire planning. | 11.3 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000002 | BVES | 2026-08-03 | Emergency Preparedness and Community Outreach | Public communication, outreach, and education | Public communication, outreach, and education |  | EP_3 | Program | • Development and integration of a comprehensive communication strategy to inform essential customers and other stakeholder groups of wildfires, outages due to wildfires, and PSPS and service restoration, as required by Public Utilities Code section 768.6. • Development and deployment of public outreach and education awareness program(s) for wildfires; outages due to wildfires, PSPS events, and protective equipment and device settings; service restoration before, during, and after the incidents and vegetation management. • Actions taken understand, evaluate, design, and implement wildfire and PSPS risk mitigation strategies, policies, and procedures specific to access and functional needs customers. | To educate customers, stakeholders, and access and functional needs customers on wildfire and PSPS programs and plans and to communicate critical wildfire and PSPS information customers, stakeholders, and access and functional needs customers. | 11.4 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000003 | BVES | 2026-08-03 | Emergency Preparedness and Community Outreach | Customer support in wildfire and PSPS emergencies | Customer support in wildfire and PSPS emergencies |  | EP_4 | Program | Development and deployment of programs, systems, and protocols to support residential and non-residential customers in wildfire emergencies and PSPS events. | To provide safety, reliable, and effective customer support to residential and non-residential customers in wildfire emergencies and PSPS events. | 11.5 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000004 | BVES | 2026-08-03 | Enterprise Systems | Asset management and inspection enterprise system(s) | Summary of Enterprise Systems |  | ENT_1 | Program | Operation of and support for centralized enterprise systems updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | To consolidate asset inspection and condition tracking and reporting to optimize resolution of inspection findings in an efficient, timely, and safety hazard prioritized manner. | 12 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000005 | BVES | 2026-08-03 | Enterprise Systems | Vegetation management enterprise system | Summary of Enterprise Systems |  | ENT_2 | Program | Operation of and support for centralized enterprise systems updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | To consolidate vegetation management inspection and condition tracking and reporting to optimize resolution of inspection findings in an efficient, timely, and safety hazard prioritized manner. | 12 | Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000006 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Covered Conductor Replacement Project (Reconductor) | Covered conductor installation |  | GD_1 | Project | Installation of covered or insulated conductors to replace standard bare or unprotected conductors (defined in accordance with GO 95 as supply conductors, including but not limited to lead wires, not enclosed in a grounded metal pole or not covered by: a “suitable protective covering” (in accordance with Rule 22.8), grounded metal conduit, or grounded metal sheath or shield). In accordance with GO 95, conductor is defined as a material suitable for: (1) carrying electric current, usually in the form of a wire, cable or bus bar, or (2) transmitting light in the case of fiber optics; insulated conductors as those which are surrounded by an insulating material (in accordance with Rule 21.6), the dielectric strength of which is sufficient to withstand the maximum difference of potential at normal operating voltages of the circuit without breakdown or puncture; and suitable protective covering as a covering of wood or other non-conductive material having the electrical insulating efficiency (12kV/in. dry) and impact strength (20ft.-lbs) of 1.5 inches of redwood or other material meeting the requirements of Rule 22.8-A, 22.8-B, 22.8-C or 22.8-D. BVES is reconductoring bare wire circuits with covered conductors in a risk prioritized manner. | To reduce likelihood of ignitions due to wire-to-wire contact, power line contact with vegetation, and power line contact with foreign objects and to raise the threshold for invoking PSPS. | 8.2.1 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition PSPS likelihood | Quantitative | Circuit Miles | No |  |  | 2026 | 2 | 5.7 |  | In Progress
1010000007 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Fuse TripSaver Automation | Installation of system automation equipment |  | GD_10 | Project | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). This project automates Fuse TripSavers through to SCADA network. | To improve ability to quickly locate and isolate faults, remotely adjust operating mode (reclosing/manual), and remotely sectionalize the grid. | 8.2.8 | Equipment ignition likelihood PSPS exposure potential PSPS vulnerability | Quantitative | # of TripSavers connected to SCADA | No |  |  | 2026 | 2 | 6 |  | In Progress
1010000008 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Non-Exempt Surge Arrester Replacement | Other grid topology improvements to minimize risk of ignitions |  | GD_11 | Project | Actions taken to minimize the risk of ignition due to the design, location, or configuration of electric equipment in HFTDs not covered by another initiative. BVES is removing all non-exempt surge arresters. | Reduce likelihood ignition due to tree failure or contact with vegetation. | 8.2.10 | Equipment ignition likelihood | Quantitative | # of Non-exempt surge arresters replaced | No |  |  | 2026 | 2 | 0 |  | Planned
1010000009 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Tree Attachment Removal Project | Other grid topology improvements to minimize risk of ignitions |  | GD_12 | Project | Actions taken to minimize the risk of ignition due to the design, location, or configuration of electric equipment in HFTDs not covered by another initiative. This project is dedicated to the removal of existing distribution line tree attachments in BVES’s distribution system. | Reduce likelihood ignition due to tree failure or contact with vegetation. | 8.2.10 | Contact from vegetation ignition likelihood | Quantitative | # of Tree Attachments Removed | No |  |  | 2026 | 2 | 62 |  | In Progress
1010000010 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Safety and Technical Upgrades to Lake Substation | Other technologies and systems not listed above |  | GD_13 | Project | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. Converts Lake Substation from an overhead-type to an underground pad-mounted design. | Reduce likelihood ignition due to equipment failure and contact with substation exposed equipment. | 8.2.12 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000011 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Partial Safety and Technical Upgrades to Village Substation | Other technologies and systems not listed above |  | GD_14 | Project | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. This project replaces overhead enclosed regulators with pad mounted regulators, installs pad mounted IntelliRupter switches, and updates substation controls. | Reduce likelihood ignition due to equipment failure and contact with substation exposed equipment. | 8.2.12 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | Planned | Planned
1010000012 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Equipment maintenance and repair | Equipment maintenance and repair |  | GD_15 | Program | Remediation, adjustments, or installations of new equipment to improve or replace existing connector equipment, such as hotline clamps. | Reduce likelihood of ignitions due to equipment failure. | 8.4 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000013 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Quality assurance / quality control | Quality assurance / quality control |  | GD_16 | Program | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | To assure compliance with asset construction, maintenance and inspection standards and specifications and to identify gaps and areas of improvement in the asset management programs. | 8.5 | Equipment ignition likelihood | Quantitative | Number of Asset QCs on WMP Work | No |  |  | 2026 | 2 | 10 |  | In Progress
1010000014 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Open work orders | Work orders |  | GD_17 | Program | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe asset management activities. | To ensure asset work orders are properly completed in an efficient, timely, and safety based prioritized manner. | 8.6 | Equipment ignition likelihood | Quantitative | 90% or more of work orders compelted on schedule for the year | No |  |  | 2026 | 2 | 100 |  | In Progress
1010000015 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk | Equipment Settings to Reduce Wildfire Risk |  | GD_18 | Program | The electrical corporation’s procedures for adjusting the sensitivity of grid elements to reduce wildfire risk. | To reduce likelihood of ignitions due to wire-to-wire contact, power line contact with vegetation, and power line contact with foreign objects and to raise the threshold for invoking PSPS. | 8.7.1 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition PSPS likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000016 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications | Grid Response Procedures and Notifications |  | GD_19 | Program | The electrical corporation’s procedures it uses to respond to faults, ignitions, or other issues detected on its grid that may result in a wildfire. | Reduce likelihood of ignitions due to equipment failure and contact with foreign objects. | 8.7.2 | Equipment ignition likelihood Contact by object ignition | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000017 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Minor Undergrounding Upgrades Projects | Undergrounding of electric lines and/or equipment |  | GD_2 | Project | Actions taken to convert overhead electric lines and/or equipment to underground electric lines and/or equipment (i.e., located underground and in accordance with GO 128). | To reduce likelihood of ignitions and to eliminate the need for invoking PSPS. | 8.2.2 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition PSPS likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000018 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk |  | GD_20 | Program | Work activity guidelines that designate what type of work can be performed during operating conditions of different levels of wildfire risk. Training for personnel on these guidelines and the procedures they prescribe, from normal operating procedures to increased mitigation measures to constraints on work performed. | To reduce likelihood of ignitions due to wire-to-wire contact, power line contact with vegetation, and power line contact with foreign objects and to raise the threshold for invoking PSPS. | 8.7.3 | Equipment ignition likelihood Contact by object ignition | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000019 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Workforce Planning | Workforce Planning |  | GD_21 | Program | Programs to ensure that the electrical corporation has qualified asset personnel and to ensure that both employees and contractors tasked with asset management responsibilities are adequately trained to perform relevant work. | To ensure staff and contractors performing Grid Design, Operations, and Maintenance activities including construction, asset maintenance, asset inspections, quality assurance audits, quality checks, data entry, work order management, and asset program management are adequately qualified and trained to perform their assigned work activities. | 8.8 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000020 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Detailed Inspections | Asset inspections |  | GD_22 | Program | Inspections of overhead electric sub-transmistion and distribution lines, equipment, and right-of-way. Detailed Inspections are careful visual inspections and maintenance, where individual assets are carefully examined, visually, and the condition of each rated and recorded per GO-95. | Reduce likelihood of ignitions due to equipment failure and contact with foreign objects. | 8.3.1 | Equipment ignition likelihood Contact by object ignition | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 28 |  | In Progress
1010000021 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Patrol Inspections | Asset inspections |  | GD_23 | Program | Inspections of overhead electric sub-transmistion and distribution lines, equipment, and right-of-way. Patrol Inspections are visual inspections of assets along rights-of- way that are designed to identify obvious hazards per GO-95. | Reduce likelihood of ignitions due to equipment failure and contact with foreign objects. | 8.3.2 | Equipment ignition likelihood Contact by object ignition | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 102 |  | In Progress
1010000022 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | UAV Thermography Inspections | Asset inspections |  | GD_24 | Program | Inspections of overhead electric sub-transmistion and distribution lines, equipment, and right-of-way. UAV Thermography Inspections are inspections of assets in the right-of-way using aerial (UAV) Thermography. | Reduce likelihood of ignitions due to equipment failure. | 8.3.3 | Equipment ignition likelihood | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000023 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | UAV HD Photography/Videography Inspections | Asset inspections |  | GD_25 | Program | Inspections of overhead electric sub-transmistion and distribution lines, equipment, and right-of-way. UAV HD Photography/ Videography Inspections are inspections of assets in the right-of-way using aerial (UAV) HD photography and high definition video cameras. | Reduce likelihood of equipment failure and contact with foreign objects. | 8.3.4 | Equipment ignition likelihood Contact by object ignition | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000024 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | 3rd Party Ground Patrol Inspections | Asset inspections |  | GD_26 | Program | Inspections of overhead electric sub-transmistion and distribution lines, equipment, and right-of-way. 3rd Party Ground Patrol Inspections are Patrol Inspections performed by an independent 3rd Party and are visual inspections of assets along rights-of- way that are designed to identify obvious hazards per GO-95. | Reduce likelihood of ignitions due to equipment failure and contact with foreign objects. | 8.3.5 | Equipment ignition likelihood Contact by object ignition | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 0 |  | Planned
1010000025 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Intrusive Pole Inspections | Asset inspections |  | GD_27 | Program | In accordance with GO 165, intrusive inspections of wood poles involve movement of soil, taking samples for analysis, and/or using more sophisticated diagnostic tools beyond visual inspections or instrument reading. | To reduce the likelihood of ignitions due to structure failures and to raise the threshold for invoking PSPS. | 8.3.6 | Equipment ignition likelihood PSPS Likelihood | Quantitative | # of Poles Tested | No |  |  | 2026 | 2 | 0 |  | Planned
1010000026 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Substation inspections | Asset inspections |  | GD_28 | Program | In accordance with GO 174, inspection of substations performed by qualified persons and according to the frequency established by the utility, including record-keeping. | Reduce likelihood of ignitions due to equipment failure and contact with foreign objects. | 8.3.7 | Equipment ignition likelihood Contact by object ignition | Quantitative | # of Substations Inspected | No |  |  | 2026 | 2 | 78 |  | In Progress
1010000027 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Covered Conductor Replacement Project (Pole Assessment) | Distribution pole replacements and reinforcements |  | GD_3 | Project | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. Pole assessments and replacement or remediation are conducted in conjuction with the covered conductor replacement (reconductor) GD_1 initiative due to synergy between the two projects. | To reduce the likelihood of ignitions due to structure failures and to raise the threshold for invoking PSPS. | 8.2.3 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition PSPS likelihood | Quantitative | # of Poles Replaced or Reinforced | No |  |  | 2026 | 2 | 158 |  | Completed
1010000028 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Evacuation Route Hardening Project | Distribution pole replacements and reinforcements |  | GD_4 | Project | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. Instals fire resistant wire wrap mesh on wood poles. Also, wood poles that must be replaced are preferentially replaced with light weight steel or fire resistant composite poles. | To harden evacuation routes) to allow the safe evacuation of the public in the event of a wildfire and to allow the mobility for First Responders to move assets in and out of the wildfire areas to allow them to actively fight the wildfire, save lives, protect property, and minimize environmental damage. | 8.2.3 | Wildfire exposure potential Wildfire vulnerability | Quantitative | # of Poles Hardened with Wire Mesh Wrap | No |  |  | 2026 | 2 | 525 |  | Completed
1010000029 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Traditional overhead hardening | Traditional overhead hardening |  | GD_5 | Program | Maintenance, repair, and replacement of capacitors, circuit breakers, cross-arms, transformers, fuses, and connectors (e.g., hot line clamps) with the intention of minimizing the risk of ignition. | To reduce the likelihood of ignitions due to equipment failures. | 8.2.5 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000030 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Bear Valley Solar Energy Project | Microgrids |  | GD_6 | Project | Development and deployment of microgrids that may reduce the risk of ignition, risk from PSPS, and wildfire consequence. “Microgrid” is defined by Public Utilities Code section 8370(d). BVES proposes to construct the Bear Valley Solar Energy Project (BVSEP), 5 MW alternating current single-axis tracker solar generation facility, to be constructed on a 21-acre site within the BVES service territory. | To minimize the impact of the loss of all SCE energy imports to the BVES service area due to a SCE-directed PSPS of the SCE supply lines to BVES. | 8.2.7 | PSPS exposure potential PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000031 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Bear Valley Energy Storage Project | Microgrids |  | GD_7 | Project | Development and deployment of microgrids that may reduce the risk of ignition, risk from PSPS, and wildfire consequence. “Microgrid” is defined by Public Utilities Code section 8370(d). BVES proposes to construct an energy storage project of approximately 5 MW/20 MWh (four-hour) Lithium-Ion NMC utility-grade battery located in the BVES maintenance yard. | To minimize the impact of the loss of all SCE energy imports to the BVES service area due to a SCE-directed PSPS of the SCE supply lines to BVES. | 8.2.7 | PSPS exposure potential PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000032 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Switch and Field Device Automation | Installation of system automation equipment |  | GD_8 | Project | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). This project automates switches and field devices through to SCADA network. | To improve ability to quickly locate and isolate faults, remotely adjust protective settings, and remotely sectionalize the grid. | 8.2.8 | Equipment ignition likelihood PSPS exposure potential PSPS vulnerability | Quantitative | # of switches connected to SCADA | No |  |  | 2026 | 2 | 5 |  | In Progress
1010000033 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Capacitor Bank Upgrade Project | Installation of system automation equipment |  | GD_9 | Project | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). This project automates switches and field devices through to SCADA network. | Reduce likelihood ignition due to equipment failure. | 8.2.8 | Equipment ignition likelihood | Quantitative | # of units replaced | No |  |  | 2026 | 2 | 0 |  | Planned
1010000034 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | Transmission pole/tower replacements and reinforcements |  | N/A | Project | Remediation, adjustments, or installations of new equipment to improve or replace existing transmission towers (e.g., structures such as lattice steel towers or tubular steel poles that support lines at or above 65kV). | BVES does not own or operate any transmission lines. | 8.2.4 | N/A | N/A |  | No |  | BVES does not own or operate any transmission assets; therefore, Bear Valley does not undertake this activity. | 2026 | 2 |  |  | Completed
1010000035 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots | Emerging grid hardening technology installations and pilots |  | N/A | Project | Development, deployment, and piloting of novel grid hardening technology. | BVES does not have any Emerging grid hardening technology installations and pilots planned for 2026 thorugh 2028. | 8.2.6 | N/A | N/A |  | No |  | BVES does not have any programs under this initiative | 2026 | 2 |  |  | Completed
1010000036 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Line removals (in HFTD) | Line removals (in HFTD) |  | N/A | Project | Removal of overhead lines to minimize the risk of ignition due to the design, location, or configuration of electric equipment in HFTDs. | BVES does not have any line removal projects planned for 2026 thorugh 2028. | 8.2.9 | N/A | N/A |  | No |  | BVES does not have any programs under this initiative | 2026 | 2 |  |  | Completed
1010000037 | BVES | 2026-08-03 | Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | Other grid topology improvements to mitigate or reduce PSPS events |  | N/A | Project | Actions taken to mitigate or reduce PSPS events in terms of geographic scope and number of customers affected not covered by another initiative. | The objectives of this initiative are achieved through BVES's installation of system automation equipment initiatives. | 8.2.11 | N/A | N/A |  | No |  | BVES does not have any programs under this initiative | 2026 | 2 |  |  | Completed
1010000038 | BVES | 2026-08-03 | Risk Methodology and Assessment | Risk Assessment enterprise system | Risk Assessment enterprise system |  | RMA_1 | Program | Development and use of tools and processes to assess the risk of wildfire and PSPS across an electrical corporation’s service territory. | Develop and implement tools and processes to assess the risk of wildfire and PSPS across the BVES service area. | 5 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000039 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Advanced weather monitoring and weather stations | Environmental monitoring systems |  | SAF_1 | Program | Development and deployment of systems which measure environmental characteristics, such as fuel moisture, air temperature, and velocity. Initiative maintains 20 weather stations and evaluates the need for additional weather stations. | Provide accurate and realtime environmental characteristics, such as fuel moisture, air temperature, and velocity. | 10.2 | Wildfire spread Wildfire hazard PSPS likelihood | Quantitative | Number of Weather Stations Serviced | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000040 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Integrate Environmental Monitoring Network as a standard feed into the Distribution Management Center. Advanced weather monitoring and weather stations | Environmental monitoring systems |  | SAF_1 | Program | Development and deployment of systems which measure environmental characteristics, such as fuel moisture, air temperature, and velocity. Initiative maintains 20 weather stations and evaluates the need for additional weather stations. | Provide accurate and realtime environmental characteristics, such as fuel moisture, air temperature, and velocity. | 10.2 | Wildfire spread Wildfire hazard PSPS likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000041 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Install Fault Indicators | Grid monitoring systems |  | SAF_2 | Program | Development and deployment of systems that checks the operational conditions of electrical facilities and equipment and detects such things as faults, failures, and recloser operations. The program aims to maintain connected fault indicators (FIs) that are installed in the sub-transmission and distribution system to the Supervisory Control and Data Acquisition (SCADA) network, which allows remote identification of the fault zone. | Reduce time to locate and identify a fault and arrive at the fault location to quickly address the fault and any associated ignition; thereby, greater opportunity to reduce the risk of a wildfire. | 10.3 | Equipment ignition likelihood | Quantitative | % of Installed FI's Serviced | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000042 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Integrate FIs as a standard feed into the Distribution Management Center. | Grid monitoring systems |  | SAF_2 | Program | Development and deployment of systems that checks the operational conditions of electrical facilities and equipment and detects such things as faults, failures, and recloser operations. The program aims to maintain connected fault indicators (FIs) that are installed in the sub-transmission and distribution system to the Supervisory Control and Data Acquisition (SCADA) network, which allows remote identification of the fault zone. | Reduce time to locate and identify a fault and arrive at the fault location to quickly address the fault and any associated ignition; thereby, greater opportunity to reduce the risk of a wildfire. | 10.3 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000043 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Online Diagnostic System | Grid monitoring systems |  | SAF_3 | Project | Development and deployment of systems that checks the operational conditions of electrical facilities and equipment and detects such things as faults, failures, and recloser operations. Project installs continuous monitor sensors to provide usable grid insight information that is measured, reported, and documented. System is designed to pinpoint irregularities, which may be due to degrading/imminent hardware failures, as well as identify objects such as vegetation contacting the lines. | Enables early detection of potential problems before they develop into ignition sources. | 10.3 | Equipment ignition likelihood Contact from vegetation ignition likelihood | Quantitative | Number of circuits installed on per year. | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000044 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Conduct annual review and evaluation of Online Diagnostic system database of system detections. | Grid monitoring systems |  | SAF_3 | Program | Development and deployment of systems that checks the operational conditions of electrical facilities and equipment and detects such things as faults, failures, and recloser operations. Project installs continuous monitor sensors to provide usable grid insight information that is measured, reported, and documented. System is designed to pinpoint irregularities, which may be due to degrading/imminent hardware failures, as well as identify objects such as vegetation contacting the lines. | Enables early detection of potential problems before they develop into ignition sources. | 10.3 | Equipment ignition likelihood Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000045 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Autonomous Monitoring of Power Line Infrastructure | Ignition detection systems |  | SAF_4 | Project | Development and deployment of systems which discover or identify the presence or existence of an ignition, such as cameras. Installs the iSIU system at various locations in the sub-transmission and distribution systems. The iSIU system leverages AI to continuous monitor facilities and provides automated monitoring of asset physical condition as well as ignition monitoring. | Allow for autonomous monitoring of the power line infrastructure to detect ignitions and to advise operators on equipment status and potential hazardous events. | 10.4 | Wildfire hazard Equipment ignition likelihood Contact from vegetation ignition likelihood | Quantitative | % of Installed Sensors Serviced | No |  |  | 2026 | 2 | 0 |  | Planned
1010000046 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Integrate issue as a standard feed into the Distribution Management Center. | Ignition detection systems |  | SAF_4 | Program | Development and deployment of systems which discover or identify the presence or existence of an ignition, such as cameras. Installs the iSIU system at various locations in the sub-transmission and distribution systems. The iSIU system leverages AI to continuous monitor facilities and provides automated monitoring of asset physical condition as well as ignition monitoring. | Allow for autonomous monitoring of the power line infrastructure to detect ignitions and to advise operators on equipment status and potential hazardous events. | 10.4 | Wildfire hazard Equipment ignition likelihood Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000047 | BVES | 2026-08-03 | Situational Awareness and Forecasting | ALERT Wildfire Cameras | Ignition detection systems |  | SAF_5 | Program | Development and deployment of systems which discover or identify the presence or existence of an ignition, such as cameras. Program involves providing assistance to the ALERT Wildfire Consortium to maintain 15 HD ALERT Wildfire Cameras, which provide complete coverage of the BVES Service Area. Additionally, the program provides support to the ALERT Wildfire Consortium in upgrading cameras and equipment and installing new cameras and equipment. | Allow for remote and autonomous monitoring of the BVES service area to detect ignitions, fires, and monitor any wildfires. | 10.4 | Wildfire hazard | Quantitative | Number of ALERTWildfire Cameras Evaluated by BVES in Operability and Coverage Review | No |  |  | 2026 | 2 | 0 |  | Planned
1010000048 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Provide assistance as requested by ALERT Wildfire Consortium to maintain, upgrade, and/or expand ALERT Wildfire Cameras covering BVES Service Area. | Ignition detection systems |  | SAF_5 | Program | Development and deployment of systems which discover or identify the presence or existence of an ignition, such as cameras. Program involves providing assistance to the ALERT Wildfire Consortium to maintain 15 HD ALERT Wildfire Cameras, which provide complete coverage of the BVES Service Area. Additionally, the program provides support to the ALERT Wildfire Consortium in upgrading cameras and equipment and installing new cameras and equipment. | Allow for remote and autonomous monitoring of the BVES service area to detect ignitions, fires, and monitor any wildfires. | 10.4 | Wildfire hazard | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000049 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Weather forecasting | Weather forecasting |  | SAF_6 | Program | Development methodology for forecast of weather conditions relevant to electrical corporation operations, forecasting weather conditions and conducting analysis to incorporate into utility decision- making, learning and updates to reduce false positives and false negatives of forecast PSPS conditions. Program leverages Technosylva’s models, to provide: (1) On-demand, real time wildfire behavior modeling, predictive spread conditions, and derivation of potential impacts analysis; (2)Ability to conduct simulations on-demand, to reflect changing conditions or local data observations, including proactive “what if” scenarios; and (3) Weather and wildfire risk forecasting for BVES’s assets and the service territory using daily weather prediction integration to support PSPS activation calls and response operations. Also, program engages an expert weather consultant to provide BVES specific weather forecasts at least weekly and more frequently during fire threat weather conditions. | Forecast weather conditions relevant to Bear Valley’s operations and support Bear Valley’s decision- making in its operational actions including PSPS to reduce wildfire risk. | 10.5 | Wildfire spread Wildfire hazard PSPS likelihood | Quantitative | Percent Time Each Year Weather Stations are Operational | No |  |  | 2026 | 2 | 100% |  | In Progress
1010000050 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Maintain WFA-E Capability and Weather Consultant Coverage for Each Year. | Weather forecasting |  | SAF_6 | Program | Development methodology for forecast of weather conditions relevant to electrical corporation operations, forecasting weather conditions and conducting analysis to incorporate into utility decision- making, learning and updates to reduce false positives and false negatives of forecast PSPS conditions. Program leverages Technosylva’s models, to provide: (1) On-demand, real time wildfire behavior modeling, predictive spread conditions, and derivation of potential impacts analysis; (2)Ability to conduct simulations on-demand, to reflect changing conditions or local data observations, including proactive “what if” scenarios; and (3) Weather and wildfire risk forecasting for BVES’s assets and the service territory using daily weather prediction integration to support PSPS activation calls and response operations. Also, program engages an expert weather consultant to provide BVES specific weather forecasts at least weekly and more frequently during fire threat weather conditions. | Forecast weather conditions relevant to Bear Valley’s operations and support Bear Valley’s decision- making in its operational actions including PSPS to reduce wildfire risk. | 10.5 | Wildfire spread Wildfire hazard PSPS likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000051 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Fire potential index | Fire potential index |  | SAF_7 | Program | Calculation and application of a landscape scale index used as a proxy for assessing real-time risk of a wildfire under current and forecasted weather conditions. Program implements a Fire Potential Index (FPI) model developed by Technosylva and a process to evaluate FPI at least daily or more frequently during fire threat weather conditions. | Identify areas susceptible to ignitions where BVES facilities are operating and inform Bear Valley’s operational decision-making in its operational actions including PSPS to reduce wildfire risk. | 10.6 | Wildfire spread Wildfire hazard PSPS likelihood | Quantitative | FPI Model Domain Size in Mi^2 | No |  |  | 2026 | 2 | 3168 |  | Completed
1010000052 | BVES | 2026-08-03 | Situational Awareness and Forecasting | Integrate FPI as a standard feed into the Distribution Management Center. | Fire potential index |  | SAF_7 | Program | Calculation and application of a landscape scale index used as a proxy for assessing real-time risk of a wildfire under current and forecasted weather conditions. Program implements a Fire Potential Index (FPI) model developed by Technosylva and a process to evaluate FPI at least daily or more frequently during fire threat weather conditions. | Identify areas susceptible to ignitions where BVES facilities are operating and inform Bear Valley’s operational decision-making in its operational actions including PSPS to reduce wildfire risk. | 10.6 | Wildfire spread Wildfire hazard PSPS likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000053 | BVES | 2026-08-03 | Vegetation Management and Inspection | Detailed Inspections | Vegetation management inspections |  | VM_1 | Program | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. Detailed Inspections are careful visual inspections and maintenance of vegetation around the distribution right-of-way, where individual trees are carefully examined, visually, and the condition of each rated and recorded per GO-95. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.2.1 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 28 |  | In Progress
1010000054 | BVES | 2026-08-03 | Vegetation Management and Inspection | Pole clearing | Pole clearing |  | VM_10 | Program | Plan and execution of vegetation removal around poles per Public Resources Code section 4292 and outside the requirements of Public Resources Code section 4292 (e.g., pole clearing performed outside of the State Responsibility Area). | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.4 | Contact from vegetation ignition likelihood | Quantitative | # of Poles Cleared | No |  |  | 2026 | 2 | 88 |  | Completed
1010000055 | BVES | 2026-08-03 | Vegetation Management and Inspection | Wood and slash management | Wood and slash management |  | VM_11 | Program | Actions taken to manage all downed wood and “slash” generated from vegetation management activities. | Reduction of available fuels for the purpose of minimizing source material that could ignite and propagate a wildfire. | 9.5 | Wildfire exposure potential | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress
1010000056 | BVES | 2026-08-03 | Vegetation Management and Inspection | Substation defensible space | Defensible space |  | VM_12 | Program | Actions taken to reduce ignition probability and wildfire consequence due to contact with substation equipment. | Reduce risk of vegetation contact with electrical facilities and substation equipment. | 9.6 | Contact from vegetation ignition likelihood | Quantitative | # of Substations Cleared | No |  |  | 2026 | 2 | 13 |  | Completed
1010000057 | BVES | 2026-08-03 | Vegetation Management and Inspection | Emergency response vegetation management | Activities based on weather conditions |  | VM_13 | Program | Actions taken in accordance with weather condition forecasts that indicate an elevated fire threat in terms of ignition probability and wildfire potential. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.9 | Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | Completed | Completed
1010000058 | BVES | 2026-08-03 | Vegetation Management and Inspection | Post-fire service restoration | Post-fire service restoration |  | VM_14 | Program | Actions taken during post-fire restoration to restore power while active fire suppression is ongoing and actions that occur following active fire suppression during the post-fire suppression repair and rehabilitation phases of fire protection operations. | Safe restoration of electric service. | 9.10 | Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Completed | Completed
1010000059 | BVES | 2026-08-03 | Vegetation Management and Inspection | Vegetation Management Quality assurance / quality control | Quality assurance / quality control |  | VM_15 | Program | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | To assure compliance with vegetation management standards and specifications and to identify gaps and areas of improvement in the vegetation management programs. | 9.11 | Contact from vegetation ignition likelihood | Quantitative | # of VM QCs Performed | No |  |  | 2026 | 2 | 66 |  | In Progress
1010000060 | BVES | 2026-08-03 | Vegetation Management and Inspection | Vegetation Management Open work orders | Work orders |  | VM_16 | Program | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe vegetation management activities. | To ensure vegetation management work orders are properly completed in an efficient, timely, and safety based prioritized manner. | 9.12 | Contact from vegetation ignition likelihood | Quantitative | 90% or more of work orders completed on schedule for the year | No |  |  | 2026 | 2 | 100 |  | In Progress
1010000061 | BVES | 2026-08-03 | Vegetation Management and Inspection | Vegetation Management Workforce planning | Workforce Planning |  | VM_17 | Program | Programs to ensure that the electrical corporation has qualified personnel and to ensure that both employees and contractors tasked with vegetation management responsibilities are adequately trained to perform relevant work. | To ensure staff and contractors performing vegetation management activities including pruning, removal, inspections, quality assurance audits, quality checks, data entry, work order management, and vegetation program management are adequately qualified and trained to perform their assigned work activities. | 9.13 | Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | Completed | Completed
1010000062 | BVES | 2026-08-03 | Vegetation Management and Inspection | Patrol Inspections | Vegetation management inspections |  | VM_2 | Program | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. Patrol Inspections are visual inspections of vegetation along rights-of- way that are designed to identify obvious hazards per GO-95. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.2.2 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 102 |  | In Progress
1010000063 | BVES | 2026-08-03 | Vegetation Management and Inspection | UAV HD Photography/Videography Inspections | Vegetation management inspections |  | VM_3 | Program | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. UAV HD Photography/ Videography Inspections are inspections of the right-of-way using aerial (UAV) HD photography and high definition video cameras. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.2.3 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000064 | BVES | 2026-08-03 | Vegetation Management and Inspection | LiDAR Inspections | Vegetation management inspections |  | VM_4 | Program | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. LiDAR Inspections are Inspections of right-of-way using LiDAR. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.2.4 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000065 | BVES | 2026-08-03 | Vegetation Management and Inspection | 3rd Party Ground Patrol Inspections | Vegetation management inspections |  | VM_5 | Program | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. 3rd Party Ground Patrol Inspections are Patrol Inspections performed by an independent 3rd Party and are visual inspections of vegetation along rights-of- way that are designed to identify obvious hazards per GO 95. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.2.5 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles Inspected | No |  |  | 2026 | 2 | 0 |  | Planned
1010000066 | BVES | 2026-08-03 | Vegetation Management and Inspection | Substation inspections | Vegetation management inspections |  | VM_6 | Program | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. Substation Inspections are inspections of vegetation surrounding substations, performed by qualified persons. | Reduce risk of vegetation contact with electrical facilities and substation equipment. | 9.2.6 | Contact from vegetation ignition likelihood | Quantitative | # of Substations Inspected | No |  |  | 2026 | 2 | 78 |  | In Progress
1010000067 | BVES | 2026-08-03 | Vegetation Management and Inspection | Satellite Imaging Inspections | Vegetation management inspections |  | VM_7 | Program | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. Satellite Imaging Inspections are inspections utilizing satellite imaging and AiDash software to provide a rapid assessment of BVES’s service territory and insight into vegetation that should be assessed or moved up in priority for upcoming patrol, detailed, or third party ground inspections. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.2.7 | Contact from vegetation ignition likelihood | Quantitative | Inspection of Entire Service Area | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000068 | BVES | 2026-08-03 | Vegetation Management and Inspection | Fall-in Mitigation and High-risk Species | Pruning and Removal |  | VM_8 | Program | Pruning, removal, and other vegetation management activities that are performed as a result of inspections. Actions taken to identify and remove or otherwise remediate trees that pose a high risk of failure or fracture that could potentially strike electrical equipment and actions taken to reduce the ignition probability and wildfire consequence attributable to high-risk species of vegetation. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.3 | Contact from vegetation ignition likelihood | Quantitative | # of trees remediated or removed to prevent fall-in | No |  |  | 2026 | 2 | 55 |  | In Progress
1010000069 | BVES | 2026-08-03 | Vegetation Management and Inspection | Clearance | Pruning and Removal |  | VM_9 | Program | Pruning, removal, and other vegetation management activities that are performed as a result of inspections. Actions taken after inspection to ensure that vegetation does not encroach upon electrical equipment and facilities, such as tree trimming. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.3 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles Cleared | No |  |  | 2026 | 2 | 33.6 |  | In Progress
1010000070 | BVES | 2026-08-03 | Vegetation Management and Inspection | Integrated vegetation management | Integrated vegetation management |  | N/A | Program | Actions taken in accordance with Integrated Vegetation Management principles that are not covered by another initiative. | Reduce risk of vegetation contact with powerlines and electrical facilities. | 9.7 | N/A | N/A |  | No |  | BVES does not have any programs under this initiative | 2026 | 2 |  |  | Completed
1010000071 | BVES | 2026-08-03 | Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development |  | WMSD_1 | Program | Development and use of processes for deciding on a portfolio of mitigation initiatives to achieve maximum feasible risk reduction and that meet the goals of the WMP. | Develop and implement of processes for deciding on a portfolio of mitigation initiatives to achieve maximum feasible risk reduction and that meet the goals of the WMP. | 6 | Wildfire exposure potential Wildfire vulnerability PSPS exposure potential PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Progress | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000001 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000002 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000003 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000004 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000005 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000006 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000007 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000008 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000009 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000010 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000011 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000012 | Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000013 | Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000014 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000015 | Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000016 | Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000017 | Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000018 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000019 | Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000020 | Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000021 | Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000022 | Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000023 | Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000024 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000025 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000026 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000027 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 8
1020000028 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000029 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000030 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000031 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000032 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000033 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000034 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000035 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000036 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000037 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000038 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000039 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000040 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000041 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000042 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000043 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000044 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000045 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000046 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000047 | Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000048 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000049 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000050 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000051 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000052 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000053 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000054 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000055 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | BVES | 2026 | 2 | 0
1020000056 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000057 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000058 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000059 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000060 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  | BV does not currently record this data | BVES | 2026 | 2
1020000061 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  | BV does not currently record this data | BVES | 2026 | 2
1020000062 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  | BV does not currently record this data | BVES | 2026 | 2
1020000063 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  | BV does not currently record this data | BVES | 2026 | 2
1020000064 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000065 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000066 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000067 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000068 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000069 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000070 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000071 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000072 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000073 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000074 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000075 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000076 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000077 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000078 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000079 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000080 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000081 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000082 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000083 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000084 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000085 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000086 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000087 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000088 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000089 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000090 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000091 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000092 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000093 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000094 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000095 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000096 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000097 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000098 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000099 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | BV does not currently record this data | BVES | 2026 | 2
1020000100 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000101 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000102 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000103 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000104 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000105 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000106 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000107 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000108 | Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | BVES | 2026 | 2 | 0
1020000109 | Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | BVES | 2026 | 2 | 0
1020000110 | Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | BVES | 2026 | 2 | 156
1020000111 | Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | BVES | 2026 | 2 | 0
1020000112 | Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  |  | BVES | 2026 | 2 | 0
1020000113 | Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | BVES | 2026 | 2 | 0
1020000114 | Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | BVES | 2026 | 2 | 0
1020000115 | Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | BVES | 2026 | 2 | 0
1020000116 | Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | BVES | 2026 | 2 | 0
1020000117 | Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | BVES | 2026 | 2 | 0
1020000118 | Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | BVES | 2026 | 2 | 0
1020000119 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | BVES | 2026 | 2 | 0
1020000120 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | BVES | 2026 | 2 | 0
1020000121 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | BVES | 2026 | 2 | 0
1020000122 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | BVES | 2026 | 2 | 0
1020000123 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | BVES | 2026 | 2 | 0
1020000124 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | BVES | 2026 | 2 | 0
1020000125 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | BVES | 2026 | 2 | 0
1020000126 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | BVES | 2026 | 2 | 0
1020000127 | Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000128 | Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000129 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000130 | Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000131 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000132 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000133 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000134 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000135 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000136 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000137 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000138 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000139 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000140 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000141 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000142 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000143 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000144 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000145 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000146 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 54
1020000147 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000148 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000149 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000150 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 18
1020000151 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000152 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000153 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000154 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000155 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000156 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000157 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000158 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000159 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000160 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000161 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000162 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000163 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000164 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000165 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000166 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000167 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000168 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000169 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000170 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000171 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000172 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000173 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000174 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000175 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000176 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000177 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000178 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000179 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000180 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000181 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000182 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000183 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000184 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000185 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000186 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 42
1020000187 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000188 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000189 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000190 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000191 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000192 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000193 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000194 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000195 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000196 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000197 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000198 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000199 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000200 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000201 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000202 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BVES does not currently record this data | BVES | 2026 | 2
1020000203 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000204 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000205 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000206 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000207 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000208 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000209 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000210 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000211 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000212 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000213 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000214 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | BVES | 2026 | 2 | 0
1020000215 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000216 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000217 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000218 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000219 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000220 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000221 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000222 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000223 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000224 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000225 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000226 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000227 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000228 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000229 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000230 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000231 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000232 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000233 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000234 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000235 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000236 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000237 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000238 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000239 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000240 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000241 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000242 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000243 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000244 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000245 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000246 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000247 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000248 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000249 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000250 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | BVES | 2026 | 2 | 0
1020000251 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000252 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000253 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000254 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000255 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000256 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000257 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000258 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000259 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000260 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000261 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000262 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000263 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000264 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000265 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000266 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000267 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000268 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000269 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000270 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000271 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000272 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000273 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000274 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000275 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000276 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000277 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000278 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000279 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000280 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000281 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000282 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000283 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000284 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000285 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000286 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000287 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000288 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000289 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000290 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000291 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000292 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000293 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000294 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000295 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000296 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000297 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000298 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000299 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000300 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000301 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000302 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000303 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000304 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000305 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000306 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000307 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000308 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000309 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000310 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000311 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000312 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000313 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000314 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000315 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000316 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000317 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000318 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000319 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000320 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000321 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000322 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000323 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000324 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000325 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000326 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000327 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000328 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000329 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000330 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000331 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000332 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000333 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000334 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000335 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000336 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000337 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000338 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000339 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000340 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000341 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000342 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000343 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000344 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000345 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000346 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000347 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000348 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000349 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000350 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000351 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000352 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000353 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000354 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000355 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000356 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000357 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000358 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000359 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000360 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000361 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000362 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000363 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000364 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000365 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000366 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000367 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000368 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000369 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000370 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000371 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000372 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000373 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000374 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000375 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000376 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000377 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000378 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000379 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000380 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000381 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000382 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000383 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000384 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000385 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000386 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000387 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000388 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000389 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000390 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000391 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000392 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000393 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000394 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000395 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000396 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000397 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000398 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000399 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000400 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000401 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000402 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000403 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000404 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000405 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000406 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000407 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000408 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000409 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000410 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000411 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000412 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000413 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000414 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000415 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000416 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000417 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000418 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000419 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000420 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000421 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000422 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000423 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000424 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000425 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000426 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000427 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000428 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000429 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000430 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000431 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000432 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000433 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000434 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000435 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000436 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000437 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000438 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000439 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000440 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000441 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000442 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000443 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000444 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000445 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000446 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000447 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000448 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000449 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000450 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000451 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000452 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000453 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000454 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000455 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000456 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000457 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000458 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000459 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000460 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000461 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000462 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000463 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000464 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000465 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000466 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000467 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000468 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000469 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000470 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000471 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000472 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000473 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000474 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000475 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000476 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000477 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000478 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000479 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000480 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000481 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000482 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000483 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000484 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000485 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000486 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000487 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000488 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000489 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000490 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000491 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000492 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000493 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000494 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000495 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000496 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000497 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000498 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000499 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000500 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000501 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000502 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000503 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000504 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000505 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000506 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000507 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000508 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000509 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000510 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000511 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000512 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000513 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000514 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000515 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000516 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000517 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000518 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000519 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000520 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000521 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000522 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000523 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000524 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000525 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000526 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000527 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000528 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000529 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000530 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000531 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000532 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000533 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000534 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000535 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000536 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000537 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000538 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000539 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000540 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000541 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000542 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000543 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000544 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000545 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000546 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000547 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000548 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000549 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000550 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000551 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000552 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000553 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000554 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000555 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000556 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000557 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000558 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000559 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000560 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000561 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000562 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | BVES | 2026 | 2 | 0
1020000563 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000564 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000565 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000566 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000567 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000568 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000569 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000570 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000571 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000572 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000573 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000574 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000575 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000576 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000577 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000578 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000579 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000580 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000581 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000582 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000583 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000584 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000585 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000586 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000587 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000588 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000589 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000590 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000591 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000592 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000593 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000594 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000595 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000596 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000597 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000598 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000599 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000600 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000601 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000602 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000603 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000604 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000605 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000606 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000607 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000608 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000609 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000610 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000611 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000612 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000613 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000614 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000615 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000616 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000617 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000618 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000619 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000620 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000621 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000622 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000623 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000624 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000625 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000626 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000627 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000628 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000629 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000630 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000631 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000632 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000633 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000634 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000635 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000636 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000637 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000638 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000639 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000640 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000641 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000642 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000643 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000644 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000645 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000646 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000647 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000648 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000649 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000650 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000651 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000652 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000653 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000654 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000655 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000656 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000657 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000658 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000659 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000660 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000661 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000662 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000663 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000664 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000665 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000666 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000667 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000668 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000669 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000670 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000671 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000672 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000673 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000674 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000675 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000676 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000677 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000678 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000679 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000680 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000681 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000682 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000683 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000684 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000685 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000686 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000687 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000688 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000689 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000690 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000691 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000692 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000693 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000694 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000695 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000696 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000697 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000698 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000699 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000700 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000701 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000702 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000703 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000704 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000705 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000706 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000707 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000708 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000709 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000710 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 1240
1020000711 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000712 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000713 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000714 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000715 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000716 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000717 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000718 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 466
1020000719 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000720 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000721 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000722 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000723 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000724 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000725 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000726 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000727 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000728 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000729 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000730 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000731 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000732 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000733 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000734 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000735 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000736 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000737 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000738 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | BVES | 2026 | 2 | 0
1020000739 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000740 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000741 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000742 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000743 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000744 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000745 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000746 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000747 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000748 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000749 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000750 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000751 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000752 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000753 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000754 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1020000755 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000756 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000757 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000758 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000759 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000760 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000761 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000762 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000763 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000764 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000765 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000766 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000767 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000768 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000769 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000770 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000771 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000772 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000773 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000774 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000775 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000776 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000777 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000778 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000779 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000780 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000781 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000782 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000783 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000784 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000785 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000786 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000787 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000788 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000789 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000790 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000791 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000792 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000793 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000794 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000795 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000796 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000797 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000798 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000799 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000800 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000801 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000802 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | BV does not have any transmission lines | BVES | 2026 | 2
1020000803 | Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  |  | BVES | 2026 | 2 | 0

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | BVES | 2026 | 2 | 0
1040000001 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | BVES | 2026 | 2 | 0
1040000002 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1040000003 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000004 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000005 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000006 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | BVES | 2026 | 2 | 0
1040000007 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | BVES | 2026 | 2 | 0
1040000008 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1040000009 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000010 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000011 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000012 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | BVES | 2026 | 2 | 0
1040000013 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | BVES | 2026 | 2 | 0
1040000014 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1040000015 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000016 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000017 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000018 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | BVES | 2026 | 2 | 0
1040000019 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | BVES | 2026 | 2 | 0
1040000020 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1040000021 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000022 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2
1040000023 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | BV does not have any transmission lines | BVES | 2026 | 2

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000001 | Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000002 | Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000003 | Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000004 | Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000005 | Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000006 | Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000007 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000008 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000009 | Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000010 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000011 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000012 | Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000013 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000014 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000015 | Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000016 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000017 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000018 | Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000019 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000020 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000021 | Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000022 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000023 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000024 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000025 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000026 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000027 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000028 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000029 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000030 | Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000031 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000032 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000033 | Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000034 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000035 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000036 | Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000037 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000038 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000039 | Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000040 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000041 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000042 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000043 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000044 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000045 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000046 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000047 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000048 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000049 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000050 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000051 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000052 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000053 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000054 | Vegetation contact | Wire down event | Grow-in | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000055 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000056 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000057 | Vegetation contact | Wire down event | Grow-in | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000058 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000059 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000060 | Vegetation contact | Wire down event | Blow-in | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000061 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000062 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000063 | Vegetation contact | Wire down event | Blow-in | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000064 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000065 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000066 | Vegetation contact | Wire down event | Trunk failure | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000067 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000068 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000069 | Vegetation contact | Wire down event | Trunk failure | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000070 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000071 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000072 | Vegetation contact | Wire down event | Root failure | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000073 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000074 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000075 | Vegetation contact | Wire down event | Root failure | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000076 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000077 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000078 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000079 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000080 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000081 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000082 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000083 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000084 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000085 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000086 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000087 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000088 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000089 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000090 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000091 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000092 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000093 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000094 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000095 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000096 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000097 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000098 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000099 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000100 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000101 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000102 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000103 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000104 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000105 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000106 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000107 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000108 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000109 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000110 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000111 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000112 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000113 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000114 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000115 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000116 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000117 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000118 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000119 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000120 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000121 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000122 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000123 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000124 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000125 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000126 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000127 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000128 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000129 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000130 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000131 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000132 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000133 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000134 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000135 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000136 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000137 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000138 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000139 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000140 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000141 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000142 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000143 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000144 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000145 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000146 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000147 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000148 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000149 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000150 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000151 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000152 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000153 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000154 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000155 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000156 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000157 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000158 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000159 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000160 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000161 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000162 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000163 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000164 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000165 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000166 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000167 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000168 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000169 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000170 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000171 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000172 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000173 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000174 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000175 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000176 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000177 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000178 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000179 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000180 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000181 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000182 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000183 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000184 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000185 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000186 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000187 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000188 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000189 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000190 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000191 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000192 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000193 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000194 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000195 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000196 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000197 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000198 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000199 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000200 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000201 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000202 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000203 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000204 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000205 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000206 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000207 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000208 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000209 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000210 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000211 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000212 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000213 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000214 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000215 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000216 | Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000217 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000218 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000219 | Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000220 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000221 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000222 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000223 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000224 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000225 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000226 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000227 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000228 | Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000229 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000230 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000231 | Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000232 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000233 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000234 | Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000235 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000236 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000237 | Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000238 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000239 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000240 | Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000241 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000242 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000243 | Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000244 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000245 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000246 | Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000247 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000248 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000249 | Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000250 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000251 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000252 | Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000253 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000254 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000255 | Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000256 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000257 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000258 | Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000259 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000260 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000261 | Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000262 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000263 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000264 | Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000265 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000266 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000267 | Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000268 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000269 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000270 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000271 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000272 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000273 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000274 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000275 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000276 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000277 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000278 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000279 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000280 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000281 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000282 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000283 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000284 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000285 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000286 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000287 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000288 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000289 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 1
1050000290 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000291 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000292 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000293 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000294 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000295 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000296 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000297 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000298 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000299 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000300 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000301 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000302 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000303 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000304 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000305 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000306 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000307 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000308 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000309 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000310 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000311 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000312 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000313 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000314 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000315 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000316 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000317 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000318 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000319 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000320 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000321 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000322 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000323 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000324 | Vegetation contact | Unplanned Outage | Root failure | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000325 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000326 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000327 | Vegetation contact | Unplanned Outage | Root failure | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000328 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000329 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000330 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000331 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000332 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000333 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000334 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000335 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000336 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000337 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000338 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000339 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000340 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000341 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000342 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000343 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000344 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000345 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000346 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000347 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000348 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000349 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 1
1050000350 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000351 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000352 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000353 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000354 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000355 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000356 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000357 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000358 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000359 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000360 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000361 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000362 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000363 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000364 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000365 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000366 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000367 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 1
1050000368 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000369 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000370 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000371 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000372 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000373 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000374 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000375 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000376 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000377 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000378 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000379 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000380 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000381 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000382 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000383 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000384 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000385 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000386 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000387 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000388 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000389 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000390 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000391 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000392 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000393 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000394 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000395 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000396 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000397 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000398 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000399 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000400 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000401 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000402 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000403 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000404 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000405 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000406 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000407 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000408 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000409 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000410 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000411 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000412 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000413 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000414 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000415 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000416 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000417 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000418 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000419 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000420 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000421 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000422 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000423 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000424 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000425 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000426 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000427 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000428 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000429 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000430 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000431 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000432 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000433 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000434 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000435 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000436 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000437 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000438 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000439 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000440 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000441 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000442 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000443 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000444 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000445 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000446 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000447 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000448 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000449 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000450 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000451 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000452 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000453 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000454 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000455 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000456 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000457 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000458 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000459 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000460 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000461 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000462 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000463 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000464 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000465 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000466 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000467 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000468 | Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000469 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000470 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000471 | Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000472 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000473 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000474 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000475 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000476 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000477 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000478 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000479 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000480 | Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000481 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000482 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000483 | Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000484 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000485 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000486 | Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000487 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000488 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000489 | Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000490 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000491 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000492 | Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000493 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000494 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000495 | Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000496 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000497 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000498 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000499 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 1
1050000500 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000501 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000502 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000503 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000504 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000505 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 3
1050000506 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000507 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000508 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000509 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000510 | Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1050000511 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | BVES | 2026 | 2 | 1
1050000512 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | BVES | 2026 | 2 | 0
1050000513 | Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000514 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2
1050000515 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  | BV does not have any transmission lines | BVES | 2026 | 2

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000001 | Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000002 | Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000003 | Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000004 | Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000005 | Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000006 | Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000007 | Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000008 | Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000009 | Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000010 | Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000011 | Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000012 | Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000013 | Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000014 | Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000015 | Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000016 | Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000017 | Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000018 | Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000019 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000020 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000021 | Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000022 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000023 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000024 | Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000025 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000026 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000027 | Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000028 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000029 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000030 | Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000031 | Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000032 | Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000033 | Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000034 | Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000035 | Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000036 | Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000037 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000038 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000039 | Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000040 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000041 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000042 | Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000043 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000044 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000045 | Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000046 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000047 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000048 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000049 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000050 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000051 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000052 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000053 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000054 | Vegetation contact | Grow-in | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000055 | Vegetation contact | Grow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000056 | Vegetation contact | Grow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000057 | Vegetation contact | Grow-in | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000058 | Vegetation contact | Grow-in | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000059 | Vegetation contact | Grow-in | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000060 | Vegetation contact | Blow-in | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000061 | Vegetation contact | Blow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000062 | Vegetation contact | Blow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000063 | Vegetation contact | Blow-in | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000064 | Vegetation contact | Blow-in | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000065 | Vegetation contact | Blow-in | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000066 | Vegetation contact | Trunk failure | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000067 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000068 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000069 | Vegetation contact | Trunk failure | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000070 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000071 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000072 | Vegetation contact | Root failure | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000073 | Vegetation contact | Root failure | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000074 | Vegetation contact | Root failure | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000075 | Vegetation contact | Root failure | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000076 | Vegetation contact | Root failure | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000077 | Vegetation contact | Root failure | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000078 | Vegetation contact | Detached frond / limb / bark | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000079 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000080 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000081 | Vegetation contact | Detached frond / limb / bark | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000082 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000083 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000084 | Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000085 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000086 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000087 | Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000088 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000089 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000090 | Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000091 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000092 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000093 | Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000094 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000095 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000096 | Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000097 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000098 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000099 | Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000100 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000101 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000102 | Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000103 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000104 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000105 | Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000106 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000107 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000108 | Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000109 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000110 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000111 | Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000112 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000113 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000114 | Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000115 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000116 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000117 | Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000118 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000119 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000120 | Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000121 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000122 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000123 | Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000124 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000125 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000126 | Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000127 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000128 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000129 | Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000130 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000131 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000132 | Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000133 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000134 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000135 | Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000136 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000137 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000138 | Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000139 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000140 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000141 | Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000142 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000143 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000144 | Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000145 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000146 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000147 | Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000148 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000149 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000150 | Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000151 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000152 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000153 | Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000154 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000155 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000156 | Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000157 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000158 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000159 | Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000160 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000161 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000162 | Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000163 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000164 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000165 | Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000166 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000167 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000168 | Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000169 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000170 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000171 | Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000172 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000173 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000174 | Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000175 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000176 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000177 | Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000178 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000179 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000180 | Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000181 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000182 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000183 | Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000184 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000185 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000186 | Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000187 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000188 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000189 | Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000190 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000191 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000192 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000193 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000194 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000195 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000196 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000197 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000198 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000199 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000200 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000201 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000202 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000203 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000204 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000205 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000206 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000207 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000208 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000209 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000210 | Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000211 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000212 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000213 | Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000214 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000215 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000216 | Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000217 | Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000218 | Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000219 | Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000220 | Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000221 | Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000222 | Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000223 | Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000224 | Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000225 | Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000226 | Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000227 | Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000228 | Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000229 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000230 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000231 | Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000232 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000233 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000234 | Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000235 | Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000236 | Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000237 | Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000238 | Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000239 | Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000240 | Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000241 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000242 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000243 | Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000244 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000245 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000246 | Other | Other (other) | Distribution | Non-HFTD | # ignitions |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1060000247 | Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000248 | Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  | BVES | 2026 | 2 | 0
1060000249 | Other | Other (other) | Transmission | Non-HFTD | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000250 | Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2
1060000251 | Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  | BV does not have any transmission lines | BVES | 2026 | 2

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000001 | Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000002 | Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000003 | Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000004 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000005 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000006 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 452.79
1070000007 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000008 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 121.99
1070000009 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000010 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000011 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000012 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000013 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000014 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 1.27
1070000015 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000016 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000017 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000018 | Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000019 | Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000020 | Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000021 | Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000022 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000023 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000024 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000025 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000026 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000027 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000028 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000029 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000030 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000031 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000032 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000033 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000034 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000035 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000036 | Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000037 | Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000038 | Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000039 | Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000040 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000041 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000042 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 103.96
1070000043 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000044 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 37.87
1070000045 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000046 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000047 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000048 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000049 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000050 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000051 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000052 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000053 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1070000054 | Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000055 | Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000056 | Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000057 | Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000058 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000059 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000060 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000061 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000062 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000063 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000064 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000065 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000066 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000067 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000068 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000069 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000070 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000071 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1070000072 | Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000073 | Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000074 | Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000075 | Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000076 | Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000077 | Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000078 | Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 12
1070000079 | Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000080 | Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 2
1070000081 | Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000082 | Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000083 | Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000084 | Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000085 | Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000086 | Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000087 | Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000088 | Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000089 | Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | BVES | 2026 | 2 | 0
1070000090 | Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000091 | Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000092 | Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000093 | Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000094 | Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000095 | Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000096 | Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 19419
1070000097 | Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000098 | Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 3297
1070000099 | Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000100 | Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000101 | Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000102 | Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000103 | Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000104 | Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000105 | Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000106 | Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000107 | Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | BVES | 2026 | 2 | 0
1070000108 | Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000109 | Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000110 | Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000111 | Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000112 | Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000113 | Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000114 | Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 1301
1070000115 | Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000116 | Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 176
1070000117 | Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000118 | Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000119 | Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000120 | Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000121 | Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000122 | Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000123 | Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000124 | Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000125 | Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | BVES | 2026 | 2 | 0
1070000126 | AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000127 | AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000128 | AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000129 | AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000130 | AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000131 | AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000132 | AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 452
1070000133 | AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000134 | AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 81
1070000135 | AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000136 | AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000137 | AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000138 | AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000139 | AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000140 | AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000141 | AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000142 | AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000143 | AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | BVES | 2026 | 2 | 0
1070000144 | Substations |  | Non-HFTD | Urban | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000145 | Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000146 | Substations |  | Non-HFTD | Rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000147 | Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000148 | Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000149 | Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000150 | Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | BVES | 2026 | 2 | 8
1070000151 | Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000152 | Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 6
1070000153 | Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000154 | Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000155 | Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000156 | Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000157 | Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000158 | Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000159 | Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000160 | Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000161 | Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1070000162 | Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000163 | Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000164 | Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000165 | Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000166 | Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000167 | Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1070000168 | Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 9
1070000169 | Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1070000170 | Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 9
1070000171 | Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1070000172 | Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1070000173 | Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1070000174 | Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1070000175 | Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1070000176 | Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 2
1070000177 | Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1070000178 | Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1070000179 | Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000001 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000002 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000003 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000004 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000005 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000006 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000007 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000008 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000009 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000010 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000011 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000012 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000013 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000014 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000015 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000016 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000017 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000018 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000019 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000020 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000021 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000022 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000023 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000024 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000025 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000026 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000027 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000028 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000029 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000030 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000031 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000032 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000033 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000034 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000035 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000036 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000037 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000038 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000039 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000040 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000041 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000042 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000043 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000044 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000045 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000046 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000047 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000048 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000049 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000050 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000051 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000052 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000053 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1080000054 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000055 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000056 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000057 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000058 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000059 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000060 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000061 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000062 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000063 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000064 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000065 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000066 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000067 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000068 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000069 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000070 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000071 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1080000072 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000073 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000074 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000075 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000076 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000077 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000078 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000079 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000080 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000081 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000082 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000083 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000084 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000085 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000086 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000087 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000088 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000089 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1080000090 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000091 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000092 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000093 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000094 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000095 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1080000096 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000097 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000098 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000099 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000100 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000101 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000102 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000103 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000104 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000105 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000106 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1080000107 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000001 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000002 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000003 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000004 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000005 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000006 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000007 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000008 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000009 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000010 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 4.8
1090000011 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000012 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000013 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000014 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000015 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000016 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000017 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | BVES | 2026 | 2 | 0
1090000018 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000019 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000020 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000021 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000022 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000023 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000024 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000025 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000026 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000027 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000028 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000029 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000030 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000031 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000032 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000033 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000034 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000035 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | BV does not have any transmission lines | BVES | 2026 | 2
1090000036 | Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000037 | Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000038 | Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000039 | Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000040 | Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000041 | Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000042 | Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000043 | Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000044 | Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000045 | Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000046 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000047 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000048 | Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000049 | Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000050 | Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000051 | Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000052 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000053 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | BVES | 2026 | 2 | 0
1090000054 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000055 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000056 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000057 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000058 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000059 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | BV does not have any assets in Non-HFTD | BVES | 2026 | 2
1090000060 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000061 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000062 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000063 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000064 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000065 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000066 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000067 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000068 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000069 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000070 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0
1090000071 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | BVES | 2026 | 2 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | BVES | 2026 | 2 | 0
1100000001 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | BVES | 2026 | 2 | 0
1100000002 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | BVES | 2026 | 2 | 0
1100000003 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | BVES | 2026 | 2 | 0
1100000004 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | BVES | 2026 | 2 | 0
1100000005 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | BVES | 2026 | 2 | 0
1100000006 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | BVES | 2026 | 2 | 0
1100000007 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | BVES | 2026 | 2 | 0
1100000008 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | BVES | 2026 | 2 | 0
1100000009 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | BVES | 2026 | 2 | 0
1100000010 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | BVES | 2026 | 2 | 0
1100000011 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | BVES | 2026 | 2 | 0
1100000012 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | BVES | 2026 | 2 | 0
1100000013 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | BVES | 2026 | 2 | 0
1100000014 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | BVES | 2026 | 2 | 0
1100000015 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | BVES | 2026 | 2 | 0
1100000016 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | BVES | 2026 | 2 | 0
1100000017 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | BVES | 2026 | 2 | 0
1100000018 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | BVES | 2026 | 2 | 0
1100000019 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | BVES | 2026 | 2 | 0
1100000020 | Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | BVES | 2026 | 2 | 0
1100000021 | Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | BVES | 2026 | 2 | 18705.5
1100000022 | Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | BVES | 2026 | 2 | 18705.5
1100000023 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | BVES | 2026 | 2 | 45.95
1100000024 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | BVES | 2026 | 2 | 45.95
1100000025 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | BVES | 2026 | 2 | 0.97386
1100000026 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | BVES | 2026 | 2 | 0.97386
1100000027 | Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | BVES | 2026 | 2 | 0
1100000028 | Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BVES | 2026 | 2 | 0
1100000029 | Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BVES | 2026 | 2 | 0
1100000030 | Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BVES | 2026 | 2 | 0
1100000031 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BVES | 2026 | 2 | 0
1100000032 | Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BVES | 2026 | 2 | 0
1100000033 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | BVES | 2026 | 2 | 0
1100000034 | Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | BVES | 2026 | 2 | 0
1100000035 | Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | BVES | 2026 | 2 | 0
1100000036 | Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | BVES | 2026 | 2 | 0
1100000037 | Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | BVES | 2026 | 2 | 0
1100000038 | Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | BVES | 2026 | 2 | 0
1100000039 | Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | BVES | 2026 | 2 | 0
1100000040 | Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | BVES | 2026 | 2 | 0
1100000041 | Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | BVES | 2026 | 2 | 0
1100000042 | Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | BVES | 2026 | 2 | 0
1100000043 | Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | BVES | 2026 | 2 | 0

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1120000000 | 2369bv | Secondary clearance with comm | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000001 | 2344BV | Ground molding high signs POLE TAG | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000002 | 5182BV | High signs | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000003 | 12291BV | Slack span guy | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000004 | 3611BV | Ground molding | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000005 | 2516BV | High signs | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000006 | 12293BV | Improper dwn guy fixture bent bolts | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000007 | 2534BV | High Signs | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000008 | 8612BV | High Signs | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000009 | 4985BV | High signs | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000010 | 1295BV | High signs | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-02 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000011 | 5175BV | High signs xarms split | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-03 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000012 | 5176BV | Ground molding | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-03 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000013 | 12413BV | High signs | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-03 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000014 | 16670BV | High signs GROUND MOLDING | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-03 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000015 | 16672BV | High Signs. Molding, Sec underarm fiber broken | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-03 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000016 | 8605BV | High signs, 3 points of attachment sec seprated primary | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-03 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000017 | 8603BV | Ground molding | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-03-03 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000018 | 4739BV | Low SEC Midspan touching comms | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-04 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000019 | 8177BV | Through Bolt to Long | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-04 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000020 | 8178BV | Through Bolt to Long | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-04 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000021 | 1014 Cameron Dr | Missing Pole Tag/ XFMR Missing ground | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-04 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000022 | BV11450 | No Primary Span Guy | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-04 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000023 | CTC1211623 | Rotten butt, high signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000024 | 11126BV | High Signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000025 | 11271BV | Secondary needs to be re sagged | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000026 | CTC1211632 | Need pipe straps on riser | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000027 | CTC1211624 | High signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000028 | CTC1210274 | High signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000029 | 12562BV | High signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000030 | NO POLE TAG | Pole tag | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000031 | 5915BV | rotten butt | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000032 | 12259BV | High signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000033 | 11625BV | Fire wrap falling off | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000034 | 6960BV | Ground molding high signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000035 | 12101BV | High signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000036 | 12102BV | High signs | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000037 | 12302BV | Pipe Straps | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-03-06 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000038 | 10362BV | Pipe Straps | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-03-06 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000039 | CIT21432 | No Dwn Guy, Side Guy Tree Attch | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-09 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000040 | 16665BV | Service Crossing Property Rotten Butt | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-09 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000041 | 8772BV | High Sign | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-09 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000042 | 8773BV | Primary Netrual Under Molding | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-09 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000043 | 8774BV | Expulsion Fuse | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-03-09 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000044 | 64640bv | High Sign Missing Hardware | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000045 | 15239BV | Berndt To Verify Pole/ High Sign | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000046 | 1116BV | Ground Molding High Sign | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000047 | 12046BV | High Sign | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000048 | 12045BV | Sec clearance on Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000049 | 11905BV | High Signs | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000050 | CTC63135 | Tree Trim | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000051 | CTC63008 | High Sign, Molding, High Leg Clearance to the west need to install Quad | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000052 | CTC63009 | High Signs Molding | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000053 | 10613BV | High Signs Ground Molding | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000054 | CIT60446 | High Signs Ground Molding | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000055 | P6242 | High Signs Ground Molding | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000056 | 5394BV | xfmr arm looks bad rotten Butt | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000057 | 10193BV | Fire Wrap Falling | HFTD Tier 2 | Distribution | 2026-03-12 | 2031-03-12 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000058 | CTC1211715 | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-12 | 2031-03-12 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000059 | 11046BV | Idle Hardware, High Signs, Molding, Sec Touching Pole | HFTD Tier 2 | Distribution | 2026-03-12 | 2031-03-12 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000060 | 9734BV | SEC Clearance at pole from Comm | HFTD Tier 2 | Distribution | 2026-03-12 | 2031-03-12 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000061 | 15005BV | No strap on bottom conduit | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000062 | 15003BV | Missing Conduit Strap | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000063 | 10928BV | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000064 | CIT35796 | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000065 | CIT35794 | SEC Clearance on Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000066 | 5334BV | Through Bolt to Long | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000067 | CIT35793 | SEC Clearance on Pole, Cross Arm Bolt to long | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000068 | 6883BV | Molding | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000069 | 6834BV | Molding, Sec Clearance on Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000070 | 13092BV | High Signs | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000071 | 10881BV | Need Split Bolt, Molding | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000072 | 9036BV | High Signs | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000073 | 10346BV | Molding Loose | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000074 | 5059BV | Loose Molding High Signs | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000075 | 8357BV | Molding | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000076 | 6682BV | Side Guy To Low | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000077 | 5553BV | high signs molding | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000078 | 12481BV | high signs molding | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000079 | 5230BV | Molding, Cross Arm Through Bolt too long | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000080 | 11777BV | Conduit Straps | HFTD Tier 2 | Distribution | 2026-03-13 | 2031-03-13 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000081 | 10207BV | Primary Crossing within 10' of pole and not attached | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000082 | CTC1210304 | Sec Clearance | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000083 | 31742CIT | Side Guy more than 2' from strain | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000084 | CIT35787 | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000085 | CIT31664 | MOLDING | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000086 | CIT35788 | Steps are to low | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000087 | CIT23914 | Loose Conduit Straps | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000088 | CIT35790 | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000089 | CIT35941 | Side guy to low Long Bolt | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000090 | CIT35942 | Ground Molding, No Side Guy, Steps above phone | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000091 | CIT35695 | SEC Clearance on Pole | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000092 | CTC62456 | High Signs | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000093 | CTC62474 | Move SEC to XARM, Sec contact spanguy east midspan | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000094 | 4526BV | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000095 | 12139BV | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000096 | CIT35696 | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000097 | 8957BV | High Signs | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000098 | 7602BV | High Signs | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000099 | 6136BV | Sec Clearance ON POLE | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000100 | 6137BV | Sec Clearance ON POLE | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000101 | 6138BV | Pole is leaning | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000102 | CIT35939 | Span Guy to low | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000103 | 16722BV | Pole Top Split needs split bolt or replace | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000104 | 16723BV | SEC Clearance on Pole | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000105 | CIT31669 | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000106 | 5006BV | Remove pole steps above phone | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000107 | 6190BV | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000108 | CIT31672 | Ground Molding | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000109 | 5013BV | Span Guy To Low SEC Clearance | HFTD Tier 2 | Distribution | 2026-03-14 | 2031-03-14 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000110 | 15992BV | Slack Down Guys and span guys pole leaning east | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-16 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000111 | 3406BV | Missing Bolt Covers, Molding, Sec Clearance | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-16 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000112 | 3410BV | Arm is pulled over to east Idle Molding | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-16 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000113 | 11309BV | Sec Clearance on Pole, Trans Lead Clearance | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-16 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000114 | 11310BV | Sec Clearance on Pole, | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-16 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000115 | 6264BV | Move span guy up to open wire | HFTD Tier 2 | Distribution | 2026-04-07 18:39 | 2031-04-07 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000116 | 6261BV | Secondary touching pole | HFTD Tier 2 | Distribution | 2026-04-07 18:49 | 2031-04-07 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000117 | 7127BV | Broken underarm fiber | HFTD Tier 2 | Distribution | 2026-04-07 18:57 | 2031-04-07 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000118 | 33115CIT | Loose hardware on pins | HFTD Tier 2 | Distribution | 2026-04-07 19:21 | 2031-04-07 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000119 | 33120CIT | Loose hardware on pins | HFTD Tier 2 | Distribution | 2026-04-07 19:27 | 2031-04-07 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000120 | 33122CIT | Bent pin | HFTD Tier 2 | Distribution | 2026-04-07 19:31 | 2031-04-07 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000121 | 33125CIT | Cross arm is bowing | HFTD Tier 2 | Distribution | 2026-04-07 19:36 | 2031-04-07 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000122 | 11613BV | Secondary touching transformer | HFTD Tier 2 | Distribution | 2026-04-07 23:47 | 2031-04-07 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000123 | 7232BV | Primary neutral lead pulling on conductor | HFTD Tier 2 | Distribution | 2026-04-08 18:15 | 2031-04-08 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000124 | 6517BV | Missing primary down guy | HFTD Tier 2 | Distribution | 2026-04-08 22:10 | 2031-04-08 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000125 | 16082BV | Paul, leaning due to improper pole, tapping or lack of raking it back to begin with when it was brand new | HFTD Tier 2 | Distribution | 2026-04-08 22:44 | 2031-04-08 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000126 | 14708BV | Sec too low. Need guard arm or pull in new UG sec service and extend conduit higher | HFTD Tier 2 | Distribution | 2026-04-09 14:48 | 2031-04-09 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000127 | 7362BV | Neutral tag. | HFTD Tier 2 | Distribution | 2026-04-09 21:36 | 2031-04-09 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000128 | 7378BV | Idle hardware | HFTD Tier 2 | Distribution | 2026-04-09 21:43 | 2031-04-09 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000129 | 11418BV | Span guy is more than 2 feet from the strain | HFTD Tier 2 | Distribution | 2026-04-10 17:08 | 2031-04-10 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000130 | 7783BV | Damaged preform and needs guy guard | HFTD Tier 2 | Distribution | 2026-04-10 17:27 | 2031-04-10 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000131 | 10779BV | Idle down guy and queen post | HFTD Tier 2 | Distribution | 2026-04-10 17:30 | 2031-04-10 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000132 | 15420BV | 4K V down guy more than 2 feet below strain. Missing secondary span guy. | HFTD Tier 2 | Distribution | 2026-04-29 20:09 | 2031-04-29 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000133 | 15421BV | Transformer, secondary clearance off transformer case | HFTD Tier 2 | Distribution | 2026-04-29 20:11 | 2031-04-29 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000134 | 15424BV | 34KV improper down guy fixtures at secondary level. Bolts are bending. | HFTD Tier 2 | Distribution | 2026-04-29 20:13 | 2031-04-29 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000135 | 10179BV | Idle ground molding | HFTD Tier 2 | Distribution | 2026-04-29 20:19 | 2031-04-29 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000136 | 15422BV | 4K V span guys are slack | HFTD Tier 2 | Distribution | 2026-04-29 20:21 | 2031-04-29 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000137 | 15901BV | Bird guard, causing pothead to lean to the south | HFTD Tier 2 | Distribution | 2026-04-29 20:25 | 2031-04-29 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000138 | 15903BV | Idle down guy and idle down guy hardware | HFTD Tier 2 | Distribution | 2026-04-29 20:28 | 2031-04-29 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000139 | 4165BV | Needs sec span guy | HFTD Tier 2 | Distribution | 2026-05-08 21:12 | 2031-05-08 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000140 | 31724CIT | Sec service under comm | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000141 | 16100BV | Secondary clearance on mast of street light | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000142 | 10156BVT | Sec service laying on comm | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000143 | 60698CIT | Rotten pole | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000144 | 35823CIT | Move service to its span to get around tree trunk | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000145 | 10724BV | Loose hardware on span guy | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000146 | 12335BV | Service clearance over edge of road | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000147 | 35825CIT | Missing span guy | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000148 | 1210269CTC | Pole is leaning hard north | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000149 | 31729CIT | Pole is leaving hard north | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000150 | 4842BV | Missing primary span guy | HFTD Tier 2 | Distribution | 2026-05-11 17:51 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000151 | 5111BV | Pole step | HFTD Tier 2 | Distribution | 2026-05-11 19:02 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000152 | P_6169 | Not Bves pole | HFTD Tier 2 | Distribution | 2026-05-11 22:11 | 2031-05-11 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000153 | 6771BV | Sec skate is bent | HFTD Tier 2 | Distribution | 2026-06-05 16:54 | 2031-06-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000154 | 4851BV | Insulation falling off of primary wire | HFTD Tier 2 | Distribution | 2026-06-05 17:13 | 2031-06-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000155 | 6728BV | Sec clearance on pole | HFTD Tier 2 | Distribution | 2026-06-05 17:19 | 2031-06-05 | Level 3 | [8 empty] | BVES | 2026 | 2
1120000156 | 4750BV | Replace angle pins and or x-arm | HFTD Tier 2 | Distribution | 2026-06-05 17:32 | 2031-06-05 | Level 3 | [8 empty] | BVES | 2026 | 2