## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID (UMAT) | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | REPORTING YEAR | REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Patrol inspections |  | AI-01 | Program | Transmission Patrol Inspections | In accordance with GO 165, a simple visual inspection of applicable utility equipment and structures that is designed to identify obvious structural problems and hazards. | 8.3.1 | Equipment ignition likelihood | Quantitative | Facility Points | Yes |  |  | 2026 | 2 | 10156 |  | In Progress
1010000001 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Patrol Inspections |  | AI-02 | Program | Distribution Patrol Inspections | In accordance with GO 165, a simple visual inspection of applicable utility equipment and structures that is designed to identify obvious structural problems and hazards. | 8.3.1 | Equipment ignition likelihood | Quantitative | Facility Points | Yes |  |  | 2026 | 2 | 40450 |  | In Progress
1010000002 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Detail Inspections |  | AI-03 | Program | Transmission Detail Inspections | In accordance with GO 165, an inspection where individual pieces of equipment and structures are carefully examined, visually and through use of routine diagnostic test, as appropriate, and (if practical and if useful information can be so gathered) opened, and the condition of each rated and recorded. | 8.3.2 | Equipment ignition likelihood | Quantitative | Facility Points | Yes |  |  | 2026 | 2 | 627 |  | In Progress
1010000003 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Detail Inspections |  | AI-04 | Program | Distribution Detail Inspections | In accordance with GO 165, an inspection where individual pieces of equipment and structures are carefully examined, visually and through use of routine diagnostic test, as appropriate, and (if practical and if useful information can be so gathered) opened, and the condition of each rated and recorded. | 8.3.2 | Equipment ignition likelihood | Quantitative | Facility Points | Yes |  |  | 2026 | 2 | 5072 |  | In Progress
1010000004 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Intrusive Pole Inspections |  | AI-05 | Program | Transmission Intrusive Pole Inspections | May include pole-sounding, inspection hole drilling and excavation tests, designed to identify decay, wear or woodpecker damage, assess the condition of wood poles and identify the need for any treatment, repair or replacement. | 8.3.3 | Equipment ignition likelihood | Quantitative | Facility Points | Yes |  |  | 2026 | 2 | 1091 |  | In Progress
1010000005 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Intrusive Pole Inspections |  | AI-06 | Program | Distribution Intrusive Pole Inspections | May include pole-sounding, inspection hole drilling and excavation tests, designed to identify decay, wear or woodpecker damage, assess the condition of wood poles and identify the need for any treatment, repair or replacement. | 8.3.3 | Equipment ignition likelihood | Quantitative | Facility Points | Yes |  |  | 2026 | 2 | 3109 |  | In Progress
1010000006 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Enhanced IR (Infrared) Inspections on Transmission Lines |  | AI-07 | Program | Enhanced IR (Infrared) Inspections on Transmission Lines | Proactive identification and prevention of equipment failures through infrared inspections during peak loading intervals. | 8.3.6 | Equipment ignition likelihood | Quantitative | Facility Points | Yes |  |  | 2026 | 2 | 2155 |  | In Progress
1010000007 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Enhanced IR (Infrared) Inspections on Distribution Lines |  | AI-08 | Pilot | Enhanced IR (Infrared) Inspections on Distribution Lines | Proactive identification and prevention of equipment failures through infrared inspections during peak loading intervals. | 8.3.5 | Equipment ignition likelihood | Quantitative | Facility Points | Yes |  |  | 2026 | 2 | 674 |  | In Progress
1010000008 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Drone Inspections |  | AI-09 | Pilot | Transmission Drone Inspections | The Drone on Demand inspection program is utilized for identified transmission lines | 8.3.7 | Equipment ignition likelihood | Quantitative | Transmission Poles | Yes |  |  | 2026 | 2 | 349 |  | In Progress
1010000009 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Drone Inspections |  | AI-10 | Pilot | Distribution Drone Inspections | The Drone on Demand program, which conducts drone inspections on distribution lines, has been completed on a reactive basis. | 8.3.8 | Equipment ignition likelihood | Quantitative | Distribution Poles | Yes |  |  | 2026 | 2 | 674 |  | In Progress
1010000010 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Substation Inspections |  | AI-11 | Program | Substation Inspections | Maintain the integrity of Pacific Power’s power delivery system through a systematic program of inspections to identify and correct deficiencies before they cause an outage or create a safety hazard. | 8.3.4 | Equipment ignition likelihood | Quantitative | Substations | Yes |  |  | 2026 | 2 | 224 |  | In Progress
1010000011 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | QA/QC of AI-01 - Transmission Patrol |  | AI-14 | Program | QA/QC of AI-01 - Transmission Patrol | Using a combination of process controls, software tools, company policy, and physical record checking to quickly identify inaccuracies for corrective action, evaluation, root cause analysis and system improvements. | 8.5 | Equipment ignition likelihood | Quantitative | Facility Points | No |  |  | 2026 | 2 | 66 |  | In Progress
1010000012 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | QA/QC of AI-02 - Distribution Patrol |  | AI-15 | Program | QA/QC of AI-02 - Distribution Patrol | Using a combination of process controls, software tools, company policy, and physical record checking to quickly identify inaccuracies for corrective action, evaluation, root cause analysis and system improvements. | 8.5 | Equipment ignition likelihood | Quantitative | Facility Points | No |  |  | 2026 | 2 | 646 |  | In Progress
1010000013 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | QA/QC of AI-03 - Transmission Detailed |  | AI-16 | Program | QA/QC of AI-03 - Transmission Detailed | Using a combination of process controls, software tools, company policy, and physical record checking to quickly identify inaccuracies for corrective action, evaluation, root cause analysis and system improvements. | 8.5 | Equipment ignition likelihood | Quantitative | Facility Points | No |  |  | 2026 | 2 | 32 |  | In Progress
1010000014 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | QA/QC of AI-04 - Distribution Detailed |  | AI-17 | Program | QA/QC of AI-04 - Distribution Detailed | Using a combination of process controls, software tools, company policy, and physical record checking to quickly identify inaccuracies for corrective action, evaluation, root cause analysis and system improvements. | 8.5 | Equipment ignition likelihood | Quantitative | Facility Points | No |  |  | 2026 | 2 | 355 |  | In Progress
1010000015 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | QA/QC of AI-05 - Transmission Intrusive |  | AI-18 | Program | QA/QC of AI-05 - Transmission Intrusive | Using a combination of process controls, software tools, company policy, and physical record checking to quickly identify inaccuracies for corrective action, evaluation, root cause analysis and system improvements. | 8.5 | Equipment ignition likelihood | Quantitative | Facility Points | No |  |  | 2026 | 2 | 101 |  | In Progress
1010000016 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | QA/QC of AI-06 - Distribution Intrusive |  | AI-19 | Program | QA/QC of AI-06 - Distribution Intrusive | Using a combination of process controls, software tools, company policy, and physical record checking to quickly identify inaccuracies for corrective action, evaluation, root cause analysis and system improvements. | 8.5 | Equipment ignition likelihood | Quantitative | Facility Points | No |  |  | 2026 | 2 | 170 |  | In Progress
1010000017 | PC | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Public Outreach and Education Awareness Program | Best Practice Sharing with Other Utilities |  | CO-04 | Program | Western Utilities Wildfire Communications Workshop | Meet with communications teams from western utilities to discuss wildfire communications | 13.2 | PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Pre-season workshop held March 3-4, 2026 in Denver, CO, at Xcel Energy. | In Progress
1010000018 | PC | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Public Outreach and Education Awareness Program | Conduct pre- and post-wildfire season customer surveys to evaluate comprehension and effectiveness of PacifiCorp's messaging |  | CO-05 | Program | Public Outreach and Education Awareness Program | Conduct pre- and post-wildfire season customer surveys to evaluate comprehension and effectiveness of PacifiCorp's messaging | 11.4 | PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Pre-season survey fielding concluded. Final report delivered in April. Pre-season survey complete | In Progress
1010000019 | PC | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan | External collaboration and coordination |  | EP-02 | Program | To enhance awareness of PSPS plan and understanding of roles and responsibilities | To enhance awareness of PSPS plan and understanding of roles and responsibilities | 11.2.1 | PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | March 10, 2026, PSPS workshop conducted as part of Wildfire Advisory Board meeting, April 15, 2026, PacifiCorp emergency management conducted a PSPS tabletop exercise in Modoc County. The exercise was a hybrid in-person/online event which focused on operational coordination and communication between PacifiCorp business units and with public safety partners, community organizations, and customers. June 2, 2026, PacifiCorp emergency management conducted a PSPS functional exercise for Del Norte County. Participants engaged remotely and the exercise focused on operational coordination and communication between PacifiCorp business units, public safety partners, community-based organizations, and customers during simulated PSPS conditions. The PacifiCorp 2026 PSPS Execution Playbook and exercise plan were distributed in advance, and participants utilized the company public safety partner portal during the exercise. | Completed
1010000020 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered Conductor installation |  | GH-01 | Program | Line Rebuild - Covered Conductor installation | Address the potential that incidental object contact will result in a fault event | 8.2.1 | Contact by object ignition | Quantitative | Circuit miles | No |  |  | 2026 | 2 | 72 |  | In Progress
1010000021 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Distribution Pole Replacement and reinforcements |  | GH-02 | Program | Distribution Pole Replacement and reinforcements | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | 8.2.3 | Contact by object ignition | Quantitative | Distribution Poles | No |  |  | 2026 | 2 | 1251 |  | In Progress
1010000022 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission Pole Replacement and reinforcements |  | GH-03 | Program | Transmission Pole Replacement and reinforcements | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | 8.2.4 | Contact by object ignition | Quantitative | Transmission Poles | No |  |  | 2026 | 2 | 127 |  | In Progress
1010000023 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment |  | GH-04 | Program | Installation of system automation equipment | Enhances fault detection capabilities, reduce fault isolation time, improve fault location and record availability, and speed up restoration efforts | 8.2.8 | PSPS exposure potential | Quantitative | Devices | No |  |  | 2026 | 2 | 3 |  | In Progress
1010000024 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Expulsion fuse replacement |  | GH-05 | Project | Expulsion fuse replacement | Install new and CAL FIRE-approved non-expulsion fuses including power fuses and current limiting fuses to replace existing expulsion fuse equipment | 8.2.12 | Equipment ignition likelihood | Quantitative | Fuse locations | No |  |  | 2026 | 2 | 949 |  | In Progress
1010000025 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electrical lines and/or equipment |  | GH-16 | Program | Undergrounding of electrical lines and/or equipment | Undergrounding of electrical lines and/or equipment for reducing wildfire risk | 8.2.2 | Contact by object ignition | Quantitative | Circuit miles | No |  |  | 2026 | 2 | 0.4 |  | In Progress
1010000026 | PC | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Equipment Settings to Reduce Wildfire Risk |  | GO-01 | Program | ESS circuit hardening | ESS modes of operation are intended to reduce fault clearing times and arc energy expended during a fault event, to detect and respond to all faults on the system and to maintain an acceptable level of customer service reliability | 8.7.1 | Equipment ignition likelihood | Quantitative | Circuits | No |  |  | 2026 | 2 | 3 |  | Completed
1010000027 | PC | 2026-08-03 | Situational Awareness and Forecasting | Weather Forecasting | Maintenance: Weather Station |  | MA-01 | Program | Weather station maintenance and calibration | Annual maintenance and calibration of the weather station fleet to ensure each weather station is operational and reporting correct and accurate data | 10.5.5 | PSPS likelihood | Quantitative | Weather Station Fleet % | No |  |  | 2026 | 2 | 98 |  | In Progress
1010000028 | PC | 2026-08-03 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Environmental Monitoring Systems |  | SA-01 | Program | Installation of weather stations | Expansion of the weather station network to provide reliable and accurate data to support better forecasting and to inform real time situational awareness and decision-making during adverse fire weather conditions | 10.2.1 | PSPS likelihood | Quantitative | Weather Stations | No |  |  | 2026 | 2 | 5 |  | Completed
1010000029 | PC | 2026-08-03 | Situational Awareness and Forecasting | Ignition Detection Systems | Wildfire Detection Cameras |  | SA-04 | Program | Total wildfire detection cameras installed | To enhance situational awareness and have the potential to speed up fire detection time and response efforts through monitoring | 10.4.1 | Wildfire spread | Quantitative | Cameras | No |  |  | 2026 | 2 | 8 |  | In Progress
1010000030 | PC | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Installation of cFCI |  | SA-07 | Program | Line Sensors: cFCI Distribution | Conductor mounted sensors with embedded communications modules that monitor conductor current, electric field intensity, and alarm on the detection of fault currents and loss of electric field associated system outages | 10.3.1 | Equipment ignition likelihood | Quantitative | Devices | No |  |  | 2026 | 2 | 5 |  | In Progress
1010000031 | PC | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Installation of SCAN |  | SA-08 | Program | Circuit Breaker/Recloser Monitoring: SCAN | Substation control advanced network (SCAN) automatically retrieves and archives enriched event data from protective relays; the data collected includes sequence of event (SOE) logs and COMTRADE event files associated with breaker operations, overcurrent faults and high-impedance faults | 10.3.1 | Equipment ignition likelihood | Quantitative | Locations | No |  |  | 2026 | 2 | 7 |  | In Progress
1010000032 | PC | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Distribution Protective Settings Review |  | SA-09 | Program | Distribution Protective Settings Review | Replace old electromechanical protection devices, like reclosers and relays, with new microprocessor-based devices | 10.3.1 | Equipment ignition likelihood | Quantitative | N/A | No |  |  | 2026 | 2 | 30 |  | In Progress
1010000033 | PC | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Installation of Advanced AMI Meters |  | SA-10 | Program | AMI: Advanced Bellwether Meters | Early detection and localization of voltage abnormalities on distribution networks | 10.3.3 | Equipment ignition likelihood | Quantitative | Meters | No |  | This activity has been cancelled | 2026 | 2 |  |  | Cancelled
1010000034 | PC | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Detailed Inspection – Distribution |  | VM-01 | Program | Detailed inspections for vegetation clearances around distribution electric lines | To minimize vegetation related reliability, safety, and wildfire ignition risks | 9.2.1 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | Yes |  |  | 2026 | 2 | 492 |  | In Progress
1010000035 | PC | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Patrol Inspection - Distribution |  | VM-03 | Program | Patrol (ground) inspections for vegetation clearances around distribution electric lines | To minimize vegetation related reliability, safety, and wildfire ignition risks by addressing vegetation conditions that require corrective action prior to the next scheduled work | 9.2.2 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | Yes |  |  | 2026 | 2 | 1087 |  | In Progress
1010000036 | PC | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Patrol Inspection - Transmission |  | VM-04 | Program | Patrol (ground) inspections for vegetation clearances around transmission electric lines | To minimize vegetation related reliability, safety, and wildfire ignition risks by addressing vegetation conditions that require corrective action while maintaining compliance with applicable Public Resource Codes, NERC requirements, and as described in the Vegetation SOP | 9.2.5 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | Yes |  |  | 2026 | 2 | 417 |  | In Progress
1010000037 | PC | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | QA/QC - Substation Defensible Space |  | VM-13 | Program | QA/QC - Substation Defensible Space | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications | 9.11 | Contact from vegetation ignition likelihood | Quantitative | Substations | No |  |  | 2026 | 2 | 55 |  | Completed
1010000038 | PC | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Routine (Detailed) Inspection - Local Transmission (TNT) |  | VM-16 | Program | Routine (Detailed) Inspection - Local Transmission (TNT) | To conduct routine inspections or detailed inspections of vegetation near local transmission lines to minimize safety, reliability, and wildfire ignition risks | 9.2.4 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | Yes |  |  | 2026 | 2 | 114 |  | In Progress
1010000039 | PC | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Routine (Detailed) Inspection - Main Grid Transmission (MGI) |  | VM-17 | Program | Routine (Detailed) Inspection - Main Grid Transmission (MGI) | To conduct routine inspections also known as detailed inspections of vegetation near main grid transmission lines to minimize safety, reliability, and wildfire ignition risks | 9.2.3 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | Yes |  |  | 2026 | 2 | 130 |  | Completed
1010000040 | PC | 2026-08-03 | Vegetation Management and Inspections | Pole Clearing | Pole Clearing PRC 4292 (DPL) |  | VM-18 | Program | Pole clearing beyond PRC 4292 (DPL) | Pole clearing is designed to reduce the risk of fire ignition if sparks are emitted from electrical equipment | 9.4 | Contact from vegetation ignition likelihood | Quantitative | Distribution Poles | Yes |  |  | 2026 | 2 | 17295 |  | In Progress
1010000041 | PC | 2026-08-03 | Vegetation Management and Inspections | Pole Clearing | Pole clearing (LRA) |  | VM-19 | Program | Pole clearing (LRA) | Pole clearing is designed to reduce the risk of fire ignition if sparks are emitted from electrical equipment | 9.4 | Contact from vegetation ignition likelihood | Quantitative | Distribution Poles | Yes |  |  | 2026 | 2 | 3915 |  | In Progress
1010000042 | PC | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | QA/QC - Routine Distribution (Detailed) |  | VM-20 | Program | QA/QC - Routine Distribution (Detailed) | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications | 9.11 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | No |  |  | 2026 | 2 | 435 |  | In Progress
1010000043 | PC | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | QA/QC - Routine Transmission (Detailed) |  | VM-21 | Program | QA/QC - Routine Transmission (Detailed) | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications | 9.11 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | No |  |  | 2026 | 2 | 83 |  | In Progress
1010000044 | PC | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | QA/QC - Off-cycle Distribution (Patrol) |  | VM-22 | Program | QA/QC - Off-cycle Distribution (Patrol) | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications | 9.11 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | No |  |  | 2026 | 2 | 744 |  | In Progress
1010000045 | PC | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | QA/QC - Non-routine Transmission (Patrol) |  | VM-23 | Program | QA/QC - Non-routine Transmission (Patrol) | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications | 9.11 | Contact from vegetation ignition likelihood | Quantitative | Circuit miles | No |  |  | 2026 | 2 | 226 |  | In Progress
1010000046 | PC | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | QA/QC - Pole Clearing (DPL and LRA) |  | VM-24 | Program | QA/QC - Pole clearing (DPL and LRA) | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications | 9.11 | Contact from vegetation ignition likelihood | Quantitative | Distribution Poles | No |  |  | 2026 | 2 | 887 |  | In Progress
1010000047 | PC | 2026-08-03 | Vegetation Management and Inspections | Defensible Space | Substation Defensible Space |  | VM-25 | Program | Substation Defensible Space | To perform substation defensible space management to reduce wildfire risk in substations in accordance with PRC 4291 | 9.6 | Contact from vegetation ignition likelihood | Quantitative | Substations | Yes |  |  | 2026 | 2 | 55 |  | Completed

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000001 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000002 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000003 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 55
1020000004 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000005 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000006 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000007 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000008 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 2
1020000009 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000010 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 2
1020000011 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 138
1020000012 | Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000013 | Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000014 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000015 | Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000016 | Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000017 | Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000018 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000019 | Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000020 | Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000021 | Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000022 | Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000023 | Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 5
1020000024 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000025 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000026 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000027 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 52
1020000028 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000029 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000030 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000031 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000032 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 2
1020000033 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000034 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000035 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 114
1020000036 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000037 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000038 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000039 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 3
1020000040 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000041 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000042 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000043 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000044 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000045 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000046 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000047 | Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 19
1020000048 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000049 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000050 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000051 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 6
1020000052 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000053 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000054 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000055 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000056 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000057 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000058 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 0
1020000059 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | PC | 2026 | 2 | 15
1020000060 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000061 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000062 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000063 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000064 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000065 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000066 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000067 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000068 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000069 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000070 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000071 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PC | 2026 | 2
1020000072 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000073 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000074 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000075 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000076 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000077 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000078 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000079 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000080 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000081 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000082 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000083 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | There were no conditions which met the criteria | PC | 2026 | 2
1020000084 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 7764
1020000085 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 33456
1020000086 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 17040
1020000087 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 17410
1020000088 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 17148
1020000089 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 20420
1020000090 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 6840
1020000091 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 12067
1020000092 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 1920
1020000093 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 32424
1020000094 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 6960
1020000095 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 64776
1020000096 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 17784
1020000097 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 104730
1020000098 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 17160
1020000099 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 117404
1020000100 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 17496
1020000101 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | PC | 2026 | 2 | 108480
1020000102 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 86376
1020000103 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 102986
1020000104 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 16608
1020000105 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 83110
1020000106 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 33552
1020000107 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | PC | 2026 | 2 | 108960
1020000108 | Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  | PacifiCorp does not issue vegetation management work at the task by task level with specific "work orders", but rather at the circuit level. That being said, PacifiCorp does identify vegetation management activities at the work location level within its mobile data management software. PacifiCorp is currently reviewing its data to identify a process to more accurately identify work locations that may be "open"/unresolved considering limitations and other variables within its mobile data management software. PacifiCorp does not assign completion date requirements at the work location level. | PC | 2026 | 2
1020000109 | Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  | PacifiCorp does not issue vegetation management work at the task by task level with specific "work orders", but rather at the circuit level. That being said, PacifiCorp does identify vegetation management activities at the work location level within its mobile data management software. PacifiCorp is currently reviewing its data to identify a process to more accurately identify work locations that may be "open"/unresolved considering limitations and other variables within its mobile data management software. PacifiCorp does not assign completion date requirements at the work location level. | PC | 2026 | 2
1020000110 | Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | PC | 2026 | 2 | 11034
1020000111 | Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | PC | 2026 | 2 | 332
1020000112 | Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  |  | PC | 2026 | 2 | 1.3
1020000113 | Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | PC | 2026 | 2 | 0
1020000114 | Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | PC | 2026 | 2 | 0
1020000115 | Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | PC | 2026 | 2 | 0
1020000116 | Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | PC | 2026 | 2 | 0
1020000117 | Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | PC | 2026 | 2 | 0
1020000118 | Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | PC | 2026 | 2 | 1.9
1020000119 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000120 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000121 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000122 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 1
1020000123 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000124 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000125 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000126 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000127 | Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000128 | Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000129 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 0
1020000130 | Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | PC | 2026 | 2 | 2
1020000131 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000132 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000133 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000134 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 10911
1020000135 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000136 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000137 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000138 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 960
1020000139 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 543
1020000140 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 543
1020000141 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000142 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 455
1020000143 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000144 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000145 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000146 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000147 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000148 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000149 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000150 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000151 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 15
1020000152 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 15
1020000153 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000154 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000155 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000156 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000157 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000158 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000159 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000160 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000161 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000162 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000163 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000164 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000165 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000166 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000167 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000168 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000169 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000170 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000171 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000172 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000173 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000174 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 89
1020000175 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000176 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000177 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000178 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 12
1020000179 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000180 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000181 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000182 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000183 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000184 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000185 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000186 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 98
1020000187 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000188 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000189 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000190 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000191 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000192 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000193 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000194 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000195 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000196 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000197 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000198 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 1
1020000199 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 131
1020000200 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 131
1020000201 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000202 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 135
1020000203 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000204 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000205 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000206 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000207 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000208 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000209 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000210 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000211 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 15
1020000212 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 15
1020000213 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000214 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000215 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000216 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000217 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000218 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000219 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000220 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000221 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000222 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000223 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000224 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000225 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000226 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000227 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000228 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000229 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000230 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000231 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000232 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000233 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000234 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000235 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000236 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000237 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000238 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 12
1020000239 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000240 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000241 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000242 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000243 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000244 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000245 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000246 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000247 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000248 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000249 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000250 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000251 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000252 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000253 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000254 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 10081
1020000255 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000256 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000257 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000258 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 2638
1020000259 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000260 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000261 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000262 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 263
1020000263 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000264 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000265 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000266 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000267 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000268 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000269 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000270 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000271 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000272 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000273 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000274 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000275 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000276 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000277 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000278 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000279 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000280 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000281 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000282 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000283 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000284 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000285 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000286 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000287 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000288 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000289 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000290 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000291 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000292 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000293 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000294 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 340
1020000295 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000296 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000297 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000298 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 6
1020000299 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000300 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000301 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000302 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000303 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000304 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000305 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000306 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 458
1020000307 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000308 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000309 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000310 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000311 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000312 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000313 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000314 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 5000
1020000315 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000316 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000317 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000318 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 982
1020000319 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 337
1020000320 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000321 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000322 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 126
1020000323 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000324 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000325 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000326 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000327 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000328 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000329 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000330 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000331 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 41
1020000332 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000333 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000334 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000335 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000336 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000337 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000338 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000339 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000340 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000341 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000342 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000343 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000344 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000345 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000346 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000347 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000348 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000349 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000350 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000351 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000352 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000353 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000354 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 74
1020000355 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000356 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000357 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000358 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 1
1020000359 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000360 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000361 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000362 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000363 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000364 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000365 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000366 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 460
1020000367 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000368 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000369 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000370 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 2
1020000371 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000372 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000373 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000374 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 3438
1020000375 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000376 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000377 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000378 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 130
1020000379 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 12
1020000380 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000381 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000382 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000383 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000384 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000385 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000386 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000387 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000388 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000389 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000390 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000391 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 172
1020000392 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000393 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000394 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000395 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000396 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000397 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000398 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000399 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000400 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000401 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000402 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000403 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000404 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000405 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000406 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000407 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000408 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000409 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000410 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000411 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000412 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000413 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000414 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000415 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000416 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000417 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000418 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000419 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000420 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000421 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000422 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000423 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000424 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000425 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000426 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000427 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000428 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000429 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000430 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000431 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000432 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000433 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000434 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 1716
1020000435 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000436 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000437 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000438 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 507
1020000439 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000440 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000441 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000442 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PC | 2026 | 2 | 69
1020000443 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000444 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000445 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000446 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000447 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000448 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000449 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000450 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000451 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000452 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000453 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000454 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PC | 2026 | 2 | 0
1020000455 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000456 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000457 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000458 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000459 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000460 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000461 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000462 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000463 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000464 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000465 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000466 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000467 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000468 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000469 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000470 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000471 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000472 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000473 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000474 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 150
1020000475 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000476 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000477 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000478 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 7
1020000479 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000480 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000481 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000482 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000483 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000484 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000485 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000486 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 79
1020000487 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000488 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000489 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000490 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PC | 2026 | 2 | 0
1020000491 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000492 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000493 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000494 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000495 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000496 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000497 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000498 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000499 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000500 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000501 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000502 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000503 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000504 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000505 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000506 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000507 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000508 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000509 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000510 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 2
1020000511 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000512 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000513 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000514 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000515 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000516 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000517 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000518 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000519 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000520 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000521 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000522 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000523 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000524 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000525 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000526 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000527 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000528 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000529 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000530 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000531 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000532 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000533 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000534 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000535 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000536 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000537 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000538 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000539 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000540 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000541 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000542 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000543 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000544 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000545 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000546 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000547 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000548 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000549 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000550 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000551 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000552 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000553 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000554 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000555 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000556 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000557 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000558 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000559 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000560 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000561 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000562 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000563 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000564 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000565 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000566 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000567 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000568 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000569 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000570 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 39
1020000571 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000572 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000573 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000574 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 1
1020000575 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000576 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000577 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000578 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000579 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000580 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000581 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000582 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 393
1020000583 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000584 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000585 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000586 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 9
1020000587 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000588 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000589 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000590 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000591 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000592 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000593 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000594 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 457
1020000595 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000596 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000597 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000598 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 6
1020000599 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000600 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000601 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000602 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000603 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000604 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000605 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000606 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000607 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000608 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000609 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000610 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000611 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000612 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000613 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000614 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000615 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000616 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000617 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000618 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000619 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000620 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000621 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000622 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000623 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000624 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000625 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000626 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000627 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000628 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000629 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000630 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000631 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000632 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000633 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000634 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000635 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000636 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000637 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000638 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000639 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000640 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000641 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000642 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000643 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000644 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000645 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000646 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000647 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000648 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000649 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000650 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000651 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000652 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000653 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000654 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000655 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000656 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000657 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000658 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000659 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000660 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000661 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000662 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000663 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000664 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000665 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000666 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000667 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000668 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000669 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000670 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000671 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000672 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000673 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000674 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000675 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000676 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000677 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000678 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 15
1020000679 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000680 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000681 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000682 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000683 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000684 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000685 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000686 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000687 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000688 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000689 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000690 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 19
1020000691 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000692 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000693 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000694 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 1
1020000695 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000696 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000697 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000698 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000699 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000700 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000701 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000702 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 73
1020000703 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000704 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000705 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 0
1020000706 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PC | 2026 | 2 | 2
1020000707 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000708 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000709 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000710 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000711 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000712 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000713 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000714 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000715 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000716 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000717 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000718 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 1191
1020000719 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000720 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000721 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000722 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 455
1020000723 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000724 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000725 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000726 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000727 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000728 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000729 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000730 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000731 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000732 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000733 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000734 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 369
1020000735 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000736 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000737 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000738 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 59
1020000739 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000740 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000741 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000742 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000743 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000744 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000745 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000746 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000747 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000748 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000749 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000750 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 157
1020000751 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000752 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000753 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000754 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 5648
1020000755 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000756 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000757 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000758 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000759 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000760 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000761 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000762 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000763 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000764 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000765 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000766 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 133
1020000767 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000768 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000769 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000770 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 167
1020000771 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000772 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000773 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000774 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000775 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000776 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000777 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000778 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000779 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000780 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000781 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000782 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 3
1020000783 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000784 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000785 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000786 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 0
1020000787 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000788 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000789 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000790 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000791 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000792 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000793 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000794 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PC | 2026 | 2
1020000795 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000796 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000797 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000798 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 40
1020000799 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PC | 2026 | 2
1020000800 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PC | 2026 | 2
1020000801 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PC | 2026 | 2
1020000802 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp provides number of trees identified during inspection for pruning or removal for 2026. (excluding brush and ROW clearing) |  | PC | 2026 | 2 | 30
1020000803 | Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | PacifiCorp does not have authority to order evacuations. This is a local jurisdiction Incident Command authority. Local jurisdictions use their own alert and warning system to execute evacuation orders. | PC | 2026 | 2

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | PSPS Customer Minutes Interrupted | The number of Customer minutes interrupted as a result of a PSPS event. | Monitoring this metric helps PacifiCorp understand the customer exposure to PSPS. | This metric helps the company understand the Customer exposure to PSPS as mitigations are implemented. This metric will be annualized. | N/A | Minutes |  |  | PC | 2026 | 2 | 0
1030000001 | PSPS Events | The number of PSPS events recorded. | Monitoring this metric helps PacifiCorp understand the customer exposure to PSPS. | This metric helps the company understand if there are changes in PSPS as mitigations designed to reduce the frequency of them are implemented. This metric will be annualized. | N/A | Events |  |  | PC | 2026 | 2 | 0
1030000002 | Enhanced Safety Settings (ESS) (PEDS) Customer Minutes Interrupted | The number of Customer minutes interrupted while Enhanced Safety Settings (ESS) (PEDS) was activated. | Monitoring this metric helps PacifiCorp understand the Customer exposure to Enhanced Safety Settings (ESS) (PEDS). | This metric helps the Company understand the Customer exposure to ESS as mitigations are implemented. This metric will be annualized. | N/A | Minutes |  |  | PC | 2026 | 2 | 321315.249
1030000003 | Risk Events | The number of risk events recorded. | Monitoring this metric helps PacifiCorp understand if hardening and asset inspection activities are impacting the likelihood of risk events. | Total number of risk events. | N/A | Events |  |  | PC | 2026 | 2 | 195
1030000004 | Ignition Events | The number of ignition events recorded. | Monitoring this metric helps PacifiCorp understand if hardening and asset inspection activities are impacting the likelihood of ignition events. | Total number of risk events and the data source is outage reporting system in which outage refers to fire in comment or outage cause . Assumption is that with mitigation activities described in the WMP, the number of ignition events will decrease. This metric will be annualized. | N/A | Events |  |  | PC | 2026 | 2 | 3
1030000005 | Equipment Inspection Findings | The number of conditions found that could cause an energy release risk. | Monitoring this metric helps PacifiCorp understand if hardening and asset inspection activities are impacting the likelihood of finding conditions that could cause an energy release risk. | With regular equipment inspections, over time PacifiCorp expects to see a decrease in findings of conditions that could cause an energy release risk. This metric will be annualized. | N/A | Conditions |  | This value will be reported in total at year's end | PC | 2026 | 2

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 587.8
1040000001 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 10.664
1040000002 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 1836.685
1040000003 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000004 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000005 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000006 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | PC | 2026 | 2 | 426.773
1040000007 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | PC | 2026 | 2 | 10.664
1040000008 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | PC | 2026 | 2 | 536.227
1040000009 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000010 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000011 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000012 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 1014.573
1040000013 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 21.328
1040000014 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 2372.912
1040000015 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000016 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000017 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | PC | 2026 | 2 | 0
1040000018 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PC | 2026 | 2 | 8041
1040000019 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PC | 2026 | 2 | 320.29
1040000020 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PC | 2026 | 2 | 21617.81
1040000021 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PC | 2026 | 2 | 4067.292
1040000022 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PC | 2026 | 2 | 395.437
1040000023 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PC | 2026 | 2 | 3576.269

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000001 | Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000002 | Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000003 | Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000004 | Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000005 | Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000006 | Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000007 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000008 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000009 | Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000010 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000011 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000012 | Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000013 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000014 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000015 | Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000016 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000017 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000018 | Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000019 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000020 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000021 | Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000022 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000023 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000024 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000025 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000026 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000027 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000028 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000029 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000030 | Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000031 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000032 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000033 | Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000034 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000035 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000036 | Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000037 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000038 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000039 | Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000040 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000041 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000042 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000043 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000044 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000045 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000046 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000047 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000048 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000049 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000050 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000051 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000052 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000053 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000054 | Vegetation contact | Wire down event | Grow-in | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000055 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000056 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000057 | Vegetation contact | Wire down event | Grow-in | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000058 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000059 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000060 | Vegetation contact | Wire down event | Blow-in | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000061 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000062 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000063 | Vegetation contact | Wire down event | Blow-in | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000064 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000065 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000066 | Vegetation contact | Wire down event | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000067 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000068 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000069 | Vegetation contact | Wire down event | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000070 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000071 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000072 | Vegetation contact | Wire down event | Root failure | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000073 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000074 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000075 | Vegetation contact | Wire down event | Root failure | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000076 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000077 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000078 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000079 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000080 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000081 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000082 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000083 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000084 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000085 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000086 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000087 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000088 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000089 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000090 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000091 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000092 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000093 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000094 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000095 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000096 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 4
1050000097 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000098 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000099 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000100 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000101 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000102 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000103 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000104 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000105 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000106 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000107 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000108 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000109 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000110 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000111 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000112 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000113 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000114 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000115 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000116 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000117 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000118 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000119 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000120 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000121 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000122 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000123 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000124 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000125 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000126 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000127 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000128 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000129 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000130 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000131 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000132 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000133 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000134 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000135 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000136 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000137 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000138 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000139 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000140 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000141 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000142 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000143 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000144 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000145 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000146 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000147 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000148 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000149 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000150 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000151 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000152 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000153 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000154 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000155 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000156 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000157 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000158 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000159 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000160 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000161 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000162 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000163 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000164 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000165 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000166 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000167 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000168 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000169 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000170 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000171 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000172 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000173 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000174 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000175 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000176 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000177 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000178 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000179 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000180 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000181 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000182 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000183 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000184 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000185 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000186 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000187 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000188 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000189 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000190 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000191 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000192 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000193 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000194 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000195 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000196 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000197 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000198 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000199 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000200 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000201 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000202 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000203 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000204 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000205 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000206 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000207 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000208 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000209 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000210 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 1
1050000211 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000212 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000213 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000214 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000215 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000216 | Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000217 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000218 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000219 | Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000220 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000221 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000222 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000223 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000224 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000225 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000226 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000227 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000228 | Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000229 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000230 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000231 | Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000232 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000233 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000234 | Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000235 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000236 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000237 | Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000238 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000239 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000240 | Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000241 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000242 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000243 | Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000244 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000245 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000246 | Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000247 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000248 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000249 | Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000250 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000251 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000252 | Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000253 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000254 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000255 | Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000256 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000257 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000258 | Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 10
1050000259 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 9
1050000260 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000261 | Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000262 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000263 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000264 | Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000265 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000266 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000267 | Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000268 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000269 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000270 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 4
1050000271 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000272 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000273 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000274 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000275 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000276 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000277 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000278 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000279 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000280 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000281 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000282 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 4
1050000283 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 6
1050000284 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000285 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000286 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000287 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000288 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 5
1050000289 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000290 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000291 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000292 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000293 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000294 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000295 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 1
1050000296 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000297 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000298 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000299 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000300 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 19
1050000301 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 3
1050000302 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000303 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000304 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000305 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000306 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000307 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000308 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000309 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000310 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000311 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000312 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000313 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000314 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000315 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000316 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000317 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000318 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000319 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000320 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000321 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000322 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000323 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000324 | Vegetation contact | Unplanned Outage | Root failure | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000325 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000326 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000327 | Vegetation contact | Unplanned Outage | Root failure | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000328 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000329 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000330 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000331 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000332 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000333 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000334 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000335 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000336 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000337 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000338 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000339 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000340 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000341 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000342 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000343 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000344 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000345 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000346 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000347 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000348 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000349 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000350 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000351 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000352 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000353 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000354 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000355 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000356 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000357 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000358 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000359 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000360 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000361 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000362 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000363 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000364 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000365 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000366 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 9
1050000367 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 5
1050000368 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000369 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000370 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000371 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000372 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000373 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000374 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000375 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000376 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000377 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000378 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000379 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000380 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000381 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000382 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000383 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000384 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000385 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000386 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000387 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000388 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000389 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000390 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000391 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000392 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000393 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000394 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000395 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000396 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 5
1050000397 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000398 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000399 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000400 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000401 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000402 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000403 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000404 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000405 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000406 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000407 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000408 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000409 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000410 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000411 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000412 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000413 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000414 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000415 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000416 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000417 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000418 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000419 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000420 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 2
1050000421 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 1
1050000422 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000423 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000424 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000425 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000426 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000427 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000428 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000429 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000430 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000431 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000432 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000433 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000434 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000435 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000436 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000437 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000438 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 37
1050000439 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 8
1050000440 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000441 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000442 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000443 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000444 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000445 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000446 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000447 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000448 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000449 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000450 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000451 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000452 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000453 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000454 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000455 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000456 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 2
1050000457 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 5
1050000458 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000459 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000460 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000461 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000462 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 3
1050000463 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000464 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000465 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000466 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000467 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000468 | Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 1
1050000469 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000470 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000471 | Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000472 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000473 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000474 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000475 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000476 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000477 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000478 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000479 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000480 | Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 7
1050000481 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000482 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000483 | Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000484 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000485 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000486 | Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000487 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000488 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000489 | Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000490 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000491 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000492 | Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000493 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000494 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000495 | Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000496 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000497 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000498 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000499 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000500 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000501 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000502 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000503 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000504 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 25
1050000505 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 12
1050000506 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000507 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000508 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000509 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000510 | Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 1
1050000511 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 6
1050000512 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0
1050000513 | Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  | PC | 2026 | 2 | 0
1050000514 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | PC | 2026 | 2 | 0
1050000515 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | PC | 2026 | 2 | 0

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000001 | Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000002 | Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000003 | Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000004 | Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000005 | Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000006 | Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000007 | Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000008 | Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000009 | Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000010 | Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000011 | Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000012 | Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000013 | Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000014 | Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000015 | Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000016 | Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000017 | Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000018 | Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000019 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000020 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000021 | Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000022 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000023 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000024 | Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000025 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000026 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000027 | Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000028 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000029 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000030 | Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000031 | Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000032 | Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000033 | Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000034 | Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000035 | Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000036 | Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000037 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000038 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000039 | Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000040 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000041 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000042 | Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000043 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000044 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000045 | Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000046 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000047 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000048 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000049 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000050 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000051 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000052 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000053 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000054 | Vegetation contact | Grow-in | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000055 | Vegetation contact | Grow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000056 | Vegetation contact | Grow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000057 | Vegetation contact | Grow-in | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000058 | Vegetation contact | Grow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000059 | Vegetation contact | Grow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000060 | Vegetation contact | Blow-in | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000061 | Vegetation contact | Blow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000062 | Vegetation contact | Blow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000063 | Vegetation contact | Blow-in | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000064 | Vegetation contact | Blow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000065 | Vegetation contact | Blow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000066 | Vegetation contact | Trunk failure | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000067 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000068 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000069 | Vegetation contact | Trunk failure | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000070 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000071 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000072 | Vegetation contact | Root failure | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000073 | Vegetation contact | Root failure | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000074 | Vegetation contact | Root failure | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000075 | Vegetation contact | Root failure | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000076 | Vegetation contact | Root failure | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000077 | Vegetation contact | Root failure | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000078 | Vegetation contact | Detached frond / limb / bark | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000079 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000080 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000081 | Vegetation contact | Detached frond / limb / bark | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000082 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000083 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000084 | Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000085 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000086 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000087 | Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000088 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000089 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000090 | Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000091 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000092 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000093 | Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000094 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000095 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000096 | Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000097 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000098 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000099 | Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000100 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000101 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000102 | Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000103 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000104 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000105 | Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000106 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000107 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000108 | Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000109 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000110 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000111 | Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000112 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000113 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000114 | Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000115 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000116 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000117 | Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000118 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000119 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000120 | Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000121 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000122 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000123 | Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000124 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000125 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000126 | Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000127 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 1
1060000128 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000129 | Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000130 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000131 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000132 | Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000133 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000134 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000135 | Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000136 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000137 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000138 | Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000139 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000140 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000141 | Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000142 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000143 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000144 | Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000145 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000146 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000147 | Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000148 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000149 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000150 | Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000151 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000152 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000153 | Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000154 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000155 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000156 | Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000157 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000158 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000159 | Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000160 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000161 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000162 | Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000163 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000164 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000165 | Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000166 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000167 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000168 | Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000169 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000170 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000171 | Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000172 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000173 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000174 | Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000175 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000176 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000177 | Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000178 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000179 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000180 | Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000181 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000182 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000183 | Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000184 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000185 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000186 | Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000187 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000188 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000189 | Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000190 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000191 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000192 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000193 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000194 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000195 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000196 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000197 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000198 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000199 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000200 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000201 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000202 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000203 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000204 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000205 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000206 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000207 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000208 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000209 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000210 | Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 1
1060000211 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000212 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000213 | Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000214 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000215 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000216 | Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000217 | Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000218 | Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000219 | Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000220 | Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000221 | Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000222 | Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000223 | Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000224 | Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000225 | Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000226 | Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000227 | Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000228 | Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000229 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000230 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000231 | Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000232 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000233 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000234 | Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000235 | Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000236 | Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000237 | Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000238 | Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000239 | Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000240 | Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 1
1060000241 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000242 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000243 | Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000244 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000245 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000246 | Other | Other (other) | Distribution | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000247 | Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000248 | Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000249 | Other | Other (other) | Transmission | Non-HFTD | # ignitions |  |  | PC | 2026 | 2 | 0
1060000250 | Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  |  | PC | 2026 | 2 | 0
1060000251 | Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  |  | PC | 2026 | 2 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 23.53
1070000001 | Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 23.46
1070000002 | Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 391.21
1070000003 | Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 319.63
1070000004 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 165.85
1070000005 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 778.86
1070000006 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 4.59
1070000007 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.03
1070000008 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 320.78
1070000009 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 90.39
1070000010 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 207.08
1070000011 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 144.51
1070000012 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000013 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000014 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 34.72
1070000015 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 5.64
1070000016 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000017 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000018 | Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 1.11
1070000019 | Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 1.76
1070000020 | Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 66.6
1070000021 | Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 95.52
1070000022 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 22.78
1070000023 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 191.98
1070000024 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.7
1070000025 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000026 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 81.35
1070000027 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 66.27
1070000028 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 57.62
1070000029 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 111.85
1070000030 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000031 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000032 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 15.42
1070000033 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 7.84
1070000034 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000035 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000036 | Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 18.6
1070000037 | Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 12.48
1070000038 | Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 79.74
1070000039 | Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 46.45
1070000040 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 23.88
1070000041 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 57.47
1070000042 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 1.67
1070000043 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.01
1070000044 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 228.62
1070000045 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 28.63
1070000046 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 64.25
1070000047 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 30.49
1070000048 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000049 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000050 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 51.66
1070000051 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 3.66
1070000052 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000053 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000054 | Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000055 | Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000056 | Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000057 | Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000058 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000059 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000060 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000061 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000062 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000063 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000064 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000065 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000066 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000067 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000068 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000069 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000070 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000071 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1070000072 | Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 81
1070000073 | Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 102
1070000074 | Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 219
1070000075 | Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 157
1070000076 | Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 108
1070000077 | Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 168
1070000078 | Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 5
1070000079 | Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 0
1070000080 | Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 284
1070000081 | Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 62
1070000082 | Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 104
1070000083 | Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 49
1070000084 | Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 0
1070000085 | Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 0
1070000086 | Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 35
1070000087 | Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 10
1070000088 | Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 0
1070000089 | Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | PC | 2026 | 2 | 0
1070000090 | Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 3003
1070000091 | Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 2636
1070000092 | Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 7851
1070000093 | Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 2648
1070000094 | Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 2435
1070000095 | Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 2416
1070000096 | Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 139
1070000097 | Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 0
1070000098 | Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 10767
1070000099 | Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 563
1070000100 | Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 3226
1070000101 | Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 664
1070000102 | Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 0
1070000103 | Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 0
1070000104 | Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 934
1070000105 | Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 68
1070000106 | Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | PC | 2026 | 2 | 0
1070000107 | Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | PC | 2026 | 2 | 0
1070000108 | Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 358
1070000109 | Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 558
1070000110 | Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 1373
1070000111 | Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 995
1070000112 | Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 571
1070000113 | Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 985
1070000114 | Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 28
1070000115 | Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 1
1070000116 | Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 2016
1070000117 | Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 319
1070000118 | Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 613
1070000119 | Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 255
1070000120 | Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 0
1070000121 | Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 0
1070000122 | Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 132
1070000123 | Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 62
1070000124 | Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 0
1070000125 | Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | PC | 2026 | 2 | 0
1070000126 | AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 291
1070000127 | AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 271
1070000128 | AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 707
1070000129 | AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 212
1070000130 | AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 178
1070000131 | AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 177
1070000132 | AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 10
1070000133 | AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 0
1070000134 | AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 840
1070000135 | AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 41
1070000136 | AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 246
1070000137 | AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 85
1070000138 | AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 0
1070000139 | AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 0
1070000140 | AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 22
1070000141 | AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 3
1070000142 | AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 0
1070000143 | AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PC | 2026 | 2 | 0
1070000144 | Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000145 | Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000146 | Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 6
1070000147 | Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000148 | Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000149 | Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000150 | Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000151 | Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000152 | Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000153 | Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 4
1070000154 | Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000155 | Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 1
1070000156 | Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000157 | Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000158 | Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 1
1070000159 | Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000160 | Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000161 | Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1070000162 | Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1070000163 | Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1070000164 | Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 11
1070000165 | Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 10
1070000166 | Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 6
1070000167 | Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 21
1070000168 | Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1070000169 | Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1070000170 | Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 18
1070000171 | Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 8
1070000172 | Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 14
1070000173 | Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 26
1070000174 | Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1070000175 | Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1070000176 | Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 3
1070000177 | Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 3
1070000178 | Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1070000179 | Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | -0.03
1080000001 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.01
1080000002 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.06
1080000003 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.03
1080000004 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.16
1080000005 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.09
1080000006 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000007 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000008 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | -0.19
1080000009 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | -0.01
1080000010 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.17
1080000011 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | -0.12
1080000012 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000013 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000014 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000015 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000016 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000017 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000018 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000019 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000020 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | -0.02
1080000021 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | -1.86
1080000022 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000023 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | -4
1080000024 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000025 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000026 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000027 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | -1.71
1080000028 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000029 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000030 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000031 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000032 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000033 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000034 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000035 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000036 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.05
1080000037 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.04
1080000038 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.06
1080000039 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.01
1080000040 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.06
1080000041 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.06
1080000042 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000043 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000044 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 1.77
1080000045 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.12
1080000046 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.12
1080000047 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.04
1080000048 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000049 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000050 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.09
1080000051 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000052 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000053 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000054 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000055 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000056 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000057 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000058 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000059 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000060 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000061 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000062 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000063 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000064 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000065 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000066 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000067 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000068 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000069 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000070 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000071 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1080000072 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000073 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000074 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000075 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000076 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000077 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000078 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000079 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000080 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000081 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000082 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000083 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000084 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000085 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000086 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000087 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000088 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000089 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1080000090 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000091 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000092 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 1
1080000093 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000094 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 1
1080000095 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 2
1080000096 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000097 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000098 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000099 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000100 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000101 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000102 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000103 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000104 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000105 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000106 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1080000107 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000001 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000002 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.69
1090000003 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 1.12
1090000004 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 10.82
1090000005 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0.79
1090000006 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000007 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000008 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 8.02
1090000009 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 1.36
1090000010 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 14.06
1090000011 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 5.98
1090000012 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000013 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000014 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000015 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000016 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000017 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000018 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000019 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000020 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000021 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000022 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000023 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000024 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000025 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000026 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000027 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000028 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000029 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000030 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000031 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000032 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000033 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000034 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000035 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PC | 2026 | 2 | 0
1090000036 | Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000037 | Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000038 | Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000039 | Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000040 | Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000041 | Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 1
1090000042 | Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000043 | Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000044 | Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000045 | Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000046 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 1
1090000047 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000048 | Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000049 | Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000050 | Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000051 | Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000052 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000053 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PC | 2026 | 2 | 0
1090000054 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000055 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000056 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 1
1090000057 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000058 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 1
1090000059 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 3
1090000060 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000061 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000062 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000063 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000064 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000065 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000066 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000067 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000068 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000069 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000070 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0
1090000071 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PC | 2026 | 2 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | PC | 2026 | 2 | 0
1100000001 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | PC | 2026 | 2 | 0
1100000002 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | PC | 2026 | 2 | 0
1100000003 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | PC | 2026 | 2 | 0
1100000004 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PC | 2026 | 2 | 0
1100000005 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PC | 2026 | 2 | 0
1100000006 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PC | 2026 | 2 | 0
1100000007 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PC | 2026 | 2 | 0
1100000008 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | PC | 2026 | 2 | 0
1100000009 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | PC | 2026 | 2 | 0
1100000010 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | PC | 2026 | 2 | 0
1100000011 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | PC | 2026 | 2 | 0
1100000012 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | PC | 2026 | 2 | 4
1100000013 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | PC | 2026 | 2 | 0
1100000014 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | PC | 2026 | 2 | 0
1100000015 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | PC | 2026 | 2 | 43
1100000016 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | PC | 2026 | 2 | 7057
1100000017 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | PC | 2026 | 2 | 0
1100000018 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | PC | 2026 | 2 | 0
1100000019 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | PC | 2026 | 2 | 41315
1100000020 | Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | PC | 2026 | 2 | 7.5
1100000021 | Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | PC | 2026 | 2 | 498.5
1100000022 | Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | PC | 2026 | 2 | 52.9
1100000023 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | PC | 2026 | 2 | 54.05
1100000024 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | PC | 2026 | 2 | 54.05
1100000025 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PC | 2026 | 2 | 0.66
1100000026 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PC | 2026 | 2 | 0.66
1100000027 | Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | PC | 2026 | 2 | 0
1100000028 | Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PC | 2026 | 2 | 0
1100000029 | Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PC | 2026 | 2 | 0
1100000030 | Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PC | 2026 | 2 | 0
1100000031 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PC | 2026 | 2 | 0
1100000032 | Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PC | 2026 | 2 | 0
1100000033 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PC | 2026 | 2 | 0
1100000034 | Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | PC | 2026 | 2 | 0
1100000035 | Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | PC | 2026 | 2 | 0
1100000036 | Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | PC | 2026 | 2 | 0
1100000037 | Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | PC | 2026 | 2 | 0
1100000038 | Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | PC | 2026 | 2 | 0
1100000039 | Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PC | 2026 | 2 | 0
1100000040 | Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PC | 2026 | 2 | 0
1100000041 | Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | PC | 2026 | 2 | 0
1100000042 | Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | PC | 2026 | 2 | 0
1100000043 | Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | PC | 2026 | 2 | 0

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1120000000 | 101096130-64470-DETAIL-02_17_2026-GO95HV-1^06239002.0093202 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000001 | 101195970-16970-DETAIL-06_23_2026-SVCDEFLC-1^07217001.0115502 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000002 | 100017283-16512-DETAIL-06_25_2024-CUSTWIRE-1^06244005.0239100 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000003 | 100064268-60573-DETAIL-09_11_2025-GO95MLD-1^07216001.0080503 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000004 | 100069014-37239-DETAIL-06_10_2026-GUYHINS-1^668086/00 8/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000005 | 100069014-37239-DETAIL-06_10_2026-GUYHINS-2^668086/00 8/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000006 | 100069014-37239-DETAIL-06_10_2026-GUYHINS-3^668086/00 8/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000007 | 100069014-37239-DETAIL-06_10_2026-GUYHINS-4^668086/00 8/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000008 | 101461629-13091-DTLTRT-07_10_2025-GUYNOINS-1^668087/00 3/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000009 | 101461629-13091-DTLTRT-07_10_2025-GUYNOINS-2^668087/00 3/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000010 | 101461629-60540-DTLTRT-07_10_2025-GUYNOINS-1^668087/00 3/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000011 | 101461629-60540-DTLTRT-07_10_2025-GUYNOINS-2^668087/00 3/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000012 | 101461629-61091-DTLTRT-07_10_2025-GUYNOINS-1^668087/00 3/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000013 | 103455426-30399-DTLSB-07_09_2025-ABNDEQPM-1^06244006.0275500 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000014 | 103550512-78909-ADMIN-10_23_2025-GO95HV-1^06246011.0359200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000015 | 103718211-70231-DETAIL-05_30_2023-CUSTWIRE-1^06243009.0028900 | OTHER | Non-HFTD | Distribution | 2023-05-30 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000016 | 103814673-49489-DETAIL-09_04_2025-GO95HV-1^06247006.0071602 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000017 | 103858313-62354-DETAIL-03_31_2025-GUYHINS-1^06241005.0115702 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000018 | 104581013-50509-DETAIL-09_10_2025-GO95HV-1^06246007.0131250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000019 | 10463013-91069-DETAIL-05_15_2024-GO95HV-1^06142012.0124701 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000020 | 102336670-99520-DETAIL-01_21_2026-COVCOTHR-2^06240004.0343904 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000021 | 102336670-99520-DETAIL-01_21_2026-COVCOTHR-3^06240004.0343904 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000022 | 102455030-77740-DETAIL-06_05_2025-GO95HV-1^668075/00 13/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000023 | 102874151-68599-AUDIT-05_19_2025-RISEBKSP-1^06243006.0272040 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000024 | 102877192-21880-DETAIL-02_12_2025-GO95HV-1^06240004.0167209 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000025 | 102877192-21880-DETAIL-02_12_2025-SVCROOF-1^06240004.0167209 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000026 | 103307430-61879-DTLSB-06_25_2025-GO95HV-1^06244007.0100400 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000027 | 105760485-47149-DETAIL-07_30_2025-GO95HV-1^06247005.0026000 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000028 | 107878849-1352-DTLSB-07_21_2025-GO95HV-1^06244006.0306441 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000029 | 108041225-47933-DETAIL-09_16_2025-GO95HV-1^06247004.0083540 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000030 | 108137230-15740-DTLSB-06_03_2026-SVCDEFLC-1^07216001.0027340 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000031 | 108674915-2099-DETAIL-01_28_2026-GO95BLTC-1^06242009.0050200 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000032 | 10877769-84079-DTLSB-07_01_2025-GO95HV-1^06244007.0133303 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000033 | 109142878-88250-DTLSB-06_03_2026-GO95HV-1^07216001.0115702 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000034 | 10923394-34769-DETAIL-04_23_2026-GO95HV-1^06142012.0146705 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000035 | 109284521-90823-DETAIL-06_17_2025-GO95HV-1^06248004.0349342 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000036 | 110837209-69299-DETAIL-09_09_2025-GO95HV-1^06246007.0228802 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000037 | 111038803-46450-DTLSB-05_29_2026-GO95HV-1^07216001.0023702 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000038 | 105321173-93109-DETAIL-08_21_2025-GO95HV-1^06247006.0257801 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000039 | 105400513-62513-DTLSB-06_08_2026-RISEGRD-2^07216001.0228203 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000040 | 105488238-66274-DETAIL-10_21_2024-RISEBKSP-1^07216001.0209341 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000041 | 105720300-83300-DETAIL-05_28_2025-ABNDEQPM-1^06142012.0037200 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000042 | 105912568-26841-DETAIL-03_06_2025-GO95HV-1^06241005.0161902 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000043 | 111701505-86363-DETAIL-07_07_2026-SVCROAD-1^07217001.0218500 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000044 | 111732320-42170-DETAIL-02_25_2026-GO95HV-1^06238003.0016700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000045 | 112104471-80929-DETAIL-05_19_2025-GO95HV-1^06142012.0119515 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000046 | 112104471-80929-DETAIL-05_19_2025-GRDRODHI-1^06142012.0119515 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000047 | 112206214-41739-DTLSB-10_03_2022-CUSTWIRE-1^06243005.0120900 | OTHER | HFTD Tier 2 | Distribution | 2022-10-03 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000048 | 112264106-78250-DETAIL-07_06_2026-GO95HV-1^07218001.0345900 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000049 | 112292551-35180-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0166301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000050 | 11477435-36899-DETAIL-08_28_2025-GO95HV-1^06247006.0195901 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000051 | 115544924-89932-DETAIL-10_15_2025-GUYHINS-1^06246012.0131700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000052 | 115839936-93136-DTLSB-05_05_2026-GO95HV-1^06241009.0140900 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000053 | 115951801-23209-ADMIN-10_07_2025-COVCOTHR-1^06245010.0161300 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000054 | 116029174-51619-DTLSB-04_23_2026-GO95HV-1^06241009.0223100 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000055 | 116184894-96409-DETAIL-08_27_2025-GO95HV-1^06247006.0171500 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000056 | 116594183-88679-ADMIN-10_21_2025-GO95HV-1^06247001.0265902 | OTHER | Non-HFTD | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000057 | 116633315-40589-DETAIL-05_29_2025-GO95HV-1^06244006.0103902 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000058 | 107674680-15340-DETAIL-03_07_2022-ENCHRW-1^06146006.0076905 | OTHER | Non-HFTD | Distribution | 2022-03-07 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000059 | 118704315-92129-DETAIL-05_13_2025-GRDRODHI-1^06142012.0013500 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000060 | 11912693-5249-DTLSB-07_17_2025-GO95HV-1^06244006.0255901 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000061 | 119327838-40160-DTLSB-05_16_2024-GO95HV-1^06244002.0204500 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000062 | 119523732-44339-DETAIL-05_08_2025-GO95HV-1^06243006.0218003 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000063 | 119757361-19809-DETAIL-09_03_2025-GO95HV-1^06247006.0210502 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000064 | 119757361-19809-DETAIL-09_03_2025-SVCDEFLC-1^06247006.0210502 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000065 | 123221305-13305-DETAIL-06_02_2025-GO95HV-1^06148014.0243901 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000066 | 123863133-99709-DETAIL-08_27_2025-GO95HV-1^06247006.0077600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000067 | 123887734-82353-DETAIL-09_22_2025-GO95HV-1^07218001.0214900 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000068 | 123937278-39660-DETAIL-08_21_2025-GO95HV-1^06246001.0200001 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000069 | 124912453-63009-DETAIL-08_12_2025-GO95HV-1^06247006.0252602 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000070 | 124964811-56000-DTLSB-06_08_2026-GUYHINS-1^07216001.0231101 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000071 | 124977959-61270-DETAIL-08_11_2025-GO95HV-1^06246002.0277800 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000072 | 125606219-63369-DTLTRT-05_22_2025-GRDRODHI-1^668075/00 11/003 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000073 | 127508212-69862-DTLTRT-04_28_2026-GO95HV-1^668004/00 7/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000074 | 12757293-97359-DTLTRT-04_20_2026-GO95HV-1^668004/02 4/002 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000075 | 127941708-72159-DETAIL-09_02_2025-GO95HV-1^07216001.0161905 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000076 | 127986176-1769-DETAIL-08_19_2025-GO95HV-1^06247006.0366400 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000077 | 128610552-48489-DETAIL-07_31_2025-GO95HV-1^06247005.0246200 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000078 | 128941185-81770-DETAIL-09_02_2025-GUYHINS-1^06246001.0175309 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000079 | 129088650-37301-DETAIL-01_14_2026-BIRDDMG-1^06239004.0135102 | POLE | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000080 | 129088650-37301-DETAIL-01_14_2026-SVCTREE-1^06239004.0135102 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000081 | 131148121-36369-DTLTRT-06_02_2021-GO95HV-1^668041/00 12/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000082 | 131496130-89470-DETAIL-02_18_2025-GO95TCH-1^06240004.0220506 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000083 | 131676811-97070-DTLTRT-05_18_2026-SVCENTCO-1^668086/00 7A/009 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000084 | 131813450-72379-DETAIL-06_19_2024-CUSTWIRE-1^06246006.0137700 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000085 | 132282943-95889-ADMIN-11_07_2025-GO95HV-1^06246001.0321901 | OTHER | Non-HFTD | Distribution | 2025-11-07 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000086 | 133371193-71759-DTLTRT-04_21_2026-GO95HV-1^668004/02 7/007 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000087 | 133847981-28150-DETAIL-03_11_2025-GRDRODHI-1^06238004.0273801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000088 | 135930326-72639-DETAIL-02_27_2024-GO95HV-1^07113002.0182400 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000089 | 136005483-3029-DTLSB-08_25_2023-CUSTWIRE-1^06243008.0241902 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000090 | 136105634-20209-DETAIL-08_20_2025-POLETOP-1^06247006.0255004 | POLE | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000091 | 136460235-28580-DTLSB-02_16_2023-CUSTWIRE-1^06248001.0210101 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000092 | 137199745-1329-DETAIL-05_19_2025-GO95MLD-1^06142012.0016400 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000093 | 137334781-16521-DETAIL-02_19_2025-BIRDDMG-1^06241005.0229901 | POLE | HFTD Tier 3 | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000094 | 138744528-39839-DTLSB-06_30_2025-GO95HV-1^06244006.0220501 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000095 | 138765859-87880-DETAIL-08_19_2025-GO95HV-1^06246002.0367404 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000096 | 13881446-12446-DETAIL-07_06_2026-CONDCOIL-1^07218001.0342807 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000097 | 139011479-26249-DTLSB-07_31_2025-GO95HV-1^07218001.0261400 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000098 | 139461121-96180-DTLTRT-05_18_2026-GO95HV-1^668086/00 7/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000099 | 139461614-10960-DETAIL-01_30_2025-GRDRODHI-1^06239004.0131040 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000100 | 140035057-84949-DTLSB-08_18_2025-GO95MLD-1^07218001.0355401 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000101 | 14065267-7789-DTLTRT-06_23_2025-GO95HV-1^668087/00 6/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000102 | 111174826-27659-ADMIN-12_29_2025-BIRDDMG-1^06245007.0272601 | POLE | Non-HFTD | Distribution | 2025-12-29 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000103 | 111347670-77080-DETAIL-02_27_2025-GUYHINS-1^06240004.0232502 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000104 | 111347670-77080-DETAIL-02_27_2025-GUYHINS-2^06240004.0232502 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000105 | 111347893-31080-DETAIL-02_24_2026-SVCDEFLC-1^06239002.0180700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000106 | 111404158-55789-AUDIT-05_19_2025-GO95BLTC-1^06243006.0303101 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000107 | 111404158-55789-AUDIT-06_03_2025-GO95HV-1^06243006.0303101 | OTHER | Non-HFTD | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000108 | 111646173-12819-DTLSB-05_11_2026-GO95HV-1^06242009.0278400 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000109 | 111843785-6700-DETAIL-02_11_2026-BIRDDMG-1^06239003.0016707 | POLE | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000110 | 11485233-66233-DETAIL-06_09_2025-GO95MLD-1^668075/00 19/028 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000111 | 114931231-82299-DTLSB-03_25_2026-BIRDDMG-1^06242008.0179301 | POLE | Non-HFTD | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000112 | 114974303-39779-DETAIL-07_30_2025-GO95HV-1^06247006.0202500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000113 | 115034206-20429-DETAIL-05_13_2025-GO95HV-1^06142012.0012601 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000114 | 11520478-17019-DTLSB-03_19_2026-RISEBKSP-1^06242009.0068601 | OTHER | HFTD Tier 2 | Distribution | 2026-03-19 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000115 | 115476838-2573-DETAIL-09_16_2025-GO95HV-1^07216001.0085200 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000116 | 115544924-89932-DETAIL-10_15_2025-GO95BLTC-1^06246012.0131700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000117 | 115546358-84029-DETAIL-04_28_2026-CLRTOPOL-1^06142012.0143702 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000118 | 118098534-9534-DETAIL-08_12_2025-GO95HV-1^06246002.0254202 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000119 | 118144135-14302-DETAIL-08_30_2018-CUSTWIRE-1^06243009.0261001 | OTHER | Non-HFTD | Distribution | 2018-08-30 | 2021-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000120 | 118454671-22139-DTLTRT-07_08_2025-GO95HV-1^668087/00 11/025 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000121 | 118521354-5783-DETAIL-09_17_2025-GO95HV-1^06246006.0079150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000122 | 118779698-66860-DETAIL-04_21_2026-GUYHINS-1^06142012.0148803 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000123 | 119453835-73699-DETAIL-07_28_2025-GO95HV-1^06247005.0313303 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000124 | 119463052-10083-AUDIT-10_07_2025-SVCENTBK-1^07216001.0175005 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000125 | 121805343-60750-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0244950 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000126 | 121917255-38149-DETAIL-07_22_2025-GO95HV-1^06247005.0090401 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000127 | 122861066-49789-DETAIL-07_31_2025-GO95HV-1^06247005.0261101 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000128 | 123053798-95060-DTLSB-05_07_2026-GO95HV-1^06142013.0346500 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000129 | 123253058-39160-DETAIL-09_09_2025-GO95HV-1^06146001.0047000 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000130 | 123301443-79651-DETAIL-03_03_2025-GUYHINS-1^06241004.0180100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000131 | 123301443-79651-DETAIL-03_03_2025-GUYHINS-2^06241004.0180100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000132 | 123348098-75499-DETAIL-09_04_2025-GO95HV-1^06146001.0050600 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000133 | 125606219-63369-DTLTRT-05_22_2025-SVCENTCO-1^668075/00 11/003 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000134 | 125933519-83529-DETAIL-06_04_2025-GO95HV-1^06142012.0106500 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000135 | 12671143-46039-DETAIL-06_10_2026-GO95TCH-1^668086/00 19/011 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000136 | 127276801-85622-DTLTRT-04_23_2026-GO95HV-1^668004/00 2/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000137 | 127481701-79001-DETAIL-04_16_2025-GO95BLTC-1^06242005.0331103 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000138 | 127508212-27070-DTLTRT-04_28_2026-GO95HV-1^668004/00 7/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000139 | 128169341-15680-DETAIL-02_16_2026-GO95HV-1^06239001.0035900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000140 | 128215468-95349-DETAIL-06_03_2024-CUSTWIRE-1^06246006.0361000 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000141 | 130444096-10589-DETAIL-08_12_2025-GO95HV-1^06247006.0265002 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000142 | 130444096-10589-DETAIL-08_12_2025-GRDRODHI-1^06247006.0265002 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000143 | 130480111-94759-DTLSB-07_29_2025-CUSTWIRE-1^07218001.0264102 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000144 | 130745758-36740-DETAIL-02_09_2026-GO95HV-1^06239003.0019004 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000145 | 130763831-88389-DETAIL-07_30_2025-GO95HV-1^06247006.0205004 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000146 | 130874195-11770-DETAIL-06_26_2025-GUYHINS-1^668087/00 15/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000147 | 130874195-11770-DETAIL-06_26_2025-GUYHINS-3^668087/00 15/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000148 | 131453084-71690-DETAIL-02_12_2026-GO95HV-1^06239003.0363502 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000149 | 13306374-2189-DETAIL-08_20_2025-GO95HV-1^06247006.0256703 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000150 | 13306374-2189-DETAIL-08_20_2025-POLETOP-1^06247006.0256703 | POLE | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000151 | 133079294-9059-DETAIL-08_19_2025-SVCENTCO-1^06247006.0367304 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000152 | 133421611-55373-DETAIL-09_18_2025-GO95HV-1^06246006.0014600 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000153 | 133514063-9012-DETAIL-04_02_2025-GUYHINS-1^06241005.0117404 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000154 | 133643466-36349-DTLSB-07_14_2025-GO95HV-1^06244006.0272402 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000155 | 134340768-35470-DETAIL-06_02_2026-GO95TCH-1^07216001.0116908 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000156 | 135787739-83919-DRONE_HY-07_15_2026-INSULDMG-2^668036/00 5/053 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000157 | 135864836-26799-DETAIL-05_28_2025-GO95HV-1^06244006.0040101 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000158 | 135914882-20519-DTLSB-05_19_2026-GO95HV-1^06240008.0131801 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000159 | 136229869-1790-DETAIL-01_28_2025-GO95HV-1^06239004.0245100 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000160 | 136538972-94031-DETAIL-03_03_2025-GUYHINS-1^06241004.0181102 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-03 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000161 | 136538972-94031-DETAIL-03_03_2025-GUYHINS-2^06241004.0181102 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-03 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000162 | 136711911-40839-DTLTRT-06_26_2025-GO95HV-1^668087/00 11/008 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000163 | 136905062-61750-DETAIL-02_11_2026-GO95HV-1^06239003.0016103 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000164 | 139268146-72152-DETAIL-04_24_2025-GO95HV-1^06242006.0177701 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000165 | 13942671-40089-DETAIL-09_10_2025-GO95HV-1^06147001.0082402 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000166 | 139461614-10960-DETAIL-01_13_2026-GO95MLD-1^06239004.0131040 | OTHER | HFTD Tier 3 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000167 | 13995679-79649-DTLSB-04_23_2024-GO95MLD-1^06245007.0224406 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000168 | 141091498-3980-DETAIL-09_03_2025-GO95BLTC-1^06146001.0079901 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000169 | 141091498-3980-DETAIL-09_03_2025-GO95HV-1^06146001.0079901 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000170 | 141199973-7929-DETAIL-04_22_2026-GO95HV-1^06142012.0146601 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000171 | 141199973-7929-DETAIL-04_22_2026-SVCDEFLC-1^06142012.0146601 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000172 | 143131870-63559-DETAIL-08_06_2025-GO95HV-1^06247005.0208001 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000173 | 14325883-91199-DETAIL-08_20_2025-GO95HV-1^06247006.0255702 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000174 | 14325883-91199-DETAIL-08_20_2025-SVCENTCO-1^06247006.0255702 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000175 | 14343979-95470-DETAIL-03_12_2026-GO95MLD-1^06240004.0211001 | OTHER | HFTD Tier 2 | Distribution | 2026-03-12 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000176 | 143533349-89080-DTLTRT-07_01_2025-GO95HV-1^668087/00 4/015 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000177 | 143690589-51443-DETAIL-06_23_2026-GO95HV-1^07217001.0114001 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000178 | 143778886-19280-ADMIN-07_25_2025-POLEDERP-1^668038/00 5/053 | POLE | HFTD Tier 2 | Transmission | 2025-07-25 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000179 | 143778886-19280-DTLTRT-05_07_2026-GO95HV-1^668038/00 5/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000180 | 142555954-74910-DETAIL-03_13_2025-GO95HV-1^06238004.0154000 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000181 | 142597312-96453-DETAIL-06_30_2026-GUYHINS-1^07217001.0221601 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000182 | 142628192-54139-DETAIL-05_20_2025-GO95HV-1^06243006.0079701 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000183 | 142720176-88379-DETAIL-09_02_2025-GO95HV-1^06246001.0176401 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000184 | 142955515-53589-DTLSB-07_02_2025-GO95HV-1^06244006.0226102 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000185 | 142967352-29179-DTLSB-07_09_2026-GO95HV-1^06240008.0147700 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000186 | 142995104-74799-DETAIL-03_06_2024-GO95HV-1^06147005.0177800 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000187 | 143023006-88880-DETAIL-09_02_2025-GO95MLD-1^06246001.0176402 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000188 | 145214479-82079-DETAIL-06_04_2025-GO95MLD-1^668075/00 7/025 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000189 | 145287633-9-DETAIL-08_14_2025-GO95HV-1^06247006.0258202 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000190 | 145302855-71299-DTLSB-05_05_2026-SVCDEFLC-1^06241009.0141701 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000191 | 145375473-81829-DTLSB-01_21_2026-GO95HV-1^06242009.0296105 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000192 | 145816906-6269-DTLSB-07_02_2025-GO95HV-1^06244006.0226302 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000193 | 145962493-3659-DTLTRT-04_21_2026-GO95HV-1^668004/02 15/005 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000194 | 145970734-81380-DTLSB-05_08_2024-GO95MLD-1^06245001.0336300 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000195 | 146324798-15523-DETAIL-09_08_2025-GO95BLTC-1^07218001.0177804 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000196 | 149244089-59090-DETAIL-01_16_2025-SVCENTCO-1^06239004.0257209 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000197 | 149336289-79299-DETAIL-08_25_2025-GO95HV-1^06247006.0281800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000198 | 149358921-5989-DETAIL-08_04_2025-GO95HV-1^06247006.0208801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000199 | 149358921-5989-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0208801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000200 | 149371755-54469-DTLSB-07_10_2025-GO95HV-1^06244007.0119001 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000201 | 149525428-34229-DETAIL-04_22_2026-GUYHINS-1^06142012.0148606 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000202 | 149550143-96021-DETAIL-02_18_2025-GO95TCH-1^06239004.0363700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000203 | 149550143-96021-DETAIL-02_18_2025-SVCENTCO-1^06239004.0363700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000204 | 153086806-17490-DETAIL-05_15_2025-GO95HV-1^06142012.0115201 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000205 | 153230435-97099-DETAIL-08_25_2025-GO95HV-1^06247006.0263903 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000206 | 153266173-94980-DETAIL-03_02_2026-GO95HV-1^06239002.0180301 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000207 | 153792948-43970-DETAIL-02_03_2025-GO95HV-1^06240004.0167901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000208 | 153916893-10489-ADMIN-08_15_2025-POLEREPL-1^06247005.0298903 | POLE | Non-HFTD | Distribution | 2025-08-15 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000209 | 153945209-71192-DTLTRT-07_02_2025-GUYNOINS-2^668087/00 6/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000210 | 153945209-79890-DTLTRT-07_02_2025-GUYNOINS-1^668087/00 6/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000211 | 155816401-26232-DTLTRT-05_05_2026-GO95HV-1^668004/00 4/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000212 | 155816401-57890-DTLTRT-05_05_2026-GO95HV-1^668004/00 4/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000213 | 156007071-82989-ADMIN-10_27_2025-GO95HV-1^06246001.0115900 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000214 | 156365975-43991-DETAIL-05_12_2026-GO95HV-1^668038/00 2/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000215 | 156365975-4991-DETAIL-05_12_2026-GO95HV-1^668038/00 2/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000216 | 156776386-56989-DETAIL-08_07_2025-GO95HV-1^06246002.0234400 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000217 | 15687832-41980-DETAIL-03_12_2026-SVCDEFLC-1^06240004.0320901 | OTHER | HFTD Tier 3 | Distribution | 2026-03-12 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000218 | 156959774-48783-DETAIL-09_17_2025-GO95HV-1^06246006.0077050 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000219 | 147438081-22190-DTLTRT-04_23_2026-GO95HV-1^668004/00 3/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000220 | 159437443-25643-DETAIL-10_12_2022-GUYHINS-2^668005/08 8X7/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000221 | 159609573-78709-DETAIL-09_04_2025-GO95BLTC-1^06247006.0075000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000222 | 159609573-78709-DETAIL-09_04_2025-GO95HV-1^06247006.0075000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000223 | 15979660-74369-DTLTRT-06_15_2021-GO95HV-1^668041/00 16/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000224 | 159887361-26543-DTLSB-06_02_2026-GO95CLSV-1^07216001.0115705 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120000225 | 159887361-26543-DTLSB-06_02_2026-GO95MLD-1^07216001.0115705 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000226 | 162289301-33900-DTLTRT-05_18_2026-GO95HV-1^668086/00 4/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000227 | 162350361-35900-DTLTRT-06_26_2025-GO95MLD-1^668087/00 15/008 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000228 | 162568131-69589-DTLSB-06_25_2025-GO95HV-1^06244007.0104901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000229 | 162994254-74153-DETAIL-08_06_2025-GO95HV-1^06247005.0300800 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000230 | 163456864-84669-DETAIL-08_21_2025-GO95BLTC-1^06247006.0259902 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000231 | 163456864-84669-DETAIL-08_21_2025-GO95HV-1^06247006.0259902 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000232 | 163533033-5559-DETAIL-06_17_2025-GO95HV-1^06248004.0331800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000233 | 164553760-18859-DETAIL-07_24_2025-GO95HV-1^06247005.0133400 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000234 | 167185713-17529-DETAIL-05_12_2025-GO95HV-1^06142012.0013804 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000235 | 167203475-30410-DETAIL-05_08_2024-GO95MLD-1^06142012.0120201 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000236 | 167341738-39618-DETAIL-07_07_2026-SVCNEUT-1^07217001.0219400 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000237 | 167427025-93063-DETAIL-07_07_2026-GO95HV-1^07217001.0095000 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000238 | 167440433-97799-DTLSB-08_21_2024-CUSTWIRE-1^06245006.0332040 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000239 | 167651161-62809-DETAIL-10_02_2025-GO95MLD-1^06246008.0067700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000240 | 147499048-61129-DETAIL-04_22_2026-SVCDEFLC-1^06142012.0149603 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000241 | 168976014-99453-DETAIL-05_21_2026-GO95HV-1^07217001.0143508 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000242 | 169019311-84811-DETAIL-01_15_2025-GO95HV-1^06239004.0255240 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000243 | 169019311-84811-DETAIL-01_15_2025-SVCENTCO-1^06239004.0255240 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000244 | 169127163-95819-DTLSB-05_11_2026-GO95HV-1^06242009.0278201 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000245 | 149688998-71329-DETAIL-04_21_2026-GUYHINS-1^06142012.0147701 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000246 | 149784-87199-DTLSB-03_09_2026-BIRDDMG-1^06242009.0174400 | POLE | Non-HFTD | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000247 | 149899385-82363-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0036100 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000248 | 149925584-85059-DETAIL-08_28_2025-GO95HV-1^07216001.0167803 | OTHER | Non-HFTD | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000249 | 172556676-20299-DETAIL-08_18_2025-BIRDDMG-1^06247006.0365300 | POLE | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000250 | 172556676-20299-DETAIL-08_18_2025-GO95HV-1^06247006.0365300 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000251 | 172656965-72065-AUDIT-06_11_2025-GO95HV-1^06148014.0248701 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000252 | 172656965-72065-DETAIL-06_03_2025-GRDRODHI-1^06148014.0248701 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000253 | 172707205-98205-DETAIL-06_02_2025-GO95HV-1^06148014.0243900 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000254 | 172827399-37569-DETAIL-08_26_2025-GO95HV-1^06247006.0332901 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000255 | 172827399-37569-DETAIL-08_26_2025-SVCDEFLC-1^06247006.0332901 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000256 | 175125736-80050-DTLSB-07_23_2025-SVCDEFLC-1^07218001.0263900 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000257 | 175166150-75359-DETAIL-10_09_2025-GO95HV-1^06248003.0275501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000258 | 175250600-12160-DETAIL-01_21_2025-BIRDDMG-1^06239004.0256544 | POLE | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000259 | 175434705-94705-DETAIL-05_15_2025-ENCHRW-1^06243006.0229703 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000260 | 175659034-17339-DETAIL-10_06_2025-GO95HV-1^06243007.0366600 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000261 | 175866431-38750-DETAIL-02_26_2026-SVCTREE-1^06238004.0022800 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000262 | 175866431-38750-DETAIL-02_26_2026-SVCTREE-2^06238004.0022800 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000263 | 179184965-7165-DTLSB-11_11_2021-CUSTWIRE-1^06148004.0348220 | OTHER | Non-HFTD | Distribution | 2021-11-11 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000264 | 179238334-22329-DETAIL-05_02_2022-CUSTWIRE-1^06143013.0191300 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000265 | 179412999-21420-DETAIL-08_11_2025-GO95HV-1^06246002.0261900 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000266 | 179571172-43070-DETAIL-03_18_2025-GRDRODHI-1^06238004.0125801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000267 | 179813971-96820-DETAIL-03_30_2026-SVCROAD-1^06240004.0271201 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000268 | 179946791-17073-DETAIL-09_10_2025-GO95HV-1^06246006.0180051 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000269 | 18003491-5273-DETAIL-09_11_2025-GO95HV-1^06248007.0224301 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000270 | 150486044-64039-DETAIL-05_08_2025-GO95HV-1^06243006.0036400 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000271 | 150606369-79549-DTLSB-07_03_2025-GO95HV-1^06244007.0136502 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000272 | 151077045-88045-AUDIT-07_07_2025-ABNDEQPM-1^06248004.0310604 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000273 | 151077045-88045-DETAIL-06_18_2025-GO95BLTC-1^06248004.0310604 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000274 | 151114644-76990-DETAIL-01_28_2026-XARMSPCR-1^06239002.0063506 | CROSSARM | Non-HFTD | Distribution | 2026-01-28 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000275 | 151155352-70330-DETAIL-07_06_2026-ABNDEQPM-1^07218001.0338600 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000276 | 151288024-16641-DETAIL-04_07_2025-SVCNEUT-1^06241005.0012802 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000277 | 151312577-81490-DETAIL-08_06_2025-GO95HV-1^06246002.0144300 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000278 | 184692811-31999-DETAIL-10_01_2025-GO95BLTC-1^06246008.0062101 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000279 | 185015744-43220-DTLSB-02_07_2023-CUSTWIRE-1^06248001.0158300 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000280 | 185058654-49860-DETAIL-01_23_2025-GO95HV-1^06239004.0257801 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000281 | 185058654-49860-DRONE_HY-07_15_2026-COVCOTHR-1^06239004.0257801 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000282 | 185350943-92709-DETAIL-09_04_2025-GO95HV-1^06247006.0073101 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000283 | 185356062-33569-DTLSB-07_09_2025-GO95HV-1^06244006.0276900 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000284 | 185356062-33569-DTLSB-07_09_2025-SVCENTCO-1^06244006.0276900 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000285 | 187871106-63106-DETAIL-03_25_2026-GRDRODHI-1^06240004.0217809 | OTHER | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000286 | 187871106-63106-DETAIL-03_25_2026-GRDRODHI-2^06240004.0217809 | OTHER | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000287 | 188158326-57470-DETAIL-01_22_2025-GO95HV-1^06239004.0255549 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000288 | 188175634-34630-DETAIL-04_13_2022-CUSTWIRE-1^06142012.0133605 | OTHER | Non-HFTD | Distribution | 2022-04-13 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000289 | 188384368-29079-DETAIL-02_01_2022-SVCWIND-1^06147005.0265405 | OTHER | Non-HFTD | Distribution | 2022-02-01 | 2025-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000290 | 188461738-82069-DTLTRT-06_10_2021-ANCHIDLE-1^668041/00 16/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-10 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000291 | 188772811-24350-DETAIL-03_04_2026-GO95HV-1^06239003.0181803 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000292 | 190388706-32389-ADMIN-10_30_2025-GO95BLTC-1^06246001.0030000 | OTHER | Non-HFTD | Distribution | 2025-10-30 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000293 | 190419765-39679-DETAIL-08_25_2025-GUYLOINS-2^06246001.0174001 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000294 | 190706225-81600-DETAIL-04_08_2026-GO95HV-1^06240002.0328301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000295 | 19094876-2579-DETAIL-08_05_2025-PWRTRN-1^06246002.0136000 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000296 | 191580928-3390-DETAIL-02_18_2025-GO95MLD-1^06239004.0361300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000297 | 191789804-3790-DETAIL-02_12_2026-SVCROAD-1^06239003.0364402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000298 | 191789804-3790-DETAIL-02_12_2026-SVCTREE-1^06239003.0364402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000299 | 191967891-80630-DETAIL-09_29_2025-DISTHDWR-1^06148001.0310509 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000300 | 193477975-11189-ADMIN-03_06_2023-CUSTWIRE-1^06148004.0192402 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000301 | 193699039-14770-AUDIT-04_27_2026-GO95MLD-1^06240004.0220902 | OTHER | HFTD Tier 2 | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000302 | 193984887-12730-DETAIL-08_11_2025-GO95HV-1^06246002.0227700 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000303 | 19412274-50690-DETAIL-03_26_2025-GO95HV-1^06239003.0019700 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000304 | 194217664-58730-DTLSB-02_06_2023-CUSTWIRE-1^06248001.0257201 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000305 | 19428246-41042-ADMIN-10_22_2025-GO95BLTC-1^06246011.0067501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000306 | 194325646-58830-DETAIL-05_29_2025-GO95HV-1^06147014.0011915 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000307 | 197060308-55691-DTLTRT-05_05_2026-GO95HV-1^668038/00 1/061 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000308 | 197285763-39-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0267902 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000309 | 1973256-38329-DETAIL-05_14_2025-GO95HV-1^06142012.0012303 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000310 | 197606046-22310-DETAIL-04_08_2026-GO95HV-1^06240002.0317301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000311 | 197638617-19049-DETAIL-06_04_2025-ABNDEQPM-1^06245006.0298900 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000312 | 19788031-69679-AUDIT-10_09_2025-GO95HV-1^06246001.0319000 | OTHER | Non-HFTD | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000313 | 198008215-29500-DETAIL-02_09_2026-SVCROAD-1^06239003.0016711 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000314 | 199978881-81640-DTLTRT-05_18_2026-GO95HV-1^668086/00 4/007 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000315 | 20017594-27729-DTLSB-01_21_2026-GO95HV-1^06242009.0298207 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000316 | 200193021-70740-DETAIL-08_19_2025-GO95HV-1^06246001.0319900 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000317 | 200543904-453-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0207640 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000318 | 200575983-14259-DETAIL-06_11_2025-GO95HV-1^06245007.0260101 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000319 | 200594599-98769-DETAIL-03_17_2025-COVCOTHR-1^668002/00 4/049 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-03-17 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000320 | 200685435-83463-DETAIL-07_07_2026-GO95HV-1^07217001.0219503 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000321 | 200955732-46780-DETAIL-02_13_2025-GO95TCH-1^06240004.0168146 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000322 | 203724746-44746-DETAIL-01_22_2026-GO95MLD-1^06239004.0267900 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000323 | 204287449-57370-DETAIL-04_02_2026-GO95HV-1^06236005.0152101 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000324 | 204461534-14039-DTLTRT-05_20_2026-GO95HV-1^668086/00 9/013 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000325 | 204472018-26879-DETAIL-01_20_2026-GO95BLTC-1^06242009.0299300 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000326 | 204596936-96849-DTLSB-07_17_2025-GO95HV-1^06244007.0113440 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000327 | 204627091-62480-DETAIL-02_12_2025-GO95HV-1^06240004.0167042 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000328 | 153330426-56590-DETAIL-05_15_2025-GO95HV-1^06142012.0115203 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000329 | 153390948-41853-DTLSB-06_05_2026-GO95HV-1^07216001.0143000 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000330 | 205991799-56640-DETAIL-08_18_2025-GO95HV-1^06246002.0345700 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000331 | 205994758-8359-DTLTRT-05_07_2026-GO95MLD-1^668004/00 7/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000332 | 206075321-44332-DTLTRT-05_12_2026-GO95HV-1^668004/00 9/008 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000333 | 206075321-69640-DTLTRT-05_12_2026-GO95HV-1^668004/00 9/008 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000334 | 206367801-62922-DTLTRT-04_23_2026-GO95HV-1^668004/00 3/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000335 | 206862763-48869-ADMIN-07_30_2025-POLEDERP-1^668002/00 10/072 | POLE | HFTD Tier 2 | Transmission | 2025-07-30 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000336 | 206862763-48870-ADMIN-07_30_2025-POLEDERP-1^668002/00 10/072 | POLE | HFTD Tier 2 | Transmission | 2025-07-30 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000337 | 207050749-2010-DTLSB-07_28_2025-GO95HV-1^07218001.0267241 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000338 | 210543017-35017-DETAIL-03_25_2024-CUSTWIRE-1^06147005.0112002 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000339 | 21057852-18199-DETAIL-05_14_2025-GRDRODHI-1^06243006.0154500 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000340 | 21057852-18199-DETAIL-05_14_2025-GRDRODHI-2^06243006.0154500 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000341 | 210874763-66253-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0047001 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000342 | 211012830-17479-DETAIL-10_08_2025-SVCROAD-1^06246008.0026601 | OTHER | HFTD Tier 2 | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000343 | 211198864-39864-DETAIL-06_18_2025-GO95BLTC-1^06248004.0364045 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000344 | 211412389-51739-DTLTRT-06_24_2025-GO95BLTC-1^668087/00 16/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000345 | 211412389-51739-DTLTRT-06_24_2025-GO95HV-1^668087/00 16/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000346 | 214659072-79223-DETAIL-03_31_2025-SVCROAD-1^06241005.0116605 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000347 | 214798039-31659-DETAIL-08_05_2025-GO95HV-1^06247005.0206600 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000348 | 215109794-79389-DETAIL-08_14_2025-GO95HV-1^06247006.0363801 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000349 | 215109794-79389-DETAIL-08_14_2025-GO95TCH-1^06247006.0363801 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000350 | 2152854-62399-DETAIL-03_20_2024-CUTOUTAR-2^06245001.0051000 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000351 | 215482210-74210-DETAIL-06_16_2025-CONDCOIL-1^06248005.0327202 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000352 | 215639996-88410-DRONE_HY-06_19_2026-XARMSPCR-2^06238004.0224642 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000353 | 217783318-60189-DTLSB-03_30_2026-SVCTREE-1^06241009.0323304 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000354 | 218017890-86789-DETAIL-04_28_2025-GO95HV-1^06242006.0103600 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000355 | 21881406-98210-DETAIL-02_26_2026-COVCOTHR-1^06238004.0118302 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000356 | 21881406-98210-DETAIL-02_26_2026-COVCOTHR-2^06238004.0118302 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000357 | 21881406-98210-DETAIL-02_26_2026-COVCOTHR-3^06238004.0118302 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000358 | 219123501-16550-DTLTRT-04_23_2026-GO95HV-1^668004/00 5/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000359 | 219123501-36522-DTLTRT-04_23_2026-GO95HV-1^668004/00 5/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000360 | 154484498-54290-DETAIL-09_30_2025-GO95HV-1^06148001.0300012 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000361 | 157275802-76639-DETAIL-05_07_2025-GO95HV-1^06243006.0352300 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000362 | 157400526-81963-DTLSB-06_15_2026-SVCDEFLC-1^07217001.0275441 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000363 | 15771780-74859-DETAIL-06_16_2025-GO95HV-1^06248005.0284101 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000364 | 15781878-2659-DETAIL-09_03_2025-GO95HV-1^07216001.0095001 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000365 | 158007011-38011-DETAIL-08_18_2025-SVCENTCO-1^06247006.0365402 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000366 | 158062428-45959-DTLSB-08_14_2025-GO95HV-1^07218001.0352200 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000367 | 158116463-32409-DETAIL-07_31_2025-GO95HV-1^06247005.0214603 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000368 | 158182699-58269-DTLSB-07_07_2025-GO95MLD-1^06244007.0039100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000369 | 220966751-39899-DTLSB-03_30_2026-GO95MLD-1^06242009.0210600 | OTHER | Non-HFTD | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000370 | 221126080-52332-DETAIL-04_02_2025-GO95BLTC-1^06241005.0117605 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000371 | 221126080-52332-DETAIL-04_02_2025-GO95CL10-1^06241005.0117605 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000372 | 22122810-99110-DETAIL-06_05_2025-GO95HV-1^668075/00 9/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000373 | 221318345-42209-DETAIL-08_12_2025-GO95HV-1^06247006.0264601 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000374 | 221318345-42209-DETAIL-08_12_2025-POLETOP-1^06247006.0264601 | POLE | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000375 | 221350683-5448-DTLSB-07_15_2025-GO95HV-1^06244006.0208702 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000376 | 221807005-63208-DTLTRT-07_09_2025-BIRDDMG-1^668087/00 2/025 | POLE | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000377 | 224872568-69360-DTLTRT-06_24_2025-CUTOUTAR-3^668087/00 5/004 | LIGHTNING ARRESTER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000378 | 225301008-61008-DETAIL-09_10_2025-GO95HV-1^07218001.0174701 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000379 | 225441082-96829-DTLSB-08_23_2023-CUSTWIRE-1^06243008.0183401 | OTHER | HFTD Tier 2 | Distribution | 2023-08-23 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000380 | 225518870-42440-DETAIL-04_01_2026-SVCTREE-1^06237005.0261400 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000381 | 22589360-97579-DTLSB-07_08_2025-GO95HV-1^06244007.0038200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000382 | 226235115-8809-DETAIL-08_14_2025-GO95HV-1^06247006.0254202 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000383 | 226256714-48079-DETAIL-09_16_2025-GUYHINS-1^06147001.0012800 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000384 | 226568681-1889-DTLSB-07_07_2025-GO95HV-1^06245007.0351000 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000385 | 227090452-14760-DTLTRT-04_28_2026-GO95HV-1^668004/00 12/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000386 | 227090452-55662-DTLTRT-04_28_2026-GO95HV-1^668004/00 12/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000387 | 227153448-17269-DETAIL-09_03_2025-GO95HV-1^06247006.0294000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000388 | 227323253-93641-DETAIL-05_13_2025-SVCDEFLC-1^06242004.0311804 | OTHER | HFTD Tier 2 | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000389 | 227358669-83913-DETAIL-08_26_2025-GO95HV-1^06247006.0288302 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000390 | 22750640-57711-DETAIL-02_24_2025-GO95MLD-1^06241005.0154400 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000391 | 227731031-77049-DETAIL-04_04_2023-CUSTWIRE-1^06245006.0222200 | OTHER | Non-HFTD | Distribution | 2023-04-04 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000392 | 229581429-90170-DETAIL-08_07_2025-GO95HV-1^06246002.0257900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000393 | 229745740-2270-DETAIL-08_12_2025-GO95BLTC-1^06246001.0300101 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000394 | 229745740-2270-DETAIL-08_12_2025-GO95HV-1^06246001.0300101 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000395 | 230143838-33399-DETAIL-06_04_2025-GO95HV-1^06245006.0199100 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000396 | 230166699-65049-DTLSB-07_07_2025-GO95HV-1^06244007.0038109 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000397 | 230178419-60041-DETAIL-04_08_2025-GO95HV-1^06241005.0092600 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000398 | 230996579-89870-DETAIL-06_04_2025-GO95HV-1^06142012.0106401 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000399 | 231031918-59839-DTLSB-06_30_2025-GO95HV-1^06244006.0221501 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000400 | 232451980-39569-DETAIL-05_06_2025-ABNDEQPM-1^06243006.0280200 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000401 | 232962481-11580-DETAIL-01_29_2026-GO95TCH-1^06240004.0307102 | OTHER | HFTD Tier 3 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000402 | 233160739-88813-DETAIL-08_26_2025-GO95HV-1^06247006.0285200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000403 | 233239805-96270-DETAIL-01_23_2026-GO95HV-1^06240003.0182700 | OTHER | HFTD Tier 2 | Distribution | 2026-01-23 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000404 | 233533146-35529-DTLSB-05_04_2026-GO95HV-1^06142013.0176501 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000405 | 233693436-40470-DETAIL-01_15_2025-GO95HV-1^06239004.0255146 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000406 | 233940393-29259-DTLTRT-04_22_2026-GO95HV-1^668004/02 2/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000407 | 234124056-20859-DETAIL-05_04_2026-GO95HV-1^668004/00 1/019 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000408 | 235679983-12129-DETAIL-04_22_2026-GO95HV-1^06142012.0149704 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000409 | 235760669-61669-DETAIL-09_03_2025-GO95HV-1^06246001.0176209 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000410 | 235806925-9370-DETAIL-03_05_2025-GO95HV-1^06240003.0184901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000411 | 236070731-42923-DETAIL-06_25_2026-GO95HV-1^07218001.0347000 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000412 | 236122064-48283-DETAIL-07_31_2025-GO95HV-1^06247006.0205540 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000413 | 236171656-73369-DTLTRT-10_09_2023-CUSTWIRE-1^668010/00 2A/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000414 | 236701385-64989-DETAIL-06_18_2025-GO95HV-1^06248004.0288102 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000415 | 239984495-28959-DETAIL-09_16_2025-GO95HV-1^06247004.0180241 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000416 | 240126603-99159-DETAIL-06_03_2025-GO95HV-1^06245007.0262101 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000417 | 240346846-68539-ADMIN-06_01_2026-POLEDERP-1^07216001.0200306 | POLE | Non-HFTD | Distribution | 2026-06-01 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000418 | 240531668-5280-DTLSB-05_06_2026-GO95HV-1^06142013.0270400 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000419 | 240620180-23559-DETAIL-08_06_2025-GO95HV-1^06247005.0208000 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000420 | 240627485-2089-DTLSB-04_22_2026-GO95BLTC-1^06241009.0249100 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000421 | 240685205-60790-DETAIL-01_26_2026-COVCOTHR-1^06240004.0230502 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000422 | 159572653-11789-DETAIL-09_04_2025-GO95HV-1^06247006.0073001 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000423 | 242097783-83540-DTLTRT-06_04_2025-GUYNOINS-2^668075/00 9/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000424 | 242664684-64622-ADMIN-10_20_2025-GO95BLTC-1^06246012.0122300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000425 | 242862374-58899-DTLSB-06_30_2025-BIRDDMG-1^06244007.0034001 | POLE | HFTD Tier 2 | Distribution | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000426 | 242862374-58899-DTLSB-06_30_2025-GO95HV-1^06244007.0034001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000427 | 243286709-13099-DETAIL-05_12_2025-GO95HV-1^06243006.0310900 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000428 | 243729633-60089-DETAIL-08_21_2025-SVCROAD-1^06247006.0254901 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000429 | 243780861-99039-DETAIL-05_05_2025-GO95HV-1^06243006.0345500 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000430 | 244193834-16809-ADMIN-10_21_2025-GO95HV-1^06246012.0056701 | OTHER | HFTD Tier 2 | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000431 | 24656335-43170-DETAIL-01_28_2026-GO95HV-1^06239002.0063401 | OTHER | Non-HFTD | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000432 | 246877029-13379-DETAIL-09_09_2025-GO95HV-1^06246007.0142250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000433 | 247141492-32759-DETAIL-07_29_2025-BIRDDMG-1^06247005.0212800 | POLE | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000434 | 247155698-54750-DETAIL-02_09_2026-GO95HV-1^06239003.0018004 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000435 | 247155698-54750-DETAIL-02_09_2026-SVCDEFLC-1^06239003.0018004 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000436 | 247519278-38743-DTLSB-07_03_2025-SVCROAD-1^06245007.0357841 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000437 | 247704747-4280-DTLTRT-06_23_2025-GO95HV-1^668087/00 11/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000438 | 247712055-82940-DETAIL-02_24_2025-GO95TCH-1^06240004.0152601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000439 | 248551525-34989-DETAIL-08_28_2025-GO95HV-1^06247006.0196900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000440 | 248722571-52770-DETAIL-02_19_2025-GO95CL10-1^06241005.0275902 | OTHER | HFTD Tier 3 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000441 | 248879780-87129-DETAIL-04_19_2022-CUSTWIRE-1^06142012.0132809 | OTHER | Non-HFTD | Distribution | 2022-04-19 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000442 | 248906643-35663-DTLTRT-08_05_2025-BIRDDMG-1^668087/00 7/012 | POLE | Non-HFTD | Transmission | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000443 | 2491718-51369-DETAIL-09_22_2025-GO95HV-1^06248007.0368300 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000444 | 249281351-98450-DETAIL-04_10_2025-GRDRODHI-1^06239003.0183801 | OTHER | HFTD Tier 3 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000445 | 24962027-95140-DETAIL-04_07_2026-GO95HV-1^06240002.0317110 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000446 | 251436873-38920-DETAIL-02_25_2025-SVCDEFLC-1^06241005.0250005 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000447 | 251498157-54218-DTLSB-02_27_2024-GO95MLD-1^07216001.0271700 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000448 | 251568360-94919-DTLSB-03_16_2026-BIRDDMG-1^06242009.0220801 | POLE | Non-HFTD | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000449 | 25162734-59809-DETAIL-10_15_2025-GO95MLD-1^06246012.0132700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000450 | 25200154-91079-DETAIL-09_23_2025-DISTHDWR-1^06247004.0074500 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000451 | 252113781-57609-DETAIL-10_16_2025-ENCHSVCE-1^06246010.0054302 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000452 | 252197881-35330-DTLTRT-05_27_2025-GO95HV-1^668075/00 9/005 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000453 | 252404612-37792-DETAIL-05_07_2025-GO95HV-1^06243006.0064741 | OTHER | HFTD Tier 2 | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000454 | 254115547-66359-DTLTRT-05_07_2026-GO95MLD-1^668004/00 5/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000455 | 25511001-76170-DETAIL-09_29_2025-GO95HV-1^06148001.0310506 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000456 | 255283240-53669-DETAIL-06_18_2025-GO95HV-1^06248004.0287200 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000457 | 255554382-63650-DETAIL-03_04_2026-COVCOTHR-1^06238004.0028401 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-04 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000458 | 255841069-40919-DETAIL-05_18_2026-CLRTOUCH-1^06242009.0285204 | CONDUCTOR | Non-HFTD | Distribution | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000459 | 255841754-91959-DETAIL-09_11_2025-GO95HV-1^06248007.0227901 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000460 | 255861784-95479-ADMIN-11_10_2025-GO95HV-1^06246010.0311200 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000461 | 256410781-26262-DTLSB-07_14_2025-GO95HV-1^06244006.0218502 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000462 | 260501579-73152-DETAIL-04_23_2025-GO95HV-1^06242006.0038701 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000463 | 260850450-80270-DETAIL-02_19_2026-GO95HV-1^06239002.0016602 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000464 | 26101264-12539-DETAIL-06_10_2026-CLMBHAZ-1^668086/00 3/013 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000465 | 26101264-12539-DTLTRT-05_20_2026-GO95BLTC-1^668086/00 3/013 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000466 | 261232185-69849-DTLSB-07_10_2025-GO95HV-1^06244007.0111740 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000467 | 262164706-61791-DETAIL-05_12_2026-GO95HV-1^668038/00 5/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000468 | 262164706-67900-DETAIL-05_12_2026-GO95HV-1^668038/00 5/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000469 | 26221672-96039-DETAIL-05_20_2025-GO95HV-1^06243006.0075101 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000470 | 264790429-40073-DETAIL-08_14_2025-GO95HV-1^06247006.0251003 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000471 | 264871463-19251-DETAIL-04_15_2025-SVCROAD-1^06242005.0334803 | OTHER | HFTD Tier 2 | Distribution | 2025-04-15 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000472 | 265323089-89379-DETAIL-07_16_2024-CUSTWIRE-1^06245007.0185400 | OTHER | HFTD Tier 2 | Distribution | 2024-07-16 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000473 | 265541828-91828-DTLTRT-06_17_2026-SVCDEFLC-1^07217001.0275141 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000474 | 265561539-66900-DETAIL-08_18_2025-GO95HV-1^06246002.0345201 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000475 | 265879513-43669-DETAIL-03_10_2026-XARMSPCR-1^668041/00 4/026 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000476 | 2661152-21439-DETAIL-05_19_2025-GO95HV-1^06243006.0230000 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000477 | 266213042-9983-DETAIL-08_21_2025-GO95HV-1^07216001.0175405 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000478 | 268499138-13989-DETAIL-04_23_2025-GO95HV-1^06242006.0108500 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000479 | 268565867-48867-DETAIL-09_29_2025-GO95BLTC-1^06148001.0317404 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000480 | 268867903-16009-DETAIL-10_16_2025-GO95HV-1^06246011.0277900 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000481 | 268970219-27510-DETAIL-08_18_2025-ABNDEQPM-1^06246002.0347900 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000482 | 269022533-37533-DETAIL-07_28_2025-GO95HV-1^06247005.0303602 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000483 | 269716834-21659-DETAIL-07_28_2025-GO95HV-1^06247005.0303401 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000484 | 269886948-40010-DTLTRT-06_24_2025-GO95CL10-1^668087/00 5/003 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000485 | 269886948-40010-DTLTRT-06_24_2025-GO95MLD-1^668087/00 5/003 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000486 | 274204746-21309-DETAIL-08_12_2025-GO95HV-1^06247006.0269101 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000487 | 274578672-61083-DETAIL-08_21_2025-GO95HV-1^07216001.0175200 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000488 | 275032983-8951-DETAIL-03_05_2025-GO95MLD-1^06241005.0132803 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000489 | 275084916-63889-DETAIL-08_25_2025-BIRDDMG-1^06247006.0269000 | POLE | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000490 | 275084916-63889-DETAIL-08_25_2025-GO95HV-1^06247006.0269000 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000491 | 275202158-49829-DTLSB-08_09_2023-CUSTWIRE-1^06243009.0150201 | OTHER | HFTD Tier 2 | Distribution | 2023-08-09 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000492 | 275370809-1809-DETAIL-08_18_2025-GO95HV-1^06247006.0361002 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000493 | 163795800-94070-DETAIL-02_19_2026-GO95HV-1^06239002.0029500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000494 | 163914854-45759-ADMIN-10_10_2024-POLEDERP-1^07216002.0247901 | POLE | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000495 | 275890732-6009-DETAIL-04_09_2024-COPLLEAN-1^06147005.0218601 | POLE | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000496 | 275890732-6009-DETAIL-04_09_2024-COVCFRAY-1^06147005.0218601 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000497 | 275890732-6009-DETAIL-04_09_2024-GO95HV-1^06147005.0218601 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000498 | 276033854-46099-DTLSB-06_24_2025-GO95HV-1^06244007.0031901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000499 | 276423933-14113-DTLSB-04_24_2024-GO95MLD-1^06245007.0227544 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000500 | 278857891-33501-DETAIL-04_09_2025-GUYHINS-1^06241005.0049500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-09 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000501 | 278932831-54080-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0167200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000502 | 279010981-90120-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0276300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000503 | 279024491-79480-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0168045 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000504 | 279147779-13470-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 4/066 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000505 | 279184566-85080-DETAIL-03_03_2025-GO95HV-1^06240004.0050005 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000506 | 279263283-75159-DETAIL-08_18_2025-GO95HV-1^06247006.0365401 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000507 | 281159569-85470-DETAIL-04_11_2023-CUSTWIRE-1^06240004.0167403 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000508 | 281304088-26199-DTLSB-07_21_2025-GO95HV-1^06244006.0308500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000509 | 281392171-57559-DETAIL-06_18_2025-GO95TCH-1^06248004.0340603 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000510 | 16397525-64565-DETAIL-02_18_2025-SVCDEFLC-1^06240004.0220406 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000511 | 164176953-67800-DTLTRT-05_13_2026-GO95HV-1^668085/00 5/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000512 | 164246909-67183-DETAIL-08_19_2025-GO95HV-1^07216001.0176906 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000513 | 164558931-82380-DETAIL-02_24_2025-GUYHINS-1^06240004.0152641 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000514 | 282157341-90109-DETAIL-07_31_2025-GO95HV-1^06247006.0207704 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000515 | 282169143-43780-DETAIL-02_23_2026-BIRDDMG-1^06239002.0150300 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000516 | 282187279-21720-AUDIT-05_27_2026-GO95TCH-1^668038/00 7/068 | OTHER | Non-HFTD | Transmission | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000517 | 282238213-56859-DTLSB-08_12_2025-GO95HV-1^07217001.0011901 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000518 | 282352504-4490-DETAIL-02_10_2026-BIRDDMG-1^06239003.0016808 | POLE | Non-HFTD | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000519 | 282458289-4389-DTLTRT-07_07_2025-GO95BLTC-1^668087/00 1/028 | OTHER | Non-HFTD | Transmission | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000520 | 282458289-4389-DTLTRT-07_07_2025-GUYHINS-1^668087/00 1/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000521 | 282484707-86899-DETAIL-06_05_2025-GO95HV-1^06245006.0300801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000522 | 284084816-63359-DTLTRT-05_07_2026-GO95HV-1^668004/00 17/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000523 | 284202492-74880-DETAIL-01_29_2026-GUYHINS-1^06240004.0318800 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000524 | 284363316-98579-DETAIL-04_01_2024-CUTOUTAR-1^06147005.0128700 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000525 | 284409200-92032-DETAIL-04_02_2025-GUYHINS-2^06241005.0117703 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000526 | 285253170-51670-DETAIL-02_17_2026-GO95HV-1^06239002.0091600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000527 | 285293466-67410-DETAIL-04_07_2026-GO95HV-1^06240002.0317106 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000528 | 285525074-83050-DTLTRT-06_03_2025-GUYNOINS-1^668075/00 5A/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000529 | 285695773-13180-DETAIL-02_23_2026-BIRDDMG-1^06239002.0225502 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000530 | 289109578-213-DETAIL-10_13_2025-GO95BLTC-1^06246012.0134800 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000531 | 289522392-42929-DTLSB-08_30_2023-CUSTWIRE-1^06243008.0179700 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000532 | 289846973-60729-DETAIL-04_23_2025-GO95HV-1^06242006.0020100 | OTHER | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000533 | 28996291-61139-DTLTRT-07_08_2025-GO95HV-1^668087/00 13/025 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000534 | 290089894-16839-DETAIL-05_06_2025-GO95HV-1^06243006.0032900 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000535 | 290232779-11230-ADMIN-08_11_2025-SVCNEUT-1^668087/00 2/007 | OTHER | Non-HFTD | Transmission | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000536 | 290485713-55089-DETAIL-09_09_2025-ABNDEQPM-1^06147001.0199801 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000537 | 290485713-55089-DETAIL-09_09_2025-GO95HV-1^06147001.0199801 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000538 | 292173513-11780-DETAIL-02_17_2026-GO95HV-1^06239002.0059501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000539 | 292459690-69670-DETAIL-02_05_2025-GO95HV-1^06240004.0167100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000540 | 292732073-78430-DRONE_HY-07_10_2026-XARMBRAC-1^06143014.0185201 | CROSSARM | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000541 | 292822789-28770-DETAIL-06_11_2025-GUYHINS-1^06236005.0167001 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000542 | 2930646-77863-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0047100 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000543 | 293077087-19160-DETAIL-06_09_2025-RISEBKSP-1^06245006.0191301 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000544 | 293354439-42669-DETAIL-08_14_2025-GO95BLTC-1^06247006.0364800 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000545 | 293354439-42669-DETAIL-08_14_2025-GO95HV-1^06247006.0364800 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000546 | 29677616-11223-DTLSB-05_01_2024-SVCWIND-1^06245007.0227341 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000547 | 296896543-67543-DETAIL-06_09_2025-GO95HV-1^668075/00 7/030 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000548 | 297165676-17676-DETAIL-05_29_2025-GO95HV-1^06148014.0360600 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000549 | 297217654-93519-DTLSB-04_23_2026-BIRDDMG-1^06241009.0225800 | POLE | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000550 | 297217654-93519-DTLSB-04_23_2026-POLISSUE-1^06241009.0225800 | POLE | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000551 | 297279900-21000-DETAIL-06_04_2025-GUYHINS-1^06245006.0289907 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000552 | 297700789-18089-DETAIL-10_14_2025-GO95HV-1^06148001.0285602 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000553 | 29778625-63429-DETAIL-05_13_2025-GO95HV-1^06142012.0016602 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000554 | 300015019-36019-DETAIL-08_14_2025-GO95BLTC-1^06247006.0360700 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000555 | 300015019-36019-DETAIL-08_14_2025-GO95TCH-1^06247006.0360700 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000556 | 300209289-60969-DETAIL-09_22_2025-GO95HV-1^06248007.0244100 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000557 | 300275988-95359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0326401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000558 | 300557888-23199-ADMIN-10_23_2025-GO95HV-1^06246011.0365102 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000559 | 30098868-5700-DETAIL-09_03_2025-GO95HV-1^06246001.0207903 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000560 | 301171741-80169-DTLTRT-05_12_2026-GO95HV-1^668004/00 2/010 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000561 | 301171741-80170-DTLTRT-05_12_2026-GO95HV-1^668004/00 2/010 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000562 | 303978348-71960-DETAIL-09_15_2025-SVCDEFLC-1^07219001.0323302 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000563 | 304011808-13808-DETAIL-04_02_2025-GO95TCH-1^06241005.0117704 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000564 | 304011808-13808-DETAIL-04_02_2025-SVCROAD-1^06241005.0117704 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000565 | 304060811-169-DTLTRT-05_12_2026-GO95HV-1^668004/00 8/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000566 | 304060811-170-DTLTRT-05_12_2026-GO95HV-1^668004/00 8/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000567 | 304203509-54509-DETAIL-03_04_2025-GO95BLTC-1^06241005.0131506 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000568 | 304226686-96989-DETAIL-08_07_2025-GO95HV-1^06246002.0234301 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000569 | 304288898-9898-DETAIL-03_04_2026-GO95HV-1^06239003.0180901 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000570 | 306419386-70661-DETAIL-04_10_2025-GUYHINS-1^06241005.0012644 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000571 | 306465054-40899-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0219803 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000572 | 30708261-300-DTLSB-10_16_2025-ABNDEQPM-1^06247001.0349500 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000573 | 30708261-300-DTLSB-10_16_2025-GO95HV-1^06247001.0349500 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000574 | 307159836-73533-DETAIL-06_17_2025-GO95HV-1^06248004.0361040 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000575 | 307372316-3650-DTLSB-06_04_2026-SVCENTBK-1^07216001.0113101 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000576 | 307422053-37659-DTLTRT-04_21_2026-GO95HV-1^668004/02 11/006 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000577 | 309689269-12522-DTLTRT-04_23_2026-GUYNOINS-1^668004/00 1X/001 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000578 | 309689269-12522-DTLTRT-04_23_2026-GUYNOINS-2^668004/00 1X/001 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000579 | 309689269-46150-DTLTRT-04_23_2026-GO95HV-1^668004/00 1X/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000580 | 309689269-46150-DTLTRT-04_23_2026-GUYNOINS-1^668004/00 1X/001 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000581 | 309689269-46150-DTLTRT-04_23_2026-GUYNOINS-2^668004/00 1X/001 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000582 | 310058828-63243-DTLSB-04_30_2024-CUSTWIRE-1^06245007.0222943 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000583 | 310372746-82746-DETAIL-01_22_2026-GO95MLD-1^06239004.0268801 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000584 | 312528165-60265-DETAIL-05_29_2025-GO95HV-1^06147014.0017801 | OTHER | HFTD Tier 2 | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000585 | 312719593-22509-DETAIL-09_10_2025-GO95HV-1^06246007.0133150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000586 | 312802984-29469-DETAIL-03_11_2026-SVCROAD-1^06242009.0111802 | OTHER | Non-HFTD | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000587 | 313053339-86379-DETAIL-09_09_2025-GO95HV-1^06246007.0142251 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000588 | 313053339-86379-DETAIL-09_09_2025-GRDRODHI-1^06246007.0142251 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000589 | 313053339-86379-DETAIL-09_09_2025-GRDRODHI-2^06246007.0142251 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000590 | 313591691-80089-DETAIL-10_01_2025-GO95HV-1^06148001.0303300 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000591 | 313603583-31780-DETAIL-03_31_2026-COVCOTHR-1^06240004.0355301 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000592 | 31684576-34929-DETAIL-05_14_2025-GO95HV-1^06142012.0012100 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000593 | 316968749-33739-DTLTRT-06_24_2025-CLRTOPOL-1^668087/00 14/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000594 | 169486375-29849-DTLSB-07_10_2025-GO95HV-1^06244007.0110840 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000595 | 169915331-95449-DTLSB-07_09_2025-GO95HV-1^06244007.0158700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000596 | 170470095-30349-DTLSB-07_10_2025-GO95HV-1^06244006.0342804 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000597 | 170577034-10940-DTLTRT-10_04_2023-CUSTWIRE-1^668010/00 9/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000598 | 170707157-15719-DTLSB-04_09_2026-GO95HV-1^06241007.0201000 | OTHER | Non-HFTD | Distribution | 2026-04-09 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000599 | 17071666-81140-DETAIL-05_19_2025-GO95HV-1^06243006.0277401 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000600 | 173208476-74870-DETAIL-01_23_2025-GO95HV-1^06239004.0256643 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000601 | 173342618-81610-ADMIN-11_12_2025-GO95HV-1^06246001.0336000 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000602 | 173342618-81610-ADMIN-11_12_2025-GRDRODHI-1^06246001.0336000 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000603 | 173391813-49939-DETAIL-06_10_2026-GUYHINS-1^668086/00 12/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000604 | 173391813-49939-DETAIL-06_10_2026-GUYHINS-2^668086/00 12/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000605 | 173391813-49939-DETAIL-06_10_2026-GUYHINS-4^668086/00 12/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000606 | 173391813-49939-DETAIL-06_10_2026-GUYHINS-5^668086/00 12/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000607 | 173391813-49939-DETAIL-06_10_2026-GUYHINS-6^668086/00 12/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000608 | 320059398-23859-DETAIL-03_18_2024-CUSTWIRE-1^06246005.0078200 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000609 | 320164943-60268-ADMIN-10_07_2025-COVCOTHR-1^06246012.0143100 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000610 | 320656158-45999-DTLSB-07_16_2025-GO95HV-1^06244006.0290001 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000611 | 321092928-63928-DETAIL-04_15_2026-GRDRODHI-1^06241008.0082802 | OTHER | Non-HFTD | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000612 | 321208391-88931-ADMIN-12_29_2025-COVCOTHR-1^06241005.0024140 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-12-29 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000613 | 32132985-74985-DETAIL-06_03_2025-GO95HV-1^06148014.0248900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000614 | 32132985-74985-DETAIL-06_03_2025-SVCROAD-1^06148014.0248900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000615 | 324508061-56439-DETAIL-05_08_2025-GO95HV-1^06243006.0162100 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000616 | 324895855-95689-DETAIL-08_13_2025-GO95BLTC-1^06247006.0263603 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000617 | 32496175-25010-DTLSB-04_29_2026-GO95HV-1^06142013.0206200 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000618 | 325057965-17249-DTLSB-06_08_2026-GO95HV-1^07216001.0228102 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000619 | 32519533-92389-DETAIL-03_05_2024-CUSTWIRE-1^06245007.0276201 | OTHER | HFTD Tier 2 | Distribution | 2024-03-05 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000620 | 325301838-29279-DETAIL-03_05_2026-GO95TCH-1^06238004.0144200 | OTHER | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000621 | 325394494-20770-DETAIL-04_21_2026-GO95HV-1^06142012.0149800 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000622 | 325394494-20770-DETAIL-04_21_2026-GUYHINS-1^06142012.0149800 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000623 | 327823406-65406-DETAIL-06_03_2025-GO95HV-1^06148014.0249802 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000624 | 328475125-62779-DETAIL-09_23_2025-GO95HV-1^06247004.0182700 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000625 | 328527056-150-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 7/049 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000626 | 328550818-10229-DETAIL-04_21_2026-GO95HV-1^06142012.0147807 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000627 | 32863693-84693-DETAIL-08_06_2025-GO95HV-1^06247005.0192001 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000628 | 329043421-24143-DETAIL-07_07_2026-GO95HV-1^07217001.0166901 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000629 | 32922131-58420-DTLTRT-06_26_2025-INSULDMG-1^668087/00 5/009 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000630 | 332138344-16899-DETAIL-08_14_2024-CUSTWIRE-1^06246005.0256800 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000631 | 332235975-12839-DTLTRT-06_26_2025-SVCROAD-1^668087/00 18/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000632 | 332341013-57570-DETAIL-02_14_2023-CUSTWIRE-1^06247002.0214600 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000633 | 332581619-592-DTLSB-07_22_2025-GO95HV-1^06244006.0195441 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000634 | 332868044-36283-DETAIL-07_29_2025-GO95HV-1^06247005.0279201 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000635 | 332952005-69470-DETAIL-01_27_2026-GRDRODHI-1^06239002.0062405 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000636 | 333026276-5742-ADMIN-11_10_2025-GO95BLTC-1^06246011.0070800 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000637 | 176262991-73819-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0227200 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000638 | 17629914-26899-DETAIL-08_28_2025-GO95HV-1^06247006.0178002 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000639 | 176387070-48989-DTLSB-09_01_2022-CUSTWIRE-1^06243004.0234501 | OTHER | Non-HFTD | Distribution | 2022-09-01 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000640 | 176742552-55850-DETAIL-03_20_2025-SVCROAD-1^06239003.0016300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000641 | 334847713-51080-DETAIL-09_16_2025-GO95HV-1^06147001.0134700 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000642 | 335143922-70879-DETAIL-07_21_2025-GO95HV-1^06247005.0159700 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000643 | 335143922-70879-DETAIL-07_21_2025-GUYHINS-1^06247005.0159700 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-21 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000644 | 337112869-75129-DETAIL-05_02_2022-CUSTWIRE-1^06143012.0244701 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000645 | 337205798-7089-DETAIL-08_13_2025-GO95HV-1^06246002.0254800 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000646 | 337232556-66369-DETAIL-04_24_2025-GO95HV-1^06242006.0192201 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000647 | 337563283-36859-DTLSB-08_11_2025-GO95HV-1^07217001.0010501 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000648 | 337645519-73679-DTLSB-09_03_2024-CUSTWIRE-1^06245007.0016200 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000649 | 337650433-10912-DTLSB-07_17_2025-GO95HV-1^06244006.0199042 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000650 | 33794732-74183-DETAIL-07_24_2025-GO95HV-1^06247005.0138300 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000651 | 340016024-75570-DETAIL-04_28_2025-GO95HV-1^06239002.0060306 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000652 | 34004793-83922-DETAIL-05_30_2025-COPLLEAN-1^06244006.0144340 | POLE | Non-HFTD | Distribution | 2025-05-30 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000653 | 340071668-15089-DETAIL-08_19_2025-GO95HV-1^06246002.0352900 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000654 | 340163363-25363-DETAIL-09_18_2025-GO95MLD-1^07218001.0085102 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000655 | 340203789-91633-DETAIL-09_10_2025-SVCENTCO-1^07218001.0177102 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000656 | 340511519-27509-DETAIL-09_30_2025-GO95HV-1^06246009.0135600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000657 | 341063761-29909-AUDIT-06_20_2024-SVCENTCO-1^06245007.0226800 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000658 | 343949069-44179-DETAIL-08_05_2025-GO95HV-1^06247005.0206500 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000659 | 343995909-75852-DTLSB-07_17_2025-BIRDDMG-1^06244006.0308442 | POLE | HFTD Tier 2 | Distribution | 2025-07-17 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000660 | 344081191-49843-DETAIL-06_30_2026-GO95HV-1^07217001.0226002 | OTHER | Non-HFTD | Distribution | 2026-06-30 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000661 | 344114476-71890-DETAIL-09_02_2025-SVCNEUT-1^06246001.0176207 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000662 | 344253119-20990-DTLTRT-06_24_2025-BIRDDMG-1^668087/00 12/005 | POLE | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000663 | 344316764-43630-DETAIL-02_25_2025-SVCDEFLC-1^06241005.0254301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000664 | 344731174-68339-DETAIL-10_06_2025-GO95HV-1^06243007.0364500 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000665 | 347837692-9650-DETAIL-02_03_2026-GUYHINS-1^06239003.0019403 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000666 | 347870214-26890-DETAIL-02_10_2026-SVCROAD-1^06239003.0015605 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000667 | 3481798-74509-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 1/015 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000668 | 34819244-38219-DETAIL-02_02_2021-CUSTWIRE-1^06242009.0058703 | OTHER | HFTD Tier 2 | Distribution | 2021-02-02 | 2024-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000669 | 348397201-4890-DETAIL-09_11_2025-GO95HV-1^07216001.0079601 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000670 | 348397201-4890-DETAIL-09_11_2025-GRDRODHI-1^07216001.0079601 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000671 | 348553856-20090-DTLTRT-05_11_2026-GO95HV-1^668038/00 4/048 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000672 | 348847588-78109-DETAIL-10_14_2025-GO95HV-1^07117008.0207600 | OTHER | HFTD Tier 2 | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000673 | 350536614-70609-DETAIL-09_10_2025-GO95HV-1^06246006.0077000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000674 | 350897485-35688-DETAIL-07_06_2023-CUSTWIRE-1^06244008.0327601 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000675 | 351504041-69590-AUDIT-10_28_2025-POLISSUE-1^06147001.0079801 | POLE | Non-HFTD | Distribution | 2025-10-28 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000676 | 351584241-80759-DETAIL-06_18_2025-GO95HV-1^06248004.0324900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000677 | 351758988-27790-DTLTRT-07_01_2025-GO95HV-1^668087/00 3/016 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000678 | 351758988-81882-DTLTRT-07_01_2025-GO95HV-1^668087/00 3/016 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000679 | 351783164-75899-DETAIL-08_13_2025-GO95HV-1^06247006.0257401 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000680 | 353591139-19133-DETAIL-09_09_2025-GO95HV-1^07218001.0175900 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000681 | 353717863-77253-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0030804 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000682 | 35382626-58029-DETAIL-04_22_2025-GO95HV-1^06242006.0067000 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000683 | 354206445-10400-DETAIL-08_20_2025-GO95HV-1^06246001.0174403 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000684 | 354293934-56449-DTLSB-04_17_2024-POLETOP-1^06245007.0224501 | POLE | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000685 | 354347779-12473-DETAIL-09_22_2025-GO95HV-1^06248007.0243701 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000686 | 354888317-29317-DETAIL-06_18_2025-GO95MLD-1^668075/00 13/045 | OTHER | Non-HFTD | Transmission | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000687 | 354972789-42579-DETAIL-02_19_2026-GO95HV-1^06239002.0029501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000688 | 178345499-69479-DTLSB-07_22_2025-GO95HV-1^06244006.0180500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000689 | 17854879-27379-DETAIL-09_09_2025-GO95HV-1^06246007.0144151 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000690 | 178722916-76020-DTLSB-04_29_2026-GO95HV-1^06142013.0209201 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000691 | 17900632-69460-DETAIL-04_29_2026-GO95HV-1^668004/00 4/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000692 | 17904009-52899-DETAIL-09_09_2025-GO95HV-1^06246007.0149151 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000693 | 179383721-52659-DTLSB-06_08_2026-GO95HV-1^07216001.0231002 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000694 | 179538776-17349-DTLSB-07_14_2025-GO95HV-1^06244006.0272502 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000695 | 179813971-96820-DETAIL-03_30_2026-SVCDEFLC-1^06240004.0271201 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000696 | 359147864-80600-DETAIL-09_08_2025-GRDRODHI-1^06147001.0299001 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000697 | 359445942-5419-DTLSB-07_09_2026-GO95HV-1^06240008.0141201 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000698 | 360118598-45549-DTLSB-07_16_2025-GO95HV-1^06244006.0317600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000699 | 360177438-44299-DETAIL-09_15_2025-GO95HV-1^06248007.0235500 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000700 | 360364036-39570-DETAIL-01_22_2025-GO95MLD-1^06239004.0256540 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000701 | 360366629-65400-DETAIL-09_30_2025-GO95HV-1^06148001.0300015 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000702 | 360420829-60859-DETAIL-06_16_2025-GO95HV-1^06248005.0330640 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000703 | 360523160-22610-DTLSB-06_16_2026-CUSTWIRE-1^07217001.0356602 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000704 | 362208767-73859-DTLSB-08_14_2025-GO95HV-1^07218001.0350901 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000705 | 362277916-94540-DETAIL-02_20_2025-GO95HV-1^06240004.0214600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-20 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000706 | 362285186-87193-DETAIL-08_18_2025-SVCDEFLC-1^06247006.0362403 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000707 | 362288442-36489-DETAIL-07_23_2025-ABNDEQPM-1^06247005.0176004 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000708 | 362652021-20810-DTLSB-05_07_2026-GO95HV-1^06142013.0347401 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000709 | 363365989-90289-DETAIL-09_04_2025-GO95HV-1^06146001.0080901 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000710 | 363545657-73988-DETAIL-05_27_2025-GO95BLTC-1^06244006.0093700 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000711 | 363596230-7273-ADMIN-12_29_2025-COVCOTHR-1^668001/00 10/048 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-12-29 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000712 | 364008046-56710-DTLTRT-05_07_2026-GO95HV-1^668038/00 7/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000713 | 364401418-15650-DETAIL-04_22_2025-GO95HV-1^06240003.0055502 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000714 | 364694796-43349-DTLSB-07_15_2025-GO95HV-1^06244006.0271201 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000715 | 36470714-59839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0218501 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000716 | 364876072-63410-DETAIL-08_14_2025-GO95HV-1^06246001.0317601 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000717 | 365244128-40233-DETAIL-09_09_2025-GO95MLD-1^07218001.0175403 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000718 | 365271606-41510-DRONE_HY-06_30_2026-BIRDDMG-1^06238004.0222500 | POLE | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000719 | 368326158-94379-AUDIT-10_20_2025-GUYHINS-1^06246009.0091700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000720 | 368416320-96920-DETAIL-06_05_2025-GO95HV-1^668075/00 16/026 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000721 | 36849221-66239-DTLTRT-07_08_2025-GO95HV-1^668087/00 1/026 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000722 | 368538114-89399-DETAIL-07_31_2025-ABNDEQPM-1^06247006.0201800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000723 | 368538114-89399-DETAIL-07_31_2025-GO95MLD-1^06247006.0201800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000724 | 368701497-95910-DETAIL-04_21_2026-ANCHIDLE-1^06142012.0141901 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000725 | 368848424-26440-DETAIL-02_26_2025-SVCENTCO-1^06240004.0217901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000726 | 369084408-94729-DETAIL-04_23_2025-GO95HV-1^06242006.0039202 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000727 | 372684725-35725-DETAIL-09_24_2025-GO95BLTC-1^06246009.0167501 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000728 | 372793211-37909-DETAIL-11_18_2025-GO95HV-1^06246010.0136600 | OTHER | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000729 | 37302235-16235-DETAIL-06_05_2025-GO95BLTC-1^06148014.0246602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000730 | 373227593-15249-DTLSB-07_17_2025-GO95HV-1^06244006.0254900 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000731 | 37323551-26839-DTLSB-07_17_2025-GO95BLTC-1^06244006.0218300 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000732 | 37323551-26839-DTLSB-07_17_2025-GUYLOINS-1^06244006.0218300 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-17 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000733 | 373334166-49642-ADMIN-11_10_2025-GO95BLTC-1^06246011.0064100 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000734 | 373337962-6659-DETAIL-06_18_2025-GO95CLSV-1^06248004.0310500 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000735 | 375794123-79420-DETAIL-05_15_2024-GRDRODHI-1^06142012.0124703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000736 | 376309648-2470-DETAIL-02_26_2025-GO95BLTC-1^06240004.0061402 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000737 | 376309648-2470-DETAIL-02_26_2025-GO95HV-1^06240004.0061402 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000738 | 376467563-47722-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0256701 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000739 | 376553018-46190-DETAIL-01_28_2025-GO95MLD-1^06239004.0244410 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000740 | 376553018-46190-DETAIL-01_28_2025-SVCENTCO-1^06239004.0244410 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000741 | 37718394-22161-DTLSB-07_27_2022-CUSTWIRE-1^06242005.0266903 | OTHER | HFTD Tier 2 | Distribution | 2022-07-27 | 2025-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000742 | 379275255-38361-DETAIL-02_24_2025-GO95MLD-1^06239004.0366604 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000743 | 3793969-8759-DTLSB-07_31_2025-GO95HV-1^07218001.0262400 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000744 | 379534264-2889-AUDIT-10_14_2025-GO95TCH-1^06241005.0029107 | OTHER | HFTD Tier 2 | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000745 | 379885758-7758-DETAIL-09_23_2025-GO95HV-1^07218001.0229203 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000746 | 38038681-37380-DETAIL-02_23_2026-GO95HV-1^06239002.0030401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000747 | 380407243-25479-DTLSB-05_28_2024-CUSTWIRE-1^06243001.0127400 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000748 | 380491816-39499-DETAIL-05_27_2025-GO95HV-1^06244006.0085703 | OTHER | HFTD Tier 2 | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000749 | 383275144-17103-DETAIL-02_24_2026-GO95HV-1^06239002.0070502 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000750 | 383275144-17103-DETAIL-02_24_2026-GUYHINS-1^06239002.0070502 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000751 | 383464864-91960-DRONE_HY-07_10_2026-RISEBKSP-1^06239004.0255004 | OTHER | HFTD Tier 2 | Distribution | 2026-07-10 | 2029-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120000752 | 384015904-27030-DETAIL-09_11_2025-GO95HV-1^06147001.0132600 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000753 | 384060018-36119-DTLSB-03_30_2026-GO95HV-1^06241009.0324202 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000754 | 384496030-23330-DTLTRT-05_14_2026-CUSTWIRE-1^668086/00 12/004 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000755 | 384581301-33301-DETAIL-09_22_2025-GRDRODHI-1^07218001.0161003 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000756 | 384659008-69973-DETAIL-02_26_2025-SVCDEFLC-1^06240004.0219740 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000757 | 387804511-93129-DTLSB-08_14_2023-CUSTWIRE-1^06243009.0236701 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000758 | 387821177-18540-DETAIL-04_23_2026-GO95HV-1^06142012.0144604 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000759 | 38792138-15170-DETAIL-01_27_2025-GO95TCH-1^06240004.0081401 | OTHER | HFTD Tier 2 | Distribution | 2025-01-27 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000760 | 387987814-86109-DETAIL-08_20_2025-GO95HV-1^06247006.0255700 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000761 | 38812184-29059-DETAIL-08_19_2025-GO95HV-1^06247006.0368300 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000762 | 388133481-55089-DETAIL-10_02_2025-GUYHINS-1^06246008.0063201 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000763 | 388133481-55089-DETAIL-10_02_2025-GUYHINS-2^06246008.0063201 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000764 | 389789626-20759-DETAIL-04_30_2026-GO95HV-1^668004/00 2/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000765 | 389883591-10111-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135500 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000766 | 390475783-62403-DETAIL-06_09_2025-GO95HV-1^06245006.0195700 | OTHER | Non-HFTD | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000767 | 39133234-35773-DETAIL-05_24_2023-CUSTWIRE-1^06245005.0298500 | OTHER | Non-HFTD | Distribution | 2023-05-24 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000768 | 391399335-51110-DRONE_HY-06_30_2026-XARMSPCR-1^06238004.0152240 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120000769 | 391588628-75450-DETAIL-01_09_2023-CUSTWIRE-1^06240004.0097502 | OTHER | HFTD Tier 2 | Distribution | 2023-01-09 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000770 | 394261709-91709-DETAIL-08_18_2025-GO95HV-1^06247006.0365100 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000771 | 394308889-16382-DTLTRT-07_09_2025-BIRDDMG-1^668087/00 1/022 | POLE | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000772 | 394308889-91239-DTLTRT-07_09_2025-BIRDDMG-1^668087/00 1/022 | POLE | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000773 | 39432408-85591-DETAIL-05_07_2026-GO95HV-1^668038/00 1/056 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000774 | 394644188-75489-DTLSB-07_10_2025-GO95HV-1^06244007.0036900 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000775 | 39470658-15191-ADMIN-07_30_2025-POLEDERP-1^668038/00 6/058 | POLE | HFTD Tier 2 | Transmission | 2025-07-30 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000776 | 394742788-57299-DETAIL-09_16_2025-GO95HV-1^07216001.0085105 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000777 | 182904781-97809-DETAIL-10_02_2025-GUYHINS-1^06246008.0064200 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000778 | 182998526-68463-DETAIL-06_23_2026-GO95HV-1^07217001.0106401 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000779 | 18356974-11959-DTLTRT-04_22_2026-GO95HV-1^668004/02 17/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000780 | 18359059-12459-DETAIL-07_28_2025-POLETOP-1^06247005.0198602 | POLE | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000781 | 183591020-60643-DETAIL-06_23_2026-GO95HV-1^07217001.0115301 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000782 | 183774213-68169-DETAIL-06_10_2024-CUSTWIRE-1^06245007.0347100 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000783 | 183898058-21720-DTLSB-05_05_2026-GO95HV-1^06142013.0163001 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000784 | 183951946-31759-DETAIL-04_30_2026-GO95HV-1^668004/00 4/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000785 | 399970755-12900-DETAIL-04_08_2026-GO95HV-1^06240002.0314301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000786 | 40007236-36609-ADMIN-10_20_2025-GO95HV-1^06246012.0110200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000787 | 400089773-63434-DETAIL-05_01_2024-GO95HV-1^06143015.0338601 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000788 | 400327076-6559-DTLSB-06_08_2026-GO95HV-1^07216001.0228101 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000789 | 400544613-93819-DTLSB-05_11_2026-GO95HV-1^06242009.0272200 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000790 | 400663908-44549-DTLSB-07_16_2025-GO95HV-1^06244006.0317500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000791 | 40069890-49099-DTLSB-06_25_2025-GO95HV-1^06244007.0101400 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000792 | 402431993-84059-DETAIL-09_05_2025-GO95HV-1^06247006.0060500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000793 | 402916699-74850-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0104300 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000794 | 403197574-74229-DETAIL-05_07_2025-GO95HV-1^06242007.0232000 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000795 | 403295814-73799-DETAIL-03_06_2024-GO95MLD-1^06147005.0177701 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000796 | 184514050-76920-AUDIT-09_15_2025-GUYHINS-1^06246001.0305001 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000797 | 184665791-48489-DTLSB-07_07_2025-GO95HV-1^06245007.0351001 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000798 | 184725933-40033-DETAIL-01_13_2026-SVCENTCO-1^06239004.0245901 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000799 | 406928999-90160-DTLTRT-05_06_2026-GO95HV-1^668004/00 7/023 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000800 | 407029498-38789-DETAIL-06_03_2024-CUSTWIRE-1^06246005.0317901 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000801 | 407029498-38789-DETAIL-06_03_2024-GO95MLD-1^06246005.0317901 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000802 | 407326474-37489-DTLSB-01_20_2026-XARMSPCR-1^06242009.0299309 | CROSSARM | Non-HFTD | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000803 | 407499849-96109-ADMIN-07_02_2026-CONDFRAY-1^06147004.0017202 | CONDUCTOR | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000804 | 407584905-21289-DETAIL-01_29_2026-GO95BLTC-1^06242009.0050503 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000805 | 407603594-5594-DETAIL-03_04_2025-SVCDEFLC-1^06240004.0065906 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000806 | 410245454-32899-ADMIN-04_05_2024-ABNDEQPM-1^06245007.0275707 | OTHER | Non-HFTD | Distribution | 2024-04-05 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000807 | 41057173-43680-DETAIL-02_17_2026-GO95HV-1^06239002.0040201 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000808 | 410711870-92370-AUDIT-02_02_2026-GO95MLD-1^06240004.0344700 | OTHER | HFTD Tier 3 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000809 | 410884599-58860-DETAIL-09_04_2025-GO95HV-1^06146001.0082903 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000810 | 410951016-9363-DETAIL-07_06_2026-CUSTWIRE-1^07217001.0030702 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000811 | 411028388-53750-AUDIT-04_22_2025-XARMSPCR-1^06239003.0019302 | CROSSARM | Non-HFTD | Distribution | 2025-04-22 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000812 | 411041623-32623-DETAIL-06_04_2025-GUYHINS-2^668075/00 13/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000813 | 411206346-73160-DTLTRT-07_03_2025-GO95HV-1^668087/00 4/011 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000814 | 18582189-71340-DETAIL-09_16_2025-GO95HV-1^06246006.0017301 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000815 | 412620811-85222-DTLTRT-04_23_2026-GO95HV-1^668004/00 7/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000816 | 412937836-66181-DETAIL-04_24_2025-GO95TCH-1^06241006.0028100 | OTHER | HFTD Tier 2 | Distribution | 2025-04-24 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000817 | 413020278-80278-DTLSB-07_02_2025-GO95HV-1^06244007.0139100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000818 | 41302104-94179-DETAIL-08_27_2025-GRDRODHI-1^06247006.0170601 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000819 | 413277889-43459-DETAIL-07_28_2025-GO95HV-1^06247005.0199700 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000820 | 413319909-61929-DETAIL-04_28_2026-GO95HV-1^06142012.0149510 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000821 | 414447670-4270-DETAIL-02_19_2026-GO95HV-1^06239002.0018600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000822 | 18610300-4110-DTLSB-06_17_2026-GO95HV-1^07217001.0352800 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000823 | 186161171-10659-DTLSB-06_08_2026-GO95HV-1^07216001.0230203 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000824 | 186613545-91863-DTLSB-07_01_2025-GO95BLTC-1^06244006.0226314 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000825 | 186777436-25030-ADMIN-10_20_2025-GO95HV-1^06247001.0365100 | OTHER | Non-HFTD | Distribution | 2025-10-20 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000826 | 186894709-40210-DTLSB-07_29_2025-GO95MLD-1^07218001.0264300 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000827 | 186995335-26979-DETAIL-04_21_2025-GO95BLTC-1^06242006.0071600 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000828 | 187117726-20440-DETAIL-07_06_2026-GO95HV-1^07218001.0342700 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000829 | 187595776-45330-DETAIL-08_12_2025-ABNDEQPM-1^06246001.0197400 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000830 | 419328793-59793-DETAIL-08_06_2025-GO95HV-1^06247005.0192002 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000831 | 419678065-87663-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0097600 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000832 | 187834475-19475-DTLSB-07_01_2025-GO95HV-1^06244006.0226404 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000833 | 188034220-63189-ADMIN-10_23_2025-GO95HV-1^06246001.0110901 | OTHER | Non-HFTD | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000834 | 188158326-57470-DETAIL-01_22_2025-RISEHDWR-1^06239004.0255549 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000835 | 188211758-79529-DETAIL-04_20_2026-GO95HV-1^06142012.0143902 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000836 | 188288933-7630-DETAIL-09_09_2025-GO95HV-1^06147001.0202500 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000837 | 421282290-36290-DETAIL-06_11_2025-GUYHINS-1^06236005.0150102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000838 | 42138396-18280-DETAIL-01_13_2026-GO95MLD-1^06239004.0244805 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000839 | 421414023-90999-DETAIL-06_11_2025-GO95HV-1^06245007.0361701 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000840 | 421691346-96970-DETAIL-08_12_2025-GO95HV-1^06246001.0193400 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000841 | 421735913-17529-DETAIL-05_12_2025-GO95HV-1^06142012.0010903 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000842 | 421866783-76853-DETAIL-06_07_2023-CUSTWIRE-1^06244010.0270801 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000843 | 188553762-49419-DTLSB-07_09_2026-GO95HV-1^06240008.0149700 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000844 | 423906694-60353-DETAIL-09_23_2025-GUYHINS-1^07218001.0224600 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000845 | 42410316-80989-DETAIL-02_03_2025-GO95HV-1^06239004.0244943 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000846 | 424272879-38389-DETAIL-09_30_2025-ABNDEQPM-1^06246009.0136200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000847 | 424440229-56380-DETAIL-08_07_2025-GO95HV-1^06246002.0256900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000848 | 424846613-95353-DETAIL-09_22_2025-GO95CL10-1^07218001.0160001 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000849 | 425060670-94359-DETAIL-10_09_2025-GO95HV-1^06248003.0274300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000850 | 425255321-46280-DETAIL-09_11_2025-GRDRODHI-1^07216001.0079600 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000851 | 425399819-47139-DTLTRT-07_09_2025-GUYNOINS-1^668087/00 3/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000852 | 427506287-86287-DETAIL-07_30_2025-GO95HV-1^06247005.0027000 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000853 | 427586376-88376-DETAIL-05_29_2025-GO95HV-1^06148014.0360300 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000854 | 427634606-44170-DETAIL-01_16_2025-ABNDEQPM-1^06239004.0256201 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000855 | 427794962-51539-DTLTRT-06_30_2025-GUYNOINS-1^668087/00 9/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000856 | 427803074-40190-DETAIL-02_12_2026-GO95HV-1^06239003.0362701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000857 | 428220224-31790-DETAIL-02_25_2026-GO95BLTC-1^06239003.0245901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000858 | 42829428-77612-DETAIL-08_19_2025-CUSTWIRE-1^07216001.0174800 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000859 | 428360152-77430-DTLSB-07_31_2025-GO95HV-1^07218001.0273200 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000860 | 431200546-20180-DETAIL-08_11_2025-GO95HV-1^06246002.0090000 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000861 | 431368380-92559-DETAIL-08_06_2025-GO95HV-1^06247005.0209000 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000862 | 431680937-71448-DETAIL-01_15_2026-SVCROAD-1^06242009.0329900 | OTHER | Non-HFTD | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000863 | 431752854-36399-DETAIL-09_04_2025-GO95HV-1^06147001.0319100 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000864 | 431778506-9506-DETAIL-01_22_2026-GO95MLD-1^06239004.0232001 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000865 | 431894752-66450-DETAIL-02_06_2025-GO95MLD-1^06239004.0136209 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000866 | 432074163-34980-DETAIL-02_24_2026-CUSTWIRE-1^06239002.0070500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000867 | 432074163-34980-DETAIL-03_18_2025-ABNDEQPM-1^06239002.0070500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000868 | 190392115-9730-ADMIN-11_03_2025-SVCNEUT-1^06246001.0222801 | OTHER | Non-HFTD | Distribution | 2025-11-03 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000869 | 190419765-39679-DETAIL-08_25_2025-GUYLOINS-1^06246001.0174001 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000870 | 434350573-68080-DETAIL-04_30_2025-GO95TCH-1^06239002.0066804 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000871 | 434816831-12450-DETAIL-03_04_2026-GO95HV-1^06239003.0181800 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000872 | 43486223-31279-DETAIL-09_15_2025-GO95HV-1^06248007.0231300 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000873 | 435119919-12433-DETAIL-09_09_2025-GO95HV-1^07218001.0176201 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000874 | 435822144-71431-DETAIL-04_08_2025-SVCROAD-1^06241005.0012708 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000875 | 435995233-86659-DETAIL-07_29_2025-GO95HV-1^06247005.0212001 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000876 | 437836708-24190-DETAIL-01_28_2025-SVCROAD-1^06239004.0244414 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000877 | 437864686-32660-DETAIL-04_30_2026-GO95HV-1^668004/00 6/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000878 | 437929824-55129-DETAIL-04_19_2022-CUSTWIRE-2^06142012.0132815 | OTHER | Non-HFTD | Distribution | 2022-04-19 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000879 | 437947663-88239-DETAIL-11_17_2025-GO95HV-1^06243007.0019500 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000880 | 437995226-4789-ADMIN-10_22_2025-GO95TCH-1^06246011.0056701 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000881 | 438054198-32290-DTLTRT-06_24_2025-GO95HV-1^668087/00 11/003 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000882 | 438056618-32769-ADMIN-09_25_2025-XARMSPCR-1^668005/00 3/041 | CROSSARM | Non-HFTD | Transmission | 2025-09-25 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000883 | 441268593-98289-DTLSB-01_22_2026-SVCROAD-2^06242009.0297201 | OTHER | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000884 | 441691371-23250-DETAIL-01_21_2026-GO95MLD-1^06239004.0124903 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000885 | 441728951-47201-DTLTRT-05_12_2026-GO95HV-1^668004/00 3/010 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000886 | 441840818-1939-DTLSB-07_01_2025-GO95MLD-1^06244006.0224402 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000887 | 442316024-28024-DTLSB-07_03_2025-GO95HV-1^06244007.0133902 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000888 | 44245479-49752-DTLSB-07_21_2025-GO95HV-1^06244006.0308740 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000889 | 442852380-38743-DETAIL-06_29_2026-GO95HV-1^07217001.0157500 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000890 | 190812345-79640-DETAIL-02_26_2025-GO95CL10-1^06240004.0217800 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000891 | 444766550-2279-DETAIL-08_21_2025-GO95CL10-1^06246001.0309900 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000892 | 444899209-66801-DETAIL-09_30_2025-GO95MLD-1^06148001.0300109 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000893 | 444906808-86808-DETAIL-08_25_2025-GO95HV-1^07216001.0179700 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000894 | 444906808-86808-DETAIL-08_25_2025-GO95MLD-1^07216001.0179700 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000895 | 445102198-42198-ADMIN-10_30_2025-GO95BLTC-1^06246001.0030001 | OTHER | Non-HFTD | Distribution | 2025-10-30 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000896 | 445376466-40070-DETAIL-01_21_2025-GO95HV-1^06239004.0255304 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000897 | 445452261-78380-DETAIL-02_13_2025-SVCNEUT-1^06240004.0169103 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000898 | 445670743-63350-DETAIL-02_04_2025-GO95MLD-1^06239004.0134040 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000899 | 447494494-75822-DETAIL-10_16_2025-GO95BLTC-1^06246012.0137502 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000900 | 447782591-37073-DETAIL-09_10_2025-GO95HV-1^06246006.0185651 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000901 | 448376861-3459-DTLSB-05_28_2026-GO95HV-1^07216001.0022500 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000902 | 448846552-2903-DETAIL-05_05_2025-GO95HV-1^06243006.0348841 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000903 | 448849441-91850-DETAIL-03_04_2026-GO95HV-1^06239003.0186701 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000904 | 448948125-20329-DETAIL-05_30_2025-GRDRODHI-1^06147014.0120800 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000905 | 448948125-20329-DETAIL-05_30_2025-RISEBKSP-1^06147014.0120800 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000906 | 449006393-4159-DETAIL-08_18_2025-GO95HV-1^06247006.0366801 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000907 | 452978021-23143-DETAIL-07_07_2026-GO95MLD-1^07217001.0165100 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000908 | 453279113-79909-AUDIT-09_02_2025-XARMSPCR-2^06247006.0256100 | CROSSARM | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000909 | 453445388-29042-DETAIL-04_30_2025-GO95HV-1^06242006.0107301 | OTHER | Non-HFTD | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000910 | 45351060-1970-DETAIL-02_23_2026-GO95HV-1^06239002.0023500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000911 | 453618141-62539-DTLSB-05_28_2026-GO95HV-2^07216001.0022400 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000912 | 453618141-62539-DTLSB-05_28_2026-SVCDEFLC-1^07216001.0022400 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000913 | 454248183-28429-DETAIL-04_22_2026-GO95HV-1^06142012.0145600 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000914 | 45434833-57539-DETAIL-05_29_2025-GO95HV-1^06244006.0108000 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000915 | 456954831-86809-DETAIL-03_11_2024-CONDFRAY-1^06147004.0037600 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000916 | 456954831-86809-DETAIL-03_11_2024-CONDFRAY-3^06147004.0037600 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000917 | 457012849-69559-DETAIL-08_05_2025-GO95HV-1^06247005.0207500 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000918 | 457279706-11521-DETAIL-09_03_2025-GO95HV-1^06246001.0179400 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000919 | 457300913-76440-DTLTRT-05_29_2025-GO95HV-1^668075/00 12/008 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000920 | 45781490-97490-DETAIL-05_28_2025-GO95MLD-1^06244006.0095500 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000921 | 458119523-69523-DETAIL-06_04_2025-GUYHINS-1^668075/00 12/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000922 | 460633808-35808-DETAIL-09_24_2025-GO95HV-1^07218001.0225100 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000923 | 192603729-5869-ADMIN-07_09_2026-POLEDERP-1^668005/03 15/005 | POLE | Non-HFTD | Transmission | 2026-07-09 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000924 | 192688069-31930-DTLTRT-06_24_2025-GO95HV-1^668087/00 14/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000925 | 192688069-31930-DTLTRT-06_24_2025-GUYHINS-2^668087/00 14/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000926 | 192846481-56380-DETAIL-02_16_2026-GO95HV-1^06239001.0048801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000927 | 193023381-57639-DETAIL-05_07_2025-GO95HV-1^06243006.0352302 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000928 | 460647462-8450-DETAIL-02_06_2025-GO95MLD-1^06239004.0137201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000929 | 460719445-18670-DETAIL-01_23_2026-BIRDDMG-1^06240003.0184902 | POLE | HFTD Tier 2 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000930 | 463145278-26840-DETAIL-02_03_2026-CUSTWIRE-1^06239003.0018203 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000931 | 463189760-6489-DETAIL-07_30_2025-GO95HV-1^06247006.0204300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000932 | 46366624-70609-DETAIL-10_15_2025-GO95BLTC-1^06246011.0180600 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000933 | 463820323-31709-DETAIL-09_04_2025-GO95HV-1^06247006.0070401 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000934 | 463867648-45099-DETAIL-09_16_2025-GO95TCH-1^07216001.0085109 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000935 | 46390553-65940-DTLTRT-05_22_2024-GO95MLD-1^06243001.0103700 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000936 | 464312818-45679-ADMIN-10_23_2025-GO95HV-1^06246011.0367203 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000937 | 467788888-9888-DETAIL-08_28_2025-GO95HV-1^06247006.0178003 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000938 | 467788888-9888-DETAIL-08_28_2025-SVCDEFLC-1^06247006.0178003 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000939 | 467919889-6733-DETAIL-09_08_2025-GO95MLD-1^07218001.0176702 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000940 | 467960938-26343-DETAIL-04_12_2023-SVCROOF-1^06240004.0166509 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000941 | 468022970-42970-DETAIL-06_05_2025-GO95HV-1^06148014.0245403 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000942 | 468026754-58689-DETAIL-05_08_2025-GRDRODHI-1^06243006.0104400 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000943 | 468450320-20469-DTLSB-07_01_2025-GO95HV-1^06244007.0133401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000944 | 47146011-97011-DETAIL-09_18_2025-GO95MLD-1^07218001.0086505 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000945 | 472216851-78659-DETAIL-06_17_2024-CUSTWIRE-1^06246006.0239100 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000946 | 472653794-60894-DETAIL-03_30_2023-CUSTWIRE-1^06142016.0084909 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000947 | 472807014-48014-DETAIL-07_22_2025-GUYNOINS-1^06247005.0040502 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-22 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000948 | 472914575-92900-DETAIL-04_08_2026-GUYHINS-2^06240002.0315301 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-08 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000949 | 472914575-92900-DETAIL-05_05_2025-GRDRODHI-1^06240002.0315301 | OTHER | HFTD Tier 2 | Distribution | 2025-05-05 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000950 | 472973432-489-DTLSB-04_08_2026-BIRDDMG-1^06241009.0107402 | POLE | Non-HFTD | Distribution | 2026-04-08 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000951 | 474463806-5659-DETAIL-07_28_2025-GO95HV-1^06247005.0318201 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000952 | 474997264-62139-DETAIL-04_23_2026-GO95HV-1^06142012.0144000 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000953 | 475101536-96659-DETAIL-07_28_2025-GO95HV-1^06247005.0317301 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000954 | 475116165-97041-DTLSB-06_09_2026-GO95HV-1^07216001.0229500 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000955 | 475150983-88041-DTLTRT-05_13_2026-GO95HV-1^668085/00 5/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000956 | 475150983-92611-DTLTRT-05_13_2026-GO95HV-1^668085/00 5/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000957 | 475194463-84979-DETAIL-07_18_2024-CUSTWIRE-1^06244005.0019400 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000958 | 475734355-56200-DETAIL-02_25_2026-BIRDDMG-1^06239003.0242101 | POLE | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000959 | 478010443-39329-DETAIL-05_13_2025-GO95HV-1^06142012.0018601 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000960 | 478034605-96939-DTLSB-06_09_2026-CLRTOUCH-1^07216001.0225010 | CONDUCTOR | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000961 | 478100625-57551-DETAIL-02_19_2025-GO95HV-1^06239004.0365906 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000962 | 478162528-76279-DETAIL-09_03_2025-GO95HV-1^06247006.0296602 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000963 | 478363316-86441-DETAIL-09_03_2025-SVCROAD-1^06246001.0176203 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000964 | 478368681-88599-DETAIL-05_22_2025-GO95HV-1^06244006.0070800 | OTHER | HFTD Tier 2 | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000965 | 479196249-37389-DTLSB-06_30_2025-GO95BLTC-1^06244007.0035102 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000966 | 479359156-69619-ADMIN-01_14_2026-CUSTWIRE-1^668005/00 9/097 | OTHER | Non-HFTD | Transmission | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000967 | 481441571-18229-DETAIL-05_19_2025-GO95HV-1^06142012.0119500 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000968 | 481480959-11359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0332401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000969 | 481583115-14115-DETAIL-06_18_2025-GO95CL10-1^06248004.0310605 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000970 | 482443661-71980-DETAIL-02_18_2026-GO95HV-1^06239001.0068600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000971 | 482513970-82470-DETAIL-06_05_2025-GO95HV-1^668075/00 4/028 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000972 | 482513970-82470-DETAIL-06_05_2025-GO95MLD-1^668075/00 4/028 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000973 | 48312819-8173-DETAIL-01_21_2025-SVCDEFLC-1^06240004.0092403 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000974 | 484770333-37190-DETAIL-02_18_2026-GO95HV-1^06239002.0164900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000975 | 484984278-93039-DETAIL-04_22_2026-ANCHIDLE-1^06142012.0143700 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000976 | 485386798-87798-DETAIL-01_26_2026-COVCOTHR-1^06240003.0315401 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000977 | 485509549-50379-DETAIL-04_29_2025-GO95HV-1^06239002.0063504 | OTHER | HFTD Tier 2 | Distribution | 2025-04-29 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000978 | 194160638-60849-DETAIL-08_12_2024-CUSTWIRE-1^06245006.0157300 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000979 | 194951442-48183-DTLSB-06_10_2026-GO95HV-1^07216001.0235700 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000980 | 195066002-51989-DETAIL-05_12_2025-GUYHINS-1^06243006.0210100 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-12 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000981 | 195159262-5739-DETAIL-05_07_2025-GO95HV-1^06243006.0356901 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000982 | 486667065-37391-DETAIL-05_12_2026-GO95HV-1^668038/00 1/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000983 | 486815104-40659-DETAIL-07_28_2025-GO95HV-1^06247005.0301301 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000984 | 486949752-71279-ADMIN-10_22_2025-GRDRODHI-1^06246001.0024700 | OTHER | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000985 | 487210283-16469-DETAIL-07_29_2025-GO95HV-1^06247005.0216801 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000986 | 487365744-79240-DETAIL-02_26_2025-GUYHINS-1^06240004.0219843 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000987 | 488021480-49389-DETAIL-07_24_2025-GO95HV-1^06247005.0131300 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000988 | 488095003-58983-DETAIL-09_17_2025-ANCHIDLE-1^07218001.0088500 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000989 | 488112638-69640-DETAIL-03_02_2026-BIRDDMG-1^06239003.0136000 | POLE | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000990 | 490469561-75419-DTLSB-11_08_2021-SVCENTBK-1^06148004.0310103 | OTHER | Non-HFTD | Distribution | 2021-11-08 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000991 | 490519241-48623-DETAIL-06_18_2025-GO95HV-1^06248004.0342640 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000992 | 490558594-68690-DETAIL-02_12_2026-GO95HV-1^06239003.0364400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000993 | 490697526-75861-DETAIL-08_21_2025-GO95HV-1^07216001.0177300 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000994 | 491289986-72710-DETAIL-02_04_2026-SVCDEFLC-1^06239003.0018901 | OTHER | Non-HFTD | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000995 | 491406692-46559-DETAIL-04_29_2026-GO95HV-1^668004/00 5/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000996 | 491693560-34649-DTLSB-07_01_2025-GO95HV-1^06244007.0131402 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000997 | 492796201-78201-DTLSB-07_17_2025-GO95HV-1^06244006.0214600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120000998 | 492861944-49422-DETAIL-10_15_2025-SVCENTCO-1^06246011.0182702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120000999 | 493100109-81029-DETAIL-04_17_2025-GO95HV-1^06242006.0035501 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001000 | 493181985-5219-DETAIL-03_25_2024-CUSTWIRE-1^06147005.0120000 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001001 | 493185814-68940-DTLTRT-05_30_2025-GO95HV-1^668075/00 16/010 | OTHER | Non-HFTD | Transmission | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001002 | 493387078-75989-DETAIL-09_03_2025-GO95HV-1^06247006.0295601 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001003 | 493407370-8778-DETAIL-07_02_2026-GO95HV-1^07217001.0047701 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001004 | 493462578-6861-DTLTRT-05_06_2026-GO95HV-1^668038/00 6/056 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001005 | 496573788-23560-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 4/016 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001006 | 4965955-10160-DTLTRT-10_09_2023-CUSTWIRE-1^668010/00 15/037 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001007 | 49673202-2339-DETAIL-05_14_2025-GO95HV-1^06243006.0221103 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001008 | 496952921-78823-DETAIL-06_26_2026-GO95HV-1^07218001.0341001 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001009 | 497034088-80940-DETAIL-02_24_2026-BIRDDMG-1^06239003.0132000 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001010 | 497628749-13879-DETAIL-06_17_2025-SVCENTCO-1^06248004.0355103 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001011 | 497641172-55604-DETAIL-04_07_2025-GO95MLD-1^06241005.0115701 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001012 | 49805851-2250-DTLTRT-05_18_2026-BIRDDMG-1^668086/00 11/009 | POLE | Non-HFTD | Transmission | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001013 | 19727809-73210-DTLSB-07_28_2025-GO95HV-1^07218001.0264201 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001014 | 197353665-80129-DETAIL-04_22_2025-GO95HV-1^06242006.0055100 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001015 | 500521473-60458-DETAIL-07_02_2026-GO95HV-1^07217001.0049605 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001016 | 500521473-60458-DETAIL-07_02_2026-SVCROAD-1^07217001.0049605 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001017 | 500875396-54579-DETAIL-05_28_2025-GO95HV-1^06244006.0040001 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001018 | 500936573-54673-AUDIT-06_24_2024-ABNDEQPM-1^06145002.0065602 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001019 | 501029454-91609-DETAIL-09_10_2025-GO95HV-1^06246006.0079400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001020 | 504020846-62868-DETAIL-04_09_2025-GO95HV-1^06241005.0025602 | OTHER | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001021 | 50413766-44770-DETAIL-01_14_2025-GO95HV-1^06239004.0256110 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001022 | 504244476-10181-DTLSB-04_29_2026-GO95HV-1^06142013.0199400 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001023 | 504336698-24181-ADMIN-11_12_2025-GO95HV-1^06246001.0333000 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001024 | 504336698-24181-ADMIN-11_12_2025-GRDRODHI-1^06246001.0333000 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001025 | 504507611-90281-DETAIL-05_14_2025-GO95HV-1^06142012.0119704 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001026 | 504577184-23281-DETAIL-06_10_2026-GUYHINS-1^668086/00 6/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001027 | 504676268-91739-DETAIL-07_30_2024-CUSTWIRE-1^06244005.0355200 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001028 | 50726436-29750-DTLSB-04_29_2026-GO95HV-1^06142013.0212201 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001029 | 507931523-68579-DTLSB-01_22_2026-GRDRODHI-1^06242009.0297205 | OTHER | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001030 | 508107241-18241-DETAIL-07_03_2024-CUSTWIRE-1^06244005.0235903 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001031 | 508259578-92481-DTLSB-05_06_2026-GO95HV-1^06142013.0275000 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001032 | 508362090-9940-DETAIL-03_31_2026-COVCOTHR-1^06239003.0063100 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001033 | 508510436-58389-DETAIL-08_04_2025-GO95HV-1^06246001.0180000 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001034 | 508515924-2581-DETAIL-09_05_2025-GO95HV-1^06147001.0292000 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001035 | 508532372-47850-AUDIT-05_06_2025-SVCROAD-1^06239003.0016105 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001036 | 510383331-85143-DETAIL-07_07_2026-CUTOUTAR-2^07217001.0166700 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001037 | 510383331-85143-DETAIL-07_07_2026-GO95MLD-1^07217001.0166700 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001038 | 510567261-76929-DTLSB-03_30_2026-SVCROOF-1^06241009.0052900 | OTHER | Non-HFTD | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001039 | 510617062-16191-DTLTRT-06_30_2025-GO95HV-1^668087/00 7/014 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001040 | 510617062-16191-DTLTRT-06_30_2025-GUYNOINS-1^668087/00 7/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001041 | 510988531-13543-DETAIL-07_06_2026-DISTHDWR-1^07217001.0162600 | CONNECTION DEVICE | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001042 | 511214908-30591-DETAIL-04_20_2026-GO95HV-1^06142012.0146905 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001043 | 511280078-67069-DETAIL-09_17_2025-GO95HV-1^06248007.0363500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001044 | 514611958-39389-DTLSB-06_30_2025-GO95HV-1^06244006.0227500 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001045 | 514723588-81179-DETAIL-08_13_2025-GO95HV-1^06246002.0359200 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001046 | 514723588-81179-DETAIL-08_13_2025-GUYHINS-1^06246002.0359200 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001047 | 514858944-5532-DETAIL-04_07_2025-GO95BLTC-1^06241005.0119204 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001048 | 514987888-19491-DETAIL-08_25_2025-GO95HV-1^06246001.0205902 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001049 | 515253021-75691-DETAIL-09_10_2025-GO95HV-1^06147001.0073100 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001050 | 515473601-38250-DETAIL-01_21_2026-GO95MLD-1^06239004.0124902 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001051 | 515473601-38250-DETAIL-02_11_2025-GO95TCH-1^06239004.0124902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001052 | 518343826-80990-DETAIL-03_31_2026-GO95MLD-1^06240004.0351602 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001053 | 518545835-28689-AUDIT-06_17_2026-CLMBHAZ-1^06242009.0280104 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001054 | 518861436-30659-DETAIL-04_29_2026-GO95HV-1^668004/00 2/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001055 | 519079272-74559-DETAIL-04_29_2026-GO95HV-1^668004/00 1/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001056 | 51944679-80933-DTLSB-06_17_2026-GO95HV-1^07217001.0347904 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001057 | 519495024-30760-DETAIL-01_15_2025-SVCDEFLC-1^06240004.0095203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001058 | 519663815-90139-DETAIL-09_23_2025-GO95HV-1^06247004.0180600 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001059 | 519719726-70273-DTLSB-06_11_2026-GO95HV-1^07217001.0277002 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001060 | 522614776-10401-DTLSB-05_05_2026-GO95HV-1^06142013.0178500 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001061 | 522699875-49663-DETAIL-06_26_2026-GO95HV-1^07217001.0097701 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001062 | 522774062-92139-DETAIL-05_20_2025-GO95HV-1^06243006.0068203 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001063 | 523051005-61005-DTLTRT-06_30_2025-GUYLOINS-1^668087/01 6/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001064 | 523051005-61005-DTLTRT-06_30_2025-GUYLOINS-2^668087/01 6/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001065 | 52311634-16279-DETAIL-05_21_2025-ABNDEQPM-1^06243006.0108100 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001066 | 52311634-16279-DETAIL-05_21_2025-GO95BLTC-1^06243006.0108100 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001067 | 523373518-6866-DETAIL-09_17_2025-GO95MLD-1^07218001.0055203 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001068 | 525401719-74999-AUDIT-07_28_2025-BIRDDMG-1^06244007.0038108 | POLE | HFTD Tier 2 | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001069 | 19788031-69679-DETAIL-08_19_2025-CLRTOUCH-1^06246001.0319000 | CONDUCTOR | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001070 | 19788031-69679-DETAIL-08_19_2025-SVCROAD-1^06246001.0319000 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001071 | 197920210-71634-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 5/013 | POLE | Non-HFTD | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001072 | 19812788-11840-DTLTRT-06_23_2025-GO95BLTC-1^668087/00 5XA/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001073 | 19812788-11840-DTLTRT-06_23_2025-GO95CL10-1^668087/00 5XA/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001074 | 525487746-97746-DETAIL-01_22_2026-GO95MLD-1^06239004.0233000 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001075 | 527621870-3061-DETAIL-04_10_2025-GO95HV-1^06241005.0094901 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001076 | 527638291-76970-DETAIL-02_19_2025-GO95TCH-1^06241005.0275800 | OTHER | HFTD Tier 3 | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001077 | 527725975-74209-DETAIL-08_13_2025-GO95HV-1^06247006.0262503 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001078 | 527975274-69683-DETAIL-09_10_2025-GO95HV-1^06246006.0077052 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001079 | 528080565-4509-DETAIL-08_27_2025-GO95HV-1^06247006.0188601 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001080 | 528179438-68960-DTLTRT-05_04_2026-GO95HV-1^668004/00 3/021 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001081 | 528189395-53110-DETAIL-02_26_2026-COVCOTHR-1^06238004.0114202 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001082 | 531367959-98543-DETAIL-07_22_2025-BIRDDMG-1^06247005.0058601 | POLE | Non-HFTD | Distribution | 2025-07-22 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001083 | 531467774-68509-DETAIL-09_10_2025-GO95HV-1^06246006.0076000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001084 | 531486873-66821-DETAIL-09_08_2025-GO95HV-1^06147001.0170300 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001085 | 532419197-53889-DETAIL-06_09_2025-GO95HV-1^06245006.0300602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001086 | 532441904-17859-DTLTRT-04_22_2026-GO95MLD-1^668004/02 9/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001087 | 532520353-84709-DETAIL-09_04_2025-GO95HV-1^06247006.0071702 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001088 | 53254493-89930-DETAIL-02_27_2025-GO95HV-1^06240004.0066006 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001089 | 532700293-86721-DETAIL-09_09_2025-GO95HV-1^06147001.0199500 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001090 | 53436564-27689-DTLSB-01_27_2026-GO95MLD-1^06242009.0056205 | OTHER | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001091 | 534482965-91663-DETAIL-06_26_2026-ENCHRW-1^07217001.0048300 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001092 | 534655448-81850-DETAIL-04_22_2025-GO95HV-1^06240003.0057800 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001093 | 535205985-76909-DETAIL-08_13_2025-GO95HV-1^06247006.0254601 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001094 | 535507115-44570-DETAIL-04_29_2025-GO95HV-1^06239002.0064201 | OTHER | HFTD Tier 2 | Distribution | 2025-04-29 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001095 | 535548719-79719-DETAIL-03_04_2025-GO95TCH-1^06240004.0150001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001096 | 535737258-51809-DETAIL-08_26_2025-GO95HV-1^06247006.0299800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001097 | 535868404-90959-DETAIL-09_02_2025-GO95HV-1^07216001.0161901 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001098 | 538745628-87730-DETAIL-01_22_2025-SVCDEFLC-1^06240004.0089602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001099 | 538895450-28469-DETAIL-06_11_2024-CUSTWIRE-1^06245007.0342602 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001100 | 539009539-29083-DETAIL-08_21_2025-SVCDEFLC-1^07216001.0175904 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001101 | 539172184-58810-DETAIL-03_13_2025-GO95BLTC-1^06238004.0150200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001102 | 539327723-15939-DTLTRT-05_13_2026-GO95HV-1^668085/00 2/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001103 | 53939858-28773-DETAIL-09_22_2025-BIRDDMG-1^06248007.0368400 | POLE | HFTD Tier 2 | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001104 | 53939858-28773-DETAIL-09_22_2025-GO95HV-1^06248007.0368400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001105 | 541397535-84449-DTLSB-07_09_2025-GO95HV-1^06244006.0346500 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001106 | 541397736-27470-DRONE_HY-07_10_2026-COVCOTHR-1^06239004.0255245 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-10 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001107 | 541477417-19417-DETAIL-06_18_2025-GUYHINS-1^668075/00 13X2/046 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001108 | 541477417-19417-DETAIL-06_18_2025-GUYHINS-2^668075/00 13X2/046 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001109 | 541613543-20463-DTLTRT-08_05_2025-GUYHINS-1^668087/00 4/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001110 | 541754153-52831-DETAIL-09_05_2025-GO95HV-1^06147001.0204400 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001111 | 541994214-61289-DETAIL-05_28_2025-CUSTWIRE-1^06244006.0091100 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001112 | 542143232-53232-DETAIL-08_13_2025-GUYHINS-1^06246002.0362501 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001113 | 545548993-81089-DETAIL-08_06_2025-SVCDEFLC-1^06247006.0200200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001114 | 545592635-8059-DTLSB-06_05_2026-GO95HV-1^07216001.0228801 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001115 | 545885342-20239-DETAIL-05_19_2025-GO95HV-1^06243006.0229000 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001116 | 546075161-32280-DETAIL-02_16_2026-GO95HV-1^06239001.0045701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001117 | 546491123-34005-DRONE_HY-09_27_2023-GO95HV-1^668033/00 5X1/003 | OTHER | Non-HFTD | Transmission | 2023-09-27 | 2028-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001118 | 546500469-74049-AUDIT-10_14_2025-SVCROAD-1^07216001.0097104 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001119 | 546653776-86759-DETAIL-04_30_2026-GO95HV-1^668004/00 3/018 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001120 | 546653776-86760-DETAIL-04_30_2026-GO95HV-1^668004/00 3/018 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001121 | 549674418-7541-DETAIL-04_21_2026-GO95HV-1^06142012.0146701 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001122 | 549682474-73849-DETAIL-08_26_2025-GO95HV-1^07216001.0160801 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001123 | 549696724-60679-DTLTRT-10_02_2023-CUSTWIRE-1^668010/00 7/034 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001124 | 198889506-56180-DETAIL-01_23_2025-GO95HV-1^06239004.0256745 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001125 | 198940166-47449-DTLSB-07_09_2025-GO95HV-1^06244006.0276601 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001126 | 199011024-31361-ADMIN-10_07_2025-COVCOTHR-1^06242005.0149000 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001127 | 199390434-43422-ADMIN-10_21_2025-SVCENTCO-1^06246012.0056703 | OTHER | HFTD Tier 2 | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001128 | 551696824-54089-DETAIL-09_04_2025-GO95HV-1^06247006.0187501 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001129 | 55176550-4979-DETAIL-10_15_2025-CONDFRAY-1^06148001.0348200 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001130 | 552197915-66772-DETAIL-06_06_2023-CUSTWIRE-1^06244010.0343500 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001131 | 552393480-77509-DETAIL-08_25_2021-CUSTWIRE-1^06148004.0353508 | OTHER | Non-HFTD | Distribution | 2021-08-25 | 2024-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001132 | 552688936-97593-DETAIL-07_29_2025-GO95HV-1^06247005.0260302 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001133 | 552932883-73330-DTLSB-07_31_2025-GO95TCH-1^07218001.0274406 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001134 | 553155956-57599-DETAIL-07_30_2025-GO95HV-1^06247005.0311101 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001135 | 554964643-86253-DETAIL-09_04_2025-GO95HV-1^06247006.0073102 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001136 | 555001763-33189-DETAIL-08_12_2025-SVCROAD-1^06247006.0251201 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001137 | 555336706-42851-DTLSB-04_29_2026-GO95HV-1^06142013.0210201 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001138 | 555532085-20653-DTLSB-06_10_2026-GO95HV-1^07217001.0350001 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001139 | 555532085-20653-DTLSB-06_10_2026-GO95TCH-1^07217001.0350001 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001140 | 555733922-9460-DETAIL-04_29_2026-GO95HV-1^668004/00 2/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001141 | 555751663-62579-DETAIL-06_03_2025-GO95HV-1^06245007.0367901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001142 | 555755266-59193-DETAIL-09_16_2025-GO95HV-1^07218001.0055703 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001143 | 557997135-53599-DETAIL-08_20_2025-SVCDEFLC-1^06247006.0256002 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001144 | 55818265-80849-DTLSB-07_14_2025-GRDRODHI-1^06244007.0146700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001145 | 558597681-5851-DTLTRT-05_18_2026-GO95HV-1^668086/00 5/007 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001146 | 558953990-69770-DETAIL-02_12_2025-RISEGRD-1^06240004.0167501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001147 | 558953990-69770-DETAIL-04_12_2023-SVCROOF-1^06240004.0167501 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001148 | 559283642-30520-DETAIL-03_30_2026-SVCTREE-1^06240004.0272040 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001149 | 559283642-30520-DETAIL-03_30_2026-SVCTREE-2^06240004.0272040 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001150 | 562640208-25359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0328400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001151 | 562677624-64689-DETAIL-08_14_2025-GO95HV-1^06247006.0251001 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001152 | 562731998-91709-ADMIN-10_20_2025-SVCENTBK-1^06246012.0118300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001153 | 56322279-87810-DTLSB-06_11_2026-GO95HV-1^07217001.0354504 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001154 | 563469101-23861-DETAIL-09_11_2025-GO95HV-1^06147001.0082500 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001155 | 563524699-44861-AUDIT-08_19_2025-ABNDEQPM-1^06246002.0269901 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001156 | 563853524-15913-DTLSB-05_02_2024-CUSTWIRE-1^06245007.0228743 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001157 | 199618358-44449-DTLSB-08_12_2025-GO95MLD-1^07217001.0028100 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001158 | 199631601-68611-DETAIL-01_15_2025-GO95HV-1^06239004.0255241 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001159 | 199840841-29189-DTLSB-07_17_2025-GO95HV-1^06244006.0217402 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001160 | 199992778-27709-DETAIL-09_03_2025-GO95HV-1^06247006.0295500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001161 | 200071134-7339-DETAIL-10_06_2025-GO95HV-1^06243007.0366700 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001162 | 566820475-65439-DTLTRT-06_26_2025-GO95CL10-1^668087/00 9/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001163 | 566820475-65439-DTLTRT-06_26_2025-SVCROAD-1^668087/00 9/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001164 | 56706378-68270-DETAIL-02_14_2025-GO95HV-1^06240004.0169401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001165 | 569559016-35553-DTLSB-06_10_2026-CUSTWIRE-1^07217001.0350100 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001166 | 569571476-28871-DETAIL-08_04_2025-GO95HV-1^06246001.0185003 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001167 | 569578333-97249-DTLSB-06_30_2025-GO95HV-1^06244007.0105240 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001168 | 569595071-67599-DETAIL-05_22_2025-GO95HV-1^06244006.0070902 | OTHER | HFTD Tier 2 | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001169 | 569855791-66649-ADMIN-10_22_2025-GUYSLACK-1^07216001.0101300 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001170 | 570133731-24499-DTLSB-10_16_2025-GRDRODHI-1^06247001.0348000 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001171 | 57024853-16853-DETAIL-08_20_2025-GO95HV-1^06247006.0369003 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001172 | 570279628-97440-DETAIL-03_05_2026-COVCOTHR-1^06238004.0146800 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001173 | 57322131-66280-DETAIL-02_16_2026-GO95HV-1^06239001.0059702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001174 | 573514551-3419-DTLSB-05_04_2026-GO95HV-1^06241009.0035400 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001175 | 573801043-90729-DTLSB-01_21_2026-GRDRODHI-1^06242009.0298109 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001176 | 574100988-23550-DETAIL-04_22_2025-GO95HV-1^06240003.0053201 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001177 | 574190015-98309-DETAIL-08_21_2025-GO95HV-1^06247006.0263801 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001178 | 574388489-10330-DETAIL-03_17_2026-COVCOTHR-2^06240004.0218906 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001179 | 574388489-10330-DETAIL-03_17_2026-COVCOTHR-3^06240004.0218906 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001180 | 574765528-53869-DTLSB-07_03_2025-GO95HV-1^06245007.0358842 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001181 | 575913676-75519-ADMIN-05_30_2017-CUSTWIRE-1^07116007.0166200 | OTHER | HFTD Tier 2 | Distribution | 2017-05-30 | 2020-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001182 | 576814958-28281-DETAIL-09_09_2025-GO95HV-1^06146001.0048000 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001183 | 576959001-80970-DETAIL-02_17_2026-GO95HV-1^06239002.0091700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001184 | 577106400-54089-DETAIL-10_14_2025-GO95HV-1^06148001.0343400 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001185 | 577396250-32870-DETAIL-02_12_2025-SVCDEFLC-1^06240004.0166504 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001186 | 577452443-2264-DTLSB-06_08_2026-GO95HV-1^07216001.0232201 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001187 | 577732553-82553-DETAIL-06_17_2025-GO95MLD-1^668075/00 21/043 | OTHER | HFTD Tier 2 | Transmission | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001188 | 581803193-12351-DETAIL-05_13_2025-GO95TCH-1^06242004.0310800 | OTHER | HFTD Tier 2 | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001189 | 581836469-38152-ADMIN-12_29_2025-COVCOTHR-2^06241005.0027242 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-12-29 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001190 | 581955948-64089-DETAIL-08_07_2025-GO95HV-1^06246002.0252900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001191 | 582048158-46881-DETAIL-10_01_2025-GO95CL10-1^06148001.0302005 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001192 | 582048158-46881-DETAIL-10_01_2025-GO95HV-1^06148001.0302005 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001193 | 582076058-44981-DTLTRT-06_24_2025-BIRDDMG-1^668087/00 4/004 | POLE | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001194 | 582257082-99880-DRONE_HY-07_02_2026-COVCOTHR-1^06240004.0169110 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001195 | 201679119-25579-DETAIL-07_24_2024-CUSTWIRE-1^06244004.0192600 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001196 | 583829014-61319-DTLSB-01_28_2026-POLETOP-1^06242009.0055700 | POLE | HFTD Tier 2 | Distribution | 2026-01-28 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001197 | 583874283-96213-DETAIL-07_15_2025-GO95HV-1^06244006.0286200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001198 | 584151570-1332-DETAIL-04_02_2025-GO95MLD-1^06241005.0117602 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001199 | 584267211-39043-DETAIL-07_01_2026-GO95HV-1^07217001.0168500 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001200 | 584267211-39043-DETAIL-07_01_2026-SVCNEUT-1^07217001.0168500 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001201 | 58436746-46746-DETAIL-01_22_2026-GO95MLD-1^06239004.0265902 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001202 | 586080006-25776-DETAIL-09_27_2021-CUSTWIRE-1^06148004.0356112 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001203 | 586080006-25776-DETAIL-09_27_2021-CUSTWIRE-2^06148004.0356112 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001204 | 58616859-94489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0174000 | POLE | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001205 | 586320079-82389-DTLSB-06_29_2022-CUSTWIRE-1^06243005.0130500 | OTHER | HFTD Tier 2 | Distribution | 2022-06-29 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001206 | 586412073-39189-DETAIL-03_05_2024-CUSTWIRE-1^06245007.0277300 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001207 | 586451468-76623-DETAIL-05_27_2026-GO95HV-1^07217001.0145000 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001208 | 588790106-52180-DETAIL-03_30_2021-CUSTWIRE-1^06239004.0244600 | OTHER | HFTD Tier 2 | Distribution | 2021-03-30 | 2024-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001209 | 588979463-96819-DTLSB-05_11_2026-GO95HV-1^06242009.0279900 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001210 | 589020933-30909-DETAIL-09_29_2025-GO95HV-1^06246009.0111202 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001211 | 589070791-3791-DETAIL-09_24_2025-GO95MLD-1^07218001.0223300 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001212 | 201706666-56240-DETAIL-05_19_2025-GO95HV-1^06243006.0277400 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001213 | 201714994-72360-DETAIL-01_16_2025-GO95TCH-1^06239004.0256210 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001214 | 201785008-95969-ADMIN-10_23_2025-CUSTWIRE-1^06246011.0366240 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001215 | 590352471-20050-DETAIL-03_04_2026-GO95HV-1^06239003.0183800 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001216 | 590787203-58249-DTLSB-06_30_2025-GO95HV-1^06244007.0105341 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001217 | 590789734-78362-DETAIL-04_16_2025-SVCROAD-2^06242005.0362240 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001218 | 590789734-78362-DETAIL-04_16_2025-SVCROAD-3^06242005.0362240 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001219 | 590849041-92899-ADMIN-11_13_2025-GO95CLSV-1^06246010.0133602 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001220 | 591198803-44249-DTLSB-07_21_2025-GO95HV-2^06244006.0256900 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001221 | 591247421-99173-DETAIL-09_23_2025-GO95HV-1^06248007.0279701 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001222 | 591251336-73189-DETAIL-08_13_2025-GO95HV-1^06247006.0263500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001223 | 594155691-39002-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 3/002 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001224 | 594382313-92599-DTLSB-03_09_2026-GO95MLD-1^06242009.0175900 | OTHER | Non-HFTD | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001225 | 594392013-27401-DETAIL-02_14_2023-CUSTWIRE-1^06247002.0214601 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001226 | 594461793-77740-DTLTRT-05_29_2025-GO95HV-1^668075/00 6/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001227 | 594487628-98628-DETAIL-06_05_2025-GO95HV-1^06148014.0245500 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001228 | 594586635-37132-DTLSB-07_10_2025-GO95HV-1^06244006.0342302 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001229 | 594695593-58380-DETAIL-02_18_2026-GO95HV-1^06239002.0169402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001230 | 599613633-14633-DETAIL-09_29_2025-GO95HV-1^06148001.0317302 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001231 | 599642919-79852-DETAIL-04_02_2025-LIGHT-1^06241005.0029001 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001232 | 599665842-80088-DETAIL-11_17_2025-GO95MLD-1^06243007.0024900 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001233 | 600254317-1417-DETAIL-07_30_2025-GO95HV-1^06247005.0025000 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001234 | 600255571-38543-DETAIL-07_07_2026-GRDRODHI-1^07217001.0165501 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001235 | 600304387-49938-DETAIL-09_23_2025-SVCENTCO-1^07218001.0233003 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001236 | 600326224-72790-DETAIL-02_12_2026-GO95HV-1^06239003.0255902 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001237 | 600495815-85953-DTLSB-06_10_2026-SVCDEFLC-1^07217001.0350102 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001238 | 602307411-18911-DTLTRT-05_19_2026-GO95HV-1^668086/00 4/010 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001239 | 602535529-37559-DETAIL-08_05_2025-GO95HV-1^06247005.0208201 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001240 | 602806776-37776-DETAIL-06_02_2025-GO95HV-1^06148014.0362701 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001241 | 602887059-7433-DETAIL-09_10_2025-GO95HV-1^07218001.0179101 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001242 | 602981943-86083-DETAIL-08_04_2025-GO95HV-1^06247006.0207542 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001243 | 60317101-42370-DTLTRT-05_19_2026-BIRDDMG-1^668086/00 2/010 | POLE | Non-HFTD | Transmission | 2026-05-19 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001244 | 603278401-19119-ADMIN-11_13_2025-GO95HV-1^06246010.0134600 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001245 | 60365763-27330-DTLSB-07_29_2025-GO95HV-1^07218001.0264707 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001246 | 606535698-92502-DETAIL-03_06_2025-GUYNOINS-3^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001247 | 606535698-92502-DETAIL-03_06_2025-GUYNOINS-4^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001248 | 606686036-77149-DETAIL-02_28_2024-GO95MLD-1^07113002.0180500 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001249 | 606796110-94033-DTLSB-06_18_2026-GO95HV-1^07217001.0347700 | OTHER | Non-HFTD | Distribution | 2026-06-18 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001250 | 607362348-80119-DTLSB-03_31_2026-SVCTREE-1^06241009.0326602 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001251 | 607382919-48670-DETAIL-02_26_2025-GO95TCH-1^06240004.0060401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001252 | 607674594-3590-DETAIL-03_02_2026-GO95HV-1^06239003.0252700 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001253 | 608035931-88621-DETAIL-04_09_2024-POLISSUE-1^06147005.0255000 | POLE | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001254 | 608173096-37209-DETAIL-08_12_2025-GO95HV-1^06247006.0265000 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001255 | 608203665-82353-DTLSB-06_10_2026-CLMBTRE-1^07217001.0351500 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001256 | 608203665-82353-DTLSB-06_10_2026-GO95MLD-1^07217001.0351500 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001257 | 608962114-98199-DTLSB-01_26_2026-SVCROAD-1^06242009.0298407 | OTHER | Non-HFTD | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001258 | 609441028-41721-DTLSB-04_30_2026-GO95HV-1^06142013.0174601 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001259 | 609729205-67921-DTLSB-06_09_2026-SVCROAD-1^07216001.0224002 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001260 | 609749653-66719-DTLSB-03_25_2026-GO95HV-1^06242009.0038500 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001261 | 612074702-47199-DETAIL-03_15_2022-CUSTWIRE-1^06148006.0348200 | OTHER | Non-HFTD | Distribution | 2022-03-15 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001262 | 612189796-25809-DETAIL-09_08_2025-GO95HV-1^06247007.0016100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001263 | 612470366-5429-DTLSB-08_10_2023-CUSTWIRE-1^06243009.0262000 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001264 | 61265233-85233-DETAIL-06_11_2025-GUYHINS-1^668075/00 5/036 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001265 | 61265233-85233-DETAIL-06_11_2025-GUYHINS-2^668075/00 5/036 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001266 | 61265233-85233-DETAIL-06_11_2025-GUYHINS-4^668075/00 5/036 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001267 | 612811891-19070-DTLTRT-05_12_2026-GO95HV-1^668004/00 6/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001268 | 614103603-80039-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0267900 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001269 | 614121718-54640-DETAIL-02_09_2026-GO95HV-1^06239003.0018005 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001270 | 614154391-44920-DETAIL-03_30_2026-GRDRODHI-2^06240004.0271004 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001271 | 614246914-86129-DETAIL-04_21_2026-SVCENTBK-1^06142012.0149805 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001272 | 614322412-18621-DETAIL-05_14_2024-CUSTWIRE-1^06142012.0123400 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001273 | 614447879-11721-DETAIL-09_04_2025-GO95HV-1^06146001.0083800 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001274 | 614508174-9034-DETAIL-05_01_2024-CUSTWIRE-1^06143015.0339900 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001275 | 617097071-50809-DETAIL-10_08_2025-GO95HV-1^06246008.0066500 | OTHER | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001276 | 617310567-60531-ADMIN-12_04_2025-REGDMGL-1^06246001.0252400 | REGULATOR | Non-HFTD | Distribution | 2025-12-04 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001277 | 617362132-20099-DETAIL-06_18_2025-ABNDEQPM-1^06248004.0310700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001278 | 617416538-92770-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0039200 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001279 | 617728546-35359-DTLTRT-05_07_2026-GO95MLD-1^668004/00 2/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001280 | 617837143-52231-DETAIL-10_21_2024-GUYNOINS-1^07216001.0209301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001281 | 617837143-52231-DETAIL-10_21_2024-GUYNOINS-2^07216001.0209301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001282 | 619042170-70922-DTLTRT-04_27_2026-GO95HV-1^668004/00 9/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001283 | 619042170-9631-DTLTRT-04_27_2026-GO95HV-1^668004/00 9/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001284 | 619042454-69799-DETAIL-08_12_2025-GO95HV-1^06247006.0252400 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001285 | 619693687-22470-DETAIL-06_12_2025-GO95HV-1^06236005.0023000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-12 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001286 | 619774665-1559-DETAIL-06_18_2025-SVCENTCO-1^06248004.0287201 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001287 | 619882842-3842-DETAIL-03_04_2026-BIRDDMG-1^06239003.0189420 | POLE | HFTD Tier 3 | Distribution | 2026-03-04 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001288 | 619985204-77790-DETAIL-02_25_2026-GO95HV-1^06238003.0018900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001289 | 62007168-17623-DETAIL-05_26_2026-GO95HV-1^07217001.0146300 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001290 | 623366074-98100-DETAIL-04_29_2025-SVCENTCO-1^06239002.0063502 | OTHER | Non-HFTD | Distribution | 2025-04-29 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001291 | 62359968-80889-ADMIN-03_20_2024-GO95STUB-1^06245002.0124301 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001292 | 623713673-24402-ADMIN-04_06_2026-POLEREPL-1^668067/00 6/008 | POLE | Non-HFTD | Transmission | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001293 | 623713673-65402-ADMIN-04_06_2026-POLEREPL-1^668067/00 6/008 | POLE | Non-HFTD | Transmission | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001294 | 623873794-24794-DETAIL-04_23_2026-SVCDEFLC-1^06142012.0145808 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001295 | 623952363-2839-DETAIL-07_18_2024-CUSTWIRE-1^06244005.0019401 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001296 | 623978090-59692-DETAIL-05_05_2025-GO95HV-1^06243006.0289041 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001297 | 626490219-64270-DETAIL-04_14_2026-GUYHINS-1^06236005.0154300 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-14 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001298 | 626842984-3290-DETAIL-02_05_2026-GO95HV-1^06239003.0019616 | OTHER | Non-HFTD | Distribution | 2026-02-05 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001299 | 626980312-80250-DETAIL-03_19_2025-SVCROAD-1^06238004.0028640 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001300 | 627270353-65889-DTLSB-05_12_2026-GO95HV-1^06242009.0270600 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001301 | 204965338-73019-DTLSB-03_23_2026-SVCDEFLC-1^06242009.0067704 | OTHER | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001302 | 205010606-22863-DETAIL-07_07_2026-SVCENTBK-1^07217001.0218700 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001303 | 20527669-15340-DETAIL-08_12_2025-GO95HV-1^06246002.0259204 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001304 | 205818365-72749-ADMIN-03_04_2025-POLEDERP-1^07216001.0295406 | POLE | Non-HFTD | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001305 | 628654179-11829-DETAIL-04_24_2025-GRDRODHI-1^06242006.0091100 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001306 | 628983865-5051-DRONE_HY-07_02_2026-POLESTEP-1^06239004.0366709 | POLE | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001307 | 629542373-5359-DTLTRT-04_22_2026-GO95HV-1^668004/02 16/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001308 | 629627230-96241-DTLSB-05_29_2026-GO95HV-1^07216001.0020702 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001309 | 629969071-53839-DTLSB-07_14_2025-GO95TCH-1^06244006.0219701 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001310 | 630513901-21499-DETAIL-10_02_2025-GUYHINS-1^06246008.0066600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001311 | 630513901-21499-DETAIL-10_02_2025-GUYHINS-2^06246008.0066600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001312 | 630705616-83510-DETAIL-02_26_2026-COVCOTHR-2^06238004.0118301 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001313 | 633411058-23352-DTLSB-07_02_2025-GO95HV-1^06244006.0227900 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001314 | 633509740-70151-DETAIL-08_21_2025-GO95HV-1^06246001.0308200 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001315 | 634284811-4653-DETAIL-09_22_2025-GO95HV-1^06247006.0063600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001316 | 634293368-26368-DTLSB-08_14_2025-GO95HV-1^07218001.0356902 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001317 | 634426509-22739-DTLTRT-06_24_2025-GO95MLD-1^668087/00 11/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001318 | 634426509-22739-DTLTRT-06_24_2025-SVCROAD-1^668087/00 11/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001319 | 634714543-12263-DTLTRT-08_05_2025-GO95HV-1^668087/00 5/012 | OTHER | Non-HFTD | Transmission | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001320 | 634714543-12263-DTLTRT-08_05_2025-GRDRODHI-1^668087/00 5/012 | OTHER | Non-HFTD | Transmission | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001321 | 637417081-81251-DTLSB-10_16_2025-GO95MLD-1^06247001.0345501 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001322 | 638016087-73409-DETAIL-06_09_2025-GO95HV-1^06245006.0300501 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001323 | 638122633-18239-DETAIL-11_17_2025-GO95HV-1^06243007.0019700 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001324 | 638318470-21398-DETAIL-06_09_2026-GUYHINS-1^668086/00 7/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001325 | 638447472-35950-DETAIL-02_26_2026-GO95TCH-1^06238004.0027241 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001326 | 638530575-7039-ADMIN-04_09_2025-POLEDERP-1^07216001.0295500 | POLE | Non-HFTD | Distribution | 2025-04-09 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001327 | 638665385-36385-DETAIL-09_02_2025-GO95HV-1^06246001.0201902 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001328 | 638842691-15129-DETAIL-05_14_2025-GO95HV-1^06142012.0115800 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001329 | 640681061-68479-DETAIL-09_29_2025-GO95HV-1^06148001.0317401 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001330 | 640683624-81240-DETAIL-03_23_2026-GO95MLD-1^06240004.0218940 | OTHER | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001331 | 640729108-74549-DTLSB-07_16_2025-GO95HV-1^06244006.0317502 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001332 | 64101309-55309-DETAIL-03_21_2024-CONDFRAY-1^06147004.0113900 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001333 | 641147831-11843-DTLSB-06_02_2026-GO95HV-1^07216001.0116601 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001334 | 641194583-58929-ADMIN-12_23_2024-POLEREPL-1^06142012.0133708 | POLE | Non-HFTD | Distribution | 2024-12-23 | 2027-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001335 | 641398006-99890-DETAIL-03_31_2026-GO95MLD-1^06240004.0350600 | OTHER | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001336 | 644409120-12170-DETAIL-01_30_2025-SVCROAD-1^06240004.0165600 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001337 | 645454882-1559-DETAIL-07_30_2025-XARMSPCR-1^06247005.0179801 | CROSSARM | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001338 | 645544607-46959-DTLSB-08_18_2025-GO95MLD-1^07218001.0354602 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001339 | 645789273-62769-DTLSB-08_21_2023-CUSTWIRE-1^06243009.0286900 | OTHER | Non-HFTD | Distribution | 2023-08-21 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001340 | 646141391-6320-DETAIL-03_25_2025-COVCOTHR-1^06240004.0273402 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001341 | 646218859-32633-DTLTRT-06_18_2026-GUYHINS-1^07217001.0348401 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-18 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001342 | 646343520-91389-DETAIL-10_14_2025-GO95HV-1^06148001.0275000 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001343 | 648352758-12271-DETAIL-09_09_2025-GO95HV-1^06146001.0045100 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001344 | 649378183-52509-DETAIL-09_10_2025-GO95HV-1^06246007.0133250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001345 | 649453174-78541-DETAIL-04_10_2025-GO95TCH-1^06241005.0058103 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001346 | 649592819-9759-DETAIL-06_16_2025-GO95HV-1^06248005.0330340 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001347 | 649861903-8009-DETAIL-08_12_2025-GO95HV-1^06247006.0250101 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001348 | 64990980-37439-DETAIL-08_20_2025-GO95HV-1^07216001.0172005 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001349 | 649922531-23399-DETAIL-05_06_2025-GO95HV-1^06243006.0335701 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001350 | 653046147-62719-DTLSB-07_08_2026-GO95HV-1^06242009.0269801 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001351 | 653155566-88300-AUDIT-03_04_2026-ABNDEQPM-1^06239003.0017900 | OTHER | Non-HFTD | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001352 | 653155566-88300-DETAIL-02_09_2026-GO95HV-1^06239003.0017900 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001353 | 653274373-96249-DTLSB-07_16_2025-GO95HV-1^06244006.0251900 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001354 | 653283744-95253-DETAIL-09_22_2025-GO95HV-1^07218001.0218902 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001355 | 653514723-97991-ADMIN-11_14_2025-GO95HV-1^06246001.0124803 | OTHER | Non-HFTD | Distribution | 2025-11-14 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001356 | 653749919-37799-DTLSB-07_02_2025-GO95HV-1^06244006.0224100 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001357 | 653987219-80299-DTLSB-02_03_2026-BIRDDMG-1^06243009.0307401 | POLE | HFTD Tier 2 | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001358 | 655468920-30791-DETAIL-09_29_2025-GO95HV-1^06148001.0312701 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001359 | 65554459-58409-DETAIL-09_30_2025-ABNDEQPM-1^06246009.0132301 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001360 | 655621092-6989-DETAIL-07_22_2025-GO95HV-1^06247005.0175401 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001361 | 655805283-38490-DETAIL-04_20_2023-CUSTWIRE-1^06240004.0176202 | OTHER | HFTD Tier 2 | Distribution | 2023-04-20 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001362 | 655805283-38490-DRONE_HY-06_19_2026-LIGHT-1^06240004.0176202 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001363 | 655806114-55891-DETAIL-09_05_2025-GRDRODHI-1^06147001.0309101 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001364 | 655809472-239-DETAIL-05_06_2025-GO95HV-1^06243006.0067900 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001365 | 658730364-59719-DTLSB-04_16_2026-GO95HV-1^06241009.0137101 | OTHER | Non-HFTD | Distribution | 2026-04-16 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001366 | 659045923-54779-DETAIL-09_29_2025-GO95HV-1^06246009.0112100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001367 | 659121503-48359-DTLTRT-04_20_2026-GO95HV-1^668004/02 6/002 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001368 | 659708225-33633-DETAIL-09_23_2025-GO95HV-1^06247004.0077541 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001369 | 659919450-39701-DETAIL-02_24_2025-GO95HV-1^06241005.0158000 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001370 | 660098146-66659-DTLTRT-04_30_2026-GO95HV-1^668004/00 2/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001371 | 660105400-15401-DETAIL-02_24_2025-SVCDEFLC-1^06241005.0158100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001372 | 660312440-85139-DTLTRT-07_09_2025-GUYNOINS-2^668087/00 1/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001373 | 207862500-96740-DETAIL-02_11_2026-GO95MLD-1^06239002.0070404 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001374 | 208042346-95089-DETAIL-05_08_2025-GO95HV-1^06243006.0104602 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001375 | 208136231-93940-DTLTRT-05_20_2026-GO95HV-1^668086/00 1/011 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001376 | 661141494-21340-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 10/043 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001377 | 66133888-88380-DETAIL-03_08_2022-CUSTWIRE-1^06146006.0214402 | OTHER | Non-HFTD | Distribution | 2022-03-08 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001378 | 662215278-30873-DETAIL-09_17_2025-GO95HV-1^06248007.0367200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001379 | 662247349-76209-DETAIL-01_31_2022-CUSTWIRE-1^06147005.0262600 | OTHER | Non-HFTD | Distribution | 2022-01-31 | 2025-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001380 | 665083769-63913-DETAIL-08_26_2025-GO95HV-1^06247006.0287200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001381 | 665195444-89444-DETAIL-04_25_2024-CUSTWIRE-1^06142016.0174800 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001382 | 665334038-23121-DTLSB-05_06_2026-GO95HV-1^06142013.0289802 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001383 | 665432448-35623-DETAIL-05_22_2026-GO95HV-1^07217001.0145302 | OTHER | Non-HFTD | Distribution | 2026-05-22 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001384 | 665448866-90039-DETAIL-05_20_2025-GO95HV-1^06243006.0091301 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001385 | 665456231-17689-DTLSB-01_21_2026-GO95HV-1^06242009.0298107 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001386 | 665536366-81759-DETAIL-07_30_2025-GO95HV-1^06247005.0310000 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001387 | 665990126-98470-DETAIL-01_14_2026-SVCTREE-1^06239004.0134001 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001388 | 668437822-7983-DETAIL-08_21_2025-GO95HV-1^07216001.0176203 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001389 | 668814508-1491-DTLTRT-05_06_2026-BIRDDMG-1^668038/00 4/057 | POLE | HFTD Tier 2 | Transmission | 2026-05-06 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001390 | 668822661-27131-DTLTRT-04_28_2026-GO95HV-1^668004/00 2/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001391 | 208681173-66850-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0134101 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001392 | 208741826-90580-DETAIL-01_12_2026-ENCHRW-1^06239004.0244501 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001393 | 209492004-16899-DETAIL-06_16_2025-GO95HV-1^06248005.0369601 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001394 | 209526578-47709-DETAIL-09_03_2025-GO95HV-1^06247006.0295501 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001395 | 209602318-91459-DETAIL-06_03_2024-CUSTWIRE-1^06246005.0319900 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001396 | 6731388-72388-DETAIL-09_24_2025-GO95HV-1^07218001.0225200 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001397 | 673344589-60069-DTLTRT-06_14_2021-GO95HV-1^668041/00 12/019 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001398 | 673399151-29141-DETAIL-10_01_2025-GO95HV-1^06148001.0301102 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001399 | 673674354-78723-DETAIL-05_06_2025-SVCROAD-1^06243006.0032504 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001400 | 673724298-47790-AUDIT-02_25_2025-GUYHINS-1^06239004.0246042 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001401 | 673890824-31824-DTLSB-02_02_2026-GUYHINS-1^06243009.0297630 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001402 | 673896013-72729-DTLSB-01_20_2026-GO95HV-1^06242009.0298203 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001403 | 674064181-75963-DTLSB-04_17_2024-SVCROAD-1^06245007.0223344 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001404 | 677415223-4799-DETAIL-05_28_2025-GO95HV-1^06244006.0090701 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001405 | 677981904-89124-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135201 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001406 | 678148400-30733-DETAIL-07_01_2026-ENCHRW-1^07217001.0151500 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120001407 | 678431141-82419-DTLSB-05_04_2026-BIRDDMG-1^06241009.0034401 | POLE | Non-HFTD | Distribution | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001408 | 678475926-77259-DETAIL-09_17_2025-GO95HV-1^06247007.0019700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001409 | 6789790-11219-DETAIL-08_13_2025-GO95HV-1^06246001.0300901 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001410 | 679019061-1630-DTLTRT-05_28_2025-GO95HV-1^668075/00 12/007 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001411 | 681574488-87861-DTLSB-06_02_2026-GO95HV-1^07216001.0116903 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001412 | 682034958-26099-DTLSB-02_04_2026-GO95HV-1^06243009.0322302 | OTHER | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001413 | 682039664-71559-DETAIL-08_27_2025-GO95HV-1^07216001.0165403 | OTHER | Non-HFTD | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001414 | 682100564-4653-DETAIL-09_11_2025-GO95HV-1^06248007.0232600 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001415 | 68268729-84049-DTLSB-07_07_2025-GO95MLD-1^06244007.0039105 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001416 | 68310381-14983-DTLTRT-06_05_2026-GUYHINS-1^07216001.0231802 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001417 | 683397010-46070-DETAIL-04_19_2023-CUSTWIRE-1^06240004.0166501 | OTHER | HFTD Tier 2 | Distribution | 2023-04-19 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001418 | 686090020-28068-DTLSB-07_08_2025-GO95HV-1^06245007.0352100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001419 | 686386144-4953-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0097500 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001420 | 686406121-73750-DETAIL-04_06_2026-GO95HV-1^06237005.0356101 | OTHER | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001421 | 686446436-81699-DETAIL-10_12_2021-ENCHRW-1^06148005.0322903 | OTHER | Non-HFTD | Distribution | 2021-10-12 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001422 | 686599204-4959-DETAIL-03_18_2024-CUSTWIRE-1^06246005.0081201 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001423 | 686928273-1741-DETAIL-05_13_2025-GUYHINS-1^06242004.0310603 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001424 | 687124432-84419-DTLSB-07_09_2026-GO95HV-1^06240008.0140200 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001425 | 689197734-29660-DETAIL-02_02_2026-GO95HV-1^06239002.0060700 | OTHER | Non-HFTD | Distribution | 2026-02-02 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001426 | 68927318-41019-DTLSB-04_02_2026-GO95HV-1^06241009.0281700 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001427 | 689438569-90129-DETAIL-05_14_2025-GO95HV-1^06142012.0117400 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001428 | 689571075-82319-ADMIN-11_13_2025-GO95HV-1^06247008.0302701 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001429 | 690203644-47953-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0047000 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001430 | 690349089-90581-DETAIL-05_02_2024-CUSTWIRE-1^06142012.0126201 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001431 | 690386433-72541-DETAIL-09_11_2025-GO95HV-1^06147001.0079803 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001432 | 693330194-85240-DTLTRT-06_02_2025-GO95HV-1^668075/00 5A/012 | OTHER | Non-HFTD | Transmission | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001433 | 693612621-28591-DTLTRT-04_23_2026-BIRDDMG-1^668004/00 5/002 | POLE | HFTD Tier 2 | Transmission | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001434 | 693713793-83830-DTLSB-08_11_2025-GO95HV-1^07218001.0276700 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001435 | 693734360-16722-DTLTRT-04_27_2026-GO95HV-1^668004/00 8/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001436 | 693734360-80091-DTLTRT-04_27_2026-GO95HV-1^668004/00 8/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001437 | 693759264-60959-DTLTRT-04_22_2026-GO95MLD-1^668004/02 16/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001438 | 693964554-33539-DETAIL-05_28_2025-GO95HV-1^06244006.0102900 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001439 | 69423134-90-DETAIL-02_03_2026-CLMBTRE-1^06239003.0018418 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001440 | 696831988-76540-DETAIL-03_20_2025-SVCROAD-1^06239003.0018105 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001441 | 69690215-36190-DETAIL-03_10_2022-CUSTWIRE-1^06147006.0272201 | OTHER | Non-HFTD | Distribution | 2022-03-10 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001442 | 69690215-36190-DETAIL-03_10_2022-CUSTWIRE-2^06147006.0272201 | OTHER | Non-HFTD | Distribution | 2022-03-10 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001443 | 210379354-90740-DETAIL-03_25_2026-COVCOTHR-2^06240004.0218601 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001444 | 210636573-31121-DETAIL-06_17_2025-ABNDEQPM-1^06237005.0249402 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001445 | 210973622-34689-DETAIL-08_25_2025-GO95HV-1^06247006.0211002 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001446 | 211169071-24380-DETAIL-02_18_2026-GO95HV-1^06239002.0049400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001447 | 698931754-81754-DETAIL-09_11_2025-BIRDDMG-1^06248007.0156040 | POLE | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001448 | 698998563-86511-DETAIL-05_23_2024-GO95HV-1^06243001.0122000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001449 | 699004814-87159-DETAIL-08_21_2024-CUSTWIRE-1^06246005.0269641 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001450 | 699141496-82659-DETAIL-04_30_2026-GO95HV-1^668004/00 7/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001451 | 699147011-20430-DTLTRT-05_28_2025-GO95HV-1^668075/00 11/005 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001452 | 699368096-82079-DTLSB-03_16_2026-GO95HV-1^06242009.0135001 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001453 | 699538123-10939-DETAIL-05_06_2025-GO95HV-1^06243006.0049202 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001454 | 705511286-41031-DTLSB-10_16_2025-GO95STUB-1^06247001.0355001 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001455 | 705511286-41031-DTLSB-10_16_2025-GRDRODHI-1^06247001.0355001 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001456 | 705745328-4331-DTLTRT-05_07_2026-BIRDDMG-1^668038/00 2/056 | POLE | HFTD Tier 2 | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001457 | 705754501-64331-DETAIL-09_11_2025-GO95HV-1^06147001.0052500 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001458 | 705917656-10652-DETAIL-04_21_2025-GO95HV-1^06242005.0369804 | OTHER | HFTD Tier 2 | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001459 | 705999990-38670-DETAIL-02_04_2025-SVCDEFLC-1^06240004.0165708 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001460 | 706608743-78743-DETAIL-06_16_2025-COVCOTHR-1^668075/00 9/041 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001461 | 706608743-78743-DETAIL-06_16_2025-GUYHINS-1^668075/00 9/041 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001462 | 707738818-77182-DTLTRT-07_01_2025-POLEDERP-1^668087/00 2/017 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001463 | 707738818-88182-DTLTRT-07_01_2025-GUYNOINS-1^668087/00 2/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001464 | 707738818-88182-DTLTRT-07_01_2025-GUYNOINS-4^668087/00 2/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001465 | 707823019-3059-DTLTRT-05_06_2026-GO95HV-1^668004/00 1/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001466 | 707823019-3060-DTLTRT-05_06_2026-GO95HV-1^668004/00 1/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001467 | 708056185-36410-DETAIL-03_12_2025-GO95HV-1^06238004.0223501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001468 | 708081266-19241-DETAIL-05_11_2026-GO95HV-1^668038/00 1/049 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001469 | 708578652-7659-DETAIL-06_18_2025-GO95HV-1^06248004.0310602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001470 | 711802361-11170-DTLTRT-05_12_2026-GO95HV-1^668004/00 4/010 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001471 | 711802804-96779-DTLSB-11_01_2021-CUSTWIRE-1^06148004.0232606 | OTHER | Non-HFTD | Distribution | 2021-11-01 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001472 | 712109807-37579-DETAIL-04_09_2024-GO95STUB-1^06147005.0217003 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001473 | 712212309-88049-DTLSB-07_08_2025-SVCENTCO-1^06244007.0036401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001474 | 712236059-69799-DETAIL-09_09_2025-GRDRODHI-1^06246007.0141151 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001475 | 712395606-81419-DTLSB-03_24_2026-GO95MLD-1^06242009.0028402 | OTHER | Non-HFTD | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001476 | 712524415-9233-DETAIL-07_22_2025-GO95HV-1^06247005.0091601 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001477 | 712625619-83099-DETAIL-01_12_2026-COVCOTHR-1^06239004.0243400 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001478 | 714032839-43669-DTLTRT-06_09_2021-GO95HV-1^668041/00 8/014 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001479 | 714140195-26349-DETAIL-02_27_2024-GO95MLD-1^07113002.0184503 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001480 | 714140195-26349-DETAIL-02_27_2024-GRDRODHI-1^07113002.0184503 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001481 | 714259501-44439-DETAIL-06_25_2025-GO95HV-1^668087/00 6/008 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001482 | 714543501-66230-DETAIL-03_04_2025-GO95CL10-1^06240004.0151303 | OTHER | HFTD Tier 3 | Distribution | 2025-03-04 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001483 | 714543501-66230-DETAIL-03_04_2025-GUYHINS-1^06240004.0151303 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001484 | 714543501-66230-DETAIL-03_17_2026-SVCROAD-1^06240004.0151303 | OTHER | HFTD Tier 3 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001485 | 71635613-95519-DTLSB-04_23_2026-GO95HV-1^06241009.0224400 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001486 | 71652830-93170-DETAIL-02_12_2025-GO95MLD-1^06240004.0166507 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001487 | 716615831-12369-DETAIL-09_22_2025-GO95HV-1^06247006.0066800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001488 | 717002249-50279-DETAIL-08_19_2025-GRDRODHI-1^06246002.0368400 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001489 | 717002249-50279-DETAIL-08_19_2025-GRDRODHI-2^06246002.0368400 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001490 | 717035083-19909-DETAIL-08_13_2025-GO95HV-1^06247006.0259400 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001491 | 71704846-99659-DETAIL-07_28_2025-BIRDDMG-1^06247005.0315204 | POLE | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001492 | 717263666-93049-DETAIL-04_24_2025-GO95HV-1^06242006.0173401 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001493 | 72013148-1089-DTLSB-07_21_2025-GO95BLTC-1^06244006.0308400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001494 | 72013148-1089-DTLSB-07_21_2025-GO95HV-1^06244006.0308400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001495 | 720314234-29230-DETAIL-06_10_2025-GO95HV-1^06236005.0333504 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001496 | 720559478-27671-DTLTRT-06_23_2025-GO95HV-1^668087/00 5/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001497 | 720766155-36789-ADMIN-06_09_2026-POLEREPL-1^06148004.0207400 | POLE | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001498 | 720777351-4391-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | Non-HFTD | Transmission | 2024-04-10 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001499 | 721777424-16609-DETAIL-08_27_2025-GO95HV-1^06247006.0174600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001500 | 722035805-16442-DETAIL-03_05_2025-GO95BLTC-1^06241005.0121202 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001501 | 726598258-89291-DTLSB-05_16_2024-GO95HV-1^06244002.0201400 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001502 | 726615618-73443-DETAIL-09_17_2025-GO95TCH-1^07218001.0055101 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001503 | 726615618-73443-DETAIL-09_17_2025-GUYHINS-1^07218001.0055101 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001504 | 726927344-94522-DETAIL-04_07_2025-SVCRUBLG-1^06241005.0027005 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001505 | 727016078-13139-DETAIL-05_07_2025-GRDRODHI-1^06243005.0061800 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001506 | 727400328-18649-DETAIL-06_04_2025-GO95HV-1^06245006.0207000 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001507 | 727425543-48789-DETAIL-06_10_2025-ABNDEQPM-1^06245006.0197600 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001508 | 728471818-85640-DETAIL-03_02_2026-GO95HV-1^06239003.0137101 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001509 | 731211621-97569-DETAIL-03_21_2024-CUSTWIRE-1^06245007.0281300 | OTHER | HFTD Tier 2 | Distribution | 2024-03-21 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001510 | 731238996-49970-DETAIL-01_23_2025-GO95MLD-1^06239004.0256646 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001511 | 731613710-44401-DETAIL-08_12_2025-GO95HV-1^06246001.0301200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001512 | 731855478-8738-DETAIL-06_09_2025-GO95HV-1^06245007.0244401 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001513 | 732259061-1950-DRONE_HY-06_19_2026-SVCDEFLC-1^06238004.0271643 | OTHER | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001514 | 732259061-1950-DRONE_HY-06_19_2026-SVCTREE-1^06238004.0271643 | OTHER | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001515 | 732479580-41601-DETAIL-01_14_2026-BIRDDMG-1^06239004.0135103 | POLE | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001516 | 735377289-30538-DTLSB-08_12_2025-GRDRODHI-1^07217001.0012003 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001517 | 736199466-97093-DETAIL-08_18_2025-GO95HV-1^06247006.0365301 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001518 | 736467651-88401-DETAIL-01_15_2026-BIRDDMG-1^06239004.0135146 | POLE | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001519 | 736763050-40840-DETAIL-01_22_2026-COVCOTHR-1^06239003.0071907 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001520 | 736763050-40840-DETAIL-01_22_2026-COVCOTHR-2^06239003.0071907 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001521 | 736974548-6548-DETAIL-05_08_2024-GO95MLD-1^06142012.0120402 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001522 | 737671153-54699-DETAIL-08_06_2025-ENCHSVCE-1^06247005.0301902 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001523 | 737878760-54570-DETAIL-02_18_2026-GO95HV-1^06239002.0045402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001524 | 740587141-86330-DETAIL-03_16_2026-GUYHINS-1^06240004.0154402 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001525 | 741474376-65163-DETAIL-06_25_2026-GO95HV-1^07217001.0038601 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001526 | 74179165-61719-DTLSB-05_05_2026-GO95HV-1^06241009.0141600 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001527 | 741876355-1079-DETAIL-10_08_2025-GO95BLTC-1^06148001.0202600 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001528 | 741921693-7309-DETAIL-06_05_2025-GO95HV-1^06245006.0190201 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001529 | 742315004-45004-DETAIL-06_10_2026-GUYHINS-1^668086/00 13X/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001530 | 742616408-52459-DETAIL-06_03_2024-CUSTWIRE-1^06246005.0319902 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001531 | 742665746-75746-DETAIL-01_22_2026-GO95MLD-1^06239004.0265900 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001532 | 745126965-67965-DETAIL-05_29_2025-GO95HV-1^06147014.0014901 | OTHER | HFTD Tier 2 | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001533 | 745358513-34180-DETAIL-02_03_2025-SVCDEFLC-1^06240004.0164900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001534 | 745375364-26364-DETAIL-04_07_2025-GO95HV-1^06241005.0027010 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001535 | 745510936-50299-DTLSB-07_15_2025-GO95BLTC-1^06244006.0271802 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001536 | 745510936-50299-DTLSB-07_15_2025-GO95HV-1^06244006.0271802 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001537 | 745510936-50299-DTLSB-07_15_2025-GUYHINS-1^06244006.0271802 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-15 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001538 | 745608796-5889-DETAIL-11_18_2025-ANCHIDLE-1^06247008.0315300 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-11-18 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001539 | 745900346-28059-DTLSB-05_29_2026-GO95HV-1^07216001.0114702 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001540 | 748981126-48759-DTLTRT-05_04_2026-GO95HV-1^668004/00 6/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001541 | 749357409-62951-DETAIL-10_01_2025-GO95HV-1^06148001.0302106 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001542 | 749407195-18195-DETAIL-05_05_2025-GO95HV-1^06243006.0288204 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001543 | 749429711-19739-DTLTRT-06_25_2025-SVCSVC-1^668087/00 2/008 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001544 | 749542738-1251-DTLSB-07_09_2025-GO95HV-1^06244007.0155800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001545 | 749798393-48609-DETAIL-08_27_2025-GO95HV-1^06247006.0080001 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001546 | 749830688-10730-DETAIL-01_22_2026-GO95MLD-1^06240003.0305201 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001547 | 750483076-98770-DETAIL-01_24_2025-GO95HV-1^06239004.0258842 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001548 | 212649425-7489-DETAIL-06_17_2025-GO95HV-1^06248004.0283103 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001549 | 213462805-38539-DETAIL-07_05_2024-CUSTWIRE-1^06244004.0197001 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001550 | 213479395-82750-DETAIL-05_19_2025-XARMSPCR-1^06142012.0112500 | CROSSARM | Non-HFTD | Distribution | 2025-05-19 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001551 | 213884473-16541-DETAIL-05_13_2025-SVCENTBK-1^06242004.0310902 | OTHER | HFTD Tier 2 | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001552 | 214019768-47179-DTLTRT-10_17_2023-GO95STUB-1^668010/00 16X/009 | OTHER | Non-HFTD | Transmission | 2023-10-17 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001553 | 214150811-12979-DETAIL-10_15_2025-CLRTOUCH-1^06148001.0308800 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001554 | 214650089-24382-DTLTRT-07_09_2025-GO95HV-1^668087/00 1/021 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001555 | 753334229-79233-DETAIL-09_10_2025-SVCENTBK-1^07218001.0173402 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001556 | 753631355-11033-DETAIL-09_16_2025-GO95HV-1^06247004.0088740 | OTHER | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001557 | 75394003-45900-DTLSB-05_29_2026-GO95HV-1^07216001.0023500 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001558 | 754119371-18680-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0168306 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001559 | 754203042-64149-DTLSB-07_16_2025-GO95HV-1^06244006.0231401 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001560 | 754472418-74902-DETAIL-03_06_2025-GO95TCH-1^06241005.0120200 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001561 | 754601623-91721-DETAIL-04_15_2026-SVCTREE-2^06237004.0206500 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001562 | 756833715-72800-DETAIL-04_08_2026-GO95HV-1^06240002.0312203 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001563 | 75700118-91200-ADMIN-11_12_2025-GO95HV-1^06246001.0335000 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001564 | 75707209-12200-DETAIL-08_13_2025-GO95HV-1^06246002.0362900 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001565 | 758029101-8643-DETAIL-07_07_2026-GUYNOINS-1^07217001.0165800 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001566 | 758077674-9353-DETAIL-08_27_2025-GO95HV-1^06247006.0179300 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001567 | 758129348-57949-DTLSB-06_25_2025-GO95HV-1^06244007.0035801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001568 | 758210884-61959-DTLTRT-04_22_2026-GO95HV-1^668004/02 2/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001569 | 758210884-61959-DTLTRT-04_22_2026-GO95MLD-1^668004/02 2/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001570 | 760579149-75459-DETAIL-06_16_2025-GO95HV-1^06248004.0357342 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001571 | 760659161-29439-DTLTRT-06_26_2025-GO95CLSV-1^668087/00 6X/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001572 | 760873570-25270-DETAIL-02_19_2026-GO95HV-1^06239002.0019601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001573 | 216290895-20250-DETAIL-08_26_2025-GO95HV-1^06246001.0174303 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001574 | 217264259-17750-DETAIL-05_02_2024-CUSTWIRE-1^06142012.0127202 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001575 | 217323961-61150-DETAIL-03_04_2026-GO95HV-1^06239003.0186600 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001576 | 217326361-40643-DETAIL-07_07_2026-GO95HV-1^07217001.0165400 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001577 | 217680717-31479-DETAIL-08_04_2025-GO95HV-1^06246002.0139700 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001578 | 762813069-16061-DTLTRT-05_06_2026-GO95HV-1^668004/00 7/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001579 | 762842044-61191-DETAIL-04_18_2022-CUSTWIRE-1^06142012.0134802 | OTHER | Non-HFTD | Distribution | 2022-04-18 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001580 | 763042636-96981-ADMIN-05_09_2025-SVCTREE-1^06241006.0116800 | OTHER | HFTD Tier 2 | Distribution | 2025-05-09 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001581 | 763053677-99491-DTLTRT-06_23_2025-GO95MLD-1^668087/00 14/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001582 | 763074510-1380-DETAIL-09_04_2025-GO95HV-1^06247006.0217000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001583 | 763103512-99691-DETAIL-05_29_2025-GO95HV-1^06147014.0010100 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001584 | 763184464-45099-DETAIL-09_11_2025-GO95HV-1^06248007.0156001 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001585 | 764741982-15149-DTLSB-07_21_2025-GO95HV-1^06244006.0230800 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001586 | 76517324-59722-ADMIN-11_10_2025-GO95BLTC-1^06246012.0129900 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001587 | 765395252-67943-DETAIL-09_24_2025-GO95HV-1^07218001.0237002 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001588 | 765689148-94350-DETAIL-02_11_2026-BIRDDMG-1^06239003.0016201 | POLE | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001589 | 765702606-64991-DTLTRT-07_03_2025-GO95HV-1^668087/00 8/011 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001590 | 765930986-56450-DETAIL-09_15_2025-GRDRODHI-1^07219001.0334301 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001591 | 765957400-50929-DETAIL-06_04_2025-GO95HV-1^06142012.0107402 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001592 | 766129603-59020-DETAIL-02_26_2025-SVCDEFLC-1^06241005.0360700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001593 | 769060325-32609-DETAIL-08_28_2025-GO95HV-1^06247006.0195902 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001594 | 769068611-36970-DETAIL-02_17_2026-GO95HV-1^06239002.0091602 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001595 | 769131993-13860-DTLTRT-06_30_2025-GO95HV-1^668087/00 13/013 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001596 | 769131993-13860-DTLTRT-06_30_2025-GUYNOINS-3^668087/00 13/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001597 | 769545503-43980-DETAIL-03_31_2026-COVCOTHR-1^06240004.0355404 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001598 | 769572498-98141-DETAIL-03_06_2025-GO95BLTC-1^06241005.0164900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001599 | 769980726-29953-DTLSB-06_16_2026-GO95HV-1^07217001.0356902 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001600 | 770140856-76681-DETAIL-05_29_2025-GO95HV-1^06148014.0357001 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001601 | 772091334-64309-DETAIL-07_30_2025-GO95HV-1^06247006.0202301 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001602 | 772492913-53913-DETAIL-09_08_2025-GO95HV-1^06147001.0322302 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001603 | 217713411-77173-DETAIL-09_16_2025-GO95HV-1^07218001.0043600 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001604 | 217900266-79950-DTLTRT-05_07_2026-GO95HV-1^668038/00 2/055 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001605 | 217909319-27169-AUDIT-06_16_2025-GO95HV-1^06245007.0264000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001606 | 217919076-57349-DTLSB-07_14_2025-GO95HV-1^06244006.0272503 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001607 | 217970212-56589-DETAIL-05_07_2025-GO95HV-1^06243006.0352200 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001608 | 772718281-11801-DETAIL-01_14_2025-SVCENTBK-1^06239004.0257342 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001609 | 77562409-68530-DTLTRT-05_22_2025-GO95HV-1^668075/00 10/003 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001610 | 776101788-79122-DETAIL-09_09_2025-GO95HV-1^06146001.0093800 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001611 | 776348368-66630-DETAIL-01_26_2026-POLEREPL-1^06240003.0304302 | POLE | HFTD Tier 3 | Distribution | 2026-01-26 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001612 | 776944352-66139-DETAIL-05_20_2025-GO95HV-1^06243006.0067301 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001613 | 777034475-46532-ADMIN-10_20_2025-GO95TCH-1^06246012.0117500 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001614 | 777224164-65622-DTLTRT-06_30_2025-GO95HV-1^668087/02 6/001 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001615 | 777276726-72479-DETAIL-01_24_2023-COPLLEAN-1^06148004.0182101 | POLE | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001616 | 780032870-49570-DETAIL-02_17_2026-GO95HV-1^06239002.0092300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001617 | 780371883-45699-DETAIL-05_30_2025-GO95HV-1^06244006.0091403 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001618 | 780458670-23270-DETAIL-02_25_2026-GO95HV-1^06238003.0019900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001619 | 780575662-12080-DETAIL-02_25_2025-GO95TCH-1^06240005.0018300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001620 | 780948823-69132-DETAIL-02_16_2023-ABNDEQPM-1^06247002.0165400 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001621 | 781907248-12209-DETAIL-09_29_2025-GO95HV-1^06246009.0105600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001622 | 782671556-36369-DETAIL-04_24_2025-GO95HV-1^06242006.0193300 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001623 | 785271553-12553-DETAIL-06_17_2025-COVCOTHR-1^668075/00 18/043 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001624 | 785271553-12553-DETAIL-06_17_2025-GUYHINS-1^668075/00 18/043 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001625 | 785559325-15800-DETAIL-04_08_2026-GO95HV-1^06240002.0311202 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001626 | 785746678-65739-DETAIL-05_08_2025-GO95HV-1^06243006.0105600 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001627 | 785765993-58439-DETAIL-06_10_2026-GO95TCH-1^668086/00 11/012 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001628 | 786046193-5952-DTLSB-05_23_2024-GO95HV-1^06243001.0125001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001629 | 786046193-5952-DTLSB-05_23_2024-GO95MLD-1^06243001.0125001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001630 | 788697986-14276-DETAIL-09_09_2021-CUSTWIRE-1^06148004.0355108 | OTHER | Non-HFTD | Distribution | 2021-09-09 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001631 | 788946925-98000-DETAIL-03_25_2025-GO95HV-1^06239003.0019508 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001632 | 788951793-3793-DETAIL-04_29_2024-SVCROAD-1^06142016.0068000 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001633 | 789006078-85440-DETAIL-04_22_2025-GO95HV-1^06240003.0077202 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001634 | 789418826-22000-DETAIL-02_05_2026-SVCDEFLC-2^06239003.0017700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001635 | 789582811-14680-DETAIL-01_23_2026-GO95HV-1^06240004.0139401 | OTHER | HFTD Tier 2 | Distribution | 2026-01-23 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001636 | 790073384-27253-DETAIL-06_26_2026-GO95HV-1^07217001.0047002 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001637 | 792643528-62172-DETAIL-08_21_2025-GO95HV-1^06246001.0204303 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001638 | 792785276-28269-DTLSB-08_24_2023-CUSTWIRE-1^06243009.0117801 | OTHER | Non-HFTD | Distribution | 2023-08-24 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001639 | 792932033-82033-DETAIL-06_09_2025-GO95MLD-1^668075/00 7/029 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001640 | 793078606-31479-DTLSB-07_15_2025-GO95HV-1^06244006.0270200 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001641 | 793327204-34360-ADMIN-01_16_2025-GO95TCH-1^06239004.0256209 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001642 | 793578676-78579-DTLSB-10_16_2025-GO95MLD-1^06247001.0354001 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001643 | 793837091-18472-DETAIL-04_11_2024-GO95MLD-1^06245002.0144100 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001644 | 795742660-50660-DETAIL-06_05_2025-GO95HV-1^668075/00 1/028 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001645 | 795742660-50660-DETAIL-06_05_2025-GO95MLD-1^668075/00 1/028 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001646 | 796207298-19769-DTLSB-07_15_2025-GRDRODHI-1^06244007.0036905 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001647 | 796347383-40782-DETAIL-09_29_2025-ABNDEQPM-1^06148001.0310902 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001648 | 796560198-6359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0326400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001649 | 796705353-24899-AUDIT-09_02_2025-CLRTOUCH-1^06247006.0364702 | CONDUCTOR | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001650 | 796852536-39589-DETAIL-07_23_2025-GO95HV-1^06247005.0118700 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001651 | 797042389-48169-DETAIL-02_17_2026-GO95HV-1^06239002.0059500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001652 | 800161805-72759-DETAIL-07_28_2025-GO95HV-1^06247005.0313600 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001653 | 800184516-33789-DETAIL-10_14_2025-GRDRODHI-1^06148001.0175204 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001654 | 800184516-33789-DETAIL-10_14_2025-GRDRODHI-2^06148001.0175204 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001655 | 800486625-61219-DETAIL-01_28_2026-GO95BLTC-1^06242009.0050104 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001656 | 800880065-68719-DTLSB-04_16_2026-CONDFRAY-1^06241009.0137200 | CONDUCTOR | Non-HFTD | Distribution | 2026-04-16 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001657 | 801052691-82780-DETAIL-02_19_2026-GO95HV-1^06239001.0061600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001658 | 801175061-90592-DETAIL-04_15_2024-CUSTWIRE-1^06145002.0190900 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001659 | 801597736-85863-DETAIL-06_26_2026-GO95HV-1^07217001.0049700 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001660 | 804080658-87802-DETAIL-09_09_2025-GO95HV-1^06146001.0097900 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001661 | 804149689-41899-DETAIL-09_09_2025-GO95HV-1^06246007.0144152 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001662 | 804644262-97699-DETAIL-10_06_2021-CUSTWIRE-1^06147005.0054902 | OTHER | Non-HFTD | Distribution | 2021-10-06 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001663 | 804783710-62189-DETAIL-07_24_2025-COPLLEAN-1^06247005.0146302 | POLE | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001664 | 804783710-62189-DETAIL-07_24_2025-GO95HV-1^06247005.0146302 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001665 | 8050293-98249-DTLSB-06_30_2025-GO95HV-1^06244007.0105441 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001666 | 805119320-65802-DTLSB-06_04_2026-GO95HV-1^07216001.0028201 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001667 | 805193312-69802-DTLSB-05_29_2026-GO95HV-1^07216001.0023601 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001668 | 806759264-37949-DETAIL-09_24_2025-CONDCOIL-1^07218001.0220102 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001669 | 806847479-74459-DETAIL-07_28_2025-SVCENTBK-1^06247005.0199701 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001670 | 807508596-18500-DETAIL-04_07_2026-GO95HV-1^06240002.0317013 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001671 | 807607119-54022-DETAIL-10_07_2025-SVCROAD-1^06148001.0303200 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001672 | 807626730-55022-DTLTRT-05_19_2026-BIRDDMG-1^668086/00 9/005 | POLE | Non-HFTD | Transmission | 2026-05-19 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001673 | 807626730-55022-DTLTRT-05_19_2026-GO95HV-1^668086/00 9/005 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001674 | 808074809-93189-DETAIL-09_22_2025-GO95HV-1^06248007.0243103 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001675 | 808222557-90522-DETAIL-04_23_2026-GO95HV-1^06142012.0144503 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001676 | 220691449-47429-DETAIL-05_28_2025-GO95HV-1^06142012.0098101 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001677 | 220910124-20989-DETAIL-08_18_2025-GO95HV-1^06246002.0345902 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001678 | 221126080-52332-DETAIL-04_02_2025-SVCROAD-1^06241005.0117605 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001679 | 221135578-52349-DTLSB-08_12_2025-GO95BLTC-1^07217001.0025501 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001680 | 809143506-35506-DETAIL-06_03_2025-GO95HV-1^06148014.0249804 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001681 | 80927881-4809-DETAIL-09_03_2025-GO95HV-1^06247006.0210503 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001682 | 809348295-77600-DETAIL-02_12_2026-GUYNOINS-1^06239003.0244000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-12 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001683 | 809348295-77600-DETAIL-02_12_2026-GUYNOINS-2^06239003.0244000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-12 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001684 | 809965560-25359-ADMIN-06_08_2026-POLEREPL-1^06248003.0275400 | POLE | HFTD Tier 2 | Distribution | 2026-06-08 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001685 | 810016299-2439-ADMIN-07_07_2025-XARMSPCR-1^668087/00 1/005 | CROSSARM | Non-HFTD | Transmission | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001686 | 81012344-84769-DETAIL-05_06_2025-GRDRODHI-1^06243006.0031300 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001687 | 810204950-48739-DTLTRT-06_25_2025-GUYHINS-1^668087/00 15/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001688 | 810347106-67106-DETAIL-01_29_2025-GO95MLD-1^06239004.0250700 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001689 | 810347106-67106-DRONE_HY-06_19_2026-COVCOTHR-2^06239004.0250700 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001690 | 810438988-9623-DETAIL-05_27_2026-GUYHINS-1^07217001.0148203 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001691 | 810466964-65839-DTLTRT-05_14_2026-GO95MLD-1^668085/00 14/004 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001692 | 812864156-66156-DETAIL-05_29_2025-GO95HV-1^06148014.0360200 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001693 | 812884410-68070-DETAIL-02_19_2026-GO95HV-1^06239002.0011501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001694 | 813125196-86139-DETAIL-03_25_2024-CUSTWIRE-1^06244005.0148402 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001695 | 223370398-87940-DETAIL-02_12_2026-GO95HV-1^06239003.0019206 | OTHER | Non-HFTD | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001696 | 223404998-55930-DTLTRT-05_22_2025-GO95HV-1^668075/00 6/001 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001697 | 223438282-71520-DETAIL-03_25_2025-COVCOTHR-2^06240004.0277442 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001698 | 223556540-48559-DETAIL-09_18_2025-GO95HV-1^06246006.0011900 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001699 | 817193693-51752-ADMIN-11_06_2025-GO95HV-1^06246001.0119700 | OTHER | Non-HFTD | Distribution | 2025-11-06 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001700 | 817194353-28249-DTLSB-07_16_2025-GO95HV-1^06244006.0269901 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001701 | 817597508-9009-DETAIL-05_15_2025-GO95HV-1^06243006.0097500 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001702 | 818226998-50539-DTLTRT-06_23_2025-GO95BLTC-1^668087/00 6/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001703 | 818226998-50539-DTLTRT-06_23_2025-GRDRODHI-1^668087/00 6/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001704 | 818226998-50539-DTLTRT-06_23_2025-INSULBRK-1^668087/00 6/002 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001705 | 818390173-33699-AUDIT-11_20_2025-GO95BLTC-1^06246009.0114000 | OTHER | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001706 | 818483753-69452-DETAIL-09_10_2025-GO95HV-1^06147001.0188600 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001707 | 819744578-75119-DETAIL-06_14_2022-CUSTWIRE-1^07116007.0113405 | OTHER | HFTD Tier 2 | Distribution | 2022-06-14 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001708 | 81975211-95743-DETAIL-07_07_2026-SVCROAD-1^07217001.0164300 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001709 | 819834544-4860-DETAIL-01_15_2025-GO95HV-1^06239004.0255200 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001710 | 820034241-6259-DTLSB-07_08_2025-GO95HV-1^06245007.0353101 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001711 | 820137071-68809-DETAIL-09_03_2025-GO95HV-1^06247006.0210605 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001712 | 820196514-58762-DTLSB-02_07_2023-CUSTWIRE-1^06248001.0157201 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001713 | 820268386-69513-DETAIL-01_14_2026-COVCOTHR-2^06239004.0135147 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001714 | 224940944-5879-DETAIL-08_06_2025-ABNDEQPM-1^06247006.0205802 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001715 | 224940944-5879-DETAIL-08_06_2025-GO95HV-1^06247006.0205802 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001716 | 822067552-28889-DETAIL-05_21_2025-ABNDEQPM-1^06243006.0154003 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001717 | 822080948-87172-DETAIL-08_25_2025-GO95HV-1^06246001.0205901 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001718 | 822199688-20659-DTLSB-08_12_2025-GO95HV-1^07217001.0025500 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001719 | 822430629-36559-DETAIL-08_05_2025-GO95HV-1^06247005.0207301 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001720 | 822560973-89559-DETAIL-07_28_2025-GO95HV-1^06247005.0300100 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001721 | 822761705-42049-DTLSB-07_02_2025-GO95TCH-1^06244006.0226309 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001722 | 825589881-51050-DETAIL-02_26_2026-RISEGRD-1^06238004.0026700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001723 | 826005248-36482-DTLTRT-06_24_2025-GO95MLD-1^668087/00 13/003 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001724 | 826220841-2169-DTLTRT-05_12_2026-GO95HV-1^668004/00 8/010 | OTHER | Non-HFTD | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001725 | 826275655-10319-ADMIN-11_13_2025-GO95HV-1^06247008.0190200 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001726 | 826528709-48709-DETAIL-08_18_2025-GO95HV-1^06247006.0362100 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001727 | 826567275-30999-DETAIL-09_09_2025-GO95HV-1^06246007.0155050 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001728 | 826599963-96482-DETAIL-06_04_2025-GO95HV-1^06142012.0189900 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001729 | 826837098-68069-DETAIL-09_17_2025-GO95HV-1^06248007.0361700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001730 | 830463266-88592-DETAIL-09_03_2025-GRDRODHI-1^06246001.0178300 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001731 | 830463266-88592-DETAIL-09_03_2025-GRDRODHI-2^06246001.0178300 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001732 | 830545193-76692-ADMIN-11_13_2025-ABNDEQPM-1^06246001.0326401 | OTHER | Non-HFTD | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001733 | 830677065-26792-DETAIL-08_26_2025-GUYHINS-1^06246001.0174307 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001734 | 830835106-55106-DETAIL-01_29_2025-GO95MLD-1^06239004.0251701 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001735 | 830909621-79092-DTLTRT-05_18_2026-GO95HV-1^668086/00 9/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001736 | 830920456-41591-DTLTRT-05_11_2026-GO95HV-1^668038/00 3/048 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001737 | 830920456-91591-DTLTRT-05_11_2026-GO95HV-1^668038/00 3/048 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001738 | 835082708-28491-DTLTRT-05_06_2026-BIRDDMG-1^668038/00 4/060 | POLE | HFTD Tier 2 | Transmission | 2026-05-06 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001739 | 835235502-36580-DETAIL-01_29_2026-COVCOTHR-2^06240004.0308303 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001740 | 835522291-42909-DTLSB-11_17_2021-CUSTWIRE-2^06148004.0277601 | OTHER | Non-HFTD | Distribution | 2021-11-17 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001741 | 835537024-34069-DETAIL-09_15_2025-GO95HV-1^06248007.0262900 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001742 | 835571650-7812-DETAIL-03_13_2024-GO95MLD-1^06147004.0190500 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001743 | 835742788-53390-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244409 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001744 | 835742788-53390-DETAIL-01_28_2025-GO95HV-1^06239004.0244409 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001745 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-4^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001746 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-5^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001747 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-6^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001748 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-9^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001749 | 838380514-86989-DETAIL-08_20_2025-SVCENTCO-1^06247006.0367500 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001750 | 838642028-49899-DETAIL-04_17_2025-GO95HV-1^06242006.0093601 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001751 | 838880148-59989-DETAIL-08_19_2025-GRDRODHI-1^06246002.0269001 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001752 | 839189639-17179-DETAIL-05_14_2026-SVCNEUT-1^06242009.0282200 | OTHER | Non-HFTD | Distribution | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001753 | 839241940-65819-DTLSB-04_21_2026-GO95HV-1^06241009.0257500 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001754 | 841097958-58340-DETAIL-04_22_2025-GO95HV-1^06240003.0076101 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001755 | 841274906-53689-DETAIL-08_11_2025-GO95BLTC-1^06247006.0268304 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001756 | 841274906-53689-DETAIL-08_11_2025-GO95HV-1^06247006.0268304 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001757 | 841274906-53689-DETAIL-08_11_2025-SVCROAD-1^06247006.0268304 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001758 | 841513253-60809-DETAIL-08_28_2025-GO95HV-1^06247006.0076600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001759 | 841621468-11169-DETAIL-09_17_2025-GO95HV-1^06248007.0364900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001760 | 841727224-59560-AUDIT-02_26_2025-GO95MLD-1^06240004.0099043 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001761 | 841757353-4032-DETAIL-10_01_2025-GO95HV-1^06148001.0312800 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001762 | 844670569-47632-DETAIL-08_18_2025-GO95HV-1^06246002.0346601 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001763 | 844905674-78630-DETAIL-06_10_2025-GO95HV-1^06236005.0334602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001764 | 844905674-78630-DETAIL-06_10_2025-GRDRODHI-1^06236005.0334602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001765 | 845111438-9342-DTLTRT-06_23_2025-GRDRODHI-1^668087/00 10/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001766 | 845274577-73183-DTLSB-10_07_2024-GO95MLD-1^06245006.0339101 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001767 | 845346403-71859-DETAIL-10_24_2024-SVCRUBLG-1^07216001.0207940 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001768 | 845390210-79159-DETAIL-08_25_2025-SVCDEFLC-1^07216001.0179704 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001769 | 848057116-87098-DETAIL-01_31_2025-GO95HV-1^06239004.0135200 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001770 | 848067755-2855-DETAIL-10_16_2025-GO95BLTC-1^06246012.0137403 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001771 | 848125454-75970-DETAIL-04_29_2025-GO95HV-1^06239002.0062305 | OTHER | Non-HFTD | Distribution | 2025-04-29 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001772 | 848158716-23660-DTLTRT-04_30_2026-GO95HV-1^668004/00 8/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001773 | 848703171-37952-DTLSB-04_29_2026-GO95HV-1^06142013.0287301 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001774 | 84871416-81929-DTLSB-04_30_2026-GO95HV-1^06142013.0186401 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001775 | 848781616-88169-DETAIL-08_19_2025-BIRDDMG-1^06247006.0367000 | POLE | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001776 | 848781616-88169-DETAIL-08_19_2025-SVCDEFLC-1^06247006.0367000 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001777 | 848812989-92919-DTLSB-05_12_2026-GO95HV-1^06242009.0287400 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001778 | 849435001-14220-DTLTRT-07_29_2025-GO95HV-1^07218001.0265000 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001779 | 849539379-38633-DTLSB-06_17_2026-GO95MLD-1^07217001.0344901 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001780 | 849836270-84270-DETAIL-02_25_2026-GO95HV-1^06238003.0019800 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001781 | 85008200-69259-DETAIL-06_23_2026-GO95HV-1^07217001.0114002 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001782 | 850522554-33240-DETAIL-03_23_2026-SVCDEFLC-1^06240004.0218804 | OTHER | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001783 | 850543321-96259-DTLSB-07_07_2025-GO95HV-1^06245007.0351102 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001784 | 850682680-52152-DETAIL-08_21_2025-GO95HV-1^06246001.0305200 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001785 | 850977333-62309-DETAIL-07_29_2025-GO95HV-1^06247006.0208001 | OTHER | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001786 | 851057811-19482-DTLSB-08_14_2023-CUSTWIRE-1^06243009.0238400 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001787 | 851101005-12449-DETAIL-02_28_2024-GO95MLD-1^07113002.0182501 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001788 | 851101005-12449-DETAIL-02_28_2024-SVCROAD-1^07113002.0182501 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001789 | 851110599-17749-DETAIL-09_03_2025-GO95HV-1^07216001.0097106 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001790 | 851147414-89939-ADMIN-03_02_2026-POLEDERP-1^07216001.0307900 | POLE | Non-HFTD | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001791 | 851374837-11289-ADMIN-11_06_2025-GO95HV-1^06246001.0235000 | OTHER | Non-HFTD | Distribution | 2025-11-06 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001792 | 225720129-12129-DTLTRT-07_02_2025-GO95HV-1^668087/00 5/015 | OTHER | Non-HFTD | Transmission | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001793 | 225720129-12129-DTLTRT-07_02_2025-POLEDERP-1^668087/00 5/015 | POLE | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001794 | 226452791-73791-DETAIL-09_24_2025-GO95MLD-1^07218001.0237004 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001795 | 226619535-35439-DETAIL-05_29_2025-GO95HV-1^06244006.0112700 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001796 | 22680948-93639-DTLSB-08_12_2025-SVCDEFLC-1^07217001.0024100 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001797 | 227171537-74799-DETAIL-06_04_2025-GO95HV-1^06245006.0298902 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001798 | 227201283-41979-DETAIL-08_13_2025-GO95HV-1^06247006.0259503 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001799 | 227350438-58860-DETAIL-04_27_2026-GO95HV-1^06142012.0144808 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001800 | 227481000-53549-DTLSB-07_02_2025-GO95HV-1^06244007.0136200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001801 | 853610508-76870-DETAIL-02_04_2025-SVCDEFLC-2^06240004.0169601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001802 | 853610508-76870-DETAIL-02_04_2025-SVCENTCO-1^06240004.0169601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001803 | 853803038-97299-ADMIN-10_23_2025-GO95HV-1^06246011.0368203 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001804 | 853807009-99019-DTLSB-04_13_2026-BIRDDMG-1^06241008.0256000 | POLE | Non-HFTD | Distribution | 2026-04-13 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001805 | 853959864-27590-DETAIL-02_12_2026-GO95HV-1^06239003.0363602 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001806 | 854228825-88700-DETAIL-04_30_2025-GO95HV-1^06239002.0064703 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001807 | 851984064-28090-DETAIL-02_12_2026-GUYHINS-1^06239003.0363600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-12 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001808 | 851984064-28090-DETAIL-02_12_2026-SVCROAD-1^06239003.0363600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001809 | 851984064-28090-DETAIL-02_12_2026-SVCROAD-2^06239003.0363600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001810 | 851992146-72610-DETAIL-02_26_2026-COVCOTHR-1^06238004.0117102 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001811 | 85243818-48749-DTLSB-08_12_2025-GO95MLD-1^07217001.0027402 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001812 | 852473941-56843-DETAIL-07_01_2026-SVCENTBK-1^07217001.0165404 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001813 | 852529250-18170-DETAIL-02_13_2025-GO95TCH-1^06240004.0169107 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001814 | 852529250-18170-DETAIL-02_13_2025-SVCROAD-1^06240004.0169107 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001815 | 828581658-38359-DTLTRT-05_07_2026-GO95HV-1^668004/00 8/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001816 | 828896771-84439-DETAIL-05_08_2025-GO95HV-1^06243006.0162000 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001817 | 828981358-35659-DTLSB-08_12_2025-GRDRODHI-1^07217001.0026801 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001818 | 829083166-24329-DTLSB-05_04_2026-GO95HV-1^06142013.0175600 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001819 | 829440599-2999-DETAIL-02_03_2022-CUSTWIRE-1^06147005.0300101 | OTHER | Non-HFTD | Distribution | 2022-02-03 | 2025-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001820 | 829484283-50759-DETAIL-07_29_2025-GO95HV-1^06247005.0215600 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001821 | 829503188-33188-DETAIL-06_19_2025-GO95HV-1^668075/00 4X/049 | OTHER | HFTD Tier 2 | Transmission | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001822 | 830463266-88592-DETAIL-09_03_2025-GO95MLD-1^06246001.0178300 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001823 | 831321023-90680-DETAIL-02_24_2026-BIRDDMG-1^06239002.0225300 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001824 | 831321023-90680-DETAIL-02_24_2026-GO95HV-1^06239002.0225300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001825 | 831903408-16429-DETAIL-04_20_2026-SVCDEFLC-1^06142012.0147910 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001826 | 831930960-94189-DETAIL-08_21_2025-GO95MLD-1^06246001.0305101 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001827 | 832135026-62602-DETAIL-08_20_2025-ABNDEQPM-1^06246001.0175402 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001828 | 832379721-35101-DETAIL-01_31_2025-GO95HV-1^06239004.0245903 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001829 | 832427698-50742-DETAIL-04_21_2025-GO95HV-1^06242006.0100800 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001830 | 832569156-18259-DETAIL-07_23_2025-GO95HV-1^06247005.0118800 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001831 | 8330901-24780-DETAIL-02_19_2026-GO95HV-1^06239001.0062600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001832 | 83352921-59650-DETAIL-01_24_2025-GO95HV-1^06239004.0258502 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001833 | 833698505-97099-DETAIL-08_13_2025-GO95HV-1^06247006.0253700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001834 | 833812631-14711-ADMIN-03_06_2026-POLEREPL-1^06239004.0255346 | POLE | HFTD Tier 2 | Distribution | 2026-03-06 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001835 | 833812631-14711-DETAIL-01_21_2025-GO95HV-1^06239004.0255346 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001836 | 834635856-47856-DETAIL-05_29_2025-GO95HV-1^06148014.0358000 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001837 | 834742531-14080-DETAIL-02_16_2026-GO95HV-1^06239001.0041700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001838 | 834901454-93783-DETAIL-09_10_2025-GO95HV-1^06246006.0076250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001839 | 852641100-4369-DETAIL-06_16_2025-COPLLEAN-1^06248005.0285201 | POLE | Non-HFTD | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001840 | 852737885-16070-DETAIL-01_24_2025-GO95HV-1^06239004.0258742 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001841 | 852873620-34152-DTLSB-06_26_2025-ANCHIDLE-1^06244007.0037040 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001842 | 852873620-34152-DTLSB-06_26_2025-GO95HV-1^06244007.0037040 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001843 | 852974885-22662-DTLTRT-05_12_2026-GO95HV-1^668038/00 3/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001844 | 852974885-28491-ADMIN-12_08_2025-POLEDERP-1^668038/00 3/047 | POLE | HFTD Tier 2 | Transmission | 2025-12-08 | 2026-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001845 | 852974885-88491-DTLTRT-05_12_2026-GO95HV-1^668038/00 3/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001846 | 853157758-92099-ADMIN-10_23_2025-GO95HV-1^06246011.0365101 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001847 | 835770848-48670-DRONE_HY-06_30_2026-IRSPOTOH-1^06240004.0169507 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001848 | 835920643-79453-DETAIL-09_22_2025-GO95HV-1^07218001.0160002 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001849 | 835928193-89212-DETAIL-09_09_2025-GO95HV-1^06147001.0199601 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001850 | 83609109-24813-DETAIL-08_25_2025-GO95HV-1^06247006.0282702 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001851 | 836191213-42669-DETAIL-02_20_2026-XARMSPCR-1^668041/00 2/026 | CROSSARM | Non-HFTD | Transmission | 2026-02-20 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001852 | 836288231-11759-DETAIL-06_18_2025-GO95HV-1^06248004.0324901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001853 | 836361064-26312-DETAIL-04_07_2025-SVCROOF-1^06241005.0118304 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001854 | 836577125-41359-DETAIL-07_22_2025-GO95HV-1^06247005.0091300 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001855 | 83726981-91139-DTLTRT-07_08_2025-GO95HV-1^668087/00 12/025 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001856 | 837669649-38269-DTLSB-07_07_2025-GO95HV-1^06244007.0039102 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001857 | 837884960-85870-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135801 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001858 | 83818332-91559-DETAIL-07_23_2025-GO95HV-1^06247005.0176101 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001859 | 838251548-6709-DETAIL-08_26_2025-GO95HV-1^06247006.0329001 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001860 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-1^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001861 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-2^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001862 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-3^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001863 | 853157758-92099-ADMIN-10_23_2025-SVCDEFLC-1^06246011.0365101 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001864 | 853201425-16129-DETAIL-04_23_2026-GO95HV-1^06142012.0144303 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001865 | 853201674-51239-DETAIL-08_27_2025-GRDRODHI-1^07216001.0164401 | OTHER | Non-HFTD | Distribution | 2025-08-27 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001866 | 853433210-44269-DETAIL-10_06_2025-GO95BLTC-1^06246008.0016300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001867 | 853602361-90662-DETAIL-10_08_2025-CLRTOUCH-1^06148001.0311601 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001868 | 853602361-90662-DETAIL-10_08_2025-GO95HV-1^06148001.0311601 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001869 | 225587959-85169-DETAIL-07_06_2026-INSULBRK-1^668041/00 8/018 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001870 | 839726125-32530-DETAIL-04_15_2026-GUYHINS-1^06236005.0113901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001871 | 839726125-32530-DETAIL-04_15_2026-GUYHINS-2^06236005.0113901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001872 | 839726125-32530-DETAIL-04_15_2026-GUYHINS-3^06236005.0113901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001873 | 840069934-64731-DETAIL-04_07_2025-GO95TCH-1^06241005.0012800 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001874 | 840121916-58122-DETAIL-08_20_2025-GO95HV-1^06246001.0175301 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001875 | 225156491-48491-DETAIL-09_25_2025-GO95HV-1^07218001.0216601 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001876 | 225156491-48491-DETAIL-09_25_2025-GRDRODHI-1^07218001.0216601 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001877 | 225226658-91660-DETAIL-08_21_2025-GRDRODHI-1^06246001.0205400 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001878 | 22528475-76689-ADMIN-10_22_2025-GO95BLTC-1^06246011.0051401 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001879 | 225389246-24760-DTLTRT-05_11_2026-GO95HV-1^668038/00 2/051 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001880 | 225587959-85169-ADMIN-07_24_2020-INSULPLM-1^668041/00 8/018 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2020-07-24 | 2023-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001881 | 840124971-68122-DTLSB-05_28_2026-GO95HV-1^07216001.0021506 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001882 | 840533429-47099-DTLSB-07_17_2025-GO95HV-1^06244006.0185102 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001883 | 840772940-16722-DTLSB-06_03_2026-GO95HV-1^07216001.0029901 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001884 | 840801505-69009-DETAIL-09_24_2025-GO95HV-1^06246009.0168500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001885 | 840806101-20739-DETAIL-05_07_2025-GO95HV-1^06243006.0025500 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001886 | 810658605-93432-DTLSB-05_13_2024-GO95MLD-1^06245001.0294200 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001887 | 811142384-95032-DETAIL-03_06_2025-GRDRODHI-1^06241005.0120504 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001888 | 811178168-52669-DETAIL-06_05_2025-GO95HV-1^06245006.0300902 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001889 | 811316889-61389-DETAIL-07_22_2025-GO95HV-1^06247005.0058400 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001890 | 811471958-82732-DTLTRT-06_30_2025-GUYNOINS-1^668087/00 2/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001891 | 811471958-82732-DTLTRT-06_30_2025-GUYNOINS-2^668087/00 2/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001892 | 811481323-72549-DTLSB-08_11_2025-CUSTWIRE-1^07218001.0279902 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001893 | 811716674-57453-DETAIL-09_22_2025-GO95MLD-1^07218001.0218900 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001894 | 81192714-5810-DETAIL-10_15_2025-GO95HV-1^06247012.0310301 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001895 | 812275808-27599-ADMIN-08_05_2024-GO95STUB-1^06246012.0119503 | OTHER | HFTD Tier 2 | Distribution | 2024-08-05 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001896 | 812303973-91680-DETAIL-02_13_2025-GO95CL10-1^06240004.0169105 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001897 | 81239914-92358-DETAIL-09_03_2025-GO95HV-1^07216001.0097009 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001898 | 812425636-45110-DETAIL-02_04_2026-GUYHINS-1^06239003.0018802 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001899 | 812461543-53602-DETAIL-04_02_2025-GO95TCH-1^06241005.0118404 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001900 | 812765523-45853-DETAIL-09_23_2025-GO95MLD-1^07218001.0223702 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001901 | 841957764-89339-DETAIL-10_06_2025-GO95HV-1^06243007.0362401 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001902 | 842092588-63159-DETAIL-09_03_2025-GO95MLD-1^07216001.0094441 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001903 | 842252734-8990-DETAIL-04_30_2025-GO95HV-1^06239002.0065705 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001904 | 842292861-93859-DETAIL-07_24_2025-GO95HV-1^06247005.0136301 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001905 | 842466631-16219-DTLSB-03_26_2026-GO95MLD-1^06242008.0173201 | OTHER | Non-HFTD | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001906 | 842750663-24529-DTLSB-03_10_2026-GO95HV-1^06243009.0345302 | OTHER | Non-HFTD | Distribution | 2026-03-10 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001907 | 84285434-77129-DETAIL-04_21_2026-GO95HV-1^06142012.0148810 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001908 | 842944733-20819-DTLSB-05_12_2026-GO95HV-1^06242009.0270603 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001909 | 223948248-64999-DTLSB-08_22_2024-ENCHRW-1^06245006.0326600 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001910 | 813197653-72920-DETAIL-03_17_2025-COVCOTHR-2^06240004.0270000 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001911 | 813360381-56442-DETAIL-10_01_2025-SVCENTCO-1^06148001.0301012 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001912 | 813364203-60780-DETAIL-02_17_2026-GO95HV-1^06239002.0059600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001913 | 814804662-634-DTLTRT-06_30_2025-GO95HV-1^668087/00 11/014 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001914 | 815123841-19280-DETAIL-02_16_2026-GO95HV-1^06239001.0059700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001915 | 815474200-14320-DETAIL-01_22_2026-SVCTREE-1^06239003.0071905 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001916 | 815517246-6209-DETAIL-08_11_2025-GO95HV-1^06247006.0268202 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001917 | 81582167-83110-DETAIL-08_11_2025-ABNDEQPM-1^06246002.0238400 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001918 | 815996070-72970-DETAIL-02_19_2026-GO95HV-1^06239002.0025502 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001919 | 816117740-97870-DETAIL-02_23_2026-GO95HV-1^06239002.0020501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001920 | 816269031-22842-DTLSB-05_06_2026-GO95HV-1^06142013.0287500 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001921 | 816588006-59383-DTLSB-07_01_2025-GO95HV-1^06244006.0226441 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001922 | 816595134-36299-DETAIL-05_21_2025-GUYHINS-1^06243006.0092001 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-21 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001923 | 817051898-62552-DETAIL-09_02_2025-GO95HV-1^06246001.0200800 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001924 | 843179575-62763-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0097800 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001925 | 843209223-11339-DETAIL-11_17_2025-GO95HV-1^06243007.0010401 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001926 | 84327829-19920-DETAIL-10_01_2025-GO95HV-1^06148001.0302203 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001927 | 843454864-33939-DETAIL-05_07_2025-GO95HV-1^06243006.0049001 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001928 | 843473348-4532-DTLTRT-06_30_2025-GO95HV-1^668087/00 1/014 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001929 | 843622100-20659-DETAIL-06_18_2025-GO95HV-1^06248004.0340801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001930 | 843903626-55791-DTLTRT-05_11_2026-BIRDDMG-1^668038/00 5/052 | POLE | HFTD Tier 2 | Transmission | 2026-05-11 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001931 | 844156523-7523-DETAIL-06_04_2025-GO95MLD-1^668075/00 11/024 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001932 | 818581078-69929-DETAIL-04_22_2026-GO95HV-1^06142012.0144605 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001933 | 818581078-69929-DETAIL-04_22_2026-GRDRODHI-1^06142012.0144605 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001934 | 818672565-5170-DETAIL-04_29_2025-GO95TCH-1^06239002.0062301 | OTHER | Non-HFTD | Distribution | 2025-04-29 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001935 | 818850478-48179-ADMIN-08_18_2025-CUTOUTAR-1^06246002.0355600 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001936 | 818850478-48179-DETAIL-08_18_2025-GO95HV-1^06246002.0355600 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001937 | 819131869-33889-DETAIL-08_13_2025-GO95HV-1^06246002.0367601 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001938 | 819157501-4939-DETAIL-06_12_2024-CUSTWIRE-1^06244005.0249640 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001939 | 819266351-94880-DETAIL-02_19_2026-GO95HV-1^06239001.0066601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001940 | 819322074-61879-DTLSB-03_09_2026-BIRDDMG-1^06242009.0208700 | POLE | Non-HFTD | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001941 | 819322074-61879-DTLSB-03_09_2026-CUSTWIRE-1^06242009.0208700 | OTHER | Non-HFTD | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001942 | 819438538-61453-DTLSB-06_04_2026-BIRDDMG-1^07216001.0141303 | POLE | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001943 | 819477724-39229-DETAIL-05_14_2024-CUSTWIRE-1^06142012.0122806 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001944 | 819550616-14179-DTLSB-05_19_2026-GO95HV-1^06240009.0149000 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001945 | 819671500-38462-DETAIL-08_12_2025-GO95HV-1^06246001.0303600 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001946 | 819717493-79169-DETAIL-07_29_2025-GO95HV-1^06247005.0215900 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001947 | 854314687-78423-DETAIL-05_22_2026-GO95HV-1^07217001.0145401 | OTHER | Non-HFTD | Distribution | 2026-05-22 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001948 | 854568429-47372-DTLTRT-06_24_2025-CLRTOUCH-1^668087/00 12B/005 | CONDUCTOR | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001949 | 8546711-82180-DETAIL-02_16_2026-GO95HV-1^06239001.0055700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001950 | 854903693-49972-DETAIL-04_27_2026-GO95HV-1^06142012.0145904 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001951 | 855213678-42419-DTLSB-03_16_2026-GO95HV-1^06242009.0131402 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001952 | 855225566-56310-DETAIL-02_10_2026-BIRDDMG-1^06239003.0016502 | POLE | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001953 | 855276209-41899-DTLSB-05_12_2026-GO95HV-1^06242009.0280203 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001954 | 855393076-17659-DETAIL-04_30_2026-GO95HV-1^668004/00 4/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001955 | 82027580-4079-DTLSB-11_04_2021-CUSTWIRE-1^06148004.0274200 | OTHER | Non-HFTD | Distribution | 2021-11-04 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001956 | 820294543-5363-DTLTRT-08_05_2025-BIRDDMG-1^668087/00 6/012 | POLE | Non-HFTD | Transmission | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001957 | 820328561-12162-DTLTRT-04_27_2026-GO95HV-1^668004/00 8/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001958 | 82036291-93510-DETAIL-03_13_2024-CUSTWIRE-1^06147004.0081001 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001959 | 820689050-52636-DETAIL-04_23_2026-GO95HV-1^06142012.0145803 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001960 | 820930255-16870-DETAIL-03_11_2025-GO95HV-1^06238004.0334305 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001961 | 820985275-64029-AUDIT-05_06_2025-GRDRODHI-1^06242006.0082602 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001962 | 821192669-65059-ADMIN-06_24_2024-POLEDERP-1^07116001.0093202 | POLE | HFTD Tier 2 | Distribution | 2024-06-24 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001963 | 821562441-65162-DTLSB-05_07_2026-GO95HV-1^06142013.0345400 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001964 | 821796819-41409-DETAIL-08_06_2025-GO95HV-1^06247006.0204900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001965 | 821831063-97270-ADMIN-10_17_2017-CUSTWIRE-1^668033/00 12/016 | OTHER | HFTD Tier 2 | Transmission | 2017-10-17 | 2020-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001966 | 22419341-30441-DETAIL-03_28_2023-CUSTWIRE-1^06142016.0053200 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001967 | 224603651-96819-DTLSB-03_18_2026-BIRDDMG-1^06242009.0220500 | POLE | Non-HFTD | Distribution | 2026-03-18 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001968 | 224714189-2360-DTLTRT-05_19_2026-GO95HV-1^668086/00 1/003 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001969 | 797132670-28388-DETAIL-07_06_2026-GO95TCH-1^07217001.0045700 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001970 | 797148571-54162-DTLSB-06_26_2025-GO95MLD-1^06244007.0107240 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001971 | 79732681-85259-DETAIL-03_20_2023-ABNDEQPM-1^07118004.0020500 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2028-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001972 | 797390982-13639-DETAIL-05_21_2025-GO95MLD-1^06243006.0155700 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001973 | 797539473-19882-DETAIL-02_05_2018-ENCHRW-1^06248001.0276600 | OTHER | Non-HFTD | Distribution | 2018-02-05 | 2021-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001974 | 798387440-88470-DETAIL-02_18_2026-GO95HV-1^06239002.0041300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001975 | 798466601-6001-DETAIL-01_14_2025-SVCENTBK-1^06239004.0258341 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001976 | 798611717-15140-DETAIL-04_08_2026-GO95HV-1^06240002.0315303 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001977 | 798638111-750-DRONE_HY-06_30_2026-XARMBRAC-1^06238004.0273702 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001978 | 799153103-37889-DETAIL-07_31_2025-GO95HV-1^06247005.0214700 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001979 | 799252210-80929-DETAIL-06_04_2025-GO95HV-1^06142012.0107300 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001980 | 79966902-23520-DETAIL-03_30_2026-SVCTREE-1^06240004.0277440 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001981 | 799790568-89599-DETAIL-06_16_2025-GO95MLD-1^06248004.0361242 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001982 | 800117361-89880-DETAIL-02_19_2026-GO95HV-1^06239001.0067600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001983 | 800118504-94790-DETAIL-03_31_2025-SVCROAD-1^06239003.0016801 | OTHER | Non-HFTD | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001984 | 845598388-64550-DETAIL-02_11_2026-GUYNOINS-1^06239003.0016106 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001985 | 845733534-14399-DETAIL-08_18_2025-GO95HV-1^06247006.0364401 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001986 | 845819227-99227-DETAIL-06_18_2025-GO95HV-1^668075/00 20/045 | OTHER | HFTD Tier 2 | Transmission | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001987 | 845896841-26259-DTLSB-07_08_2025-GO95HV-1^06245007.0353200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001988 | 846027081-79739-DETAIL-05_19_2025-GO95HV-1^06243006.0274501 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001989 | 846081924-85759-DETAIL-06_16_2025-GO95HV-1^06248005.0367800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001990 | 846531112-69999-DETAIL-03_21_2024-CUSTWIRE-1^06147004.0365400 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001991 | 801602984-7460-DETAIL-01_23_2025-GO95BLTC-1^06239004.0257805 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001992 | 802085172-22539-DETAIL-05_15_2025-GO95HV-1^06243006.0163802 | OTHER | HFTD Tier 2 | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001993 | 802112441-45202-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001994 | 21866434-75989-DETAIL-05_08_2025-GO95BLTC-1^06243006.0105001 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001995 | 218877272-96283-DTLSB-06_05_2026-GO95HV-1^07216001.0235801 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120001996 | 218902816-48409-DETAIL-04_08_2024-CONDFRAY-1^06147005.0237201 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001997 | 219111178-95550-ADMIN-11_10_2025-POLEDERP-1^668087/00 5/018 | POLE | Non-HFTD | Transmission | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001998 | 219342309-2270-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0165740 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120001999 | 802363124-85244-DETAIL-06_10_2026-GUYHINS-4^668086/00 10B/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002000 | 802363124-85244-DETAIL-06_10_2026-GUYHINS-5^668086/00 10B/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002001 | 802681799-35991-DTLTRT-04_28_2026-GO95HV-1^668038/00 5/066 | OTHER | HFTD Tier 2 | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002002 | 803104538-45379-DETAIL-09_04_2025-GO95HV-1^06146001.0083801 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002003 | 803302504-79902-DETAIL-09_08_2025-GO95HV-1^06147001.0329501 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002004 | 803370960-27570-DETAIL-02_04_2025-GO95HV-1^06240004.0167602 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002005 | 803499521-12939-DETAIL-05_08_2025-GO95HV-1^06243006.0284940 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002006 | 822781140-55170-DETAIL-02_13_2025-GO95CL10-1^06240004.0168106 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002007 | 822893803-89259-DTLTRT-04_22_2026-GO95HV-1^668004/02 4/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002008 | 822961723-2983-DETAIL-08_19_2025-GO95HV-1^06247006.0365901 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002009 | 823255745-74979-DTLSB-07_17_2025-GO95BLTC-1^06244007.0112402 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002010 | 82380883-68710-ADMIN-10_28_2025-GRDRODHI-1^06246001.0120701 | OTHER | Non-HFTD | Distribution | 2025-10-28 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002011 | 824035043-95043-DETAIL-06_10_2025-GO95MLD-1^668075/00 7/031 | OTHER | Non-HFTD | Transmission | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002012 | 824097186-23740-AUDIT-04_27_2026-RISEBKSP-1^06240004.0214701 | OTHER | HFTD Tier 2 | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002013 | 824659616-35572-DTLSB-05_06_2026-GO95HV-1^06142013.0220102 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002014 | 80524223-89639-DTLSB-08_11_2025-GO95HV-1^07217001.0013400 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002015 | 80546186-68399-DTLSB-09_05_2024-CUSTWIRE-2^06245007.0235600 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002016 | 805468183-7690-DETAIL-02_24_2026-GO95HV-1^06239002.0274300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002017 | 805497570-5270-DETAIL-02_19_2026-GO95HV-1^06239002.0019602 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002018 | 805508642-77139-DETAIL-05_06_2025-GO95HV-1^06243006.0066400 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002019 | 80552008-559-DETAIL-05_16_2022-GO95MLD-1^07116001.0059300 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002020 | 80555285-27851-DETAIL-04_14_2025-SVCROAD-1^06241005.0012544 | OTHER | HFTD Tier 2 | Distribution | 2025-04-14 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002021 | 805581588-28912-DETAIL-04_20_2026-SVCENTBK-1^06142012.0146908 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002022 | 805985773-4680-DETAIL-02_17_2026-GO95HV-1^06239002.0040200 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002023 | 806033883-65909-DETAIL-08_14_2025-GO95HV-1^06247006.0259000 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002024 | 806096576-82676-DETAIL-05_29_2025-GO95HV-1^06148014.0360501 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002025 | 806237081-64639-DETAIL-05_07_2025-GO95HV-1^06243006.0018800 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002026 | 806266651-8843-DETAIL-07_01_2026-GO95HV-1^07217001.0169504 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002027 | 806266651-8843-DETAIL-07_01_2026-SVCROAD-1^07217001.0169504 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002028 | 806484527-99712-ADMIN-10_22_2025-GRDRODHI-2^06246001.0108001 | OTHER | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002029 | 824704178-40179-DETAIL-06_17_2025-GO95CLSV-1^06248004.0299106 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002030 | 824763553-82279-DTLSB-01_20_2026-GO95HV-1^06242009.0298101 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002031 | 824847765-865-DETAIL-05_29_2025-GO95HV-1^06147014.0012900 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002032 | 824885076-58870-DETAIL-02_19_2025-CUSTWIRE-1^06239004.0364300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002033 | 824885076-58870-DRONE_HY-07_01_2026-BIRDDMG-1^06239004.0364300 | POLE | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002034 | 82498781-51869-DTLTRT-05_12_2026-GO95HV-1^668004/00 4/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002035 | 825009975-19899-DETAIL-09_09_2025-GO95HV-1^06246007.0227851 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002036 | 825114826-3000-DETAIL-03_02_2026-SVCDEFLC-1^06239003.0242701 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002037 | 808317614-65759-DETAIL-06_16_2025-GO95HV-1^06248005.0367700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002038 | 808370309-10869-ADMIN-07_08_2026-POLEDERP-1^668005/03 3/005 | POLE | Non-HFTD | Transmission | 2026-07-08 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002039 | 808402550-45189-DETAIL-08_06_2025-GO95HV-1^06247005.0207101 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002040 | 808558770-36179-DETAIL-06_18_2025-GO95HV-1^06248004.0270000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002041 | 808635085-35249-DETAIL-09_02_2025-GO95HV-1^07216001.0165702 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002042 | 809072736-52380-DETAIL-01_22_2025-GO95MLD-1^06239004.0255543 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002043 | 809072736-52380-DETAIL-01_22_2025-GO95TCH-1^06239004.0255543 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002044 | 219761000-85370-DETAIL-04_12_2023-CUSTWIRE-1^06240004.0167604 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002045 | 220036819-71359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0334600 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002046 | 220278255-65579-DETAIL-01_18_2023-COPLLEAN-1^06148004.0207701 | POLE | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002047 | 220278255-65579-DETAIL-01_18_2023-GO95BLTC-1^06148004.0207701 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2028-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002048 | 220278255-65579-DETAIL-01_18_2023-GO95MLD-2^06148004.0207701 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002049 | 220650184-1253-DETAIL-06_29_2026-GUYHINS-1^07217001.0043200 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-29 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002050 | 774159336-71889-DETAIL-06_09_2025-GO95HV-1^06245007.0245700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002051 | 774433368-10899-DTLSB-01_21_2026-BIRDDMG-1^06242009.0297110 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002052 | 774602923-24009-DETAIL-08_12_2025-GO95HV-1^06247006.0251502 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002053 | 774910339-85759-DTLSB-07_29_2025-GO95HV-1^07218001.0264100 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002054 | 774921004-41004-DETAIL-11_17_2025-GO95BLTC-1^06243007.0019302 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002055 | 774986832-54559-DETAIL-02_27_2024-GO95HV-1^07113002.0182402 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002056 | 775146820-18422-DTLTRT-04_27_2026-GO95HV-1^668004/00 2/005 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002057 | 775332406-46522-ADMIN-10_30_2025-GUYHINS-1^06246001.0101800 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-30 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002058 | 777668416-97480-DRONE_HY-07_15_2026-COVCOTHR-1^06239004.0256546 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002059 | 77797994-52700-DTLTRT-06_23_2025-GO95HV-1^668087/02 1/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002060 | 778171555-45493-DETAIL-08_19_2025-SVCENTCO-1^06247006.0365700 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002061 | 778587419-83929-DETAIL-04_27_2026-GO95HV-1^06142012.0146501 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002062 | 77886986-99389-DTLSB-07_14_2025-GO95HV-1^06244007.0145602 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002063 | 779027717-88490-DETAIL-02_03_2025-GO95HV-1^06239004.0244847 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002064 | 779207907-42532-ADMIN-10_29_2025-GRDRODHI-1^06246001.0032001 | OTHER | Non-HFTD | Distribution | 2025-10-29 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002065 | 779583536-90289-DETAIL-05_21_2025-ENCHRW-1^06243006.0105000 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002066 | 779653074-53132-DETAIL-09_22_2025-CONDFRAY-1^06147001.0257301 | CONDUCTOR | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002067 | 779653074-53132-DETAIL-09_22_2025-GO95HV-1^06147001.0257301 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002068 | 779653074-53132-DETAIL-09_22_2025-GO95TCH-1^06147001.0257301 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002069 | 779725598-1730-DETAIL-01_26_2026-GO95MLD-1^06240003.0305100 | OTHER | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002070 | 779725598-1730-DETAIL-01_26_2026-SVCDEFLC-1^06240003.0305100 | OTHER | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002071 | 77986938-91919-DTLSB-04_15_2026-GO95HV-1^06241008.0078400 | OTHER | Non-HFTD | Distribution | 2026-04-15 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002072 | 779943278-83570-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0222603 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002073 | 779943278-83570-DETAIL-03_23_2026-COVCOTHR-3^06240004.0222603 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002074 | 847094614-46309-DTLSB-11_01_2021-CUSTWIRE-1^06148004.0232605 | OTHER | Non-HFTD | Distribution | 2021-11-01 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002075 | 847163059-13542-DTLTRT-06_25_2025-GO95HV-1^668087/00 15/005 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002076 | 847163059-13542-DTLTRT-06_25_2025-GO95MLD-1^668087/00 15/005 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002077 | 847188316-43311-DETAIL-01_13_2026-COVCOTHR-1^06239004.0243940 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002078 | 84774819-79120-DETAIL-09_10_2025-GO95HV-1^06146001.0088801 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002079 | 847829662-60149-DTLSB-07_16_2025-GO95HV-1^06244006.0232002 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002080 | 848003333-99499-DETAIL-05_30_2025-GO95HV-1^06244006.0145601 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002081 | 782839857-24942-DTLTRT-06_23_2025-GO95HV-1^668087/00 7/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002082 | 782932304-85629-DTLSB-01_15_2026-GO95MLD-1^06242009.0299005 | OTHER | Non-HFTD | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002083 | 782960903-3142-ADMIN-10_20_2025-ABNDEQPM-1^06247001.0368401 | OTHER | Non-HFTD | Distribution | 2025-10-20 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002084 | 783004290-5142-DTLTRT-05_05_2026-GO95HV-1^668004/00 4X/001 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002085 | 783031481-80839-DETAIL-05_19_2025-GO95HV-1^06243006.0274800 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002086 | 783376956-40200-DETAIL-04_07_2026-GO95MLD-1^06240002.0317109 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002087 | 783466324-19960-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0134044 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002088 | 784109896-47229-DTLSB-05_05_2026-GO95HV-1^06142013.0220500 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002089 | 784117905-51800-DETAIL-04_08_2026-GO95HV-1^06240002.0313200 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002090 | 784138334-58334-DETAIL-07_22_2025-GO95HV-1^06247005.0091301 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002091 | 784360690-3979-DETAIL-10_06_2025-GO95HV-1^06148001.0311906 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002092 | 784508941-96450-DRONE_HY-06_19_2026-XARMSPCR-1^06238004.0270400 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002093 | 784733739-1442-DETAIL-08_18_2025-GO95HV-1^06246002.0264402 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002094 | 784814679-999-DTLSB-07_07_2025-BIRDDMG-1^06244007.0039103 | POLE | HFTD Tier 2 | Distribution | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002095 | 78497811-38601-DETAIL-01_15_2025-SVCENTBK-1^06239004.0255243 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002096 | 809485680-23722-DTLTRT-05_05_2026-GO95HV-1^668004/00 3X/001 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002097 | 22122984-17909-DETAIL-08_13_2025-GO95HV-1^06247006.0255500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002098 | 221602301-85949-DETAIL-09_18_2025-GO95HV-1^07219001.0327002 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002099 | 22170638-81638-DETAIL-06_05_2025-GO95HV-1^06148014.0245601 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002100 | 222041831-59359-DETAIL-07_01_2024-CUSTWIRE-1^06245007.0305700 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002101 | 222089816-92533-DETAIL-06_17_2025-GO95HV-1^06248004.0360040 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002102 | 222223444-11789-DETAIL-08_14_2025-GO95HV-1^06247006.0255100 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002103 | 222223444-11789-DETAIL-08_14_2025-SVCENTCO-1^06247006.0255100 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002104 | 786104514-22799-DETAIL-02_17_2025-SVCROOF-1^06240004.0166643 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002105 | 786122268-81570-DETAIL-01_29_2025-GO95TCH-1^06240004.0161402 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002106 | 786550712-22183-DETAIL-08_21_2025-SVCDEFLC-1^07216001.0175404 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002107 | 786597081-79830-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 6/027 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002108 | 786759791-5539-DETAIL-05_14_2025-GO95HV-1^06243006.0169400 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002109 | 787055694-71883-DETAIL-08_18_2025-GO95HV-1^06247006.0363301 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002110 | 787447432-55989-DTLSB-07_16_2025-GUYHINS-1^06244006.0231102 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-16 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002111 | 787447432-55989-DTLSB-07_16_2025-GUYHINS-2^06244006.0231102 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-16 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002112 | 787495821-98821-DETAIL-02_25_2026-GO95HV-1^06239003.0134001 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002113 | 787782013-49299-DETAIL-09_30_2025-GO95BLTC-1^06246009.0121202 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002114 | 787848628-72189-DETAIL-09_24_2025-GRDRODHI-1^06246009.0078100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002115 | 788112111-22652-DTLTRT-05_05_2026-GO95HV-1^668004/00 5/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002116 | 788308306-54823-DTLSB-04_23_2024-GO95MLD-1^06245007.0222643 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002117 | 788320823-62350-DETAIL-01_31_2025-GO95HV-1^06239004.0136203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002118 | 788441804-24390-DETAIL-03_27_2025-GO95HV-1^06239003.0019705 | OTHER | Non-HFTD | Distribution | 2025-03-27 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002119 | 222347570-71460-DETAIL-06_04_2025-GO95HV-1^06142012.0080000 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002120 | 223070450-92360-ADMIN-10_21_2025-INSULDMG-1^06247001.0136000 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002121 | 223138010-6309-DETAIL-03_05_2024-GO95HV-1^06147004.0022003 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002122 | 809511261-5722-DETAIL-09_10_2025-GO95HV-1^06147001.0082700 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002123 | 809697678-69822-DETAIL-02_05_2018-ENCHRW-1^06247001.0019902 | OTHER | Non-HFTD | Distribution | 2018-02-05 | 2021-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002124 | 809711916-71463-DETAIL-07_06_2026-CUSTWIRE-1^07217001.0031700 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002125 | 809711916-71463-DETAIL-07_06_2026-GO95HV-1^07217001.0031700 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002126 | 758472371-65999-AUDIT-10_20_2025-ENCHSVCE-1^06246008.0065101 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002127 | 758472371-65999-DETAIL-10_02_2025-GO95BLTC-1^06246008.0065101 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002128 | 758472371-65999-DETAIL-10_02_2025-GUYHINS-2^06246008.0065101 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002129 | 215787338-50950-DETAIL-09_09_2025-GO95HV-1^06146001.0094802 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002130 | 215821441-1811-DETAIL-06_19_2025-GO95HV-1^06237004.0205602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002131 | 215978356-2950-DETAIL-04_15_2026-CUSTWIRE-1^06236005.0113801 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002132 | 216147923-57559-ADMIN-08_15_2025-POLEREPL-1^06247005.0298900 | POLE | Non-HFTD | Distribution | 2025-08-15 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002133 | 216255522-78069-DETAIL-05_20_2025-GO95HV-1^06243006.0068400 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002134 | 759093073-69649-DETAIL-06_10_2025-GO95HV-1^06245006.0195240 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002135 | 759153688-75390-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244411 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002136 | 759671818-20669-DETAIL-04_06_2023-CUSTWIRE-1^06245006.0245400 | OTHER | Non-HFTD | Distribution | 2023-04-06 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002137 | 759724049-56619-DTLSB-03_25_2026-GO95HV-1^06242009.0041201 | OTHER | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002138 | 759760635-23951-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0366803 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002139 | 759942966-39281-DETAIL-08_07_2025-ABNDEQPM-1^06246001.0191000 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002140 | 760458381-77130-DTLTRT-05_28_2025-GO95HV-1^668075/00 3/007 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002141 | 790235282-1880-DETAIL-02_13_2025-SVCDEFLC-1^06240004.0168000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002142 | 790280224-12322-DETAIL-10_15_2025-GO95BLTC-1^06246011.0182703 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002143 | 790414071-40399-DTLSB-07_17_2025-ABNDEQPM-1^06244006.0217302 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002144 | 790430779-64362-DETAIL-08_25_2025-GO95HV-1^06246001.0206501 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002145 | 790819800-27762-DTLTRT-05_14_2026-GO95HV-1^668086/00 9/004 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002146 | 790836359-71409-DETAIL-04_09_2024-CUTOUTAR-1^06147005.0217601 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002147 | 791176347-87590-DETAIL-01_12_2026-COVCOTHR-2^06239004.0244843 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002148 | 760900782-1782-DETAIL-02_19_2025-GO95HV-1^06240004.0219913 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002149 | 760923476-27181-DETAIL-09_03_2025-GO95HV-1^06246001.0177302 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002150 | 761176175-6275-DETAIL-06_05_2025-GO95HV-1^06148014.0236601 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002151 | 761488369-85870-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 3/062 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002152 | 761704322-63250-DETAIL-01_23_2025-GO95HV-1^06239004.0257705 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002153 | 761843515-26049-DTLSB-07_01_2025-SVCROOF-1^06244006.0225403 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002154 | 761855621-3430-DTLTRT-05_28_2025-GO95MLD-1^668075/00 12/005 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002155 | 761855621-3430-DTLTRT-05_28_2025-GO95MLD-2^668075/00 12/005 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002156 | 761871945-41589-DTLSB-01_27_2026-BIRDDMG-1^06242009.0057400 | POLE | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002157 | 761911310-8981-DETAIL-03_13_2024-GO95MLD-1^06147004.0180800 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002158 | 762263476-21399-DETAIL-04_01_2024-CUSTWIRE-1^06147005.0124900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002159 | 762456824-99809-DETAIL-10_15_2025-GO95HV-1^06246012.0132701 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002160 | 762536729-45083-DETAIL-08_19_2025-SVCDEFLC-1^07216001.0175906 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002161 | 7625933-85229-ADMIN-10_27_2025-GRDRODHI-1^06246001.0014601 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002162 | 762810264-72859-DTLTRT-04_21_2026-GO95HV-1^668004/02 15/008 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002163 | 791176347-87590-DETAIL-01_12_2026-SVCROAD-1^06239004.0244843 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002164 | 791176347-87590-DETAIL-02_03_2025-GO95MLD-1^06239004.0244843 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002165 | 791364045-36762-DETAIL-05_15_2024-GO95MLD-1^06142012.0122700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002166 | 791435076-55076-DETAIL-01_22_2026-GUYHINS-1^06239004.0227301 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002167 | 791435076-55076-DETAIL-01_29_2025-GO95HV-1^06239004.0227301 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002168 | 791473531-76162-DETAIL-05_14_2025-GO95HV-1^06142012.0119902 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002169 | 791774398-59749-ADMIN-03_19_2025-POLEREPL-1^06245006.0155301 | POLE | Non-HFTD | Distribution | 2025-03-19 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002170 | 792476784-35999-DETAIL-09_04_2025-GO95MLD-1^06147001.0319501 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002171 | 76329608-29769-ADMIN-12_21_2022-GUYHINS-1^668005/00 11/032 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002172 | 763445544-3131-DETAIL-04_08_2025-GO95TCH-1^06241005.0012601 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002173 | 763465928-2689-DETAIL-09_03_2025-GRDRODHI-1^06247006.0295200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002174 | 763553726-94759-DETAIL-04_30_2026-GO95HV-1^668004/00 11/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002175 | 763553726-94760-DETAIL-04_30_2026-GO95HV-1^668004/00 11/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002176 | 763708698-79829-DETAIL-04_23_2025-GO95CLSV-1^06242006.0039401 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002177 | 7638284-69910-DETAIL-03_13_2025-GO95MLD-1^06238004.0151003 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002178 | 764022535-87393-DETAIL-08_19_2025-ABNDEQPM-1^06247006.0367001 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002179 | 764041548-17889-DETAIL-10_09_2025-GO95HV-1^06148001.0155300 | OTHER | Non-HFTD | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002180 | 764092656-17419-DTLSB-07_08_2026-GO95HV-1^06242009.0246202 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002181 | 764208369-50469-DTLSB-07_02_2025-GO95HV-1^06244007.0136403 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002182 | 764292773-97891-ADMIN-10_21_2025-GO95HV-1^06247001.0268900 | OTHER | Non-HFTD | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002183 | 764547221-55809-DETAIL-09_03_2025-GO95HV-1^06247006.0211401 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002184 | 764586625-8570-DETAIL-01_27_2026-GO95HV-1^06239002.0062402 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002185 | 764602376-44376-DETAIL-05_29_2025-GO95HV-1^06148014.0360201 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002186 | 764741982-15149-DTLSB-07_21_2025-ABNDEQPM-1^06244006.0230800 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002187 | 827270376-49889-DETAIL-03_06_2024-CUSTWIRE-1^06245007.0275500 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002188 | 827337409-22030-DTLTRT-05_27_2025-GO95HV-1^668075/00 1/004 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002189 | 827941939-77413-DETAIL-09_10_2025-GO95HV-1^06246007.0249950 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002190 | 828022075-59982-DTLTRT-07_03_2025-GUYLOINS-2^668087/00 3/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002191 | 828099948-889-DETAIL-06_10_2025-GO95CLSV-1^06245006.0205000 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002192 | 828099948-889-DETAIL-06_10_2025-GO95HV-1^06245006.0205000 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002193 | 828534038-54923-ADMIN-06_11_2026-POLEDERP-1^07217001.0273202 | POLE | Non-HFTD | Distribution | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002194 | 82857760-79760-DETAIL-07_22_2025-GO95HV-1^06247005.0175302 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002195 | 766181139-20070-DETAIL-04_06_2026-GO95MLD-1^06236005.0165400 | OTHER | HFTD Tier 2 | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002196 | 766276768-13849-DTLSB-04_22_2024-GO95MLD-1^06245007.0225401 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002197 | 76640489-36899-DTLSB-07_08_2025-BIRDDMG-1^06244007.0037300 | POLE | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002198 | 766696413-44799-DETAIL-05_28_2025-GO95HV-1^06244006.0090801 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002199 | 766883132-79159-DETAIL-06_03_2025-GO95HV-1^06245007.0262001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002200 | 766934054-75153-DETAIL-05_21_2026-GO95HV-1^07217001.0142502 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002201 | 767016933-12730-DETAIL-02_25_2025-SVCDEFLC-1^06240004.0150904 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002202 | 767016933-12730-DETAIL-03_09_2026-SVCDEFLC-1^06240004.0150904 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002203 | 767232573-36459-DTLTRT-04_20_2026-GO95HV-1^668004/02 4/003 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002204 | 767464261-47261-DTLSB-04_25_2024-CUSTWIRE-1^06245007.0229646 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002205 | 767465980-86749-DETAIL-09_09_2025-GO95HV-1^07218001.0175602 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002206 | 767852661-27802-DTLTRT-04_27_2026-GO95HV-1^668004/00 7/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002207 | 768347623-95599-DETAIL-09_17_2025-GO95HV-1^06147001.0237900 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002208 | 768609673-8330-DTLSB-07_29_2025-GO95HV-1^07218001.0264602 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002209 | 768609673-8330-DTLSB-07_29_2025-GRDRODHI-1^07218001.0264602 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002210 | 742739988-69988-DETAIL-06_18_2025-GO95HV-1^668075/00 15/048 | OTHER | HFTD Tier 2 | Transmission | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002211 | 742771171-39809-DETAIL-08_27_2025-GO95HV-1^06247006.0187801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002212 | 742810813-36569-DETAIL-07_30_2025-GO95HV-1^06247005.0213000 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002213 | 742811448-71031-DETAIL-09_09_2025-GO95HV-1^06146001.0045000 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002214 | 742893611-38173-DETAIL-09_15_2025-GO95HV-1^06248007.0279901 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002215 | 742949597-24523-DETAIL-05_27_2026-GO95HV-1^07217001.0145103 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002216 | 743746514-29039-DETAIL-04_23_2026-GO95HV-1^06142012.0144300 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002217 | 743809826-21179-DTLSB-07_08_2025-SVCNEUT-1^06244007.0035806 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002218 | 744017485-49423-DTLSB-04_30_2024-CUSTWIRE-1^06245007.0223900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002219 | 744017485-49423-DTLSB-04_30_2024-CUSTWIRE-2^06245007.0223900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002220 | 744218393-23653-DETAIL-05_27_2026-GO95HV-1^07217001.0149600 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002221 | 744274591-34541-DTLTRT-04_28_2026-GO95HV-1^668004/00 5/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002222 | 744274591-82732-DTLTRT-04_28_2026-GO95HV-1^668004/00 5/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002223 | 744557883-45109-DETAIL-08_21_2025-GO95HV-1^06247006.0259901 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002224 | 744990934-55060-DETAIL-01_23_2025-GO95TCH-1^06239004.0257809 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002225 | 79396443-67599-DETAIL-09_17_2025-GO95HV-1^06147001.0237703 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002226 | 794125095-37095-DETAIL-05_29_2025-GO95HV-1^06147014.0018800 | OTHER | HFTD Tier 2 | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002227 | 79416860-99399-ADMIN-02_19_2025-POLEREPL-1^06245007.0218803 | POLE | Non-HFTD | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002228 | 794254106-74106-DETAIL-01_29_2025-GO95MLD-1^06239004.0251700 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002229 | 794258428-78919-DTLSB-04_15_2026-GRDRODHI-1^06241008.0056000 | OTHER | Non-HFTD | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002230 | 794549708-77749-DTLSB-07_16_2025-GO95HV-1^06244006.0293801 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002231 | 794629056-43150-DETAIL-07_06_2026-GO95HV-1^07218001.0342401 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002232 | 794631796-42072-DETAIL-08_07_2025-GO95HV-1^06246002.0234201 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002233 | 74664518-54389-DTLSB-07_08_2025-GO95HV-1^06244007.0038903 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002234 | 74665906-43793-DETAIL-09_17_2025-GO95MLD-1^07218001.0088201 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002235 | 747011516-64599-DETAIL-04_01_2024-CUSTWIRE-1^06247005.0347101 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002236 | 747267431-38211-DETAIL-02_18_2025-CUSTWIRE-1^06239004.0364600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002237 | 747341889-4933-DETAIL-09_09_2025-GO95HV-1^07218001.0176402 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002238 | 747496170-17699-DETAIL-06_18_2025-GO95HV-1^06248004.0340602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002239 | 74782155-29600-DETAIL-04_08_2026-GO95HV-1^06240002.0328300 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002240 | 747865140-87540-DETAIL-06_05_2025-GO95HV-1^668075/00 14/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002241 | 748220191-15279-DETAIL-10_02_2025-GO95BLTC-1^06246008.0066700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002242 | 748220191-15279-DETAIL-10_02_2025-SVCTREE-1^06246008.0066700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002243 | 748263039-61599-DTLSB-04_10_2024-POLETOP-1^06245007.0222005 | POLE | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002244 | 748650370-92589-DTLSB-02_09_2026-GRDRODHI-1^06243010.0365200 | OTHER | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002245 | 748855478-51709-DETAIL-03_28_2024-CUSTWIRE-1^06147005.0117003 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002246 | 748887237-67439-DTLSB-08_18_2025-GO95HV-1^07218001.0352000 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002247 | 770155166-43990-DETAIL-03_31_2026-COVCOTHR-1^06240004.0358441 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002248 | 770155166-43990-DETAIL-03_31_2026-COVCOTHR-2^06240004.0358441 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002249 | 77017278-30059-DTLTRT-05_06_2026-GO95HV-1^668004/00 6/021 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002250 | 770553045-43409-DETAIL-08_21_2025-GO95HV-1^06247006.0265800 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002251 | 770660053-7009-DETAIL-07_31_2025-GO95HV-1^06247006.0209302 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002252 | 770700608-46859-DETAIL-03_21_2024-CUSTWIRE-1^06246005.0073002 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002253 | 770791198-12970-DETAIL-03_23_2026-COVCOTHR-1^06240004.0227501 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002254 | 750661946-76850-DETAIL-04_06_2026-PWRTRN-1^06236005.0115801 | OTHER | HFTD Tier 2 | Distribution | 2026-04-06 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002255 | 751041197-32197-DETAIL-05_30_2024-CUSTWIRE-1^06246005.0273210 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002256 | 751163708-21699-DTLSB-07_01_2025-GO95HV-1^06244006.0224403 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002257 | 751163708-21699-DTLSB-07_01_2025-GO95MLD-1^06244006.0224403 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002258 | 75123920-72700-DTLTRT-05_05_2026-GO95HV-1^668004/00 10X/001 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002259 | 751417745-2059-DETAIL-09_16_2025-GO95HV-1^06247004.0183600 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002260 | 751524268-51689-DTLSB-07_09_2025-GO95HV-1^06244006.0276903 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002261 | 751953161-90659-DETAIL-06_18_2025-GO95HV-1^06248004.0340700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002262 | 752003301-7561-DETAIL-09_11_2025-GO95HV-1^07216001.0075601 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002263 | 752144144-19409-DETAIL-09_03_2025-GO95HV-1^06247006.0174000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002264 | 752191908-24661-DTLSB-05_05_2026-GO95HV-1^06142013.0153200 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002265 | 752319628-29999-DETAIL-04_10_2024-GO95HV-1^06147005.0212900 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002266 | 752454018-27261-DTLSB-05_16_2024-GO95HV-1^06244002.0208500 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002267 | 752492861-57280-DETAIL-02_16_2026-GO95HV-1^06239001.0046702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002268 | 771029871-64912-ADMIN-03_27_2024-ABNDEQPM-1^06147004.0056902 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002269 | 771583525-73789-DETAIL-09_24_2025-GO95HV-1^06247006.0259801 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002270 | 771607878-11099-DETAIL-08_19_2025-GO95HV-1^06246002.0368200 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002271 | 77165274-10979-DETAIL-09_23_2025-SVCENTCO-1^06247004.0075500 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002272 | 771872543-34912-DETAIL-06_10_2026-GUYHINS-2^668086/00 9/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002273 | 771872543-34912-DETAIL-06_10_2026-GUYHINS-4^668086/00 9/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002274 | 772032095-92329-DETAIL-05_13_2025-GO95HV-1^06142012.0016500 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002275 | 772033154-63159-DETAIL-08_15_2024-GO95MLD-1^06246005.0130101 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002276 | 214659072-79223-DETAIL-03_31_2025-GO95MLD-1^06241005.0116605 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002277 | 214799813-14249-DTLSB-07_21_2025-GO95HV-1^06244006.0257900 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002278 | 214903439-6669-DTLSB-07_16_2025-GO95HV-1^06244006.0318800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002279 | 215267313-80650-DETAIL-04_20_2026-GO95HV-1^06142012.0145902 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002280 | 215639996-88410-DRONE_HY-06_19_2026-XARMSPCR-1^06238004.0224642 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002281 | 215683419-49852-DTLSB-07_15_2025-GO95HV-1^06244006.0308440 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002282 | 215698114-80322-DETAIL-05_07_2025-GO95HV-1^06242007.0265901 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002283 | 215762740-9201-DETAIL-01_15_2026-GUYNOINS-1^06239004.0136216 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002284 | 752545828-56689-DETAIL-08_27_2025-GO95HV-1^06247006.0284900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002285 | 752549951-30561-DTLTRT-04_23_2026-GO95HV-1^668004/00 6/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002286 | 752785054-82761-DETAIL-09_08_2025-GO95HV-1^06147001.0299300 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002287 | 75302220-87218-ADMIN-03_13_2025-POLEREPL-2^06245007.0217703 | POLE | Non-HFTD | Distribution | 2025-03-13 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002288 | 753068270-78068-DETAIL-07_02_2026-GO95HV-1^07217001.0048600 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002289 | 753168184-34869-DETAIL-07_05_2024-CUSTWIRE-1^06244005.0125801 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002290 | 753205683-49150-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0134142 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002291 | 715589231-55761-DTLSB-05_07_2026-GO95HV-1^06142013.0346400 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002292 | 715668653-99061-ADMIN-10_22_2025-GUYHINS-1^06246001.0023400 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002293 | 715758381-73480-DETAIL-02_13_2025-GO95TCH-1^06240004.0168242 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002294 | 715893628-97889-DETAIL-10_09_2025-GO95HV-1^06148001.0151300 | OTHER | Non-HFTD | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002295 | 715937382-66830-DTLTRT-04_29_2026-GO95HV-1^668004/00 5/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002296 | 715937382-95459-DTLTRT-04_29_2026-GO95HV-1^668004/00 5/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002297 | 716115674-56829-DETAIL-04_19_2022-CUSTWIRE-1^06142012.0131804 | OTHER | Non-HFTD | Distribution | 2022-04-19 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002298 | 717493605-56379-DETAIL-09_02_2025-GO95HV-1^06247006.0279400 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002299 | 717534474-89739-DETAIL-05_29_2025-GO95HV-1^06244006.0159802 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002300 | 717593391-47771-DTLSB-05_28_2026-GO95HV-1^07216001.0020504 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002301 | 717637732-18419-DTLSB-07_09_2026-GO95HV-1^06240008.0146600 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002302 | 717651370-98771-DETAIL-09_11_2025-GO95HV-1^06147001.0106801 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002303 | 717725679-48649-DTLSB-06_11_2026-GO95HV-1^07217001.0353500 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002304 | 718255480-50789-DETAIL-03_21_2024-GO95MLD-1^06246005.0063500 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002305 | 718336323-71809-DETAIL-08_28_2025-GO95HV-1^06247006.0075800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002306 | 71855685-58909-DETAIL-08_13_2025-SVCENTCO-1^06247006.0259501 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002307 | 718980741-65850-DETAIL-03_04_2026-GO95HV-1^06239003.0186700 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002308 | 719217732-24520-DETAIL-03_19_2025-SVCENTCO-1^06240004.0289001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002309 | 719223463-58771-ADMIN-01_30_2026-POLEREPL-1^07216001.0214902 | POLE | Non-HFTD | Distribution | 2026-01-30 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002310 | 719226006-8959-DTLSB-08_18_2025-GO95HV-1^07218001.0355703 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002311 | 71923136-45136-DETAIL-06_02_2025-GO95HV-1^06148014.0257900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002312 | 719327068-16159-DTLTRT-06_09_2021-UNIGRDSG-1^668041/00 1/017 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002313 | 719334260-37260-DETAIL-05_06_2025-GO95HV-1^06243006.0032830 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002314 | 794690014-79241-DETAIL-04_09_2025-GUYHINS-2^06241005.0037900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-09 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002315 | 794869518-34729-DETAIL-04_23_2025-GO95HV-1^06242006.0039002 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002316 | 794970373-36852-DETAIL-06_21_2023-CUSTWIRE-1^06244009.0306901 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002317 | 795110400-72070-DETAIL-02_19_2026-GO95HV-1^06239002.0029502 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002318 | 795234915-45915-DETAIL-06_05_2025-GO95HV-1^06148014.0245802 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002319 | 795281667-64479-DETAIL-04_28_2025-GUYHINS-1^06242006.0104900 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-04-28 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002320 | 79528898-24502-DETAIL-04_07_2025-SVCDEFLC-1^06241005.0119000 | OTHER | HFTD Tier 3 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002321 | 722307888-94881-ADMIN-11_12_2025-GO95HV-1^06246001.0335700 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002322 | 722823853-799-DETAIL-05_28_2025-GO95HV-1^06244006.0094100 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002323 | 723127633-68881-ADMIN-11_13_2025-GO95HV-1^06246001.0325401 | OTHER | Non-HFTD | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002324 | 723337738-20939-DTLSB-06_30_2025-GO95HV-1^06244006.0223300 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002325 | 723514761-66639-DETAIL-05_07_2025-GO95HV-1^06243006.0014701 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002326 | 724694293-8291-DRONE_HY-07_10_2026-DISTHDWR-1^06143014.0189200 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002327 | 725185119-45890-DETAIL-01_16_2025-ABNDEQPM-1^06239004.0257303 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002328 | 725450944-7339-DETAIL-04_17_2025-GO95MLD-1^06242005.0361501 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002329 | 725462385-19699-ADMIN-10_22_2025-GO95BLTC-1^06246011.0052502 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002330 | 725492808-54039-DETAIL-04_22_2026-GO95HV-1^06142012.0142701 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002331 | 725614684-68519-DTLTRT-08_17_2022-UBPBXARM-1^668005/00 1/095 | CROSSARM | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002332 | 725737842-65419-DTLSB-07_09_2026-GO95HV-1^06240008.0141200 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002333 | 726319624-17759-DETAIL-06_16_2025-GO95HV-1^06248005.0368900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002334 | 726347675-45009-DETAIL-08_12_2025-SVCDEFLC-1^06247006.0250401 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002335 | 754601623-91721-DETAIL-04_15_2026-SVCTREE-3^06237004.0206500 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002336 | 755069736-71340-DETAIL-02_24_2025-RISEGRD-1^06240004.0153600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002337 | 755497697-35961-DTLTRT-06_23_2025-SVCNEUT-1^668087/00 15/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002338 | 755525406-510-AUDIT-04_02_2025-GRDRODHI-1^06238004.0223543 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002339 | 75554298-48260-DETAIL-09_15_2025-GO95HV-1^07219001.0327300 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002340 | 755580684-23360-DETAIL-01_21_2025-GO95TCH-1^06239004.0255301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002341 | 755592811-4811-DETAIL-05_14_2025-GO95BLTC-1^06242006.0196622 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002342 | 755654588-55588-DETAIL-09_24_2025-GO95HV-1^07218001.0229102 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002343 | 728720836-3836-DTLSB-01_20_2026-GO95HV-1^06242009.0298005 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002344 | 728750533-79262-DETAIL-05_05_2025-GO95HV-1^06243006.0060740 | OTHER | HFTD Tier 2 | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002345 | 728801569-97701-ADMIN-11_07_2025-GO95MLD-1^06246001.0292900 | OTHER | Non-HFTD | Distribution | 2025-11-07 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002346 | 72881401-97043-DETAIL-07_01_2026-GO95TCH-1^07217001.0169600 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002347 | 728922198-85659-DTLSB-08_12_2025-GO95HV-1^07217001.0027301 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002348 | 729062528-95779-DETAIL-08_07_2025-GO95HV-1^06246002.0269902 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002349 | 729293703-82921-ADMIN-02_18_2025-ANCHIDLE-1^06239004.0362506 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002350 | 729453995-66603-DTLSB-06_03_2026-SVCROAD-1^07216001.0027301 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002351 | 729460363-85001-DETAIL-04_21_2022-CUSTWIRE-1^06142012.0246803 | OTHER | Non-HFTD | Distribution | 2022-04-21 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002352 | 72995716-23091-DETAIL-05_12_2026-GO95HV-1^668038/00 6/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002353 | 729998211-79811-DETAIL-04_14_2026-COVCOTHR-1^06237004.0171701 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-04-14 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002354 | 730075765-21700-DETAIL-04_08_2026-GO95HV-1^06240002.0324301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002355 | 730206639-97770-DETAIL-01_29_2025-SVCDEFLC-1^06240004.0161403 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002356 | 730206639-97770-DETAIL-01_29_2025-SVCDEFLC-2^06240004.0161403 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002357 | 73052328-61200-DETAIL-08_21_2025-GO95HV-1^06246001.0202000 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002358 | 755766016-13359-DTLTRT-05_07_2026-GO95HV-1^668004/00 16/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002359 | 755893298-69471-ADMIN-11_12_2025-GRDRODHI-1^06246001.0334001 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002360 | 755958615-10370-DETAIL-01_23_2026-GO95HV-1^06240003.0183800 | OTHER | HFTD Tier 2 | Distribution | 2026-01-23 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002361 | 756115820-41170-DETAIL-02_19_2026-GO95HV-1^06239002.0012500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002362 | 756260414-28719-DTLSB-04_16_2026-GO95HV-1^06241009.0137301 | OTHER | Non-HFTD | Distribution | 2026-04-16 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002363 | 756496956-42949-DTLSB-07_08_2025-BIRDDMG-1^06244007.0038701 | POLE | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002364 | 756496956-42949-DTLSB-07_08_2025-GO95HV-1^06244007.0038701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002365 | 756606727-19490-DETAIL-02_03_2025-GO95HV-1^06239004.0244845 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002366 | 211198864-39864-DETAIL-06_18_2025-GO95HV-1^06248004.0364045 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002367 | 697203295-88410-DETAIL-03_12_2025-SVCENTCO-1^06238004.0224600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002368 | 697610604-3069-DETAIL-09_15_2025-GO95HV-1^06248007.0264700 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002369 | 697666484-74211-DETAIL-09_29_2025-GUYHINS-1^06148001.0312603 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002370 | 697714928-97360-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 8/053 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002371 | 697747948-20311-DETAIL-04_21_2026-GO95HV-1^06142012.0141903 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002372 | 69780505-37129-DETAIL-04_26_2022-CUSTWIRE-1^06143012.0258201 | OTHER | Non-HFTD | Distribution | 2022-04-26 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002373 | 69787839-66929-DETAIL-04_23_2025-GO95MLD-1^06242006.0037808 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002374 | 698080628-11911-DTLTRT-06_23_2025-GO95MLD-1^668087/00 17/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002375 | 698491235-52229-DETAIL-05_13_2025-GRDRODHI-1^06142012.0015602 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002376 | 698622532-72859-AUDIT-09_09_2025-GO95MLD-1^07216001.0177303 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002377 | 698770638-37329-DTLSB-05_06_2026-GO95HV-1^06142013.0287700 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002378 | 69878709-20739-DTLTRT-06_24_2025-BIRDDMG-1^668087/00 8/004 | POLE | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002379 | 698802211-12029-DTLSB-08_15_2023-CUSTWIRE-1^06243009.0244401 | OTHER | Non-HFTD | Distribution | 2023-08-15 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002380 | 732568916-57249-DTLSB-06_26_2025-BIRDDMG-1^06244007.0108500 | POLE | HFTD Tier 2 | Distribution | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002381 | 732863711-33580-DETAIL-02_23_2026-GO95HV-1^06239002.0035402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002382 | 733038590-55129-DTLSB-08_03_2023-CUSTWIRE-1^06243009.0144001 | OTHER | Non-HFTD | Distribution | 2023-08-03 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002383 | 733297761-70211-DETAIL-09_10_2025-CLRTOUCH-1^06147001.0077801 | CONDUCTOR | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002384 | 733312146-55871-DETAIL-04_14_2025-GUYHINS-1^06241005.0013540 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-14 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002385 | 73359396-52369-DETAIL-04_24_2025-GO95HV-1^06242006.0198700 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002386 | 73369479-22479-ADMIN-11_12_2025-GO95HV-1^06246001.0286500 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002387 | 700216310-42269-DTLTRT-06_02_2021-GO95HV-1^668041/00 13/003 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002388 | 700224822-20980-DETAIL-03_12_2026-SVCDEFLC-1^06240004.0298102 | OTHER | HFTD Tier 3 | Distribution | 2026-03-12 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002389 | 700418883-36029-DTLSB-09_08_2023-CUSTWIRE-1^06243008.0262801 | OTHER | HFTD Tier 2 | Distribution | 2023-09-08 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002390 | 700833214-96351-DTLSB-07_25_2022-CUSTWIRE-1^06242005.0238701 | OTHER | HFTD Tier 2 | Distribution | 2022-07-25 | 2025-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002391 | 700955638-36638-DTLSB-06_15_2026-SVCTREE-1^07217001.0276740 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002392 | 701129675-98589-DETAIL-10_06_2025-GO95HV-1^06148001.0185001 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002393 | 701618809-57281-DETAIL-02_24_2025-GO95TCH-1^06241005.0153100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002394 | 702196856-4989-DETAIL-08_07_2025-GO95HV-1^06246002.0234900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002395 | 702255521-23801-DETAIL-01_14_2025-SVCWIND-1^06239004.0255244 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002396 | 702355805-68609-ADMIN-10_20_2025-GO95HV-1^06246012.0113401 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002397 | 702649513-89599-DETAIL-06_11_2025-ENCHRW-1^06245007.0269600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002398 | 703595444-85421-DETAIL-04_22_2026-XARMSPCR-1^668041/00 17/028 | CROSSARM | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002399 | 704433828-39829-DETAIL-04_23_2025-GO95HV-1^06242006.0109803 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002400 | 704548086-11859-DTLTRT-05_04_2026-GO95HV-1^668004/00 3/019 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002401 | 733719581-55639-DETAIL-05_07_2025-GO95HV-1^06243006.0017800 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002402 | 733949403-4841-DETAIL-03_05_2025-GUYHINS-1^06241005.0131904 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002403 | 734114633-88569-DETAIL-03_10_2026-XARMSPCR-1^668041/00 13/025 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002404 | 734178974-40200-DETAIL-02_09_2026-GO95HV-1^06239003.0016909 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002405 | 734251934-24639-DETAIL-08_28_2025-GO95HV-1^07216001.0166803 | OTHER | Non-HFTD | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002406 | 734831899-84749-DTLSB-07_01_2025-GO95HV-1^06244007.0130700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002407 | 735096324-22283-DETAIL-07_29_2025-GO95HV-1^06247005.0277002 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002408 | 735302023-68629-DTLSB-01_21_2026-GO95BLTC-1^06242009.0296001 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002409 | 706679088-3689-DETAIL-06_17_2025-SVCROAD-1^06248004.0299108 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002410 | 706810812-28453-DETAIL-06_30_2026-GO95HV-1^07217001.0222602 | OTHER | Non-HFTD | Distribution | 2026-06-30 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002411 | 706813873-94109-DETAIL-08_21_2025-GO95HV-1^06247006.0258901 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002412 | 211412389-51739-DTLTRT-06_24_2025-SVCROAD-1^668087/00 16/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002413 | 211422080-88002-DETAIL-07_03_2024-CUSTWIRE-1^06244005.0236802 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002414 | 2114593-72639-DETAIL-05_28_2025-GO95HV-1^06244006.0104900 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002415 | 211633270-75650-DTLSB-06_08_2026-SVCROAD-1^07216001.0029900 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002416 | 211657805-73879-DETAIL-09_23_2025-GO95CL10-1^06247004.0180601 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002417 | 706956650-19170-DETAIL-02_19_2026-GO95HV-1^06239002.0015601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002418 | 707214863-3979-DTLSB-08_21_2023-CUSTWIRE-1^06243009.0286901 | OTHER | Non-HFTD | Distribution | 2023-08-21 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002419 | 707530833-45089-DETAIL-10_01_2025-GO95BLTC-1^06246009.0123201 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002420 | 707738818-24341-ADMIN-11_10_2025-POLEDERP-1^668087/00 2/017 | POLE | Non-HFTD | Transmission | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002421 | 707738818-24341-DTLTRT-07_01_2025-GUYNOINS-1^668087/00 2/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002422 | 707738818-24341-DTLTRT-07_01_2025-GUYNOINS-2^668087/00 2/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002423 | 707738818-24341-DTLTRT-07_01_2025-GUYNOINS-4^668087/00 2/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002424 | 77275301-61580-DETAIL-02_23_2026-GO95HV-1^06239002.0034400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002425 | 772859397-46139-DTLSB-08_14_2025-GO95BLTC-1^07218001.0350801 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002426 | 773048158-59350-DETAIL-02_11_2026-GO95HV-1^06239003.0016203 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002427 | 773157776-70970-DETAIL-01_23_2025-GO95MLD-1^06239004.0256740 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002428 | 773265285-49849-DTLSB-07_10_2025-GO95HV-1^06244007.0111741 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002429 | 773601151-85022-DTLSB-05_07_2026-GO95HV-1^06142013.0348701 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002430 | 773843881-11622-DETAIL-09_10_2025-GO95HV-1^06147001.0083701 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002431 | 773954410-78753-DETAIL-09_04_2025-GO95HV-1^06247006.0160100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002432 | 708595885-95979-DETAIL-07_23_2025-GO95HV-1^06247005.0124500 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002433 | 709197374-90860-DETAIL-01_22_2025-GO95TCH-1^06239004.0255700 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002434 | 709373591-7620-DETAIL-03_11_2026-COVCOTHR-1^06240004.0278400 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002435 | 710187254-75639-DTLSB-09_20_2022-CUSTWIRE-1^06243005.0110200 | OTHER | Non-HFTD | Distribution | 2022-09-20 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002436 | 710240910-16251-DTLTRT-04_27_2026-GO95HV-1^668004/00 2/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002437 | 710240910-822-DTLTRT-04_27_2026-GO95HV-1^668004/00 2/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002438 | 710270600-66251-DETAIL-02_11_2026-GO95HV-1^06239002.0070400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002439 | 710271715-45329-DETAIL-05_13_2025-GO95HV-1^06142012.0013504 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002440 | 710540690-35851-ADMIN-10_21_2025-SVCNEUT-1^06247001.0245800 | OTHER | Non-HFTD | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002441 | 710541701-2839-DETAIL-05_19_2025-GO95HV-1^06243006.0274300 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002442 | 710711222-82559-DETAIL-07_22_2025-GO95HV-1^06247005.0177701 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002443 | 710780354-3539-DETAIL-05_28_2025-GO95HV-1^06244006.0103903 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002444 | 711472121-4779-DETAIL-10_02_2025-GO95HV-1^06148001.0305700 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002445 | 711549168-89651-DTLSB-05_06_2026-GO95HV-1^06142013.0274000 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002446 | 711802361-11169-DTLTRT-05_12_2026-GO95HV-1^668004/00 4/010 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002447 | 679168492-86460-DETAIL-04_29_2026-GO95HV-1^668004/00 7/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002448 | 679193636-64470-DETAIL-02_06_2025-GO95BLTC-1^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002449 | 679193636-64470-DETAIL-02_06_2025-GO95HV-1^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002450 | 679193636-64470-DETAIL-02_06_2025-SVCROAD-1^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002451 | 679193636-64470-DETAIL-02_06_2025-SVCROAD-2^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002452 | 679328839-97499-DTLSB-06_30_2025-BIRDDMG-1^06244007.0035103 | POLE | HFTD Tier 2 | Distribution | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002453 | 679328839-97499-DTLSB-06_30_2025-GO95HV-1^06244007.0035103 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002454 | 679391395-7379-DETAIL-03_28_2024-GO95HV-1^06147005.0118500 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002455 | 679884106-78070-DETAIL-01_23_2025-GO95HV-1^06239004.0256645 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002456 | 679911591-73591-DETAIL-09_24_2025-GO95HV-1^07218001.0222301 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002457 | 680397926-54310-DETAIL-03_13_2025-GO95HV-1^06238004.0222900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002458 | 680441279-4361-DETAIL-03_18_2024-CUTOUTAR-3^06245002.0038300 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002459 | 680531172-86089-AUDIT-06_03_2025-GRDRODHI-1^06243006.0068202 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002460 | 680531172-86089-DETAIL-05_20_2025-GO95HV-1^06243006.0068202 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002461 | 680821192-7559-DETAIL-04_29_2026-GO95HV-1^668004/00 6/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002462 | 681069188-28989-DETAIL-08_14_2025-GO95HV-1^06246002.0264802 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002463 | 737969759-49169-ADMIN-07_24_2020-INSULPLM-1^668041/00 4/020 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2020-07-24 | 2023-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002464 | 737998558-25469-DETAIL-09_02_2025-GO95HV-1^06247006.0275900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002465 | 737998558-25469-DETAIL-09_02_2025-GRDRODHI-2^06247006.0275900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002466 | 738063082-55559-DTLTRT-04_29_2026-GO95HV-1^668004/00 3/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002467 | 738063082-55560-DTLTRT-04_29_2026-GO95HV-1^668004/00 3/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002468 | 738094749-12421-DETAIL-09_05_2025-GO95HV-1^06147001.0294701 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002469 | 738436118-1869-DETAIL-06_03_2025-GO95HV-1^06245007.0365900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002470 | 73858096-32900-DETAIL-08_06_2025-GO95HV-1^06246002.0037300 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002471 | 683401280-73169-DETAIL-09_29_2025-GO95HV-1^06246009.0138100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002472 | 683650461-31739-DETAIL-05_07_2025-GO95HV-1^06243006.0022502 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002473 | 683740977-99049-DETAIL-06_10_2025-GO95HV-1^06245006.0292600 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002474 | 683752939-56771-DETAIL-09_04_2025-GO95HV-1^06146001.0050400 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002475 | 684010899-23070-DETAIL-06_11_2025-GO95HV-1^06236005.0220942 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002476 | 684235229-17229-DTLTRT-07_01_2025-GUYNOINS-1^668087/00 13/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002477 | 684235229-17229-DTLTRT-07_01_2025-GUYNOINS-2^668087/00 13/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002478 | 684235229-23029-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 13/015 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002479 | 684235229-44029-DTLTRT-07_01_2025-GUYNOINS-2^668087/00 13/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002480 | 684697635-42100-DETAIL-02_25_2026-BIRDDMG-1^06239003.0242201 | POLE | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002481 | 685079480-22859-DETAIL-06_16_2025-GO95HV-1^06248005.0332901 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002482 | 68531594-89279-DETAIL-06_02_2025-GO95HV-1^06244006.0158400 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002483 | 685395941-69130-DETAIL-03_26_2026-COVCOTHR-2^06240004.0206401 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002484 | 685616579-3549-DTLSB-07_16_2025-GO95HV-1^06244006.0317041 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002485 | 685987703-88451-DETAIL-03_04_2025-GO95MLD-1^06241005.0130502 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002486 | 712625619-83099-DETAIL-01_12_2026-COVCOTHR-2^06239004.0243400 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002487 | 712625619-83099-DETAIL-01_12_2026-SVCDEFLC-1^06239004.0243400 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002488 | 712625619-83099-DETAIL-01_28_2025-SVCROAD-1^06239004.0243400 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002489 | 712734139-14240-DETAIL-03_05_2026-GUYHINS-1^06238004.0011803 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002490 | 712734139-14240-DETAIL-03_05_2026-GUYHINS-2^06238004.0011803 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002491 | 712916004-44939-DETAIL-05_07_2025-GO95HV-1^06243006.0100901 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002492 | 713276879-27879-DETAIL-03_30_2026-SVCDEFLC-1^06240004.0272141 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002493 | 713793311-45419-DTLSB-04_08_2026-GO95HV-1^06241009.0105400 | OTHER | Non-HFTD | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002494 | 68737908-19919-DTLSB-05_12_2026-BIRDDMG-1^06242009.0286601 | POLE | Non-HFTD | Distribution | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002495 | 68737908-19919-DTLSB-05_12_2026-GO95HV-1^06242009.0286601 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002496 | 687809968-659-DETAIL-09_03_2025-SVCDEFLC-1^07216001.0091040 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002497 | 687822904-95229-DETAIL-04_28_2025-GO95HV-1^06242007.0248100 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002498 | 687968226-79489-DETAIL-10_08_2025-GO95HV-1^06148001.0204200 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002499 | 68869901-39480-DETAIL-02_23_2026-GO95HV-1^06239002.0034402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002500 | 688796978-96281-DETAIL-04_27_2026-GO95HV-1^06142012.0147804 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002501 | 688982649-28299-DTLSB-04_17_2024-GO95MLD-1^06245007.0223404 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002502 | 689007975-72939-DETAIL-05_06_2025-GO95HV-1^06243006.0048005 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002503 | 209676970-71859-DETAIL-06_16_2025-GO95HV-1^06248005.0331940 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002504 | 20975069-64740-ADMIN-10_21_2025-XARMSPCR-1^06247001.0245801 | CROSSARM | Non-HFTD | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002505 | 209840222-99650-DETAIL-02_03_2026-GO95HV-1^06239003.0018413 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002506 | 209840222-99650-DETAIL-02_03_2026-SVCENTCO-1^06239003.0018413 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002507 | 210379354-90740-DETAIL-03_25_2026-COVCOTHR-1^06240004.0218601 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002508 | 689155779-87430-AUDIT-06_09_2025-GO95HV-1^668075/00 6/003 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002509 | 68916608-48779-DETAIL-08_18_2025-GO95HV-1^06246002.0264501 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002510 | 713850641-9080-DETAIL-02_06_2025-SVCDEFLC-2^06240004.0166207 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002511 | 713969478-55549-DTLSB-07_16_2025-GO95HV-1^06244006.0319801 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002512 | 714015593-26593-DETAIL-09_18_2025-GO95HV-1^07218001.0086202 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002513 | 211915084-30869-DETAIL-08_14_2025-GO95HV-1^06247006.0364802 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002514 | 212324201-16201-DETAIL-04_23_2025-GO95HV-1^06242006.0038707 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002515 | 212361609-65099-DETAIL-07_28_2025-GO95HV-1^06247005.0198100 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002516 | 212383405-84939-DTLSB-07_02_2025-GO95HV-1^06244006.0226200 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002517 | 212469303-66039-DETAIL-06_10_2026-GUYHINS-1^668086/00 5/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002518 | 690516685-92681-DTLSB-04_29_2026-GO95HV-1^06142013.0204200 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002519 | 690752409-52070-DETAIL-03_23_2026-COVCOTHR-3^06240004.0220507 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002520 | 691509541-21991-DETAIL-09_29_2025-GO95HV-1^06148001.0310702 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002521 | 691701596-74229-DETAIL-04_22_2026-GO95HV-1^06142012.0148608 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002522 | 691773070-39045-DETAIL-04_22_2026-XARMSPCR-1^668041/00 4/029 | CROSSARM | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002523 | 691802791-68070-DTLTRT-05_12_2026-GO95HV-1^668004/00 5/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002524 | 691970295-3295-DETAIL-06_02_2025-GO95HV-1^06147014.0027201 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002525 | 691984306-5779-DETAIL-07_21_2025-GO95HV-1^06247005.0118500 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002526 | 692002986-65679-DETAIL-03_25_2024-CUSTWIRE-1^06147005.0145903 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002527 | 692047163-58659-DTLTRT-04_21_2026-GO95HV-1^668004/02 15/006 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002528 | 692365944-32990-DETAIL-03_02_2026-GO95HV-1^06239003.0250700 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002529 | 692952303-33059-DETAIL-05_29_2024-GO95HV-1^06246005.0219700 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002530 | 692968898-43523-DETAIL-09_10_2025-SVCNEUT-1^07218001.0176100 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002531 | 693199268-59713-DETAIL-09_02_2025-GO95HV-1^06247006.0276840 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002532 | 693322972-76869-AUDIT-05_18_2026-CONDFRAY-1^06241009.0105642 | CONDUCTOR | Non-HFTD | Distribution | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002533 | 657552489-61899-DETAIL-09_09_2025-SVCDEFLC-1^06246007.0144250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002534 | 657707193-12601-DETAIL-05_16_2024-GO95HV-1^06142012.0121703 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002535 | 657707193-12601-DETAIL-05_16_2024-GO95MLD-1^06142012.0121703 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002536 | 65785523-28669-DTLTRT-10_08_2020-CUSTWIRE-3^668047/00 13/016 | OTHER | HFTD Tier 2 | Transmission | 2020-10-08 | 2023-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002537 | 65847215-57210-DETAIL-03_12_2025-GO95HV-1^06238004.0223600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002538 | 65851154-13209-ADMIN-09_29_2025-GO95CLMP-1^06246009.0107500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002539 | 658681851-69180-DETAIL-02_16_2026-GO95HV-1^06239001.0045702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002540 | 660380571-86599-DETAIL-05_22_2025-GO95HV-1^06244006.0061001 | OTHER | HFTD Tier 2 | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002541 | 660724820-26740-DETAIL-01_22_2026-BIRDDMG-1^06239003.0071908 | POLE | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002542 | 660724820-26740-DETAIL-01_22_2026-COVCOTHR-1^06239003.0071908 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002543 | 660724820-26740-DETAIL-01_22_2026-COVCOTHR-2^06239003.0071908 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002544 | 660871523-70359-DTLTRT-04_22_2026-GO95HV-1^668004/02 7/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002545 | 660888490-12411-DETAIL-08_21_2025-GO95HV-1^06246001.0309202 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002546 | 66098039-51259-DETAIL-05_07_2026-GO95HV-1^668004/00 15/024 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002547 | 207094192-16319-DETAIL-04_08_2024-CUSTWIRE-1^06147005.0220401 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002548 | 207094192-16319-DETAIL-04_08_2024-CUSTWIRE-2^06147005.0220401 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002549 | 207228269-2719-DTLSB-05_05_2026-GO95HV-1^06241009.0146200 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002550 | 207374729-35729-DETAIL-07_24_2025-GO95HV-1^06247005.0161900 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002551 | 20755183-9429-DETAIL-05_19_2025-GO95HV-1^06142012.0012300 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002552 | 207713018-11741-DETAIL-03_10_2025-GO95BLTC-1^06241005.0167700 | OTHER | HFTD Tier 3 | Distribution | 2025-03-10 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002553 | 207752731-71740-DTLSB-05_06_2026-GO95HV-1^06142013.0288601 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002554 | 738738416-67789-DETAIL-10_14_2025-GRDRODHI-1^06148001.0176303 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002555 | 739007796-88796-DETAIL-06_02_2025-GO95HV-1^06148014.0362705 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002556 | 740037379-88599-DETAIL-10_27_2021-CUSTWIRE-2^06148005.0357900 | OTHER | Non-HFTD | Distribution | 2021-10-27 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002557 | 740089028-68331-DETAIL-08_21_2025-DISTHDWR-1^06246001.0205402 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002558 | 740189746-84789-DETAIL-10_15_2025-GO95HV-1^06148001.0204900 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002559 | 740309750-49750-DTLSB-05_02_2024-CUSTWIRE-1^06245007.0227700 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002560 | 740587141-86330-DETAIL-02_27_2025-GUYHINS-1^06240004.0154402 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002561 | 662386658-81459-DETAIL-06_04_2024-CUSTWIRE-1^06246005.0320700 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002562 | 662577072-77689-DETAIL-07_30_2025-GO95HV-1^06247005.0237002 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002563 | 663023240-74599-DETAIL-06_18_2025-GO95HV-1^06248004.0341805 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002564 | 663297616-84839-DETAIL-05_06_2025-GO95HV-2^06243006.0032701 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002565 | 663615596-92449-DTLSB-07_09_2025-GO95HV-1^06244006.0276000 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002566 | 663615596-92449-DTLSB-07_09_2025-GO95MLD-1^06244006.0276000 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002567 | 663811058-96309-DETAIL-06_10_2025-GO95HV-1^06245006.0291702 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002568 | 663891788-10940-DETAIL-02_24_2026-GO95HV-1^06239003.0132002 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002569 | 664052061-88380-DETAIL-01_29_2026-COVCOTHR-1^06240004.0304000 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002570 | 664052061-88380-DETAIL-01_29_2026-COVCOTHR-2^06240004.0304000 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002571 | 664212996-58853-DTLSB-06_11_2026-GO95HV-1^07217001.0353700 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002572 | 664417283-85459-DTLTRT-04_20_2026-GO95HV-1^668004/02 6/003 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002573 | 664605046-12570-DETAIL-01_22_2025-GO95TCH-1^06239004.0256744 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002574 | 664626469-41269-DTLTRT-06_14_2021-GO95HV-1^668041/00 14/020 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002575 | 664884575-53899-DTLSB-07_09_2025-GO95BLTC-1^06244006.0349500 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002576 | 665033746-9621-DETAIL-08_12_2025-GO95HV-1^06246001.0195500 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002577 | 694529848-16398-ENHANCED-01_09_2025-IRSPOTOH-1^668086/00 16/011 | OTHER | Non-HFTD | Transmission | 2025-01-09 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002578 | 694599771-14430-DETAIL-02_05_2025-GO95MLD-1^06240004.0170601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002579 | 694693925-72399-DTLSB-07_10_2025-GO95HV-1^06244006.0342304 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002580 | 695225158-89689-DETAIL-08_06_2025-GO95HV-1^06247006.0204801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002581 | 695331358-49959-DTLTRT-05_06_2026-GO95HV-1^668004/00 5/021 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002582 | 695331358-49960-DTLTRT-05_06_2026-GO95HV-1^668004/00 5/021 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002583 | 695426902-72950-DETAIL-02_11_2026-GO95HV-1^06239003.0016401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002584 | 695494888-85859-DTLTRT-05_04_2026-GO95HV-1^668004/00 2/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002585 | 666033949-30359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0330400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002586 | 666082548-48282-ADMIN-08_05_2025-GO95HV-1^668087/00 1/018 | OTHER | Non-HFTD | Transmission | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002587 | 666122904-65521-DETAIL-09_16_2025-GO95TCH-1^06147001.0137901 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002588 | 666264513-86559-DTLTRT-04_20_2026-GO95HV-1^668004/02 15/004 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002589 | 666469301-29870-DETAIL-02_05_2025-SVCDEFLC-1^06240004.0166201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002590 | 666544460-5103-DETAIL-02_17_2026-GO95HV-1^06239002.0070501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002591 | 666594191-34939-DETAIL-06_12_2024-CUSTWIRE-1^06244005.0249642 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002592 | 666815641-29350-DETAIL-03_24_2025-GO95CL10-1^06238004.0028603 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002593 | 667013363-10590-DETAIL-02_24_2026-GO95HV-1^06239002.0272800 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002594 | 667059414-56949-DETAIL-02_26_2024-COPLLEAN-1^07113001.0085101 | POLE | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002595 | 667113502-11149-DTLSB-07_16_2025-GO95HV-1^06244006.0232102 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002596 | 667584108-1519-ADMIN-02_26_2026-POLEDERP-1^668005/00 9/070 | POLE | Non-HFTD | Transmission | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002597 | 667713194-80590-DETAIL-03_31_2025-GO95HV-1^06239003.0017705 | OTHER | Non-HFTD | Distribution | 2025-03-31 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002598 | 667986041-76731-DTLTRT-05_20_2026-GO95HV-1^668086/00 9/010 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002599 | 695494888-85860-DTLTRT-05_04_2026-GO95HV-1^668004/00 2/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002600 | 695497093-26020-DETAIL-03_10_2025-SVCENTCO-1^06240004.0288402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002601 | 695610540-82692-DETAIL-05_01_2025-GRDRODHI-1^06243006.0288040 | OTHER | Non-HFTD | Distribution | 2025-05-01 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002602 | 695610540-82692-DETAIL-05_01_2025-GRDRODHI-2^06243006.0288040 | OTHER | Non-HFTD | Distribution | 2025-05-01 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002603 | 695735356-51642-ADMIN-11_10_2025-GO95BLTC-1^06246011.0062202 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002604 | 695782628-88589-DTLSB-03_30_2026-SVCDEFLC-1^06241009.0325202 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002605 | 696116264-69839-DETAIL-05_06_2025-GO95HV-1^06243006.0030302 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002606 | 696771554-22039-DTLTRT-05_21_2026-GO95MLD-1^668086/00 1/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002607 | 638932453-51450-DETAIL-02_04_2025-RISEBKSP-1^06239004.0134042 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002608 | 639130621-66449-DTLSB-07_09_2025-GO95HV-1^06244007.0159700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002609 | 639235893-98769-DRONE_HY-09_20_2023-GO95HV-1^668002/00 15/063 | OTHER | Non-HFTD | Transmission | 2023-09-20 | 2028-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002610 | 639400859-85899-DETAIL-09_09_2025-GO95HV-1^06246007.0230951 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002611 | 639732321-28069-DTLTRT-05_12_2026-GO95HV-1^668004/00 8/008 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002612 | 639859912-18880-DETAIL-03_12_2026-GO95TCH-1^06240004.0320902 | OTHER | HFTD Tier 3 | Distribution | 2026-03-12 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002613 | 640050474-42651-DETAIL-09_02_2025-GO95HV-1^06246001.0177500 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002614 | 640223546-7189-DTLSB-07_01_2025-GUYHINS-1^06244006.0226405 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002615 | 640313657-43970-DETAIL-02_26_2025-GO95TCH-1^06240004.0061307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002616 | 640340723-41359-DTLTRT-04_22_2026-GO95HV-1^668004/02 6/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002617 | 640416118-42469-DETAIL-05_15_2025-SVCENTCO-1^06243006.0097600 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002618 | 640510081-72749-DTLSB-07_28_2025-GO95HV-1^07218001.0269103 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002619 | 640563454-85851-DETAIL-06_09_2026-GUYHINS-1^668086/00 10/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002620 | 640563454-85851-DETAIL-06_09_2026-GUYHINS-3^668086/00 10/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002621 | 640563454-85851-DETAIL-06_09_2026-GUYHINS-4^668086/00 10/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002622 | 640563454-85851-DETAIL-06_09_2026-GUYHINS-5^668086/00 10/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002623 | 668853384-25289-DETAIL-05_08_2025-GO95HV-1^06243006.0106400 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002624 | 669100006-15180-DRONE_HY-07_01_2026-COVCOTHR-1^06239004.0363300 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002625 | 669192391-59809-DETAIL-03_11_2024-GO95HV-1^06147004.0049800 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002626 | 669982003-19389-DTLSB-01_21_2026-GO95HV-1^06242009.0297003 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002627 | 670183245-91209-DETAIL-08_13_2025-GO95HV-1^06247006.0263701 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002628 | 670878889-88919-DTLSB-05_12_2026-BIRDDMG-1^06242009.0285602 | POLE | Non-HFTD | Distribution | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002629 | 671173071-22943-DTLSB-06_02_2026-GO95HV-1^07216001.0116703 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002630 | 671610156-81156-DETAIL-05_29_2025-GO95HV-1^06148014.0360101 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002631 | 641476709-6170-DETAIL-03_24_2026-COVCOTHR-1^06240004.0220504 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002632 | 641517453-529-DETAIL-04_25_2022-CUSTWIRE-1^06143012.0255202 | OTHER | Non-HFTD | Distribution | 2022-04-25 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002633 | 641771756-4756-DETAIL-05_29_2025-GO95HV-1^06148014.0356000 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002634 | 642632338-16599-DETAIL-06_04_2024-CUSTWIRE-1^06246005.0318701 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002635 | 64273571-52949-DETAIL-07_01_2026-GUYHINS-1^07217001.0165403 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002636 | 642736474-36461-DETAIL-09_08_2025-GO95HV-1^06147001.0319403 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002637 | 642744576-80659-DTLTRT-04_29_2026-GO95HV-1^668004/00 3/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002638 | 642744576-80660-DTLTRT-04_29_2026-GO95HV-1^668004/00 3/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002639 | 64275513-19709-DETAIL-08_27_2025-GO95HV-1^06247006.0078300 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002640 | 643072804-70939-DETAIL-05_06_2025-GO95HV-1^06243006.0049200 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002641 | 643171555-67089-DTLSB-07_02_2025-GO95HV-1^06244006.0227000 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002642 | 643464149-83261-DETAIL-10_01_2025-GO95HV-1^06148001.0300206 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002643 | 643546934-37039-DTLTRT-07_10_2025-ABNDEQPM-1^668087/00 4/026 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002644 | 643626374-30361-DTLTRT-05_20_2026-GO95HV-1^668086/00 4/013 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002645 | 64414298-96080-DETAIL-09_09_2025-GO95HV-1^06146001.0100700 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002646 | 671679775-30129-DETAIL-04_22_2025-GO95HV-1^06242006.0054200 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002647 | 671761084-89630-DETAIL-06_10_2025-GO95BLTC-1^06236005.0333506 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002648 | 671761084-89630-DETAIL-06_10_2025-GO95HV-1^06236005.0333506 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002649 | 671947199-48359-DETAIL-07_22_2025-GO95HV-1^06247005.0059001 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002650 | 671989459-32599-DETAIL-09_22_2025-GO95HV-1^06248007.0242501 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002651 | 672110636-41340-DETAIL-03_24_2026-GO95HV-1^06240004.0213940 | OTHER | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002652 | 672513978-11409-DETAIL-08_06_2025-GO95HV-1^06247006.0205900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002653 | 673070936-12941-DETAIL-09_03_2025-GO95BLTC-1^06246001.0176202 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002654 | 646373143-14143-DETAIL-06_09_2025-GO95MLD-1^668075/00 2/031 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002655 | 646556436-10759-DETAIL-07_28_2025-GO95HV-1^06247005.0314201 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002656 | 646569953-30249-DETAIL-05_30_2025-GO95HV-1^06244006.0143201 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002657 | 646689005-90149-DTLSB-06_08_2026-GO95HV-1^07216001.0229202 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002658 | 64708816-63240-DETAIL-03_09_2026-SVCDEFLC-1^06240004.0152706 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002659 | 647159099-50089-DTLSB-07_08_2025-GO95BLTC-1^06244007.0038300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002660 | 647402252-33559-DTLTRT-04_29_2026-GO95HV-1^668004/00 10/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002661 | 647402252-33560-DTLTRT-04_29_2026-GO95HV-1^668004/00 10/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002662 | 647463103-51809-DETAIL-08_28_2025-GO95HV-1^06247006.0075801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002663 | 647592891-9411-DETAIL-01_21_2025-GO95TCH-1^06239004.0255445 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002664 | 647592891-9411-DETAIL-01_21_2025-SVCROAD-1^06239004.0255445 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002665 | 647995641-9371-DETAIL-06_10_2026-GUYHINS-2^668086/00 16/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002666 | 648091209-74759-DTLSB-07_29_2025-GO95MLD-1^07218001.0264105 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002667 | 648101168-97071-DETAIL-08_21_2025-ABNDEQPM-1^06246001.0207401 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002668 | 648128480-20171-DETAIL-09_16_2025-GO95CLSV-1^06147001.0060800 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002669 | 648237383-36009-DETAIL-08_12_2025-GO95HV-1^06247006.0251301 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002670 | 71465031-82430-DETAIL-03_26_2026-COVCOTHR-1^06240004.0200601 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002671 | 714697801-10901-DETAIL-09_25_2025-GO95HV-1^07218001.0215700 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002672 | 714882966-72409-DETAIL-08_21_2025-GO95TCH-1^06247006.0267801 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002673 | 715018536-36473-DTLSB-06_17_2026-GO95HV-1^07217001.0275000 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002674 | 715148266-52759-DTLTRT-04_30_2026-GO95HV-1^668004/00 6/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002675 | 71526139-87209-DETAIL-03_04_2024-LIGHT-1^06147004.0011301 | CONNECTION DEVICE | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002676 | 715303090-33090-DETAIL-10_14_2025-GO95HV-1^06148001.0179300 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002677 | 715383658-39019-DTLSB-04_01_2026-SVCENTCO-1^06241009.0326901 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002678 | 64993376-15779-DETAIL-04_08_2024-POLISSUE-1^06147005.0245400 | POLE | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002679 | 650039284-46533-DETAIL-07_01_2026-SVCENTBK-1^07217001.0165402 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002680 | 650391365-84365-DETAIL-06_03_2025-GO95HV-1^06148014.0248806 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002681 | 650583786-21799-DTLSB-06_24_2025-GO95HV-1^06244007.0033600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002682 | 651360024-65050-DTLTRT-10_11_2023-BIRDDMG-1^668010/00 8A/040 | POLE | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002683 | 65152551-82511-DETAIL-04_09_2025-GRDRODHI-1^06241005.0020604 | OTHER | HFTD Tier 2 | Distribution | 2025-04-09 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002684 | 65158090-90470-DETAIL-03_17_2026-GO95TCH-1^06240004.0221402 | OTHER | HFTD Tier 3 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002685 | 651884606-10489-DETAIL-05_08_2025-GO95HV-1^06243006.0104301 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002686 | 652120311-34981-DTLSB-06_02_2026-ENCHRW-1^07216001.0028000 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002687 | 652303182-80559-DETAIL-07_30_2025-GO95HV-1^06247005.0179803 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002688 | 652427921-77191-DTLTRT-05_18_2026-GO95HV-1^668086/00 8/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002689 | 65273718-34718-DTLTRT-05_14_2026-GRDRODHI-1^668085/00 3/005 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002690 | 652859971-32691-DTLTRT-04_28_2026-GO95HV-1^668004/00 3/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002691 | 65295614-60780-DTLTRT-06_30_2025-GO95HV-1^668087/02 3/001 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002692 | 652984576-67563-ADMIN-04_28_2025-POLEREPL-1^06247005.0332500 | POLE | Non-HFTD | Distribution | 2025-04-28 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002693 | 621394333-26350-DETAIL-01_23_2025-GO95TCH-1^06239004.0256805 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002694 | 621612157-48049-DETAIL-06_04_2025-GO95HV-1^06245006.0299700 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002695 | 621809971-29431-DTLTRT-05_18_2026-GO95HV-1^668086/00 2/007 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002696 | 621874200-33189-ADMIN-10_23_2025-GO95MLD-1^06246001.0110900 | OTHER | Non-HFTD | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002697 | 62237976-39632-DETAIL-04_29_2025-GUYHINS-1^06242005.0328301 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-29 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002698 | 622415749-12259-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0338400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002699 | 622563484-56840-DETAIL-03_25_2026-GO95MLD-1^06240004.0218706 | OTHER | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002700 | 622575944-14649-DETAIL-10_22_2024-CONDFRAY-1^07216001.0208100 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002701 | 622575944-14649-DETAIL-10_22_2024-POLANCRD-1^07216001.0208100 | POLE | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002702 | 622606306-21049-DETAIL-09_02_2025-GO95HV-1^07216001.0161703 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002703 | 622807311-86249-DTLSB-07_01_2025-GO95HV-1^06244007.0106401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002704 | 622855420-16331-DETAIL-03_13_2024-GO95MLD-1^06147004.0180700 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002705 | 622889712-82139-ADMIN-07_16_2026-POLEREPL-1^06243006.0348700 | POLE | Non-HFTD | Distribution | 2026-07-16 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002706 | 623062173-11259-DETAIL-03_10_2026-XARMSPCR-1^668041/00 10/027 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002707 | 674171228-43589-DTLSB-07_08_2025-SVCROAD-1^06244007.0038907 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002708 | 674205306-75306-DETAIL-04_24_2025-GO95MLD-1^06241006.0028330 | OTHER | HFTD Tier 2 | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002709 | 674260121-93330-DTLTRT-05_28_2025-GO95HV-1^668075/00 8/007 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002710 | 675058348-27340-DETAIL-04_22_2025-GO95HV-1^06240003.0075002 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002711 | 675224955-20629-DTLSB-05_04_2026-SVCDEFLC-1^06142013.0061700 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002712 | 675947764-99139-DTLSB-05_04_2026-CUSTWIRE-1^06142013.0058900 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002713 | 675969731-6632-DTLTRT-05_11_2026-GO95HV-1^668004/00 1/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002714 | 676068395-95689-DTLSB-07_02_2025-GO95HV-1^06244006.0226001 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002715 | 624076480-91309-ADMIN-03_16_2026-ABNDEQPM-1^06242009.0220800 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002716 | 624132986-95842-ADMIN-10_22_2025-GO95BLTC-1^06246011.0050500 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002717 | 624238673-21069-DETAIL-09_18_2025-GO95HV-1^06248007.0266400 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002718 | 624506285-38285-DETAIL-08_04_2025-GO95HV-1^06246001.0189002 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002719 | 624762061-84809-DETAIL-09_03_2025-GO95HV-1^06247006.0211506 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002720 | 625046638-25841-DETAIL-04_10_2024-CUSTWIRE-1^06245002.0118200 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002721 | 625144902-3705-DETAIL-07_13_2023-CUSTWIRE-1^06244008.0270000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-13 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002722 | 62527816-63949-DTLSB-07_08_2025-GO95HV-1^06244007.0037702 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002723 | 625638646-35849-DTLSB-07_09_2025-GO95HV-1^06244007.0142800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002724 | 625654261-19141-DETAIL-06_04_2025-GO95HV-1^06142012.0081100 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002725 | 625780603-84199-DETAIL-06_03_2025-GO95HV-1^06245007.0362401 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002726 | 626219649-90749-DETAIL-06_18_2025-GO95HV-1^06248004.0324000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002727 | 626313529-56079-DETAIL-10_15_2025-SVCSVC-1^06148001.0365400 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002728 | 626433657-15657-DETAIL-06_16_2025-GO95HV-1^06248004.0362120 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002729 | 626433657-15657-DETAIL-06_16_2025-RISEBKSP-1^06248004.0362120 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002730 | 654029496-68491-DETAIL-08_11_2025-ABNDEQPM-1^06246002.0095001 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002731 | 654179707-64970-DETAIL-02_25_2025-GO95MLD-1^06240004.0060100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002732 | 65465008-58179-DETAIL-06_19_2025-GO95HV-1^06248004.0297100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002733 | 206241986-39699-DETAIL-08_04_2025-GO95HV-1^06246002.0129600 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002734 | 206345028-56779-DETAIL-08_07_2025-GO95HV-1^06246002.0268901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002735 | 206367801-62940-DTLTRT-04_23_2026-GO95HV-1^668004/00 3/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002736 | 206615227-449-DTLSB-06_26_2025-GO95HV-1^06244007.0107841 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002737 | 206644756-54509-ADMIN-11_13_2025-GO95HV-1^06246008.0028601 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002738 | 205819454-88540-DETAIL-04_21_2026-GUYHINS-1^06142012.0149802 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002739 | 627462954-97860-DRONE_HY-07_15_2026-COVCOTHR-1^06239004.0257802 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002740 | 627477470-13889-DTLSB-07_01_2025-GO95HV-1^06244006.0225200 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002741 | 627477691-35730-DTLTRT-05_28_2025-DISTHDWR-1^668075/00 15/007 | CONNECTION DEVICE | Non-HFTD | Transmission | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002742 | 627477691-35730-DTLTRT-05_28_2025-GO95HV-1^668075/00 15/007 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002743 | 627540668-2668-AUDIT-02_02_2026-SVCDEFLC-1^06239004.0136218 | OTHER | HFTD Tier 2 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002744 | 627541831-92111-DRONE_HY-07_02_2026-POLETOP-1^06239004.0257041 | POLE | HFTD Tier 2 | Distribution | 2026-07-02 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002745 | 627879811-44349-DTLSB-06_25_2025-GO95HV-1^06244007.0103700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002746 | 627889424-79153-DETAIL-07_02_2026-GO95HV-1^07217001.0032800 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002747 | 62788945-29020-DETAIL-12_06_2024-BIRDDMG-1^668014/00 7/045 | POLE | HFTD Tier 3 | Transmission | 2024-12-06 | 2027-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002748 | 628139783-78040-DTLTRT-05_29_2025-GO95HV-1^668075/00 14/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002749 | 628147956-68173-DTLTRT-06_15_2026-GO95HV-1^07217001.0273401 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002750 | 62820975-81975-DETAIL-08_11_2025-GO95MLD-1^06247006.0267520 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002751 | 628416876-10341-DETAIL-09_08_2025-GO95HV-1^06147001.0329503 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002752 | 628416876-10341-DETAIL-09_08_2025-GO95MLD-1^06147001.0329503 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002753 | 654845714-17153-DETAIL-09_23_2025-GO95MLD-1^07218001.0224603 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002754 | 655114590-91449-DETAIL-09_05_2025-GO95MLD-1^07216001.0098601 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002755 | 655117684-75059-DETAIL-08_28_2025-GO95HV-1^07216001.0166802 | OTHER | Non-HFTD | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002756 | 655239388-10488-DETAIL-09_24_2025-GO95HV-1^07218001.0227200 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002757 | 655239388-10488-DETAIL-09_24_2025-GO95MLD-1^07218001.0227200 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002758 | 655358662-62070-DETAIL-03_18_2025-GRDRODHI-1^06238004.0124801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002759 | 655386292-76950-DETAIL-03_19_2025-SVCENTCO-1^06238004.0027240 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002760 | 655468920-30791-DETAIL-09_29_2025-GO95BLTC-1^06148001.0312701 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002761 | 630705616-83510-DETAIL-02_26_2026-COVCOTHR-3^06238004.0118301 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002762 | 630937391-71439-DTLTRT-06_26_2025-GUYHINS-1^668087/00 2/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002763 | 631074455-62209-DETAIL-08_13_2025-GO95HV-1^06247006.0264600 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002764 | 631295760-2289-DETAIL-10_15_2025-GO95HV-1^06148001.0332000 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002765 | 631428984-37509-DETAIL-08_28_2025-GO95HV-1^06247006.0187502 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002766 | 631512825-11110-DRONE_HY-06_30_2026-XARMSPCR-1^06238004.0152141 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120002767 | 631562778-83143-DTLSB-04_29_2024-GO95MLD-1^06245007.0220540 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002768 | 631562778-83143-DTLSB-04_29_2024-SVCENTCO-1^06245007.0220540 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002769 | 632085829-48829-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 11/015 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002770 | 632648354-34783-DETAIL-08_18_2025-BIRDDMG-1^06247006.0362401 | POLE | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002771 | 632757265-76900-DETAIL-04_28_2025-GO95TCH-1^06239002.0061506 | OTHER | HFTD Tier 2 | Distribution | 2025-04-28 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002772 | 633256390-98630-DETAIL-03_26_2026-COVCOTHR-1^06240004.0202641 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002773 | 633350374-122-DETAIL-10_15_2025-GO95BLTC-1^06246011.0181702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002774 | 633354889-57699-DTLSB-05_19_2026-GO95HV-1^06240007.0181500 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002775 | 605551191-40870-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 2/002 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002776 | 605692512-38559-DETAIL-04_29_2026-GO95HV-1^668004/00 9/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002777 | 606339372-91750-DETAIL-02_11_2026-GO95HV-1^06239003.0016208 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002778 | 606449262-10880-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0166307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002779 | 606535698-92502-DETAIL-03_06_2025-GUYHINS-3^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002780 | 606535698-92502-DETAIL-03_06_2025-GUYHINS-4^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002781 | 606535698-92502-DETAIL-03_06_2025-GUYNOINS-2^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002782 | 607716179-8982-DETAIL-06_03_2024-CUSTWIRE-1^06245006.0029601 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002783 | 60786219-16282-DTLTRT-07_02_2025-GUYNOINS-1^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002784 | 60786219-16282-DTLTRT-07_02_2025-GUYNOINS-3^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002785 | 60786219-16282-DTLTRT-07_02_2025-GUYNOINS-4^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002786 | 60786219-30770-DTLTRT-07_02_2025-GUYNOINS-4^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002787 | 60786219-96282-DTLTRT-07_02_2025-BIRDDMG-1^668087/00 2/020 | POLE | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002788 | 60786219-96282-DTLTRT-07_02_2025-GUYNOINS-2^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002789 | 60786219-96282-DTLTRT-07_02_2025-GUYNOINS-3^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002790 | 60786219-96282-DTLTRT-07_02_2025-GUYNOINS-4^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002791 | 608035931-88621-DETAIL-04_09_2024-GO95TCH-1^06147005.0255000 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002792 | 608035931-88621-DETAIL-04_09_2024-GUYHINS-1^06147005.0255000 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002793 | 608035931-88621-DETAIL-04_09_2024-INSULDMG-1^06147005.0255000 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002794 | 676217151-7180-DETAIL-02_18_2026-GO95HV-1^06239002.0045401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002795 | 676279125-83770-DETAIL-01_22_2025-GO95HV-1^06239004.0256602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002796 | 676401408-40551-DETAIL-08_14_2025-GO95HV-1^06246002.0254401 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002797 | 676561254-21219-DTLSB-01_27_2026-GO95MLD-1^06242009.0055100 | OTHER | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002798 | 676586401-69689-ADMIN-10_10_2024-POLEREPL-1^06146002.0034400 | POLE | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002799 | 677282776-67659-DTLTRT-04_30_2026-GO95HV-1^668004/00 5/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002800 | 677364488-41940-DETAIL-01_21_2025-RISECLMB-1^06240004.0091601 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002801 | 677411508-15651-ADMIN-11_06_2025-GUYHINS-1^06246001.0269600 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-11-06 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002802 | 609803209-84979-DETAIL-06_16_2025-GO95HV-1^06248004.0355541 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002803 | 609878644-8339-DETAIL-10_06_2025-BIRDDMG-1^06243007.0365500 | POLE | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002804 | 609895596-50280-DETAIL-01_31_2025-GO95MLD-1^06239004.0245905 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002805 | 610189440-10659-DETAIL-08_05_2025-GO95HV-1^06247005.0205300 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002806 | 610268660-65543-DETAIL-06_26_2026-GO95HV-1^07217001.0117300 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002807 | 610472929-56613-ADMIN-10_07_2025-COVCOTHR-1^06242005.0282940 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002808 | 610673768-90390-DETAIL-01_14_2025-SVCENTCO-1^06239004.0255103 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002809 | 610793353-23359-DTLTRT-04_22_2026-GO95HV-1^668004/02 12/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002810 | 610814805-96739-DETAIL-05_08_2025-GO95HV-1^06243006.0105903 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002811 | 61123410-67759-DTLSB-07_31_2025-GO95HV-1^07218001.0261200 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002812 | 611273843-12798-DTLTRT-05_07_2026-GO95HV-1^668004/00 6/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002813 | 611273843-12798-DTLTRT-05_07_2026-GO95MLD-1^668004/00 6/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002814 | 61127801-40901-DETAIL-04_07_2026-GO95HV-1^06240002.0317113 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002815 | 611611018-57579-DETAIL-08_11_2025-GO95HV-1^06246002.0235500 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002816 | 611812788-22119-DTLSB-04_13_2026-GO95HV-1^06241008.0365600 | OTHER | Non-HFTD | Distribution | 2026-04-13 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002817 | 61205545-27299-DTLSB-11_08_2021-CUSTWIRE-1^06148004.0259003 | OTHER | Non-HFTD | Distribution | 2021-11-08 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002818 | 634813076-60051-DETAIL-09_03_2025-ABNDEQPM-1^06246001.0179301 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002819 | 634813076-60051-DETAIL-09_03_2025-GO95HV-1^06246001.0179301 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002820 | 635275379-81490-DETAIL-01_16_2025-GO95MLD-1^06239004.0257404 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002821 | 635371831-69330-DETAIL-02_19_2025-RISEGRD-1^06240004.0177900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002822 | 635629418-26890-DETAIL-01_24_2025-GO95TCH-1^06239004.0247140 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002823 | 635844064-57064-DTLTRT-07_07_2025-GO95HV-1^668087/00 5/029 | OTHER | Non-HFTD | Transmission | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002824 | 635903981-88951-DETAIL-10_01_2025-GO95HV-1^06148001.0303103 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002825 | 636024865-6399-DETAIL-09_16_2025-GO95HV-1^06247004.0184800 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002826 | 612848158-82389-DETAIL-10_15_2025-GO95HV-1^06148001.0265200 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002827 | 612858829-62169-DETAIL-08_26_2025-GO95HV-1^06247006.0285300 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002828 | 613237886-321-DETAIL-08_25_2025-SVCENTBK-1^06246001.0175307 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002829 | 202350743-68629-DETAIL-04_30_2025-GO95HV-1^06242006.0112003 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002830 | 202899540-8483-DETAIL-08_19_2025-GO95HV-1^07216001.0172802 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002831 | 202944964-22783-DETAIL-09_22_2025-CUSTWIRE-1^07218001.0086300 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002832 | 203496969-72440-DETAIL-08_13_2025-GO95HV-1^06246002.0366401 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002833 | 203621161-8029-DETAIL-05_29_2025-GO95HV-1^06142012.0152900 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002834 | 613299735-82600-DETAIL-02_10_2026-BIRDDMG-1^06239003.0016806 | POLE | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002835 | 613496385-26321-DTLSB-05_15_2024-GO95HV-1^06244001.0190100 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002836 | 613728761-85979-DETAIL-10_07_2025-GO95HV-1^06148001.0311809 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002837 | 613728761-85979-DETAIL-10_07_2025-GUYHINS-1^06148001.0311809 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002838 | 613750749-63421-DETAIL-04_24_2024-GRDRODHI-1^06145001.0055100 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002839 | 613825483-85421-DTLSB-06_24_2026-CLRTOUCH-1^07217001.0346800 | CONDUCTOR | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002840 | 61385156-89680-DETAIL-01_30_2025-GO95HV-1^06239004.0245701 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002841 | 636188490-24739-DTLSB-07_22_2025-BIRDDMG-1^06244006.0181101 | POLE | HFTD Tier 2 | Distribution | 2025-07-22 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002842 | 636285441-52819-DETAIL-05_25_2023-RISEGRD-1^07117007.0227400 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002843 | 636402485-93532-DETAIL-04_03_2025-GO95TCH-1^06241005.0028303 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002844 | 636548079-40570-DETAIL-02_14_2025-GO95BLTC-1^06240004.0166102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002845 | 637030511-64970-DETAIL-02_17_2026-GO95HV-1^06239002.0090801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002846 | 637041594-19759-DTLTRT-04_21_2026-GO95HV-1^668004/02 7/008 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002847 | 637314935-14970-DETAIL-01_27_2026-SVCDEFLC-1^06239002.0062401 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002848 | 586495996-92852-DETAIL-04_24_2025-GO95HV-1^06242006.0199800 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002849 | 586861060-51270-DETAIL-02_19_2026-GO95HV-1^06239002.0016600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002850 | 587066144-58289-DTLSB-11_11_2021-CUSTWIRE-1^06148004.0303300 | OTHER | Non-HFTD | Distribution | 2021-11-11 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002851 | 58711653-41130-DTLSB-08_11_2025-GO95HV-1^07218001.0279700 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002852 | 587484799-60979-DETAIL-07_28_2025-CLRTOUCH-1^06247005.0198401 | CONDUCTOR | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002853 | 587887233-28699-DETAIL-10_06_2021-CUSTWIRE-1^06147005.0054901 | OTHER | Non-HFTD | Distribution | 2021-10-06 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002854 | 587887233-28699-DETAIL-10_06_2021-CUSTWIRE-2^06147005.0054901 | OTHER | Non-HFTD | Distribution | 2021-10-06 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002855 | 58798490-68690-DETAIL-01_22_2026-SVCTREE-1^06239003.0070901 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002856 | 588097681-97119-ADMIN-11_13_2025-SVCDEFLC-1^06246010.0133800 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002857 | 588262076-69779-DETAIL-05_20_2025-GO95HV-1^06243006.0094204 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002858 | 588487005-78649-DTLSB-06_09_2026-SVCROAD-1^07216001.0225007 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002859 | 58855719-52199-DETAIL-04_21_2025-GO95BLTC-1^06242006.0037810 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002860 | 588670751-44849-DTLSB-06_02_2026-SVCROAD-1^07216001.0116904 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002861 | 588694686-24199-DETAIL-06_05_2025-GUYHINS-2^06245007.0249601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002862 | 588772003-91950-DETAIL-01_30_2025-GUYHINS-1^06239004.0131000 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002863 | 614723611-59249-DTLSB-05_29_2026-SVCROAD-1^07216001.0020802 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002864 | 614873221-67201-DETAIL-02_04_2025-GO95HV-1^06239004.0135048 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002865 | 615288919-15789-ADMIN-04_13_2026-ABNDEQPM-1^06241008.0258401 | OTHER | Non-HFTD | Distribution | 2026-04-13 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002866 | 615352498-79459-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0311501 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002867 | 615534787-40479-DETAIL-08_11_2025-GO95HV-1^06246002.0168800 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002868 | 615809281-101-DETAIL-01_15_2026-GO95TCH-1^06239004.0135145 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002869 | 615853726-46099-DTLSB-03_31_2026-GO95MLD-1^06241009.0326608 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002870 | 201951875-14700-DETAIL-04_08_2026-GO95HV-1^06240002.0329301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002871 | 202232561-24840-DTLTRT-06_26_2025-BIRDDMG-1^668087/00 16/008 | POLE | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002872 | 589157111-27970-DETAIL-02_17_2026-GO95HV-1^06239002.0092402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002873 | 589201708-16869-DTLTRT-06_09_2021-GO95HV-1^668041/00 9/016 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002874 | 589486113-39179-DETAIL-06_17_2025-GO95HV-1^06248004.0332802 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002875 | 589542938-47250-DETAIL-02_24_2026-GO95HV-1^06239003.0132301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002876 | 589620643-97820-DETAIL-01_21_2026-SVCTREE-1^06240004.0289303 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002877 | 589898833-70009-AUDIT-09_02_2025-XARMSPCR-1^06247006.0258200 | CROSSARM | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002878 | 589898833-70009-DETAIL-08_14_2025-GO95HV-1^06247006.0258200 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002879 | 590086704-7291-DETAIL-04_13_2022-CUSTWIRE-1^06142012.0133402 | OTHER | Non-HFTD | Distribution | 2022-04-13 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002880 | 590108851-66530-DTLTRT-05_28_2025-GO95HV-1^668075/00 11/007 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002881 | 590123163-9940-DTLTRT-05_29_2025-ABNDEQPM-1^668075/00 12/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002882 | 59030795-76140-DETAIL-02_25_2025-GO95MLD-1^06240004.0151901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002883 | 590309232-57829-DTLSB-08_24_2023-CUSTWIRE-1^06243008.0186400 | OTHER | HFTD Tier 2 | Distribution | 2023-08-24 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002884 | 616058033-30469-AUDIT-06_16_2025-GO95HV-1^06245007.0367602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002885 | 61610451-11679-DTLSB-01_20_2026-GO95HV-1^06242009.0299307 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002886 | 616116353-24390-DETAIL-02_24_2026-GO95MLD-1^06239002.0272501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002887 | 616408321-26831-DETAIL-09_29_2025-GUYHINS-1^06148001.0313500 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002888 | 616499144-33229-DETAIL-04_22_2026-GO95HV-1^06142012.0149611 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002889 | 616690346-28329-DETAIL-05_13_2025-GO95HV-1^06142012.0012302 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002890 | 616797631-51231-DETAIL-09_11_2025-GRDRODHI-1^06147001.0056801 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002891 | 616934281-49380-DETAIL-02_16_2026-GO95HV-1^06239001.0049801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002892 | 591432243-4201-DETAIL-10_01_2025-GO95HV-1^06148001.0312901 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002893 | 591719387-13189-DETAIL-03_09_2026-SVCENTCO-1^06242009.0068900 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002894 | 59180768-41279-DTLSB-04_09_2026-GO95HV-1^06241007.0213001 | OTHER | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002895 | 59195443-48370-DETAIL-05_14_2025-GO95HV-1^06142012.0117802 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002896 | 592073473-87541-DETAIL-04_15_2025-SVCROAD-1^06242005.0334802 | OTHER | HFTD Tier 2 | Distribution | 2025-04-15 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002897 | 592170471-17349-DETAIL-07_01_2026-GO95HV-1^07217001.0169501 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002898 | 592249954-93699-DETAIL-05_22_2025-GO95HV-1^06244006.0092501 | OTHER | Non-HFTD | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002899 | 592390950-24709-DTLSB-11_08_2021-CUSTWIRE-1^06148004.0282603 | OTHER | Non-HFTD | Distribution | 2021-11-08 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002900 | 593032701-7949-ADMIN-04_02_2026-POLEREPL-1^07116001.0093204 | POLE | HFTD Tier 2 | Distribution | 2026-04-02 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002901 | 593139343-78501-DETAIL-09_10_2025-GO95HV-1^06147001.0187703 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002902 | 593475362-43831-DETAIL-02_27_2025-GO95MLD-1^06241005.0173600 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002903 | 593483424-64069-DETAIL-09_15_2025-GO95HV-1^06248007.0263900 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002904 | 59361130-23819-DTLSB-03_12_2026-SVCNEUT-1^06242009.0161700 | OTHER | Non-HFTD | Distribution | 2026-03-12 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002905 | 593695188-52073-DETAIL-08_26_2025-GO95HV-1^07216001.0168003 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002906 | 593852593-28901-ADMIN-10_21_2025-GO95HV-1^06247001.0265800 | OTHER | Non-HFTD | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002907 | 594091063-8883-DETAIL-09_17_2025-SVCROAD-1^07218001.0087001 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002908 | 656038949-75733-AUDIT-10_14_2025-GO95MLD-1^07218001.0177100 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002909 | 65640588-8819-DRONE_HY-07_15_2026-UBPBXARM-1^668036/00 2/052 | CROSSARM | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002910 | 656930454-18701-DETAIL-10_08_2025-SVCNEUT-1^06148001.0312600 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002911 | 657035659-95029-DTLSB-05_12_2026-GO95HV-1^06242009.0281214 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002912 | 657101531-16130-DETAIL-03_26_2026-COVCOTHR-1^06240004.0207500 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002913 | 657145498-31873-DETAIL-09_15_2025-GO95HV-1^07216001.0086100 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002914 | 657307934-18183-DETAIL-09_11_2025-GO95HV-1^06248007.0222800 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002915 | 657552489-61899-DETAIL-09_09_2025-GO95HV-1^06246007.0144250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002916 | 595050419-60739-DETAIL-06_24_2025-GUYHINS-1^668087/00 9/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002917 | 596166660-80001-DETAIL-08_07_2025-GO95HV-1^06246001.0301900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002918 | 596185108-66859-DTLTRT-05_04_2026-GO95MLD-1^668004/00 4/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002919 | 596228485-89485-DETAIL-06_02_2025-GO95HV-1^06148014.0240903 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002920 | 596441414-24069-DETAIL-09_15_2025-GO95HV-1^06248007.0263901 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002921 | 596633788-15401-DTLTRT-06_24_2025-GO95HV-1^668087/00 15/003 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002922 | 596633788-15401-DTLTRT-06_24_2025-GO95TCH-1^668087/00 15/003 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002923 | 597138598-37959-DTLTRT-05_04_2026-GO95HV-1^668004/00 10/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002924 | 598120034-33601-DETAIL-09_05_2025-GO95HV-1^06147001.0294001 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002925 | 598671385-16259-DETAIL-07_21_2025-COPLLEAN-1^06247005.0118502 | POLE | Non-HFTD | Distribution | 2025-07-21 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002926 | 598836928-31299-DTLSB-04_01_2026-SVCDEFLC-1^06241009.0326100 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002927 | 598880406-98070-DETAIL-01_15_2025-GO95MLD-1^06239004.0254142 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002928 | 598893539-58569-DTLTRT-06_09_2021-GO95HV-1^668041/00 7/014 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002929 | 599107974-26299-DTLSB-07_02_2025-GO95HV-1^06244006.0226204 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002930 | 599158349-75081-AUDIT-03_04_2025-ANCHIDLE-1^06241005.0152401 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002931 | 599612618-33291-DTLTRT-05_05_2026-BIRDDMG-1^668038/00 2/061 | POLE | HFTD Tier 2 | Transmission | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002932 | 5705003-24480-DETAIL-01_30_2025-SVCROOF-1^06240004.0163702 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002933 | 570507194-69041-DETAIL-04_10_2025-GO95MLD-1^06241005.0012602 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002934 | 570567882-22139-DETAIL-05_20_2025-GO95HV-1^06243006.0078902 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002935 | 570999673-7089-DETAIL-08_12_2025-GO95HV-1^06247006.0251302 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002936 | 571019792-34209-DETAIL-07_23_2025-GUYHINS-1^06247005.0177403 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-23 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002937 | 571496914-83069-DETAIL-09_15_2025-GO95HV-1^06248007.0263800 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002938 | 571782798-43639-DTLSB-08_12_2025-GO95MLD-1^07217001.0024702 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002939 | 5719815-85309-DETAIL-10_15_2025-GO95BLTC-1^06246012.0133702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002940 | 572270158-71089-DETAIL-08_18_2025-GO95HV-1^06246002.0264101 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002941 | 572287601-47809-DETAIL-10_02_2025-ABNDEQPM-1^06246008.0063200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002942 | 572336488-16089-DTLSB-07_08_2025-GO95HV-1^06244007.0038904 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002943 | 572530542-37430-DTLSB-08_11_2025-GO95HV-1^07218001.0279900 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002944 | 572781111-20271-DTLSB-03_29_2022-GO95HV-1^06144006.0105400 | OTHER | Non-HFTD | Distribution | 2022-03-29 | 2027-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002945 | 5728426-32509-DTLSB-05_04_2026-GO95HV-1^06142013.0174400 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002946 | 573151824-24090-DETAIL-01_28_2026-GO95MLD-1^06239002.0065701 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002947 | 617985908-14331-DTLTRT-06_23_2025-GO95HV-1^668087/00 16/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002948 | 617985908-14331-DTLTRT-06_23_2025-GO95MLD-1^668087/00 16/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002949 | 618004770-9459-DETAIL-07_23_2025-BIRDDMG-1^06247005.0178501 | POLE | Non-HFTD | Distribution | 2025-07-23 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002950 | 618260028-85599-ADMIN-10_23_2025-GO95HV-1^06246011.0368204 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002951 | 618282615-97089-DTLSB-07_10_2025-GO95MLD-1^06244006.0342201 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002952 | 618616774-67810-DETAIL-03_13_2025-GO95HV-1^06238004.0150102 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002953 | 618705791-70780-DETAIL-02_19_2026-GO95HV-1^06239001.0060601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002954 | 618986291-97631-DTLSB-06_03_2026-SVCROAD-1^07216001.0026303 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002955 | 20016031-29849-DTLSB-06_02_2026-GO95HV-1^07216001.0116701 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002956 | 200166930-77143-DETAIL-10_09_2025-GO95HV-1^06248003.0270140 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002957 | 200269423-37243-DETAIL-01_14_2025-CUSTWIRE-1^06240004.0079800 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002958 | 200333012-61450-DETAIL-01_31_2025-GO95MLD-1^06239004.0136200 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002959 | 200867269-32289-DETAIL-10_07_2025-GO95HV-1^06148001.0276500 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002960 | 200886438-23359-DETAIL-07_28_2025-CLRTOUCH-1^06247005.0086440 | CONDUCTOR | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002961 | 200886438-23359-DETAIL-07_28_2025-GO95HV-1^06247005.0086440 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002962 | 200955732-46780-DETAIL-02_13_2025-SVCDEFLC-1^06240004.0168146 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002963 | 201157804-11162-DETAIL-10_06_2025-GO95HV-1^06243007.0255400 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002964 | 201415966-29209-DETAIL-08_12_2025-GO95HV-1^06247006.0266102 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002965 | 574979079-4071-DETAIL-01_25_2023-COPLLEAN-1^06148003.0355700 | POLE | Non-HFTD | Distribution | 2023-01-25 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002966 | 575480368-75299-DETAIL-08_13_2024-CUSTWIRE-1^06245006.0155101 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002967 | 575531602-2759-DETAIL-07_29_2025-GO95HV-1^06247005.0213800 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002968 | 575579522-40622-ADMIN-11_12_2025-GO95MLD-1^06146001.0313101 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002969 | 600580860-93670-DETAIL-06_10_2025-GO95HV-1^06236005.0347803 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002970 | 600581519-81449-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0148400 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002971 | 600619114-81979-ADMIN-03_06_2026-POLEREPL-1^06243007.0256201 | POLE | Non-HFTD | Distribution | 2026-03-06 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002972 | 600927959-8439-DTLSB-07_18_2022-CUSTWIRE-1^06243005.0144200 | OTHER | Non-HFTD | Distribution | 2022-07-18 | 2025-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002973 | 60103248-75932-DETAIL-04_24_2025-GO95HV-1^06242006.0160901 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002974 | 601082643-72559-DETAIL-10_01_2025-GO95HV-1^06148001.0302200 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002975 | 577910593-34779-DETAIL-07_29_2025-GO95HV-1^06247005.0210200 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002976 | 578023743-56683-DETAIL-09_17_2025-GRDRODHI-1^07218001.0088203 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002977 | 578966534-68139-DTLSB-05_04_2026-GO95HV-1^06142013.0054601 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002978 | 57902966-21760-DETAIL-08_11_2025-DISTHDWR-2^06246002.0097003 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002979 | 579187762-63831-DETAIL-02_27_2025-GO95MLD-1^06241005.0172600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002980 | 579430443-88879-DTLSB-01_20_2026-GO95HV-1^06242009.0299104 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002981 | 580209422-68453-DETAIL-06_30_2026-GO95HV-1^07217001.0222601 | OTHER | Non-HFTD | Distribution | 2026-06-30 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002982 | 580293903-21299-DETAIL-05_30_2025-GO95HV-1^06244006.0143600 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002983 | 580721971-52380-DETAIL-02_16_2026-GO95HV-1^06239001.0047702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002984 | 580862514-6481-DETAIL-09_08_2025-GO95HV-1^06147001.0330400 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002985 | 580976323-97323-DETAIL-03_27_2023-ENCHRW-1^06240004.0167030 | OTHER | HFTD Tier 2 | Distribution | 2023-03-27 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002986 | 581029936-11036-DETAIL-06_03_2025-GO95HV-1^06148014.0255401 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002987 | 581076928-83750-DETAIL-02_25_2026-BIRDDMG-1^06239003.0139101 | POLE | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002988 | 581221268-84270-DTLTRT-10_10_2023-BIRDDMG-1^668010/00 3A/045 | POLE | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002989 | 581420975-46259-DETAIL-07_23_2025-GO95HV-1^06247005.0118501 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120002990 | 601102276-99079-DETAIL-03_25_2024-CUSTWIRE-1^06147005.0145900 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002991 | 601346396-23489-DTLSB-03_16_2026-GRDRODHI-1^06242009.0135301 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002992 | 601360701-32511-DETAIL-01_21_2025-SVCROOF-1^06239004.0255248 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002993 | 601636398-82819-DRONE_HY-07_15_2026-UBPBXARM-1^668036/00 6/051 | CROSSARM | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002994 | 601699173-39579-DETAIL-06_02_2025-SVCROAD-1^06245007.0367801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002995 | 601786588-35979-ADMIN-06_13_2024-CUTOUTAR-1^06148005.0330902 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-06-13 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002996 | 602271544-9731-DETAIL-04_07_2025-GO95TCH-1^06241005.0012801 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002997 | 582618371-58901-DETAIL-01_13_2026-BIRDDMG-1^06239004.0135043 | POLE | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002998 | 582838070-98149-DETAIL-09_04_2025-GRDRODHI-1^07216001.0098303 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120002999 | 58292279-56349-DETAIL-06_03_2024-CUSTWIRE-1^06246006.0361002 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003000 | 583283831-7750-DETAIL-06_12_2025-GO95HV-1^06237005.0362504 | OTHER | HFTD Tier 2 | Distribution | 2025-06-12 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003001 | 583322491-63491-DETAIL-09_24_2025-GO95HV-1^07218001.0216600 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003002 | 583326816-96352-DETAIL-04_21_2025-GO95TCH-1^06242005.0368604 | OTHER | HFTD Tier 2 | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003003 | 5833468-85630-DETAIL-01_26_2026-GO95MLD-1^06240003.0304400 | OTHER | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003004 | 58337269-68270-DETAIL-09_03_2025-GO95HV-1^07216001.0099104 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003005 | 583406426-43410-DETAIL-01_30_2025-GUYHINS-2^06240004.0163609 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003006 | 583495309-71890-DETAIL-01_12_2026-SVCROAD-1^06239004.0244300 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003007 | 583627164-31264-DTLTRT-08_07_2025-GUYNOINS-1^668087/00 11/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-07 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003008 | 583646611-88699-DETAIL-01_15_2026-GO95MLD-1^06239004.0135105 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003009 | 201516118-23339-DTLSB-08_13_2025-GO95BLTC-1^07217001.0024901 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003010 | 201516118-23339-DTLSB-08_13_2025-GO95HV-1^07217001.0024901 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003011 | 201577117-34590-DETAIL-01_30_2025-GO95TCH-1^06239004.0245541 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003012 | 201674374-66379-DETAIL-07_30_2025-GO95HV-1^06247006.0206004 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003013 | 550507370-78089-DETAIL-10_08_2025-GO95BLTC-1^06246008.0044200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003014 | 550604430-30350-DETAIL-01_22_2026-SVCDEFLC-1^06239003.0072800 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003015 | 550726024-53253-DETAIL-07_02_2026-GO95HV-1^07217001.0033801 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003016 | 551027986-59513-DETAIL-01_14_2026-SVCROOF-1^06239004.0135049 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003017 | 551264562-4689-AUDIT-06_03_2025-GO95HV-1^06243006.0222101 | OTHER | Non-HFTD | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003018 | 551277364-32460-DETAIL-01_23_2025-GO95BLTC-1^06239004.0257804 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003019 | 551351983-75429-DETAIL-05_13_2025-GO95HV-1^06142012.0014601 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003020 | 551509606-61341-DETAIL-09_02_2025-GO95HV-1^06246001.0176206 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003021 | 553417844-60590-DETAIL-02_12_2026-GO95HV-1^06239003.0252300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003022 | 553642103-20669-DTLTRT-06_04_2021-GO95HV-1^668041/00 3/009 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003023 | 553754358-42049-DTLSB-07_08_2025-CUSTWIRE-1^06244007.0035805 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003024 | 553853014-79751-DETAIL-06_11_2026-GO95TCH-1^668086/00 19/013 | OTHER | Non-HFTD | Transmission | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003025 | 553987318-32450-DETAIL-02_10_2026-CUSTWIRE-1^06239003.0018407 | OTHER | Non-HFTD | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003026 | 554063016-62470-DETAIL-01_23_2025-GO95HV-1^06239004.0256800 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003027 | 554063016-62470-DRONE_HY-07_15_2026-GO95TCH-1^06239004.0256800 | OTHER | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003028 | 554192049-36733-DTLSB-06_15_2026-GO95MLD-1^07217001.0278900 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003029 | 554308039-74299-DETAIL-03_11_2024-GO95MLD-1^06147004.0014902 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003030 | 554439868-78649-ADMIN-04_01_2026-CLMBHAZ-1^07216001.0165800 | OTHER | Non-HFTD | Distribution | 2026-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003031 | 554439868-78649-ADMIN-04_01_2026-SVCROAD-1^07216001.0165800 | OTHER | Non-HFTD | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003032 | 554446146-73161-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0366907 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003033 | 554446146-73161-DRONE_HY-07_02_2026-COVCOTHR-4^06239004.0366907 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003034 | 554934385-95551-DTLSB-02_02_2023-ENCHRW-1^06248001.0360901 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003035 | 61899664-25622-ADMIN-10_21_2025-ABNDEQPM-1^06246012.0052605 | OTHER | HFTD Tier 2 | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003036 | 204472018-26879-DETAIL-01_20_2026-GO95HV-1^06242009.0299300 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003037 | 204766742-52842-DETAIL-07_24_2025-GO95HV-1^06247005.0148301 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003038 | 204788206-60629-DETAIL-05_13_2025-GO95HV-1^06142012.0017502 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003039 | 204788206-60629-DETAIL-05_13_2025-GUYHINS-1^06142012.0017502 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003040 | 204918958-16493-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 10/002 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003041 | 619005582-68279-DTLSB-07_16_2025-GO95HV-1^06244006.0230100 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003042 | 619007961-34550-DETAIL-02_27_2025-GO95HV-1^06240004.0139400 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003043 | 556059182-37859-DTLTRT-05_04_2026-GO95HV-1^668004/00 4X/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003044 | 556163125-30339-DTLTRT-06_26_2025-GO95MLD-1^668087/00 20/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003045 | 556201428-72651-DTLSB-05_05_2026-GO95HV-1^06142013.0153401 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003046 | 556369021-1273-DETAIL-09_10_2025-GO95HV-1^06246006.0184350 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003047 | 556628286-75329-DETAIL-04_27_2026-GO95HV-1^06142012.0148600 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003048 | 556748271-57032-DTLTRT-04_28_2026-GO95HV-1^668004/00 3/008 | OTHER | HFTD Tier 2 | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003049 | 557019334-29334-DETAIL-07_22_2025-GO95HV-1^06247005.0091500 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003050 | 557054915-12849-DTLSB-07_17_2025-GO95HV-1^06244007.0114100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003051 | 557417951-31280-DETAIL-02_18_2026-GO95HV-1^06239002.0046400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003052 | 557458865-68299-ADMIN-10_07_2025-COVCOTHR-1^06246012.0118201 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003053 | 557473711-63349-DTLSB-06_25_2025-GO95HV-1^06244007.0103800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003054 | 557621303-61303-DETAIL-06_11_2025-GUYHINS-2^668075/00 15/036 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003055 | 557687904-71789-DETAIL-08_20_2025-GO95HV-1^06247006.0255601 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003056 | 557833410-97932-DETAIL-04_21_2025-GO95HV-1^06242005.0361101 | OTHER | HFTD Tier 2 | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003057 | 557902086-64451-DETAIL-08_04_2025-GO95HV-1^06246001.0185002 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003058 | 557932894-9759-DETAIL-06_05_2024-CUSTWIRE-1^06246006.0251901 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003059 | 584482933-48950-DETAIL-01_23_2025-SVCROAD-1^06239004.0256801 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003060 | 58463668-84182-DTLTRT-07_01_2025-GO95HV-1^668087/00 2/016 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003061 | 584644045-17132-DETAIL-07_12_2023-CUSTWIRE-1^06244008.0335200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003062 | 584654219-29991-DETAIL-09_04_2025-GO95HV-1^06146001.0082901 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003063 | 584718243-10191-DRONE_HY-07_10_2026-XARMBRAC-1^06143014.0213900 | CROSSARM | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003064 | 584839151-40291-DTLTRT-05_20_2026-GO95HV-1^668086/00 12/010 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003065 | 584920539-61321-DETAIL-04_03_2025-GO95MLD-1^06241005.0093002 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003066 | 559386656-9351-DETAIL-08_11_2025-GO95HV-1^06246002.0094001 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003067 | 559473269-6929-DETAIL-04_23_2025-GO95HV-1^06242006.0038702 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003068 | 559898877-69751-DETAIL-08_06_2025-GO95HV-1^06246002.0144200 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003069 | 560478795-42999-DETAIL-09_09_2025-GO95HV-1^06246007.0151150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003070 | 560718643-1863-DTLTRT-07_03_2025-POLEREPL-1^668087/00 9/012 | POLE | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003071 | 560823560-63833-DETAIL-09_10_2025-SVCROAD-1^07218001.0178200 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003072 | 561036958-67350-DETAIL-04_09_2026-BIRDDMG-1^06240003.0081801 | POLE | HFTD Tier 2 | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003073 | 561036958-67350-DETAIL-04_22_2025-GO95HV-1^06240003.0081801 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003074 | 561277569-58152-DTLSB-07_15_2025-GO95HV-1^06244006.0313042 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003075 | 561448463-63340-DTLTRT-05_29_2025-GO95HV-1^668075/00 10/008 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003076 | 561574584-61009-DETAIL-08_13_2025-GO95HV-1^06247006.0255400 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003077 | 561655568-5659-DTLSB-08_12_2025-GO95MLD-1^07217001.0025801 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003078 | 562502724-5379-DTLSB-07_09_2026-GO95HV-1^06240008.0158100 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003079 | 562513891-34902-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003080 | 562543083-58480-DETAIL-02_11_2025-RISEGRD-1^06240004.0167405 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003081 | 584998364-62068-DETAIL-09_03_2025-GO95HV-1^07216001.0098000 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003082 | 58535886-11500-DETAIL-02_05_2026-GO95HV-1^06239003.0017602 | OTHER | Non-HFTD | Distribution | 2026-02-05 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003083 | 585614788-55939-DETAIL-05_15_2025-GO95HV-1^06243006.0097400 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003084 | 585665311-64373-DETAIL-09_18_2025-GO95HV-1^06246006.0013600 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003085 | 585999785-29469-DETAIL-05_28_2025-GO95BLTC-1^06244006.0030800 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003086 | 586028101-6979-DETAIL-10_01_2025-CLRTOUCH-1^06148001.0303101 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003087 | 586058816-72491-DETAIL-05_14_2025-GO95HV-1^06142012.0117401 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003088 | 532969466-88970-DETAIL-04_07_2025-GRDRODHI-1^06241005.0017800 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003089 | 533009564-88683-DETAIL-09_22_2025-GO95MLD-1^07218001.0085100 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003090 | 533009564-88683-DETAIL-09_22_2025-GRDRODHI-1^07218001.0085100 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003091 | 533487581-2052-DETAIL-06_26_2023-CUSTWIRE-1^06244009.0310701 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003092 | 198162248-10830-DETAIL-01_22_2026-GO95MLD-1^06240003.0314700 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003093 | 198186279-35630-DETAIL-08_25_2025-GO95HV-1^06246001.0206601 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003094 | 198187651-9919-DRONE_HY-07_15_2026-UBPBXARM-1^668036/00 4/054 | CROSSARM | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003095 | 198490137-67199-DETAIL-06_11_2025-GO95HV-1^06245006.0297201 | OTHER | Non-HFTD | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003096 | 19856601-53840-ADMIN-12_23_2024-POLEREPL-1^06142012.0132507 | POLE | Non-HFTD | Distribution | 2024-12-23 | 2027-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003097 | 533576029-66753-AUDIT-05_22_2024-SVCRUBLG-1^06245007.0226447 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003098 | 533630950-35139-DTLTRT-07_10_2025-BIRDDMG-1^668087/00 2/024 | POLE | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003099 | 533630950-66382-DTLTRT-07_10_2025-BIRDDMG-1^668087/00 2/024 | POLE | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003100 | 534046015-6089-DETAIL-08_28_2025-GO95MLD-1^06247006.0192800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003101 | 534046015-6089-DETAIL-08_28_2025-GRDRODHI-1^06247006.0192800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003102 | 564014925-78763-DETAIL-05_26_2026-GO95HV-1^07217001.0143202 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003103 | 564128511-13261-AUDIT-10_14_2025-GO95MLD-1^07216001.0077700 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003104 | 564128511-13261-AUDIT-10_14_2025-GO95TCH-1^07216001.0077700 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003105 | 564199214-88453-DETAIL-05_21_2026-SVCDEFLC-1^07217001.0142700 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003106 | 564229589-47969-DETAIL-04_08_2026-GO95HV-1^06240002.0323301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003107 | 564655734-18219-DTLSB-01_28_2026-GO95MLD-1^06242009.0057800 | OTHER | Non-HFTD | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003108 | 564835823-63780-DETAIL-02_24_2026-GO95HV-1^06239002.0180801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003109 | 564893163-79961-ADMIN-11_14_2025-GRDRODHI-1^06246001.0328600 | OTHER | Non-HFTD | Distribution | 2025-11-14 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003110 | 536240365-49400-DETAIL-02_09_2026-BIRDDMG-1^06239003.0015800 | POLE | Non-HFTD | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003111 | 536403473-23590-DETAIL-02_24_2026-BIRDDMG-1^06239002.0275202 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003112 | 536533709-83721-DETAIL-09_03_2025-GO95HV-1^06146001.0077501 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003113 | 537107136-56789-DETAIL-10_14_2025-SVCROAD-1^06148001.0175200 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003114 | 537190354-67121-DETAIL-10_06_2025-SVCROAD-1^06148001.0310601 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003115 | 537257984-16710-DETAIL-03_18_2025-GO95HV-1^06238004.0156400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003116 | 537327118-25153-DTLSB-06_04_2026-GO95HV-1^07216001.0146502 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003117 | 537327118-25153-DTLSB-06_04_2026-GUYHINS-1^07216001.0146502 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003118 | 537538278-39450-DETAIL-04_09_2026-BIRDDMG-1^06240003.0052000 | POLE | HFTD Tier 2 | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003119 | 537948730-54879-DETAIL-06_18_2025-GO95HV-1^06248004.0341803 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003120 | 53800670-57919-DRONE_HY-07_15_2026-UBPRMSHD-1^668036/00 18/053 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120003121 | 538085736-97169-DETAIL-08_12_2025-GO95HV-1^06247006.0269300 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003122 | 538366685-71199-ADMIN-10_20_2025-GUYHINS-1^06246012.0119606 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003123 | 538380671-55180-DETAIL-03_12_2026-COVCOTHR-1^06240004.0323500 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-12 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003124 | 538637544-29053-DETAIL-05_21_2026-GO95HV-1^07217001.0144801 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003125 | 538637544-29053-DETAIL-05_21_2026-SVCNEUT-1^07217001.0144801 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003126 | 564948479-41061-DETAIL-08_13_2025-GO95HV-1^06246002.0365400 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003127 | 565068096-63279-DETAIL-04_21_2025-GO95HV-1^06242006.0071500 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003128 | 565482479-36769-DTLSB-04_23_2026-GUYHINS-1^06241009.0272700 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003129 | 565591216-97879-DETAIL-02_03_2025-GO95BLTC-1^06239004.0244948 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003130 | 565906035-92499-DTLSB-07_03_2025-GO95HV-1^06244006.0225208 | OTHER | Non-HFTD | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003131 | 565909093-26729-DTLSB-01_26_2026-SVCROAD-1^06242009.0298404 | OTHER | Non-HFTD | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003132 | 56627484-81039-DTLTRT-05_21_2026-GRDRODHI-1^668086/00 4/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003133 | 566423883-94883-DETAIL-10_02_2025-GO95HV-1^06148001.0304204 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003134 | 539478486-88831-DETAIL-05_15_2025-GO95HV-1^06142012.0117202 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003135 | 539520571-28469-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003136 | 539520571-55702-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003137 | 539549600-11310-DTLSB-06_10_2026-GRDRODHI-1^07217001.0351405 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003138 | 539573396-48119-DTLSB-07_17_2025-ABNDEQPM-1^06244006.0218304 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003139 | 540283085-19770-DETAIL-04_07_2026-GO95HV-1^06240003.0367006 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003140 | 540494985-77631-DTLSB-04_30_2026-GO95HV-1^06142013.0183400 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003141 | 540513126-37990-DTLTRT-10_24_2023-CUSTWIRE-1^668010/00 3/010 | OTHER | HFTD Tier 2 | Transmission | 2023-10-24 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003142 | 540574998-43259-DETAIL-09_02_2025-GO95HV-1^06247006.0277800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003143 | 540585861-7731-ADMIN-02_09_2024-POLEREPL-1^06144006.0109901 | POLE | Non-HFTD | Distribution | 2024-02-09 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003144 | 541064243-61529-DETAIL-05_12_2025-GO95HV-1^06142012.0014802 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003145 | 541116418-77418-DETAIL-04_17_2019-SVCROOF-1^06142012.0122002 | OTHER | Non-HFTD | Distribution | 2019-04-17 | 2022-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003146 | 541138623-39949-DTLSB-04_09_2024-CUSTWIRE-1^06245007.0228006 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003147 | 603965329-75029-DETAIL-07_01_2025-GO95HV-1^668087/00 14/015 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003148 | 603965329-76029-DETAIL-07_01_2025-GO95HV-1^668087/00 14/015 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003149 | 603965329-8329-DETAIL-07_01_2025-GO95HV-1^668087/00 14/015 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003150 | 604389039-39829-DTLSB-02_03_2026-GO95HV-1^06243009.0304401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003151 | 604743991-84480-DETAIL-02_23_2026-GO95HV-1^06239002.0033402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003152 | 604785533-6189-DETAIL-09_22_2025-GO95HV-1^06247006.0064400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003153 | 605333475-35121-DETAIL-08_25_2025-GO95HV-1^06246001.0174300 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003154 | 605520221-82869-DTLSB-07_14_2025-GRDRODHI-1^06244007.0157800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003155 | 542286853-73359-DTLTRT-04_22_2026-GO95HV-1^668004/02 13/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003156 | 542357709-97709-DETAIL-08_18_2025-GO95HV-1^06247006.0362102 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003157 | 54332695-93933-DETAIL-09_16_2025-GO95HV-1^06247004.0081542 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003158 | 54337856-35789-DETAIL-10_07_2025-GO95HV-1^06148001.0173000 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003159 | 543559419-27359-DETAIL-07_22_2025-GO95HV-1^06247005.0058801 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003160 | 543852957-20759-DETAIL-08_18_2025-GO95HV-1^07218001.0355301 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003161 | 543964741-96350-DETAIL-01_21_2026-COVCOTHR-1^06239004.0124904 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003162 | 544123690-28870-DETAIL-02_18_2026-GO95HV-1^06239002.0094001 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003163 | 544581343-57370-ADMIN-04_08_2026-POLEREPL-1^668067/00 2/008 | POLE | Non-HFTD | Transmission | 2026-04-08 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003164 | 544735771-92941-DETAIL-08_13_2025-SVCROAD-1^06246002.0360001 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003165 | 544907046-41509-ADMIN-11_10_2025-GO95BLTC-1^06246011.0063101 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003166 | 545012342-91560-DETAIL-04_29_2026-GO95HV-1^668004/00 7/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003167 | 545109973-81729-DTLSB-01_20_2026-GO95HV-1^06242009.0299202 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003168 | 545302729-48631-DETAIL-08_13_2025-GO95HV-1^06246002.0364400 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003169 | 545312945-76451-DETAIL-02_24_2025-GO95MLD-1^06239004.0366705 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003170 | 545548993-81089-DETAIL-08_06_2025-GO95HV-1^06247006.0200200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003171 | 515565498-9389-DETAIL-09_30_2025-GO95HV-1^06148001.0300014 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003172 | 516146933-35021-DRONE_HY-06_19_2026-COVCOTHR-2^06239004.0364900 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003173 | 516179316-32280-DETAIL-01_24_2025-GO95HV-1^06239004.0257945 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003174 | 516180060-17491-DETAIL-06_04_2025-GO95HV-1^06142012.0105501 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003175 | 516236391-28739-DETAIL-05_19_2025-GO95HV-1^06243006.0274200 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003176 | 516890569-41519-DTLSB-05_19_2026-GO95HV-1^06240008.0134900 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003177 | 516890663-79779-DETAIL-08_13_2025-ABNDEQPM-1^06247006.0258300 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003178 | 51754250-27539-DETAIL-07_06_2026-GO95HV-1^07217001.0117900 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003179 | 517808425-15009-DETAIL-08_04_2025-GO95HV-1^06247006.0208405 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003180 | 517808425-15009-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0208405 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003181 | 517808425-15009-DETAIL-08_04_2025-SVCENTCO-1^06247006.0208405 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003182 | 517942952-52560-DETAIL-04_29_2026-GO95HV-1^668004/00 8/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003183 | 518110264-90960-DRONE_HY-06_19_2026-COVCOTHR-2^06240004.0161406 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003184 | 518110264-90960-DRONE_HY-06_19_2026-COVCOTHR-3^06240004.0161406 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003185 | 518226964-94401-DETAIL-09_04_2025-GO95HV-1^06147001.0319001 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003186 | 518343826-80990-DETAIL-02_11_2025-GO95BLTC-1^06240004.0351602 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003187 | 567414163-64699-DETAIL-08_19_2025-GO95HV-1^06247006.0366604 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003188 | 567597763-25683-ADMIN-10_22_2025-ENCHRW-1^07218001.0087501 | OTHER | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003189 | 567783101-50231-DETAIL-04_15_2025-GO95MLD-1^06242005.0333300 | OTHER | HFTD Tier 2 | Distribution | 2025-04-15 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003190 | 567829369-53549-DTLSB-07_16_2025-GO95HV-1^06244006.0317141 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003191 | 567938860-29270-DETAIL-03_24_2026-COVCOTHR-2^06240004.0220403 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003192 | 567938860-29270-DETAIL-03_24_2026-GUYHINS-1^06240004.0220403 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003193 | 567938860-29270-DETAIL-03_24_2026-GUYHINS-2^06240004.0220403 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003194 | 568091435-94435-DETAIL-05_29_2025-GO95HV-1^06147014.0010600 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003195 | 519974165-32700-DETAIL-03_02_2026-SVCROAD-1^06239003.0243904 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003196 | 520050671-52620-ADMIN-10_23_2025-GO95MLD-1^07117002.0211102 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003197 | 520255701-22489-DTLSB-01_22_2026-GRDRODHI-1^06242009.0296301 | OTHER | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003198 | 520255701-22489-DTLSB-01_22_2026-SVCDEFLC-1^06242009.0296301 | OTHER | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003199 | 520316529-56529-DETAIL-04_17_2025-GO95HV-1^06242005.0354901 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003200 | 520383598-49773-DETAIL-09_15_2025-GO95HV-1^07216001.0085103 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003201 | 520575753-22953-DETAIL-10_12_2022-GUYHINS-1^668005/08 8X8/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003202 | 520575753-22953-DETAIL-10_12_2022-GUYHINS-3^668005/08 8X8/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003203 | 520575753-22953-DETAIL-10_12_2022-GUYHINS-4^668005/08 8X8/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003204 | 520973408-59229-DETAIL-05_15_2025-GO95HV-1^06142012.0114205 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003205 | 521101882-42750-DETAIL-02_11_2026-GO95HV-1^06239003.0015303 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003206 | 521437178-90550-DETAIL-04_22_2025-GO95HV-1^06240003.0052100 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003207 | 521645673-17589-ADMIN-03_05_2025-POLEREPL-1^06245007.0274202 | POLE | Non-HFTD | Distribution | 2025-03-05 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003208 | 521970284-30049-ADMIN-03_18_2024-POLEDERP-1^07113001.0175500 | POLE | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003209 | 546761285-83285-DETAIL-06_02_2025-GO95HV-1^06148014.0239900 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003210 | 546816666-90041-DETAIL-05_15_2025-GO95HV-1^06142012.0119202 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003211 | 547147698-60899-DETAIL-09_24_2025-GO95HV-1^06246009.0075002 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003212 | 547187722-48980-DETAIL-02_25_2025-SVCNEUT-1^06240005.0016000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003213 | 547335161-97280-DETAIL-02_16_2026-GO95HV-1^06239001.0046701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003214 | 547578809-39389-DETAIL-09_30_2025-ABNDEQPM-1^06246009.0243500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003215 | 54830916-59129-DETAIL-05_12_2025-GO95HV-1^06142012.0017801 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003216 | 548330817-48490-DETAIL-01_14_2026-GO95CL10-1^06239004.0244946 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003217 | 523405175-99899-DETAIL-09_09_2025-GO95HV-1^06246007.0225950 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003218 | 523492864-25864-DTLTRT-07_08_2025-GUYHINS-1^668087/00 5/027 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003219 | 523492864-25864-DTLTRT-07_08_2025-GUYHINS-2^668087/00 5/027 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003220 | 523832510-7683-DETAIL-08_19_2025-SVCDEFLC-1^07216001.0176603 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003221 | 52390228-52613-DETAIL-09_02_2025-GO95HV-1^06247006.0278400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003222 | 52390228-52613-DETAIL-09_02_2025-GO95MLD-1^06247006.0278400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003223 | 523974843-12559-DTLTRT-04_20_2026-GO95HV-1^668004/02 4/004 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003224 | 524041634-7539-DETAIL-05_22_2025-GO95HV-1^06244006.0092300 | OTHER | Non-HFTD | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003225 | 524486506-66711-DTLSB-06_04_2026-GO95HV-1^07216001.0114101 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003226 | 524581891-16811-DTLTRT-06_25_2025-BIRDDMG-1^668087/00 5/008 | POLE | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003227 | 524623178-94299-DTLSB-04_01_2026-GO95HV-1^06241009.0328101 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003228 | 52499796-8080-DETAIL-01_23_2025-GO95HV-1^06239004.0256647 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003229 | 525003106-3489-DTLSB-07_15_2025-GO95HV-1^06244006.0271704 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003230 | 525003106-3489-DTLSB-07_15_2025-SVCROAD-1^06244006.0271704 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003231 | 525018584-29829-DETAIL-03_14_2017-CUSTWIRE-1^06142012.0132811 | OTHER | Non-HFTD | Distribution | 2017-03-14 | 2020-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003232 | 548375586-31441-DTLSB-10_16_2025-GO95TCH-1^06247001.0355000 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003233 | 548702716-84659-DETAIL-07_28_2025-GO95HV-1^06247005.0318200 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003234 | 548720243-85641-DETAIL-09_29_2025-GO95HV-1^06148001.0310604 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003235 | 548841583-49983-DTLSB-07_24_2025-GO95HV-1^07218001.0266960 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003236 | 549258023-75699-DTLSB-01_21_2026-ABNDEQPM-1^06242009.0296107 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003237 | 549258023-75699-DTLSB-01_21_2026-SVCROAD-1^06242009.0296107 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003238 | 54956659-76659-DETAIL-06_23_2025-GRDRODHI-1^06241003.0331700 | OTHER | Non-HFTD | Distribution | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003239 | 549673598-69499-DTLSB-07_21_2025-GO95HV-1^06244007.0036904 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003240 | 525503871-97809-DETAIL-09_03_2025-SVCDEFLC-1^06247006.0210603 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003241 | 525658313-52979-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0263400 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003242 | 525701883-77659-DETAIL-07_29_2025-GO95HV-1^06247005.0215601 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003243 | 525783513-67580-DETAIL-02_18_2026-BIRDDMG-1^06239002.0168500 | POLE | HFTD Tier 2 | Distribution | 2026-02-18 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003244 | 525783513-67580-DETAIL-02_18_2026-GO95HV-1^06239002.0168500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003245 | 525950083-71779-DETAIL-04_04_2024-SVCWIND-1^06247005.0280300 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003246 | 526120966-2011-DETAIL-08_21_2025-GO95HV-1^06246001.0199200 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003247 | 526832730-38401-AUDIT-05_07_2025-COVCOTHR-1^06241005.0030800 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-05-07 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003248 | 526963548-76259-DETAIL-09_02_2025-GO95HV-1^06247006.0276503 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003249 | 526963548-76259-DETAIL-09_02_2025-GRDRODHI-2^06247006.0276503 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003250 | 526998190-94859-DETAIL-06_16_2025-GO95HV-1^06248005.0285100 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003251 | 527077018-1911-DTLTRT-06_23_2025-BIRDDMG-1^668087/00 14/002 | POLE | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003252 | 527139438-90570-DETAIL-04_06_2026-GUYHINS-1^06236005.0116900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003253 | 527276629-37279-DETAIL-09_17_2025-GO95HV-1^06248007.0240403 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003254 | 527466101-33929-DETAIL-06_04_2025-GO95HV-1^06142012.0082100 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003255 | 494612864-49932-DETAIL-03_06_2025-GO95TCH-1^06241005.0120106 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003256 | 49474198-41919-DETAIL-05_18_2026-GUYHINS-2^06242009.0287202 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003257 | 495027085-29085-DETAIL-06_02_2025-GRDRODHI-1^06148014.0238901 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003258 | 495275263-26669-DETAIL-08_18_2025-SVCDEFLC-1^06247006.0364700 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003259 | 496299484-45071-DETAIL-09_11_2025-GO95BLTC-1^06147001.0113300 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003260 | 496381888-73159-DETAIL-01_23_2026-COVCOTHR-1^06240004.0132200 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003261 | 496381888-73159-DETAIL-01_23_2026-COVCOTHR-2^06240004.0132200 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003262 | 496381888-73159-DETAIL-01_23_2026-GUYHINS-1^06240004.0132200 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003263 | 498115248-66550-DETAIL-02_03_2026-GO95HV-1^06239003.0018416 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003264 | 498500142-83142-DETAIL-09_18_2025-GO95HV-1^06246006.0011600 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003265 | 499144023-50030-DTLSB-07_30_2025-GO95HV-1^07218001.0272200 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003266 | 499219948-27240-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 1/054 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003267 | 499268881-60401-DETAIL-04_15_2025-ANCHIDLE-1^06242005.0332501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-15 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003268 | 49928789-10350-DTLTRT-06_24_2025-SVCROAD-1^668087/00 9/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003269 | 49964320-29753-DETAIL-09_04_2025-GO95HV-1^06247006.0160201 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003270 | 499751358-98779-DETAIL-08_18_2025-GO95HV-1^06246002.0264300 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003271 | 499783024-98629-DETAIL-04_26_2022-CUSTWIRE-1^06143012.0239303 | OTHER | Non-HFTD | Distribution | 2022-04-26 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003272 | 500148458-11378-DETAIL-09_17_2025-GO95MLD-1^07218001.0055600 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003273 | 500223351-35351-DETAIL-02_24_2026-BIRDDMG-1^06239002.0225202 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003274 | 500469104-4790-DETAIL-01_27_2026-GO95HV-1^06239002.0063602 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003275 | 196367789-21975-AUDIT-06_24_2026-GRDRODHI-1^07216001.0023800 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003276 | 196367789-21975-DTLSB-05_29_2026-GO95HV-1^07216001.0023800 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003277 | 196774323-15323-DETAIL-06_10_2025-GUYHINS-1^668075/00 14/034 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003278 | 196999440-52261-DETAIL-04_08_2025-ANCHIDLE-1^06241005.0092305 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003279 | 568238026-65552-AUDIT-05_06_2025-ABNDEQPM-1^06242005.0368701 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003280 | 56829986-57842-ADMIN-11_10_2025-GO95BLTC-1^06246011.0065402 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003281 | 568387239-49929-DETAIL-04_21_2025-GO95HV-1^06242006.0037804 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003282 | 568578933-59071-ADMIN-11_12_2025-GO95MLD-1^06246001.0323101 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003283 | 568666850-87299-DETAIL-10_07_2025-GO95BLTC-1^06246008.0028902 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003284 | 568666850-87299-DETAIL-10_07_2025-GO95TCH-1^06246008.0028902 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003285 | 568812213-32679-DETAIL-06_09_2025-GO95HV-1^06245006.0195501 | OTHER | Non-HFTD | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003286 | 569534936-35050-DETAIL-06_26_2026-CUSTWIRE-1^07218001.0342100 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003287 | 501039956-75660-DTLTRT-04_30_2026-GO95HV-1^668004/00 3/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003288 | 501369293-77709-DETAIL-09_04_2025-GO95HV-1^06247006.0071200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003289 | 501405711-3100-DTLSB-06_08_2026-GUYHINS-1^07216001.0231102 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003290 | 501460501-94449-DTLSB-07_14_2025-GO95HV-1^06244007.0228701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003291 | 501994201-26632-DETAIL-04_02_2025-SVCROAD-1^06241005.0117707 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003292 | 502505799-4153-DTLSB-04_22_2024-SVCROOF-1^06245007.0225441 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003293 | 502930756-31669-DETAIL-08_18_2025-GO95HV-1^06247006.0364300 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003294 | 502930756-31669-DETAIL-08_18_2025-SVCDEFLC-1^06247006.0364300 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003295 | 502960254-2881-DTLTRT-06_30_2025-GO95HV-1^668087/02 5/001 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003296 | 503074884-6081-DTLTRT-05_14_2026-CUSTWIRE-1^668085/00 16/004 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003297 | 503078241-959-DETAIL-09_23_2025-GO95HV-1^06248007.0279600 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003298 | 503171202-9809-DETAIL-09_30_2025-GRDRODHI-1^06246008.0181000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003299 | 503171202-9809-DETAIL-09_30_2025-GRDRODHI-2^06246008.0181000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003300 | 503897763-7699-DTLSB-01_20_2026-GO95HV-1^06242009.0298000 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003301 | 50395584-82799-DTLSB-07_10_2025-BIRDDMG-1^06244007.0144904 | POLE | HFTD Tier 2 | Distribution | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003302 | 50395584-82799-DTLSB-07_10_2025-GO95HV-1^06244007.0144904 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003303 | 528353088-91659-DETAIL-09_03_2025-GO95HV-1^07216001.0095000 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003304 | 528873533-96979-DTLSB-03_31_2022-ENCHRW-1^06145006.0223502 | OTHER | Non-HFTD | Distribution | 2022-03-31 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003305 | 52888046-44069-DTLSB-03_16_2026-GO95HV-1^06242009.0136303 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003306 | 529785251-23569-DETAIL-09_11_2025-SVCDEFLC-1^06248007.0222101 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003307 | 529819333-96599-DETAIL-09_17_2025-GRDRODHI-2^06147001.0237701 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003308 | 529839073-55411-ADMIN-10_21_2025-GO95HV-1^06247001.0266901 | OTHER | Non-HFTD | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003309 | 53014774-82390-DETAIL-01_28_2026-GO95BLTC-1^06239002.0067807 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003310 | 505033128-3550-DETAIL-03_26_2025-GO95HV-1^06239003.0018401 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003311 | 505106568-48960-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 9/064 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003312 | 505113600-11029-DETAIL-03_20_2017-SVCWIND-1^06142012.0133501 | OTHER | Non-HFTD | Distribution | 2017-03-20 | 2020-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003313 | 5052350-17270-DETAIL-02_18_2025-GO95TCH-1^06240004.0220409 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003314 | 505398239-86639-DETAIL-06_04_2025-GO95MLD-1^668075/00 15/025 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003315 | 505673798-80190-DRONE_HY-07_01_2026-COVCOTHR-1^06239004.0365504 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003316 | 505823698-32009-ADMIN-10_23_2025-GO95HV-1^06246011.0366100 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003317 | 505922959-27029-DETAIL-06_04_2025-GRDRODHI-1^06142012.0105400 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003318 | 50628686-72500-DETAIL-02_25_2026-GO95HV-1^06239003.0242901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003319 | 506323694-58681-DETAIL-06_09_2026-GUYHINS-1^668086/00 17/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003320 | 506356815-76815-DETAIL-06_24_2025-GO95HV-1^06248004.0312907 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003321 | 506617200-64889-DETAIL-07_08_2024-GO95MLD-1^06244005.0136700 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003322 | 506795108-15890-DETAIL-01_30_2025-SVCENTCO-1^06239004.0245605 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003323 | 50693608-5109-DETAIL-10_14_2025-GO95HV-1^07117008.0178300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003324 | 507261939-45343-DETAIL-06_17_2025-GO95HV-1^06248004.0355240 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003325 | 530345266-65770-DETAIL-01_22_2025-GO95HV-1^06239004.0256652 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003326 | 530345266-65770-DETAIL-01_22_2025-GO95TCH-1^06239004.0256652 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003327 | 530580289-51911-DTLTRT-06_25_2025-GUYHINS-1^668087/00 13/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003328 | 530985590-76739-DTLTRT-06_25_2025-GO95MLD-1^668087/00 8/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003329 | 53103065-35790-ADMIN-10_10_2017-CUSTWIRE-1^668033/00 9/024 | OTHER | HFTD Tier 2 | Transmission | 2017-10-10 | 2020-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003330 | 531079135-63600-DETAIL-03_27_2025-GRDRODHI-1^06239003.0016717 | OTHER | HFTD Tier 2 | Distribution | 2025-03-27 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003331 | 531118520-44162-DETAIL-04_21_2025-GO95TCH-1^06242006.0037840 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003332 | 531338061-60711-DETAIL-04_10_2025-SVCROAD-1^06241005.0040202 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003333 | 479476876-28409-DETAIL-10_09_2025-ANCHIDLE-1^06246008.0029400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-09 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003334 | 479701569-46010-DTLSB-06_16_2026-GO95HV-1^07217001.0355901 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003335 | 479805194-689-DETAIL-08_13_2025-GO95HV-1^06247006.0253100 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003336 | 480338876-13759-DTLTRT-04_30_2026-GO95HV-1^668004/00 7/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003337 | 480457126-60470-DETAIL-01_23_2025-GO95HV-1^06239004.0256649 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003338 | 480457126-60470-DETAIL-01_23_2025-GO95MLD-1^06239004.0256649 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003339 | 480711500-96919-DTLSB-03_16_2026-GO95HV-1^06242009.0221601 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003340 | 480980129-88779-DETAIL-09_15_2025-GO95HV-1^06248007.0235400 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003341 | 481023918-33089-DETAIL-08_07_2025-GO95HV-1^06246002.0266901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003342 | 48107301-24809-DETAIL-09_03_2025-ANCHIDLE-1^06247006.0210400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003343 | 481075519-46430-DETAIL-03_17_2026-SVCDEFLC-1^06240004.0150143 | OTHER | HFTD Tier 3 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003344 | 481135159-60359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0331400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003345 | 481265538-66538-DTLSB-07_29_2025-GO95HV-1^07218001.0263701 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003346 | 481320844-5051-DETAIL-09_08_2025-GO95HV-1^06147001.0333000 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003347 | 48138651-29689-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0226701 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003348 | 508567765-10865-DETAIL-06_05_2025-GO95HV-1^06148014.0238401 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003349 | 508804475-71781-DETAIL-05_27_2025-GO95HV-1^06142012.0111600 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003350 | 508853850-59870-DETAIL-02_23_2026-GO95HV-1^06239002.0022502 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003351 | 508937355-71881-ADMIN-11_03_2025-GO95HV-1^06246001.0221901 | OTHER | Non-HFTD | Distribution | 2025-11-03 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003352 | 509004595-94881-ADMIN-11_03_2025-DISTHDWR-1^06246001.0223600 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-11-03 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003353 | 509040624-98329-DTLSB-03_03_2026-BIRDDMG-1^06243009.0255801 | POLE | Non-HFTD | Distribution | 2026-03-03 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003354 | 50914461-39883-DTLSB-06_05_2026-CUSTWIRE-1^07216001.0231908 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003355 | 509183170-15369-DTLTRT-06_15_2021-GO95HV-1^668041/00 17/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003356 | 483154833-3379-DTLSB-03_25_2026-SVCENTBK-1^06242009.0037300 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003357 | 48334525-38989-AUDIT-07_16_2025-GO95HV-1^06244006.0342101 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003358 | 483411570-77509-DETAIL-09_30_2025-GO95BLTC-1^06246009.0132700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003359 | 48342731-6809-DETAIL-09_03_2025-GO95HV-1^06247006.0211502 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003360 | 48342731-6809-DETAIL-09_03_2025-SVCDEFLC-1^06247006.0211502 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003361 | 483513959-37510-DETAIL-02_20_2025-SVCROAD-1^06241005.0262200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-20 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003362 | 483687076-85029-DETAIL-05_15_2025-GO95HV-1^06142012.0116202 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003363 | 483871104-5104-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 7/016 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003364 | 484068709-9709-DETAIL-08_18_2025-GO95BLTC-1^06247006.0361005 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003365 | 484068709-9709-DETAIL-08_18_2025-GO95HV-1^06247006.0361005 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003366 | 484101504-42763-DETAIL-09_11_2025-GO95HV-1^06248007.0230701 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003367 | 484123763-2051-DETAIL-03_10_2026-XARMSPCR-1^668041/00 12/026 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003368 | 484384914-83151-DETAIL-09_17_2025-ABNDEQPM-1^06147001.0143200 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003369 | 484689299-66183-DETAIL-08_19_2025-GO95HV-1^07216001.0176804 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003370 | 484689299-66183-DETAIL-08_19_2025-GO95MLD-1^07216001.0176804 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003371 | 484750784-89190-DETAIL-03_27_2025-GO95HV-1^06239003.0019615 | OTHER | Non-HFTD | Distribution | 2025-03-27 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003372 | 509575299-31191-DETAIL-08_21_2025-GO95HV-1^06246001.0206402 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003373 | 50975569-93950-AUDIT-09_02_2025-GRDRODHI-1^06246002.0345001 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003374 | 509763562-26850-DETAIL-02_11_2026-GO95HV-1^06239003.0016104 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003375 | 509945214-86214-DETAIL-07_24_2025-GO95HV-1^06247005.0160900 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003376 | 50997411-40823-DETAIL-06_17_2025-GO95HV-1^06248004.0349341 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003377 | 510094728-43179-ADMIN-11_12_2025-GO95BLTC-1^06246001.0283600 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003378 | 510094728-43179-ADMIN-11_12_2025-GO95HV-1^06246001.0283600 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003379 | 510227509-83530-DTLTRT-05_27_2025-GO95HV-1^668075/00 14/004 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003380 | 195244938-99233-DTLSB-07_07_2026-GO95HV-1^07217001.0272901 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003381 | 48569126-74169-DETAIL-08_20_2025-GO95HV-1^06247006.0369301 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003382 | 485712455-33455-DETAIL-02_09_2026-GO95HV-1^06239003.0019103 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003383 | 485839558-18259-DTLTRT-05_12_2026-GO95HV-1^668004/00 6/027 | OTHER | Non-HFTD | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003384 | 48588162-10139-DETAIL-05_21_2025-GO95HV-1^06243006.0079301 | OTHER | HFTD Tier 2 | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003385 | 485887625-1799-DTLSB-07_17_2025-GO95HV-1^06244007.0111600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003386 | 485930963-94351-DETAIL-04_20_2026-GO95HV-1^06142012.0146902 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003387 | 486011108-98550-DETAIL-04_22_2025-GO95HV-1^06240003.0054401 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003388 | 486106306-22510-DETAIL-03_05_2026-COVCOTHR-1^06238004.0114001 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003389 | 486106306-22510-DETAIL-03_05_2026-COVCOTHR-2^06238004.0114001 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003390 | 48611458-54479-DETAIL-10_15_2025-GO95HV-1^06148001.0143100 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003391 | 486123802-53802-DETAIL-09_17_2025-GO95HV-1^06246006.0080701 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003392 | 486230075-68939-DTLSB-07_02_2025-GO95HV-1^06244006.0226205 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003393 | 486596376-10476-DETAIL-09_08_2025-GO95HV-1^06147001.0330501 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003394 | 486664835-85439-DETAIL-05_29_2025-GO95HV-1^06244006.0112701 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003395 | 486667065-19751-DETAIL-05_12_2026-GO95HV-1^668038/00 1/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003396 | 199618358-44449-DTLSB-08_12_2025-GO95HV-1^07217001.0028100 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003397 | 549767632-20559-DTLTRT-04_29_2026-GO95HV-1^668004/00 5/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003398 | 549767632-20560-DTLTRT-04_29_2026-GO95HV-1^668004/00 5/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003399 | 549781192-20559-DETAIL-07_24_2025-GO95BLTC-1^06247005.0179901 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003400 | 549819258-86110-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 6/056 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003401 | 549865634-80549-DETAIL-09_18_2025-GO95HV-1^07218001.0086603 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003402 | 550201846-17659-DETAIL-07_28_2025-GO95HV-1^06247005.0318300 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003403 | 550259143-84880-DETAIL-02_12_2025-GO95CL10-1^06240004.0167006 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003404 | 488112638-69640-DETAIL-03_02_2026-GO95HV-1^06239003.0136000 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003405 | 488311678-459-DETAIL-06_17_2025-SVCENTCO-1^06248004.0356100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003406 | 48847993-67999-DETAIL-08_20_2025-XARMSPCR-1^06247006.0257601 | CROSSARM | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003407 | 488759894-58994-DETAIL-03_30_2023-CUSTWIRE-1^06142016.0084910 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003408 | 488839334-11179-DETAIL-06_17_2025-GO95HV-1^06248004.0281000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003409 | 488976428-72999-DETAIL-05_14_2026-CLRTOUCH-1^06242009.0283304 | CONDUCTOR | Non-HFTD | Distribution | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003410 | 488996653-41661-DETAIL-06_10_2026-GUYHINS-1^668086/00 14/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003411 | 489107926-90409-DETAIL-08_21_2025-GO95HV-1^06247006.0262900 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003412 | 489238624-36761-DETAIL-09_08_2025-GO95HV-1^06147001.0332200 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003413 | 489246553-88783-DETAIL-09_18_2025-GO95HV-1^07218001.0088100 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003414 | 489364936-27861-DTLTRT-05_21_2026-DISTHDWR-1^668086/00 1/015 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003415 | 489624481-3480-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0167201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003416 | 489757650-16759-DTLSB-07_29_2025-GO95HV-1^07218001.0263100 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003417 | 490156254-99719-ADMIN-11_04_2024-GO95STUB-1^668036/00 10/032 | OTHER | Non-HFTD | Transmission | 2024-11-04 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003418 | 490214021-25320-ADMIN-10_23_2025-GO95MLD-1^07117002.0211101 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003419 | 460719445-18670-DETAIL-01_23_2026-GO95MLD-1^06240003.0184902 | OTHER | HFTD Tier 2 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003420 | 461159446-3340-DETAIL-02_24_2025-GO95TCH-1^06240004.0152600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003421 | 461215324-71399-DETAIL-06_17_2025-GO95HV-1^06248004.0282001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003422 | 461471540-61799-DETAIL-10_07_2025-ABNDEQPM-1^06246008.0041400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003423 | 461481216-83069-DTLSB-03_16_2026-BIRDDMG-1^06242009.0136203 | POLE | Non-HFTD | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003424 | 461516944-46069-DETAIL-09_29_2025-GO95BLTC-1^06246009.0110300 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003425 | 461526851-34189-ADMIN-10_27_2025-GRDRODHI-1^06246001.0014500 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003426 | 462619863-40929-DETAIL-05_12_2025-GO95HV-1^06142012.0017804 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003427 | 462642253-82621-DRONE_HY-07_10_2026-DISTHDWR-1^06143014.0183300 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003428 | 462644784-16859-DTLTRT-04_22_2026-GO95HV-1^668004/02 7/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003429 | 462816486-98169-DTLTRT-10_14_2020-CUSTWIRE-1^668047/00 8/030 | OTHER | HFTD Tier 2 | Transmission | 2020-10-14 | 2023-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003430 | 463044741-61543-DTLSB-06_02_2026-SVCROAD-1^07216001.0116800 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003431 | 463085748-62640-DETAIL-07_06_2022-CUSTWIRE-1^07116007.0219600 | OTHER | HFTD Tier 2 | Distribution | 2022-07-06 | 2025-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003432 | 463129819-14670-DETAIL-04_02_2026-GO95MLD-1^06236005.0169001 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003433 | 511319291-60391-DETAIL-09_25_2025-GUYHINS-1^07218001.0212900 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-25 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003434 | 512186983-81870-DETAIL-12_18_2024-BIRDDMG-1^668002/00 7/064 | POLE | HFTD Tier 2 | Transmission | 2024-12-18 | 2027-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003435 | 512477290-21559-DETAIL-09_16_2025-GO95HV-1^06246006.0018203 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003436 | 512939710-50810-DETAIL-06_03_2025-GO95HV-1^06148015.0312200 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003437 | 51306423-90039-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0267801 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003438 | 513096091-37919-DTLSB-03_16_2026-BIRDDMG-1^06242009.0221501 | POLE | Non-HFTD | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003439 | 513096091-37919-DTLSB-03_16_2026-GO95HV-1^06242009.0221501 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003440 | 464319998-23449-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0147502 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003441 | 464471384-15969-DTLSB-01_21_2026-GO95HV-1^06242009.0298305 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003442 | 464723443-67584-DETAIL-03_31_2025-GO95MLD-1^06241005.0115606 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003443 | 464723443-67584-DETAIL-03_31_2025-SVCENTCO-1^06241005.0115606 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003444 | 464738854-56954-DETAIL-01_13_2025-SVCDEFLC-1^06240004.0085220 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003445 | 46492642-13040-DTLSB-07_07_2025-GO95HV-1^06245007.0357400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003446 | 465090434-41829-DETAIL-04_19_2022-CUSTWIRE-1^06142012.0131805 | OTHER | Non-HFTD | Distribution | 2022-04-19 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003447 | 465220879-15549-ADMIN-07_19_2024-POLETOP-1^06245007.0224008 | POLE | Non-HFTD | Distribution | 2024-07-19 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003448 | 465367332-61980-ADMIN-04_22_2026-SVCTREE-1^06240004.0290000 | OTHER | HFTD Tier 3 | Distribution | 2026-04-22 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003449 | 465586139-70631-ADMIN-07_12_2024-POLEDERP-1^668038/00 1/068 | POLE | Non-HFTD | Transmission | 2024-07-12 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003450 | 46621629-90440-DETAIL-02_06_2025-GO95MLD-1^06239003.0061103 | OTHER | HFTD Tier 3 | Distribution | 2025-02-06 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003451 | 46626069-70679-DTLSB-05_19_2026-GO95HV-1^06240007.0183401 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003452 | 46714394-78460-DRONE_HY-07_15_2026-COVCOTHR-2^06239004.0256702 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003453 | 467448009-57931-ADMIN-11_12_2025-GO95HV-1^06246001.0335600 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003454 | 491856678-97029-DETAIL-04_28_2026-GO95HV-1^06142012.0148702 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003455 | 491856678-97029-DETAIL-04_28_2026-SVCDEFLC-1^06142012.0148702 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003456 | 491887025-75189-ADMIN-10_22_2025-GO95BLTC-1^06246011.0067301 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003457 | 491887025-75189-ADMIN-10_22_2025-GUYHINS-1^06246011.0067301 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003458 | 491888554-63809-ADMIN-10_21_2025-CUSTWIRE-1^06246012.0052600 | OTHER | HFTD Tier 2 | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003459 | 195528596-96189-DETAIL-06_05_2025-GO95HV-1^06245007.0249700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003460 | 195557951-79199-DETAIL-06_18_2025-GO95HV-1^06248004.0340702 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003461 | 195650256-77199-DETAIL-08_21_2024-SVCSVC-1^06245006.0095900 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003462 | 468825946-71953-DTLSB-06_16_2026-GO95HV-1^07217001.0355802 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003463 | 468858075-24939-DTLSB-07_02_2025-GO95HV-1^06244006.0228200 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003464 | 468858075-24939-DTLSB-07_02_2025-GO95MLD-1^06244006.0228200 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003465 | 469286349-43739-DTLTRT-06_25_2025-GUYHINS-1^668087/00 2/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003466 | 46963070-35070-DETAIL-03_03_2025-SVCROAD-1^06241005.0132600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003467 | 469709969-51199-DETAIL-09_17_2025-GO95HV-1^06248007.0241300 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003468 | 193053821-2722-DTLTRT-04_27_2026-GO95HV-1^668004/00 8/004 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003469 | 193230510-43269-DETAIL-10_09_2025-CUSTWIRE-1^06248003.0272201 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003470 | 193477561-150-DETAIL-03_04_2026-BIRDDMG-1^06239003.0185700 | POLE | HFTD Tier 3 | Distribution | 2026-03-04 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003471 | 193676572-72639-DETAIL-05_21_2025-GO95HV-1^06243006.0155900 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003472 | 193709919-90349-ADMIN-03_13_2025-POLEREPL-1^06245007.0217704 | POLE | Non-HFTD | Distribution | 2025-03-13 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003473 | 4697123-35659-DTLTRT-04_21_2026-GO95HV-1^668004/02 5/006 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003474 | 470020098-63053-DTLSB-06_04_2026-GO95HV-1^07216001.0144600 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003475 | 470835171-14380-DETAIL-02_14_2025-GO95BLTC-1^06240004.0168044 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003476 | 471213369-52352-DTLSB-07_21_2025-GO95HV-1^06244006.0307542 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003477 | 471231631-38020-DETAIL-02_20_2025-GO95HV-1^06241005.0265300 | OTHER | HFTD Tier 3 | Distribution | 2025-02-20 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003478 | 196306326-56470-DRONE_HY-07_15_2026-COVCOTHR-1^06239004.0257700 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003479 | 196306326-56470-DRONE_HY-07_15_2026-COVCOTHR-3^06239004.0257700 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003480 | 491941609-74609-DETAIL-03_05_2025-GO95BLTC-1^06241005.0121201 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003481 | 492091289-64569-DETAIL-09_16_2025-GO95HV-1^06246006.0017300 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003482 | 492147606-67606-DETAIL-01_22_2026-GO95MLD-1^06239004.0227202 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003483 | 492168154-32089-DETAIL-08_27_2025-GO95HV-1^06247006.0174200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003484 | 492597325-425-DETAIL-06_05_2025-ABNDEQPM-1^06148014.0245000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003485 | 492597325-425-DETAIL-06_05_2025-GO95HV-1^06148014.0245000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003486 | 473360166-88552-DETAIL-04_24_2025-GO95HV-1^06242006.0174501 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003487 | 473388193-90822-ADMIN-11_10_2025-GO95BLTC-1^06246012.0128800 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003488 | 473398640-84899-DETAIL-10_02_2025-GO95TCH-1^06246008.0050702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003489 | 473913341-23523-DETAIL-06_17_2024-CUSTWIRE-1^06246006.0137702 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003490 | 474129808-59359-DETAIL-06_04_2024-CUSTWIRE-1^06246005.0320503 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003491 | 474212246-14246-DETAIL-09_30_2025-GO95HV-1^06246009.0133303 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003492 | 47426518-50760-DETAIL-10_21_2024-BIRDDMG-1^668014/00 6/053 | POLE | HFTD Tier 3 | Transmission | 2024-10-21 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003493 | 474315067-8590-DETAIL-01_12_2026-GO95MLD-1^06239004.0244841 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003494 | 474315067-8590-DETAIL-01_12_2026-SVCROAD-1^06239004.0244841 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003495 | 474340058-70830-DETAIL-01_26_2026-COVCOTHR-1^06240003.0313602 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003496 | 474340058-70830-DETAIL-01_26_2026-COVCOTHR-2^06240003.0313602 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003497 | 474340058-70830-DETAIL-02_17_2025-GUYHINS-1^06240003.0313602 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003498 | 474414936-87936-DETAIL-06_16_2025-GO95HV-1^06248004.0361145 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003499 | 474427053-78629-DTLSB-01_20_2026-GO95HV-1^06242009.0299101 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003500 | 474432336-31661-DETAIL-02_19_2025-GO95MLD-1^06239004.0365501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003501 | 440375414-35359-DETAIL-05_21_2026-CUSTWIRE-1^07217001.0144902 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003502 | 440375414-35359-DETAIL-05_21_2026-GO95HV-1^07217001.0144902 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003503 | 440403251-49889-DTLSB-01_29_2026-BIRDDMG-1^06242009.0052901 | POLE | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003504 | 440546318-55813-DETAIL-08_28_2025-GO95HV-1^06247006.0284902 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003505 | 440653326-18940-DTLSB-07_30_2025-GO95MLD-1^07218001.0277001 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003506 | 440833506-87959-AUDIT-09_09_2025-GRDRODHI-1^07218001.0355702 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003507 | 440938924-42629-DETAIL-04_20_2022-CUSTWIRE-1^06143012.0362100 | OTHER | Non-HFTD | Distribution | 2022-04-20 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003508 | 441268593-98289-DTLSB-01_22_2026-BIRDDMG-1^06242009.0297201 | POLE | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003509 | 190843918-38930-DETAIL-09_09_2025-GO95HV-1^06146001.0094800 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003510 | 191129149-91509-DETAIL-09_30_2025-ANCHIDLE-1^06246009.0132500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003511 | 19171060-92670-DETAIL-06_10_2025-GO95HV-1^06236005.0347702 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003512 | 192175263-78519-DTLSB-04_02_2026-GO95HV-1^06241009.0218100 | OTHER | Non-HFTD | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003513 | 442901273-28541-DETAIL-03_04_2025-ABNDEQPM-1^06241005.0130602 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003514 | 442927254-4959-DTLTRT-04_22_2026-GUYHINS-1^668004/02 7/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003515 | 442987044-10609-DETAIL-09_17_2025-GO95HV-1^06246006.0079201 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003516 | 443116041-85259-DTLSB-07_08_2025-GO95HV-1^06245007.0353100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003517 | 443143113-49499-DETAIL-10_05_2021-CUSTWIRE-1^06147005.0070300 | OTHER | Non-HFTD | Distribution | 2021-10-05 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003518 | 443164483-98229-DETAIL-04_28_2026-GO95HV-1^06142012.0148705 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003519 | 443164483-98229-DETAIL-04_28_2026-GUYHINS-1^06142012.0148705 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003520 | 443289285-61940-DETAIL-03_04_2025-SVCROAD-1^06240004.0150541 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003521 | 443916288-53801-ADMIN-11_12_2025-GO95HV-1^06246001.0336700 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003522 | 444376673-96009-DETAIL-08_12_2025-GO95HV-1^06247006.0251200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003523 | 444743801-80349-DETAIL-06_25_2025-GO95HV-1^06244007.0104804 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003524 | 444743801-80349-DETAIL-06_25_2025-SVCROAD-1^06244007.0104804 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003525 | 513237039-1259-DETAIL-05_30_2024-CUSTWIRE-1^06246005.0340403 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003526 | 513376756-14589-DTLSB-07_09_2025-GO95HV-1^06244007.0141900 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003527 | 513712145-22699-AUDIT-05_19_2025-GRDRODHI-1^06243006.0105800 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003528 | 513712145-22699-DETAIL-05_08_2025-GO95HV-1^06243006.0105800 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003529 | 514033283-78903-DTLSB-07_30_2025-GO95HV-1^07218001.0276201 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003530 | 514186515-20569-DETAIL-02_26_2025-GO95TCH-1^06240004.0061100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003531 | 514312844-28739-DETAIL-06_02_2025-GO95HV-1^06244006.0156640 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003532 | 514356688-97729-DETAIL-04_21_2025-GO95HV-1^06242006.0100900 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003533 | 445778643-59941-DETAIL-05_13_2025-GO95MLD-1^06242004.0310604 | OTHER | HFTD Tier 2 | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003534 | 446094741-58839-DETAIL-02_22_2024-SVCROAD-1^07113001.0099300 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003535 | 446250468-57499-DTLSB-07_10_2025-ANCHIDLE-1^06244007.0036901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003536 | 446286155-56499-DETAIL-01_28_2026-GO95BLTC-1^06242009.0053100 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003537 | 446360246-85449-DTLSB-07_09_2025-ENCHRW-1^06244006.0276401 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003538 | 446555988-20940-DETAIL-04_09_2026-BIRDDMG-1^06240003.0078401 | POLE | HFTD Tier 2 | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003539 | 446685995-87839-DTLSB-06_09_2026-GO95HV-1^07216001.0227102 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003540 | 446742300-79633-DETAIL-06_29_2026-GO95HV-1^07217001.0159400 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003541 | 446799650-46270-DETAIL-03_24_2026-COVCOTHR-1^06240004.0220410 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003542 | 446945216-71499-DETAIL-07_29_2025-GO95HV-1^06247005.0316901 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003543 | 446945216-71499-DETAIL-07_29_2025-SVCROAD-1^06247005.0316901 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003544 | 446962206-11401-DETAIL-08_12_2025-GO95HV-1^06246001.0199500 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003545 | 446973929-17229-DETAIL-05_02_2024-CUSTWIRE-1^06142012.0126200 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003546 | 447178743-29743-DETAIL-06_17_2025-GO95HV-1^668075/00 10/042 | OTHER | HFTD Tier 2 | Transmission | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003547 | 447215660-33878-DTLSB-07_16_2025-GO95HV-1^06244006.0237001 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003548 | 447301459-27989-DTLSB-05_12_2026-GRDRODHI-1^06242009.0289502 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003549 | 476130968-62841-DTLTRT-05_05_2026-BIRDDMG-1^668038/00 2/063 | POLE | HFTD Tier 2 | Transmission | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003550 | 476316491-64480-AUDIT-02_18_2025-SVCDEFLC-1^06240004.0169411 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003551 | 476414381-81369-DTLSB-07_14_2025-GO95HV-1^06244007.0156700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003552 | 476536450-67941-DTLTRT-05_05_2026-GO95HV-1^668004/00 7X/001 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003553 | 476765740-54371-DETAIL-03_10_2025-GO95HV-1^06241005.0242300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003554 | 476849386-56241-DETAIL-09_03_2025-GO95HV-1^06246001.0178200 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003555 | 476849386-56241-DETAIL-09_03_2025-GO95MLD-1^06246001.0178200 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003556 | 477581918-65229-DETAIL-04_22_2026-GO95HV-1^06142012.0142700 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003557 | 449208045-9989-DTLTRT-04_16_2026-GRDRODHI-1^06241009.0137801 | OTHER | Non-HFTD | Distribution | 2026-04-16 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003558 | 449278270-53598-DTLTRT-05_21_2026-SVCENTCO-1^668086/00 11/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003559 | 449442356-78801-DETAIL-08_12_2025-GO95HV-1^06246001.0195700 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003560 | 449696444-939-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0219600 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003561 | 449795833-84669-DTLTRT-06_23_2021-UBPBXARM-1^668041/00 5/032 | CROSSARM | Non-HFTD | Transmission | 2021-06-23 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003562 | 4498009-29009-DETAIL-06_03_2025-GO95HV-1^06245007.0241502 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003563 | 450064106-85129-DETAIL-04_28_2025-GO95HV-1^06242006.0190202 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003564 | 450515411-84811-DETAIL-05_28_2025-GO95HV-1^06142012.0112200 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003565 | 451242350-70833-DETAIL-09_09_2025-GO95HV-1^07218001.0174202 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003566 | 45253180-34970-DETAIL-02_25_2026-GO95HV-1^06238003.0017903 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003567 | 452678902-41139-DETAIL-05_20_2025-GO95HV-1^06243006.0078501 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003568 | 452708076-36742-DETAIL-04_08_2025-LIGHT-1^06241005.0027300 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003569 | 45283756-74642-ADMIN-11_10_2025-GO95BLTC-1^06246011.0062201 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003570 | 452868954-56550-DTLTRT-11_03_2023-BIRDDMG-1^668010/00 7/036 | POLE | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003571 | 452977171-16811-DETAIL-09_29_2025-GO95HV-1^06148001.0310708 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003572 | 477794418-64150-DETAIL-04_22_2025-GO95HV-1^06240003.0080600 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003573 | 477913606-33606-DETAIL-01_22_2026-GO95MLD-1^06239004.0230101 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003574 | 193767791-37739-DETAIL-05_14_2025-GO95HV-1^06243006.0275100 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003575 | 193776133-92799-DETAIL-05_30_2025-GO95HV-1^06244006.0090502 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003576 | 194081800-25549-DETAIL-09_04_2025-GO95HV-1^07216001.0098403 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003577 | 194110384-41329-DETAIL-05_09_2024-SVCRUBLG-1^06142012.0120508 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003578 | 19412274-50690-AUDIT-03_04_2026-SVCROAD-1^06239003.0019700 | OTHER | Non-HFTD | Distribution | 2026-03-04 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003579 | 188556748-98830-DETAIL-09_09_2025-GO95HV-1^06146001.0096900 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003580 | 18877044-29709-DETAIL-10_13_2025-GO95BLTC-1^06246012.0123603 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003581 | 188962303-44480-DETAIL-02_23_2026-BIRDDMG-1^06239002.0151300 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003582 | 189649158-6289-DETAIL-08_28_2025-GO95HV-1^06247006.0299902 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003583 | 422059105-89239-DTLTRT-06_26_2025-GUYLOINS-1^668087/00 13/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003584 | 422423342-97929-DETAIL-05_15_2024-GO95HV-1^06142012.0126840 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003585 | 422541743-2743-DETAIL-06_17_2025-GO95HV-1^668075/00 5/042 | OTHER | HFTD Tier 2 | Transmission | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003586 | 422621247-61570-DETAIL-04_20_2026-GO95HV-1^06142012.0144909 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003587 | 422879653-66889-DETAIL-05_28_2025-GO95MLD-2^06244006.0090301 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003588 | 422962237-27590-DETAIL-01_30_2025-GO95HV-1^06239004.0245642 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003589 | 422966710-35540-DETAIL-03_10_2026-COVCOTHR-2^06239003.0061005 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003590 | 423429453-33230-DTLSB-07_30_2025-GO95MLD-1^07218001.0276101 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003591 | 423515264-95264-DETAIL-04_20_2022-CUSTWIRE-1^06143012.0363100 | OTHER | Non-HFTD | Distribution | 2022-04-20 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003592 | 42382350-41559-DETAIL-07_23_2025-GO95HV-1^06247005.0175000 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003593 | 423841660-4570-DETAIL-02_18_2026-GO95HV-1^06239002.0044300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003594 | 454435878-27919-DTLSB-04_15_2026-GO95HV-1^06241008.0050001 | OTHER | Non-HFTD | Distribution | 2026-04-15 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003595 | 454573183-99939-DETAIL-06_10_2026-GUYHINS-1^668086/00 17/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003596 | 455081893-23783-DETAIL-08_14_2025-GO95HV-1^06247006.0364901 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003597 | 455102741-87670-DETAIL-02_19_2025-GO95MLD-1^06241005.0277900 | OTHER | HFTD Tier 3 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003598 | 455306356-81759-DTLTRT-04_30_2026-GO95HV-1^668004/00 5/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003599 | 455306356-81760-DTLTRT-04_30_2026-GO95HV-1^668004/00 5/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003600 | 455658288-71550-DETAIL-04_09_2026-BIRDDMG-1^06240003.0053100 | POLE | HFTD Tier 2 | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003601 | 456019801-47321-DETAIL-09_10_2025-GO95HV-1^06147001.0075800 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003602 | 425399819-47139-DTLTRT-07_09_2025-GUYNOINS-2^668087/00 3/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003603 | 425399819-85082-DTLTRT-07_09_2025-GUYNOINS-1^668087/00 3/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003604 | 425399819-86082-DTLTRT-07_09_2025-GUYNOINS-1^668087/00 3/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003605 | 425478383-36579-DETAIL-05_27_2025-GO95TCH-1^06244006.0091402 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003606 | 425632056-54056-DETAIL-05_29_2025-GO95HV-1^06148014.0360000 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003607 | 425763801-2639-DETAIL-05_15_2025-GO95HV-1^06243006.0165401 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003608 | 426027781-59001-DETAIL-01_15_2026-RISEBKSP-1^06239004.0135144 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003609 | 426403738-68079-DETAIL-06_17_2025-BIRDDMG-1^06248004.0299107 | POLE | HFTD Tier 2 | Distribution | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003610 | 426444268-19779-DETAIL-08_18_2025-GO95HV-1^06246002.0264100 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003611 | 426495558-95159-DETAIL-04_08_2024-CUSTWIRE-1^06247005.0285001 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003612 | 427130178-36440-DETAIL-03_05_2026-COVCOTHR-2^06238004.0145900 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003613 | 427130178-36440-DETAIL-03_05_2026-GUYHINS-1^06238004.0145900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003614 | 427130178-36440-DETAIL-03_17_2025-GO95TCH-1^06238004.0145900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003615 | 427358924-42940-DTLSB-07_29_2025-GO95HV-1^07218001.0263703 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003616 | 456029694-77239-DTLTRT-05_20_2026-GO95HV-1^668086/00 7/013 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003617 | 456209675-70559-DETAIL-06_18_2025-GO95HV-1^06248004.0287203 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003618 | 45658623-12721-DETAIL-02_18_2025-GUYHINS-1^06239004.0364804 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003619 | 456632136-80449-DETAIL-10_10_2024-GO95CL10-1^07216001.0201204 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003620 | 45664188-79479-DTLSB-07_10_2025-GO95HV-1^06244007.0038909 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003621 | 456778739-50659-DETAIL-08_05_2025-GO95HV-1^06247005.0207501 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003622 | 456778739-50659-DETAIL-08_05_2025-POLETOP-1^06247005.0207501 | POLE | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003623 | 428541680-65440-DETAIL-03_10_2026-BIRDDMG-1^06239003.0061201 | POLE | HFTD Tier 3 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003624 | 428875973-92309-DETAIL-06_09_2025-GO95HV-1^06245006.0195600 | OTHER | Non-HFTD | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003625 | 428962956-35956-DETAIL-05_29_2025-GO95HV-1^06148014.0359000 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003626 | 429075758-29359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0320501 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003627 | 429106104-24899-DETAIL-07_30_2025-GO95CLSV-1^06247006.0204103 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003628 | 429106104-24899-DETAIL-07_30_2025-GO95HV-1^06247006.0204103 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003629 | 429233698-75359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0327401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003630 | 429388308-6659-DTLTRT-08_14_2025-GO95HV-1^07217001.0027801 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003631 | 429641748-98960-DTLTRT-05_04_2026-GO95HV-1^668004/00 4/021 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003632 | 429664395-47395-DETAIL-06_02_2025-GO95HV-1^06147014.0027500 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003633 | 429789773-64683-DETAIL-08_18_2025-GO95HV-1^06247006.0364600 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003634 | 43007455-36479-DTLSB-07_10_2025-GO95HV-1^06244007.0120101 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003635 | 430935878-34980-DTLSB-05_06_2026-GO95HV-1^06142013.0272300 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003636 | 431039998-97980-DETAIL-08_12_2025-GO95HV-1^06246002.0259002 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003637 | 431039998-97980-DETAIL-08_12_2025-GUYHINS-1^06246002.0259002 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003638 | 493506696-77861-DTLTRT-07_03_2025-GO95HV-1^668087/00 7/011 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003639 | 494059418-73313-DETAIL-09_02_2025-GO95HV-1^06247006.0276700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003640 | 494087915-42959-DTLSB-06_08_2026-GO95HV-1^07216001.0228201 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003641 | 494210966-63059-DETAIL-07_29_2025-GO95HV-1^06247005.0269801 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003642 | 494268159-98561-DETAIL-09_30_2025-GUYHINS-1^06148001.0300004 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003643 | 494351221-2280-DETAIL-01_23_2026-BIRDDMG-1^06240004.0236801 | POLE | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003644 | 494407405-50849-DTLSB-07_17_2025-GO95HV-1^06244007.0144700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003645 | 494612864-49932-DETAIL-03_06_2025-GO95MLD-1^06241005.0120106 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003646 | 432147515-53609-DETAIL-08_28_2025-GO95HV-1^06247006.0193800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003647 | 432375449-16449-DETAIL-10_15_2025-BIRDDMG-1^06247012.0310400 | POLE | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003648 | 432392500-83269-DETAIL-10_09_2025-CUSTWIRE-1^06248003.0272202 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003649 | 432481135-83849-DTLSB-07_10_2025-GO95HV-1^06244007.0144802 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003650 | 433323321-31201-DETAIL-01_21_2025-GO95HV-1^06239004.0255441 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003651 | 433590678-8779-DETAIL-08_14_2025-GO95HV-1^06246002.0264900 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003652 | 433919613-46709-DETAIL-09_04_2025-GO95HV-1^06247006.0070101 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003653 | 433936682-82189-DETAIL-08_14_2025-GO95HV-1^06246001.0317901 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003654 | 434186291-4580-DETAIL-02_27_2025-GO95HV-1^06240004.0137201 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003655 | 434203944-89362-DETAIL-04_22_2025-GO95HV-1^06242005.0360140 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003656 | 434203944-89362-DETAIL-04_22_2025-SVCNEUT-1^06242005.0360140 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003657 | 189870925-18529-DTLSB-05_04_2026-GO95HV-1^06142013.0060602 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003658 | 190019644-6489-ADMIN-10_21_2025-GUYLOINS-1^06246012.0055600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003659 | 190324746-14379-DTLSB-07_09_2025-SVCENTCO-1^06244006.0277701 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003660 | 19033029-45389-DTLSB-02_09_2026-BIRDDMG-1^06243010.0362100 | POLE | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003661 | 40760463-30959-DTLSB-08_11_2025-GO95HV-1^07217001.0012205 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003662 | 407780811-95369-DTLTRT-06_02_2021-GO95HV-1^668041/00 11/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003663 | 4077830-84709-DETAIL-08_21_2025-GO95HV-1^06246001.0307502 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003664 | 408021776-81039-DETAIL-05_20_2025-GO95HV-1^06243006.0090200 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003665 | 408158573-73159-DETAIL-08_19_2025-DISTHDWR-1^06247006.0366602 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003666 | 408199970-41099-DETAIL-10_13_2025-GUYHINS-1^06246010.0144102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-13 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003667 | 408311290-99039-DTLTRT-07_09_2025-GO95HV-1^668087/00 4/025 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003668 | 408447211-44580-DETAIL-02_16_2026-GO95HV-1^06239001.0033901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003669 | 408609236-13153-DTLSB-06_16_2026-GO95HV-1^07217001.0357200 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003670 | 409224629-84919-DTLSB-05_18_2026-GO95HV-1^06242009.0284601 | OTHER | Non-HFTD | Distribution | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003671 | 409236686-7860-DETAIL-08_06_2025-GO95HV-1^06246002.0037201 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003672 | 409357743-89860-ADMIN-11_13_2025-GO95HV-1^06246001.0325400 | OTHER | Non-HFTD | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003673 | 409547359-379-DTLSB-07_14_2025-GO95HV-1^06244006.0289601 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003674 | 409870801-56889-DETAIL-08_20_2025-BIRDDMG-1^06247006.0369000 | POLE | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003675 | 410136434-69830-DTLSB-07_23_2025-GO95HV-1^07218001.0264903 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003676 | 410160609-54633-DETAIL-09_09_2025-GO95MLD-1^07218001.0179301 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003677 | 458140691-29221-DETAIL-09_10_2025-GO95MLD-1^06147001.0077900 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003678 | 458581105-73409-DETAIL-08_21_2025-GO95HV-1^06247006.0265801 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003679 | 458684813-19080-DETAIL-02_25_2025-GO95TCH-1^06240005.0016102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003680 | 458716499-19769-ADMIN-07_08_2026-POLEDERP-1^668005/03 1/005 | POLE | Non-HFTD | Transmission | 2026-07-08 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003681 | 459022634-80760-DETAIL-01_23_2025-GO95HV-1^06239004.0257706 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003682 | 459022634-80760-DRONE_HY-07_15_2026-COVCOTHR-1^06239004.0257706 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003683 | 459028452-18750-DETAIL-03_02_2026-SVCROAD-1^06238004.0026100 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003684 | 411247054-1040-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/043 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003685 | 411386837-27049-DETAIL-06_11_2025-GO95HV-1^06245006.0297300 | OTHER | Non-HFTD | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003686 | 411609676-24274-DETAIL-05_29_2025-GO95HV-1^06148014.0360700 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003687 | 411645211-87211-DETAIL-09_18_2025-GO95MLD-1^07218001.0085020 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003688 | 41188537-92099-DTLSB-08_21_2024-CUSTWIRE-1^06245006.0332103 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003689 | 411981968-5270-DRONE_HY-06_30_2026-SVCTREE-1^06240004.0168400 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003690 | 412067294-71919-DTLSB-03_30_2026-GRDRODHI-1^06242009.0210602 | OTHER | Non-HFTD | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003691 | 412220203-4219-DETAIL-10_13_2025-GO95BLTC-1^06246010.0240700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003692 | 412237085-36429-DETAIL-05_13_2025-GO95HV-1^06142012.0016700 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003693 | 412425004-35509-DETAIL-09_04_2025-GO95HV-1^06247006.0186602 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003694 | 412620811-61060-DTLTRT-04_23_2026-GO95HV-1^668004/00 7/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003695 | 185486181-56420-DTLSB-05_06_2026-GO95HV-1^06142013.0271300 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003696 | 185489324-27379-ADMIN-03_01_2023-CUSTWIRE-1^06148004.0192401 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003697 | 185699610-52599-DTLSB-09_03_2024-GO95MLD-1^06245007.0015103 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003698 | 185740523-31523-DETAIL-06_04_2025-GO95MLD-1^668075/00 9/024 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003699 | 436438289-84569-DETAIL-09_16_2025-GO95BLTC-1^06246006.0016200 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003700 | 436986508-27508-DETAIL-02_26_2026-GO95HV-1^06238004.0111300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003701 | 437002809-59090-DETAIL-09_04_2025-GO95HV-1^06146001.0086800 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003702 | 437050305-12305-DETAIL-07_24_2025-GO95MLD-1^06247005.0139303 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003703 | 437122253-8630-DTLSB-07_23_2025-GO95TCH-1^07218001.0264740 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003704 | 43717811-70782-DTLSB-08_15_2023-CUSTWIRE-1^06243009.0245401 | OTHER | Non-HFTD | Distribution | 2023-08-15 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003705 | 437425035-58933-DETAIL-09_16_2025-GO95HV-1^06247004.0085440 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003706 | 414525264-12453-DETAIL-09_25_2025-GO95HV-1^07218001.0224300 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003707 | 414786676-71391-DETAIL-05_07_2026-GO95HV-1^668038/00 4/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003708 | 414793320-49383-DETAIL-08_19_2025-GO95HV-1^07216001.0174805 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003709 | 414987783-5959-DETAIL-09_15_2025-XARMSPCR-2^06248007.0230001 | CROSSARM | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003710 | 415193608-46919-DETAIL-06_20_2022-CUSTWIRE-1^07116007.0111901 | OTHER | HFTD Tier 2 | Distribution | 2022-06-20 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003711 | 415284634-73129-DETAIL-03_16_2017-SVCWIND-1^06142012.0130614 | OTHER | Non-HFTD | Distribution | 2017-03-16 | 2020-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003712 | 415554751-843-DETAIL-07_02_2026-GUYNOINS-1^07217001.0221701 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003713 | 415776454-31999-DETAIL-03_21_2024-GO95HV-1^06147005.0206700 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003714 | 415776454-31999-DETAIL-03_21_2024-GO95MLD-1^06147005.0206700 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003715 | 416092575-52040-DETAIL-02_24_2025-SVCDEFLC-1^06240004.0151804 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003716 | 416178140-1371-ADMIN-04_26_2017-CUSTWIRE-1^06242005.0258840 | OTHER | HFTD Tier 2 | Distribution | 2017-04-26 | 2020-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003717 | 416315461-18280-DETAIL-02_18_2026-GO95HV-1^06239002.0048402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003718 | 41632359-33271-DETAIL-02_24_2025-GRDRODHI-1^06241005.0152600 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003719 | 185844043-77289-DTLSB-01_21_2026-GO95HV-1^06242009.0298110 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003720 | 437495887-47887-DETAIL-09_03_2025-GO95TCH-1^06247006.0294600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003721 | 437787109-39073-DETAIL-08_05_2025-GO95CL10-1^06247005.0207900 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003722 | 437787109-39073-DETAIL-08_05_2025-GO95HV-1^06247005.0207900 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003723 | 437787109-39073-DETAIL-08_05_2025-RISEBKSP-1^06247005.0207900 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003724 | 4378173-1069-DETAIL-09_18_2025-GO95HV-1^06248007.0266401 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003725 | 437836708-24190-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244414 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003726 | 437836708-24190-DETAIL-01_12_2026-COVCOTHR-4^06239004.0244414 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003727 | 187595776-45330-DETAIL-08_12_2025-GO95HV-1^06246001.0197400 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003728 | 416333438-12009-DETAIL-04_09_2024-SVCROAD-1^06147005.0215802 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003729 | 416478044-64759-DETAIL-07_28_2025-GO95HV-1^06247005.0311801 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003730 | 41656741-90199-DETAIL-03_15_2022-CUSTWIRE-1^06148006.0270102 | OTHER | Non-HFTD | Distribution | 2022-03-15 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003731 | 416933134-78639-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0269041 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003732 | 417548906-47270-DTLSB-04_29_2026-GO95HV-1^06142013.0211201 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003733 | 418064506-58670-DETAIL-09_03_2025-GO95HV-1^06246001.0178201 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003734 | 418207646-63610-DETAIL-03_13_2025-GO95HV-1^06238004.0225702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003735 | 418594815-15815-DETAIL-06_24_2025-GO95HV-1^06248004.0312905 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003736 | 418736573-17299-DETAIL-08_14_2025-GO95HV-1^06247006.0254003 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003737 | 41886001-57250-DETAIL-02_26_2026-GUYHINS-1^06238004.0022802 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003738 | 41886001-57250-DETAIL-03_24_2025-GRDRODHI-1^06238004.0022802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003739 | 418984346-66259-DTLTRT-05_07_2026-GUYHINS-1^668004/00 2/025 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003740 | 418997242-48370-DETAIL-06_10_2026-GUYHINS-1^668086/00 15/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003741 | 418997242-48370-DETAIL-06_10_2026-GUYHINS-2^668086/00 15/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003742 | 389321165-95889-DETAIL-08_11_2025-GRDRODHI-1^06247006.0266501 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003743 | 389321165-95889-DETAIL-08_11_2025-GRDRODHI-2^06247006.0266501 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003744 | 389325535-96889-DETAIL-06_05_2025-GO95HV-1^06148014.0247001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003745 | 389394908-3540-ADMIN-08_11_2025-GUYHINS-1^668087/00 3/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003746 | 389414793-97983-DETAIL-09_17_2025-GO95STUB-1^07218001.0088501 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003747 | 389549520-46349-DTLSB-06_25_2025-BIRDDMG-1^06244007.0101401 | POLE | HFTD Tier 2 | Distribution | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003748 | 389661669-42459-DETAIL-07_28_2025-CONDFRAY-1^06247005.0198601 | CONDUCTOR | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003749 | 389661669-42459-DETAIL-07_28_2025-SVCROAD-1^06247005.0198601 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003750 | 391822453-72140-DTLSB-05_22_2024-GO95MLD-1^06243001.0103701 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003751 | 392012871-36289-DETAIL-05_05_2025-GO95HV-1^06243006.0347203 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003752 | 392115831-26809-DETAIL-09_03_2025-GO95HV-1^06247006.0211503 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003753 | 392144929-47799-DETAIL-07_28_2025-GO95HV-1^06247005.0197102 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003754 | 392144929-47799-DETAIL-07_28_2025-SVCENTCO-1^06247005.0197102 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003755 | 392844607-47323-DETAIL-05_26_2026-GO95HV-1^07217001.0146301 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003756 | 392982575-22379-DETAIL-08_20_2025-GO95HV-1^06247006.0256900 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003757 | 392991571-51380-DETAIL-02_18_2026-GO95HV-1^06239002.0048400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003758 | 393066046-33079-DTLSB-03_16_2026-BIRDDMG-1^06242009.0136201 | POLE | HFTD Tier 2 | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003759 | 393526669-34019-DTLSB-05_19_2026-GO95HV-1^06240007.0180300 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003760 | 393640245-98872-DETAIL-04_23_2025-SVCROAD-1^06242005.0360144 | OTHER | HFTD Tier 2 | Distribution | 2025-04-23 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003761 | 393647108-64919-DTLSB-04_16_2026-GO95HV-1^06241008.0074200 | OTHER | Non-HFTD | Distribution | 2026-04-16 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003762 | 393805646-46379-DETAIL-08_12_2025-GO95HV-1^06246001.0195402 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003763 | 393805646-46379-DETAIL-08_12_2025-GO95TCH-1^06246001.0195402 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003764 | 39392821-37169-DETAIL-05_27_2025-GO95HV-1^06244006.0085700 | OTHER | HFTD Tier 2 | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003765 | 394114195-26909-DETAIL-08_13_2025-GO95HV-1^06247006.0254600 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003766 | 459279099-16121-DETAIL-09_04_2025-GO95HV-1^06146001.0085900 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003767 | 459355356-35770-DETAIL-02_04_2025-GO95HV-1^06239004.0258400 | OTHER | HFTD Tier 3 | Distribution | 2025-02-04 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003768 | 459413653-69959-DETAIL-09_18_2025-GO95HV-1^06248007.0268100 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003769 | 459552124-7953-DETAIL-05_21_2026-GO95HV-1^07217001.0144803 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003770 | 459627623-20499-DETAIL-06_03_2025-GO95HV-1^06245007.0366900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003771 | 459918801-96030-DETAIL-01_29_2025-SVCROOF-1^06240004.0177702 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003772 | 460142176-44721-DTLSB-04_29_2026-GO95HV-1^06142013.0207200 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003773 | 460490663-88949-DTLSB-04_09_2024-CUSTWIRE-1^06245007.0228004 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003774 | 395107134-66253-DETAIL-07_02_2026-GO95HV-1^07217001.0033800 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003775 | 395492615-63059-DETAIL-09_23_2025-GO95HV-1^06247004.0181600 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003776 | 395902604-82240-DTLSB-07_31_2025-GO95HV-1^07218001.0264705 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003777 | 396039404-70504-DETAIL-08_28_2025-GO95HV-1^06247006.0284905 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003778 | 396122130-60432-DETAIL-04_02_2025-SVCROAD-1^06241005.0118505 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003779 | 396132573-77009-DETAIL-08_04_2025-GO95HV-1^06247006.0207600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003780 | 396148108-80640-DETAIL-04_21_2026-GO95HV-1^06142012.0147702 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003781 | 396179276-26533-DETAIL-06_16_2025-GRDRODHI-1^06248004.0360142 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003782 | 396337134-62053-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0100401 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003783 | 3964710-28359-DETAIL-10_09_2025-CUSTWIRE-1^06248003.0332900 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003784 | 396971123-12123-DETAIL-06_09_2025-GO95MLD-1^668075/00 13/028 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003785 | 397170894-89479-DETAIL-04_17_2025-GO95MLD-1^06242005.0361600 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003786 | 397170894-89479-DETAIL-04_17_2025-GO95TCH-1^06242005.0361600 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003787 | 397235115-55115-DETAIL-06_16_2025-GO95MLD-1^06248004.0310901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003788 | 397328856-69856-DETAIL-06_03_2025-GO95HV-1^06148015.0321500 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003789 | 419705488-5261-ADMIN-11_10_2025-PWRTRN-1^07117008.0178103 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2026-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003790 | 419715894-44770-AUDIT-06_24_2026-BIRDDMG-1^07216001.0229402 | POLE | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003791 | 419788202-91870-ADMIN-01_16_2018-CUSTWIRE-1^06146002.0153600 | OTHER | Non-HFTD | Distribution | 2018-01-16 | 2021-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003792 | 419837173-26249-DTLSB-07_16_2025-GO95HV-1^06244006.0252900 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003793 | 420109774-36970-DTLSB-06_05_2026-BIRDDMG-1^07216001.0229901 | POLE | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003794 | 420109774-36970-DTLSB-06_05_2026-SVCROAD-1^07216001.0229901 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003795 | 420602807-5140-DETAIL-04_08_2026-GO95HV-1^06240002.0315304 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003796 | 183986005-40105-DETAIL-06_02_2025-GRDRODHI-1^06148014.0241900 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003797 | 184156408-68649-DETAIL-06_10_2025-GO95TCH-1^06245006.0204100 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003798 | 397700797-56323-DETAIL-05_22_2026-GO95HV-1^07217001.0146303 | OTHER | Non-HFTD | Distribution | 2026-05-22 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003799 | 397971416-21689-DETAIL-08_05_2025-GO95HV-1^06246002.0019600 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003800 | 398124456-30469-DETAIL-06_04_2025-GO95TCH-1^06245006.0288801 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003801 | 398249991-89950-DETAIL-05_15_2025-GO95HV-1^06142012.0113200 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003802 | 398547236-9236-DETAIL-06_02_2025-GO95HV-1^06148014.0258900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003803 | 39883243-34450-DETAIL-01_24_2025-SVCENTCO-1^06239004.0258701 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003804 | 398880991-49411-DETAIL-06_19_2025-SVCENTCO-1^06237004.0171802 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003805 | 398914501-62059-DTLSB-06_05_2026-GO95HV-1^07216001.0234700 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003806 | 399012593-42593-DETAIL-06_18_2025-GO95CL10-1^668075/00 8/048 | OTHER | HFTD Tier 2 | Transmission | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003807 | 39923614-90959-DETAIL-09_11_2025-GRDRODHI-1^06248007.0228802 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003808 | 399743498-12829-DTLSB-01_22_2026-GO95MLD-1^06242009.0297202 | OTHER | Non-HFTD | Distribution | 2026-01-22 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003809 | 399768139-91549-DTLSB-07_02_2025-GO95TCH-1^06244007.0137301 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003810 | 399792608-39189-ADMIN-11_12_2025-GRDRODHI-1^06246001.0335001 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003811 | 399868478-34089-AUDIT-03_18_2026-CONDFRAY-1^06242009.0135002 | CONDUCTOR | Non-HFTD | Distribution | 2026-03-18 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003812 | 420758003-25329-DETAIL-05_13_2025-GO95HV-1^06142012.0014501 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003813 | 420759676-25029-DETAIL-05_13_2025-XARMSPCR-1^06142012.0016505 | CROSSARM | Non-HFTD | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003814 | 420936038-57399-DETAIL-09_24_2025-GO95HV-1^06246009.0075003 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003815 | 420936038-57399-DETAIL-09_24_2025-GRDRODHI-1^06246009.0075003 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003816 | 420940098-97470-DTLTRT-06_23_2025-GUYHINS-2^668087/00 11/002 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003817 | 421140014-17729-DTLSB-01_26_2026-GO95HV-1^06242009.0299400 | OTHER | Non-HFTD | Distribution | 2026-01-26 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003818 | 421161844-3190-DETAIL-03_26_2025-GO95HV-1^06239003.0018505 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003819 | 421236724-46724-DETAIL-04_22_2025-GO95BLTC-1^06242006.0081500 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003820 | 369205853-30709-DETAIL-08_27_2025-GO95HV-1^06247006.0079200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003821 | 369680303-44510-DTLTRT-05_13_2026-GO95MLD-1^668085/00 11/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003822 | 370109821-72499-DETAIL-07_29_2025-GO95HV-1^06247006.0205005 | OTHER | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003823 | 370359366-53163-DETAIL-06_23_2026-GO95HV-1^07217001.0105502 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003824 | 370520451-28802-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003825 | 370520451-29802-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003826 | 370542501-91250-DETAIL-03_04_2026-GO95HV-1^06239003.0189400 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003827 | 370809073-24390-DRONE_HY-06_19_2026-COVCOTHR-1^06240004.0178303 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003828 | 370941383-9779-DETAIL-06_09_2025-GO95HV-1^06245006.0195701 | OTHER | Non-HFTD | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003829 | 371006360-96583-DETAIL-08_19_2025-GO95MLD-1^07216001.0173700 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003830 | 371132284-12379-DETAIL-10_15_2025-GO95BLTC-1^06246011.0181802 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003831 | 371360156-39670-DETAIL-01_23_2025-GO95HV-1^06239004.0256742 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003832 | 371534914-26914-DETAIL-09_03_2025-GRDRODHI-1^07216001.0097006 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003833 | 372041738-32738-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0219601 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003834 | 3722989-67619-DTLSB-03_25_2026-GO95MLD-1^06242009.0044103 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003835 | 40070728-12760-ADMIN-08_14_2024-BIRDDMG-1^668018/00 8/003 | POLE | HFTD Tier 2 | Transmission | 2024-08-14 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003836 | 401194018-2649-DTLSB-07_03_2025-GO95MLD-1^06244007.0133803 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003837 | 40119440-5749-DTLSB-07_01_2025-GO95HV-1^06244007.0131500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003838 | 401213326-20950-DETAIL-09_02_2025-GO95HV-1^06246001.0175400 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003839 | 401217156-37489-DTLSB-07_10_2025-BIRDDMG-1^06244007.0037801 | POLE | HFTD Tier 2 | Distribution | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003840 | 401271399-71950-DETAIL-10_02_2025-CUSTWIRE-1^06148001.0304006 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003841 | 401330111-66522-DTLTRT-04_23_2026-GO95HV-1^668004/00 8/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003842 | 373536153-17603-DETAIL-06_05_2025-GO95HV-1^06245006.0196140 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003843 | 373885159-5320-DTLTRT-05_19_2026-GO95HV-1^668086/00 10/002 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003844 | 374034480-44480-DETAIL-02_11_2026-SVCDEFLC-1^06239003.0016306 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003845 | 374193830-31301-DETAIL-01_15_2026-SVCTREE-1^06239004.0136107 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003846 | 374422602-27162-DTLSB-06_26_2025-GO95HV-1^06244007.0108140 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003847 | 374636764-50720-DETAIL-04_18_2022-CUSTWIRE-1^06142012.0134801 | OTHER | Non-HFTD | Distribution | 2022-04-18 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003848 | 374647152-31979-DETAIL-05_05_2025-GO95TCH-1^06243006.0347300 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003849 | 374652722-13722-ADMIN-11_10_2025-GO95HV-1^06246001.0254302 | OTHER | Non-HFTD | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003850 | 374892249-90739-DTLTRT-06_24_2025-BIRDDMG-1^668087/00 12/004 | POLE | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003851 | 374998653-18920-DTLSB-03_28_2022-POLETOP-1^06144006.0153101 | POLE | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003852 | 374998653-18920-DTLSB-03_28_2022-XARMSPCR-1^06144006.0153101 | CROSSARM | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003853 | 37501933-76030-DTLSB-10_16_2025-GO95HV-1^06247001.0350100 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003854 | 375783378-85679-DTLSB-07_21_2025-GO95HV-1^06244007.0037904 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003855 | 375794123-79420-DETAIL-05_15_2024-GO95HV-1^06142012.0124703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003856 | 401400844-79041-DETAIL-04_03_2025-GO95MLD-1^06241005.0089002 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003857 | 401423384-41009-DETAIL-08_13_2025-GO95HV-1^06247006.0255501 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003858 | 401469008-58950-DETAIL-04_27_2026-GO95HV-1^06142012.0143802 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003859 | 401729682-6559-DETAIL-04_29_2026-GO95HV-1^668004/00 4/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003860 | 401729682-6560-DETAIL-04_29_2026-GO95HV-1^668004/00 4/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003861 | 40200770-56059-DETAIL-09_03_2025-GO95HV-1^07216001.0094001 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003862 | 402060494-88129-DTLSB-05_04_2026-GO95HV-1^06142013.0050300 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003863 | 402263930-14543-DETAIL-06_23_2026-GO95HV-1^07217001.0113600 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003864 | 37733279-44913-DETAIL-08_26_2025-GO95HV-1^06247006.0288300 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003865 | 377520503-31509-DETAIL-09_10_2025-GO95HV-1^06246007.0132250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003866 | 377534072-18759-DETAIL-07_30_2025-GO95HV-1^06247005.0240302 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003867 | 37807268-87473-DETAIL-08_26_2025-SVCDEFLC-1^07216001.0168301 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003868 | 378102533-79679-DETAIL-02_24_2025-GO95TCH-1^06240004.0154900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003869 | 378102533-79679-DETAIL-03_09_2026-GUYHINS-1^06240004.0154900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003870 | 378102533-79679-DETAIL-03_09_2026-GUYHINS-2^06240004.0154900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003871 | 37818340-93072-DTLSB-07_17_2023-CUSTWIRE-1^06243010.0116801 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003872 | 378347183-49330-DETAIL-04_05_2023-CUSTWIRE-1^06143014.0240804 | OTHER | HFTD Tier 2 | Distribution | 2023-04-05 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003873 | 378494642-95642-DETAIL-09_29_2025-GO95HV-1^06246009.0102603 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003874 | 378551481-1594-DETAIL-03_30_2023-CUSTWIRE-1^06142016.0054201 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003875 | 378614728-80499-DETAIL-10_06_2021-CUSTWIRE-2^06148005.0342002 | OTHER | Non-HFTD | Distribution | 2021-10-06 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003876 | 379120073-74930-DRONE_HY-07_10_2026-DISTHDWR-1^06143014.0185200 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003877 | 438151759-18390-ADMIN-11_07_2025-GRDRODHI-1^06246001.0291901 | OTHER | Non-HFTD | Distribution | 2025-11-07 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003878 | 438189085-7851-DETAIL-02_24_2025-SVCROAD-1^06239004.0366701 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003879 | 438561388-24099-AUDIT-06_17_2025-SVCROAD-1^06248004.0355102 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003880 | 438746560-34890-DETAIL-08_07_2025-GO95HV-1^06246001.0301901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003881 | 438767683-23599-DETAIL-09_17_2025-GO95HV-1^06147001.0144300 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003882 | 438811604-72959-DTLTRT-04_22_2026-GO95MLD-1^668004/02 5/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003883 | 438811604-72959-DTLTRT-04_22_2026-GRDRODHI-1^668004/02 5/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003884 | 438950773-33159-DETAIL-08_19_2025-XARMSPCR-1^06247006.0366504 | CROSSARM | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003885 | 380511259-91599-DETAIL-04_28_2025-GO95BLTC-1^06242006.0092502 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003886 | 380534526-65689-DTLSB-07_08_2026-GO95HV-1^06242009.0242202 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003887 | 380534526-65689-DTLSB-07_08_2026-GRDRODHI-1^06242009.0242202 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003888 | 380534526-65689-DTLSB-07_08_2026-SVCROAD-1^06242009.0242202 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003889 | 380705589-37549-DTLSB-07_01_2025-GO95HV-1^06244007.0133200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003890 | 380914466-83799-DETAIL-06_09_2025-GO95HV-1^06245007.0244301 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003891 | 381040557-6690-DETAIL-01_20_2026-GUYHINS-1^06239004.0245505 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003892 | 381771604-753-DETAIL-06_29_2026-GO95HV-1^07217001.0097402 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003893 | 381800903-72819-DTLSB-05_11_2026-GO95HV-1^06242009.0272100 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003894 | 381848121-95109-DTLSB-08_26_2024-CUSTWIRE-1^06245007.0115201 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003895 | 381882136-68730-DETAIL-09_02_2025-CLMBHAZ-1^06246001.0176403 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003896 | 382369550-48170-DETAIL-02_19_2026-GO95HV-1^06239002.0014600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003897 | 382399399-59130-DETAIL-08_11_2025-GO95HV-1^06246002.0261901 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003898 | 382702361-73330-DETAIL-09_30_2025-GO95HV-1^06148001.0301108 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003899 | 38303615-94615-DETAIL-06_05_2025-GO95HV-1^06148014.0235203 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003900 | 355669029-28829-DTLSB-02_03_2026-BIRDDMG-1^06243009.0306400 | POLE | HFTD Tier 2 | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003901 | 355981129-12500-DETAIL-08_18_2025-GO95HV-1^06246002.0354500 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003902 | 35602849-96059-DTLTRT-05_06_2026-GO95HV-1^668004/00 9/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003903 | 356069914-82932-DETAIL-10_15_2025-GO95BLTC-1^06246012.0133701 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003904 | 356162058-75949-DTLSB-07_08_2025-GO95HV-1^06244007.0037905 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003905 | 3561793-81609-DTLTRT-05_13_2026-GO95MLD-1^668085/00 9/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003906 | 356237892-76980-DETAIL-02_26_2025-GO95TCH-1^06240005.0019201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003907 | 356237892-76980-DETAIL-02_26_2025-SVCNEUT-1^06240005.0019201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003908 | 35643020-53730-DETAIL-01_29_2025-SVCDEFLC-1^06240004.0176940 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003909 | 356638505-12542-DETAIL-03_05_2025-GO95BLTC-1^06241005.0121200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003910 | 356680064-39899-DETAIL-03_21_2024-GO95HV-1^06147005.0209501 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003911 | 356830023-62059-DETAIL-09_22_2025-GO95HV-1^06247006.0063400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003912 | 356856244-60809-ADMIN-10_20_2025-SVCDEFLC-1^06246012.0123400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003913 | 356904101-19000-DTLTRT-05_18_2026-GO95HV-1^668086/00 10/007 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003914 | 178232302-97559-DETAIL-04_29_2026-GO95HV-1^668004/00 8/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003915 | 18482708-44708-DETAIL-04_07_2025-SVCROAD-1^06241005.0027210 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003916 | 184949145-11220-DTLSB-06_05_2026-CUSTWIRE-1^07216001.0227801 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003917 | 403363516-27810-DETAIL-02_05_2026-GO95HV-1^06239003.0017740 | OTHER | Non-HFTD | Distribution | 2026-02-05 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003918 | 403492944-19953-DETAIL-05_27_2026-GO95HV-1^07217001.0147701 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003919 | 403592216-72089-DETAIL-08_13_2025-GO95HV-1^06247006.0265300 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003920 | 404050332-39980-DETAIL-02_25_2025-GO95BLTC-1^06240005.0017201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003921 | 40447691-81780-DETAIL-02_19_2026-GO95HV-1^06239001.0061601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003922 | 404956732-79039-DETAIL-05_21_2025-GO95HV-1^06243006.0078200 | OTHER | HFTD Tier 2 | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003923 | 180021218-36299-DETAIL-06_10_2025-GO95HV-1^06245006.0204001 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003924 | 356936294-20139-ADMIN-03_02_2026-POLEDERP-1^07216001.0307903 | POLE | Non-HFTD | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003925 | 357272109-64300-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0103300 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003926 | 357302739-52659-DETAIL-08_05_2025-GO95HV-1^06247005.0206902 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003927 | 357710013-16109-DETAIL-08_21_2025-GO95HV-1^06247006.0251803 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003928 | 357824829-1449-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0149101 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003929 | 357825205-13099-DTLSB-07_02_2025-GO95TCH-1^06244006.0226308 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003930 | 358093516-99871-DETAIL-02_19_2025-SVCROAD-1^06239004.0365842 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003931 | 358281493-580-DRONE_HY-06_19_2026-ABNDPOLE-1^06240004.0167301 | POLE | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003932 | 358281493-580-DRONE_HY-06_19_2026-SVCCOMMD-1^06240004.0167301 | OTHER | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003933 | 358451376-31200-DETAIL-08_06_2025-CLRTOUCH-1^06246002.0156002 | CONDUCTOR | Non-HFTD | Distribution | 2025-08-06 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003934 | 35857908-77730-DETAIL-09_02_2025-GO95HV-1^06246001.0200701 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003935 | 358685764-28200-DETAIL-09_30_2025-SVCENTCO-1^06148001.0310712 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003936 | 358839373-31819-DTLSB-05_11_2026-GO95HV-1^06242009.0278500 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003937 | 358940561-42730-DETAIL-03_16_2026-GUYHINS-1^06240004.0155404 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003938 | 384944760-81370-DETAIL-06_05_2025-GO95HV-1^668075/00 3/028 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003939 | 385045336-35858-DETAIL-05_26_2026-GO95HV-1^07217001.0144305 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003940 | 385186688-32523-DTLTRT-06_15_2026-GO95CLSV-1^07217001.0275501 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003941 | 38549061-91952-DTLSB-07_14_2025-GO95HV-1^06244006.0218501 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003942 | 38599633-19350-DETAIL-01_14_2026-SVCROAD-1^06239004.0133002 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003943 | 385996515-15870-DETAIL-01_16_2025-SVCENTBK-1^06239004.0256211 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003944 | 386428699-94712-DETAIL-06_29_2023-CUSTWIRE-1^06244009.0242300 | OTHER | HFTD Tier 2 | Distribution | 2023-06-29 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003945 | 360636444-90141-DETAIL-04_07_2025-GO95TCH-1^06241005.0013604 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003946 | 360874340-15340-DETAIL-06_04_2025-GUYHINS-2^06245006.0289910 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003947 | 360874340-15340-DETAIL-06_04_2025-GUYHINS-3^06245006.0289910 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003948 | 360874340-15340-DETAIL-06_04_2025-GUYHINS-4^06245006.0289910 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003949 | 361097789-47592-DTLSB-07_15_2025-GO95HV-1^06244006.0209700 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003950 | 36113289-76030-DETAIL-08_18_2025-GO95HV-1^06246002.0346700 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003951 | 361260351-25709-DETAIL-10_07_2025-GUYHINS-1^06246008.0056400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003952 | 36132277-37030-DETAIL-08_06_2025-GO95HV-1^06246002.0144201 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003953 | 361345100-75070-DETAIL-02_19_2026-GO95HV-1^06239002.0010501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003954 | 361513678-17129-DETAIL-04_22_2026-GO95HV-1^06142012.0143701 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003955 | 361630119-28119-DETAIL-08_19_2025-GO95HV-1^06247006.0366500 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003956 | 361864726-55726-DETAIL-07_24_2025-SVCDEFLC-1^06247005.0160901 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003957 | 362050495-60159-DETAIL-05_26_2026-SVCDEFLC-1^07217001.0143200 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003958 | 362064925-26700-DETAIL-04_30_2025-GO95HV-1^06239002.0064702 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003959 | 362156895-72999-DETAIL-09_09_2025-GO95HV-1^06246007.0150150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003960 | 386837351-68411-DETAIL-02_18_2025-GRDRODHI-1^06239004.0362401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003961 | 387090444-77331-DETAIL-04_08_2025-SVCROAD-1^06241005.0064900 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003962 | 387199500-31140-DETAIL-06_04_2025-GO95HV-1^06142012.0107401 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003963 | 387283273-57249-DTLSB-07_16_2025-GO95HV-1^06244006.0250900 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003964 | 387289522-22450-DETAIL-01_31_2025-GO95HV-1^06239004.0136300 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003965 | 387289522-22450-DETAIL-01_31_2025-GO95MLD-1^06239004.0136300 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003966 | 38733593-97729-DETAIL-05_12_2025-GO95HV-1^06142012.0015900 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003967 | 387397218-34949-DTLSB-07_08_2025-GO95HV-1^06244007.0039901 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003968 | 180580256-56963-DETAIL-07_02_2026-GO95HV-1^07217001.0030802 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003969 | 180664981-39659-DETAIL-06_18_2025-GO95HV-1^06248004.0325500 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003970 | 180730754-53020-DTLTRT-05_13_2026-GO95MLD-1^668085/00 12/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003971 | 180854056-90770-DETAIL-03_11_2025-GO95HV-1^06238004.0334304 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003972 | 181358900-32449-DETAIL-09_05_2025-GO95HV-1^07216001.0099602 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003973 | 182087404-26499-AUDIT-01_26_2026-SVCROAD-1^06242009.0297301 | OTHER | Non-HFTD | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003974 | 182087404-26499-DTLSB-01_22_2026-BIRDDMG-1^06242009.0297301 | POLE | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003975 | 182349405-83849-DTLSB-06_08_2026-GRDRODHI-1^07216001.0229203 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003976 | 182484554-22609-DETAIL-09_10_2025-GO95HV-1^06246006.0079500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003977 | 182596712-92920-DTLTRT-04_28_2026-GO95HV-1^668004/00 8/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003978 | 182716174-83609-AUDIT-11_20_2025-GO95HV-1^06246006.0079700 | OTHER | HFTD Tier 2 | Distribution | 2025-11-20 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003979 | 363685474-66474-DETAIL-02_27_2025-SVCDEFLC-1^06240004.0063208 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003980 | 363688529-1510-DETAIL-08_18_2025-GO95HV-1^06246002.0345000 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003981 | 363876765-57332-DTLSB-07_10_2025-GO95HV-1^06244006.0342300 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003982 | 363960656-78623-ADMIN-02_19_2025-POLEREPL-1^06245007.0220542 | POLE | Non-HFTD | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003983 | 364008046-56710-DTLTRT-05_07_2026-BIRDDMG-1^668038/00 7/054 | POLE | HFTD Tier 2 | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003984 | 335751903-47903-DETAIL-03_23_2023-CUSTWIRE-1^06142016.0080900 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003985 | 335869638-78490-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244307 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003986 | 335869638-78490-DETAIL-01_12_2026-COVCOTHR-2^06239004.0244307 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003987 | 335965678-68678-DTLSB-04_02_2026-GO95MLD-1^06241009.0153524 | OTHER | Non-HFTD | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003988 | 336140295-42089-DTLSB-07_17_2025-GO95HV-1^06244007.0149600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003989 | 336164568-12913-DETAIL-08_28_2025-GO95HV-1^06247006.0284801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003990 | 336636524-7229-DETAIL-04_25_2022-CUSTWIRE-1^06143012.0250000 | OTHER | Non-HFTD | Distribution | 2022-04-25 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003991 | 338233189-15349-DTLSB-07_29_2025-GO95MLD-1^07218001.0265002 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003992 | 338352730-65349-DTLSB-06_25_2025-BIRDDMG-1^06244007.0103600 | POLE | HFTD Tier 2 | Distribution | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003993 | 338352730-65349-DTLSB-06_25_2025-GO95HV-1^06244007.0103600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003994 | 338390705-22705-DETAIL-06_24_2025-GO95HV-1^06248004.0318901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003995 | 338481472-5559-DETAIL-04_29_2026-GO95HV-1^668004/00 2/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003996 | 338481472-5560-DETAIL-04_29_2026-GO95HV-1^668004/00 2/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003997 | 338714504-58081-DTLSB-07_25_2023-ENCHRW-1^06243009.0054400 | OTHER | HFTD Tier 2 | Distribution | 2023-07-25 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120003998 | 338857411-52709-DETAIL-10_07_2025-GO95BLTC-1^06246008.0057501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120003999 | 338918142-86780-DRONE_HY-06_19_2026-COVCOTHR-1^06240004.0167341 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004000 | 339611184-12189-DETAIL-10_15_2025-GO95BLTC-1^06246011.0181701 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004001 | 339611184-12189-DETAIL-10_15_2025-SVCROAD-1^06246011.0181701 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004002 | 33976946-63352-DETAIL-04_21_2025-GRDRODHI-1^06242005.0369805 | OTHER | HFTD Tier 2 | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004003 | 33985303-49430-DETAIL-09_10_2025-GO95HV-1^06147001.0188800 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004004 | 339910316-2989-DETAIL-11_18_2025-GO95MLD-1^06247008.0315201 | OTHER | HFTD Tier 2 | Distribution | 2025-11-18 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004005 | 339945279-18330-DTLTRT-05_22_2025-GO95HV-2^668075/00 2/002 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004006 | 40538924-51229-DETAIL-04_22_2026-GO95HV-1^06142012.0149608 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004007 | 406346754-40283-DETAIL-09_11_2025-GO95HV-1^06248007.0223500 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004008 | 406394009-81850-DTLSB-06_04_2026-GO95HV-1^07216001.0115301 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004009 | 406451099-15209-DETAIL-02_03_2022-CUSTWIRE-1^06147005.0300800 | OTHER | Non-HFTD | Distribution | 2022-02-03 | 2025-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004010 | 406789759-83739-DTLTRT-06_25_2025-GO95HV-1^668087/00 3/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004011 | 406792293-88160-ADMIN-11_13_2025-POLEDERP-1^668085/00 10/002 | POLE | Non-HFTD | Transmission | 2025-11-13 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004012 | 406860635-53635-DETAIL-05_29_2025-GO95HV-1^06147014.0010800 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004013 | 341063761-29909-DTLSB-05_06_2024-GO95HV-1^06245007.0226800 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004014 | 341104805-25899-DETAIL-01_28_2026-SVCENTCO-1^06242009.0051300 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004015 | 341234086-64880-DTLTRT-07_03_2025-SVCDEFLC-1^668087/00 19/010 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004016 | 341277054-5689-DETAIL-08_18_2025-GO95HV-1^06247006.0362402 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004017 | 341335428-33549-DTLSB-07_16_2025-GO95HV-1^06244006.0317201 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004018 | 341804384-23429-DTLSB-05_04_2026-GRDRODHI-1^06142013.0062000 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004019 | 341937059-68059-ADMIN-09_25_2025-XARMSPCR-1^668005/00 3X/026 | CROSSARM | Non-HFTD | Transmission | 2025-09-25 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004020 | 342647473-78880-DETAIL-09_10_2025-GO95HV-1^06147001.0170400 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004021 | 342858351-1501-DETAIL-04_15_2026-GO95HV-1^06237004.0172300 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004022 | 343097036-563-DETAIL-06_23_2026-GO95HV-1^07217001.0104400 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004023 | 343217144-68583-DETAIL-09_17_2025-GO95HV-1^07218001.0088202 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004024 | 343246186-58190-DETAIL-08_04_2025-GO95HV-1^06246001.0185100 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004025 | 343421063-8390-DTLSB-05_29_2026-SVCROAD-1^07216001.0023706 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004026 | 343622209-31929-DETAIL-03_27_2023-CUSTWIRE-1^06142016.0052208 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004027 | 343719174-19459-DETAIL-10_10_2024-ENCHRW-1^07216001.0205008 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004028 | 365407076-80699-DETAIL-05_27_2025-GO95HV-1^06244006.0087900 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004029 | 365465814-39029-DETAIL-04_22_2026-GO95HV-1^06142012.0149607 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004030 | 365643079-63910-DETAIL-08_18_2025-ANCHIDLE-1^06246002.0346600 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004031 | 365688657-36970-DETAIL-02_25_2025-GO95CL10-1^06240004.0061109 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004032 | 36614774-85339-DETAIL-10_06_2025-CUSTWIRE-2^06243007.0369901 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004033 | 366239825-9529-DETAIL-05_13_2025-GO95HV-1^06142012.0012503 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004034 | 366620117-96899-DETAIL-06_05_2025-GO95HV-1^06245006.0300901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004035 | 367106368-37368-DTLSB-06_30_2025-GO95TCH-1^06244007.0036104 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004036 | 345059303-7859-DETAIL-08_12_2025-GO95HV-1^07217001.0010801 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004037 | 345295463-13979-DTLSB-01_21_2026-BIRDDMG-1^06242009.0298106 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004038 | 345483803-63840-DTLTRT-05_29_2025-GO95HV-1^668075/00 8/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004039 | 345674968-39909-ADMIN-10_23_2025-GO95HV-1^06246011.0361200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004040 | 345918386-18129-DETAIL-04_21_2026-GO95HV-1^06142012.0148802 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004041 | 346342234-47589-DETAIL-08_11_2025-GO95HV-1^06246002.0094002 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004042 | 346342234-47589-DETAIL-08_11_2025-XARMSPCR-1^06246002.0094002 | CROSSARM | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004043 | 346525860-11043-DETAIL-10_09_2025-CUSTWIRE-1^06248003.0332940 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004044 | 346525860-11043-DETAIL-10_09_2025-GO95HV-1^06248003.0332940 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004045 | 346683143-93309-DETAIL-07_31_2025-GO95HV-1^06247006.0201400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004046 | 347019778-2533-DETAIL-09_10_2025-GO95HV-1^07218001.0174502 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004047 | 347160361-79690-DETAIL-10_15_2025-GO95HV-1^06148001.0306902 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004048 | 347817019-40079-DETAIL-09_30_2025-CONDCOIL-1^06246009.0134600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004049 | 347817019-40079-DETAIL-09_30_2025-GO95MLD-1^06246009.0134600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004050 | 347817019-40079-DETAIL-09_30_2025-GRDBROKE-1^06246009.0134600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004051 | 367315178-72910-DTLSB-02_02_2023-CUSTWIRE-1^06247001.0010200 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004052 | 36739136-11349-DTLSB-07_10_2025-GO95HV-1^06244006.0272001 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004053 | 367772354-68599-DTLSB-04_06_2026-GO95MLD-1^06241009.0153901 | OTHER | Non-HFTD | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004054 | 367945929-99953-DTLSB-04_17_2024-POLETOP-1^06245007.0225342 | POLE | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004055 | 36799166-40630-DTLSB-04_30_2026-GO95HV-1^06142013.0171401 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004056 | 367993943-78310-DTLTRT-05_13_2026-GO95HV-1^668085/00 13/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004057 | 36819701-74449-DTLSB-07_14_2025-GO95HV-1^06244007.0228601 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004058 | 174396931-74080-DETAIL-02_16_2026-GO95HV-1^06239001.0042702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004059 | 174977364-83090-DETAIL-02_12_2026-GO95HV-1^06239003.0367002 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004060 | 317666859-7259-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0332400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004061 | 317682110-15860-DETAIL-08_13_2025-GO95HV-1^06246001.0300900 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004062 | 317895148-35459-DETAIL-06_04_2024-CUSTWIRE-1^06246005.0315601 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004063 | 317952717-3349-DTLSB-08_18_2025-GO95HV-1^07218001.0353600 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004064 | 318008961-4980-ADMIN-06_08_2026-SVCTREE-1^06240004.0168307 | OTHER | HFTD Tier 2 | Distribution | 2026-06-08 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004065 | 318891889-55733-DTLSB-06_17_2026-GO95MLD-1^07217001.0342901 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004066 | 319284411-20529-DETAIL-05_14_2025-GO95HV-1^06142012.0119900 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004067 | 319420179-53790-DETAIL-01_16_2025-GO95MLD-1^06239004.0256216 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004068 | 319565555-37559-DTLSB-06_10_2026-GO95HV-1^07216001.0226000 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004069 | 319663410-73399-DTLSB-06_25_2025-GO95HV-1^06244007.0104803 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004070 | 319841353-39780-DETAIL-02_23_2026-GO95HV-1^06239002.0154003 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004071 | 319957466-79466-DETAIL-08_19_2025-GO95HV-1^06247006.0365101 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004072 | 320041795-11342-DETAIL-05_07_2025-GO95HV-1^06242007.0265900 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004073 | 349236201-41970-DETAIL-02_18_2026-GO95HV-1^06239002.0094000 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004074 | 349367914-79189-ADMIN-03_05_2026-CLRTOUCH-1^06242009.0120101 | CONDUCTOR | Non-HFTD | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004075 | 349533279-35279-DETAIL-08_21_2025-GO95TCH-1^07216001.0177240 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004076 | 349650471-45042-DETAIL-04_07_2025-GUYHINS-1^06241005.0119502 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004077 | 349650471-45042-DETAIL-04_07_2025-GUYNOINS-2^06241005.0119502 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004078 | 349962879-44199-DETAIL-04_21_2025-GO95HV-1^06242006.0037803 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004079 | 350025335-93319-ADMIN-11_13_2025-GO95HV-1^06247008.0314701 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004080 | 350255213-41650-DETAIL-06_12_2025-GO95HV-1^06237005.0356100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-12 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004081 | 32132985-74985-DETAIL-06_03_2025-SVCROAD-2^06148014.0248900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004082 | 32142145-92740-DETAIL-02_26_2025-GO95TCH-1^06240004.0219700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004083 | 321687936-44560-ADMIN-10_20_2025-GRDRODHI-1^06247001.0365101 | OTHER | Non-HFTD | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004084 | 321721166-90029-DETAIL-05_19_2025-GO95HV-1^06142012.0014101 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004085 | 321789396-69199-DETAIL-06_03_2025-GO95HV-1^06245007.0244405 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004086 | 322057905-96059-DETAIL-08_20_2025-SVCDEFLC-1^06247006.0369001 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004087 | 322394179-71829-DETAIL-02_05_2026-GUYHINS-1^06243009.0318800 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004088 | 322744132-43450-DETAIL-01_15_2026-COVCOTHR-1^06239004.0135203 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004089 | 32289658-95749-DTLSB-07_16_2025-GO95HV-1^06244006.0291502 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004090 | 322935914-40039-DETAIL-06_10_2026-SVCNEUT-1^668086/00 19/012 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004091 | 323105578-96190-DETAIL-04_05_2021-CUSTWIRE-1^06239004.0245507 | OTHER | HFTD Tier 3 | Distribution | 2021-04-05 | 2024-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004092 | 323307956-12670-DETAIL-07_03_2025-GUYHINS-1^668087/00 18/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004093 | 323307956-12670-DETAIL-07_03_2025-GUYHINS-2^668087/00 18/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004094 | 323742741-83979-DETAIL-10_07_2025-GO95HV-1^06148001.0311802 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004095 | 3239549-60289-DETAIL-10_07_2025-GO95HV-1^06148001.0274700 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004096 | 324401943-76719-DTLSB-03_25_2026-GO95HV-1^06242009.0038501 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004097 | 350266192-49253-DETAIL-07_24_2025-RISEGRD-1^06247005.0179940 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004098 | 176969486-49659-DTLSB-08_18_2025-GO95HV-1^07218001.0355200 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004099 | 177077611-67449-DETAIL-08_20_2025-GO95HV-1^07216001.0173003 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004100 | 177639291-97609-DETAIL-09_08_2025-GO95HV-1^06246006.0053002 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004101 | 177887134-83519-DETAIL-06_27_2022-CUSTWIRE-1^07116007.0155700 | OTHER | HFTD Tier 2 | Distribution | 2022-06-27 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004102 | 178018092-4453-DETAIL-06_24_2026-GO95HV-1^07217001.0221300 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004103 | 350441839-9169-DTLTRT-06_14_2021-GO95HV-1^668041/00 2/020 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004104 | 325525401-68099-AUDIT-10_15_2024-CUSTWIRE-1^06245007.0119703 | OTHER | HFTD Tier 2 | Distribution | 2024-10-15 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004105 | 175094235-6235-DTLSB-06_26_2025-GO95HV-1^06244007.0108801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004106 | 175234401-68710-DETAIL-09_11_2025-GO95HV-1^06147001.0082501 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004107 | 175513511-52089-DETAIL-05_14_2025-ABNDEQPM-1^06243006.0251000 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004108 | 175515624-81489-ADMIN-03_06_2026-POLEREPL-1^06247006.0251004 | POLE | Non-HFTD | Distribution | 2026-03-06 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004109 | 175796251-48180-DETAIL-02_16_2026-GO95HV-1^06239001.0044700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004110 | 326057936-72278-DTLSB-03_10_2026-GO95HV-1^06243009.0347001 | OTHER | Non-HFTD | Distribution | 2026-03-10 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004111 | 326302128-78469-DETAIL-03_26_2024-CUSTWIRE-1^06244005.0147100 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004112 | 326593109-93513-DETAIL-08_26_2025-GO95HV-1^06247006.0331702 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004113 | 327006911-14580-DETAIL-02_23_2026-GO95HV-1^06239002.0035400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004114 | 327033002-34620-DETAIL-07_01_2026-GO95HV-1^07217001.0151700 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004115 | 327148451-95730-DETAIL-03_26_2026-COVCOTHR-1^06240004.0208501 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004116 | 327237171-57599-DETAIL-09_10_2025-GO95HV-1^06246006.0183202 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004117 | 327468612-71253-DETAIL-07_30_2025-ENCHRW-1^06247005.0179700 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004118 | 388176355-20409-DETAIL-08_11_2025-BIRDDMG-1^06247006.0265601 | POLE | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004119 | 388176355-20409-DETAIL-08_11_2025-GO95HV-1^06247006.0265601 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004120 | 388254953-40740-DTLSB-03_28_2022-GO95HV-1^06144006.0153100 | OTHER | Non-HFTD | Distribution | 2022-03-28 | 2027-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004121 | 388943181-17639-DETAIL-05_07_2025-GO95HV-1^06243006.0352301 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004122 | 388956747-98919-ADMIN-01_15_2025-POLTOPSW-1^668036/00 1/036 | SWITCH | Non-HFTD | Transmission | 2025-01-15 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004123 | 389206916-16449-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0111900 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004124 | 329242284-41849-DTLSB-07_10_2025-GO95HV-1^06244007.0144702 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004125 | 329347265-19972-DETAIL-05_29_2025-GO95HV-1^06244006.0030400 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004126 | 329366836-15570-ADMIN-01_15_2025-GO95CL10-1^06239004.0256207 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004127 | 329655523-8999-DETAIL-07_31_2025-GO95HV-1^06247005.0210001 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004128 | 330016663-73639-DETAIL-05_29_2025-GO95HV-1^06244006.0109903 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004129 | 330047104-32470-DTLSB-01_30_2023-CONDCOIL-1^06248001.0259101 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004130 | 33014148-7139-DETAIL-09_03_2025-GO95HV-1^07216001.0093002 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004131 | 330181070-74359-DETAIL-10_09_2025-GO95HV-1^06248003.0273300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004132 | 330205249-63659-DETAIL-09_05_2025-ANCHIDLE-1^07216001.0094400 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-05 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004133 | 330600280-84370-DETAIL-03_17_2026-COVCOTHR-1^06240004.0222401 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004134 | 330615634-32553-DETAIL-09_22_2025-GO95HV-1^07218001.0215800 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004135 | 331292040-10620-DTLSB-07_28_2025-GO95HV-1^07218001.0265203 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004136 | 331470426-2070-DTLTRT-05_11_2026-GO95HV-1^668038/00 3/050 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004137 | 33151417-71417-DETAIL-06_18_2025-GO95HV-1^668075/00 13/046 | OTHER | HFTD Tier 2 | Transmission | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004138 | 331965214-97599-DETAIL-01_29_2026-GO95BLTC-1^06242009.0051502 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004139 | 304350311-88062-ADMIN-03_06_2026-POLEREPL-1^06244007.0107444 | POLE | HFTD Tier 2 | Distribution | 2026-03-06 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004140 | 30438443-69799-DETAIL-10_01_2025-GO95BLTC-1^06246009.0128702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004141 | 304499635-91219-DTLSB-01_28_2026-BIRDDMG-1^06242009.0050100 | POLE | HFTD Tier 2 | Distribution | 2026-01-28 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004142 | 305033715-75715-DETAIL-06_05_2025-GO95HV-1^06148014.0235301 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004143 | 166870591-36729-DTLSB-09_05_2023-ENCHRW-1^06243008.0092502 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004144 | 167288449-50449-DETAIL-06_03_2024-CUSTWIRE-1^06245006.0027900 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004145 | 167341738-39618-DETAIL-07_07_2026-GO95HV-1^07217001.0219400 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004146 | 167593553-44553-DETAIL-06_17_2025-GO95MLD-1^668075/00 1/044 | OTHER | HFTD Tier 2 | Transmission | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004147 | 168085999-40010-DETAIL-08_14_2025-GO95HV-1^06246002.0361900 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004148 | 305296689-15629-DTLSB-02_04_2026-GO95HV-1^06243009.0321303 | OTHER | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004149 | 305608921-66580-DETAIL-02_23_2026-GO95HV-1^06239002.0037403 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004150 | 306091471-15750-DETAIL-09_10_2025-GO95HV-1^06147001.0082403 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004151 | 306114283-3489-DETAIL-07_31_2025-GO95HV-1^06247006.0200300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004152 | 306121966-850-AUDIT-08_19_2025-CLMBHAZ-1^06246001.0185000 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004153 | 306292648-46069-DETAIL-09_17_2025-GO95HV-1^06248007.0365300 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004154 | 351847140-84159-DTLSB-07_30_2025-CUSTWIRE-1^07218001.0264101 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004155 | 351847140-84159-DTLSB-07_30_2025-GO95HV-1^07218001.0264101 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004156 | 351869621-61280-DETAIL-01_23_2026-COVCOTHR-1^06240004.0236802 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004157 | 351869621-61280-DETAIL-01_23_2026-COVCOTHR-2^06240004.0236802 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004158 | 351869621-61280-DETAIL-01_23_2026-COVCOTHR-4^06240004.0236802 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004159 | 352334061-96852-DETAIL-06_08_2023-CUSTWIRE-1^06244009.0327802 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004160 | 352420009-99073-DETAIL-08_05_2025-GO95HV-1^06247005.0207800 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004161 | 307601241-15711-DETAIL-06_19_2025-GO95GUYB-1^06237004.0205601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-06-19 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004162 | 307601241-15711-DETAIL-06_19_2025-XARMSPCR-1^06237004.0205601 | CROSSARM | HFTD Tier 2 | Distribution | 2025-06-19 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004163 | 307726848-15479-DETAIL-07_28_2025-GO95HV-1^06247005.0086540 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004164 | 307829090-69090-DETAIL-06_05_2025-GO95MLD-1^668075/00 7/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004165 | 307857749-71589-DTLSB-04_21_2026-GO95HV-1^06241008.0312100 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004166 | 308052421-67639-DETAIL-05_07_2025-GO95HV-1^06243006.0012701 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004167 | 308150634-21079-DETAIL-09_23_2025-GO95HV-1^06247004.0071500 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004168 | 308165227-6227-DETAIL-04_06_2026-GUYHINS-2^06236005.0110303 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004169 | 308731589-53799-DETAIL-08_26_2025-GO95BLTC-1^06247006.0331900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004170 | 308731589-53799-DETAIL-08_26_2025-GO95HV-1^06247006.0331900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004171 | 309211598-90561-DETAIL-02_25_2025-GO95BLTC-1^06241005.0151701 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004172 | 30925686-64579-DETAIL-09_02_2025-GO95HV-1^06246001.0175310 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004173 | 309281710-3710-DETAIL-06_03_2025-GO95HV-1^06148015.0313300 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004174 | 309281720-43173-DETAIL-06_16_2025-BIRDDMG-1^06248005.0328140 | POLE | Non-HFTD | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004175 | 309507392-71139-DETAIL-05_20_2025-GO95HV-1^06243006.0079800 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004176 | 333026276-5742-ADMIN-11_10_2025-SVCENTCO-1^06246011.0070800 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004177 | 333362343-44959-DETAIL-09_15_2025-GO95HV-1^06248007.0231100 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004178 | 333845011-44459-DETAIL-08_20_2025-GO95HV-1^07216001.0173104 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004179 | 334037388-7380-DTLSB-05_05_2026-GO95HV-1^06142013.0152000 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004180 | 334070228-97380-DTLSB-02_14_2023-CUSTWIRE-1^06248001.0226901 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004181 | 334158119-60389-ADMIN-11_12_2025-GO95HV-1^06246001.0336500 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004182 | 334158119-60389-ADMIN-11_12_2025-SVCENTCO-1^06246001.0336500 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004183 | 310895373-3509-DETAIL-09_10_2025-GO95HV-1^06246007.0134251 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004184 | 311252920-28389-ADMIN-10_23_2025-GO95BLTC-1^06246011.0369201 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004185 | 311304647-76647-DTLSB-07_03_2025-GO95HV-1^06245007.0355980 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004186 | 311473427-76427-DETAIL-08_14_2025-GO95HV-1^06247006.0360720 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004187 | 311574674-31959-DTLTRT-04_22_2026-GO95HV-1^668004/02 1/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004188 | 168392699-24110-DETAIL-08_19_2025-GO95HV-1^06246002.0360900 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004189 | 168614433-41210-DTLSB-05_29_2026-GO95HV-1^07216001.0023801 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004190 | 168758258-57210-ADMIN-11_12_2025-GO95HV-1^06246001.0343300 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004191 | 168988190-29310-DTLTRT-06_25_2025-GO95HV-1^668087/00 10/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004192 | 168988190-29310-DTLTRT-06_25_2025-GUYHINS-1^668087/00 10/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004193 | 3119019-80240-DETAIL-06_19_2025-GO95HV-1^06237004.0077300 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004194 | 312059784-17910-DETAIL-11_16_2022-CUSTWIRE-1^06238004.0155000 | OTHER | HFTD Tier 2 | Distribution | 2022-11-16 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004195 | 312089571-75380-DETAIL-02_23_2026-POLETOP-1^06239002.0030402 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004196 | 312115798-76652-ADMIN-10_20_2025-GO95TCH-1^06246012.0119502 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004197 | 31244140-49740-DETAIL-03_31_2026-COVCOTHR-3^06239003.0063203 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004198 | 334226598-42843-DTLSB-07_03_2025-GO95HV-1^06245007.0359840 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004199 | 3343371-23952-DTLSB-07_14_2025-GO95HV-1^06244006.0218600 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004200 | 334680568-54189-ADMIN-10_23_2025-BIRDDMG-1^06246011.0361300 | POLE | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004201 | 334716341-68080-DETAIL-02_18_2026-GO95HV-1^06239002.0043301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004202 | 334752384-44729-DTLSB-01_21_2026-XARMSPCR-1^06242009.0298306 | CROSSARM | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004203 | 334764945-56299-DTLSB-07_09_2025-GUYHINS-1^06244006.0347503 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004204 | 176215011-36780-DETAIL-02_12_2025-SVCROOF-1^06240004.0167543 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004205 | 313603583-31780-DETAIL-03_31_2026-COVCOTHR-2^06240004.0355301 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004206 | 313603583-31780-DETAIL-03_31_2026-COVCOTHR-3^06240004.0355301 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004207 | 313921161-23660-DTLTRT-05_18_2026-GO95HV-1^668086/00 12/009 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004208 | 313993237-5189-DTLSB-10_03_2024-ABNDEQPM-1^06245006.0336401 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004209 | 314169180-53580-DETAIL-06_05_2025-GO95HV-1^668075/00 6/028 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004210 | 314483279-56599-DETAIL-09_09_2025-GO95HV-1^06246007.0144251 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004211 | 314797657-68140-DETAIL-02_17_2026-GUYNOINS-1^06239003.0129801 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-17 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004212 | 315120336-12359-DTLTRT-05_07_2026-GO95HV-1^668004/00 13/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004213 | 315243991-49460-DETAIL-09_30_2025-GO95HV-1^06148001.0301300 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004214 | 315936651-60942-DETAIL-04_01_2025-GRDRODHI-1^06241005.0119801 | OTHER | HFTD Tier 2 | Distribution | 2025-04-01 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004215 | 316083951-64109-DETAIL-07_31_2025-GO95HV-1^06247006.0206501 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004216 | 316225814-55309-DETAIL-07_30_2025-GO95HV-1^06247006.0202200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004217 | 316265702-94383-DTLSB-06_05_2026-GO95HV-1^07216001.0230803 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004218 | 316351124-58599-ADMIN-03_21_2024-ABNDEQPM-1^06147005.0186600 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004219 | 31677679-84119-DTLSB-04_22_2026-GO95HV-1^06241008.0300500 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004220 | 283276389-5040-DETAIL-03_31_2026-BIRDDMG-1^06237004.0078100 | POLE | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004221 | 283276389-5040-DETAIL-03_31_2026-GO95HV-1^06237004.0078100 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004222 | 283299811-53089-DETAIL-10_02_2025-GO95BLTC-1^06246008.0067702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004223 | 28338222-6079-ADMIN-10_28_2025-ABNDEQPM-1^06246001.0019500 | OTHER | Non-HFTD | Distribution | 2025-10-28 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004224 | 283395509-47239-DETAIL-05_12_2025-GO95HV-1^06243006.0310901 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004225 | 283479485-47089-DETAIL-08_04_2025-GO95HV-1^06247006.0208404 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004226 | 283479485-47089-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0208404 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004227 | 283621615-61359-DTLSB-07_03_2025-GO95HV-1^06245007.0358702 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004228 | 285740499-35373-DETAIL-09_22_2025-GO95HV-1^06248007.0242200 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004229 | 285760762-23208-DTLTRT-06_23_2025-GO95MLD-1^668087/00 7A/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004230 | 285760762-23208-DTLTRT-06_23_2025-GUYLOINS-1^668087/00 7A/002 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004231 | 285794318-1599-ADMIN-10_23_2025-GO95MLD-1^06246011.0362000 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004232 | 285838123-37559-DTLTRT-04_20_2026-GO95HV-1^668004/02 1/005 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004233 | 286278994-50262-ADMIN-10_07_2025-COVCOTHR-1^06242005.0361241 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004234 | 286453084-5490-DETAIL-02_03_2026-SVCTREE-1^06239002.0067901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-03 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004235 | 286775236-60670-DETAIL-01_14_2025-GO95MLD-1^06239004.0255000 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004236 | 287009463-74420-ADMIN-10_21_2025-GO95HV-1^06247001.0250901 | OTHER | Non-HFTD | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004237 | 287059941-64720-DETAIL-01_23_2026-BIRDDMG-1^06240004.0134101 | POLE | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004238 | 287666256-34720-DETAIL-09_03_2025-GO95HV-1^06246001.0177401 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004239 | 287806011-26011-DETAIL-05_08_2025-GO95HV-1^06243006.0285901 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004240 | 288234773-95180-DETAIL-02_18_2026-GO95HV-1^06239002.0164901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004241 | 288358366-64419-DTLSB-03_16_2026-GO95HV-1^06242009.0239500 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004242 | 288857309-83409-DETAIL-09_30_2025-GO95HV-1^06246009.0242500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004243 | 289107218-84949-DTLSB-07_08_2025-GO95HV-1^06244007.0037901 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004244 | 352730046-94671-DETAIL-02_19_2025-GO95HV-1^06239004.0365944 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004245 | 352827637-99329-DETAIL-05_09_2024-CUSTWIRE-1^06142012.0120310 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004246 | 35304670-27780-DETAIL-04_01_2026-COVCOTHR-1^06237005.0261205 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004247 | 353064893-25893-DETAIL-06_18_2025-ANCHIDLE-1^668075/00 2/048 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004248 | 353097006-91591-DETAIL-05_07_2026-GO95HV-1^668038/00 1/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004249 | 353136698-42600-DETAIL-08_25_2025-CONDCOIL-1^06246001.0204700 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004250 | 353343773-35700-DETAIL-09_09_2025-GO95HV-1^06147001.0196400 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004251 | 353507953-82053-DETAIL-06_05_2025-GO95HV-1^06245006.0190100 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004252 | 290503573-15553-DETAIL-09_22_2025-GO95HV-1^07218001.0161100 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004253 | 290531146-3899-DTLSB-06_25_2025-GO95HV-1^06244007.0106903 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004254 | 290626581-82430-DTLTRT-05_18_2026-GO95HV-1^668086/00 5/008 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004255 | 290655259-14430-DETAIL-08_12_2025-GO95HV-1^06246002.0259202 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004256 | 290974389-76879-DTLSB-04_22_2026-GO95HV-1^06241008.0302400 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004257 | 29100283-63779-DETAIL-09_17_2025-GRDRODHI-1^06147001.0237600 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004258 | 291024124-30553-DETAIL-05_21_2026-GO95HV-1^07217001.0143507 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004259 | 291246674-86040-DETAIL-02_26_2025-GUYHINS-1^06240004.0218901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004260 | 291432848-73470-DRONE_HY-06_19_2026-COVCOTHR-1^06240004.0160200 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004261 | 291527006-71849-DETAIL-10_24_2024-GO95CL10-1^07216001.0203901 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004262 | 291527006-71849-DETAIL-10_24_2024-GUYHINS-1^07216001.0203901 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004263 | 291527006-71849-DETAIL-10_24_2024-GUYHINS-2^07216001.0203901 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004264 | 291811964-77030-DETAIL-01_28_2025-GO95HV-1^06240004.0070900 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004265 | 291952204-45029-DETAIL-08_20_2025-GO95HV-1^06247006.0255806 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004266 | 291967186-70860-DETAIL-05_04_2026-GO95HV-1^668004/00 2/019 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004267 | 170951428-63859-DETAIL-03_18_2024-CUSTWIRE-1^06246005.0078201 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004268 | 171071001-59201-DETAIL-01_21_2025-GO95HV-1^06239004.0255443 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004269 | 171339661-10639-DETAIL-05_14_2025-GO95HV-1^06243006.0154400 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004270 | 171941664-62309-DETAIL-08_12_2025-GO95HV-1^06247006.0250201 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004271 | 172003058-66810-DETAIL-08_19_2025-GO95HV-1^06246002.0353903 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004272 | 172262437-31409-DETAIL-06_05_2025-GO95HV-1^06245006.0300001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004273 | 172339310-55843-DETAIL-07_01_2026-GO95HV-1^07217001.0153500 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004274 | 293586724-68030-DRONE_HY-07_15_2026-DISTHDWR-1^06143013.0137301 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-07-15 | 2027-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120004275 | 293619348-58249-DTLSB-08_13_2025-GO95HV-1^07217001.0024400 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004276 | 293765759-51859-DETAIL-06_16_2025-COPLLEAN-1^06248005.0330840 | POLE | Non-HFTD | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004277 | 293765759-51859-DETAIL-06_16_2025-GO95HV-1^06248005.0330840 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004278 | 293998955-29955-DETAIL-03_10_2026-SVCENTCO-1^06238004.0029610 | OTHER | HFTD Tier 2 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004279 | 294153705-68563-DETAIL-05_26_2026-SVCNEUT-1^07217001.0142402 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004280 | 294253638-83560-DTLTRT-07_02_2025-GO95HV-1^668087/00 4/017 | OTHER | Non-HFTD | Transmission | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004281 | 294304493-61509-DETAIL-09_10_2025-GO95HV-1^06246007.0133251 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004282 | 294597201-35159-AUDIT-09_09_2025-SVCNEUT-1^07216001.0172003 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004283 | 295572123-83809-DETAIL-08_25_2021-CUSTWIRE-1^06148004.0353206 | OTHER | Non-HFTD | Distribution | 2021-08-25 | 2024-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004284 | 295770521-21059-DTLSB-04_09_2024-CUSTWIRE-1^06245007.0227109 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004285 | 296060523-16129-DETAIL-11_08_2021-GO95CLSV-1^06142012.0149700 | OTHER | Non-HFTD | Distribution | 2021-11-08 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004286 | 296126756-48756-DETAIL-05_29_2025-GO95HV-1^06148014.0357000 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004287 | 296272004-65789-DETAIL-08_20_2025-GO95HV-1^06247006.0255602 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004288 | 172339310-55843-DETAIL-07_01_2026-GRDRODHI-1^07217001.0153500 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004289 | 17262133-3133-DETAIL-06_11_2025-GUYHINS-1^668075/00 4/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004290 | 316968749-33739-DTLTRT-06_24_2025-SVCNEUT-1^668087/00 14/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004291 | 316987419-61460-DETAIL-08_19_2025-GO95HV-1^06246002.0260400 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004292 | 317034143-62879-DTLSB-05_11_2026-SVCENTBK-1^06242009.0274300 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004293 | 317271174-16139-DTLSB-05_04_2026-GO95HV-1^06142013.0062001 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004294 | 317601148-32333-DETAIL-09_09_2025-GRDRODHI-1^07218001.0174200 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004295 | 173168166-21659-DTLTRT-04_29_2026-GO95HV-1^668004/00 4/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004296 | 269965384-49399-DETAIL-09_24_2025-ANCHIDLE-1^06246009.0107300 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-24 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004297 | 269965384-49399-DETAIL-09_24_2025-GO95BLTC-1^06246009.0107300 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004298 | 269965384-49399-DETAIL-09_24_2025-GO95HV-1^06246009.0107300 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004299 | 270880975-7879-DETAIL-06_17_2025-GO95HV-1^06248004.0283001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004300 | 270974563-96779-ADMIN-11_12_2025-GO95TCH-1^06246001.0320500 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004301 | 271030814-87453-DETAIL-05_27_2026-ABNDEQPM-1^07217001.0147600 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004302 | 271259575-41500-DETAIL-02_05_2026-GUYHINS-1^06239003.0017709 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004303 | 271259575-41500-DETAIL-02_05_2026-GUYHINS-2^06239003.0017709 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004304 | 271605593-51250-DETAIL-01_14_2026-GO95MLD-1^06239004.0134143 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004305 | 271868454-69632-DETAIL-04_07_2025-GUYHINS-1^06241005.0119202 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004306 | 271883494-68840-DTLTRT-06_04_2025-GO95HV-1^668075/00 13/010 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004307 | 272034042-76339-DETAIL-05_21_2025-GO95HV-1^06243006.0155002 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004308 | 272873876-79389-DETAIL-08_05_2025-PWRTRN-1^06246002.0135001 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004309 | 27327102-57241-DTLSB-08_30_2023-CUSTWIRE-1^06243008.0173101 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004310 | 273829389-50159-DTLTRT-05_06_2026-GO95HV-1^668004/00 6/023 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004311 | 274204746-21309-DETAIL-08_12_2025-GO95BLTC-1^06247006.0269101 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004312 | 297800941-87689-DTLSB-07_08_2025-GO95HV-1^06244007.0039904 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004313 | 297940767-44323-DETAIL-05_27_2026-GO95HV-1^07217001.0148202 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004314 | 298122542-5829-DETAIL-05_13_2024-CUSTWIRE-1^06142012.0123302 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004315 | 298206547-81940-DETAIL-08_05_2025-GO95HV-1^06246002.0247900 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004316 | 298257821-77079-DETAIL-09_02_2021-CUSTWIRE-1^06148004.0344200 | OTHER | Non-HFTD | Distribution | 2021-09-02 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004317 | 298269870-15139-DTLTRT-07_10_2025-ABNDEQPM-1^668087/00 3/024 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004318 | 298799715-88909-ADMIN-06_09_2026-POLEREPL-1^06148004.0179300 | POLE | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004319 | 275530298-94298-AUDIT-04_01_2026-GUYHINS-1^06238004.0028541 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004320 | 275557619-83769-DETAIL-07_22_2025-GO95HV-1^06247005.0059502 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004321 | 275576133-29879-DTLSB-01_20_2026-GO95HV-1^06242009.0298102 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004322 | 275709467-13410-ADMIN-11_07_2025-GO95HV-1^06246001.0267900 | OTHER | Non-HFTD | Distribution | 2025-11-07 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004323 | 275726486-25799-DETAIL-05_28_2025-GO95HV-1^06244006.0040002 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004324 | 2758171-79209-DETAIL-10_06_2022-CUSTWIRE-1^06245010.0213803 | OTHER | HFTD Tier 2 | Distribution | 2022-10-06 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004325 | 161963586-15700-AUDIT-05_27_2026-GUYHINS-1^668086/00 6/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004326 | 162168306-68800-DETAIL-08_25_2025-GO95HV-1^06246001.0175201 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004327 | 162350361-35900-DTLTRT-06_26_2025-GO95HV-1^668087/00 15/008 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004328 | 16261656-30879-DETAIL-03_25_2024-POLISSUE-1^06147005.0139901 | POLE | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004329 | 162634509-69000-DETAIL-08_19_2025-GO95HV-1^06246002.0261401 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004330 | 163026075-69899-DETAIL-09_09_2025-GO95HV-1^06246007.0226850 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004331 | 16357026-71359-DTLTRT-05_07_2026-GO95HV-1^668004/00 12/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004332 | 163794011-86309-DETAIL-07_31_2025-GO95HV-1^06247006.0205804 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004333 | 298799715-88909-DETAIL-01_16_2023-GO95MLD-1^06148004.0179300 | OTHER | Non-HFTD | Distribution | 2023-01-16 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004334 | 299059709-99709-DETAIL-08_18_2025-GO95HV-1^06247006.0361003 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004335 | 299175111-4180-DETAIL-02_16_2026-GO95HV-1^06239001.0056701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004336 | 299395323-33059-DETAIL-08_28_2025-GO95HV-1^06247006.0062401 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004337 | 299494304-43490-AUDIT-02_09_2026-GO95TCH-1^06239002.0063614 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004338 | 29975858-38430-DETAIL-01_26_2026-ANCHIDLE-1^06240003.0304502 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004339 | 299914027-15829-DETAIL-04_20_2026-SVCDEFLC-1^06142012.0143907 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004340 | 300000167-10267-DTLSB-07_14_2025-ENCHRW-1^06244006.0271640 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004341 | 276533431-39739-DTLTRT-06_25_2025-SVCRUBLG-1^668087/00 3/008 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004342 | 276697402-47460-DTLTRT-04_29_2026-GO95HV-1^668004/00 8/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004343 | 276749468-5110-DETAIL-04_22_2026-ANCHIDLE-1^06142012.0143604 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004344 | 276784883-81210-DETAIL-09_03_2025-SVCDEFLC-1^06247006.0210740 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004345 | 277495043-31780-DETAIL-02_23_2026-GO95HV-1^06239002.0153101 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004346 | 277582493-92983-DETAIL-09_17_2025-GO95BLTC-1^07218001.0088600 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004347 | 277671913-84909-DETAIL-09_30_2025-GO95BLTC-1^06246009.0120200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004348 | 277872258-66209-DTLSB-06_30_2025-GO95HV-1^06244006.0221303 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004349 | 277923336-35369-DETAIL-04_24_2025-GO95HV-1^06242006.0195302 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004350 | 277997218-43910-DETAIL-09_04_2025-GO95HV-1^06146001.0050800 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004351 | 278477874-2974-DTLTRT-07_07_2025-GO95HV-1^668087/00 13/029 | OTHER | Non-HFTD | Transmission | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004352 | 278491971-53059-DETAIL-08_28_2025-GO95HV-1^06247006.0062402 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004353 | 278521662-85139-ADMIN-05_15_2024-ENCHRW-1^06142012.0126802 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004354 | 278521662-85139-DETAIL-05_15_2024-CUSTWIRE-1^06142012.0126802 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004355 | 278596023-6719-DTLSB-03_25_2026-GO95HV-1^06242009.0037400 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004356 | 335277356-96280-DETAIL-08_12_2025-GO95HV-1^06246001.0194401 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004357 | 335368219-84380-DETAIL-09_08_2025-GO95HV-1^06147001.0329101 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004358 | 335487661-61170-DTLTRT-05_12_2026-GO95HV-1^668004/00 5/010 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004359 | 335503905-31800-DETAIL-04_08_2026-GO95HV-1^06240002.0313201 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004360 | 335521015-72015-DETAIL-06_05_2025-GO95HV-1^06148014.0246001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004361 | 335576919-89759-DETAIL-06_16_2025-GO95HV-1^06248005.0330440 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004362 | 335581529-73529-DTLTRT-07_01_2025-GO95HV-1^668087/00 17/014 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004363 | 279401196-17310-DETAIL-02_17_2025-GRDRODHI-1^06240004.0163605 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004364 | 279454464-87990-DETAIL-03_31_2025-GO95MLD-1^06239003.0017901 | OTHER | Non-HFTD | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004365 | 279518095-68059-DETAIL-08_20_2025-GO95MLD-1^06247006.0368200 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004366 | 279539133-8920-DETAIL-09_09_2025-GO95HV-1^06147001.0202501 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004367 | 279589654-83683-DETAIL-09_17_2025-GO95TCH-1^07218001.0088702 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004368 | 279835351-78180-DETAIL-02_18_2026-GO95HV-1^06239002.0046402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004369 | 279894209-17769-DETAIL-03_17_2025-COVCOTHR-1^668002/00 5/049 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-03-17 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004370 | 279920338-98120-DTLSB-06_09_2026-SVCROAD-1^07216001.0226003 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004371 | 280057231-57750-DETAIL-01_21_2026-COVCOTHR-1^06239004.0124905 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004372 | 280057231-57750-DETAIL-01_21_2026-GO95MLD-1^06239004.0124905 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004373 | 280091069-99713-DETAIL-08_25_2025-GO95HV-1^06247006.0282703 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004374 | 280146483-45429-DETAIL-05_13_2025-GO95HV-1^06142012.0014600 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004375 | 280834692-85312-DTLSB-07_16_2025-GO95HV-1^06244006.0237000 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004376 | 28093136-68189-DETAIL-10_02_2025-GO95HV-1^06247006.0263400 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004377 | 280989848-93489-DETAIL-06_17_2025-GO95HV-1^06248004.0299201 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004378 | 249657894-17053-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0037101 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004379 | 249929969-52399-DTLSB-07_14_2025-CUSTWIRE-1^06244006.0289700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004380 | 249929969-52399-DTLSB-07_14_2025-GO95HV-1^06244006.0289700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004381 | 250203654-3680-DTLSB-02_06_2023-CUSTWIRE-1^06248001.0257101 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004382 | 250443064-66399-AUDIT-09_02_2025-CLRTOUCH-1^06247006.0255001 | CONDUCTOR | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004383 | 250526541-20339-DETAIL-05_14_2025-GO95HV-1^06243006.0223100 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004384 | 250569860-12270-DETAIL-02_19_2026-GO95HV-1^06239002.0017600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004385 | 250680178-6440-DETAIL-03_12_2025-SVCENTCO-1^06238004.0223402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004386 | 250680178-6440-DETAIL-11_18_2022-CUSTWIRE-1^06238004.0223402 | OTHER | HFTD Tier 2 | Distribution | 2022-11-18 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004387 | 250827333-75980-DTLSB-03_28_2022-POLETOP-1^06144006.0224700 | POLE | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004388 | 251327791-48843-DETAIL-06_30_2026-CLMBTRE-1^07217001.0226003 | OTHER | Non-HFTD | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004389 | 251420894-8699-DETAIL-09_17_2025-GO95HV-1^06246006.0079100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004390 | 251420894-8699-DETAIL-09_17_2025-SVCDEFLC-1^06246006.0079100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004391 | 301566513-3040-DETAIL-05_13_2026-GO95HV-1^668085/00 2/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004392 | 301677181-54723-DETAIL-06_18_2025-GO95HV-1^06248004.0347640 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004393 | 301752595-30599-DETAIL-05_06_2025-SVCENTBK-1^06243006.0038800 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004394 | 301789763-3353-DETAIL-08_25_2025-GO95MLD-1^06247006.0285900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004395 | 302094930-50739-DTLSB-07_17_2025-GO95HV-1^06244006.0185104 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004396 | 302287109-28109-DTLSB-07_02_2025-GO95HV-1^06244007.0131741 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004397 | 302377398-31063-DETAIL-06_05_2025-GO95HV-1^06245006.0306741 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004398 | 302648961-58280-DRONE_HY-06_30_2026-DISTHDWR-1^06240004.0165302 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004399 | 252511276-72190-DETAIL-08_04_2025-GO95HV-1^06246001.0185004 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004400 | 252760935-75390-DETAIL-05_15_2024-GO95BLTC-1^06142012.0124700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004401 | 252760935-75390-DETAIL-05_15_2024-GO95HV-1^06142012.0124700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004402 | 252825715-64699-DETAIL-03_17_2025-SVCDEFLC-1^06240004.0271100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004403 | 252853138-16179-DETAIL-10_07_2025-GO95HV-1^06148001.0263000 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004404 | 253086302-37302-DETAIL-01_22_2025-GO95HV-1^06239004.0254540 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004405 | 253100895-409-DETAIL-08_11_2025-GO95HV-1^06247006.0269201 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004406 | 253162179-67490-DETAIL-09_04_2025-GO95HV-1^06146001.0082800 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004407 | 253329148-45159-ADMIN-06_20_2025-ABNDEQPM-1^668005/00 11/036 | OTHER | Non-HFTD | Transmission | 2025-06-20 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004408 | 253509365-11500-DETAIL-02_11_2026-GO95HV-1^06239003.0016600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004409 | 253736939-53579-DTLTRT-10_19_2023-CUSTWIRE-2^668010/00 15/025 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004410 | 253795178-87399-DETAIL-09_25_2025-ANCHIDLE-2^06246009.0089503 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-25 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004411 | 253808991-36790-DETAIL-09_30_2025-CONDFRAY-1^06148001.0300107 | CONDUCTOR | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004412 | 253933341-48239-DTLTRT-06_26_2025-GUYHINS-1^668087/00 6/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004413 | 254098983-50499-DETAIL-06_02_2025-GO95HV-1^06245007.0365840 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004414 | 164683624-2253-DETAIL-09_22_2025-GO95HV-1^07218001.0222801 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004415 | 164683624-2253-DETAIL-09_22_2025-GO95MLD-1^07218001.0222801 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004416 | 16471375-53289-DETAIL-10_22_2024-GO95BLTC-1^07216001.0207901 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004417 | 164736992-11499-DTLSB-01_20_2026-GO95HV-1^06242009.0299308 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004418 | 165315424-10060-DETAIL-01_13_2026-SVCTREE-1^06239004.0242940 | OTHER | HFTD Tier 3 | Distribution | 2026-01-13 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004419 | 165369458-25919-DTLSB-05_05_2026-GUYHINS-1^06241009.0252101 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004420 | 165473418-72610-DTLTRT-06_24_2025-GO95MLD-1^668087/00 1/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004421 | 166188413-52729-DTLSB-01_20_2026-GO95HV-1^06242009.0298204 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004422 | 256450248-91190-DETAIL-05_06_2026-GO95HV-1^668038/00 4/058 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004423 | 256594187-58719-DTLSB-04_09_2026-GO95HV-1^06241007.0207400 | OTHER | Non-HFTD | Distribution | 2026-04-09 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004424 | 257258521-90169-DETAIL-03_11_2026-SVCENTCO-1^06240004.0278603 | OTHER | HFTD Tier 2 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004425 | 257392253-98629-DTLSB-01_20_2026-GO95HV-1^06242009.0299102 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004426 | 258115908-30990-DTLSB-06_02_2026-SVCNEUT-1^07216001.0115706 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004427 | 258178418-12659-DTLSB-08_12_2025-GO95HV-1^07217001.0027302 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004428 | 258393147-39959-DTLSB-08_18_2025-GO95HV-1^07218001.0355840 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004429 | 258436741-78280-DETAIL-02_16_2026-GO95HV-1^06239001.0059701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004430 | 258833319-14042-DETAIL-04_17_2025-GO95HV-1^06242006.0091602 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004431 | 258850180-88959-DETAIL-03_12_2024-CUSTWIRE-1^06245007.0286801 | OTHER | HFTD Tier 2 | Distribution | 2024-03-12 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004432 | 259075198-24779-DETAIL-02_10_2026-GO95TCH-1^06239003.0016506 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004433 | 259511242-48039-DETAIL-05_20_2025-GO95HV-1^06243006.0077202 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004434 | 259668559-39559-DETAIL-08_05_2025-GO95HV-1^06247005.0207402 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004435 | 259837968-72540-DETAIL-03_05_2026-COVCOTHR-1^06238004.0147703 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004436 | 260210734-74179-DETAIL-06_17_2025-GO95HV-1^06248004.0283000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004437 | 166417101-47599-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0226200 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004438 | 166483599-9010-DETAIL-08_13_2025-GO95HV-1^06246002.0365200 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004439 | 166519764-110-DTLSB-06_05_2026-GO95HV-1^07216001.0229800 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004440 | 281425231-67280-DETAIL-01_23_2026-COVCOTHR-5^06240004.0238900 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004441 | 281677906-16571-DETAIL-02_19_2025-GO95HV-1^06239004.0365841 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004442 | 281831670-72270-DETAIL-06_05_2025-GO95HV-1^668075/00 4/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004443 | 282112213-24249-DETAIL-07_21_2025-SVCNEUT-1^06244006.0257901 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004444 | 26227556-91839-DETAIL-05_08_2025-GO95HV-1^06243006.0104300 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004445 | 262503418-47200-DTLTRT-06_23_2025-INSULBRK-1^668087/00 8/002 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004446 | 262564294-73859-DTLTRT-04_21_2026-GO95HV-1^668004/02 3/009 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004447 | 26259468-46870-DETAIL-10_01_2025-GO95HV-1^06148001.0303105 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004448 | 262625118-489-DETAIL-09_02_2025-GO95HV-1^06247006.0274701 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004449 | 26272129-52149-DETAIL-08_26_2025-GO95HV-1^07216001.0160803 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004450 | 263129900-96899-DETAIL-06_25_2025-GO95CL10-1^06244007.0104805 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004451 | 263668438-20891-DTLTRT-05_06_2026-GO95HV-1^668038/00 3/058 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004452 | 263668438-27800-DTLTRT-05_06_2026-GO95HV-1^668038/00 3/058 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004453 | 26370463-80069-DETAIL-09_18_2025-GO95HV-1^06248007.0266300 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004454 | 264073090-23100-DETAIL-03_17_2026-COVCOTHR-1^06240004.0220100 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004455 | 264221654-82654-DTLTRT-07_07_2025-GO95HV-1^668087/00 6/029 | OTHER | Non-HFTD | Transmission | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004456 | 264412891-38659-DTLTRT-04_30_2026-GO95HV-1^668004/00 7/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004457 | 264412891-38660-DTLTRT-04_30_2026-GO95HV-1^668004/00 7/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004458 | 264690948-29649-DTLSB-07_21_2025-SVCENTCO-1^06244006.0307700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004459 | 264735926-63370-DETAIL-01_15_2025-GO95HV-1^06239004.0255144 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004460 | 231911553-62219-DTLSB-04_20_2026-GRDRODHI-1^06241009.0122100 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004461 | 231974241-28670-DETAIL-05_27_2025-RISEBKSP-1^06142012.0112104 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004462 | 232232169-19759-DTLSB-07_29_2025-CUSTWIRE-1^07218001.0265001 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004463 | 232260319-84929-DETAIL-04_27_2026-SVCDEFLC-1^06142012.0147504 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004464 | 232302093-51799-DETAIL-05_28_2025-GO95HV-1^06244006.0094301 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004465 | 232342204-64579-DETAIL-09_01_2021-ENCHRW-1^06240008.0298500 | OTHER | Non-HFTD | Distribution | 2021-09-01 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004466 | 232376141-84970-DETAIL-05_27_2026-GO95HV-1^07216001.0021705 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004467 | 234124056-20860-DETAIL-05_04_2026-GO95HV-1^668004/00 1/019 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004468 | 234296577-48590-DETAIL-02_03_2025-GO95HV-1^06239004.0243942 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004469 | 234447644-55149-ADMIN-03_03_2026-POLEDERP-1^07216001.0199302 | POLE | Non-HFTD | Distribution | 2026-03-03 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004470 | 234630489-86819-ADMIN-01_15_2025-POLTOPSW-1^668005/00 1/078 | SWITCH | Non-HFTD | Transmission | 2025-01-15 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004471 | 234691302-27980-DETAIL-02_25_2025-GO95CL10-1^06240005.0019100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004472 | 234701349-93599-DTLSB-06_30_2025-BIRDDMG-1^06244007.0035100 | POLE | HFTD Tier 2 | Distribution | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004473 | 234937884-39260-DETAIL-01_22_2025-BIRDDMG-1^06239004.0255547 | POLE | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004474 | 234937884-39260-DETAIL-01_22_2025-GO95HV-1^06239004.0255547 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004475 | 235000814-37299-DETAIL-08_14_2025-GO95HV-1^06247006.0252002 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004476 | 235139953-96629-DTLSB-01_20_2026-GO95HV-1^06242009.0298003 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004477 | 235197339-4199-DETAIL-07_28_2025-GO95HV-1^06247005.0197101 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004478 | 23530956-97923-DETAIL-05_06_2025-GO95BLTC-1^06243006.0032901 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004479 | 235358823-14530-DTLSB-07_29_2025-GO95HV-1^07218001.0264601 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004480 | 235435131-59180-DETAIL-02_16_2026-GO95HV-1^06239001.0058701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004481 | 235497498-72615-DTLSB-05_28_2026-GO95MLD-2^07216001.0020300 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004482 | 302658518-19518-DTLSB-07_24_2025-CUSTWIRE-1^07218001.0260740 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004483 | 302684014-47014-DETAIL-07_24_2025-GO95HV-1^06247005.0160803 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004484 | 302886613-72499-DETAIL-06_11_2025-GO95HV-1^06245007.0268600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004485 | 303233640-73940-DTLTRT-05_14_2026-GO95HV-1^668086/00 11/005 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004486 | 303237494-54400-DETAIL-04_30_2025-GO95HV-1^06239002.0064701 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004487 | 303520773-29050-DRONE_HY-07_10_2026-DISTHDWR-1^06143014.0186200 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004488 | 303815904-32219-DTLSB-01_27_2026-BIRDDMG-1^06242009.0059205 | POLE | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004489 | 236776495-98189-DETAIL-08_18_2025-GO95HV-1^06247006.0365305 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004490 | 237038156-50470-ADMIN-10_30_2025-ABNDEQPM-1^06246001.0045000 | OTHER | Non-HFTD | Distribution | 2025-10-30 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004491 | 237234715-63999-DETAIL-09_10_2025-SVCDEFLC-1^06246006.0183203 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004492 | 237392559-11099-DETAIL-07_22_2025-CUTOUTAR-3^06247005.0058502 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2025-07-22 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004493 | 237495403-88680-DETAIL-01_30_2025-GO95MLD-1^06240004.0164604 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004494 | 237871374-70999-DETAIL-07_03_2025-GO95TCH-1^06245007.0357700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004495 | 238362205-48789-DTLSB-07_02_2025-GO95HV-1^06244006.0226311 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004496 | 238374245-31209-DETAIL-08_11_2025-POLETOP-1^06247006.0264700 | POLE | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004497 | 238568369-24973-DETAIL-08_19_2025-SVCDEFLC-1^07216001.0176805 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004498 | 238654231-71311-DETAIL-04_10_2025-SVCDEFLC-1^06241005.0041701 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004499 | 238796013-72780-DETAIL-02_17_2026-GO95HV-1^06239002.0059402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004500 | 239019686-8660-DTLTRT-04_30_2026-GO95HV-1^668004/00 6/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004501 | 239561555-19259-DETAIL-06_23_2026-GO95HV-1^07217001.0107400 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004502 | 239632110-86070-DETAIL-02_13_2025-GO95BLTC-1^06240004.0169207 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004503 | 266353439-53400-DTLTRT-07_10_2025-GUYNOINS-1^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004504 | 266353439-72682-DTLTRT-07_10_2025-GUYNOINS-3^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004505 | 266353439-72682-DTLTRT-07_10_2025-GUYNOINS-4^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004506 | 266433342-70560-DETAIL-04_29_2026-GO95HV-1^668004/00 6/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004507 | 266619910-93443-DETAIL-06_23_2026-GUYLOINS-1^07217001.0113601 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004508 | 266893449-18352-DETAIL-04_23_2025-GO95HV-1^06242006.0037705 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004509 | 266893449-18352-DETAIL-04_23_2025-GRDRODHI-1^06242006.0037705 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004510 | 159609573-78709-DETAIL-09_04_2025-GO95MLD-1^06247006.0075000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004511 | 160352225-48225-DETAIL-04_21_2026-SVCDEFLC-1^06142012.0144813 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004512 | 160541661-78900-DTLSB-06_04_2026-GUYNOINS-1^07216001.0021900 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004513 | 1607226-90589-DTLSB-04_15_2024-SVCENTCO-1^06245007.0227105 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004514 | 160946481-95999-DETAIL-09_10_2025-GO95HV-1^06246006.0184402 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004515 | 160965755-48069-DTLSB-04_16_2024-CUSTWIRE-1^06245007.0228305 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004516 | 161007053-68483-ADMIN-10_23_2025-GO95MLD-1^07218001.0086501 | OTHER | Non-HFTD | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004517 | 161007053-68483-DETAIL-09_18_2025-SVCNEUT-1^07218001.0086501 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004518 | 161106241-87939-DTLTRT-05_18_2026-GO95MLD-1^668086/00 9/009 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004519 | 24076010-28010-DETAIL-04_10_2024-CUSTWIRE-1^06147005.0164002 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004520 | 240966606-86606-DETAIL-01_22_2026-GO95MLD-1^06239004.0227200 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004521 | 241348195-96763-DETAIL-06_26_2026-GO95HV-1^07217001.0097700 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004522 | 241644564-86564-DTLTRT-07_08_2025-GO95HV-1^668087/00 13/027 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004523 | 241816352-40180-DETAIL-08_19_2025-POLISSUE-1^06246001.0315002 | POLE | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004524 | 242097783-83540-DTLTRT-06_04_2025-GUYNOINS-1^668075/00 9/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004525 | 266898047-18329-DETAIL-03_03_2026-COVCOTHR-1^06243009.0257402 | CONDUCTOR | Non-HFTD | Distribution | 2026-03-03 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004526 | 267319071-3629-DTLSB-02_04_2026-SVCTREE-1^06243009.0319002 | OTHER | HFTD Tier 2 | Distribution | 2026-02-04 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004527 | 267541223-91370-DRONE_HY-10_13_2023-CUSTWIRE-1^668033/00 2/020 | OTHER | HFTD Tier 2 | Transmission | 2023-10-13 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004528 | 268094192-37192-DETAIL-08_18_2025-GO95HV-1^06246002.0345904 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004529 | 268094192-37192-DETAIL-08_18_2025-GO95MLD-1^06246002.0345904 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004530 | 268360295-59259-DETAIL-07_22_2025-GO95HV-1^06247005.0040301 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004531 | 268362600-62210-ADMIN-11_12_2025-GO95HV-1^06146001.0313100 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004532 | 154860076-56349-DTLSB-07_14_2025-GO95HV-1^06244006.0272401 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004533 | 154889419-92490-DETAIL-08_18_2025-GO95HV-1^06246002.0346902 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004534 | 155052421-80539-DETAIL-05_15_2025-GO95HV-1^06243006.0163600 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004535 | 155159505-24849-DTLSB-06_05_2026-CLMBTRE-1^07216001.0229803 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004536 | 155224048-62865-DTLSB-06_08_2026-BIRDDMG-1^07216001.0231203 | POLE | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004537 | 15535758-55469-DETAIL-09_02_2025-GO95HV-1^06247006.0276800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004538 | 155585923-11983-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0207502 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004539 | 155730099-689-DETAIL-07_28_2025-GO95HV-1^06247005.0198201 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004540 | 155970198-83089-DETAIL-05_15_2025-GO95HV-1^06243006.0098500 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004541 | 156187952-10090-DTLTRT-05_13_2026-GO95HV-1^668085/00 3/001 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004542 | 156365975-8090-DETAIL-05_12_2026-GO95HV-1^668038/00 2/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004543 | 156578316-28349-DTLSB-07_15_2025-GO95HV-1^06244006.0271702 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004544 | 157035135-78390-DETAIL-08_25_2025-GO95HV-1^06246001.0174002 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004545 | 157150646-60100-DETAIL-08_12_2025-GO95HV-1^06246001.0194400 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004546 | 157205883-74959-DETAIL-09_15_2025-GO95HV-1^06248007.0230100 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004547 | 157217116-463-DETAIL-07_06_2026-CUSTWIRE-1^07217001.0030701 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004548 | 244257643-69398-DTLTRT-05_07_2026-GO95HV-1^668004/00 3/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004549 | 244446910-90170-DETAIL-02_25_2026-GO95HV-1^06238003.0016701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004550 | 244463208-57240-DETAIL-01_30_2025-SVCDEFLC-1^06240004.0162703 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004551 | 244467921-34762-DTLSB-06_26_2025-GO95HV-1^06244007.0107341 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004552 | 24451558-91558-DETAIL-06_04_2025-GUYHINS-1^668075/00 7/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004553 | 24451558-91558-DETAIL-06_04_2025-GUYHINS-2^668075/00 7/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004554 | 244616044-44469-DTLSB-07_08_2025-GO95HV-1^06244007.0037504 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004555 | 244643076-52880-DETAIL-01_12_2026-SVCTREE-1^06239004.0244602 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004556 | 220014836-7091-DTLTRT-05_07_2026-GO95HV-1^668038/00 6/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004557 | 220126504-56529-DETAIL-04_21_2026-GO95HV-1^06142012.0146702 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004558 | 220278255-65579-DETAIL-01_18_2023-GO95HV-1^06148004.0207701 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2028-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004559 | 220278255-65579-DETAIL-01_18_2023-GO95MLD-1^06148004.0207701 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004560 | 220533048-25299-DETAIL-06_17_2025-GO95HV-1^06248004.0299202 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004561 | 220535678-73749-DTLSB-07_03_2025-GO95TCH-1^06244007.0130801 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004562 | 220650184-1253-DETAIL-06_29_2026-GO95HV-1^07217001.0043200 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004563 | 220706633-21450-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0134000 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004564 | 220709613-34360-DTLSB-03_28_2022-GO95HV-1^06144006.0225701 | OTHER | Non-HFTD | Distribution | 2022-03-28 | 2027-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004565 | 220709613-34360-DTLSB-03_28_2022-POLETOP-1^06144006.0225701 | POLE | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004566 | 220841894-75309-DETAIL-07_30_2025-GO95HV-1^06247006.0202101 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004567 | 220884182-16182-ADMIN-10_28_2025-GO95HV-1^06246001.0118301 | OTHER | Non-HFTD | Distribution | 2025-10-28 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004568 | 220895326-48689-DETAIL-05_27_2025-GO95HV-1^06244006.0040501 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004569 | 220910124-20989-DETAIL-08_18_2025-GUYHINS-1^06246002.0345902 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004570 | 244797204-5780-DETAIL-06_09_2026-GUYHINS-1^668086/00 18/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004571 | 244797204-5780-DETAIL-06_09_2026-GUYHINS-4^668086/00 18/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004572 | 245144941-72709-AUDIT-10_01_2025-GO95MLD-1^06246006.0057700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004573 | 245692458-81690-AUDIT-04_02_2025-GRDRODHI-1^06239004.0361002 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004574 | 245939061-47709-AUDIT-10_20_2025-ANCHIDLE-1^06246008.0067802 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004575 | 246159278-63599-AUDIT-10_01_2025-ANCHIDLE-1^06247006.0278503 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004576 | 246183736-98299-DETAIL-07_28_2025-GO95BLTC-1^06247005.0317400 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004577 | 246468722-49230-DTLSB-08_13_2025-GO95HV-1^07218001.0288300 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004578 | 221919996-50260-ADMIN-11_03_2025-GO95HV-1^06246001.0222400 | OTHER | Non-HFTD | Distribution | 2025-11-03 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004579 | 222397865-30965-DETAIL-06_02_2025-GO95HV-1^06148014.0238900 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004580 | 222643931-33419-DTLSB-05_05_2026-GO95HV-1^06241009.0035200 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004581 | 222700811-52589-DTLSB-07_08_2025-GO95HV-1^06245007.0350201 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004582 | 223024576-28340-DETAIL-03_09_2026-SVCENTCO-1^06240004.0151801 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004583 | 223024576-28340-DETAIL-03_09_2026-SVCROAD-1^06240004.0151801 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004584 | 223063639-79249-ADMIN-02_19_2025-POLEREPL-1^06245007.0218802 | POLE | Non-HFTD | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004585 | 22334809-5809-DETAIL-08_19_2025-GO95HV-1^06247006.0365202 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004586 | 223438282-71520-DETAIL-03_30_2026-GO95TCH-1^06240004.0277442 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004587 | 223520914-6339-DETAIL-10_06_2025-GO95HV-1^06243007.0369801 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004588 | 223984089-12860-DETAIL-05_12_2026-GO95HV-1^668086/00 1/001 | OTHER | Non-HFTD | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004589 | 224007643-89863-DTLTRT-07_03_2025-BIRDDMG-1^668087/00 8/012 | POLE | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004590 | 224312168-85419-DETAIL-04_09_2024-CUSTWIRE-1^06147005.0254703 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004591 | 224478320-96740-DETAIL-04_01_2026-SVCTREE-1^06237005.0261104 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004592 | 224844146-98360-DTLTRT-07_03_2025-GO95HV-1^668087/00 2/012 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004593 | 282490209-1209-DTLSB-07_02_2025-GO95HV-1^06244007.0130842 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004594 | 282652220-14839-DETAIL-05_06_2025-ENCHRW-1^06243006.0285002 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004595 | 282785886-15710-DETAIL-02_04_2026-SVCDEFLC-1^06239003.0018801 | OTHER | Non-HFTD | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004596 | 282962754-47199-DTLSB-01_28_2026-BIRDDMG-1^06242009.0058601 | POLE | HFTD Tier 2 | Distribution | 2026-01-28 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004597 | 283036763-68763-DETAIL-06_18_2025-GO95HV-1^06248004.0323100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004598 | 283190070-63640-DETAIL-03_18_2025-GO95TCH-1^06238004.0012700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004599 | 283201923-83494-AUDIT-07_07_2025-GO95MLD-1^06242004.0311704 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004600 | 283201923-83494-DETAIL-05_13_2025-SVCROAD-1^06242004.0311704 | OTHER | HFTD Tier 2 | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004601 | 158434671-68543-DETAIL-07_07_2026-GO95HV-1^07217001.0164404 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004602 | 158434671-68543-DETAIL-07_07_2026-GUYHINS-1^07217001.0164404 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004603 | 158659180-10689-DETAIL-08_05_2025-GO95HV-1^06246002.0019501 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004604 | 158873931-30850-DETAIL-03_04_2026-GO95HV-1^06239003.0186702 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004605 | 158911790-37559-DETAIL-06_18_2025-GO95HV-1^06248004.0340501 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004606 | 159186369-67409-DETAIL-09_30_2025-GO95HV-1^06246009.0132201 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004607 | 159437443-25643-DETAIL-10_12_2022-GO95HV-1^668005/08 8X7/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004608 | 159437443-25643-DETAIL-10_12_2022-GUYHINS-3^668005/08 8X7/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004609 | 159437443-25643-DETAIL-10_12_2022-GUYHINS-4^668005/08 8X7/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004610 | 159531699-6818-DETAIL-06_05_2025-GO95HV-1^06245006.0190802 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004611 | 226688715-71721-DETAIL-06_05_2025-GO95HV-1^06148014.0235302 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004612 | 226688715-71721-DETAIL-06_05_2025-SVCROAD-1^06148014.0235302 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004613 | 226864681-53830-DTLTRT-05_28_2025-GO95HV-1^668075/00 9/006 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004614 | 227063638-24638-DETAIL-06_05_2025-GO95HV-1^06148014.0245600 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004615 | 200996239-40230-DTLTRT-05_27_2025-GO95HV-1^668075/00 4/004 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004616 | 201269579-77552-DTLSB-07_01_2025-GO95HV-1^06244006.0226443 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004617 | 201381003-33749-DETAIL-06_09_2025-GO95HV-1^06245006.0192601 | OTHER | Non-HFTD | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004618 | 201674374-66379-DETAIL-07_30_2025-GO95BLTC-1^06247006.0206004 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004619 | 202218321-63840-DETAIL-09_29_2025-GO95HV-1^06148001.0312500 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004620 | 202273034-53899-DETAIL-01_29_2026-GO95BLTC-1^06242009.0054500 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004621 | 202277003-95480-DETAIL-02_23_2026-XARMSPCR-1^06239002.0152201 | CROSSARM | HFTD Tier 2 | Distribution | 2026-02-23 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004622 | 202455879-96940-DTLTRT-05_19_2026-GO95HV-1^668086/00 14/002 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004623 | 202499905-10005-DTLTRT-06_30_2025-GO95HV-1^668087/01 1/001 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004624 | 202615168-95949-DTLSB-07_08_2025-GO95HV-1^06244007.0037804 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004625 | 202715873-8803-DETAIL-09_18_2025-GO95HV-1^07219001.0325102 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004626 | 202715873-8803-DETAIL-09_18_2025-GUYHINS-1^07219001.0325102 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004627 | 203621161-8029-DETAIL-05_29_2025-ABNDEQPM-1^06142012.0152900 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004628 | 203626962-52540-AUDIT-05_18_2026-GO95HV-1^668004/00 2/012 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004629 | 203691189-18540-DETAIL-09_08_2025-GO95HV-1^06147001.0322301 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004630 | 203713648-5289-DTLSB-07_16_2025-GO95HV-1^06244006.0317501 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004631 | 247712055-82940-DETAIL-02_24_2025-GUYNOINS-1^06240004.0152601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004632 | 247712055-82940-DETAIL-02_24_2025-GUYNOINS-2^06240004.0152601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004633 | 247761244-13353-DETAIL-09_22_2025-GO95HV-1^07218001.0213903 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004634 | 161430528-73549-DTLSB-07_16_2025-GO95HV-1^06244006.0317301 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004635 | 161547366-87093-DETAIL-08_19_2025-GO95HV-1^06247006.0367400 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004636 | 161861144-10250-DTLTRT-10_11_2023-CUSTWIRE-1^668010/00 9A/040 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004637 | 161910529-43919-DRONE_HY-07_15_2026-UBPBXARM-1^668036/00 4/053 | CROSSARM | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004638 | 153598218-64790-DETAIL-08_25_2025-GO95HV-1^06246001.0205701 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004639 | 153635468-95790-DTLSB-05_06_2026-GO95HV-1^06142013.0270500 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004640 | 153706861-67530-AUDIT-08_26_2025-SVCENTCO-1^07218001.0285500 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004641 | 15374645-45479-ADMIN-11_13_2025-GO95HV-1^06247008.0304000 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004642 | 153842101-77080-DETAIL-02_16_2026-GO95HV-1^06239001.0054700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004643 | 153945209-71192-DTLTRT-07_02_2025-GUYNOINS-1^668087/00 6/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004644 | 153945209-92192-DTLTRT-07_02_2025-GUYNOINS-1^668087/00 6/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004645 | 154228916-91789-DETAIL-05_27_2025-GO95HV-1^06244006.0042800 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004646 | 204789661-26140-DETAIL-09_11_2025-GUYHINS-1^06147001.0079802 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004647 | 204827843-8359-DETAIL-06_11_2025-GO95HV-1^06245007.0361500 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004648 | 205053011-55240-DETAIL-09_11_2025-GO95HV-1^07216001.0079701 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004649 | 205070328-81729-DETAIL-04_23_2025-GO95HV-1^06242006.0107600 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004650 | 205486805-11800-DETAIL-02_11_2026-GO95HV-1^06239003.0016606 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004651 | 205538474-89440-DETAIL-09_04_2025-GO95HV-1^06147001.0318000 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004652 | 205610818-10549-DTLSB-07_22_2025-GO95MLD-1^06244006.0180303 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004653 | 205813371-68540-DTLSB-05_29_2026-CLMBTRE-1^07216001.0024000 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004654 | 227954811-3180-DETAIL-02_14_2025-GO95TCH-1^06240004.0168043 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004655 | 228031291-18260-DTLTRT-04_23_2026-GO95HV-1^668004/00 2/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004656 | 228202168-73690-DETAIL-04_07_2025-GO95HV-1^06241005.0015641 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004657 | 228333109-50713-DETAIL-08_27_2025-GO95HV-1^06247006.0284903 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004658 | 228685926-14659-DTLTRT-04_30_2026-GO95HV-1^668004/00 10/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004659 | 228779154-70409-DETAIL-08_06_2025-GO95HV-1^06247006.0205800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004660 | 229078143-12180-DETAIL-02_25_2025-RISEGRD-1^06240005.0016201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004661 | 229082838-38649-DETAIL-06_10_2025-GO95HV-1^06245006.0203000 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004662 | 207300659-80229-DTLSB-05_14_2026-SVCDEFLC-1^06242009.0282308 | OTHER | Non-HFTD | Distribution | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004663 | 208050947-14579-ADMIN-10_29_2025-POLISSUE-1^06246001.0142101 | POLE | Non-HFTD | Distribution | 2025-10-29 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004664 | 208592519-95349-DTLSB-02_20_2024-SVCROAD-1^07216001.0262301 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004665 | 208681173-66850-DETAIL-01_14_2026-SVCDEFLC-2^06239004.0134101 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004666 | 208786749-74250-DETAIL-08_18_2025-GO95HV-1^06246002.0345300 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004667 | 208941056-47849-DTLSB-04_15_2024-CUSTWIRE-1^06245007.0227100 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004668 | 209152056-75929-DETAIL-05_15_2025-GO95HV-1^06142012.0119201 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004669 | 20936785-10659-DETAIL-03_12_2024-CUSTWIRE-1^06245007.0276902 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004670 | 209476776-63410-DETAIL-03_12_2025-GO95HV-1^06238004.0223540 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004671 | 209768295-33449-DTLSB-07_10_2025-CUSTWIRE-1^06244006.0342702 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004672 | 210067176-22429-DETAIL-05_15_2025-GO95HV-1^06142012.0117201 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004673 | 21019508-69508-DETAIL-08_20_2025-GO95MLD-1^07216001.0179030 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004674 | 210434788-7050-DTLSB-04_30_2026-GO95HV-1^06142013.0214900 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004675 | 210434788-7050-DTLSB-04_30_2026-GO95MLD-1^06142013.0214900 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004676 | 229236154-25499-DETAIL-07_28_2025-GO95HV-1^06247005.0303300 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004677 | 229259008-64223-DTLSB-06_24_2026-GO95HV-1^07217001.0274000 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004678 | 229457775-69529-DETAIL-04_19_2022-CUSTWIRE-1^06143012.0360002 | OTHER | Non-HFTD | Distribution | 2022-04-19 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004679 | 229457775-69529-DETAIL-04_19_2022-CUSTWIRE-2^06143012.0360002 | OTHER | Non-HFTD | Distribution | 2022-04-19 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004680 | 229489600-38070-DTLTRT-05_05_2026-GO95HV-1^668004/00 5X/001 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004681 | 229515792-3759-DETAIL-07_29_2025-GO95HV-1^06247005.0211801 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004682 | 229546515-99070-DTLSB-06_09_2026-GO95HV-1^07216001.0225003 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004683 | 211524306-10949-DTLSB-07_10_2025-GO95HV-1^06244007.0112640 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004684 | 211657805-73879-DETAIL-09_23_2025-GO95HV-1^06247004.0180601 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004685 | 21166336-20591-DETAIL-05_11_2026-GO95HV-1^668038/00 1/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004686 | 21166336-99491-DETAIL-05_11_2026-GO95HV-1^668038/00 1/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004687 | 211752588-29989-DETAIL-07_22_2025-GO95HV-1^06247005.0058603 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004688 | 212390314-53963-DETAIL-09_11_2025-GO95HV-1^06248007.0234542 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004689 | 212529081-61839-DTLTRT-06_26_2025-SVCROAD-1^668087/00 8/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004690 | 212784124-9250-DETAIL-09_05_2025-GO95TCH-1^06147001.0293000 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004691 | 213580735-10863-DETAIL-05_26_2026-GO95HV-1^07217001.0143201 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004692 | 213672614-39839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0219500 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004693 | 213699363-40680-DETAIL-02_17_2026-GO95HV-1^06239002.0059900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004694 | 214129268-58359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0321501 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004695 | 21432715-34715-DTLSB-03_25_2026-RISEBKSP-1^06242009.0047001 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004696 | 214639492-88392-DETAIL-05_05_2025-GO95HV-1^06243006.0064942 | OTHER | HFTD Tier 2 | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004697 | 214650089-35239-DTLTRT-07_09_2025-GO95HV-1^668087/00 1/021 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004698 | 182904781-97809-DETAIL-10_02_2025-GUYHINS-2^06246008.0064200 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004699 | 183221358-27139-DETAIL-05_01_2025-GO95HV-1^06243006.0295000 | OTHER | Non-HFTD | Distribution | 2025-05-01 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004700 | 183518071-33520-DTLTRT-05_18_2026-GO95HV-1^668086/00 10/011 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004701 | 18359059-12459-DETAIL-07_28_2025-GO95HV-1^06247005.0198602 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004702 | 183951946-31760-DETAIL-04_30_2026-GO95HV-1^668004/00 4/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004703 | 184061798-42820-DETAIL-08_14_2025-GO95HV-1^06246002.0264701 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004704 | 18446021-93389-DETAIL-05_07_2025-GO95TCH-1^06243006.0265000 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004705 | 184673850-34850-DETAIL-05_07_2025-GO95HV-1^06243006.0344900 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004706 | 185454514-38830-DETAIL-04_13_2026-GO95MLD-1^06236005.0332500 | OTHER | HFTD Tier 2 | Distribution | 2026-04-13 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004707 | 185570915-2915-DETAIL-06_05_2025-GO95HV-1^06148014.0245801 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004708 | 18577196-94961-DETAIL-02_24_2025-GO95MLD-1^06239004.0366708 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004709 | 185844043-77289-DTLSB-01_21_2026-BIRDDMG-1^06242009.0298110 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004710 | 186037314-28620-DETAIL-09_22_2025-GO95HV-1^06147001.0257000 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004711 | 186086823-98889-DETAIL-06_11_2025-GO95HV-1^06245007.0261703 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004712 | 186362353-25429-DTLSB-08_25_2023-CUSTWIRE-1^06243007.0180901 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004713 | 18640161-5231-DETAIL-02_27_2025-GO95MLD-1^06241005.0177801 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004714 | 186529928-66089-DETAIL-04_22_2025-GO95HV-1^06242006.0091700 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004715 | 186624512-44512-ADMIN-03_04_2026-PWRTRN-1^06239003.0182805 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004716 | 186624512-44512-DETAIL-03_04_2026-GO95HV-1^06239003.0182805 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004717 | 186723830-30-AUDIT-09_15_2025-GRDRODHI-1^06246001.0309201 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004718 | 18681393-54380-DETAIL-02_18_2026-BIRDDMG-1^06239002.0167600 | POLE | HFTD Tier 2 | Distribution | 2026-02-18 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004719 | 186864999-1899-DETAIL-09_09_2025-GO95HV-1^06246007.0144153 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004720 | 186894709-40210-DTLSB-07_29_2025-GO95HV-1^07218001.0264300 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004721 | 186979482-82530-DTLSB-07_31_2025-GO95MLD-1^07218001.0273702 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004722 | 161963586-15700-AUDIT-05_27_2026-CLRTOUCH-1^668086/00 6/015 | CONDUCTOR | Non-HFTD | Transmission | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004723 | 247761244-13353-DETAIL-09_22_2025-GUYHINS-1^07218001.0213903 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004724 | 247827586-16415-DETAIL-06_29_2026-GO95HV-1^07217001.0156401 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004725 | 248081348-28989-DETAIL-09_15_2025-GO95HV-1^06248007.0235600 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004726 | 24814924-51819-ADMIN-06_17_2026-FRGNELEC-1^668036/00 16/032 | OTHER | Non-HFTD | Transmission | 2026-06-17 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004727 | 248408075-99580-DTLSB-05_13_2024-GO95MLD-1^06245001.0292200 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004728 | 248408075-99580-DTLSB-05_13_2024-GO95MLD-2^06245001.0292200 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004729 | 18906898-64109-DTLSB-07_03_2025-GO95HV-1^06245007.0357802 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004730 | 189081571-17980-DETAIL-02_18_2026-GO95HV-1^06239001.0050602 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004731 | 152601729-12299-DETAIL-03_04_2024-CUSTWIRE-2^06147004.0019302 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004732 | 152995164-44659-DETAIL-07_28_2025-GO95HV-1^06247005.0302600 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004733 | 153086806-17490-DETAIL-05_15_2025-XARMSPCR-1^06142012.0115201 | CROSSARM | Non-HFTD | Distribution | 2025-05-15 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004734 | 1531948-54419-DETAIL-05_25_2017-CUSTWIRE-1^07116007.0152500 | OTHER | HFTD Tier 2 | Distribution | 2017-05-25 | 2020-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004735 | 153201635-54635-DETAIL-06_05_2025-GO95HV-1^06148014.0247400 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004736 | 189164795-7640-DTLSB-07_23_2025-GO95HV-1^07218001.0262803 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004737 | 189244035-51870-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 4/045 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004738 | 189368754-55233-DETAIL-09_16_2025-GO95HV-1^06247004.0082600 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004739 | 189462214-33519-DTLSB-04_06_2026-BIRDDMG-1^06241009.0155000 | POLE | Non-HFTD | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004740 | 189567883-55690-DETAIL-02_24_2026-BIRDDMG-1^06239002.0275201 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004741 | 189643611-64430-DTLTRT-05_05_2026-GO95HV-1^668004/00 6/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004742 | 189643611-76732-DTLTRT-05_05_2026-GO95HV-1^668004/00 6/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004743 | 190078701-22329-DTLSB-01_22_2026-GO95HV-1^06242009.0297600 | OTHER | Non-HFTD | Distribution | 2026-01-22 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004744 | 215683419-49852-DTLSB-07_15_2025-BIRDDMG-1^06244006.0308440 | POLE | HFTD Tier 2 | Distribution | 2025-07-15 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004745 | 21603715-64715-DETAIL-06_05_2025-GO95HV-1^06148014.0245700 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004746 | 216334474-10999-DTLSB-07_03_2025-GO95HV-1^06245007.0357604 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004747 | 216607359-62769-DTLSB-01_27_2026-BIRDDMG-1^06242009.0059200 | POLE | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004748 | 216733603-78249-DTLSB-06_30_2025-GO95HV-1^06244007.0105440 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004749 | 216798523-89909-DETAIL-08_14_2025-GO95HV-1^06247006.0257100 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004750 | 216980678-67189-DTLSB-07_16_2025-GO95HV-1^06244006.0319900 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004751 | 191967891-80630-DETAIL-09_29_2025-GO95HV-1^06148001.0310509 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004752 | 192034279-82630-ADMIN-11_12_2025-GO95HV-1^06146001.0310400 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004753 | 192061391-61080-DETAIL-02_16_2026-GO95HV-1^06239001.0052701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004754 | 192067066-69389-DTLSB-07_08_2025-GO95HV-1^06244007.0036500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004755 | 192132800-52743-DETAIL-10_09_2025-GO95HV-1^06248003.0336940 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004756 | 19254995-93940-DETAIL-09_02_2025-GO95HV-1^06246001.0176306 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004757 | 192581750-95061-DETAIL-04_17_2025-GRDRODHI-1^06242005.0349600 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004758 | 19265911-46449-DTLSB-07_09_2025-GO95MLD-1^06244007.0159701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004759 | 192688069-31930-DTLTRT-06_24_2025-GUYHINS-1^668087/00 14/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004760 | 192837860-28930-DETAIL-03_13_2024-GUYHINS-1^06147004.0190400 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004761 | 192973689-13030-DETAIL-10_01_2025-GO95HV-1^06148001.0303204 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004762 | 192977576-4419-DTLSB-03_11_2026-GO95HV-1^06242009.0238000 | OTHER | Non-HFTD | Distribution | 2026-03-11 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004763 | 193053821-26030-DTLTRT-04_27_2026-GO95HV-1^668004/00 8/004 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004764 | 193230510-43269-DETAIL-10_09_2025-ABNDEQPM-1^06248003.0272201 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004765 | 193477561-150-DETAIL-03_04_2026-GO95HV-1^06239003.0185700 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004766 | 217028468-4359-DETAIL-05_30_2024-CUSTWIRE-1^06246005.0273700 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004767 | 21709894-29260-DETAIL-04_29_2025-GO95BLTC-1^06239002.0063100 | OTHER | HFTD Tier 2 | Distribution | 2025-04-29 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004768 | 217216809-36489-DTLSB-02_04_2026-GO95HV-1^06243009.0320300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004769 | 217216809-36489-DTLSB-02_04_2026-GUYHINS-1^06243009.0320300 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004770 | 21724276-39550-ADMIN-10_30_2025-ENCHRW-1^06246001.0101700 | OTHER | Non-HFTD | Distribution | 2025-10-30 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004771 | 217264259-17750-DETAIL-05_02_2024-GO95MLD-1^06142012.0127202 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004772 | 217680717-31479-AUDIT-08_19_2025-POLISSUE-1^06246002.0139700 | POLE | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004773 | 148172488-26359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0325400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004774 | 148280494-99489-ADMIN-11_10_2025-GO95HV-1^06246010.0310201 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004775 | 148334728-23690-DTLTRT-06_24_2025-GUYHINS-1^668087/00 2/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004776 | 148638080-84139-DTLTRT-07_10_2025-GO95HV-1^668087/00 4/024 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004777 | 149007201-72743-DETAIL-07_07_2026-SVCDEFLC-1^07217001.0164403 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004778 | 149199101-32201-DTLSB-07_17_2025-GO95HV-1^06244006.0213600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004779 | 149510455-68310-DETAIL-02_26_2026-COVCOTHR-1^06238004.0114203 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004780 | 149525428-34229-DETAIL-04_22_2026-GO95HV-1^06142012.0148606 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004781 | 149643666-87390-DETAIL-08_20_2025-ABNDEQPM-1^06246001.0175404 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004782 | 167688608-35359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0328401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004783 | 167705144-93729-DTLSB-01_20_2026-CUSTWIRE-1^06242009.0299311 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004784 | 168301878-54259-DETAIL-09_02_2025-GO95HV-1^06247006.0276201 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004785 | 168392699-24110-DETAIL-08_19_2025-DISTHDWR-1^06246002.0360900 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004786 | 168464088-44390-DETAIL-01_16_2025-GO95HV-1^06239004.0256213 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004787 | 168566643-85819-DTLSB-05_11_2026-GO95HV-1^06242009.0276201 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004788 | 194414406-46179-DETAIL-10_08_2025-GO95HV-1^06148001.0194700 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004789 | 194766450-17559-DETAIL-09_23_2025-GO95HV-1^06246006.0012400 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004790 | 195764656-27079-DTLSB-03_31_2026-XARMSPCR-1^06241009.0326501 | CROSSARM | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004791 | 195846614-62779-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0219401 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004792 | 195906194-15339-DETAIL-10_06_2025-GO95HV-1^06243007.0258201 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004793 | 195916524-89889-AUDIT-06_03_2025-RISEBKSP-1^06244006.0092400 | OTHER | Non-HFTD | Distribution | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004794 | 196306326-56470-DETAIL-01_22_2025-GO95HV-1^06239004.0257700 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004795 | 150010036-79593-DETAIL-08_19_2025-GO95HV-1^06247006.0365601 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004796 | 169131606-11839-DETAIL-05_08_2025-GO95HV-1^06243006.0105302 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004797 | 169259256-55411-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135600 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004798 | 169538929-27813-DETAIL-08_26_2025-GO95HV-1^06247006.0285400 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004799 | 169565158-78158-DETAIL-09_24_2025-GO95HV-1^07218001.0233007 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004800 | 170242934-7853-DETAIL-06_25_2026-GO95HV-1^07217001.0039740 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004801 | 170901248-85340-DETAIL-02_24_2026-GO95TCH-1^06239002.0070001 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004802 | 171071001-59201-DETAIL-01_21_2025-SVCENTBK-1^06239004.0255443 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004803 | 171160494-85729-DTLSB-01_21_2026-ANCHIDLE-1^06242009.0298301 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004804 | 171162580-54769-DETAIL-06_09_2025-GO95HV-1^06245006.0302701 | OTHER | Non-HFTD | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004805 | 171644108-54009-ADMIN-10_23_2025-ABNDEQPM-1^06246011.0368200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004806 | 171646758-38758-DETAIL-09_24_2025-GO95HV-1^07218001.0232101 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004807 | 172252992-39350-DETAIL-01_31_2025-GO95HV-1^06239004.0137204 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004808 | 172458588-62189-DTLSB-07_21_2025-GO95HV-1^06244006.0308700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004809 | 196306326-56470-DRONE_HY-07_15_2026-COVCOTHR-2^06239004.0257700 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004810 | 196326643-55880-DETAIL-02_17_2026-GO95HV-1^06239002.0180600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004811 | 196431116-40830-DTLTRT-05_07_2026-GO95HV-1^668038/00 2/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004812 | 196431116-68091-DTLTRT-05_07_2026-GO95HV-1^668038/00 2/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004813 | 196469570-92149-DTLSB-07_28_2025-GO95HV-1^07218001.0269102 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004814 | 196516511-62150-DRONE_HY-06_19_2026-INSULBRK-1^06238004.0270440 | INSULATOR AND BUSHING | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004815 | 197003900-75220-DTLSB-07_29_2025-SVCDEFLC-1^07218001.0265204 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004816 | 172928788-93830-DETAIL-01_15_2025-SVCDEFLC-1^06240004.0095202 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004817 | 173168166-31660-DTLTRT-04_29_2026-GO95HV-1^668004/00 4/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004818 | 173245921-20080-DETAIL-02_16_2026-GO95HV-1^06239001.0041702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004819 | 173266247-71323-DETAIL-05_22_2026-ABNDEQPM-1^07217001.0145400 | OTHER | Non-HFTD | Distribution | 2026-05-22 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004820 | 173391813-49939-DETAIL-06_10_2026-GUYHINS-3^668086/00 12/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004821 | 173459215-22393-DETAIL-08_19_2025-GO95HV-1^06247006.0367102 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004822 | 173579694-3553-DETAIL-09_23_2025-GO95HV-1^07218001.0223801 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004823 | 174169124-71224-DTLSB-06_15_2026-GO95TCH-1^07217001.0278703 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004824 | 174177875-74700-DETAIL-02_10_2026-BIRDDMG-1^06239003.0015702 | POLE | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004825 | 174359468-48359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0321500 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004826 | 1744415-82779-DETAIL-09_23_2025-GO95HV-1^06247004.0181700 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004827 | 174539148-46019-DTLSB-04_01_2026-BIRDDMG-1^06241009.0328100 | POLE | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004828 | 174667439-7919-DTLSB-05_05_2026-GO95HV-1^06241009.0255000 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004829 | 174841996-45939-DTLSB-07_02_2025-SVCROAD-1^06244006.0226142 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004830 | 175104144-37144-DTLTRT-07_10_2025-GO95HV-1^668087/00 7/028 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004831 | 175104144-37144-DTLTRT-07_10_2025-POLEDERP-1^668087/00 7/028 | POLE | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004832 | 231129513-46140-DTLTRT-05_29_2025-GO95HV-1^668075/00 16/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004833 | 231242223-31759-DETAIL-07_29_2025-GO95HV-1^06247005.0217801 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004834 | 2312795-4289-DETAIL-09_04_2025-GO95HV-1^06247006.0186600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004835 | 231286013-27480-DETAIL-02_23_2026-BIRDDMG-1^06239002.0225601 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004836 | 231367279-71040-DETAIL-04_14_2026-GO95HV-1^06237004.0079001 | OTHER | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004837 | 231492523-28099-DTLSB-02_09_2026-GRDRODHI-1^06243009.0330800 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004838 | 23174166-89689-DETAIL-05_08_2025-GO95HV-1^06243006.0103301 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004839 | 231880283-47553-DETAIL-06_23_2026-GO95HV-1^07217001.0105401 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004840 | 176117124-74220-DETAIL-09_08_2025-GO95HV-1^06147001.0331301 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004841 | 176186294-53789-DTLSB-01_27_2026-GUYHINS-1^06242009.0055201 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004842 | 176378673-773-DETAIL-03_16_2026-SVCDEFLC-1^06240004.0156402 | OTHER | HFTD Tier 3 | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004843 | 176695264-72469-DETAIL-05_08_2025-GO95HV-1^06243006.0036302 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004844 | 176742552-55850-DETAIL-02_11_2026-SVCDEFLC-1^06239003.0016300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004845 | 176742552-55850-DETAIL-03_20_2025-SVCENTBK-1^06239003.0016300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004846 | 176785411-12620-DETAIL-10_06_2025-GO95TCH-1^06148001.0310807 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004847 | 177028614-1714-DETAIL-05_27_2026-GO95TCH-1^07217001.0147001 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004848 | 177463683-29673-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135501 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004849 | 17758041-65259-DTLSB-07_08_2025-GO95HV-1^06245007.0353000 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004850 | 178232302-97560-DETAIL-04_29_2026-GO95HV-1^668004/00 8/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004851 | 17883981-49259-DTLSB-07_08_2025-GO95HV-1^06245007.0350203 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004852 | 178877019-46639-DTLSB-07_17_2025-GO95HV-1^06244006.0195800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004853 | 17900632-69459-DETAIL-04_29_2026-GO95HV-1^668004/00 4/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004854 | 179075425-80933-DETAIL-09_23_2025-GO95HV-1^06247004.0077540 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004855 | 150787624-70289-DTLSB-01_22_2026-GO95MLD-1^06242009.0294000 | OTHER | HFTD Tier 2 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004856 | 150846428-62659-DTLSB-08_12_2025-GO95HV-1^07217001.0027201 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004857 | 150941128-80699-DETAIL-03_19_2026-SVCDEFLC-1^06242009.0068704 | OTHER | HFTD Tier 2 | Distribution | 2026-03-19 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004858 | 15102179-59029-DETAIL-05_21_2018-CUSTWIRE-2^06243009.0023501 | OTHER | Non-HFTD | Distribution | 2018-05-21 | 2021-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004859 | 15102179-59029-DETAIL-06_06_2023-CUSTWIRE-1^06243009.0023501 | OTHER | Non-HFTD | Distribution | 2023-06-06 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004860 | 151061113-37099-DETAIL-10_13_2025-GO95HV-1^06246010.0238900 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004861 | 151077045-88045-DETAIL-06_18_2025-GO95CL10-1^06248004.0310604 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004862 | 151485198-83750-DETAIL-02_02_2026-SVCNEUT-1^06239002.0060300 | OTHER | Non-HFTD | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004863 | 151949669-12679-DTLSB-02_04_2026-GO95MLD-1^06243009.0324302 | OTHER | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004864 | 152154020-9901-DETAIL-01_21_2025-GO95HV-1^06239004.0255447 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004865 | 15244509-63649-DTLSB-04_15_2024-CUSTWIRE-1^06245007.0223204 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004866 | 152601729-12299-DETAIL-03_04_2024-CUSTWIRE-1^06147004.0019302 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004867 | 152639909-64039-DTLTRT-05_19_2026-GO95HV-1^668086/00 7/001 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004868 | 152927399-61390-DETAIL-09_08_2025-GO95HV-1^06147001.0324200 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004869 | 198234893-19630-DETAIL-10_25_2024-SVCENTBK-1^07216001.0208609 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004870 | 198390481-45830-DETAIL-03_24_2026-COVCOTHR-1^06240004.0209900 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004871 | 198698893-7059-DTLSB-09_30_2024-CUSTWIRE-1^06245007.0231501 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004872 | 198881225-54063-DETAIL-07_07_2026-GO95HV-1^07217001.0096000 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004873 | 199038388-81750-DETAIL-02_03_2026-GO95HV-1^06239003.0019305 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004874 | 199091993-70140-DTLTRT-05_29_2025-GO95HV-1^668075/00 15/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004875 | 199144894-65259-DETAIL-03_20_2023-ABNDEQPM-1^07118004.0020501 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2028-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004876 | 153945209-79890-DTLTRT-07_02_2025-GUYNOINS-2^668087/00 6/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004877 | 153945209-92192-DTLTRT-07_02_2025-GUYNOINS-2^668087/00 6/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004878 | 154063535-17535-DETAIL-05_29_2025-XARMSPCR-1^06147014.0010701 | CROSSARM | Non-HFTD | Distribution | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004879 | 154293967-18209-DTLSB-10_03_2024-CUSTWIRE-1^06245006.0337900 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004880 | 154293967-18209-DTLSB-10_03_2024-GO95MLD-1^06245006.0337900 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004881 | 154804785-57849-DTLSB-07_17_2025-GO95HV-1^06244007.0112501 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004882 | 155186333-85590-DETAIL-09_05_2025-GO95HV-1^06147001.0202900 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004883 | 155233604-30690-DETAIL-03_02_2026-GO95HV-1^06239003.0251602 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004884 | 15535167-23189-DETAIL-08_11_2025-BIRDDMG-1^06246002.0168802 | POLE | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004885 | 15537879-5189-AUDIT-02_09_2026-SVCROAD-1^06243009.0303402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004886 | 155634271-73380-DETAIL-02_16_2026-GO95HV-1^06239001.0047701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004887 | 155651285-27149-DETAIL-07_30_2025-GO95HV-1^06247005.0025101 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004888 | 155663863-33441-DTLSB-08_02_2022-CUSTWIRE-1^06242005.0081201 | OTHER | HFTD Tier 2 | Distribution | 2022-08-02 | 2025-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004889 | 155730099-689-DETAIL-07_28_2025-XARMSPCR-1^06247005.0198201 | CROSSARM | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004890 | 180276755-16489-DETAIL-07_28_2025-SVCROAD-1^06247005.0313200 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004891 | 18064999-96343-DETAIL-08_27_2025-GO95HV-1^06247006.0160200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004892 | 180870571-77020-DTLSB-06_03_2026-BIRDDMG-1^07216001.0025201 | POLE | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004893 | 181024594-61120-DETAIL-09_08_2025-GO95HV-1^06147001.0329701 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004894 | 181032828-68730-DETAIL-01_22_2026-GO95MLD-1^06240003.0314801 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004895 | 181435208-91059-DETAIL-07_29_2025-GO95HV-1^06247005.0269500 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004896 | 181537503-85109-DETAIL-08_21_2025-SVCENTCO-1^06247006.0251804 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004897 | 181728078-22270-DTLSB-06_04_2026-GO95HV-1^07216001.0142500 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004898 | 157072944-65490-DTLSB-06_09_2026-CUSTWIRE-1^07216001.0227200 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004899 | 157217116-463-DETAIL-07_06_2026-GO95HV-1^07217001.0030701 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004900 | 15738710-76110-DTLSB-06_16_2026-CLMBTRE-1^07217001.0355903 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004901 | 157890750-15500-DETAIL-06_04_2025-GO95HV-1^06142012.0107600 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004902 | 157962979-81768-DETAIL-08_13_2025-GO95BLTC-1^06247006.0253200 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004903 | 157962979-81768-DETAIL-08_13_2025-GO95HV-1^06247006.0253200 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004904 | 158277278-89829-DETAIL-09_18_2025-GUYHINS-1^07218001.0055706 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004905 | 158824544-36253-DETAIL-09_24_2025-GO95HV-1^07218001.0224102 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004906 | 158873931-30850-ADMIN-03_04_2026-PWRTRN-1^06239003.0186702 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004907 | 159033908-69550-DETAIL-02_10_2026-BIRDDMG-1^06239003.0016403 | POLE | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004908 | 159437443-25643-DETAIL-10_12_2022-GUYHINS-1^668005/08 8X7/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004909 | 146303403-64403-DETAIL-05_24_2023-CUSTWIRE-1^06245006.0352201 | OTHER | Non-HFTD | Distribution | 2023-05-24 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004910 | 146324798-15523-AUDIT-10_29_2025-GO95HV-1^07218001.0177804 | OTHER | Non-HFTD | Distribution | 2025-10-29 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004911 | 146845493-51840-DTLTRT-05_29_2025-GO95HV-1^668075/00 7/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004912 | 147036640-30880-ADMIN-10_22_2025-GRDRODHI-1^07216001.0020700 | OTHER | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004913 | 181896196-55659-DETAIL-07_28_2025-GO95HV-1^06247005.0317100 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004914 | 181896196-55659-DETAIL-07_28_2025-GRDRODHI-1^06247005.0317100 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004915 | 181896196-55659-DETAIL-07_28_2025-GRDRODHI-2^06247005.0317100 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004916 | 182596712-58962-DTLTRT-04_28_2026-GO95HV-1^668004/00 8/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004917 | 182741571-57920-DETAIL-09_10_2025-GO95HV-1^06147001.0082401 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004918 | 182904781-97809-DETAIL-10_02_2025-GO95BLTC-1^06246008.0064200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004919 | 182904781-97809-DETAIL-10_02_2025-GO95TCH-1^06246008.0064200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004920 | 150228653-69-DETAIL-09_18_2025-GO95HV-1^06248007.0267201 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004921 | 160190415-73129-DETAIL-04_27_2026-GO95HV-1^06142012.0144403 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004922 | 160237205-49959-DETAIL-09_16_2025-GO95HV-1^06247004.0182241 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004923 | 160437266-27449-DTLSB-07_09_2025-GO95HV-1^06244006.0276600 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004924 | 160510383-13383-ADMIN-11_04_2025-GUYNOINS-1^06246001.0227480 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-11-04 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004925 | 160510383-13383-ADMIN-11_04_2025-GUYNOINS-2^06246001.0227480 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-11-04 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004926 | 160541661-78900-DTLSB-06_04_2026-GUYLOINS-1^07216001.0021900 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004927 | 160930039-82100-DETAIL-08_18_2025-GO95HV-1^06246002.0345200 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004928 | 161007053-68483-DETAIL-09_18_2025-GO95TCH-1^07218001.0086501 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004929 | 161063409-66100-DETAIL-08_21_2025-GO95HV-1^06246001.0204301 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004930 | 161694071-83600-DETAIL-10_08_2025-COPLLEAN-1^06148001.0321300 | POLE | Non-HFTD | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004931 | 161883449-29449-DTLSB-06_16_2026-CUSTWIRE-1^07217001.0354702 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004932 | 161941956-31283-DTLSB-07_01_2025-GO95HV-1^06244006.0226442 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004933 | 162123516-3699-DETAIL-05_27_2025-GO95HV-1^06244006.0058900 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004934 | 162168306-68800-AUDIT-09_15_2025-CLMBHAZ-1^06246001.0175201 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004935 | 162168306-68800-AUDIT-09_15_2025-CLRTOPOL-1^06246001.0175201 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004936 | 141561426-13370-DETAIL-01_16_2025-GO95HV-1^06239004.0257603 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004937 | 141642151-93151-DETAIL-02_05_2025-GO95HV-1^06240004.0165201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004938 | 135510969-26080-DETAIL-04_24_2024-XARMSPCR-1^06145001.0089902 | CROSSARM | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004939 | 135591361-31189-DETAIL-05_05_2025-GUYHINS-1^06243006.0347100 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-05 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004940 | 135713206-41519-DTLSB-07_08_2026-GO95HV-1^06242009.0240002 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004941 | 135787739-83919-ADMIN-10_28_2022-UBPBXARM-1^668036/00 5/053 | CROSSARM | Non-HFTD | Transmission | 2022-10-28 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004942 | 135787739-83919-DRONE_HY-07_15_2026-INSULDMG-1^668036/00 5/053 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004943 | 136905062-61750-DETAIL-02_11_2026-SVCDEFLC-1^06239003.0016103 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004944 | 137199745-1329-DETAIL-05_19_2025-GO95HV-1^06142012.0016400 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004945 | 13725265-94332-DTLSB-07_10_2025-GO95HV-1^06244006.0342203 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004946 | 137277828-36949-DTLSB-07_09_2025-ANCHIDLE-1^06244007.0036700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004947 | 137479929-75909-DETAIL-08_14_2025-GO95HV-1^06247006.0259100 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004948 | 137492991-87069-DTLTRT-04_28_2026-GO95HV-1^668004/00 6/008 | OTHER | HFTD Tier 2 | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004949 | 137492991-87070-DTLTRT-04_28_2026-GO95HV-1^668004/00 6/008 | OTHER | HFTD Tier 2 | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004950 | 13750978-3889-AUDIT-07_28_2025-GO95HV-1^06244006.0304301 | OTHER | HFTD Tier 2 | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004951 | 137569896-50170-DRONE_HY-06_19_2026-XARMSPCR-1^06238004.0289301 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004952 | 137800035-24609-DETAIL-08_28_2025-GO95HV-1^06247006.0192601 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004953 | 137814819-62599-DTLSB-02_04_2026-BIRDDMG-1^06243009.0321300 | POLE | HFTD Tier 2 | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004954 | 13860699-28383-DETAIL-08_19_2025-GO95HV-1^07216001.0176802 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004955 | 138690186-2186-DETAIL-09_09_2025-GO95HV-1^07218001.0177403 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004956 | 138842373-88309-DETAIL-07_31_2025-GO95HV-1^06247006.0200201 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004957 | 138895278-51980-ADMIN-11_04_2025-GO95HV-1^06246001.0267301 | OTHER | Non-HFTD | Distribution | 2025-11-04 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004958 | 13925471-13709-DETAIL-09_08_2025-GO95HV-1^06246006.0058801 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004959 | 199250528-14370-DETAIL-01_23_2023-CUSTWIRE-1^06240004.0080206 | OTHER | HFTD Tier 2 | Distribution | 2023-01-23 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004960 | 199373818-38799-DETAIL-03_28_2024-CUSTWIRE-1^06147005.0155901 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004961 | 199411421-79811-DETAIL-01_10_2022-CUSTWIRE-1^06241005.0226801 | OTHER | HFTD Tier 3 | Distribution | 2022-01-10 | 2025-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004962 | 199418445-39445-ADMIN-11_06_2025-GO95HV-1^06246001.0118100 | OTHER | Non-HFTD | Distribution | 2025-11-06 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004963 | 199478083-89340-DETAIL-09_09_2025-GO95HV-1^06147001.0170200 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004964 | 199721076-71039-DETAIL-05_20_2025-GO95HV-1^06243006.0090201 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004965 | 14135775-38429-DTLSB-05_04_2026-GUYHINS-1^06142013.0052201 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004966 | 141426653-31033-DETAIL-06_02_2025-CUSTWIRE-1^06245007.0368300 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004967 | 141498613-96250-DETAIL-02_04_2025-SVCROAD-1^06239004.0135149 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004968 | 141854931-22430-DTLTRT-05_28_2025-CUTOUTAR-1^668075/00 9/007 | LIGHTNING ARRESTER | Non-HFTD | Transmission | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004969 | 141854931-22430-DTLTRT-05_28_2025-XARMSPCR-1^668075/00 9/007 | CROSSARM | Non-HFTD | Transmission | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004970 | 141956299-54473-DETAIL-09_22_2025-GO95HV-1^06248007.0244800 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004971 | 141989533-71562-DTLSB-07_01_2025-GO95HV-1^06244007.0106440 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004972 | 14217658-27649-DTLSB-07_16_2025-GO95HV-1^06244006.0290100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004973 | 14220482-519-DTLSB-05_19_2026-XARMSPCR-1^06240008.0130800 | CROSSARM | Non-HFTD | Distribution | 2026-05-19 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004974 | 142274919-93889-DTLSB-02_09_2026-GO95MLD-1^06243010.0364201 | OTHER | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004975 | 142337708-87952-DTLSB-07_21_2025-GO95HV-1^06244006.0230702 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004976 | 142720176-88379-DETAIL-09_02_2025-CLRTOUCH-1^06246001.0176401 | CONDUCTOR | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004977 | 142881971-23150-DETAIL-03_11_2025-GO95HV-1^06238004.0274804 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004978 | 142955515-53589-DTLSB-07_02_2025-SVCNEUT-1^06244006.0226102 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004979 | 143023006-88880-DETAIL-09_02_2025-GO95HV-1^06246001.0176402 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004980 | 143124519-2980-DTLSB-05_07_2024-CONDFRAY-1^06245002.0248700 | CONDUCTOR | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004981 | 164613096-75659-DETAIL-07_28_2025-GO95HV-1^06247005.0317101 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004982 | 16471375-53289-DETAIL-10_22_2024-GO95HV-1^07216001.0207901 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004983 | 16471375-53289-DETAIL-10_22_2024-GO95MLD-1^07216001.0207901 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004984 | 164897303-80309-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0209700 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004985 | 164918120-40870-DETAIL-02_04_2025-GO95BLTC-1^06240004.0166704 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004986 | 164919671-78639-DETAIL-05_07_2025-GO95HV-1^06243006.0029600 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004987 | 165003138-97749-DTLSB-07_16_2025-GO95HV-1^06244006.0292800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004988 | 143778886-28791-DTLTRT-05_07_2026-GO95HV-1^668038/00 5/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004989 | 143781945-21933-DETAIL-09_23_2025-GO95HV-1^06247004.0078542 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004990 | 144047621-13350-DETAIL-01_21_2026-GO95MLD-1^06239004.0124900 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004991 | 144255523-95523-DETAIL-06_10_2025-GUYHINS-1^668075/00 14/033 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004992 | 144255523-95523-DETAIL-06_10_2025-GUYHINS-2^668075/00 14/033 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004993 | 144388003-63909-DETAIL-08_14_2025-GO95HV-1^06247006.0256102 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004994 | 144701990-99249-DTLSB-06_25_2025-GO95HV-1^06244007.0104704 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004995 | 14479946-58050-DTLSB-07_23_2025-SVCDEFLC-1^07218001.0263805 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004996 | 145039073-61669-DETAIL-03_10_2026-POLETOP-1^668041/00 18/025 | POLE | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120004997 | 141748764-50440-DTLTRT-05_30_2025-GO95HV-1^668075/00 2/011 | OTHER | Non-HFTD | Transmission | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004998 | 141842756-13989-DTLSB-07_09_2025-GO95HV-1^06244006.0276603 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120004999 | 141854931-22430-DTLTRT-05_28_2025-CUTOUTAR-2^668075/00 9/007 | LIGHTNING ARRESTER | Non-HFTD | Transmission | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005000 | 141854931-22430-DTLTRT-05_28_2025-GO95HV-1^668075/00 9/007 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005001 | 141881974-81453-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0097900 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005002 | 141929976-47400-DETAIL-04_08_2026-GO95HV-1^06240002.0316301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005003 | 14220482-519-DTLSB-05_19_2026-GO95HV-1^06240008.0130800 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005004 | 165135903-72410-DETAIL-09_05_2025-GO95HV-1^06147001.0203502 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005005 | 165440653-1729-DETAIL-05_01_2025-GO95HV-1^06242006.0020700 | OTHER | Non-HFTD | Distribution | 2025-05-01 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005006 | 165949091-78343-DETAIL-07_06_2026-GO95HV-1^07217001.0163701 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005007 | 166147223-91910-DETAIL-09_10_2025-GO95HV-1^06147001.0185900 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005008 | 166658412-92550-DETAIL-03_02_2026-COVCOTHR-1^06238004.0027103 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005009 | 166693874-15710-DETAIL-03_18_2025-GO95HV-1^06238004.0156302 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005010 | 166926568-3310-DTLTRT-06_23_2025-PWRTRN-1^668087/00 4/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005011 | 167141175-79899-DETAIL-09_09_2025-GO95HV-1^06246007.0226851 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005012 | 115631728-19679-ADMIN-10_07_2025-COVCOTHR-1^668001/00 11/045 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005013 | 115746756-71499-DETAIL-05_27_2025-GO95HV-1^06244006.0056601 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005014 | 115801066-86849-DTLSB-07_09_2025-GO95HV-1^06244007.0140701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005015 | 116035368-30629-DTLSB-01_29_2026-BIRDDMG-1^06242009.0054901 | POLE | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005016 | 116167998-46550-DETAIL-03_20_2025-GRDRODHI-1^06239003.0016304 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005017 | 116471243-42260-ADMIN-12_04_2025-POLEREPL-1^06243001.0119000 | POLE | Non-HFTD | Distribution | 2025-12-04 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005018 | 117193739-64470-DRONE_HY-06_30_2026-COVCOTHR-1^06240004.0169541 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005019 | 117341734-92422-DETAIL-10_15_2025-ABNDEQPM-1^06246011.0181800 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005020 | 117451143-82359-DTLTRT-04_22_2026-GO95HV-1^668004/02 11/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005021 | 117643863-32150-DETAIL-01_23_2025-GO95HV-1^06239004.0256806 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005022 | 117643863-32150-DETAIL-01_23_2025-GO95MLD-1^06239004.0256806 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005023 | 117643863-32150-DETAIL-01_23_2025-GO95TCH-1^06239004.0256806 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005024 | 117826615-37940-DETAIL-02_25_2025-SVCDEFLC-1^06240004.0151501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005025 | 117993921-83499-DTLSB-10_16_2025-GRDRODHI-1^06247001.0347000 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005026 | 118024659-34160-DTLTRT-06_24_2025-GO95HV-1^668087/00 6/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005027 | 118098534-9534-DETAIL-08_12_2025-GO95BLTC-1^06246002.0254202 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005028 | 145137222-49222-DETAIL-07_24_2025-GO95HV-1^06247005.0149301 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005029 | 145350716-45550-DETAIL-07_28_2025-POLEREPL-1^668018/00 6/001 | POLE | HFTD Tier 2 | Transmission | 2025-07-28 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005030 | 145456119-97080-DETAIL-10_01_2025-GO95HV-1^06148001.0302206 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005031 | 14559258-6530-DETAIL-01_26_2026-GO95MLD-1^06240003.0304401 | OTHER | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005032 | 14571663-96109-DETAIL-07_31_2025-GO95HV-1^06247006.0204102 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005033 | 143541853-24959-DETAIL-09_15_2025-GO95HV-1^06248007.0230202 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005034 | 143694-36860-DETAIL-01_16_2025-GO95HV-1^06239004.0257608 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005035 | 143778886-77791-DTLTRT-05_07_2026-BIRDDMG-1^668038/00 5/053 | POLE | HFTD Tier 2 | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005036 | 119463052-10083-AUDIT-10_13_2025-GO95HV-1^07216001.0175005 | OTHER | Non-HFTD | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005037 | 119626361-81732-DETAIL-04_02_2025-GO95BLTC-1^06241005.0117706 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005038 | 119626361-81732-DETAIL-04_02_2025-GUYHINS-1^06241005.0117706 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005039 | 119703866-77879-DETAIL-05_15_2025-GO95HV-1^06243006.0096200 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005040 | 119719140-49540-DETAIL-06_05_2025-GO95MLD-1^668075/00 3/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005041 | 120396513-52499-DETAIL-06_11_2025-GO95HV-1^06245007.0269601 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005042 | 120398563-47469-DTLSB-07_22_2025-GO95HV-1^06244006.0195440 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005043 | 120483368-41089-DETAIL-04_30_2025-ABNDEQPM-1^06242006.0108100 | OTHER | Non-HFTD | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005044 | 120561605-89899-DTLSB-07_14_2025-GO95HV-1^06244007.0143504 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005045 | 12095198-89582-DTLTRT-07_02_2025-BIRDDMG-1^668087/00 4/019 | POLE | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005046 | 121236415-34289-DTLSB-07_09_2025-GO95HV-1^06244006.0345503 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005047 | 121351489-81160-DETAIL-06_09_2026-GUYHINS-1^668086/00 2X/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005048 | 121351489-81160-DETAIL-06_09_2026-GUYHINS-3^668086/00 2X/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005049 | 121644823-84823-DETAIL-06_10_2025-GO95HV-1^668075/00 7/032 | OTHER | Non-HFTD | Transmission | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005050 | 121644823-84823-DETAIL-06_10_2025-GUYHINS-1^668075/00 7/032 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005051 | 121717501-19501-DETAIL-05_28_2025-GO95HV-1^06142012.0154901 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005052 | 143778886-77791-DTLTRT-05_07_2026-GO95HV-1^668038/00 5/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005053 | 143900639-10359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0330401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005054 | 144047621-13350-DETAIL-01_21_2026-COVCOTHR-1^06239004.0124900 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005055 | 144073769-60473-DETAIL-09_22_2025-GO95HV-1^06248007.0243601 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005056 | 144473750-270-DETAIL-02_19_2026-GO95HV-1^06239002.0015600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005057 | 144750656-96499-DETAIL-05_27_2025-GO95HV-1^06244006.0057600 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005058 | 145123474-76474-DETAIL-04_25_2024-CUSTWIRE-1^06142016.0160000 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005059 | 123478275-85468-DETAIL-07_29_2025-GO95HV-1^06247005.0260200 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005060 | 123557303-74249-DTLSB-07_21_2025-GO95HV-1^06244006.0256901 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005061 | 123880653-9249-DTLSB-06_30_2025-GO95HV-1^06244007.0104541 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005062 | 124264496-45371-DETAIL-04_10_2025-GO95TCH-1^06241005.0011744 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005063 | 124573260-48769-DETAIL-07_31_2024-CUSTWIRE-1^06244005.0333900 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005064 | 124607216-81698-DETAIL-02_03_2025-SVCENTBK-1^06239004.0244945 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005065 | 124642163-8469-DTLSB-07_21_2025-GO95HV-1^06244006.0307642 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005066 | 12465844-46309-DETAIL-07_30_2025-GO95HV-1^06247006.0202100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005067 | 124768478-24949-DETAIL-08_25_2025-GO95HV-1^07216001.0160900 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005068 | 124804878-75069-DTLSB-03_16_2026-GO95HV-1^06242009.0139000 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005069 | 124857228-75349-DETAIL-05_04_2023-CUSTWIRE-1^06245006.0135700 | OTHER | Non-HFTD | Distribution | 2023-05-04 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005070 | 124912453-63009-DETAIL-08_12_2025-GO95BLTC-1^06247006.0252602 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005071 | 124964811-56000-DTLSB-06_08_2026-GO95HV-1^07216001.0231101 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005072 | 125337651-13470-DTLTRT-05_20_2026-GO95HV-1^668086/00 11/010 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005073 | 125606219-63369-DTLTRT-05_22_2025-GO95HV-1^668075/00 11/003 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005074 | 151485198-83750-ADMIN-02_09_2026-GRDBROKE-1^06239002.0060300 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005075 | 151514353-12809-DETAIL-09_09_2021-CUSTWIRE-2^06148004.0354108 | OTHER | Non-HFTD | Distribution | 2021-09-09 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005076 | 151514353-12809-DETAIL-09_09_2021-CUSTWIRE-3^06148004.0354108 | OTHER | Non-HFTD | Distribution | 2021-09-09 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005077 | 151607240-98353-DETAIL-08_21_2025-GO95HV-1^06247006.0258900 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005078 | 151896809-26790-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0106501 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005079 | 152025947-44099-DETAIL-04_09_2024-INSULDMG-1^06147005.0213001 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005080 | 128435021-35570-DTLTRT-04_23_2026-GO95HV-1^668004/00 1/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005081 | 128435021-3922-DTLTRT-04_23_2026-GO95HV-1^668004/00 1/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005082 | 128459689-54790-DETAIL-01_15_2025-GO95HV-1^06239004.0256102 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005083 | 128493862-60083-DETAIL-08_20_2025-GO95MLD-1^07216001.0176009 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005084 | 128604798-90690-DETAIL-01_21_2025-GO95MLD-1^06239004.0256301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005085 | 128775773-23553-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0039302 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005086 | 129066414-84159-DETAIL-08_18_2025-GO95HV-1^06247006.0364500 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005087 | 129070686-19770-DTLSB-05_05_2026-GO95HV-1^06142013.0220603 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005088 | 129070686-19770-DTLSB-05_05_2026-GUYHINS-1^06142013.0220603 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005089 | 129726294-97840-DETAIL-03_25_2026-COVCOTHR-1^06240004.0218704 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005090 | 129787909-86340-DETAIL-03_11_2026-BIRDDMG-1^06238004.0011300 | POLE | HFTD Tier 2 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005091 | 129787909-86340-DETAIL-03_11_2026-GO95BLTC-1^06238004.0011300 | OTHER | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005092 | 129842653-57561-DETAIL-04_23_2025-GO95HV-1^06242006.0039200 | OTHER | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005093 | 129934151-98270-DTLSB-06_03_2026-GO95HV-1^07216001.0026000 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005094 | 130275043-85043-DETAIL-06_16_2025-BIRDDMG-1^668075/00 1/042 | POLE | HFTD Tier 2 | Transmission | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005095 | 130372678-92570-DETAIL-09_11_2025-GO95HV-1^06146001.0090901 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005096 | 12930260-94579-AUDIT-10_15_2024-CUSTWIRE-1^06245007.0016201 | OTHER | HFTD Tier 2 | Distribution | 2024-10-15 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005097 | 12930260-94579-DTLSB-09_03_2024-CUSTWIRE-1^06245007.0016201 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005098 | 129367895-31970-DTLTRT-06_26_2025-GO95HV-1^668087/00 10/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005099 | 129375461-12391-ENHANCED-01_26_2026-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2026-01-26 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005100 | 129375461-90391-ENHANCED-01_26_2026-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2026-01-26 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005101 | 129375461-95770-ENHANCED-01_26_2026-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2026-01-26 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005102 | 12945151-9479-DTLSB-08_27_2024-CUSTWIRE-1^06245007.0118900 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005103 | 129684470-92270-DETAIL-02_19_2026-GO95HV-1^06239002.0018601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005104 | 130391479-42889-DETAIL-08_13_2025-GO95HV-1^06246002.0368800 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005105 | 130480111-94759-DTLSB-07_29_2025-GO95HV-1^07218001.0264102 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005106 | 130763831-88389-DETAIL-07_30_2025-ABNDEQPM-1^06247006.0205004 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005107 | 130763831-88389-DETAIL-07_30_2025-GO95MLD-1^06247006.0205004 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005108 | 130874195-11770-DETAIL-06_26_2025-GUYHINS-2^668087/00 15/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005109 | 146467364-23532-DETAIL-10_14_2025-GO95BLTC-1^06246012.0135900 | OTHER | HFTD Tier 2 | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005110 | 146881085-43600-DETAIL-02_12_2026-GO95HV-1^06239003.0244001 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005111 | 14715359-54489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0174101 | POLE | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005112 | 147196131-569-DTLSB-06_26_2025-SVCENTCO-1^06244007.0108501 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005113 | 147241803-97089-DTLSB-01_20_2026-GO95HV-1^06242009.0299205 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005114 | 147566294-61139-DETAIL-04_23_2026-GO95HV-1^06142012.0144202 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005115 | 147841166-14390-DETAIL-08_20_2025-GO95HV-1^06246001.0175312 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005116 | 147915656-48390-DTLSB-05_04_2026-GO95HV-1^06142013.0175401 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005117 | 133893845-74769-DTLSB-04_23_2026-GO95HV-1^06241009.0222800 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005118 | 134097890-69822-DTLTRT-05_14_2026-GO95HV-1^668086/00 2/006 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005119 | 134252546-35461-DETAIL-02_24_2025-GO95MLD-1^06239004.0366902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005120 | 134267240-95170-DETAIL-02_19_2026-GO95HV-1^06239002.0014602 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005121 | 134399161-28659-DETAIL-06_18_2025-GO95HV-1^06248004.0312802 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005122 | 134429198-96952-DTLSB-07_02_2025-GO95HV-1^06244006.0228700 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005123 | 134516505-92393-DETAIL-08_14_2025-SVCDEFLC-1^06247006.0363800 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005124 | 13473439-92669-DETAIL-08_26_2025-GO95TCH-1^06247006.0286600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005125 | 13473439-92669-DETAIL-08_26_2025-SVCDEFLC-1^06247006.0286600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005126 | 135246418-32658-DTLSB-02_15_2024-GO95MLD-1^07216001.0263000 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005127 | 135510969-26080-DETAIL-04_24_2024-GRDRODHI-1^06145001.0089902 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005128 | 135591361-31189-DETAIL-05_05_2025-GO95HV-1^06243006.0347100 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005129 | 135591361-31189-DETAIL-05_05_2025-GO95HV-2^06243006.0347100 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005130 | 135677450-27180-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 5A/046 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005131 | 135928169-10259-DTLTRT-05_07_2026-GO95HV-1^668004/00 17/024 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005132 | 131510663-9199-DTLSB-06_26_2025-GO95HV-1^06244007.0107241 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005133 | 131557263-53639-DETAIL-05_28_2025-GO95HV-1^06244006.0108900 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005134 | 131676811-97070-DETAIL-06_10_2026-GO95TCH-1^668086/00 7A/009 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005135 | 131808236-90759-DTLTRT-04_30_2026-GO95HV-1^668004/00 3/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005136 | 131808236-90760-DTLTRT-04_30_2026-GO95HV-1^668004/00 3/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005137 | 131995668-61119-DRONE_HY-06_19_2026-GUYHINS-1^668036/00 2/019 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005138 | 132045652-72350-DETAIL-01_26_2026-COVCOTHR-1^06239004.0139000 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005139 | 132045652-72350-DETAIL-01_26_2026-COVCOTHR-2^06239004.0139000 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005140 | 107766890-3869-DETAIL-10_08_2025-GUYHINS-1^06246008.0043200 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005141 | 10795136-16329-DETAIL-05_12_2025-GO95HV-1^06142012.0014803 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005142 | 108501435-3435-DETAIL-05_30_2025-GO95HV-1^06147014.0120300 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005143 | 108539842-50520-DETAIL-03_30_2026-SVCROAD-1^06240004.0272041 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005144 | 108882491-75274-ADMIN-09_02_2025-SVCENTCO-1^06246002.0264502 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005145 | 108883776-53259-DETAIL-07_21_2025-GO95HV-1^06247005.0115500 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005146 | 109195667-37789-DETAIL-06_04_2025-GO95HV-1^06245006.0299600 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005147 | 109284521-90823-DETAIL-06_17_2025-GO95BLTC-1^06248004.0349342 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005148 | 10944384-75859-DTLTRT-04_22_2026-GO95HV-1^668004/02 6/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005149 | 109464194-93633-DETAIL-09_16_2025-GO95HV-1^06247004.0046940 | OTHER | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005150 | 137814819-62599-DTLSB-02_04_2026-GO95BLTC-1^06243009.0321300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005151 | 137950573-76009-DETAIL-08_12_2025-GO95HV-1^06247006.0252300 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005152 | 138078619-55252-DETAIL-04_07_2025-GO95CL10-1^06241005.0028249 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005153 | 138149858-60889-DTLSB-08_09_2023-CUSTWIRE-1^06243009.0150200 | OTHER | HFTD Tier 2 | Distribution | 2023-08-09 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005154 | 138169644-14649-DTLTRT-05_28_2025-GO95HV-1^668075/00 4/008 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005155 | 132045652-72350-DETAIL-01_26_2026-GO95HV-1^06239004.0139000 | OTHER | HFTD Tier 3 | Distribution | 2026-01-26 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005156 | 132197649-91269-ADMIN-03_25_2025-POLEDERP-1^668002/00 11/066 | POLE | HFTD Tier 2 | Transmission | 2025-03-25 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005157 | 132527053-19659-DETAIL-07_29_2025-GO95HV-1^06247005.0217800 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005158 | 132544988-77988-DETAIL-09_24_2025-GO95HV-1^07218001.0226201 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005159 | 132565820-33568-DETAIL-02_27_2025-GO95BLTC-1^06241005.0173601 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005160 | 133032124-64790-DETAIL-02_12_2026-GO95HV-1^06239003.0255901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005161 | 133054263-21298-ADMIN-01_14_2026-GO95HV-1^668041/00 4/025 | OTHER | Non-HFTD | Transmission | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005162 | 133060636-78473-AUDIT-07_01_2026-SVCNEUT-1^07217001.0276007 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005163 | 140765661-25433-DETAIL-05_19_2025-GO95HV-1^06243006.0228502 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005164 | 140776968-65959-DTLTRT-05_04_2026-GO95HV-1^668004/00 7/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005165 | 14089106-60206-DETAIL-01_22_2026-GO95MLD-1^06239004.0269801 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005166 | 140898174-2880-DETAIL-09_02_2025-GO95HV-1^06246001.0176500 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005167 | 141245101-59069-DTLTRT-05_12_2026-GO95HV-1^668004/00 7/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005168 | 141245101-59070-DTLTRT-05_12_2026-GO95HV-1^668004/00 7/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005169 | 14128983-14109-DETAIL-08_20_2025-POLETOP-1^06247006.0257700 | POLE | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005170 | 109486623-64080-DETAIL-02_11_2025-GUYHINS-1^06240004.0357000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005171 | 109655897-12650-DETAIL-08_11_2025-GO95HV-1^06246002.0227600 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005172 | 109876451-28843-DTLTRT-06_02_2026-GO95HV-1^07216001.0117701 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005173 | 109876451-28843-DTLTRT-06_02_2026-INSULDMG-1^07216001.0117701 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005174 | 110146151-1050-DTLSB-05_06_2026-GO95HV-1^06142013.0347800 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005175 | 110398278-15913-DETAIL-08_27_2025-GO95HV-1^06247006.0285703 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005176 | 110933854-450-DTLTRT-05_13_2026-GO95MLD-1^668085/00 15/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005177 | 110941628-94959-DTLSB-08_14_2025-GO95HV-1^07218001.0351200 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005178 | 111132885-63363-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0035100 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005179 | 110268568-65050-DETAIL-09_02_2025-GO95HV-1^06246001.0200700 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005180 | 110612072-1530-DTLSB-07_31_2025-GO95HV-1^07218001.0274603 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005181 | 110619611-31932-DETAIL-04_02_2025-SVCROAD-1^06241005.0117405 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005182 | 110645487-35250-DETAIL-08_06_2025-ABNDEQPM-1^06246002.0144401 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005183 | 110665082-99899-DETAIL-10_16_2025-GO95BLTC-1^06246011.0278800 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005184 | 110694084-80209-DETAIL-09_24_2025-GO95HV-1^06246009.0098401 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005185 | 110816661-87329-DETAIL-06_08_2023-CUSTWIRE-1^06244009.0327900 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005186 | 106156986-53640-DETAIL-02_15_2023-CUSTWIRE-1^06247002.0232602 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005187 | 106489846-36209-DETAIL-08_11_2025-GO95HV-1^06247006.0268203 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005188 | 106539253-63230-DTLSB-07_24_2025-GO95HV-1^07218001.0264811 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005189 | 106683335-66329-DETAIL-05_13_2025-GRDRODHI-1^06142012.0016601 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005190 | 106794763-24249-DTLSB-10_07_2024-GO95STUB-1^06245007.0211300 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005191 | 106957748-56749-DTLSB-07_16_2025-GO95HV-1^06244006.0292701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005192 | 107037933-49921-DRONE_HY-06_19_2026-IRSPOTOH-1^06239004.0364702 | OTHER | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005193 | 10718888-12260-DETAIL-11_18_2024-BIRDDMG-1^668014/00 3/059 | POLE | HFTD Tier 2 | Transmission | 2024-11-18 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005194 | 10718888-91370-DETAIL-11_18_2024-BIRDDMG-1^668014/00 3/059 | POLE | HFTD Tier 2 | Transmission | 2024-11-18 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005195 | 107308245-72199-DTLSB-07_09_2025-GO95HV-1^06244006.0345604 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005196 | 111072953-25719-DETAIL-03_24_2026-COVCOTHR-1^06242009.0039503 | CONDUCTOR | Non-HFTD | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005197 | 111072953-25719-DETAIL-03_24_2026-COVCOTHR-2^06242009.0039503 | CONDUCTOR | Non-HFTD | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005198 | 111347893-31080-DETAIL-02_24_2026-BIRDDMG-1^06239002.0180700 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005199 | 11165033-87680-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0168302 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005200 | 148334728-23690-DTLTRT-06_24_2025-GUYHINS-2^668087/00 2/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005201 | 148351984-83353-DETAIL-05_21_2026-SVCNEUT-1^07217001.0144900 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005202 | 148410093-45690-DTLTRT-05_13_2026-BIRDDMG-1^668085/00 15X/001 | POLE | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005203 | 148487690-3639-DETAIL-07_06_2026-GO95HV-1^07217001.0118700 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005204 | 148498036-14000-DETAIL-02_05_2026-SVCDEFLC-1^06239003.0017601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005205 | 148553020-40140-DETAIL-04_01_2026-SVCTREE-1^06237005.0261103 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005206 | 148718471-4909-DTLSB-05_02_2024-CUSTWIRE-1^06245007.0229903 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005207 | 148718471-4909-DTLSB-05_02_2024-CUSTWIRE-2^06245007.0229903 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005208 | 112292551-35180-DETAIL-02_06_2025-SVCROAD-1^06240004.0166301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005209 | 112438300-76683-DETAIL-08_19_2025-GO95HV-1^07216001.0176705 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005210 | 112507891-6059-DETAIL-07_29_2025-GO95HV-1^06247006.0208002 | OTHER | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005211 | 112628879-2289-DTLSB-07_01_2025-GO95HV-1^06244007.0132600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005212 | 112783358-16979-ADMIN-05_12_2026-BIRDDMG-1^06248004.0356401 | POLE | Non-HFTD | Distribution | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005213 | 113100536-12536-DETAIL-10_13_2025-GO95BLTC-1^06246012.0121100 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005214 | 113639191-77739-DETAIL-05_14_2025-GO95HV-1^06243006.0274100 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005215 | 114367658-55479-DETAIL-06_16_2025-GO95HV-1^06248004.0363040 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005216 | 114424606-44606-DETAIL-01_29_2025-GO95HV-1^06239004.0229100 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005217 | 114632073-94260-ADMIN-10_20_2025-CONDFRAY-1^06247001.0364601 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005218 | 114635508-12759-DETAIL-09_04_2025-GO95HV-1^07216001.0099401 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005219 | 114650121-92523-DETAIL-06_17_2024-CUSTWIRE-1^06246006.0136701 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005220 | 114692641-29339-DTLSB-05_28_2026-CUSTWIRE-1^07216001.0022301 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005221 | 114720133-86799-DETAIL-10_01_2025-GO95BLTC-1^06246009.0136800 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005222 | 114720133-86799-DETAIL-10_01_2025-GUYHINS-1^06246009.0136800 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005223 | 114720133-86799-DETAIL-10_01_2025-GUYHINS-2^06246009.0136800 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005224 | 112307191-20829-DETAIL-05_02_2022-CUSTWIRE-1^06143012.0244100 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005225 | 112438300-76683-DETAIL-08_19_2025-GO95MLD-1^07216001.0176705 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005226 | 112582728-46640-DETAIL-03_02_2026-GO95HV-1^06239003.0137100 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005227 | 112797151-46880-AUDIT-03_16_2026-ABNDEQPM-1^06239001.0067602 | OTHER | HFTD Tier 2 | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005228 | 113114868-9670-DRONE_HY-06_30_2026-IRSPOTOH-1^06240004.0169400 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005229 | 113308191-1930-DETAIL-03_05_2025-CUSTWIRE-1^06240004.0202500 | OTHER | HFTD Tier 3 | Distribution | 2025-03-05 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005230 | 113668216-69889-AUDIT-05_18_2026-SECFRAY-1^06241009.0326702 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-05-18 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005231 | 116659740-5559-DETAIL-08_05_2025-GO95HV-1^06247005.0205101 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005232 | 1167223-4090-DETAIL-02_24_2026-GO95HV-1^06239002.0224100 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005233 | 117163212-14799-DETAIL-07_30_2025-CUSTWIRE-1^06247005.0179807 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005234 | 117163212-14799-DETAIL-07_30_2025-ENCHRW-1^06247005.0179807 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005235 | 117163212-14799-DETAIL-07_30_2025-GO95HV-1^06247005.0179807 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005236 | 117193739-64470-DRONE_HY-06_30_2026-COVCOTHR-2^06240004.0169541 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005237 | 117276223-75660-DETAIL-09_09_2025-GO95HV-1^06147001.0199902 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005238 | 118178095-80339-DTLTRT-06_26_2025-GO95HV-1^668087/00 3/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005239 | 118323303-47530-DTLSB-07_31_2025-GO95MLD-1^07218001.0274405 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005240 | 118383060-28309-DETAIL-08_06_2025-GO95HV-1^06247006.0203801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005241 | 118557788-77788-DETAIL-09_08_2025-GO95HV-1^06247007.0018000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005242 | 107374393-3783-DETAIL-08_14_2024-CUSTWIRE-1^06246004.0182041 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005243 | 107502521-95621-DETAIL-10_06_2025-GO95HV-1^06243007.0254400 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005244 | 107522547-15240-DETAIL-08_05_2025-SVCROAD-1^06246002.0137000 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005245 | 107604624-38509-DETAIL-09_10_2025-GO95HV-1^06246006.0190500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005246 | 1136980-80180-DETAIL-02_27_2025-GUYHINS-1^06240004.0233602 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005247 | 113761518-35640-DETAIL-03_02_2026-GO95HV-1^06239003.0137102 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005248 | 113932165-64850-DTLSB-06_10_2026-CLMBTRE-1^07216001.0229000 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005249 | 114196178-35359-DETAIL-07_22_2025-GO95HV-1^06247005.0059501 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005250 | 114419263-21669-DETAIL-03_10_2026-XARMSPCR-1^668041/00 17/025 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005251 | 11444282-42899-DETAIL-07_22_2025-GO95HV-1^06247005.0175300 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005252 | 114635508-12759-DETAIL-09_04_2025-GO95CL10-1^07216001.0099401 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005253 | 114705824-2789-DETAIL-08_20_2025-GO95HV-1^06247006.0254701 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005254 | 119757361-19809-DETAIL-09_03_2025-SVCENTCO-1^06247006.0210502 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005255 | 119955552-57450-DETAIL-01_15_2026-GO95MLD-1^06239004.0135201 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005256 | 120515037-21968-DETAIL-08_20_2025-GO95HV-1^06247006.0256702 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005257 | 120875958-54743-AUDIT-06_20_2024-SVCWIND-1^06245007.0222840 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005258 | 12095198-42969-DTLTRT-07_02_2025-BIRDDMG-1^668087/00 4/019 | POLE | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005259 | 121351489-81160-DETAIL-06_09_2026-GUYHINS-2^668086/00 2X/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005260 | 121423185-5185-DETAIL-06_05_2025-GO95HV-1^06148014.0239401 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005261 | 121434068-24959-DETAIL-07_31_2025-GO95HV-1^06247005.0263102 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005262 | 100069014-37239-DETAIL-06_10_2026-GUYHINS-6^668086/00 8/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005263 | 100069014-37239-DTLTRT-05_20_2026-GO95HV-1^668086/00 8/013 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005264 | 10041910-97369-DETAIL-05_05_2026-COPLLEAN-1^668004/00 2X/001 | POLE | HFTD Tier 2 | Transmission | 2026-05-05 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005265 | 10055074-67074-DTLTRT-07_07_2025-GO95HV-1^668087/00 15/027 | OTHER | Non-HFTD | Transmission | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005266 | 101287851-23440-DTLSB-10_16_2025-GRDRODHI-1^06247001.0349400 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005267 | 101461629-61091-DTLTRT-07_10_2025-POLEDERP-1^668087/00 3/020 | POLE | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005268 | 101467320-92139-DTLTRT-07_10_2025-GO95HV-1^668087/00 12/024 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005269 | 101509608-80613-DETAIL-09_02_2025-GO95HV-1^06247006.0276500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005270 | 121644823-84823-DETAIL-06_10_2025-GUYHINS-2^668075/00 7/032 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005271 | 121805343-60750-DETAIL-01_14_2026-SVCTREE-1^06239004.0244950 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005272 | 121805343-60750-DETAIL-02_04_2025-GO95MLD-1^06239004.0244950 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005273 | 122372964-83760-DETAIL-05_14_2025-GO95HV-1^06142012.0117405 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005274 | 1225156-93869-DTLSB-07_03_2025-GO95HV-1^06245007.0358700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005275 | 122575831-1050-DETAIL-04_10_2025-BIRDDMG-1^06239003.0188500 | POLE | HFTD Tier 3 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005276 | 12304680-14970-AUDIT-02_26_2025-GO95BLTC-1^06240004.0165505 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005277 | 123119499-97769-DTLTRT-05_22_2025-GO95HV-1^668075/00 3/002 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005278 | 101461629-61091-DTLTRT-07_10_2025-GUYNOINS-2^668087/00 3/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005279 | 101573294-17710-DETAIL-03_13_2025-GO95HV-1^06238004.0156200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005280 | 1019036-91371-DRONE_HY-07_01_2026-COVCOTHR-1^06239004.0367702 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005281 | 101925621-67620-DETAIL-03_11_2026-COVCOTHR-1^06240004.0274600 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005282 | 102168170-80898-DTLTRT-05_21_2026-GO95MLD-1^668086/00 9/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005283 | 102336670-99520-DETAIL-01_21_2026-COVCOTHR-1^06240004.0343904 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005284 | 102345329-91659-DETAIL-08_05_2025-GO95HV-1^06247005.0206702 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005285 | 102616278-6253-DTLSB-06_04_2026-GO95HV-1^07216001.0146501 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005286 | 102644680-91240-DTLTRT-05_14_2026-GO95HV-1^668086/00 1/006 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005287 | 102877192-21880-DETAIL-02_12_2025-SVCENTBK-1^06240004.0167209 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005288 | 102985826-15310-DETAIL-03_13_2025-GO95HV-1^06238004.0224901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005289 | 102985826-15310-DETAIL-11_10_2022-CUSTWIRE-1^06238004.0224901 | OTHER | HFTD Tier 2 | Distribution | 2022-11-10 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005290 | 103047737-57340-DTLTRT-06_23_2025-BIRDDMG-1^668087/00 10/001 | POLE | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005291 | 103281898-16859-DTLTRT-05_04_2026-GO95HV-1^668004/00 3/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005292 | 134803976-13019-DETAIL-03_25_2024-CUSTWIRE-1^06147005.0144900 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005293 | 135131663-73870-DTLTRT-05_20_2026-GO95MLD-1^668086/00 15/012 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005294 | 135246418-32658-DTLSB-02_15_2024-GO95HV-1^07216001.0263000 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005295 | 135510969-26080-DETAIL-04_24_2024-GO95MLD-1^06145001.0089902 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005296 | 14135775-38429-DTLSB-05_04_2026-GO95HV-1^06142013.0052201 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005297 | 14145623-57109-DETAIL-08_21_2025-GO95HV-1^06247006.0252900 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005298 | 141466418-57259-DETAIL-05_27_2026-SVCROAD-1^07217001.0149402 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005299 | 104669533-64190-DRONE_HY-06_30_2026-IRSPOTOH-1^06240004.0150540 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005300 | 104840984-12831-DETAIL-04_08_2025-GO95TCH-1^06241005.0012603 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005301 | 104915082-30453-DETAIL-07_02_2026-GUYNOINS-1^07217001.0221503 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005302 | 104932878-10533-DTLSB-06_15_2026-GO95HV-1^07217001.0277702 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005303 | 105045545-9545-DETAIL-09_15_2025-GO95HV-1^07219001.0323403 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005304 | 105272909-65329-DETAIL-06_04_2025-SVCROAD-1^06142012.0104400 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005305 | 105400513-62513-DTLSB-06_08_2026-RISEGRD-1^07216001.0228203 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005306 | 105400513-62513-DTLSB-06_08_2026-RISEGRD-3^07216001.0228203 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005307 | 105475179-53140-DETAIL-08_18_2025-GO95HV-1^06246002.0345400 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005308 | 105488238-66274-DETAIL-10_21_2024-INSULDMG-1^07216001.0209341 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005309 | 105488238-66274-DETAIL-10_21_2024-SVCNEUT-1^07216001.0209341 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005310 | 105541898-57079-DETAIL-06_17_2025-GO95HV-1^06248004.0299105 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005311 | 105720300-83300-DETAIL-05_28_2025-GO95HV-1^06142012.0037200 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005312 | 101964805-8089-DETAIL-01_29_2026-SVCDEFLC-1^06242009.0050501 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005313 | 102168170-80898-AUDIT-05_27_2026-GUYHINS-1^668086/00 9/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005314 | 102168170-80898-DTLTRT-05_21_2026-GO95BLTC-1^668086/00 9/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005315 | 10005839-65879-DTLSB-07_02_2025-GO95HV-1^06244007.0136302 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005316 | 100069014-37239-DETAIL-06_10_2026-GO95MLD-1^668086/00 8/013 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005317 | 100069014-37239-DETAIL-06_10_2026-GUYHINS-5^668086/00 8/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005318 | 100083980-18543-DETAIL-06_25_2026-GUYLOINS-1^07217001.0118300 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005319 | 100100869-33840-DETAIL-09_30_2025-GO95HV-1^06148001.0301013 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005320 | 10055074-67074-DTLTRT-07_07_2025-GO95MLD-1^668087/00 15/027 | OTHER | Non-HFTD | Transmission | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005321 | 100600716-26849-DTLSB-07_10_2025-GO95HV-1^06244007.0113540 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005322 | 10068454-79753-DETAIL-05_21_2026-GO95HV-1^07217001.0144901 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005323 | 125786632-39632-DETAIL-02_18_2025-SVCENTCO-1^06239004.0362405 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005324 | 126171276-9989-DTLSB-07_14_2025-GO95HV-1^06244006.0271603 | OTHER | Non-HFTD | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005325 | 126209801-7870-DETAIL-10_06_2025-GO95CL10-1^06148001.0310703 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005326 | 126209801-7870-DETAIL-10_06_2025-GO95HV-1^06148001.0310703 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005327 | 126416800-14479-DETAIL-08_25_2025-GO95HV-1^06247006.0280841 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005328 | 126419615-80715-DETAIL-06_05_2025-GO95HV-1^06148014.0245604 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005329 | 127014490-33870-DETAIL-09_11_2025-GO95HV-1^06147001.0050900 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005330 | 1270221-80380-DETAIL-02_02_2026-COVCOTHR-1^06240004.0316703 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005331 | 10576374-68839-DETAIL-05_06_2025-GO95HV-1^06243006.0032502 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005332 | 105853219-32059-DTLTRT-05_06_2026-GO95HV-1^668004/00 11/021 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005333 | 105853219-32060-DTLTRT-05_06_2026-GO95HV-1^668004/00 11/021 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005334 | 106453223-62743-DTLSB-08_11_2025-SVCDEFLC-1^07218001.0250100 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005335 | 103372542-82542-DETAIL-05_14_2025-GO95HV-1^06142012.0117406 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005336 | 103551370-13659-DETAIL-06_17_2024-CUSTWIRE-1^06246006.0135701 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005337 | 103769905-2005-DETAIL-06_05_2025-GO95HV-1^06148014.0241401 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005338 | 104258932-1850-DETAIL-03_20_2025-SVCROAD-1^06239003.0018101 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005339 | 104669533-64190-DETAIL-03_04_2025-GO95TCH-1^06240004.0150540 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005340 | 106909203-2729-DTLSB-01_20_2026-GO95HV-1^06242009.0299200 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005341 | 107308245-72199-DTLSB-07_09_2025-GO95MLD-1^06244006.0345604 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005342 | 107408886-77859-DTLTRT-04_22_2026-GO95HV-1^668004/02 8/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005343 | 107522547-15240-DETAIL-08_05_2025-GO95MLD-1^06246002.0137000 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005344 | 107661963-24080-DETAIL-02_23_2026-GO95HV-1^06239002.0153102 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005345 | 107766890-3869-DETAIL-10_08_2025-ABNDEQPM-1^06246008.0043200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005346 | 1019036-91371-DRONE_HY-07_01_2026-POLETOP-1^06239004.0367702 | POLE | HFTD Tier 2 | Distribution | 2026-07-01 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005347 | 100743301-96080-DRONE_HY-06_30_2026-IRSPOTOH-1^06240004.0166645 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005348 | 100773788-15140-DETAIL-09_09_2025-GO95HV-1^06146001.0091901 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005349 | 100776096-6409-DETAIL-08_21_2025-ABNDEQPM-1^06247006.0269802 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005350 | 10120037-49-DTLSB-10_03_2024-GO95HV-1^06245006.0339800 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005351 | 101287851-23440-DTLSB-10_16_2025-GRDRODHI-2^06247001.0349400 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005352 | 101332684-4684-DTLTRT-07_07_2025-GO95HV-1^668087/00 14/029 | OTHER | Non-HFTD | Transmission | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005353 | 1270221-80380-DETAIL-02_02_2026-COVCOTHR-2^06240004.0316703 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005354 | 1270221-80380-DETAIL-02_02_2026-COVCOTHR-3^06240004.0316703 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005355 | 127119696-76579-DTLSB-07_10_2025-GO95HV-1^06244007.0113000 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005356 | 127276801-46970-DTLTRT-04_23_2026-GO95HV-1^668004/00 2/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005357 | 127276801-46970-DTLTRT-04_23_2026-GUYNOINS-1^668004/00 2/003 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005358 | 12745213-59323-DETAIL-06_18_2025-GO95HV-1^06248004.0339340 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005359 | 127476374-28232-AUDIT-03_04_2025-GUYHINS-1^06241005.0120104 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005360 | 127476374-28232-AUDIT-03_04_2025-GUYHINS-2^06241005.0120104 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005361 | 109285758-41089-DETAIL-08_18_2025-GO95HV-1^06246002.0264200 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005362 | 109464194-93633-DETAIL-09_16_2025-GO95BLTC-1^06247004.0046940 | OTHER | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005363 | 109486623-64080-DETAIL-03_31_2026-COVCOTHR-1^06240004.0357000 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005364 | 109776619-74299-DETAIL-09_22_2025-GO95HV-1^06248007.0243102 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005365 | 109919809-94809-ADMIN-02_13_2017-CUSTWIRE-1^06146005.0097800 | OTHER | Non-HFTD | Distribution | 2017-02-13 | 2020-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005366 | 110200872-88049-DTLSB-07_16_2025-GO95HV-1^06244006.0235002 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005367 | 110268568-65050-DETAIL-09_02_2025-ABNDEQPM-1^06246001.0200700 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005368 | 863018653-43802-DETAIL-03_10_2026-XARMSPCR-1^668041/00 9/026 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005369 | 863206945-7600-DETAIL-04_08_2026-GO95HV-1^06240002.0325300 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005370 | 863346766-62709-ADMIN-10_20_2025-CUSTWIRE-1^06246012.0119300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005371 | 863346766-62709-ADMIN-10_20_2025-GO95MLD-1^06246012.0119300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005372 | 863436319-78319-DETAIL-04_20_2026-GO95HV-1^06142012.0143903 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005373 | 863562511-46702-DTLTRT-05_20_2026-GO95HV-1^668086/00 15/010 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005374 | 863633731-89702-DETAIL-09_29_2025-GO95HV-1^06148001.0310403 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005375 | 86377801-87922-DTLTRT-04_23_2026-GO95HV-1^668004/00 3/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005376 | 869981596-84270-DETAIL-01_16_2025-GO95TCH-1^06239004.0256212 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005377 | 870022438-14222-DETAIL-09_30_2025-GO95HV-1^06148001.0300303 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005378 | 870022438-14222-DETAIL-09_30_2025-GRDRODHI-1^06148001.0300303 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005379 | 234484843-86970-DETAIL-09_09_2025-GO95HV-1^06147001.0200500 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005380 | 23530956-97923-DETAIL-05_06_2025-GO95HV-1^06243006.0032901 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005381 | 235358823-14530-DTLSB-07_29_2025-SVCDEFLC-1^07218001.0264601 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005382 | 235418874-25239-DETAIL-04_04_2023-CUSTWIRE-1^06143013.0241000 | OTHER | HFTD Tier 2 | Distribution | 2023-04-04 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005383 | 855393076-17660-DETAIL-04_30_2026-GO95HV-1^668004/00 4/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005384 | 855595268-29340-DETAIL-04_22_2025-GO95HV-1^06240003.0077200 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005385 | 855684354-13090-DETAIL-02_12_2026-SVCTREE-1^06239003.0362601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005386 | 855873323-50169-DETAIL-10_16_2025-GO95HV-1^06246011.0279702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005387 | 855873323-50169-DETAIL-10_16_2025-GRDRODHI-1^06246011.0279702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005388 | 85632844-23590-DETAIL-02_12_2026-GO95HV-1^06239003.0252401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005389 | 856534384-16384-DTLTRT-06_30_2025-GUYNOINS-2^668087/00 14/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005390 | 856889528-49359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0320502 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005391 | 857141723-74889-ADMIN-11_07_2025-GO95HV-1^06246001.0324900 | OTHER | Non-HFTD | Distribution | 2025-11-07 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005392 | 857358471-75999-DETAIL-09_10_2025-GO95HV-1^06246006.0184200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005393 | 857588622-58792-DETAIL-05_07_2025-GO95HV-1^06243006.0064640 | OTHER | HFTD Tier 2 | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005394 | 857683636-99489-DETAIL-10_08_2025-GO95HV-1^06148001.0204100 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005395 | 857765688-16688-AUDIT-07_14_2025-GO95HV-1^06243006.0068940 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005396 | 857765688-16688-AUDIT-07_14_2025-GO95MLD-1^06243006.0068940 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005397 | 857904463-12182-DTLTRT-05_13_2026-GO95MLD-1^668085/00 15/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005398 | 85806164-91153-DETAIL-06_29_2026-GO95HV-1^07217001.0047200 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005399 | 85817709-28929-DETAIL-06_03_2025-GO95HV-1^06148014.0248805 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005400 | 858197380-73670-DETAIL-02_17_2026-GO95HV-1^06239002.0093201 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005401 | 858302294-29690-DETAIL-01_28_2026-GO95CL10-1^06239002.0066903 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005402 | 858333796-75294-DETAIL-06_02_2025-SVCROAD-1^06148014.0362704 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005403 | 858338512-75780-DETAIL-02_05_2025-GO95CL10-1^06240004.0167240 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005404 | 858881008-69639-DTLTRT-06_24_2025-GUYHINS-1^668087/00 17/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005405 | 858957670-24559-DETAIL-08_06_2025-GO95HV-1^06247005.0207100 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005406 | 859119960-89282-DTLSB-05_28_2026-GO95HV-1^07216001.0021201 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005407 | 859660680-81192-DTLTRT-05_05_2026-GO95HV-1^668004/00 1/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005408 | 859680606-54600-DETAIL-02_10_2026-BIRDDMG-1^06239003.0016507 | POLE | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005409 | 859700531-46080-DETAIL-02_18_2026-GO95HV-1^06239002.0042300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005410 | 859748184-4290-DETAIL-02_12_2026-SVCDEFLC-1^06239003.0252100 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005411 | 859998601-11092-DTLSB-06_04_2026-GO95HV-1^07216001.0021902 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005412 | 86003703-96703-DTLSB-07_09_2025-GO95HV-1^06244006.0345501 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005413 | 86047139-90479-DETAIL-10_14_2025-GUYHINS-1^06148001.0273100 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005414 | 860713746-3339-DTLTRT-05_21_2026-GO95MLD-1^668086/00 10/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005415 | 22771533-26979-ADMIN-01_23_2017-CUSTWIRE-1^06145006.0223500 | OTHER | Non-HFTD | Distribution | 2017-01-23 | 2020-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005416 | 228031291-81622-DTLTRT-04_23_2026-GO95HV-1^668004/00 2/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005417 | 228144764-78863-DETAIL-09_15_2025-GO95HV-1^06248007.0234440 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005418 | 228211915-11339-DTLTRT-06_26_2025-GO95HV-1^668087/00 19/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005419 | 228545872-86039-DETAIL-05_20_2025-GO95HV-1^06243006.0075200 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005420 | 228626555-68600-DETAIL-02_10_2026-GO95HV-1^06239003.0016713 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005421 | 228668352-62903-DETAIL-05_05_2025-GO95HV-1^06243006.0348840 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005422 | 228685926-14660-DTLTRT-04_30_2026-GO95HV-1^668004/00 10/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005423 | 228954591-92099-DETAIL-05_25_2023-GO95HV-1^07117007.0227600 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2028-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005424 | 229167281-38380-DETAIL-02_16_2026-GO95HV-1^06239001.0048800 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005425 | 229367055-46479-ADMIN-11_13_2025-GO95HV-1^06247008.0190201 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005426 | 229546515-99070-DTLSB-06_09_2026-SVCNEUT-1^07216001.0225003 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005427 | 229581429-90170-DETAIL-08_07_2025-GO95HV-2^06246002.0257900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005428 | 229651246-35429-DETAIL-05_13_2025-GO95HV-1^06142012.0012401 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005429 | 229894193-92183-DETAIL-08_18_2025-GO95HV-1^06247006.0366700 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005430 | 860896379-70259-DETAIL-05_30_2024-CUSTWIRE-1^06246005.0340300 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005431 | 861781803-27402-DETAIL-09_09_2025-GO95HV-1^06147001.0199700 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005432 | 861808898-28402-DETAIL-09_02_2025-GO95HV-1^06246001.0200900 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005433 | 861809327-32039-DETAIL-04_22_2026-GO95HV-1^06142012.0144601 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005434 | 861892288-44550-DETAIL-04_22_2025-GO95HV-1^06240003.0053200 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005435 | 230129915-43890-DTLTRT-10_16_2023-CUSTWIRE-1^668010/00 6X/008 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005436 | 230202363-72589-DETAIL-05_28_2025-ABNDEQPM-1^06244006.0095000 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005437 | 230599853-93529-DTLSB-03_10_2026-DISTHDWR-1^06243009.0346100 | CONNECTION DEVICE | Non-HFTD | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005438 | 230921108-31659-DTLSB-08_12_2025-GO95HV-1^07217001.0027500 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005439 | 231154699-66739-DTLTRT-06_25_2025-GO95HV-1^668087/00 4/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005440 | 86211698-41169-DETAIL-09_22_2025-GO95HV-1^06248007.0365800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005441 | 862460663-10380-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0165701 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005442 | 862493796-15796-DETAIL-06_18_2025-GUYHINS-1^668075/00 19/045 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005443 | 862529152-73302-DETAIL-08_19_2025-GO95HV-1^06246001.0315003 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005444 | 8628289-21443-DETAIL-06_23_2026-GO95HV-1^07217001.0114000 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005445 | 863919544-66489-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0225201 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005446 | 864187060-7839-DETAIL-02_25_2025-SVCDEFLC-1^06240004.0150410 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005447 | 864187060-7839-DETAIL-03_16_2026-SVCTREE-1^06240004.0150410 | OTHER | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005448 | 864378998-10702-DTLSB-05_05_2026-DISTHDWR-1^06142013.0175402 | CONNECTION DEVICE | Non-HFTD | Distribution | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005449 | 864407276-39659-DETAIL-07_30_2025-GO95HV-1^06247005.0319403 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005450 | 864486056-28056-DETAIL-05_29_2025-GO95HV-1^06148014.0360100 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005451 | 864538408-4902-ADMIN-11_12_2025-GO95HV-1^06246001.0334000 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005452 | 864745751-70709-DETAIL-09_08_2025-GO95HV-1^06246006.0056502 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005453 | 864784663-59422-DETAIL-05_30_2025-GO95HV-1^06244006.0142241 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005454 | 864969910-13139-DTLTRT-07_10_2025-GO95HV-1^668087/00 11/024 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005455 | 864977424-10929-DETAIL-04_13_2022-CUSTWIRE-1^06142012.0133610 | OTHER | Non-HFTD | Distribution | 2022-04-13 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005456 | 865192810-93810-DETAIL-06_03_2025-GO95HV-1^06148015.0312201 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005457 | 865512585-16099-DETAIL-06_04_2025-GO95HV-1^06245006.0280500 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005458 | 865811228-11379-DTLSB-05_11_2026-GO95HV-1^06242009.0286203 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005459 | 865862010-74123-DTLSB-07_03_2025-BIRDDMG-1^06244007.0133840 | POLE | HFTD Tier 2 | Distribution | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005460 | 865938257-10590-DETAIL-02_03_2025-GO95HV-1^06239004.0243943 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005461 | 866031501-79012-DTLTRT-06_25_2025-GUYLOINS-1^668087/00 1A/008 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005462 | 231627623-10743-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135400 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005463 | 231796580-75090-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135700 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005464 | 231809543-76570-DETAIL-09_05_2025-GO95HV-1^06147001.0204100 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005465 | 232046298-10189-DTLSB-01_22_2026-BIRDDMG-1^06242009.0297203 | POLE | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005466 | 232376141-84970-DETAIL-05_27_2026-GO95BLTC-1^07216001.0021705 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005467 | 866209563-63339-DETAIL-11_17_2025-GO95HV-1^06243007.0026600 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005468 | 866507679-35089-DTLSB-07_17_2025-GO95HV-1^06244006.0171300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005469 | 866541154-56399-DETAIL-09_04_2025-GO95HV-1^06147001.0319101 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005470 | 866634556-89939-DETAIL-05_20_2025-GO95HV-1^06243006.0093200 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005471 | 86663803-66921-DETAIL-04_14_2026-XARMSPCR-1^06237004.0185100 | CROSSARM | HFTD Tier 2 | Distribution | 2026-04-14 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005472 | 232410653-37909-DTLSB-05_02_2024-ENCHRW-1^06245007.0228800 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005473 | 232630967-36719-DTLSB-04_09_2026-GO95HV-1^06241007.0203200 | OTHER | Non-HFTD | Distribution | 2026-04-09 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005474 | 232962481-11580-DETAIL-01_29_2026-COVCOTHR-1^06240004.0307102 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005475 | 233513731-81470-DETAIL-03_13_2024-CUSTWIRE-1^06147004.0070200 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005476 | 233540680-97080-DETAIL-02_26_2025-GO95HV-1^06240004.0217401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005477 | 866869484-76649-DTLSB-07_24_2025-GO95BLTC-1^07218001.0264712 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005478 | 867050218-86559-DETAIL-08_28_2025-GO95HV-1^07216001.0162503 | OTHER | Non-HFTD | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005479 | 867357861-83289-DTLSB-01_26_2026-XARMSPCR-1^06242009.0296704 | CROSSARM | HFTD Tier 2 | Distribution | 2026-01-26 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005480 | 867385325-29772-DETAIL-06_06_2023-CUSTWIRE-1^06244010.0342501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005481 | 867421536-59212-DETAIL-08_12_2025-GO95HV-1^06246001.0195300 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005482 | 233579980-53470-DETAIL-06_04_2025-GO95HV-1^06142012.0108400 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005483 | 234140619-98759-DTLSB-07_31_2025-GO95HV-1^07218001.0262300 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005484 | 234296577-48590-AUDIT-01_26_2026-ANCHIDLE-1^06239004.0243942 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005485 | 234296577-48590-DETAIL-01_13_2026-GO95MLD-1^06239004.0243942 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005486 | 234344118-72970-DETAIL-04_23_2026-GO95HV-1^06142012.0144702 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005487 | 867421536-59212-DETAIL-08_12_2025-GRDRODHI-1^06246001.0195300 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005488 | 867421536-59212-DETAIL-08_12_2025-GRDRODHI-3^06246001.0195300 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005489 | 867523538-4349-DETAIL-09_04_2025-SVCDEFLC-1^07216001.0098503 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005490 | 867577243-94509-DETAIL-09_17_2025-GO95HV-1^06246007.0137150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005491 | 868110613-59359-DTLTRT-04_20_2026-GO95HV-1^668004/02 7/002 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005492 | 868128636-53560-DTLTRT-06_04_2025-GUYHINS-1^668075/00 18/015 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005493 | 868459466-41622-DETAIL-06_09_2026-GUYHINS-1^668086/00 5/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005494 | 868464328-15079-DETAIL-06_16_2025-GO95HV-1^06248004.0364043 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005495 | 868739053-50850-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0133001 | OTHER | HFTD Tier 3 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005496 | 869296308-85159-DTLSB-08_14_2025-SVCDEFLC-1^07217001.0023201 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005497 | 869353266-72752-DETAIL-04_24_2025-GO95HV-1^06242006.0174500 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005498 | 869368509-38190-DETAIL-01_15_2025-GO95CL10-1^06239004.0256113 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005499 | 869398188-40422-DTLSB-05_05_2026-GO95HV-1^06142013.0163301 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005500 | 869551515-85000-DETAIL-03_25_2025-GO95HV-1^06239003.0019605 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005501 | 869677888-82119-DTLSB-04_13_2026-GO95HV-1^06241008.0365501 | OTHER | Non-HFTD | Distribution | 2026-04-13 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005502 | 869981596-84270-DETAIL-01_16_2025-GO95HV-1^06239004.0256212 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005503 | 869981596-84270-DETAIL-01_16_2025-GO95MLD-1^06239004.0256212 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005504 | 235460011-72839-DETAIL-05_19_2025-GO95HV-1^06243006.0276400 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005505 | 235478436-87223-DTLSB-04_25_2024-CUSTWIRE-1^06245007.0228340 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005506 | 235497498-72615-DTLSB-05_28_2026-GO95MLD-1^07216001.0020300 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005507 | 235648978-41550-DETAIL-02_11_2026-SVCDEFLC-1^06239003.0016206 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005508 | 235760669-61669-DETAIL-09_03_2025-GO95MLD-1^06246001.0176209 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005509 | 235806925-9370-DETAIL-01_23_2026-BIRDDMG-1^06240003.0184901 | POLE | HFTD Tier 2 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005510 | 870088068-92409-DTLSB-07_08_2025-GO95BLTC-1^06244007.0037701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005511 | 870088068-92409-DTLSB-07_08_2025-GO95HV-1^06244007.0037701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005512 | 870204544-283-DETAIL-09_11_2025-GO95HV-1^06248007.0223502 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005513 | 870360824-88383-DETAIL-09_18_2025-GO95HV-1^07218001.0087100 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005514 | 870408379-36973-AUDIT-10_13_2025-GO95MLD-1^07216001.0175802 | OTHER | Non-HFTD | Distribution | 2025-10-13 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005515 | 2358355-41559-DETAIL-06_18_2025-GO95HV-1^06248004.0286200 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005516 | 23604798-92459-DETAIL-06_03_2024-CUSTWIRE-1^06246005.0317900 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005517 | 236191011-56070-DETAIL-05_14_2025-GO95HV-1^06142012.0117602 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005518 | 23640373-17150-ADMIN-10_21_2025-GO95HV-1^06247001.0267900 | OTHER | Non-HFTD | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005519 | 236701514-71904-DETAIL-03_30_2023-CUSTWIRE-1^06142016.0084913 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005520 | 870960938-74609-DETAIL-09_17_2025-GO95HV-1^06246006.0080702 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005521 | 871049916-39659-DETAIL-04_30_2026-GO95HV-1^668004/00 9/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005522 | 87115855-9600-DETAIL-04_08_2026-GO95HV-1^06240002.0327300 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005523 | 871408503-19229-DETAIL-04_28_2026-GO95HV-1^06142012.0148700 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005524 | 871512170-29170-DETAIL-07_02_2026-GO95HV-1^07217001.0049607 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005525 | 871573888-13142-DETAIL-04_30_2025-GO95HV-1^06242006.0106300 | OTHER | Non-HFTD | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005526 | 871756168-24759-DTLSB-08_14_2025-GO95HV-1^07218001.0352601 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005527 | 87201353-55589-DTLSB-01_21_2026-GO95HV-1^06242009.0297004 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005528 | 872104921-94020-DETAIL-03_25_2025-COVCOTHR-1^06240004.0273401 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005529 | 872244143-88629-DETAIL-04_30_2025-GO95HV-1^06242006.0111100 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005530 | 872252245-92245-DETAIL-07_06_2026-GO95HV-1^07217001.0117805 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005531 | 872425569-65189-DETAIL-04_22_2025-GO95HV-1^06242006.0092401 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005532 | 872473730-86732-DTLSB-06_04_2026-GO95HV-1^07216001.0028200 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005533 | 872757256-73932-DETAIL-08_06_2025-GO95HV-1^06246002.0106300 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005534 | 872954975-98970-DETAIL-01_16_2025-GO95HV-1^06239004.0257305 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005535 | 873098536-23680-DETAIL-01_30_2025-GO95HV-1^06239004.0244604 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005536 | 87404802-34802-DETAIL-09_17_2025-GO95HV-1^06246006.0080703 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005537 | 874075848-19643-DTLSB-04_30_2024-CUSTWIRE-1^06245007.0222842 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005538 | 874136713-28580-DETAIL-02_23_2026-GO95HV-1^06239002.0152200 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005539 | 874693414-33069-DETAIL-09_15_2025-GO95HV-1^06248007.0263801 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005540 | 874708915-49915-DETAIL-06_05_2025-GO95HV-1^06148014.0246000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005541 | 874956818-53959-DTLSB-08_14_2025-GO95HV-1^07218001.0353200 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005542 | 875073993-97189-DETAIL-05_29_2025-GO95HV-1^06244006.0101500 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005543 | 875165677-92777-DETAIL-06_09_2025-GO95BLTC-1^06245006.0191302 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005544 | 875165677-92777-DETAIL-06_09_2025-GO95HV-1^06245006.0191302 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005545 | 875211325-64439-DETAIL-05_29_2025-GO95HV-1^06244006.0110801 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005546 | 875232135-13449-ADMIN-03_04_2025-POLEDERP-1^07216001.0296408 | POLE | Non-HFTD | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005547 | 875642123-6730-DTLSB-07_30_2025-GO95HV-1^07218001.0274301 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005548 | 875913020-57739-DTLTRT-06_25_2025-GO95MLD-1^668087/00 12/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005549 | 876085390-70479-DTLSB-04_21_2026-DISTHDWR-1^06241008.0310340 | CONNECTION DEVICE | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005550 | 237145126-14342-ADMIN-10_22_2025-GO95BLTC-1^06246011.0069400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005551 | 237234715-63999-DETAIL-09_10_2025-SVCENTCO-1^06246006.0183203 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005552 | 237772606-6129-DETAIL-04_28_2025-GO95HV-1^06242006.0191301 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005553 | 237919111-41211-DETAIL-09_18_2025-GO95HV-1^07218001.0085000 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005554 | 238055804-36189-DTLSB-01_27_2026-GO95HV-1^06242009.0058201 | OTHER | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005555 | 238151438-54789-DETAIL-09_02_2025-GO95HV-1^06246001.0205904 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005556 | 238669031-57623-DETAIL-06_18_2025-GO95HV-1^06248004.0341641 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005557 | 239019686-8659-DTLTRT-04_30_2026-GO95HV-1^668004/00 6/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005558 | 239286604-18099-DETAIL-08_05_2024-CUSTWIRE-1^06244005.0029002 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005559 | 239454128-83189-AUDIT-05_18_2026-GUYHINS-1^06241009.0259103 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005560 | 239454975-88899-DETAIL-09_09_2025-GO95HV-1^06246007.0227850 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005561 | 239561555-19259-DETAIL-06_23_2026-CUSTWIRE-1^07217001.0107400 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005562 | 23959709-98789-DETAIL-03_18_2024-CUSTWIRE-1^06245005.0060400 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005563 | 239630254-81453-DETAIL-09_22_2025-GO95HV-1^07218001.0221901 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005564 | 239732109-379-DETAIL-10_15_2025-GO95HV-1^06148001.0365401 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005565 | 239740406-88499-DETAIL-05_27_2025-GO95HV-1^06244006.0085801 | OTHER | HFTD Tier 2 | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005566 | 239869238-16080-DETAIL-09_30_2025-GO95HV-1^06148001.0300210 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005567 | 239990709-31709-DETAIL-08_18_2025-GO95HV-1^06247006.0364101 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005568 | 239999281-99080-DETAIL-05_14_2025-GO95HV-1^06142012.0117601 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005569 | 240223083-40819-DTLSB-05_11_2026-GO95HV-1^06242009.0278700 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005570 | 876151770-61342-DTLSB-06_03_2026-GO95HV-1^07216001.0028902 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005571 | 876425246-14642-DETAIL-08_25_2025-GO95HV-1^06246001.0176107 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005572 | 876713363-45299-DETAIL-10_05_2021-CUSTWIRE-1^06147005.0062100 | OTHER | Non-HFTD | Distribution | 2021-10-05 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005573 | 876839776-72849-DTLSB-07_14_2025-GO95HV-1^06244007.0145604 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005574 | 876956274-89019-DTLSB-03_09_2026-GO95HV-1^06242009.0175400 | OTHER | Non-HFTD | Distribution | 2026-03-09 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005575 | 877070189-45559-DETAIL-08_05_2025-GO95HV-1^06247005.0205201 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005576 | 877309085-23552-DTLSB-06_09_2026-GO95HV-1^07216001.0229400 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005577 | 877317721-66569-DETAIL-05_27_2025-GO95BLTC-1^06243006.0165704 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005578 | 877317721-66569-DETAIL-05_27_2025-GUYHINS-1^06243006.0165704 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-27 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005579 | 877427238-85590-AUDIT-03_13_2025-GO95BLTC-1^06239004.0245101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005580 | 877427238-85590-DETAIL-01_28_2025-GO95HV-1^06239004.0245101 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005581 | 877673709-97139-DTLTRT-07_09_2025-POLEDERP-1^668087/00 1/023 | POLE | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005582 | 877777897-55252-ADMIN-11_04_2025-GO95MLD-1^06246001.0264901 | OTHER | Non-HFTD | Distribution | 2025-11-04 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005583 | 877902792-76370-DETAIL-01_28_2025-GO95HV-1^06240004.0085001 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005584 | 878244851-32652-DTLTRT-05_18_2026-GO95HV-1^668086/00 10/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005585 | 87839481-51509-DTLSB-11_01_2021-CUSTWIRE-1^06148004.0233600 | OTHER | Non-HFTD | Distribution | 2021-11-01 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005586 | 87839481-51509-DTLSB-11_01_2021-CUSTWIRE-2^06148004.0233600 | OTHER | Non-HFTD | Distribution | 2021-11-01 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005587 | 878482773-56599-DETAIL-07_31_2025-GO95HV-1^06247006.0207707 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005588 | 878536798-46550-DETAIL-02_25_2026-GO95HV-1^06239003.0139202 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005589 | 878548446-73989-DETAIL-08_21_2025-GO95HV-1^06247006.0268800 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005590 | 878863330-24170-DETAIL-02_19_2026-GO95HV-1^06239002.0013601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005591 | 87887054-20959-DTLTRT-04_22_2026-GO95MLD-1^668004/02 15/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005592 | 878920673-85469-DETAIL-07_29_2025-POLETOP-1^06247005.0216802 | POLE | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005593 | 879110805-75869-DTLSB-07_07_2025-GO95MLD-1^06245007.0357605 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005594 | 879110805-75869-DTLSB-07_07_2025-GO95MLD-2^06245007.0357605 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005595 | 879132259-56559-DETAIL-08_05_2025-BIRDDMG-1^06247005.0207200 | POLE | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005596 | 879179508-60752-DTLTRT-06_23_2025-BIRDDMG-1^668087/00 13/002 | POLE | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005597 | 879393406-49790-DTLTRT-10_24_2023-CUSTWIRE-1^668010/00 1/010 | OTHER | HFTD Tier 2 | Transmission | 2023-10-24 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005598 | 880950963-20189-DETAIL-05_01_2025-ABNDEQPM-1^06242006.0021700 | OTHER | Non-HFTD | Distribution | 2025-05-01 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005599 | 881444036-94000-DETAIL-02_10_2026-SVCDEFLC-1^06239003.0016709 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005600 | 881603542-27659-DETAIL-06_18_2025-GO95HV-1^06248004.0310601 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005601 | 881689484-99953-DETAIL-06_25_2026-GO95HV-1^07217001.0038200 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005602 | 882733115-57115-DETAIL-05_30_2025-GO95HV-1^06147014.0029201 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005603 | 88281038-9759-DETAIL-09_03_2025-GO95HV-1^07216001.0092606 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005604 | 882812240-74389-ADMIN-10_23_2025-GO95HV-1^06246001.0113900 | OTHER | Non-HFTD | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005605 | 240273081-88789-DTLSB-07_08_2025-GO95HV-1^06245007.0351202 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005606 | 240627485-2089-DTLSB-04_22_2026-SVCDEFLC-1^06241009.0249100 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005607 | 240758848-20739-DETAIL-07_30_2024-CUSTWIRE-1^06244005.0355300 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005608 | 240777181-50839-DETAIL-05_19_2025-GO95HV-1^06243006.0274701 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005609 | 240788504-76179-DETAIL-03_05_2026-SVCDEFLC-1^06243009.0360501 | OTHER | Non-HFTD | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005610 | 241282521-79580-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0169044 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005611 | 241517329-41449-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0148300 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005612 | 241644564-86564-DTLTRT-07_08_2025-GO95MLD-1^668087/00 13/027 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005613 | 241734593-40689-DETAIL-08_13_2025-GO95HV-1^06247006.0258502 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005614 | 242369952-92559-DETAIL-04_29_2026-GO95HV-1^668004/00 9/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005615 | 242369952-92560-DETAIL-04_29_2026-GO95HV-1^668004/00 9/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005616 | 242844005-32589-ADMIN-11_10_2025-GO95BLTC-1^06246011.0065201 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005617 | 243016913-79780-ADMIN-11_14_2025-GO95HV-1^06246001.0329500 | OTHER | Non-HFTD | Distribution | 2025-11-14 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005618 | 243321450-9870-DETAIL-02_23_2026-POLETOP-1^06239002.0021501 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005619 | 243439476-69142-DTLSB-06_26_2025-GO95HV-1^06244007.0108641 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005620 | 243560023-1023-DETAIL-06_10_2025-GUYHINS-1^668075/00 10/033 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-10 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005621 | 243616771-70230-DTLSB-08_13_2025-GO95HV-1^07218001.0289701 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005622 | 243616783-53683-DETAIL-08_21_2025-GO95HV-1^07216001.0177140 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005623 | 243630588-20349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061901 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005624 | 244031376-98209-DETAIL-08_12_2025-GO95HV-1^06247006.0266101 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005625 | 244512234-73099-DETAIL-05_06_2025-GO95HV-1^06243006.0034501 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005626 | 244515675-74680-DTLSB-06_09_2026-GO95MLD-1^07216001.0228406 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005627 | 2446026-46799-DETAIL-08_12_2025-GO95HV-1^06246001.0195301 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005628 | 244727336-32780-DTLSB-04_30_2026-GO95HV-1^06142013.0188400 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005629 | 244797204-5780-DETAIL-06_09_2026-GUYHINS-2^668086/00 18/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005630 | 882832075-9840-DETAIL-03_23_2026-COVCOTHR-1^06240004.0219803 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005631 | 882832075-9840-DETAIL-03_23_2026-COVCOTHR-3^06240004.0219803 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005632 | 883273228-88379-DETAIL-06_16_2025-GO95MLD-1^06248004.0360242 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005633 | 883273228-88379-DETAIL-06_16_2025-RISEHDWR-1^06248004.0360242 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005634 | 883723306-55971-DETAIL-02_24_2025-GO95MLD-1^06239004.0367842 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005635 | 88386936-72720-DETAIL-08_12_2025-GRDRODHI-1^06246001.0195200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005636 | 88393205-45205-DETAIL-06_02_2025-SVCROAD-1^06148014.0242901 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005637 | 884044784-43860-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0245900 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005638 | 884254494-6509-DETAIL-09_04_2025-GO95HV-1^06247006.0185701 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005639 | 884722784-31159-DETAIL-08_19_2025-GO95HV-1^06247006.0367303 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005640 | 884767705-66363-DETAIL-06_23_2026-CUSTWIRE-1^07217001.0107301 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005641 | 88484473-72460-AUDIT-06_23_2025-GO95HV-1^06239002.0060600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005642 | 884900918-4479-ADMIN-11_13_2025-GO95BLTC-1^06247008.0314902 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005643 | 884900918-4479-ADMIN-11_13_2025-GO95HV-1^06247008.0314902 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005644 | 886072298-35749-DTLSB-07_16_2025-GO95HV-1^06244006.0291800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005645 | 886121016-48149-ADMIN-10_21_2025-POLEDERP-1^07216001.0297510 | POLE | Non-HFTD | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005646 | 887064143-61109-DETAIL-07_31_2025-GO95HV-1^06247006.0207706 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005647 | 88713355-76451-DRONE_HY-07_01_2026-COVCOTHR-1^06239004.0366601 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005648 | 887330088-2419-DETAIL-06_27_2022-CUSTWIRE-1^07116007.0156401 | OTHER | HFTD Tier 2 | Distribution | 2022-06-27 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005649 | 887533643-96699-DETAIL-05_30_2025-GO95HV-1^06244006.0089301 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005650 | 244797204-5780-DETAIL-06_09_2026-GUYHINS-3^668086/00 18/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005651 | 244797204-5780-DETAIL-06_09_2026-GUYHINS-5^668086/00 18/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005652 | 244797204-5780-DETAIL-06_09_2026-GUYHINS-6^668086/00 18/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005653 | 244930831-45750-DETAIL-01_21_2026-GO95MLD-1^06239004.0125900 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005654 | 244953456-79342-DTLSB-06_30_2025-GO95HV-1^06244007.0106540 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005655 | 245127244-51371-DETAIL-04_02_2025-GO95BLTC-1^06241005.0114500 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005656 | 245127244-51371-DETAIL-04_02_2025-GRDRODHI-1^06241005.0114500 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005657 | 245127244-51371-DETAIL-04_02_2025-GUYHINS-1^06241005.0114500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005658 | 24530308-84970-DETAIL-03_23_2026-COVCOTHR-1^06240004.0228502 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005659 | 24531251-74270-DTLSB-06_03_2026-GO95HV-1^07216001.0026300 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005660 | 24546187-18089-DETAIL-08_05_2025-GO95HV-1^06246002.0139006 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005661 | 245667494-70189-DETAIL-07_16_2024-CUSTWIRE-1^06244005.0275301 | OTHER | Non-HFTD | Distribution | 2024-07-16 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005662 | 245692458-81690-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0361002 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005663 | 246183736-98299-DETAIL-07_28_2025-GO95HV-1^06247005.0317400 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005664 | 246359774-65722-DETAIL-10_15_2025-GO95TCH-1^06246011.0181505 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005665 | 246627398-41292-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 5/016 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005666 | 246785749-67749-DETAIL-06_18_2025-GO95HV-1^06248004.0323000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005667 | 246999483-68709-ADMIN-11_10_2025-GO95BLTC-1^06246012.0126704 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005668 | 247158994-33430-DETAIL-03_03_2025-GO95MLD-1^06241005.0365200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005669 | 247337193-30080-DETAIL-02_14_2025-GO95HV-1^06240004.0164500 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005670 | 247341155-73639-DETAIL-10_09_2024-GO95CL10-1^07216001.0204202 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005671 | 247341155-73639-DETAIL-10_09_2024-SVCROAD-1^07216001.0204202 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005672 | 247519278-38743-DTLSB-07_03_2025-GO95HV-1^06245007.0357841 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005673 | 247553075-63900-DETAIL-02_04_2026-GO95HV-1^06239003.0018904 | OTHER | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005674 | 247663535-90679-DTLSB-06_30_2025-GO95HV-1^06244006.0225301 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005675 | 247814655-97999-DETAIL-09_10_2025-GO95HV-1^06246006.0182201 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005676 | 887549941-3880-DETAIL-02_19_2026-GO95HV-1^06239001.0065601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005677 | 887573425-67425-DETAIL-05_26_2026-GO95HV-1^07217001.0142302 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005678 | 887585549-91230-DETAIL-02_06_2025-GO95HV-1^06240004.0164303 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005679 | 887618676-36759-DETAIL-04_30_2026-GO95HV-1^668004/00 2/018 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005680 | 887618676-36760-DETAIL-04_30_2026-GO95HV-1^668004/00 2/018 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005681 | 88775915-58915-DETAIL-06_05_2025-GO95HV-1^06148014.0236401 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005682 | 887974934-10869-DTLSB-03_09_2026-SVCDEFLC-1^06242009.0068904 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005683 | 888055394-16582-DETAIL-10_24_2024-POLISSUE-1^07216001.0209908 | POLE | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005684 | 888695291-15879-DETAIL-09_03_2025-SVCDEFLC-1^06247006.0210504 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005685 | 888927523-77523-DETAIL-06_11_2025-GUYHINS-1^668075/00 15/033 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005686 | 888927523-77523-DETAIL-06_11_2025-GUYHINS-3^668075/00 15/033 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005687 | 888927523-77523-DETAIL-06_11_2025-GUYHINS-4^668075/00 15/033 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005688 | 889707760-22460-DETAIL-06_05_2025-GO95HV-1^668075/00 2/028 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005689 | 88979726-52079-ADMIN-04_04_2024-ABNDEQPM-1^06147005.0238102 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005690 | 889963221-87350-DETAIL-03_04_2026-GO95HV-1^06239003.0181801 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005691 | 890114734-9859-DTLTRT-04_22_2026-GO95HV-1^668004/02 13/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005692 | 89020100-62120-DTLSB-05_28_2026-GO95HV-1^07216001.0020505 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005693 | 890328030-74443-DETAIL-06_26_2026-GO95HV-1^07217001.0117201 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005694 | 890490781-80292-DTLTRT-04_28_2026-GO95HV-1^668004/00 4/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005695 | 890510412-89239-DETAIL-05_14_2025-GO95HV-1^06243006.0223103 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005696 | 890876058-70729-DETAIL-04_27_2026-CUSTWIRE-1^06142012.0142502 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005697 | 890913948-4948-DETAIL-05_12_2025-GO95HV-1^06142012.0014800 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005698 | 89091431-14859-DETAIL-07_24_2025-GO95HV-1^06247005.0136302 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005699 | 891130279-56892-ADMIN-11_04_2025-GUYHINS-1^06246001.0276800 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-11-04 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005700 | 891160680-22292-DTLSB-06_05_2026-GO95HV-1^07216001.0028900 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005701 | 247906200-16349-DTLSB-06_25_2025-GO95HV-1^06244007.0101500 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005702 | 24793884-6670-DETAIL-09_04_2025-GO95HV-1^06147001.0319302 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005703 | 247967685-3600-DETAIL-04_07_2026-GO95HV-1^06240002.0317021 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005704 | 24814924-51819-ADMIN-06_17_2026-FRGNELEC-2^668036/00 16/032 | OTHER | Non-HFTD | Transmission | 2026-06-17 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005705 | 248489091-83080-DETAIL-02_16_2026-GO95HV-1^06239001.0053700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005706 | 248604024-59589-DETAIL-08_20_2025-GO95HV-1^06247006.0369101 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005707 | 248799715-34815-DETAIL-06_02_2025-GO95HV-1^06147014.0028501 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005708 | 249241593-94589-DTLSB-05_11_2026-GO95HV-1^06242009.0278802 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005709 | 249357119-59940-DETAIL-04_14_2026-COVCOTHR-1^06237004.0170900 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-04-14 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005710 | 249357119-59940-DETAIL-04_14_2026-GO95TCH-1^06237004.0170900 | OTHER | HFTD Tier 2 | Distribution | 2026-04-14 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005711 | 249357119-59940-DETAIL-04_14_2026-SVCDEFLC-1^06237004.0170900 | OTHER | HFTD Tier 2 | Distribution | 2026-04-14 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005712 | 249597010-54019-DETAIL-03_25_2024-CUSTWIRE-1^06147005.0147901 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005713 | 24962027-95140-DETAIL-04_07_2026-GO95BLTC-1^06240002.0317110 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005714 | 249657894-17053-DETAIL-06_25_2026-GO95HV-1^07217001.0037101 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005715 | 249952346-84849-DTLSB-07_17_2025-GO95HV-1^06244007.0114340 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005716 | 250046738-44580-DTLSB-05_07_2026-GO95HV-1^06142013.0215402 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005717 | 250064546-12680-DETAIL-05_29_2025-GO95HV-1^06147014.0012915 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005718 | 250205177-41590-DETAIL-02_03_2025-GO95MLD-1^06239004.0243941 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005719 | 250361152-41929-DTLSB-08_25_2023-CUSTWIRE-1^06243008.0176500 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005720 | 250443064-66399-AUDIT-09_02_2025-RISEBKSP-1^06247006.0255001 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005721 | 891198495-19495-DETAIL-03_10_2026-BIRDDMG-1^06238004.0029608 | POLE | HFTD Tier 2 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005722 | 891198495-19495-DETAIL-03_24_2025-GUYHINS-1^06238004.0029608 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005723 | 891198495-19495-DETAIL-03_24_2025-GUYHINS-2^06238004.0029608 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005724 | 891266669-20790-DETAIL-01_14_2026-GO95MLD-1^06239004.0133041 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005725 | 891679168-50109-DTLTRT-05_06_2026-GO95HV-1^668038/00 4/059 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005726 | 891791990-17192-ADMIN-11_12_2025-ABNDEQPM-1^06146001.0312201 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005727 | 891791990-17192-ADMIN-11_12_2025-GRDRODHI-1^06146001.0312201 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005728 | 891809806-88660-DETAIL-04_30_2026-GO95HV-1^668004/00 8/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005729 | 89206448-61690-DETAIL-01_13_2026-GO95BLTC-1^06239004.0245304 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005730 | 89206448-61690-DETAIL-01_13_2026-SVCROAD-1^06239004.0245304 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005731 | 892145341-65479-DETAIL-10_06_2025-GO95TCH-1^06148001.0311710 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005732 | 893012263-21729-DTLSB-01_21_2026-BIRDDMG-1^06242009.0298105 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005733 | 893012263-21729-DTLSB-01_21_2026-GO95HV-1^06242009.0298105 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005734 | 893055758-98702-DETAIL-08_19_2025-GO95HV-1^06246002.0353900 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005735 | 893077036-59640-DETAIL-03_24_2026-GO95CL10-1^06240004.0210907 | OTHER | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005736 | 893495333-71729-DTLSB-01_20_2026-GO95HV-1^06242009.0299201 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005737 | 89350643-90643-DETAIL-01_23_2026-CUSTWIRE-1^06242009.0299671 | OTHER | Non-HFTD | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005738 | 894191074-44779-DETAIL-06_16_2025-GO95HV-1^06248005.0369800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005739 | 894201846-74509-DETAIL-10_08_2025-GO95HV-1^06246008.0027604 | OTHER | HFTD Tier 2 | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005740 | 894815629-58829-DTLSB-02_03_2026-BIRDDMG-1^06243009.0305401 | POLE | HFTD Tier 2 | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005741 | 894861099-61612-DETAIL-09_08_2025-GO95HV-1^06147001.0324201 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005742 | 89496035-80814-DETAIL-04_16_2025-GO95MLD-1^06242005.0368540 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005743 | 89512396-94353-DTLSB-06_16_2026-GO95HV-1^07217001.0356302 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005744 | 895148257-63089-DETAIL-06_10_2025-GO95HV-1^06245006.0291701 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005745 | 895660527-43527-DETAIL-03_06_2025-GO95BLTC-1^06241005.0163902 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005746 | 895764919-46813-DETAIL-08_26_2025-GO95HV-1^06247006.0285401 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005747 | 89581863-66389-DETAIL-08_18_2025-SVCDEFLC-1^06247006.0253002 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005748 | 895836093-19790-DETAIL-02_24_2026-BIRDDMG-1^06239002.0273900 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005749 | 895836093-19790-DETAIL-02_24_2026-GO95HV-1^06239002.0273900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005750 | 895942471-4799-DETAIL-08_04_2025-GO95HV-1^06247006.0208603 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005751 | 895942471-4799-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0208603 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005752 | 896042636-50912-DTLTRT-07_03_2025-GO95HV-1^668087/00 1/012 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005753 | 896042636-50912-DTLTRT-07_03_2025-GO95MLD-1^668087/00 1/012 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005754 | 896156559-25739-DTLTRT-06_25_2025-GO95CL10-1^668087/00 11/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005755 | 896173221-62959-DETAIL-06_20_2024-CUSTWIRE-1^06246006.0234000 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005756 | 896295918-16779-DETAIL-08_07_2025-GO95HV-1^06246002.0267900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005757 | 250832958-85980-DETAIL-04_27_2026-GO95HV-1^06142012.0144904 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005758 | 250988148-4190-DETAIL-10_16_2025-GO95BLTC-1^06246012.0137400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005759 | 251498157-54218-DTLSB-02_27_2024-GO95HV-1^07216001.0271700 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005760 | 251590191-9879-DETAIL-10_02_2025-GO95HV-1^06148001.0298500 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005761 | 25200154-91079-DETAIL-09_23_2025-DISTHDWR-2^06247004.0074500 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005762 | 252055586-42861-DETAIL-02_24_2025-GO95MLD-1^06239004.0366802 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005763 | 252419178-32190-DTLSB-06_10_2026-GO95HV-1^07217001.0350002 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005764 | 25259294-77970-DETAIL-09_05_2025-GO95HV-1^06147001.0291000 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005765 | 252760935-75390-DETAIL-05_15_2024-GO95MLD-1^06142012.0124700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005766 | 252825715-64699-DETAIL-03_17_2025-GUYHINS-1^06240004.0271100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005767 | 253066916-42079-DETAIL-02_18_2026-GO95HV-1^06239002.0040300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005768 | 253086302-37302-DETAIL-01_22_2025-GO95MLD-1^06239004.0254540 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005769 | 253113904-32819-DTLSB-04_22_2026-GO95MLD-1^06241009.0247101 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005770 | 253124706-27170-DETAIL-01_24_2025-GO95HV-1^06239004.0257942 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005771 | 253491659-74349-DTLSB-07_14_2025-GO95HV-1^06244006.0289600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005772 | 253509365-11500-DETAIL-02_11_2026-GUYHINS-1^06239003.0016600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005773 | 253736939-53579-DTLTRT-10_19_2023-CUSTWIRE-1^668010/00 15/025 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005774 | 253795178-87399-DETAIL-09_25_2025-ANCHIDLE-1^06246009.0089503 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-25 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005775 | 253808991-36790-DETAIL-09_30_2025-SVCENTCO-1^06148001.0300107 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005776 | 253933341-48239-DTLTRT-06_26_2025-GUYHINS-2^668087/00 6/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005777 | 896664171-25839-DTLSB-07_17_2025-ABNDEQPM-1^06244006.0217300 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005778 | 896664171-25839-DTLSB-07_17_2025-GO95HV-1^06244006.0217300 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005779 | 896794448-62712-DTLSB-05_06_2026-XARMSPCR-1^06142013.0285900 | CROSSARM | Non-HFTD | Distribution | 2026-05-06 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005780 | 897309923-82559-DETAIL-06_17_2025-GO95HV-1^06248004.0332702 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005781 | 897459310-8070-DETAIL-03_29_2023-CUSTWIRE-1^06240004.0165707 | OTHER | HFTD Tier 2 | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005782 | 897862834-78183-DETAIL-09_11_2025-GO95HV-1^06248007.0222701 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005783 | 897997709-17370-DRONE_HY-06_30_2026-COVCOTHR-1^06240004.0169542 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005784 | 898201172-64684-DETAIL-04_02_2025-GUYHINS-2^06241005.0116702 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005785 | 898220994-74860-DETAIL-01_23_2025-GO95HV-1^06239004.0257610 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005786 | 898251008-7222-DETAIL-05_19_2025-GO95HV-1^06142012.0113501 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005787 | 898433773-6779-DETAIL-06_13_2022-CUSTWIRE-1^07116007.0029000 | OTHER | HFTD Tier 2 | Distribution | 2022-06-13 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005788 | 898517016-58509-ADMIN-10_22_2025-GO95BLTC-1^06246011.0055700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005789 | 898569465-86309-DETAIL-08_11_2025-POLETOP-1^06247006.0265501 | POLE | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005790 | 898630549-92549-DETAIL-06_18_2025-GO95HV-1^06248004.0325200 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005791 | 899533746-40879-DETAIL-07_29_2025-GRDRODHI-1^06247005.0261300 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005792 | 899897333-27021-DETAIL-04_10_2025-GO95TCH-1^06241005.0040300 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005793 | 900107139-48639-DTLSB-07_17_2025-GO95HV-1^06244006.0187201 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005794 | 900327659-36689-DTLSB-07_03_2025-GO95HV-1^06244007.0131900 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005795 | 900356168-92532-DETAIL-08_19_2025-GO95HV-1^06246002.0353800 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005796 | 900444525-51738-DETAIL-08_26_2025-GO95HV-1^07216001.0168200 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005797 | 900775159-36399-DTLSB-02_16_2026-GRDRODHI-1^06243009.0308700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005798 | 900920211-24580-DETAIL-02_13_2025-SVCDEFLC-1^06240004.0169040 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005799 | 901115596-85432-DETAIL-08_20_2025-GO95HV-1^06246001.0175403 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005800 | 901115596-85432-DETAIL-08_20_2025-GRDRODHI-1^06246001.0175403 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005801 | 901298201-69201-DETAIL-09_22_2025-GRDRODHI-1^07218001.0161002 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005802 | 254544681-18939-DTLTRT-05_19_2026-BIRDDMG-1^668086/00 14/009 | POLE | Non-HFTD | Transmission | 2026-05-19 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005803 | 254675790-76970-DETAIL-02_19_2026-GO95HV-1^06239002.0027501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005804 | 254831058-46333-ADMIN-10_23_2025-GO95MLD-1^07218001.0174201 | OTHER | Non-HFTD | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005805 | 255110851-20759-DETAIL-06_18_2025-GO95HV-1^06248004.0324702 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005806 | 255296904-54940-DTLTRT-06_04_2025-GO95HV-1^668075/00 14/010 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005807 | 255371754-2509-DETAIL-08_27_2025-GO95HV-1^06247006.0188700 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005808 | 255381841-38659-DETAIL-06_24_2025-GO95HV-1^06248004.0312900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005809 | 255421504-67710-DETAIL-03_17_2025-GO95HV-1^06238004.0157202 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005810 | 256175889-49549-DTLSB-07_02_2025-GO95HV-1^06244007.0136500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005811 | 25628983-15059-DETAIL-09_05_2025-GO95HV-1^06247006.0061401 | OTHER | HFTD Tier 2 | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005812 | 256450248-43491-DETAIL-05_06_2026-GO95HV-1^668038/00 4/058 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005813 | 256514815-34815-DETAIL-06_24_2025-GO95HV-1^06248004.0312904 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005814 | 256534009-27039-DTLSB-09_19_2022-CUSTWIRE-1^06243005.0105801 | OTHER | Non-HFTD | Distribution | 2022-09-19 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005815 | 256548861-88079-DETAIL-07_29_2025-GO95BLTC-1^06247006.0206001 | OTHER | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005816 | 256571644-55299-DETAIL-08_27_2025-GO95HV-1^06247006.0171502 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005817 | 256611849-54889-DETAIL-08_13_2025-GO95HV-1^06247006.0259500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005818 | 256698022-71122-DETAIL-07_24_2025-GO95HV-1^06247005.0131200 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005819 | 256842778-26609-DETAIL-09_08_2025-GO95HV-1^06246006.0082802 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005820 | 256984821-30909-DETAIL-10_17_2022-CUSTWIRE-1^06246010.0154100 | OTHER | HFTD Tier 2 | Distribution | 2022-10-17 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005821 | 256985051-14179-DETAIL-10_02_2025-GO95HV-1^06148001.0299401 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005822 | 257099214-81859-DTLTRT-04_21_2026-GO95HV-1^668004/02 13/008 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005823 | 257104362-17009-ADMIN-10_23_2025-GO95HV-1^06246011.0279601 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005824 | 257258521-90169-DETAIL-03_11_2026-BIRDDMG-1^06240004.0278603 | POLE | HFTD Tier 2 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005825 | 257316295-27295-DETAIL-06_23_2026-CUSTWIRE-1^07217001.0107204 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005826 | 257378173-90809-DETAIL-08_28_2025-GO95HV-1^06247006.0076701 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005827 | 90152326-11820-DETAIL-05_07_2026-GO95HV-1^668038/00 4/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005828 | 901537768-97882-DTLTRT-08_05_2025-GUYNOINS-1^668087/00 3/018 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005829 | 901537768-98882-DTLTRT-08_05_2025-GUYNOINS-1^668087/00 3/018 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005830 | 901856631-2380-DETAIL-02_02_2026-GO95TCH-1^06240004.0316702 | OTHER | HFTD Tier 3 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005831 | 90195864-74820-DETAIL-08_20_2025-GO95HV-1^06246001.0174506 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005832 | 902118443-88942-DTLSB-05_22_2024-GO95HV-1^06243001.0102800 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005833 | 902460319-56349-AUDIT-09_09_2025-GO95HV-1^07216001.0166004 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005834 | 902461771-46980-DETAIL-02_18_2026-GO95HV-1^06239001.0069600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005835 | 90266218-11318-DTLSB-07_09_2025-GO95HV-1^06244006.0346800 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005836 | 902678999-32442-DETAIL-06_25_2025-GO95HV-1^668087/00 14/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005837 | 903197024-59442-DETAIL-09_05_2025-GO95HV-1^06147001.0309300 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005838 | 903206294-15609-DETAIL-10_15_2025-GO95BLTC-1^06246011.0182705 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005839 | 903232348-22542-DTLSB-05_06_2026-GO95HV-1^06142013.0287800 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005840 | 903497879-21683-DETAIL-08_19_2025-SVCDEFLC-1^07216001.0176704 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005841 | 903653648-93379-DETAIL-04_30_2025-GO95HV-1^06242006.0106500 | OTHER | Non-HFTD | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005842 | 904127249-76390-DETAIL-01_14_2025-GO95MLD-2^06239004.0255003 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005843 | 904206606-10059-DETAIL-07_29_2025-GO95HV-1^06247005.0262502 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005844 | 904268411-86589-DETAIL-08_04_2025-GO95HV-1^06247006.0208600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005845 | 904340753-90052-DETAIL-06_09_2026-GUYHINS-1^668086/00 9A/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005846 | 904340753-90052-DETAIL-06_09_2026-GUYHINS-2^668086/00 9A/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005847 | 904640414-72490-DETAIL-02_12_2026-GO95BLTC-1^06239003.0252101 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005848 | 904654966-52709-ADMIN-10_20_2025-ANCHIDLE-1^06246012.0119301 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005849 | 904663135-151-DETAIL-02_18_2025-SVCROAD-1^06239004.0365908 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005850 | 904664630-8362-DETAIL-04_21_2025-GUYNOINS-1^06242006.0037841 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005851 | 905167636-63442-ADMIN-10_22_2025-SVCENTBK-1^06246011.0051501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005852 | 257495504-96619-DTLSB-04_06_2026-BIRDDMG-1^06241009.0156201 | POLE | Non-HFTD | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005853 | 257513926-45940-DTLSB-07_24_2025-GO95HV-1^07218001.0264709 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005854 | 257541770-4559-DETAIL-08_06_2025-GO95HV-1^06247005.0207000 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005855 | 257934940-30340-DETAIL-06_05_2025-GO95HV-1^668075/00 15/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005856 | 258115908-30990-DTLSB-06_02_2026-GO95HV-1^07216001.0115706 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005857 | 258140214-22214-DETAIL-04_25_2024-CUSTWIRE-1^06142016.0177901 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005858 | 258460327-77099-DETAIL-10_09_2025-GO95HV-1^06248003.0228100 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005859 | 258547673-22979-DETAIL-10_06_2025-GO95TCH-1^06148001.0311907 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005860 | 258680891-86273-DETAIL-04_30_2025-GO95MLD-1^06239002.0066700 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005861 | 259350970-89570-DETAIL-02_17_2026-GO95HV-1^06239002.0093300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005862 | 259775265-83160-DTLTRT-06_04_2025-GO95HV-1^668075/00 12/015 | OTHER | HFTD Tier 2 | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005863 | 259968634-32359-DTLSB-07_07_2025-BIRDDMG-1^06245007.0356800 | POLE | HFTD Tier 2 | Distribution | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005864 | 260134958-73160-DETAIL-09_15_2025-GO95HV-1^07219001.0326202 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005865 | 260532403-16400-DETAIL-05_14_2025-GO95HV-1^06142012.0119640 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005866 | 260659678-20330-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 7/052 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005867 | 260754665-83389-DETAIL-08_21_2025-GO95HV-1^06247006.0269803 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005868 | 260901058-56959-DETAIL-07_29_2025-GRDRODHI-1^06247005.0266400 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005869 | 261354161-91299-DETAIL-08_04_2025-GO95BLTC-1^06247006.0209804 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005870 | 261416843-74079-DETAIL-09_11_2025-GUYHINS-1^06147001.0205300 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005871 | 261473783-96763-DETAIL-03_11_2025-GO95HV-1^06238004.0273802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005872 | 261473783-96763-DRONE_HY-06_30_2026-IRSPOTOH-1^06238004.0273802 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005873 | 261535733-43700-DETAIL-09_09_2025-GO95HV-1^06147001.0201501 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005874 | 261594408-41759-DTLSB-08_18_2025-GO95HV-1^07218001.0357200 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005875 | 261839149-70179-DETAIL-08_18_2025-XARMSPCR-1^06246002.0355500 | CROSSARM | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005876 | 261890144-35209-DETAIL-07_30_2025-GO95HV-1^06247006.0203401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005877 | 905276753-71009-DETAIL-10_01_2025-ANCHIDLE-1^06246009.0126500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005878 | 905660275-68663-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0097703 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005879 | 905663973-39021-DRONE_HY-06_19_2026-GUYHINS-1^06239004.0364803 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005880 | 906116635-4352-DTLSB-04_29_2026-GO95HV-1^06142013.0200200 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005881 | 906223608-90150-DETAIL-02_25_2026-SVCDEFLC-1^06239003.0132201 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005882 | 906223918-6651-AUDIT-04_22_2025-ANCHIDLE-1^06241005.0162901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-22 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005883 | 906556828-33651-DETAIL-01_13_2022-CUSTWIRE-1^06241005.0163900 | OTHER | HFTD Tier 2 | Distribution | 2022-01-13 | 2025-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005884 | 906562258-79952-DETAIL-03_18_2024-GO95MLD-1^06245002.0037901 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005885 | 906606070-74670-DETAIL-06_10_2025-GO95HV-1^06236005.0347800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005886 | 906647141-45259-DTLSB-07_08_2025-GO95HV-1^06245007.0354001 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005887 | 90692873-99440-DTLTRT-05_29_2025-GO95HV-1^668075/00 7/010 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005888 | 90697598-15549-DTLSB-07_16_2025-GO95HV-1^06244006.0318700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005889 | 908430639-80269-DTLTRT-07_05_2022-GO95HV-1^668005/00 16/033 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005890 | 908440446-62962-DETAIL-08_04_2025-GO95HV-1^06246001.0186002 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005891 | 908463453-58939-DETAIL-06_10_2026-GO95TCH-1^668086/00 1/012 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005892 | 908615169-58169-DTLSB-08_21_2023-CUSTWIRE-1^06243009.0216005 | OTHER | Non-HFTD | Distribution | 2023-08-21 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005893 | 908661811-52580-DETAIL-02_04_2025-GO95HV-1^06240004.0165749 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005894 | 908663866-25759-DETAIL-04_30_2026-GO95HV-1^668004/00 12/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005895 | 908663866-25760-DETAIL-04_30_2026-GO95HV-1^668004/00 12/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005896 | 908785364-87109-DETAIL-08_18_2025-GO95HV-1^06247006.0363400 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005897 | 908848644-14709-ADMIN-10_20_2025-GO95MLD-1^06246012.0121700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005898 | 909030206-6658-DETAIL-06_02_2025-GO95HV-1^06148014.0368600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005899 | 909049079-55059-DTLTRT-05_06_2026-GO95HV-1^668004/00 6/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005900 | 909093106-14106-DETAIL-01_29_2025-GO95MLD-1^06239004.0252701 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005901 | 909093106-14106-DRONE_HY-06_19_2026-COVCOTHR-1^06239004.0252701 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005902 | 909544838-42209-ADMIN-07_18_2024-GO95STUB-1^06246009.0105500 | OTHER | HFTD Tier 2 | Distribution | 2024-07-18 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005903 | 909544838-42209-DETAIL-09_29_2025-GO95HV-1^06246009.0105500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005904 | 909604263-60029-DETAIL-05_04_2022-CUSTWIRE-1^06143012.0249300 | OTHER | Non-HFTD | Distribution | 2022-05-04 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005905 | 91024345-85345-DTLSB-04_15_2026-GO95BLTC-1^06241008.0074403 | OTHER | Non-HFTD | Distribution | 2026-04-15 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005906 | 910378506-92370-DETAIL-01_22_2025-GO95HV-1^06239004.0254402 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005907 | 910609926-6572-DTLSB-04_30_2026-ENCHRW-1^06142013.0172502 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005908 | 910719233-11423-DETAIL-06_18_2025-GO95HV-1^06248004.0338240 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005909 | 910858554-48990-DETAIL-03_02_2026-GO95MLD-1^06239003.0269700 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005910 | 910883883-84140-DETAIL-03_24_2026-GO95HV-1^06240004.0217940 | OTHER | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005911 | 911123875-25539-DETAIL-05_29_2025-GO95HV-1^06244006.0032501 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005912 | 911303149-52029-DTLSB-02_02_2026-SVCENTCO-1^06243009.0292303 | OTHER | HFTD Tier 2 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005913 | 911572474-69783-DETAIL-08_18_2025-GO95BLTC-1^06247006.0362301 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005914 | 911572474-69783-DETAIL-08_18_2025-GO95HV-1^06247006.0362301 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005915 | 911833936-28259-DETAIL-09_17_2025-GO95HV-1^06247007.0018900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005916 | 912140552-43850-DETAIL-02_11_2026-SVCDEFLC-1^06239003.0016303 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005917 | 261973904-94089-DTLSB-07_10_2025-CUSTWIRE-1^06244007.0038908 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005918 | 262164706-11791-DETAIL-05_12_2026-GO95HV-1^668038/00 5/047 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005919 | 26217576-85699-DETAIL-09_08_2025-GO95HV-1^06247007.0018001 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005920 | 262469043-40253-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0099540 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005921 | 262513875-15700-DETAIL-04_08_2026-GO95HV-1^06240002.0329101 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005922 | 262556645-76329-DTLSB-05_04_2026-GO95HV-1^06142013.0061601 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005923 | 262556645-76329-DTLSB-05_04_2026-GRDRODHI-1^06142013.0061601 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005924 | 262772734-51119-ADMIN-03_09_2026-GO95CLSV-1^06242009.0208701 | OTHER | Non-HFTD | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005925 | 262772734-51119-DTLSB-03_09_2026-CUSTWIRE-1^06242009.0208701 | OTHER | Non-HFTD | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005926 | 262865764-21400-DETAIL-10_01_2025-GO95HV-1^06148001.0312902 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005927 | 263228589-67609-DETAIL-08_27_2025-GO95HV-1^06247006.0172900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005928 | 263577480-15970-DETAIL-02_19_2026-GO95HV-1^06239002.0026500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005929 | 263668438-69791-DTLTRT-05_06_2026-GO95HV-1^668038/00 3/058 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005930 | 263737167-40829-DTLSB-08_21_2023-CUSTWIRE-1^06243009.0219205 | OTHER | Non-HFTD | Distribution | 2023-08-21 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005931 | 263778333-79519-DTLSB-04_02_2026-GO95HV-1^06241009.0219200 | OTHER | Non-HFTD | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005932 | 263862039-30689-DTLSB-02_09_2026-GO95MLD-1^06243010.0361101 | OTHER | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005933 | 263872861-88900-DETAIL-05_15_2025-GO95TCH-1^06142012.0112010 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005934 | 263966094-84879-DTLSB-01_27_2026-BIRDDMG-1^06242009.0056202 | POLE | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005935 | 263980893-70369-DTLTRT-06_23_2021-COPLLEAN-1^668041/00 15/032 | POLE | Non-HFTD | Transmission | 2021-06-23 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005936 | 264345053-25929-DRONE_HY-07_10_2026-XARMBRAC-1^06143014.0182300 | CROSSARM | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005937 | 264663364-83583-DETAIL-09_27_2021-CUSTWIRE-1^06148004.0355205 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005938 | 264735926-63370-DRONE_HY-07_10_2026-COVCOTHR-1^06239004.0255144 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-10 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005939 | 264861426-94779-DETAIL-08_12_2025-GO95HV-1^06247006.0263501 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005940 | 265056784-35032-DETAIL-03_06_2025-GRDRODHI-1^06241005.0120600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005941 | 265076648-71748-DETAIL-01_27_2017-CUSTWIRE-1^06144006.0165005 | OTHER | Non-HFTD | Distribution | 2017-01-27 | 2020-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005942 | 912241854-55882-DETAIL-09_05_2025-GO95HV-1^06147001.0292501 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005943 | 912378173-9173-DETAIL-06_18_2025-COVCOTHR-1^668075/00 11/047 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005944 | 912836682-40519-DTLSB-05_19_2026-GO95HV-1^06240008.0131800 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005945 | 912875446-76449-DTLSB-07_09_2025-GO95HV-1^06244006.0276605 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005946 | 912903655-60839-DETAIL-05_08_2025-GO95HV-1^06243006.0105200 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005947 | 912991098-22098-DETAIL-06_19_2025-SVCENTCO-1^06237004.0172403 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005948 | 913004313-98459-DTLTRT-04_20_2026-GO95HV-1^668004/02 12/003 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005949 | 913335686-23152-DETAIL-04_24_2025-GO95HV-1^06242006.0171001 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005950 | 913480404-35822-DETAIL-10_13_2025-GO95BLTC-1^06246012.0124601 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005951 | 913480404-35822-DETAIL-10_13_2025-GUYHINS-1^06246012.0124601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-13 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005952 | 913722041-70180-DETAIL-02_18_2026-GO95HV-1^06239002.0044301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005953 | 913938892-56009-DETAIL-10_16_2025-GO95HV-1^06246011.0277801 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005954 | 91396633-78633-ADMIN-10_30_2025-ENCHRW-1^06246001.0101780 | OTHER | Non-HFTD | Distribution | 2025-10-30 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005955 | 913966506-66779-DETAIL-04_08_2024-CUSTWIRE-1^06147005.0245100 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005956 | 913966506-66779-DETAIL-04_08_2024-GO95MLD-1^06147005.0245100 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005957 | 913977611-90509-DTLSB-11_01_2021-CUSTWIRE-2^06148004.0232601 | OTHER | Non-HFTD | Distribution | 2021-11-01 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005958 | 913977611-90509-DTLSB-11_01_2021-CUSTWIRE-3^06148004.0232601 | OTHER | Non-HFTD | Distribution | 2021-11-01 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005959 | 914000526-88029-DETAIL-04_22_2025-GO95HV-1^06242006.0077900 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005960 | 91413417-73417-DETAIL-06_18_2025-GO95HV-1^668075/00 13X1/046 | OTHER | HFTD Tier 2 | Transmission | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005961 | 914343688-17592-DETAIL-04_23_2024-GO95BLTC-1^06145001.0026304 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005962 | 914458294-45590-DETAIL-03_02_2026-SVCDEFLC-1^06239003.0252702 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005963 | 914683370-42939-DETAIL-05_08_2025-GO95HV-1^06243006.0280800 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005964 | 914693716-55079-DETAIL-06_16_2025-GO95TCH-1^06248004.0364001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005965 | 91510046-88603-DTLTRT-06_30_2025-GUYHINS-1^668087/00 12/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005966 | 91510046-88603-DTLTRT-06_30_2025-GUYNOINS-1^668087/00 12/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005967 | 265136235-75269-DTLSB-07_01_2025-GO95HV-1^06244006.0226305 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005968 | 265136235-75269-DTLSB-07_01_2025-GUYNOINS-1^06244006.0226305 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005969 | 265416121-75589-DTLSB-07_07_2025-GO95HV-1^06245007.0352000 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005970 | 265611094-46353-DETAIL-05_21_2026-GO95TCH-1^07217001.0143509 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005971 | 265614404-64560-DETAIL-01_28_2025-GO95HV-1^06239004.0258500 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005972 | 26564306-59699-DTLSB-03_31_2026-SVCDEFLC-1^06241009.0327700 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005973 | 265659742-21662-DTLTRT-04_28_2026-GO95HV-1^668004/00 11/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005974 | 265659742-64000-DTLTRT-04_28_2026-GO95HV-1^668004/00 11/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005975 | 265966656-8100-DTLSB-05_29_2026-GO95HV-1^07216001.0113601 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005976 | 2662494-47499-DETAIL-08_20_2025-GO95HV-1^06246001.0173701 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005977 | 2663458-89458-DETAIL-09_25_2025-GO95MLD-1^07218001.0230100 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005978 | 266353439-53400-DTLTRT-07_10_2025-GUYNOINS-2^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005979 | 266353439-53400-DTLTRT-07_10_2025-GUYNOINS-3^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005980 | 266353439-53400-DTLTRT-07_10_2025-GUYNOINS-4^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005981 | 266353439-72682-DTLTRT-07_10_2025-GUYNOINS-1^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005982 | 266353439-72682-DTLTRT-07_10_2025-GUYNOINS-2^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005983 | 266353439-73682-DTLTRT-07_10_2025-GO95HV-1^668087/00 4/020 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005984 | 266353439-73682-DTLTRT-07_10_2025-GUYNOINS-1^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005985 | 266353439-73682-DTLTRT-07_10_2025-GUYNOINS-2^668087/00 4/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005986 | 266433342-70559-DETAIL-04_29_2026-GO95HV-1^668004/00 6/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005987 | 266546388-29170-DETAIL-01_23_2025-SVCDEFLC-1^06240004.0080204 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005988 | 266660863-95849-DTLSB-08_11_2025-GO95BLTC-1^07217001.0012503 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005989 | 266931361-97280-DETAIL-02_18_2026-GO95HV-1^06239002.0047400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005990 | 915126703-96369-DETAIL-08_20_2025-GO95HV-1^06247006.0253900 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005991 | 915141841-13120-DETAIL-03_25_2025-COVCOTHR-3^06240004.0272503 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005992 | 915228226-81481-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0366840 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005993 | 915682370-81678-DETAIL-07_02_2026-GO95HV-1^07217001.0048700 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005994 | 915709922-57909-DETAIL-10_16_2025-GO95HV-1^06246011.0354901 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005995 | 915963620-6001-DETAIL-01_31_2025-GO95HV-1^06239004.0136109 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005996 | 916064124-37949-DTLSB-06_24_2025-GO95HV-1^06244007.0034701 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005997 | 916469981-9209-DETAIL-08_04_2025-GO95HV-1^06247006.0209803 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120005998 | 916789955-10055-DETAIL-03_10_2026-ENCHRW-1^06238004.0029606 | OTHER | HFTD Tier 2 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120005999 | 917092352-66039-DETAIL-05_20_2025-GO95HV-1^06243006.0075301 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006000 | 917189076-81789-DETAIL-10_08_2025-GO95HV-1^06148001.0188400 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006001 | 917510885-32299-DETAIL-08_21_2025-GO95HV-1^06247006.0258801 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006002 | 917596695-84399-DETAIL-08_13_2025-GO95HV-1^06247006.0253702 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006003 | 91762665-83820-DETAIL-09_03_2025-GO95HV-1^06246001.0174200 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006004 | 917731798-1173-DETAIL-08_26_2025-GO95HV-1^07216001.0168001 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006005 | 266962984-35729-DTLSB-01_21_2026-BIRDDMG-1^06242009.0298303 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006006 | 266987890-70700-ADMIN-11_12_2025-GO95HV-1^06146001.0311300 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006007 | 267045404-8404-DETAIL-03_29_2023-CUSTWIRE-1^06142016.0084601 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006008 | 267124653-68249-DTLSB-07_16_2025-GO95HV-1^06244006.0268900 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006009 | 267427343-28908-DTLTRT-06_23_2025-GUYHINS-1^668087/00 7/002 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006010 | 267500203-51799-DTLSB-10_02_2024-CUSTWIRE-1^06245007.0218302 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006011 | 267637659-20010-ADMIN-07_25_2025-POLEDERP-1^668038/00 4/068 | POLE | Non-HFTD | Transmission | 2025-07-25 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006012 | 267676365-6251-DETAIL-02_24_2025-SVCROAD-1^06239004.0366707 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006013 | 267724792-37419-DTLSB-07_09_2026-GO95HV-1^06240008.0144501 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006014 | 267991248-21440-DETAIL-11_18_2022-CUSTWIRE-1^06238004.0223407 | OTHER | HFTD Tier 2 | Distribution | 2022-11-18 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006015 | 268032451-28031-DETAIL-02_27_2025-GO95MLD-1^06241005.0177900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006016 | 26815363-67019-DRONE_HY-07_15_2026-UBPBXARM-1^668036/00 15/055 | CROSSARM | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006017 | 268449066-96369-DETAIL-04_24_2025-GO95HV-1^06242006.0192200 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006018 | 268465019-36019-DTLSB-07_22_2025-GO95HV-1^06244006.0197340 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006019 | 268542190-87210-DETAIL-09_29_2025-GO95HV-1^06148001.0310503 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006020 | 268565867-48867-DETAIL-09_29_2025-GO95HV-1^06148001.0317404 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006021 | 268617713-80813-DETAIL-04_29_2024-GO95MLD-1^06142016.0079700 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006022 | 268859866-96849-DTLSB-07_09_2025-GO95HV-1^06244007.0140700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006023 | 268937453-99559-DTLTRT-04_20_2026-GO95HV-1^668004/02 7/005 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006024 | 268970219-27510-DETAIL-08_18_2025-GO95HV-1^06246002.0347900 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006025 | 268970219-27510-DETAIL-08_18_2025-GO95MLD-1^06246002.0347900 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006026 | 269000148-24529-DTLSB-04_29_2026-GO95HV-1^06142013.0285802 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006027 | 269135385-15449-DTLSB-07_09_2025-GO95MLD-1^06244006.0347502 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006028 | 26923633-94570-DTLTRT-05_13_2026-CUSTWIRE-1^668085/00 7/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006029 | 269579830-34543-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0114602 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006030 | 91775263-30069-DETAIL-09_18_2025-GO95HV-1^06248007.0267200 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006031 | 91789651-17909-DETAIL-09_04_2025-GO95HV-1^06247006.0210802 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006032 | 918286095-1803-DETAIL-03_05_2024-CUSTWIRE-1^06245007.0276301 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006033 | 918451009-83069-DTLTRT-06_14_2021-ANCHIDLE-1^668041/00 9/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-14 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006034 | 918451009-83069-DTLTRT-06_14_2021-GO95HV-1^668041/00 9/020 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006035 | 918578034-10459-ADMIN-12_30_2024-POLEDERP-1^07113001.0144200 | POLE | Non-HFTD | Distribution | 2024-12-30 | 2027-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006036 | 918829003-47959-AUDIT-10_01_2025-GRDRODHI-1^06248007.0233400 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006037 | 918844316-66449-DTLSB-07_09_2025-GO95HV-1^06244006.0276500 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006038 | 918863281-44780-DETAIL-02_13_2025-GO95HV-1^06240004.0169143 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006039 | 919326500-9540-DETAIL-01_22_2026-COVCOTHR-1^06239003.0070903 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006040 | 919591451-94639-DETAIL-05_07_2025-GO95HV-1^06243006.0018801 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006041 | 919655688-16688-DETAIL-09_02_2025-GO95HV-1^06247006.0279401 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006042 | 920150099-9212-DETAIL-10_01_2025-GO95HV-1^06148001.0300103 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006043 | 920450923-69930-DETAIL-07_30_2025-GO95HV-1^07218001.0272201 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006044 | 92045880-44779-DTLSB-11_04_2021-CUSTWIRE-1^06148004.0287600 | OTHER | Non-HFTD | Distribution | 2021-11-04 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006045 | 920521085-5739-DETAIL-05_08_2025-GO95HV-1^06243006.0105500 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006046 | 920598690-79222-DETAIL-09_29_2025-GUYHINS-2^06148001.0310508 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006047 | 920724489-61259-DTLTRT-05_07_2026-GUYHINS-1^668004/00 20/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006048 | 920724489-61259-DTLTRT-05_07_2026-GUYHINS-2^668004/00 20/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006049 | 92079919-98159-DETAIL-05_06_2026-ENCHRW-1^668004/00 13/024 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006050 | 921011968-20009-DETAIL-04_10_2024-CUSTWIRE-1^06147005.0164001 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006051 | 921331962-18989-DTLSB-05_04_2026-GO95HV-1^06241009.0035600 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006052 | 921606658-49470-DETAIL-03_24_2026-COVCOTHR-1^06240004.0220706 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006053 | 92187523-79030-DETAIL-05_27_2025-SVCROAD-1^06142012.0111000 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006054 | 922257179-83022-DETAIL-10_01_2025-GO95HV-1^06148001.0303201 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006055 | 269579830-34543-DETAIL-06_25_2026-GO95HV-1^07217001.0114602 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006056 | 269602676-10400-DETAIL-04_07_2026-GO95MLD-1^06240002.0317022 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006057 | 269881255-43255-DETAIL-06_09_2025-GO95HV-1^06245006.0300706 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006058 | 270176934-8934-DETAIL-09_30_2025-GO95HV-1^06148001.0300400 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006059 | 270345184-38189-DETAIL-09_29_2025-GO95HV-1^06148001.0310504 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006060 | 270374085-73479-DETAIL-09_16_2025-ABNDEQPM-1^06247004.0180242 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006061 | 270412298-21019-DTLSB-04_02_2026-GO95HV-1^06241009.0282801 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006062 | 270580043-41043-DETAIL-06_09_2025-GO95MLD-1^668075/00 4/031 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006063 | 271605593-51250-DETAIL-02_04_2025-GO95HV-1^06239004.0134143 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006064 | 271911684-82659-DETAIL-07_28_2025-GO95HV-1^06247005.0301401 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006065 | 272102909-73173-DETAIL-01_21_2025-SVCDEFLC-1^06240004.0091502 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006066 | 272167824-34460-AUDIT-03_13_2025-GO95TCH-1^06239004.0244952 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006067 | 272430601-9410-DETAIL-04_16_2024-GO95HV-1^06145002.0186900 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006068 | 272430601-9410-DETAIL-04_16_2024-INSULDMG-1^06145002.0186900 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006069 | 272561601-90469-DETAIL-02_23_2023-GO95HV-1^668002/00 8/030 | OTHER | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-29 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006070 | 272972881-12043-DTLSB-06_02_2026-GO95HV-1^07216001.0116902 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006071 | 273026474-29540-DTLSB-07_30_2025-GO95MLD-1^07218001.0261704 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006072 | 273329163-32053-DETAIL-09_23_2025-GUYHINS-1^07218001.0229303 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006073 | 273479144-60599-DTLSB-04_23_2026-GO95MLD-1^06241009.0225801 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006074 | 273693774-21314-DETAIL-04_21_2025-GO95TCH-1^06242005.0368740 | OTHER | HFTD Tier 2 | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006075 | 273814173-16149-DETAIL-06_02_2025-GO95HV-1^06244006.0149300 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006076 | 273829389-50160-DTLTRT-05_06_2026-GO95HV-1^668004/00 6/023 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006077 | 273897618-39618-DETAIL-05_21_2026-GUYHINS-1^07217001.0144502 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006078 | 274045714-31679-DETAIL-09_11_2025-GO95BLTC-1^06248007.0230700 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006079 | 274075885-37885-DETAIL-02_12_2026-SVCENTCO-1^06239003.0362702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006080 | 922357068-29022-DETAIL-09_09_2025-GO95HV-1^06146001.0045300 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006081 | 922394063-86222-DTLSB-05_23_2024-GO95MLD-1^06243001.0123000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006082 | 922508313-91434-DETAIL-03_31_2025-SVCROAD-1^06241005.0115604 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006083 | 922723149-73149-DETAIL-02_05_2025-SVCDEFLC-1^06240004.0167108 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006084 | 923020255-83191-DETAIL-05_12_2026-GO95HV-1^668038/00 4/046 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006085 | 923020255-9522-DETAIL-05_12_2026-GO95HV-1^668038/00 4/046 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006086 | 923069149-70249-DETAIL-05_31_2023-CUSTWIRE-1^06243009.0025409 | OTHER | Non-HFTD | Distribution | 2023-05-31 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006087 | 923455680-132-AUDIT-03_27_2024-GO95MLD-1^06147004.0180900 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006088 | 92366401-29821-DETAIL-02_17_2025-GO95MLD-1^06241005.0230100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006089 | 923885358-97849-DTLSB-07_09_2025-GO95HV-1^06244007.0141600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006090 | 924102709-58359-DETAIL-07_22_2025-GO95HV-1^06247005.0059000 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006091 | 924150040-89559-DETAIL-08_05_2025-GO95HV-1^06247005.0206300 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006092 | 924467093-45683-DTLSB-06_04_2026-GO95MLD-1^07216001.0114200 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006093 | 924775554-56590-DETAIL-02_04_2026-GUYHINS-1^06239003.0019702 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006094 | 924796822-38459-DETAIL-04_29_2026-GO95HV-1^668004/00 1/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006095 | 924796822-38460-DETAIL-04_29_2026-GO95HV-1^668004/00 1/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006096 | 924812336-30891-DTLTRT-05_07_2026-GO95HV-1^668038/00 5/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006097 | 924812336-77132-ADMIN-01_08_2026-POLEDERP-1^668038/00 5/054 | POLE | HFTD Tier 2 | Transmission | 2026-01-08 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006098 | 924812336-77132-DTLTRT-05_07_2026-GO95HV-1^668038/00 5/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006099 | 924861285-22600-DETAIL-02_12_2026-GO95HV-1^06239003.0243000 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006100 | 274156982-53610-DETAIL-03_14_2024-GO95HV-1^06147004.0325600 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006101 | 274220164-53609-DETAIL-09_17_2025-GO95HV-1^06246006.0079701 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006102 | 274464619-42810-DTLTRT-06_24_2025-GRDBROKE-1^668087/00 3/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006103 | 274785123-99910-DTLSB-10_16_2025-GRDRODHI-1^06247001.0353000 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006104 | 274975010-17010-DETAIL-08_01_2024-CUSTWIRE-1^06245006.0152901 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006105 | 275150434-80434-DETAIL-07_23_2025-GO95HV-1^06247005.0091901 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006106 | 275370809-1809-DETAIL-08_18_2025-BIRDDMG-1^06247006.0361002 | POLE | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006107 | 275377019-10369-DETAIL-08_26_2025-GO95HV-1^06247006.0285701 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006108 | 275450727-67210-DETAIL-08_05_2025-SVCNEUT-1^06246002.0149000 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006109 | 275576133-29879-DTLSB-01_20_2026-SVCENTBK-1^06242009.0298102 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006110 | 275771819-88649-DTLSB-04_17_2024-GO95MLD-1^06245007.0223403 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006111 | 275825874-33453-DETAIL-07_07_2026-CLMBTRE-1^07217001.0095200 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006112 | 275890732-6009-DETAIL-04_09_2024-GO95MLD-1^06147005.0218601 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006113 | 275890732-6009-DETAIL-04_09_2024-GRDRODHI-1^06147005.0218601 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006114 | 276029368-83450-DETAIL-04_22_2025-GO95HV-1^06240003.0052001 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006115 | 276092593-31693-DETAIL-09_22_2025-GO95HV-1^06248007.0242302 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006116 | 276535323-27323-DETAIL-04_29_2024-ABNDEQPM-1^06142016.0069103 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006117 | 276584593-92010-DTLSB-05_29_2026-GO95MLD-1^07216001.0023602 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006118 | 276616121-11859-DETAIL-07_30_2025-GO95HV-1^06247005.0243900 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006119 | 276660148-78010-DTLSB-04_28_2026-GO95HV-1^06142013.0214403 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006120 | 276660148-78010-DTLSB-04_28_2026-GRDRODHI-1^06142013.0214403 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006121 | 276660148-78010-DTLSB-04_28_2026-GRDRODHI-2^06142013.0214403 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006122 | 276697402-47459-DTLTRT-04_29_2026-GO95HV-1^668004/00 8/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006123 | 276735045-55499-DETAIL-06_17_2025-GO95HV-1^06248004.0282003 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006124 | 276764619-42189-DETAIL-10_14_2025-SVCENTCO-1^06148001.0270701 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006125 | 924884493-23159-DETAIL-08_19_2025-SVCENTCO-1^06247006.0367501 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006126 | 925165909-3082-DETAIL-07_09_2025-GO95HV-1^668087/00 3/022 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006127 | 925165909-80239-DETAIL-07_09_2025-GO95HV-1^668087/00 3/022 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006128 | 925224301-75301-DTLSB-07_17_2025-GO95HV-1^06244006.0214601 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006129 | 925753746-73746-DETAIL-01_22_2026-GO95MLD-1^06239004.0267800 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006130 | 926145179-30943-DETAIL-06_17_2025-GO95HV-1^06248004.0352342 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006131 | 926379750-68422-DTLTRT-04_27_2026-GO95HV-1^668004/00 7/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006132 | 926379750-90742-DTLTRT-04_27_2026-GO95HV-1^668004/00 7/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006133 | 926524366-33953-DTLSB-06_16_2026-GO95HV-1^07217001.0356702 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006134 | 927417506-96953-DTLSB-06_16_2026-GO95HV-1^07217001.0356803 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006135 | 927955433-2839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0262401 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006136 | 927993660-44073-DETAIL-06_16_2025-GO95HV-1^06248005.0327201 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006137 | 928416398-90052-DETAIL-04_27_2026-SVCROAD-1^06142012.0142801 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006138 | 928527350-96739-DTLTRT-06_25_2025-GO95HV-1^668087/00 9/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006139 | 928710338-60452-DTLTRT-06_24_2025-GO95HV-1^668087/00 3/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006140 | 928760186-67491-DETAIL-05_11_2026-GO95HV-1^668038/00 1/052 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006141 | 928781501-57452-DTLSB-06_05_2026-GUYHINS-1^07216001.0027903 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006142 | 928818274-53659-DETAIL-07_28_2025-GO95HV-1^06247005.0303600 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006143 | 928986915-27933-DETAIL-06_10_2024-ENCHRW-1^06245007.0346702 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006144 | 929384843-70330-DETAIL-02_26_2025-SVCDEFLC-1^06240004.0066002 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006145 | 929405187-68652-ADMIN-10_30_2025-GO95HV-1^06246001.0040600 | OTHER | Non-HFTD | Distribution | 2025-10-30 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006146 | 929457964-20613-DTLSB-04_25_2024-CUSTWIRE-1^06245007.0229745 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006147 | 929565088-17252-DETAIL-09_02_2025-GO95HV-1^06246001.0201901 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006148 | 929605874-71909-DETAIL-08_13_2025-GO95HV-1^06247006.0256400 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006149 | 929693382-46370-DETAIL-01_23_2023-CUSTWIRE-1^06240004.0087004 | OTHER | HFTD Tier 2 | Distribution | 2023-01-23 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006150 | 276839411-60511-DETAIL-09_18_2025-GO95HV-1^07218001.0086800 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006151 | 277081250-57701-DETAIL-04_10_2025-GO95HV-1^06241005.0031704 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006152 | 277081250-57701-DETAIL-04_10_2025-GO95MLD-1^06241005.0031704 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006153 | 277137569-72812-DETAIL-04_16_2025-GO95MLD-1^06242005.0362401 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006154 | 277455091-23029-DETAIL-09_08_2025-GO95HV-1^06147001.0299003 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006155 | 277495043-31780-DETAIL-02_23_2026-BIRDDMG-1^06239002.0153101 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006156 | 277506-8506-DETAIL-01_22_2026-GO95MLD-1^06239004.0233002 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006157 | 277518566-43953-DTLSB-06_16_2026-GO95HV-1^07217001.0356701 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006158 | 277742718-3718-DTLSB-06_24_2026-GO95TCH-1^07217001.0345740 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006159 | 278178704-83020-DTLTRT-06_23_2025-GO95HV-1^668087/02 2/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006160 | 278244754-45020-DTLTRT-06_30_2025-GO95HV-1^668087/02 4/001 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006161 | 278396404-40660-DETAIL-04_28_2025-GO95MLD-1^06239002.0063204 | OTHER | HFTD Tier 2 | Distribution | 2025-04-28 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006162 | 278521662-85139-DETAIL-05_15_2024-ENCHRW-1^06142012.0126802 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006163 | 278681306-30299-DETAIL-06_09_2025-GO95MLD-1^06245007.0244400 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006164 | 278894841-93053-DETAIL-07_29_2025-GO95BLTC-1^06247006.0206103 | OTHER | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006165 | 279024491-79480-DETAIL-02_14_2025-GO95TCH-1^06240004.0168045 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006166 | 279263283-75159-DETAIL-08_18_2025-GO95BLTC-1^06247006.0365401 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006167 | 27940535-39800-DETAIL-04_09_2026-GO95HV-1^06240002.0310102 | OTHER | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006168 | 279518095-68059-DETAIL-08_20_2025-GO95HV-1^06247006.0368200 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006169 | 279546145-27040-DTLSB-07_24_2025-GO95HV-1^07218001.0265802 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006170 | 929824925-21863-DETAIL-05_22_2026-GO95HV-1^07217001.0144402 | OTHER | Non-HFTD | Distribution | 2026-05-22 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006171 | 930351031-9762-DETAIL-09_30_2025-SVCENTCO-1^06148001.0310813 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006172 | 930488136-81162-DETAIL-08_05_2025-GO95HV-1^06246002.0134200 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006173 | 930509958-73269-DTLSB-07_07_2025-GO95TCH-1^06244007.0039007 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006174 | 930586285-22363-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0037100 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006175 | 930586285-22363-DETAIL-06_25_2026-GO95HV-1^07217001.0037100 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006176 | 930686389-36343-DETAIL-07_28_2025-GO95HV-1^06247005.0196200 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006177 | 930700109-40109-DETAIL-06_03_2025-GO95HV-1^06245007.0241503 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006178 | 930728792-34070-DETAIL-03_10_2026-COVCOTHR-1^06238004.0125800 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006179 | 930728792-34070-DETAIL-03_10_2026-COVCOTHR-2^06238004.0125800 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006180 | 930992555-78310-DETAIL-03_12_2025-GO95HV-1^06238004.0223801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006181 | 931030268-85362-DETAIL-09_03_2025-GO95HV-1^06246001.0207901 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006182 | 931152741-97762-DETAIL-09_11_2025-GO95HV-1^07216001.0078600 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006183 | 931316814-28822-ADMIN-10_20_2025-GO95BLTC-1^06246012.0122301 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006184 | 931610932-93889-DETAIL-07_31_2025-GO95HV-1^06247005.0244000 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006185 | 93171801-36589-DETAIL-05_15_2025-GO95MLD-1^06243006.0167402 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006186 | 932016692-15080-DETAIL-02_25_2025-SVCNEUT-1^06240005.0015001 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006187 | 932180009-6220-DETAIL-01_28_2025-GO95HV-1^06240004.0085042 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006188 | 932634951-86439-DETAIL-05_08_2025-GO95HV-1^06243006.0162101 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006189 | 932875569-27091-DETAIL-04_10_2025-GO95HV-1^06241005.0030600 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006190 | 933076134-10334-DETAIL-04_09_2024-CUSTWIRE-1^06147005.0219520 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006191 | 933130145-96872-DETAIL-09_02_2025-GO95HV-1^06246001.0174102 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006192 | 933231648-86972-DETAIL-09_04_2025-GO95HV-1^06146001.0050301 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006193 | 933292709-33709-DETAIL-08_18_2025-GO95HV-1^06247006.0364000 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006194 | 933347626-74849-DTLSB-07_10_2025-GO95HV-1^06244007.0115340 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006195 | 933426635-47049-AUDIT-10_22_2025-GO95MLD-1^07216001.0048104 | OTHER | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006196 | 93351588-16811-DETAIL-06_26_2026-GO95HV-1^07217001.0031901 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006197 | 93355921-71449-DETAIL-04_24_2024-SVCROAD-2^06245007.0225604 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006198 | 93396339-59052-DTLSB-07_16_2025-GO95HV-1^06244006.0314342 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006199 | 934316526-53599-DTLSB-03_16_2026-GO95HV-1^06242009.0136202 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006200 | 934621735-21409-DETAIL-08_25_2025-SVCDEFLC-1^06247006.0263902 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006201 | 934705253-59799-DETAIL-08_20_2025-GRDRODHI-1^06247006.0256601 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006202 | 934724932-34139-DETAIL-05_15_2024-RISEBKSP-1^06142012.0126801 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006203 | 934863220-87289-DETAIL-08_12_2025-GO95TCH-1^06246001.0300100 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006204 | 934898711-45750-DETAIL-02_26_2026-GO95MLD-1^06238004.0027700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006205 | 934993719-88389-DETAIL-09_30_2025-GO95BLTC-1^06246009.0133200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006206 | 935266788-91670-DETAIL-04_06_2026-PWRTRN-1^06236005.0109401 | OTHER | HFTD Tier 2 | Distribution | 2026-04-06 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006207 | 935289378-36478-DETAIL-07_13_2023-CUSTWIRE-1^06244008.0337900 | OTHER | HFTD Tier 2 | Distribution | 2023-07-13 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006208 | 935842124-43529-DETAIL-05_02_2022-CUSTWIRE-1^06143013.0190903 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006209 | 936635328-81082-DTLTRT-06_23_2025-GO95HV-1^668087/00 18/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006210 | 936642890-25840-DETAIL-03_19_2025-GUYHINS-1^06238004.0029504 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006211 | 936865711-62330-DTLTRT-05_28_2025-GO95HV-1^668075/00 7/007 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006212 | 936895460-47570-DETAIL-02_18_2026-GO95HV-1^06239002.0093100 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006213 | 93699651-85379-DETAIL-07_31_2025-GO95HV-1^06247006.0204401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006214 | 937045199-53999-DETAIL-06_16_2025-GO95HV-1^06248004.0356441 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006215 | 937142849-21859-DETAIL-06_16_2025-COPLLEAN-1^06248005.0330841 | POLE | Non-HFTD | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006216 | 937298079-20179-DETAIL-08_21_2025-GO95HV-1^06247006.0268902 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006217 | 937413341-98689-ADMIN-10_10_2024-POLEREPL-1^06146002.0034500 | POLE | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006218 | 93755278-91260-DETAIL-09_15_2025-GO95HV-1^07219001.0326200 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006219 | 937559121-77062-DTLSB-07_17_2025-GO95HV-1^06244006.0210800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006220 | 937656441-16639-DETAIL-05_07_2025-GO95HV-1^06243006.0015800 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006221 | 937746934-57253-DETAIL-07_02_2026-GO95HV-1^07217001.0033700 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006222 | 937798175-43900-DETAIL-03_27_2025-SVCNEUT-1^06239003.0018905 | OTHER | HFTD Tier 2 | Distribution | 2025-03-27 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006223 | 93797588-29588-DETAIL-09_24_2025-GO95HV-1^07218001.0229103 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006224 | 938362990-99270-DETAIL-02_12_2025-CUSTWIRE-1^06240004.0166511 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006225 | 939013379-25019-DTLSB-05_19_2026-GO95HV-1^06240007.0181301 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006226 | 939329968-62590-DETAIL-01_14_2025-GO95HV-1^06239004.0255206 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006227 | 939344463-39463-DTLSB-05_28_2026-GO95HV-1^07216001.0021001 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006228 | 939389054-33229-DETAIL-05_07_2025-GO95HV-1^06242007.0234002 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006229 | 939516087-98439-AUDIT-09_16_2025-SVCROAD-1^668087/00 8/001 | OTHER | Non-HFTD | Transmission | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006230 | 939516087-98439-DTLTRT-06_23_2025-BIRDDMG-1^668087/00 8/001 | POLE | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006231 | 939534804-56353-DETAIL-09_23_2025-GO95HV-1^07218001.0224601 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006232 | 939655536-65491-DETAIL-05_11_2026-GO95HV-1^668038/00 1/051 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006233 | 939737846-9589-DETAIL-08_11_2025-GO95BLTC-1^06247006.0268301 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006234 | 939947713-7679-DETAIL-03_05_2025-GO95HV-1^06241005.0131802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006235 | 939980780-32479-DTLSB-04_22_2026-GO95MLD-1^06241008.0309300 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006236 | 939998759-28509-DETAIL-09_30_2025-ABNDEQPM-1^06246009.0136203 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006237 | 94019936-18570-DETAIL-01_24_2025-GO95HV-1^06239004.0257842 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006238 | 94019936-18570-DETAIL-01_24_2025-SVCROAD-1^06239004.0257842 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006239 | 940300783-38150-DETAIL-01_24_2025-GO95HV-1^06239004.0258600 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006240 | 940346603-74439-DTLTRT-05_13_2026-GO95HV-1^668085/00 1/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006241 | 940475534-6189-DETAIL-09_09_2025-GO95HV-1^06147001.0295000 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006242 | 940688292-26092-DETAIL-04_03_2025-GUYHINS-1^06241005.0115541 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006243 | 941133908-45542-DETAIL-04_23_2025-GO95HV-1^06242006.0039203 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006244 | 94143371-84380-DETAIL-02_16_2026-GO95HV-1^06239001.0048700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006245 | 279709423-46680-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0166203 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006246 | 279814854-84063-DETAIL-08_27_2025-GO95HV-1^06247006.0187701 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006247 | 279854620-23999-DTLSB-07_15_2025-GO95HV-1^06244006.0288740 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006248 | 279883821-8120-DETAIL-03_30_2026-SVCTREE-1^06240004.0273001 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006249 | 280128201-87099-DETAIL-03_15_2022-CUSTWIRE-1^06148006.0288400 | OTHER | Non-HFTD | Distribution | 2022-03-15 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006250 | 280336934-94922-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0269040 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006251 | 280554753-12253-DETAIL-06_25_2026-SVCROAD-1^07217001.0099401 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006252 | 280790691-53691-DETAIL-09_24_2025-GO95HV-1^07218001.0223202 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006253 | 280808237-48469-DETAIL-08_21_2025-GO95HV-1^06247006.0264800 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006254 | 2809218-24549-DTLSB-07_16_2025-GO95HV-1^06244006.0317401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006255 | 280945260-18459-DETAIL-07_23_2025-GO95HV-1^06247005.0177402 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006256 | 281019208-42239-DETAIL-03_20_2024-CUSTWIRE-1^06244005.0142302 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006257 | 281314061-20709-DETAIL-09_08_2025-GO95HV-1^06246006.0055402 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006258 | 281425231-67280-DETAIL-01_23_2026-COVCOTHR-1^06240004.0238900 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006259 | 281425231-67280-DETAIL-01_23_2026-COVCOTHR-2^06240004.0238900 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006260 | 281425231-67280-DETAIL-01_23_2026-COVCOTHR-3^06240004.0238900 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006261 | 281425231-67280-DETAIL-01_23_2026-COVCOTHR-4^06240004.0238900 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006262 | 281590352-80520-DETAIL-03_30_2026-COVCOTHR-1^06240004.0271142 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006263 | 281923440-78420-DTLTRT-05_05_2026-GO95HV-1^668004/00 6X/001 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006264 | 282003912-22019-DRONE_HY-07_15_2026-UBPRMSHD-1^668036/00 15/054 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120006265 | 282112213-24249-DETAIL-07_21_2025-GO95BLTC-1^06244006.0257901 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006266 | 282172266-38739-DETAIL-07_06_2026-GO95BLTC-1^07218001.0349200 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006267 | 282187279-21720-DTLTRT-05_04_2026-GRDRODHI-1^668038/00 7/068 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006268 | 282352504-4490-DETAIL-02_10_2026-GO95HV-1^06239003.0016808 | OTHER | Non-HFTD | Distribution | 2026-02-10 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006269 | 282419588-27260-DETAIL-09_15_2025-GRDRODHI-1^07219001.0327301 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006270 | 282495316-93593-DETAIL-08_21_2025-SVCENTCO-1^06247006.0267702 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006271 | 941486768-71870-DETAIL-02_26_2025-GO95TCH-1^06240004.0060301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006272 | 94247353-87353-DETAIL-06_17_2025-GO95HV-1^668075/00 13/042 | OTHER | HFTD Tier 2 | Transmission | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006273 | 942559981-61689-DTLSB-01_26_2026-GO95HV-1^06242009.0295600 | OTHER | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006274 | 942749641-87201-DETAIL-01_21_2025-GO95MLD-1^06239004.0255545 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006275 | 942856909-52003-DETAIL-09_08_2025-GO95HV-1^06147001.0328201 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006276 | 942911305-46003-DETAIL-09_02_2025-GO95HV-1^06246001.0173004 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006277 | 942923278-69129-DETAIL-04_21_2026-GO95HV-1^06142012.0148807 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006278 | 942924736-5659-DETAIL-04_30_2026-GO95HV-1^668004/00 1/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006279 | 942942496-8203-DTLTRT-05_21_2026-GO95MLD-1^668086/00 7/015 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006280 | 943096492-55253-DETAIL-07_23_2025-GO95HV-1^06247005.0176400 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006281 | 943097250-76239-DETAIL-08_25_2025-GO95HV-1^07216001.0179604 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006282 | 943338765-96989-DTLSB-07_10_2025-ABNDEQPM-1^06244006.0343700 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006283 | 943672743-33743-DTLSB-07_23_2025-GO95HV-1^07218001.0264907 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006284 | 943693294-59460-DETAIL-01_23_2025-GO95HV-1^06239004.0257704 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006285 | 943773935-54935-DTLSB-06_30_2025-GO95BLTC-1^06244006.0223404 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006286 | 943773935-54935-DTLSB-06_30_2025-GO95MLD-1^06244006.0223404 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006287 | 943919313-71022-DETAIL-05_30_2025-GO95HV-1^06244006.0146541 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006288 | 943990904-22508-DTLTRT-07_01_2025-GUYNOINS-1^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006289 | 943990904-22508-DTLTRT-07_01_2025-GUYNOINS-2^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006290 | 943990904-22508-DTLTRT-07_01_2025-GUYNOINS-3^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006291 | 943990904-22508-DTLTRT-07_01_2025-GUYNOINS-4^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006292 | 943990904-24904-DTLTRT-07_01_2025-GUYNOINS-1^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006293 | 943990904-2734-ADMIN-11_10_2025-POLEDERP-1^668087/00 6/016 | POLE | Non-HFTD | Transmission | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006294 | 943990904-2734-DTLTRT-07_01_2025-GUYNOINS-2^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006295 | 944212548-34282-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 1/016 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006296 | 944286126-49540-DETAIL-07_06_2026-CUSTWIRE-1^07218001.0342800 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006297 | 945069234-1334-DETAIL-03_28_2023-CUSTWIRE-1^06142016.0083700 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006298 | 945219574-63253-DETAIL-06_25_2026-CUSTWIRE-1^07217001.0039201 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006299 | 945487812-6943-DETAIL-09_24_2025-GUYHINS-1^07218001.0237101 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-24 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006300 | 9457743-9743-DTLSB-07_21_2025-SVCENTBK-1^06244006.0230501 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006301 | 945916901-71683-DTLSB-06_05_2026-GO95HV-1^07216001.0235702 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006302 | 946100998-40998-DETAIL-09_11_2025-GO95HV-1^06248007.0228801 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006303 | 9461253-40899-DTLSB-01_21_2026-GO95HV-1^06242009.0297111 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006304 | 9461253-40899-DTLSB-01_21_2026-SVCROAD-1^06242009.0297111 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006305 | 28261292-58520-DETAIL-03_30_2026-COVCOTHR-1^06240004.0270403 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006306 | 282727743-57743-DETAIL-06_17_2025-GO95HV-1^668075/00 9/042 | OTHER | HFTD Tier 2 | Transmission | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006307 | 282775706-60519-DTLSB-07_08_2026-GO95HV-1^06242009.0240101 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006308 | 283201923-83494-DETAIL-05_13_2025-GO95TCH-1^06242004.0311704 | OTHER | HFTD Tier 2 | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006309 | 283381227-26129-DETAIL-04_20_2026-GO95HV-1^06142012.0143908 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006310 | 283469119-31520-DETAIL-09_05_2025-GO95HV-1^06147001.0294100 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006311 | 283527964-9139-DTLSB-05_04_2026-GO95HV-1^06142013.0054700 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006312 | 283621615-61359-DTLSB-07_03_2025-GO95BLTC-1^06245007.0358702 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006313 | 283750268-94440-DETAIL-03_05_2026-COVCOTHR-1^06238004.0145901 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006314 | 283955453-46290-DRONE_HY-06_19_2026-COVCOTHR-1^06240004.0176201 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006315 | 284048999-35419-DTLSB-07_09_2026-GO95HV-1^06240008.0159200 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006316 | 284048999-35419-DTLSB-07_09_2026-POLETOP-1^06240008.0159200 | POLE | Non-HFTD | Distribution | 2026-07-09 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006317 | 2842796-10170-DETAIL-01_24_2025-GO95HV-1^06239004.0257941 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006318 | 284409200-92032-DETAIL-04_02_2025-GO95TCH-1^06241005.0117703 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006319 | 284409200-92032-DETAIL-04_02_2025-GUYHINS-1^06241005.0117703 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006320 | 284409200-92032-DETAIL-04_02_2025-GUYHINS-3^06241005.0117703 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006321 | 284533601-49201-DETAIL-01_31_2025-GO95HV-1^06239004.0135005 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006322 | 284974393-49259-DTLTRT-04_22_2026-GO95HV-1^668004/02 3/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006323 | 285139944-18651-DETAIL-05_13_2025-GO95CL10-1^06242004.0313801 | OTHER | HFTD Tier 2 | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006324 | 285270254-76860-DETAIL-01_21_2025-SVCENTCO-1^06239004.0256203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006325 | 285404995-64189-DTLSB-10_07_2024-CUSTWIRE-1^06245007.0230401 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006326 | 285760762-23208-DTLTRT-06_23_2025-GUYHINS-1^668087/00 7A/002 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006327 | 285760762-23208-DTLTRT-06_23_2025-GUYLOINS-2^668087/00 7A/002 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006328 | 285794318-1599-ADMIN-10_23_2025-GO95HV-1^06246011.0362000 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006329 | 286095189-21019-DTLSB-04_14_2026-GO95HV-1^06241008.0237301 | OTHER | Non-HFTD | Distribution | 2026-04-14 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006330 | 946713483-85313-DETAIL-09_05_2025-GO95HV-1^06147001.0171200 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006331 | 9467669-92859-DETAIL-08_13_2025-ABNDEQPM-1^06246002.0364500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006332 | 9467669-92859-DETAIL-08_13_2025-GO95HV-1^06246002.0364500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006333 | 946772606-93589-DETAIL-09_08_2025-ABNDEQPM-1^06247007.0015201 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006334 | 946782098-92369-DETAIL-03_17_2026-COVCOTHR-1^06240004.0221406 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006335 | 946782098-92369-DETAIL-03_17_2026-COVCOTHR-2^06240004.0221406 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006336 | 947131991-28922-DTLTRT-04_23_2026-GO95HV-1^668004/00 1/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006337 | 947327475-26899-DTLSB-04_22_2026-GO95HV-1^06241009.0248101 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006338 | 947395490-64939-DETAIL-05_08_2025-GO95HV-1^06243006.0287801 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006339 | 94753726-96730-DETAIL-05_15_2025-GO95HV-1^06142012.0117000 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006340 | 947650105-74933-DETAIL-09_16_2025-GO95HV-1^06247004.0081640 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006341 | 947973990-69559-AUDIT-07_22_2025-ABNDEQPM-1^06248004.0341901 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006342 | 948212637-55798-DETAIL-01_15_2026-BIRDDMG-1^06239004.0136104 | POLE | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006343 | 948332196-43760-DETAIL-04_30_2026-GO95HV-1^668004/00 8/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006344 | 948643375-27375-DETAIL-06_05_2025-GO95HV-1^06148014.0237400 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006345 | 948869784-79253-DETAIL-05_26_2026-GRDRODHI-1^07217001.0140501 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006346 | 9489543-34750-DETAIL-01_20_2026-GO95MLD-1^06239004.0134200 | OTHER | HFTD Tier 3 | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006347 | 948960342-53589-DETAIL-05_20_2025-GO95HV-1^06243006.0077201 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006348 | 949333692-64339-DETAIL-05_08_2025-GO95HV-1^06243006.0217101 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006349 | 949639141-83720-DETAIL-03_30_2026-COVCOTHR-1^06240004.0272402 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006350 | 949767349-88409-DETAIL-09_30_2025-GO95HV-1^06246009.0132401 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006351 | 949792741-12180-DETAIL-02_06_2025-SVCROOF-1^06240004.0166304 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006352 | 94987176-70276-DETAIL-08_21_2025-GO95HV-1^06247006.0266900 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006353 | 949905588-60979-DTLSB-07_08_2025-ANCHIDLE-1^06244007.0036640 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006354 | 950032709-41439-DTLTRT-06_25_2025-GUYHINS-1^668087/00 18/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006355 | 286130843-26709-DETAIL-09_08_2025-GO95HV-1^06247007.0129001 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006356 | 286471070-5979-DETAIL-10_07_2025-GO95TCH-1^06148001.0311904 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006357 | 28652134-15179-DETAIL-06_17_2025-GO95HV-1^06248004.0283002 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006358 | 286638443-19443-DETAIL-03_23_2026-CUSTWIRE-1^06240004.0219800 | OTHER | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006359 | 286865899-45852-DTLSB-07_17_2025-GO95HV-1^06244006.0308443 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006360 | 287034526-3899-DETAIL-03_25_2024-CUSTWIRE-1^06244005.0146101 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006361 | 287503670-7379-DTLSB-04_22_2026-GO95HV-1^06241009.0258800 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006362 | 287618413-33720-DETAIL-09_09_2025-GO95HV-1^06147001.0199800 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006363 | 287833345-6345-ADMIN-10_23_2025-GO95MLD-1^07219001.0323307 | OTHER | Non-HFTD | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006364 | 288044891-70030-DETAIL-09_11_2025-GO95HV-1^06147001.0050501 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006365 | 288503882-4689-DETAIL-07_22_2025-ABNDEQPM-1^06247005.0175301 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006366 | 288503882-4689-DETAIL-07_22_2025-GO95HV-1^06247005.0175301 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006367 | 288932223-74223-DETAIL-02_18_2025-GO95TCH-1^06240004.0220610 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006368 | 289353241-63792-DETAIL-05_12_2025-GO95HV-1^06243006.0210200 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006369 | 289713876-73059-DETAIL-07_29_2025-GO95HV-1^06247005.0269800 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006370 | 289859095-3030-DTLSB-05_13_2024-GO95MLD-1^06244001.0108101 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006371 | 289882848-62850-DETAIL-04_22_2025-GO95HV-1^06240003.0058800 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006372 | 289917924-66759-DETAIL-06_16_2025-GO95HV-1^06248005.0368901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006373 | 289982187-53970-DETAIL-02_26_2025-GO95TCH-1^06240004.0061203 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006374 | 290070639-92283-DETAIL-08_21_2025-CONDCOIL-1^07216001.0177700 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006375 | 29015773-25839-DTLTRT-05_13_2026-GO95BLTC-1^668085/00 6/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006376 | 290232779-11230-DTLTRT-06_25_2025-GO95HV-1^668087/00 2/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006377 | 290356572-9049-DTLSB-07_16_2025-GO95HV-1^06244006.0234000 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006378 | 290531146-3899-DTLSB-06_25_2025-GRDRODHI-1^06244007.0106903 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006379 | 290531146-3899-DTLSB-06_25_2025-SVCENTCO-1^06244007.0106903 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006380 | 29100283-63779-DETAIL-09_17_2025-GRDRODHI-2^06147001.0237600 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006381 | 950032709-41439-DTLTRT-06_25_2025-GUYHINS-2^668087/00 18/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006382 | 950032709-41439-DTLTRT-06_25_2025-GUYHINS-3^668087/00 18/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006383 | 950055566-38770-DRONE_HY-07_01_2026-COVCOTHR-1^06239004.0363302 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006384 | 950055566-38770-DRONE_HY-07_01_2026-COVCOTHR-2^06239004.0363302 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006385 | 950101791-10323-DETAIL-10_01_2025-GO95HV-1^06148001.0303203 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006386 | 950479300-3843-DETAIL-07_01_2026-GO95MLD-1^07217001.0154500 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006387 | 950523361-13299-DETAIL-10_02_2025-GO95BLTC-1^06246008.0063202 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006388 | 950651328-18490-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244413 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006389 | 950651328-18490-DETAIL-01_12_2026-COVCOTHR-2^06239004.0244413 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006390 | 951114914-10119-DTLSB-03_31_2026-SVCTREE-1^06241009.0327801 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006391 | 9511881-73881-AUDIT-11_03_2025-GO95HV-1^06247001.0345003 | OTHER | Non-HFTD | Distribution | 2025-11-03 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006392 | 9511881-73881-DTLSB-10_16_2025-GRDRODHI-1^06247001.0345003 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006393 | 951411074-79099-DETAIL-09_04_2025-GO95HV-1^06247006.0188501 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006394 | 951466049-32533-DETAIL-08_18_2025-GO95HV-1^06246002.0345301 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006395 | 951714734-91133-DETAIL-09_08_2025-GO95HV-1^06246001.0176702 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006396 | 952025963-82433-DTLSB-05_28_2026-CUSTWIRE-1^07216001.0020600 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006397 | 952300818-79439-DTLTRT-06_23_2025-GRDRODHI-1^668087/00 9/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006398 | 952465983-36983-DETAIL-05_14_2025-GUYNOINS-1^06142012.0119803 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-14 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006399 | 952500915-13589-DETAIL-07_31_2025-GO95HV-1^06247006.0200600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006400 | 952757517-92333-DTLTRT-06_23_2025-GUYHINS-1^668087/00 9/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006401 | 95276056-30-DTLSB-05_04_2026-GO95HV-1^06142013.0177501 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006402 | 952777684-26759-DETAIL-06_16_2025-GO95HV-1^06248005.0368801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006403 | 952803304-51679-DETAIL-08_19_2025-GO95HV-1^06247006.0367302 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006404 | 953041188-91188-DETAIL-06_19_2025-GUYHINS-2^668075/00 3X/049 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-19 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006405 | 95318892-53339-DETAIL-05_08_2025-SVCNEUT-1^06243006.0218200 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006406 | 291246674-86040-DETAIL-02_26_2025-GO95TCH-1^06240004.0218901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006407 | 291811964-77030-DETAIL-01_28_2025-GO95BLTC-1^06240004.0070900 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006408 | 291814458-83459-DETAIL-06_03_2024-CUSTWIRE-1^06246005.0315701 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006409 | 291814458-83459-DETAIL-06_03_2024-GO95MLD-1^06246005.0315701 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006410 | 291952204-45029-DETAIL-08_20_2025-SVCDEFLC-1^06247006.0255806 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006411 | 291952204-45029-DETAIL-08_20_2025-SVCROAD-1^06247006.0255806 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006412 | 292294334-47334-DTLTRT-07_08_2025-BIRDDMG-1^668087/00 9/027 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006413 | 292421085-12799-DTLSB-01_28_2026-GO95MLD-1^06242009.0053300 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006414 | 292505499-96498-DETAIL-04_17_2025-GO95HV-1^06242006.0035800 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006415 | 292801401-81401-DTLSB-06_30_2025-GO95TCH-1^06244006.0224305 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006416 | 292873370-61890-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0258003 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006417 | 293077087-19160-DETAIL-06_09_2025-GO95HV-1^06245006.0191301 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006418 | 293077087-19160-DETAIL-06_09_2025-GRDRODHI-1^06245006.0191301 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006419 | 293077087-19160-DETAIL-06_09_2025-GRDRODHI-2^06245006.0191301 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006420 | 293082021-86021-DETAIL-10_06_2025-GO95HV-1^06243007.0253300 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006421 | 29384499-86989-DETAIL-06_16_2025-GO95HV-1^06248004.0356440 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006422 | 293918093-7083-DETAIL-09_17_2025-GRDRODHI-1^07218001.0088800 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006423 | 294109894-81390-DETAIL-01_27_2026-SVCROAD-1^06239002.0062502 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006424 | 294109894-81390-DETAIL-04_29_2025-GRDRODHI-1^06239002.0062502 | OTHER | Non-HFTD | Distribution | 2025-04-29 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006425 | 294114746-6849-DTLSB-07_09_2025-GO95HV-1^06244007.0142801 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006426 | 294225621-9280-DETAIL-02_02_2026-COVCOTHR-1^06240004.0317603 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006427 | 294253638-44582-ADMIN-11_10_2025-POLEDERP-1^668087/00 4/017 | POLE | Non-HFTD | Transmission | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006428 | 294253638-64330-ADMIN-11_10_2025-POLEDERP-1^668087/00 4/017 | POLE | Non-HFTD | Transmission | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006429 | 294253638-83560-ADMIN-11_10_2025-POLEDERP-1^668087/00 4/017 | POLE | Non-HFTD | Transmission | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006430 | 294370556-16430-DTLSB-05_29_2026-GO95MLD-1^07216001.0112503 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006431 | 953302361-5630-DTLTRT-05_28_2025-GO95HV-1^668075/00 4/006 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006432 | 953389205-21579-ADMIN-04_03_2024-ABNDEQPM-1^06147005.0142006 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006433 | 95343738-50194-ADMIN-03_04_2026-COPLLEAN-1^07216001.0261506 | POLE | Non-HFTD | Distribution | 2026-03-04 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006434 | 953515929-61733-DTLSB-06_15_2026-CUSTWIRE-1^07217001.0278501 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006435 | 953515929-61733-DTLSB-06_15_2026-SVCENTBK-1^07217001.0278501 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006436 | 953960161-40801-DETAIL-06_19_2025-ABNDEQPM-1^06237004.0172102 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006437 | 954019589-72939-DETAIL-05_08_2025-GO95HV-1^06243006.0285900 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006438 | 954031658-23233-DETAIL-08_18_2025-GO95BLTC-1^06246002.0357901 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006439 | 954110388-54998-DETAIL-04_02_2025-GUYNOINS-2^06241005.0118700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006440 | 95453113-84309-DETAIL-07_31_2025-GO95HV-1^06247005.0210002 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006441 | 954714811-83879-DETAIL-07_31_2025-GO95HV-1^06247006.0208700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006442 | 95476769-94849-DETAIL-09_04_2025-GO95HV-1^07216001.0097201 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006443 | 954828837-33829-DTLSB-08_17_2023-CUSTWIRE-1^06243009.0215201 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006444 | 955265359-43251-DETAIL-04_03_2025-GO95MLD-1^06241005.0092001 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006445 | 955324054-71529-DETAIL-04_23_2026-GO95HV-1^06142012.0146803 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006446 | 95534470-48470-DETAIL-08_14_2025-GO95HV-1^06247006.0361601 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006447 | 95534470-48470-DETAIL-08_14_2025-GRDRODHI-1^06247006.0361601 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006448 | 955510708-77779-DETAIL-08_07_2025-GO95HV-1^06246002.0265901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006449 | 95584212-16212-DTLSB-07_09_2025-GO95HV-1^06244006.0276200 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006450 | 955949363-34980-DETAIL-02_23_2026-GO95HV-1^06239002.0224901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006451 | 955968286-34809-DETAIL-09_08_2025-GO95HV-1^06247007.0017001 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006452 | 956455860-51901-DETAIL-04_10_2025-ENCHRW-1^06241005.0031701 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006453 | 956941723-80341-DETAIL-04_15_2025-GO95TCH-1^06242005.0334804 | OTHER | HFTD Tier 2 | Distribution | 2025-04-15 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006454 | 956993291-22022-DTLTRT-04_27_2026-GO95HV-1^668004/00 3/004 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006455 | 956993291-89543-DTLTRT-04_27_2026-GO95HV-1^668004/00 3/004 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006456 | 294675666-52699-DTLSB-03_16_2026-GO95HV-1^06242009.0136400 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006457 | 294675666-52699-DTLSB-03_16_2026-GO95MLD-1^06242009.0136400 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006458 | 294720810-36599-DETAIL-05_19_2025-GO95BLTC-1^06243006.0288702 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006459 | 295005378-26459-DETAIL-08_05_2025-POLETOP-1^06247005.0201903 | POLE | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006460 | 295202486-48602-DTLTRT-04_17_2024-CUSTWIRE-1^668067/00 2/020 | OTHER | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006461 | 295577999-28930-DTLTRT-05_27_2025-GO95HV-1^668075/00 17/003 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006462 | 29579609-28590-DETAIL-09_04_2025-GO95HV-1^06146001.0087800 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006463 | 296083759-92870-DETAIL-03_17_2026-SVCTREE-1^06240004.0221902 | OTHER | HFTD Tier 2 | Distribution | 2026-03-17 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006464 | 296326388-25009-ADMIN-10_23_2025-SVCENTCO-1^06246011.0367200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006465 | 296647862-50149-DTLSB-07_16_2025-GO95HV-1^06244006.0232001 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006466 | 296816560-71043-DETAIL-06_29_2026-GO95HV-1^07217001.0158401 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006467 | 296997216-56539-DETAIL-05_27_2025-GO95HV-1^06244006.0040300 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006468 | 29714342-74593-AUDIT-07_01_2026-ABNDEQPM-1^07217001.0351000 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006469 | 297292028-37129-DETAIL-04_21_2026-GO95HV-1^06142012.0148809 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006470 | 297696906-49561-DETAIL-11_15_2022-CUSTWIRE-1^06239004.0368900 | OTHER | HFTD Tier 2 | Distribution | 2022-11-15 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006471 | 297978436-99399-DTLSB-03_16_2026-GO95MLD-1^06242009.0136200 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006472 | 298086208-43289-DETAIL-09_02_2025-GO95HV-1^06247006.0274800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006473 | 298136609-79840-DETAIL-05_06_2024-GO95STUB-1^06142012.0124008 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006474 | 298496231-93329-DTLSB-01_26_2026-BIRDDMG-1^06242009.0297802 | POLE | Non-HFTD | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006475 | 298888915-33800-DETAIL-02_25_2026-GO95MLD-1^06239003.0242700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006476 | 299017425-58210-DRONE_HY-06_30_2026-XARMSPCR-1^06238004.0223601 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006477 | 29961994-33994-DETAIL-06_28_2022-CUSTWIRE-1^07116007.0157404 | OTHER | HFTD Tier 2 | Distribution | 2022-06-28 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006478 | 299845716-42839-DTLTRT-07_03_2025-BIRDDMG-1^668087/00 2/011 | POLE | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006479 | 299909809-5239-DTLTRT-07_09_2025-GO95HV-1^668087/00 3/021 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006480 | 299909809-88982-DTLTRT-07_09_2025-GO95HV-1^668087/00 3/021 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006481 | 957065180-95769-DTLSB-01_27_2026-BIRDDMG-1^06242009.0055203 | POLE | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006482 | 957159273-77083-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0207541 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006483 | 957159273-77083-DETAIL-08_04_2025-SVCDEFLC-2^06247006.0207541 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006484 | 957176979-32143-DTLTRT-06_24_2025-GUYHINS-1^668087/00 8/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006485 | 957176979-32143-DTLTRT-06_24_2025-GUYHINS-2^668087/00 8/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006486 | 957176979-32143-DTLTRT-06_24_2025-GUYHINS-3^668087/00 8/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006487 | 957417426-13739-DETAIL-05_21_2025-GO95HV-1^06243006.0106101 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006488 | 958014464-59940-DTLTRT-06_03_2025-GO95HV-1^668075/00 5/013 | OTHER | Non-HFTD | Transmission | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006489 | 958014464-59940-DTLTRT-06_03_2025-GUYHINS-1^668075/00 5/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006490 | 958078136-64343-DETAIL-08_11_2025-CUTOUTAR-1^06246002.0095002 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006491 | 958169585-55509-DETAIL-09_04_2025-GO95HV-1^06247006.0186700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006492 | 958185854-90179-DETAIL-06_17_2025-GO95HV-1^06248004.0280001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006493 | 958218460-65583-DETAIL-08_19_2025-GO95HV-1^07216001.0173701 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006494 | 958218460-65583-DETAIL-08_19_2025-GO95MLD-1^07216001.0173701 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006495 | 95822966-22463-DETAIL-07_30_2025-GO95HV-1^06247005.0310102 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006496 | 958371333-19609-DETAIL-08_27_2025-GO95HV-1^06247006.0078000 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006497 | 958402654-78654-DETAIL-03_29_2023-CUSTWIRE-1^06142016.0084812 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006498 | 958469969-65899-DETAIL-09_09_2025-GO95HV-1^06246007.0230950 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006499 | 958552043-69989-DETAIL-10_01_2025-GO95BLTC-1^06246009.0127702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006500 | 958573999-51029-DTLSB-04_28_2026-GO95HV-1^06142013.0214402 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006501 | 958573999-51029-DTLSB-04_28_2026-GRDRODHI-1^06142013.0214402 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006502 | 959238797-46843-ADMIN-11_06_2025-DISTHDWR-1^06246001.0040700 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-11-06 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006503 | 959300613-60613-DETAIL-04_09_2024-CONDFRAY-2^06147005.0254704 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006504 | 959315128-97289-DTLSB-03_30_2026-SVCTREE-1^06241009.0324200 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006505 | 959470397-8098-DTLTRT-06_24_2026-GO95HV-1^07217001.0356304 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006506 | 959492521-12153-DTLTRT-04_23_2026-GO95HV-1^668004/00 4/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006507 | 299909809-99982-DTLTRT-07_09_2025-GO95HV-1^668087/00 3/021 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006508 | 300047914-41789-DETAIL-08_20_2025-GO95HV-1^06247006.0256600 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006509 | 300099918-13989-DETAIL-10_15_2025-GO95HV-1^06148001.0141400 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006510 | 300643868-30749-DTLSB-07_21_2025-GO95HV-1^06244006.0304404 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006511 | 300753999-8033-DETAIL-06_18_2026-ABNDEQPM-1^07217001.0345202 | OTHER | Non-HFTD | Distribution | 2026-06-18 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006512 | 300753999-8033-DETAIL-06_18_2026-GO95TCH-1^07217001.0345202 | OTHER | Non-HFTD | Distribution | 2026-06-18 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006513 | 300898003-93529-DETAIL-06_04_2025-GO95HV-1^06142012.0184700 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006514 | 301117062-65689-DETAIL-07_23_2025-GO95HV-1^06247005.0176002 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006515 | 301352136-63689-DTLSB-07_07_2025-GO95HV-1^06245007.0359900 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006516 | 301541391-61391-DETAIL-05_12_2025-GUYHINS-1^06243006.0212200 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-12 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006517 | 30157069-6899-DETAIL-09_09_2025-GO95HV-1^06246007.0230952 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006518 | 301721291-92009-DETAIL-03_12_2024-CONDFRAY-1^06147004.0058800 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006519 | 301789763-3353-AUDIT-10_28_2025-GO95HV-1^06247006.0285900 | OTHER | HFTD Tier 2 | Distribution | 2025-10-28 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006520 | 301789763-3353-DETAIL-08_25_2025-GRDRODHI-1^06247006.0285900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006521 | 301810683-95249-DTLSB-07_16_2025-GO95HV-1^06244006.0253901 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006522 | 301919880-30249-DETAIL-09_03_2025-GO95HV-1^07216001.0092701 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006523 | 30212259-85489-DETAIL-07_22_2025-GO95HV-1^06247005.0057301 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006524 | 302134590-41209-DETAIL-07_30_2025-GO95HV-1^06247006.0206201 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006525 | 30214415-52099-DETAIL-04_22_2025-GO95HV-1^06242006.0076602 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006526 | 302648961-58280-DRONE_HY-06_19_2026-DISTHDWR-1^06240004.0165302 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006527 | 302697768-86470-DETAIL-03_09_2026-BIRDDMG-1^06240004.0152903 | POLE | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006528 | 303219438-77139-DTLSB-09_26_2022-CUSTWIRE-1^06243005.0086301 | OTHER | Non-HFTD | Distribution | 2022-09-26 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006529 | 303233640-73940-DTLTRT-05_14_2026-BIRDDMG-1^668086/00 11/005 | POLE | Non-HFTD | Transmission | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006530 | 303421003-25050-DTLSB-05_22_2024-GO95MLD-1^06243001.0048800 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006531 | 303435694-9959-DETAIL-07_29_2025-GO95HV-1^06247005.0266900 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006532 | 960029775-58170-DETAIL-02_27_2025-GO95HV-1^06240003.0180501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006533 | 960544701-59799-DETAIL-04_07_2025-SVCROAD-1^06241005.0118510 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006534 | 960756443-4553-ADMIN-10_27_2025-GRDRODHI-1^06246001.0014700 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006535 | 961121671-70239-DETAIL-05_19_2025-GO95HV-1^06243006.0228400 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006536 | 961366619-52879-DETAIL-09_30_2025-GO95HV-1^06148001.0300212 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006537 | 961384991-64780-DETAIL-02_13_2025-SVCNEUT-1^06240004.0168144 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006538 | 96146456-99849-DETAIL-02_27_2024-GO95MLD-1^07113002.0073300 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006539 | 96157218-93549-DTLSB-07_16_2025-GO95HV-1^06244006.0317400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006540 | 961896551-18430-DETAIL-03_26_2026-SVCTREE-1^06240004.0200700 | OTHER | HFTD Tier 3 | Distribution | 2026-03-26 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006541 | 961956184-25353-DETAIL-09_24_2025-SVCNEUT-1^07218001.0224101 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006542 | 961969398-30753-ADMIN-11_12_2025-ABNDEQPM-1^06246001.0336800 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006543 | 961990929-80753-DETAIL-09_05_2025-GO95HV-1^06147001.0308400 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006544 | 962128473-1383-DETAIL-08_25_2025-GO95HV-1^07216001.0178401 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006545 | 962160170-66770-DETAIL-06_05_2025-GO95HV-1^668075/00 5/028 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006546 | 962360201-78879-DETAIL-10_02_2025-GO95HV-1^06148001.0299500 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006547 | 962408341-41839-DTLTRT-06_26_2025-GO95HV-1^668087/00 14/008 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006548 | 962498021-47939-AUDIT-05_27_2026-GUYHINS-1^668086/00 7/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006549 | 962499576-69542-ADMIN-11_10_2025-GO95BLTC-1^06246011.0063201 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006550 | 96279628-40070-DETAIL-03_23_2026-COVCOTHR-1^06240004.0229500 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006551 | 96279628-40070-DETAIL-03_23_2026-COVCOTHR-2^06240004.0229500 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006552 | 963131343-32540-DTLTRT-05_29_2025-DISTHDWR-1^668075/00 3/008 | CONNECTION DEVICE | Non-HFTD | Transmission | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006553 | 963166151-80853-DETAIL-05_08_2024-GO95MLD-1^06142012.0120104 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006554 | 963281853-45153-DTLSB-05_23_2024-GO95HV-1^06243001.0121000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006555 | 963388815-40479-DETAIL-09_10_2025-GO95BLTC-1^06246006.0183206 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006556 | 963388815-40479-DETAIL-09_10_2025-GO95HV-1^06246006.0183206 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006557 | 303650029-10449-ADMIN-03_03_2025-POLEDERP-1^07216001.0299400 | POLE | Non-HFTD | Distribution | 2025-03-03 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006558 | 303796913-13009-DETAIL-10_01_2025-GO95BLTC-1^06246009.0129902 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006559 | 304029208-7919-DTLSB-01_20_2026-GO95HV-1^06242009.0299303 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006560 | 30417706-24329-DETAIL-04_28_2026-GUYHINS-1^06142012.0149705 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006561 | 304284488-25488-DETAIL-09_03_2025-GO95BLTC-1^06146001.0079902 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006562 | 304323182-83218-DETAIL-07_07_2026-GO95TCH-1^07217001.0164600 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006563 | 304516259-95879-DTLSB-02_04_2026-BIRDDMG-1^06243009.0321100 | POLE | HFTD Tier 2 | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006564 | 304525240-31479-DETAIL-02_24_2025-GUYHINS-1^06240004.0152610 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006565 | 304757375-41699-DTLSB-01_27_2026-BIRDDMG-1^06242009.0054400 | POLE | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006566 | 305338471-77669-DTLSB-07_09_2025-GO95HV-1^06244007.0155500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006567 | 305375594-489-DETAIL-08_18_2025-SVCENTCO-1^06247006.0363300 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006568 | 305784870-77550-ADMIN-10_21_2025-GO95CL10-1^06247001.0139401 | OTHER | Non-HFTD | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006569 | 305890460-39650-DTLTRT-05_14_2026-GO95HV-1^668086/00 1/005 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006570 | 306121966-850-DETAIL-08_04_2025-GO95HV-1^06246001.0185000 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006571 | 306345585-41950-DETAIL-04_24_2024-CUSTWIRE-1^06145001.0043100 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006572 | 30657438-17200-DTLTRT-06_23_2025-GO95HV-1^668087/00 1/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006573 | 306581160-86919-DRONE_HY-07_15_2026-UBPRMSHD-1^668036/00 16/053 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120006574 | 306829893-79629-DETAIL-04_24_2025-GO95HV-1^06242006.0110500 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006575 | 307023764-1469-DETAIL-07_28_2025-GO95HV-1^06247005.0302000 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006576 | 30748950-270-DETAIL-04_12_2023-CUSTWIRE-1^06240004.0167702 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006577 | 307591388-59650-DTLTRT-06_30_2025-GUYHINS-1^668087/00 7/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006578 | 307726848-15479-DETAIL-07_28_2025-ABNDEQPM-1^06247005.0086540 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006579 | 307829090-69090-DETAIL-06_05_2025-GO95HV-1^668075/00 7/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006580 | 307857749-71589-DETAIL-07_28_2021-CUSTWIRE-1^06241008.0312100 | OTHER | Non-HFTD | Distribution | 2021-07-28 | 2024-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006581 | 307857749-71589-DTLSB-04_21_2026-GRDRODHI-1^06241008.0312100 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006582 | 308165227-6227-DETAIL-04_06_2026-GUYHINS-1^06236005.0110303 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006583 | 308165227-6227-DETAIL-04_06_2026-GUYHINS-3^06236005.0110303 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006584 | 963590512-86198-DETAIL-06_09_2026-GUYHINS-4^668086/00 15/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006585 | 963590512-86198-DETAIL-06_09_2026-GUYHINS-5^668086/00 15/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006586 | 963590512-86198-DTLTRT-05_21_2026-GO95MLD-1^668086/00 15/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006587 | 963918665-6479-ADMIN-11_13_2025-GO95HV-1^06247008.0303500 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006588 | 964213520-61089-DETAIL-06_18_2025-GO95HV-1^06248004.0341801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006589 | 964301819-36463-DTLTRT-05_19_2026-GO95MLD-1^668086/00 4/003 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006590 | 964376133-20663-DETAIL-03_10_2026-XARMSPCR-1^668041/00 4/027 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006591 | 965205128-27839-DTLSB-07_02_2025-GO95HV-1^06244006.0224001 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006592 | 965235085-49085-DETAIL-06_03_2025-GO95HV-1^06148014.0248902 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006593 | 965303190-42180-DETAIL-01_23_2026-GUYHINS-1^06240004.0233601 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006594 | 965359181-38563-DETAIL-10_08_2025-GO95HV-1^06148001.0323300 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006595 | 96540768-11939-DTLSB-06_30_2025-GO95HV-1^06244006.0225408 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006596 | 965886364-30353-DETAIL-06_29_2026-GO95HV-1^07217001.0095202 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006597 | 966024034-37059-DETAIL-08_20_2025-GO95BLTC-1^06247006.0369200 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006598 | 966162176-43563-DTLSB-05_29_2026-GO95HV-1^07216001.0113900 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006599 | 966294141-48563-DTLTRT-05_20_2026-GO95HV-1^668086/00 3/011 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006600 | 966583595-59700-DETAIL-04_08_2026-GO95HV-1^06240002.0313204 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006601 | 966986688-37688-DETAIL-09_02_2025-GO95MLD-1^06247006.0279300 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006602 | 967593585-60140-ADMIN-05_12_2026-POLEREPL-1^06240004.0150603 | POLE | HFTD Tier 2 | Distribution | 2026-05-12 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006603 | 967689493-12069-DETAIL-09_18_2025-GO95HV-1^06248007.0264600 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006604 | 9677113-16650-DETAIL-01_24_2025-GO95TCH-1^06239004.0256907 | OTHER | HFTD Tier 2 | Distribution | 2025-01-24 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006605 | 967920436-62772-DETAIL-07_11_2023-CUSTWIRE-1^06244008.0291002 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006606 | 967932234-61479-DETAIL-08_21_2024-CUSTWIRE-2^06246005.0269741 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006607 | 968069365-20099-DETAIL-08_27_2025-GO95HV-1^06247006.0188600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006608 | 968249356-19259-DETAIL-07_23_2025-GO95HV-1^06247005.0117900 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006609 | 308165227-6227-DETAIL-04_06_2026-GUYHINS-4^06236005.0110303 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006610 | 308247520-12483-DETAIL-08_19_2025-SVCROAD-1^07216001.0173802 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006611 | 308299584-7759-ADMIN-03_05_2025-POLEREPL-1^06245007.0274201 | POLE | Non-HFTD | Distribution | 2025-03-05 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006612 | 308406049-27049-DETAIL-09_25_2025-PWRTRN-1^06246009.0094703 | OTHER | HFTD Tier 2 | Distribution | 2025-09-25 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006613 | 308511933-91359-DTLTRT-04_22_2026-GO95HV-1^668004/02 9/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006614 | 308586886-65840-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 3/048 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006615 | 308731589-53799-DETAIL-08_26_2025-SVCENTBK-1^06247006.0331900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006616 | 309046073-24209-DETAIL-08_14_2025-GO95HV-1^06247006.0253000 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006617 | 309099871-11659-DTLSB-06_08_2026-SVCNEUT-1^07216001.0231202 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006618 | 309172593-79309-DETAIL-06_05_2025-ENCHRW-1^06245006.0190800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006619 | 309174005-4539-DETAIL-05_29_2025-GUYHINS-1^06244006.0031200 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006620 | 309174005-4539-DETAIL-05_29_2025-GUYHINS-2^06244006.0031200 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006621 | 309510668-82419-DTLSB-03_16_2026-GO95HV-1^06242009.0132400 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006622 | 309689269-12522-DTLTRT-04_23_2026-GO95HV-1^668004/00 1X/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006623 | 309736744-47749-DTLSB-07_23_2025-GO95HV-1^07218001.0263803 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006624 | 309761399-43399-DETAIL-07_12_2023-ENCHRW-1^06244008.0274400 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006625 | 309834354-23899-DETAIL-05_28_2025-GO95HV-1^06244006.0093103 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006626 | 30984863-21500-ADMIN-11_14_2025-GRDRODHI-1^06246001.0328701 | OTHER | Non-HFTD | Distribution | 2025-11-14 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006627 | 309946924-16339-DETAIL-10_06_2025-GO95HV-1^06243007.0369800 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006628 | 310136171-4520-DETAIL-03_11_2026-SVCROAD-1^06240004.0275401 | OTHER | HFTD Tier 2 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006629 | 968436299-24379-DTLSB-06_25_2025-GO95BLTC-1^06244007.0106905 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006630 | 96847331-82059-DTLSB-05_28_2026-GO95HV-1^07216001.0022202 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006631 | 968540768-52479-DETAIL-04_28_2025-GO95HV-1^06242006.0160801 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006632 | 968933483-11503-DETAIL-06_04_2025-GUYHINS-2^668075/00 15/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006633 | 969442012-80139-DETAIL-05_21_2025-GO95HV-1^06243006.0078402 | OTHER | HFTD Tier 2 | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006634 | 969594191-49873-DTLTRT-05_18_2026-GO95HV-1^668086/00 6/007 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006635 | 969704214-36229-DETAIL-04_28_2025-GO95HV-1^06242007.0247100 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006636 | 970205198-13190-DETAIL-01_12_2026-BIRDDMG-1^06239004.0244405 | POLE | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006637 | 970268566-19229-DTLSB-05_06_2026-GO95HV-1^06142013.0220101 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006638 | 971043893-84083-DETAIL-09_22_2025-GO95HV-1^06147001.0238601 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006639 | 971230016-19283-DTLSB-05_05_2026-GO95HV-1^06142013.0161100 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006640 | 97123510-86210-DETAIL-06_05_2025-GO95HV-1^668075/00 10/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006641 | 971259276-51573-AUDIT-07_15_2026-GRDRODHI-1^07217001.0346903 | OTHER | Non-HFTD | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006642 | 971388426-31229-DETAIL-05_12_2025-GO95HV-1^06142012.0010800 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006643 | 972394230-59410-DTLSB-06_16_2026-GO95HV-1^07217001.0357500 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006644 | 972480356-67870-DETAIL-04_07_2025-ANCHIDLE-1^06241005.0016801 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006645 | 972553088-83088-DETAIL-06_18_2025-COVCOTHR-2^668075/00 18/048 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006646 | 972774189-50869-ADMIN-12_29_2025-COVCOTHR-1^668002/00 20/049 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-12-29 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006647 | 972834645-99409-ADMIN-11_10_2025-GO95BLTC-1^06246011.0071900 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006648 | 973573478-66139-DTLSB-08_18_2025-GO95BLTC-1^07218001.0357800 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006649 | 973663980-26983-DETAIL-09_11_2025-GO95HV-1^06147001.0107902 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006650 | 973674471-86471-DETAIL-01_21_2026-COVCOTHR-1^06239004.0014002 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006651 | 973838616-36483-DETAIL-05_11_2026-GO95HV-1^668038/00 3/052 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006652 | 973988830-93201-DETAIL-01_15_2026-GO95HV-1^06239004.0136108 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006653 | 973988830-93201-DETAIL-01_15_2026-SVCTREE-1^06239004.0136108 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006654 | 974594223-32489-DETAIL-09_16_2025-GO95HV-1^06147001.0135700 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006655 | 974678536-72670-DETAIL-01_22_2025-GO95HV-1^06239004.0254500 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006656 | 974678536-72670-DRONE_HY-06_19_2026-GUYHINS-1^06239004.0254500 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006657 | 974765486-71383-DETAIL-06_04_2025-GO95HV-1^06245006.0280600 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006658 | 974991148-9283-DTLSB-05_05_2026-GRDRODHI-1^06142013.0152500 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006659 | 310331295-92170-DETAIL-01_21_2025-GO95HV-1^06239004.0256305 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006660 | 310364070-90609-DETAIL-10_07_2025-GO95HV-1^06246008.0042400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006661 | 310364070-90609-DETAIL-10_07_2025-GO95TCH-1^06246008.0042400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006662 | 310746646-15750-DETAIL-08_12_2025-GO95HV-1^06246001.0193401 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006663 | 310832995-52589-DETAIL-07_28_2025-GO95BLTC-1^06247005.0310700 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006664 | 310929338-64949-DTLSB-07_21_2025-ENCHRW-1^06244007.0038905 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006665 | 311418485-84250-ADMIN-11_03_2025-GRDRODHI-1^06246001.0210400 | OTHER | Non-HFTD | Distribution | 2025-11-03 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006666 | 311574674-31959-DTLTRT-04_22_2026-GO95MLD-1^668004/02 1/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006667 | 311771875-14450-DTLTRT-06_26_2025-SVCROAD-1^668087/00 11/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006668 | 311972225-78370-DETAIL-01_23_2026-GO95HV-1^06240003.0184900 | OTHER | HFTD Tier 2 | Distribution | 2026-01-23 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006669 | 312010103-61650-DTLTRT-05_13_2026-GO95HV-1^668085/00 6/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006670 | 312010103-61650-DTLTRT-05_13_2026-GO95MLD-1^668085/00 6/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006671 | 312100888-25839-DETAIL-09_04_2025-GO95HV-1^07216001.0099502 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006672 | 312100888-25839-DETAIL-09_04_2025-GRDRODHI-1^07216001.0099502 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006673 | 31218377-50729-DETAIL-09_15_2025-GO95BLTC-1^06248007.0239300 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006674 | 31244140-49740-DETAIL-03_31_2026-COVCOTHR-1^06239003.0063203 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006675 | 31244140-49740-DETAIL-03_31_2026-COVCOTHR-2^06239003.0063203 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006676 | 31244140-49740-DETAIL-03_31_2026-COVCOTHR-4^06239003.0063203 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006677 | 31244140-49740-DETAIL-03_31_2026-COVCOTHR-5^06239003.0063203 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006678 | 312663961-31659-DETAIL-06_18_2025-GO95HV-1^06248004.0340600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006679 | 312817058-81030-DETAIL-01_26_2026-COVCOTHR-1^06240003.0304901 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006680 | 313053339-86379-DETAIL-09_09_2025-SVCDEFLC-1^06246007.0142251 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006681 | 313099933-60033-DETAIL-06_09_2025-GO95MLD-1^668075/00 6/029 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006682 | 313101075-87075-DETAIL-06_05_2025-GO95HV-1^06148014.0236600 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006683 | 313212585-62699-DETAIL-01_28_2026-GO95BLTC-1^06242009.0051100 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006684 | 975081293-18659-DETAIL-07_29_2025-GO95HV-1^06247005.0216701 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006685 | 975368293-18919-DRONE_HY-07_15_2026-UBPRMSHD-1^668036/00 20/053 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120006686 | 975405426-79659-DTLTRT-04_30_2026-GO95HV-1^668004/00 1/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006687 | 975405426-79660-DTLTRT-04_30_2026-GO95HV-1^668004/00 1/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006688 | 975517449-5679-DETAIL-09_22_2025-SVCDEFLC-1^06248007.0132000 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006689 | 975639105-62319-DTLSB-01_28_2026-GO95BLTC-1^06242009.0057901 | OTHER | Non-HFTD | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006690 | 975760606-90606-DETAIL-01_22_2026-GO95MLD-1^06239004.0231000 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006691 | 976013091-98693-DETAIL-09_10_2025-GO95HV-1^06147001.0076800 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006692 | 976086029-97639-DTLSB-07_17_2025-GO95HV-1^06244006.0186101 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006693 | 976195500-27739-DETAIL-06_25_2025-GO95CLSV-1^668087/00 11/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006694 | 976205081-3393-DETAIL-10_08_2025-GO95HV-1^06148001.0321501 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006695 | 976248442-68983-DETAIL-08_21_2025-GUYHINS-1^07216001.0175201 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006696 | 976465583-49559-DETAIL-07_28_2025-GO95HV-1^06247005.0301100 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006697 | 976608172-67193-AUDIT-06_04_2025-SVCENTCO-1^06142012.0112306 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006698 | 976859181-67999-DETAIL-08_04_2025-SVCROAD-1^06247006.0209704 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006699 | 976973730-4299-DETAIL-08_05_2025-BIRDDMG-1^06247005.0205301 | POLE | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006700 | 976973730-4299-DETAIL-08_05_2025-GO95HV-1^06247005.0205301 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006701 | 977380506-51179-DETAIL-08_04_2025-GO95HV-1^06246001.0182001 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006702 | 977429591-86593-DTLSB-06_03_2026-GO95HV-1^07216001.0024300 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006703 | 977429591-86593-DTLSB-06_03_2026-SVCROAD-1^07216001.0024300 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006704 | 97745689-57289-DETAIL-08_26_2025-ABNDEQPM-1^06247006.0289300 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006705 | 977484603-97799-DETAIL-08_14_2025-GO95MLD-1^06247006.0256004 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006706 | 977484603-97799-DETAIL-08_14_2025-GRDRODHI-1^06247006.0256004 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006707 | 977722390-23599-DTLSB-03_16_2026-BIRDDMG-1^06242009.0220901 | POLE | Non-HFTD | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006708 | 977743893-15670-DETAIL-06_20_2022-CUSTWIRE-1^07116007.0113941 | OTHER | HFTD Tier 2 | Distribution | 2022-06-20 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006709 | 97834523-94523-DETAIL-06_04_2025-GUYHINS-1^668075/00 10/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006710 | 978612801-21139-DTLTRT-07_08_2025-GO95HV-1^668087/00 14/025 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006711 | 978672398-23398-DRONE_HY-06_30_2026-POLESTEP-1^06238004.0152201 | POLE | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006712 | 978746072-4699-DETAIL-07_22_2025-GO95HV-1^06247005.0175600 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006713 | 978773939-79321-DETAIL-04_08_2025-GO95MLD-1^06241005.0092103 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006714 | 31333578-22439-DTLTRT-06_24_2025-GUYHINS-1^668087/00 7/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006715 | 31333578-22439-DTLTRT-06_24_2025-GUYHINS-2^668087/00 7/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006716 | 313427946-17869-DETAIL-02_11_2025-GO95TCH-1^06240004.0356102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006717 | 313427946-17869-DETAIL-03_31_2026-COVCOTHR-1^06240004.0356102 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006718 | 313469310-89370-DETAIL-03_29_2023-CUSTWIRE-1^06240004.0165706 | OTHER | HFTD Tier 2 | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006719 | 313469310-89370-DETAIL-03_29_2023-CUSTWIRE-2^06240004.0165706 | OTHER | HFTD Tier 2 | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006720 | 313469310-89370-DETAIL-03_29_2023-CUSTWIRE-3^06240004.0165706 | OTHER | HFTD Tier 2 | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006721 | 313601679-31739-DTLTRT-06_24_2025-GO95BLTC-1^668087/00 15/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006722 | 313603583-31780-DETAIL-03_31_2026-GO95MLD-1^06240004.0355301 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006723 | 313766228-97460-DTLSB-04_28_2026-GO95HV-1^06142013.0215301 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006724 | 313859824-18859-DTLTRT-04_22_2026-GO95HV-1^668004/02 12/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006725 | 313915014-45014-DETAIL-07_22_2025-GO95HV-1^06247005.0040501 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006726 | 313915014-45014-DETAIL-07_22_2025-GUYNOINS-1^06247005.0040501 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-22 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006727 | 314065072-62139-DETAIL-05_20_2025-GO95HV-1^06243006.0068200 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006728 | 314797657-68140-DETAIL-02_17_2026-GO95CL10-1^06239003.0129801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006729 | 315036033-58559-DTLTRT-04_20_2026-GO95HV-1^668004/02 4/005 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006730 | 31557116-96270-DETAIL-01_24_2025-GO95HV-1^06239004.0257943 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006731 | 316155083-92151-DETAIL-04_16_2025-GO95BLTC-1^06242005.0331104 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006732 | 316265702-94383-DTLSB-06_05_2026-GRDRODHI-1^07216001.0230803 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006733 | 316430962-56520-DETAIL-01_21_2026-COVCOTHR-1^06240004.0289401 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006734 | 316439323-64089-DETAIL-08_13_2025-GO95HV-1^06247006.0258400 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006735 | 316513483-32659-DTLTRT-04_21_2026-GO95MLD-1^668004/02 13/005 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006736 | 31657458-50591-DTLTRT-05_05_2026-BIRDDMG-1^668038/00 4/062 | POLE | HFTD Tier 2 | Transmission | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006737 | 316671929-33929-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 7/015 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006738 | 31684576-34929-DETAIL-05_14_2025-GRDRODHI-1^06142012.0012100 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006739 | 978927991-42493-DTLSB-05_28_2026-GO95HV-1^07216001.0022601 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006740 | 979346298-55359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0327400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006741 | 979397431-92779-DETAIL-10_02_2025-ABNDEQPM-1^06148001.0295501 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006742 | 979512167-84099-DETAIL-08_14_2025-GO95HV-1^06246001.0319301 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006743 | 97960233-70279-DETAIL-09_15_2025-GO95HV-1^06248007.0232300 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006744 | 979820576-85870-DETAIL-01_21_2025-SVCENTCO-1^06239004.0256406 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006745 | 979877113-39629-DTLSB-01_20_2026-GO95HV-1^06242009.0299204 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006746 | 980025994-14330-ADMIN-03_10_2025-CUSTWIRE-1^06241005.0257800 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006747 | 980060191-34203-DTLTRT-05_18_2026-GO95HV-1^668086/00 7/007 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006748 | 980349136-12440-DETAIL-07_06_2026-GO95HV-1^07218001.0342701 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006749 | 980613982-55312-DTLSB-07_16_2025-GO95HV-1^06244006.0236000 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006750 | 980643443-3003-DETAIL-05_28_2025-SVCENTCO-1^06142012.0111302 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006751 | 980732234-33234-DETAIL-02_12_2025-GUYHINS-1^06240004.0284600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006752 | 981159691-3230-DETAIL-09_24_2024-GRDSHDBK-1^668014/00 8/027 | OTHER | HFTD Tier 2 | Transmission | 2024-09-24 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006753 | 981196968-57499-DETAIL-08_26_2025-GO95HV-1^06247006.0299801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006754 | 981634581-39803-DTLTRT-06_26_2025-GO95HV-1^668087/00 1/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006755 | 981634581-39803-DTLTRT-06_26_2025-GUYHINS-2^668087/00 1/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006756 | 981788552-15553-DETAIL-06_30_2026-GO95HV-1^07217001.0223700 | OTHER | Non-HFTD | Distribution | 2026-06-30 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006757 | 98188801-8209-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0208902 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006758 | 982041249-32399-DETAIL-09_09_2025-GO95HV-1^06246007.0141250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006759 | 982111822-29460-DTLTRT-04_29_2026-GO95HV-1^668004/00 3/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006760 | 982449135-32399-DETAIL-08_19_2025-GO95HV-1^06247006.0367002 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006761 | 982471957-12003-DETAIL-08_06_2025-GO95HV-1^06246002.0156901 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006762 | 982710237-69689-DETAIL-10_26_2021-CUSTWIRE-2^06148005.0240101 | OTHER | Non-HFTD | Distribution | 2021-10-26 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006763 | 982713345-92863-DETAIL-05_26_2026-ABNDEQPM-1^07217001.0141400 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006764 | 98272334-76379-DETAIL-10_15_2025-GO95TCH-1^06246011.0181501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006765 | 982865279-67739-DETAIL-05_08_2025-GO95HV-1^06243006.0035100 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006766 | 98445283-59939-DTLTRT-05_20_2026-GO95MLD-1^668086/00 16/012 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006767 | 984711461-24543-DETAIL-07_01_2026-GO95HV-1^07217001.0167502 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006768 | 984832473-37249-DTLSB-07_16_2025-GO95HV-1^06244006.0251901 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006769 | 985124614-22659-DETAIL-07_28_2025-GO95HV-1^06247005.0302401 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006770 | 985161204-22213-DETAIL-08_27_2025-GO95HV-1^07216001.0169402 | OTHER | Non-HFTD | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006771 | 985235024-17383-DETAIL-09_18_2025-GO95HV-1^07218001.0086103 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006772 | 98551360-54139-DTLTRT-07_10_2025-GO95HV-1^668087/00 6/024 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006773 | 98551360-54139-DTLTRT-07_10_2025-GUYLOINS-1^668087/00 6/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006774 | 316858431-95750-DETAIL-04_06_2026-BIRDDMG-1^06237005.0355100 | POLE | HFTD Tier 2 | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006775 | 316968749-33739-DTLTRT-06_24_2025-GO95TCH-1^668087/00 14/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006776 | 317007153-40550-DETAIL-01_23_2025-GO95HV-1^06239004.0256904 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006777 | 317007153-40550-DETAIL-01_23_2025-GO95TCH-1^06239004.0256904 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006778 | 317181265-66939-DTLSB-07_02_2025-GO95HV-1^06244006.0226005 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006779 | 317465373-15053-DETAIL-09_23_2025-GO95HV-1^07218001.0229202 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006780 | 317701649-26779-DETAIL-10_02_2025-GUYHINS-1^06148001.0284602 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006781 | 318008961-4980-DETAIL-02_14_2025-GO95HV-1^06240004.0168307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006782 | 318139283-67749-DTLSB-08_11_2025-GO95HV-1^07217001.0011504 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006783 | 318515779-24560-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 3/061 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006784 | 318708571-46460-DTLSB-10_16_2025-GRDRODHI-1^06247001.0345300 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006785 | 319063773-32909-DETAIL-08_14_2025-GO95HV-1^06247006.0254002 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006786 | 319160211-63909-DETAIL-09_03_2025-GO95HV-1^06247006.0211500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006787 | 319387841-62629-DTLSB-01_29_2026-BIRDDMG-1^06242009.0050904 | POLE | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006788 | 319391489-67660-DTLTRT-06_25_2025-CLRTOPOL-1^668087/00 5/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006789 | 319420179-53790-DETAIL-01_16_2025-GO95HV-1^06239004.0256216 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006790 | 319420179-53790-DETAIL-01_16_2025-SVCENTCO-1^06239004.0256216 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006791 | 319724837-41860-ADMIN-11_06_2025-GO95HV-1^06246001.0235001 | OTHER | Non-HFTD | Distribution | 2025-11-06 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006792 | 320286829-17029-DETAIL-06_05_2025-SVCROAD-1^06142012.0103400 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006793 | 320570395-79460-ADMIN-11_03_2025-GO95HV-1^06246001.0223500 | OTHER | Non-HFTD | Distribution | 2025-11-03 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006794 | 320830463-2199-DTLSB-08_16_2023-CUSTWIRE-1^06243009.0284200 | OTHER | Non-HFTD | Distribution | 2023-08-16 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006795 | 320895123-4780-DETAIL-02_17_2026-GO95HV-1^06239002.0059400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006796 | 320993616-38860-DETAIL-08_11_2025-GO95MLD-1^06246002.0097000 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006797 | 321010404-53729-DETAIL-04_28_2026-GO95HV-1^06142012.0149506 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006798 | 321435235-47235-DTLTRT-05_11_2026-BIRDDMG-1^668038/00 999/050 | POLE | HFTD Tier 2 | Transmission | 2026-05-11 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006799 | 98551360-54139-DTLTRT-07_10_2025-GUYNOINS-1^668087/00 6/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006800 | 985975529-84389-DETAIL-10_15_2025-GO95HV-1^06148001.0252200 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006801 | 98636070-42879-ADMIN-08_07_2025-CUTOUTAR-1^06246001.0303901 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2025-08-07 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006802 | 98636070-42879-DETAIL-08_07_2025-GO95HV-1^06246001.0303901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006803 | 986434860-84833-DTLSB-06_24_2026-GO95TCH-1^07217001.0346400 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006804 | 986494539-41999-DTLSB-07_08_2025-GO95HV-1^06244007.0037400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006805 | 986908089-82813-DETAIL-08_18_2025-GO95HV-1^06246002.0346801 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006806 | 987456734-28890-DETAIL-04_30_2025-SVCENTCO-1^06239002.0063608 | OTHER | Non-HFTD | Distribution | 2025-04-30 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006807 | 987528316-44323-DTLSB-06_03_2026-GO95HV-1^07216001.0114605 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006808 | 98775679-54019-DTLSB-05_19_2026-GO95HV-1^06240007.0181501 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006809 | 987801612-10759-DETAIL-07_29_2025-POLETOP-1^06247005.0214604 | POLE | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006810 | 988115383-98180-DETAIL-02_13_2025-CUSTWIRE-1^06240004.0168101 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006811 | 98815029-31029-DETAIL-07_01_2025-GO95HV-1^668087/00 12/015 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006812 | 98815029-40029-DETAIL-07_01_2025-GO95HV-1^668087/00 12/015 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006813 | 988200371-91943-DETAIL-07_07_2026-SVCDEFLC-1^07217001.0164500 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006814 | 321638546-79546-DETAIL-09_29_2025-GO95HV-1^06148001.0317300 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006815 | 321687936-44560-ADMIN-10_20_2025-GRDRODHI-2^06247001.0365101 | OTHER | Non-HFTD | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006816 | 321839501-60601-DETAIL-09_25_2025-GO95HV-1^07218001.0213801 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006817 | 321965736-78301-DETAIL-03_03_2025-GO95MLD-1^06241005.0255500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006818 | 322428463-54129-DETAIL-04_22_2026-GO95HV-1^06142012.0149810 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006819 | 322449820-48550-DETAIL-01_20_2026-GUYHINS-1^06239003.0070601 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006820 | 322657670-54933-DETAIL-09_18_2025-GO95HV-1^07218001.0087040 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006821 | 322665808-92650-DETAIL-02_25_2026-GO95HV-1^06239003.0139201 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006822 | 323307956-12670-DETAIL-07_03_2025-GUYHINS-3^668087/00 18/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006823 | 323573525-1640-DETAIL-03_09_2026-COVCOTHR-1^06240004.0151902 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006824 | 323742741-83979-DETAIL-10_07_2025-POLISSUE-1^06148001.0311802 | POLE | Non-HFTD | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006825 | 324293204-6299-DETAIL-01_29_2026-GO95BLTC-1^06242009.0052501 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006826 | 324450169-27152-DTLSB-07_15_2025-GO95HV-1^06244006.0313141 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006827 | 324818103-87941-DETAIL-03_05_2025-GO95MLD-1^06241005.0132801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006828 | 324840104-75379-DTLSB-07_09_2026-GO95HV-1^06240008.0156100 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006829 | 324840104-75379-DTLSB-07_09_2026-XARMSPCR-1^06240008.0156100 | CROSSARM | Non-HFTD | Distribution | 2026-07-09 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006830 | 324895855-95689-DETAIL-08_13_2025-GO95HV-1^06247006.0263603 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006831 | 324927316-83339-DETAIL-06_10_2026-SVCROAD-1^668086/00 8/015 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006832 | 325393955-68070-DETAIL-01_27_2026-SVCENTCO-1^06239002.0062307 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006833 | 325405033-60770-DETAIL-06_10_2026-CLMBHAZ-1^668086/00 13/012 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006834 | 988215071-49469-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006835 | 988626321-98653-DETAIL-09_22_2025-GO95HV-1^06247006.0065700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006836 | 989150436-19759-DETAIL-05_04_2026-GO95HV-1^668004/00 7/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006837 | 989150436-19760-DETAIL-05_04_2026-GO95HV-1^668004/00 7/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006838 | 989223859-20090-DETAIL-01_28_2025-GO95TCH-1^06239004.0244301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006839 | 989223859-20090-DETAIL-01_28_2025-SVCROAD-1^06239004.0244301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006840 | 989354109-45133-ADMIN-04_22_2024-ABNDEQPM-1^06146001.0365101 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006841 | 989357771-44709-DETAIL-10_07_2025-GO95BLTC-1^06246008.0057400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006842 | 989357771-44709-DETAIL-10_07_2025-GUYHINS-1^06246008.0057400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006843 | 989357771-44709-DETAIL-10_07_2025-GUYHINS-2^06246008.0057400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006844 | 989513818-23191-DETAIL-05_06_2026-GO95HV-1^668038/00 6/057 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006845 | 989932415-91529-DTLSB-05_04_2026-GO95HV-1^06142013.0053900 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006846 | 990074506-98310-DETAIL-02_14_2025-GO95HV-1^06240004.0163607 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006847 | 99111918-63240-DTLSB-05_05_2026-GO95HV-1^06142013.0222800 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006848 | 991157910-87230-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135902 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006849 | 991338169-99833-DTLTRT-06_25_2025-GO95HV-1^668087/00 1/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006850 | 991435995-48133-DTLSB-06_09_2026-GO95MLD-1^07216001.0225101 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006851 | 991435995-48133-DTLSB-06_09_2026-GUYHINS-1^07216001.0225101 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006852 | 991628011-83189-DTLSB-07_01_2025-GO95HV-1^06244007.0107401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006853 | 99168854-24040-DTLSB-07_23_2025-GO95HV-1^07218001.0263904 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006854 | 991716228-83359-DETAIL-07_22_2025-GO95HV-1^06247005.0087440 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006855 | 991989576-24419-DTLSB-03_11_2026-GO95HV-1^06242009.0239000 | OTHER | Non-HFTD | Distribution | 2026-03-11 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006856 | 992306843-62562-DTLSB-06_30_2025-GO95HV-1^06244007.0105443 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006857 | 992495931-95883-DETAIL-10_25_2024-GO95TCH-1^07216001.0208401 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006858 | 992495931-95883-DETAIL-10_25_2024-SVCENTBK-1^07216001.0208401 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006859 | 992582732-96769-DETAIL-05_06_2025-GO95MLD-1^06243006.0342200 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006860 | 992587044-89883-DETAIL-09_18_2025-GO95HV-1^07218001.0086502 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006861 | 992901604-56730-DETAIL-06_10_2025-GO95HV-1^06236005.0338800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006862 | 99306879-62733-DTLSB-06_18_2026-GO95MLD-1^07217001.0343900 | OTHER | Non-HFTD | Distribution | 2026-06-18 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006863 | 99310291-94229-DTLSB-08_08_2023-CUSTWIRE-1^06243009.0140701 | OTHER | Non-HFTD | Distribution | 2023-08-08 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006864 | 993137873-35519-DTLSB-04_23_2026-GO95HV-1^06241009.0225501 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006865 | 993345773-87243-ADMIN-05_23_2024-ABNDEQPM-1^06243001.0149600 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006866 | 9934987-24099-DTLSB-08_21_2024-CUSTWIRE-1^06245006.0332600 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006867 | 993822892-56460-DTLTRT-04_29_2026-GO95HV-1^668004/00 6/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006868 | 994224519-91143-DETAIL-08_13_2025-GO95HV-1^06246002.0366500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006869 | 99431694-70319-DTLSB-01_28_2026-BIRDDMG-1^06242009.0053800 | POLE | HFTD Tier 2 | Distribution | 2026-01-28 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006870 | 994481180-4943-DTLTRT-04_27_2026-GO95HV-1^668004/00 5/005 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006871 | 994648648-3451-DETAIL-10_14_2025-SVCENTCO-1^07117008.0177101 | OTHER | HFTD Tier 2 | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006872 | 994765509-46143-ADMIN-10_21_2025-GUYHINS-1^06247001.0239401 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006873 | 994857618-81390-DETAIL-01_13_2026-GUYHINS-2^06239004.0246100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006874 | 995118466-18939-DETAIL-05_15_2025-GO95HV-1^06243006.0096201 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006875 | 995187201-73650-DETAIL-03_02_2026-BIRDDMG-1^06238004.0024040 | POLE | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006876 | 995467827-86199-DETAIL-06_28_2022-CUSTWIRE-1^07116007.0110402 | OTHER | HFTD Tier 2 | Distribution | 2022-06-28 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006877 | 995554559-5913-DETAIL-05_06_2025-GO95BLTC-1^06243006.0343940 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006878 | 995770913-46243-DETAIL-03_14_2024-GO95HV-1^06147004.0300901 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006879 | 995948774-43299-DETAIL-06_16_2025-CLMBHAZ-1^06248004.0310900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006880 | 325405033-60770-DTLTRT-05_20_2026-GO95MLD-1^668086/00 13/012 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006881 | 325525401-68099-DTLSB-08_27_2024-CUSTWIRE-1^06245007.0119703 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006882 | 32616396-58789-DETAIL-05_06_2025-GO95HV-1^06243006.0031701 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006883 | 326249064-69189-DETAIL-07_30_2025-GO95HV-1^06247006.0206400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006884 | 326279332-38039-DETAIL-05_20_2025-GO95HV-1^06243006.0077203 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006885 | 995965280-30079-DETAIL-08_07_2025-GO95HV-1^06246001.0304900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006886 | 995965280-30079-DETAIL-08_07_2025-GO95MLD-1^06246001.0304900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006887 | 996261268-58830-DTLTRT-05_22_2025-GO95HV-1^668075/00 4/001 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006888 | 996464724-66229-DETAIL-04_28_2025-GO95HV-1^06242007.0245001 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006889 | 996585710-7710-DETAIL-06_03_2025-GO95HV-1^06148015.0312300 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006890 | 326594073-9380-DETAIL-02_13_2025-SVCDEFLC-1^06240004.0168200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006891 | 327551931-54989-DTLSB-07_07_2025-GO95HV-1^06245007.0353400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006892 | 327865688-24170-DETAIL-08_07_2025-GO95HV-1^06246002.0252901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006893 | 327983931-38080-DETAIL-02_16_2026-GO95HV-1^06239001.0042700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006894 | 328583893-4419-DTLSB-07_09_2026-GO95HV-1^06240008.0155101 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006895 | 996802665-30599-DTLSB-07_07_2025-GO95BLTC-1^06245007.0357501 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006896 | 996802665-30599-DTLSB-07_07_2025-GO95HV-1^06245007.0357501 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006897 | 996900669-31459-DETAIL-08_06_2025-GO95HV-1^06247005.0194100 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006898 | 996922594-23553-DETAIL-09_05_2025-GO95HV-1^06247006.0176500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006899 | 996928615-24000-DETAIL-02_25_2026-BIRDDMG-1^06239003.0242401 | POLE | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006900 | 996928615-24000-DETAIL-02_25_2026-GO95HV-1^06239003.0242401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006901 | 996932585-93585-DETAIL-06_05_2025-GO95HV-1^06148014.0241400 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006902 | 996940723-86399-DETAIL-07_30_2025-GO95HV-1^06247006.0204400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006903 | 996977408-96049-DTLSB-02_13_2024-ABNDEQPM-1^07216001.0185101 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006904 | 997090030-97709-DTLSB-07_23_2024-CUSTWIRE-1^06245007.0108100 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006905 | 997301993-69430-DTLSB-07_24_2025-GO95HV-1^07218001.0263811 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006906 | 997470829-69670-DETAIL-06_11_2025-GO95HV-1^06236005.0150100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006907 | 998237031-64539-DETAIL-05_15_2025-GO95HV-1^06243006.0168400 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006908 | 998325956-84679-ADMIN-10_20_2025-GRDRODHI-1^06247001.0365304 | OTHER | Non-HFTD | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006909 | 998383175-92059-DETAIL-09_16_2025-GO95HV-1^06247004.0184700 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006910 | 998544015-58015-DETAIL-06_02_2025-GO95HV-1^06147014.0029200 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006911 | 998588861-50839-DTLSB-06_08_2026-GO95HV-1^07216001.0232101 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006912 | 999217484-30773-DETAIL-09_04_2025-GO95HV-1^06147001.0319701 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006913 | 999595272-12750-DETAIL-02_11_2026-BIRDDMG-1^06239003.0016209 | POLE | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006914 | 999659282-85139-DETAIL-05_20_2025-GO95HV-1^06243006.0068100 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006915 | 328643996-45996-DETAIL-06_02_2025-GO95HV-1^06148014.0364702 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006916 | 32877216-6420-DETAIL-09_02_2025-GO95HV-1^06246001.0176407 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006917 | 328854346-50089-DETAIL-08_11_2025-GO95HV-1^06246002.0094000 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006918 | 329033596-41180-DETAIL-02_19_2025-GO95MLD-1^06239004.0363303 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006919 | 329069993-49089-DETAIL-09_29_2025-GO95HV-1^06246009.0111200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006920 | 329069993-49089-DETAIL-09_29_2025-SVCENTCO-1^06246009.0111200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006921 | 329340521-30169-DTLTRT-05_12_2026-GO95HV-1^668004/00 9/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006922 | 329340521-30170-DTLTRT-05_12_2026-GO95HV-1^668004/00 9/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006923 | 329366836-15570-DETAIL-01_15_2025-GO95HV-1^06239004.0256207 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006924 | 32964765-67163-DETAIL-06_23_2026-CUSTWIRE-1^07217001.0107200 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006925 | 329655523-8999-DETAIL-07_31_2025-BIRDDMG-1^06247005.0210001 | POLE | Non-HFTD | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006926 | 329865020-17370-DTLTRT-04_27_2026-GO95HV-1^668004/00 3/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006927 | 329865020-32122-DTLTRT-04_27_2026-GO95HV-1^668004/00 3/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006928 | 330205606-87949-DTLSB-07_08_2025-GO95HV-1^06244007.0035802 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006929 | 330509342-53779-DETAIL-07_24_2025-GRDRODHI-1^06247005.0139600 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006930 | 330526769-25919-DRONE_HY-07_15_2026-UBPRMSHD-1^668036/00 10/053 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120006931 | 330526769-25919-DRONE_HY-07_15_2026-UBPRMSHD-2^668036/00 10/053 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006932 | 330533307-56899-DETAIL-06_05_2025-GO95HV-1^06245006.0300700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006933 | 330615634-32553-DETAIL-09_22_2025-GO95MLD-1^07218001.0215800 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006934 | 330655106-3929-DTLSB-04_30_2026-GO95HV-1^06142013.0183401 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006935 | 330944123-60983-DETAIL-08_14_2024-CUSTWIRE-1^06246004.0184040 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006936 | 330944270-89839-DTLSB-06_16_2026-CUSTWIRE-1^07217001.0356601 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006937 | 330944270-89839-DTLSB-06_16_2026-GO95HV-1^07217001.0356601 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006938 | 330998460-18801-DETAIL-04_10_2025-ENCHRW-1^06241005.0031703 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006939 | 331006289-16870-DETAIL-09_30_2025-GO95HV-1^06148001.0300200 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006940 | 331214388-32099-DETAIL-08_19_2025-GO95HV-1^06246002.0368000 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006941 | 331454626-21879-DETAIL-10_14_2025-GRDRODHI-1^06148001.0176302 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006942 | 331456771-71070-DETAIL-08_19_2025-GO95HV-1^06246001.0319002 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006943 | 331470426-27591-DTLTRT-05_11_2026-BIRDDMG-1^668038/00 3/050 | POLE | HFTD Tier 2 | Transmission | 2026-05-11 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006944 | 331542418-24070-DETAIL-08_19_2025-GO95HV-1^06246002.0261200 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006945 | 331542418-24070-DETAIL-08_19_2025-GRDRODHI-1^06246002.0261200 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006946 | 332235975-12839-DTLTRT-06_26_2025-GUYHINS-1^668087/00 18/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006947 | 332235975-12839-DTLTRT-06_26_2025-GUYHINS-2^668087/00 18/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006948 | 332235975-12839-DTLTRT-06_26_2025-GUYHINS-3^668087/00 18/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006949 | 332245015-37015-DETAIL-06_05_2025-GO95HV-1^06148014.0246400 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006950 | 332445724-50949-DTLSB-07_14_2025-GO95HV-1^06244007.0230801 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006951 | 33244959-82019-DTLSB-04_14_2026-GO95HV-1^06241008.0241101 | OTHER | Non-HFTD | Distribution | 2026-04-14 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006952 | 332531643-42359-DTLTRT-04_22_2026-GO95HV-1^668004/02 10/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006953 | 332598338-80770-DTLSB-07_09_2025-GO95HV-1^06244007.0156740 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006954 | 33274884-7690-DETAIL-02_10_2026-GO95TCH-1^06239003.0015503 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006955 | 332893869-27999-DETAIL-02_03_2022-CUSTWIRE-1^06147005.0310502 | OTHER | Non-HFTD | Distribution | 2022-02-03 | 2025-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006956 | 333026276-5742-ADMIN-11_10_2025-GO95HV-1^06246011.0070800 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006957 | 333211093-62629-DETAIL-05_12_2025-GO95HV-1^06142012.0013900 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006958 | 33323049-50359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0331401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006959 | 333353404-85229-DETAIL-04_28_2025-GO95HV-1^06242007.0249100 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006960 | 333693429-27429-DETAIL-06_06_2023-CUSTWIRE-1^06244010.0342320 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006961 | 334477323-90030-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 5/031 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006962 | 334570819-29919-DTLSB-04_14_2026-GRDRODHI-1^06241008.0234400 | OTHER | Non-HFTD | Distribution | 2026-04-14 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006963 | 334764945-56299-DTLSB-07_09_2025-GO95HV-1^06244006.0347503 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006964 | 334891071-49530-DETAIL-07_02_2026-GO95HV-1^07218001.0339400 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006965 | 335487661-61169-DTLTRT-05_12_2026-GO95HV-1^668004/00 5/010 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006966 | 335626394-84194-DTLSB-07_24_2025-GO95HV-1^07218001.0265905 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006967 | 335859801-85901-DETAIL-06_23_2025-ANCHIDLE-1^06237004.0192800 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006968 | 336256211-93580-DETAIL-02_16_2026-GO95HV-1^06239001.0033902 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006969 | 336488128-53329-DETAIL-05_12_2025-GO95HV-1^06142012.0017805 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006970 | 337074934-43279-DETAIL-09_16_2025-GO95HV-1^06147001.0010600 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006971 | 337346715-33570-DETAIL-04_29_2025-ABNDEQPM-1^06239002.0062408 | OTHER | Non-HFTD | Distribution | 2025-04-29 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006972 | 338012124-42739-DETAIL-05_21_2025-GO95HV-1^06243006.0106102 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006973 | 338174235-52800-DETAIL-04_28_2025-GO95HV-1^06239002.0060702 | OTHER | HFTD Tier 2 | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006974 | 338232265-25265-ADMIN-06_04_2025-GO95CLSV-1^06148014.0248801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006975 | 338345240-38149-DETAIL-09_10_2025-GO95HV-1^07218001.0178005 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006976 | 33846231-55750-DETAIL-01_24_2025-GO95HV-1^06239004.0258501 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006977 | 33863168-52540-DETAIL-11_18_2022-CUSTWIRE-1^06238004.0223406 | OTHER | HFTD Tier 2 | Distribution | 2022-11-18 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006978 | 338918142-86780-DRONE_HY-06_19_2026-COVCOTHR-2^06240004.0167341 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006979 | 339293858-73149-ADMIN-12_03_2025-POLEREPL-1^07216001.0203200 | POLE | Non-HFTD | Distribution | 2025-12-03 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006980 | 339299409-5789-DETAIL-07_28_2025-GO95HV-1^06247005.0198301 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006981 | 339945279-18330-DTLTRT-05_22_2025-GO95HV-1^668075/00 2/002 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006982 | 340016024-75570-DETAIL-01_27_2026-SVCDEFLC-1^06239002.0060306 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006983 | 340082163-98709-DETAIL-08_27_2025-GO95HV-1^06247006.0079300 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006984 | 340239316-8019-DTLSB-03_31_2026-SVCTREE-1^06241009.0327702 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006985 | 340305885-87849-DTLSB-07_17_2025-GO95HV-1^06244007.0112500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006986 | 340313126-20153-DTLSB-06_16_2026-GRDRODHI-1^07217001.0358200 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006987 | 340647771-56550-DETAIL-02_26_2026-GO95MLD-1^06238004.0027600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006988 | 340675324-56324-DETAIL-07_08_2020-CUSTWIRE-1^06148014.0257903 | OTHER | HFTD Tier 2 | Distribution | 2020-07-08 | 2023-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006989 | 340685599-20899-DETAIL-04_23_2025-GO95HV-1^06242006.0037601 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006990 | 341058695-91979-DETAIL-06_18_2025-GO95HV-1^06248004.0289101 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006991 | 341063761-29909-DTLSB-05_06_2024-GO95TCH-1^06245007.0226800 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006992 | 341104805-25899-DETAIL-01_28_2026-GO95BLTC-1^06242009.0051300 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006993 | 341343999-10669-DETAIL-09_03_2025-GO95HV-1^06247006.0295701 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006994 | 34178993-20730-DETAIL-09_11_2025-DISTHDWR-1^06147001.0132700 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006995 | 341804384-23429-DTLSB-05_04_2026-GO95HV-1^06142013.0062000 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006996 | 341837013-73280-DETAIL-02_14_2023-CUSTWIRE-1^06247002.0214500 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006997 | 341939804-41813-DTLSB-04_29_2024-SVCWIND-1^06245007.0226542 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120006998 | 341951295-9042-DETAIL-05_07_2025-GO95HV-1^06242007.0266800 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120006999 | 341955554-87260-DETAIL-01_22_2025-GO95HV-1^06239004.0255701 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007000 | 341956263-28280-DETAIL-09_09_2025-GO95HV-1^06147001.0197401 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007001 | 342109890-12409-DETAIL-08_06_2025-GO95HV-1^06247006.0202802 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007002 | 342144808-19380-DTLSB-05_05_2026-GO95HV-1^06142013.0152200 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007003 | 342347955-98259-DETAIL-06_23_2026-CUSTWIRE-1^07217001.0107300 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007004 | 342626121-59-DETAIL-08_28_2025-GO95HV-1^06247006.0063100 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007005 | 343252448-96670-DETAIL-02_04_2025-SVCDEFLC-1^06240004.0169503 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007006 | 343288255-91889-ADMIN-10_22_2025-GO95BLTC-1^06246011.0068400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007007 | 343442731-54743-DTLSB-06_02_2026-GO95CL10-1^07216001.0117900 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007008 | 343526501-41079-DTLSB-03_26_2026-BIRDDMG-1^06242008.0172300 | POLE | HFTD Tier 2 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007009 | 344004245-35310-DETAIL-03_13_2025-GO95HV-1^06238004.0224902 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007010 | 344206093-9579-DETAIL-08_19_2025-GRDRODHI-1^06247006.0367602 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007011 | 344206093-9579-DETAIL-08_19_2025-GRDRODHI-2^06247006.0367602 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007012 | 34462064-2874-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135301 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007013 | 34489383-48599-DETAIL-10_01_2025-GO95BLTC-1^06246009.0128806 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007014 | 344894387-89790-DETAIL-01_20_2026-SVCDEFLC-1^06239004.0245504 | OTHER | HFTD Tier 3 | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007015 | 344925023-42190-DETAIL-02_23_2026-BIRDDMG-1^06239002.0225401 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007016 | 344925023-42190-DETAIL-02_23_2026-GO95HV-1^06239002.0225401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007017 | 345874498-15498-DETAIL-09_09_2025-GO95HV-1^07218001.0176401 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007018 | 346111162-34880-DETAIL-02_12_2025-ANCHIDLE-1^06240004.0166401 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007019 | 346221353-41050-DETAIL-01_23_2025-GO95MLD-1^06239004.0256802 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007020 | 346235114-83830-AUDIT-05_06_2026-SVCROAD-1^06236005.0334603 | OTHER | HFTD Tier 2 | Distribution | 2026-05-06 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007021 | 346235114-83830-AUDIT-05_06_2026-SVCTREE-1^06236005.0334603 | OTHER | HFTD Tier 2 | Distribution | 2026-05-06 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007022 | 34640953-9030-DTLSB-06_04_2026-CUSTWIRE-1^07216001.0021901 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007023 | 346861045-8229-DETAIL-04_28_2025-GO95HV-1^06242007.0252900 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007024 | 347013146-99750-DETAIL-06_12_2025-GO95HV-1^06236005.0110600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-12 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007025 | 347022598-23590-DTLTRT-06_24_2025-GO95HV-1^668087/00 16/003 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007026 | 347181598-51790-DTLSB-05_05_2026-GO95HV-1^06142013.0163400 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007027 | 347228001-81419-DTLSB-05_04_2026-GO95HV-1^06241009.0032500 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007028 | 347336303-46959-DTLSB-08_11_2025-GO95HV-1^07217001.0012500 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007029 | 347574433-94433-DETAIL-06_11_2025-GUYHINS-1^668075/00 16/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007030 | 347817019-40079-DETAIL-09_30_2025-ABNDEQPM-1^06246009.0134600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007031 | 347817019-40079-DETAIL-09_30_2025-GO95HV-1^06246009.0134600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007032 | 348093069-30379-DETAIL-06_16_2025-GO95HV-1^06248004.0357341 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007033 | 348153156-51653-DTLSB-06_17_2026-GO95HV-1^07217001.0352801 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007034 | 348553856-78191-DTLTRT-05_11_2026-GO95HV-1^668038/00 4/048 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007035 | 348653904-70753-DTLSB-07_01_2025-GO95HV-1^06244006.0226411 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007036 | 348676329-93029-DTLSB-08_14_2023-CUSTWIRE-1^06243009.0243100 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007037 | 34874699-19282-DTLTRT-07_09_2025-GO95HV-1^668087/00 2/021 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007038 | 34874699-25239-DTLTRT-07_09_2025-GO95HV-1^668087/00 2/021 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007039 | 348814591-15480-DETAIL-02_16_2026-GO95HV-1^06239001.0031801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007040 | 349228146-61240-DETAIL-02_26_2025-SVCDEFLC-1^06241005.0362900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007041 | 349273463-81259-DETAIL-06_10_2024-CUSTWIRE-1^06245007.0346004 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007042 | 349438975-44490-DETAIL-03_10_2022-CUSTWIRE-1^06147006.0273201 | OTHER | Non-HFTD | Distribution | 2022-03-10 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007043 | 349650471-45042-DETAIL-04_07_2025-GUYHINS-2^06241005.0119502 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007044 | 349650471-45042-DETAIL-04_07_2025-GUYNOINS-1^06241005.0119502 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007045 | 349786751-54239-DETAIL-05_19_2025-GO95HV-1^06243006.0228503 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007046 | 349845154-10849-ADMIN-03_03_2026-POLEDERP-1^07216001.0199300 | POLE | Non-HFTD | Distribution | 2026-03-03 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007047 | 349875343-46659-DETAIL-07_29_2025-GO95HV-1^06247005.0211100 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007048 | 349949926-41579-DTLSB-07_14_2025-GO95HV-1^06244007.0146600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007049 | 350074191-29890-DETAIL-06_04_2025-GO95HV-1^06142012.0171900 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007050 | 350078660-45478-DTLSB-07_16_2025-GO95HV-1^06244006.0252902 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007051 | 35024270-29459-DETAIL-07_23_2025-GO95HV-1^06247005.0178500 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007052 | 35077864-3070-DETAIL-01_27_2026-GO95HV-1^06239002.0062306 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007053 | 350823176-81659-DETAIL-04_29_2026-GO95HV-1^668004/00 5/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007054 | 350823176-81660-DETAIL-04_29_2026-GO95HV-1^668004/00 5/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007055 | 351052083-50152-DETAIL-06_21_2023-CUSTWIRE-1^06244009.0305903 | OTHER | HFTD Tier 2 | Distribution | 2023-06-21 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007056 | 351314754-14810-DETAIL-03_18_2025-GO95HV-1^06238004.0156301 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007057 | 351504041-69590-DETAIL-09_11_2025-GO95HV-1^06147001.0079801 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007058 | 3515087-30149-DETAIL-06_10_2025-GO95HV-1^06245006.0292700 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007059 | 351585674-80609-DETAIL-08_28_2025-GO95HV-1^06247006.0185100 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007060 | 351863384-70519-DTLSB-04_06_2026-GO95MLD-1^06241009.0155700 | OTHER | Non-HFTD | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007061 | 351863384-70519-DTLSB-04_06_2026-SVCDEFLC-1^06241009.0155700 | OTHER | Non-HFTD | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007062 | 351869621-61280-DETAIL-01_23_2026-COVCOTHR-3^06240004.0236802 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007063 | 352174751-45523-DETAIL-06_17_2024-CUSTWIRE-1^06246006.0136600 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007064 | 35304670-27780-DETAIL-04_01_2026-SVCTREE-1^06237005.0261205 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007065 | 353064893-25893-DETAIL-06_18_2025-GUYHINS-1^668075/00 2/048 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007066 | 353097006-31600-DETAIL-05_07_2026-GO95HV-1^668038/00 1/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007067 | 353591139-19133-DETAIL-09_09_2025-GO95MLD-1^07218001.0175900 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007068 | 353945028-74109-ADMIN-11_10_2025-PWRTRN-1^07117008.0178101 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2026-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007069 | 353945028-74109-ADMIN-11_10_2025-PWRTRN-2^07117008.0178101 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2026-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007070 | 354002240-6479-DETAIL-09_18_2025-GO95BLTC-1^06248007.0279202 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007071 | 354002240-6479-DETAIL-09_18_2025-GO95HV-1^06248007.0279202 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007072 | 354003699-58143-DETAIL-06_17_2025-GO95HV-1^06248004.0353341 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007073 | 35401485-89449-DTLSB-07_09_2025-GO95HV-1^06244006.0346440 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007074 | 3540170-70170-DTLSB-05_04_2026-GO95HV-1^06241009.0032401 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007075 | 354182109-61943-DETAIL-07_28_2025-GO95HV-1^06247005.0198200 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007076 | 354191793-74609-ADMIN-02_16_2017-CUSTWIRE-1^06146005.0037901 | OTHER | Non-HFTD | Distribution | 2017-02-16 | 2020-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007077 | 354195550-58375-DTLSB-06_24_2026-CUSTWIRE-1^07217001.0349500 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007078 | 354195550-58375-DTLSB-06_24_2026-GO95HV-1^07217001.0349500 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007079 | 355792818-2779-DETAIL-04_10_2024-CUTOUTAR-1^06245002.0119201 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007080 | 356014811-71329-DTLSB-01_22_2026-BIRDDMG-1^06242009.0297501 | POLE | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007081 | 356014811-71329-DTLSB-01_22_2026-GO95HV-1^06242009.0297501 | OTHER | Non-HFTD | Distribution | 2026-01-22 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007082 | 35602849-96060-DTLTRT-05_06_2026-GO95HV-1^668004/00 9/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007083 | 356057008-45670-DETAIL-03_09_2026-COVCOTHR-1^06240004.0152805 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007084 | 3561793-81609-DTLTRT-05_13_2026-GRDRODHI-1^668085/00 9/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007085 | 356760761-20900-DETAIL-08_19_2025-GO95HV-1^06246001.0316000 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007086 | 357054101-31200-DTLTRT-05_18_2026-GO95HV-1^668086/00 11/007 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007087 | 357775263-80700-DETAIL-09_05_2025-GO95HV-1^06147001.0203600 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007088 | 357961164-27783-DETAIL-09_17_2025-GO95HV-1^06246006.0078150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007089 | 358281493-580-DETAIL-02_06_2025-GO95HV-1^06240004.0167301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007090 | 358655574-91883-DETAIL-09_15_2025-GO95HV-1^06248007.0154100 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007091 | 358701883-90279-DETAIL-09_15_2025-GO95HV-1^06248007.0232301 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007092 | 358728952-3569-DTLSB-07_09_2025-GO95HV-1^06244006.0276800 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007093 | 358966183-96930-DETAIL-03_04_2025-GO95MLD-1^06240004.0064700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007094 | 358978278-79749-DETAIL-09_10_2025-GO95HV-1^07218001.0174504 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007095 | 359380672-67379-ADMIN-09_29_2025-GO95CLMP-1^06246009.0110402 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007096 | 359584554-74053-DETAIL-06_26_2026-GO95HV-1^07217001.0030803 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007097 | 359787955-83163-DETAIL-06_23_2026-GRDRODHI-1^07217001.0107302 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007098 | 360241435-20951-DETAIL-04_10_2025-GO95TCH-1^06241005.0011647 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007099 | 360366629-65400-DETAIL-09_30_2025-CLRTOUCH-1^06148001.0300015 | CONDUCTOR | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007100 | 360439693-58880-DETAIL-03_31_2026-SVCDEFLC-1^06240004.0358400 | OTHER | HFTD Tier 3 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007101 | 360633640-33799-DTLSB-07_01_2025-GO95HV-1^06244007.0132401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007102 | 360874340-15340-DETAIL-06_04_2025-GUYHINS-1^06245006.0289910 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007103 | 361122241-86369-DTLSB-07_09_2025-GO95HV-1^06244007.0154400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007104 | 361206449-50973-DETAIL-09_17_2025-SVCENTCO-1^06248007.0240401 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007105 | 361260351-25709-DETAIL-10_07_2025-GUYHINS-2^06246008.0056400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007106 | 361287341-14720-DETAIL-03_11_2026-SVCTREE-1^06240004.0279601 | OTHER | HFTD Tier 2 | Distribution | 2026-03-11 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007107 | 361415634-5399-ADMIN-07_18_2023-POLEREPL-1^06241009.0220501 | POLE | Non-HFTD | Distribution | 2023-07-18 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007108 | 361415634-5399-DTLSB-04_23_2026-BIRDDMG-1^06241009.0220501 | POLE | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007109 | 361616133-90559-DTLTRT-04_20_2026-GO95HV-1^668004/02 1/004 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007110 | 361914379-77779-DTLSB-07_08_2025-GO95BLTC-1^06244007.0036400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007111 | 362141548-86460-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 3/052 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007112 | 362152314-51640-DTLSB-07_23_2025-GO95HV-1^07218001.0264904 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007113 | 362291138-49340-DETAIL-03_12_2025-GO95HV-1^06238004.0223300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007114 | 362930272-74149-DTLSB-07_21_2025-GO95HV-1^06244006.0230701 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007115 | 362951905-81609-DETAIL-07_31_2025-GO95HV-1^06247006.0200701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007116 | 363684050-32883-DETAIL-08_19_2025-GRDRODHI-1^07216001.0176600 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007117 | 36375504-51379-DTLSB-07_10_2025-GO95CL10-1^06244007.0114002 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007118 | 363818625-10849-DTLSB-07_10_2025-GO95HV-1^06244007.0119002 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007119 | 363960656-78623-DTLSB-04_17_2024-GO95MLD-1^06245007.0220542 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007120 | 364008046-72291-DTLTRT-05_07_2026-GO95HV-1^668038/00 7/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007121 | 36408264-99213-DTLSB-04_25_2024-SVCRUBLG-1^06245007.0228545 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007122 | 364117579-27919-DTLSB-05_12_2026-GO95HV-1^06242009.0286603 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007123 | 364356745-43889-ADMIN-11_10_2025-GO95BLTC-1^06246011.0062001 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007124 | 364471066-42066-DETAIL-01_13_2025-GO95MLD-1^06239004.0257300 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007125 | 364548422-8189-DETAIL-05_15_2025-ABNDEQPM-1^06243006.0155200 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007126 | 364771469-84310-DTLSB-05_20_2024-GO95HV-1^06244003.0287600 | OTHER | Non-HFTD | Distribution | 2024-05-20 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007127 | 365271606-41510-DRONE_HY-06_30_2026-POLETOP-1^06238004.0222500 | POLE | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007128 | 365500475-28989-DTLSB-07_10_2025-GO95HV-1^06244007.0118100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007129 | 365581396-75942-ADMIN-11_10_2025-GO95BLTC-1^06246011.0065501 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007130 | 365717069-20429-DTLSB-05_18_2026-BIRDDMG-1^06242009.0332701 | POLE | Non-HFTD | Distribution | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007131 | 36614774-85339-DETAIL-10_06_2025-CUSTWIRE-1^06243007.0369901 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007132 | 366198796-79779-DETAIL-08_04_2025-GO95HV-1^06246002.0129801 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007133 | 366799376-62059-DETAIL-07_29_2025-GO95HV-1^06247005.0269700 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007134 | 367444151-77229-DETAIL-05_19_2025-GO95HV-1^06142012.0118503 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007135 | 367602185-51199-DETAIL-07_28_2025-GRDRODHI-1^06247005.0311601 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007136 | 367622987-10199-DTLSB-08_30_2022-CUSTWIRE-1^06243004.0099501 | OTHER | Non-HFTD | Distribution | 2022-08-30 | 2025-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007137 | 367970604-47540-DTLSB-07_23_2025-GO95HV-1^07218001.0263903 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007138 | 368096240-7959-DTLTRT-04_22_2026-GO95HV-1^668004/02 8X/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007139 | 368180006-70863-DETAIL-07_02_2026-GO95HV-1^07217001.0099801 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007140 | 368245249-60749-DETAIL-06_05_2025-GO95HV-1^668075/00 19/025 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007141 | 36838305-53140-DETAIL-03_04_2025-GO95TCH-1^06240004.0150501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007142 | 368538114-89399-DETAIL-07_31_2025-GO95HV-1^06247006.0201800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007143 | 368590984-22910-DETAIL-09_04_2025-GO95TCH-1^06147001.0316002 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007144 | 369304123-13109-DETAIL-07_31_2025-GO95HV-1^06247006.0208704 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007145 | 369467493-8149-DETAIL-06_02_2025-GO95HV-1^06244006.0142000 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007146 | 36973819-33659-DETAIL-08_05_2025-GO95HV-1^06247005.0206800 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007147 | 369776064-87290-DETAIL-02_17_2026-ABNDEQPM-1^06239003.0252801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007148 | 370063521-57979-DTLSB-01_21_2026-GO95HV-1^06242009.0297105 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007149 | 370063521-57979-DTLSB-01_21_2026-SVCDEFLC-1^06242009.0297105 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007150 | 370104231-16231-DETAIL-05_13_2025-GO95HV-1^06142012.0016508 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007151 | 370242238-63238-DTLSB-06_03_2026-SVCROAD-1^07216001.0011840 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007152 | 370520451-16180-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007153 | 370541125-80320-DETAIL-05_12_2026-GO95HV-1^668038/00 1/046 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007154 | 370727809-76359-DETAIL-07_22_2025-GO95HV-1^06247005.0058700 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007155 | 371006360-96583-DETAIL-08_19_2025-GO95HV-1^07216001.0173700 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007156 | 371008606-77920-DETAIL-08_12_2025-GO95HV-1^06246001.0198300 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007157 | 37117746-27746-DETAIL-01_22_2026-GO95MLD-1^06239004.0234000 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007158 | 371219929-6630-DTLTRT-05_22_2025-GO95MLD-1^668075/00 12/003 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007159 | 371534914-26914-DETAIL-09_03_2025-GO95MLD-1^07216001.0097006 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007160 | 371534914-26914-DETAIL-09_03_2025-GUYHINS-1^07216001.0097006 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007161 | 37170956-40770-DETAIL-01_24_2025-GO95HV-1^06239004.0258843 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007162 | 371807860-3839-DETAIL-05_06_2025-GO95HV-1^06243006.0280100 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007163 | 371841074-17399-DETAIL-09_04_2025-GO95HV-1^06147001.0319400 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007164 | 371843494-37409-DETAIL-08_27_2025-GO95HV-1^06247006.0170500 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007165 | 371946764-43920-DTLSB-02_06_2023-CUSTWIRE-1^06248001.0257100 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007166 | 372267429-33570-DETAIL-02_13_2025-SVCNEUT-1^06240004.0169201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007167 | 372582803-13803-DETAIL-03_16_2026-SVCTREE-1^06240004.0151301 | OTHER | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007168 | 372744261-16261-DETAIL-03_27_2023-ABNDEQPM-1^06142016.0050600 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007169 | 372869218-49069-DETAIL-09_18_2025-GO95HV-1^06248007.0360800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007170 | 372958000-63759-DETAIL-09_04_2025-GO95HV-1^07216001.0098304 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007171 | 37302235-16235-DETAIL-06_05_2025-GO95HV-1^06148014.0246602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007172 | 373198038-96820-DETAIL-09_03_2025-GO95HV-1^06246001.0208900 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007173 | 373927451-67659-DETAIL-06_17_2024-CUSTWIRE-1^06246006.0241100 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007174 | 373936830-59830-AUDIT-10_14_2025-ABNDEQPM-1^07219001.0323107 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007175 | 374128661-36459-DTLSB-05_28_2026-GO95HV-1^07216001.0022402 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007176 | 374284531-25301-DETAIL-01_14_2026-SVCRUBLG-1^06239004.0135148 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007177 | 374422602-27162-DTLSB-06_26_2025-GO95BLTC-1^06244007.0108140 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007178 | 374483229-1649-DTLSB-07_07_2025-GO95MLD-1^06244007.0134704 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007179 | 374509205-51609-DETAIL-07_31_2025-GO95HV-1^06247006.0200700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007180 | 37466229-44030-DETAIL-09_05_2025-GO95HV-1^06147001.0294201 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007181 | 37483164-77353-DETAIL-08_27_2025-GO95HV-1^06247006.0179200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007182 | 374867693-71080-DETAIL-02_24_2026-BIRDDMG-1^06239002.0070401 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007183 | 374867693-71080-DETAIL-02_24_2026-SVCDEFLC-1^06239002.0070401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007184 | 37493473-68859-DTLSB-08_12_2025-GO95HV-1^07217001.0012102 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007185 | 37493473-68859-DTLSB-08_12_2025-GO95MLD-1^07217001.0012102 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007186 | 374942809-78929-DETAIL-06_04_2025-GO95HV-1^06148014.0248804 | OTHER | HFTD Tier 2 | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007187 | 375355381-10481-DETAIL-01_30_2025-SVCDEFLC-1^06240004.0162706 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007188 | 375391286-55289-ADMIN-11_03_2025-GO95HV-1^06246001.0221401 | OTHER | Non-HFTD | Distribution | 2025-11-03 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007189 | 375402656-34789-DETAIL-10_15_2025-GO95HV-1^06148001.0203845 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007190 | 375794123-79420-DETAIL-05_15_2024-GO95MLD-1^06142012.0124703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007191 | 3760070-49459-DETAIL-07_30_2025-GO95HV-1^06247005.0178601 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007192 | 376043629-21549-DTLSB-07_03_2025-GO95MLD-1^06244007.0138300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007193 | 376553018-46190-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244410 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007194 | 376553018-46190-DETAIL-01_12_2026-COVCOTHR-2^06239004.0244410 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007195 | 376587888-46973-DETAIL-09_22_2025-GO95HV-1^06248007.0367400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007196 | 376702505-1229-DETAIL-05_13_2025-GO95HV-1^06142012.0014503 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007197 | 376728997-32120-DETAIL-04_27_2026-GO95HV-1^06142012.0144912 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007198 | 376733020-50483-AUDIT-09_09_2025-SVCENTCO-1^07216001.0174802 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007199 | 376887788-42059-DETAIL-01_23_2026-BIRDDMG-1^06240004.0131101 | POLE | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007200 | 376973862-57679-DETAIL-08_14_2025-GO95HV-1^06246001.0314402 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007201 | 377205904-73789-ADMIN-11_10_2025-GO95BLTC-1^06246012.0128801 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007202 | 377995296-61859-DTLTRT-05_04_2026-GO95HV-1^668004/00 4/019 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007203 | 377995296-61860-DTLTRT-05_04_2026-GO95HV-1^668004/00 4/019 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007204 | 378279076-87281-ADMIN-05_09_2025-SVCTREE-1^06241006.0115703 | OTHER | HFTD Tier 2 | Distribution | 2025-05-09 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007205 | 378282420-51469-DTLSB-07_01_2025-GO95TCH-1^06244007.0130300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007206 | 378316543-66129-DETAIL-04_12_2022-CUSTWIRE-1^06142012.0130606 | OTHER | Non-HFTD | Distribution | 2022-04-12 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007207 | 378316543-66129-DETAIL-04_12_2022-CUSTWIRE-2^06142012.0130606 | OTHER | Non-HFTD | Distribution | 2022-04-12 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007208 | 37832779-25750-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/064 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007209 | 378375593-17593-DETAIL-03_11_2025-GO95HV-1^06238004.0274904 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007210 | 378614728-80499-DETAIL-10_06_2021-CUSTWIRE-1^06148005.0342002 | OTHER | Non-HFTD | Distribution | 2021-10-06 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007211 | 378960437-82437-DETAIL-06_18_2025-GO95HV-1^668075/00 3/046 | OTHER | HFTD Tier 2 | Transmission | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007212 | 379151031-29180-DETAIL-02_16_2026-GO95HV-1^06239001.0058702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007213 | 379496861-32230-DTLTRT-05_18_2026-GO95HV-1^668086/00 13/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007214 | 379854056-69629-DETAIL-05_12_2025-GO95HV-1^06142012.0012800 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007215 | 38008791-31889-DTLSB-07_08_2025-GO95HV-1^06245007.0350202 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007216 | 380606514-75509-DETAIL-09_04_2025-GO95HV-1^06247006.0186601 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007217 | 380976908-91289-DETAIL-07_31_2025-GO95HV-1^06247005.0264001 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007218 | 381619641-89530-DETAIL-09_11_2025-GO95HV-1^07216001.0079604 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007219 | 381777815-32870-DETAIL-01_24_2025-GO95HV-1^06239004.0258740 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007220 | 381813182-84139-DETAIL-05_20_2025-GO95HV-1^06243006.0068001 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007221 | 382189033-97780-DETAIL-02_24_2026-BIRDDMG-1^06239002.0180701 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007222 | 382190406-64406-DTLSB-06_10_2026-GO95TCH-1^07217001.0353330 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007223 | 382441591-32080-DETAIL-02_18_2026-GO95HV-1^06239001.0053702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007224 | 382502901-13662-DTLSB-06_26_2025-GO95HV-1^06244007.0107442 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007225 | 382560541-22709-DETAIL-09_08_2025-GO95HV-1^06246006.0057701 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007226 | 382560541-22709-DETAIL-09_08_2025-GUYNOINS-1^06246006.0057701 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-08 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007227 | 382702361-73330-DETAIL-09_30_2025-GO95CL10-1^06148001.0301108 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007228 | 382823664-23430-DETAIL-04_20_2026-SVCROOF-1^06142012.0147912 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007229 | 383023170-32530-DTLTRT-05_14_2026-BIRDDMG-1^668086/00 14/005 | POLE | Non-HFTD | Transmission | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007230 | 383023170-32530-DTLTRT-05_14_2026-GO95HV-1^668086/00 14/005 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007231 | 383292401-22173-DETAIL-09_10_2025-GO95HV-1^06246006.0185751 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007232 | 3832971-7389-ADMIN-10_27_2025-GO95HV-1^06246001.0115901 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007233 | 383424921-15730-DTLSB-06_03_2026-GO95HV-1^07216001.0025200 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007234 | 383450873-8521-DRONE_HY-06_19_2026-COVCOTHR-1^06239004.0362507 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007235 | 383453420-24489-DTLSB-07_22_2025-GO95HV-1^06244006.0183100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007236 | 383485793-27359-DTLTRT-04_20_2026-GO95HV-1^668004/02 3/002 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007237 | 383485793-27359-DTLTRT-04_20_2026-GO95MLD-1^668004/02 3/002 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007238 | 384204778-18999-DETAIL-05_08_2025-GO95HV-1^06243006.0104600 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007239 | 384618015-74000-DETAIL-02_04_2026-GO95HV-1^06239003.0019606 | OTHER | Non-HFTD | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007240 | 384692483-93430-ADMIN-11_14_2025-GO95HV-1^06246001.0324504 | OTHER | Non-HFTD | Distribution | 2025-11-14 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007241 | 384730011-57059-DETAIL-08_20_2025-GO95HV-1^06247006.0369201 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007242 | 384961679-33679-DETAIL-07_31_2025-GO95HV-1^06247006.0207709 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007243 | 385146939-93570-DETAIL-02_13_2025-GO95CL10-1^06240004.0169200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007244 | 38575086-29319-DETAIL-11_18_2025-ANCHIDLE-1^06247009.0247400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-11-18 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007245 | 385906550-37559-DETAIL-09_18_2025-BIRDDMG-1^06246006.0012401 | POLE | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007246 | 385906550-37559-DETAIL-09_18_2025-GO95HV-1^06246006.0012401 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007247 | 385996515-15870-DETAIL-01_16_2025-SVCROAD-1^06239004.0256211 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007248 | 386041398-76570-DETAIL-01_23_2025-ANCHIDLE-1^06240004.0083303 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007249 | 386121268-6270-DRONE_HY-06_30_2026-SVCTREE-1^06240004.0168401 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007250 | 386127511-76133-DETAIL-05_07_2025-GO95HV-1^06243006.0100801 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007251 | 386228866-18399-DETAIL-04_28_2025-GO95HV-1^06242006.0191302 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007252 | 386292878-80629-DETAIL-01_29_2026-BIRDDMG-1^06242009.0053900 | POLE | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007253 | 386480286-20263-DETAIL-07_02_2026-GUYHINS-1^07217001.0049603 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007254 | 386480286-20263-DETAIL-07_02_2026-SVCROAD-1^07217001.0049603 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007255 | 386489247-22719-DTLSB-07_08_2026-GO95HV-1^06242009.0269800 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007256 | 386867664-62509-DETAIL-08_27_2025-GO95HV-1^06247006.0187802 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007257 | 387078331-6239-DETAIL-05_19_2025-GO95HV-1^06243006.0226502 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007258 | 387143158-26339-DTLTRT-06_23_2025-GO95HV-1^668087/00 3/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007259 | 387161984-21299-DETAIL-09_23_2025-GO95HV-1^06247004.0074400 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007260 | 387205156-98923-DTLSB-05_01_2024-CUSTWIRE-1^06245007.0228444 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007261 | 387241121-66039-DETAIL-07_09_2024-CUSTWIRE-1^06244005.0139402 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007262 | 38733593-97729-DETAIL-05_12_2025-SVCENTCO-1^06142012.0015900 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007263 | 387417364-45153-DETAIL-07_28_2025-GO95HV-1^06247005.0301600 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007264 | 387464436-83809-DETAIL-09_08_2025-GO95HV-1^06247007.0127900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007265 | 387542195-24539-DETAIL-05_29_2025-GUYHINS-1^06244006.0031201 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007266 | 387774688-5688-DETAIL-09_02_2025-GO95HV-1^06247006.0278401 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007267 | 38781391-47069-DTLTRT-04_28_2026-GO95HV-1^668004/00 5/008 | OTHER | HFTD Tier 2 | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007268 | 38781391-47070-DTLTRT-04_28_2026-GO95HV-1^668004/00 5/008 | OTHER | HFTD Tier 2 | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007269 | 387828325-84439-DETAIL-05_29_2025-GO95HV-1^06244006.0110800 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007270 | 388133481-55089-DETAIL-10_02_2025-GO95BLTC-1^06246008.0063201 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007271 | 388193044-75044-DTLTRT-07_08_2025-BIRDDMG-1^668087/00 8/027 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007272 | 388254953-40740-ADMIN-02_09_2024-POLEREPL-1^06144006.0153100 | POLE | Non-HFTD | Distribution | 2024-02-09 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007273 | 388487031-44499-DTLSB-10_16_2025-GRDRODHI-1^06247001.0348001 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007274 | 38862529-16799-DETAIL-09_10_2025-GO95CLSV-1^06246007.0249502 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007275 | 388812849-20183-DETAIL-08_19_2025-GO95HV-1^07216001.0175901 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007276 | 388812849-20183-DETAIL-08_19_2025-SVCDEFLC-1^07216001.0175901 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007277 | 38920300-62800-DETAIL-06_05_2025-SVCENTCO-1^668075/00 7/026 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007278 | 389394908-3540-DTLTRT-06_23_2025-GO95HV-1^668087/00 3/003 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007279 | 389491353-12230-DTLSB-07_31_2025-GO95HV-1^07218001.0270700 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007280 | 389661669-42459-DETAIL-07_28_2025-CONDFRAY-2^06247005.0198601 | CONDUCTOR | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007281 | 389789626-20760-DETAIL-04_30_2026-GO95HV-1^668004/00 2/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007282 | 390015942-37942-DETAIL-07_24_2025-GO95HV-1^06247005.0147300 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007283 | 390097090-74658-DETAIL-08_05_2025-GO95HV-1^06247005.0206301 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007284 | 390113685-6070-DETAIL-10_15_2025-BIRDDMG-1^668047/00 2/025 | POLE | HFTD Tier 2 | Transmission | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007285 | 390160032-84139-DETAIL-05_15_2024-GO95MLD-1^06142012.0125806 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007286 | 390196783-11690-DETAIL-02_24_2026-BIRDDMG-1^06239002.0273301 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007287 | 390205833-33040-ADMIN-10_28_2025-PWRTRN-1^06246001.0010000 | OTHER | Non-HFTD | Distribution | 2025-10-28 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007288 | 390948740-86201-DETAIL-01_31_2025-GO95HV-1^06239004.0136217 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007289 | 390970205-22205-DETAIL-06_02_2025-GO95HV-1^06148014.0242900 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007290 | 391140124-46759-DETAIL-06_16_2025-GO95HV-1^06248005.0368800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007291 | 391351061-4819-DETAIL-05_25_2023-GO95HV-1^07117007.0227202 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2028-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007292 | 391488759-62829-DTLSB-02_05_2026-BIRDDMG-1^06243009.0316701 | POLE | HFTD Tier 2 | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007293 | 391599671-10771-DETAIL-05_12_2025-GUYHINS-1^06243006.0209202 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-12 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007294 | 392012871-36289-DETAIL-05_05_2025-GUYHINS-1^06243006.0347203 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-05 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007295 | 392151920-3240-DETAIL-09_04_2025-GO95HV-1^07216001.0099203 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007296 | 392358568-14340-ADMIN-04_23_2024-ABNDEQPM-1^06145001.0023205 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007297 | 392421735-83735-DETAIL-05_29_2025-GO95HV-1^06147014.0010901 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007298 | 392590063-86929-DETAIL-04_22_2026-GO95HV-1^06142012.0146600 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007299 | 392870195-94200-DETAIL-01_28_2026-BIRDDMG-1^06239002.0063611 | POLE | Non-HFTD | Distribution | 2026-01-28 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007300 | 393506679-68099-DETAIL-10_20_2021-CUSTWIRE-1^06148005.0261505 | OTHER | Non-HFTD | Distribution | 2021-10-20 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007301 | 393640245-98872-DETAIL-04_23_2025-GO95HV-1^06242005.0360144 | OTHER | HFTD Tier 2 | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007302 | 393640245-98872-DETAIL-04_23_2025-GO95TCH-1^06242005.0360144 | OTHER | HFTD Tier 2 | Distribution | 2025-04-23 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007303 | 393805646-46379-DETAIL-08_12_2025-GO95BLTC-1^06246001.0195402 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007304 | 394011664-83664-DTLTRT-08_04_2025-GO95HV-1^668087/00 4/028 | OTHER | Non-HFTD | Transmission | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007305 | 39418234-19619-DTLSB-04_23_2026-ENCHRW-1^06241009.0221802 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007306 | 394660434-67939-DETAIL-05_15_2025-GO95HV-1^06243006.0096002 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007307 | 39470658-88430-DTLTRT-05_06_2026-BIRDDMG-1^668038/00 6/058 | POLE | HFTD Tier 2 | Transmission | 2026-05-06 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007308 | 395059089-50129-DTLSB-05_14_2026-SVCDEFLC-1^06242009.0282401 | OTHER | Non-HFTD | Distribution | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007309 | 395137060-90932-DETAIL-04_07_2025-SVCROOF-1^06241005.0119501 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007310 | 395141695-71999-DETAIL-09_09_2025-GO95HV-1^06246007.0152050 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007311 | 395192621-13329-DTLSB-01_26_2026-BIRDDMG-1^06242009.0296701 | POLE | HFTD Tier 2 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007312 | 395259671-80133-DETAIL-09_18_2025-GO95BLTC-1^07219001.0325103 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007313 | 395369866-16359-DTLTRT-05_07_2026-GO95MLD-1^668004/00 4/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007314 | 395429065-73199-DTLSB-07_01_2025-GO95HV-1^06244006.0225413 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007315 | 3956503-77589-DETAIL-03_06_2024-CUSTWIRE-1^06245007.0275403 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007316 | 395674795-75629-DETAIL-08_21_2024-SVCROAD-1^06245008.0245100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007317 | 395711273-46180-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0165402 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007318 | 395755099-70479-DETAIL-06_16_2025-GO95HV-1^06248004.0359242 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007319 | 395843789-26289-DETAIL-06_04_2025-GUYHINS-1^668075/00 9/025 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007320 | 395843789-26289-DETAIL-06_04_2025-GUYHINS-2^668075/00 9/025 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007321 | 39610979-10769-DTLSB-03_25_2026-GO95HV-1^06242009.0044200 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007322 | 396844849-81550-DTLTRT-07_08_2025-BIRDDMG-1^668087/00 10/026 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007323 | 396991709-31450-AUDIT-11_12_2025-GRDRODHI-1^06246001.0294700 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007324 | 397294091-650-DTLSB-05_06_2026-GO95HV-1^06142013.0270401 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007325 | 397347141-2831-DETAIL-04_09_2025-GRDRODHI-1^06241005.0020402 | OTHER | HFTD Tier 2 | Distribution | 2025-04-09 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007326 | 397559699-4070-DETAIL-06_11_2025-GO95HV-1^06236005.0220941 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007327 | 39784913-21669-DTLTRT-06_04_2021-GO95HV-1^668041/00 5/009 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007328 | 397961130-95133-DTLSB-06_17_2026-GO95HV-1^07217001.0341900 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007329 | 398102401-53401-DRONE_HY-06_30_2026-IRSPOTOH-1^06240004.0166611 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007330 | 398129478-76609-DETAIL-09_08_2025-GO95HV-1^06246006.0082800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007331 | 398134749-75470-DRONE_HY-06_30_2026-COVCOTHR-1^06240004.0169640 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007332 | 398308496-64990-DETAIL-02_11_2025-GO95MLD-1^06240004.0355000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007333 | 398308496-64990-DETAIL-03_31_2026-COVCOTHR-1^06240004.0355000 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007334 | 398605558-44529-DTLSB-04_29_2026-GO95HV-1^06142013.0283700 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007335 | 398765911-73150-DTLTRT-05_18_2026-BIRDDMG-1^668086/00 9/008 | POLE | Non-HFTD | Transmission | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007336 | 398880991-49411-DETAIL-04_14_2026-CUSTWIRE-1^06237004.0171802 | OTHER | HFTD Tier 2 | Distribution | 2026-04-14 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007337 | 398986349-27841-DETAIL-04_03_2025-GO95MLD-1^06241005.0091001 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007338 | 399187588-28079-DETAIL-06_10_2025-GO95HV-1^06245006.0293500 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007339 | 399518609-50713-DETAIL-08_27_2025-GO95HV-1^06247006.0284901 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007340 | 399723381-21529-DETAIL-05_15_2025-SVCNEUT-1^06142012.0112008 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007341 | 399990209-50670-DRONE_HY-06_19_2026-ABNDPOLE-1^06240004.0164404 | POLE | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007342 | 40009694-11939-DETAIL-05_06_2025-GO95HV-1^06243006.0048102 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007343 | 400161375-82499-DETAIL-08_13_2025-GO95HV-1^06247006.0262601 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007344 | 400298979-57429-DTLSB-02_09_2026-BIRDDMG-1^06243010.0366402 | POLE | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007345 | 400330964-5809-ADMIN-10_21_2025-GO95HV-1^06246012.0052606 | OTHER | HFTD Tier 2 | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007346 | 400352145-70033-DETAIL-09_16_2025-GO95HV-1^06247004.0087641 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007347 | 400441870-54389-DTLSB-04_22_2026-CONDFRAY-1^06241009.0257800 | CONDUCTOR | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007348 | 400441870-54389-DTLSB-04_22_2026-GO95MLD-1^06241009.0257800 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007349 | 400640304-96132-DETAIL-03_06_2025-GRDRODHI-1^06241005.0120502 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007350 | 401111102-75230-DTLSB-08_14_2025-GO95HV-1^07218001.0286902 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007351 | 401135374-88683-DETAIL-08_18_2025-GO95HV-1^06247006.0362405 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007352 | 401217156-37489-DTLSB-07_10_2025-GO95HV-1^06244007.0037801 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007353 | 401330111-84950-DTLTRT-04_23_2026-GO95HV-1^668004/00 8/001 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007354 | 401393084-44489-DETAIL-09_17_2025-GO95HV-1^06147001.0014901 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007355 | 401476175-35159-DETAIL-07_23_2025-GO95HV-1^06247005.0116900 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007356 | 402834784-83261-DETAIL-02_17_2025-CUSTWIRE-1^06241005.0235600 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007357 | 403724939-21269-DTLTRT-06_14_2021-GO95HV-1^668041/00 13/020 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007358 | 403780456-21271-DETAIL-02_24_2025-GO95BLTC-1^06239004.0367700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007359 | 404099844-73462-DETAIL-04_22_2025-GO95TCH-1^06242005.0360141 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007360 | 404232111-92363-DTLSB-04_10_2024-SVCROAD-1^06245007.0223042 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007361 | 404625942-62589-DETAIL-07_22_2025-GO95HV-1^06247005.0175500 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007362 | 40463401-80759-DETAIL-08_20_2025-GO95MLD-1^07216001.0175001 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007363 | 405071493-87659-DETAIL-07_29_2025-GO95HV-1^06247005.0216600 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007364 | 405411901-25043-DETAIL-07_01_2026-GUYHINS-1^07217001.0169503 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007365 | 405714066-91450-DETAIL-08_06_2025-GO95HV-1^06246002.0106400 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007366 | 405729533-22450-DTLTRT-05_13_2026-GO95HV-1^668085/00 3/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007367 | 405900385-86589-DETAIL-10_06_2025-GRDRODHI-1^06148001.0189002 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007368 | 405964113-81479-DETAIL-09_29_2025-GO95HV-1^06246009.0112201 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007369 | 40600130-16955-DETAIL-02_24_2026-GO95HV-1^06239003.0129100 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007370 | 406077829-20750-DETAIL-09_30_2025-SVCENTCO-1^06148001.0301205 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007371 | 406204828-10770-DETAIL-02_03_2025-GO95HV-1^06240004.0167804 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007372 | 406515079-8133-DTLSB-06_24_2026-SVCDEFLC-1^07217001.0348000 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007373 | 406792293-88160-DTLTRT-05_13_2026-GRDRODHI-1^668085/00 10/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007374 | 406864934-69469-DETAIL-06_02_2025-GO95HV-1^06244006.0155100 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007375 | 406900128-28260-DETAIL-09_30_2025-GO95HV-1^06148001.0300211 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007376 | 406928999-90159-DTLTRT-05_06_2026-GO95HV-1^668004/00 7/023 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007377 | 407265167-38590-DETAIL-01_12_2026-BIRDDMG-1^06239004.0244840 | POLE | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007378 | 407640755-17789-DTLSB-07_09_2025-GO95HV-1^06244006.0345500 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007379 | 407841950-75550-DETAIL-06_05_2025-GO95HV-1^668075/00 16/027 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007380 | 408012504-92473-DETAIL-03_29_2023-SVCROAD-1^06142016.0084602 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007381 | 408051026-95940-DTLSB-07_24_2025-CUSTWIRE-1^07218001.0264700 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007382 | 408068691-72129-DETAIL-05_28_2025-GO95HV-1^06142012.0151900 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007383 | 408363294-83939-DETAIL-05_07_2025-GO95HV-1^06243006.0049000 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007384 | 408449173-32519-ADMIN-01_14_2026-GO95HV-1^668005/00 8/093 | OTHER | Non-HFTD | Transmission | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007385 | 408571548-84869-DETAIL-05_08_2025-GO95HV-1^06243006.0036200 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007386 | 408609236-13153-DTLSB-06_16_2026-COPLLEAN-1^07217001.0357200 | POLE | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007387 | 408785888-87369-DTLTRT-07_06_2022-GO95HV-1^668005/00 5/036 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007388 | 409357743-89860-ADMIN-11_13_2025-GO95CLSV-1^06246001.0325400 | OTHER | Non-HFTD | Distribution | 2025-11-13 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007389 | 409571914-33779-DETAIL-08_21_2024-CUSTWIRE-1^06246005.0269640 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007390 | 409870801-56889-DETAIL-08_20_2025-GO95HV-1^06247006.0369000 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007391 | 410222844-1659-DETAIL-07_28_2025-RISEBKSP-1^06247005.0303400 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007392 | 410245454-32899-AUDIT-03_21_2024-POLETOP-1^06245007.0275707 | POLE | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007393 | 410703298-27290-DETAIL-01_13_2026-GO95MLD-1^06239004.0246000 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007394 | 41098491-18511-DETAIL-01_21_2025-GO95TCH-1^06239004.0256440 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007395 | 411028388-53750-DETAIL-02_03_2026-GO95HV-1^06239003.0019302 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007396 | 411041623-32623-DETAIL-06_04_2025-GO95HV-1^668075/00 13/024 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007397 | 411041623-32623-DETAIL-06_04_2025-GUYHINS-1^668075/00 13/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007398 | 411041623-32623-DETAIL-06_04_2025-GUYHINS-3^668075/00 13/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007399 | 411206139-90659-DETAIL-08_05_2025-GO95HV-1^06247005.0207600 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007400 | 411206139-90659-DETAIL-08_05_2025-POLETOP-1^06247005.0207600 | POLE | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007401 | 41123813-22630-ADMIN-11_06_2025-GO95BLTC-1^06246001.0122800 | OTHER | Non-HFTD | Distribution | 2025-11-06 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007402 | 411247054-450-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/043 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007403 | 41153351-48259-DTLSB-07_07_2025-GO95HV-1^06245007.0352307 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007404 | 411539912-41759-DETAIL-07_29_2025-GO95HV-1^06247005.0214701 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007405 | 412200825-31549-DTLSB-07_10_2025-GO95HV-1^06244006.0342202 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007406 | 412642436-22060-DTLTRT-05_21_2026-GO95MLD-1^668086/00 10/015 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007407 | 412742973-59590-DETAIL-02_24_2026-BIRDDMG-1^06239002.0272401 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007408 | 412827069-10473-DETAIL-09_22_2025-GO95HV-1^06248007.0242600 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007409 | 412937836-66181-DETAIL-04_24_2025-GO95BLTC-1^06241006.0028100 | OTHER | HFTD Tier 2 | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007410 | 41302104-94179-DETAIL-08_27_2025-GO95HV-1^06247006.0170601 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007411 | 413208558-42939-DTLSB-06_30_2025-GO95HV-1^06244006.0225409 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007412 | 413352844-88699-DETAIL-05_22_2025-GO95HV-1^06244006.0092200 | OTHER | Non-HFTD | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007413 | 413494398-45398-DETAIL-01_23_2025-GO95TCH-1^06239004.0256402 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007414 | 41408605-2800-DETAIL-04_08_2026-GO95HV-1^06240002.0312204 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007415 | 414118315-59499-DETAIL-01_28_2026-GO95BLTC-1^06242009.0053101 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007416 | 414129084-35760-ADMIN-09_16_2025-GO95HV-1^06147001.0111200 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007417 | 414189067-10240-DETAIL-02_17_2026-GUYHINS-1^06239002.0070601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-17 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007418 | 414327035-60329-DETAIL-05_19_2025-GO95HV-1^06142012.0016300 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007419 | 414510043-78998-DTLTRT-05_07_2026-GO95HV-1^668004/00 9/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007420 | 414629081-19380-DETAIL-02_23_2026-GO95HV-1^06239002.0031402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007421 | 41477991-33150-DETAIL-03_04_2026-COVCOTHR-1^06238004.0028542 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-04 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007422 | 414786676-84460-DETAIL-05_07_2026-GO95HV-1^668038/00 4/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007423 | 414790875-64700-DETAIL-04_08_2026-GO95HV-1^06240002.0329201 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007424 | 414793320-49383-DETAIL-08_19_2025-SVCDEFLC-1^07216001.0174805 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007425 | 414847555-13059-DETAIL-09_16_2025-GO95HV-1^06247004.0184801 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007426 | 414968655-9829-DETAIL-05_08_2024-CUSTWIRE-1^06142012.0120404 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007427 | 414987783-5959-DETAIL-09_15_2025-XARMSPCR-1^06248007.0230001 | CROSSARM | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007428 | 415048997-95959-DTLSB-08_18_2025-GO95HV-1^07218001.0355600 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007429 | 415647070-37743-DETAIL-06_29_2026-GO95HV-1^07217001.0158500 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007430 | 41569509-17930-DETAIL-08_11_2025-GO95HV-1^06246002.0260900 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007431 | 416125065-63209-DETAIL-08_13_2025-GO95HV-1^06247006.0263602 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007432 | 416333438-12009-DETAIL-04_09_2024-GO95BLTC-1^06147005.0215802 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007433 | 416493478-47259-DETAIL-09_17_2025-GO95HV-1^06247007.0019600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007434 | 416555994-52963-DETAIL-09_11_2025-GO95HV-1^06248007.0234540 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007435 | 416555994-52963-DETAIL-09_11_2025-XARMSPCR-1^06248007.0234540 | CROSSARM | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007436 | 416859559-92770-DETAIL-08_25_2025-GO95HV-1^06246001.0206801 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007437 | 416972476-13070-DETAIL-01_24_2025-GO95HV-1^06239004.0258941 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007438 | 417480745-12129-DETAIL-04_22_2025-GO95HV-1^06242006.0085701 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007439 | 417908069-62730-DTLTRT-05_27_2025-GO95MLD-1^668075/00 3/005 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007440 | 418660705-17560-DRONE_HY-07_15_2026-COVCOTHR-1^06239004.0256505 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007441 | 418713474-76474-DTLTRT-07_08_2025-GO95HV-1^668087/00 16/027 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007442 | 418713474-76474-DTLTRT-07_08_2025-GUYHINS-1^668087/00 16/027 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007443 | 41886001-57250-DETAIL-02_26_2026-COVCOTHR-1^06238004.0022802 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007444 | 418984346-66259-DTLTRT-05_07_2026-GUYHINS-2^668004/00 2/025 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007445 | 418984346-66259-DTLTRT-05_07_2026-GUYHINS-3^668004/00 2/025 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007446 | 418997242-48370-DETAIL-06_10_2026-GUYHINS-3^668086/00 15/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007447 | 419225473-39659-ADMIN-04_30_2024-POLEREPL-1^668004/02 2/007 | POLE | Non-HFTD | Transmission | 2024-04-30 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007448 | 419233698-20409-DETAIL-09_24_2025-GO95HV-1^06246009.0075100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007449 | 41981815-13609-DETAIL-08_28_2025-GO95HV-1^06247006.0194801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007450 | 420047476-64319-ADMIN-11_13_2025-GO95HV-1^06247008.0315600 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007451 | 420274018-36018-DETAIL-03_28_2023-CUSTWIRE-1^06142016.0084807 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007452 | 420360309-9359-DETAIL-07_22_2025-GO95HV-1^06247005.0059102 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007453 | 420403576-31400-DETAIL-04_08_2026-GO95HV-1^06240002.0316200 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007454 | 420628554-14370-DETAIL-08_20_2025-GO95HV-1^06246001.0171500 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007455 | 420859512-90179-DETAIL-05_12_2025-GO95HV-1^06243006.0215900 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007456 | 420940098-97470-DTLTRT-06_23_2025-GRDRODHI-1^668087/00 11/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007457 | 420940098-97470-DTLTRT-06_23_2025-GUYHINS-1^668087/00 11/002 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007458 | 421357313-11514-DETAIL-03_31_2025-SVCENTCO-1^06241005.0115603 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007459 | 421449849-24349-DTLSB-07_14_2025-GO95HV-1^06244006.0289500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007460 | 421797606-8606-DETAIL-01_22_2026-GO95MLD-1^06239004.0227300 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007461 | 421917606-76170-DETAIL-08_07_2025-GO95HV-1^06246002.0234000 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007462 | 422085546-49670-DETAIL-01_22_2025-GO95HV-1^06239004.0256541 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007463 | 422085546-49670-DETAIL-01_22_2025-GO95MLD-1^06239004.0256541 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007464 | 422255148-37370-DTLTRT-06_30_2025-GUYNOINS-1^668087/00 4/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007465 | 422255148-37370-DTLTRT-06_30_2025-GUYNOINS-2^668087/00 4/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007466 | 422352966-75470-DTLSB-04_29_2026-GO95HV-1^06142013.0198600 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007467 | 422423342-97929-DETAIL-05_15_2024-GO95MLD-1^06142012.0126840 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007468 | 422538963-74359-DTLTRT-04_22_2026-GO95HV-1^668004/02 15/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007469 | 422542594-29299-DETAIL-08_13_2025-GO95HV-1^06247006.0252201 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007470 | 422621247-61570-ADMIN-11_12_2025-GO95MLD-1^06142012.0144909 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007471 | 422640005-50005-DTLTRT-06_30_2025-ABNDEQPM-1^668087/01 2/001 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007472 | 422640005-50005-DTLTRT-06_30_2025-BIRDDMG-1^668087/01 2/001 | POLE | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007473 | 422640005-50005-DTLTRT-06_30_2025-GO95HV-1^668087/01 2/001 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007474 | 422757135-39891-DTLTRT-05_12_2026-GO95HV-1^668038/00 2/044 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007475 | 422757135-70670-DTLTRT-05_12_2026-GO95HV-1^668038/00 2/044 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007476 | 422765750-70840-DETAIL-04_01_2026-BIRDDMG-1^06237005.0261200 | POLE | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007477 | 422765750-70840-DETAIL-04_01_2026-CUSTWIRE-1^06237005.0261200 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007478 | 422879653-66889-DETAIL-05_28_2025-GO95MLD-1^06244006.0090301 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007479 | 422966710-35540-DETAIL-03_10_2026-COVCOTHR-1^06239003.0061005 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007480 | 423059571-58070-DETAIL-10_08_2020-CUSTWIRE-1^668047/00 5/016 | OTHER | HFTD Tier 2 | Transmission | 2020-10-08 | 2023-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007481 | 423227954-67769-DETAIL-09_11_2025-POLISSUE-1^06248007.0223501 | POLE | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007482 | 423326908-999-DETAIL-09_02_2025-GO95HV-1^06247006.0276402 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007483 | 423969432-44450-DETAIL-02_06_2025-GO95MLD-1^06239004.0137202 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007484 | 42410316-80989-DETAIL-01_14_2026-BIRDDMG-1^06239004.0244943 | POLE | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007485 | 424272879-38389-DETAIL-09_30_2025-GO95HV-1^06246009.0136200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007486 | 424624266-75253-DTLSB-06_16_2026-GO95HV-1^07217001.0355302 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007487 | 424732642-57383-DETAIL-07_24_2025-GO95HV-1^06247005.0139240 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007488 | 424795646-14770-DETAIL-01_15_2025-GO95HV-1^06239004.0255246 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007489 | 425095729-88389-DETAIL-06_16_2025-GO95HV-1^06248004.0354541 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007490 | 425194944-51053-DETAIL-06_26_2026-GO95HV-1^07217001.0048500 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007491 | 425399819-85082-DTLTRT-07_09_2025-GUYNOINS-2^668087/00 3/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007492 | 425399819-86082-DTLTRT-07_09_2025-GUYNOINS-2^668087/00 3/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007493 | 425478383-36579-DETAIL-05_27_2025-GO95HV-1^06244006.0091402 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007494 | 425714878-12880-DTLTRT-06_24_2025-BIRDDMG-1^668087/00 6/004 | POLE | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007495 | 425717500-10179-DETAIL-03_09_2026-SVCROAD-1^06240004.0152511 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007496 | 425849440-58870-DETAIL-02_23_2026-GO95HV-1^06239002.0021502 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007497 | 425986761-97020-DETAIL-03_30_2026-SVCDEFLC-1^06240004.0270400 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007498 | 42600111-26743-DTLSB-06_02_2026-GO95HV-1^07216001.0115602 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007499 | 426157661-4550-DRONE_HY-06_19_2026-INSULBRK-1^06238004.0271400 | INSULATOR AND BUSHING | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007500 | 426319890-8558-DETAIL-08_14_2025-GO95HV-1^06247006.0253003 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007501 | 426403738-68079-DETAIL-06_17_2025-GO95HV-1^06248004.0299107 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007502 | 426440361-81180-DTLSB-06_04_2026-SVCNEUT-1^07216001.0020905 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007503 | 42676185-20549-DTLSB-07_09_2025-GO95HV-1^06244006.0346540 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007504 | 426764236-9749-DTLSB-08_18_2025-GO95HV-1^07218001.0355800 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007505 | 426912349-9373-DETAIL-09_22_2025-GO95HV-1^06248007.0242400 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007506 | 427016578-16929-DTLSB-05_05_2026-GO95HV-1^06142013.0163300 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007507 | 427022921-74209-DETAIL-07_31_2025-GO95HV-1^06247006.0204403 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007508 | 427022921-74209-DETAIL-07_31_2025-GO95MLD-1^06247006.0204403 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007509 | 427130178-36440-DETAIL-03_05_2026-COVCOTHR-1^06238004.0145900 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007510 | 427130178-36440-DETAIL-03_05_2026-CUSTWIRE-1^06238004.0145900 | OTHER | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007511 | 427188172-43080-DETAIL-02_25_2025-GO95HV-1^06240005.0016103 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007512 | 427295820-78079-DETAIL-03_05_2024-CONDFRAY-1^06147004.0020203 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007513 | 427340574-68689-DETAIL-06_30_2025-GO95HV-1^06244007.0034102 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007514 | 427496963-40699-DETAIL-06_03_2025-GO95HV-1^06245007.0367840 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007515 | 427496963-40699-DETAIL-06_03_2025-GO95MLD-1^06245007.0367840 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007516 | 427794962-51539-DTLTRT-06_30_2025-BIRDDMG-1^668087/00 9/014 | POLE | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007517 | 427978438-69980-DTLSB-04_28_2026-GO95HV-1^06142013.0214400 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007518 | 428079818-3080-DETAIL-08_19_2025-GO95HV-1^06246002.0260200 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007519 | 428106106-40059-DETAIL-08_06_2025-GO95HV-1^06247005.0263500 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007520 | 428220224-31790-DETAIL-02_25_2026-GO95HV-1^06239003.0245901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007521 | 428497579-55613-DETAIL-08_26_2025-GO95HV-1^06247006.0331901 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007522 | 428642511-53511-DETAIL-09_18_2025-GO95HV-1^07218001.0086801 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007523 | 429276144-47479-DETAIL-09_11_2025-GO95HV-1^06248007.0232500 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007524 | 429441901-12233-DETAIL-05_12_2025-GO95HV-1^06243006.0214401 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007525 | 429641748-98961-DTLTRT-05_04_2026-GO95HV-1^668004/00 4/021 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007526 | 430371168-83580-DETAIL-03_28_2024-CUSTWIRE-1^06147005.0095001 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007527 | 430594026-11153-DTLSB-06_16_2026-GO95HV-1^07217001.0357201 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007528 | 430600658-45899-DTLSB-04_01_2026-GRDRODHI-1^06241009.0326900 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007529 | 430654364-78000-DETAIL-03_20_2025-GO95HV-1^06240003.0367009 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007530 | 43097122-33940-DTLTRT-04_28_2026-GO95HV-1^668004/00 9/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007531 | 43097122-82062-DTLTRT-04_28_2026-GO95HV-1^668004/00 9/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007532 | 430986973-64483-DETAIL-07_31_2025-GO95HV-1^06247006.0206840 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007533 | 431196145-10180-DTLSB-06_05_2026-GO95HV-1^07216001.0230802 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007534 | 431200546-20180-DETAIL-08_11_2025-GO95CL10-1^06246002.0090000 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007535 | 431220401-93180-DETAIL-03_04_2026-GO95HV-1^06239003.0189401 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007536 | 431305849-96713-DETAIL-08_26_2025-GO95HV-1^06247006.0330901 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007537 | 431697541-76909-DETAIL-09_04_2025-GO95HV-1^06247006.0211700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007538 | 431705661-53380-DTLTRT-05_18_2026-GO95HV-1^668086/00 1/007 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007539 | 431731674-81480-DTLTRT-05_13_2026-GO95MLD-1^668085/00 4/004 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007540 | 431859013-71113-DETAIL-09_11_2025-BIRDDMG-1^06248007.0226940 | POLE | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007541 | 432074163-34980-DETAIL-02_24_2026-GO95HV-1^06239002.0070500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007542 | 432077838-65069-DETAIL-09_17_2025-GO95HV-1^06248007.0366100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007543 | 432229108-1459-DETAIL-06_17_2025-SVCTREE-1^06248004.0355100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007544 | 432375449-16449-DETAIL-10_15_2025-GO95MLD-1^06247012.0310400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007545 | 432422467-60039-DETAIL-04_27_2026-GO95HV-1^06142012.0144500 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007546 | 432563984-20319-DETAIL-01_29_2026-GO95BLTC-1^06242009.0054501 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007547 | 433143543-67559-ADMIN-08_15_2025-POLEREPL-1^06247005.0299900 | POLE | Non-HFTD | Distribution | 2025-08-15 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007548 | 433192423-73679-DTLSB-05_11_2026-GO95HV-1^06242009.0278200 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007549 | 433361165-47589-DETAIL-10_06_2025-GO95CL10-1^06148001.0187000 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007550 | 433567268-37609-DETAIL-09_08_2025-GO95HV-1^06246006.0082901 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007551 | 434243536-32189-DTLSB-07_15_2025-GO95HV-1^06244006.0270901 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007552 | 434323442-84309-DETAIL-06_04_2025-GO95HV-1^06245006.0193101 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007553 | 434512505-5440-DETAIL-03_09_2026-SVCDEFLC-1^06240004.0152701 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007554 | 434744629-46021-DETAIL-04_08_2025-GO95HV-1^06241005.0092401 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007555 | 435165450-39190-DETAIL-06_04_2025-GO95BLTC-1^06142012.0107601 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007556 | 435165450-39190-DETAIL-06_04_2025-GO95MLD-1^06142012.0107601 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007557 | 435238601-89601-DETAIL-05_29_2025-GO95HV-1^06142012.0154801 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007558 | 435249654-66471-DETAIL-03_31_2025-GUYHINS-1^06241005.0114600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007559 | 435249654-66471-DETAIL-03_31_2025-GUYHINS-2^06241005.0114600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007560 | 435429493-79550-DETAIL-01_23_2025-GUYHINS-1^06239004.0256909 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007561 | 435811834-24339-DTLTRT-05_21_2026-GUYHINS-1^668086/00 20/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007562 | 436438289-84569-DETAIL-09_16_2025-GO95HV-1^06246006.0016200 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007563 | 436442392-36389-ADMIN-10_23_2025-GO95HV-1^06246001.0023000 | OTHER | Non-HFTD | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007564 | 436526712-56779-ADMIN-05_14_2026-POLETOP-1^06248004.0310701 | POLE | HFTD Tier 2 | Distribution | 2026-05-14 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007565 | 436688424-66339-DETAIL-10_06_2025-GO95HV-1^06243007.0367701 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007566 | 437050305-12305-DETAIL-07_24_2025-GO95HV-1^06247005.0139303 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007567 | 437494373-51690-DTLSB-06_03_2026-GO95HV-1^07216001.0025300 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007568 | 437528496-68500-DETAIL-02_10_2026-GO95HV-1^06239003.0015504 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007569 | 437579528-83149-AUDIT-09_09_2025-GO95TCH-1^07216001.0162603 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007570 | 437787109-39073-ADMIN-03_06_2026-POLEREPL-1^06247005.0207900 | POLE | Non-HFTD | Distribution | 2026-03-06 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007571 | 437815519-13029-DTLSB-08_14_2023-CUSTWIRE-1^06243009.0246102 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007572 | 437836708-24190-DETAIL-01_12_2026-COVCOTHR-2^06239004.0244414 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007573 | 437836708-24190-DETAIL-01_12_2026-COVCOTHR-3^06239004.0244414 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007574 | 437864686-32659-DETAIL-04_30_2026-GO95HV-1^668004/00 6/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007575 | 437929824-55129-DETAIL-04_19_2022-CUSTWIRE-1^06142012.0132815 | OTHER | Non-HFTD | Distribution | 2022-04-19 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007576 | 437995226-4789-ADMIN-10_22_2025-GO95BLTC-1^06246011.0056701 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007577 | 437995226-4789-ADMIN-10_22_2025-SVCENTCO-1^06246011.0056701 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007578 | 438584243-68290-DETAIL-02_24_2026-BIRDDMG-1^06239002.0273901 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007579 | 438584243-68290-DETAIL-02_24_2026-GO95HV-1^06239002.0273901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007580 | 438811604-72959-DTLTRT-04_22_2026-GO95HV-1^668004/02 5/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007581 | 438867863-89990-DETAIL-09_10_2025-GO95HV-1^06147001.0189501 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007582 | 438905124-7090-DETAIL-02_16_2023-CUSTWIRE-1^06247002.0219600 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007583 | 438950773-33159-DETAIL-08_19_2025-GO95HV-1^06247006.0366504 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007584 | 43927043-71559-DTLTRT-04_20_2026-GO95HV-1^668004/02 3/004 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007585 | 439553490-56752-AUDIT-09_22_2025-GO95TCH-1^06241005.0028342 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007586 | 439670278-11979-DETAIL-02_02_2022-CUSTWIRE-1^06147005.0261400 | OTHER | Non-HFTD | Distribution | 2022-02-02 | 2025-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007587 | 439683956-55956-DETAIL-03_27_2024-CUSTWIRE-1^06247005.0330101 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007588 | 439733809-46590-DETAIL-08_18_2025-XARMSPCR-1^06246002.0345801 | CROSSARM | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007589 | 44016714-14222-DETAIL-10_16_2025-GO95BLTC-1^06246011.0185601 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007590 | 440301885-52029-DETAIL-04_17_2025-GO95HV-1^06242006.0089600 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007591 | 440633496-35481-DETAIL-04_24_2025-GUYHINS-1^06241006.0115702 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-24 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007592 | 440666589-78973-DETAIL-08_21_2025-GO95HV-1^07216001.0177707 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007593 | 440711263-46249-DTLSB-07_16_2025-GO95HV-1^06244006.0252901 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007594 | 440833506-87959-AUDIT-09_09_2025-GO95MLD-1^07218001.0355702 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007595 | 440833506-87959-AUDIT-09_09_2025-GO95STUB-1^07218001.0355702 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007596 | 440880412-96312-DTLSB-07_16_2025-GO95BLTC-1^06244006.0242000 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007597 | 441268593-98289-DTLSB-01_22_2026-SVCROAD-1^06242009.0297201 | OTHER | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007598 | 441561129-85990-ADMIN-04_11_2024-CUTOUTAR-1^06245002.0102201 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007599 | 441728951-56132-DTLTRT-05_12_2026-GO95HV-1^668004/00 3/010 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007600 | 44192453-50340-DTLTRT-05_29_2025-DISTHDWR-1^668075/00 8/008 | CONNECTION DEVICE | Non-HFTD | Transmission | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007601 | 442067966-19300-DETAIL-04_08_2026-GO95HV-1^06240002.0315300 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007602 | 442073070-24270-DETAIL-02_25_2026-GO95HV-1^06238003.0019801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007603 | 442524821-16589-DETAIL-05_01_2025-GRDRODHI-1^06243006.0274000 | OTHER | Non-HFTD | Distribution | 2025-05-01 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007604 | 442927254-4959-DTLTRT-04_22_2026-GO95HV-1^668004/02 7/010 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007605 | 442927254-4959-DTLTRT-04_22_2026-GUYHINS-2^668004/02 7/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007606 | 442994929-66629-DTLSB-02_04_2026-BIRDDMG-1^06243009.0322401 | POLE | HFTD Tier 2 | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007607 | 443143113-49499-DETAIL-10_05_2021-CUSTWIRE-2^06147005.0070300 | OTHER | Non-HFTD | Distribution | 2021-10-05 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007608 | 443273202-36253-DETAIL-07_22_2025-CONDCOIL-1^06247005.0175200 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007609 | 443289285-61940-AUDIT-05_07_2026-GO95CLSV-1^06240004.0150541 | OTHER | HFTD Tier 2 | Distribution | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007610 | 443404073-54133-DETAIL-06_02_2025-GO95HV-1^06245007.0366840 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007611 | 44342858-53858-DETAIL-10_07_2025-GO95HV-1^06246008.0056500 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007612 | 443886336-13879-DETAIL-05_28_2025-GO95HV-1^06244006.0040100 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007613 | 443916288-53801-ADMIN-11_12_2025-GO95MLD-1^06246001.0336700 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007614 | 443989478-2642-DETAIL-04_30_2025-GO95MLD-1^06242006.0107240 | OTHER | Non-HFTD | Distribution | 2025-04-30 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007615 | 443989478-2642-DETAIL-04_30_2025-GUYHINS-1^06242006.0107240 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-04-30 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007616 | 444376673-96009-DETAIL-08_12_2025-GRDRODHI-1^06247006.0251200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007617 | 444376673-96009-DETAIL-08_12_2025-GRDRODHI-2^06247006.0251200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007618 | 444475501-38501-DTLSB-07_17_2025-GO95HV-1^06244006.0216500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007619 | 444754902-97902-DETAIL-04_02_2025-GO95MLD-1^06241005.0118601 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007620 | 444844010-54799-DETAIL-08_05_2025-GO95BLTC-1^06247005.0208200 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007621 | 445391939-92390-DETAIL-01_16_2025-GO95TCH-1^06239004.0257208 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007622 | 445444269-17301-DTLTRT-06_25_2025-ABNDEQPM-1^668087/00 2A/008 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007623 | 445585120-31549-DETAIL-09_04_2025-GO95HV-1^07216001.0098302 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007624 | 445665331-16459-DTLSB-05_28_2026-GO95HV-1^07216001.0022401 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007625 | 445670743-63350-DETAIL-01_14_2026-GO95MLD-1^06239004.0134040 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007626 | 446075891-76701-DETAIL-09_10_2025-DISTHDWR-1^06147001.0074000 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007627 | 446464202-83039-DETAIL-05_18_2026-SVCDEFLC-1^668086/00 12/011 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007628 | 446464339-33029-DTLSB-05_13_2026-BIRDDMG-1^06242009.0280000 | POLE | Non-HFTD | Distribution | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007629 | 446518284-47330-DETAIL-02_26_2025-GO95MLD-1^06241005.0367902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007630 | 446853905-61689-DETAIL-06_11_2024-CUSTWIRE-1^06245007.0346500 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007631 | 446945216-71499-DETAIL-07_29_2025-GO95BLTC-1^06247005.0316901 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007632 | 446945216-71499-DETAIL-07_29_2025-GRDRODHI-1^06247005.0316901 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007633 | 447047059-97549-DTLSB-07_01_2025-GO95HV-1^06244007.0134400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007634 | 447272931-13680-DETAIL-02_16_2026-GO95HV-1^06239001.0035902 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007635 | 447301459-27989-DTLSB-05_12_2026-GRDRODHI-2^06242009.0289502 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007636 | 447596673-65359-DTLTRT-04_20_2026-GO95HV-1^668004/02 17/001 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007637 | 447661875-11979-DTLSB-07_15_2025-GO95HV-1^06244006.0343300 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007638 | 44791589-14940-DETAIL-09_05_2025-ANCPUCO-1^06147001.0290000 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-05 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007639 | 44791589-14940-DETAIL-09_05_2025-GO95TCH-1^06147001.0290000 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007640 | 447925760-89589-DETAIL-08_05_2025-GO95HV-1^06246001.0060401 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007641 | 448230858-82749-DTLSB-07_21_2025-GO95HV-1^06244006.0304500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007642 | 448345160-77949-DETAIL-06_29_2026-GO95HV-1^07217001.0154404 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007643 | 448383906-40101-DTLSB-04_30_2026-GO95HV-1^06142013.0172501 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007644 | 448480791-19770-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 1/002 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007645 | 448849441-91850-DETAIL-03_04_2026-BIRDDMG-1^06239003.0186701 | POLE | HFTD Tier 3 | Distribution | 2026-03-04 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007646 | 448936661-199-DETAIL-03_15_2022-CUSTWIRE-1^06148006.0271000 | OTHER | Non-HFTD | Distribution | 2022-03-15 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007647 | 449124302-91799-ADMIN-10_27_2025-GRDRODHI-1^06246001.0016701 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007648 | 449226725-76725-DETAIL-02_17_2025-GO95TCH-1^06241005.0229102 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007649 | 449278270-53598-DETAIL-06_10_2026-CLRTOUCH-1^668086/00 11/014 | CONDUCTOR | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007650 | 449795833-84669-DTLTRT-06_23_2021-GO95MLD-1^668041/00 5/032 | OTHER | Non-HFTD | Transmission | 2021-06-23 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007651 | 450479401-26030-DETAIL-03_26_2026-COVCOTHR-1^06240004.0209500 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007652 | 450513546-23039-DTLTRT-05_21_2026-WASHOUT-1^668086/00 3/015 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007653 | 450617073-54590-DETAIL-02_24_2026-GO95HV-1^06239002.0275200 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007654 | 450926539-60449-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0149100 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007655 | 451488184-83711-DETAIL-09_11_2025-GO95HV-1^06147001.0297000 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007656 | 451576193-1280-DETAIL-02_11_2025-GO95MLD-1^06240004.0356001 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007657 | 451600999-11699-ADMIN-10_07_2025-COVCOTHR-1^06245010.0179800 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007658 | 451724754-36754-DETAIL-03_29_2023-CUSTWIRE-1^06142016.0085801 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007659 | 452078665-23263-DETAIL-06_23_2026-CUSTWIRE-1^07217001.0106200 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007660 | 452078665-23263-DETAIL-06_23_2026-GO95HV-1^07217001.0106200 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007661 | 45216631-46259-DTLSB-07_08_2025-GO95HV-1^06245007.0353201 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007662 | 452193463-12211-DETAIL-10_06_2025-GO95HV-1^06148001.0310704 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007663 | 45253180-34970-DETAIL-02_25_2026-BIRDDMG-1^06238003.0017903 | POLE | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007664 | 452829004-68611-DETAIL-09_08_2025-GO95HV-1^06147001.0329600 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007665 | 453078146-80389-DETAIL-09_08_2025-GO95HV-1^06247007.0138800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007666 | 453078146-80389-DETAIL-09_08_2025-SVCROAD-1^06247007.0138800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007667 | 453279113-79909-AUDIT-09_02_2025-XARMSPCR-1^06247006.0256100 | CROSSARM | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007668 | 453279113-79909-DETAIL-08_14_2025-GO95HV-1^06247006.0256100 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007669 | 453279551-30699-DTLSB-03_10_2026-GRDRODHI-1^06243009.0349102 | OTHER | Non-HFTD | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007670 | 453618141-62539-DTLSB-05_28_2026-GO95HV-1^07216001.0022400 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007671 | 453618141-62539-DTLSB-05_28_2026-SVCENTCO-1^07216001.0022400 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007672 | 453686143-17143-ADMIN-10_21_2025-GUYHINS-1^06246012.0056901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007673 | 454005108-78528-DETAIL-09_27_2021-CUSTWIRE-1^06148004.0356321 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007674 | 454212829-99159-DETAIL-08_28_2025-SVCNEUT-1^07216001.0163801 | OTHER | Non-HFTD | Distribution | 2025-08-28 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007675 | 454230063-18329-DETAIL-04_27_2022-CUSTWIRE-1^06143012.0255702 | OTHER | Non-HFTD | Distribution | 2022-04-27 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007676 | 454351810-36361-DETAIL-04_15_2025-ABNDEQPM-1^06242005.0334903 | OTHER | HFTD Tier 2 | Distribution | 2025-04-15 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007677 | 454353018-91039-DTLSB-08_12_2025-GO95HV-1^07217001.0024204 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007678 | 45436659-38340-ADMIN-04_24_2024-ABNDEQPM-1^06145001.0057000 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007679 | 454573183-99939-DETAIL-06_10_2026-RISEBKSP-1^668086/00 17/012 | OTHER | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007680 | 454658695-25102-DETAIL-04_22_2025-GO95HV-1^06242006.0089301 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007681 | 454905776-1573-DTLSB-06_17_2026-SVCDEFLC-1^07217001.0276005 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007682 | 454905776-1573-DTLSB-06_17_2026-SVCNEUT-1^07217001.0276005 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007683 | 455218428-73711-DTLSB-05_15_2024-GO95HV-1^06244002.0226600 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007684 | 45535946-95440-DTLSB-05_29_2026-GO95HV-1^07216001.0114700 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007685 | 455452095-46489-DETAIL-09_09_2025-GO95HV-1^06246007.0169150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007686 | 455550172-20880-DETAIL-02_06_2025-GUYNOINS-1^06240004.0166310 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007687 | 455872353-73729-DETAIL-05_13_2025-GO95HV-1^06142012.0015505 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007688 | 455910451-81699-DETAIL-10_02_2025-GO95BLTC-1^06246008.0066400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007689 | 455933704-64321-DETAIL-09_08_2025-GO95HV-1^06147001.0329700 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007690 | 455966364-53589-DETAIL-05_20_2025-SVCENTBK-1^06243006.0091300 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007691 | 456093161-87230-DETAIL-03_26_2026-COVCOTHR-1^06240004.0205402 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007692 | 456201732-17383-DETAIL-07_30_2025-GO95HV-1^06247005.0237001 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007693 | 456230838-5889-DETAIL-10_09_2025-GO95HV-1^06148001.0151301 | OTHER | Non-HFTD | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007694 | 456261106-91106-DETAIL-01_29_2025-GO95MLD-1^06239004.0252601 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007695 | 456346336-84359-DTLTRT-05_07_2026-GO95MLD-1^668004/00 1/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007696 | 456521678-42689-DETAIL-04_23_2025-GO95HV-1^06242006.0039001 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007697 | 456617763-12040-AUDIT-06_09_2025-GO95TCH-1^668075/00 3/012 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007698 | 456617763-12040-DTLTRT-06_02_2025-GUYHINS-1^668075/00 3/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007699 | 456632136-80449-DETAIL-10_10_2024-SVCROOF-1^07216001.0201204 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007700 | 456954831-86809-DETAIL-03_11_2024-CONDFRAY-2^06147004.0037600 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007701 | 457349472-8989-DETAIL-07_24_2025-GO95BLTC-1^06247005.0179804 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007702 | 457349472-8989-DETAIL-07_24_2025-GO95HV-1^06247005.0179804 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007703 | 457361238-73621-DETAIL-08_07_2025-GO95HV-1^06246002.0250901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007704 | 457510128-6150-DETAIL-04_22_2025-GO95HV-1^06240003.0081702 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007705 | 45751469-58540-DETAIL-10_01_2025-GO95HV-1^06148001.0301100 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007706 | 45756048-24470-DETAIL-03_24_2026-COVCOTHR-1^06240004.0220709 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007707 | 45781490-97490-DETAIL-05_28_2025-GO95BLTC-1^06244006.0095500 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007708 | 45781490-97490-DETAIL-05_28_2025-GO95HV-1^06244006.0095500 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007709 | 457924991-14939-DETAIL-06_12_2024-CUSTWIRE-1^06244005.0249641 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007710 | 458076135-54789-DETAIL-09_02_2025-SVCNEUT-1^06246001.0171002 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007711 | 458119523-69523-DETAIL-06_04_2025-GO95HV-1^668075/00 12/024 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007712 | 458140691-29221-DETAIL-09_10_2025-GO95HV-1^06147001.0077900 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007713 | 45834262-44149-DTLSB-07_16_2025-GO95HV-1^06244006.0231402 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007714 | 458477539-48521-DETAIL-06_25_2025-GUYHINS-1^668087/00 16/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007715 | 458787028-34079-DETAIL-06_16_2025-GO95HV-1^06248004.0361142 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007716 | 458866058-54821-DETAIL-07_02_2026-GO95HV-1^07217001.0222603 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007717 | 459022634-80760-DETAIL-01_23_2025-GO95BLTC-1^06239004.0257706 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007718 | 459093280-49243-DETAIL-07_01_2026-GO95HV-1^07217001.0169301 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007719 | 459178445-40545-DETAIL-09_15_2025-GO95MLD-1^07219001.0323402 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007720 | 459245643-58149-DETAIL-06_02_2025-GO95HV-1^06244006.0142100 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007721 | 459356248-80440-DETAIL-03_12_2025-ABNDEQPM-1^06238004.0222402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007722 | 459722274-72430-DETAIL-01_28_2025-GO95MLD-1^06240004.0086042 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007723 | 45988531-83899-DTLSB-01_26_2026-GO95MLD-1^06242009.0298600 | OTHER | Non-HFTD | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007724 | 460147531-46239-DTLTRT-07_08_2025-BIRDDMG-1^668087/00 2/026 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007725 | 460207664-6810-DRONE_HY-06_30_2026-DISTHDWR-1^06238004.0153000 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007726 | 460217928-25959-DTLSB-08_14_2025-GO95HV-1^07218001.0351201 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007727 | 460721844-48419-DETAIL-06_27_2022-CUSTWIRE-1^07116007.0155601 | OTHER | HFTD Tier 2 | Distribution | 2022-06-27 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007728 | 460854418-91449-DTLSB-07_09_2025-GO95HV-1^06244006.0276501 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007729 | 460983648-10690-DRONE_HY-07_02_2026-GO95STUB-1^06239004.0361001 | OTHER | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007730 | 461019866-68770-DETAIL-01_23_2025-GO95HV-1^06239004.0256642 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007731 | 46133134-48459-DETAIL-08_27_2025-GO95HV-1^07216001.0164304 | OTHER | Non-HFTD | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007732 | 461366391-18391-DETAIL-09_24_2025-GO95HV-1^07218001.0221400 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007733 | 461471540-61799-DETAIL-10_07_2025-GO95BLTC-1^06246008.0041400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007734 | 461578078-65525-DETAIL-09_22_2025-GO95HV-1^07218001.0221900 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007735 | 4617463-58580-DETAIL-02_17_2026-GO95HV-1^06239002.0059301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007736 | 462041635-54299-DETAIL-07_31_2025-RISEGRD-1^06247006.0209300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007737 | 462041635-54299-DETAIL-07_31_2025-RISEGRD-2^06247006.0209300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007738 | 462041635-54299-DETAIL-07_31_2025-RISEGRD-3^06247006.0209300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007739 | 462140580-48270-DETAIL-02_25_2026-GO95HV-1^06238002.0070901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007740 | 46231701-20699-DETAIL-05_22_2025-GO95HV-1^06244006.0070401 | OTHER | HFTD Tier 2 | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007741 | 462629186-16450-DETAIL-09_15_2025-GO95HV-1^07219001.0334400 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007742 | 462695933-46933-DETAIL-06_09_2025-GO95MLD-1^668075/00 4/029 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007743 | 463129819-14670-DETAIL-04_02_2026-SVCDEFLC-1^06236005.0169001 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007744 | 463189760-6489-DETAIL-07_30_2025-BIRDDMG-1^06247006.0204300 | POLE | HFTD Tier 2 | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007745 | 463673198-10431-DETAIL-06_23_2025-GO95HV-1^668087/00 1/003 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007746 | 46390553-65940-DTLTRT-05_22_2024-GO95HV-1^06243001.0103700 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007747 | 464106224-48739-DETAIL-06_02_2025-GO95HV-1^06244006.0155900 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007748 | 464263311-32150-DETAIL-02_26_2026-COVCOTHR-1^06238004.0025801 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007749 | 464732963-51850-DETAIL-01_23_2025-GO95BLTC-1^06239004.0257703 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007750 | 465060165-54409-DETAIL-08_21_2025-GO95HV-1^06247006.0268901 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007751 | 465093404-99029-DETAIL-04_22_2026-GO95HV-1^06142012.0149605 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007752 | 465221811-73580-DETAIL-02_23_2026-GO95HV-1^06239002.0035401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007753 | 465244311-38431-DTLTRT-05_18_2026-GO95HV-1^668086/00 6/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007754 | 465685386-72449-DTLSB-07_09_2025-ENCHRW-1^06244006.0277400 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007755 | 465956314-88153-DETAIL-09_23_2025-GO95HV-1^07218001.0224602 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007756 | 466757351-45850-DETAIL-04_15_2026-GO95HV-1^06237005.0362500 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007757 | 466762298-54199-DTLSB-04_09_2026-BIRDDMG-1^06241007.0283901 | POLE | HFTD Tier 2 | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007758 | 466763046-84860-DTLTRT-05_04_2026-GO95MLD-1^668004/00 10/019 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007759 | 466763046-84860-DTLTRT-05_04_2026-GO95MLD-2^668004/00 10/019 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007760 | 46684844-49409-DETAIL-09_03_2025-GO95HV-1^06247006.0174001 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007761 | 46714394-78460-DRONE_HY-07_15_2026-COVCOTHR-1^06239004.0256702 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007762 | 46714394-78460-DRONE_HY-07_15_2026-COVCOTHR-3^06239004.0256702 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007763 | 467341788-83218-DETAIL-08_25_2025-GO95HV-1^06247006.0282600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007764 | 468450320-20469-DTLSB-07_01_2025-GRDRODHI-1^06244007.0133401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007765 | 468561549-15631-DETAIL-08_11_2025-GO95HV-1^06246002.0263900 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007766 | 46884974-43170-DETAIL-01_27_2026-XARMSPCR-1^06239002.0062308 | CROSSARM | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007767 | 468995618-17209-DETAIL-08_06_2025-GO95HV-1^06247005.0262600 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007768 | 470008269-89733-DETAIL-09_09_2025-GRDRODHI-1^07218001.0177202 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007769 | 470009861-83862-DTLSB-07_09_2025-GO95HV-1^06244007.0157700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007770 | 470215448-24531-ADMIN-11_12_2025-GRDRODHI-1^06246001.0342300 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007771 | 47052694-30390-DETAIL-03_27_2025-GO95HV-1^06239003.0019704 | OTHER | Non-HFTD | Distribution | 2025-03-27 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007772 | 470835171-14380-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0168044 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007773 | 47118118-31459-DETAIL-06_17_2025-GO95HV-1^06248004.0355001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007774 | 471990226-60570-DETAIL-01_30_2025-GO95HV-1^06239004.0245802 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007775 | 472355898-69989-DETAIL-08_14_2025-GO95HV-1^06246002.0264700 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007776 | 47252104-89759-DTLTRT-04_21_2026-GO95HV-1^668004/02 9/008 | OTHER | Non-HFTD | Transmission | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007777 | 472653794-60894-DETAIL-03_30_2023-ABNDEQPM-1^06142016.0084909 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2028-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007778 | 472729761-17741-DETAIL-09_10_2025-GO95HV-1^06147001.0072000 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007779 | 472776843-38241-DETAIL-03_03_2025-GUYHINS-1^06241004.0182200 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-03 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007780 | 472914575-92900-DETAIL-04_08_2026-GUYHINS-1^06240002.0315301 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-08 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007781 | 472966275-66409-DETAIL-08_21_2025-GO95HV-1^06247006.0250800 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007782 | 472973432-489-ADMIN-04_08_2026-ABNDEQPM-1^06241009.0107402 | OTHER | Non-HFTD | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007783 | 472977661-32950-DETAIL-04_15_2026-GO95HV-1^06237005.0362501 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007784 | 473193651-33329-DETAIL-04_23_2026-GO95HV-1^06142012.0144404 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007785 | 47330721-38120-DETAIL-03_11_2026-GO95TCH-1^06240004.0271700 | OTHER | HFTD Tier 3 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007786 | 473558239-48341-DETAIL-08_19_2025-GO95HV-1^06246002.0369400 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007787 | 473704771-73920-DETAIL-03_11_2026-SVCDEFLC-1^06240004.0270801 | OTHER | HFTD Tier 3 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007788 | 47381895-92319-DETAIL-01_29_2026-GO95BLTC-1^06242009.0050504 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007789 | 474024380-17349-DTLSB-07_17_2025-GRDRODHI-1^06244007.0099301 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007790 | 47426518-65360-DETAIL-10_21_2024-BIRDDMG-1^668014/00 6/053 | POLE | HFTD Tier 3 | Transmission | 2024-10-21 | 2029-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007791 | 474315067-8590-DETAIL-01_12_2026-SVCTREE-1^06239004.0244841 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007792 | 474471051-73741-DETAIL-09_11_2025-GO95HV-1^06147001.0081701 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007793 | 474691385-46989-DETAIL-08_13_2025-GO95HV-1^06247006.0262500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007794 | 474859866-70150-AUDIT-05_06_2026-SVCENTBK-1^06236005.0110401 | OTHER | HFTD Tier 2 | Distribution | 2026-05-06 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007795 | 475196638-87509-DTLSB-09_29_2022-CUSTWIRE-1^06243005.0088302 | OTHER | Non-HFTD | Distribution | 2022-09-29 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007796 | 475553195-74195-DETAIL-05_05_2025-GO95HV-1^06243006.0288203 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007797 | 475673214-67859-DTLTRT-04_22_2026-GO95HV-1^668004/02 10/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007798 | 475673214-67859-DTLTRT-04_22_2026-GO95MLD-1^668004/02 10/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007799 | 475712278-83819-DTLSB-04_09_2026-GO95MLD-1^06241007.0307701 | OTHER | Non-HFTD | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007800 | 476130968-48291-DTLTRT-05_05_2026-BIRDDMG-1^668038/00 2/063 | POLE | HFTD Tier 2 | Transmission | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007801 | 476130968-48291-DTLTRT-05_05_2026-GO95HV-1^668038/00 2/063 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007802 | 476131988-88590-DETAIL-01_16_2025-GO95HV-1^06239004.0257304 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007803 | 47618038-72832-DETAIL-04_21_2025-GO95HV-1^06242006.0034602 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007804 | 476228111-24909-DETAIL-09_08_2025-GO95HV-1^06247006.0212501 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007805 | 476414381-81369-DTLSB-07_14_2025-GO95BLTC-1^06244007.0156700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007806 | 476700226-38029-DETAIL-04_22_2025-GO95HV-1^06242006.0066000 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007807 | 477034445-81863-DETAIL-05_26_2026-GO95HV-1^07217001.0143105 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007808 | 477216882-93070-DETAIL-03_10_2026-COVCOTHR-1^06238004.0125802 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007809 | 477287105-29548-DETAIL-06_05_2025-GO95HV-1^06148014.0242400 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007810 | 477303211-32499-DETAIL-09_23_2025-GO95BLTC-1^06246006.0012300 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007811 | 477303211-32499-DETAIL-09_23_2025-GO95HV-1^06246006.0012300 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007812 | 477324764-16910-DETAIL-03_13_2025-GO95HV-1^06238004.0155001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007813 | 477341804-6653-DETAIL-05_27_2026-GO95MLD-1^07217001.0149700 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007814 | 477544855-90790-ADMIN-10_10_2017-CUSTWIRE-1^668033/00 10A/024 | OTHER | HFTD Tier 2 | Transmission | 2017-10-10 | 2020-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007815 | 477829791-61731-DETAIL-02_27_2025-GO95MLD-1^06241005.0176601 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007816 | 477925279-12879-DETAIL-09_30_2025-GO95HV-1^06148001.0300203 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007817 | 477925279-12879-DETAIL-09_30_2025-GO95MLD-1^06148001.0300203 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007818 | 478080814-59140-AUDIT-05_07_2026-SVCDEFLC-1^06240004.0218941 | OTHER | HFTD Tier 2 | Distribution | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007819 | 478136715-98715-DETAIL-01_13_2026-CUSTWIRE-1^06239004.0243801 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007820 | 478252645-64199-DTLSB-07_09_2025-GO95HV-1^06244006.0346401 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007821 | 478363316-86441-DETAIL-09_03_2025-GO95TCH-1^06246001.0176203 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007822 | 478830188-77841-DETAIL-08_19_2025-GO95HV-1^06246002.0260100 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007823 | 478953249-67240-DETAIL-04_15_2026-GO95HV-1^06237004.0058202 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007824 | 479253870-91159-DETAIL-03_16_2026-SVCTREE-1^06240004.0151413 | OTHER | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007825 | 479640234-46609-DETAIL-08_27_2025-GO95HV-1^06247006.0174700 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007826 | 479805194-689-DETAIL-08_13_2025-CUTOUTAR-1^06247006.0253100 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007827 | 479814795-7700-DETAIL-03_02_2026-GO95MLD-1^06239003.0242801 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007828 | 480232915-78629-DETAIL-04_26_2022-CUSTWIRE-1^06143012.0239300 | OTHER | Non-HFTD | Distribution | 2022-04-26 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007829 | 480255051-38051-DTLTRT-05_20_2026-CUSTWIRE-1^668086/00 6/011 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007830 | 480279130-25559-DETAIL-09_18_2025-GO95HV-1^06246006.0013701 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007831 | 480338876-13760-DTLTRT-04_30_2026-GO95HV-1^668004/00 7/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007832 | 48046799-87499-DETAIL-06_03_2024-CUSTWIRE-1^06246006.0358001 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007833 | 480597989-1299-DETAIL-09_22_2025-GO95HV-1^06248007.0242300 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007834 | 480668809-46389-DTLSB-06_30_2025-GO95HV-1^06244006.0221400 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007835 | 480741445-67551-DTLTRT-06_26_2025-GO95HV-1^668087/00 7/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007836 | 480821863-1852-DETAIL-06_20_2023-CUSTWIRE-1^06244010.0252301 | OTHER | HFTD Tier 2 | Distribution | 2023-06-20 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007837 | 481012290-73389-DETAIL-03_05_2024-CUSTWIRE-1^06147004.0020301 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007838 | 481035435-6929-DETAIL-06_05_2025-GO95HV-1^06148014.0243400 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007839 | 481075519-46430-DETAIL-03_17_2026-GO95HV-1^06240004.0150143 | OTHER | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007840 | 481260040-66951-DETAIL-10_06_2025-GO95HV-1^06148001.0310600 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007841 | 481442191-32780-DRONE_HY-06_30_2026-COVCOTHR-1^06240004.0167241 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007842 | 481800723-62839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0260400 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007843 | 482209181-65751-DETAIL-10_06_2025-CUSTWIRE-1^06148001.0311702 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007844 | 48235343-98149-DETAIL-06_02_2025-GO95HV-1^06244006.0142101 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007845 | 482465096-95944-DETAIL-06_02_2025-GO95HV-1^06148014.0365702 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007846 | 482476655-94870-DETAIL-01_22_2025-GO95BLTC-1^06239004.0254401 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007847 | 482519794-97059-DTLSB-06_09_2026-GO95HV-1^07216001.0229401 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007848 | 482795928-91019-DTLSB-04_02_2026-GO95HV-1^06241009.0281600 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007849 | 483625054-92949-DETAIL-08_14_2024-CUSTWIRE-1^06245005.0341001 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007850 | 48374540-95349-DTLSB-06_25_2025-BIRDDMG-1^06244007.0102500 | POLE | HFTD Tier 2 | Distribution | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007851 | 48374540-95349-DTLSB-06_25_2025-GO95HV-1^06244007.0102500 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007852 | 483881031-58130-DETAIL-03_26_2026-COVCOTHR-1^06240004.0206502 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007853 | 484088988-49870-DETAIL-03_23_2026-COVCOTHR-1^06240004.0226500 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007854 | 484088988-49870-DETAIL-03_23_2026-COVCOTHR-2^06240004.0226500 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007855 | 484841728-75451-DETAIL-08_25_2025-GO95HV-1^06246001.0203301 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007856 | 485196466-44239-DETAIL-03_20_2024-CUSTWIRE-1^06244005.0142101 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007857 | 485683589-83151-DETAIL-04_11_2024-GO95MLD-1^06245002.0105401 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007858 | 485706419-44151-DETAIL-09_03_2025-GO95HV-1^06247006.0295600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007859 | 485739404-16229-DETAIL-04_28_2025-GO95HV-1^06242007.0247101 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007860 | 486078464-21851-ADMIN-10_07_2025-COVCOTHR-1^06242005.0148002 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007861 | 48611458-54479-DETAIL-10_15_2025-GO95BLTC-1^06148001.0143100 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007862 | 486135210-70451-DETAIL-04_18_2022-CUSTWIRE-1^06142012.0133700 | OTHER | Non-HFTD | Distribution | 2022-04-18 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007863 | 486187995-8849-DTLSB-07_17_2025-GO95HV-1^06244007.0111500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007864 | 486418891-44651-DETAIL-09_10_2025-GO95HV-1^06147001.0083700 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007865 | 486418891-44651-DETAIL-09_10_2025-GUYHINS-1^06147001.0083700 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007866 | 486676518-52659-DTLSB-08_12_2025-GO95HV-1^07217001.0027200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007867 | 486681426-49751-DETAIL-04_18_2024-XARMSPCR-1^06145001.0250100 | CROSSARM | Non-HFTD | Distribution | 2024-04-18 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007868 | 486945200-76369-DTLTRT-06_15_2021-GO95HV-1^668041/00 20/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007869 | 48698068-31168-DETAIL-06_21_2022-CUSTWIRE-1^07116007.0039804 | OTHER | HFTD Tier 2 | Distribution | 2022-06-21 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007870 | 487102007-97038-DETAIL-03_05_2025-GO95MLD-1^06241005.0120400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007871 | 487807488-8488-DETAIL-09_24_2025-GO95HV-1^07218001.0228100 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007872 | 48808551-30859-DETAIL-07_30_2025-GO95HV-1^06247005.0243700 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007873 | 488247543-22199-DETAIL-08_19_2025-GO95HV-1^06247006.0365701 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007874 | 488479410-22271-DETAIL-04_24_2024-CUSTWIRE-1^06145001.0041001 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007875 | 48849061-13161-DETAIL-03_30_2023-CUSTWIRE-1^06142016.0054008 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007876 | 488543221-47273-DETAIL-09_11_2025-GO95HV-1^06248007.0223101 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007877 | 488987870-38859-DETAIL-07_24_2025-GO95HV-1^06247005.0132400 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007878 | 489016889-94699-DTLSB-07_02_2025-GO95MLD-1^06244007.0136501 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007879 | 489364936-27861-DTLTRT-05_21_2026-GRDBROKE-1^668086/00 1/015 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007880 | 489470231-30961-DETAIL-09_16_2025-GUYHINS-1^06147001.0062900 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007881 | 489494043-98249-DTLSB-07_16_2025-GO95HV-1^06244006.0268902 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007882 | 489554848-55023-DTLSB-06_11_2026-GO95MLD-1^07217001.0270200 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007883 | 489657029-41659-DETAIL-08_05_2025-GO95HV-1^06247005.0206700 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007884 | 490435477-83699-DETAIL-08_04_2025-GO95HV-1^06246002.0139601 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007885 | 490524138-78718-AUDIT-07_16_2025-GO95HV-1^06244006.0226003 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007886 | 491063136-15369-DETAIL-04_28_2025-GO95HV-1^06242006.0195301 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007887 | 491214676-80261-DETAIL-08_06_2025-GO95HV-1^06246002.0106700 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007888 | 491283855-59249-DTLSB-07_10_2025-GO95HV-1^06244006.0342001 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007889 | 491330784-83361-DETAIL-04_13_2022-CUSTWIRE-1^06142012.0134703 | OTHER | Non-HFTD | Distribution | 2022-04-13 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007890 | 491406692-46560-DETAIL-04_29_2026-GO95HV-1^668004/00 5/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007891 | 49145914-92459-DETAIL-03_07_2024-SVCROAD-1^06245007.0278900 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007892 | 491815684-28661-DETAIL-09_04_2025-GO95HV-1^06147001.0319600 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007893 | 492232166-89961-DETAIL-04_20_2026-GO95HV-1^06142012.0148903 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007894 | 492508818-86650-DETAIL-04_22_2025-GO95HV-1^06240003.0055501 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007895 | 492646371-55589-DTLSB-04_21_2026-GO95MLD-1^06241009.0257300 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007896 | 492980446-48100-DETAIL-04_07_2026-GO95MLD-1^06240002.0317010 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007897 | 493345843-53329-DETAIL-05_13_2025-GO95HV-1^06142012.0015504 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007898 | 493407370-8778-DETAIL-07_02_2026-CUSTWIRE-1^07217001.0047701 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007899 | 493462578-70191-DTLTRT-05_06_2026-GO95HV-1^668038/00 6/056 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007900 | 493591694-81659-DETAIL-07_28_2025-GO95HV-1^06247005.0301302 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007901 | 493703575-5263-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0097602 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007902 | 493839838-55930-DETAIL-01_23_2025-CUSTWIRE-1^06240004.0081602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007903 | 494268159-98561-DETAIL-09_30_2025-GO95HV-1^06148001.0300004 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007904 | 494452964-84639-DTLSB-09_20_2022-CUSTWIRE-1^06243005.0112200 | OTHER | Non-HFTD | Distribution | 2022-09-20 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007905 | 49474198-41919-DETAIL-05_18_2026-GUYHINS-1^06242009.0287202 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007906 | 49478444-96150-DTLTRT-10_11_2023-BIRDDMG-1^668010/00 9/040 | POLE | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007907 | 495102910-93930-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135800 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007908 | 495192799-93749-DTLSB-07_29_2025-GO95HV-1^07218001.0264000 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007909 | 495223663-25569-DTLSB-07_22_2025-GO95HV-1^06244006.0196340 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007910 | 495275263-26669-DETAIL-08_18_2025-GO95HV-1^06247006.0364700 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007911 | 495391202-87789-DETAIL-08_19_2025-GO95HV-1^06246001.0317001 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007912 | 495682044-96709-ADMIN-11_10_2025-GO95BLTC-1^06246012.0126801 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007913 | 495840491-31780-DETAIL-02_19_2026-GO95HV-1^06239001.0060600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007914 | 495863414-3371-DETAIL-08_27_2025-SVCDEFLC-1^07216001.0169401 | OTHER | Non-HFTD | Distribution | 2025-08-27 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007915 | 496280234-94071-DETAIL-09_08_2025-GO95HV-1^06147001.0333100 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007916 | 496476978-83271-DETAIL-09_04_2025-GO95HV-1^06146001.0082700 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007917 | 496669835-87449-ADMIN-03_14_2025-POLEREPL-1^06245007.0224605 | POLE | Non-HFTD | Distribution | 2025-03-14 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007918 | 496845238-92379-DETAIL-06_16_2025-GO95MLD-1^06248004.0364042 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007919 | 497063606-47762-DETAIL-04_16_2025-GO95TCH-1^06242005.0367600 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007920 | 497116306-17589-DETAIL-08_04_2025-GO95HV-1^06246002.0019001 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007921 | 497144429-571-DETAIL-08_13_2025-ABNDEQPM-1^06246002.0368900 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007922 | 497194654-54480-DTLTRT-10_08_2020-CUSTWIRE-1^668047/00 6/019 | OTHER | HFTD Tier 2 | Transmission | 2020-10-08 | 2023-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007923 | 497233915-72219-DTLSB-01_27_2026-GO95HV-1^06242009.0059204 | OTHER | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007924 | 497507986-82671-DTLSB-05_05_2026-GO95HV-1^06142013.0220501 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007925 | 497554578-4589-DETAIL-09_04_2025-GO95HV-1^06146001.0082600 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007926 | 497575599-92492-DTLSB-07_22_2025-GO95HV-1^06244006.0195640 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007927 | 497589883-21983-DETAIL-06_11_2026-GO95HV-1^07217001.0275206 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007928 | 498043660-43971-DETAIL-06_10_2026-GUYHINS-1^668086/00 5/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007929 | 498043660-43971-DETAIL-06_10_2026-GUYHINS-2^668086/00 5/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007930 | 498050742-38099-DTLSB-02_27_2019-ENCHRW-1^06147005.0220302 | OTHER | Non-HFTD | Distribution | 2019-02-27 | 2022-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007931 | 498212567-55071-ADMIN-10_30_2025-GO95HV-1^06246001.0040101 | OTHER | Non-HFTD | Distribution | 2025-10-30 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007932 | 498479364-19000-DETAIL-01_28_2026-GUYHINS-1^06239002.0063507 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-01-28 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007933 | 498740044-34954-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135401 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007934 | 498778675-35779-DTLSB-07_10_2025-GO95HV-1^06244007.0020000 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007935 | 49881356-2356-DETAIL-04_06_2023-CUSTWIRE-1^06245006.0244401 | OTHER | Non-HFTD | Distribution | 2023-04-06 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007936 | 49908140-36559-DETAIL-09_18_2025-GO95HV-1^06246006.0011602 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007937 | 499583740-21039-DETAIL-09_04_2025-GO95HV-1^07216001.0098301 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007938 | 499962719-13659-DETAIL-08_05_2025-GO95HV-1^06247005.0206901 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007939 | 501039956-75659-DTLTRT-04_30_2026-GO95HV-1^668004/00 3/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007940 | 50108409-4450-DETAIL-10_01_2025-GO95HV-1^06148001.0300104 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007941 | 501376350-88589-DETAIL-08_05_2025-GO95HV-1^06246001.0060300 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007942 | 501435734-95560-DETAIL-01_27_2026-GO95HV-1^06239002.0062703 | OTHER | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007943 | 501551528-1340-DETAIL-01_30_2025-GUYHINS-1^06240004.0162705 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007944 | 501959531-9180-DETAIL-02_13_2025-SVCROAD-1^06240004.0168041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007945 | 501994201-26632-AUDIT-04_22_2025-GUYHINS-1^06241005.0117707 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-22 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007946 | 502038473-6149-DETAIL-06_02_2025-GO95HV-1^06244006.0149200 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007947 | 50212908-29719-DTLSB-04_09_2026-XARMSPCR-1^06241007.0209301 | CROSSARM | HFTD Tier 2 | Distribution | 2026-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007948 | 502576268-64749-DTLSB-07_17_2025-GO95CL10-1^06244007.0149800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007949 | 502688144-4681-DETAIL-06_10_2026-GUYHINS-1^668086/00 1/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007950 | 502760489-65389-DETAIL-05_30_2024-CUSTWIRE-1^06246005.0339300 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007951 | 503074884-6081-DTLTRT-05_14_2026-GO95HV-1^668085/00 16/004 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007952 | 503103856-7449-DTLSB-07_09_2025-GO95HV-1^06244006.0276604 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007953 | 503846912-15799-DTLSB-05_04_2026-GO95HV-1^06241009.0035900 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007954 | 50413766-44770-DETAIL-01_14_2025-GUYHINS-1^06239004.0256110 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007955 | 504178241-11081-DTLTRT-06_23_2025-BIRDDMG-1^668087/00 3/001 | POLE | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007956 | 504223930-45570-DETAIL-04_02_2026-CUSTWIRE-1^06236005.0214901 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007957 | 504577184-23281-DETAIL-06_10_2026-GUYHINS-2^668086/00 6/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007958 | 504577184-23281-DETAIL-06_10_2026-GUYHINS-3^668086/00 6/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007959 | 504802534-99481-DETAIL-04_22_2026-XARMSPCR-1^668041/00 16/028 | CROSSARM | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007960 | 504806388-581-DTLSB-05_06_2026-GO95HV-1^06142013.0285901 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007961 | 504815058-11581-DTLSB-04_29_2026-GO95HV-1^06142013.0287502 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007962 | 505101814-84890-DETAIL-05_01_2025-GO95MLD-1^06239002.0066906 | OTHER | HFTD Tier 2 | Distribution | 2025-05-01 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007963 | 505114285-39259-DETAIL-07_22_2025-GO95HV-1^06247005.0040200 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007964 | 505133164-58281-DETAIL-04_17_2025-GO95MLD-1^06242005.0361602 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007965 | 505138600-35901-DETAIL-01_15_2026-SVCTREE-1^06239004.0135003 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007966 | 505244451-13273-DETAIL-09_18_2025-DISTHDWR-1^06248007.0278301 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007967 | 505398239-86639-DETAIL-06_04_2025-GO95HV-1^668075/00 15/025 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007968 | 505673798-80190-DETAIL-02_19_2025-GO95MLD-1^06239004.0365504 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007969 | 505673798-80190-DRONE_HY-07_01_2026-COVCOTHR-2^06239004.0365504 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007970 | 505918798-48540-DETAIL-02_09_2026-GO95HV-1^06239003.0018102 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007971 | 506029548-91740-DETAIL-02_09_2026-SVCDEFLC-1^06239003.0019000 | OTHER | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007972 | 506069294-65729-DTLSB-01_21_2026-GO95HV-1^06242009.0298302 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007973 | 506078246-91349-DTLSB-07_10_2025-GO95HV-1^06244006.0272000 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007974 | 506236688-12039-DETAIL-04_22_2026-GO95HV-1^06142012.0144603 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007975 | 506290890-77970-DETAIL-02_19_2026-GO95HV-1^06239002.0027500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007976 | 506323694-58681-DETAIL-06_09_2026-GUYHINS-2^668086/00 17/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007977 | 507020209-60209-DTLSB-07_02_2025-GO95HV-1^06244007.0131840 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007978 | 50743538-59750-DETAIL-08_07_2025-GO95HV-1^06246002.0250902 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007979 | 50751272-11899-DTLSB-09_09_2022-CUSTWIRE-1^06243004.0054100 | OTHER | Non-HFTD | Distribution | 2022-09-09 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007980 | 50759973-70850-DETAIL-05_14_2025-GO95HV-1^06142012.0117901 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007981 | 50777493-79419-DTLSB-04_06_2026-BIRDDMG-1^06241009.0154703 | POLE | Non-HFTD | Distribution | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007982 | 50777493-79419-DTLSB-04_06_2026-GO95BLTC-1^06241009.0154703 | OTHER | Non-HFTD | Distribution | 2026-04-06 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007983 | 507894984-17789-DETAIL-07_30_2024-CUSTWIRE-1^06244005.0349100 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007984 | 508060464-61464-DETAIL-09_08_2025-GO95HV-1^06147001.0330500 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007985 | 508060464-61464-DETAIL-09_08_2025-GUYHINS-1^06147001.0330500 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-08 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007986 | 508130326-86593-DETAIL-07_29_2025-DISTHDWR-1^06247005.0260301 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007987 | 508313694-87499-DETAIL-03_12_2024-CUSTWIRE-1^06245007.0276801 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007988 | 508459694-5999-DETAIL-03_11_2024-COPLLEAN-1^06147005.0173001 | POLE | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007989 | 508510436-58389-DETAIL-08_04_2025-GO95BLTC-1^06246001.0180000 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007990 | 509060387-96719-DTLSB-07_08_2026-GO95HV-1^06242009.0261203 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007991 | 509148580-2559-DETAIL-09_23_2025-GO95HV-1^06246006.0019201 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007992 | 509476520-8091-DETAIL-08_12_2025-GO95BLTC-1^06246001.0300102 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007993 | 509476520-8091-DETAIL-08_12_2025-GO95HV-1^06246001.0300102 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007994 | 50975569-93950-AUDIT-09_02_2025-GRDRODHI-2^06246002.0345001 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007995 | 50975569-93950-DETAIL-08_18_2025-GO95HV-1^06246002.0345001 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007996 | 510037270-51589-DTLSB-07_01_2025-GO95MLD-1^06244007.0130840 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007997 | 510547418-96779-DETAIL-08_07_2025-GO95HV-1^06246002.0266900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120007998 | 510617062-16191-DTLTRT-06_30_2025-GUYNOINS-2^668087/00 7/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120007999 | 510688254-69069-DETAIL-09_17_2025-GO95HV-1^06248007.0364701 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008000 | 510959010-90110-DETAIL-08_01_2024-CUSTWIRE-1^06245006.0152900 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008001 | 511734559-69999-DETAIL-04_01_2024-GO95MLD-1^06147005.0097700 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008002 | 511734559-69999-DETAIL-04_01_2024-GRDRODHI-1^06147005.0097700 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008003 | 511815511-33891-DTLSB-10_16_2025-GO95HV-1^06247001.0275300 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008004 | 511828981-53891-DETAIL-09_16_2025-GO95HV-1^06147001.0061700 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008005 | 511828981-53891-DETAIL-09_16_2025-GO95TCH-1^06147001.0061700 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008006 | 512186983-81869-DETAIL-12_18_2024-BIRDDMG-1^668002/00 7/064 | POLE | HFTD Tier 2 | Transmission | 2024-12-18 | 2027-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008007 | 512251033-1180-DETAIL-02_25_2025-GO95TCH-1^06240005.0018200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008008 | 512926445-59933-DETAIL-09_16_2025-GO95HV-1^06247004.0086540 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008009 | 513062408-90849-ADMIN-10_22_2025-GO95MLD-1^07216001.0203105 | OTHER | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008010 | 513088042-37139-DETAIL-05_20_2025-GO95HV-1^06243006.0068403 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008011 | 513193819-31471-DETAIL-02_25_2025-GO95BLTC-1^06241005.0152701 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008012 | 513532299-3491-DETAIL-08_13_2025-GO95HV-1^06246002.0361901 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008013 | 51371168-69709-DETAIL-08_26_2025-GO95HV-1^06247006.0299102 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008014 | 51433939-23250-DTLTRT-06_24_2025-BIRDDMG-1^668087/00 11/004 | POLE | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008015 | 515526149-43991-DETAIL-08_18_2025-GO95HV-1^06246002.0263400 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008016 | 516115957-3409-DETAIL-06_05_2025-GO95HV-1^06245006.0300300 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008017 | 516146933-35021-DRONE_HY-06_19_2026-COVCOTHR-1^06239004.0364900 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008018 | 516286048-64149-DETAIL-10_14_2024-SVCRUBLG-1^07216001.0204209 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008019 | 516545125-75125-DETAIL-07_06_2026-GO95HV-1^07217001.0117804 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008020 | 516690116-30279-DETAIL-02_16_2026-GO95HV-1^06239001.0052702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008021 | 516953755-90033-DETAIL-09_16_2025-GO95HV-1^06247004.0087640 | OTHER | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008022 | 517303903-96529-DTLSB-08_10_2023-CUSTWIRE-1^06243009.0276002 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008023 | 517846459-89159-DTLSB-06_17_2026-CLMBTRE-1^07217001.0276004 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008024 | 51786428-87079-DETAIL-06_17_2025-GO95BLTC-1^06248004.0299000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008025 | 517937598-30478-DETAIL-09_16_2025-GO95MLD-1^07218001.0058600 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008026 | 517942952-52559-DETAIL-04_29_2026-GO95HV-1^668004/00 8/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008027 | 518003156-67281-ADMIN-05_09_2025-SVCTREE-1^06241006.0115600 | OTHER | HFTD Tier 2 | Distribution | 2025-05-09 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008028 | 518003156-67281-DETAIL-04_24_2025-SVCDEFLC-1^06241006.0115600 | OTHER | HFTD Tier 2 | Distribution | 2025-04-24 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008029 | 518110264-90960-DRONE_HY-06_19_2026-COVCOTHR-1^06240004.0161406 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008030 | 518861436-30660-DETAIL-04_29_2026-GO95HV-1^668004/00 2/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008031 | 518988543-58559-ADMIN-08_15_2025-POLEREPL-1^06247005.0298902 | POLE | Non-HFTD | Distribution | 2025-08-15 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008032 | 519073165-83739-DETAIL-05_08_2025-GO95HV-1^06243006.0105401 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008033 | 519079272-74560-DETAIL-04_29_2026-GO95HV-1^668004/00 1/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008034 | 519174663-85180-DETAIL-03_31_2026-SVCDEFLC-1^06240004.0357001 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008035 | 519719726-70273-DTLSB-06_11_2026-CLMBTRE-1^07217001.0277002 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008036 | 519745195-58195-DETAIL-06_02_2025-GO95HV-1^06147014.0027200 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008037 | 519893445-28799-DETAIL-05_22_2025-GO95HV-1^06244006.0042941 | OTHER | Non-HFTD | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008038 | 520287248-38949-DTLSB-07_08_2025-GO95HV-1^06244007.0035901 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008039 | 520502684-56290-DETAIL-02_05_2026-SVCDEFLC-1^06239003.0019617 | OTHER | Non-HFTD | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008040 | 520575753-22953-DETAIL-10_12_2022-GO95HV-1^668005/08 8X8/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008041 | 520575753-22953-DETAIL-10_12_2022-GUYHINS-2^668005/08 8X8/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008042 | 520791606-12606-DETAIL-01_22_2026-GO95MLD-1^06239004.0231101 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008043 | 520820558-51829-DETAIL-04_28_2026-GO95HV-1^06142012.0149500 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008044 | 521472210-78110-DETAIL-06_05_2025-GO95HV-1^668075/00 13/026 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008045 | 521756098-62742-DETAIL-04_21_2025-GO95HV-1^06242006.0100700 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008046 | 52185716-78949-DETAIL-07_29_2025-GO95HV-1^06247005.0261400 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008047 | 522072954-39839-DETAIL-05_06_2025-GO95HV-1^06243006.0030400 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008048 | 522277481-6142-DETAIL-04_07_2025-SVCROOF-1^06241005.0118500 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008049 | 522366558-39101-DETAIL-09_09_2025-GO95HV-1^06146001.0045200 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008050 | 522541615-66615-DETAIL-06_02_2025-GO95HV-1^06147014.0028201 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008051 | 522699875-49663-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0097701 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008052 | 523051005-61005-DTLTRT-06_30_2025-BIRDDMG-1^668087/01 6/001 | POLE | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008053 | 523172022-65022-DETAIL-07_24_2025-GO95HV-1^06247005.0131201 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008054 | 523687197-11999-DTLSB-08_22_2024-CUSTWIRE-1^06245006.0324200 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008055 | 52390228-52613-DETAIL-09_02_2025-GO95BLTC-1^06247006.0278400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008056 | 524045363-32179-ADMIN-10_28_2025-COVCFRAY-1^06246001.0129701 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-28 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008057 | 524060018-45532-DETAIL-04_17_2025-GO95HV-1^06242006.0094700 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008058 | 52411106-26889-DTLSB-07_14_2025-GO95HV-1^06244007.0143600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008059 | 524445738-98611-DETAIL-04_21_2026-GO95HV-1^06142012.0143800 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008060 | 524486506-66711-DTLSB-06_04_2026-CUSTWIRE-1^07216001.0114101 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008061 | 524544865-12339-DTLTRT-06_26_2025-SVCENTCO-1^668087/00 8/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008062 | 524844393-18519-DETAIL-04_02_2026-GO95HV-1^06241009.0216100 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008063 | 525085666-47342-DETAIL-04_29_2025-GO95MLD-1^06242005.0323800 | OTHER | HFTD Tier 2 | Distribution | 2025-04-29 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008064 | 525291921-85839-DTLSB-07_17_2025-ABNDEQPM-1^06244006.0218301 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008065 | 52555363-68603-DTLTRT-04_25_2024-CUSTWIRE-1^06245007.0229542 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008066 | 52564413-11809-DETAIL-08_28_2025-GO95HV-1^06247006.0076700 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008067 | 525726347-62970-DETAIL-02_26_2025-SVCNEUT-1^06240004.0061304 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008068 | 526263764-7419-DETAIL-06_28_2022-CUSTWIRE-1^07116007.0159501 | OTHER | HFTD Tier 2 | Distribution | 2022-06-28 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008069 | 5263880-24561-DETAIL-05_30_2023-CUSTWIRE-1^06243009.0028902 | OTHER | HFTD Tier 2 | Distribution | 2023-05-30 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008070 | 526489982-78850-DETAIL-02_05_2026-GO95HV-1^06239003.0019308 | OTHER | Non-HFTD | Distribution | 2026-02-05 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008071 | 526880731-61680-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0169045 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008072 | 526963548-76259-DETAIL-09_02_2025-GRDRODHI-1^06247006.0276503 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008073 | 527122719-61911-DETAIL-09_02_2025-GO95HV-1^06246001.0201900 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008074 | 527198826-63280-DETAIL-01_24_2025-GO95HV-1^06239004.0257946 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008075 | 527276629-37279-DETAIL-09_17_2025-SVCDEFLC-1^06248007.0240403 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008076 | 527324754-22959-DETAIL-09_15_2025-GO95HV-1^06248007.0156000 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008077 | 527408885-36739-AUDIT-10_07_2025-ANCHIDLE-1^07216001.0165506 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008078 | 527746385-68385-DETAIL-06_02_2025-GO95HV-1^06148014.0240900 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008079 | 527854933-76411-DTLSB-05_23_2024-GO95HV-1^06243001.0117001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008080 | 528080565-4509-DETAIL-08_27_2025-GUYHINS-1^06247006.0188601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-08-27 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008081 | 5280980-33789-DETAIL-06_18_2025-GO95BLTC-1^06248004.0340604 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008082 | 528189395-53110-DETAIL-02_26_2026-GO95HV-1^06238004.0114202 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008083 | 528189395-53110-DETAIL-02_26_2026-PWRTRN-1^06238004.0114202 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008084 | 528536076-48209-DETAIL-08_12_2025-GO95HV-1^06247006.0265200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008085 | 528756088-86088-DETAIL-06_19_2025-GO95HV-1^668075/00 1X/049 | OTHER | HFTD Tier 2 | Transmission | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008086 | 528878138-68559-DTLSB-08_13_2025-GO95HV-1^07217001.0024300 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008087 | 529047102-46369-DETAIL-06_24_2025-GO95HV-1^06248004.0312901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008088 | 529109218-12459-DETAIL-06_03_2024-CUSTWIRE-1^06246005.0319901 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008089 | 529459764-87774-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135200 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008090 | 529671434-27183-DETAIL-09_11_2025-GO95HV-1^06248007.0222802 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008091 | 529819333-96599-DETAIL-09_17_2025-GRDRODHI-1^06147001.0237701 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008092 | 529850242-42242-DETAIL-08_12_2025-GO95HV-1^06246001.0300103 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008093 | 530109683-22783-DETAIL-03_30_2023-ENCHRW-1^06142016.0059005 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008094 | 530109683-22783-DETAIL-03_30_2023-ENCHRW-2^06142016.0059005 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008095 | 530287668-92450-DETAIL-02_24_2026-GO95HV-1^06239003.0132300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008096 | 530287668-92450-DETAIL-02_24_2026-GO95MLD-1^06239003.0132300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008097 | 530299381-79570-DETAIL-02_19_2025-GO95TCH-1^06241005.0277001 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008098 | 530438963-66080-DETAIL-02_23_2026-GO95HV-1^06239002.0225301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008099 | 531079135-63600-DETAIL-02_10_2026-GRDRODHI-1^06239003.0016717 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008100 | 532381790-85123-AUDIT-03_04_2026-ABNDEQPM-1^06239002.0070100 | OTHER | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008101 | 532441904-17859-DTLTRT-04_22_2026-GRDRODHI-1^668004/02 9/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008102 | 532786870-91859-DETAIL-06_16_2025-GO95HV-1^06248005.0332902 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008103 | 532843305-56989-DTLSB-07_01_2025-GO95HV-1^06244006.0225401 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008104 | 532852040-46099-DETAIL-09_18_2025-CLRTOUCH-1^06246006.0011802 | CONDUCTOR | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008105 | 532852040-46099-DETAIL-09_18_2025-GO95HV-1^06246006.0011802 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008106 | 533030126-38021-DTLSB-04_30_2026-GO95HV-1^06142013.0187400 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008107 | 533067297-83588-DTLSB-06_24_2026-GO95HV-1^07217001.0356200 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008108 | 533183332-77949-ADMIN-03_06_2024-ABNDEQPM-1^07113002.0183203 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008109 | 533576029-66753-DTLSB-04_29_2024-GO95MLD-1^06245007.0226447 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008110 | 533583131-83801-DETAIL-01_14_2025-SVCROAD-1^06239004.0255140 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008111 | 533912907-94621-ADMIN-11_10_2025-GO95HV-1^06246001.0254300 | OTHER | Non-HFTD | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008112 | 533983816-14721-DTLSB-04_28_2026-GO95HV-1^06142013.0187200 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008113 | 534154250-59921-AUDIT-10_13_2025-ABNDEQPM-1^06148001.0304202 | OTHER | Non-HFTD | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008114 | 53425034-12810-DETAIL-03_13_2025-GO95HV-1^06238004.0152202 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008115 | 53425034-12810-DRONE_HY-06_30_2026-DISTHDWR-1^06238004.0152202 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008116 | 534280595-47595-DTLSB-06_03_2026-SVCDEFLC-1^07216001.0029320 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008117 | 534280595-47595-DTLSB-06_03_2026-SVCROAD-1^07216001.0029320 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008118 | 534340201-33780-DETAIL-02_19_2026-GO95HV-1^06239001.0062602 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008119 | 534535196-51373-DETAIL-09_10_2025-GO95TCH-1^07218001.0177103 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008120 | 534535196-51373-DETAIL-09_10_2025-GUYHINS-1^07218001.0177103 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008121 | 534538873-93309-DETAIL-09_15_2025-GO95HV-1^06248007.0231200 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008122 | 534542630-32240-DETAIL-03_10_2026-COVCOTHR-1^06239003.0060300 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008123 | 534755644-84789-DETAIL-07_30_2025-CUTOUTAR-2^06247005.0310103 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008124 | 534755644-84789-DETAIL-07_30_2025-GO95HV-1^06247005.0310103 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008125 | 535263470-56978-DETAIL-07_06_2026-GO95HV-1^07217001.0047700 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008126 | 535422471-94179-ADMIN-11_13_2025-GO95BLTC-1^06246010.0132700 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008127 | 53547544-29440-DETAIL-03_25_2026-COVCOTHR-1^06240004.0216601 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008128 | 53547544-29440-DETAIL-03_25_2026-COVCOTHR-2^06240004.0216601 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008129 | 535807362-94980-DETAIL-01_29_2026-GO95BLTC-1^06240004.0309200 | OTHER | HFTD Tier 3 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008130 | 535814280-94970-DETAIL-02_19_2026-GO95HV-1^06239002.0026501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008131 | 535986478-93913-DETAIL-08_27_2025-GO95HV-1^06247006.0285704 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008132 | 536904234-88021-DETAIL-08_20_2025-GO95HV-1^06246001.0172501 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008133 | 536929718-79409-ADMIN-01_23_2024-POLEREPL-1^06147005.0268301 | POLE | Non-HFTD | Distribution | 2024-01-23 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008134 | 537007988-92121-DETAIL-08_18_2025-GO95HV-1^06246002.0354901 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008135 | 537302301-48221-DETAIL-09_10_2025-GO95HV-1^06147001.0073001 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008136 | 53753349-97059-DTLTRT-05_06_2026-GO95HV-1^668004/00 1/023 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008137 | 53753349-97060-DTLTRT-05_06_2026-GO95HV-1^668004/00 1/023 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008138 | 537615635-31100-DETAIL-04_07_2026-GO95HV-1^06240002.0317108 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008139 | 538087189-7821-DETAIL-09_08_2025-GO95HV-1^06147001.0329400 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008140 | 538115293-8429-DETAIL-05_19_2025-GO95HV-1^06142012.0013301 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008141 | 538364670-42329-DTLTRT-10_26_2022-CUSTWIRE-1^668001/00 12/028 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008142 | 538404289-22579-DTLSB-04_22_2024-SVCENTCO-1^06245007.0224407 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008143 | 538500175-37761-DRONE_HY-07_01_2026-COVCOTHR-1^06239004.0367701 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008144 | 53853858-57649-DTLSB-07_03_2025-GO95HV-1^06244007.0132802 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008145 | 538637544-29053-DETAIL-05_21_2026-SVCROAD-1^07217001.0144801 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008146 | 538637544-29053-DETAIL-05_21_2026-SVCROAD-2^07217001.0144801 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008147 | 538763741-93523-DETAIL-06_17_2024-CUSTWIRE-1^06246006.0136700 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008148 | 538915501-98739-DTLTRT-06_25_2025-GUYHINS-1^668087/00 1/008 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008149 | 539089235-63335-DETAIL-05_30_2025-GO95HV-1^06147014.0119900 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008150 | 539327723-15939-DTLTRT-05_13_2026-CUSTWIRE-1^668085/00 2/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008151 | 539367873-1621-DETAIL-06_16_2025-GO95HV-1^06237005.0249501 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008152 | 539376628-15779-DETAIL-08_07_2025-GO95HV-1^06246002.0250900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008153 | 53940106-60873-DTLSB-06_11_2026-GO95HV-1^07217001.0276001 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008154 | 539466649-80521-DETAIL-04_03_2025-GO95HV-1^06241005.0092000 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008155 | 539520571-24702-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008156 | 539573396-48119-DTLSB-07_17_2025-GO95HV-1^06244006.0218304 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008157 | 539682300-1930-DTLTRT-11_03_2023-CUSTWIRE-1^668010/00 12/027 | OTHER | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008158 | 539852214-64159-DETAIL-08_18_2025-GO95HV-1^06247006.0364402 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008159 | 540319280-44479-DETAIL-09_30_2025-ABNDEQPM-1^06246009.0133700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008160 | 540319280-44479-DETAIL-09_30_2025-SVCROAD-1^06246009.0133700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008161 | 540418863-70799-DETAIL-05_28_2025-GO95HV-1^06244006.0093300 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008162 | 54046793-20129-DETAIL-04_22_2026-GO95HV-1^06142012.0149606 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008163 | 540599300-76609-DETAIL-10_08_2025-ANCHIDLE-1^06246008.0103601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008164 | 540761492-53189-DETAIL-08_14_2025-GO95HV-1^06246001.0316901 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008165 | 540977502-50450-DETAIL-01_31_2025-GO95HV-1^06239004.0136201 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008166 | 541397736-27470-DETAIL-01_15_2025-GO95HV-1^06239004.0255245 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008167 | 541477417-19417-DETAIL-06_18_2025-GUYHINS-3^668075/00 13X2/046 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008168 | 541700289-43279-DETAIL-10_13_2025-GO95MLD-1^06148001.0365500 | OTHER | Non-HFTD | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008169 | 541825424-15831-DETAIL-09_05_2025-GO95HV-1^06147001.0309301 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008170 | 541842596-23596-DETAIL-04_09_2025-GO95TCH-1^06241005.0026602 | OTHER | HFTD Tier 2 | Distribution | 2025-04-09 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008171 | 541889790-5890-DETAIL-01_21_2025-SVCENTCO-1^06239004.0255400 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008172 | 542143232-53232-DETAIL-08_13_2025-GRDRODHI-1^06246002.0362501 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008173 | 542143232-53232-DETAIL-08_13_2025-GRDRODHI-2^06246002.0362501 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008174 | 542145771-50309-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0209705 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008175 | 542392959-5331-DTLSB-05_20_2024-GO95BLTC-1^06244003.0287700 | OTHER | Non-HFTD | Distribution | 2024-05-20 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008176 | 542468109-6541-DETAIL-04_08_2025-GO95HV-1^06241005.0092601 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008177 | 543655576-42089-DTLSB-04_01_2026-GRDRODHI-1^06241009.0328200 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008178 | 54384845-54800-DETAIL-04_28_2025-GO95HV-1^06239002.0061701 | OTHER | HFTD Tier 2 | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008179 | 543964741-96350-DETAIL-02_11_2025-GUYHINS-1^06239004.0124904 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008180 | 544180349-24899-DETAIL-09_09_2025-GO95HV-1^06246007.0144050 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008181 | 544229683-97799-DETAIL-03_11_2024-CUSTWIRE-1^06147005.0177300 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008182 | 544342143-94330-DETAIL-03_10_2025-GO95MLD-1^06240004.0064601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008183 | 544578531-44959-DETAIL-03_13_2024-CUSTWIRE-1^06245007.0282301 | OTHER | HFTD Tier 2 | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008184 | 544943881-53131-DETAIL-09_10_2025-GO95HV-1^06147001.0077800 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008185 | 545012342-91559-DETAIL-04_29_2026-GO95HV-1^668004/00 7/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008186 | 545086128-57128-DTLSB-06_03_2026-CUSTWIRE-1^07216001.0028340 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008187 | 545086128-57128-DTLSB-06_03_2026-SVCROAD-1^07216001.0028340 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008188 | 545226640-46631-DTLSB-06_02_2026-GO95TCH-1^07216001.0115903 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008189 | 545312945-76451-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0366705 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008190 | 54542250-93389-DETAIL-10_14_2025-GO95HV-1^06148001.0346601 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008191 | 54551779-52113-DETAIL-08_25_2025-GO95HV-1^06247006.0282401 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008192 | 545836162-71341-DETAIL-08_14_2025-DISTHDWR-1^06246001.0318400 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008193 | 545901660-60678-DTLSB-07_16_2025-GO95HV-1^06244006.0236001 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008194 | 546266270-1541-DETAIL-09_29_2025-GO95HV-1^06148001.0310605 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008195 | 54637741-30723-DETAIL-06_18_2025-GO95HV-1^06248004.0342641 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008196 | 546500469-74049-AUDIT-10_14_2025-CLRTOUCH-1^07216001.0097104 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008197 | 546500469-74049-DETAIL-09_04_2025-GRDRODHI-1^07216001.0097104 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008198 | 546794021-2059-DETAIL-08_28_2025-GO95HV-1^06247006.0063201 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008199 | 547385671-21550-DRONE_HY-07_15_2026-GUYSLACK-1^06239004.0256504 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008200 | 547414443-79950-DETAIL-01_14_2026-GO95MLD-1^06239004.0244949 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008201 | 547525541-10939-ADMIN-07_01_2024-POLEDERP-1^07216001.0033108 | POLE | Non-HFTD | Distribution | 2024-07-01 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008202 | 547768899-669-DETAIL-09_03_2025-GO95HV-1^06247006.0295700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008203 | 548053049-33990-DETAIL-01_12_2026-GO95TCH-1^06239004.0245403 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008204 | 548303154-12999-DTLSB-06_30_2025-BIRDDMG-1^06244007.0034100 | POLE | HFTD Tier 2 | Distribution | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008205 | 548303154-12999-DTLSB-06_30_2025-GO95BLTC-1^06244007.0034100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008206 | 548303154-12999-DTLSB-06_30_2025-GO95MLD-1^06244007.0034100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008207 | 548330817-48490-DETAIL-02_03_2025-GO95HV-1^06239004.0244946 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008208 | 548457189-88279-DETAIL-04_21_2025-GO95HV-1^06242006.0036807 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008209 | 548612548-89653-DTLSB-06_10_2026-GO95HV-1^07216001.0142000 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008210 | 548841583-49983-AUDIT-08_04_2025-GUYHINS-1^07218001.0266960 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008211 | 548873446-36849-DTLSB-07_09_2025-GO95HV-1^06244007.0141902 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008212 | 549007633-95853-DETAIL-09_23_2025-GO95HV-1^07218001.0229201 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008213 | 549170273-53273-DTLSB-07_03_2025-GO95TCH-1^06245007.0357603 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008214 | 549258911-31141-DETAIL-05_07_2025-GO95HV-1^06243006.0100900 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008215 | 549341308-26289-DETAIL-10_07_2025-GO95HV-1^06148001.0261201 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008216 | 549611761-74541-DETAIL-09_29_2025-ABNDEQPM-1^06148001.0310401 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008217 | 549731234-19309-DETAIL-07_30_2025-GO95HV-1^06247006.0202402 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008218 | 549781192-20559-DETAIL-07_24_2025-GO95HV-1^06247005.0179901 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008219 | 549781192-20559-DETAIL-07_24_2025-SVCDEFLC-1^06247005.0179901 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008220 | 550015773-99179-DETAIL-09_15_2025-GO95HV-1^06248007.0233402 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008221 | 550128177-63941-DETAIL-08_18_2025-GO95HV-1^06246002.0354600 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008222 | 550234955-32900-DETAIL-04_28_2025-GO95HV-1^06239002.0060603 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008223 | 55035306-18829-DETAIL-05_15_2025-GO95HV-1^06142012.0115202 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008224 | 550928894-82841-DETAIL-08_26_2025-GO95HV-1^07216001.0169304 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008225 | 551245703-99020-DETAIL-01_21_2026-SVCTREE-1^06240004.0289300 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008226 | 551264562-4689-DETAIL-05_14_2025-RISEGRD-1^06243006.0222101 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008227 | 551525014-80283-DETAIL-08_04_2025-GO95HV-1^06247006.0208541 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008228 | 551525014-80283-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0208541 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008229 | 551859979-71430-DETAIL-01_24_2025-SVCDEFLC-1^06240004.0081601 | OTHER | HFTD Tier 2 | Distribution | 2025-01-24 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008230 | 551948440-66201-DETAIL-01_21_2025-GO95HV-1^06239004.0255342 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008231 | 551948440-66201-DETAIL-01_21_2025-GO95TCH-1^06239004.0255342 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008232 | 551990345-53200-DETAIL-02_04_2026-XARMSPCR-1^06239003.0019504 | CROSSARM | Non-HFTD | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008233 | 552059649-42459-DETAIL-06_17_2025-GO95HV-1^06248004.0352341 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008234 | 552145716-46129-DETAIL-04_28_2025-GO95HV-1^06242006.0190200 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008235 | 552339651-37889-DTLSB-07_08_2025-GO95HV-1^06245007.0352202 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008236 | 552343909-96340-DETAIL-03_05_2026-COVCOTHR-1^06238004.0011703 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008237 | 5524725-60549-DETAIL-08_27_2025-GO95HV-1^07216001.0169307 | OTHER | Non-HFTD | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008238 | 552540311-54841-DTLTRT-05_20_2026-GO95HV-1^668086/00 14/010 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008239 | 552729555-61339-DTLTRT-06_26_2025-BIRDDMG-1^668087/00 2/010 | POLE | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008240 | 553147726-69799-DETAIL-06_09_2025-GO95HV-1^06245007.0243600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008241 | 553226026-67261-DETAIL-04_07_2025-GUYHINS-1^06241005.0013800 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008242 | 553360903-95840-DTLTRT-05_29_2025-GO95HV-1^668075/00 9/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008243 | 553480268-33259-DETAIL-09_08_2025-GO95HV-1^07218001.0176701 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008244 | 553622364-32630-DETAIL-04_13_2026-GO95TCH-1^06236005.0335604 | OTHER | HFTD Tier 2 | Distribution | 2026-04-13 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008245 | 55389872-1529-DTLSB-09_09_2022-CUSTWIRE-1^06243004.0054103 | OTHER | Non-HFTD | Distribution | 2022-09-09 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008246 | 554048169-31179-DETAIL-10_15_2025-ENCHRW-1^06148001.0256300 | OTHER | Non-HFTD | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008247 | 554060756-17399-DETAIL-07_28_2025-GO95HV-1^06247005.0318403 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008248 | 554308039-74299-DETAIL-03_11_2024-GO95HV-1^06147004.0014902 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008249 | 554355633-42839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0261401 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008250 | 554446146-73161-DRONE_HY-07_02_2026-COVCOTHR-2^06239004.0366907 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008251 | 554446146-73161-DRONE_HY-07_02_2026-COVCOTHR-3^06239004.0366907 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008252 | 554446146-73161-DRONE_HY-07_02_2026-COVCOTHR-5^06239004.0366907 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008253 | 554446146-73161-DRONE_HY-07_02_2026-COVCOTHR-6^06239004.0366907 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008254 | 554684624-78859-DTLTRT-04_22_2026-GO95MLD-1^668004/02 11/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008255 | 554719077-39859-DETAIL-08_27_2025-GO95HV-1^07216001.0162904 | OTHER | Non-HFTD | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008256 | 55479676-48959-DETAIL-07_29_2025-GO95HV-1^06247005.0265802 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008257 | 554957686-76949-DTLSB-07_08_2025-GO95HV-1^06244007.0036702 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008258 | 554981348-23348-DTLSB-06_03_2026-GO95HV-1^07216001.0027300 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008259 | 555113940-16949-DETAIL-09_03_2025-GO95HV-1^07216001.0092002 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008260 | 555532085-20653-DTLSB-06_10_2026-GO95MLD-1^07217001.0350001 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008261 | 555733922-9459-DETAIL-04_29_2026-GO95HV-1^668004/00 2/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008262 | 555735049-8070-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/063 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008263 | 555803279-72889-DETAIL-08_13_2025-GO95HV-1^06246002.0368700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008264 | 555898263-65490-DETAIL-02_24_2026-GO95HV-1^06239002.0272400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008265 | 556104369-42879-DETAIL-09_30_2025-GO95HV-1^06148001.0300204 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008266 | 556111998-10809-DETAIL-08_26_2025-GO95HV-1^06247006.0299903 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008267 | 556163125-30339-DTLTRT-06_26_2025-ABNDEQPM-1^668087/00 20/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008268 | 556252406-76229-AUDIT-05_12_2026-GO95MLD-1^06142013.0187402 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008269 | 556262309-15651-DETAIL-08_19_2025-GO95HV-1^06246002.0261400 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008270 | 556293518-11170-DETAIL-03_09_2026-SVCENTCO-1^06240004.0153900 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008271 | 556411145-82145-DTLSB-05_28_2026-GO95HV-1^07216001.0022101 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008272 | 55655808-24919-DTLSB-04_16_2026-GO95HV-1^06241008.0073201 | OTHER | Non-HFTD | Distribution | 2026-04-16 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008273 | 556565783-4280-DETAIL-02_23_2026-GO95HV-1^06239002.0151200 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008274 | 556579056-56849-DTLSB-07_09_2025-GO95HV-1^06244007.0141701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008275 | 556748271-30851-DTLTRT-04_28_2026-GO95HV-1^668004/00 3/008 | OTHER | HFTD Tier 2 | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008276 | 556828581-52851-DTLSB-05_06_2026-GO95HV-1^06142013.0271400 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008277 | 556888891-25379-ADMIN-05_16_2025-XRFMBUIN-1^06242009.0298901 | INSULATOR AND BUSHING | HFTD Tier 2 | Distribution | 2025-05-16 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008278 | 556900048-80809-DETAIL-09_03_2025-GO95HV-1^06247006.0296600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008279 | 557383073-809-DETAIL-10_13_2025-GO95HV-1^06246012.0122302 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008280 | 557477829-53929-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 10/015 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008281 | 557575903-42323-DETAIL-09_10_2025-GO95HV-1^06246007.0132252 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008282 | 557621303-61303-DETAIL-06_11_2025-GUYHINS-1^668075/00 15/036 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008283 | 557646429-15351-DETAIL-09_30_2025-GO95HV-1^06148001.0301202 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008284 | 558095903-96551-ADMIN-10_27_2025-GO95HV-1^06246001.0026000 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008285 | 558323488-72119-DTLSB-04_13_2026-GO95HV-1^06241008.0365500 | OTHER | Non-HFTD | Distribution | 2026-04-13 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008286 | 558463030-43751-DTLTRT-05_14_2026-GO95HV-1^668086/00 13/004 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008287 | 558589344-19699-DETAIL-05_28_2025-GO95HV-1^06244006.0092102 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008288 | 55864203-65203-DETAIL-06_11_2025-GO95HV-1^668075/00 12/036 | OTHER | Non-HFTD | Transmission | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008289 | 559283642-30520-DETAIL-03_30_2026-GO95TCH-1^06240004.0272040 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008290 | 559585610-69922-DETAIL-04_23_2025-GO95TCH-1^06242005.0361105 | OTHER | HFTD Tier 2 | Distribution | 2025-04-23 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008291 | 559812482-42639-DETAIL-05_14_2025-GO95HV-1^06243006.0150500 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008292 | 559883121-79970-DETAIL-02_18_2026-GO95HV-1^06239002.0040302 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008293 | 559979806-28700-DETAIL-04_07_2026-GO95HV-1^06240002.0317020 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008294 | 560050791-4979-DTLSB-02_20_2023-CUSTWIRE-1^06248001.0288500 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008295 | 560176199-26040-DETAIL-06_19_2025-GO95HV-1^06237004.0078202 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008296 | 560580491-5191-DETAIL-03_27_2023-ABNDEQPM-1^06142016.0082903 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008297 | 560695329-69251-DTLTRT-06_26_2025-GO95HV-1^668087/00 6/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008298 | 560705571-99251-DETAIL-09_10_2025-GO95HV-1^06147001.0073400 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008299 | 560714395-68799-DETAIL-05_27_2025-GO95HV-1^06244006.0042940 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008300 | 560718643-1863-DTLTRT-07_03_2025-GO95HV-1^668087/00 9/012 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008301 | 56082189-41513-DETAIL-08_26_2025-GO95HV-1^06247006.0332900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008302 | 56152846-73360-DTLSB-05_29_2026-GO95HV-1^07216001.0114701 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008303 | 561923235-1100-DETAIL-03_25_2021-CUSTWIRE-1^06240002.0317107 | OTHER | HFTD Tier 2 | Distribution | 2021-03-25 | 2024-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008304 | 561923235-1100-DETAIL-04_07_2026-GO95HV-1^06240002.0317107 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008305 | 561997718-48069-DETAIL-05_08_2025-GO95HV-1^06243006.0096801 | OTHER | HFTD Tier 2 | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008306 | 562100713-97239-DETAIL-07_10_2024-ENCHRW-1^06244005.0289900 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008307 | 562513891-30170-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008308 | 562543083-58480-DETAIL-02_11_2025-GO95MLD-1^06240004.0167405 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008309 | 562543083-58480-DRONE_HY-06_30_2026-RISEGRD-1^06240004.0167405 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008310 | 562559329-21449-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0149200 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008311 | 562636611-26161-DETAIL-10_02_2025-GO95HV-1^06148001.0306400 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008312 | 562767948-57799-DETAIL-06_04_2024-CUSTWIRE-1^06246005.0315500 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008313 | 562908131-23022-DTLTRT-04_23_2026-GO95HV-1^668004/00 6/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008314 | 562908131-67361-DTLTRT-04_23_2026-GO95HV-1^668004/00 6/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008315 | 563515646-65680-DETAIL-01_22_2025-GO95HV-1^06239004.0257640 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008316 | 563984465-14209-DETAIL-08_13_2025-BIRDDMG-1^06247006.0262602 | POLE | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008317 | 563984465-14209-DETAIL-08_13_2025-GO95HV-1^06247006.0262602 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008318 | 564008238-53359-DETAIL-07_28_2025-GO95HV-1^06247005.0086441 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008319 | 564060919-33029-DTLSB-08_14_2023-CUSTWIRE-1^06243009.0245100 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008320 | 564324528-77253-DTLSB-06_04_2026-GO95HV-1^07216001.0142301 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008321 | 564354700-95053-DETAIL-09_04_2025-GO95HV-1^06247006.0160000 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008322 | 564520854-19189-DETAIL-08_18_2025-SVCROAD-1^06247006.0363401 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008323 | 564654136-32761-DETAIL-02_20_2023-CUSTWIRE-1^06247002.0297501 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008324 | 564695422-869-DTLTRT-09_26_2023-GO95STUB-1^668010/00 2/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-26 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008325 | 564799324-9739-DETAIL-06_02_2025-GO95HV-1^06244006.0154901 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008326 | 56481259-60660-DETAIL-09_30_2025-GO95TCH-1^06148001.0300001 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008327 | 564835823-63780-DETAIL-02_24_2026-BIRDDMG-1^06239002.0180801 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008328 | 565272796-15953-DTLSB-06_16_2026-GO95HV-1^07217001.0357601 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008329 | 565591216-97879-DETAIL-01_14_2026-GUYNOINS-1^06239004.0244948 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008330 | 565591216-97879-DETAIL-02_03_2025-GO95HV-1^06239004.0244948 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008331 | 566110641-18373-DETAIL-09_16_2025-GO95MLD-1^07218001.0046701 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008332 | 566320775-24061-DTLSB-06_09_2026-GO95HV-1^07216001.0226101 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008333 | 566320775-24061-DTLSB-06_09_2026-SVCROAD-1^07216001.0226101 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008334 | 566390515-63000-DETAIL-02_25_2026-GO95HV-1^06239003.0242500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008335 | 566514644-58639-DETAIL-04_07_2025-SVCROAD-1^06241005.0119307 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008336 | 566591503-58659-DETAIL-07_29_2025-GO95HV-1^06247005.0216700 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008337 | 566629774-13329-ADMIN-07_16_2024-POLEREPL-1^668067/00 1/016 | POLE | Non-HFTD | Transmission | 2024-07-16 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008338 | 566629774-13329-DTLTRT-04_16_2024-XARMSPCR-1^668067/00 1/016 | CROSSARM | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008339 | 566643413-19359-DETAIL-06_11_2025-GO95HV-1^06245007.0360800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008340 | 566820475-65439-DTLTRT-06_26_2025-CLRTOPOL-1^668087/00 9/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008341 | 566820475-65439-DTLTRT-06_26_2025-GO95HV-1^668087/00 9/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008342 | 566820475-65439-DTLTRT-06_26_2025-GO95MLD-1^668087/00 9/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008343 | 566820475-65439-DTLTRT-06_26_2025-GO95TCH-1^668087/00 9/010 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008344 | 566943569-71459-DETAIL-07_28_2025-GO95HV-1^06247005.0195101 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008345 | 567210656-26610-DETAIL-03_13_2025-GO95BLTC-1^06238004.0225701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008346 | 567345445-96199-DTLSB-07_15_2025-GO95HV-1^06244006.0344100 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008347 | 567359176-12276-DETAIL-06_03_2025-GO95HV-1^06148015.0323400 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008348 | 567524064-20439-DETAIL-10_06_2025-GO95HV-1^06243007.0361402 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008349 | 567528141-98080-DETAIL-02_16_2026-GO95HV-1^06239001.0043701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008350 | 567590115-63800-DETAIL-04_08_2026-GO95HV-1^06240002.0312200 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008351 | 567705864-88361-DETAIL-08_20_2025-GO95HV-1^06246001.0174500 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008352 | 567938860-29270-DETAIL-02_18_2025-SVCROAD-1^06240004.0220403 | OTHER | HFTD Tier 3 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008353 | 567938860-29270-DETAIL-03_24_2026-COVCOTHR-1^06240004.0220403 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008354 | 56806106-66106-DRONE_HY-06_19_2026-COVCOTHR-1^06239004.0251702 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008355 | 56806106-66106-DRONE_HY-06_19_2026-COVCOTHR-2^06239004.0251702 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008356 | 56806106-66106-DRONE_HY-06_19_2026-COVCOTHR-3^06239004.0251702 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008357 | 568100098-94629-AUDIT-03_17_2026-SVCENTCO-1^06243009.0322300 | OTHER | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008358 | 56829986-57842-ADMIN-11_10_2025-SVCDEFLC-1^06246011.0065402 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008359 | 568567525-93849-DTLSB-07_10_2025-GO95HV-1^06244007.0110801 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008360 | 568791903-68680-DETAIL-02_17_2026-GO95HV-1^06239002.0040101 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008361 | 568986314-33879-DETAIL-09_22_2025-GO95MLD-1^06147001.0238503 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008362 | 569067811-76233-DETAIL-05_12_2025-GO95HV-1^06243006.0162401 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008363 | 569235884-23659-DETAIL-07_28_2025-GO95HV-1^06247005.0301500 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008364 | 569312843-4862-DTLSB-06_30_2025-GO95HV-1^06244007.0105140 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008365 | 56956326-83989-DETAIL-07_29_2025-GO95HV-1^06247005.0315900 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008366 | 569796405-43340-DTLSB-07_24_2025-GO95HV-1^07218001.0265803 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008367 | 56988609-49609-DETAIL-08_19_2025-GO95HV-1^06247006.0365201 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008368 | 570070893-23280-DETAIL-02_11_2025-GO95MLD-1^06240004.0356100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008369 | 570126645-74600-DETAIL-04_08_2026-GO95HV-1^06240002.0321301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008370 | 570177923-62680-DETAIL-02_24_2026-GO95HV-1^06239002.0225100 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008371 | 570215051-25171-DETAIL-09_29_2025-GO95HV-1^06148001.0310906 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008372 | 570215051-25171-DETAIL-09_29_2025-SVCROAD-1^06148001.0310906 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008373 | 570279628-97440-DETAIL-03_05_2026-COVCOTHR-2^06238004.0146800 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008374 | 570320744-80699-DTLSB-01_28_2026-GO95MLD-1^06242009.0058702 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008375 | 570985558-63459-DETAIL-06_03_2024-CUSTWIRE-1^06246005.0315600 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008376 | 571289458-20558-DETAIL-06_04_2025-GO95MLD-1^668075/00 6/024 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008377 | 571546106-99271-DETAIL-08_06_2025-GO95HV-1^06246002.0039400 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008378 | 571574901-69599-DETAIL-10_02_2025-GO95HV-1^06148001.0305301 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008379 | 571953354-671-ADMIN-11_06_2025-GO95HV-1^06246001.0121100 | OTHER | Non-HFTD | Distribution | 2025-11-06 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008380 | 572057839-20771-DETAIL-08_18_2025-GO95HV-1^06246002.0264403 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008381 | 572287601-47809-DETAIL-10_02_2025-GO95MLD-1^06246008.0063200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008382 | 572338691-29691-ADMIN-10_22_2025-GO95HV-1^06246011.0067201 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008383 | 572345654-90139-DETAIL-04_23_2026-GUYNOINS-1^06142012.0144305 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008384 | 572530542-37430-DTLSB-08_11_2025-GO95MLD-1^07218001.0279900 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008385 | 572781111-20271-DTLSB-03_29_2022-POLETOP-1^06144006.0105400 | POLE | Non-HFTD | Distribution | 2022-03-29 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008386 | 573151815-76471-DETAIL-08_20_2025-GO95HV-1^06246001.0173301 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008387 | 573163663-2860-DETAIL-02_02_2026-SVCROAD-1^06239002.0062600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-02 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008388 | 57331895-66839-DETAIL-05_06_2025-GO95HV-1^06243006.0037800 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008389 | 57335688-22550-DETAIL-04_22_2025-GO95HV-1^06240003.0053202 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008390 | 573510881-59070-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008391 | 573510881-90302-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008392 | 573801043-90729-DTLSB-01_21_2026-GO95HV-1^06242009.0298109 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008393 | 573815904-98832-DETAIL-10_15_2025-GO95BLTC-1^06246012.0133901 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008394 | 573815904-98832-DETAIL-10_15_2025-SVCROAD-1^06246012.0133901 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008395 | 573838913-4619-DTLSB-04_23_2026-BIRDDMG-1^06241009.0221400 | POLE | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008396 | 574100731-78963-DTLSB-04_29_2024-CUSTWIRE-1^06245007.0222442 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008397 | 574388489-10330-DETAIL-03_17_2026-COVCOTHR-1^06240004.0218906 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008398 | 574388489-10330-DETAIL-03_17_2026-COVCOTHR-4^06240004.0218906 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008399 | 574396121-8180-DETAIL-02_16_2026-GO95HV-1^06239001.0057700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008400 | 574492459-27610-DETAIL-02_20_2025-SVCDEFLC-1^06241005.0261200 | OTHER | HFTD Tier 3 | Distribution | 2025-02-20 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008401 | 574580153-28771-ADMIN-11_14_2025-CUSTWIRE-1^06246001.0123904 | OTHER | Non-HFTD | Distribution | 2025-11-14 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008402 | 575026769-85489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0204800 | POLE | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008403 | 575257121-48099-DETAIL-08_14_2025-GO95HV-1^06246001.0310402 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008404 | 575396879-34271-DETAIL-09_08_2025-GO95HV-1^06147001.0321301 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008405 | 57554861-94239-DETAIL-05_19_2025-GO95HV-1^06243006.0228600 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008406 | 575868953-19953-DETAIL-06_17_2025-GUYHINS-1^668075/00 21/042 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008407 | 575965741-49169-DTLSB-07_25_2023-CUSTWIRE-1^06243010.0025500 | OTHER | HFTD Tier 2 | Distribution | 2023-07-25 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008408 | 576150512-18459-DTLTRT-04_29_2026-GO95HV-1^668004/00 10/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008409 | 576150512-18460-DTLTRT-04_29_2026-GO95HV-1^668004/00 10/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008410 | 576328465-9163-DETAIL-07_30_2025-GO95HV-1^06247005.0319700 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008411 | 576354253-37009-DETAIL-07_31_2025-GO95HV-1^06247006.0209200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008412 | 577116236-74199-ADMIN-11_10_2025-GO95BLTC-1^06246011.0060000 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008413 | 57731046-59560-ADMIN-10_29_2025-DISTHDWR-1^06246001.0035001 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-10-29 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008414 | 577961970-70880-DETAIL-01_22_2026-BIRDDMG-1^06239003.0071906 | POLE | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008415 | 578145090-88281-DETAIL-08_21_2025-GO95HV-1^06246001.0305700 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008416 | 578214185-86839-DETAIL-05_06_2025-GO95HV-1^06243006.0037801 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008417 | 578383525-36529-DETAIL-04_25_2022-CUSTWIRE-1^06143012.0255004 | OTHER | Non-HFTD | Distribution | 2022-04-25 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008418 | 578384299-62190-DETAIL-01_15_2025-GO95HV-1^06239004.0256103 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008419 | 578685574-59190-DETAIL-02_12_2026-GO95HV-1^06239003.0362800 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008420 | 578914702-98999-DETAIL-03_21_2024-COPLLEAN-1^06147004.0366400 | POLE | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008421 | 578914702-98999-DETAIL-03_21_2024-GO95HV-1^06147004.0366400 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008422 | 57902966-21760-DETAIL-08_11_2025-DISTHDWR-1^06246002.0097003 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008423 | 57902966-21760-DETAIL-08_11_2025-SVCENTCO-1^06246002.0097003 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008424 | 57916743-16780-DETAIL-02_24_2026-BIRDDMG-1^06239002.0225200 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008425 | 57916743-16780-DETAIL-02_24_2026-GO95HV-1^06239002.0225200 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008426 | 57956145-38145-DTLSB-05_28_2026-GO95HV-1^07216001.0023100 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008427 | 580138634-27219-DTLSB-01_27_2026-BIRDDMG-1^06242009.0057302 | POLE | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008428 | 580160871-43830-DETAIL-03_26_2026-ABNDEQPM-1^06240004.0204703 | OTHER | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008429 | 580232493-93981-DTLSB-02_07_2023-CUSTWIRE-1^06248001.0156300 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008430 | 580293903-21299-DETAIL-05_30_2025-GUYHINS-1^06244006.0143600 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-30 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008431 | 580436335-78335-DETAIL-05_29_2025-GO95HV-1^06147014.0120200 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008432 | 580783573-34481-DETAIL-09_05_2025-GO95HV-1^06147001.0203800 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008433 | 580862514-6481-DETAIL-09_08_2025-DISTHDWR-1^06147001.0330400 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-09-08 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008434 | 581063233-61350-DETAIL-01_14_2026-SVCTREE-1^06239004.0134144 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008435 | 581076928-83750-DETAIL-02_25_2026-GO95HV-1^06239003.0139101 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008436 | 58142814-20830-DTLSB-07_23_2025-SVCDEFLC-1^07218001.0264902 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008437 | 581676188-16099-ADMIN-10_23_2025-GO95HV-1^06246011.0364002 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008438 | 581836469-38152-ADMIN-12_29_2025-COVCOTHR-1^06241005.0027242 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-12-29 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008439 | 581836469-38152-ADMIN-12_29_2025-COVCOTHR-3^06241005.0027242 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-12-29 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008440 | 581925013-57149-DETAIL-05_30_2025-GO95HV-1^06244006.0146500 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008441 | 582001409-52633-DETAIL-09_08_2025-GO95HV-1^07218001.0179303 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008442 | 582391963-4550-DETAIL-02_04_2025-GO95MLD-1^06239004.0245902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008443 | 582560853-68239-DETAIL-11_17_2025-GO95HV-1^06243007.0019501 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008444 | 583406426-43410-DETAIL-01_30_2025-GUYHINS-1^06240004.0163609 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008445 | 583469321-15719-ADMIN-03_25_2025-POLEDERP-1^668002/00 11/072 | POLE | HFTD Tier 2 | Transmission | 2025-03-25 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008446 | 583495309-71890-DETAIL-01_12_2026-SVCTREE-1^06239004.0244300 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008447 | 583627164-31264-DTLTRT-08_07_2025-GO95HV-1^668087/00 11/028 | OTHER | Non-HFTD | Transmission | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008448 | 583627164-31264-DTLTRT-08_07_2025-GUYNOINS-2^668087/00 11/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-07 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008449 | 583646611-88699-DETAIL-01_15_2026-GO95TCH-1^06239004.0135105 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008450 | 584001199-12659-ADMIN-03_06_2026-POLEREPL-1^06247005.0207901 | POLE | Non-HFTD | Distribution | 2026-03-06 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008451 | 584090253-74529-DETAIL-04_20_2026-GO95MLD-1^06142012.0146907 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008452 | 584090253-74529-DETAIL-04_20_2026-SVCDEFLC-1^06142012.0146907 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008453 | 584244998-51873-DETAIL-09_17_2025-GO95HV-1^06248007.0367300 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008454 | 584292723-159-DETAIL-08_19_2025-DISTHDWR-1^06247006.0369402 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008455 | 584292723-159-DETAIL-08_19_2025-GO95HV-1^06247006.0369402 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008456 | 584329142-10330-DTLSB-08_13_2025-GRDRODHI-1^07218001.0289500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008457 | 584482933-48950-DETAIL-01_23_2025-GO95MLD-1^06239004.0256801 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008458 | 584588073-92680-DETAIL-02_13_2025-SVCROAD-1^06240004.0169102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008459 | 58463668-37470-DTLTRT-07_01_2025-GO95HV-1^668087/00 2/016 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008460 | 584722204-82069-DETAIL-09_15_2025-GO95HV-1^06248007.0264701 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008461 | 584820331-52138-DTLSB-08_14_2025-POLEREPL-1^07218001.0289201 | POLE | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008462 | 585442554-47009-ADMIN-09_20_2024-POLEREPL-1^06245007.0224706 | POLE | Non-HFTD | Distribution | 2024-09-20 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008463 | 586028101-6979-DETAIL-10_01_2025-GO95HV-1^06148001.0303101 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008464 | 586028101-6979-DETAIL-10_01_2025-SVCROAD-1^06148001.0303101 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008465 | 586080006-25776-DETAIL-09_27_2021-CUSTWIRE-3^06148004.0356112 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008466 | 586122309-83749-DTLSB-07_21_2025-GO95HV-1^06244006.0302500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008467 | 586211649-86591-DTLTRT-07_08_2025-BIRDDMG-1^668087/00 6/026 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008468 | 586303356-31200-DETAIL-03_31_2025-GO95HV-1^06239003.0017606 | OTHER | Non-HFTD | Distribution | 2025-03-31 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008469 | 58649598-3670-DTLSB-05_05_2026-GO95HV-1^06142013.0152101 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008470 | 586656400-79440-DETAIL-04_01_2026-BIRDDMG-1^06237005.0261300 | POLE | HFTD Tier 2 | Distribution | 2026-04-01 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008471 | 587033290-4699-DTLSB-07_07_2025-GO95HV-1^06244007.0134800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008472 | 587253983-66380-DETAIL-01_30_2025-GO95TCH-1^06240004.0163500 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008473 | 587377753-73670-DTLTRT-09_26_2023-GO95STUB-1^668010/00 13/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-26 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008474 | 587456676-45689-DETAIL-08_12_2025-GO95HV-1^06247006.0250200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008475 | 587484799-60979-DETAIL-07_28_2025-GO95HV-1^06247005.0198401 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008476 | 587806726-88470-DETAIL-01_24_2025-GO95HV-1^06239004.0257841 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008477 | 588043940-25679-DETAIL-08_07_2025-GO95HV-1^06246001.0305901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008478 | 588097681-97119-ADMIN-11_13_2025-GO95BLTC-1^06246010.0133800 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008479 | 58819498-77699-DETAIL-07_31_2025-BIRDDMG-1^06247005.0264003 | POLE | Non-HFTD | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008480 | 588384706-4759-DETAIL-04_30_2026-GO95HV-1^668004/00 9/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008481 | 588384706-4760-DETAIL-04_30_2026-GO95HV-1^668004/00 9/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008482 | 58855719-52199-DETAIL-04_21_2025-GO95HV-1^06242006.0037810 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008483 | 588694686-24199-DETAIL-06_05_2025-GUYHINS-1^06245007.0249601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008484 | 588772003-91950-DETAIL-01_30_2025-GO95HV-1^06239004.0131000 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008485 | 588772003-91950-DETAIL-01_30_2025-GO95MLD-1^06239004.0131000 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008486 | 589289649-75479-DETAIL-09_09_2025-GO95MLD-1^06246007.0141150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008487 | 589443397-81298-DTLSB-06_16_2026-GO95HV-1^07217001.0356303 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008488 | 589542938-47250-DETAIL-02_24_2026-GO95BLTC-1^06239003.0132301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008489 | 589620643-97820-DETAIL-01_21_2026-SVCTREE-2^06240004.0289303 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008490 | 589686912-74879-DETAIL-07_30_2025-ENCHRW-1^06247005.0179810 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008491 | 589686912-74879-DETAIL-07_30_2025-GO95HV-1^06247005.0179810 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008492 | 59020704-80659-DETAIL-07_28_2025-GO95HV-1^06247005.0302300 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008493 | 590237443-70639-DETAIL-05_29_2025-GO95HV-1^06244006.0106301 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008494 | 590352471-20050-DETAIL-04_10_2025-BIRDDMG-1^06239003.0183800 | POLE | HFTD Tier 3 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008495 | 590370553-4529-DTLSB-03_11_2026-DISTHDWR-1^06243009.0345200 | CONNECTION DEVICE | Non-HFTD | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008496 | 590370553-4529-DTLSB-03_11_2026-GO95HV-1^06243009.0345200 | OTHER | Non-HFTD | Distribution | 2026-03-11 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008497 | 590789734-78362-DETAIL-04_16_2025-SVCROAD-1^06242005.0362240 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008498 | 591023834-57699-DETAIL-05_28_2025-GO95HV-1^06244006.0092002 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008499 | 591198803-44249-DTLSB-07_21_2025-GO95HV-1^06244006.0256900 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008500 | 591344835-38508-DTLSB-07_03_2025-GO95HV-1^06245007.0358701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008501 | 591529516-50483-DETAIL-06_04_2025-GO95HV-1^06245006.0287940 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008502 | 591682719-51359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0334601 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008503 | 592035033-87539-DETAIL-05_29_2025-GO95HV-1^06244006.0109000 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008504 | 592383831-15783-DTLSB-06_09_2026-BIRDDMG-1^07216001.0230401 | POLE | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008505 | 592549765-67059-DTLSB-06_09_2026-GO95HV-1^07216001.0228600 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008506 | 592549765-67059-DTLSB-06_09_2026-GO95MLD-1^07216001.0228600 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008507 | 592638959-57589-DTLSB-05_18_2026-GO95HV-1^06242009.0288600 | OTHER | Non-HFTD | Distribution | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008508 | 592796884-31609-DETAIL-08_28_2025-GO95HV-1^06247006.0185001 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008509 | 592966124-14183-DETAIL-09_11_2025-GO95HV-1^06248007.0152001 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008510 | 593081421-28259-DTLSB-07_07_2025-GO95HV-1^06245007.0351203 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008511 | 593123109-7249-ADMIN-02_19_2025-POLEREPL-1^06245007.0219701 | POLE | Non-HFTD | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008512 | 593748959-84829-DTLSB-02_16_2026-GO95HV-1^06243009.0308902 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008513 | 594091063-8883-DETAIL-09_17_2025-GO95HV-1^07218001.0087001 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008514 | 594091063-8883-DETAIL-09_17_2025-GO95MLD-1^07218001.0087001 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008515 | 594208476-86659-DTLSB-08_18_2025-GO95MLD-1^07218001.0354040 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008516 | 594375844-11369-DETAIL-09_11_2025-GO95HV-1^06248007.0223601 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008517 | 594512348-39252-DTLSB-07_21_2025-GO95HV-1^06244006.0304302 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008518 | 594695593-58380-DETAIL-02_18_2026-BIRDDMG-1^06239002.0169402 | POLE | HFTD Tier 2 | Distribution | 2026-02-18 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008519 | 594748129-86001-ADMIN-07_08_2025-POLEDERP-1^668087/00 9/006 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008520 | 594764193-16889-DETAIL-06_17_2025-GO95HV-1^06248004.0332904 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008521 | 594822008-42149-DETAIL-06_05_2025-ABNDEQPM-1^06245006.0307800 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008522 | 59495134-47339-DETAIL-10_06_2025-GO95HV-1^06243007.0365600 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008523 | 595043576-94576-DETAIL-05_29_2025-GO95HV-1^06148014.0360500 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008524 | 595050419-60739-DETAIL-06_24_2025-GO95HV-1^668087/00 9/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008525 | 595050419-60739-DETAIL-06_24_2025-GUYHINS-2^668087/00 9/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008526 | 595851386-17989-DETAIL-08_07_2025-GO95HV-1^06246002.0234300 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008527 | 596185108-66859-DTLTRT-05_04_2026-GRDRODHI-1^668004/00 4/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008528 | 596185108-66860-DTLTRT-05_04_2026-GO95HV-1^668004/00 4/020 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008529 | 596192966-39513-DETAIL-02_04_2025-GO95HV-1^06239004.0135046 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008530 | 596268700-58339-DTLTRT-05_14_2026-GO95HV-1^668086/00 5/005 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008531 | 596370302-16650-DETAIL-03_02_2026-COVCOTHR-1^06238004.0027102 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008532 | 596610503-24829-DETAIL-04_20_2026-GO95HV-1^06142012.0145901 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008533 | 596614043-84898-DTLTRT-05_07_2026-GO95HV-1^668004/00 10/025 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008534 | 596633788-15401-DTLTRT-06_24_2025-CLRTOUCH-1^668087/00 15/003 | CONDUCTOR | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008535 | 596883106-24261-DETAIL-02_19_2025-GO95MLD-1^06239004.0365600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008536 | 596979273-52680-DETAIL-02_17_2026-GO95HV-1^06239002.0059700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008537 | 596983462-27039-DETAIL-05_20_2025-GO95HV-1^06243006.0075201 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008538 | 597195339-82441-DETAIL-04_03_2025-GO95CL10-1^06241005.0089004 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008539 | 597195339-82441-DETAIL-04_03_2025-GO95MLD-1^06241005.0089004 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008540 | 597640475-82475-DETAIL-06_05_2025-GO95HV-1^06148014.0237600 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008541 | 597777504-39504-DETAIL-09_02_2021-CUSTWIRE-1^06148004.0347241 | OTHER | Non-HFTD | Distribution | 2021-09-02 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008542 | 59785808-20559-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0311500 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008543 | 598136084-81009-DETAIL-08_13_2025-GO95HV-1^06247006.0255401 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008544 | 598341223-42799-DETAIL-05_28_2025-CUSTWIRE-1^06244006.0103900 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008545 | 598579031-53080-DETAIL-02_18_2026-GO95HV-1^06239002.0041301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008546 | 598658717-15983-DTLSB-04_22_2024-CUSTWIRE-1^06245007.0227247 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008547 | 598685709-8509-DETAIL-09_29_2025-GO95MLD-1^06246009.0137200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008548 | 599459096-27759-DETAIL-05_04_2026-GO95HV-1^668004/00 4/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008549 | 599459096-27760-DETAIL-05_04_2026-GO95HV-1^668004/00 4/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008550 | 599471602-37559-DETAIL-04_29_2026-GO95HV-1^668004/00 7/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008551 | 599471602-37560-DETAIL-04_29_2026-GO95HV-1^668004/00 7/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008552 | 599612618-62291-DTLTRT-05_05_2026-BIRDDMG-1^668038/00 2/061 | POLE | HFTD Tier 2 | Transmission | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008553 | 599612618-62291-DTLTRT-05_05_2026-GO95HV-1^668038/00 2/061 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008554 | 599612618-73911-DTLTRT-05_05_2026-BIRDDMG-1^668038/00 2/061 | POLE | HFTD Tier 2 | Transmission | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008555 | 599612618-73911-DTLTRT-05_05_2026-GO95HV-1^668038/00 2/061 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008556 | 599665842-80088-DETAIL-11_17_2025-GO95CLMP-1^06243007.0024900 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2026-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008557 | 600115768-45768-DETAIL-08_13_2025-GO95HV-1^06247006.0253300 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008558 | 600506049-71309-ADMIN-01_23_2024-POLEREPL-1^06147005.0261702 | POLE | Non-HFTD | Distribution | 2024-01-23 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008559 | 60058436-51570-DETAIL-01_23_2025-GO95HV-1^06239004.0256741 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008560 | 60092681-92531-ADMIN-12_29_2025-COVCOTHR-1^06241005.0022100 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-12-29 | 2028-12-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008561 | 600967715-23815-DETAIL-06_05_2025-GO95HV-1^06148014.0245701 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008562 | 600999928-64911-ADMIN-11_10_2025-POLEDERP-1^668087/00 3/017 | POLE | Non-HFTD | Transmission | 2025-11-10 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008563 | 601199450-76443-DETAIL-06_25_2026-SVCNEUT-1^07217001.0118201 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008564 | 601514842-44593-DTLSB-06_10_2026-CLRTOUCH-1^07217001.0350000 | CONDUCTOR | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008565 | 601806061-80359-DTLSB-07_07_2025-GO95HV-1^06245007.0352304 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008566 | 601836109-48713-DETAIL-06_04_2024-CUSTWIRE-1^06246005.0336100 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008567 | 602275461-8039-DTLTRT-07_09_2025-GO95HV-1^668087/00 10/025 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008568 | 60248896-63270-DETAIL-08_04_2025-GO95HV-1^06246001.0185200 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008569 | 602523968-88629-DETAIL-04_22_2026-GO95HV-1^06142012.0143600 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008570 | 602654521-17859-DETAIL-06_05_2024-CUSTWIRE-1^06246006.0267501 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008571 | 602757874-56350-DTLTRT-11_03_2023-BIRDDMG-1^668010/00 15/036 | POLE | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008572 | 603066113-84799-DETAIL-05_28_2025-GO95HV-1^06244006.0090900 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008573 | 60317101-42370-DTLTRT-05_19_2026-GO95HV-1^668086/00 2/010 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008574 | 603562012-44789-DTLSB-07_16_2025-GO95HV-1^06244006.0233101 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008575 | 603726938-28191-DTLTRT-05_06_2026-GO95MLD-1^668038/00 2/059 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008576 | 603951966-50811-DETAIL-05_11_2026-GO95HV-1^668038/00 4/051 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008577 | 604108903-54811-ADMIN-06_24_2024-POLEDERP-1^07216001.0210801 | POLE | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008578 | 605027756-18811-DTLSB-07_29_2025-SVCDEFLC-1^07218001.0265503 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008579 | 605143591-72709-DTLSB-08_26_2024-CUSTWIRE-1^06245007.0111800 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008580 | 605265646-47589-DETAIL-06_09_2025-GO95HV-1^06245006.0190501 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008581 | 605436480-38121-DTLTRT-05_14_2026-BIRDDMG-1^668086/00 15/005 | POLE | Non-HFTD | Transmission | 2026-05-14 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008582 | 605436480-38121-DTLTRT-05_14_2026-GO95HV-1^668086/00 15/005 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008583 | 605604389-62759-DETAIL-09_04_2025-GO95MLD-1^07216001.0099302 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008584 | 605692512-38560-DETAIL-04_29_2026-GO95HV-1^668004/00 9/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008585 | 605868539-18373-DETAIL-09_22_2025-GO95HV-1^06248007.0242401 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008586 | 606482923-91121-DETAIL-04_21_2026-GO95HV-1^06142012.0149908 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008587 | 606535698-92502-DETAIL-03_06_2025-GUYHINS-1^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008588 | 606535698-92502-DETAIL-03_06_2025-GUYHINS-2^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008589 | 606535698-92502-DETAIL-03_06_2025-GUYNOINS-1^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008590 | 606686036-77149-DETAIL-02_28_2024-GO95HV-1^07113002.0180500 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008591 | 606736462-89049-DTLSB-07_16_2025-GO95HV-1^06244006.0233000 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008592 | 607024298-56913-DETAIL-08_26_2025-GO95HV-1^06247006.0285702 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008593 | 607086574-8010-DETAIL-03_13_2025-GO95HV-1^06238004.0156241 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008594 | 607408266-38321-DETAIL-08_06_2025-GO95HV-1^06246002.0106701 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008595 | 60782934-53890-DETAIL-02_03_2026-SVCTREE-1^06239003.0018512 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008596 | 60786219-16282-DTLTRT-07_02_2025-BIRDDMG-1^668087/00 2/020 | POLE | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008597 | 60786219-16282-DTLTRT-07_02_2025-GUYNOINS-2^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008598 | 60786219-30770-DTLTRT-07_02_2025-BIRDDMG-1^668087/00 2/020 | POLE | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008599 | 60786219-30770-DTLTRT-07_02_2025-GUYNOINS-1^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008600 | 60786219-30770-DTLTRT-07_02_2025-GUYNOINS-2^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008601 | 60786219-30770-DTLTRT-07_02_2025-GUYNOINS-3^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008602 | 60786219-96282-DTLTRT-07_02_2025-GUYNOINS-1^668087/00 2/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008603 | 608035931-88621-DETAIL-04_09_2024-GO95MLD-1^06147005.0255000 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008604 | 608173096-37209-ADMIN-03_06_2026-POLEREPL-1^06247006.0265000 | POLE | Non-HFTD | Distribution | 2026-03-06 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008605 | 608862088-56199-DETAIL-05_15_2025-GO95HV-1^06243006.0097502 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008606 | 608942559-70729-DETAIL-04_28_2022-CUSTWIRE-1^06143012.0246700 | OTHER | Non-HFTD | Distribution | 2022-04-28 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008607 | 609498452-87050-DETAIL-02_05_2026-SVCENTCO-1^06239003.0018340 | OTHER | Non-HFTD | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008608 | 609732603-56921-DETAIL-05_15_2024-GO95MLD-1^06142012.0124600 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008609 | 61004014-94740-DETAIL-03_17_2026-COVCOTHR-1^06240004.0217902 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008610 | 61004014-94740-DETAIL-03_17_2026-COVCOTHR-2^06240004.0217902 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008611 | 61015459-16739-DTLTRT-06_25_2025-GO95HV-1^668087/00 18/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008612 | 610178242-82850-DETAIL-02_03_2026-GO95BLTC-1^06239003.0018405 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008613 | 610340845-13179-DETAIL-04_28_2025-GO95HV-1^06242007.0251800 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008614 | 610689383-99483-DETAIL-03_23_2023-CUSTWIRE-1^06142016.0081940 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008615 | 610763123-92680-DETAIL-02_24_2026-GO95HV-1^06239002.0223001 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008616 | 610847208-25201-DETAIL-09_16_2025-GO95MLD-1^07218001.0054900 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008617 | 610908588-65821-DETAIL-08_13_2025-DISTHDWR-1^06246002.0359100 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008618 | 610947681-24050-DRONE_HY-06_19_2026-XARMBRAC-1^06238004.0272740 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008619 | 611133505-41479-DETAIL-08_20_2025-GO95HV-1^06246001.0173403 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008620 | 611391723-25723-DETAIL-06_05_2025-SVCENTCO-1^06245006.0190602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008621 | 611741618-28059-DETAIL-04_03_2024-CUSTWIRE-1^06247005.0287100 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008622 | 611873683-11399-DTLSB-04_20_2026-GO95HV-1^06241009.0120900 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008623 | 612453704-67940-DTLTRT-06_04_2025-GO95HV-1^668075/00 15/010 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008624 | 612526483-68280-DETAIL-02_23_2026-GO95HV-1^06239002.0225701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008625 | 612609439-11821-DETAIL-09_04_2025-GO95HV-1^06146001.0050202 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008626 | 61265233-85233-DETAIL-06_11_2025-GUYHINS-3^668075/00 5/036 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008627 | 612811891-19069-DTLTRT-05_12_2026-GO95HV-1^668004/00 6/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008628 | 612865819-86052-DTLSB-07_15_2025-GO95HV-1^06244006.0314440 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008629 | 613089761-51861-DETAIL-05_22_2026-SVCROAD-1^07217001.0142504 | OTHER | Non-HFTD | Distribution | 2026-05-22 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008630 | 613502642-97253-DETAIL-07_22_2025-GO95HV-1^06247005.0175400 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008631 | 613506988-76988-DETAIL-06_18_2025-GO95HV-1^668075/00 13/048 | OTHER | HFTD Tier 2 | Transmission | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008632 | 613663734-74734-DTLSB-05_07_2026-GO95MLD-1^06142013.0180200 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008633 | 613750749-63421-DETAIL-04_24_2024-INSULDMG-1^06145001.0055100 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008634 | 61385156-89680-DETAIL-01_30_2025-GO95TCH-1^06239004.0245701 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008635 | 614012421-83150-DETAIL-03_11_2025-GO95HV-1^06238004.0272742 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008636 | 614105234-86339-DETAIL-10_06_2025-GO95HV-1^06243007.0367700 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008637 | 614154391-44920-DETAIL-03_30_2026-GRDRODHI-1^06240004.0271004 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008638 | 614163711-73621-DTLTRT-05_19_2026-GO95HV-1^668086/00 3/010 | OTHER | Non-HFTD | Transmission | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008639 | 614493828-5828-DETAIL-03_23_2023-CUSTWIRE-1^06142016.0081802 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008640 | 614590804-82379-DTLSB-04_23_2026-SVCTREE-1^06241009.0221900 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008641 | 614595529-35059-DETAIL-08_25_2025-ANCHIDLE-1^07216001.0179807 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008642 | 614700661-78721-DTLTRT-05_20_2026-GO95HV-1^668086/00 13/010 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008643 | 614830535-23040-DTLSB-07_24_2025-GO95HV-1^07218001.0265800 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008644 | 614876809-1699-DETAIL-07_31_2025-GO95HV-1^06247006.0200802 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008645 | 615340950-23739-DTLSB-07_22_2025-GO95HV-1^06244006.0181201 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008646 | 615407673-54850-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0134002 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008647 | 615407673-54850-DETAIL-01_14_2026-SVCTREE-1^06239004.0134002 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008648 | 615534787-40479-DETAIL-08_11_2025-CLRTOUCH-1^06246002.0168800 | CONDUCTOR | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008649 | 615681951-32951-DETAIL-07_06_2026-SVCENTBK-1^07217001.0031701 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008650 | 615896420-87531-DTLTRT-05_14_2026-GO95HV-1^668086/00 8/005 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008651 | 61592153-96539-DTLSB-07_29_2025-GO95HV-1^07218001.0264702 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008652 | 616091307-16858-DTLSB-07_31_2025-GO95MLD-1^07218001.0264402 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008653 | 616239837-72218-DETAIL-07_24_2025-GO95HV-1^06247005.0137500 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008654 | 616243056-22831-DETAIL-05_07_2026-GO95HV-1^668038/00 1/055 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008655 | 616243056-63591-DETAIL-05_07_2026-GO95HV-1^668038/00 1/055 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008656 | 616275813-13831-DETAIL-09_29_2025-GO95HV-1^06148001.0310502 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008657 | 616275813-13831-DETAIL-09_29_2025-GUYHINS-1^06148001.0310502 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008658 | 616275813-13831-DETAIL-09_29_2025-GUYHINS-2^06148001.0310502 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008659 | 616275813-13831-DETAIL-09_29_2025-GUYHINS-3^06148001.0310502 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008660 | 616408321-26831-DETAIL-09_29_2025-GO95HV-1^06148001.0313500 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008661 | 61660041-83470-DETAIL-09_10_2025-GO95HV-1^06147001.0074102 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008662 | 61660041-83470-DETAIL-09_10_2025-GUYHINS-1^06147001.0074102 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008663 | 616809340-94559-DETAIL-08_06_2025-GO95HV-1^06247005.0205100 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008664 | 617045829-92713-DETAIL-08_26_2025-GO95HV-1^06247006.0285600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008665 | 617079709-67331-DETAIL-09_08_2025-GO95HV-1^06147001.0329100 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008666 | 617310567-60531-ADMIN-11_10_2025-GO95BLTC-1^06246001.0252400 | OTHER | Non-HFTD | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008667 | 617344333-72983-DETAIL-08_19_2025-GO95HV-1^06247006.0366802 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008668 | 617416538-92770-DETAIL-06_25_2026-GO95HV-1^07217001.0039200 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008669 | 617447354-80039-AUDIT-05_27_2026-GUYHINS-1^668086/00 2/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008670 | 61767581-25039-DTLTRT-05_18_2026-SVCENTCO-1^668086/00 11/011 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008671 | 617726960-1131-ADMIN-10_27_2025-GO95HV-1^06246001.0114902 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008672 | 617985908-14331-DTLTRT-06_23_2025-GUYHINS-1^668087/00 16/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008673 | 618327835-44599-DETAIL-06_18_2025-GO95HV-1^06248004.0284201 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008674 | 618364939-30589-DETAIL-09_17_2025-GO95HV-1^06248007.0241400 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008675 | 618364939-30589-DETAIL-09_17_2025-SVCDEFLC-1^06248007.0241400 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008676 | 618364939-30589-DETAIL-09_17_2025-SVCDEFLC-2^06248007.0241400 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008677 | 618364939-30589-DETAIL-09_17_2025-SVCENTCO-1^06248007.0241400 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008678 | 618790275-999-DETAIL-09_09_2025-GO95HV-1^06246007.0225951 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008679 | 618917609-74489-DTLSB-05_12_2026-GO95HV-1^06242009.0281216 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008680 | 619223670-79709-DTLSB-07_23_2024-CUSTWIRE-1^06245007.0106400 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008681 | 619497805-38805-DETAIL-06_24_2025-GO95HV-1^06248004.0318907 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008682 | 619774665-1559-DETAIL-06_18_2025-GO95HV-1^06248004.0287201 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008683 | 620110498-40331-DETAIL-08_25_2025-GO95HV-1^06246001.0204604 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008684 | 620205996-64849-DTLSB-07_10_2025-GO95HV-1^06244007.0113001 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008685 | 62117331-98331-ADMIN-10_23_2025-GO95MLD-1^07117002.0212004 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008686 | 621202164-31883-DETAIL-09_18_2025-SVCNEUT-1^07218001.0087502 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008687 | 621320576-2576-DETAIL-09_24_2025-GO95HV-1^07218001.0234003 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008688 | 621460761-57769-DRONE_HY-06_19_2026-GUYSLACK-1^668002/00 6/063 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008689 | 621460761-57769-DRONE_HY-06_19_2026-INSULDMG-1^668002/00 6/063 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008690 | 621622500-8229-DETAIL-04_22_2026-GO95HV-1^06142012.0142403 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008691 | 621633759-44349-DTLSB-07_14_2025-GO95HV-1^06244006.0289602 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008692 | 622420436-36008-DETAIL-03_10_2026-SVCDEFLC-1^06238004.0029603 | OTHER | HFTD Tier 2 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008693 | 622563484-56840-DETAIL-03_25_2026-BIRDDMG-1^06240004.0218706 | POLE | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008694 | 622563484-56840-DETAIL-03_25_2026-GUYHINS-1^06240004.0218706 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008695 | 622564691-1131-DTLSB-06_02_2026-CUSTWIRE-1^07216001.0028100 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008696 | 622575944-14649-DETAIL-10_22_2024-GO95MLD-1^07216001.0208100 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008697 | 622575944-14649-DETAIL-10_22_2024-GUYHINS-1^07216001.0208100 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008698 | 622575944-14649-DETAIL-10_22_2024-GUYHINS-2^07216001.0208100 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008699 | 622778365-96151-DETAIL-04_14_2025-SVCROAD-1^06241005.0012502 | OTHER | HFTD Tier 2 | Distribution | 2025-04-14 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008700 | 622785331-95080-DETAIL-04_17_2023-GO95BLTC-1^06240004.0165643 | OTHER | HFTD Tier 2 | Distribution | 2023-04-17 | 2028-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008701 | 623061920-21234-DETAIL-04_27_2026-SVCROAD-1^06142012.0145903 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008702 | 62308650-14369-DTLTRT-06_15_2021-GO95HV-1^668041/00 15/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008703 | 623221170-84939-DETAIL-06_12_2024-CUSTWIRE-1^06244005.0249643 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008704 | 623713673-20569-ADMIN-04_06_2026-POLEREPL-1^668067/00 6/008 | POLE | Non-HFTD | Transmission | 2026-04-06 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008705 | 624132986-95842-ADMIN-10_22_2025-GUYHINS-1^06246011.0050500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008706 | 624165884-9253-DETAIL-09_24_2025-GO95HV-1^07218001.0221500 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008707 | 62419133-64580-DETAIL-06_04_2025-GO95HV-1^06142012.0186800 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008708 | 624490016-85441-DTLSB-05_05_2026-GO95HV-1^06142013.0220601 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008709 | 624556709-27709-DETAIL-08_18_2025-BIRDDMG-1^06247006.0362103 | POLE | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008710 | 624574434-49353-DETAIL-09_23_2025-GO95HV-1^07218001.0215000 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008711 | 624590634-65543-ADMIN-09_22_2017-CUSTWIRE-1^668033/00 12/037 | OTHER | HFTD Tier 2 | Transmission | 2017-09-22 | 2020-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008712 | 624685486-80419-DETAIL-11_18_2025-GO95HV-1^06247009.0247502 | OTHER | HFTD Tier 2 | Distribution | 2025-11-18 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008713 | 624921338-49750-DETAIL-04_22_2025-GO95HV-1^06240003.0057700 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008714 | 624989611-25580-DETAIL-02_14_2025-GO95HV-1^06240004.0169343 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008715 | 625392788-3290-DETAIL-02_19_2025-GO95HV-1^06239004.0365505 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008716 | 625514329-19912-ADMIN-10_07_2025-COVCOTHR-1^06242005.0361401 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008717 | 625909036-17949-DTLSB-07_08_2025-GO95MLD-1^06244007.0035803 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008718 | 625990724-65790-DETAIL-03_26_2025-GO95HV-1^06239003.0018511 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008719 | 626013201-46920-DETAIL-03_30_2026-BIRDDMG-1^06240004.0271200 | POLE | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008720 | 626013201-46920-DETAIL-03_30_2026-GO95MLD-1^06240004.0271200 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008721 | 626074198-48069-DETAIL-09_17_2025-GO95HV-1^06248007.0361701 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008722 | 626329684-74709-DETAIL-10_13_2025-GO95HV-1^06246012.0124600 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008723 | 626333329-38549-DTLSB-04_10_2024-SVCWIND-1^06245007.0222007 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008724 | 626346409-67833-AUDIT-07_01_2026-RISEBKSP-1^07217001.0347903 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008725 | 626346409-67833-DTLSB-06_11_2026-SVCNEUT-1^07217001.0347903 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008726 | 626507458-17649-DTLSB-07_16_2025-GO95HV-1^06244006.0290002 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008727 | 62658660-26340-DETAIL-03_12_2026-COVCOTHR-1^06239003.0061300 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-12 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008728 | 626593556-70041-DETAIL-08_04_2025-GO95HV-1^06246002.0139004 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008729 | 626797096-57989-DETAIL-08_07_2025-GO95HV-1^06246002.0234200 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008730 | 626853353-76360-DETAIL-03_17_2025-GO95HV-1^06240003.0369100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008731 | 626962959-6830-DTLTRT-05_27_2025-GO95HV-1^668075/00 16/003 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008732 | 627174035-28541-ADMIN-11_10_2025-GO95HV-1^06246001.0161000 | OTHER | Non-HFTD | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008733 | 627402025-70463-DETAIL-06_25_2026-GO95HV-1^07217001.0038801 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008734 | 627462954-97860-DRONE_HY-07_15_2026-COVCOTHR-2^06239004.0257802 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008735 | 627501141-1839-DTLTRT-06_26_2025-GO95BLTC-1^668087/00 13/008 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008736 | 627563270-85270-DETAIL-02_19_2026-GO95HV-1^06239002.0019600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008737 | 627975603-1941-ADMIN-10_28_2025-DISTHDWR-1^06246001.0129801 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-10-28 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008738 | 62798045-80329-DETAIL-05_19_2025-GO95HV-1^06142012.0016301 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008739 | 628013600-64640-DETAIL-01_20_2026-COVCOTHR-1^06239003.0070604 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008740 | 628264461-3130-DETAIL-03_02_2026-SVCDEFLC-1^06239003.0252701 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008741 | 62830684-50690-DETAIL-02_10_2026-BIRDDMG-1^06239003.0015505 | POLE | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008742 | 628499698-12341-DTLSB-05_05_2026-GO95HV-1^06142013.0152100 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008743 | 628521173-42189-DETAIL-08_20_2025-GUYLOINS-1^06247006.0255803 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008744 | 628608456-58456-DTLSB-06_03_2026-GO95TCH-1^07216001.0114630 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008745 | 628610573-54913-DETAIL-05_08_2025-GO95HV-1^06243006.0104101 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008746 | 628930329-2329-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 14/014 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008747 | 62894315-26032-DETAIL-10_15_2025-GO95BLTC-1^06246012.0131600 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008748 | 629191018-31039-DETAIL-04_22_2026-GO95TCH-1^06142012.0143603 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008749 | 629608898-56241-DETAIL-08_13_2025-GO95HV-1^06246002.0254700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008750 | 629608898-56241-DETAIL-08_13_2025-GRDRODHI-1^06246002.0254700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008751 | 629608898-56241-DETAIL-08_13_2025-GRDRODHI-2^06246002.0254700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008752 | 629627230-96241-DTLSB-05_29_2026-GRDRODHI-1^07216001.0020702 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008753 | 629812839-30859-DETAIL-06_16_2025-GO95HV-1^06248005.0330740 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008754 | 630059700-66901-DETAIL-01_21_2025-GO95HV-1^06239004.0256542 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008755 | 630059700-66901-DETAIL-01_21_2025-GO95TCH-1^06239004.0256542 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008756 | 630191671-32439-DETAIL-05_08_2025-GO95HV-1^06243006.0213500 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008757 | 630513901-21499-DETAIL-10_02_2025-GO95BLTC-1^06246008.0066600 | OTHER | HFTD Tier 2 | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008758 | 630705616-83510-DETAIL-02_26_2026-COVCOTHR-1^06238004.0118301 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008759 | 630705616-83510-DETAIL-02_26_2026-COVCOTHR-4^06238004.0118301 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008760 | 630737641-15639-DETAIL-05_07_2025-GO95HV-1^06243006.0017801 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008761 | 630937391-71439-DTLTRT-06_26_2025-GUYHINS-2^668087/00 2/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008762 | 63095625-86800-DETAIL-02_11_2026-CUSTWIRE-1^06239003.0017405 | OTHER | Non-HFTD | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008763 | 631156149-49333-DETAIL-06_18_2026-CLMBHAZ-1^07217001.0345502 | OTHER | Non-HFTD | Distribution | 2026-06-18 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008764 | 631347203-4250-DETAIL-01_16_2025-GO95HV-1^06239004.0257602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008765 | 631514230-90640-DETAIL-02_06_2025-GO95TCH-1^06239003.0061003 | OTHER | HFTD Tier 3 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008766 | 631514230-90640-DETAIL-02_06_2025-GUYHINS-1^06239003.0061003 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008767 | 631514230-90640-DETAIL-03_10_2026-COVCOTHR-1^06239003.0061003 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008768 | 631562778-83143-ADMIN-03_14_2025-POLEREPL-1^06245007.0220540 | POLE | Non-HFTD | Distribution | 2025-03-14 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008769 | 631985613-92659-DETAIL-03_12_2024-CUSTWIRE-1^06245007.0276906 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008770 | 632726480-9109-DETAIL-05_07_2025-GO95HV-1^06243006.0287500 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008771 | 632823783-39629-DETAIL-05_14_2024-GO95MLD-1^06142012.0122707 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008772 | 633079161-31261-DTLSB-05_05_2026-GO95HV-1^06142013.0175404 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008773 | 633241874-4219-DTLSB-01_27_2026-BIRDDMG-1^06242009.0057102 | POLE | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008774 | 633286451-9380-DETAIL-01_23_2026-GO95MLD-1^06240004.0132100 | OTHER | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008775 | 633326375-8375-DETAIL-07_29_2025-GO95HV-1^06247005.0260201 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008776 | 633350374-122-DETAIL-10_15_2025-SVCENTCO-1^06246011.0181702 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008777 | 633441821-65559-DETAIL-06_18_2025-GO95MLD-1^06248004.0343701 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008778 | 633570386-26559-DTLSB-06_08_2026-SVCDEFLC-1^07216001.0228000 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008779 | 633744813-30499-DTLSB-09_28_2022-CUSTWIRE-1^06243004.0085000 | OTHER | Non-HFTD | Distribution | 2022-09-28 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008780 | 633744813-30499-DTLSB-09_28_2022-GO95HV-1^06243004.0085000 | OTHER | Non-HFTD | Distribution | 2022-09-28 | 2027-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008781 | 634235284-45783-ADMIN-09_17_2025-POLEDERP-1^07218001.0088001 | POLE | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008782 | 634354152-26593-DTLSB-06_24_2026-GUYHINS-1^07217001.0357000 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008783 | 634368634-66309-DETAIL-08_06_2025-GO95HV-1^06247006.0200101 | OTHER | HFTD Tier 2 | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008784 | 634765763-60522-DETAIL-05_30_2025-GO95HV-1^06244006.0142240 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008785 | 63494651-53559-DETAIL-09_18_2025-GO95HV-1^06246006.0013100 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008786 | 63496238-8180-DETAIL-08_25_2025-GO95HV-1^06246001.0202302 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008787 | 634973068-98909-ADMIN-10_23_2025-GO95HV-1^06246011.0360200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008788 | 635275379-81490-DETAIL-01_16_2025-GO95HV-1^06239004.0257404 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008789 | 635469463-75351-DETAIL-06_10_2026-GUYHINS-1^668086/00 2/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008790 | 635469463-75351-DETAIL-06_10_2026-GUYHINS-2^668086/00 2/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008791 | 635469463-75351-DETAIL-06_10_2026-GUYHINS-3^668086/00 2/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008792 | 635629418-26890-DETAIL-01_13_2026-COVCOTHR-1^06239004.0247140 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008793 | 635629418-26890-DETAIL-01_24_2025-GO95HV-1^06239004.0247140 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008794 | 635753630-37851-DTLTRT-04_27_2026-GO95HV-1^668004/00 4/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008795 | 63576853-82499-DTLSB-03_18_2026-GO95HV-1^06242009.0089901 | OTHER | Non-HFTD | Distribution | 2026-03-18 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008796 | 635809659-473-DETAIL-09_22_2025-GO95HV-1^06248007.0242500 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008797 | 635822031-26079-DTLSB-07_07_2025-GO95HV-1^06245007.0351205 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008798 | 635822031-26079-DTLSB-07_07_2025-GRDRODHI-1^06245007.0351205 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008799 | 636064783-75150-DETAIL-01_24_2025-GO95HV-1^06239004.0258601 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008800 | 636234418-13351-ADMIN-11_12_2025-GO95HV-1^06246001.0337001 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008801 | 636298663-48709-DETAIL-09_04_2025-GO95HV-1^06247006.0184901 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008802 | 636387760-48760-DETAIL-08_14_2025-GO95HV-1^06247006.0361500 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008803 | 636505173-25299-DETAIL-10_05_2021-CUSTWIRE-1^06147005.0061201 | OTHER | Non-HFTD | Distribution | 2021-10-05 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008804 | 636906734-52283-DETAIL-07_29_2025-GO95HV-1^06247005.0278100 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008805 | 63698267-47999-DTLSB-10_03_2024-CUSTWIRE-1^06245006.0330600 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008806 | 637274926-77980-DETAIL-01_28_2025-GO95BLTC-1^06240004.0070901 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008807 | 637274926-77980-DETAIL-01_28_2025-GO95HV-1^06240004.0070901 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008808 | 637365170-24779-DETAIL-08_07_2025-GO95HV-1^06246001.0303900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008809 | 637449148-20879-DTLSB-04_15_2026-GRDRODHI-1^06241008.0078500 | OTHER | Non-HFTD | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008810 | 637581746-12746-DETAIL-01_22_2026-GO95MLD-1^06239004.0269802 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008811 | 637630588-75250-DETAIL-02_10_2026-GO95HV-1^06239003.0018306 | OTHER | Non-HFTD | Distribution | 2026-02-10 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008812 | 638105843-89569-DETAIL-03_10_2026-XARMSPCR-1^668041/00 15/025 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008813 | 638318470-21398-DTLTRT-05_21_2026-GO95MLD-1^668086/00 7/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008814 | 638349315-92409-DETAIL-08_21_2025-GO95HV-1^06247006.0264801 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008815 | 638939659-11951-DETAIL-09_30_2025-GO95HV-1^06148001.0300213 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008816 | 63899284-75199-DETAIL-10_13_2025-SVCROAD-1^06246012.0121601 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008817 | 639655502-80550-DETAIL-03_02_2026-SVCROAD-1^06238004.0025102 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008818 | 639655502-80550-DETAIL-03_02_2026-SVCROOF-1^06238004.0025102 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008819 | 639732321-28070-DTLTRT-05_12_2026-GO95HV-1^668004/00 8/008 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008820 | 640194339-59813-DETAIL-08_26_2025-GO95HV-1^06247006.0285100 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008821 | 640218151-29180-DETAIL-02_12_2025-GO95TCH-1^06240004.0167041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008822 | 640311655-37132-DETAIL-07_12_2023-CUSTWIRE-1^06244008.0334200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008823 | 640313657-43970-DETAIL-02_26_2025-SVCNEUT-1^06240004.0061307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008824 | 640563454-85851-DETAIL-06_09_2026-GUYHINS-2^668086/00 10/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008825 | 640563454-85851-DETAIL-06_09_2026-GUYHINS-6^668086/00 10/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008826 | 640743601-98059-ADMIN-10_02_2024-POLEDERP-1^07217001.0266300 | POLE | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008827 | 640983933-66161-DRONE_HY-09_26_2023-GO95HV-1^668033/00 7X1/002 | OTHER | Non-HFTD | Transmission | 2023-09-26 | 2028-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008828 | 641611686-82686-DETAIL-09_04_2025-GO95HV-1^06247006.0216101 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008829 | 642153743-36723-DETAIL-06_18_2025-GO95HV-1^06248004.0337140 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008830 | 642338252-19869-DTLSB-04_08_2026-GO95MLD-1^06241009.0100640 | OTHER | Non-HFTD | Distribution | 2026-04-08 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008831 | 642904491-47661-AUDIT-11_03_2025-CONDFRAY-1^06246001.0120903 | CONDUCTOR | Non-HFTD | Distribution | 2025-11-03 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008832 | 642918229-52240-DETAIL-03_31_2026-GO95HV-1^06237004.0057500 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008833 | 643014766-14343-DETAIL-06_03_2025-GO95HV-1^06245007.0242640 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008834 | 643176442-67183-DETAIL-08_20_2025-CUSTWIRE-1^07216001.0179000 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008835 | 643192364-45364-DTLTRT-07_08_2025-GO95HV-1^668087/00 12/027 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008836 | 643574989-9099-DETAIL-08_05_2025-GO95HV-1^06246002.0144001 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008837 | 64360018-46730-DETAIL-01_22_2026-GO95MLD-1^06240003.0314900 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008838 | 643607468-79049-DETAIL-09_03_2025-GO95HV-1^07216001.0094000 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008839 | 643767711-26580-DETAIL-02_23_2026-GO95HV-1^06239002.0036400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008840 | 643926874-27461-DETAIL-09_02_2025-GO95HV-1^06246001.0176501 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008841 | 644183438-71999-DTLSB-08_22_2024-CUSTWIRE-1^06245006.0323201 | OTHER | HFTD Tier 2 | Distribution | 2024-08-22 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008842 | 644633194-88151-AUDIT-04_22_2025-ABNDEQPM-1^06241005.0131500 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008843 | 64472204-71259-DRONE_HY-06_19_2026-COVCOTHR-1^06240004.0166601 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008844 | 644728536-71889-DETAIL-10_02_2025-GO95HV-1^06247006.0262400 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008845 | 644810711-79861-DETAIL-09_29_2025-GO95HV-1^06148001.0311501 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008846 | 644813678-10250-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/059 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008847 | 645625601-87209-DETAIL-08_04_2025-GO95HV-1^06247006.0208804 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008848 | 645665388-56388-DETAIL-09_24_2025-GO95HV-1^07218001.0226200 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008849 | 646093398-73961-DTLSB-05_07_2026-DISTHDWR-1^06142013.0347600 | CONNECTION DEVICE | Non-HFTD | Distribution | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008850 | 646141391-6320-DETAIL-03_25_2025-COVCOTHR-2^06240004.0273402 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008851 | 646167733-97909-DETAIL-08_20_2025-SVCDEFLC-1^06247006.0259502 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008852 | 646169824-24753-DETAIL-07_28_2025-GO95HV-1^06247005.0300501 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008853 | 646169824-24753-DETAIL-07_28_2025-POLETOP-1^06247005.0300501 | POLE | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008854 | 646220000-56049-DETAIL-05_17_2023-CUSTWIRE-1^06245006.0345800 | OTHER | Non-HFTD | Distribution | 2023-05-17 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008855 | 646506633-67261-DTLSB-05_29_2026-GO95HV-1^07216001.0023501 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008856 | 646678390-11461-DETAIL-09_11_2025-GO95HV-1^06147001.0050800 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008857 | 646689005-90149-DTLSB-06_08_2026-GRDRODHI-1^07216001.0229202 | OTHER | Non-HFTD | Distribution | 2026-06-08 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008858 | 647170173-98920-DETAIL-01_21_2026-COVCOTHR-1^06240004.0289000 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008859 | 647170715-79529-DTLSB-05_04_2026-SVCENTCO-1^06142013.0061602 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008860 | 647398728-66871-DTLTRT-06_24_2025-SVCDEFLC-1^668087/00 2A/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008861 | 647831383-85179-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0260100 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008862 | 647873422-53139-DETAIL-05_21_2025-GO95HV-1^06243006.0078401 | OTHER | HFTD Tier 2 | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008863 | 647995641-9371-DETAIL-06_10_2026-GUYHINS-1^668086/00 16/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008864 | 648218333-27529-DTLSB-08_16_2023-CUSTWIRE-1^06243009.0283300 | OTHER | Non-HFTD | Distribution | 2023-08-16 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008865 | 648398748-65043-DETAIL-03_24_2026-GO95HV-1^06240004.0212942 | OTHER | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008866 | 649185281-42531-DETAIL-02_27_2025-GO95MLD-1^06241005.0177700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008867 | 649455610-69010-DETAIL-06_05_2025-GO95MLD-1^668075/00 9/026 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008868 | 649698901-77909-DETAIL-11_18_2025-GUYHINS-1^06246010.0138700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-11-18 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008869 | 649795799-71839-DETAIL-09_03_2025-GO95HV-1^07216001.0097204 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008870 | 64993376-15779-ADMIN-04_08_2024-ABNDEQPM-1^06147005.0245400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008871 | 64993376-15779-DETAIL-04_08_2024-CUTOUTAR-1^06147005.0245400 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008872 | 64993376-15779-DETAIL-04_08_2024-GO95MLD-1^06147005.0245400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008873 | 650351069-50090-DETAIL-01_16_2025-GO95HV-1^06239004.0257403 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008874 | 650462114-79381-DETAIL-08_20_2025-GO95HV-1^06246001.0175601 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008875 | 650524405-47970-ADMIN-10_16_2025-BIRDDMG-1^668047/00 9/021 | POLE | HFTD Tier 2 | Transmission | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008876 | 650566056-91173-DTLSB-06_15_2026-GO95HV-1^07217001.0274402 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008877 | 650784618-86023-DETAIL-06_11_2026-GO95TCH-1^07217001.0276703 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008878 | 650824090-4180-DETAIL-02_27_2025-GUYHINS-1^06240004.0233600 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008879 | 651059891-12480-DETAIL-02_23_2026-GO95HV-1^06239002.0032401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008880 | 65127516-63081-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0367945 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008881 | 65127516-63081-DRONE_HY-07_02_2026-GUYSLACK-1^06239004.0367945 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-07-02 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008882 | 652696601-69039-DTLTRT-07_09_2025-GO95HV-1^668087/00 5/025 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008883 | 652859971-61232-DTLTRT-04_28_2026-GO95HV-1^668004/00 3/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008884 | 65295614-60780-DTLTRT-06_30_2025-GUYHINS-1^668087/02 3/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008885 | 65295614-60780-DTLTRT-06_30_2025-GUYHINS-2^668087/02 3/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008886 | 65295614-60780-DTLTRT-06_30_2025-GUYHINS-3^668087/02 3/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008887 | 653184830-99091-DETAIL-06_04_2025-GO95HV-1^06142012.0106600 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008888 | 653457681-11179-DETAIL-09_10_2025-GO95HV-1^06147001.0082400 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008889 | 653611269-18559-DETAIL-08_05_2025-GO95HV-1^06247005.0208303 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008890 | 653836898-16949-DTLSB-07_16_2025-GO95HV-1^06244007.0037906 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008891 | 654319856-361-DETAIL-05_29_2025-GO95HV-1^06148014.0358001 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008892 | 654700291-56152-DETAIL-05_07_2025-GO95HV-1^06243006.0022501 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008893 | 654794323-13839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0260401 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008894 | 654806909-1109-DTLSB-07_03_2025-GO95HV-1^06244007.0138100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008895 | 654859008-108-DTLSB-06_24_2026-CLMBTRE-1^07217001.0346801 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008896 | 654940484-98491-DETAIL-09_08_2025-GO95HV-1^06147001.0298000 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008897 | 655114590-91449-DETAIL-09_05_2025-GRDRODHI-1^07216001.0098601 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008898 | 655217724-68724-DETAIL-04_25_2024-CUTOUTAR-1^06142016.0161800 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008899 | 655217724-68724-DETAIL-04_25_2024-GRDRODHI-1^06142016.0161800 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008900 | 65532631-75880-DETAIL-09_11_2025-GO95HV-1^06147001.0079900 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008901 | 655386292-76950-DETAIL-02_26_2026-COVCOTHR-1^06238004.0027240 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008902 | 655417399-42399-DETAIL-09_09_2025-GO95HV-1^06246007.0228800 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008903 | 655468920-30791-DETAIL-09_29_2025-GUYHINS-1^06148001.0312701 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008904 | 655775743-16743-DETAIL-06_17_2025-GO95HV-1^668075/00 8/042 | OTHER | HFTD Tier 2 | Transmission | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008905 | 655806114-55891-DETAIL-09_05_2025-GO95HV-1^06147001.0309101 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008906 | 655806114-55891-DETAIL-09_05_2025-GRDRODHI-2^06147001.0309101 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008907 | 655863287-14287-DETAIL-07_30_2025-POLETOP-1^06247005.0028001 | POLE | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008908 | 655867016-86079-DETAIL-02_18_2026-GO95HV-1^06239001.0069603 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008909 | 656098346-29346-DETAIL-07_02_2026-GO95HV-1^07218001.0342405 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008910 | 656647093-40753-DETAIL-08_27_2025-GO95HV-1^06247006.0081000 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008911 | 656780508-62273-DETAIL-09_16_2025-SVCENTCO-1^07216001.0085001 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008912 | 656808188-98570-DETAIL-02_26_2025-GO95TCH-1^06240004.0061103 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008913 | 656937468-63459-DETAIL-08_05_2025-GO95HV-1^06247005.0200701 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008914 | 657015826-50919-DETAIL-03_06_2025-GO95HV-1^06241005.0162900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008915 | 657037508-88030-DETAIL-01_14_2025-GO95TCH-1^06240004.0098200 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008916 | 657078546-80329-DETAIL-05_12_2025-GO95HV-1^06142012.0012802 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008917 | 657096600-60700-DTLSB-07_17_2025-GO95HV-1^06244006.0212701 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008918 | 657168220-80859-DTLSB-07_28_2025-GO95HV-1^07218001.0269208 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008919 | 657193093-3299-DETAIL-04_01_2024-SVCROAD-1^06147005.0113900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008920 | 657392968-41570-DETAIL-02_03_2025-GO95HV-1^06240004.0167802 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008921 | 657428286-5301-ADMIN-10_22_2025-GRDRODHI-1^06246001.0109900 | OTHER | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008922 | 657453555-6301-ADMIN-01_29_2026-POLEDERP-1^07216001.0169201 | POLE | Non-HFTD | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008923 | 657489296-49401-DETAIL-09_02_2025-GO95HV-1^06246001.0176404 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008924 | 657844496-84329-DETAIL-03_03_2026-GO95BLTC-1^06243009.0254200 | OTHER | Non-HFTD | Distribution | 2026-03-03 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008925 | 65785523-28669-DTLTRT-10_08_2020-CUSTWIRE-1^668047/00 13/016 | OTHER | HFTD Tier 2 | Transmission | 2020-10-08 | 2023-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008926 | 65785523-28669-DTLTRT-10_08_2020-CUSTWIRE-2^668047/00 13/016 | OTHER | HFTD Tier 2 | Transmission | 2020-10-08 | 2023-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008927 | 658225110-60152-DTLSB-07_08_2025-CUSTWIRE-1^06244007.0038240 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008928 | 65847215-57210-DRONE_HY-06_30_2026-XARMSPCR-1^06238004.0223600 | CROSSARM | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008929 | 65851154-13209-DETAIL-09_29_2025-GO95HV-1^06246009.0107500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008930 | 65873238-9830-DETAIL-01_26_2026-POLEREPL-1^06240003.0304300 | POLE | HFTD Tier 3 | Distribution | 2026-01-26 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008931 | 659062384-54732-DETAIL-10_14_2025-GO95BLTC-1^06246012.0134900 | OTHER | HFTD Tier 2 | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008932 | 659266668-97301-DETAIL-06_23_2025-GO95HV-1^668087/00 19/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008933 | 659418221-78099-DETAIL-08_14_2025-GO95HV-1^06246001.0310403 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008934 | 659547099-22909-DETAIL-03_14_2022-CUSTWIRE-1^06147006.0072900 | OTHER | Non-HFTD | Distribution | 2022-03-14 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008935 | 659910746-62206-DETAIL-09_28_2021-SVCWIND-1^06148004.0356006 | OTHER | Non-HFTD | Distribution | 2021-09-28 | 2024-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008936 | 660098146-66660-DTLTRT-04_30_2026-GO95HV-1^668004/00 2/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008937 | 660312440-10482-DTLTRT-07_09_2025-GO95HV-1^668087/00 1/024 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008938 | 660312440-69760-DTLTRT-07_09_2025-GO95HV-1^668087/00 1/024 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008939 | 660312440-69760-DTLTRT-07_09_2025-GUYNOINS-1^668087/00 1/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008940 | 660312440-69760-DTLTRT-07_09_2025-GUYNOINS-2^668087/00 1/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008941 | 660312440-85139-DTLTRT-07_09_2025-GO95HV-1^668087/00 1/024 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008942 | 660312440-85139-DTLTRT-07_09_2025-GUYNOINS-1^668087/00 1/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008943 | 660684994-76099-DETAIL-09_18_2025-GO95HV-1^06248007.0359900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008944 | 66086429-58429-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 16/014 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008945 | 66086429-58429-DTLTRT-07_01_2025-GO95HV-1^668087/00 16/014 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008946 | 661275133-16133-DETAIL-06_09_2025-GO95MLD-1^668075/00 9/029 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008947 | 661590919-67411-DETAIL-08_07_2025-GO95HV-1^06246002.0256901 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008948 | 661852583-68869-DTLSB-03_09_2026-GO95MLD-1^06242009.0082000 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008949 | 66218936-48936-DTLTRT-07_07_2025-POLEDERP-1^668087/00 17/029 | POLE | Non-HFTD | Transmission | 2025-07-07 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008950 | 662958121-57180-DETAIL-02_16_2026-GO95HV-1^06239001.0057701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008951 | 662993845-6089-DETAIL-04_22_2025-GRDRODHI-1^06242006.0085601 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008952 | 663297616-84839-DETAIL-05_06_2025-GO95BLTC-1^06243006.0032701 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008953 | 663297616-84839-DETAIL-05_06_2025-GO95HV-1^06243006.0032701 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008954 | 663615596-92449-DTLSB-07_09_2025-GRDRODHI-1^06244006.0276000 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008955 | 66373460-73080-DETAIL-01_26_2026-COVCOTHR-1^06240004.0230501 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008956 | 66373460-73080-DETAIL-01_26_2026-COVCOTHR-2^06240004.0230501 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008957 | 66373460-73080-DETAIL-02_27_2025-GO95BLTC-1^06240004.0230501 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008958 | 663854499-76421-DTLSB-05_07_2024-INSULDMG-1^06245002.0137300 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008959 | 66391006-75580-DTLSB-04_29_2026-GO95HV-1^06142013.0213102 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008960 | 663963274-29199-DETAIL-08_14_2025-GO95HV-1^06247006.0365800 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008961 | 664041477-25721-ADMIN-11_10_2025-GO95BLTC-1^06246001.0253400 | OTHER | Non-HFTD | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008962 | 664441608-3608-DETAIL-09_04_2025-GO95HV-1^07216001.0099220 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008963 | 664477710-41589-DETAIL-08_30_2021-CUSTWIRE-2^06148004.0353602 | OTHER | Non-HFTD | Distribution | 2021-08-30 | 2024-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008964 | 664758381-8153-DETAIL-07_02_2026-GO95HV-1^07217001.0222604 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008965 | 664969186-51286-DETAIL-09_09_2025-GO95BLTC-1^07218001.0177301 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008966 | 664982776-93776-DETAIL-06_02_2025-GO95HV-1^06148014.0362700 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008967 | 665271202-73139-DETAIL-05_20_2025-GO95HV-1^06243006.0078600 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008968 | 665456231-17689-DTLSB-01_21_2026-BIRDDMG-1^06242009.0298107 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008969 | 665456231-17689-DTLSB-01_21_2026-SVCENTCO-1^06242009.0298107 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008970 | 665853462-45083-DETAIL-08_21_2025-GO95HV-1^07216001.0177205 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008971 | 665888779-22949-DTLSB-07_15_2025-GO95HV-1^06244007.0246902 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008972 | 666006438-82799-DTLSB-01_20_2026-GO95HV-1^06242009.0298201 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008973 | 666076916-38270-DETAIL-01_15_2025-GO95HV-1^06239004.0255145 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008974 | 666188670-26839-DETAIL-05_07_2025-GO95HV-1^06243006.0286500 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008975 | 666298403-43503-DETAIL-10_25_2021-CUSTWIRE-1^06148005.0234702 | OTHER | Non-HFTD | Distribution | 2021-10-25 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008976 | 666363675-69040-DETAIL-03_24_2026-RISEBKSP-1^06240004.0214700 | OTHER | HFTD Tier 2 | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008977 | 666815641-29350-DETAIL-03_24_2025-SVCROAD-1^06238004.0028603 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008978 | 667007826-62949-DTLSB-07_08_2025-GO95HV-1^06244007.0036501 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008979 | 667013363-10590-DETAIL-02_24_2026-BIRDDMG-1^06239002.0272800 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008980 | 667273079-48999-DTLSB-07_08_2025-GO95HV-1^06244007.0037303 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008981 | 667638681-43739-DETAIL-05_07_2025-GO95HV-1^06243006.0353802 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008982 | 667713972-59289-DETAIL-05_21_2025-ABNDEQPM-1^06243006.0155800 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008983 | 667713972-59289-DETAIL-05_21_2025-GO95HV-1^06243006.0155800 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008984 | 668084409-84879-DETAIL-10_07_2025-GO95HV-1^06148001.0354501 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008985 | 668600362-24559-DETAIL-04_29_2026-GO95HV-1^668004/00 11/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008986 | 668600362-24560-DETAIL-04_29_2026-GO95HV-1^668004/00 11/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008987 | 668822661-48932-DTLTRT-04_28_2026-GO95HV-1^668004/00 2/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008988 | 668973223-61459-DTLTRT-04_20_2026-GO95HV-1^668004/02 11/002 | OTHER | Non-HFTD | Transmission | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008989 | 669100006-15180-DRONE_HY-07_01_2026-COVCOTHR-2^06239004.0363300 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008990 | 669213621-53731-DETAIL-09_11_2025-SVCNEUT-1^06147001.0050901 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008991 | 66937398-27440-DETAIL-03_05_2026-COVCOTHR-1^06238004.0145803 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008992 | 66939300-87229-DETAIL-04_22_2026-SVCENTCO-1^06142012.0142401 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008993 | 66943928-20409-DETAIL-04_10_2024-CUSTWIRE-1^06147005.0212901 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008994 | 669632895-15895-DTLSB-07_08_2026-GO95HV-1^06242009.0261204 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008995 | 669911673-62540-DTLTRT-05_29_2025-GUYNOINS-1^668075/00 8/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008996 | 669911673-62540-DTLTRT-05_29_2025-GUYNOINS-2^668075/00 8/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008997 | 670493038-69309-DETAIL-04_10_2024-CLRTOUCH-1^06147005.0212703 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120008998 | 670493038-69309-DETAIL-04_10_2024-GO95MLD-1^06147005.0212703 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120008999 | 670878889-88919-DTLSB-05_12_2026-GO95HV-1^06242009.0285602 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009000 | 671031936-88631-DETAIL-09_03_2025-GO95HV-1^06246001.0179401 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009001 | 671989459-32599-DETAIL-09_22_2025-POLETOP-1^06248007.0242501 | POLE | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009002 | 672390424-37841-ADMIN-02_26_2021-COPLLEAN-1^668041/00 12/028 | POLE | Non-HFTD | Transmission | 2021-02-26 | 2024-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009003 | 672431384-44679-DETAIL-08_28_2025-GO95HV-1^06247006.0185000 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009004 | 67251328-78440-DETAIL-03_05_2026-COVCOTHR-1^06238004.0147700 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009005 | 672594934-58499-DETAIL-06_16_2025-GO95HV-1^06248005.0259004 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009006 | 67282954-27009-DETAIL-08_12_2025-SVCDEFLC-1^06247006.0251102 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009007 | 672978193-97763-DETAIL-03_11_2025-GO95HV-1^06238004.0274903 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009008 | 673373989-53789-DETAIL-10_06_2025-GUYHINS-1^06148001.0301001 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009009 | 673373989-53789-DETAIL-10_06_2025-GUYHINS-2^06148001.0301001 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009010 | 673384953-87723-DETAIL-06_18_2025-GO95HV-1^06248004.0336041 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009011 | 673593560-38459-DETAIL-07_23_2025-GO95HV-1^06247005.0177401 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009012 | 673724298-47790-DETAIL-01_13_2026-COVCOTHR-1^06239004.0246042 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009013 | 673966860-74570-DETAIL-02_12_2025-GO95BLTC-1^06240004.0167008 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009014 | 673966860-74570-DETAIL-02_12_2025-GO95CL10-1^06240004.0167008 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009015 | 674171228-43589-DTLSB-07_08_2025-GO95HV-1^06244007.0038907 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009016 | 674181869-79330-DTLTRT-05_27_2025-GO95HV-1^668075/00 5/003 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009017 | 675098153-50029-DTLSB-09_05_2023-CUSTWIRE-1^06243008.0235000 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009018 | 675207419-19030-DTLTRT-05_27_2025-GO95HV-1^668075/00 2/004 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009019 | 675343763-1709-DETAIL-09_04_2025-GO95HV-1^06247006.0072101 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009020 | 675355496-22889-DETAIL-07_28_2025-GO95HV-1^06247005.0315300 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009021 | 675524919-85939-DTLTRT-05_14_2026-GO95MLD-1^668086/00 10/003 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009022 | 675556804-90809-DETAIL-10_13_2025-GO95BLTC-1^06246012.0123300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009023 | 675851113-30429-DETAIL-06_15_2023-CUSTWIRE-1^06244009.0307802 | OTHER | HFTD Tier 2 | Distribution | 2023-06-15 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009024 | 675969731-11151-DTLTRT-05_11_2026-GO95HV-1^668004/00 1/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009025 | 676106254-56739-DETAIL-06_02_2025-GO95HV-1^06244006.0154301 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009026 | 676555209-10119-DTLSB-04_13_2026-BIRDDMG-1^06241008.0366900 | POLE | Non-HFTD | Distribution | 2026-04-13 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009027 | 676555209-10119-DTLSB-04_13_2026-GO95HV-1^06241008.0366900 | OTHER | Non-HFTD | Distribution | 2026-04-13 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009028 | 676702016-64151-DETAIL-05_14_2025-GO95HV-1^06142012.0117404 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009029 | 676836654-77654-DETAIL-06_03_2025-GO95MLD-1^06245007.0366700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009030 | 676838325-7289-DTLSB-07_09_2025-GO95HV-1^06244006.0346600 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009031 | 676838325-7289-DTLSB-07_09_2025-GO95MLD-1^06244006.0346600 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009032 | 676944974-83632-ADMIN-10_21_2025-ENCHSVCE-1^06246012.0142900 | OTHER | HFTD Tier 2 | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009033 | 677198524-14959-DETAIL-03_18_2024-CUSTWIRE-1^06246005.0082201 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009034 | 677282776-67660-DTLTRT-04_30_2026-GO95HV-1^668004/00 5/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009035 | 677731306-59851-DETAIL-05_19_2025-GO95HV-1^06142012.0113500 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009036 | 67781005-33005-DETAIL-06_05_2025-GO95HV-1^06245006.0190003 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009037 | 677930858-55419-DETAIL-04_09_2024-CUSTWIRE-1^06147005.0254702 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009038 | 678820440-35689-DETAIL-06_18_2025-GO95HV-1^06248004.0340704 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009039 | 679094916-9029-DETAIL-04_22_2025-GO95BLTC-1^06242006.0077901 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009040 | 679147866-27099-DTLSB-07_08_2025-GO95HV-1^06244007.0038600 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009041 | 679168492-86459-DETAIL-04_29_2026-GO95HV-1^668004/00 7/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009042 | 679193636-64470-DETAIL-01_15_2026-SVCDEFLC-1^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009043 | 679206506-50700-DETAIL-02_10_2026-GUYHINS-1^06239003.0016505 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009044 | 679391395-7379-DETAIL-03_28_2024-GO95MLD-1^06147005.0118500 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009045 | 680031995-23500-DETAIL-02_05_2026-GO95HV-1^06239003.0017609 | OTHER | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009046 | 680159703-99680-DETAIL-02_17_2026-GO95HV-1^06239002.0059800 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009047 | 680195345-50499-DETAIL-01_28_2026-GO95BLTC-1^06242009.0052000 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009048 | 680531172-86089-DETAIL-05_20_2025-SVCROAD-1^06243006.0068202 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009049 | 68059176-63953-DTLTRT-06_16_2026-GO95HV-1^07217001.0357701 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009050 | 68071367-81367-ADMIN-10_07_2025-COVCOTHR-1^06242005.0361106 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009051 | 680821192-7560-DETAIL-04_29_2026-GO95HV-1^668004/00 6/014 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009052 | 680903295-83295-DETAIL-05_07_2025-GO95HV-1^06243006.0288302 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009053 | 680951145-60549-DTLSB-07_09_2025-GO95TCH-1^06244006.0345602 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009054 | 681007472-73499-DETAIL-05_08_2025-GO95HV-1^06243006.0155901 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009055 | 681195469-38429-DTLSB-02_09_2026-BIRDDMG-1^06243010.0366500 | POLE | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009056 | 681574488-87861-DTLSB-06_02_2026-GO95MLD-1^07216001.0116903 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009057 | 681648778-89041-DETAIL-03_06_2025-GO95BLTC-1^06241005.0161800 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009058 | 681648778-89041-DETAIL-03_06_2025-GO95HV-1^06241005.0161800 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009059 | 681841809-2809-DETAIL-08_18_2025-GO95HV-1^06247006.0361001 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009060 | 682099729-96130-DTLTRT-05_22_2025-GO95HV-1^668075/00 17/002 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009061 | 682220045-63029-DETAIL-04_17_2025-GO95HV-1^06242006.0084601 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009062 | 682420853-21589-DTLSB-01_20_2026-GO95HV-1^06242009.0299002 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009063 | 68310381-14983-DTLTRT-06_05_2026-GO95HV-1^07216001.0231802 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009064 | 68347334-67334-DETAIL-08_12_2025-GO95BLTC-1^06246002.0254201 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009065 | 68347334-67334-DETAIL-08_12_2025-GO95HV-1^06246002.0254201 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009066 | 683588233-8959-DTLSB-08_12_2025-GO95HV-1^07217001.0013001 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009067 | 683813580-91971-DETAIL-09_29_2025-SVCENTCO-1^06148001.0310606 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009068 | 683844275-50599-DTLSB-07_03_2025-GO95HV-1^06245007.0356500 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009069 | 683985394-95189-DETAIL-07_30_2025-GO95HV-1^06247006.0204100 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009070 | 684140329-34713-DETAIL-08_26_2025-GO95HV-1^06247006.0285502 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009071 | 684235229-23029-DTLTRT-07_01_2025-GUYNOINS-1^668087/00 13/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009072 | 684235229-23029-DTLTRT-07_01_2025-GUYNOINS-2^668087/00 13/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009073 | 684235229-44029-DTLTRT-07_01_2025-GUYNOINS-1^668087/00 13/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009074 | 684664380-32071-DTLSB-06_02_2026-ABNDEQPM-1^07216001.0028001 | OTHER | Non-HFTD | Distribution | 2026-06-02 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009075 | 684906256-26579-DETAIL-08_06_2025-GO95HV-1^06246002.0156003 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009076 | 685306106-21863-DETAIL-07_02_2026-CUSTWIRE-1^07217001.0099800 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009077 | 685395941-69130-DETAIL-03_26_2026-COVCOTHR-1^06240004.0206401 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009078 | 685395941-69130-DETAIL-03_26_2026-COVCOTHR-3^06240004.0206401 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009079 | 685580879-73499-DETAIL-04_22_2025-GO95HV-1^06242006.0096100 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009080 | 686111926-61449-DTLSB-07_09_2025-GO95MLD-1^06244006.0276602 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009081 | 686386144-4953-DETAIL-06_25_2026-GO95HV-1^07217001.0097500 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009082 | 686415293-90499-DETAIL-06_03_2025-GO95HV-1^06245007.0364840 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009083 | 686655446-32000-DETAIL-04_08_2026-GO95HV-1^06240002.0317202 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009084 | 687013624-75229-DETAIL-04_21_2026-GO95HV-1^06142012.0149906 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009085 | 687287482-88943-DETAIL-09_23_2025-GUYHINS-1^07218001.0232001 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009086 | 68737908-19919-DTLSB-05_12_2026-GO95BLTC-1^06242009.0286601 | OTHER | Non-HFTD | Distribution | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009087 | 687449073-43183-DETAIL-07_29_2025-GO95HV-1^06247005.0211200 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009088 | 687642681-66789-DTLSB-07_08_2025-GO95HV-1^06245007.0350205 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009089 | 687756765-1759-DETAIL-08_20_2025-GO95HV-1^07216001.0175002 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009090 | 687968226-79489-DETAIL-10_08_2025-DISTHDWR-1^06148001.0204200 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009091 | 688029411-1511-ADMIN-06_05_2026-POLEREPL-1^06142015.0027901 | POLE | HFTD Tier 2 | Distribution | 2026-06-05 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009092 | 688029411-1511-DETAIL-04_30_2024-GO95HV-1^06142015.0027901 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009093 | 688299490-12590-DETAIL-06_24_2024-CUSTWIRE-1^06244005.0233200 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009094 | 688395143-97639-DTLSB-09_21_2022-CUSTWIRE-1^06243005.0116801 | OTHER | Non-HFTD | Distribution | 2022-09-21 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009095 | 688578695-98799-DETAIL-05_27_2025-GO95HV-1^06244006.0042840 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009096 | 688787580-82611-DETAIL-04_16_2025-GUYHINS-1^06242005.0331000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-16 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009097 | 689126627-8049-DETAIL-06_11_2025-GO95HV-1^06245006.0298500 | OTHER | Non-HFTD | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009098 | 689197734-29660-DETAIL-04_28_2025-GRDRODHI-1^06239002.0060700 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009099 | 689230056-91189-DETAIL-06_04_2025-GO95HV-1^06245006.0283501 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009100 | 689244663-41850-DETAIL-01_30_2025-GO95TCH-1^06239004.0133004 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009101 | 689290674-49983-DETAIL-09_18_2025-GO95HV-1^07218001.0086101 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009102 | 689366482-38353-DETAIL-06_24_2026-GO95HV-1^07217001.0223200 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009103 | 690386433-72541-AUDIT-10_28_2025-CONDFRAY-1^06147001.0079803 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-28 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009104 | 690473761-30739-DETAIL-05_07_2025-GO95HV-1^06243006.0025501 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009105 | 690692741-72369-DTLTRT-06_02_2021-GO95HV-1^668041/00 6/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009106 | 690748539-70019-DTLSB-05_19_2026-GO95HV-1^06240007.0070700 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009107 | 690752409-52070-DETAIL-03_23_2026-COVCOTHR-1^06240004.0220507 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009108 | 690752409-52070-DETAIL-03_23_2026-COVCOTHR-2^06240004.0220507 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009109 | 690752409-52070-DETAIL-03_23_2026-COVCOTHR-4^06240004.0220507 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009110 | 690753792-27759-DETAIL-07_30_2025-GO95HV-1^06247005.0239201 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009111 | 690819066-79282-DETAIL-07_11_2023-CUSTWIRE-1^06244008.0321901 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009112 | 691036358-7391-DETAIL-04_21_2026-GO95HV-1^06142012.0140902 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009113 | 691129549-83691-DETAIL-08_11_2025-GO95HV-1^06246002.0279901 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009114 | 691230532-43449-DETAIL-02_27_2024-GO95HV-1^07113002.0182300 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009115 | 691841934-26890-DETAIL-03_02_2026-GO95HV-1^06239003.0251600 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009116 | 692144913-77909-DETAIL-08_13_2025-DISTHDWR-1^06247006.0258500 | CONNECTION DEVICE | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009117 | 692322347-93423-DETAIL-05_27_2026-GO95TCH-1^07217001.0149400 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009118 | 692729088-54290-DETAIL-01_20_2026-GUYHINS-1^06239004.0245509 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009119 | 692729088-54290-DETAIL-01_20_2026-GUYHINS-2^06239004.0245509 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009120 | 692729088-54290-DETAIL-01_30_2025-GO95HV-1^06239004.0245509 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009121 | 692826320-24443-DETAIL-06_26_2026-GO95HV-1^07217001.0117301 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009122 | 692886826-65593-DETAIL-08_13_2025-GO95HV-1^06247006.0265600 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009123 | 692959438-70391-ADMIN-11_12_2025-GO95HV-1^06246001.0340100 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009124 | 692959438-70391-ADMIN-11_12_2025-GRDRODHI-1^06246001.0340100 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009125 | 692962815-6645-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 6/001 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009126 | 693330194-85240-DTLTRT-06_02_2025-GUYNOINS-1^668075/00 5A/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009127 | 693330194-85240-DTLTRT-06_02_2025-GUYNOINS-2^668075/00 5A/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-02 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009128 | 693368121-99970-DETAIL-02_11_2025-SVCDEFLC-1^06240004.0167306 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009129 | 693447539-37029-DETAIL-05_07_2024-CUSTWIRE-1^06142012.0123201 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009130 | 693786726-57369-DETAIL-04_07_2025-ANCHIDLE-1^06241005.0016802 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009131 | 693801949-40041-DETAIL-04_08_2025-GO95MLD-1^06241005.0092201 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009132 | 69417784-78810-DETAIL-03_13_2025-GO95HV-1^06238004.0152204 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009133 | 694236541-50489-DTLSB-01_29_2026-BIRDDMG-1^06242009.0051901 | POLE | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009134 | 694236541-50489-DTLSB-01_29_2026-SVCDEFLC-1^06242009.0051901 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009135 | 694599771-14430-DETAIL-04_20_2023-CUSTWIRE-1^06240004.0170601 | OTHER | HFTD Tier 2 | Distribution | 2023-04-20 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009136 | 694709223-46819-DTLSB-05_11_2026-GO95HV-1^06242009.0278300 | OTHER | Non-HFTD | Distribution | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009137 | 695039384-71432-DETAIL-10_15_2025-GO95BLTC-1^06246012.0133501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009138 | 695047459-80791-DETAIL-08_25_2025-GO95HV-1^06246001.0206800 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009139 | 695087594-98540-DETAIL-03_25_2026-SVCROOF-1^06240004.0217602 | OTHER | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009140 | 695092459-11579-DETAIL-10_14_2025-GRDRODHI-1^06148001.0339901 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009141 | 695244001-98369-DTLSB-07_09_2025-GO95HV-1^06244007.0158702 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009142 | 695761663-43663-DETAIL-04_08_2026-GO95HV-1^06240002.0314303 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009143 | 696015212-22612-DTLSB-07_21_2025-GO95HV-1^06244006.0230440 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009144 | 696015583-7850-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0133100 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009145 | 696321688-72643-DTLSB-08_12_2025-GO95GUYB-1^07217001.0020201 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009146 | 696609018-40649-DETAIL-09_16_2025-SVCROAD-1^07216001.0085010 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009147 | 696680499-99501-ADMIN-11_12_2025-GO95HV-1^06246001.0335701 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009148 | 696831988-76540-DETAIL-02_09_2026-GO95HV-1^06239003.0018105 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009149 | 696977618-87479-DETAIL-08_12_2025-GO95HV-1^06246002.0254301 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009150 | 697561998-89469-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0258300 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009151 | 697667385-55159-DETAIL-08_18_2025-GO95HV-1^06247006.0365400 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009152 | 697714928-16340-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 8/053 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009153 | 698080628-11911-DTLTRT-06_23_2025-SVCNEUT-1^668087/00 17/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009154 | 698385371-96399-DTLSB-03_10_2026-GO95BLTC-1^06243009.0347000 | OTHER | Non-HFTD | Distribution | 2026-03-10 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009155 | 698430989-75979-DTLSB-07_01_2025-GO95HV-1^06244007.0132301 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009156 | 698454613-65719-DTLSB-03_25_2026-GO95HV-1^06242009.0038400 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009157 | 698622532-72859-DETAIL-08_21_2025-GO95HV-1^07216001.0177303 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009158 | 698684458-41011-DETAIL-09_09_2025-GO95HV-1^06146001.0045201 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009159 | 698794174-76174-DTLTRT-08_04_2025-GO95HV-1^668087/00 15/028 | OTHER | Non-HFTD | Transmission | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009160 | 698794174-76174-DTLTRT-08_04_2025-GUYNOINS-1^668087/00 15/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009161 | 698961754-95639-DTLSB-09_20_2022-CUSTWIRE-1^06243005.0110201 | OTHER | Non-HFTD | Distribution | 2022-09-20 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009162 | 699141496-82660-DETAIL-04_30_2026-GO95HV-1^668004/00 7/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009163 | 699183939-57059-DTLTRT-05_06_2026-GO95HV-1^668004/00 10/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009164 | 699183939-57060-DTLTRT-05_06_2026-GO95HV-1^668004/00 10/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009165 | 699223859-67019-DTLSB-05_26_2026-GO95HV-1^06240007.0183300 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009166 | 699669484-82360-DETAIL-01_16_2025-GO95HV-1^06239004.0257504 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009167 | 70021334-12109-DETAIL-08_20_2025-SVCENTCO-1^06247006.0255801 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009168 | 700655606-65606-DETAIL-01_22_2026-GO95MLD-1^06239004.0228200 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009169 | 700792236-93069-DTLSB-03_16_2026-GO95HV-1^06242009.0137201 | OTHER | Non-HFTD | Distribution | 2026-03-16 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009170 | 700857682-79880-DETAIL-02_12_2025-GO95TCH-1^06240004.0165400 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009171 | 700857682-79880-DETAIL-02_12_2025-GUYHINS-1^06240004.0165400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009172 | 700990167-97621-DETAIL-08_04_2025-GO95HV-1^06246002.0139200 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009173 | 701190028-41740-DETAIL-03_05_2026-GO95HV-1^06238004.0142201 | OTHER | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009174 | 70119394-64490-DETAIL-03_10_2026-XARMSPCR-1^668041/00 9/028 | CROSSARM | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009175 | 701522805-26363-DETAIL-06_25_2026-GUYHINS-1^07217001.0034400 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-25 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009176 | 702021343-74509-DETAIL-09_17_2025-GO95HV-1^06246007.0137151 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009177 | 702410804-66469-DETAIL-07_25_2024-CUSTWIRE-1^06244005.0347001 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009178 | 702478559-81289-DETAIL-10_07_2025-GO95HV-1^06148001.0276600 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009179 | 702534609-85712-DETAIL-06_29_2023-CUSTWIRE-1^06244009.0241300 | OTHER | HFTD Tier 2 | Distribution | 2023-06-29 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009180 | 702567153-26750-DETAIL-01_23_2025-GO95TCH-1^06239004.0257605 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009181 | 702649513-89599-DETAIL-06_11_2025-GO95HV-1^06245007.0269600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009182 | 702933978-53383-ADMIN-03_07_2024-POLEREPL-1^06245007.0275840 | POLE | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009183 | 703324054-40540-DTLSB-07_30_2025-GO95MLD-1^07218001.0261703 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009184 | 703402416-35416-DTLSB-06_24_2025-GO95HV-1^06244007.0034702 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009185 | 703449206-18999-DTLSB-04_15_2024-SVCWIND-1^06245007.0226100 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009186 | 703560024-72421-DETAIL-09_05_2025-GO95HV-1^06147001.0309200 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009187 | 703592865-64865-DETAIL-06_03_2025-GO95HV-1^06148014.0248600 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009188 | 703640169-6721-DTLTRT-06_24_2025-GO95HV-1^668087/00 14A/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009189 | 703753183-47330-DTLSB-07_31_2025-GO95HV-1^07218001.0273102 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009190 | 703935511-23930-DTLTRT-05_28_2025-GO95HV-1^668075/00 10/006 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009191 | 704047991-90231-DETAIL-09_30_2025-SVCENTCO-1^06148001.0301206 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009192 | 704083035-16379-DTLSB-07_15_2025-GO95HV-1^06244006.0345100 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009193 | 704295295-56295-DETAIL-09_05_2025-GO95HV-1^06146001.0060702 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009194 | 704298649-65759-DETAIL-09_03_2025-GO95HV-1^07216001.0097005 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009195 | 704310979-62739-DTLSB-07_22_2025-GO95HV-1^06244006.0180302 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009196 | 705169662-70099-DETAIL-05_14_2025-GO95BLTC-1^06243006.0168402 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009197 | 705354618-92931-DTLSB-04_29_2026-ABNDEQPM-1^06142013.0287100 | OTHER | Non-HFTD | Distribution | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009198 | 705586790-37790-AUDIT-07_15_2026-ANCHIDLE-1^07216001.0116500 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009199 | 705586790-37790-AUDIT-07_15_2026-GRDRODHI-1^07216001.0116500 | OTHER | Non-HFTD | Distribution | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009200 | 705679869-55770-DETAIL-06_11_2025-GO95HV-1^06236005.0163000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009201 | 705713485-53389-DETAIL-09_29_2025-GUYHINS-1^06246009.0102602 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009202 | 705917656-10652-DETAIL-04_21_2025-GUYHINS-1^06242005.0369804 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009203 | 706197814-3269-DTLTRT-10_11_2023-BIRDDMG-1^668010/00 8/040 | POLE | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009204 | 706331002-91231-DETAIL-07_13_2023-CUSTWIRE-1^06244008.0271100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-13 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009205 | 706608743-78743-DETAIL-06_16_2025-GUYHINS-2^668075/00 9/041 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009206 | 706679088-3689-DETAIL-06_17_2025-GO95HV-1^06248004.0299108 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009207 | 70678809-9929-DETAIL-06_05_2025-GO95HV-1^06148014.0248802 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009208 | 706936656-79759-DTLTRT-05_04_2026-GO95HV-1^668004/00 9/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009209 | 706936656-79760-DTLTRT-05_04_2026-GO95HV-1^668004/00 9/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009210 | 70700888-23523-DTLSB-06_15_2026-GO95HV-1^07217001.0278502 | OTHER | Non-HFTD | Distribution | 2026-06-15 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009211 | 707019109-79109-DTLSB-07_02_2025-GO95HV-1^06244007.0131740 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009212 | 707250398-30210-DETAIL-09_23_2025-GO95MLD-1^07218001.0233005 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009213 | 707267545-39249-DTLSB-07_15_2025-GO95HV-1^06244006.0345101 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009214 | 707440981-53439-DETAIL-05_08_2025-GUYHINS-1^06243006.0213700 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-08 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009215 | 707738818-24341-DTLTRT-07_01_2025-GUYNOINS-3^668087/00 2/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009216 | 707738818-88182-DTLTRT-07_01_2025-GUYNOINS-2^668087/00 2/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009217 | 707738818-88182-DTLTRT-07_01_2025-GUYNOINS-3^668087/00 2/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009218 | 707746482-44080-DETAIL-02_25_2025-GO95CL10-1^06240005.0016003 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009219 | 707840348-14350-DETAIL-02_24_2026-GO95HV-1^06239003.0132402 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009220 | 707864811-11350-DETAIL-03_04_2026-BIRDDMG-1^06239003.0180900 | POLE | HFTD Tier 3 | Distribution | 2026-03-04 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009221 | 708081266-90491-DETAIL-05_11_2026-GO95HV-1^668038/00 1/049 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009222 | 708733541-72339-DTLSB-05_28_2026-GO95HV-1^07216001.0021401 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009223 | 709518220-89289-DETAIL-08_21_2025-GO95HV-1^06247006.0259903 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009224 | 709518220-89289-DETAIL-08_21_2025-GO95MLD-1^06247006.0259903 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009225 | 709948263-24509-DETAIL-09_17_2025-GO95HV-1^06246007.0136151 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009226 | 710118104-82289-DETAIL-06_02_2025-ABNDEQPM-1^06244006.0156800 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009227 | 710129216-73659-DETAIL-04_30_2026-GO95HV-1^668004/00 9/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009228 | 710129216-83660-DETAIL-04_30_2026-GO95HV-1^668004/00 9/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009229 | 710307815-9815-DETAIL-06_05_2025-GO95MLD-1^06148014.0235600 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009230 | 710380346-10670-DETAIL-01_24_2025-GO95HV-1^06239004.0257843 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009231 | 71043663-84821-DETAIL-04_10_2025-ABNDEQPM-1^06241005.0040800 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009232 | 710510683-9899-DETAIL-06_17_2025-GO95HV-1^06248004.0330902 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009233 | 710832909-98669-DTLSB-03_25_2026-GO95MLD-1^06242009.0045000 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009234 | 711043663-44663-DTLSB-07_09_2025-GO95HV-1^06244007.0155601 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009235 | 71119463-10083-DETAIL-08_20_2024-CUSTWIRE-1^06246004.0185140 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009236 | 711565709-48940-DETAIL-03_05_2026-COVCOTHR-1^06238004.0011901 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009237 | 711911085-68899-DETAIL-03_12_2024-CUSTWIRE-1^06245007.0274505 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009238 | 712009805-68459-DETAIL-06_18_2025-GO95HV-1^06248004.0289001 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009239 | 712324245-65703-DETAIL-03_06_2024-SVCROAD-1^06245007.0271900 | OTHER | HFTD Tier 2 | Distribution | 2024-03-06 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009240 | 712387715-18551-DTLSB-05_07_2024-GO95MLD-1^06245001.0295301 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009241 | 712395606-81419-DTLSB-03_24_2026-BIRDDMG-1^06242009.0028402 | POLE | Non-HFTD | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009242 | 712395606-81419-DTLSB-03_24_2026-SVCDEFLC-1^06242009.0028402 | OTHER | Non-HFTD | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009243 | 712560548-25740-DETAIL-02_24_2026-BIRDDMG-1^06239002.0180901 | POLE | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009244 | 71256194-64489-DETAIL-09_17_2025-GO95HV-1^06147001.0014900 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009245 | 712755379-93259-DETAIL-06_04_2024-CUSTWIRE-1^06246005.0337301 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009246 | 712881106-57661-DTLSB-05_04_2026-GO95HV-1^06142013.0174201 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009247 | 712926271-9211-DETAIL-06_19_2025-GO95HV-1^06237004.0202900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009248 | 713163549-27489-DETAIL-07_28_2025-GO95HV-1^06247005.0198501 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009249 | 713232363-9861-DETAIL-03_10_2026-POLETOP-1^668041/00 11/026 | POLE | Non-HFTD | Transmission | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009250 | 713276879-27879-DETAIL-03_30_2026-GO95TCH-1^06240004.0272141 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009251 | 713366611-75580-DETAIL-02_16_2026-GO95HV-1^06239001.0033900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009252 | 713621604-36260-DETAIL-01_29_2025-GO95BLTC-1^06240004.0160800 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009253 | 713711103-63749-DETAIL-06_09_2025-GO95HV-1^06245006.0191700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009254 | 713850641-9080-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0166207 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009255 | 714015593-26593-DETAIL-09_18_2025-GO95MLD-1^07218001.0086202 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009256 | 714125371-72861-DTLTRT-05_18_2026-GO95HV-1^668086/00 9/011 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009257 | 714132261-93861-DETAIL-08_14_2025-GO95HV-1^06246001.0316900 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009258 | 71436214-55589-DTLSB-07_03_2025-GO95HV-1^06245007.0356805 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009259 | 714379872-68049-DTLSB-07_16_2025-GO95HV-1^06244006.0235001 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009260 | 71486741-14559-DETAIL-09_18_2025-GO95HV-1^06246006.0013300 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009261 | 714882966-72409-DETAIL-08_21_2025-SVCENTCO-1^06247006.0267801 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009262 | 715143325-57000-DETAIL-04_07_2026-GO95HV-1^06240002.0316004 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009263 | 715148266-52760-DTLTRT-04_30_2026-GO95HV-1^668004/00 6/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009264 | 71526874-97783-DETAIL-08_18_2025-GO95HV-1^06247006.0362302 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009265 | 71561980-32859-DETAIL-06_16_2025-GO95HV-1^06248005.0332900 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009266 | 716027595-47595-DETAIL-06_04_2024-CUSTWIRE-1^06246006.0362201 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009267 | 71620613-55300-ADMIN-10_20_2025-GO95HV-1^06247001.0360300 | OTHER | Non-HFTD | Distribution | 2025-10-20 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009268 | 716306493-23721-DETAIL-11_14_2022-CUSTWIRE-1^06239004.0363900 | OTHER | HFTD Tier 2 | Distribution | 2022-11-14 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009269 | 716432973-73989-DTLSB-04_20_2026-GO95HV-1^06241009.0122001 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009270 | 716432973-73989-DTLSB-04_20_2026-GRDRODHI-1^06241009.0122001 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009271 | 716568165-90770-DETAIL-01_14_2025-GO95HV-1^06240004.0078800 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009272 | 716696302-17230-DTLSB-08_13_2025-GO95HV-1^07218001.0286201 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009273 | 716703850-11270-DETAIL-02_19_2026-GO95HV-1^06239002.0016601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009274 | 716732768-60813-DETAIL-09_02_2025-GO95HV-1^06247006.0276741 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009275 | 717124940-8739-DTLTRT-06_25_2025-GO95HV-1^668087/00 14/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009276 | 717845304-80010-DETAIL-11_16_2022-CUSTWIRE-1^06238004.0152000 | OTHER | HFTD Tier 2 | Distribution | 2022-11-16 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009277 | 717900998-87550-DETAIL-04_22_2025-GO95HV-1^06240003.0053300 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009278 | 718074606-84606-DETAIL-01_22_2026-GO95MLD-1^06239004.0229101 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009279 | 718236153-19889-DETAIL-08_20_2025-GO95HV-1^06247006.0256700 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009280 | 718336323-71809-DETAIL-08_28_2025-GRDRODHI-1^06247006.0075800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009281 | 718388304-15759-DETAIL-06_16_2025-GUYLOINS-1^06248005.0368701 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009282 | 71849813-60500-DETAIL-08_18_2025-SVCROAD-1^06246002.0358000 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009283 | 718578991-57669-DETAIL-10_17_2022-CUSTWIRE-1^06246010.0218000 | OTHER | HFTD Tier 2 | Distribution | 2022-10-17 | 2025-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009284 | 718749523-48971-DTLSB-05_29_2026-GO95HV-1^07216001.0023700 | OTHER | Non-HFTD | Distribution | 2026-05-29 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009285 | 719223463-58771-ADMIN-11_14_2025-GUYSLACK-1^07216001.0214902 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-11-14 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009286 | 719327068-16159-DETAIL-07_07_2026-INSULBRK-1^668041/00 1/017 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009287 | 719327068-16159-DTLTRT-06_09_2021-INSULBRK-1^668041/00 1/017 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009288 | 719327068-16159-DTLTRT-06_09_2021-UBPBCTGD-1^668041/00 1/017 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009289 | 719589731-14309-DETAIL-05_08_2025-SVCROAD-1^06243006.0162201 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009290 | 720333188-73540-DETAIL-02_09_2026-GO95HV-1^06239003.0018200 | OTHER | Non-HFTD | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009291 | 720592670-20899-DETAIL-09_30_2025-GO95BLTC-1^06246009.0133702 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009292 | 720777351-5391-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | Non-HFTD | Transmission | 2024-04-10 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009293 | 720777351-65180-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | Non-HFTD | Transmission | 2024-04-10 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009294 | 721027312-75983-DETAIL-08_21_2025-GO95HV-1^07216001.0176100 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009295 | 721298408-34830-DETAIL-01_14_2025-GO95MLD-1^06240004.0079841 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009296 | 721336295-56909-DETAIL-08_13_2025-GO95HV-1^06247006.0254700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009297 | 721603752-71903-DETAIL-05_05_2025-GO95HV-1^06243006.0347840 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009298 | 721731798-60169-DETAIL-09_17_2025-GO95HV-1^06248007.0364801 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009299 | 721755841-39081-DTLSB-05_07_2026-ENCHRW-1^06142013.0345501 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009300 | 721946761-53980-DETAIL-02_18_2026-GO95HV-1^06239001.0069602 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009301 | 722347225-91949-DTLSB-06_10_2026-SVCROAD-1^07217001.0350104 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009302 | 722531609-87179-DETAIL-10_07_2025-GO95HV-1^06148001.0264000 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009303 | 722560993-74280-DETAIL-02_11_2025-GO95MLD-1^06240004.0355200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009304 | 722680931-53680-DETAIL-02_23_2026-GO95HV-1^06239002.0039500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009305 | 722716466-20881-DTLSB-10_16_2025-GRDRODHI-1^06247001.0351000 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009306 | 72281636-59959-DTLSB-08_18_2025-GO95HV-1^07218001.0355902 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009307 | 723181781-79919-DRONE_HY-07_15_2026-UBPRMSHD-1^668036/00 6/054 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | A | [7 empty] | PC | 2026 | 2
1120009308 | 723199657-50790-AUDIT-01_26_2026-GO95MLD-1^06239004.0245603 | OTHER | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009309 | 723199657-50790-DETAIL-01_30_2025-GO95MLD-1^06239004.0245603 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009310 | 723312999-66669-DTLSB-03_25_2026-SVCDEFLC-1^06242009.0047000 | OTHER | Non-HFTD | Distribution | 2026-03-25 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009311 | 723574151-89401-DETAIL-04_15_2025-GO95TCH-1^06242005.0333700 | OTHER | HFTD Tier 2 | Distribution | 2025-04-15 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009312 | 723797451-53609-DETAIL-01_17_2023-GO95HV-1^06148004.0223003 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2028-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009313 | 723855148-16749-DTLSB-07_16_2025-GO95HV-1^06244006.0292601 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009314 | 723927549-69159-DETAIL-05_07_2026-GO95CLMP-1^668004/00 16/024 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009315 | 723927549-69159-DETAIL-05_07_2026-GO95HV-1^668004/00 16/024 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009316 | 724306337-38337-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244603 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009317 | 724306337-38337-DETAIL-01_12_2026-COVCOTHR-2^06239004.0244603 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009318 | 724306337-38337-DETAIL-01_12_2026-COVCOTHR-3^06239004.0244603 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009319 | 724897351-52691-DTLTRT-05_20_2026-GO95HV-1^668086/00 10/010 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009320 | 725494375-75159-DETAIL-07_30_2025-GO95HV-1^06247005.0026001 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009321 | 725614684-68519-DTLTRT-08_17_2022-GO95MLD-1^668005/00 1/095 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009322 | 7257531-5799-DETAIL-09_18_2025-GO95HV-1^06246006.0014401 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009323 | 725983595-19779-DTLSB-08_18_2020-CUSTWIRE-1^06247005.0024100 | OTHER | Non-HFTD | Distribution | 2020-08-18 | 2023-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009324 | 726013094-2659-DETAIL-07_28_2025-GO95HV-1^06247005.0301400 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009325 | 726072631-75909-DETAIL-09_08_2025-GO95HV-1^06247006.0211601 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009326 | 726777106-45659-DETAIL-07_28_2025-GO95HV-1^06247005.0318100 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009327 | 726791880-13568-DETAIL-05_28_2025-GO95HV-1^06244006.0094400 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009328 | 726854203-1491-DTLSB-05_28_2024-GO95MLD-1^06243001.0125004 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009329 | 726927344-94522-DETAIL-04_07_2025-ANCHIDLE-1^06241005.0027005 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009330 | 727101716-27799-DETAIL-05_27_2025-GO95HV-1^06244006.0040301 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009331 | 727425543-48789-DETAIL-06_10_2025-GO95HV-1^06245006.0197600 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009332 | 727791900-39559-DETAIL-06_18_2025-GO95HV-1^06248004.0341902 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009333 | 727806113-50339-DETAIL-11_17_2025-GO95HV-1^06243007.0011401 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009334 | 727819369-98999-DETAIL-08_25_2025-GO95HV-1^06247006.0281201 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009335 | 727954485-52101-DETAIL-08_25_2025-GO95HV-1^06246001.0174004 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009336 | 728322101-823-DETAIL-06_17_2025-GO95HV-1^06248004.0349340 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009337 | 728332946-22009-DETAIL-03_31_2026-COVCOTHR-1^06240004.0357101 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009338 | 728550572-59049-DTLSB-07_16_2025-GO95HV-1^06244006.0234002 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009339 | 728637610-33701-DETAIL-09_04_2025-GO95HV-1^06247006.0288900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009340 | 72881401-97043-DETAIL-07_01_2026-CLRTOUCH-1^07217001.0169600 | CONDUCTOR | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009341 | 72881401-97043-DETAIL-07_01_2026-GO95HV-1^07217001.0169600 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009342 | 728821153-55153-DETAIL-03_25_2025-GO95HV-1^06239003.0019320 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009343 | 72900783-94839-DTLTRT-05_13_2026-GO95MLD-1^668085/00 9/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009344 | 72900783-94839-DTLTRT-05_13_2026-GRDRODHI-1^668085/00 9/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009345 | 729037249-8899-DTLTRT-08_14_2023-CUSTWIRE-1^06243009.0244404 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009346 | 729134485-76410-DETAIL-03_12_2025-GO95HV-1^06238004.0222501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009347 | 729330928-99150-DETAIL-02_24_2026-GO95HV-1^06239003.0132302 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009348 | 729450050-24389-DTLSB-07_01_2025-GO95CL10-1^06244007.0132400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009349 | 729453995-66603-DTLSB-06_03_2026-CLRTOPOL-1^07216001.0027301 | OTHER | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009350 | 729453995-66603-DTLSB-06_03_2026-CLRTOUCH-1^07216001.0027301 | CONDUCTOR | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009351 | 729668530-701-DETAIL-10_06_2025-GO95HV-1^06148001.0310904 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009352 | 730029089-46739-DTLTRT-06_25_2025-GO95HV-1^668087/00 3/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009353 | 730029089-46739-DTLTRT-06_25_2025-GRDRODHI-1^668087/00 3/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009354 | 730150745-11491-DTLTRT-05_12_2026-GO95HV-1^668038/00 3/044 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009355 | 730150745-43301-DTLTRT-05_12_2026-GO95HV-1^668038/00 3/044 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009356 | 730230283-16009-DETAIL-08_12_2025-GO95HV-1^06247006.0251300 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009357 | 730314900-5599-DTLSB-07_02_2025-GO95BLTC-1^06244007.0136201 | OTHER | HFTD Tier 2 | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009358 | 730415759-35759-DETAIL-03_23_2026-SVCTREE-1^06240004.0226504 | OTHER | HFTD Tier 3 | Distribution | 2026-03-23 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009359 | 730764270-83739-DTLSB-07_22_2025-GO95HV-1^06244006.0181300 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009360 | 731238996-49970-DETAIL-01_23_2025-GO95CL10-1^06239004.0256646 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009361 | 732086253-72251-DETAIL-04_15_2025-GO95TCH-1^06242005.0336500 | OTHER | HFTD Tier 2 | Distribution | 2025-04-15 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009362 | 732098541-62180-DETAIL-02_18_2026-GO95HV-1^06239002.0044400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009363 | 732400739-53799-DETAIL-06_16_2025-GO95HV-1^06248004.0354540 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009364 | 732479580-41601-DETAIL-01_14_2026-GO95MLD-1^06239004.0135103 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009365 | 733022736-5849-DTLSB-07_09_2025-GO95HV-1^06244007.0142802 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009366 | 733171805-33805-DETAIL-02_19_2025-GUYHINS-1^06240004.0100200 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009367 | 733315925-74800-DETAIL-04_08_2026-BIRDDMG-1^06240002.0311203 | POLE | HFTD Tier 2 | Distribution | 2026-04-08 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009368 | 733454594-86822-DETAIL-10_16_2025-GO95BLTC-1^06246012.0137501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009369 | 733454594-86822-DETAIL-10_16_2025-SVCDEFLC-1^06246012.0137501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009370 | 733742810-10640-DETAIL-03_05_2026-COVCOTHR-1^06238004.0012600 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009371 | 733949403-4841-DETAIL-03_05_2025-GUYHINS-2^06241005.0131904 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009372 | 733990661-53309-DETAIL-07_29_2025-GO95HV-1^06247006.0206000 | OTHER | HFTD Tier 2 | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009373 | 734201086-73811-DETAIL-08_12_2025-GO95HV-1^06246001.0198402 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009374 | 734326099-62648-DTLSB-07_16_2025-GO95HV-1^06244006.0319800 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009375 | 734638989-67170-DETAIL-04_11_2023-CUSTWIRE-1^06240004.0167548 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009376 | 734704132-58139-DETAIL-05_06_2025-GO95HV-1^06243006.0064500 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009377 | 734976650-87471-DETAIL-04_08_2025-GUYHINS-1^06241005.0093300 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009378 | 735103558-48742-DETAIL-04_17_2025-GO95HV-1^06242006.0034902 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009379 | 735186650-82929-DTLSB-01_15_2026-SVCENTCO-1^06242009.0328800 | OTHER | Non-HFTD | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009380 | 735252736-80836-DTLTRT-07_08_2025-GO95HV-1^668087/00 1/027 | OTHER | Non-HFTD | Transmission | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009381 | 735302023-68629-DTLSB-01_21_2026-CUSTWIRE-1^06242009.0296001 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009382 | 73551701-27080-DETAIL-02_16_2026-GO95HV-1^06239001.0054701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009383 | 735613004-10711-DETAIL-04_28_2026-GO95HV-1^06142012.0149511 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009384 | 735613004-10711-DETAIL-04_28_2026-GUYHINS-1^06142012.0149511 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009385 | 735694946-64509-ADMIN-11_10_2025-GO95BLTC-1^06246011.0065403 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009386 | 735767239-67711-ADMIN-11_12_2025-GUYHINS-1^06246001.0346400 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009387 | 73577418-29929-DETAIL-04_21_2026-GO95HV-1^06142012.0149801 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009388 | 73586841-8841-DTLSB-01_20_2026-SVCDEFLC-1^06242009.0298007 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009389 | 735958488-77591-DTLTRT-05_06_2026-GO95HV-1^668038/00 1/057 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009390 | 736500446-15721-DTLSB-05_06_2026-GO95HV-1^06142013.0220201 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009391 | 73651133-81619-DTLSB-04_23_2026-GO95BLTC-1^06241009.0224101 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009392 | 736756009-65421-DTLTRT-06_24_2025-GUYHINS-1^668087/00 2/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009393 | 736763050-40840-DETAIL-02_10_2025-GO95MLD-1^06239003.0071907 | OTHER | HFTD Tier 3 | Distribution | 2025-02-10 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009394 | 736995439-73952-DTLSB-07_15_2025-GO95HV-1^06244006.0307142 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009395 | 737368260-72099-DTLSB-07_01_2025-GO95HV-1^06244006.0225406 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009396 | 737671153-54699-DETAIL-08_06_2025-GO95HV-1^06247005.0301902 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009397 | 737949868-10968-DETAIL-01_29_2026-GO95BLTC-1^06242009.0052503 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009398 | 737998558-25469-DETAIL-09_02_2025-GRDRODHI-1^06247006.0275900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009399 | 738094749-12421-DETAIL-09_05_2025-ABNDEQPM-1^06147001.0294701 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009400 | 738184154-47154-DETAIL-03_29_2023-CUSTWIRE-1^06142016.0085901 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009401 | 738265350-47022-DTLTRT-04_27_2026-GO95HV-1^668004/00 3/005 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009402 | 738265350-47022-DTLTRT-04_27_2026-GUYNOINS-1^668004/00 3/005 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009403 | 738265350-91521-DTLTRT-04_27_2026-GO95HV-1^668004/00 3/005 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009404 | 738462123-95780-DETAIL-02_24_2026-GO95HV-1^06239002.0181700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009405 | 738614161-89673-DETAIL-09_10_2025-GO95TCH-1^06246006.0184302 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009406 | 738614161-89673-DETAIL-09_10_2025-SVCENTCO-1^06246006.0184302 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009407 | 738777509-78569-DTLSB-03_18_2026-GO95HV-1^06242009.0161701 | OTHER | Non-HFTD | Distribution | 2026-03-18 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009408 | 738836184-98809-DETAIL-08_13_2025-GO95HV-1^06247006.0253102 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009409 | 739116147-42999-DTLSB-08_22_2024-CUSTWIRE-1^06245006.0324101 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009410 | 739163140-4640-AUDIT-05_19_2026-ANCHIDLE-1^06237005.0357000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-05-19 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009411 | 739686633-86031-DETAIL-09_10_2025-GO95HV-1^06147001.0186800 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009412 | 739865880-76880-DETAIL-02_27_2025-GO95MLD-1^06240004.0065402 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009413 | 740044025-71653-DTLSB-07_01_2025-GO95HV-1^06244006.0225414 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009414 | 74005074-6353-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0097702 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009415 | 740229285-82649-DETAIL-09_02_2025-GO95HV-1^07216001.0165600 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009416 | 740587141-86330-DETAIL-02_27_2025-GUYNOINS-1^06240004.0154402 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009417 | 740587141-86330-DETAIL-02_27_2025-GUYNOINS-3^06240004.0154402 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009418 | 740698016-92731-DTLSB-04_28_2026-GRDRODHI-1^06142013.0187404 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009419 | 740874256-58359-DETAIL-04_01_2024-CUSTWIRE-1^06247005.0342503 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009420 | 741080754-76589-DETAIL-10_18_2021-CUSTWIRE-1^06148005.0208001 | OTHER | Non-HFTD | Distribution | 2021-10-18 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009421 | 741302782-12782-DETAIL-02_19_2025-GO95HV-1^06240004.0219914 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009422 | 74143908-50100-DETAIL-09_30_2025-GO95HV-1^06148001.0300111 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009423 | 741484833-37930-DTLSB-08_11_2025-GO95HV-1^07218001.0277700 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009424 | 741756663-77663-DTLSB-07_09_2025-GO95HV-1^06244007.0155602 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009425 | 741851478-47690-DETAIL-01_28_2025-GO95HV-1^06239004.0246142 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009426 | 741876355-1079-DETAIL-10_08_2025-GO95CL10-1^06148001.0202600 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009427 | 741944-81683-DETAIL-09_17_2025-GO95STUB-1^07218001.0087200 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009428 | 742609083-41631-DETAIL-09_09_2025-GO95HV-1^06147001.0194400 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009429 | 742670364-18731-DETAIL-09_04_2025-GO95HV-1^06147001.0319200 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009430 | 742949597-24523-DETAIL-05_27_2026-SVCRUBLG-1^07217001.0145103 | OTHER | Non-HFTD | Distribution | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009431 | 743060126-95942-ADMIN-10_22_2025-GO95BLTC-1^06246011.0069403 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009432 | 74310851-51739-DETAIL-05_07_2025-GO95HV-1^06243006.0022500 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009433 | 743198235-30335-DTLSB-06_26_2025-GO95HV-1^06244007.0109800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009434 | 743290724-41740-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 1/039 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009435 | 743629513-53141-DETAIL-04_14_2022-CUSTWIRE-1^06142012.0135404 | OTHER | Non-HFTD | Distribution | 2022-04-14 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009436 | 743730609-38141-DTLSB-06_04_2026-GO95HV-1^07216001.0115300 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009437 | 743730609-38141-DTLSB-06_04_2026-GRDRODHI-1^07216001.0115300 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009438 | 743809826-21179-DTLSB-07_08_2025-GO95HV-1^06244007.0035806 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009439 | 744059184-8329-DETAIL-04_23_2026-GUYHINS-1^06142012.0145703 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009440 | 744288706-94053-DTLSB-06_18_2026-GO95HV-1^07217001.0353803 | OTHER | Non-HFTD | Distribution | 2026-06-18 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009441 | 74431119-74699-DTLSB-02_16_2026-BIRDDMG-1^06243009.0308800 | POLE | HFTD Tier 2 | Distribution | 2026-02-16 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009442 | 744374231-22780-DETAIL-01_23_2026-BIRDDMG-1^06240004.0148000 | POLE | HFTD Tier 3 | Distribution | 2026-01-23 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009443 | 744703791-94178-DETAIL-06_16_2025-GO95HV-1^06248004.0362141 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009444 | 744767720-83269-DETAIL-06_16_2025-GO95HV-1^06248005.0285300 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009445 | 744775003-89209-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0209702 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009446 | 744775003-89209-DETAIL-08_04_2025-SVCDEFLC-2^06247006.0209702 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009447 | 745358513-34180-DETAIL-02_03_2025-GO95TCH-1^06240004.0164900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009448 | 745375364-26364-DETAIL-04_07_2025-GO95BLTC-1^06241005.0027010 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009449 | 745497211-72970-DETAIL-02_17_2026-GO95HV-1^06239002.0090901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009450 | 746297053-80109-DETAIL-08_21_2025-GO95HV-1^06247006.0256805 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009451 | 746434146-53451-DETAIL-08_20_2025-CONDCOIL-1^06246001.0175401 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009452 | 746525213-94480-DETAIL-02_14_2025-GO95HV-1^06240004.0164509 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009453 | 746812831-16201-DETAIL-01_21_2025-GO95HV-1^06239004.0255440 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009454 | 746910633-59680-DETAIL-02_18_2026-BIRDDMG-1^06239002.0165701 | POLE | HFTD Tier 2 | Distribution | 2026-02-18 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009455 | 747011516-64599-ADMIN-04_28_2025-POLEREPL-1^06247005.0347101 | POLE | Non-HFTD | Distribution | 2025-04-28 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009456 | 747407936-2369-DETAIL-08_19_2025-GO95HV-1^06247006.0367300 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009457 | 747483804-39529-DETAIL-05_04_2022-CUSTWIRE-1^06143013.0192600 | OTHER | Non-HFTD | Distribution | 2022-05-04 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009458 | 747496170-17699-DETAIL-06_18_2025-SVCROAD-1^06248004.0340602 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009459 | 747553778-73459-DETAIL-06_17_2025-GO95TCH-1^06248004.0351300 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009460 | 74776578-3839-DETAIL-05_08_2025-GO95HV-1^06243006.0104601 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009461 | 747878130-53201-DETAIL-01_31_2025-GO95HV-1^06239004.0136105 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009462 | 747878130-53201-DETAIL-01_31_2025-GO95MLD-1^06239004.0136105 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009463 | 747914904-88329-DETAIL-04_28_2022-CUSTWIRE-1^06143012.0256603 | OTHER | Non-HFTD | Distribution | 2022-04-28 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009464 | 748087896-21280-DETAIL-04_09_2026-GUYHINS-1^06240003.0368002 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009465 | 748676533-78680-DETAIL-02_23_2026-BIRDDMG-1^06239002.0224900 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009466 | 748724289-11019-DTLSB-04_14_2026-GO95HV-1^06241008.0237300 | OTHER | Non-HFTD | Distribution | 2026-04-14 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009467 | 748739609-46433-DETAIL-09_09_2025-GO95HV-1^07218001.0176300 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009468 | 748874121-37879-DETAIL-10_02_2025-GO95HV-1^06148001.0296500 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009469 | 748981126-48760-DTLTRT-05_04_2026-GO95HV-1^668004/00 6/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009470 | 749357409-62951-DETAIL-10_01_2025-GO95MLD-1^06148001.0302106 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009471 | 749433213-1159-DETAIL-08_19_2025-GO95HV-1^06247006.0367600 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009472 | 749648829-60769-DTLTRT-06_08_2021-GO95HV-1^668041/00 5/014 | OTHER | Non-HFTD | Transmission | 2021-06-08 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009473 | 749805351-33351-DETAIL-05_29_2026-GUYHINS-1^07216001.0020903 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-29 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009474 | 749830688-10730-DETAIL-01_22_2026-COVCOTHR-1^06240003.0305201 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009475 | 749830688-10730-DETAIL-01_22_2026-COVCOTHR-2^06240003.0305201 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009476 | 750019753-34651-DTLTRT-05_13_2026-GRDRODHI-1^668085/00 14/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009477 | 750083235-43399-DETAIL-01_28_2026-GO95BLTC-1^06242009.0050103 | OTHER | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009478 | 750262309-54309-DETAIL-03_31_2026-COVCOTHR-1^06240004.0354300 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009479 | 750262309-54309-DETAIL-03_31_2026-COVCOTHR-2^06240004.0354300 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009480 | 750262309-54309-DETAIL-03_31_2026-COVCOTHR-3^06240004.0354300 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009481 | 750803996-55661-DETAIL-08_07_2025-GO95CLSV-1^06246001.0193000 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009482 | 750911706-68861-DTLSB-03_28_2022-CUSTWIRE-1^06144006.0163100 | OTHER | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009483 | 751193061-29859-DETAIL-09_23_2025-GO95HV-1^06248007.0279500 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009484 | 751675785-21453-DTLSB-06_11_2026-BIRDDMG-1^07217001.0352701 | POLE | Non-HFTD | Distribution | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009485 | 751675785-21453-DTLSB-06_11_2026-GO95MLD-1^07217001.0352701 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009486 | 7519041-95211-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0257244 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009487 | 752038536-10073-DTLSB-06_11_2026-GO95HV-1^07217001.0275240 | OTHER | Non-HFTD | Distribution | 2026-06-11 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009488 | 752168848-75079-DETAIL-09_22_2025-GO95HV-1^06248007.0368403 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009489 | 752285944-30799-DETAIL-05_22_2025-GO95HV-1^06244006.0092202 | OTHER | Non-HFTD | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009490 | 752339746-6019-DTLSB-04_01_2026-GO95HV-1^06241009.0327300 | OTHER | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009491 | 752444553-34261-DTLTRT-05_13_2026-GO95HV-1^668085/00 4/003 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009492 | 752454884-54829-DETAIL-04_20_2026-GO95MLD-1^06142012.0147909 | OTHER | Non-HFTD | Distribution | 2026-04-20 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009493 | 752549951-28022-DTLTRT-04_23_2026-GO95HV-1^668004/00 6/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009494 | 752591980-27670-DETAIL-02_05_2025-SVCDEFLC-1^06240004.0166205 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009495 | 752728406-20506-DETAIL-06_03_2025-GO95HV-1^06148014.0249803 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009496 | 753068270-78068-DETAIL-07_02_2026-CUSTWIRE-1^07217001.0048600 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009497 | 753797600-50700-DETAIL-01_30_2025-ABNDEQPM-1^06240004.0162504 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009498 | 753797600-50700-DETAIL-01_30_2025-GO95BLTC-1^06240004.0162504 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009499 | 753832548-76959-DETAIL-07_29_2025-GO95HV-1^06247005.0266401 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009500 | 754260423-20489-DTLSB-07_21_2025-GO95HV-1^06244006.0258900 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009501 | 754534089-41570-DETAIL-04_02_2026-GUYHINS-1^06236005.0151040 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-02 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009502 | 754534089-41570-DETAIL-06_11_2025-ABNDEQPM-1^06236005.0151040 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009503 | 754534089-41570-DETAIL-06_11_2025-GO95HV-1^06236005.0151040 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009504 | 754601623-91721-DETAIL-04_15_2026-GO95MLD-1^06237004.0206500 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009505 | 754601623-91721-DETAIL-04_15_2026-SVCTREE-1^06237004.0206500 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009506 | 754623856-32542-ADMIN-10_22_2025-GO95BLTC-1^06246011.0067402 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009507 | 754759130-84170-DETAIL-02_13_2025-GO95CL10-1^06240004.0169106 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009508 | 754904216-54759-DETAIL-04_30_2026-GO95HV-1^668004/00 10/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009509 | 754904216-54760-DETAIL-04_30_2026-GO95HV-1^668004/00 10/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009510 | 755087728-80489-DETAIL-09_03_2025-GO95HV-1^06146001.0080801 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009511 | 755246903-80863-DETAIL-03_11_2025-GO95HV-1^06238004.0274805 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009512 | 755592811-4811-DETAIL-05_14_2025-GO95HV-1^06242006.0196622 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009513 | 755719910-7049-DTLSB-06_30_2025-GO95HV-1^06244006.0225302 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009514 | 755776166-5499-DETAIL-05_27_2025-GO95TCH-1^06244006.0053700 | OTHER | HFTD Tier 2 | Distribution | 2025-05-27 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009515 | 756580346-98699-ADMIN-10_22_2025-GO95BLTC-1^06246011.0056800 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009516 | 756841344-95953-DETAIL-06_26_2026-CUSTWIRE-1^07217001.0097901 | OTHER | Non-HFTD | Distribution | 2026-06-26 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009517 | 757004212-67370-DETAIL-01_22_2025-GO95TCH-1^06240004.0087003 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009518 | 757110105-97571-DTLSB-05_13_2024-GO95MLD-1^06245001.0294300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009519 | 757206446-8210-DETAIL-02_04_2026-GO95HV-1^06239003.0019802 | OTHER | Non-HFTD | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009520 | 757206446-8210-DETAIL-04_01_2025-GO95MLD-1^06239003.0019802 | OTHER | Non-HFTD | Distribution | 2025-04-01 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009521 | 757210700-77799-DETAIL-03_07_2024-INSULDMG-1^06147004.0238500 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009522 | 75749410-20870-DETAIL-02_04_2025-SVCDEFLC-1^06240004.0167603 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009523 | 757522175-80771-DETAIL-03_10_2022-CUSTWIRE-1^06147006.0273200 | OTHER | Non-HFTD | Distribution | 2022-03-10 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009524 | 758029101-8643-DETAIL-07_07_2026-GO95HV-1^07217001.0165800 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009525 | 758119615-73059-DETAIL-09_23_2025-GO95HV-1^06247004.0181701 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009526 | 758129348-57949-DTLSB-06_25_2025-GRDRODHI-1^06244007.0035801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009527 | 758328435-33949-DETAIL-06_10_2025-GO95HV-1^06245006.0288000 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009528 | 75842275-45041-DETAIL-04_10_2025-GO95TCH-1^06241005.0010641 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009529 | 758472371-65999-DETAIL-10_02_2025-GUYHINS-1^06246008.0065101 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009530 | 759058724-83362-AUDIT-06_25_2025-GO95HV-1^06242005.0362042 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009531 | 759153688-75390-DETAIL-01_12_2026-COVCOTHR-2^06239004.0244411 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009532 | 759153688-75390-DETAIL-01_12_2026-SVCROAD-1^06239004.0244411 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009533 | 759760635-23951-DETAIL-02_24_2025-GO95HV-1^06239004.0366803 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009534 | 759760635-23951-DETAIL-02_24_2025-SVCROAD-1^06239004.0366803 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009535 | 760659161-29439-DTLTRT-06_26_2025-CLRTOUCH-1^668087/00 6X/009 | CONDUCTOR | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009536 | 760659161-29439-DTLTRT-06_26_2025-GO95CL10-1^668087/00 6X/009 | OTHER | Non-HFTD | Transmission | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009537 | 760659161-29439-DTLTRT-06_26_2025-GUYHINS-1^668087/00 6X/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009538 | 760697641-55081-DTLTRT-05_20_2026-CUSTWIRE-1^668086/00 4/011 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009539 | 760808386-89989-DETAIL-07_29_2025-GO95HV-1^06247005.0269603 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009540 | 760887688-49342-DETAIL-04_23_2025-GO95HV-1^06242006.0038400 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009541 | 760933733-98509-DETAIL-09_10_2025-SVCDEFLC-1^06246006.0077001 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009542 | 760966156-79560-DETAIL-06_04_2025-GO95HV-1^668075/00 1/016 | OTHER | HFTD Tier 2 | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009543 | 760966156-79560-DETAIL-06_04_2025-GUYHINS-1^668075/00 1/016 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009544 | 761496256-83150-DETAIL-09_23_2025-GO95TCH-1^07218001.0232004 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009545 | 761843515-26049-DTLSB-07_01_2025-GO95HV-1^06244006.0225403 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009546 | 761855621-3430-DTLTRT-05_28_2025-GO95HV-1^668075/00 12/005 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009547 | 761871945-41589-DTLSB-01_27_2026-SVCROAD-1^06242009.0057400 | OTHER | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009548 | 762263476-21399-DETAIL-04_01_2024-CUSTWIRE-2^06147005.0124900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009549 | 762263541-33530-DTLTRT-05_28_2025-GO95HV-1^668075/00 16/005 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009550 | 762265881-36291-DTLSB-05_28_2026-SVCDEFLC-1^07216001.0020503 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009551 | 762436119-67391-DETAIL-09_08_2025-GO95HV-1^06147001.0326201 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009552 | 762618609-48391-DETAIL-07_08_2020-CUSTWIRE-1^06148015.0310700 | OTHER | HFTD Tier 2 | Distribution | 2020-07-08 | 2023-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009553 | 76275383-91069-DETAIL-09_18_2025-GO95HV-1^06248007.0265500 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009554 | 76304195-27419-DETAIL-05_30_2024-CUSTWIRE-1^06246005.0272900 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009555 | 763053677-99491-DTLTRT-06_23_2025-GO95BLTC-1^668087/00 14/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009556 | 763142629-46629-DTLSB-02_04_2026-BIRDDMG-1^06243009.0321401 | POLE | HFTD Tier 2 | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009557 | 763142629-46629-DTLSB-02_04_2026-GO95HV-1^06243009.0321401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009558 | 763271263-38899-DETAIL-09_04_2025-GO95HV-1^06247006.0072102 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009559 | 763329165-80500-DETAIL-02_12_2026-GO95HV-1^06239003.0242001 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009560 | 763465928-2689-DETAIL-09_03_2025-GRDRODHI-2^06247006.0295200 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009561 | 763480798-65969-DTLTRT-04_04_2024-CUSTWIRE-1^668067/00 8/025 | OTHER | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009562 | 763484633-18819-DRONE_HY-07_15_2026-UBPBXARM-1^668036/00 9/056 | CROSSARM | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009563 | 763556146-69349-DTLSB-07_15_2025-GO95MLD-1^06244006.0271801 | OTHER | Non-HFTD | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009564 | 763658780-93139-DTLTRT-07_10_2025-ABNDEQPM-1^668087/00 8/024 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009565 | 763658780-93139-DTLTRT-07_10_2025-BIRDDMG-1^668087/00 8/024 | POLE | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009566 | 763658780-93139-DTLTRT-07_10_2025-GO95HV-1^668087/00 8/024 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009567 | 764022569-74713-DETAIL-07_23_2024-ABNDEQPM-1^06245006.0141001 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2029-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009568 | 764038874-53453-DETAIL-09_23_2025-GO95MLD-1^07218001.0229302 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009569 | 764267039-29039-DTLTRT-07_01_2025-BIRDDMG-1^668087/00 9/015 | POLE | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009570 | 764548388-8769-DTLSB-02_09_2026-GRDRODHI-1^06243009.0326500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009571 | 764795102-22491-DETAIL-07_13_2023-CUSTWIRE-1^06244008.0272101 | OTHER | HFTD Tier 2 | Distribution | 2023-07-13 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009572 | 76484897-36103-DTLSB-07_22_2024-CUSTWIRE-1^06245006.0062441 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009573 | 76493486-87209-DETAIL-08_12_2025-GO95HV-1^06247006.0265100 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009574 | 765040259-49733-DTLSB-06_24_2026-SVCENTBK-1^07217001.0344904 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009575 | 765181102-47980-DETAIL-02_25_2025-SVCNEUT-1^06240005.0019101 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009576 | 765689373-44059-DETAIL-09_05_2025-GO95HV-1^06247006.0061402 | OTHER | HFTD Tier 2 | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009577 | 765909360-81243-DETAIL-07_07_2026-ABNDEQPM-1^07217001.0153700 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009578 | 765930986-56450-DETAIL-09_15_2025-GO95MLD-1^07219001.0334301 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009579 | 766265365-72429-DETAIL-05_13_2025-XARMSPCR-1^06142012.0016506 | CROSSARM | Non-HFTD | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009580 | 766276768-13849-DTLSB-04_22_2024-SVCENTCO-1^06245007.0225401 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009581 | 766585380-55701-DETAIL-02_06_2025-GO95MLD-1^06239004.0135205 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009582 | 766585380-55701-DETAIL-02_06_2025-GO95TCH-1^06239004.0135205 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009583 | 766589971-70179-DETAIL-10_07_2025-GO95CL10-1^06148001.0311903 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009584 | 76659464-44239-ADMIN-03_03_2026-POLEDERP-1^07216001.0199307 | POLE | Non-HFTD | Distribution | 2026-03-03 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009585 | 766728789-29499-AUDIT-05_06_2025-GUYHINS-1^06242006.0091003 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009586 | 766728789-29499-DETAIL-04_28_2025-ENCHRW-1^06242006.0091003 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009587 | 767044154-39339-DETAIL-10_06_2025-GO95HV-1^06243007.0363402 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009588 | 767852661-55322-DTLTRT-04_27_2026-GO95HV-1^668004/00 7/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009589 | 767913008-98089-DETAIL-08_14_2025-GO95HV-1^06246002.0254500 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009590 | 768100316-48202-DETAIL-08_05_2025-GO95HV-1^06246002.0134004 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009591 | 768263925-85509-ADMIN-10_22_2025-GO95HV-1^06246011.0067300 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009592 | 768341230-96470-DETAIL-02_18_2026-GO95HV-1^06239002.0040301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009593 | 76876293-70759-DETAIL-07_29_2025-BIRDDMG-1^06247005.0216601 | POLE | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009594 | 769069383-34329-DETAIL-04_25_2022-CUSTWIRE-1^06143012.0253704 | OTHER | Non-HFTD | Distribution | 2022-04-25 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009595 | 769131993-13860-DTLTRT-06_30_2025-GUYNOINS-1^668087/00 13/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009596 | 769131993-13860-DTLTRT-06_30_2025-GUYNOINS-2^668087/00 13/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009597 | 769131993-13860-DTLTRT-06_30_2025-GUYNOINS-4^668087/00 13/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009598 | 769250203-47151-DETAIL-04_08_2025-GUYHINS-1^06241005.0026509 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009599 | 769545503-43980-DETAIL-02_11_2025-GO95MLD-1^06240004.0355404 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009600 | 769686270-99278-DETAIL-08_27_2025-GO95HV-1^06247006.0173400 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009601 | 769925116-29939-DETAIL-05_15_2025-GO95BLTC-1^06243006.0094201 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009602 | 769980726-29953-DTLSB-06_16_2026-GRDRODHI-1^07217001.0356902 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009603 | 770154269-16269-DTLSB-08_14_2025-GO95HV-1^07218001.0358901 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009604 | 77017278-30060-DTLTRT-05_06_2026-GO95HV-1^668004/00 6/021 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009605 | 770208478-11802-DETAIL-03_05_2025-GO95MLD-1^06241005.0121002 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009606 | 770409056-87312-DTLTRT-05_05_2026-GO95HV-1^06142013.0178200 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009607 | 770791198-12970-DETAIL-03_23_2026-COVCOTHR-2^06240004.0227501 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009608 | 770976249-37249-DETAIL-08_04_2025-GO95HV-1^06247006.0208803 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009609 | 771025414-68431-DETAIL-01_14_2025-GO95HV-1^06239004.0255101 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009610 | 771025414-68431-DETAIL-01_14_2025-SVCROAD-1^06239004.0255101 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009611 | 771255638-21740-DETAIL-02_09_2026-ABNDEQPM-1^06239003.0018001 | OTHER | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009612 | 771332789-78949-DTLSB-06_24_2026-GO95TCH-1^07217001.0346403 | OTHER | Non-HFTD | Distribution | 2026-06-24 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009613 | 771587443-50279-DETAIL-09_15_2025-GO95HV-1^06248007.0233300 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009614 | 77165274-10979-DETAIL-09_23_2025-GO95HV-1^06247004.0075500 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009615 | 771868094-39129-DTLSB-05_04_2026-GO95HV-1^06142013.0051300 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009616 | 771872543-34912-DETAIL-06_10_2026-GUYHINS-1^668086/00 9/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009617 | 771872543-34912-DETAIL-06_10_2026-GUYHINS-3^668086/00 9/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009618 | 772226453-80429-DETAIL-05_12_2025-GO95HV-1^06142012.0016901 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009619 | 772608391-28879-DETAIL-10_02_2025-GO95HV-1^06148001.0297500 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009620 | 772859397-46139-DTLSB-08_14_2025-GO95MLD-1^07218001.0350801 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009621 | 773055759-98151-DETAIL-04_08_2025-GO95MLD-1^06241005.0092202 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009622 | 773157776-70970-DETAIL-01_23_2025-GO95TCH-1^06239004.0256740 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009623 | 774008336-86569-DETAIL-01_23_2025-GO95HV-1^06240004.0082203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009624 | 774008336-86569-DETAIL-01_23_2025-SVCDEFLC-1^06240004.0082203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009625 | 774433368-10899-DTLSB-01_21_2026-GO95HV-1^06242009.0297110 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009626 | 774457918-98069-DETAIL-05_07_2025-GO95HV-1^06243006.0096803 | OTHER | HFTD Tier 2 | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009627 | 774782299-16781-DETAIL-02_24_2025-GO95HV-1^06241005.0153202 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009628 | 774879768-96829-DETAIL-04_22_2025-GO95HV-1^06242006.0165900 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009629 | 774986832-54559-DETAIL-02_27_2024-GO95MLD-1^07113002.0182402 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009630 | 774986832-54559-DETAIL-02_27_2024-GUYHINS-1^07113002.0182402 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009631 | 775083698-82949-DETAIL-09_04_2025-GO95HV-1^07216001.0099500 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009632 | 775130675-12289-AUDIT-05_18_2026-CLRTOUCH-1^06241009.0134701 | CONDUCTOR | Non-HFTD | Distribution | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009633 | 775146820-44722-DTLTRT-04_27_2026-GO95HV-1^668004/00 2/005 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009634 | 775258205-41000-DTLTRT-05_12_2026-GO95HV-1^668038/00 4/045 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009635 | 775258205-90191-DTLTRT-05_12_2026-GO95HV-1^668038/00 4/045 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009636 | 775485121-46799-DETAIL-10_07_2025-GO95BLTC-1^06246008.0057502 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009637 | 775570499-1449-DETAIL-06_03_2024-CUSTWIRE-1^06246006.0358002 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009638 | 775917185-4080-DETAIL-06_05_2025-GO95HV-1^06148014.0239402 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009639 | 775917185-4080-DETAIL-06_05_2025-XARMSPCR-1^06148014.0239402 | CROSSARM | Non-HFTD | Distribution | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009640 | 776234411-87042-DETAIL-04_07_2025-GO95MLD-1^06241005.0118503 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009641 | 776278424-55183-DETAIL-09_11_2025-GO95HV-1^06248007.0222901 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009642 | 776293765-56765-DETAIL-06_03_2025-GO95HV-1^06148014.0248500 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009643 | 776348368-66630-DETAIL-01_26_2026-GO95MLD-1^06240003.0304302 | OTHER | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009644 | 776414586-24922-DTLSB-05_04_2026-GRDRODHI-1^06142013.0175502 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009645 | 776773324-84183-DETAIL-09_11_2025-GO95HV-1^06248007.0152000 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009646 | 776815081-13809-DETAIL-08_25_2025-GO95HV-1^06247006.0211004 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009647 | 776968610-41022-DTLSB-07_24_2023-CUSTWIRE-1^06243010.0025800 | OTHER | HFTD Tier 2 | Distribution | 2023-07-24 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009648 | 777133633-22709-DETAIL-08_30_2021-SVCWIND-1^06148004.0354410 | OTHER | Non-HFTD | Distribution | 2021-08-30 | 2024-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009649 | 777224164-65622-DTLTRT-06_30_2025-GUYHINS-1^668087/02 6/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009650 | 777224164-65622-DTLTRT-06_30_2025-GUYHINS-2^668087/02 6/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009651 | 777227939-85622-DETAIL-08_21_2025-GO95HV-1^06246001.0208401 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009652 | 777342780-52859-DTLSB-07_28_2025-CUSTWIRE-1^07218001.0269204 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009653 | 777430726-45593-DETAIL-07_29_2025-GO95HV-1^06247005.0279202 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009654 | 77797994-52700-DTLTRT-06_23_2025-GO95BLTC-1^668087/02 1/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009655 | 778183337-3232-DETAIL-08_11_2025-GO95HV-1^06246002.0232101 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009656 | 778265885-72600-DETAIL-02_11_2026-BIRDDMG-1^06239003.0016702 | POLE | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009657 | 778593779-95359-DETAIL-07_22_2025-GO95HV-1^06247005.0058300 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009658 | 778679778-50250-DETAIL-03_26_2025-GO95HV-1^06239003.0018302 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009659 | 778718161-39171-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135701 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009660 | 779112178-49689-DETAIL-06_17_2025-GO95HV-1^06248004.0298000 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009661 | 779128438-14349-DETAIL-03_14_2024-ENCHRW-1^06245006.0120900 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009662 | 779213683-4732-DRONE_HY-07_10_2026-DISTHDWR-1^06143014.0188200 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009663 | 779226786-61959-ADMIN-02_13_2026-POLEREPL-1^06247005.0353800 | POLE | Non-HFTD | Distribution | 2026-02-13 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009664 | 779534079-82889-DETAIL-08_13_2025-GO95HV-1^06246002.0367700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009665 | 779539761-64280-DETAIL-02_16_2026-GO95HV-1^06239001.0045700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009666 | 779653074-53132-DETAIL-09_22_2025-GUYHINS-1^06147001.0257301 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009667 | 779722151-2232-DETAIL-05_18_2026-GO95HV-1^668086/00 10/009 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009668 | 779725598-1730-DETAIL-01_26_2026-COVCOTHR-1^06240003.0305100 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009669 | 779725598-1730-DETAIL-01_26_2026-GUYHINS-1^06240003.0305100 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009670 | 779762469-3532-DETAIL-08_11_2025-GO95HV-1^06246002.0277700 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009671 | 779943278-83570-DETAIL-03_23_2026-COVCOTHR-1^06240004.0222603 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009672 | 779943278-83570-DETAIL-03_23_2026-COVCOTHR-2^06240004.0222603 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009673 | 779943278-83570-DETAIL-03_23_2026-COVCOTHR-4^06240004.0222603 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009674 | 780331572-68979-DETAIL-07_29_2025-GO95HV-1^06247005.0210802 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009675 | 780571105-77440-DETAIL-02_24_2025-SVCDEFLC-1^06240004.0151700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009676 | 780571199-49919-DTLSB-05_19_2026-GO95HV-1^06240007.0060000 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009677 | 780692512-71932-DETAIL-08_14_2025-GO95HV-1^06246001.0311701 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009678 | 780693339-81932-DETAIL-10_01_2025-GO95HV-1^06148001.0300106 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009679 | 780728749-50259-DETAIL-08_26_2025-GO95HV-1^06247006.0330301 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009680 | 780948823-69132-DETAIL-02_16_2023-ABNDEQPM-2^06247002.0165400 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009681 | 781409632-82033-DETAIL-05_08_2025-GO95HV-1^06243006.0218000 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009682 | 781572304-6349-ADMIN-06_19_2024-POLEDERP-1^07216001.0198311 | POLE | Non-HFTD | Distribution | 2024-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009683 | 782280449-87592-DTLSB-07_17_2025-GO95HV-1^06244006.0197240 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009684 | 782648812-61742-DETAIL-08_14_2025-GO95HV-1^06246001.0312700 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009685 | 782660504-3209-DETAIL-07_30_2025-SVCENTCO-1^06247006.0205400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009686 | 782675398-24750-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0164740 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009687 | 782711340-64742-DETAIL-03_13_2024-GO95HV-1^06147004.0180101 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009688 | 782828779-70829-DETAIL-04_22_2025-GO95HV-1^06242006.0091200 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009689 | 783025715-4279-DETAIL-10_08_2025-GO95HV-1^06148001.0189300 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009690 | 783529723-37529-DETAIL-05_12_2025-GO95HV-1^06142012.0010902 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009691 | 783723731-45709-DETAIL-10_02_2025-GUYHINS-1^06246008.0053500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009692 | 783723731-45709-DETAIL-10_02_2025-GUYHINS-2^06246008.0053500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009693 | 783746501-94663-ADMIN-01_10_2025-POLEREPL-1^06245007.0272102 | POLE | Non-HFTD | Distribution | 2025-01-10 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009694 | 783815995-33779-DETAIL-09_23_2025-GO95HV-1^06247004.0180602 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009695 | 783841543-12450-DETAIL-01_15_2026-GO95TCH-1^06239004.0135240 | OTHER | HFTD Tier 3 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009696 | 783852809-92809-DETAIL-08_18_2025-GO95HV-1^06247006.0361000 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009697 | 783873378-5099-ADMIN-07_19_2024-POLETOP-1^06245005.0061600 | POLE | Non-HFTD | Distribution | 2024-07-19 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009698 | 783921794-57599-DETAIL-01_29_2026-GO95BLTC-1^06242009.0053501 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009699 | 784731328-90442-ADMIN-11_12_2025-GO95HV-1^06246001.0282501 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009700 | 784898612-62742-DTLTRT-06_22_2021-LIGHT-1^668041/00 7/030 | CONNECTION DEVICE | Non-HFTD | Transmission | 2021-06-22 | 2024-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009701 | 785097051-96499-DETAIL-07_31_2025-GO95HV-1^06247006.0204200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009702 | 785098289-35559-DETAIL-08_05_2025-GO95HV-1^06247005.0205200 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009703 | 785271553-12553-DETAIL-06_17_2025-GUYHINS-2^668075/00 18/043 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009704 | 785339639-60029-DETAIL-04_21_2025-GO95HV-1^06242006.0036803 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009705 | 785403453-37742-DETAIL-09_05_2025-GO95HV-1^06147001.0203500 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009706 | 7854256-67259-DETAIL-07_23_2025-GO95HV-1^06247005.0118801 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009707 | 785559325-15800-DETAIL-04_08_2026-BIRDDMG-1^06240002.0311202 | POLE | HFTD Tier 2 | Distribution | 2026-04-08 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009708 | 785602831-43699-DETAIL-05_08_2025-SVCROAD-1^06243006.0162302 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009709 | 786153669-7019-DTLSB-05_19_2026-GO95HV-1^06240007.0183500 | OTHER | Non-HFTD | Distribution | 2026-05-19 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009710 | 78622185-23140-DETAIL-02_24_2025-GO95TCH-1^06240004.0152802 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009711 | 787328745-5600-DETAIL-04_08_2026-GO95HV-1^06240002.0322301 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009712 | 787367161-20789-DETAIL-08_28_2025-GO95HV-1^06247006.0063301 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009713 | 787447432-55989-DTLSB-07_16_2025-GO95HV-1^06244006.0231102 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009714 | 787729363-50589-AUDIT-08_27_2024-CUSTWIRE-1^06244005.0346901 | OTHER | Non-HFTD | Distribution | 2024-08-27 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009715 | 788045219-47019-DTLSB-04_13_2026-GO95HV-1^06241008.0257501 | OTHER | Non-HFTD | Distribution | 2026-04-13 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009716 | 788112111-33532-DTLTRT-05_05_2026-GO95HV-1^668004/00 5/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009717 | 788179998-36259-DETAIL-09_02_2025-GRDRODHI-1^06247006.0276401 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009718 | 788195170-12999-DETAIL-10_13_2025-ABNDEQPM-1^06246010.0241902 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009719 | 788207080-3859-DETAIL-06_16_2025-GO95HV-1^06248005.0333804 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009720 | 788324144-13810-DETAIL-03_17_2025-GO95HV-1^06238004.0157203 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009721 | 788410035-56799-DTLSB-03_02_2017-CUSTWIRE-1^06147005.0266203 | OTHER | Non-HFTD | Distribution | 2017-03-02 | 2020-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009722 | 788523894-79910-DETAIL-03_13_2025-GO95HV-1^06238004.0150001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009723 | 788949165-62319-ADMIN-11_13_2025-GO95HV-1^06247008.0302702 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009724 | 789343456-67162-DETAIL-08_12_2025-GO95HV-1^06246001.0195600 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009725 | 789418826-22000-DETAIL-02_05_2026-SVCDEFLC-1^06239003.0017700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009726 | 789811591-28589-DTLSB-01_26_2026-BIRDDMG-1^06242009.0296600 | POLE | HFTD Tier 2 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009727 | 789973046-22299-DTLSB-03_31_2026-GRDRODHI-1^06241009.0326607 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009728 | 79025024-64234-DTLTRT-06_08_2021-GO95HV-1^668041/00 1/014 | OTHER | Non-HFTD | Transmission | 2021-06-08 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009729 | 790414071-40399-DTLSB-07_17_2025-GO95HV-1^06244006.0217302 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009730 | 790767370-68570-DETAIL-02_13_2025-GO95HV-1^06240004.0169002 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009731 | 79085850-48559-DETAIL-06_18_2025-GO95HV-1^06248004.0340705 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009732 | 791049304-29561-DETAIL-02_07_2022-CUSTWIRE-1^06241005.0235900 | OTHER | HFTD Tier 3 | Distribution | 2022-02-07 | 2025-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009733 | 791049304-29561-DETAIL-02_07_2022-CUSTWIRE-2^06241005.0235900 | OTHER | HFTD Tier 3 | Distribution | 2022-02-07 | 2025-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009734 | 791176347-87590-AUDIT-02_25_2025-GO95CL10-1^06239004.0244843 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009735 | 791176347-87590-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244843 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009736 | 791214348-21849-DETAIL-08_12_2024-CUSTWIRE-1^06245006.0159301 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009737 | 791295006-99959-DETAIL-07_29_2025-GO95HV-1^06247005.0262501 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009738 | 791435076-55076-DETAIL-01_22_2026-GO95BLTC-1^06239004.0227301 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009739 | 791472410-75770-DETAIL-04_13_2026-BIRDDMG-1^06236005.0346905 | POLE | HFTD Tier 2 | Distribution | 2026-04-13 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009740 | 791472410-75770-DETAIL-04_13_2026-GO95HV-1^06236005.0346905 | OTHER | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009741 | 791656335-57229-DETAIL-04_28_2025-GO95HV-1^06242007.0252902 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009742 | 791770151-3862-DTLTRT-05_12_2026-GO95HV-1^668004/00 9/010 | OTHER | Non-HFTD | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009743 | 791770151-94432-DTLTRT-05_12_2026-GO95HV-1^668004/00 9/010 | OTHER | Non-HFTD | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009744 | 791825036-89110-DETAIL-03_31_2025-GO95HV-1^06239003.0018804 | OTHER | Non-HFTD | Distribution | 2025-03-31 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009745 | 792133541-40019-DRONE_HY-07_15_2026-POLISSUE-1^668036/00 8/054 | POLE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009746 | 79219406-19410-DTLTRT-05_21_2026-GO95MLD-1^668086/00 19/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009747 | 792393905-2489-DETAIL-10_28_2021-ENCHRW-1^06148005.0146103 | OTHER | Non-HFTD | Distribution | 2021-10-28 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009748 | 792447984-69984-DETAIL-04_07_2025-SVCDEFLC-1^06241005.0028010 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009749 | 792476784-35999-DETAIL-09_04_2025-GO95HV-1^06147001.0319501 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009750 | 792643528-62172-DETAIL-08_21_2025-GRDRODHI-1^06246001.0204303 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009751 | 792939515-41615-DETAIL-06_05_2025-GO95HV-1^06148014.0235202 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009752 | 793327204-34360-DETAIL-01_16_2025-SVCROAD-1^06239004.0256209 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009753 | 793327204-34360-DRONE_HY-07_10_2026-COVCOTHR-1^06239004.0256209 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-10 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009754 | 793578676-78579-DTLSB-10_16_2025-GRDRODHI-1^06247001.0354001 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009755 | 793578676-78579-DTLSB-10_16_2025-GRDRODHI-2^06247001.0354001 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009756 | 793578676-78579-DTLSB-10_16_2025-GRDRODHI-3^06247001.0354001 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009757 | 793595344-33429-DETAIL-04_26_2022-CUSTWIRE-1^06143012.0257402 | OTHER | Non-HFTD | Distribution | 2022-04-26 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009758 | 793796405-26472-DETAIL-05_15_2024-GUYHINS-1^06142012.0124601 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009759 | 793837091-18472-DETAIL-04_11_2024-INSULDMG-1^06245002.0144100 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009760 | 793945866-39-DETAIL-05_20_2025-GO95HV-1^06243006.0092201 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009761 | 79396133-32839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0261400 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009762 | 794156984-30883-DETAIL-08_18_2025-GO95HV-1^06247006.0362300 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009763 | 794254106-74106-DRONE_HY-06_19_2026-COVCOTHR-1^06239004.0251700 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009764 | 794254106-74106-DRONE_HY-06_19_2026-COVCOTHR-2^06239004.0251700 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009765 | 794258428-78919-DTLSB-04_15_2026-GO95BLTC-1^06241008.0056000 | OTHER | Non-HFTD | Distribution | 2026-04-15 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009766 | 794690014-79241-DETAIL-04_09_2025-GUYHINS-1^06241005.0037900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-09 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009767 | 795047534-88439-DETAIL-06_10_2026-GUYHINS-1^668086/00 20/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009768 | 795238673-85050-DETAIL-01_24_2025-GO95HV-1^06239004.0258602 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009769 | 795390375-83899-ADMIN-03_06_2026-POLEREPL-1^06248004.0287202 | POLE | HFTD Tier 2 | Distribution | 2026-03-06 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009770 | 795390375-83899-DETAIL-06_18_2025-GO95HV-1^06248004.0287202 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009771 | 79555343-69699-DETAIL-03_23_2020-CUSTWIRE-1^06243006.0100802 | OTHER | Non-HFTD | Distribution | 2020-03-23 | 2023-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009772 | 795950184-40482-DETAIL-08_20_2025-GO95HV-1^06246001.0173602 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009773 | 796207298-19769-DTLSB-07_15_2025-GO95HV-1^06244007.0036905 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009774 | 796207298-19769-DTLSB-07_15_2025-GRDRODHI-2^06244007.0036905 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009775 | 796233145-62479-DETAIL-08_19_2025-GO95HV-1^06247006.0366601 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009776 | 796233145-62479-DETAIL-08_19_2025-POLETOP-1^06247006.0366601 | POLE | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009777 | 796233145-62479-DETAIL-08_19_2025-XARMSPCR-1^06247006.0366601 | CROSSARM | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009778 | 796248368-51450-DETAIL-04_09_2026-BIRDDMG-1^06240003.0082900 | POLE | HFTD Tier 2 | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009779 | 796473571-46999-DETAIL-09_10_2025-GO95HV-1^06246006.0184500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009780 | 796593118-96512-DETAIL-06_20_2023-CUSTWIRE-1^06244009.0356001 | OTHER | Non-HFTD | Distribution | 2023-06-20 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009781 | 796687435-93609-DETAIL-08_28_2025-GO95HV-1^06247006.0192700 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009782 | 796703335-54335-DTLSB-06_26_2025-GO95HV-1^06244007.0109700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-26 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009783 | 796705353-24899-DETAIL-08_18_2025-GO95BLTC-1^06247006.0364702 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009784 | 79672336-98289-DTLSB-01_31_2023-CUSTWIRE-1^06248001.0368806 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009785 | 796871715-47851-DETAIL-04_10_2025-GO95TCH-1^06241005.0012643 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009786 | 797007719-89852-DTLSB-07_15_2025-GO95HV-1^06244006.0308342 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009787 | 797132670-28388-DETAIL-07_06_2026-GUYHINS-1^07217001.0045700 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009788 | 797389552-41070-DETAIL-03_10_2026-GO95HV-1^06238004.0122701 | OTHER | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009789 | 797390982-13639-DETAIL-05_21_2025-GO95HV-1^06243006.0155700 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009790 | 79740835-98800-DETAIL-02_25_2026-GO95HV-1^06239003.0242600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009791 | 797898689-43909-DETAIL-08_25_2025-GO95HV-1^06247006.0281901 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009792 | 798271008-81939-DTLSB-07_01_2025-GO95MLD-1^06244006.0224401 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009793 | 798284205-13089-DETAIL-08_20_2025-GO95HV-1^06247006.0368201 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009794 | 798284205-13089-DETAIL-08_20_2025-POLETOP-1^06247006.0368201 | POLE | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009795 | 798514833-31659-DETAIL-03_11_2024-CUSTWIRE-1^06245007.0276909 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009796 | 798585011-9062-DTLSB-07_01_2025-BIRDDMG-1^06244007.0107443 | POLE | HFTD Tier 2 | Distribution | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009797 | 798780911-70280-DETAIL-02_27_2025-GUYHINS-1^06240004.0235700 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009798 | 799024180-63722-DTLTRT-04_23_2026-GO95HV-1^668004/00 5/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009799 | 79913776-34953-DTLSB-06_10_2026-SVCNEUT-1^07217001.0353302 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009800 | 799153103-37889-DETAIL-07_31_2025-SVCENTCO-1^06247005.0214700 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009801 | 799209854-84809-ADMIN-10_21_2025-GO95HV-1^06246012.0055602 | OTHER | HFTD Tier 2 | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009802 | 799259371-4369-DTLTRT-06_02_2021-GO95HV-1^668041/00 8/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009803 | 799564780-7670-DETAIL-02_18_2026-GO95HV-1^06239002.0094100 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009804 | 79966902-23520-DETAIL-03_30_2026-SVCTREE-2^06240004.0277440 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009805 | 800161805-72759-AUDIT-09_02_2025-GRDRODHI-1^06247005.0313600 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009806 | 800184516-33789-DETAIL-10_14_2025-ABNDEQPM-1^06148001.0175204 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009807 | 800596840-56559-DETAIL-09_18_2025-GO95HV-1^06246006.0011601 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009808 | 801447882-15299-DETAIL-05_20_2025-GO95HV-1^06243006.0075100 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009809 | 801625584-27089-DTLSB-01_27_2026-BIRDDMG-1^06242009.0057101 | POLE | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009810 | 801625584-27089-DTLSB-01_27_2026-GRDRODHI-1^06242009.0057101 | OTHER | Non-HFTD | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009811 | 801866188-48499-DETAIL-09_03_2025-GO95HV-1^06247006.0295302 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009812 | 802112441-94070-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009813 | 802363124-85244-DETAIL-06_10_2026-GUYHINS-1^668086/00 10B/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009814 | 802363124-85244-DETAIL-06_10_2026-GUYHINS-2^668086/00 10B/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009815 | 802363124-85244-DETAIL-06_10_2026-GUYHINS-3^668086/00 10B/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009816 | 80248935-47719-DTLSB-04_16_2026-GO95HV-1^06241009.0136502 | OTHER | Non-HFTD | Distribution | 2026-04-16 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009817 | 802681799-35991-DTLTRT-04_28_2026-BIRDDMG-1^668038/00 5/066 | POLE | HFTD Tier 2 | Transmission | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009818 | 802875190-98559-DETAIL-08_05_2025-GO95HV-1^06247005.0208301 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009819 | 803009245-99449-DTLSB-07_09_2025-GO95HV-1^06244006.0346400 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009820 | 803162739-18409-DTLSB-09_03_2024-CUSTWIRE-1^06245007.0015202 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009821 | 803825431-94959-DETAIL-03_13_2024-CUSTWIRE-1^06245007.0282302 | OTHER | HFTD Tier 2 | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009822 | 803867291-56302-DTLSB-05_06_2026-GO95HV-1^06142013.0289500 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009823 | 804100210-20210-DETAIL-01_22_2025-SVCDEFLC-1^06240004.0089512 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009824 | 804530662-68409-DTLSB-07_16_2025-GO95HV-1^06244006.0233001 | OTHER | Non-HFTD | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009825 | 804644262-97699-DETAIL-10_06_2021-CUSTWIRE-2^06147005.0054902 | OTHER | Non-HFTD | Distribution | 2021-10-06 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009826 | 804983116-1861-DETAIL-02_24_2025-SVCENTCO-1^06239004.0367800 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009827 | 805247108-31289-DETAIL-10_06_2025-GO95BLTC-1^06246007.0063400 | OTHER | HFTD Tier 2 | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009828 | 80546186-68399-DTLSB-09_05_2024-CUSTWIRE-1^06245007.0235600 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009829 | 805468183-7690-DETAIL-02_24_2026-GO95MLD-1^06239002.0274300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009830 | 80552008-559-DETAIL-05_16_2022-POLETOP-1^07116001.0059300 | POLE | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009831 | 805998569-85552-DTLSB-07_14_2025-GO95HV-1^06244006.0289540 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009832 | 806484527-99712-ADMIN-10_22_2025-GRDRODHI-1^06246001.0108001 | OTHER | Non-HFTD | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009833 | 806596861-44879-DETAIL-10_06_2025-GUYHINS-1^06148001.0310814 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009834 | 806773739-53283-DETAIL-08_19_2025-CUSTWIRE-1^07216001.0176800 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009835 | 807211756-6691-DETAIL-05_07_2026-GO95HV-1^668038/00 3/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009836 | 807211756-76012-DETAIL-05_07_2026-GO95HV-1^668038/00 3/053 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009837 | 80727001-73030-AUDIT-05_07_2026-GUYMARK-1^06240004.0209501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009838 | 807607119-54022-DETAIL-10_07_2025-GO95BLTC-1^06148001.0303200 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009839 | 807618134-28479-DETAIL-08_14_2024-CUSTWIRE-1^06246005.0254700 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009840 | 807892099-15399-DETAIL-06_04_2025-GO95MLD-1^668075/00 17/024 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009841 | 808248369-97409-DETAIL-09_30_2025-GO95HV-1^06246009.0132202 | OTHER | HFTD Tier 2 | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009842 | 808518452-5149-DTLSB-07_21_2025-GO95HV-1^06244006.0232900 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009843 | 808613718-29089-DETAIL-08_14_2025-GO95HV-1^06246002.0254400 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009844 | 80871128-28610-DETAIL-04_22_2024-POLISSUE-1^06145001.0029600 | POLE | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009845 | 808820590-61559-DETAIL-09_16_2025-GO95HV-1^06246006.0019200 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009846 | 808883006-67731-DETAIL-06_02_2025-GO95HV-1^06148014.0366700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009847 | 808915669-18991-DETAIL-04_10_2025-GO95HV-1^06241005.0030700 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009848 | 809444770-55270-DETAIL-02_25_2026-GO95HV-1^06238002.0070900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009849 | 809715355-38600-DETAIL-02_25_2026-GO95HV-1^06239003.0244903 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009850 | 809965560-25359-DETAIL-10_09_2025-COPLLEAN-1^06248003.0275400 | POLE | HFTD Tier 2 | Distribution | 2025-10-09 | 2026-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009851 | 810017891-43080-DETAIL-02_16_2026-GO95HV-1^06239001.0053701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009852 | 810086174-69389-DETAIL-10_15_2025-GO95BLTC-1^06246011.0182501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-15 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009853 | 81012344-84769-DETAIL-05_06_2025-GO95HV-1^06243006.0031300 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009854 | 810264073-57150-DETAIL-01_16_2025-GO95HV-1^06239004.0257609 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009855 | 810327719-74979-DETAIL-06_16_2025-GO95HV-1^06248004.0355540 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009856 | 810347106-67106-DRONE_HY-06_19_2026-COVCOTHR-1^06239004.0250700 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009857 | 810384202-55943-DETAIL-09_24_2025-GO95HV-1^07218001.0237001 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009858 | 810622486-51432-DETAIL-08_05_2025-GO95HV-1^06246002.0134002 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009859 | 810622486-51432-DETAIL-08_05_2025-GO95TCH-1^06246002.0134002 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009860 | 810849874-12632-DETAIL-09_04_2025-GO95HV-1^06147001.0317000 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009861 | 81100089-8979-DETAIL-04_23_2025-SVCROOF-1^06242006.0037701 | OTHER | Non-HFTD | Distribution | 2025-04-23 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009862 | 811252654-20839-DTLSB-07_15_2025-GO95HV-1^06244006.0210700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009863 | 81149183-4599-DETAIL-09_17_2025-GO95HV-1^06147001.0144200 | OTHER | Non-HFTD | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009864 | 811537581-54639-DETAIL-05_07_2025-GO95HV-1^06243006.0019801 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009865 | 811701371-81371-DTLSB-05_28_2026-ENCHRW-1^07216001.0023604 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009866 | 811820393-99239-DETAIL-11_17_2025-GO95HV-1^06243007.0013400 | OTHER | HFTD Tier 2 | Distribution | 2025-11-17 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009867 | 811892601-4601-DETAIL-05_29_2025-GO95HV-1^06142012.0154800 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009868 | 812393809-14809-DETAIL-08_19_2025-GO95HV-1^06247006.0363100 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009869 | 812461543-53602-DETAIL-04_02_2025-GO95BLTC-1^06241005.0118404 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009870 | 812461543-53602-DETAIL-04_02_2025-GUYNOINS-1^06241005.0118404 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009871 | 812461543-53602-DETAIL-04_02_2025-SVCNEUT-1^06241005.0118404 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009872 | 812764793-17680-DETAIL-02_17_2026-GO95HV-1^06239002.0040000 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009873 | 812770573-46149-DETAIL-06_02_2025-GO95HV-1^06244006.0149301 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009874 | 812850580-80909-DTLSB-08_27_2024-CUSTWIRE-1^06245007.0014102 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009875 | 813026870-15242-DETAIL-10_02_2025-GRDRODHI-1^06148001.0304103 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009876 | 813092808-14730-DETAIL-01_22_2026-GO95MLD-1^06240003.0304000 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009877 | 81332393-24279-DTLSB-01_21_2026-SVCENTCO-1^06242009.0296102 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009878 | 813759776-876-DETAIL-05_27_2025-GUYHINS-1^06244006.0040402 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-27 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009879 | 814153248-66559-DETAIL-08_28_2025-GO95HV-1^07216001.0163500 | OTHER | Non-HFTD | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009880 | 814366040-87040-AUDIT-06_25_2025-GO95HV-1^06244006.0092741 | OTHER | Non-HFTD | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009881 | 814993809-20019-DTLSB-04_14_2026-GO95BLTC-1^06241008.0235401 | OTHER | Non-HFTD | Distribution | 2026-04-14 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009882 | 815191356-69050-DTLSB-07_24_2025-SVCDEFLC-1^07218001.0264711 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009883 | 815225535-53449-DTLSB-07_09_2025-GO95HV-1^06244006.0346601 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009884 | 815455975-77742-ADMIN-11_03_2025-ABNDEQPM-1^06246001.0226402 | OTHER | Non-HFTD | Distribution | 2025-11-03 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009885 | 815474200-14320-DETAIL-01_22_2026-COVCOTHR-1^06239003.0071905 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009886 | 815481454-91329-DETAIL-06_05_2025-GO95MLD-1^06148014.0245702 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009887 | 815648521-9039-DTLTRT-07_09_2025-BIRDDMG-1^668087/00 7/025 | POLE | Non-HFTD | Transmission | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009888 | 815648521-9039-DTLTRT-07_09_2025-GO95HV-1^668087/00 7/025 | OTHER | Non-HFTD | Transmission | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009889 | 81582167-83110-DETAIL-08_11_2025-GO95HV-1^06246002.0238400 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009890 | 81582632-10750-DETAIL-02_03_2026-GO95HV-1^06239003.0018409 | OTHER | Non-HFTD | Distribution | 2026-02-03 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009891 | 816072115-37542-DETAIL-08_20_2025-GRDRODHI-1^06246001.0175701 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009892 | 816303736-25153-DTLSB-06_16_2026-GO95HV-1^07217001.0356201 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009893 | 816365876-33319-ADMIN-11_13_2025-GO95HV-1^06247008.0314800 | OTHER | HFTD Tier 2 | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009894 | 816494489-33813-DETAIL-08_28_2025-GO95HV-1^06247006.0284800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009895 | 816532974-14840-DETAIL-03_25_2026-PWRTRN-1^06240004.0217801 | OTHER | HFTD Tier 2 | Distribution | 2026-03-25 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009896 | 816595220-78220-DTLSB-05_04_2026-GO95HV-1^06142013.0060603 | OTHER | Non-HFTD | Distribution | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009897 | 816790411-71529-DETAIL-05_08_2024-ABNDEQPM-1^06142012.0120003 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009898 | 816839720-6770-DETAIL-06_10_2025-GO95HV-1^06236005.0346904 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009899 | 817044704-20010-DETAIL-03_13_2025-GO95HV-1^06238004.0150101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009900 | 817107244-37379-DETAIL-08_20_2025-GO95HV-1^06246001.0171503 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009901 | 817245991-66899-DTLSB-07_14_2025-ABNDEQPM-1^06244007.0227601 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009902 | 817380854-95319-DETAIL-03_24_2026-COVCOTHR-1^06242009.0023502 | CONDUCTOR | Non-HFTD | Distribution | 2026-03-24 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009903 | 817424278-20099-DETAIL-08_14_2024-ABNDEQPM-1^06245005.0341000 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009904 | 818007221-97331-DETAIL-02_27_2025-GO95HV-1^06241005.0178901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009905 | 818007221-97331-DETAIL-02_27_2025-GO95MLD-1^06241005.0178901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009906 | 818040898-34609-DETAIL-09_17_2025-ABNDEQPM-1^06246006.0080700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009907 | 818040898-34609-DETAIL-09_17_2025-GO95HV-1^06246006.0080700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009908 | 818040898-34609-DETAIL-09_17_2025-RISEGRD-1^06246006.0080700 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009909 | 818058640-50740-DETAIL-07_06_2026-GO95HV-1^07218001.0342806 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009910 | 818058640-50740-DETAIL-07_06_2026-GO95TCH-1^07218001.0342806 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009911 | 818181058-48819-DTLSB-05_18_2026-GO95HV-1^06242009.0286401 | OTHER | Non-HFTD | Distribution | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009912 | 818360456-62456-DETAIL-06_02_2025-ABNDEQPM-1^06148015.0312900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009913 | 818390173-33699-DETAIL-09_24_2025-GUYHINS-1^06246009.0114000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-24 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009914 | 818390173-33699-DETAIL-09_24_2025-GUYHINS-2^06246009.0114000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-24 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009915 | 818486955-46399-DETAIL-07_28_2025-BIRDDMG-1^06247005.0313701 | POLE | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009916 | 818486955-46399-DETAIL-07_28_2025-GO95HV-1^06247005.0313701 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009917 | 818581078-69929-DETAIL-04_22_2026-GRDRODHI-2^06142012.0144605 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009918 | 818592863-89859-DTLSB-08_12_2025-GO95HV-1^07217001.0012200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009919 | 818850478-48179-ADMIN-08_18_2025-CUTOUTAR-2^06246002.0355600 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009920 | 818863133-39752-DETAIL-09_05_2025-GO95HV-1^06147001.0204101 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009921 | 818935988-87069-DETAIL-09_17_2025-GO95HV-1^06248007.0362600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009922 | 81913694-23183-DETAIL-09_11_2025-GO95HV-1^06248007.0152102 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009923 | 819163436-32183-DTLSB-06_30_2025-GO95HV-1^06244006.0229440 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009924 | 819256432-88139-DETAIL-05_05_2025-GO95HV-1^06243006.0064600 | OTHER | HFTD Tier 2 | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009925 | 820137071-68809-DETAIL-09_03_2025-SVCDEFLC-1^06247006.0210605 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009926 | 820144776-10799-DETAIL-08_12_2025-GO95HV-1^06247006.0266100 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009927 | 820328561-17622-DTLTRT-04_27_2026-GO95HV-1^668004/00 8/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009928 | 820462974-48253-DETAIL-09_24_2025-GO95HV-1^07218001.0220400 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009929 | 820496499-4999-DETAIL-09_22_2025-GO95HV-1^06248007.0242301 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009930 | 820542300-11279-DTLSB-06_30_2025-GO95HV-1^06244007.0036206 | OTHER | HFTD Tier 2 | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009931 | 820799564-34533-DETAIL-09_16_2025-GO95HV-1^06247004.0083600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009932 | 820876545-94962-DTLSB-06_05_2026-SVCDEFLC-1^07216001.0230801 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009933 | 820985275-64029-DETAIL-04_17_2025-GO95BLTC-1^06242006.0082602 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009934 | 821190323-93341-ADMIN-10_07_2025-COVCOTHR-1^06242005.0365201 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-10-07 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009935 | 821208319-16669-DTLSB-06_30_2022-CUSTWIRE-1^06243005.0237201 | OTHER | HFTD Tier 2 | Distribution | 2022-06-30 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009936 | 821426552-75520-DETAIL-01_21_2026-COVCOTHR-1^06240004.0288403 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009937 | 821953687-37838-DETAIL-05_21_2026-GO95HV-1^07217001.0144500 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009938 | 822072033-27721-DETAIL-04_10_2025-GO95TCH-1^06241005.0059101 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009939 | 822308296-70059-DETAIL-08_06_2025-GO95HV-1^06247005.0263602 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009940 | 822806936-27809-DETAIL-09_08_2025-GO95HV-1^06247007.0139900 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009941 | 823105188-98002-DETAIL-03_05_2025-GO95HV-1^06241005.0121001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009942 | 823255745-74979-DTLSB-07_17_2025-GO95HV-1^06244007.0112402 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009943 | 823478851-11550-DETAIL-03_04_2026-GO95HV-1^06239003.0184802 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009944 | 823755861-40480-DETAIL-01_29_2026-GUYHINS-1^06240004.0304100 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009945 | 823755861-40480-DETAIL-02_20_2025-SVCROAD-1^06240004.0304100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-20 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009946 | 823781684-33139-DETAIL-04_23_2026-GO95HV-1^06142012.0235800 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009947 | 82380883-68710-ADMIN-10_28_2025-GO95MLD-1^06246001.0120701 | OTHER | Non-HFTD | Distribution | 2025-10-28 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009948 | 82380883-68710-ADMIN-10_28_2025-GRDRODHI-2^06246001.0120701 | OTHER | Non-HFTD | Distribution | 2025-10-28 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009949 | 823961050-86772-DETAIL-06_03_2026-GUYHINS-1^07216001.0026306 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-03 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009950 | 82405866-23389-ADMIN-10_23_2025-GO95HV-1^06246001.0038000 | OTHER | Non-HFTD | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009951 | 824097186-23740-AUDIT-03_25_2025-GO95TCH-1^06240004.0214701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009952 | 824258114-94199-DETAIL-05_07_2025-GRDRODHI-1^06243006.0048002 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009953 | 824322849-55739-DETAIL-06_25_2025-GO95HV-1^668087/00 17/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009954 | 824383813-3669-DETAIL-02_20_2026-XARMSPCR-1^668041/00 3/026 | CROSSARM | Non-HFTD | Transmission | 2026-02-20 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009955 | 82459228-41689-DTLSB-01_26_2026-GO95HV-1^06242009.0298307 | OTHER | Non-HFTD | Distribution | 2026-01-26 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009956 | 824720746-6599-DETAIL-07_30_2025-GO95HV-1^06247005.0310400 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009957 | 82483929-60910-DETAIL-03_05_2025-GO95MLD-1^06241005.0135500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009958 | 82498781-51870-DTLTRT-05_12_2026-GO95HV-1^668004/00 4/009 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009959 | 825193159-65599-DTLSB-07_17_2025-GO95HV-1^06244006.0170301 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009960 | 825203976-8991-DTLTRT-05_11_2026-GO95HV-1^668038/00 2/049 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009961 | 825378956-97182-DETAIL-08_11_2025-GO95HV-1^06246002.0094003 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009962 | 825571769-52652-DTLSB-07_21_2025-GO95HV-1^06244006.0308741 | OTHER | HFTD Tier 2 | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009963 | 825799495-92500-DETAIL-02_05_2026-GO95HV-1^06239003.0017610 | OTHER | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009964 | 82580475-21999-DETAIL-09_09_2025-GO95HV-1^06246007.0153050 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009965 | 826005248-36482-DTLTRT-06_24_2025-GUYHINS-1^668087/00 13/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009966 | 826022782-29309-DETAIL-06_05_2025-GO95HV-1^06245006.0190401 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009967 | 826496809-69359-DETAIL-06_17_2025-GO95HV-1^06248004.0357003 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009968 | 826551661-42059-DETAIL-08_28_2025-GO95HV-1^06247006.0063300 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009969 | 826996644-98339-DETAIL-10_06_2025-BIRDDMG-1^06243007.0364501 | POLE | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009970 | 827206973-93640-DTLTRT-05_29_2025-GO95HV-1^668075/00 3/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009971 | 827264769-60259-DTLTRT-05_07_2026-GUYHINS-1^668004/00 18/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009972 | 827836151-36709-DETAIL-08_26_2025-GO95HV-1^06247006.0329000 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009973 | 827956813-11689-DETAIL-07_31_2025-GO95HV-1^06247006.0203400 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009974 | 828022075-59982-DTLTRT-07_03_2025-GO95HV-1^668087/00 3/012 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009975 | 828022075-59982-DTLTRT-07_03_2025-GUYHINS-1^668087/00 3/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009976 | 828022075-59982-DTLTRT-07_03_2025-GUYHINS-2^668087/00 3/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009977 | 828022075-59982-DTLTRT-07_03_2025-GUYHINS-3^668087/00 3/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009978 | 828022075-59982-DTLTRT-07_03_2025-GUYLOINS-1^668087/00 3/012 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-03 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009979 | 828053056-89473-DTLSB-06_17_2026-SVCROAD-1^07217001.0276006 | OTHER | Non-HFTD | Distribution | 2026-06-17 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009980 | 828252699-96939-DETAIL-10_15_2024-SVCROAD-1^07216001.0204203 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009981 | 828558078-35989-DTLSB-07_15_2025-GO95HV-1^06244007.0036903 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009982 | 828685748-98663-DETAIL-06_10_2025-GO95HV-1^06245006.0205001 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009983 | 828943519-56169-DETAIL-03_05_2024-CUSTWIRE-1^06245007.0276200 | OTHER | HFTD Tier 2 | Distribution | 2024-03-05 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009984 | 829177174-99590-DETAIL-02_12_2026-GO95HV-1^06239003.0363501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009985 | 829451541-34450-DETAIL-03_04_2026-GO95HV-1^06239003.0182802 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009986 | 829464690-4939-DETAIL-05_08_2025-GO95HV-1^06243006.0286800 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009987 | 829490939-32199-DTLSB-02_04_2026-BIRDDMG-1^06243009.0320000 | POLE | HFTD Tier 2 | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009988 | 829501925-76749-DTLSB-07_14_2025-GO95MLD-1^06244007.0142101 | OTHER | HFTD Tier 2 | Distribution | 2025-07-14 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009989 | 829634442-16050-DETAIL-03_25_2025-INSULDMG-1^06239003.0019401 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009990 | 829687037-38037-DETAIL-04_21_2025-GO95TCH-1^06242006.0037908 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009991 | 829696322-83759-DETAIL-07_31_2025-GO95HV-1^06247005.0244001 | OTHER | Non-HFTD | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009992 | 830422820-71140-DETAIL-03_10_2026-COVCOTHR-1^06239003.0062101 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009993 | 830673094-16792-DETAIL-09_04_2025-GO95HV-1^06147001.0319700 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009994 | 830677065-26792-DETAIL-08_26_2025-GO95HV-1^06246001.0174307 | OTHER | Non-HFTD | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009995 | 830727613-30039-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0267802 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009996 | 830761582-18992-DTLTRT-04_29_2026-GO95HV-1^668004/00 4/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009997 | 830761582-862-DTLTRT-04_29_2026-GO95HV-1^668004/00 4/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120009998 | 830920456-50192-DTLTRT-05_11_2026-BIRDDMG-1^668038/00 3/048 | POLE | HFTD Tier 2 | Transmission | 2026-05-11 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120009999 | 830920456-50192-DTLTRT-05_11_2026-GO95HV-1^668038/00 3/048 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010000 | 831695631-631-DETAIL-04_17_2025-GO95MLD-1^06242005.0350500 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010001 | 831930960-94189-DETAIL-08_21_2025-GO95HV-1^06246001.0305101 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010002 | 831930960-94189-DETAIL-08_21_2025-GRDRODHI-1^06246001.0305101 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010003 | 831930960-94189-DETAIL-08_21_2025-GRDRODHI-2^06246001.0305101 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010004 | 832312553-48522-DETAIL-07_15_2024-CUSTWIRE-1^06244005.0269202 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010005 | 832418909-88759-DETAIL-06_16_2025-GO95HV-1^06248005.0330240 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010006 | 832568199-99402-DETAIL-05_28_2025-ABNDEQPM-1^06142012.0039201 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010007 | 832568199-99402-DETAIL-05_28_2025-GO95HV-1^06142012.0039201 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010008 | 832831106-58309-ADMIN-03_06_2026-POLEREPL-1^06247006.0265401 | POLE | Non-HFTD | Distribution | 2026-03-06 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010009 | 832831106-58309-DETAIL-08_13_2025-GO95HV-1^06247006.0265401 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010010 | 833093843-70259-DETAIL-06_03_2025-GO95HV-1^06245007.0261100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010011 | 833588408-50508-DETAIL-03_23_2023-CUSTWIRE-1^06142016.0050170 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010012 | 833741176-32152-DETAIL-04_24_2025-GO95HV-1^06242006.0171100 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010013 | 833875575-66500-DETAIL-02_11_2026-GO95HV-1^06239003.0016603 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010014 | 833907389-33113-DETAIL-08_25_2025-GO95HV-1^06247006.0282400 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010015 | 834370198-3823-ADMIN-06_24_2024-POLEDERP-1^07217001.0273801 | POLE | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010016 | 834370198-3823-DTLSB-06_11_2026-BIRDDMG-1^07217001.0273801 | POLE | Non-HFTD | Distribution | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010017 | 834758556-53210-DETAIL-03_02_2026-CUSTWIRE-1^06239003.0242800 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010018 | 834840350-22701-DETAIL-04_10_2025-GO95HV-1^06241005.0030601 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010019 | 83498553-58629-DETAIL-04_30_2025-GO95HV-1^06242006.0112002 | OTHER | HFTD Tier 2 | Distribution | 2025-04-30 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010020 | 83515233-24469-DETAIL-06_11_2025-GO95HV-1^06245007.0261701 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010021 | 835235502-36580-DETAIL-01_29_2026-COVCOTHR-1^06240004.0308303 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010022 | 835594504-61159-DETAIL-08_19_2025-ABNDEQPM-1^06247006.0367301 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010023 | 835610108-79229-DETAIL-04_28_2026-GO95HV-1^06142012.0149509 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010024 | 835637010-7909-DETAIL-03_13_2024-CUSTWIRE-1^06147004.0170900 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010025 | 835684168-13450-AUDIT-04_22_2025-GUYHINS-1^06239003.0015304 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-22 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010026 | 835728694-80729-DTLSB-01_21_2026-BIRDDMG-1^06242009.0298108 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010027 | 835728694-80729-DTLSB-01_21_2026-GO95HV-1^06242009.0298108 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010028 | 835742788-53390-DETAIL-01_12_2026-COVCOTHR-2^06239004.0244409 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010029 | 835742788-53390-DETAIL-01_28_2025-SVCROAD-1^06239004.0244409 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010030 | 83608213-84699-DTLSB-05_11_2026-BIRDDMG-1^06242009.0270000 | POLE | Non-HFTD | Distribution | 2026-05-11 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010031 | 836435786-45400-DETAIL-04_07_2026-GO95HV-1^06240002.0317014 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010032 | 836608566-53780-DETAIL-01_13_2026-SVCTREE-1^06239004.0244701 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010033 | 836663528-45489-DTLSB-04_15_2026-GO95MLD-1^06241008.0078300 | OTHER | Non-HFTD | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010034 | 836886369-95330-DTLTRT-05_27_2025-GO95HV-1^668075/00 4/003 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010035 | 83707653-66620-ADMIN-11_13_2025-ABNDEQPM-1^06246001.0326400 | OTHER | Non-HFTD | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010036 | 837270015-29363-DETAIL-06_25_2026-GO95HV-1^07217001.0037900 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010037 | 837542251-73239-DETAIL-05_19_2025-GO95HV-1^06243006.0228601 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010038 | 837547890-39422-DETAIL-03_13_2024-GO95MLD-1^06147004.0190900 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010039 | 83787558-20658-DTLSB-03_18_2026-SVCROAD-1^06242009.0084200 | OTHER | HFTD Tier 2 | Distribution | 2026-03-18 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010040 | 838006661-69022-DETAIL-09_10_2025-XARMBRAC-1^06147001.0081700 | CROSSARM | Non-HFTD | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010041 | 838026668-27743-DETAIL-07_07_2025-GO95CL10-1^06245007.0358440 | OTHER | HFTD Tier 2 | Distribution | 2025-07-07 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010042 | 838296199-39019-DTLSB-04_13_2026-GO95HV-1^06241008.0257100 | OTHER | Non-HFTD | Distribution | 2026-04-13 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010043 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-10^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010044 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-7^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010045 | 83833233-93233-DETAIL-06_09_2025-GUYHINS-8^668075/00 18/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010046 | 838380514-86989-DETAIL-08_20_2025-GO95HV-1^06247006.0367500 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010047 | 838880148-59989-DETAIL-08_19_2025-GO95HV-1^06246002.0269001 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010048 | 839153395-98779-DETAIL-07_30_2025-GO95HV-1^06247005.0024000 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010049 | 839335880-65880-DETAIL-03_31_2026-SVCTREE-1^06241009.0326703 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010050 | 839726125-32530-DETAIL-04_15_2026-GUYHINS-4^06236005.0113901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-04-15 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010051 | 840017467-38999-DETAIL-04_10_2024-GO95HV-1^06147005.0163001 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010052 | 840336634-7509-DETAIL-09_04_2025-SVCDEFLC-1^06247006.0184801 | OTHER | HFTD Tier 2 | Distribution | 2025-09-04 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010053 | 840378577-94323-DETAIL-05_22_2026-GUYHINS-1^07217001.0146403 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-22 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010054 | 84049900-10733-DETAIL-06_29_2026-GO95HV-1^07217001.0159500 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010055 | 84049900-10733-DETAIL-06_29_2026-GUYHINS-1^07217001.0159500 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-29 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010056 | 840532484-71622-DETAIL-09_04_2025-GO95HV-1^06147001.0319305 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010057 | 840551335-17399-DTLSB-07_17_2025-GO95HV-1^06244007.0112401 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010058 | 840751442-28983-DETAIL-08_20_2025-GO95HV-1^07216001.0176006 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010059 | 841290765-33765-DETAIL-06_05_2025-GO95HV-1^06148014.0236402 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010060 | 84142380-51889-DTLSB-07_22_2025-GO95HV-1^06244006.0181204 | OTHER | HFTD Tier 2 | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010061 | 841648992-35831-DETAIL-02_27_2025-GO95BLTC-1^06241005.0171600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010062 | 841648992-35831-DETAIL-02_27_2025-GO95MLD-1^06241005.0171600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010063 | 842092588-63159-DETAIL-09_03_2025-GO95HV-1^07216001.0094441 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010064 | 842508463-10279-DETAIL-09_15_2025-GO95HV-1^06248007.0232400 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010065 | 842530609-12029-DETAIL-04_17_2025-GO95HV-1^06242006.0035500 | OTHER | Non-HFTD | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010066 | 842634048-73199-DTLSB-06_30_2025-GO95HV-1^06244006.0229400 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010067 | 842872310-56129-DTLSB-08_03_2023-CUSTWIRE-1^06243009.0142003 | OTHER | Non-HFTD | Distribution | 2023-08-03 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010068 | 843111717-63717-DETAIL-06_18_2025-GUYHINS-1^668075/00 18/045 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010069 | 843903626-55132-DTLTRT-05_11_2026-GO95HV-1^668038/00 5/052 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010070 | 843903626-55791-DTLTRT-05_11_2026-GO95HV-1^668038/00 5/052 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010071 | 843957535-48132-DETAIL-08_20_2025-GO95CL10-1^06246001.0174406 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010072 | 843957535-48132-DETAIL-08_20_2025-GO95HV-1^06246001.0174406 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010073 | 844658715-14540-DETAIL-03_09_2026-SVCDEFLC-1^06240004.0152603 | OTHER | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010074 | 844961469-95639-DETAIL-07_30_2024-CUSTWIRE-1^06244005.0359200 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010075 | 845190041-94442-DTLTRT-05_20_2026-GO95HV-1^668086/00 2/011 | OTHER | Non-HFTD | Transmission | 2026-05-20 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010076 | 845346403-71859-DETAIL-10_24_2024-GUYNOINS-1^07216001.0207940 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010077 | 845435401-37401-DETAIL-09_09_2025-GO95HV-1^06246007.0221920 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010078 | 845475148-2350-DETAIL-02_24_2026-GO95HV-1^06239003.0132404 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010079 | 845733534-14399-DETAIL-08_18_2025-GRDRODHI-1^06247006.0364401 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010080 | 845913873-94642-ADMIN-11_13_2025-GO95HV-1^06246001.0328001 | OTHER | Non-HFTD | Distribution | 2025-11-13 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010081 | 846079568-84742-DETAIL-09_09_2025-GO95HV-1^06146001.0044300 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010082 | 846118995-42270-DETAIL-01_23_2026-GO95HV-1^06240003.0182600 | OTHER | HFTD Tier 2 | Distribution | 2026-01-23 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010083 | 846237654-20754-DETAIL-03_29_2023-CUSTWIRE-1^06142016.0085800 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010084 | 84629178-16759-DETAIL-09_03_2025-GO95HV-1^07216001.0099004 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010085 | 846393328-97669-DETAIL-03_26_2026-COVCOTHR-1^06240004.0206500 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010086 | 846398936-11680-DETAIL-01_12_2026-SVCTREE-1^06239004.0244601 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010087 | 846398936-11680-DETAIL-03_30_2021-CUSTWIRE-1^06239004.0244601 | OTHER | HFTD Tier 2 | Distribution | 2021-03-30 | 2024-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010088 | 846728251-25880-DETAIL-02_19_2026-GO95HV-1^06239001.0066600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010089 | 847163059-13542-DTLTRT-06_25_2025-GO95BLTC-1^668087/00 15/005 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010090 | 847188316-43311-DETAIL-01_13_2026-COVCOTHR-2^06239004.0243940 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010091 | 847539142-39759-DETAIL-07_30_2025-GO95HV-1^06247005.0242601 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010092 | 847680175-44770-DETAIL-04_07_2026-GO95HV-1^06240003.0367004 | OTHER | Non-HFTD | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010093 | 848158716-23659-DTLTRT-04_30_2026-GO95HV-1^668004/00 8/015 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010094 | 848196839-9552-DETAIL-08_18_2025-GO95HV-1^06246002.0264400 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010095 | 848649263-59109-DETAIL-09_15_2025-GO95HV-1^06248007.0233403 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010096 | 848781616-88169-DETAIL-08_19_2025-GO95HV-1^06247006.0367000 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010097 | 848966811-75809-DETAIL-09_03_2025-GO95HV-1^06247006.0211501 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010098 | 849044806-81942-ADMIN-11_10_2025-GO95BLTC-1^06246011.0061001 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010099 | 849153580-64643-DETAIL-10_09_2025-GO95HV-1^06248003.0339940 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010100 | 849493635-76063-DETAIL-07_07_2026-GO95HV-1^07217001.0096001 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010101 | 849579075-42409-DETAIL-08_21_2025-GO95HV-1^06247006.0267802 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010102 | 849720084-30429-DETAIL-06_03_2025-GO95HV-1^06148014.0248811 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010103 | 849756853-22839-DETAIL-07_18_2024-CUSTWIRE-1^06244005.0019301 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010104 | 849807445-72059-DETAIL-09_16_2025-GO95HV-1^06247004.0184701 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010105 | 849885101-56663-DETAIL-02_25_2025-SVCROAD-1^06240005.0128904 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010106 | 850096560-11579-DTLSB-09_05_2024-CUSTWIRE-1^06245007.0015201 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010107 | 85015516-5169-DETAIL-08_20_2025-GO95HV-1^06247006.0369300 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010108 | 851101005-12449-DETAIL-02_28_2024-GO95HV-1^07113002.0182501 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010109 | 851196630-77739-DTLTRT-06_25_2025-GO95BLTC-1^668087/00 13/007 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010110 | 851196630-77739-DTLTRT-06_25_2025-GUYHINS-1^668087/00 13/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010111 | 85126034-73132-DETAIL-04_07_2025-GO95TCH-1^06241005.0119203 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010112 | 85129747-63139-DTLSB-08_14_2025-GO95HV-1^07218001.0352500 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010113 | 85129747-63139-DTLSB-08_14_2025-GUYHINS-1^07218001.0352500 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010114 | 851339268-9062-DTLSB-05_06_2026-GO95HV-1^06142013.0274101 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010115 | 85140143-6579-DTLSB-01_21_2026-BIRDDMG-1^06242009.0297005 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010116 | 85140143-6579-DTLSB-01_21_2026-GO95HV-1^06242009.0297005 | OTHER | Non-HFTD | Distribution | 2026-01-21 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010117 | 852088020-94649-DETAIL-08_12_2024-CUSTWIRE-1^06245006.0102500 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010118 | 852340606-37562-DETAIL-08_25_2025-POLISSUE-1^06246001.0175202 | POLE | Non-HFTD | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010119 | 852641100-4369-DETAIL-06_16_2025-GO95HV-1^06248005.0285201 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010120 | 852661309-84739-DTLTRT-06_25_2025-GO95HV-1^668087/00 7/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010121 | 852661309-84739-DTLTRT-06_25_2025-SVCDEFLC-1^668087/00 7/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010122 | 852977958-98359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0320500 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010123 | 853226990-82399-DTLSB-04_21_2026-GRDRODHI-1^06241008.0311240 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010124 | 853261575-54575-DETAIL-06_05_2025-GO95HV-1^06148014.0238400 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010125 | 85327731-90479-DETAIL-08_19_2025-GO95HV-1^06246001.0317002 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010126 | 853574144-58553-DETAIL-05_21_2026-GO95HV-1^07217001.0144601 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010127 | 853574144-58553-DETAIL-05_21_2026-GO95TCH-1^07217001.0144601 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010128 | 853610508-76870-DETAIL-02_04_2025-SVCDEFLC-1^06240004.0169601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010129 | 853688325-39291-DTLTRT-05_12_2026-GO95HV-1^668038/00 1/044 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010130 | 853688325-52862-DTLTRT-05_12_2026-GO95HV-1^668038/00 1/044 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010131 | 853828554-88262-DETAIL-09_29_2025-GO95BLTC-1^06148001.0312702 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010132 | 853828554-88262-DETAIL-09_29_2025-GO95HV-1^06148001.0312702 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010133 | 853846858-99262-DETAIL-08_13_2025-GO95HV-1^06246002.0369903 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010134 | 85390997-45039-DETAIL-04_22_2026-GO95HV-1^06142012.0142501 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010135 | 853972236-17329-DETAIL-05_13_2025-GO95HV-1^06142012.0012505 | OTHER | Non-HFTD | Distribution | 2025-05-13 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010136 | 854029601-701-DETAIL-06_04_2025-GO95HV-1^06245006.0207001 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010137 | 854112985-19762-DTLSB-06_09_2026-GO95HV-1^07216001.0228403 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010138 | 854169401-54080-DETAIL-02_16_2026-GO95HV-1^06239001.0054702 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010139 | 854377291-48601-DETAIL-04_16_2025-SVCNEUT-1^06242005.0331201 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010140 | 854455335-21249-DETAIL-09_02_2025-GO95HV-1^07216001.0168740 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010141 | 854759416-31572-DETAIL-09_03_2025-GO95BLTC-1^06246001.0176302 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010142 | 854759416-31572-DETAIL-09_03_2025-GO95HV-1^06246001.0176302 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010143 | 854759416-31572-DETAIL-09_03_2025-SVCROAD-1^06246001.0176302 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010144 | 854804219-45219-DTLSB-09_07_2022-GO95HV-1^06243004.0060502 | OTHER | HFTD Tier 2 | Distribution | 2022-09-07 | 2027-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010145 | 854853703-99429-DETAIL-05_12_2025-GO95HV-1^06142012.0018801 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010146 | 855276209-41899-DTLSB-05_12_2026-GUYHINS-1^06242009.0280203 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010147 | 855452743-91272-DRONE_HY-09_28_2023-GO95HV-1^668033/00 13X1/004 | OTHER | Non-HFTD | Transmission | 2023-09-28 | 2028-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010148 | 855478519-61449-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0148301 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010149 | 85602081-53230-DTLSB-08_13_2025-GO95HV-1^07218001.0288700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010150 | 856260435-972-DTLSB-06_05_2026-GO95HV-1^07216001.0228800 | OTHER | Non-HFTD | Distribution | 2026-06-05 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010151 | 856429770-66269-DTLTRT-06_02_2021-GO95HV-1^668041/00 5/004 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010152 | 856534384-16384-DTLTRT-06_30_2025-GO95HV-1^668087/00 14/013 | OTHER | Non-HFTD | Transmission | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010153 | 856534384-16384-DTLTRT-06_30_2025-GUYNOINS-1^668087/00 14/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-30 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010154 | 856916389-38199-DETAIL-06_03_2024-CUSTWIRE-1^06245006.0029500 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010155 | 857022533-60689-DETAIL-06_17_2025-GO95TCH-1^06248004.0332701 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010156 | 857026304-90779-DTLSB-04_22_2026-GO95BLTC-1^06241009.0247100 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010157 | 857574491-54650-DRONE_HY-06_30_2026-EARMSPCR-1^06238004.0274800 | OTHER | HFTD Tier 2 | Distribution | 2026-06-30 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010158 | 857710984-41882-DETAIL-09_08_2025-GO95HV-1^06147001.0327201 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010159 | 857765688-16688-DETAIL-05_06_2025-GRDRODHI-1^06243006.0068940 | OTHER | HFTD Tier 2 | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010160 | 857844546-27899-DETAIL-07_28_2025-GO95HV-1^06247005.0317300 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010161 | 85818688-71939-DTLSB-06_30_2025-GO95HV-1^06244006.0224301 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010162 | 858318190-43820-DETAIL-01_22_2026-SVCTREE-1^06239003.0070900 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010163 | 858586923-78529-DTLSB-08_16_2023-CUSTWIRE-1^06243009.0283401 | OTHER | HFTD Tier 2 | Distribution | 2023-08-16 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010164 | 858881008-69639-DTLTRT-06_24_2025-GO95HV-1^668087/00 17/003 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010165 | 858881008-69639-DTLTRT-06_24_2025-GUYHINS-2^668087/00 17/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010166 | 859005786-74809-DETAIL-09_08_2025-GO95HV-1^06247007.0017100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010167 | 859043944-35944-DETAIL-07_07_2026-GO95TCH-1^07217001.0165602 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010168 | 859245439-70129-DETAIL-04_28_2022-CUSTWIRE-1^06143012.0242800 | OTHER | Non-HFTD | Distribution | 2022-04-28 | 2025-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010169 | 859660680-222-DTLTRT-05_05_2026-GO95HV-1^668004/00 1/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010170 | 859888068-99660-ADMIN-09_24_2025-POLEREPL-1^668018/00 4/002 | POLE | HFTD Tier 2 | Transmission | 2025-09-24 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010171 | 859928075-2549-DTLSB-07_10_2025-GO95HV-1^06244006.0342601 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010172 | 86047139-90479-DETAIL-10_14_2025-GO95HV-1^06148001.0273100 | OTHER | Non-HFTD | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010173 | 860596378-64798-DETAIL-04_10_2025-GO95TCH-1^06241005.0013620 | OTHER | HFTD Tier 2 | Distribution | 2025-04-10 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010174 | 860664525-37379-DETAIL-08_28_2025-GO95HV-1^06247006.0194800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-28 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010175 | 860713768-7312-DETAIL-06_28_2023-CUSTWIRE-1^06244009.0253200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010176 | 861032091-79392-DETAIL-09_11_2025-GO95HV-1^06147001.0082600 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010177 | 861201303-5009-DETAIL-08_12_2025-GO95HV-1^06247006.0250400 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010178 | 862254435-45435-DTLSB-07_17_2025-GO95HV-1^06244007.0111602 | OTHER | HFTD Tier 2 | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010179 | 862290014-41014-DETAIL-07_22_2025-GO95HV-1^06247005.0040401 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010180 | 862943568-5429-DETAIL-04_21_2026-GO95HV-1^06142012.0140904 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010181 | 863484173-42702-ADMIN-10_28_2025-GO95HV-1^06246001.0120900 | OTHER | Non-HFTD | Distribution | 2025-10-28 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010182 | 863560492-36702-DETAIL-05_15_2024-GO95HV-1^06142012.0125701 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010183 | 86373431-33743-DETAIL-07_07_2026-CLRTOUCH-1^07217001.0221505 | CONDUCTOR | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010184 | 86377801-65220-DTLTRT-04_23_2026-GO95HV-1^668004/00 3/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010185 | 864206838-49069-ADMIN-10_23_2025-GRDRODHI-1^06246011.0369204 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010186 | 864435432-46562-DTLTRT-04_28_2026-GO95HV-1^668004/00 10/011 | OTHER | Non-HFTD | Transmission | 2026-04-28 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010187 | 864521598-12079-DRONE_HY-09_22_2023-GO95HV-1^668002/00 2/075 | OTHER | HFTD Tier 2 | Transmission | 2023-09-22 | 2028-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010188 | 864766670-85302-DETAIL-03_13_2024-CUSTWIRE-1^06147004.0181900 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010189 | 864781755-69739-DETAIL-05_08_2025-GO95HV-1^06243006.0105102 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010190 | 865115452-5419-DTLSB-04_08_2026-GO95HV-1^06241009.0102400 | OTHER | Non-HFTD | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010191 | 866031501-79012-DTLTRT-06_25_2025-GUYLOINS-2^668087/00 1A/008 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010192 | 866829802-87459-DETAIL-04_29_2026-GO95HV-1^668004/00 9/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010193 | 866829802-87460-DETAIL-04_29_2026-GO95HV-1^668004/00 9/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010194 | 867190746-39759-DETAIL-05_04_2026-GO95HV-1^668004/00 8/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010195 | 867190746-39760-DETAIL-05_04_2026-GO95HV-1^668004/00 8/018 | OTHER | Non-HFTD | Transmission | 2026-05-04 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010196 | 867210365-86712-DETAIL-09_02_2025-GO95HV-1^06246001.0174202 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010197 | 867421536-59212-DETAIL-08_12_2025-GRDRODHI-2^06246001.0195300 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010198 | 867523538-4349-DETAIL-09_04_2025-GO95MLD-1^07216001.0098503 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010199 | 867605404-1790-DETAIL-03_31_2025-GRDRODHI-1^06239003.0016802 | OTHER | Non-HFTD | Distribution | 2025-03-31 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010200 | 867709673-39909-DETAIL-08_13_2025-GO95HV-1^06247006.0259401 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010201 | 867924387-97309-DTLSB-07_08_2026-GO95HV-1^06242009.0260201 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010202 | 867971589-80422-ADMIN-11_12_2025-GO95HV-1^06146001.0311301 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010203 | 868050259-25369-DETAIL-05_30_2025-GO95HV-1^06147014.0011101 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010204 | 868406158-28158-DETAIL-09_29_2025-GO95HV-1^06148001.0317403 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010205 | 868443273-6053-DETAIL-09_25_2025-GO95HV-1^07218001.0224201 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010206 | 86920496-67959-DTLSB-08_18_2025-GO95HV-1^07218001.0355704 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010207 | 870022438-14222-DETAIL-09_30_2025-GRDRODHI-2^06148001.0300303 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010208 | 870197253-46989-DETAIL-08_18_2025-GO95HV-1^06247006.0366701 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010209 | 870266550-61299-DETAIL-08_05_2025-GO95HV-1^06247005.0205400 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010210 | 870384732-78139-DETAIL-05_05_2025-GRDRODHI-1^06243006.0064502 | OTHER | HFTD Tier 2 | Distribution | 2025-05-05 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010211 | 870407413-20359-DTLTRT-04_22_2026-GO95HV-1^668004/02 5/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010212 | 870408379-36973-AUDIT-10_13_2025-GRDRODHI-1^07216001.0175802 | OTHER | Non-HFTD | Distribution | 2025-10-13 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010213 | 870507246-15569-DETAIL-03_03_2026-GO95BLTC-1^06243009.0250200 | OTHER | Non-HFTD | Distribution | 2026-03-03 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010214 | 87058545-29259-DETAIL-06_23_2026-GO95HV-1^07217001.0107401 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010215 | 870839258-90540-DETAIL-03_05_2026-COVCOTHR-1^06238004.0148701 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010216 | 870855945-66219-DTLSB-01_27_2026-BIRDDMG-1^06242009.0057401 | POLE | HFTD Tier 2 | Distribution | 2026-01-27 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010217 | 870987163-50069-DETAIL-09_18_2025-GO95HV-1^06248007.0267300 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010218 | 871049916-39660-DETAIL-04_30_2026-GO95HV-1^668004/00 9/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010219 | 871080924-71979-DTLSB-01_26_2026-GO95TCH-1^06242009.0298308 | OTHER | Non-HFTD | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010220 | 871451468-13913-DETAIL-08_27_2025-GO95HV-1^06247006.0285800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010221 | 871590385-53385-DETAIL-06_05_2025-GO95HV-1^06148014.0240401 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010222 | 87166024-26293-DTLSB-06_04_2026-SVCROAD-1^07216001.0145900 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010223 | 871832709-62709-DETAIL-08_18_2025-GO95HV-1^06247006.0364100 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010224 | 871832709-62709-DETAIL-08_18_2025-GRDRODHI-1^06247006.0364100 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010225 | 872104921-94020-DETAIL-03_25_2025-COVCOTHR-2^06240004.0273401 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010226 | 872104921-94020-DETAIL-03_25_2025-COVCOTHR-3^06240004.0273401 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010227 | 872205760-5929-DETAIL-06_04_2025-GO95HV-1^06142012.0105502 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010228 | 872337728-80509-DTLSB-06_30_2025-GO95HV-1^06244006.0229401 | OTHER | Non-HFTD | Distribution | 2025-06-30 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010229 | 872551281-42832-DTLSB-06_04_2026-SVCDEFLC-1^07216001.0020900 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010230 | 872551281-42832-DTLSB-06_04_2026-SVCDEFLC-2^07216001.0020900 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010231 | 872575126-78029-DETAIL-04_22_2025-GO95HV-1^06242006.0066001 | OTHER | Non-HFTD | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010232 | 87267211-91820-DETAIL-03_12_2024-CONDFRAY-1^06147004.0085901 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010233 | 872900628-41449-DETAIL-05_25_2023-ENCHRW-1^06245005.0200400 | OTHER | Non-HFTD | Distribution | 2023-05-25 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010234 | 872989477-33859-DTLSB-08_13_2025-GO95HV-1^07218001.0351902 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010235 | 873098536-23680-DETAIL-01_12_2026-COVCOTHR-1^06239004.0244604 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010236 | 873228383-34380-DETAIL-02_03_2025-SVCDEFLC-1^06240004.0163800 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010237 | 873238923-2629-DETAIL-05_12_2025-GO95HV-1^06142012.0019604 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010238 | 873696644-83744-DTLTRT-08_04_2025-GO95HV-1^668087/00 10/029 | OTHER | Non-HFTD | Transmission | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010239 | 873745766-75759-DETAIL-04_30_2026-GO95HV-1^668004/00 1/018 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010240 | 873745766-75760-DETAIL-04_30_2026-GO95HV-1^668004/00 1/018 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010241 | 873882178-91951-DETAIL-03_06_2025-GO95CL10-1^06241005.0160901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010242 | 874030540-31540-DTLSB-05_28_2026-GO95HV-1^07216001.0020200 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010243 | 874132068-48740-DETAIL-02_25_2026-SVCDEFLC-1^06239003.0134000 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010244 | 874136713-28580-DETAIL-02_23_2026-BIRDDMG-1^06239002.0152200 | POLE | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010245 | 874144009-85389-DETAIL-09_30_2025-GO95HV-1^06148001.0300005 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010246 | 874169161-51261-DETAIL-01_13_2026-SVCTREE-1^06239004.0243800 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010247 | 874296836-95842-DTLSB-05_05_2026-GO95HV-1^06142013.0163101 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010248 | 874921792-71379-DTLSB-07_09_2026-GO95HV-1^06240008.0144500 | OTHER | Non-HFTD | Distribution | 2026-07-09 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010249 | 875008864-27040-DTLSB-07_24_2025-GO95MLD-1^07218001.0260700 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010250 | 875008864-27040-DTLSB-07_24_2025-SVCDEFLC-1^07218001.0260700 | OTHER | Non-HFTD | Distribution | 2025-07-24 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010251 | 87529221-39580-DETAIL-02_16_2026-GO95HV-1^06239001.0034900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010252 | 875913020-57739-DTLTRT-06_25_2025-GUYLOINS-1^668087/00 12/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010253 | 875940256-12142-DETAIL-08_05_2025-GO95HV-1^06246002.0134400 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010254 | 876113328-31428-DRONE_HY-10_16_2023-GO95HV-1^668033/00 13/003 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010255 | 876160182-39943-DETAIL-09_23_2025-GO95MLD-1^07218001.0232000 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010256 | 87650804-49309-DETAIL-07_30_2025-GO95HV-1^06247006.0203002 | OTHER | HFTD Tier 2 | Distribution | 2025-07-30 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010257 | 876633-99729-DTLSB-01_21_2026-BIRDDMG-1^06242009.0297103 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010258 | 876679273-61069-DETAIL-09_18_2025-GO95HV-1^06248007.0265501 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010259 | 876808922-40989-DETAIL-08_25_2025-GO95HV-1^06247006.0211000 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010260 | 876808922-40989-DETAIL-08_25_2025-SVCDEFLC-1^06247006.0211000 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010261 | 876922256-92256-AUDIT-05_06_2025-GUYHINS-1^06242005.0332700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-05-06 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010262 | 876922256-92256-DETAIL-04_15_2025-GUYHINS-1^06242005.0332700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-15 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010263 | 87707918-29020-DETAIL-08_25_2025-GO95HV-1^06246001.0205601 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010264 | 877777897-55252-AUDIT-11_12_2025-GO95MLD-1^06246001.0264901 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010265 | 87796610-89540-DETAIL-03_10_2026-SVCTREE-1^06239003.0060000 | OTHER | HFTD Tier 3 | Distribution | 2026-03-10 | 2026-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010266 | 878210106-30106-DETAIL-01_29_2025-GO95MLD-1^06239004.0253600 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010267 | 878216799-59649-DTLSB-04_17_2024-GO95MLD-1^06245007.0224400 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010268 | 87845119-38019-DTLSB-04_13_2026-BIRDDMG-1^06241008.0259302 | POLE | Non-HFTD | Distribution | 2026-04-13 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010269 | 878524054-47529-DTLSB-07_31_2023-CUSTWIRE-1^06243009.0085201 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010270 | 878851698-95550-DETAIL-04_22_2025-GO95HV-1^06240003.0053301 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010271 | 87887054-20959-DTLTRT-04_22_2026-GO95HV-1^668004/02 15/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010272 | 878996734-20990-AUDIT-03_16_2026-XARMSPCR-1^06239003.0016902 | CROSSARM | Non-HFTD | Distribution | 2026-03-16 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010273 | 879138085-57340-DETAIL-03_17_2026-COVCOTHR-1^06240004.0219907 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010274 | 879227302-55279-DETAIL-05_27_2025-GUYHINS-1^06243006.0165703 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-27 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010275 | 88021326-26320-DTLTRT-05_21_2026-GRDBROKE-1^668086/00 20/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010276 | 880220144-52030-DETAIL-06_10_2025-GO95HV-1^06236005.0333500 | OTHER | HFTD Tier 2 | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010277 | 88027000-22370-DETAIL-02_25_2026-GO95HV-1^06238003.0018901 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010278 | 880656924-60253-DETAIL-09_23_2025-GO95MLD-1^07218001.0223703 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010279 | 880656924-60253-DETAIL-09_23_2025-SVCROAD-1^07218001.0223703 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010280 | 881172961-51362-DTLTRT-05_18_2026-GO95HV-1^668086/00 14/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010281 | 881444036-94000-DETAIL-02_10_2026-SVCROAD-1^06239003.0016709 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010282 | 881591881-19962-DETAIL-05_14_2025-GO95HV-1^06142012.0117702 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010283 | 881990709-1083-DETAIL-08_20_2025-GO95MLD-1^07216001.0177801 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010284 | 882337176-43399-DETAIL-08_20_2025-BIRDDMG-1^06247006.0266000 | POLE | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010285 | 882395293-58429-DETAIL-04_22_2026-GO95MLD-1^06142012.0145602 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010286 | 882774004-39021-DRONE_HY-07_02_2026-COVCOTHR-1^06239004.0256000 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010287 | 882774004-39021-DRONE_HY-07_02_2026-COVCOTHR-2^06239004.0256000 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010288 | 882774004-39021-DRONE_HY-07_02_2026-COVCOTHR-3^06239004.0256000 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010289 | 882832075-9840-DETAIL-03_23_2026-COVCOTHR-2^06240004.0219803 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010290 | 882832075-9840-DETAIL-03_23_2026-COVCOTHR-4^06240004.0219803 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010291 | 882857165-17599-DETAIL-08_21_2025-GO95HV-1^06247006.0269801 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010292 | 882977441-85639-DETAIL-05_07_2025-GO95HV-1^06243006.0016801 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010293 | 883056259-38929-DETAIL-04_21_2025-SVCENTBK-1^06242006.0036900 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010294 | 883220054-45772-DETAIL-08_20_2025-GO95HV-1^06246001.0174509 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010295 | 88340839-60720-DETAIL-08_18_2025-GO95HV-1^06246002.0345100 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010296 | 88355259-43099-DETAIL-08_05_2025-GO95CL10-1^06246002.0135000 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010297 | 884236951-9872-DTLTRT-05_18_2026-GO95HV-1^668086/00 11/006 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010298 | 884580890-26472-DETAIL-06_04_2025-GO95HV-1^06142012.0107400 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010299 | 884603214-49839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0219501 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010300 | 884980520-50999-DETAIL-08_05_2025-GO95HV-1^06247005.0207300 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010301 | 885083964-32710-DETAIL-03_17_2025-GO95HV-1^06238004.0158200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010302 | 885200949-90859-DETAIL-06_16_2025-GO95HV-1^06248005.0330842 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010303 | 88526125-50872-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0220040 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010304 | 885349750-28549-DTLSB-07_28_2025-SVCDEFLC-1^07218001.0267502 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010305 | 885396288-80619-ADMIN-10_08_2020-POLEDERP-1^668005/00 2/074 | POLE | Non-HFTD | Transmission | 2020-10-08 | 2023-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010306 | 885496335-17800-DETAIL-04_09_2026-GO95HV-1^06240002.0310104 | OTHER | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010307 | 885496646-1309-DETAIL-08_12_2025-GO95HV-1^06247006.0269001 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010308 | 885525440-51989-DETAIL-06_05_2025-GO95HV-1^06245006.0190801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010309 | 885532885-40449-DETAIL-02_28_2024-POLISSUE-1^07113002.0181700 | POLE | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010310 | 885582010-12489-DTLSB-01_20_2026-GO95HV-1^06242009.0297002 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010311 | 885837699-34639-DETAIL-05_07_2025-GO95HV-1^06243006.0019800 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010312 | 885940388-62940-DETAIL-02_24_2026-GO95HV-1^06239003.0132101 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010313 | 88598403-52829-DTLSB-01_22_2026-BIRDDMG-1^06242009.0296202 | POLE | Non-HFTD | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010314 | 886257386-9429-DETAIL-05_12_2025-GO95HV-1^06142012.0019605 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010315 | 886351238-28682-DETAIL-04_27_2026-SVCROOF-1^06142012.0146904 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010316 | 886528289-57930-DTLTRT-05_22_2025-GO95HV-1^668075/00 14/002 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010317 | 88683029-66773-DETAIL-04_02_2026-GO95HV-1^06236005.0152102 | OTHER | HFTD Tier 2 | Distribution | 2026-04-02 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010318 | 886883918-49709-DETAIL-08_26_2025-GO95TCH-1^06247006.0299100 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010319 | 887016761-33011-DETAIL-06_19_2025-GO95HV-1^06237004.0203700 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010320 | 88702761-8659-DETAIL-06_18_2025-GO95HV-1^06248004.0312803 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010321 | 887039594-94689-DETAIL-08_18_2025-SVCROAD-1^06247006.0362404 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010322 | 887039594-94689-DETAIL-08_18_2025-SVCROAD-2^06247006.0362404 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010323 | 887182359-330-DTLTRT-05_22_2025-GO95HV-1^668075/00 16/001 | OTHER | Non-HFTD | Transmission | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010324 | 887202328-86989-DTLSB-01_20_2026-GO95HV-1^06242009.0299301 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010325 | 887305576-98571-DETAIL-04_23_2025-GO95TCH-1^06242005.0361044 | OTHER | HFTD Tier 2 | Distribution | 2025-04-23 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010326 | 887408743-72753-DETAIL-06_30_2026-CUSTWIRE-1^07217001.0227000 | OTHER | Non-HFTD | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010327 | 887698248-8479-DTLSB-04_22_2026-GO95MLD-1^06241009.0257600 | OTHER | Non-HFTD | Distribution | 2026-04-22 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010328 | 887764638-38182-DETAIL-08_12_2025-GO95HV-1^06246002.0254000 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010329 | 88780393-69850-DETAIL-01_14_2026-SVCDEFLC-1^06239004.0133000 | OTHER | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010330 | 887844116-48379-DETAIL-02_16_2026-BIRDDMG-1^06239001.0041701 | POLE | HFTD Tier 2 | Distribution | 2026-02-16 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010331 | 887844116-48379-DETAIL-02_16_2026-GO95HV-1^06239001.0041701 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010332 | 887911960-36282-DETAIL-09_11_2025-XARMBRAC-1^06147001.0105300 | CROSSARM | Non-HFTD | Distribution | 2025-09-11 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010333 | 888168009-74813-DETAIL-08_25_2025-GO95HV-1^06247006.0282704 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010334 | 888454759-97449-DETAIL-09_03_2025-GO95HV-1^07216001.0099001 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010335 | 888531302-70779-DTLSB-07_21_2025-GO95HV-1^06244006.0233801 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010336 | 88865171-58229-DETAIL-05_19_2025-GRDRODHI-1^06142012.0118506 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010337 | 888686039-54782-DETAIL-09_30_2025-GO95HV-1^06148001.0301203 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010338 | 888695291-15879-DETAIL-09_03_2025-GO95TCH-1^06247006.0210504 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010339 | 888927523-77523-DETAIL-06_11_2025-GUYHINS-2^668075/00 15/033 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-11 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010340 | 889302201-23729-DETAIL-05_02_2022-CUSTWIRE-1^06143012.0245801 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010341 | 889342252-98039-DETAIL-05_20_2025-GO95HV-1^06243006.0076201 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010342 | 889421038-37849-DTLSB-07_09_2025-GO95HV-1^06244007.0141601 | OTHER | HFTD Tier 2 | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010343 | 889519798-93682-DETAIL-04_21_2026-GO95HV-1^06142012.0144803 | OTHER | Non-HFTD | Distribution | 2026-04-21 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010344 | 890329845-9933-DETAIL-09_16_2025-GO95HV-1^06247004.0086541 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010345 | 890431731-54192-DETAIL-05_13_2024-CUSTWIRE-1^06142012.0122300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010346 | 890520130-97849-DTLSB-04_22_2024-ENCHRW-1^06245007.0227204 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010347 | 890796766-2293-DETAIL-09_16_2025-GO95HV-1^07218001.0056700 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010348 | 891198495-19495-DETAIL-03_10_2026-SVCROAD-1^06238004.0029608 | OTHER | HFTD Tier 2 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010349 | 891513203-88080-DETAIL-02_25_2025-GO95TCH-1^06240005.0017100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010350 | 891795113-21969-DTLTRT-10_08_2020-CUSTWIRE-1^668047/00 12/016 | OTHER | HFTD Tier 2 | Transmission | 2020-10-08 | 2023-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010351 | 891809806-88659-DETAIL-04_30_2026-GO95HV-1^668004/00 8/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010352 | 891990896-82896-DETAIL-06_02_2025-GO95HV-1^06148014.0363700 | OTHER | Non-HFTD | Distribution | 2025-06-02 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010353 | 89206448-61690-DETAIL-01_13_2026-SVCTREE-1^06239004.0245304 | OTHER | HFTD Tier 2 | Distribution | 2026-01-13 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010354 | 892077896-69229-DTLSB-04_30_2026-GO95HV-1^06142013.0172503 | OTHER | Non-HFTD | Distribution | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010355 | 892145341-65479-DETAIL-10_06_2025-GO95HV-1^06148001.0311710 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010356 | 89214989-43220-DETAIL-08_12_2025-GO95BLTC-1^06246002.0257200 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010357 | 89214989-43220-DETAIL-08_12_2025-GUYHINS-1^06246002.0257200 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-12 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010358 | 892288911-91079-DETAIL-10_08_2025-SVCENTCO-1^06246008.0023000 | OTHER | HFTD Tier 2 | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010359 | 892403731-14792-DTLSB-06_04_2026-GO95HV-1^07216001.0024900 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010360 | 89241365-81719-DTLSB-05_05_2026-GO95HV-1^06241009.0141601 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010361 | 892629604-11199-DETAIL-08_05_2024-CUSTWIRE-1^06244005.0324701 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010362 | 892681832-72202-DETAIL-05_15_2025-SVCROAD-1^06142012.0111002 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010363 | 892721794-65829-DETAIL-04_23_2026-GO95HV-1^06142012.0235801 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010364 | 892767948-47649-DTLSB-07_16_2025-GO95HV-1^06244006.0290200 | OTHER | HFTD Tier 2 | Distribution | 2025-07-16 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010365 | 893051878-479-DETAIL-06_16_2025-GO95HV-1^06248004.0360245 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010366 | 893165612-81639-DETAIL-05_21_2025-GO95HV-1^06243006.0153201 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010367 | 893433717-34719-DTLSB-07_08_2026-GO95HV-1^06242009.0267400 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010368 | 893796844-59859-DTLTRT-04_22_2026-GO95HV-1^668004/02 14/009 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010369 | 893811750-74732-DETAIL-04_07_2025-GO95TCH-1^06241005.0118501 | OTHER | HFTD Tier 2 | Distribution | 2025-04-07 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010370 | 893981130-93410-DTLSB-06_10_2026-CLMBTRE-1^07217001.0351401 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010371 | 89398373-32320-DETAIL-09_08_2025-GO95HV-1^06147001.0170401 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010372 | 894104475-56402-DETAIL-05_08_2024-GO95HV-1^06142012.0120105 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010373 | 894202805-52805-DETAIL-06_24_2025-GO95HV-1^06248004.0318905 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010374 | 894665585-96909-DETAIL-08_13_2025-GO95HV-1^06247006.0254500 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010375 | 894919591-41691-DETAIL-09_25_2025-GO95HV-1^07218001.0217601 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010376 | 895108629-1029-DETAIL-04_21_2025-GO95HV-1^06242006.0035702 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010377 | 89512396-94353-DTLSB-06_16_2026-SVCROAD-1^07217001.0356302 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010378 | 895321143-96699-DETAIL-10_06_2021-CUSTWIRE-1^06147005.0055901 | OTHER | Non-HFTD | Distribution | 2021-10-06 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010379 | 895565049-73873-DETAIL-05_12_2025-GO95HV-1^06243006.0301101 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010380 | 895592136-35229-DTLSB-04_28_2026-GRDRODHI-1^06142013.0187101 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010381 | 895592136-35229-DTLSB-04_28_2026-GRDRODHI-2^06142013.0187101 | OTHER | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010382 | 895731827-65590-DETAIL-01_12_2026-COVCOTHR-1^06239004.0245644 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010383 | 89598014-4162-DETAIL-10_06_2025-GO95HV-1^06243007.0253601 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010384 | 896156559-25739-DTLTRT-06_25_2025-GO95TCH-1^668087/00 11/006 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010385 | 896439993-27929-DETAIL-05_19_2025-GO95HV-1^06142012.0014300 | OTHER | Non-HFTD | Distribution | 2025-05-19 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010386 | 896617526-63961-DETAIL-02_19_2025-GO95TCH-1^06239004.0365700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010387 | 896714416-50910-DETAIL-02_25_2026-BIRDDMG-1^06239003.0241301 | POLE | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010388 | 896787972-99989-DETAIL-05_20_2025-GO95BLTC-1^06243006.0069100 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010389 | 896971604-58839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0219502 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010390 | 896987671-81301-DETAIL-04_09_2025-GO95BLTC-1^06241005.0021400 | OTHER | HFTD Tier 2 | Distribution | 2025-04-09 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010391 | 897141410-71943-DETAIL-10_09_2025-GO95HV-1^06248003.0335940 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010392 | 897460476-72839-DTLTRT-07_03_2025-GO95BLTC-1^668087/00 14/011 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010393 | 897460476-72839-DTLTRT-07_03_2025-GO95MLD-1^668087/00 14/011 | OTHER | Non-HFTD | Transmission | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010394 | 897470016-90369-DETAIL-02_17_2026-GO95HV-1^06239002.0092501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010395 | 897868119-95133-DETAIL-06_18_2026-SVCNEUT-1^07217001.0345303 | OTHER | Non-HFTD | Distribution | 2026-06-18 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010396 | 897997709-17370-DRONE_HY-06_30_2026-COVCOTHR-2^06240004.0169542 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010397 | 898201172-64684-DETAIL-04_02_2025-GUYHINS-1^06241005.0116702 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010398 | 898546378-87722-DETAIL-08_19_2025-GO95HV-1^06246002.0353901 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010399 | 898569465-86309-DETAIL-08_11_2025-GO95HV-1^06247006.0265501 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010400 | 898646725-47122-DRONE_HY-07_10_2026-DISTHDWR-1^06143014.0182301 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010401 | 898677329-19122-DETAIL-01_25_2023-ABNDEQPM-1^06147003.0023901 | OTHER | Non-HFTD | Distribution | 2023-01-25 | 2028-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010402 | 899308829-27149-DETAIL-08_27_2025-GO95HV-1^07216001.0162804 | OTHER | Non-HFTD | Distribution | 2025-08-27 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010403 | 899524884-94253-DETAIL-05_21_2026-GO95HV-1^07217001.0146504 | OTHER | Non-HFTD | Distribution | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010404 | 899533746-40879-DETAIL-07_29_2025-GO95HV-1^06247005.0261300 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010405 | 899594388-84110-DETAIL-09_23_2025-GUYHINS-1^07218001.0233001 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-23 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010406 | 899673806-9499-DETAIL-05_27_2025-GO95HV-1^06244006.0085800 | OTHER | HFTD Tier 2 | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010407 | 899834188-84188-DETAIL-08_20_2025-GO95HV-1^06246001.0175603 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010408 | 899964274-29432-ADMIN-05_21_2026-GO95GUYB-1^668086/00 11/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-21 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010409 | 900314240-21539-DTLSB-07_28_2025-GO95HV-1^07218001.0268501 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010410 | 900387684-72490-DETAIL-04_08_2026-GO95HV-1^06240002.0329200 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010411 | 90050600-38839-DTLTRT-02_15_2024-SVCROAD-1^07216001.0264101 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010412 | 900518119-56271-DETAIL-10_14_2025-GO95BLTC-1^07117008.0177001 | OTHER | HFTD Tier 2 | Distribution | 2025-10-14 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010413 | 900742391-53939-DETAIL-06_12_2024-CUSTWIRE-1^06244005.0248601 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010414 | 900788969-40232-DETAIL-10_01_2025-GO95HV-1^06148001.0302205 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010415 | 900817724-79839-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0218500 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010416 | 90085544-47219-DTLSB-01_27_2026-GO95HV-1^06242009.0057200 | OTHER | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010417 | 900961050-1570-DETAIL-02_18_2026-GO95HV-1^06239002.0042301 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010418 | 901489900-62219-DETAIL-10_13_2025-GO95HV-1^06246010.0237901 | OTHER | HFTD Tier 2 | Distribution | 2025-10-13 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010419 | 90152326-4391-DETAIL-05_07_2026-GO95HV-1^668038/00 4/054 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010420 | 901537768-90832-DTLTRT-08_05_2025-GUYNOINS-1^668087/00 3/018 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-05 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010421 | 901625478-51029-DTLSB-02_03_2026-BIRDDMG-1^06243009.0292500 | POLE | HFTD Tier 2 | Distribution | 2026-02-03 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010422 | 901856631-2380-DETAIL-02_20_2025-GUYHINS-1^06240004.0316702 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-20 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010423 | 902118443-88942-DTLSB-05_22_2024-GO95MLD-1^06243001.0102800 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010424 | 902333531-88659-DETAIL-06_24_2025-GO95HV-1^06248004.0314800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010425 | 902452452-61031-DETAIL-03_03_2025-CUSTWIRE-1^06241004.0180104 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010426 | 902843981-3739-DETAIL-05_07_2025-GO95HV-1^06243006.0353803 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010427 | 90291459-6170-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 4/063 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010428 | 903188754-68409-DETAIL-09_03_2025-GO95HV-1^06247006.0174101 | OTHER | HFTD Tier 2 | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010429 | 903622688-78989-DETAIL-08_14_2025-GO95HV-1^06246002.0264801 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010430 | 903656311-28311-DETAIL-09_08_2025-GO95HV-1^06247007.0016202 | OTHER | HFTD Tier 2 | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010431 | 903804815-98649-DTLSB-06_09_2026-SVCROAD-1^07216001.0225006 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010432 | 90388882-84149-DTLSB-07_21_2025-GO95HV-1^06244006.0230700 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010433 | 904127249-76390-DETAIL-01_14_2025-GO95MLD-1^06239004.0255003 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010434 | 904268411-86589-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0208600 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010435 | 905167636-63442-ADMIN-10_22_2025-GO95BLTC-1^06246011.0051501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010436 | 905400754-21852-DETAIL-09_08_2025-GO95HV-1^06147001.0280200 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010437 | 905947374-6160-DETAIL-01_14_2025-GO95MLD-1^06239004.0256107 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010438 | 906226042-26450-DETAIL-01_15_2026-BIRDDMG-1^06239004.0136210 | POLE | HFTD Tier 2 | Distribution | 2026-01-15 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010439 | 906268705-53779-DETAIL-10_28_2021-CUSTWIRE-1^06148005.0146100 | OTHER | Non-HFTD | Distribution | 2021-10-28 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010440 | 906304891-65723-DETAIL-06_18_2025-GO95HV-1^06248004.0348640 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010441 | 906563244-23990-DETAIL-03_02_2026-GO95HV-1^06239003.0269701 | OTHER | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010442 | 906903828-76730-DETAIL-01_22_2026-GO95MLD-1^06240003.0314901 | OTHER | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010443 | 907037015-38940-DTLSB-07_23_2025-GO95HV-1^07218001.0263700 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010444 | 907647633-21692-DRONE_HY-09_27_2023-GO95HV-1^668033/00 7X1/003 | OTHER | Non-HFTD | Transmission | 2023-09-27 | 2028-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010445 | 907785199-82453-DTLSB-04_29_2024-GO95MLD-1^06245007.0226442 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010446 | 908255348-47762-ADMIN-04_23_2024-ABNDEQPM-1^06145001.0022170-A | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010447 | 908482703-16119-DTLSB-03_18_2026-GO95HV-1^06242009.0084803 | OTHER | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010448 | 908637659-74939-DETAIL-06_10_2026-GUYHINS-1^668086/00 3/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010449 | 908637659-74939-DETAIL-06_10_2026-GUYHINS-2^668086/00 3/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010450 | 908645591-90762-DETAIL-09_11_2025-GO95HV-1^06147001.0083600 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010451 | 908829394-44353-DETAIL-07_02_2026-GO95HV-1^07217001.0031900 | OTHER | Non-HFTD | Distribution | 2026-07-02 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010452 | 908848644-14709-ADMIN-10_20_2025-SVCENTCO-1^06246012.0121700 | OTHER | HFTD Tier 2 | Distribution | 2025-10-20 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010453 | 908886438-71262-DTLTRT-06_23_2025-BIRDDMG-1^668087/00 16/002 | POLE | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010454 | 909043216-52689-DETAIL-07_29_2025-CUSTWIRE-1^06247005.0317700 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010455 | 909043216-52689-DETAIL-07_29_2025-GO95HV-1^06247005.0317700 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010456 | 909049079-55060-DTLTRT-05_06_2026-GO95HV-1^668004/00 6/022 | OTHER | Non-HFTD | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010457 | 909123528-15549-AUDIT-07_28_2025-GUYHINS-1^06244007.0136405 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010458 | 909188009-19409-DTLSB-09_03_2024-CUSTWIRE-1^06245007.0016300 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010459 | 909637388-81549-DTLSB-07_03_2025-GO95HV-1^06244007.0137403 | OTHER | HFTD Tier 2 | Distribution | 2025-07-03 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010460 | 909711824-14399-DETAIL-06_27_2022-CUSTWIRE-1^07116007.0156902 | OTHER | HFTD Tier 2 | Distribution | 2022-06-27 | 2025-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010461 | 909870541-28872-DETAIL-10_01_2025-CLRTOUCH-1^06148001.0302301 | CONDUCTOR | Non-HFTD | Distribution | 2025-10-01 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010462 | 909870541-28872-DETAIL-10_01_2025-GO95HV-1^06148001.0302301 | OTHER | Non-HFTD | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010463 | 910359237-41970-DETAIL-02_27_2025-SVCDEFLC-1^06240004.0061401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010464 | 910412844-17072-DETAIL-09_22_2025-GO95HV-1^06147001.0369701 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010465 | 910553471-15329-DTLSB-01_26_2026-BIRDDMG-1^06242009.0298803 | POLE | Non-HFTD | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010466 | 910602041-92880-DETAIL-02_19_2026-GO95HV-1^06239001.0064600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010467 | 911182837-23423-DETAIL-05_26_2026-ENCHRW-1^07217001.0147202 | OTHER | Non-HFTD | Distribution | 2026-05-26 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010468 | 911586298-40349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061900 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010469 | 911681599-4182-DTLSB-05_20_2024-GO95HV-1^06244003.0227000 | OTHER | Non-HFTD | Distribution | 2024-05-20 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010470 | 911779658-81459-DTLTRT-05_07_2026-GO95HV-1^668004/00 16/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010471 | 911779658-81459-DTLTRT-05_07_2026-GO95MLD-1^668004/00 16/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010472 | 911923479-12683-DETAIL-08_19_2025-SVCDEFLC-1^07216001.0175601 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010473 | 911991963-14359-DTLTRT-04_22_2026-GO95HV-1^668004/02 14/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010474 | 912123412-65412-DETAIL-09_15_2025-GO95HV-1^07219001.0323208 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010475 | 912787009-66509-DETAIL-09_10_2025-GO95HV-1^06246007.0249600 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010476 | 91284512-68909-ADMIN-10_23_2025-GO95HV-1^06246011.0358201 | OTHER | HFTD Tier 2 | Distribution | 2025-10-23 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010477 | 913480404-35822-DETAIL-10_13_2025-GUYHINS-2^06246012.0124601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-10-13 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010478 | 913647409-9399-DTLSB-05_19_2026-BIRDDMG-1^06240007.0072201 | POLE | Non-HFTD | Distribution | 2026-05-19 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010479 | 913821255-71282-DTLTRT-05_12_2026-GO95HV-1^668038/00 4/044 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010480 | 913966506-66779-DETAIL-04_08_2024-GO95HV-1^06147005.0245100 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010481 | 913977611-90509-DTLSB-11_01_2021-CUSTWIRE-1^06148004.0232601 | OTHER | Non-HFTD | Distribution | 2021-11-01 | 2024-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010482 | 914072598-16859-DETAIL-03_21_2024-CUSTWIRE-1^06246005.0073001 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010483 | 91447889-63879-DETAIL-02_19_2026-GO95HV-1^06239001.0063601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010484 | 91460859-99240-DETAIL-04_14_2026-GO95HV-1^06237004.0058303 | OTHER | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010485 | 914749811-71680-DETAIL-01_23_2026-GO95HV-1^06240004.0139300 | OTHER | HFTD Tier 3 | Distribution | 2026-01-23 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010486 | 915141841-13120-DETAIL-03_25_2025-COVCOTHR-1^06240004.0272503 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010487 | 915141841-13120-DETAIL-03_25_2025-COVCOTHR-4^06240004.0272503 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010488 | 915280476-12476-DETAIL-08_13_2025-GO95HV-1^06247006.0253301 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010489 | 915740789-86292-DETAIL-08_13_2025-GO95MLD-1^06246002.0364300 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010490 | 915775483-79309-DTLSB-01_13_2026-SVCENTCO-1^06242009.0325300 | OTHER | Non-HFTD | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010491 | 91583311-28629-DETAIL-05_02_2022-CUSTWIRE-1^06143012.0244800 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010492 | 915921539-59839-DETAIL-06_04_2025-GO95HV-1^668075/00 14/025 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010493 | 91631303-77720-DTLSB-03_22_2022-CUSTWIRE-1^06146005.0235402 | OTHER | Non-HFTD | Distribution | 2022-03-22 | 2025-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010494 | 916524851-81529-DTLSB-03_10_2026-CUSTWIRE-1^06243009.0348101 | OTHER | Non-HFTD | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010495 | 916524851-81529-DTLSB-03_10_2026-GO95HV-1^06243009.0348101 | OTHER | Non-HFTD | Distribution | 2026-03-10 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010496 | 916547875-43263-DETAIL-07_29_2025-GO95HV-1^06247005.0317803 | OTHER | Non-HFTD | Distribution | 2025-07-29 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010497 | 91665168-9720-DETAIL-08_19_2025-GO95HV-1^06246002.0353700 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010498 | 916711574-56381-DETAIL-04_17_2025-GO95MLD-1^06242005.0361601 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010499 | 916783442-20553-DETAIL-06_30_2026-COPLLEAN-1^07217001.0229600 | POLE | Non-HFTD | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010500 | 917077757-50149-DETAIL-06_10_2025-GO95HV-1^06245006.0291700 | OTHER | Non-HFTD | Distribution | 2025-06-10 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010501 | 917460196-38970-DETAIL-01_15_2025-GO95HV-1^06239004.0256104 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010502 | 917460196-38970-DRONE_HY-07_10_2026-COVCOTHR-1^06239004.0256104 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-07-10 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010503 | 917484528-35779-DETAIL-08_07_2025-GO95HV-1^06246002.0269900 | OTHER | Non-HFTD | Distribution | 2025-08-07 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010504 | 917609592-32950-DETAIL-02_11_2026-GO95HV-1^06239003.0016400 | OTHER | HFTD Tier 2 | Distribution | 2026-02-11 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010505 | 917736889-86343-DETAIL-07_28_2025-GO95HV-1^06247005.0197200 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010506 | 917878106-14309-DETAIL-08_11_2025-GO95HV-1^06247006.0265500 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010507 | 917962541-82299-DETAIL-09_18_2025-GO95HV-1^06248007.0278300 | OTHER | Non-HFTD | Distribution | 2025-09-18 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010508 | 918154874-59029-DETAIL-04_23_2026-GUYHINS-1^06142012.0145000 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010509 | 918603757-88049-DETAIL-06_04_2025-GO95HV-1^06245006.0299800 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010510 | 918818198-24012-DTLSB-05_05_2026-GO95HV-1^06142013.0152001 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010511 | 918829003-47959-DETAIL-09_15_2025-GO95HV-1^06248007.0233400 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010512 | 919326500-9540-DETAIL-01_22_2026-COVCOTHR-2^06239003.0070903 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-22 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010513 | 919326500-9540-DETAIL-02_06_2025-GUYHINS-1^06239003.0070903 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-06 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010514 | 919803295-93295-DETAIL-06_23_2026-GO95HV-1^07217001.0107203 | OTHER | Non-HFTD | Distribution | 2026-06-23 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010515 | 919832639-61440-DETAIL-03_10_2026-COVCOTHR-1^06239003.0061102 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-10 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010516 | 920190544-7039-DTLTRT-07_08_2025-BIRDDMG-1^668087/00 5/026 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010517 | 920411060-23122-DETAIL-03_13_2024-GO95HV-1^06147004.0180901 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010518 | 920598690-79222-DETAIL-09_29_2025-GUYHINS-1^06148001.0310508 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-29 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010519 | 920724489-61259-DTLTRT-05_07_2026-GO95HV-1^668004/00 20/024 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010520 | 920724489-61259-DTLTRT-05_07_2026-GUYHINS-3^668004/00 20/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010521 | 921032663-33222-ADMIN-10_21_2025-GUYHINS-1^06247001.0265400 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-21 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010522 | 921335305-67170-DETAIL-01_24_2025-GO95HV-1^06239004.0258741 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010523 | 921715214-86381-DETAIL-04_17_2025-GO95MLD-1^06242005.0360701 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010524 | 921801945-80163-DETAIL-07_07_2026-SVCDEFLC-1^07217001.0216903 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010525 | 922118678-85922-DTLSB-05_07_2026-GO95HV-1^06142013.0287400 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010526 | 922473323-16509-DETAIL-09_17_2025-GO95HV-1^06246007.0139250 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010527 | 922483255-77800-DETAIL-04_28_2025-GO95HV-1^06239002.0061703 | OTHER | HFTD Tier 2 | Distribution | 2025-04-28 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010528 | 922555614-90289-DETAIL-09_04_2025-GO95HV-1^06147001.0309001 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010529 | 922758434-84579-DETAIL-09_11_2025-GO95HV-1^06248007.0222801 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010530 | 922859569-90730-DTLTRT-05_27_2025-GO95HV-1^668075/00 2/005 | OTHER | Non-HFTD | Transmission | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010531 | 92291306-81810-DETAIL-02_25_2026-BIRDDMG-1^06239003.0135000 | POLE | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010532 | 923035571-49281-DETAIL-10_07_2021-SVCWIND-1^06147005.0043900 | OTHER | Non-HFTD | Distribution | 2021-10-07 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010533 | 923294513-25532-DETAIL-03_14_2024-GO95HV-1^06147004.0301700 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010534 | 923559151-21251-DETAIL-02_10_2026-ENCHRW-1^06239003.0015703 | OTHER | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010535 | 923637924-82129-DETAIL-04_28_2026-GUYHINS-1^06142012.0149707 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-28 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010536 | 923735768-52989-DETAIL-08_25_2025-GO95HV-1^06246001.0205700 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010537 | 923766926-22370-DETAIL-01_14_2025-GO95HV-1^06239004.0256111 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010538 | 923777261-23950-DETAIL-02_26_2026-COVCOTHR-1^06238004.0027701 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010539 | 923784560-5238-DTLSB-07_21_2025-GO95HV-1^06244006.0233802 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010540 | 924133698-41019-ADMIN-06_17_2026-FRGNELEC-2^668036/00 8/036 | OTHER | Non-HFTD | Transmission | 2026-06-17 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010541 | 924196408-36232-DETAIL-04_23_2026-GUYHINS-1^06142012.0144700 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010542 | 924295535-85489-DTLSB-07_09_2025-GO95HV-1^06244006.0345603 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010543 | 924467093-45683-DTLSB-06_04_2026-SVCENTBK-1^07216001.0114200 | OTHER | Non-HFTD | Distribution | 2026-06-04 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010544 | 924533704-33732-DETAIL-09_05_2025-GO95HV-1^06147001.0290001 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010545 | 924669538-57179-ADMIN-11_12_2025-GO95HV-1^06246001.0330500 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010546 | 924810265-89600-DETAIL-04_08_2026-GO95HV-1^06240002.0329202 | OTHER | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010547 | 924838564-98283-DETAIL-07_31_2025-SVCDEFLC-1^06247006.0207740 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010548 | 925255189-16710-DETAIL-02_20_2025-SVCDEFLC-1^06241005.0268000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-20 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010549 | 925626550-76122-DTLTRT-04_27_2026-GO95HV-1^668004/00 6/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010550 | 925626550-81632-DTLTRT-04_27_2026-GO95HV-1^668004/00 6/006 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010551 | 925702949-35229-DETAIL-04_27_2026-GO95HV-1^06142012.0146504 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010552 | 926123471-93809-DETAIL-10_07_2025-GO95BLTC-1^06246008.0065100 | OTHER | HFTD Tier 2 | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010553 | 926244956-32309-DETAIL-08_12_2025-GO95HV-1^06247006.0268102 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010554 | 926367281-8289-DETAIL-08_04_2025-SVCDEFLC-1^06247006.0209703 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010555 | 926459556-75642-ADMIN-10_22_2025-GO95BLTC-1^06247011.0329200 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010556 | 926637849-65142-DETAIL-08_11_2025-GO95HV-1^06246002.0263901 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010557 | 926679388-7309-DETAIL-05_05_2025-GO95HV-1^06243006.0347002 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010558 | 926922100-31200-AUDIT-06_24_2025-RISEBKSP-1^06142012.0013803 | OTHER | Non-HFTD | Distribution | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010559 | 927036616-85009-DETAIL-06_09_2025-GO95HV-1^06245007.0243740 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010560 | 927307890-63369-DETAIL-06_16_2025-GO95HV-1^06248005.0284100 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010561 | 927587686-41259-DETAIL-07_21_2025-GO95HV-1^06247005.0114500 | OTHER | Non-HFTD | Distribution | 2025-07-21 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010562 | 927753733-85239-ADMIN-08_11_2025-POLEDERP-1^07113001.0055500 | POLE | Non-HFTD | Distribution | 2025-08-11 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010563 | 927771719-49819-DRONE_HY-07_15_2026-UBPBXARM-1^668036/00 8/052 | CROSSARM | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010564 | 927892416-30142-DETAIL-08_26_2025-GUYHINS-1^07216001.0168501 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-26 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010565 | 927909889-1342-DETAIL-08_18_2025-GO95HV-1^06246002.0346900 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010566 | 927993660-44073-DETAIL-06_16_2025-ABNDEQPM-1^06248005.0327201 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010567 | 928043425-91249-DETAIL-05_30_2025-GO95HV-1^06244006.0146602 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010568 | 928265925-17029-DETAIL-04_21_2025-GO95HV-1^06242006.0075600 | OTHER | Non-HFTD | Distribution | 2025-04-21 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010569 | 928330749-93300-DTLTRT-07_08_2025-BIRDDMG-1^668087/00 8/026 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010570 | 928525280-82670-DETAIL-02_17_2026-GO95HV-1^06239002.0092500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010571 | 928601420-38029-DETAIL-05_29_2025-GO95HV-1^06142012.0101002 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010572 | 928640437-66140-DETAIL-04_07_2026-GO95HV-1^06240002.0317111 | OTHER | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010573 | 928689498-38250-DETAIL-02_10_2026-SVCDEFLC-1^06239003.0018307 | OTHER | Non-HFTD | Distribution | 2026-02-10 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010574 | 928760186-18491-DETAIL-05_11_2026-GO95HV-1^668038/00 1/052 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010575 | 928760186-25452-DETAIL-05_11_2026-GO95HV-1^668038/00 1/052 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010576 | 928818274-53659-DETAIL-07_28_2025-GUYHINS-1^06247005.0303600 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-07-28 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010577 | 928826247-47590-DETAIL-01_31_2025-GO95HV-1^06239004.0242941 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010578 | 928986978-7552-DETAIL-08_25_2025-GO95HV-1^06246001.0206900 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010579 | 929124150-56159-DETAIL-06_05_2025-GO95HV-1^06245007.0249200 | OTHER | HFTD Tier 2 | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010580 | 929205568-18439-DETAIL-09_02_2025-GO95HV-1^07216001.0161605 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010581 | 929253541-54541-DETAIL-02_25_2025-SVCDEFLC-1^06240004.0218805 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010582 | 929384843-70330-DETAIL-04_26_2023-CUSTWIRE-1^06240004.0066002 | OTHER | HFTD Tier 2 | Distribution | 2023-04-26 | 2026-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010583 | 92947388-57870-DETAIL-02_26_2025-GO95CL10-1^06240004.0060300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010584 | 929771736-80689-DETAIL-10_06_2025-GO95HV-1^06148001.0184001 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010585 | 929828655-34449-DTLSB-07_09_2025-GO95HV-1^06244006.0348500 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010586 | 930264533-85639-DTLSB-08_11_2025-GO95HV-1^07217001.0012300 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010587 | 930280658-13929-DTLSB-08_10_2023-CUSTWIRE-1^06243009.0157100 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010588 | 930392453-13451-DETAIL-03_15_2017-CUSTWIRE-1^06241005.0026503 | OTHER | HFTD Tier 2 | Distribution | 2017-03-15 | 2020-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010589 | 930411129-45862-DETAIL-09_05_2025-GO95HV-1^06147001.0294200 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010590 | 930657960-35743-DETAIL-06_29_2026-GO95HV-1^07217001.0159503 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010591 | 930762403-53729-DETAIL-03_06_2017-SVCWIND-1^06142012.0130611 | OTHER | Non-HFTD | Distribution | 2017-03-06 | 2020-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010592 | 930898328-66191-DTLTRT-05_06_2026-GO95HV-1^668038/00 2/058 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010593 | 931082470-92798-DTLTRT-05_21_2026-GO95HV-1^668086/00 12/014 | OTHER | Non-HFTD | Transmission | 2026-05-21 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010594 | 932129543-79543-DETAIL-06_09_2025-GO95HV-1^668075/00 8/030 | OTHER | Non-HFTD | Transmission | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010595 | 932848936-78799-ADMIN-10_22_2025-GO95BLTC-1^06246011.0057801 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010596 | 932848936-78799-ADMIN-10_22_2025-GO95TCH-1^06246011.0057801 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010597 | 932879904-96050-DTLTRT-07_02_2025-BIRDDMG-1^668087/00 6/017 | POLE | Non-HFTD | Transmission | 2025-07-02 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010598 | 932913948-60850-DETAIL-03_25_2025-GO95HV-1^06239003.0019404 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010599 | 93355921-71449-DETAIL-04_24_2024-SVCROAD-1^06245007.0225604 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010600 | 933590348-15972-DTLTRT-06_23_2025-GO95BLTC-1^668087/00 2/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010601 | 933824509-27239-DETAIL-05_12_2025-GO95HV-1^06243006.0310902 | OTHER | Non-HFTD | Distribution | 2025-05-12 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010602 | 934229398-89139-DETAIL-05_06_2025-GO95HV-1^06243006.0309002 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010603 | 934396665-92759-DETAIL-07_28_2025-GO95HV-1^06247005.0313601 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010604 | 934623048-58182-ADMIN-11_04_2025-GO95HV-1^06246001.0264301 | OTHER | Non-HFTD | Distribution | 2025-11-04 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010605 | 934699873-5313-DTLSB-04_25_2024-CUSTWIRE-1^06245007.0228547 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010606 | 934705253-59799-DETAIL-08_20_2025-GO95HV-1^06247006.0256601 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010607 | 934705253-59799-DETAIL-08_20_2025-GO95MLD-1^06247006.0256601 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010608 | 934863220-87289-DETAIL-08_12_2025-GO95HV-1^06246001.0300100 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010609 | 934898711-45750-DETAIL-02_26_2026-GO95TCH-1^06238004.0027700 | OTHER | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010610 | 935085815-95815-DETAIL-06_24_2025-GO95HV-1^06248004.0312906 | OTHER | HFTD Tier 2 | Distribution | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010611 | 935103686-13449-DTLSB-07_09_2025-GO95HV-1^06244006.0276002 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010612 | 93550216-84030-ADMIN-10_30_2025-GUYHINS-1^06246001.0101801 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-30 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010613 | 935526670-32640-DETAIL-03_11_2026-COVCOTHR-1^06238004.0012702 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-11 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010614 | 935571325-11109-DETAIL-09_24_2025-GO95BLTC-1^06246009.0167400 | OTHER | HFTD Tier 2 | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010615 | 935764014-54222-ADMIN-10_21_2025-GO95HV-1^06246012.0053501 | OTHER | HFTD Tier 2 | Distribution | 2025-10-21 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010616 | 93581071-93380-DETAIL-02_18_2026-GO95HV-1^06239002.0049401 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010617 | 935904181-27389-ADMIN-10_27_2025-GO95HV-1^06246001.0116901 | OTHER | Non-HFTD | Distribution | 2025-10-27 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010618 | 935979985-61369-DTLSB-05_05_2026-SVCDEFLC-1^06241009.0148900 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010619 | 936325623-63799-DETAIL-05_30_2025-GO95HV-1^06244006.0090601 | OTHER | Non-HFTD | Distribution | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010620 | 936635328-81082-DTLTRT-06_23_2025-ABNDEQPM-1^668087/00 18/001 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010621 | 936683009-72842-DETAIL-04_28_2025-ENCHRW-1^06242006.0091002 | OTHER | Non-HFTD | Distribution | 2025-04-28 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010622 | 936983540-5369-DTLSB-06_25_2025-GO95HV-1^06244007.0104801 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010623 | 937073741-64692-DETAIL-09_11_2025-GO95MLD-1^07216001.0078702 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010624 | 937081222-27419-DTLSB-04_08_2026-GO95HV-1^06241009.0109100 | OTHER | Non-HFTD | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010625 | 937142849-21859-DETAIL-06_16_2025-GO95HV-1^06248005.0330841 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010626 | 937257732-87909-ADMIN-11_10_2025-GO95HV-1^06246011.0358600 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010627 | 937471136-89199-DTLSB-07_01_2025-GO95HV-1^06244006.0226306 | OTHER | Non-HFTD | Distribution | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010628 | 937826559-91992-DETAIL-09_05_2025-GO95HV-1^06147001.0294900 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010629 | 938093598-58092-DETAIL-08_13_2025-GO95MLD-1^06246002.0254701 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010630 | 938162674-73109-DETAIL-07_31_2025-GO95HV-1^06247006.0207702 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010631 | 938253111-16031-DETAIL-04_17_2025-GO95MLD-1^06242005.0351500 | OTHER | HFTD Tier 2 | Distribution | 2025-04-17 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010632 | 938417359-74829-DTLSB-02_16_2026-GRDRODHI-1^06243009.0309801 | OTHER | HFTD Tier 2 | Distribution | 2026-02-16 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010633 | 938572612-37731-AUDIT-03_04_2025-RISEGRD-1^06241005.0175601 | OTHER | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010634 | 938572612-37731-DETAIL-02_27_2025-GO95MLD-1^06241005.0175601 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010635 | 938628776-72039-DETAIL-05_20_2025-GO95HV-1^06243006.0090101 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010636 | 938865741-42530-DTLTRT-05_28_2025-GO95HV-1^668075/00 15/005 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010637 | 939177940-9143-DETAIL-10_09_2025-GO95HV-1^06248003.0289040 | OTHER | HFTD Tier 2 | Distribution | 2025-10-09 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010638 | 939276139-13739-DTLTRT-06_25_2025-BIRDDMG-1^668087/00 1/006 | POLE | Non-HFTD | Transmission | 2025-06-25 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010639 | 939477584-10684-DTLTRT-08_04_2025-POLEDERP-1^668087/00 14/028 | POLE | Non-HFTD | Transmission | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010640 | 939534804-56353-DETAIL-09_23_2025-GO95MLD-1^07218001.0224601 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010641 | 939554568-659-DTLSB-08_13_2025-GO95HV-1^07217001.0024501 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010642 | 939737846-9589-DETAIL-08_11_2025-GO95HV-1^06247006.0268301 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010643 | 93985629-95279-DETAIL-07_29_2024-CUSTWIRE-1^06245006.0149201 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010644 | 940039559-41979-DETAIL-08_25_2025-GO95HV-1^06247006.0330900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010645 | 940068248-44469-DETAIL-09_02_2025-GO95HV-1^06247006.0276502 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010646 | 940075708-15692-DTLSB-05_14_2024-GO95MLD-1^06244001.0221400 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010647 | 940093368-6692-DTLSB-05_06_2026-GO95HV-1^06142013.0274100 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010648 | 940206106-949-DTLSB-07_10_2025-GO95HV-1^06244007.0112641 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010649 | 94042931-51201-AUDIT-01_26_2026-SVCROAD-1^06239004.0136112 | OTHER | HFTD Tier 2 | Distribution | 2026-01-26 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010650 | 941069326-65419-DTLSB-07_08_2026-GO95HV-1^06242009.0248301 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010651 | 941558360-3870-DETAIL-02_14_2025-GO95HV-1^06240004.0168304 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010652 | 941726297-36439-DTLTRT-06_23_2025-BIRDDMG-1^668087/00 8A/001 | POLE | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010653 | 941836047-85970-DETAIL-02_25_2025-SVCENTCO-1^06240004.0061110 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010654 | 942064079-78509-DETAIL-08_21_2025-GO95HV-1^06247006.0267701 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010655 | 942204293-11853-DETAIL-09_24_2025-GO95HV-1^07218001.0229100 | OTHER | Non-HFTD | Distribution | 2025-09-24 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010656 | 942264505-60059-DETAIL-09_16_2025-ENCHRW-1^06247004.0183402 | OTHER | Non-HFTD | Distribution | 2025-09-16 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010657 | 942380433-71359-DTLTRT-04_22_2026-GO95HV-1^668004/02 8/001 | OTHER | Non-HFTD | Transmission | 2026-04-22 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010658 | 942668128-69128-DETAIL-06_05_2025-GO95HV-1^06148014.0245402 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010659 | 942714413-13303-DTLTRT-05_13_2026-GO95HV-1^668085/00 8/001 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010660 | 942924736-5660-DETAIL-04_30_2026-GO95HV-1^668004/00 1/016 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010661 | 943049703-32480-DETAIL-03_04_2025-GO95TCH-1^06240004.0150500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010662 | 943096492-55253-DETAIL-07_23_2025-CUSTWIRE-1^06247005.0176400 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010663 | 943392503-1509-DETAIL-09_10_2025-GO95HV-1^06246007.0132251 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010664 | 943716844-19839-DETAIL-05_06_2025-GO95HV-1^06243006.0031400 | OTHER | Non-HFTD | Distribution | 2025-05-06 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010665 | 9438755-69200-DETAIL-02_25_2026-GO95TCH-1^06239003.0242100 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010666 | 943990904-24904-DTLTRT-07_01_2025-GUYNOINS-2^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010667 | 943990904-24904-DTLTRT-07_01_2025-GUYNOINS-3^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010668 | 943990904-24904-DTLTRT-07_01_2025-GUYNOINS-4^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010669 | 943990904-2734-DTLTRT-07_01_2025-GUYNOINS-1^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010670 | 943990904-2734-DTLTRT-07_01_2025-GUYNOINS-3^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010671 | 943990904-2734-DTLTRT-07_01_2025-GUYNOINS-4^668087/00 6/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-01 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010672 | 944042150-54559-DETAIL-08_06_2025-GO95HV-1^06247005.0206101 | OTHER | Non-HFTD | Distribution | 2025-08-06 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010673 | 944120011-41011-DETAIL-09_18_2025-GUYHINS-1^07218001.0086402 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-09-18 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010674 | 944219159-98113-DTLTRT-06_24_2025-GO95HV-1^668087/00 13/004 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010675 | 944334139-73213-DETAIL-08_19_2025-GO95HV-1^06246002.0369701 | OTHER | Non-HFTD | Distribution | 2025-08-19 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010676 | 944673444-82569-DETAIL-10_01_2025-ABNDEQPM-1^06246009.0127800 | OTHER | HFTD Tier 2 | Distribution | 2025-10-01 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010677 | 944873315-53189-ADMIN-08_15_2025-POLETOP-1^06247005.0342501 | POLE | Non-HFTD | Distribution | 2025-08-15 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010678 | 944879945-64200-DETAIL-02_25_2026-CUSTWIRE-1^06239003.0242102 | OTHER | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010679 | 944938378-99449-DETAIL-09_03_2025-GO95HV-1^07216001.0099005 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010680 | 945041143-4959-DETAIL-09_15_2025-GO95HV-1^06248007.0231101 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010681 | 945233873-85873-DETAIL-07_07_2026-SVCENTBK-1^07217001.0220503 | OTHER | Non-HFTD | Distribution | 2026-07-07 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010682 | 945516076-40199-DTLSB-07_09_2025-GO95HV-1^06244006.0276402 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010683 | 945811076-4679-ADMIN-10_30_2025-GO95CL10-1^06246001.0047002 | OTHER | Non-HFTD | Distribution | 2025-10-30 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010684 | 945939037-64978-DETAIL-08_26_2025-GO95HV-1^06247006.0333900 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010685 | 945957509-8509-DETAIL-02_18_2026-GO95HV-1^06239002.0165900 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010686 | 946054443-66880-DETAIL-02_17_2026-GO95HV-1^06239002.0180502 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010687 | 946060668-80440-DETAIL-04_22_2025-GRDRODHI-1^06240003.0077201 | OTHER | HFTD Tier 2 | Distribution | 2025-04-22 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010688 | 9461253-40899-DTLSB-01_21_2026-BIRDDMG-1^06242009.0297111 | POLE | Non-HFTD | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010689 | 946230186-85070-DETAIL-01_24_2025-GO95HV-1^06239004.0257940 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010690 | 946263831-67439-DETAIL-05_08_2025-GO95BLTC-1^06243006.0162300 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010691 | 946266898-26329-DTLTRT-05_12_2026-GO95MLD-1^668086/00 1X4/001 | OTHER | Non-HFTD | Transmission | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010692 | 946527476-19476-DETAIL-05_29_2025-GO95HV-1^06148014.0360400 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010693 | 946587976-75450-DETAIL-09_15_2025-GO95HV-1^07219001.0333400 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010694 | 9467669-92859-AUDIT-08_19_2025-GUYHINS-1^06246002.0364500 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010695 | 946802893-31799-DETAIL-05_28_2025-GO95HV-1^06244006.0094300 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010696 | 947131991-44123-DTLTRT-04_23_2026-GO95HV-1^668004/00 1/003 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010697 | 947153129-37430-AUDIT-05_07_2026-GUYTAIL-1^06240004.0150240 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2026-05-07 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010698 | 947416325-95339-DETAIL-06_11_2026-GUYHINS-1^668086/00 6/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-11 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010699 | 947474787-74987-DETAIL-06_09_2025-GO95HV-1^06245006.0191303 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010700 | 947474787-74987-DETAIL-06_09_2025-RISEGRD-1^06245006.0191303 | OTHER | HFTD Tier 2 | Distribution | 2025-06-09 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010701 | 947496814-11099-DETAIL-01_29_2026-GO95BLTC-1^06242009.0051501 | OTHER | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010702 | 947541495-54530-DETAIL-01_27_2025-SVCDEFLC-1^06240004.0085340 | OTHER | HFTD Tier 2 | Distribution | 2025-01-27 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010703 | 947973990-69559-DETAIL-06_18_2025-GO95HV-1^06248004.0341901 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010704 | 948332196-43759-DETAIL-04_30_2026-GO95HV-1^668004/00 8/017 | OTHER | Non-HFTD | Transmission | 2026-04-30 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010705 | 948333826-45023-DETAIL-05_15_2025-GO95MLD-1^06142012.0115204 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010706 | 948473958-64999-DTLSB-07_10_2025-GO95HV-1^06244007.0144900 | OTHER | HFTD Tier 2 | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010707 | 948556768-87223-DTLSB-05_05_2026-GO95HV-1^06142013.0222900 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010708 | 94913240-44830-DTLTRT-05_14_2026-GO95HV-1^668086/00 10/005 | OTHER | Non-HFTD | Transmission | 2026-05-14 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010709 | 94913283-86780-DETAIL-02_11_2025-GO95MLD-1^06240004.0355403 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010710 | 94913283-86780-DETAIL-03_31_2026-COVCOTHR-1^06240004.0355403 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010711 | 94913283-86780-DETAIL-03_31_2026-COVCOTHR-2^06240004.0355403 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010712 | 949186591-28939-DETAIL-05_01_2025-GO95HV-1^06243006.0335802 | OTHER | Non-HFTD | Distribution | 2025-05-01 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010713 | 949414493-34493-DETAIL-06_23_2026-GUYHINS-1^07217001.0115505 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-23 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010714 | 949501272-95952-DETAIL-06_26_2023-CUSTWIRE-1^06244010.0259001 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010715 | 949512791-44230-DTLSB-08_13_2025-GO95HV-1^07218001.0287801 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010716 | 949833319-98359-DETAIL-06_17_2025-GO95HV-1^06248004.0357002 | OTHER | HFTD Tier 2 | Distribution | 2025-06-17 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010717 | 94987176-70276-DETAIL-08_21_2025-GRDRODHI-1^06247006.0266900 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010718 | 949959164-15839-DETAIL-07_09_2024-CUSTWIRE-1^06244005.0229000 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010719 | 950034298-40050-DETAIL-02_24_2026-GO95HV-1^06239003.0132203 | OTHER | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010720 | 950056424-19223-DETAIL-09_08_2025-GO95HV-1^06147001.0332201 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010721 | 950094300-43139-DTLTRT-07_10_2025-BIRDDMG-1^668087/00 10/024 | POLE | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010722 | 950094300-43139-DTLTRT-07_10_2025-GO95HV-1^668087/00 10/024 | OTHER | Non-HFTD | Transmission | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010723 | 950734016-70800-DETAIL-02_05_2026-GO95TCH-1^06239003.0018704 | OTHER | Non-HFTD | Distribution | 2026-02-05 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010724 | 950990474-41699-DETAIL-10_06_2025-GO95HV-1^06243007.0361400 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010725 | 951135458-39799-DETAIL-06_16_2025-BIRDDMG-1^06248004.0361141 | POLE | HFTD Tier 2 | Distribution | 2025-06-16 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010726 | 951135458-39799-DETAIL-06_16_2025-GO95HV-1^06248004.0361141 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010727 | 951244506-7209-DETAIL-08_12_2025-GO95HV-1^06247006.0264000 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010728 | 951507468-16699-DTLSB-01_29_2026-BIRDDMG-1^06242009.0054900 | POLE | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010729 | 951980326-82010-DETAIL-02_11_2026-SVCDEFLC-1^06239003.0017500 | OTHER | Non-HFTD | Distribution | 2026-02-11 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010730 | 952025963-82433-DTLSB-05_28_2026-GO95HV-1^07216001.0020600 | OTHER | Non-HFTD | Distribution | 2026-05-28 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010731 | 952313820-29933-DETAIL-09_29_2025-GO95HV-1^06148001.0312703 | OTHER | Non-HFTD | Distribution | 2025-09-29 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010732 | 952465983-36983-DETAIL-05_14_2025-GUYNOINS-2^06142012.0119803 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-05-14 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010733 | 952757517-92333-DTLTRT-06_23_2025-GUYHINS-2^668087/00 9/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-23 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010734 | 952803304-51679-DETAIL-08_19_2025-GUYHINS-1^06247006.0367302 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-19 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010735 | 953041188-91188-DETAIL-06_19_2025-GUYHINS-1^668075/00 3X/049 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-19 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010736 | 953041188-91188-DETAIL-06_19_2025-GUYHINS-3^668075/00 3X/049 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2025-06-19 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010737 | 953078801-1733-DTLSB-05_07_2026-GO95HV-1^06142013.0348601 | OTHER | Non-HFTD | Distribution | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010738 | 95318892-53339-DETAIL-05_08_2025-GO95CL10-1^06243006.0218200 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010739 | 953298385-21991-DTLTRT-05_12_2026-GO95HV-1^668038/00 2/045 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010740 | 953843683-16680-DETAIL-02_17_2026-GO95HV-1^06239002.0090902 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010741 | 954031658-23233-DETAIL-08_18_2025-GO95HV-1^06246002.0357901 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010742 | 954031658-23233-DETAIL-08_18_2025-GO95MLD-1^06246002.0357901 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010743 | 954110388-54998-DETAIL-04_02_2025-GUYNOINS-1^06241005.0118700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010744 | 954141641-72311-DETAIL-04_16_2025-GO95MLD-1^06242005.0351400 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010745 | 954557631-44801-DETAIL-04_15_2026-PWRTRN-1^06237004.0195800 | OTHER | HFTD Tier 2 | Distribution | 2026-04-15 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010746 | 954600850-19520-DETAIL-03_23_2026-SVCTREE-1^06240004.0219842 | OTHER | HFTD Tier 2 | Distribution | 2026-03-23 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010747 | 954605788-69359-DTLTRT-05_07_2026-GO95HV-1^668004/00 11/026 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010748 | 954714811-83879-DETAIL-07_31_2025-SVCENTCO-1^06247006.0208700 | OTHER | HFTD Tier 2 | Distribution | 2025-07-31 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010749 | 954908385-32549-DTLSB-07_10_2025-GO95HV-1^06244006.0342701 | OTHER | Non-HFTD | Distribution | 2025-07-10 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010750 | 955002981-66201-DRONE_HY-07_02_2026-GO95MLD-1^06239004.0257242 | OTHER | HFTD Tier 2 | Distribution | 2026-07-02 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010751 | 955046808-80879-DETAIL-09_09_2025-GO95HV-1^06146001.0100400 | OTHER | Non-HFTD | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010752 | 955150156-48740-DETAIL-06_25_2026-GO95HV-1^07218001.0345101 | OTHER | Non-HFTD | Distribution | 2026-06-25 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010753 | 955310480-53970-DETAIL-02_19_2026-GO95HV-1^06239002.0025500 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010754 | 955529890-52032-DTLTRT-05_05_2026-GO95HV-1^668004/00 3/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010755 | 955529890-76143-DTLTRT-05_05_2026-GO95HV-1^668004/00 3/007 | OTHER | HFTD Tier 2 | Transmission | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010756 | 955575443-6723-DETAIL-06_18_2025-GO95HV-1^06248004.0337141 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010757 | 955714319-70343-DTLSB-05_20_2024-GO95HV-1^06244003.0270800 | OTHER | Non-HFTD | Distribution | 2024-05-20 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010758 | 955820116-78370-DETAIL-01_24_2025-GO95HV-1^06239004.0257944 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010759 | 955835563-33109-DETAIL-08_21_2025-GO95HV-1^06247006.0257802 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010760 | 955840294-3255-DETAIL-05_08_2025-GO95HV-1^06243006.0209000 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010761 | 95584212-16212-DTLSB-07_09_2025-GO95MLD-1^06244006.0276200 | OTHER | Non-HFTD | Distribution | 2025-07-09 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010762 | 955873306-8306-DETAIL-07_11_2024-CUSTWIRE-1^06244005.0219000 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010763 | 956049071-1422-DTLTRT-04_23_2026-BIRDDMG-1^668004/00 11/002 | POLE | HFTD Tier 2 | Transmission | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010764 | 956049071-1422-DTLTRT-04_23_2026-GO95HV-1^668004/00 11/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010765 | 956049071-1422-DTLTRT-04_23_2026-INSULDMG-1^668004/00 11/002 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2026-04-23 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010766 | 956167380-80532-DETAIL-04_02_2025-GO95CL10-1^06241005.0118604 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010767 | 956298558-53249-ADMIN-09_24_2024-POLEDERP-1^07117001.0303401 | POLE | HFTD Tier 2 | Distribution | 2024-09-24 | 2025-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010768 | 956298558-53249-DETAIL-05_16_2022-GO95MLD-1^07117001.0303401 | OTHER | HFTD Tier 2 | Distribution | 2022-05-16 | 2025-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010769 | 956510374-62260-DETAIL-01_14_2025-SVCWIND-1^06239004.0256106 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010770 | 956558065-31165-DETAIL-06_03_2025-GO95HV-1^06148014.0248702 | OTHER | HFTD Tier 2 | Distribution | 2025-06-03 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010771 | 956655181-76181-DETAIL-05_07_2025-GO95HV-1^06243006.0287300 | OTHER | Non-HFTD | Distribution | 2025-05-07 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010772 | 956657208-67559-DTLSB-08_14_2025-GO95HV-1^07217001.0024203 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010773 | 956930229-82739-DTLTRT-06_25_2025-GO95BLTC-1^668087/00 19/005 | OTHER | Non-HFTD | Transmission | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010774 | 956980340-67170-DRONE_HY-06_30_2026-COVCOTHR-1^06240004.0166512 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-30 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010775 | 957159273-77083-DETAIL-08_04_2025-GO95HV-1^06247006.0207541 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010776 | 957413598-27540-DETAIL-02_25_2026-BIRDDMG-1^06239003.0139203 | POLE | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010777 | 957495401-85043-DETAIL-07_01_2026-GO95HV-1^07217001.0169502 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010778 | 957523656-54179-DETAIL-10_08_2025-GO95HV-1^06148001.0206000 | OTHER | Non-HFTD | Distribution | 2025-10-08 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010779 | 957523656-54179-DETAIL-10_08_2025-GUYHINS-1^06148001.0206000 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-10-08 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010780 | 957788822-98689-DETAIL-07_22_2025-GO95HV-1^06247005.0177700 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010781 | 957891070-40370-DETAIL-01_21_2026-PWRTRN-1^06240004.0343902 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2027-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010782 | 958131930-74173-DETAIL-06_16_2025-GO95HV-1^06248005.0330241 | OTHER | Non-HFTD | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010783 | 958137579-61813-DETAIL-08_25_2025-GO95HV-1^06247006.0282800 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010784 | 958258430-75349-DTLSB-06_25_2025-GO95HV-1^06244007.0102501 | OTHER | HFTD Tier 2 | Distribution | 2025-06-25 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010785 | 958469969-65899-DETAIL-09_09_2025-GRDRODHI-1^06246007.0230950 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010786 | 958707315-25400-DETAIL-01_28_2026-GO95HV-1^06239002.0063505 | OTHER | Non-HFTD | Distribution | 2026-01-28 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010787 | 958732578-35379-DETAIL-09_25_2025-GO95HV-1^06246009.0097500 | OTHER | HFTD Tier 2 | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010788 | 958732578-35379-DETAIL-09_25_2025-GUYHINS-1^06246009.0097500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-25 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010789 | 958980875-8543-DTLSB-05_07_2024-GO95MLD-1^06245001.0291201 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010790 | 959261595-13491-ADMIN-05_15_2025-POLEDERP-1^668038/00 3/045 | POLE | HFTD Tier 2 | Transmission | 2025-05-15 | 2026-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010791 | 959261595-13491-DRONE_VS-11_13_2024-XARMSPCR-1^668038/00 3/045 | CROSSARM | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010792 | 959261595-13491-DTLTRT-05_12_2026-BIRDDMG-1^668038/00 3/045 | POLE | HFTD Tier 2 | Transmission | 2026-05-12 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010793 | 959300613-60613-DETAIL-04_09_2024-CONDFRAY-1^06147005.0254704 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010794 | 959308850-60438-DETAIL-08_04_2025-GO95HV-1^06247006.0202801 | OTHER | HFTD Tier 2 | Distribution | 2025-08-04 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010795 | 959330886-71053-DTLSB-06_10_2026-GUYLOINS-1^07217001.0353300 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-06-10 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010796 | 959366768-27069-DETAIL-09_17_2025-GO95HV-1^06248007.0363501 | OTHER | HFTD Tier 2 | Distribution | 2025-09-17 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010797 | 959399600-11649-DTLSB-04_11_2024-CUSTWIRE-1^06245007.0222200 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010798 | 959492521-25222-DTLTRT-04_23_2026-GO95HV-1^668004/00 4/002 | OTHER | HFTD Tier 2 | Transmission | 2026-04-23 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010799 | 959638567-16789-DETAIL-03_19_2026-SVCROAD-1^06242009.0067705 | OTHER | HFTD Tier 2 | Distribution | 2026-03-19 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010800 | 959853174-69739-DETAIL-05_29_2025-GO95HV-1^06244006.0159900 | OTHER | Non-HFTD | Distribution | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010801 | 960057455-49232-ADMIN-11_10_2025-GO95BLTC-1^06246011.0063000 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010802 | 960063709-25709-DETAIL-08_18_2025-GO95HV-1^06247006.0363102 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010803 | 960063709-25709-DETAIL-08_18_2025-RISEBKSP-1^06247006.0363102 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010804 | 960352281-81153-DETAIL-09_10_2025-GO95HV-1^06147001.0074103 | OTHER | Non-HFTD | Distribution | 2025-09-10 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010805 | 96146456-99849-DETAIL-02_27_2024-GO95HV-1^07113002.0073300 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010806 | 96146456-99849-DETAIL-02_27_2024-SVCRUBLG-1^07113002.0073300 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010807 | 961514284-85284-DTLTRT-08_07_2025-GUYNOINS-1^668087/00 13/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-08-07 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010808 | 961986933-99041-DETAIL-06_29_2026-GO95HV-1^07217001.0156502 | OTHER | Non-HFTD | Distribution | 2026-06-29 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010809 | 962105838-37753-DETAIL-02_20_2023-CUSTWIRE-1^06247002.0296600 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010810 | 962141173-18241-DETAIL-05_13_2025-GO95TCH-1^06242004.0311902 | OTHER | HFTD Tier 2 | Distribution | 2025-05-13 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010811 | 962498021-47939-AUDIT-05_27_2026-GUYHINS-2^668086/00 7/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010812 | 962498021-47939-AUDIT-05_27_2026-GUYHINS-3^668086/00 7/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-05-27 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010813 | 962498021-47939-DTLTRT-05_18_2026-GO95MLD-1^668086/00 7/009 | OTHER | Non-HFTD | Transmission | 2026-05-18 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010814 | 962573788-32259-DETAIL-09_02_2025-GO95HV-1^06247006.0277601 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010815 | 962573788-32259-DETAIL-09_02_2025-SVCENTCO-1^06247006.0277601 | OTHER | HFTD Tier 2 | Distribution | 2025-09-02 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010816 | 962772936-44653-DTLTRT-05_11_2026-GO95HV-1^668038/00 2/048 | OTHER | HFTD Tier 2 | Transmission | 2026-05-11 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010817 | 96279628-40070-DETAIL-03_23_2026-COVCOTHR-3^06240004.0229500 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010818 | 962864999-18653-DETAIL-09_30_2025-SVCROAD-1^06148001.0300110 | OTHER | Non-HFTD | Distribution | 2025-09-30 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010819 | 962942506-62553-DTLSB-06_16_2026-RISEGRD-1^07217001.0358201 | OTHER | Non-HFTD | Distribution | 2026-06-16 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010820 | 963004694-93753-DETAIL-09_11_2025-GO95HV-1^06248007.0231600 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010821 | 963147696-62369-DETAIL-04_24_2025-GO95HV-1^06242006.0198601 | OTHER | Non-HFTD | Distribution | 2025-04-24 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010822 | 963281853-45153-DTLSB-05_23_2024-GO95MLD-1^06243001.0121000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010823 | 963281853-45153-DTLSB-05_23_2024-GRDRODHI-1^06243001.0121000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010824 | 963388815-40479-DETAIL-09_10_2025-SVCDEFLC-1^06246006.0183206 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010825 | 963463614-36153-DETAIL-09_08_2025-GO95HV-1^06147001.0330401 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010826 | 963590512-86198-DETAIL-06_09_2026-GUYHINS-1^668086/00 15/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010827 | 963590512-86198-DETAIL-06_09_2026-GUYHINS-2^668086/00 15/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010828 | 963590512-86198-DETAIL-06_09_2026-GUYHINS-3^668086/00 15/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010829 | 963590512-86198-DETAIL-06_09_2026-GUYHINS-6^668086/00 15/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010830 | 963666109-10753-DETAIL-08_18_2025-GO95HV-1^06246002.0345800 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010831 | 963836432-41892-DETAIL-05_05_2025-GO95HV-1^06243006.0063740 | OTHER | HFTD Tier 2 | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010832 | 96392096-46419-DTLSB-07_08_2026-GO95HV-1^06242009.0246200 | OTHER | Non-HFTD | Distribution | 2026-07-08 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010833 | 963928581-61230-DTLSB-08_13_2025-GO95HV-1^07218001.0289700 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010834 | 963983350-49353-DETAIL-09_02_2025-GO95HV-1^06247006.0248001 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010835 | 964501776-60642-DETAIL-04_21_2025-GO95MLD-1^06242005.0367800 | OTHER | HFTD Tier 2 | Distribution | 2025-04-21 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010836 | 964564375-21263-DETAIL-08_20_2025-GO95HV-1^06246001.0175305 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010837 | 964564838-7170-AUDIT-02_18_2025-SVCDEFLC-1^06240004.0168504 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010838 | 964948501-98723-DETAIL-06_20_2023-CUSTWIRE-1^06244009.0356000 | OTHER | Non-HFTD | Distribution | 2023-06-20 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010839 | 965503954-66240-DTLTRT-05_30_2025-GO95HV-1^668075/00 19/010 | OTHER | Non-HFTD | Transmission | 2025-05-30 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010840 | 965503954-66240-DTLTRT-05_30_2025-GUYHINS-1^668075/00 19/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-05-30 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010841 | 965660099-6699-DETAIL-06_05_2025-GO95MLD-1^668075/00 5/026 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010842 | 965675548-48089-ADMIN-11_12_2025-GO95HV-1^06246001.0332501 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010843 | 96571803-94821-DRONE_HY-06_19_2026-COVCOTHR-1^06239004.0364800 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010844 | 965852995-78059-DETAIL-08_20_2025-GO95HV-1^06247006.0368101 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010845 | 966123566-42563-DTLSB-05_06_2026-GO95HV-1^06142013.0220200 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010846 | 966474503-18489-DETAIL-08_12_2025-GO95HV-1^06247006.0250402 | OTHER | Non-HFTD | Distribution | 2025-08-12 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010847 | 966614632-7419-DTLSB-04_08_2026-GO95HV-1^06241009.0109000 | OTHER | Non-HFTD | Distribution | 2026-04-08 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010848 | 966767183-83259-DETAIL-06_11_2025-GO95HV-1^06245007.0260100 | OTHER | HFTD Tier 2 | Distribution | 2025-06-11 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010849 | 966986688-37688-DETAIL-09_02_2025-GO95HV-1^06247006.0279300 | OTHER | Non-HFTD | Distribution | 2025-09-02 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010850 | 967026659-6259-DTLTRT-05_07_2026-GO95HV-1^668004/00 29/024 | OTHER | Non-HFTD | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010851 | 967430708-94359-DETAIL-05_31_2024-CUSTWIRE-1^06246005.0329401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010852 | 967593585-60140-DETAIL-03_04_2025-SVCROOF-1^06240004.0150603 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010853 | 967593585-60140-DETAIL-03_16_2026-SVCTREE-1^06240004.0150603 | OTHER | HFTD Tier 2 | Distribution | 2026-03-16 | 2027-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010854 | 967751656-28499-DETAIL-05_28_2025-GO95HV-1^06244006.0058000 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010855 | 96782916-77459-DETAIL-02_18_2026-GO95HV-1^06239002.0043300 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010856 | 967932234-61479-DETAIL-08_21_2024-CUSTWIRE-1^06246005.0269741 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010857 | 967954357-46229-DETAIL-04_27_2026-SVCROAD-1^06142012.0144501 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010858 | 968402553-78880-DETAIL-02_18_2026-GO95HV-1^06239002.0167601 | OTHER | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010859 | 968551603-11703-DTLSB-04_08_2026-SVCENTCO-1^06241009.0159901 | OTHER | Non-HFTD | Distribution | 2026-04-08 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010860 | 968933483-11503-DETAIL-06_04_2025-GUYHINS-1^668075/00 15/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010861 | 968933483-11503-DETAIL-06_04_2025-GUYHINS-3^668075/00 15/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010862 | 969087471-12901-DETAIL-01_14_2025-GO95MLD-1^06239004.0257441 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010863 | 969642763-95180-DETAIL-03_31_2026-COVCOTHR-1^06240004.0357100 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010864 | 969700958-38229-DETAIL-04_27_2026-SVCROAD-1^06142012.0145501 | OTHER | Non-HFTD | Distribution | 2026-04-27 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010865 | 969729471-37820-DETAIL-03_30_2026-GO95MLD-1^06240004.0272401 | OTHER | HFTD Tier 2 | Distribution | 2026-03-30 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010866 | 970363130-92170-DETAIL-02_19_2026-GO95HV-1^06239002.0012600 | OTHER | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010867 | 970514303-16073-ADMIN-11_14_2025-SVCNEUT-1^06246001.0325504 | OTHER | Non-HFTD | Distribution | 2025-11-14 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010868 | 970544604-20689-DETAIL-08_14_2025-GO95HV-1^06247006.0363701 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010869 | 970602714-15690-DETAIL-03_31_2025-GO95HV-1^06239003.0016811 | OTHER | Non-HFTD | Distribution | 2025-03-31 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010870 | 970987319-29170-DETAIL-02_18_2025-SVCDEFLC-1^06240004.0220702 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010871 | 971043893-84083-DETAIL-09_22_2025-POLISSUE-1^06147001.0238601 | POLE | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010872 | 971043893-84083-DETAIL-09_22_2025-XARMSPCR-1^06147001.0238601 | CROSSARM | Non-HFTD | Distribution | 2025-09-22 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010873 | 971096849-91739-DTLTRT-06_24_2025-GO95MLD-1^668087/00 4/005 | OTHER | Non-HFTD | Transmission | 2025-06-24 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010874 | 971274073-99680-DETAIL-03_31_2026-COVCOTHR-1^06240004.0355400 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010875 | 971274073-99680-DETAIL-03_31_2026-GRDRODHI-1^06240004.0355400 | OTHER | HFTD Tier 2 | Distribution | 2026-03-31 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010876 | 971919470-19570-DETAIL-02_12_2025-GO95BLTC-1^06240004.0166001 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010877 | 972454019-46199-DETAIL-07_28_2025-GO95HV-1^06247005.0196101 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010878 | 972553088-83088-DETAIL-06_18_2025-COVCOTHR-1^668075/00 18/048 | CONDUCTOR | HFTD Tier 2 | Transmission | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010879 | 972619853-81490-DETAIL-04_09_2026-BIRDDMG-1^06240001.0345003 | POLE | HFTD Tier 2 | Distribution | 2026-04-09 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010880 | 972619853-81490-DETAIL-04_09_2026-GO95HV-1^06240001.0345003 | OTHER | HFTD Tier 2 | Distribution | 2026-04-09 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010881 | 97295143-47880-DETAIL-02_17_2026-GO95HV-1^06239002.0180501 | OTHER | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-02-28 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010882 | 97302116-44499-DETAIL-05_22_2025-GO95HV-1^06244006.0054900 | OTHER | HFTD Tier 2 | Distribution | 2025-05-22 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010883 | 973216199-14099-DETAIL-06_05_2025-GO95MLD-1^668075/00 17/025 | OTHER | Non-HFTD | Transmission | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010884 | 973293245-4245-DETAIL-07_06_2026-GO95HV-1^07217001.0118800 | OTHER | Non-HFTD | Distribution | 2026-07-06 | 2031-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010885 | 973429529-90869-ADMIN-07_08_2026-POLEDERP-1^668005/03 5/005 | POLE | Non-HFTD | Transmission | 2026-07-08 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010886 | 973431159-54152-DTLSB-07_15_2025-GO95HV-1^06244006.0313240 | OTHER | HFTD Tier 2 | Distribution | 2025-07-15 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010887 | 973628628-4789-AUDIT-09_15_2025-GRDRODHI-1^06246001.0204300 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010888 | 973674471-86471-DETAIL-01_21_2026-GO95MLD-1^06239004.0014002 | OTHER | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010889 | 973988830-93201-DETAIL-01_15_2026-GO95CL10-1^06239004.0136108 | OTHER | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010890 | 974021344-84253-DETAIL-09_23_2025-GO95HV-1^07218001.0219900 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010891 | 974136241-56241-DETAIL-01_30_2025-SVCDEFLC-1^06240004.0162604 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010892 | 974294626-74310-DETAIL-02_26_2026-COVCOTHR-1^06238004.0118500 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010893 | 974294626-74310-DETAIL-02_26_2026-COVCOTHR-2^06238004.0118500 | CONDUCTOR | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010894 | 974586334-37334-DETAIL-07_22_2025-GO95HV-1^06247005.0090101 | OTHER | Non-HFTD | Distribution | 2025-07-22 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010895 | 974624734-44440-DTLSB-07_30_2025-GO95TCH-1^07218001.0273301 | OTHER | Non-HFTD | Distribution | 2025-07-30 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010896 | 97481914-35583-DETAIL-09_11_2025-GO95HV-1^06248007.0228800 | OTHER | Non-HFTD | Distribution | 2025-09-11 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010897 | 974991148-9283-DTLSB-05_05_2026-GUYHINS-1^06142013.0152500 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010898 | 975139720-67540-DETAIL-01_20_2026-COVCOTHR-1^06239003.0070700 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-01-20 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010899 | 97515440-74139-DTLTRT-07_10_2025-TRNSLOOS-1^668087/00 5/024 | CONNECTION DEVICE | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010900 | 975517449-5679-DETAIL-09_22_2025-GO95HV-1^06248007.0132000 | OTHER | Non-HFTD | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010901 | 9757039-69553-DTLSB-04_29_2024-GO95MLD-1^06245007.0226446 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010902 | 9757039-69553-DTLSB-04_29_2024-GO95TCH-1^06245007.0226446 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010903 | 976066361-76819-DTLSB-03_18_2026-GO95HV-1^06242009.0220501 | OTHER | Non-HFTD | Distribution | 2026-03-18 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010904 | 976248442-68983-DETAIL-08_21_2025-GO95HV-1^07216001.0175201 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010905 | 976355320-9559-DETAIL-06_18_2025-SVCENTCO-1^06248004.0341800 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010906 | 976772619-25899-DETAIL-09_09_2025-GO95HV-1^06246007.0145150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010907 | 976772619-25899-DETAIL-09_09_2025-SVCDEFLC-1^06246007.0145150 | OTHER | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010908 | 976973730-4299-DETAIL-08_05_2025-GO95MLD-1^06247005.0205301 | OTHER | Non-HFTD | Distribution | 2025-08-05 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010909 | 977000995-77893-ADMIN-05_13_2024-ABNDEQPM-1^06244001.0207300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010910 | 977066209-909-DETAIL-06_04_2025-GO95HV-1^668075/00 1/025 | OTHER | Non-HFTD | Transmission | 2025-06-04 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010911 | 977380506-51179-DETAIL-08_04_2025-GO95TCH-1^06246001.0182001 | OTHER | Non-HFTD | Distribution | 2025-08-04 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010912 | 977484603-97799-DETAIL-08_14_2025-GO95HV-1^06247006.0256004 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010913 | 977484603-97799-DETAIL-08_14_2025-GRDRODHI-2^06247006.0256004 | OTHER | Non-HFTD | Distribution | 2025-08-14 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010914 | 977769739-40779-DETAIL-10_02_2025-GO95HV-1^06148001.0284501 | OTHER | Non-HFTD | Distribution | 2025-10-02 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010915 | 977966302-58989-DETAIL-08_25_2025-GO95HV-1^06247006.0210200 | OTHER | HFTD Tier 2 | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010916 | 978123403-56330-DTLSB-07_23_2025-GO95HV-1^07218001.0263907 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010917 | 978188451-38919-DRONE_HY-07_15_2026-UBPRMSHD-1^668036/00 21/053 | CONNECTION DEVICE | Non-HFTD | Transmission | 2026-07-15 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010918 | 978218786-45799-DETAIL-05_28_2025-GO95BLTC-1^06244006.0040102 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010919 | 978218786-45799-DETAIL-05_28_2025-GO95HV-1^06244006.0040102 | OTHER | Non-HFTD | Distribution | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010920 | 978315386-78829-DETAIL-04_23_2026-SVCENTCO-1^06142012.0146807 | OTHER | Non-HFTD | Distribution | 2026-04-23 | 2029-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010921 | 97834523-94523-DETAIL-06_04_2025-GUYHINS-2^668075/00 10/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010922 | 97834523-94523-DETAIL-06_04_2025-GUYHINS-3^668075/00 10/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010923 | 97836275-43530-DETAIL-09_03_2025-SVCENTCO-1^06246001.0174201 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010924 | 978374764-62453-DETAIL-09_23_2025-GO95HV-1^07218001.0224400 | OTHER | Non-HFTD | Distribution | 2025-09-23 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010925 | 978439508-8179-DETAIL-06_19_2025-GO95HV-1^06248004.0297101 | OTHER | HFTD Tier 2 | Distribution | 2025-06-19 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010926 | 978597606-9210-DETAIL-03_13_2025-GO95HV-1^06238004.0224900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010927 | 978600695-58979-DETAIL-07_23_2025-GO95HV-1^06247005.0121500 | OTHER | Non-HFTD | Distribution | 2025-07-23 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010928 | 978997342-88489-DETAIL-05_20_2025-GO95HV-1^06243006.0077000 | OTHER | HFTD Tier 2 | Distribution | 2025-05-20 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010929 | 979297576-26299-ADMIN-11_10_2025-GO95BLTC-1^06246011.0063200 | OTHER | HFTD Tier 2 | Distribution | 2025-11-10 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010930 | 97959611-19530-DETAIL-05_14_2025-GO95HV-1^06142012.0119802 | OTHER | Non-HFTD | Distribution | 2025-05-14 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010931 | 979877113-39629-DTLSB-01_20_2026-GO95BLTC-1^06242009.0299204 | OTHER | Non-HFTD | Distribution | 2026-01-20 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010932 | 979906526-60089-DETAIL-08_01_2024-INSULDMG-1^06245006.0111800 | INSULATOR AND BUSHING | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010933 | 980357073-41503-DETAIL-09_05_2025-GO95HV-1^06147001.0202801 | OTHER | Non-HFTD | Distribution | 2025-09-05 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010934 | 980371878-42952-DTLSB-07_02_2025-GO95HV-1^06244006.0220101 | OTHER | Non-HFTD | Distribution | 2025-07-02 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010935 | 980667696-6889-ADMIN-05_02_2025-POLEREPL-1^06247005.0331600 | POLE | Non-HFTD | Distribution | 2025-05-02 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010936 | 981417116-1779-ADMIN-10_22_2025-GO95BLTC-1^06247011.0327001 | OTHER | HFTD Tier 2 | Distribution | 2025-10-22 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010937 | 981634581-39803-DTLTRT-06_26_2025-GUYHINS-1^668087/00 1/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-06-26 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010938 | 981648682-30539-DETAIL-05_15_2025-GO95HV-1^06243006.0162502 | OTHER | Non-HFTD | Distribution | 2025-05-15 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010939 | 981740554-13554-DTLTRT-07_08_2025-BIRDDMG-1^668087/00 6/027 | POLE | Non-HFTD | Transmission | 2025-07-08 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010940 | 981978996-8949-DTLSB-07_08_2025-GO95HV-1^06244007.0035804 | OTHER | HFTD Tier 2 | Distribution | 2025-07-08 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010941 | 982027745-40319-ADMIN-08_05_2024-GO95STUB-1^06247008.0191100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-05 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010942 | 982036345-66659-DTLSB-08_18_2025-GO95MLD-1^07218001.0354041 | OTHER | Non-HFTD | Distribution | 2025-08-18 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010943 | 982041249-32399-DETAIL-09_09_2025-GUYLOINS-1^06246007.0141250 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-09-09 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010944 | 982111822-29459-DTLTRT-04_29_2026-GO95HV-1^668004/00 3/013 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010945 | 982192399-50083-DETAIL-08_21_2025-GO95MLD-1^07216001.0177802 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010946 | 982299410-18220-DETAIL-06_10_2026-GO95HV-1^07217001.0352400 | OTHER | Non-HFTD | Distribution | 2026-06-10 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010947 | 982500543-7879-DETAIL-08_20_2025-GO95HV-1^06247006.0255701 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010948 | 982683274-31603-DETAIL-09_08_2025-GO95HV-1^06147001.0319401 | OTHER | Non-HFTD | Distribution | 2025-09-08 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010949 | 982710237-69689-DETAIL-10_26_2021-CUSTWIRE-1^06148005.0240101 | OTHER | Non-HFTD | Distribution | 2021-10-26 | 2024-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010950 | 982911176-18803-DTLTRT-05_07_2026-GO95HV-1^668038/00 4/055 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010951 | 982911176-36391-DTLTRT-05_07_2026-GO95HV-1^668038/00 4/055 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010952 | 982911176-7391-DTLTRT-05_07_2026-GO95HV-1^668038/00 4/055 | OTHER | HFTD Tier 2 | Transmission | 2026-05-07 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010953 | 983147927-8927-ADMIN-10_28_2025-GO95HV-1^06246001.0119301 | OTHER | Non-HFTD | Distribution | 2025-10-28 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010954 | 983290621-64013-DETAIL-05_27_2025-SVCROAD-1^06142012.0110000 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010955 | 98362286-32669-DETAIL-08_06_2024-CUSTWIRE-1^06245006.0155000 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010956 | 98384426-99559-DETAIL-04_29_2026-GO95HV-1^668004/00 1/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010957 | 98384426-99560-DETAIL-04_29_2026-GO95HV-1^668004/00 1/015 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010958 | 983880141-60859-DTLSB-07_28_2025-GO95HV-1^07218001.0267600 | OTHER | Non-HFTD | Distribution | 2025-07-28 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010959 | 984063253-23813-DTLTRT-10_16_2025-GO95HV-1^06247001.0350400 | OTHER | Non-HFTD | Distribution | 2025-10-16 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010960 | 984066752-91070-DETAIL-03_10_2026-GO95HV-1^06238004.0123802 | OTHER | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010961 | 98410028-17289-DETAIL-10_07_2025-GO95HV-1^06148001.0262200 | OTHER | Non-HFTD | Distribution | 2025-10-07 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010962 | 984218582-1213-DETAIL-03_14_2024-GO95HV-1^06147004.0325601 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010963 | 984311598-82370-DETAIL-11_18_2024-BIRDDMG-1^668014/00 4/059 | POLE | HFTD Tier 2 | Transmission | 2024-11-18 | 2027-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010964 | 984460209-20269-DTLSB-02_04_2026-BIRDDMG-1^06243009.0321201 | POLE | HFTD Tier 2 | Distribution | 2026-02-04 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010965 | 984711461-24543-DETAIL-07_01_2026-SVCROAD-1^07217001.0167502 | OTHER | Non-HFTD | Distribution | 2026-07-01 | 2029-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010966 | 984994963-45113-DRONE_HY-07_10_2026-DISTHDWR-1^06143014.0184300 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2026-07-10 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010967 | 985139390-70213-DTLSB-05_06_2026-GO95HV-1^06142013.0287501 | OTHER | Non-HFTD | Distribution | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010968 | 985348972-11859-DETAIL-08_20_2025-GUYHINS-1^07216001.0176004 | ANCHOR/GUY | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010969 | 985510041-30059-DETAIL-09_22_2025-GO95HV-1^06247006.0064100 | OTHER | HFTD Tier 2 | Distribution | 2025-09-22 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010970 | 98551360-54139-DTLTRT-07_10_2025-GUYLOINS-2^668087/00 6/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-07-10 | 2028-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010971 | 986212448-66513-DETAIL-06_23_2025-GO95HV-1^668087/00 17/002 | OTHER | Non-HFTD | Transmission | 2025-06-23 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010972 | 98636070-42879-DETAIL-08_07_2025-CUTOUTAR-1^06246001.0303901 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2025-08-07 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010973 | 987915050-62259-DETAIL-08_25_2025-GO95HV-1^07216001.0179605 | OTHER | Non-HFTD | Distribution | 2025-08-25 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010974 | 98815029-47129-DETAIL-07_01_2025-GO95HV-1^668087/00 12/015 | OTHER | Non-HFTD | Transmission | 2025-07-01 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010975 | 988215071-36891-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010976 | 988215071-5891-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010977 | 988381212-58699-DETAIL-05_21_2025-GO95MLD-1^06243006.0224101 | OTHER | Non-HFTD | Distribution | 2025-05-21 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010978 | 988406265-11532-DETAIL-07_12_2023-CUSTWIRE-1^06244008.0334102 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010979 | 988779181-59230-DETAIL-03_26_2026-COVCOTHR-1^06240004.0204403 | CONDUCTOR | HFTD Tier 3 | Distribution | 2026-03-26 | 2029-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010980 | 988857569-59569-ADMIN-03_06_2023-CUSTWIRE-1^06148004.0192000 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010981 | 989101651-4050-DETAIL-03_04_2026-GO95HV-1^06239003.0180800 | OTHER | HFTD Tier 3 | Distribution | 2026-03-04 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010982 | 989382582-56659-DETAIL-06_18_2025-ABNDEQPM-1^06248004.0310501 | OTHER | HFTD Tier 2 | Distribution | 2025-06-18 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010983 | 989513818-99633-DETAIL-05_06_2026-GO95HV-1^668038/00 6/057 | OTHER | HFTD Tier 2 | Transmission | 2026-05-06 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010984 | 989530293-45252-DETAIL-06_21_2023-CUSTWIRE-1^06244009.0309600 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2026-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010985 | 989920461-34189-DETAIL-09_10_2025-SVCDEFLC-1^06246006.0183204 | OTHER | HFTD Tier 2 | Distribution | 2025-09-10 | 2028-09-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010986 | 990481903-32903-DETAIL-05_05_2025-GO95BLTC-1^06243006.0348101 | OTHER | Non-HFTD | Distribution | 2025-05-05 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010987 | 990636265-95739-DETAIL-05_08_2025-GO95HV-1^06243006.0105601 | OTHER | Non-HFTD | Distribution | 2025-05-08 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010988 | 990878454-67479-DETAIL-09_15_2025-GO95HV-1^06248007.0234500 | OTHER | Non-HFTD | Distribution | 2025-09-15 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010989 | 990925015-29649-DTLTRT-06_09_2026-SVCROAD-1^07216001.0225005 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2029-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010990 | 991435995-48133-DTLSB-06_09_2026-GO95HV-1^07216001.0225101 | OTHER | Non-HFTD | Distribution | 2026-06-09 | 2031-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010991 | 992243315-29691-DETAIL-05_12_2026-GO95HV-1^668038/00 5/045 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010992 | 992243315-53943-DETAIL-05_12_2026-GO95HV-1^668038/00 5/045 | OTHER | HFTD Tier 2 | Transmission | 2026-05-12 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010993 | 992339005-88302-DETAIL-04_29_2025-GUYHINS-1^06242005.0329300 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-29 | 2028-04-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010994 | 992741450-15343-DETAIL-10_06_2025-CLRTOPOL-1^06148001.0310806 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2028-10-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010995 | 992741450-15343-DETAIL-10_06_2025-GO95HV-1^06148001.0310806 | OTHER | Non-HFTD | Distribution | 2025-10-06 | 2030-10-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010996 | 993123908-93843-DTLSB-05_05_2026-GUYHINS-1^06142013.0222700 | ANCHOR/GUY | Non-HFTD | Distribution | 2026-05-05 | 2029-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120010997 | 993205008-77043-DTLSB-05_05_2026-GO95HV-1^06142013.0220602 | OTHER | Non-HFTD | Distribution | 2026-05-05 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010998 | 993276706-49309-DETAIL-08_13_2025-GO95HV-1^06247006.0265400 | OTHER | Non-HFTD | Distribution | 2025-08-13 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120010999 | 99338701-69701-DETAIL-09_25_2025-GO95HV-1^07218001.0214700 | OTHER | Non-HFTD | Distribution | 2025-09-25 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011000 | 993502053-43343-ADMIN-11_12_2025-GO95HV-1^06246001.0320400 | OTHER | Non-HFTD | Distribution | 2025-11-12 | 2030-11-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011001 | 993822892-56459-DTLTRT-04_29_2026-GO95HV-1^668004/00 6/012 | OTHER | Non-HFTD | Transmission | 2026-04-29 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011002 | 994299440-91350-DETAIL-03_05_2026-GO95HV-1^06238004.0011705 | OTHER | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-03-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011003 | 994481180-5822-DTLTRT-04_27_2026-GO95HV-1^668004/00 5/005 | OTHER | HFTD Tier 2 | Transmission | 2026-04-27 | 2031-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011004 | 994615018-37890-DETAIL-01_28_2025-GO95HV-1^06239004.0246141 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011005 | 994796778-48143-DETAIL-08_21_2025-GO95TCH-1^06246001.0207500 | OTHER | Non-HFTD | Distribution | 2025-08-21 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011006 | 994857618-81390-DETAIL-01_13_2026-GUYHINS-1^06239004.0246100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011007 | 994857618-81390-DETAIL-01_13_2026-GUYHINS-3^06239004.0246100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011008 | 994857618-81390-DETAIL-01_13_2026-GUYHINS-4^06239004.0246100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2026-01-13 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011009 | 994945065-87059-DETAIL-08_20_2025-BIRDDMG-1^06247006.0368100 | POLE | Non-HFTD | Distribution | 2025-08-20 | 2028-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011010 | 994945065-87059-DETAIL-08_20_2025-GO95HV-1^06247006.0368100 | OTHER | Non-HFTD | Distribution | 2025-08-20 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011011 | 995248013-40643-DTLSB-05_22_2024-GO95MLD-1^06243001.0048700 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011012 | 99554896-7383-DETAIL-06_04_2025-GO95TCH-1^06245006.0288940 | OTHER | Non-HFTD | Distribution | 2025-06-04 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011013 | 995585843-28843-DTLTRT-05_13_2026-GO95HV-1^668085/00 8/002 | OTHER | Non-HFTD | Transmission | 2026-05-13 | 2031-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011014 | 995611070-2070-DRONE_HY-06_19_2026-SVCTREE-1^06238004.0271800 | OTHER | HFTD Tier 2 | Distribution | 2026-06-19 | 2027-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011015 | 99566121-47930-DTLTRT-05_28_2025-GO95HV-1^668075/00 11/006 | OTHER | Non-HFTD | Transmission | 2025-05-28 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011016 | 995765099-17190-DETAIL-01_12_2026-GO95CL10-1^06239004.0245440 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-01-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011017 | 995765099-17190-DETAIL-01_12_2026-GO95TCH-1^06239004.0245440 | OTHER | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-01-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011018 | 995948774-43299-DETAIL-06_16_2025-GO95CL10-1^06248004.0310900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011019 | 995948774-43299-DETAIL-06_16_2025-GO95HV-1^06248004.0310900 | OTHER | HFTD Tier 2 | Distribution | 2025-06-16 | 2030-06-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011020 | 996834306-96799-DETAIL-05_27_2025-GO95HV-1^06244006.0040400 | OTHER | Non-HFTD | Distribution | 2025-05-27 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011021 | 996886353-50739-DTLSB-08_11_2025-GO95HV-1^07217001.0012301 | OTHER | Non-HFTD | Distribution | 2025-08-11 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011022 | 996932585-93585-DETAIL-06_05_2025-GRDRODHI-1^06148014.0241400 | OTHER | Non-HFTD | Distribution | 2025-06-05 | 2028-06-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011023 | 997090030-97709-DTLSB-07_23_2024-CUSTWIRE-2^06245007.0108100 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011024 | 997554993-84249-DTLSB-07_17_2025-GO95HV-1^06244006.0255900 | OTHER | Non-HFTD | Distribution | 2025-07-17 | 2030-07-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011025 | 997680079-55699-DETAIL-08_15_2024-CUSTWIRE-1^06246005.0135900 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011026 | 997751339-61259-DETAIL-08_26_2025-GO95HV-1^06247006.0330500 | OTHER | HFTD Tier 2 | Distribution | 2025-08-26 | 2030-08-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011027 | 997864946-66562-DETAIL-04_16_2025-GO95HV-1^06242005.0368505 | OTHER | HFTD Tier 2 | Distribution | 2025-04-16 | 2030-04-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011028 | 998110290-33759-DETAIL-09_04_2025-GO95MLD-1^07216001.0098200 | OTHER | Non-HFTD | Distribution | 2025-09-04 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011029 | 99837103-2669-DETAIL-02_20_2026-XARMSPCR-1^668041/00 1/026 | CROSSARM | Non-HFTD | Transmission | 2026-02-20 | 2029-02-28 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011030 | 998417919-91063-ADMIN-11_07_2025-GRDRODHI-1^06246001.0294503 | OTHER | Non-HFTD | Distribution | 2025-11-07 | 2028-11-30 | Level 2 | B | [7 empty] | PC | 2026 | 2
1120011031 | 998947146-57763-DETAIL-09_03_2025-GO95HV-1^06246001.0177301 | OTHER | Non-HFTD | Distribution | 2025-09-03 | 2030-09-30 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011032 | 9995233-56940-DTLTRT-05_29_2025-GO95HV-1^668075/00 11/009 | OTHER | Non-HFTD | Transmission | 2025-05-29 | 2030-05-31 | Level 3 | C | [7 empty] | PC | 2026 | 2
1120011033 | 9995233-56940-DTLTRT-05_29_2025-GUYHINS-1^668075/00 11/009 | ANCHOR/GUY | Non-HFTD | Transmission | 2025-05-29 | 2028-05-31 | Level 2 | B | [7 empty] | PC | 2026 | 2