## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID (UMAT) | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | REPORTING YEAR | REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | LSP | 2026-11-02 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment |  | GD-01 | Pilot | Investigate advanced protection system enhancements for potential inclusion in project design | Evaluate protection system technologies to enhance grid resilience and identify opportunities for design improvements. | 8.2.8 | Equipment ignition likelihood | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Review and investigation initiated in Q2 2026 | In Progress
1010000001 | LSP | 2026-11-02 | Grid Design, Operations, and Maintenance | Asset Inspections | Substation Inspection Program |  | GD-02 | Program | Monthly Substation Inspections | Ensure ongoing reliability and safety through routine visual and technical inspections of substation equipment. | 8.3 | Equipment ignition likelihood | Quantitative | # of inspections | No |  | Not Applicable | 2026 | 3 | 12 |  | In Progress
1010000002 | LSP | 2026-11-02 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair | Transformer Dissolved Gas Analysis |  | GD-03 | Program | Dissolved Gas Analysis Test at energized transformers | Detect internal transformer issues early to prevent failures by analyzing dissolved gases in transformer | 8.4 | Equipment ignition likelihood | Quantitative | # of inspections | No |  | Not Applicable | 2026 | 3 | 1 |  | In Progress
1010000003 | LSP | 2026-11-02 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) | Maximo Asset and Maintenance Management |  | GD-04 | Program | Use Maximo to manage assets, inspections, and maintenance | Optimize asset performance and lifecycle management through consistent use of Maximo for tracking and inspections. | 8.6 | Equipment ignition likelihood | Qualitative |  | No | Maximo improves consistency and oversight, enabling timely actions that support wildfire risk reduction indirectly. | Not Applicable | 2026 | 3 |  | System configuration in progress. | In Progress
1010000004 | LSP | 2026-11-02 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Grid Response Procedures and Notifications |  | GD-05 | Program | Review Emergency Operations Plan and update annually | Keep emergency response strategies up to date and compliant by conducting annual reviews and updates to the plan. | 8.7 | Wildfire vulnerability | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Emergency Operations Plan reviewed and updated in August 2026. | In Progress
1010000005 | LSP | 2026-11-02 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) | HFTD Safety Training Program |  | GD-06 | Program | Create and rollout HFTD safety training | Promote safety awareness and preparedness by delivering targeted training to staff in high fire threat areas. | 8.8 | Wildfire exposure potential | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | HFTD safety training created and rolled out to Field Operations personnel accessing Fern Road Substation (Tier 2 HFTD). | Completed
1010000006 | LSP | 2026-11-02 | Vegetation Management and Inspections | Integrated Vegetation Management | Future Transmission Line Vegetation Standards Implementation |  | VM-01 | Program | Application of current Vegetation Management standards to future Transmission Line assets | Ensure consistent application of current VM standards in future projects to reduce wildfire ignition risk. | 9.7 | Contact from vegetation ignition likelihood | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Gap analysis initiated in Q3 2026. | In Progress
1010000007 | LSP | 2026-11-02 | Vegetation Management and Inspections | Wood and Slash Management | Future Transmission Line Wood and Slash Standards Implementation |  | VM-02 | Program | Applications of current Wood and Slash Management standards to future Transmission Line assets | Apply latest wood and slash handling methods to new projects to improve fire safety and regulatory compliance. | 9.5 | Wildfire spread | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Gap analysis initiated in Q3 2026. | In Progress
1010000008 | LSP | 2026-11-02 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) | Transmission Line Construction Fire Safety Planning |  | VM-03 | Program | Development of construction fire safety plan for Transmission Line vegetation activities | Create and implement fire safety protocols during transmission line vegetation work to reduce fire risk from construction activities. | 9.13 | Wildfire hazard | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Construction fire prevention plan development in progress for LSPGC development projects. | In Progress
1010000009 | LSP | 2026-11-02 | Vegetation Management and Inspections | Defensible Space | Defensible Space Management |  | VM-04 | Program | Defensible Space | To ensure defensible space inspections are according to procedure and to remedy any non-conformance. | 9.6 | Wildfire vulnerability | Quantitative | # of inspections | No |  | Not Applicable | 2026 | 3 | 10 |  | In Progress
1010000010 | LSP | 2026-11-02 | Vegetation Management and Inspections | Vegetation Management Inspections | Annual MVCD Transmission Inspections |  | VM-05 | Program | Transmission Annual MVCD System Inspections | To prevent vegetation-related threats to transmission systems. | 9.2 | Contact from vegetation ignition likelihood | Quantitative | % Inspection completed and logged | No | LSPGC will not have T lines until Q2 2028. | Not Applicable | 2026 | 3 | 0 |  | Planned
1010000011 | LSP | 2026-11-02 | Vegetation Management and Inspections | Vegetation Management Inspections | Detailed Ground Vegetation Evaluations |  | VM-06 | Program | Transmission Detailed Ground Vegetation Evaluations | Evaluate ground-level vegetation for compliance and fire risk to inform mitigation and maintenance. | 9.2 | Contact from vegetation ignition likelihood | Quantitative | % Evaluation documented and reviewed | No | LSPGC will not have T lines until Q2 2028. | Not Applicable | 2026 | 3 | 0 |  | Planned
1010000012 | LSP | 2026-11-02 | Vegetation Management and Inspections | Pole Clearing | Pole Clearing Initiative |  | VM-07 | Program | Pole clearing | Remove flammable vegetation near poles to maintain code compliance and reduce wildfire exposure. | 9.4 | Wildfire exposure potential | Quantitative | % of structures inspected | No | LSPGC will not have T lines & Poles until Q2 2028. | Not Applicable | 2026 | 3 | 0 |  | Planned
1010000013 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Grid Monitoring Systems | Substation Perimeter Camera Installation | 1 | SAF-01 | Program | Install perimeter cameras at substations | Enhance physical security by installing cameras that enable remote monitoring and deter unauthorized access. | 10.3 | Equipment ignition likelihood | Quantitative | # of cameras | No | Perimeter cameras installed at Fern Road Substation. Additional cameras planned at future construction sites; final quantities TBD pending site design completion. Fern camera feeds are integrated into the operations center per SAF-01 qualitative target. | Not Applicable | 2026 | 3 | 28 |  | In Progress
1010000014 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Grid Monitoring Systems | Substation Perimeter Camera Installation | 2 | SAF-01 | Program | Install perimeter cameras at substations | Integrate camera feeds from energized sites as a standard feed into the operations center. | 10.3 | Equipment ignition likelihood | Qualitative |  | No | Qualitative target for camera feed integration into operations center. | Not Applicable | 2026 | 3 |  | Fern Road camera feed integrated into the command operations center. | In Progress
1010000015 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Ignition Detection Systems | Integrated Fire Detection System Installation | 1 | SAF-02 | Project | Install integrated fire-detection systems in STATCOM buildings | Deploy fire-detection systems in STATCOM buildings to support early ignition detection and rapid response. | 10.4 | Equipment ignition likelihood | Quantitative | # of detection systems | No | Fire-detection systems installed in Fern Road Substation buildings. | Not Applicable | 2026 | 3 | 4 |  | In Progress
1010000016 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Ignition Detection Systems | Ignition Sensor Feasibility Study | 2 | SAF-02 | Project | Complete ignition sensor feasibility study at HFTD energized assets | Assess the feasibility of ignition sensors to improve early detection and response to wildfire conditions. | 10.4 | Equipment ignition likelihood | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Ignition sensor feasibility study initiated in Q3 2026. | In Progress
1010000017 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Weather Station Deployment Program | 1 | SAF-03 | Program | Install weather stations at planned project sites | Deploy weather stations to support site-specific fire risk modeling and operational readiness. | 10.2 | Wildfire hazard | Quantitative | # of weather stations | No | 1 weather station installed at Fern Road Substation in Q1 2026. Additional weather stations planned for installation near project completion at future sites (2027-2028). | Not Applicable | 2026 | 3 | 1 |  | In Progress
1010000018 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Weather Station Deployment Program | 2 | SAF-03 | Program | Integrate weather station feed from energized site as a standard feed into the operations center | Integrate weather station data feeds into centralized operations for real-time situational awareness. | 10.2 | Wildfire hazard | Qualitative |  | No | Qualitative target for weather station feed integration. | Not Applicable | 2026 | 3 |  | Orchard and Fern Road weather station feeds active in the operations center. | In Progress
1010000019 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Weather Forecasting | Semi-Annual Weather Station Calibration | 1 | SAF-04 | Program | Calibrate weather stations semi-annually | Maintain weather data accuracy by calibrating all stations to ensure reliable readings. | 10.5 | Wildfire hazard | Quantitative | # of weather stations | No | The manufacturer specifies no user-performed field calibration for the installed weather stations; calibration is a factory service only. | Not Applicable | 2026 | 3 | 0 |  | In Progress
1010000020 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Weather Forecasting | Semi-Annual Weather Station Calibration | 2 | SAF-04 | Program | Follow manufacturer calibration procedures and document compliance | Ensure weather data accuracy by following manufacturer calibration procedures and documenting compliance. | 10.5 | Wildfire hazard | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | The manufacturer's user manual for the installed weather stations specifies no user-performed or periodic field calibration; calibration is performed only as a factory service, and routine maintenance consists of sensor inspection and cleaning. | In Progress
1010000021 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Weather Forecasting | Weather Forecasting Capability Enhancement | 1 | SAF-05 | Program | Expand weather forecasting capability at planned project sites. | Expand predictive capability by integrating localized forecasting tools into wildfire mitigation strategies. | 10.5 | Wildfire hazard | Quantitative | # of weather stations | No | This is planned to be initiated and completed in 2028. | Not Applicable | 2026 | 3 | 0 |  | Planned
1010000022 | LSP | 2026-11-02 | Situational Awareness and Forecasting | Weather Forecasting | Weather Forecasting Capability Enhancement | 2 | SAF-05 | Program | Integrate weather-forecasting support tool into operations | Integrate localized weather forecasting tools into operations to enhance wildfire risk awareness and operational readiness. | 10.5 | Wildfire hazard | Qualitative |  | No | DTN weather forecasting service established at Fern Road Substation. NWS monitoring at other construction sites; DTN integration planned as sites progress. | Not Applicable | 2026 | 3 |  | DTN weather forecasting service established at Fern Road Substation. NWS monitoring in place at other construction sites; DTN integration planned as sites progress toward energization. | In Progress
1010000023 | LSP | 2026-11-02 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan | Fern Road System Restoration Plan Update |  | EP-01 | Program | Update System Restoration Plan to include Fern Road Substation | Incorporate Fern Road Substation into system restoration planning to strengthen emergency recovery efforts. | 11.2 | Wildfire vulnerability | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | System Restoration Plan updated to include both Orchard and Fern Road Substations. | Completed
1010000024 | LSP | 2026-11-02 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness | Wildfire Communication Protocol Development |  | EP-02 | Program | Establish wildfire-specific communication protocols | Develop communication standards to coordinate wildfire response actions effectively across public safety partners, transitioning from project-specific outreach to standardized protocols aligned with the Emergency Operations Plan. | 11.4 | Wildfire vulnerability | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Development of wildfire-specific communication protocols with public safety partners in progress. | In Progress
1010000025 | LSP | 2026-11-02 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination | Local Agency Wildfire Outreach Initiative |  | EP-03 | Program | Initiate and maintain annual outreach with local fire/emergency agencies near energized assets | Engage emergency partners to align response protocols and enhance coordination near energized sites. | 11.3 | Wildfire vulnerability | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Local fire agency coordination in place for Fern Road Substation with CAL FIRE Shasta-Trinity Unit; outreach initiated at LSPGC project sites in Q2 2026. | In Progress
1010000026 | LSP | 2026-11-02 | Enterprise Systems | Enterprise Systems Development | Centralized Vegetation Data and Inspection Integration |  | ENT-01 | Program | Centralize vegetation data and integrate inspection workflows | Streamline vegetation tracking by consolidating data and improving inspection process efficiency. | 12.2 | Contact from vegetation ignition likelihood | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | Begun review of data and in planning phases | In Progress
1010000027 | LSP | 2026-11-02 | Enterprise Systems | Enterprise Systems Development | Substation SCADA and Telemetry Maintenance |  | ENT-02 | Program | Maintain SCADA and operational telemetry for substation oversight | Ensure visibility and control over substation operations with continuous SCADA and telemetry | 12.2 | Equipment ignition likelihood | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | SCADA and telemetry commissioning checks performed for Fern Road Substation; baseline monitoring visibility confirmed. | In Progress
1010000028 | LSP | 2026-11-02 | Enterprise Systems | Enterprise Systems Development | Inspection Trend and Risk Dashboard Development |  | ENT-03 | Program | Develop basic dashboards for inspection trends and risk prioritization | Create actionable dashboards to visualize trends, prioritize risks, and guide mitigation activities. | 12.2 | Wildfire vulnerability | Qualitative |  | No |  | Not Applicable | 2026 | 3 |  | A local dashboard has been initiated to monitor daily wildfire conditions. | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000001 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000002 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000003 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000004 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000005 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000006 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000007 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000008 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000009 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000010 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000011 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000012 | Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000013 | Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000014 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000015 | Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000016 | Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000017 | Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000018 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000019 | Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000020 | Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000021 | Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000022 | Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000023 | Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000024 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000025 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000026 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000027 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000028 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000029 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000030 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000031 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000032 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000033 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000034 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000035 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000036 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000037 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000038 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000039 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000040 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000041 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000042 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000043 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000044 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000045 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000046 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000047 | Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000048 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000049 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000050 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000051 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000052 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000053 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000054 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000055 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000056 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000057 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000058 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000059 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1020000060 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000061 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000062 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000063 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000064 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000065 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000066 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000067 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000068 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000069 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000070 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000071 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  | Not Applicable | LSP | 2026 | 3
1020000072 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000073 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000074 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000075 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000076 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000077 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000078 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000079 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000080 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000081 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000082 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000083 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000084 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000085 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000086 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000087 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000088 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000089 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000090 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000091 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000092 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000093 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000094 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000095 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000096 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000097 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000098 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000099 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000100 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000101 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000102 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000103 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000104 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000105 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000106 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000107 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | LSP | 2026 | 3
1020000108 | Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  | Not Applicable | LSP | 2026 | 3
1020000109 | Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  | Not Applicable | LSP | 2026 | 3
1020000110 | Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  | Not Applicable | LSP | 2026 | 3 | 1
1020000111 | Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  | Not Applicable | LSP | 2026 | 3
1020000112 | Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  | Not Applicable | LSP | 2026 | 3
1020000113 | Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  | Not Applicable | LSP | 2026 | 3
1020000114 | Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  | Not Applicable | LSP | 2026 | 3
1020000115 | Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  | Not Applicable | LSP | 2026 | 3
1020000116 | Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  | Not Applicable | LSP | 2026 | 3
1020000117 | Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  | Not Applicable | LSP | 2026 | 3
1020000118 | Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  | Not Applicable | LSP | 2026 | 3
1020000119 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000120 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000121 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000122 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000123 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000124 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000125 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000126 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000127 | Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000128 | Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000129 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000130 | Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  | Not Applicable | LSP | 2026 | 3
1020000131 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000132 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000133 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000134 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000135 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000136 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000137 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000138 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000139 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000140 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000141 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000142 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000143 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000144 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000145 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000146 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000147 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000148 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000149 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000150 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000151 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000152 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000153 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000154 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000155 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000156 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000157 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000158 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000159 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000160 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000161 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000162 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000163 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000164 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000165 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000166 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000167 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000168 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000169 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000170 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000171 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000172 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000173 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000174 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000175 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000176 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000177 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000178 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000179 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000180 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000181 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000182 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000183 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000184 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000185 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000186 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000187 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000188 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000189 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000190 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000191 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000192 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000193 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000194 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000195 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000196 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000197 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000198 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000199 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000200 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000201 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000202 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000203 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000204 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000205 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000206 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000207 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000208 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000209 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000210 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000211 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000212 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000213 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000214 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000215 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000216 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000217 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000218 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000219 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000220 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000221 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000222 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000223 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000224 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000225 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000226 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000227 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000228 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000229 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000230 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000231 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000232 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000233 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000234 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000235 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000236 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000237 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000238 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000239 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000240 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000241 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000242 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000243 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000244 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000245 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000246 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000247 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000248 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000249 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000250 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000251 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000252 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000253 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000254 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000255 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000256 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000257 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000258 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000259 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000260 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000261 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000262 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000263 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000264 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000265 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000266 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000267 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000268 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000269 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000270 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000271 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000272 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000273 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000274 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000275 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000276 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000277 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000278 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000279 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000280 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000281 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000282 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000283 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000284 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000285 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000286 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000287 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000288 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000289 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000290 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000291 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000292 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000293 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000294 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000295 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000296 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000297 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000298 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000299 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000300 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000301 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000302 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000303 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000304 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000305 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000306 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000307 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000308 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000309 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000310 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000311 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000312 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000313 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000314 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000315 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000316 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000317 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000318 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000319 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000320 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000321 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000322 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | 358 unique assets at Fern Road Substation inspected monthly via human visual walk-around inspection (Other Inspection / Other method). Fern Road Substation is located in HFTD Tier 2. | Not Applicable | LSP | 2026 | 3 | 358
1020000323 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000324 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000325 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000326 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000327 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000328 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000329 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000330 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000331 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000332 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000333 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000334 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000335 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000336 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000337 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000338 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000339 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000340 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000341 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000342 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000343 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000344 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000345 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000346 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000347 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000348 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000349 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000350 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000351 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000352 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000353 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000354 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000355 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000356 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000357 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000358 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000359 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000360 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000361 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000362 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000363 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000364 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000365 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000366 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000367 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000368 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000369 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000370 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000371 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000372 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000373 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000374 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000375 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000376 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000377 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000378 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000379 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000380 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000381 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000382 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000383 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000384 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000385 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000386 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000387 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000388 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000389 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000390 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000391 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000392 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000393 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000394 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000395 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000396 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000397 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000398 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000399 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000400 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000401 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000402 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000403 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000404 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000405 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000406 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000407 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000408 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000409 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000410 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000411 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000412 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000413 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000414 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000415 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000416 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000417 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000418 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000419 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000420 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000421 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000422 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000423 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000424 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000425 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000426 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000427 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000428 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000429 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000430 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000431 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000432 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000433 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000434 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000435 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000436 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000437 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000438 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000439 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000440 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000441 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000442 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | 245 unique assets at Orchard Substation inspected monthly via human visual walk-around inspection (Other Inspection / Other method). Orchard Substation is located in Non-HFTD. | Not Applicable | LSP | 2026 | 3 | 245
1020000443 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000444 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000445 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000446 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000447 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000448 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000449 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000450 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000451 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000452 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000453 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000454 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | LSP | 2026 | 3
1020000455 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000456 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000457 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000458 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000459 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000460 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000461 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000462 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000463 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000464 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000465 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000466 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000467 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000468 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000469 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000470 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000471 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000472 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000473 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000474 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000475 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000476 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000477 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000478 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000479 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000480 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000481 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000482 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000483 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000484 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000485 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000486 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000487 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000488 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000489 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | LSP | 2026 | 3
1020000490 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections | No Level 3 findings identified during monthly human visual walk-around inspections at Orchard Substation in Q3 2026. Non-HFTD, Transmission, Other Inspection / Other method. | Not Applicable | LSP | 2026 | 3 | 0
1020000491 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000492 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000493 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000494 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000495 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000496 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000497 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000498 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000499 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000500 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000501 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000502 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000503 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000504 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000505 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000506 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000507 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000508 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000509 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000510 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000511 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000512 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000513 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000514 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000515 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000516 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000517 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000518 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000519 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000520 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000521 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000522 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000523 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000524 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000525 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000526 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000527 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000528 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000529 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000530 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000531 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000532 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000533 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000534 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000535 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000536 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000537 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000538 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000539 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000540 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000541 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000542 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000543 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000544 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000545 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000546 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000547 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000548 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000549 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000550 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000551 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000552 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000553 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000554 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000555 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000556 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000557 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000558 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000559 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000560 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000561 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000562 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000563 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000564 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000565 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000566 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000567 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000568 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000569 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000570 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000571 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000572 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000573 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000574 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000575 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000576 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000577 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000578 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000579 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000580 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000581 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000582 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000583 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000584 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000585 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000586 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000587 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000588 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000589 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000590 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000591 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000592 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000593 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000594 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000595 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000596 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000597 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000598 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000599 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000600 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000601 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000602 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000603 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000604 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000605 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000606 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000607 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000608 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000609 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000610 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000611 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000612 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000613 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000614 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000615 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000616 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000617 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000618 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000619 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000620 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000621 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000622 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000623 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000624 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000625 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000626 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000627 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000628 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000629 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000630 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000631 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000632 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000633 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000634 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000635 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000636 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000637 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000638 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000639 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000640 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000641 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000642 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000643 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000644 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000645 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000646 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000647 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000648 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000649 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000650 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000651 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000652 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000653 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000654 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000655 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000656 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000657 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000658 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000659 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000660 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000661 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000662 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000663 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000664 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000665 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000666 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000667 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000668 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000669 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000670 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000671 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000672 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000673 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000674 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000675 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000676 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000677 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000678 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000679 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000680 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000681 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000682 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000683 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000684 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000685 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000686 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000687 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000688 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000689 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000690 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000691 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000692 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000693 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000694 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000695 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000696 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000697 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000698 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000699 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000700 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000701 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000702 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000703 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000704 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000705 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000706 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | LSP | 2026 | 3
1020000707 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000708 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000709 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000710 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000711 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000712 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000713 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000714 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000715 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000716 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000717 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000718 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000719 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000720 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000721 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000722 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000723 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000724 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000725 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000726 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000727 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000728 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000729 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000730 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000731 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000732 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000733 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000734 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000735 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000736 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000737 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000738 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000739 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000740 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000741 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000742 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000743 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000744 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000745 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000746 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000747 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000748 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000749 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000750 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000751 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000752 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000753 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000754 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000755 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000756 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000757 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000758 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000759 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000760 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000761 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000762 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000763 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000764 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000765 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000766 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000767 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000768 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000769 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000770 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000771 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000772 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000773 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000774 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000775 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000776 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000777 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000778 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000779 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000780 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000781 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000782 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000783 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000784 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000785 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000786 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000787 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000788 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000789 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000790 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000791 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000792 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000793 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000794 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000795 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000796 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000797 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000798 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000799 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000800 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000801 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000802 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | LSP | 2026 | 3
1020000803 | Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | Not Applicable | LSP | 2026 | 3

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | [7 empty] | Not Applicable | LSP | 2026 | 3

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000001 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000002 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000003 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000004 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000005 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000006 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000007 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000008 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000009 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000010 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000011 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000012 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000013 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000014 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000015 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000016 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000017 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000018 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000019 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000020 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000021 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000022 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3
1040000023 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  | Not Applicable | LSP | 2026 | 3

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000001 | Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000002 | Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000003 | Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000004 | Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000005 | Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000006 | Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000007 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000008 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000009 | Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000010 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000011 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000012 | Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000013 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000014 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000015 | Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000016 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000017 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000018 | Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000019 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000020 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000021 | Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000022 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000023 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000024 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000025 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000026 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000027 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000028 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000029 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000030 | Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000031 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000032 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000033 | Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000034 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000035 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000036 | Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000037 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000038 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000039 | Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000040 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000041 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000042 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000043 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000044 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000045 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000046 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000047 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000048 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000049 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000050 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000051 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000052 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000053 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000054 | Vegetation contact | Wire down event | Grow-in | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000055 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000056 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000057 | Vegetation contact | Wire down event | Grow-in | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000058 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000059 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000060 | Vegetation contact | Wire down event | Blow-in | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000061 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000062 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000063 | Vegetation contact | Wire down event | Blow-in | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000064 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000065 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000066 | Vegetation contact | Wire down event | Trunk failure | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000067 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000068 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000069 | Vegetation contact | Wire down event | Trunk failure | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000070 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000071 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000072 | Vegetation contact | Wire down event | Root failure | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000073 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000074 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000075 | Vegetation contact | Wire down event | Root failure | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000076 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000077 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000078 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000079 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000080 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000081 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000082 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000083 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000084 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000085 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000086 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000087 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000088 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000089 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000090 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000091 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000092 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000093 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000094 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000095 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000096 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000097 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000098 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000099 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000100 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000101 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000102 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000103 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000104 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000105 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000106 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000107 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000108 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000109 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000110 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000111 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000112 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000113 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000114 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000115 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000116 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000117 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000118 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000119 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000120 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000121 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000122 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000123 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000124 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000125 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000126 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000127 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000128 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000129 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000130 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000131 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000132 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000133 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000134 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000135 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000136 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000137 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000138 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000139 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000140 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000141 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000142 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000143 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000144 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000145 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000146 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000147 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000148 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000149 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000150 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000151 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000152 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000153 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000154 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000155 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000156 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000157 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000158 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000159 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000160 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000161 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000162 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000163 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000164 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000165 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000166 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000167 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000168 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000169 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000170 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000171 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000172 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000173 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000174 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000175 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000176 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000177 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000178 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000179 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000180 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000181 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000182 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000183 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000184 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000185 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000186 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000187 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000188 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000189 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000190 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000191 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000192 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000193 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000194 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000195 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000196 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000197 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000198 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000199 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000200 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000201 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000202 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000203 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000204 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000205 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000206 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000207 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000208 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000209 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000210 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000211 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000212 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000213 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000214 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000215 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000216 | Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000217 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000218 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000219 | Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000220 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000221 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000222 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000223 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000224 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000225 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000226 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000227 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000228 | Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000229 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000230 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000231 | Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000232 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000233 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000234 | Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000235 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000236 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000237 | Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000238 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000239 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000240 | Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000241 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000242 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000243 | Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000244 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000245 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000246 | Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000247 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000248 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000249 | Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000250 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000251 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000252 | Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000253 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000254 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000255 | Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000256 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000257 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000258 | Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000259 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000260 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000261 | Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000262 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000263 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000264 | Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000265 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000266 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000267 | Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000268 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000269 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000270 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000271 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000272 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000273 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000274 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000275 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000276 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000277 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000278 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000279 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000280 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000281 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000282 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000283 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000284 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000285 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000286 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000287 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000288 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000289 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000290 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000291 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000292 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000293 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000294 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000295 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000296 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000297 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000298 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000299 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000300 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000301 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000302 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000303 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000304 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000305 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000306 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000307 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000308 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000309 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000310 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000311 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000312 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000313 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000314 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000315 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000316 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000317 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000318 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000319 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000320 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000321 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000322 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000323 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000324 | Vegetation contact | Unplanned Outage | Root failure | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000325 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000326 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000327 | Vegetation contact | Unplanned Outage | Root failure | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000328 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000329 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000330 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000331 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000332 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000333 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000334 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000335 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000336 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000337 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000338 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000339 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000340 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000341 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000342 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000343 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000344 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000345 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000346 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000347 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000348 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000349 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000350 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000351 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000352 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000353 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000354 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000355 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000356 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000357 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000358 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000359 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000360 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000361 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000362 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000363 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000364 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000365 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000366 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000367 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000368 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000369 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000370 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000371 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000372 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000373 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000374 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000375 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000376 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000377 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000378 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000379 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000380 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000381 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000382 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000383 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000384 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000385 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000386 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000387 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000388 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000389 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000390 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000391 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000392 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000393 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000394 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000395 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000396 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000397 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000398 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000399 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000400 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000401 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000402 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000403 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000404 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000405 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000406 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000407 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000408 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000409 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000410 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000411 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000412 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000413 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000414 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000415 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000416 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000417 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000418 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000419 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000420 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000421 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000422 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000423 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000424 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000425 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000426 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000427 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000428 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000429 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000430 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000431 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000432 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000433 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000434 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000435 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000436 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000437 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000438 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000439 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000440 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000441 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000442 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000443 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000444 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000445 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000446 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000447 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000448 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000449 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000450 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000451 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000452 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000453 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000454 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000455 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000456 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000457 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000458 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000459 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000460 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000461 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000462 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000463 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000464 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000465 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000466 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000467 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000468 | Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000469 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000470 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000471 | Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000472 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000473 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000474 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000475 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000476 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000477 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000478 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000479 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000480 | Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000481 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000482 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000483 | Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000484 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000485 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000486 | Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000487 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000488 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000489 | Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000490 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000491 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000492 | Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000493 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000494 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000495 | Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000496 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000497 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000498 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000499 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000500 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000501 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000502 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000503 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000504 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000505 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000506 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000507 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000508 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000509 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000510 | Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000511 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000512 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000513 | Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000514 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  | Not Applicable | LSP | 2026 | 3
1050000515 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  | Not Applicable | LSP | 2026 | 3

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000001 | Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000002 | Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000003 | Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000004 | Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000005 | Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000006 | Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000007 | Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000008 | Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000009 | Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000010 | Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000011 | Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000012 | Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000013 | Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000014 | Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000015 | Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000016 | Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000017 | Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000018 | Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000019 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000020 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000021 | Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000022 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000023 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000024 | Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000025 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000026 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000027 | Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000028 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000029 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000030 | Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000031 | Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000032 | Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000033 | Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000034 | Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000035 | Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000036 | Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000037 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000038 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000039 | Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000040 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000041 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000042 | Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000043 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000044 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000045 | Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000046 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000047 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000048 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000049 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000050 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000051 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000052 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000053 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000054 | Vegetation contact | Grow-in | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000055 | Vegetation contact | Grow-in | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000056 | Vegetation contact | Grow-in | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000057 | Vegetation contact | Grow-in | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000058 | Vegetation contact | Grow-in | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000059 | Vegetation contact | Grow-in | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000060 | Vegetation contact | Blow-in | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000061 | Vegetation contact | Blow-in | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000062 | Vegetation contact | Blow-in | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000063 | Vegetation contact | Blow-in | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000064 | Vegetation contact | Blow-in | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000065 | Vegetation contact | Blow-in | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000066 | Vegetation contact | Trunk failure | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000067 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000068 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000069 | Vegetation contact | Trunk failure | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000070 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000071 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000072 | Vegetation contact | Root failure | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000073 | Vegetation contact | Root failure | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000074 | Vegetation contact | Root failure | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000075 | Vegetation contact | Root failure | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000076 | Vegetation contact | Root failure | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000077 | Vegetation contact | Root failure | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000078 | Vegetation contact | Detached frond / limb / bark | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000079 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000080 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000081 | Vegetation contact | Detached frond / limb / bark | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000082 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000083 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000084 | Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000085 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000086 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000087 | Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000088 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000089 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000090 | Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000091 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000092 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000093 | Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000094 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000095 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000096 | Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000097 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000098 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000099 | Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000100 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000101 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000102 | Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000103 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000104 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000105 | Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000106 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000107 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000108 | Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000109 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000110 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000111 | Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000112 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000113 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000114 | Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000115 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000116 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000117 | Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000118 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000119 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000120 | Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000121 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000122 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000123 | Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000124 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000125 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000126 | Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000127 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000128 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000129 | Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000130 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000131 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000132 | Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000133 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000134 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000135 | Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000136 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000137 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000138 | Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000139 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000140 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000141 | Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000142 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000143 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000144 | Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000145 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000146 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000147 | Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000148 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000149 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000150 | Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000151 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000152 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000153 | Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000154 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000155 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000156 | Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000157 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000158 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000159 | Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000160 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000161 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000162 | Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000163 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000164 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000165 | Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000166 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000167 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000168 | Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000169 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000170 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000171 | Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000172 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000173 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000174 | Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000175 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000176 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000177 | Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000178 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000179 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000180 | Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000181 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000182 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000183 | Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000184 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000185 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000186 | Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000187 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000188 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000189 | Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000190 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000191 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000192 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000193 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000194 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000195 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000196 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000197 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000198 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000199 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000200 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000201 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000202 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000203 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000204 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000205 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000206 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000207 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000208 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000209 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000210 | Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000211 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000212 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000213 | Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000214 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000215 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000216 | Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000217 | Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000218 | Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000219 | Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000220 | Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000221 | Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000222 | Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000223 | Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000224 | Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000225 | Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000226 | Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000227 | Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000228 | Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000229 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000230 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000231 | Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000232 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000233 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000234 | Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000235 | Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000236 | Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000237 | Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000238 | Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000239 | Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000240 | Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000241 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000242 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000243 | Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000244 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000245 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000246 | Other | Other (other) | Distribution | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000247 | Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000248 | Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000249 | Other | Other (other) | Transmission | Non-HFTD | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000250 | Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  | Not Applicable | LSP | 2026 | 3
1060000251 | Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  | Not Applicable | LSP | 2026 | 3

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000001 | Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000002 | Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000003 | Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000004 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000005 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000006 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000007 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000008 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000009 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000010 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000011 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000012 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000013 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000014 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000015 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000016 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000017 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000018 | Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000019 | Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000020 | Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000021 | Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000022 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000023 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000024 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000025 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000026 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000027 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000028 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000029 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000030 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000031 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000032 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000033 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000034 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000035 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000036 | Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000037 | Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000038 | Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000039 | Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000040 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000041 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000042 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000043 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000044 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000045 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000046 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000047 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000048 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000049 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000050 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000051 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000052 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000053 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000054 | Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000055 | Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000056 | Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000057 | Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000058 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000059 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000060 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000061 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000062 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000063 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000064 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000065 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000066 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000067 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000068 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000069 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000070 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000071 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1070000072 | Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000073 | Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000074 | Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000075 | Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000076 | Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000077 | Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000078 | Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000079 | Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000080 | Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000081 | Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000082 | Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000083 | Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000084 | Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000085 | Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000086 | Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000087 | Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000088 | Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000089 | Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  | Not Applicable | LSP | 2026 | 3
1070000090 | Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000091 | Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000092 | Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000093 | Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000094 | Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000095 | Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000096 | Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000097 | Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000098 | Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000099 | Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000100 | Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000101 | Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000102 | Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000103 | Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000104 | Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000105 | Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000106 | Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000107 | Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  | Not Applicable | LSP | 2026 | 3
1070000108 | Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000109 | Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000110 | Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000111 | Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000112 | Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000113 | Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000114 | Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000115 | Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000116 | Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000117 | Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000118 | Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000119 | Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000120 | Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000121 | Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000122 | Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000123 | Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000124 | Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000125 | Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  | Not Applicable | LSP | 2026 | 3
1070000126 | AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000127 | AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000128 | AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000129 | AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000130 | AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000131 | AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000132 | AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000133 | AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000134 | AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000135 | AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000136 | AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000137 | AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000138 | AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000139 | AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000140 | AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000141 | AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000142 | AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000143 | AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  | Not Applicable | LSP | 2026 | 3
1070000144 | Substations |  | Non-HFTD | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000145 | Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000146 | Substations |  | Non-HFTD | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000147 | Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | Orchard Substation. Located in Non-HFTD, Rural, Non-WUI area. | Not Applicable | LSP | 2026 | 3 | 1
1070000148 | Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000149 | Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000150 | Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000151 | Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000152 | Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000153 | Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | Fern Road Substation. Located in HFTD Tier 2, Rural, Non-WUI area. | Not Applicable | LSP | 2026 | 3 | 1
1070000154 | Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000155 | Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000156 | Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000157 | Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000158 | Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000159 | Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000160 | Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000161 | Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1070000162 | Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000163 | Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000164 | Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000165 | Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | 1 weather station installed at Orchard Substation. Located in Non-HFTD, Rural, Non-WUI area. | Not Applicable | LSP | 2026 | 3 | 1
1070000166 | Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000167 | Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000168 | Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000169 | Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000170 | Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000171 | Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | 1 weather station at Fern Road Substation (HFTD Tier 2, Rural, Non-WUI). | Not Applicable | LSP | 2026 | 3 | 1
1070000172 | Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000173 | Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000174 | Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000175 | Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000176 | Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000177 | Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000178 | Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1070000179 | Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000001 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000002 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000003 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000004 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000005 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000006 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000007 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000008 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000009 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000010 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000011 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000012 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000013 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000014 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000015 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000016 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000017 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000018 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000019 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000020 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000021 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000022 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000023 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000024 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000025 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000026 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000027 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000028 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000029 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000030 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000031 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000032 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000033 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000034 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000035 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000036 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000037 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000038 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000039 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000040 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000041 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000042 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000043 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000044 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000045 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000046 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000047 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000048 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000049 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000050 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000051 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000052 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000053 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000054 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000055 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000056 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000057 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000058 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000059 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000060 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000061 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000062 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000063 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000064 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000065 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000066 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000067 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000068 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000069 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000070 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000071 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1080000072 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000073 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000074 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000075 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000076 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000077 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000078 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000079 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000080 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000081 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3 | 1
1080000082 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000083 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000084 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000085 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000086 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000087 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000088 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000089 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1080000090 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000091 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000092 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000093 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000094 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000095 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000096 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000097 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000098 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000099 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000100 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000101 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000102 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000103 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000104 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000105 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000106 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1080000107 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000001 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000002 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000003 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000004 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000005 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000006 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000007 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000008 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000009 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000010 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000011 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000012 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000013 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000014 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000015 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000016 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000017 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000018 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000019 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000020 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000021 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000022 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000023 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000024 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000025 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000026 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000027 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000028 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000029 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000030 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000031 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000032 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000033 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000034 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000035 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  | Not Applicable | LSP | 2026 | 3
1090000036 | Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000037 | Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000038 | Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000039 | Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000040 | Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000041 | Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000042 | Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000043 | Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000044 | Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000045 | Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000046 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000047 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000048 | Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000049 | Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000050 | Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000051 | Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000052 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000053 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  | Not Applicable | LSP | 2026 | 3
1090000054 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000055 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000056 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000057 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000058 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000059 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000060 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000061 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000062 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000063 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000064 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000065 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000066 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000067 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000068 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000069 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000070 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3
1090000071 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  | Not Applicable | LSP | 2026 | 3

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000001 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000002 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000003 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000004 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  | Not Applicable | LSP | 2026 | 3
1100000005 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  | Not Applicable | LSP | 2026 | 3
1100000006 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  | Not Applicable | LSP | 2026 | 3
1100000007 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  | Not Applicable | LSP | 2026 | 3
1100000008 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  | Not Applicable | LSP | 2026 | 3
1100000009 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  | Not Applicable | LSP | 2026 | 3
1100000010 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  | Not Applicable | LSP | 2026 | 3
1100000011 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  | Not Applicable | LSP | 2026 | 3
1100000012 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000013 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000014 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000015 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000016 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  | Not Applicable | LSP | 2026 | 3
1100000017 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  | Not Applicable | LSP | 2026 | 3
1100000018 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  | Not Applicable | LSP | 2026 | 3
1100000019 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  | Not Applicable | LSP | 2026 | 3
1100000020 | Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  | Not Applicable | LSP | 2026 | 3
1100000021 | Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  | Not Applicable | LSP | 2026 | 3
1100000022 | Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  | Not Applicable | LSP | 2026 | 3
1100000023 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  | Not Applicable | LSP | 2026 | 3
1100000024 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  | Not Applicable | LSP | 2026 | 3
1100000025 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  | Not Applicable | LSP | 2026 | 3
1100000026 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  | Not Applicable | LSP | 2026 | 3
1100000027 | Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  | Not Applicable | LSP | 2026 | 3
1100000028 | Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not Applicable | LSP | 2026 | 3
1100000029 | Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not Applicable | LSP | 2026 | 3
1100000030 | Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not Applicable | LSP | 2026 | 3
1100000031 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not Applicable | LSP | 2026 | 3
1100000032 | Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not Applicable | LSP | 2026 | 3
1100000033 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  | Not Applicable | LSP | 2026 | 3
1100000034 | Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  | Not Applicable | LSP | 2026 | 3
1100000035 | Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  | Not Applicable | LSP | 2026 | 3
1100000036 | Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  | Not Applicable | LSP | 2026 | 3
1100000037 | Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  | Not Applicable | LSP | 2026 | 3
1100000038 | Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  | Not Applicable | LSP | 2026 | 3
1100000039 | Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  | Not Applicable | LSP | 2026 | 3
1100000040 | Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  | Not Applicable | LSP | 2026 | 3
1100000041 | Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  | Not Applicable | LSP | 2026 | 3
1100000042 | Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  | Not Applicable | LSP | 2026 | 3
1100000043 | Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  | Not Applicable | LSP | 2026 | 3

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER