## Table 6-4 Corrected
Line No. | Circuit Segment Name | Initial Overall Utility Risk | % of Circuit Segment UG through 2025 | % of Circuit Segment OH through 2025 | % of Circuit Segment Removed through 2025 | 2026 Activities | 2026 Overall Utility Risk | 2026 Forecast UG Miles | 2026 Forecast OH Miles | 2026 Forecast Removal Miles | 2027 Activities | 2027 Overall Utility Risk | 2027 Forecast UG Miles | 2027 Forecast OH Miles | 2027 Forecast Removal Miles | 2028 Activities | 2028 Overall Utility Risk | 2028 Forecast UG Miles | 2028 Forecast OH Miles | 2028 Forecast Removal Miles
1 | CLAYTON 2212681608 | 99.7 | 0 | 0 | 0 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.77 | 0.04 | 26.97 | 0.19 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.69 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.62 | 0 | 0 | 0
2 | BALCH NO 1 1101105414 | 91.52 | 0 | 0 | 0 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 22.36 | 0 | 3.1 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 22.33 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 22.3 | 0 | 0 | 0
3 | CLOVERDALE 1102672 | 80.9 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 28.04 | 0 | 0 | 0 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32 | 45.27 | 1.88 | 0.4 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32 | 0 | 0 | 0
4 | PLACERVILLE 21067522 | 72.83 | 0.016072 | 0 | 0.0014539 | Line removal Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 27.14 | 0 | 0 | 0.7 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 26.32 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 25.5 | 0 | 0 | 0
5 | PLACERVILLE 210611132 | 67.32 | 0 | 0.018952 | 0.0061755 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.71 | 21.65 | 12.6 | 0.12 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.47 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.23 | 0 | 0 | 0
6 | MIDDLETOWN 1101644756 | 66.9 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 23 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 22.42 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 21.84 | 0 | 0 | 0
7 | STANISLAUS 1701CB | 64.28 | 0.075596 | 0.087615 | 0 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.26 | 0 | 8.65 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 19.01 | 0.14 | 2.04 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 9.88 | 1.85 | 25.51 | 0
8 | EL DORADO PH 210119752 | 61.34 | 0.11771 | 0.6458 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 23.25 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 22.66 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.93 | 2.09 | 28.91 | 0
9 | CALPINE 1144CB | 60.7 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.43 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.43 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.43 | 0 | 0 | 0
10 | ALLEGHANY 1102CB | 60.06 | 0 | 0.021538 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.71 | 2.56 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.93 | 18.67 | 0.78 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.67 | 0 | 0 | 0
11 | MARIPOSA 210237282 | 59.39 | 0 | 0 | 0.0019136 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.5 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 19.83 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 19.15 | 0 | 0 | 0
12 | BIG BEND 1101CB | 57.54 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 23.05 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 22.78 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 22.5 | 0 | 0 | 0
13 | WEST POINT 11024788 | 57.42 | 0.036704 | 0 | 0.0060646 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 21.12 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.5 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 19.88 | 0 | 0 | 0
14 | CALAVERAS CEMENT 1101544800 | 57.32 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 19.97 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.78 | 9.01 | 1.01 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.94 | 15 | 0 | 0
15 | CALAVERAS CEMENT 1101502 | 56.13 | 0 | 0 | 0.013383 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.48 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.45 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.42 | 0 | 0 | 0
16 | CORNING 110185152 | 54.43 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 22.26 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 21.99 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 21.71 | 0 | 0 | 0
17 | CURTIS 17048140 | 54.04 | 0 | 0 | 0.0054616 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 19.28 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.7 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.11 | 0 | 0 | 0
18 | COLUMBIA HILL 1101CB | 53.47 | 0 | 0 | 0.0003876 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 19.11 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.5 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.89 | 0 | 0 | 0
19 | TEMPLETON 2113A12 | 53.42 | 0 | 0 | 0.0024091 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 19.35 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.83 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.31 | 0 | 0 | 0
20 | FORT ROSS 112170288 | 52.93 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.53 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.27 | 25.33 | 1.05 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.54 | 0 | 0 | 0
21 | BIG BEND 1101641808 | 52.57 | 0 | 0.017722 | 0.00032819 | Line removal Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.86 | 0 | 0 | 1.78 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.52 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.19 | 0 | 0 | 0
22 | MARIPOSA 2101752630 | 51.4 | 0 | 0 | 0.011399 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.78 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.45 | 5.2 | 12.32 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.14 | 0 | 0 | 0
23 | SILVERADO 2104633600 | 50.56 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.77 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.56 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.08 | 20.07 | 4.86 | 0
24 | VACAVILLE 110838316 | 49.31 | 0.40886 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.53 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.23 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.93 | 0 | 0 | 0
25 | APPLE HILL 110497086 | 49.2 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.03 | 0 | 0 | 0 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.53 | 0 | 5.61 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.26 | 20.93 | 0 | 0
26 | APPLE HILL 21029722 | 48.54 | 0 | 0.031281 | 0.0022344 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.24 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.05 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.86 | 0 | 0 | 0
27 | MIDDLETOWN 1101548 | 48.5 | 0.099081 | 0.2322 | 0.0023436 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.32 | 5.06 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.71 | 11.5 | 0.48 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 2.87 | 15.71 | 0.6 | 0
28 | PINE GROVE 11026080 | 48.12 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.76 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.75 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.74 | 0 | 0 | 0
29 | HIGHLANDS 1102628 | 46.86 | 0 | 0.072338 | 0.063239 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.7 | 5.57 | 1.19 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.16 | 3.81 | 4.02 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 2.71 | 11.26 | 0 | 0
30 | PLACERVILLE 21069712 | 46.29 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.61 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.48 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 4.05 | 20.23 | 4.9 | 0
31 | HARTLEY 1101698 | 46.18 | 0.006867 | 0.23262 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.48 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.24 | 0.41 | 12.77 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 7.41 | 4.89 | 0 | 0
32 | PUEBLO 2103678 | 45.96 | 0 | 0 | 0.0063475 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.18 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 2.02 | 36.49 | 1.52 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.49 | 0 | 0 | 0
33 | MARTELL 110191216 | 45.65 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.62 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.03 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.44 | 0 | 0 | 0
34 | REDBUD 1101323962 | 45.53 | 0.33636 | 0.0039597 | 0.0050396 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.76 | 1.09 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.58 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 20.39 | 0 | 0 | 0
35 | MOLINO 1102318 | 45.41 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.61 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.98 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.35 | 0 | 0 | 0
36 | HIGHLANDS 1103520 | 44.29 | 0 | 0 | 0.0012262 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.46 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.01 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.55 | 0 | 0 | 0
37 | COARSEGOLD 210410110 | 43.96 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.8 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.32 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.84 | 0 | 0 | 0
38 | AUBERRY 1101R2578 | 43.64 | 0.0090535 | 0.25741 | 0.0030864 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.31 | 0.12 | 15.64 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.82 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.33 | 0 | 0 | 0
39 | MARIPOSA 210237288 | 43.57 | 0 | 0 | 0.0017168 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.76 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.22 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.69 | 0 | 0 | 0
40 | FROGTOWN 170113412 | 43.55 | 0 | 0.0040673 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.1 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.7 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.3 | 0 | 0 | 0
41 | ELECTRA 1101CB | 43.22 | 0 | 0 | 0.0023566 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.65 | 0 | 0 | 0 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 9.51 | 0 | 15.34 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 5.91 | 6.35 | 0 | 0
42 | CORNING 11021622 | 42.71 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.01 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.84 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.67 | 0 | 0 | 0
43 | DIAMOND SPRINGS 110676088 | 42.32 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.45 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.1 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.75 | 0 | 0 | 0
44 | BONNIE NOOK 1102CB | 41.86 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.35 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 4.07 | 25.31 | 1.05 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.64 | 0 | 0 | 0
45 | BRUNSWICK 11021010 | 41.68 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.19 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.04 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.89 | 0 | 0 | 0
46 | CURTIS 170390320 | 41.02 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.14 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.89 | 0 | 0 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 4.58 | 22.83 | 0 | 0
47 | MARIPOSA 210110070 | 40.91 | 0 | 0 | 0.0018932 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.72 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.78 | 1.23 | 2.9 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 4.7 | 5.81 | 12.66 | 0
48 | GIRVAN 11011330 | 40.53 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.28 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.87 | 0 | 0 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 4.92 | 20.75 | 0 | 0
49 | APPLE HILL 110413512 | 40.3 | 0 | 0.0048655 | 0.011162 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.67 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.3 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.92 | 0 | 0 | 0
50 | DIAMOND SPRINGS 11057722 | 40.18 | 0 | 0 | 0.0014892 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.09 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.64 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.18 | 0 | 0 | 0
51 | BALCH NO 1 1101406582 | 40.11 | 0 | 0 | 0 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.34 | 0 | 3.67 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.33 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.32 | 0 | 0 | 0
52 | MOUNTAIN QUARRIES 21011130 | 39.65 | 0 | 0 | 0.00086319 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.07 | 0 | 0 | 0 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 9.34 | 0 | 13.15 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.3 | 5.45 | 0 | 0
53 | APPLE HILL 2102836878 | 39.47 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.61 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.29 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 17.97 | 0 | 0 | 0
54 | COALINGA NO 2 11059260 | 39.36 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 18.8 | 0 | 0 | 0 | Line removal Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.85 | 0 | 0 | 4.1 | Line removal Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.55 | 0 | 0 | 8.69
55 | LAYTONVILLE 1101518 | 38.9 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.97 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.57 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.18 | 1.22 | 16.91 | 0
56 | APPLE HILL 21028372 | 38.77 | 0 | 0 | 0.0016203 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.56 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.32 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.07 | 0 | 0 | 0
57 | LOS OSITOS 21037014 | 38.72 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.99 | 0 | 0 | 0
58 | STILLWATER 11021466 | 38.39 | 0 | 0 | 0.0051326 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.03 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.64 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.17 | 16.47 | 3.99 | 0
59 | PIT NO 3 21011482 | 37.31 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.21 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.55 | 12.83 | 0.53 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.44 | 0 | 0 | 0
60 | GEYSERVILLE 1102904170 | 36.99 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.13 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.93 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.8 | 5.78 | 12.6 | 0
61 | FORESTHILL 11011802 | 36.44 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.31 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 5.82 | 23.44 | 0.97 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 5.43 | 0 | 0 | 0
62 | FITCH MOUNTAIN 111324918 | 36.43 | 0 | 0.19922 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.61 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.12 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.64 | 0 | 0 | 0
63 | MARIPOSA 2101439030 | 36.07 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.56 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.27 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.97 | 0 | 0 | 0
64 | CLAYTON 221296224 | 35.98 | 0.12482 | 0.097518 | 0.022163 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 7.88 | 0.79 | 4.68 | 0.25 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.37 | 0.52 | 1.24 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.19 | 0 | 0 | 0
65 | PEORIA 170190090 | 35.85 | 0 | 0 | 0.0028809 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.49 | 0 | 1.71 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.32 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.15 | 0 | 0 | 0
66 | HOPLAND 11014626 | 35.61 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.93 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.5 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.07 | 0 | 0 | 0
67 | SILVERADO 2104632 | 35.58 | 0 | 0 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 8 | 10.12 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 7.6 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 7.19 | 0 | 0 | 0
68 | PLACERVILLE 2106935216 | 35.45 | 0 | 0 | 0.0094552 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.31 | 24.16 | 0.02 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.94 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.57 | 0 | 0 | 0
69 | APPLE HILL 2102186912 | 34.93 | 0 | 0.0099398 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.32 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.08 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.85 | 0 | 0 | 0
70 | SHADY GLEN 1101941844 | 34.6 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.92 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.8 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 7.37 | 13.33 | 3.23 | 0
71 | PINE GROVE 1102269286 | 34.15 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 16.3 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.99 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 15.67 | 0 | 0 | 0
72 | ORO FINO 110239154 | 34.08 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.59 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 14.22 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.85 | 0 | 0 | 0
73 | WEST POINT 110234416 | 33.91 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.8 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.42 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.04 | 0 | 0 | 0
74 | CEDAR CREEK 1101CB | 33.76 | 0 | 0 | 0.0021782 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.69 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.36 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.03 | 0 | 0 | 0
75 | SISQUOC 1102M52 | 33.41 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.15 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.86 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.56 | 0 | 0 | 0
76 | TEMPLETON 2113641367 | 33.39 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.18 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.97 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.75 | 0 | 0 | 0
77 | MARIPOSA 21019400 | 33.3 | 0.22669 | 0 | 0.0040018 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 12.13 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.5 | 0.14 | 2.11 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.14 | 0 | 0 | 0
78 | FORESTHILL 1102359542 | 32.8 | 0 | 0 | 0 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.43 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.06 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 2.69 | 0 | 0 | 0
79 | CALAVERAS CEMENT 11011419 | 32.63 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.86 | 0 | 0 | 0 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.54 | 0 | 0.65 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.84 | 15.44 | 0 | 0
80 | BRUNSWICK 110651486 | 32.08 | 0.0013522 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.2 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.82 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.44 | 0 | 0 | 0
81 | SHINGLE SPRINGS 210913322 | 32.02 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.4 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.04 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 9.68 | 0 | 0 | 0
82 | PINE GROVE 11013170 | 32 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.87 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.84 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.8 | 0 | 0 | 0
83 | WEST POINT 110236676 | 31.8 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.73 | 0 | 0 | 0 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 9.12 | 0 | 3.65 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 2.31 | 13.62 | 0 | 0
84 | APPLE HILL 21021532 | 31.44 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.66 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.47 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 13.29 | 0 | 0 | 0
85 | CALAVERAS CEMENT 110147968 | 30.78 | 0 | 0 | 0.0057208 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.09 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 11.07 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.88 | 17.75 | 0.68 | 0
86 | WILDWOOD 1101384582 | 30.76 | 0 | 0 | 0 | EPSS Vegetation routine patrol Vegetation hazard patrol | 9.75 | 0 | 0 | 0 | EPSS Vegetation routine patrol Vegetation hazard patrol | 9.75 | 0 | 0 | 0 | EPSS Vegetation routine patrol Vegetation hazard patrol | 9.75 | 0 | 0 | 0
87 | SANTA YNEZ 1102320270 | 30.73 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.88 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.6 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 5.82 | 8.56 | 0.33 | 0
88 | FRENCH GULCH 11022902 | 30.57 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.58 | 0 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 5.06 | 0.39 | 5.86 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 5.04 | 0 | 0 | 0
89 | STANISLAUS 17011812 | 30.56 | 0 | 0.0072681 | 0 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 6.62 | 14.86 | 0 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.96 | 7.24 | 0.3 | 0 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.09 | 12.79 | 0.49 | 0
90 | PERRY 110179696 | 30.43 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.47 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 10.08 | 0 | 0 | 0 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 9.69 | 0 | 0 | 0