## OEIS_004_Q4_a
WMP-Discovery2026-2028_DR_OEIS_004-Q004aAtch01.xlsx
| 2026 | [8 empty] | 2027 | [8 empty] | 2028
Hardening Type | WMP Target | DR - Updated | Delta - Updated | i. | ii. FRRB | ii. PSPS | ii. Other | iii. | iv. Community Rebuild | WMP Target | DR - Updated | Delta - Updated | i. | ii. FRRB | ii. PSPS | ii. Other | iii. | iv. Community Rebuild | WMP Target | DR - Updated | Delta - Updated | i. | ii. FRRB | ii. PSPS | ii. Other | iii. | iv. Community Rebuild
UG | 370 | 86.034 | 283.966 | 246.5383 | 2.6511 | 17.1686 | 1.7312 | 5.9 | 10.3699 | 307 | 226.93 | 80.1 | 80.07 | - | - | - | - | - | 400 | 278.2 | 121.8 | 121.8 | - | - | - | - | -
OH | 294 | 78.23 | 215.77 | 211.085 | 0.037879 | 4.3799 | 0 | 0 | 0 | 190 | 91.2 | 98.8 | 98.77 | - | - | - | - | - | 190 | 115.6 | 74.3 | 74.3 | - | - | - | - | -
Line Removal | 24 | 3.04 | 20.96 | 12.175 | 8.9 | 0 | 0 | 0 | 0 | 10 | 4.5 | 5.5 | 5.5 | - | - | - | - | - | 10 | 8.7 | 1.3 | 1.3 | - | - | - | - | -
Categories
i. Work prescribed in lower 80% of risk due to prioritization based on WDRM v3 v4
ii. Work prescribed in lower 80% of risk due to other qualifying threshold, broken out by threshold (i.e., ingress/egress issue, tree strike potential, PSPS risk)
iii. Work not yet planned for specific circuit segments
iv. Other not listed above, including associated reasoning