## Sheet1
Line No. | Circuit Segment Name | Total Primary Overhead Miles | Initial Overall Utility Risk per Primary Overhead Mile | 2026 Activities | 2026 Overall Utility Risk per Primary Overhead Mile | 2027 Activities | 2027 Overall Utility Risk per Primary Overhead Mile | 2028 Activities | 2028 Overall Utility Risk per Primary Overhead Mile
1 | CLAYTON 2212681608 | 26.8792 | 3.7092 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.69828 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.6583 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.61832
2 | BALCH NO 1 1101105414 | 6.9964 | 13.0815 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.1957 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.1915 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 3.1874
3 | CLOVERDALE 1102672 | 22.2308 | 3.6392 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.2613 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.014545 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.014545
4 | PLACERVILLE 21067522 | 67.1149 | 1.0852 | Line removal Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.40438 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.39213 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.37988
5 | PLACERVILLE 210611132 | 42.3984 | 1.5879 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.27629 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.27057 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.26485
6 | MIDDLETOWN 1101644756 | 18.2599 | 3.6635 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.2596 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.2279 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.1962
7 | STANISLAUS 1701CB | 36.5471 | 1.7589 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.55433 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.52008 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.27034
8 | EL DORADO PH 210119752 | 38.3707 | 1.5985 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.60598 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.5906 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.33691
9 | CALPINE 1144CB | 26.5401 | 2.2869 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.76996 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.76982 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.76967
10 | ALLEGHANY 1102CB | 17.6766 | 3.3977 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.002 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.052399 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.038103
11 | MARIPOSA 210237282 | 58.8825 | 1.0087 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.34818 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.33671 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32524
12 | BIG BEND 1101CB | 23.0448 | 2.4971 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.0004 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.98831 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.97618
13 | WEST POINT 11024788 | 71.9787 | 0.79768 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.2934 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.28481 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.27623
14 | CALAVERAS CEMENT 1101544800 | 22.9908 | 2.4931 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.86846 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.55596 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.08433
15 | CALAVERAS CEMENT 1101502 | 40.3825 | 1.3901 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.50705 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.5064 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.50576
16 | CORNING 110185152 | 23.068 | 2.3597 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.96492 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.95306 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.94119
17 | CURTIS 17048140 | 35.6786 | 1.5147 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.54049 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.52404 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.50759
18 | COLUMBIA HILL 1101CB | 45.3488 | 1.179 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.42139 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.40799 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.39459
19 | TEMPLETON 2113A12 | 40.8007 | 1.3093 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.4742 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.46145 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.4487
20 | FORT ROSS 112170288 | 23.9732 | 2.2077 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.68941 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.053086 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.022568
21 | BIG BEND 1101641808 | 28.579 | 1.8395 | Line removal Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.72994 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.71814 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.70633
22 | MARIPOSA 2101752630 | 18.7097 | 2.7473 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.95013 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.34465 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32821
23 | SILVERADO 2104633600 | 30.9598 | 1.6331 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.67079 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.66401 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.3255
24 | VACAVILLE 110838316 | 23.0221 | 2.1419 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.76145 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.74838 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.73532
25 | APPLE HILL 110497086 | 25.5664 | 1.9243 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.66614 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.5684 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.12763
26 | APPLE HILL 21029722 | 38.2109 | 1.2703 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.45126 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.44625 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.44124
27 | MIDDLETOWN 1101548 | 27.4134 | 1.7691 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.66815 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.42733 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.10481
28 | PINE GROVE 11026080 | 34.3546 | 1.4006 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.48777 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.4875 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.48722
29 | HIGHLANDS 1102628 | 18.3254 | 2.5569 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.802 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.55447 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.14815
30 | PLACERVILLE 21069712 | 24.7065 | 1.8738 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.67214 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.66687 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.16408
31 | HARTLEY 1101698 | 23.6406 | 1.9534 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.65475 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.43295 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.31354
32 | PUEBLO 2103678 | 34.7132 | 1.3241 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.49486 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.058289 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.04288
33 | MARTELL 110191216 | 40.2733 | 1.1335 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.36303 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.34833 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.33363
34 | REDBUD 1101323962 | 24.2801 | 1.8751 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.85497 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.84743 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.83989
35 | MOLINO 1102318 | 25.9564 | 1.7496 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.56283 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.53852 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.51422
36 | HIGHLANDS 1103520 | 43.5981 | 1.016 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.37761 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.36712 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.35664
37 | COARSEGOLD 210410110 | 49.2666 | 0.89224 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32073 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.31093 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.30113
38 | AUBERRY 1101R2578 | 45.401 | 0.96123 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.29307 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.2823 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.27153
39 | MARIPOSA 210237288 | 85.0596 | 0.51222 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.17348 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.16719 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.1609
40 | FROGTOWN 170113412 | 38.7264 | 1.1247 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.46729 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.45695 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.44661
41 | ELECTRA 1101CB | 23.2823 | 1.8561 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.67205 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.40864 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.25399
42 | CORNING 11021622 | 34.8931 | 1.2239 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.45871 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.45397 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.44922
43 | DIAMOND SPRINGS 110676088 | 32.3941 | 1.3064 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.4461 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.43521 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.42433
44 | BONNIE NOOK 1102CB | 26.307 | 1.591 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.65941 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.1548 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.13845
45 | BRUNSWICK 11021010 | 44.5169 | 0.93622 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.31883 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.31547 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.3121
46 | CURTIS 170390320 | 27.8875 | 1.4708 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.50697 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.49825 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.16417
47 | MARIPOSA 210110070 | 25.6959 | 1.5919 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.53412 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.45855 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.18296
48 | GIRVAN 11011330 | 25.3505 | 1.599 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.64206 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.62593 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.19406
49 | APPLE HILL 110413512 | 30.1932 | 1.3349 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.58527 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.5729 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.56054
50 | DIAMOND SPRINGS 11057722 | 61.3393 | 0.65511 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.22977 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.22235 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.21492
51 | BALCH NO 1 1101406582 | 3.6869 | 10.879 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.7206 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.7167 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.7129
52 | MOUNTAIN QUARRIES 21011130 | 19.9683 | 1.9857 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.70472 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.46755 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.31549
53 | APPLE HILL 2102836878 | 40.8623 | 0.96592 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.45542 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.44763 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.43984
54 | COALINGA NO 2 11059260 | 19.4858 | 2.0201 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.96498 | Line removal Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.76234 | Line removal Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.33623
55 | LAYTONVILLE 1101518 | 22.4404 | 1.7333 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.57807 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.5603 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.27559
56 | APPLE HILL 21028372 | 62.5465 | 0.6198 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.24876 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.24487 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.24098
57 | LOS OSITOS 21037014 | 39.714 | 0.97488 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.35262 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.35248 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.35234
58 | STILLWATER 11021466 | 20.2325 | 1.8976 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.7427 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.7237 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.15684
59 | PIT NO 3 21011482 | 12.1426 | 3.0725 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.0054 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.1279 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.11893
60 | GEYSERVILLE 1102904170 | 22.2964 | 1.6592 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.63352 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.62496 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.30519
61 | FORESTHILL 11011802 | 22.1857 | 1.6425 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.69031 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.2623 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.24491
62 | FITCH MOUNTAIN 111324918 | 24.3858 | 1.4937 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.47607 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.45618 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.43629
63 | MARIPOSA 2101439030 | 19.4407 | 1.8555 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.59457 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.57947 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.56436
64 | CLAYTON 221296224 | 7.6873 | 4.6805 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.0245 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.82903 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.8049
65 | PEORIA 170190090 | 29.8564 | 1.2009 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.4519 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.44616 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.44041
66 | HOPLAND 11014626 | 31.1598 | 1.1427 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.41491 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.40107 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.38724
67 | SILVERADO 2104632 | 18.2646 | 1.9481 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.4382 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.416 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.3938
68 | PLACERVILLE 2106935216 | 20.5891 | 1.7218 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.063524 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.045638 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.027752
69 | APPLE HILL 2102186912 | 60.4075 | 0.57824 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.237 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.23313 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.22926
70 | SHADY GLEN 1101941844 | 16.788 | 2.0608 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.88897 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.88164 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.43915
71 | PINE GROVE 1102269286 | 28.1454 | 1.2134 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.57908 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.56799 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.5569
72 | ORO FINO 110239154 | 42.2784 | 0.80618 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.34519 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.33634 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32749
73 | WEST POINT 110234416 | 25.7537 | 1.3166 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.45804 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.4433 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.42855
74 | CEDAR CREEK 1101CB | 48.5703 | 0.69497 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.28183 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.27504 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.26826
75 | SISQUOC 1102M52 | 35.0806 | 0.95235 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.31782 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.30943 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.30105
76 | TEMPLETON 2113641367 | 39.067 | 0.85475 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.31189 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.30637 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.30084
77 | MARIPOSA 21019400 | 60.7782 | 0.54787 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.19955 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.18919 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.18331
78 | FORESTHILL 1102359542 | 18.4759 | 1.7752 | Line removal Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.18549 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.16552 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.14555
79 | CALAVERAS CEMENT 11011419 | 14.8883 | 2.1915 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.79637 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.77541 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.12388
80 | BRUNSWICK 110651486 | 55.8922 | 0.57387 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.20035 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.19354 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.18674
81 | SHINGLE SPRINGS 210913322 | 40.964 | 0.78164 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.254 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.24515 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.2363
82 | PINE GROVE 11013170 | 39.5687 | 0.80874 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.3001 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.2991 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.2981
83 | WEST POINT 110236676 | 16.6413 | 1.9106 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.64503 | Overhead hardening Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.54786 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.13902
84 | APPLE HILL 21021532 | 41.8884 | 0.7505 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32613 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32167 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.31721
85 | CALAVERAS CEMENT 110147968 | 17.114 | 1.7987 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.64775 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.64657 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.10974
86 | WILDWOOD 1101384582 | 4.5387 | 6.7774 | EPSS Vegetation routine patrol Vegetation hazard patrol | 2.149 | EPSS Vegetation routine patrol Vegetation hazard patrol | 2.149 | EPSS Vegetation routine patrol Vegetation hazard patrol | 2.149
87 | SANTA YNEZ 1102320270 | 17.2292 | 1.7837 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.63138 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.61496 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.33783
88 | FRENCH GULCH 11022902 | 7.0229 | 4.3534 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 1.5067 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.72093 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.71733
89 | STANISLAUS 17011812 | 19.1869 | 1.5925 | Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.34503 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.20628 | Overhead hardening Undergrounding Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.0047418
90 | PERRY 110179696 | 32.6472 | 0.93213 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.32075 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.30884 | Pole clearing EPSS Vegetation routine patrol Vegetation hazard patrol | 0.29693