## OEIS Table 6-4
[8 empty] | 14.i | 14.ii | 14.iii | 14.iiii
Circuit, Segment, or Span ID | Initial Overall Utility Risk | 2026 Activities | 2026 Overall Utility Risk | 2027 Activities | 2027 Overall Utility Risk | 2028 Activities | 2028 Overall Utility Risk | Total SUG Miles EOY 2025 | Total CC Miles EOY 2025 | SUG Planned Miles 2026-2028 | CC Planned Miles 2026-2028
1001-1130R | 2758.2829 | ['Drone Inspections'] | 2545.3029 | ['Drone Inspections'] | 2537.5029 | ['Drone Inspections', 'Strategic Pole Replacement'] | 2508.0229 | 8.8769 | 0 | 0 | 0
1001-1140R | 1005.6848 |  |  | ['EFD'] |  | ['Strategic Pole Replacement'] |  | 7.0114 | 0 | 0 | 0
1001-1814AE | 409.2853 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 330.2953 | ['Oh Patrol Inspections', 'Detailed Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 254.4553 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol'] | 91.9653 | 0.17746 | 0 | 0 | 0
1001-1820F | 4222.3431 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3770.9131 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2601.3531 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1740.2031 | 24.7617 | 0 | 0 | 0
1021-1748F | 35156.1557 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 27801.6657 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 22602.7457 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'EFD', 'Pole Brushing'] | 8657.3857 | 8.3489 | 0 | 0 | 0
1021-1760R | 7055.743 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5527.123 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4432.033 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'EFD', 'Pole Brushing'] | 1782.543 | 2.4116 | 0 | 0 | 0
1021-25R | 18825.7719 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 14759.5319 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 12318.4419 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'EFD', 'Pole Brushing'] | 5042.4219 | 0.77235 | 0 | 0 | 0
1021-855 | 5034.3731 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3882.1931 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3209.9931 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1727.6231 | 0.79129 | 0 | 0 | 0
1021-883R | 1386.6863 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 792.2663 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 603.6663 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 280.2463 | 0.1089 | 0 | 0 | 0
1021-92 | 794.4957 | ['Oh Patrol Inspections', 'Detailed Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 514.7157 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 428.8257 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'EFD'] | 161.8657 | 0 | 0 | 0 | 0
1022-17F | 9800.8294 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6510.9494 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'EFD', 'Pole Brushing'] | 3515.5194 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'EFD', 'Strategic Undergrounding'] | 0 | 0.20284 | 0 | 5.5295 | 0
1022-26R | 694.7563 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 398.0063 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 303.8663 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 110.0463 | 0 | 0 | 0 | 0
1022-322R | 5072.2032 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3251.0432 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2570.7632 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'EFD', 'Detailed Inspections', 'Pole Brushing'] | 552.2632 | 0.45587 | 0 | 0 | 0
1023-200R | 2889.9745 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2370.1345 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1585.2345 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1141.1445 | 0.91723 | 0 | 0 | 0
1023-46AE | 9470.024 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Detailed Inspections', 'Pole Brushing'] | 7382.374 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5104.514 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3524.084 | 11.9203 | 0 | 0 | 0
1030-1728R | 5124.295 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4481.915 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 3949.805 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2688.655 | 0 | 0 | 0 | 0
1030-1777 | 11817.629 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8277.829 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 7003.719 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 0.53674 | 0 | 0 | 0
1030-1823F | 2151.0969 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1800.5669 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1541.1069 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1094.2069 | 0.11629 | 0 | 0 | 0
1030-18R | 6620.9092 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5729.2292 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5017.5192 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3764.4392 | 0.026515 | 0 | 4.2258 | 0
1030-20R | 25318.4598 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 20568.1698 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 17359.8598 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 11743.0398 | 0.50871 | 0 | 0 | 0
1030-42R | 28398.8683 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 23144.6283 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 19807.5383 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 13679.1583 | 1.7682 | 0 | 0 | 0
1030-989R | 26696.46 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 23240.31 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 19886.16 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7489.4 | 0.82159 | 0 | 0 | 0
1039-13 | 15957.1707 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 14036.5207 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 11954.2507 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Detailed Inspections', 'Pole Brushing'] | 6924.9807 | 13.3591 | 0 | 0 | 0
1090-73F | 5899.4166 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4012.9566 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3265.4866 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2504.3166 | 5.6197 | 0 | 0 | 0
1090-74F | 4991.252 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3360.692 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2553.822 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1925.132 | 1.8667 | 0 | 0 | 0
1094-35F | 2514.5413 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2204.4113 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1539.5213 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1223.0813 | 10.1386 | 0 | 0 | 0
1100-1172R | 2145.2734 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1835.9034 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1424.9834 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1119.5834 | 0.31686 | 0 | 0 | 0
1105-1479 | 4228.127 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3665.977 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3064.267 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2498.067 | 0.050379 | 0 | 0 | 0
1105-1483 | 417.0004 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 364.4904 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 269.2704 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 162.8404 | 1.2271 | 0 | 0 | 0
1118-1718F | 788.3799 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 692.4199 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 319.7499 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 218.9199 | 0.027652 | 0 | 0 | 0
1166-15R | 3965.2333 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3150.5533 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1975.9133 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1416.7933 | 1.2189 | 0 | 0 | 0
1166-18R | 10108.5696 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7501.2296 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4159.2896 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 0.069318 | 0 | 9.2248 | 0
1166-342R | 10322.7394 | ['Oh Patrol Inspections', 'Fuel Management', 'Traditional Hardening', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Detailed Inspections', 'Pole Brushing'] | 5878.9694 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4241.7494 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2859.3794 | 0.74886 | 0 | 0 | 0
1215-12R | 6147.3096 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5348.8896 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3721.3696 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2921.8496 | 10.5725 | 0 | 0 | 0
1215-28R | 2215.3076 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1936.1776 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1572.9376 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 794.0276 | 0.37973 | 0 | 0 | 0
1215-32R | 8696.6047 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7565.2847 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6385.2047 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3235.6747 | 0.097538 | 0 | 0 | 0
1233-585R | 3562.0081 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3084.4981 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2599.2481 | ['Oh Patrol Inspections', 'Covered Conductor', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 81.2981 | 0.10701 | 6.3138 | 0 | 6.3138
1233-591R | 4300.3764 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3744.4164 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3194.8364 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2028.0164 | 0.36894 | 6.5537 | 0 | 0
1250-27R | 6418.5188 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 6179.3188 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol'] | 5893.2788 | ['Drone Inspections', 'Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 5592.8888 | 13.3644 | 0 | 0 | 0
1250-671R | 6815.4887 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6112.4287 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5136.5487 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4355.9887 | 15.1044 | 0 | 0 | 0
1250-677R | 11749.1247 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9935.4547 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7742.1147 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6273.1347 | 2.1004 | 0 | 0 | 0
1250-8R | 3685.1269 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3216.3269 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2562.4569 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2165.7469 | 0.071591 | 0 | 0 | 0
1458-1056 | 427.4459 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 262.7259 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 211.6959 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 165.1459 | 0.43314 | 0 | 0 | 0
1458-1058F | 2365.8707 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1635.3207 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1331.7807 | ['Oh Patrol Inspections', 'Covered Conductor', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 151.5607 | 7.997 | 0 | 0 | 1.4878
1458-1061 | 4370.0973 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2988.8573 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2459.9373 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1951.4473 | 0.96023 | 0 | 0 | 0
1458-1131R | 15987.5823 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 14357.1223 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 12634.5523 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 10921.5423 | 3.4466 | 0 | 0 | 0
1458-565R | 8159.9882 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 7205.0582 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4004.6882 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2757.8582 | 0.37538 | 0 | 0 | 0
1458-601R | 37077.3007 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 27720.5407 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 21543.3907 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 16852.2307 | 1.9023 | 0 | 0 | 0
157-1928R | 3052.6796 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1821.5296 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1401.0796 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 973.3496 | 0.25644 | 1.7983 | 0 | 0
157-81R | 18749.6613 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 12082.4413 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9648.9513 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6640.3513 | 1.8644 | 4.796 | 0 | 0
175-2024R | 4029.1638 | ['Oh Patrol Inspections', 'Fuel Management', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 3352.3138 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2458.7338 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1018.3138 | 0.28182 | 0 | 0 | 0
175-24R | 2651.6338 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2455.6138 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2158.5638 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1530.8738 | 20.154 | 0 | 0 | 0
176-161R | 11523.41 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 10125.17 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8750.73 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Detailed Inspections', 'Strategic Undergrounding'] | 0 | 1.2981 | 0 | 11.8819 | 0
176-164R | 4185.0256 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2461.7856 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1908.0156 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1309.4256 | 1.0172 | 0 | 0 | 0
176-1834R | 10068.6139 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8936.7339 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7457.1939 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3664.1839 | 8.9538 | 4.6009 | 0 | 0
176-194R | 4934.4724 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4399.5724 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3827.2924 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'EFD', 'Detailed Inspections', 'Pole Brushing'] | 1211.7624 | 0.53182 | 2.5445 | 0 | 0
176-197F | 13173.0595 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8889.2795 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7424.1295 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5760.7395 | 8.6375 | 0.34583 | 0 | 0
176-200F | 1636.1529 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1066.0429 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 878.9129 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 611.1329 | 2.7852 | 0 | 0 | 0
177-955 | 2963.4048 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2882.6748 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2779.5648 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2665.9648 | 25.8081 | 0 | 0 | 0
182-2240F | 11917.5043 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 10820.2243 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7724.5443 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6502.3943 | 21.2875 | 0 | 0 | 0
182-2250 | 1939.314 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1615.234 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 612.474 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 318.464 | 0.29167 | 0 | 0 | 0
182-2252R | 4230.0465 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3717.9765 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2335.4365 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1807.3965 | 0.1375 | 0 | 0 | 0
182-2254R | 655.8033 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 575.8433 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 461.5133 | ['Oh Patrol Inspections', 'Detailed Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 174.4633 | 0.036932 | 0 | 0 | 0
214-1122R | 26281.2903 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 20566.6503 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 17250.5803 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 12249.6203 | 1.4316 | 0 | 0 | 0
214-1135R | 6667.1927 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5545.6027 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4588.1927 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2260.9927 | 0.58523 | 0 | 0 | 0
214-647R | 22354.3127 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 19847.7627 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 17268.9827 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 13352.6727 | 0.18655 | 0 | 0 | 0
215-1531R | 12702.421 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 11207.891 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9479.331 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6853.461 | 3.2294 | 0 | 10.2795 | 0
215-1534R | 19489.7214 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 13758.4314 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 11274.1914 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7351.9114 | 2.621 | 0 | 9.5237 | 0
215-1544R | 1412.5344 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1235.9644 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 999.2144 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 733.1744 | 1.625 | 0 | 0 | 0
215-38R | 5435.0248 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4337.4148 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3602.3348 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2521.2248 | 2.9913 | 0 | 7.8141 | 0
216-1859F | 14041.3097 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9430.1497 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7797.7097 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5160.7897 | 0.65284 | 0 | 0 | 0
217-835R | 10687.0531 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9168.0831 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7732.0131 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5865.7431 | 0.32879 | 0 | 22.2581 | 0
217-983R | 10117.0409 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8771.6709 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7416.7809 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4056.2109 | 15.8763 | 0 | 0 | 0
221-1230F | 3691.0949 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3353.7549 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3007.9949 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2653.5849 | 0.044508 | 0 | 0 | 0
221-35 | 710.3466 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 503.1366 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 406.6566 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 307.7466 | 0 | 0 | 0 | 0
221-37AE | 3934.7814 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3565.3814 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3138.5114 | ['Oh Patrol Inspections', 'Fuel Management', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 2709.6314 | 0.24924 | 0 | 0 | 0
221-6R | 3904.3307 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2690.4407 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2194.7107 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1686.6007 | 0 | 0 | 0 | 0
221-788 | 4482.1315 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3851.3815 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3306.2115 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2747.4115 | 0.094697 | 0 | 0 | 0
221-824 | 2324.2798 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2094.3798 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1852.2898 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1614.2798 | 0.13371 | 0 | 0 | 0
222-1433R | 9618.1626 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8440.9226 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6812.7226 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5581.6126 | 0.067235 | 0 | 0 | 0
222-1503R | 1359.4185 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1214.5585 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1071.8585 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 909.6485 | 0.84129 | 0 | 0 | 0
222-1523R | 7406.8447 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6645.0647 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5843.2347 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4936.6647 | 9.1911 | 0 | 0 | 0
222-1986R | 79194.5961 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 69554.2061 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 59786.8061 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 49495.0761 | 20.8909 | 0 | 0 | 0
222-1988R | 3619.6476 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 3161.3376 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2691.5776 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2144.7676 | 1.8712 | 0 | 0 | 0
222-1990R | 45106.6656 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 39578.9756 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 33949.1656 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 27695.5556 | 1.9527 | 0.49564 | 0 | 0
222-2013R | 7427.1 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6663.18 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5858.79 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5016.15 | 6.7271 | 0 | 0 | 0
222-2063 | 4859.8395 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 4238.4195 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 3601.4795 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2948.5995 | 0 | 0 | 0 | 0
222-2085 | 16772.4524 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 15194.1224 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 13511.1924 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 11763.7724 | 18.7693 | 0 | 0 | 0
230-133AE | 6388.7164 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5685.8564 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3661.5464 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2978.5364 | 2.8769 | 0 | 0 | 0
235-897R | 4375.1884 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3321.3684 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2905.8684 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2512.1684 | 3.6699 | 0 | 0 | 0
235-899R | 23678.7817 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 17810.9717 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 15479.9717 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 12597.5417 | 3.0087 | 0 | 0 | 0
236-1535R | 9719.0446 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6776.8946 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5615.3946 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4256.2146 | 0.91193 | 0 | 0 | 0
236-1561R | 2823.8282 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1985.1582 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1688.2082 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1339.2282 | 0 | 0 | 0 | 0
236-1563R | 2260.6644 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1432.1044 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1162.3344 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 884.8544 | 0.023295 | 0 | 0 | 0
236-1567R | 5332.0274 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4371.0674 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3797.1274 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3138.6874 | 1.8373 | 0 | 0 | 0
236-1569R | 21222.9889 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 17178.4589 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 14787.8789 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 12006.6389 | 1.9712 | 0 | 0 | 0
236-1573R | 6928.1303 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6227.0203 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5486.8603 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4594.5903 | 1.8814 | 0 | 0 | 0
237-1761R | 3634.2785 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3163.2685 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2682.8685 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2181.4985 | 0.089015 | 0 | 0 | 0
237-1765R | 28249.2525 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 22421.0525 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 19140.6925 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 15812.7725 | 0.9053 | 0 | 0 | 0
237-17R | 27080.9145 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 22138.2945 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 19313.8745 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 16376.0745 | 1.793 | 0 | 0 | 0
237-28F | 2530.295 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2287.665 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2066.815 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1774.255 | 1.4521 | 0 | 0 | 0
237-2R | 30894.2514 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 27623.0114 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 24226.7414 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 20289.6414 | 6.3508 | 0 | 0 | 0
237-30R | 65515.4913 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 56580.3413 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 48290.3113 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 8.1388 | 1.3013 | 0 | 0
239-2211R | 1585.2372 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1284.1272 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1075.0572 | ['Oh Patrol Inspections', 'Covered Conductor', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 17.0672 | 0 | 0 | 0 | 0
239-2215R | 6268.7625 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5441.0825 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4523.2425 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3305.2825 | 0.51629 | 0 | 0 | 0
283-55R | 5299.6597 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3611.6597 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2394.3597 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1580.5797 | 1.5826 | 0 | 0 | 0
307-1538F | 2407.2331 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1895.9131 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1169.4931 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 711.5731 | 17.518 | 0 | 0 | 0
307-234R | 4762.8858 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3362.2758 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2561.3458 | ['Oh Patrol Inspections', 'Fuel Management', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 1964.6358 | 18.0189 | 0 | 0 | 0
350-2182R | 302.6131 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 271.0131 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 232.5431 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 197.2031 | 0 | 0 | 0 | 0
350-2201R | 13521.8125 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 10592.1125 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8927.7125 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6201.3625 | 2.8568 | 0 | 0 | 0
350-41R | 11201.4899 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7221.6799 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5430.9799 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3083.4999 | 2.7699 | 0 | 0 | 0
351-819R | 23517.5211 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 19939.3511 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 16980.7911 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9543.3411 | 1.7996 | 0 | 12.7459 | 0
351-871R | 9144.336 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6655.316 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5468.106 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3421.796 | 0.029167 | 0 | 5.0315 | 0
352-27R | 18614.484 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'EFD', 'Detailed Inspections', 'Pole Brushing'] | 10843.994 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'EFD', 'Pole Brushing'] | 4824.054 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 528.564 | 1.9824 | 0 | 0 | 0
353-1429R | 9221.9518 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6541.5018 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5485.8718 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3291.4318 | 15.6487 | 0 | 0 | 0
353-593F | 2519.2688 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2122.3288 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1651.2488 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1181.8288 | 0.58125 | 0 | 0 | 0
353-594F | 2215.7067 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1815.3467 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1458.9767 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 921.0667 | 0.065909 | 0 | 0 | 0
353-900F | 1991.3557 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1304.0657 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1063.4857 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 670.8557 | 7.7138 | 0 | 0 | 0
353-901F | 4555.8093 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3461.4093 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2834.4493 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1997.2093 | 13.6441 | 0 | 0 | 0
353-902F | 465.3438 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 339.5038 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 275.2938 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 214.3438 | 7.743 | 0 | 0 | 0
353-904R | 13534.6152 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 10317.5552 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8405.2852 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5171.6552 | 2.2737 | 0 | 0 | 0
354-1706R | 20510.3916 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 18212.8016 | ['Oh Patrol Inspections', 'Fuel Management', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 14908.8316 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 10834.2416 | 4.8697 | 0 | 0 | 0
354-24AE | 3653.9042 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3134.5642 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2649.5942 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2039.4142 | 10.4907 | 0 | 0 | 0
355-41R | 7500.5846 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5451.5546 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4485.5746 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3637.1246 | 2.4867 | 0 | 0 | 0
355-6R | 1698.8021 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1280.7521 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1129.5621 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 996.5521 | 2.2172 | 0 | 0 | 0
356-16R | 5437.676 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4236.776 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3517.696 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2966.966 | 3.6555 | 0 | 0 | 0
356-19R | 16012.7866 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 13506.3766 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9945.7866 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8160.3266 | 7.9608 | 0 | 0 | 0
357-1147R | 1251.3309 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 940.7309 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 820.6109 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 707.1509 | 0 | 0 | 0 | 0
357-1299R | 5098.8469 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4433.5369 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2327.2569 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1618.3369 | 0.10985 | 0 | 0 | 0
357-2047F | 879.114 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 655.974 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 562.604 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 417.644 | 1.403 | 0 | 0 | 0
357-2049F | 16869.8437 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 12761.2837 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 10969.0537 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 0.84583 | 0 | 6.83 | 0
357-45R | 17696.8639 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 13115.6939 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9954.7039 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 8.3477 | 0 | 0 | 0
357-50R | 10432.7133 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8352.7233 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6207.3933 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4981.5333 | 7.1004 | 0 | 0 | 0
357-750R | 11757.9126 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8254.8526 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6403.1826 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4839.2626 | 5.7292 | 0 | 0 | 0
358-1175F | 599.8394 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 515.0794 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 436.6594 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 390.9194 | 0.17102 | 0 | 0 | 0
358-33 | 1344.7325 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1175.9625 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1002.9825 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 825.6925 | 0.8642 | 0 | 0 | 0
358-682F | 37602.2054 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 33799.6454 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 27688.8754 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 23347.7754 | 1.2089 | 0 | 12.7019 | 0
441-23R | 3518.1774 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3049.6374 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1848.1274 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1315.1574 | 2.0002 | 0 | 0 | 0
441-27R | 4750.293 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4053.583 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3106.653 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2462.133 | 0.15473 | 0 | 0 | 0
441-30R | 5349.1155 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4636.9355 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2443.6455 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1464.9655 | 0.54205 | 0 | 0 | 0
442-728R | 11572.3746 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 10362.6646 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8712.5346 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7739.8246 | 4.5034 | 0 | 0 | 0
442-758F | 550.1247 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 471.1447 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 390.1947 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 307.2247 | 0.0094697 | 0 | 0 | 0
445-1311R | 9632.593 | ['Oh Patrol Inspections', 'Fuel Management', 'Traditional Hardening', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Detailed Inspections', 'Pole Brushing'] | 8140.793 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5628.253 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4240.753 | 0.83049 | 0 | 0 | 0
445-1325F | 7250.7936 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6367.7336 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4527.4836 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2443.3936 | 6.8905 | 2.8985 | 0 | 0
445-897R | 1352.0041 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1175.8941 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 803.1441 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 488.3041 | 0.41799 | 0 | 0 | 0
449-16R | 1495.543 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1295.503 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 789.033 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 589.293 | 0.11742 | 0 | 0 | 0
449-693R | 5260.7035 | ['Oh Patrol Inspections', 'Fuel Management', 'Traditional Hardening', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 4394.4235 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2764.2835 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2045.7035 | 0.055492 | 0 | 0 | 0
450-1850 | 296.9434 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 266.4334 | ['Drone Inspections', 'Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 215.6334 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections'] | 79.4434 | 0.035985 | 0 | 0 | 0
450-1851F | 8274.1289 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7245.7089 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6071.0789 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2979.3989 | 0.57216 | 0 | 0 | 0
450-1853F | 792.2023 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 731.9523 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 565.9423 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 291.2923 | 2.2973 | 0 | 0 | 0
450-1854 | 1132.5433 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1002.5833 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 718.1632 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 295.5733 | 0.25114 | 0 | 0 | 0
450-50R | 537.0727 | ['Drone Inspections', 'Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 514.0927 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 505.3127 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections'] | 475.9327 | 8.3117 | 0 | 0 | 0
452-1404F | 625.6531 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 551.9831 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol'] | 422.3031 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections'] | 76.3931 | 0.22955 | 0 | 0 | 0
452-38AE | 2823.8867 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2394.5167 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2027.0467 | ['Oh Patrol Inspections', 'Covered Conductor', 'Wood Pole Intrusive', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Detailed Inspections', 'Pole Brushing'] | 0 | 6.828 | 0 | 3.3602 | 2.8002
454-48F | 3441.2436 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 3063.6936 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2676.7336 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 844.7436 | 0.11212 | 0 | 0 | 0
470-40AE | 5265.3206 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4544.3706 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1871.9206 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1077.2806 | 6.2625 | 0 | 0 | 0
470-47R | 16740.5965 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 13573.4065 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9038.0965 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6735.0465 | 1.7297 | 0 | 0 | 0
471-36F | 4253.7501 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4035.9701 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3724.9801 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3513.2701 | 7.2398 | 0 | 0 | 0
500-1531 | 800.6942 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 776.0642 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 737.3542 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 670.9742 | 29.3417 | 0 | 0 | 0
520-1527R | 6763.0022 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5868.0522 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4990.7622 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4116.1522 | 3.2477 | 0 | 0 | 0
521-14R | 11350.3196 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8680.0296 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7044.6196 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5444.4696 | 6.0693 | 0 | 0 | 0
521-1856R | 8478.0066 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6688.7366 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5519.2966 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4396.8766 | 3.5246 | 0 | 0 | 0
521-18R | 8713.0776 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7237.0676 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4561.7476 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2769.4176 | 5.5864 | 0 | 0 | 0
521-27R | 5618.7355 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4373.5555 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3352.3755 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2642.1155 | 3.2833 | 0 | 0 | 0
521-32R | 12241.7968 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 10736.5268 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9196.6668 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7123.9168 | 0.30284 | 0 | 0 | 0
521-700R | 9012.7998 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7708.9798 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5663.0198 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4433.5198 | 5.4576 | 0 | 0 | 0
524-1782F | 5468.3294 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3602.7894 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2804.7694 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1988.0694 | 0.75455 | 0 | 0 | 0
524-27R | 11317.9478 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8067.6578 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6725.0678 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5355.0478 | 1.9866 | 0 | 0 | 0
524-46R | 13711.0428 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8899.8128 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7109.8428 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5095.3828 | 1.2189 | 0 | 0 | 0
524-50R | 8802.0067 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5890.1167 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4692.1267 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3453.5467 | 0.60644 | 0.36837 | 0 | 0
524-69R | 40375.4804 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 26637.4004 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 20655.4104 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 14736.0704 | 2.5879 | 0 | 0 | 0
540-241R | 833.767 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 764.297 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 693.097 | ['Oh Patrol Inspections', 'Detailed Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 443.737 | 6.296 | 0 | 0 | 0
597-595 | 18774.532 | ['Oh Patrol Inspections', 'Fuel Management', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 16012.142 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8073.542 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4759.212 | 25.7814 | 0 | 0 | 0
599-19R | 25743.5797 | ['Oh Patrol Inspections', 'Fuel Management', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 21888.4497 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 11243.8897 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6840.8297 | 4.5947 | 0 | 0 | 0
73-1130R | 6201.8595 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4682.9795 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3470.7995 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2709.2795 | 0.32064 | 6.0741 | 0 | 0
73-1163 | 15337.4275 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 13634.5475 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 10659.9475 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8919.7075 | 2.1504 | 0 | 0 | 0
73-1164 | 2448.8919 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2176.0019 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1880.2819 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1607.5019 | 0.67708 | 0 | 0 | 0
73-23R | 5733.8945 | ['Oh Patrol Inspections', 'Covered Conductor', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Detailed Inspections', 'Pole Brushing'] | 3652.7945 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2976.7345 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2235.8245 | 0.40644 | 4.3405 | 0 | 8.3244
73-678R | 10591.5904 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9308.9004 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7963.7304 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6468.2604 | 1.6634 | 0 | 0 | 0
73-683R | 9288.0332 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8215.6432 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7100.6132 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5915.8732 | 3.4025 | 0 | 0 | 0
75-2259F | 3135.6491 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2048.6791 | ['Oh Patrol Inspections', 'Fuel Management', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 1602.7691 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1200.4291 | 2.1494 | 0 | 0 | 0
75-32R | 1708.5067 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1087.8367 | ['Oh Patrol Inspections', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 829.9667 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 551.0267 | 2.2428 | 0 | 0 | 0
75-41 | 1937.8205 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1228.1905 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 965.6205 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 692.9305 | 0.31136 | 0 | 0 | 0
78-26R | 14526.8543 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 12955.9143 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 11155.5743 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9382.3443 | 8.0005 | 1.3648 | 0 | 0
78-35R | 5696.5099 | ['Drone Inspections', 'Oh Patrol Inspections', 'Pole Brushing'] | 4995.9799 | ['Drone Inspections', 'Oh Patrol Inspections', 'Pole Brushing'] | 4277.9299 | ['Drone Inspections', 'Oh Patrol Inspections', 'Pole Brushing', 'Detailed Inspections'] | 2069.9699 | 1.8616 | 0 | 0 | 0
78-782R | 7202.337 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 6269.577 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 5313.487 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4327.567 | 0.06553 | 0 | 0 | 0
788-34R | 9132.5262 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8554.2162 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7638.5362 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6527.2462 | 11.7979 | 0 | 0 | 0
79-658R | 12321.1285 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 10770.0485 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7038.4685 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4945.8985 | 0.17822 | 0 | 0 | 0
79-676R | 9714.1692 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8788.0692 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6886.6492 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5895.7192 | 0.07197 | 0 | 0 | 0
79-679R | 18448.7952 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 16558.7052 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 14193.5452 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 0.35038 | 0 | 7.3941 | 0
79-685R | 2564.9365 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2246.8665 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1899.8365 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1554.8865 | 0 | 0 | 0 | 0
79-714R | 5536.6483 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5032.0883 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3540.0583 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3009.9483 | 0.1036 | 0 | 0 | 0
79-785 | 18781.0203 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 17096.2203 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 12248.5303 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 10449.9303 | 0.40284 | 0 | 0 | 0
79-808R | 19978.4816 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 17544.9116 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 12806.2116 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9543.2516 | 0.052652 | 0 | 0 | 0
791-419F | 3349.9192 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3120.1892 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2695.9392 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2454.5692 | 7.4222 | 0 | 0 | 0
855-46AE | 188.4192 | ['Oh Patrol Inspections', 'Pole Brushing', 'Off Cycle Patrol'] | 165.2592 | ['Oh Patrol Inspections', 'Pole Brushing', 'Wood Pole Intrusive', 'Off Cycle Patrol'] | 127.3792 | ['Oh Patrol Inspections', 'Pole Brushing', 'Detailed Inspections', 'Off Cycle Patrol'] | 44.2192 | 19.5705 | 0 | 0 | 0
859-42R | 8607.1404 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7538.7004 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6652.5404 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6004.6304 | 12.7456 | 0 | 0 | 0
907-1562AE | 8439.9356 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7376.8656 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6191.9056 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4521.0056 | 13.5258 | 0 | 0 | 0
907-1702R | 9100.5575 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7533.9075 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6269.8675 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4401.6975 | 0.9108 | 0 | 0 | 0
907-1716R | 27066.6734 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 22294.7634 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 18703.0734 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 13560.4634 | 25.8888 | 0 | 0 | 0
907-2820R | 6348.6381 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 5581.7481 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 4795.7081 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3632.7281 | 0 | 0 | 0 | 0
908-1172R | 15766.7747 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 13451.4447 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 11265.3047 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8192.5047 | 5.6466 | 0 | 12.3657 | 0
908-1236 | 11763.9322 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7892.7322 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6292.7522 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1514.5922 | 2.0511 | 0 | 0 | 0
908-1372R | 7960.2905 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5247.0005 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3997.8605 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Pole Brushing', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Strategic Undergrounding'] | 0 | 3.786 | 0 | 0 | 0
908-2038R | 41258.5836 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 28069.8936 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 22349.5136 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 15288.2836 | 7.4161 | 0 | 0 | 0
908-2040 | 3646.8116 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3200.8116 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2761.8316 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2107.2416 | 10.0477 | 0 | 0 | 0
908-2055F | 22564.0753 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 16780.1853 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 13948.0053 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9338.6553 | 1.1496 | 0 | 14.0213 | 0
908-30 | 847.7134 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 739.3734 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 593.9134 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 445.5034 | 0.2392 | 0 | 0 | 0
909-451 | 55252.7007 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 36496.0607 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 28693.4907 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 3.9883 | 0 | 0 | 0
909-453R | 5703.3814 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections'] | 5196.3014 | ['Drone Inspections', 'Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 4760.5914 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol'] | 4203.0714 | 0.050947 | 0 | 0 | 0
909-805R | 32313.2432 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 25076.9532 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 20572.8432 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 12762.4132 | 0.91383 | 0 | 0 | 0
920-1342R | 3406.8363 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2916.6963 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1577.0463 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'EFD', 'Detailed Inspections', 'Pole Brushing'] | 349.9363 | 0.32765 | 0 | 0 | 0
970-1341R | 12961.791 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 11351.381 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9914.611 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8153.541 | 1.6523 | 0 | 0 | 0
971-1973R | 15149.1723 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 10970.9923 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9235.3223 | ['Oh Patrol Inspections', 'Fuel Management', 'Strategic Pole Replacement', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 7044.0523 | 0.5678 | 0 | 0 | 0
971-2050R | 28484.8715 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 21002.8315 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 17548.4015 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 13716.0515 | 4.7417 | 0 | 0 | 0
971-29R | 8015.5632 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5118.7332 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4126.2432 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2823.9932 | 3.6604 | 0 | 0 | 0
971-371R | 4351.5692 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2681.6892 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2130.2292 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1560.7592 | 0.073485 | 0 | 0 | 0
971-383R | 14770.6432 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9766.2732 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7691.6532 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5636.7532 | 9.2106 | 0 | 0 | 0
971-388R | 11268.0706 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9924.1706 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8546.7006 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 7006.1106 | 0.76629 | 0 | 0 | 0
972-1582R | 8019.3586 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4934.7186 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3943.0786 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2917.1786 | 7.3564 | 4.7076 | 0 | 0
972-1590F | 23409.1528 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 15945.9628 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 13108.8928 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 10283.4628 | 2.4282 | 0 | 0 | 0
972-32R | 22914.3321 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 15150.7021 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 12293.9921 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9190.4621 | 4.0339 | 0 | 0 | 0
972-942R | 9149.7215 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5894.5915 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4824.1315 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3578.7115 | 0.99659 | 0.83258 | 0 | 0
973-1226R | 5177.8713 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4136.6413 | ['Oh Patrol Inspections', 'Covered Conductor', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 549.2913 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 0 | 7.6638 | 0 | 0 | 8.59
973-1245R | 8620.4197 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7393.6897 | ['Oh Patrol Inspections', 'Covered Conductor', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3303.5797 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1696.8297 | 4.592 | 0 | 0 | 3.3857
973-626R | 6521.8348 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5521.3148 | ['Oh Patrol Inspections', 'Covered Conductor', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 817.0648 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 0 | 4.7083 | 0 | 0 | 11.0435
974-715R | 7107.3384 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6176.6984 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5043.2784 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4082.0184 | 1.4203 | 0 | 0 | 0
975-22R | 6417.0689 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5927.6289 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5425.9589 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4911.7589 | 21.2085 | 0 | 0 | 0
991-1 | 627.141 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 567.901 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 439.541 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 377.271 | 6.7294 | 0 | 0 | 0
991-1206R | 4576.8822 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 3985.4922 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2068.3822 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 812.2322 | 0.26894 | 0 | 0 | 0
CB 1023 | 3332.7416 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2913.9516 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 2562.6716 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2057.9616 | 1.032 | 0 | 0 | 0
CB 1106 | 1647.1008 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1571.3108 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1424.3908 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1329.9408 | 20.0523 | 0 | 0 | 0
CB 1250 | 4075.5104 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'EFD', 'Pole Brushing'] | 2878.0004 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2321.7604 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1765.3104 | 0.081439 | 0 | 0 | 0
CB 236 | 12711.4327 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9890.4727 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8674.6027 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 3.1932 | 0 | 7.6831 | 0
CB 237 | 2111.5925 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1836.2525 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 1694.6025 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1533.3825 | 0 | 0 | 0 | 0
CB 327 | 1456.7995 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1254.9695 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'EFD', 'Pole Brushing'] | 687.0995 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 57.3695 | 0.028977 | 0 | 0 | 0
CB 351 | 14599.8727 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 10699.9327 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 9034.2427 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Pole Brushing', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Strategic Undergrounding'] | 0 | 1.1619 | 0 | 7.8789 | 0
CB 355 | 11288.5503 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 8463.0203 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 6805.0103 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 2.2837 | 0 | 0 | 0
CB 357 | 6111.0634 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 4588.7234 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3569.0134 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2819.0434 | 7.7886 | 0 | 0 | 0
CB 358 | 861.5446 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 837.9646 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 823.2346 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 805.7246 | 11.3629 | 0 | 0 | 0
CB 470 | 6922.0497 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6561.2597 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 5913.6797 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5577.9597 | 11.8992 | 0 | 0 | 0
CB 576 | 417.8079 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 379.6479 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 331.3179 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 295.4279 | 8.6784 | 0 | 0 | 0
CB 907 | 2742.335 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2360.265 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2021.325 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1354.225 | 0.55436 | 0 | 0 | 0
CB 971 | 11456.9173 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 7909.9173 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6661.6773 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 0.25189 | 0 | 6.2061 | 0
CB 975 | 1304.4828 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1097.6728 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 921.6228 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 741.1728 | 0.40417 | 0 | 0 | 0
CB JU1 | 1531.8936 | ['Oh Patrol Inspections', 'Traditional Hardening', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1211.6736 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1026.3036 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 830.4536 | 0.55587 | 0 | 0 | 0
CB MOR1 | 5119.8406 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3441.7906 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2782.0606 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1997.1406 | 1.7284 | 0 | 0 | 0
CB OK1 | 6915.8867 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5871.8167 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5039.2267 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4178.6267 | 0.050758 | 0 | 0 | 0
CB RA1 | 10517.1513 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 9104.6712 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8017.7413 | ['Oh Patrol Inspections', 'Fuel Management', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Strategic Undergrounding'] | 0 | 1.2809 | 0 | 0 | 0
CB RA2 | 5230.1212 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 3875.1712 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3387.2712 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2849.6712 | 0.072727 | 0 | 0 | 0
CB RC1 | 3739.8767 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3283.8667 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2686.3167 | ['Oh Patrol Inspections', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 1389.0967 | 0 | 0 | 0 | 0
CB SL1 | 3361.7756 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2913.1956 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2427.0256 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1958.7956 | 8.4797 | 0 | 0 | 0
DV1-3R | 3719.4994 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2457.6494 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2020.7794 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 1470.3494 | 3.0015 | 0 | 0 | 0
RA1-402R | 9339.3968 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 8425.8868 | ['Oh Patrol Inspections', 'Pole Brushing', 'Veg Detail Inspections', 'Off Cycle Patrol'] | 7542.3568 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6514.6668 | 0.86458 | 0 | 0 | 0
RB1-427R | 6920.1275 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 6004.7175 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'EFD', 'Pole Brushing'] | 4013.5375 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Detailed Inspections', 'Pole Brushing'] | 2849.8975 | 0.47197 | 0 | 0 | 0
RB1-433R | 5946.7314 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 5177.7714 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 4391.8514 | ['Oh Patrol Inspections', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3207.5614 | 1.264 | 0 | 0 | 0
TM1-10R | 3782.9419 | ['Oh Patrol Inspections', 'Fuel Management', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 3318.5219 | ['Oh Patrol Inspections', 'Veg Detail Inspections', 'Drone Inspections', 'Off Cycle Patrol', 'Pole Brushing'] | 2855.5819 | ['Oh Patrol Inspections', 'Covered Conductor', 'Fuel Management', 'Wood Pole Intrusive', 'Veg Detail Inspections', 'Off Cycle Patrol', 'Drone Inspections', 'Pole Brushing'] | 126.1419 | 0.16023 | 0 | 4.1192 | 3.4327