## GH-04 Workplan 2026-28
PG&E 2026-28 Undergrounding Workplan (GH-04)
Data as of March 31, 2025
[14 empty] | 0.02579% |  | 0.001824% |  | 0.009621% |  |  | Total | 23.9 | 23.9 | 0 | 0
Circuit Protection Zone | Order | Category | MAT Code | SAP Status | Status | Division | Region | City | County | Latitude | Longitude | Applicable Risk Model | Risk Rank (V2) | Est. Wildfire Risk Reduction (V2) | Risk Rank (V3) | Est. Wildfire Risk Reduction (V3) | Risk Rank (V4) | Est. Wildfire Risk Reduction (V4) | HFTD Tier | Start Year | End Year | Total Planned UG Miles | 2026 Forecast UG Miles | 2027 Forecast UG Miles | 2028 Forecast UG Miles
| 35544699 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 6.7974e-07 | 120 | 2.1256e-05 | 108 | 1.5308e-05 | Tier 3 | 2026 | 2026 | 0.2 | 0.2 | 0 | 0
| 35544720 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 1.8179e-06 | 120 | 5.9001e-05 | 108 | 2.0874e-05 | Tier 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35544721 | SH | 08W | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 1.4736e-06 | 120 | 4.7144e-05 | 108 | 2.0178e-05 | Tier 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35544722 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 1.3119e-06 | 120 | 4.2176e-05 | 108 | 2.0874e-05 | Tier 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35544723 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 3.0187e-06 | 120 | 9.4654e-05 | 108 | 5.2185e-05 | Tier 3 | 2026 | 2026 | 0.8 | 0.8 | 0 | 0
| 35544724 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 4.3495e-06 | 120 | 0.00013621 | 108 | 0.00011829 | Tier 3 | 2026 | 2026 | 1.7 | 1.7 | 0 | 0
| 35522102 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 1.7506e-06 | 120 | 5.5611e-05 | 108 | 5.9143e-05 | Tier 3 | 2026 | 2026 | 0.8 | 0.9 | 0 | 0
| 35448810 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Alleghany | SIERRA |  |  | v3 | 1700 | 4.5199e-06 | 41 | 0.00022565 | 58 | 0.000368 | Tier 3 | 2026 | 2026 | 2.6 | 2.6 | 0 | 0
| 35231621 | SH | 08W | PEND | Estimating | Humboldt | Region 1 - North Coast | Clearlake | LAKE |  |  | v2 | 27 | 0.0001793 | 29 | 0.00050297 | 85 | 0.00031123 | Tier 2 & 3 | 2026 | 2026 | 2.9 | 2.9 | 0 | 0
| 35231620 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Clearlake | LAKE |  |  | v2 | 27 | 4.3999e-07 | 29 | 1.2342e-06 | 85 | 0.00028862 | Tier 2 & 3 | 2026 | 2026 | 2.7 | 2.7 | 0 | 0
| 35404352 | SH | 3UG | PEND | Permitting/Dependency | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 1254 | 2.3023e-05 | 101 | 0.00018102 | 152 | 0.000109 | Tier 3 | 2025 | 2026 | 1.4 | 1.4 | 0 | 0
| 35539107 | SH | 3UG | PEND | Estimating | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 2810 | 1.2081e-07 | 98 | 0.00010265 | 268 | 7.2749e-05 | Tier 3 | 2025 | 2026 | 1.6 | 1.6 | 0 | 0
| 35473990 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 3.7623e-05 | 58 | 0.00022315 | 179 | 0.00022699 | Tier 3 | 2026 | 2026 | 3.2 | 3.2 | 0 | 0
| 35278890 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | v2 | 163 | 0.00014933 | 569 | 4.9521e-05 | 458 | 4.7284e-06 | Tier 2 | 2026 | 2026 | 0.1 | 0.1 | 0 | 0
| 35519776 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 844 | 5.0742e-05 | 76 | 0.00030721 | 431 | 6.3412e-06 | Tier 2 | 2026 | 2026 | 0.2 | 0.2 | 0 | 0
| 35547351 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 844 | 4.8944e-05 | 76 | 0.00028776 | 431 | 8.4126e-05 | Tier 2 | 2025 | 2026 | 2 | 2 | 0 | 0
| 35523414 | SH | 3UG | PEND | Estimating | Kern | Region 5 - Central Valley | Lebec | KERN |  |  | v3 | 583 | 7.3036e-05 | 219 | 0.00010574 | 239 | 0.00010368 | Tier 2 | 2026 | 2026 | 2.1 | 2.1 | 0 | 0
| 35519782 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Oroville | BUTTE |  |  | v3 | 1246 | 7.6867e-06 | 108 | 7.1811e-05 | 404 | 6.7824e-06 | Tier 3 | 2026 | 2026 | 0.2 | 0.2 | 0 | 0
| 35554840 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Oroville | BUTTE |  |  | v3 | 1246 | 2.9032e-05 | 108 | 0.00026541 | 404 | 1.3565e-05 | Tier 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35554841 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Oroville | BUTTE |  |  | v3 | 1246 | 2.5218e-06 | 108 | 2.2394e-05 | 404 | 1.1304e-05 | Tier 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35401012 | SH | 3UG | ESTS | Permitting/Dependency | Yosemite | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | v3 | 679 | 2.4237e-05 | 126 | 8.7699e-05 | 322 | 1.4192e-05 | Tier 2 & 3 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35365064 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Dutch Flat | PLACER |  |  | v3 | 1526 | 4.6243e-05 | 20 | 0.0010713 | 140 | 0.00033721 | Tier 3 | 2025 | 2026 | 4.2 | 4.2 | 0 | 0
| 35374564 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Twain | PLUMAS |  |  | v3 | 378 | 4.0747e-05 | 45 | 0.00027589 | 12 | 7.8775e-07 | Tier 2 | 2025 | 2026 | 1 | 1 | 0 | 0
| 35430879 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Twain | PLUMAS |  |  | v3 | 378 | 2.4525e-05 | 45 | 0.00016549 | 12 | 6.8833e-08 | Tier 2 | 2026 | 2026 | 0.1 | 0.1 | 0 | 0
| 35430880 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Twain | PLUMAS |  |  | v3 | 378 | 6.014e-05 | 45 | 0.00039844 | 12 | 1.7591e-06 | Tier 2 | 2026 | 2026 | 2.3 | 2.3 | 0 | 0
| 35522104 | SH | 08W | ESTS | Estimating | North Bay | Region 1 - North Coast | Calistoga | NAPA |  |  | v3 | 1093 | 0 | 134 | 4.5609e-05 | 858 | 5.5092e-05 | Tier 3 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35521819 | SH | 08W | ESTS | Estimating | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00028427 | 56 | 6.0814e-06 | Tier 2 & 3 | 2026 | 2026 | 0 | 0 | 0 | 0
| 35433366 | SH | 3UG | ADER | Estimating | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 377 | 3.3103e-05 | 15 | 0.0001349 | 31 | 0.00011586 | Tier 3 | 2026 | 2026 | 0.8 | 0.8 | 0 | 0
| 35545295 | SH | 08W | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | NEVADA |  |  | v3 | 408 | 9.4112e-05 | 75 | 0.0002503 | 454 | 2.5724e-05 | Tier 2 | 2026 | 2026 | 0.6 | 0.7 | 0 | 0
| 35545296 | SH | 08W | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | NEVADA |  |  | v3 | 408 | 6.1489e-05 | 75 | 0.00016396 | 454 | 1.1477e-05 | Tier 2 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35545299 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | NEVADA |  |  | v3 | 408 | 4.8393e-05 | 75 | 0.00012994 | 454 | 3.5617e-06 | Tier 2 | 2026 | 2026 | 0.1 | 0.1 | 0 | 0
| 35544237 | SH | 08W | ADER | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 1062 | 5.348e-06 | 34 | 7.7857e-05 |  | 0 | Tier 2 | 2026 | 2026 | 0.2 | 0.3 | 0 | 0
| 35547190 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 2550 | 8.5038e-07 | 67 | 0.00016915 | 224 | 5.6418e-05 | Tier 2 | 2026 | 2026 | 1.7 | 1.7 | 0 | 0
| 35547191 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 2550 | 1.1728e-06 | 67 | 0.00023335 | 224 | 7.2147e-05 | Tier 2 | 2026 | 2026 | 2.1 | 2.1 | 0 | 0
| 35547192 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 2550 | 1.3923e-06 | 67 | 0.00027694 | 224 | 8.0695e-05 | Tier 2 | 2026 | 2026 | 2.4 | 2.4 | 0 | 0
| 35547193 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 2550 | 1.3673e-06 | 67 | 0.00027196 | 224 | 0.00011147 | Tier 2 | 2026 | 2026 | 3.3 | 3.3 | 0 | 0
| 35524564 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 2550 | 1.2005e-06 | 67 | 0.0002388 | 224 | 5.2315e-05 | Tier 2 | 2026 | 2026 | 1.5 | 1.5 | 0 | 0
| 35493212 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 1412 | 2.3951e-05 | 66 | 0.00025274 | 210 | 8.4938e-05 | Tier 3 | 2025 | 2026 | 2 | 2 | 0 | 0
| 35548785 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Alta | PLACER |  |  | v3 | 942 | 1.2834e-05 | 103 | 8.6185e-05 | 39 | 4.3933e-05 | Tier 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35343741 | SH | 08W | PEND | Permitting/Dependency | Sonoma | Region 1 - North Coast | Sonoma | SONOMA |  |  | v2 | 1827 | 2.3114e-06 | 440 | 0 |  | 0 | Tier 2 & 3 | 2025 | 2026 | 0.7 | 0.7 | 0 | 0
| 35421187 | SH | 3UG | PEND | Estimating | Stockton | Region 5 - Central Valley | Pioneer | AMADOR |  |  | v3 | 1765 | 1.391e-06 | 218 | 0.00012784 | 219 | 2.6432e-05 | Tier 3 | 2025 | 2026 | 3.7 | 0.5 | 0 | 0
| 74001486 | Other | 30A | CONS | * In-Construction | East Bay | Region 3 - Bay Area | Berkeley | ALAMEDA |  |  | v2 | 2792 | 2.6852e-07 | 2633 | 3.9289e-06 | 4071 | 8.6408e-06 | Tier 2 & 3 | 2025 | 2026 | 1.7 | 1.7 | 0 | 0
| 35524565 | SH | 08W | ESTS | Permitting/Dependency | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 2550 | 5.2523e-07 | 67 | 0.00010447 | 224 | 4.9922e-05 | Tier 2 & 3 | 2026 | 2026 | 1.5 | 1.5 | 0 | 0
| 35401226 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Pollock Pines | EL DORADO |  |  | v3 | 2250 | 2.0212e-06 | 81 | 0.00016774 | 84 | 0.00021667 | Tier 3 | 2025 | 2026 | 2 | 2 | 0 | 0
| 35367468 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Pollock Pines | EL DORADO |  |  | v3 | 2250 | 7.1083e-06 | 81 | 0.00058529 | 84 | 0.00030801 | Tier 3 | 2026 | 2026 | 2.9 | 2.9 | 0 | 0
| 35539162 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 4.4611e-05 | 58 | 0.0002646 | 179 | 0.00016827 | Tier 3 | 2026 | 2026 | 2.3 | 2.4 | 0 | 0
| 35546590 | SH | 08W | ESTS | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 1791 | 5.4324e-06 | 143 | 0.0001431 | 1015 | 4.3504e-05 | Tier 2 & 3 | 2025 | 2026 | 2.4 | 2.4 | 0 | 0
| 35538297 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 1.9623e-05 | 97 | 0.00020723 | 1173 | 0.00016109 | Tier 3 | 2026 | 2026 | 3.3 | 3.3 | 0 | 0
| 35538298 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 1.9146e-05 | 97 | 0.00020075 | 1173 | 4.2828e-05 | Tier 3 | 2026 | 2026 | 0.9 | 0.9 | 0 | 0
| 35538299 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 2.3068e-05 | 97 | 0.00024362 | 1173 | 8.7602e-05 | Tier 3 | 2025 | 2026 | 1.8 | 1.8 | 0 | 0
| 35544813 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1378 | 1.0781e-05 | 89 | 0.0001041 | 428 | 2.4654e-05 | Tier 2 & 3 | 2025 | 2026 | 0.6 | 0.6 | 0 | 0
| 35539104 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 2810 | 1.6998e-07 | 98 | 0.00014443 | 268 | 8.3799e-05 | Tier 3 | 2025 | 2026 | 1.8 | 1.8 | 0 | 0
| 35285594 | FRRB | 08W | UNSE | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Twin Bridges | EL DORADO |  |  | v2 | 2005 | 1.497e-06 | 2299 | 7.7954e-07 | 790 | 4.2779e-06 | Tier 2 | 2026 | 2026 | 0.2 | 0.2 | 0 | 0
| 35538523 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 2.7112e-05 | 97 | 0.00028633 | 1173 | 0.00015866 | Tier 2 & 3 | 2026 | 2026 | 3.3 | 3.3 | 0 | 0
| 35544224 | SH | 08W | ESTS | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1614 | 2.1642e-05 | 43 | 0.00039679 | 321 | 0.00013689 | Tier 3 | 2025 | 2026 | 2.7 | 2.7 | 0 | 0
| 35538525 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 1.9431e-05 | 97 | 0.00020798 | 1173 | 3.5041e-05 | Tier 2 & 3 | 2025 | 2026 | 0.7 | 0.7 | 0 | 0
| 35538526 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 1.0704e-05 | 97 | 0.00011549 | 1173 | 1.5087e-05 | Tier 2 & 3 | 2025 | 2026 | 0.3 | 0.3 | 0 | 0
| 35538527 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 6.8547e-05 | 97 | 0.00073513 | 1173 | 0.00013822 | Tier 2 & 3 | 2026 | 2026 | 2.8 | 2.8 | 0 | 0
| 35539118 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 2.3918e-05 | 58 | 0.00014186 | 179 | 0.00014536 | Tier 3 | 2026 | 2026 | 2 | 2 | 0 | 0
| 35488068 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 2763 | 3.935e-07 | 61 | 0.00038094 | 293 | 0.00019773 | Tier 3 | 2025 | 2026 | 3.6 | 3.7 | 0 | 0
| 35404353 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 1254 | 2.6545e-05 | 101 | 0.00020872 | 152 | 0.00016235 | Tier 3 | 2026 | 2026 | 2.1 | 2.1 | 0 | 0
| 35417110 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 3.2654e-05 | 97 | 0.00034486 | 1173 | 0.00017569 | Tier 3 | 2025 | 2026 | 3.6 | 3.6 | 0 | 0
| 35544380 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1403 | 7.1075e-06 | 73 | 7.596e-05 | 507 | 1.1828e-05 | Tier 2 & 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35284810 | FRRB | 08W | PEND | Permitting/Dependency | Peninsula | Region 3 - Bay Area | Pescadero | SAN MATEO |  |  | v2 | 2186 | 2.3289e-06 | 2434 | 4.7189e-06 | 1999 | 5.3711e-05 | Tier 2 | 2026 | 2026 | 0.9 | 0.9 | 0 | 0
| 35523412 | SH | 3UG | PEND | Permitting/Dependency | Kern | Region 5 - Central Valley | Lebec | KERN |  |  | v3 | 583 | 0.00017486 | 219 | 0.00025318 | 239 | 0.00015871 | Tier 2 | 2026 | 2026 | 3.2 | 3.2 | 0 | 0
| 35538522 | SH | 08W | ESTS | Scoping/Scoped | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 2.7562e-05 | 97 | 0.00029107 | 1173 | 0.00014454 | Tier 3 | 2026 | 2026 | 3 | 3 | 0 | 0
| 35561176 | SH | 08W | UNSE | Scoping/Scoped | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 144 | 0.00010212 | 530 | 1.7843e-05 | Tier 2 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35561177 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 144 | 0.00016789 | 530 | 9.2934e-06 | Tier 2 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35451494 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | El Portal | MARIPOSA |  |  | v3 | 555 | 1.4612e-05 | 10 | 0.00012928 | 78 | 5.4678e-05 | Tier 2 | 2026 | 2026 | 0.4 | 0.4 | 0 | 0
| 35436100 | SH | 3UG | PEND | Permitting/Dependency | Yosemite | Region 5 - Central Valley | El Portal | MARIPOSA |  |  | v3 | 555 | 4.9587e-05 | 10 | 0.00043338 | 78 | 0.00020137 | Tier 2 | 2026 | 2026 | 1.5 | 1.5 | 0 | 0
| 35435899 | SH | 3UG | PEND | Permitting/Dependency | Yosemite | Region 5 - Central Valley | El Portal | MARIPOSA |  |  | v3 | 555 | 4.5376e-05 | 10 | 0.00039651 | 78 | 0.00016003 | Tier 2 | 2026 | 2026 | 1.2 | 1.2 | 0 | 0
| 35519786 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 456 | 0.00025108 | 119 | 0.00041006 | 216 | 1.662e-05 | Tier 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35544812 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1378 | 1.7359e-05 | 89 | 0.00016762 | 428 | 5.6582e-05 | Tier 2 & 3 | 2025 | 2026 | 1.4 | 1.4 | 0 | 0
| 35420113 | SH | 3UG | PEND | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 1.3662e-05 | 68 | 0.00029977 | 215 | 0.00015003 | Tier 2 & 3 | 2026 | 2026 | 2.4 | 2.4 | 0 | 0
| 35519767 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Shasta | SHASTA |  |  | v3 | 1614 | 1.1239e-05 | 43 | 0.00021158 | 321 | 3.3461e-05 | Tier 3 | 2026 | 2026 | 0.7 | 0.7 | 0 | 0
| 35539163 | FRRB | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1434 | 2.846e-06 | 322 | 2.5093e-05 | 987 | 1.0032e-05 | Tier 2 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35545067 | SH | 3UG | ADER | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Gold Run | PLACER |  |  | v3 | 2022 | 1.5724e-06 | 93 | 8.8181e-05 | 453 | 2.7355e-05 | Tier 2 | 2025 | 2026 | 0.8 | 0.8 | 0 | 0
| 35373620 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Pollock Pines | EL DORADO |  |  | v3 | 2250 | 1.1158e-06 | 81 | 9.2472e-05 | 84 | 6.9037e-05 | Tier 3 | 2026 | 2026 | 0.7 | 0.7 | 0 | 0
| 35538520 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 2.157e-05 | 97 | 0.0002278 | 1173 | 0.00012118 | Tier 3 | 2026 | 2026 | 2.5 | 2.5 | 0 | 0
| 35417127 | SH | 3UG | PEND | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 6.4497e-05 | 58 | 0.00038255 | 179 | 0.00021482 | Tier 3 | 2026 | 2026 | 3 | 3 | 0 | 0
| 35401011 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | v3 | 679 | 0.00012052 | 126 | 0.00043252 | 322 | 4.0627e-05 | Tier 2 & 3 | 2026 | 2026 | 1.5 | 1.5 | 0 | 0
| 35519777 | SH | 08W | PEND | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1135 | 6.026e-06 | 83 | 0.00012767 | 661 | 3.5466e-05 | Tier 2 & 3 | 2026 | 2026 | 1.2 | 1.2 | 0 | 0
| 35274589 | SH | 08W | ADER | Estimating | Yosemite | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | v2 | 428 | 6.2279e-05 | 0 | 0 |  | 0 | Tier 2 & 3 | 2026 | 2026 | 2.7 | 2.7 | 0 | 0
| 35409203 | SH | 3UG | ESTS | Estimating | Humboldt | Region 1 - North Coast | Middletown | LAKE |  |  | v3 | 0 | 0 | 99 | 0.00027289 | 355 | 6.3462e-05 | Tier 2 & 3 | 2026 | 2026 | 1.4 | 1.4 | 0 | 0
| 35226857 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Middletown | LAKE |  |  | v2 | 474 | 5.0461e-05 | 102 | 0.00011487 | 202 | 6.8745e-05 | Tier 3 | 2026 | 2026 | 1.1 | 1.1 | 0 | 0
| 35227007 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Middletown | LAKE |  |  | v2 | 474 | 8.0464e-05 | 102 | 0.00018317 | 202 | 0.00017367 | Tier 3 | 2026 | 2026 | 2.9 | 2.9 | 0 | 0
| 35174478 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Middletown | LAKE |  |  | v2 | 474 | 6.9554e-05 | 102 | 0.00015834 | 202 | 6.2715e-05 | Tier 3 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35521812 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Sonora | TUOLUMNE |  |  | v3 | 2426 | 6.4523e-07 | 50 | 8.6484e-05 | 72 | 3.6422e-05 | Tier 3 | 2026 | 2026 | 0.4 | 0.4 | 0 | 0
| 35374202 | SH | 3UG | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 1043 | 1.4456e-05 | 37 | 0.00015223 | 123 | 9.3668e-05 | Tier 3 | 2026 | 2026 | 1.1 | 1.1 | 0 | 0
| 35454650 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 1043 | 8.6851e-06 | 37 | 9.1455e-05 | 123 | 4.4645e-05 | Tier 3 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35454651 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 1043 | 2.6766e-05 | 37 | 0.00028222 | 123 | 0.00012168 | Tier 3 | 2026 | 2026 | 1.4 | 1.4 | 0 | 0
| 35454652 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 1043 | 3.1585e-05 | 37 | 0.0003326 | 123 | 0.00023636 | Tier 3 | 2026 | 2026 | 2.7 | 2.7 | 0 | 0
| 35519761 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 9.1703e-06 | 22 | 0.00039546 | 301 | 6.1711e-05 | Tier 3 | 2026 | 2026 | 1.3 | 1.3 | 0 | 0
| 35543416 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 9.6602e-06 | 22 | 0.00042383 | 301 | 2.8518e-05 | Tier 3 | 2025 | 2026 | 0.6 | 0.6 | 0 | 0
| 35543417 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 1.8664e-06 | 22 | 7.9001e-05 | 301 | 3.3661e-05 | Tier 3 | 2025 | 2026 | 0.7 | 0.7 | 0 | 0
| 35543418 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 6.0531e-06 | 22 | 0.00026663 | 301 | 1.87e-06 | Tier 3 | 2025 | 2026 | 0 | 0 | 0 | 0
| 35543419 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 4.4589e-06 | 22 | 0.00019676 | 301 | 3.7401e-05 | Tier 3 | 2025 | 2026 | 0.8 | 0.8 | 0 | 0
| 35543440 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 6.1936e-06 | 22 | 0.00026485 | 301 | 4.6751e-05 | Tier 3 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35543441 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 3.7951e-06 | 22 | 0.00016472 | 301 | 1.9168e-05 | Tier 3 | 2025 | 2026 | 0.4 | 0.4 | 0 | 0
| 35543443 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 5.8915e-06 | 22 | 0.0002556 | 301 | 2.1038e-05 | Tier 3 | 2025 | 2026 | 0.5 | 0.5 | 0 | 0
| 35543444 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 8.1343e-06 | 22 | 0.00035411 | 301 | 2.1973e-05 | Tier 3 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35543445 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 6.911e-06 | 22 | 0.00029923 | 301 | 1.5428e-05 | Tier 3 | 2025 | 2026 | 0.3 | 0.3 | 0 | 0
| 35543447 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Bass Lake | MADERA |  |  | v3 | 1854 | 5.5599e-06 | 22 | 0.00023872 | 301 | 6.3114e-05 | Tier 3 | 2025 | 2026 | 1.4 | 1.4 | 0 | 0
| 35538521 | SH | 08W | ESTS | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 2.7621e-05 | 97 | 0.00028878 | 1173 | 5.0614e-05 | Tier 3 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35539177 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Shasta Lake | SHASTA |  |  | v3 | 1773 | 1.0728e-05 | 64 | 0.00029653 | 350 | 7.9357e-05 | Tier 2 | 2026 | 2026 | 1.7 | 1.7 | 0 | 0
| 35367504 | SH | 3UG | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 2763 | 5.6839e-07 | 61 | 0.00055025 | 293 | 0.00023165 | Tier 3 | 2026 | 2026 | 4.4 | 4.4 | 0 | 0
| 35538524 | SH | 08W | PEND | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 3.2045e-05 | 97 | 0.0003506 | 1173 | 4.3801e-06 | Tier 2 & 3 | 2026 | 2026 | 0.1 | 0.1 | 0 | 0
| 35544225 | SH | 08W | PEND | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1614 | 1.7106e-05 | 43 | 0.00031405 | 321 | 9.4299e-05 | Tier 3 | 2025 | 2026 | 1.9 | 1.9 | 0 | 0
| 35539172 | SH | 08W | PEND | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1773 | 5.8057e-06 | 64 | 0.00016048 | 350 | 7.3756e-05 | Tier 2 | 2026 | 2026 | 1.6 | 1.6 | 0 | 0
| 35526464 | SH | 08W | ESTS | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 7.7802e-06 | 97 | 8.4055e-05 | 1173 | 4.5748e-05 | Tier 3 | 2026 | 2026 | 0.9 | 0.9 | 0 | 0
| 35375452 | SH | 3UG | UNSE | Scoping/Scoped | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1710 | 1.0488e-05 | 52 | 0.00048686 | 55 | 0.00046759 | Tier 3 | 2026 | 2026 | 3.1 | 3.1 | 0 | 0
| 35452898 | SH | 3UG | UNSE | Scoping/Scoped | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1710 | 1.3404e-05 | 52 | 0.0006222 | 55 | 0.00066669 | Tier 3 | 2026 | 2026 | 4.4 | 4.4 | 0 | 0
| 35377525 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 6.4047e-06 | 116 | 9.6755e-05 | 492 | 4.2664e-05 | Tier 3 | 2026 | 2026 | 1.6 | 1.6 | 0 | 0
| 35375449 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | SIERRA |  |  | v3 | 1484 | 2.7056e-05 | 116 | 0.00041689 | 492 | 5.7939e-05 | Tier 3 | 2025 | 2026 | 2.2 | 2.2 | 0 | 0
| 35375450 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 4.8977e-06 | 116 | 7.3989e-05 | 492 | 3.687e-05 | Tier 3 | 2026 | 2026 | 1.4 | 1.4 | 0 | 0
| 35553016 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | SIERRA |  |  | v3 | 1484 | 1.4222e-05 | 116 | 0.00021485 | 492 | 4.7931e-05 | Tier 3 | 2025 | 2026 | 1.8 | 1.8 | 0 | 0
| 35553017 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | SIERRA |  |  | v3 | 1484 | 9.042e-06 | 116 | 0.00013659 | 492 | 2.5546e-05 | Tier 3 | 2025 | 2026 | 1 | 1 | 0 | 0
| 35553018 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | SIERRA |  |  | v3 | 1484 | 1.6519e-05 | 116 | 0.00024865 | 492 | 3.8977e-05 | Tier 3 | 2025 | 2026 | 1.5 | 1.5 | 0 | 0
| 35553265 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | SIERRA |  |  | v3 | 1484 | 1.0549e-05 | 116 | 0.00015936 | 492 | 3.3183e-05 | Tier 3 | 2025 | 2026 | 1.3 | 1.3 | 0 | 0
| 35553266 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | SIERRA |  |  | v3 | 1484 | 1.2449e-05 | 116 | 0.00018766 | 492 | 3.1603e-05 | Tier 3 | 2025 | 2026 | 1.2 | 1.2 | 0 | 0
| 35553267 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 3.6733e-06 | 116 | 5.5492e-05 | 492 | 3.0286e-05 | Tier 3 | 2026 | 2026 | 1.1 | 1.2 | 0 | 0
| 35553268 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 8.9478e-06 | 116 | 0.00013517 | 492 | 2.5546e-05 | Tier 3 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35553269 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 7.4408e-06 | 116 | 0.00011241 | 492 | 3.6607e-05 | Tier 3 | 2026 | 2026 | 1.4 | 1.4 | 0 | 0
| 35553270 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 1.7091e-05 | 116 | 0.00026281 | 492 | 4.4244e-05 | Tier 3 | 2025 | 2026 | 1.7 | 1.7 | 0 | 0
| 35552171 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 7.535e-06 | 116 | 0.00011383 | 492 | 2.7126e-05 | Tier 3 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35552172 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 8.2885e-06 | 116 | 0.00012521 | 492 | 2.5809e-05 | Tier 3 | 2025 | 2026 | 1 | 1 | 0 | 0
| 35552173 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 1.6081e-05 | 116 | 0.00024238 | 492 | 4.0557e-05 | Tier 3 | 2025 | 2026 | 1.5 | 1.5 | 0 | 0
| 35552175 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 6.9699e-06 | 116 | 0.00010529 | 492 | 3.924e-05 | Tier 3 | 2026 | 2026 | 1.5 | 1.5 | 0 | 0
| 35524572 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Montgomery Creek | SHASTA |  |  | v3 | 2224 | 1.5802e-06 | 104 | 9.5565e-05 | 69 | 9.3888e-05 | Tier 2 | 2026 | 2026 | 0.7 | 0.7 | 0 | 0
| 35391471 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 3.4552e-06 | 68 | 7.612e-05 | 215 | 4.6497e-05 | Tier 2 & 3 | 2026 | 2026 | 0.8 | 0.8 | 0 | 0
| 35391721 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 1.745e-05 | 68 | 0.00038452 | 215 | 0.00024798 | Tier 3 | 2026 | 2026 | 4 | 4 | 0 | 0
| 35391722 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 2.325e-05 | 68 | 0.00051088 | 215 | 0.00022133 | Tier 3 | 2026 | 2026 | 3.6 | 3.6 | 0 | 0
| 35420109 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 4.408e-06 | 68 | 9.8912e-05 | 215 | 1.1159e-05 | Tier 2 & 3 | 2026 | 2026 | 0.2 | 0.2 | 0 | 0
| 35420110 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 1.1203e-05 | 68 | 0.00024801 | 215 | 0.00013329 | Tier 2 & 3 | 2026 | 2026 | 2.2 | 2.2 | 0 | 0
| 35420112 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 8.5825e-06 | 68 | 0.00019091 | 215 | 3.4718e-05 | Tier 2 & 3 | 2026 | 2026 | 0.6 | 0.6 | 0 | 0
| 35548782 | SH | 08W | ADER | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1885 | 4.7408e-06 | 120 | 0.00013107 | 197 | 5.6047e-05 | Tier 2 | 2026 | 2026 | 0.8 | 0.8 | 0 | 0
| 35537866 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 3.2344e-06 | 68 | 7.0611e-05 | 215 | 4.6497e-05 | Tier 2 & 3 | 2026 | 2026 | 0.7 | 0.8 | 0 | 0
| 35424580 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 2.0133e-05 | 68 | 0.0004467 | 215 | 0.00012771 | Tier 3 | 2026 | 2026 | 2.1 | 2.1 | 0 | 0
| 35424581 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Garden Valley | EL DORADO |  |  | v3 | 1666 | 8.3362e-06 | 68 | 0.00018456 | 215 | 0.00010725 | Tier 3 | 2026 | 2026 | 1.7 | 1.7 | 0 | 0
| 35424356 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 1.0078e-05 | 68 | 0.0002227 | 215 | 0.00010911 | Tier 3 | 2025 | 2026 | 1.8 | 1.8 | 0 | 0
| 35424357 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 7.459e-06 | 68 | 0.00016284 | 215 | 0.00010663 | Tier 3 | 2025 | 2026 | 1.7 | 1.7 | 0 | 0
| 35548784 | SH | 08W | ESTS | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1885 | 4.7848e-06 | 120 | 0.00013618 | 197 | 4.337e-05 | Tier 2 | 2026 | 2026 | 0.7 | 0.7 | 0 | 0
| 35376558 | SH | 3UG | ESTS | Permitting/Dependency | North Bay | Region 1 - North Coast | Saint Helena | NAPA |  |  | v3 | 1361 | 4.084e-06 | 105 | 5.4182e-05 | 918 | 2.6924e-05 | Tier 3 | 2025 | 2026 | 1.2 | 1.2 | 0 | 0
| 35418305 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 4.5686e-05 | 58 | 0.00027097 | 179 | 0.00018331 | Tier 3 | 2026 | 2026 | 2.6 | 2.6 | 0 | 0
| 35548717 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Shasta | SHASTA |  |  | v3 | 1614 | 6.9065e-06 | 43 | 0.00012922 | 321 | 2.6363e-05 | Tier 3 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35418255 | SH | 3UG | PEND | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 9094 | 1.5076e-05 | 58 | 8.9418e-05 | 179 | 4.01e-05 | Tier 3 | 2026 | 2026 | 0.6 | 0.6 | 0 | 0
| 35401224 | SH | 3UG | PEND | Estimating | Sierra | Region 2 - North Valley and Sierra | Pollock Pines | EL DORADO |  |  | v3 | 2250 | 1.6012e-06 | 81 | 0.00013171 | 84 | 6.4789e-05 | Tier 3 | 2026 | 2026 | 0.6 | 0.6 | 0 | 0
| 35543514 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Grass Valley | NEVADA |  |  | v3 | 2201 | 1.1722e-06 | 71 | 8.3128e-05 | 241 | 1.691e-05 | Tier 2 | 2025 | 2026 | 0.3 | 0.3 | 0 | 0
| 35554778 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 5.2941e-05 | 58 | 0.00031401 | 179 | 0.00018403 | Tier 3 | 2026 | 2026 | 2.6 | 2.6 | 0 | 0
| 35563467 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 2.4993e-05 | 58 | 0.00014824 | 179 | 6.9458e-05 | Tier 3 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35563469 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 1.8812e-05 | 58 | 0.00011158 | 179 | 7.8767e-05 | Tier 3 | 2026 | 2026 | 1.1 | 1.1 | 0 | 0
| 35539117 | SH | 3UG | PEND | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 3.6333e-05 | 58 | 0.0002155 | 179 | 0.00012101 | Tier 3 | 2026 | 2026 | 1.7 | 1.7 | 0 | 0
| 35311896 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Auburn | PLACER |  |  | v2 | 118 | 0.0002517 | 2685 | 3.4082e-06 | 3218 | 2.4427e-05 | Tier 2 | 2025 | 2026 | 3.7 | 3.7 | 0 | 0
| 35473991 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 4.5827e-05 | 58 | 0.00027191 | 179 | 0.00012101 | Tier 3 | 2026 | 2026 | 1.7 | 1.7 | 0 | 0
| 35297464 | FRRB | 08W | PEND | Permitting/Dependency | Central Coast | Region 4 - South Bay and Central Coast | Davenport | SANTA CRUZ |  |  | v2 | 2199 | 1.96e-06 | 2216 | 4.9809e-06 | 3821 | 4.6414e-06 | Tier 2 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35321894 | FRRB | 08W | PEND | Permitting/Dependency | Central Coast | Region 4 - South Bay and Central Coast | Davenport | SANTA CRUZ |  |  | v2 | 2199 | 1.6552e-07 | 2216 | 4.2079e-07 | 3821 | 5.1055e-07 | Tier 2 | 2026 | 2026 | 0.1 | 0.1 | 0 | 0
| 35290504 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | v2 | 75 | 2.9377e-05 | 573 | 9.8334e-06 | 1598 | 1.4174e-05 | Tier 2 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35424354 | SH | 3UG | PEND | Estimating | Sierra | Region 2 - North Valley and Sierra | Dutch Flat | PLACER |  |  | v3 | 1526 | 1.6476e-06 | 20 | 3.8171e-05 | 140 | 3.0437e-05 | Tier 3 | 2026 | 2026 | 0.4 | 0.4 | 0 | 0
| 35544809 | SH | 08W | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Grass Valley | NEVADA |  |  | v3 | 1378 | 2.4668e-05 | 89 | 0.00023819 | 428 | 7.0728e-05 | Tier 2 & 3 | 2025 | 2026 | 1.8 | 1.8 | 0 | 0
| 35317399 | SH | 08W | CONS | * In-Construction | Humboldt | Region 1 - North Coast | Clearlake Oaks | LAKE |  |  | v2 | 423 | 0.00011355 | 127 | 0.00024233 | 204 | 7.4172e-05 | Tier 2 & 3 | 2023 | 2026 | 1.1 | 1.1 | 0 | 0
| 35493219 | SH | 3UG | PEND | Estimating | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 1412 | 3.0995e-05 | 66 | 0.00032708 | 210 | 9.5717e-05 | Tier 3 | 2026 | 2026 | 2.2 | 2.2 | 0 | 0
| 35548783 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1885 | 4.4557e-06 | 120 | 0.00012497 | 197 | 6.6723e-05 | Tier 2 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35290510 | SH | 08W | PEND | Estimating | Humboldt | Region 1 - North Coast | Upper Lake | LAKE |  |  | v2 | 75 | 9.2939e-05 | 573 | 3.1053e-05 | 1598 | 7.4958e-06 | Tier 2 | 2026 | 2026 | 0.6 | 0.6 | 0 | 0
| 35543504 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2201 | 3.6092e-06 | 71 | 0.00025427 | 241 | 7.6656e-05 | Tier 2 | 2025 | 2026 | 1.4 | 1.4 | 0 | 0
| 35543506 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2201 | 2.8908e-06 | 71 | 0.00020087 | 241 | 0.00010033 | Tier 2 | 2026 | 2026 | 1.8 | 1.8 | 0 | 0
| 35543507 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2201 | 2.413e-06 | 71 | 0.00016767 | 241 | 7.3275e-05 | Tier 2 | 2025 | 2026 | 1.3 | 1.3 | 0 | 0
| 35543509 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2201 | 1.4573e-06 | 71 | 0.00010126 | 241 | 5.411e-05 | Tier 2 | 2025 | 2026 | 1 | 1 | 0 | 0
| 35543511 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2201 | 3.3275e-06 | 71 | 0.00023075 | 241 | 7.1584e-05 | Tier 2 | 2025 | 2026 | 1.3 | 1.3 | 0 | 0
| 35543512 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2201 | 1.4615e-06 | 71 | 0.00010126 | 241 | 3.0437e-05 | Tier 2 | 2025 | 2026 | 0.5 | 0.5 | 0 | 0
| 35546442 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | French Gulch | SHASTA |  |  | v3 | 1135 | 4.9304e-06 | 83 | 0.00010445 | 661 | 2.6979e-05 | Tier 2 & 3 | 2026 | 2026 | 0.9 | 0.9 | 0 | 0
| 35422749 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 1.9155e-06 | 93 | 0.00010742 | 453 | 4.1033e-05 | Tier 2 | 2026 | 2026 | 1.2 | 1.2 | 0 | 0
| 35422750 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 2.573e-07 | 93 | 1.443e-05 | 453 | 6.4626e-05 | Tier 3 | 2026 | 2026 | 1.9 | 1.9 | 0 | 0
| 35422751 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 3.4593e-06 | 93 | 0.000194 | 453 | 7.1465e-05 | Tier 3 | 2025 | 2026 | 2.1 | 2.1 | 0 | 0
| 35544819 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 2.8875e-06 | 93 | 0.00016193 | 453 | 3.8297e-05 | Tier 2 | 2025 | 2026 | 1.1 | 1.1 | 0 | 0
| 35545060 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 2.5444e-06 | 93 | 0.00014269 | 453 | 3.7271e-05 | Tier 2 | 2025 | 2026 | 1.1 | 1.1 | 0 | 0
| 35545061 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 1.0121e-05 | 93 | 0.00056757 | 453 | 0.00017952 | Tier 2 | 2026 | 2026 | 5.3 | 5.3 | 0 | 0
| 35545062 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Gold Run | PLACER |  |  | v3 | 2022 | 1.5152e-06 | 93 | 8.4974e-05 | 453 | 3.4536e-05 | Tier 2 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35545064 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Gold Run | PLACER |  |  | v3 | 2022 | 2.716e-06 | 93 | 0.00015231 | 453 | 4.3426e-05 | Tier 2 | 2026 | 2026 | 1.3 | 1.3 | 0 | 0
| 35545065 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Gold Run | PLACER |  |  | v3 | 2022 | 3.1162e-06 | 93 | 0.00017476 | 453 | 4.7529e-05 | Tier 2 | 2025 | 2026 | 1.4 | 1.4 | 0 | 0
| 35545066 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Gold Run | PLACER |  |  | v3 | 2022 | 4.587e-06 | 93 | 0.00025659 | 453 | 4.8897e-05 | Tier 2 | 2026 | 2026 | 1.4 | 1.4 | 0 | 0
| 35526463 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 2207 | 2.083e-06 | 94 | 0.00012718 | 470 | 1.7429e-05 | Tier 2 | 2025 | 2026 | 0.7 | 0.7 | 0 | 0
| 35545068 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Gold Run | PLACER |  |  | v3 | 2022 | 1.5152e-06 | 93 | 8.4974e-05 | 453 | 2.5303e-05 | Tier 2 | 2026 | 2026 | 0.7 | 0.7 | 0 | 0
| 35545069 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Gold Run | PLACER |  |  | v3 | 2022 | 1.9155e-06 | 93 | 0.00010742 | 453 | 3.522e-05 | Tier 2 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35543400 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 4.0311e-06 | 93 | 0.00022606 | 453 | 6.7362e-05 | Tier 2 | 2026 | 2026 | 2 | 2 | 0 | 0
| 35543401 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 4.8865e-06 | 93 | 0.00027304 | 453 | 4.9239e-05 | Tier 2 | 2025 | 2026 | 1.4 | 1.4 | 0 | 0
| 35543402 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 3.9167e-06 | 93 | 0.00021965 | 453 | 7.9672e-05 | Tier 2 | 2026 | 2026 | 2.3 | 2.3 | 0 | 0
| 35543403 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2022 | 2.7732e-06 | 93 | 0.00015552 | 453 | 3.7613e-05 | Tier 2 | 2025 | 2026 | 1.1 | 1.1 | 0 | 0
| 35397962 | SH | 3UG | ESTS | Permitting/Dependency | Yosemite | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | v3 | 679 | 0.00012197 | 126 | 0.00044944 | 322 | 1.2522e-05 | Tier 2 & 3 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35544220 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Shasta | SHASTA |  |  | v3 | 1614 | 3.5919e-05 | 43 | 0.00068838 | 321 | 1.5717e-05 | Tier 3 | 2026 | 2026 | 0.3 | 0.3 | 0 | 0
| 35290508 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | v2 | 75 | 6.03e-05 | 573 | 2.0184e-05 | 1598 | 8.4498e-06 | Tier 2 | 2026 | 2026 | 0.6 | 0.6 | 0 | 0
| 35546591 | SH | 08W | ADER | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 1791 | 4.4528e-06 | 143 | 0.00011859 | 1015 | 1.7149e-05 | Tier 2 & 3 | 2026 | 2026 | 1 | 1 | 0 | 0
| 35544810 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1378 | 2.1957e-05 | 89 | 0.00021173 | 428 | 4.567e-05 | Tier 2 & 3 | 2026 | 2026 | 1.1 | 1.1 | 0 | 0
| 35544814 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1378 | 2.0664e-05 | 89 | 0.00019938 | 428 | 4.4053e-05 | Tier 2 & 3 | 2026 | 2026 | 1.1 | 1.1 | 0 | 0
| 35526462 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Grass Valley | NEVADA |  |  | v3 | 1378 | 5.7085e-06 | 89 | 5.4696e-05 | 428 | 2.9099e-05 | Tier 2 & 3 | 2026 | 2026 | 0.7 | 0.7 | 0 | 0
| 35418361 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1378 | 1.0781e-05 | 89 | 0.0001041 | 428 | 6.3857e-05 | Tier 2 & 3 | 2026 | 2026 | 1.6 | 1.6 | 0 | 0
| 35429566 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Saint Helena | NAPA |  |  | v3 | 0 | 0 | 33 | 0.00046174 | 1995 | 0.00027006 | Tier 3 | 2026 | 2026 | 3.8 | 3.8 | 0 | 0
| 35428406 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 0 | 0 | 33 | 0.00030523 | 1995 | 9.8787e-05 | Tier 3 | 2026 | 2026 | 1.4 | 1.4 | 0 | 0
| 35385804 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 792 | 5.7248e-05 | 59 | 0.0002568 | 160 | 0.00019851 | Tier 3 | 2026 | 2026 | 2.7 | 2.7 | 0 | 0
| 35428425 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 792 | 8.4946e-05 | 59 | 0.00038104 | 160 | 0.00019252 | Tier 3 | 2026 | 2026 | 2.6 | 2.6 | 0 | 0
| 35425878 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 792 | 4.8291e-05 | 59 | 0.00021662 | 160 | 0.00012585 | Tier 3 | 2025 | 2026 | 1.7 | 1.7 | 0 | 0
| 35425645 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 792 | 0.0001021 | 59 | 0.00045799 | 160 | 0.00024046 | Tier 3 | 2025 | 2026 | 3.2 | 3.2 | 0 | 0
| 35526465 | SH | 08W | ESTS | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 1.3631e-05 | 97 | 0.00014395 | 1173 | 8.8089e-05 | Tier 2 & 3 | 2025 | 2026 | 1.8 | 1.8 | 0 | 0
| 35404351 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 1254 | 3.2114e-05 | 101 | 0.00025251 | 152 | 0.00012601 | Tier 3 | 2026 | 2026 | 1.6 | 1.6 | 0 | 0
| 35539161 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 2.2843e-05 | 58 | 0.00013549 | 179 | 8.0915e-05 | Tier 3 | 2026 | 2026 | 1.1 | 1.1 | 0 | 0
| 35546592 | SH | 08W | ESTS | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 1791 | 2.2301e-06 | 143 | 5.8443e-05 | 1015 | 1.0289e-05 | Tier 2 & 3 | 2026 | 2026 | 0.6 | 0.6 | 0 | 0
| 35562010 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Saint Helena | NAPA |  |  | v3 | 1361 | 1.3365e-05 | 105 | 0.00018093 | 918 | 1.3128e-05 | Tier 3 | 2026 | 2026 | 0.6 | 0.6 | 0 | 0
| 35562011 | SH | 3UG | UNSE | Scoping/Scoped | North Bay | Region 1 - North Coast | Saint Helena | NAPA |  |  | v3 | 1361 | 2.604e-06 | 105 | 3.4698e-05 | 918 | 5.3403e-06 | Tier 3 | 2026 | 2026 | 0.2 | 0.2 | 0 | 0
| 35430872 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Saint Helena | NAPA |  |  | v3 | 1361 | 1.7949e-05 | 105 | 0.00024214 | 918 | 1.3351e-05 | Tier 3 | 2026 | 2026 | 0.6 | 0.6 | 0 | 0
| 35430873 | SH | 3UG | UNSE | Scoping/Scoped | North Bay | Region 1 - North Coast | Saint Helena | NAPA |  |  | v3 | 1361 | 1.0643e-05 | 105 | 0.0001412 | 918 | 2.1361e-05 | Tier 3 | 2025 | 2026 | 1 | 1 | 0 | 0
| 35430875 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Saint Helena | NAPA |  |  | v3 | 1361 | 4.7028e-06 | 105 | 6.2392e-05 | 918 | 1.8468e-05 | Tier 3 | 2025 | 2026 | 0.8 | 0.8 | 0 | 0
| 35460162 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Chico | BUTTE |  |  | v3 | 2537 | 2.2281e-06 | 57 | 0.00062075 | 286 | 0.00023042 | Tier 3 | 2026 | 2026 | 5.3 | 5 | 0 | 0
| 35464321 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Chico | BUTTE |  |  | v3 | 2537 | 1.1628e-06 | 57 | 0.00032371 | 286 | 8.1998e-05 | Tier 3 | 2026 | 2026 | 1.8 | 1.8 | 0 | 0
| 35493213 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 1412 | 1.3776e-05 | 66 | 0.00014537 | 210 | 4.1822e-05 | Tier 3 | 2025 | 2026 | 1 | 1 | 0 | 0
| 35493214 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 1412 | 2.583e-05 | 66 | 0.00027257 | 210 | 7.2866e-05 | Tier 3 | 2026 | 2026 | 1.7 | 1.7 | 0 | 0
| 35493215 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 1412 | 2.6544e-05 | 66 | 0.00027917 | 210 | 6.2518e-05 | Tier 3 | 2026 | 2026 | 1.4 | 1.5 | 0 | 0
| 35493216 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 1412 | 9.0795e-06 | 66 | 9.5811e-05 | 210 | 0.00012633 | Tier 3 | 2026 | 2026 | 2.9 | 2.9 | 0 | 0
| 35493217 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 1412 | 5.2755e-05 | 66 | 0.0005567 | 210 | 0.00015651 | Tier 3 | 2026 | 2026 | 3.6 | 3.6 | 0 | 0
| 35546589 | SH | 08W | ESTS | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 1791 | 4.0328e-06 | 143 | 0.00010548 | 1015 | 1.2275e-05 | Tier 2 & 3 | 2026 | 2026 | 0.7 | 0.7 | 0 | 0
| 35418379 | SH | 3UG | ESTS | Estimating | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 2810 | 2.669e-07 | 98 | 0.00022679 | 268 | 0.00011925 | Tier 3 | 2026 | 2026 | 2.6 | 2.6 | 0 | 0
| 35544816 | SH | 3UG | PEND | Estimating | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 2763 | 3.8219e-07 | 61 | 0.00036973 | 293 | 0.00011662 | Tier 3 | 2025 | 2026 | 2.6 | 2.2 | 0 | 0
| 35544811 | SH | 3UG | ADER | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1378 | 1.9493e-05 | 89 | 0.00018825 | 428 | 8.0832e-05 | Tier 2 & 3 | 2025 | 2026 | 2 | 2 | 0 | 0
| 35539106 | SH | 3UG | ESTS | Estimating | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 2810 | 2.8657e-07 | 98 | 0.0002435 | 268 | 0.00015286 | Tier 3 | 2026 | 2026 | 3.3 | 3.3 | 0 | 0
| 35539105 | SH | 3UG | ESTS | Estimating | Stockton | Region 5 - Central Valley | Arnold | CALAVERAS |  |  | v3 | 2810 | 1.756e-07 | 98 | 0.0001492 | 268 | 6.1698e-05 | Tier 3 | 2026 | 2026 | 1.3 | 1.3 | 0 | 0
| 35550921 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 2763 | 3.8598e-07 | 61 | 0.00037294 | 293 | 0.00011132 | Tier 3 | 2025 | 2026 | 2.6 | 2.1 | 0 | 0
| 35563468 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 2.338e-05 | 58 | 0.00013867 | 179 | 9.5952e-05 | Tier 3 | 2026 | 2026 | 1.3 | 1.3 | 0 | 0
| 35544815 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 2763 | 2.741e-07 | 61 | 0.00026536 | 293 | 8.7466e-05 | Tier 3 | 2025 | 2026 | 2.7 | 1.7 | 0 | 0
| 35523413 | SH | 3UG | PEND | Permitting/Dependency | Kern | Region 5 - Central Valley | Lebec | KERN |  |  | v3 | 583 | 0.00020509 | 219 | 0.0002969 | 239 | 0.00014249 | Tier 2 | 2026 | 2026 | 2.9 | 2.9 | 0 | 0
| 35526466 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 2.0821e-05 | 97 | 0.00021989 | 1173 | 8.9062e-05 | Tier 2 | 2025 | 2026 | 1.8 | 1.8 | 0 | 0
| 35523415 | SH | 3UG | PEND | Permitting/Dependency | Kern | Region 5 - Central Valley | Lebec | KERN |  |  | v3 | 583 | 0.00011658 | 219 | 0.00016878 | 239 | 9.8763e-05 | Tier 2 | 2025 | 2026 | 2 | 2 | 0 | 0
| 35372461 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Pioneer | AMADOR |  |  | v3 | 1744 | 8.3292e-07 | 8 | 9.8656e-05 | 5 | 0.00027656 | Tier 2 & 3 | 2026 | 2026 | 4.3 | 4.3 | 0 | 0
| 35367516 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 1254 | 1.7021e-05 | 101 | 0.00013384 | 152 | 0.00010514 | Tier 3 | 2026 | 2026 | 1.4 | 1.4 | 0 | 0
| 35411027 | SH | 3UG | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Pioneer | AMADOR |  |  | v3 | 2468 | 3.3908e-06 | 107 | 0.00050172 | 368 | 0.00013822 | Tier 3 | 2026 | 2026 | 3.5 | 3.5 | 0 | 0
| 35554850 | SH | 08W | ESTS | Estimating | Stockton | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS |  |  | v3 | 1815 | 1.5624e-05 | 110 | 0.00044489 | 253 | 0.00020965 | Tier 2 & 3 | 2026 | 2026 | 3.5 | 3.5 | 0 | 0
| 35546585 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Platina | SHASTA |  |  | v3 | 454 | 1.9585e-05 | 109 | 9.3513e-05 | 338 | 1.9656e-05 | Tier 2 | 2026 | 2026 | 0.5 | 0.5 | 0 | 0
| 35546586 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Platina | SHASTA |  |  | v3 | 454 | 5.9278e-05 | 109 | 0.00027238 | 338 | 4.9349e-05 | Tier 2 | 2026 | 2026 | 1.2 | 1.2 | 0 | 0
| 35546587 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Platina | SHASTA |  |  | v3 | 454 | 3.6614e-05 | 109 | 0.00017534 | 338 | 2.9693e-05 | Tier 2 | 2026 | 2026 | 0.7 | 0.7 | 0 | 0
| 35519784 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Platina | SHASTA |  |  | v3 | 454 | 2.7177e-05 | 109 | 0.00012598 | 338 | 9.6189e-05 | Tier 2 | 2026 | 2026 | 2.3 | 2.3 | 0 | 0
| TBD | None | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 2026 | 5.9 | 5.9 | 0 | 0
| 35246595 | Community Rebuild | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | None | BUTTE |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None | 2025 | 2026 | 2.3 | 2.3 | 0 | 0
| 35424604 | Community Rebuild | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | None | BUTTE |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None | 2026 | 2026 | 1.8 | 1.8 | 0 | 0
| 35227412 | Community Rebuild | 95F O | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | None | BUTTE |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None | 2026 | 2026 | 1 | 1 | 0 | 0
| 35246591 | Community Rebuild | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | None | BUTTE |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None | 2026 | 2026 | 3.9 | 3.9 | 0 | 0
| 35227417 | Community Rebuild | 95F O | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | None | BUTTE |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None | 2026 | 2026 | 1.4 | 1.4 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | El Dorado | Region 2 - North Valley and Sierra | El Dorado | El Dorado |  |  | v4 | 644 | N/A | 2 | N/A | 15 | 1.4181e-05 | Tier 2 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | French Gulch | Shasta |  |  | v4 | 252 | N/A | 271 | N/A | 27 | 0.00071478 | Tier 2 | 2026 | 2027 | 3.2 | 0 | 3.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Amador | Region 5 - Central Valley |  | Amador |  |  | v4 | 1765 | N/A | 218 | N/A | 32 | 0.00070065 | Tier 3 | 2026 | 2027 | 4 | 0 | 4 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | French Gulch | Shasta |  |  | v4 | 2518 | N/A | 262 | N/A | 36 | 7.8219e-05 | Tier 2 | 2026 | 2027 | 0.4 | 0 | 0.4 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast | Pope Valley | Napa |  |  | v4 | 614 | N/A | 389 | N/A | 37 | 0.00062891 | Tier 3 | 2026 | 2027 | 3.1 | 0 | 3.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Sonoma | Region 1 - North Coast |  | Sonoma |  |  | v4 | 272 | N/A | 374 | N/A | 50 | 0.0041052 | Tier 2 & 3 | 2026 | 2027 | 45.3 | 0 | 45.3 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra |  | Sierra |  |  | v4 | 1700 | N/A | 41 | N/A | 58 | 0.0026844 | Tier 3 | 2026 | 2027 | 18.7 | 0 | 18.7 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Fresno | Region 5 - Central Valley | Shaver Lake | Fresno |  |  | v4 | 490 | N/A | 235 | N/A | 66 | 2.9909e-05 | Tier 2 | 2026 | 2027 | 0.2 | 0 | 0.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Mariposa | Region 5 - Central Valley | Midpines | Mariposa |  |  | v4 | 700 | N/A | 199 | N/A | 73 | 0.00066072 | Tier 2 & 3 | 2026 | 2027 | 5.2 | 0 | 5.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | Clearlake | Lake |  |  | v4 | 27 | N/A | 29 | N/A | 85 | 0.00041028 | Tier 2 & 3 | 2026 | 2027 | 3.8 | 0 | 3.8 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley | Mountain Ranch | Calaveras |  |  | v4 |  | N/A | 331 | N/A | 88 | 0.0010416 | Tier 2 | 2026 | 2027 | 9 | 0 | 9 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Amador | Region 5 - Central Valley | Pioneer | Amador |  |  | v4 | 2447 | N/A | 233 | N/A | 91 | 0.0010977 | Tier 2 & 3 | 2026 | 2027 | 10.6 | 0 | 10.6 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Placer | Region 2 - North Valley and Sierra | Alta | Placer |  |  | v4 |  | N/A |  | N/A | 96 | 0.00077046 | Tier 3 | 2026 | 2027 | 4.1 | 0 | 4.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley | Jamestown | Tuolumne |  |  | v4 | 619 | N/A | 377 | N/A | 102 | 0.00053166 | Tier 2 | 2026 | 2027 | 5.3 | 0 | 5.3 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Sonoma | Region 1 - North Coast | Cazadero | Sonoma |  |  | v4 | 1366 | N/A | 1226 | N/A | 107 | 0.0023423 | Tier 2 & 3 | 2026 | 2027 | 25.3 | 0 | 25.3 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | North San Juan | Sierra |  |  | v4 | 1308 | N/A | 162 | N/A | 129 | 1.0922e-05 | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast |  | Lake |  |  | v4 | 58 | N/A | 486 | N/A | 130 | 3.2571e-05 | Tier 2 | 2026 | 2027 | 0.4 | 0 | 0.4 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Amador | Region 5 - Central Valley |  | Amador |  |  | v4 | 2334 | N/A | 6 | N/A | 165 | 0.00011421 | Tier 2 | 2026 | 2027 | 2.4 | 0 | 2.4 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley | MI Wuk Village | Tuolumne |  |  | v4 | 56 | N/A | 95 | N/A | 167 | 8.3634e-06 | Tier 2 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Kern | Region 5 - Central Valley | Lebec | Kern |  |  | v4 | 691 | N/A | 368 | N/A | 184 | 0.00013113 | Tier 2 | 2026 | 2027 | 1.5 | 0 | 1.5 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Mariposa | Region 5 - Central Valley | Mariposa | Mariposa |  |  | v4 | 187 | N/A | 531 | N/A | 191 | 8.7872e-05 | Tier 2 | 2026 | 2027 | 1.2 | 0 | 1.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast |  | Lake |  |  | v4 | 474 | N/A | 102 | N/A | 202 | 0.00069375 | Tier 2 & 3 | 2026 | 2027 | 11.5 | 0 | 11.5 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley | Murphys | Calaveras |  |  | v4 | 1412 | N/A | 66 | N/A | 210 | 0.00031228 | Tier 2 & 3 | 2026 | 2027 | 7.2 | 0 | 7.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Amador | Region 5 - Central Valley | Pioneer | Amador |  |  | v4 | 2589 | N/A | 352 | N/A | 219 | 2.0447e-05 | Tier 3 | 2026 | 2027 | 0.4 | 0 | 0.4 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley | Groveland | Tuolumne |  |  | v4 | 2550 | N/A | 67 | N/A | 224 | 0.00012715 | Tier 2 & 3 | 2026 | 2027 | 3.7 | 0 | 3.7 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | El Dorado | Region 2 - North Valley and Sierra |  | El Dorado |  |  | v4 | 2732 | N/A | 278 | N/A | 233 | 0.00031981 | Tier 3 | 2026 | 2027 | 5.7 | 0 | 5.7 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Kern | Region 5 - Central Valley | Lebec | Kern |  |  | v4 | 583 | N/A | 219 | N/A | 239 | 0.00049877 | Tier 2 | 2026 | 2027 | 10.2 | 0 | 10.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Placer | Region 2 - North Valley and Sierra | Foresthill | Placer |  |  | v4 | 1865 | N/A | 179 | N/A | 243 | 0.0013793 | Tier 3 | 2026 | 2027 | 23.4 | 0 | 23.4 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Placer | Region 2 - North Valley and Sierra | Alta | Placer |  |  | v4 | 2087 | N/A | 192 | N/A | 263 | 0.0014617 | Tier 3 | 2026 | 2027 | 25.3 | 0 | 25.3 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | Middletown | Lake |  |  | v4 | 915 | N/A | 56 | N/A | 277 | 4.8763e-05 | Tier 2 & 3 | 2026 | 2027 | 0.9 | 0 | 0.9 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast | Napa | Napa |  |  | v3 | 1224 | N/A | 255 | N/A | 307 | 0.0019167 | Tier 2 & 3 | 2026 | 2027 | 36.5 | 0 | 36.5 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Mariposa | Region 5 - Central Valley | Mariposa | Mariposa |  |  | v3 | 679 | N/A | 126 | N/A | 322 | 2.994e-05 | Tier 2 & 3 | 2026 | 2027 | 1.1 | 0 | 1.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Fresno | Region 5 - Central Valley | Auberry | Fresno |  |  | v2 | 330 | N/A | 734 | N/A | 325 | 1.0741e-05 | Tier 2 | 2026 | 2027 | 0.2 | 0 | 0.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Amador | Region 5 - Central Valley | Pioneer | Amador |  |  | v3 | 2468 | N/A | 107 | N/A | 368 | 6.5566e-05 | Tier 3 | 2026 | 2027 | 1.7 | 0 | 1.7 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast | Napa | Napa |  |  | v4 |  | N/A | 338 | N/A | 483 | 2.6947e-06 | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast | Calistoga | Napa |  |  | v3 | 1005 | N/A | 105 | N/A | 501 | 8.373e-05 | Tier 2 & 3 | 2026 | 2027 | 2.4 | 0 | 2.4 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Yuba | Region 2 - North Valley and Sierra | Brownsville | Yuba |  |  | v2 | 1428 | N/A | 408 | N/A | 789 | 0.0003247% | Tier 2 & 3 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | Middletown | Lake |  |  | v2 | 8 | N/A | 392 | N/A | 817 | 3.5605e-06 | Tier 2 | 2026 | 2027 | 0.2 | 0 | 0.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast | Calistoga | Napa |  |  | v3 |  | N/A | 134 | N/A | 858 | 8.7189e-07 | Tier 2 & 3 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Sonoma | Region 1 - North Coast |  | Sonoma |  |  | v2 | 1313 | N/A | 1448 | N/A | 891 | 7.362e-05% | Tier 2 & 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Mariposa | Region 5 - Central Valley | Mariposa | Mariposa |  |  | v3 | 655 | N/A | 504 | N/A | 940 | 3.0691e-06 | Tier 2 & 3 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | Clearlake | Lake |  |  | v2 | 74 | N/A | 1256 | N/A | 1104 | 0.0002244% | Tier 2 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Plumas | Region 2 - North Valley and Sierra | Canyon Dam | Plumas |  |  | v2 | 3328 | N/A | 969 | N/A | 3862 | 0.0002315% | Tier 2 | 2026 | 2027 | 0.5 | 0 | 0.5 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Redding | Shasta |  |  | v4 | 3032 | N/A | 153 | N/A | 7 | 3.4535e-06 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley | MI Wuk Village | Tuolumne |  |  | v4 | 911 | N/A | 335 | N/A | 8 | 2.052e-06 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Kern | Region 5 - Central Valley |  | Kern |  |  | v4 |  | N/A | 821 | N/A | 14 | 9.9021e-06 | Tier 2 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Oak Run | Shasta |  |  | v4 | 563 | N/A | 1190 | N/A | 25 | 6.5623e-07 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Nevada | Region 2 - North Valley and Sierra |  | Nevada |  |  | v4 | 323 | N/A | 136 | N/A | 26 | 6.7082e-07 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Redding | Shasta |  |  | v4 |  | N/A |  | N/A | 29 | 1.7759e-05 | Tier 3 | 2026 | 2027 | 0.2 | 0 | 0.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Contra Costa | Region 3 - Bay Area | Clayton | Contra Costa |  |  | v4 | 377 | N/A | 15 | N/A | 31 | 7.646e-05 | Tier 3 | 2026 | 2027 | 0.5 | 0 | 0.5 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Placer | Region 2 - North Valley and Sierra | Alta | Placer |  |  | v4 | 942 | N/A | 103 | N/A | 39 | 5.6978e-06 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Santa Cruz | Region 4 - South Bay and Central Coast |  | Santa Cruz |  |  | v4 |  | N/A |  | N/A | 40 | 5.5702e-07 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Santa Cruz | Region 4 - South Bay and Central Coast | Davenport | Santa Cruz |  |  | v4 | 226 | N/A | 2760 | N/A | 41 | 6.1227e-07 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Butte | Region 2 - North Valley and Sierra | Magalia | Butte |  |  | v4 | 1287 | N/A | 129 | N/A | 44 | 0.00041338 | Tier 3 | 2026 | 2027 | 2.7 | 0 | 2.7 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Redding | Shasta |  |  | v4 | 7 | N/A | 48 | N/A | 46 | 5.1474e-06 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Sonoma | Region 1 - North Coast | Cazadero | Sonoma |  |  | v4 | 365 | N/A | 1955 | N/A | 47 | 2.9956e-08 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Santa Barbara | Region 4 - South Bay and Central Coast |  | Santa Barbara |  |  | v4 | 462 | N/A | 650 | N/A | 59 | 1.1703e-05 | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Marin | Region 1 - North Coast | Mill Valley | Marin |  |  | v4 | 1714 | N/A | 680 | N/A | 60 | 0.00029163 | Tier 3 | 2026 | 2027 | 2.1 | 0 | 2.1 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley | Long Barn | Tuolumne |  |  | v4 | 3426 | N/A | 1283 | N/A | 61 | 1.7694e-06 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Kern | Region 5 - Central Valley | Lebec | Kern |  |  | v4 | 931 | N/A | 387 | N/A | 62 | 0.00010359 | Tier 2 | 2026 | 2027 | 0.4 | 0 | 0.4 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 3182 | N/A | 316 | N/A | 63 | 0.00026442 | Tier 2 | 2026 | 2027 | 2 | 0 | 2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 2320 | N/A | 394 | N/A | 65 | 0.0017062 | Tier 2 | 2026 | 2027 | 12.8 | 0 | 12.8 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 3139 | N/A | 224 | N/A | 67 | 6.2039e-07 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley | Sonora | Tuolumne |  |  | v4 | 2426 | N/A | 50 | N/A | 72 | 2.1316e-05 | Tier 3 | 2026 | 2027 | 0.3 | 0 | 0.3 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | Middletown | Lake |  |  | v4 |  | N/A | 160 | N/A | 74 | 2.5699e-06 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast | Angwin | Napa |  |  | v4 |  | N/A | 14 | N/A | 76 | 0.00031577 | Tier 3 | 2026 | 2027 | 2.7 | 0 | 2.7 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Sonoma | Region 1 - North Coast | Cazadero | Sonoma |  |  | v4 | 2061 | N/A | 1445 | N/A | 79 | 0.00047038 | Tier 3 | 2026 | 2027 | 4.2 | 0 | 4.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Santa Barbara | Region 4 - South Bay and Central Coast | Santa Barbara | Santa Barbara |  |  | v4 | 961 | N/A | 337 | N/A | 100 | 0.00029928 | Tier 3 | 2026 | 2027 | 3.2 | 0 | 3.2 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Santa Clara | Region 4 - South Bay and Central Coast |  | Santa Clara |  |  | v4 | 1444 | N/A | 424 | N/A | 80 | 0.00064938 | Tier 2 | 2027 | 2028 | 5.6 | 0 | 0 | 5.6
| TBD | SH | TBD | TBD | Pre-Scoping | Solano | Region 1 - North Coast |  | Solano |  |  | v4 |  | N/A |  | N/A | 87 | 0.00033332 | Tier 2 | 2027 | 2028 | 7.1 | 0 | 0 | 7.1
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast | Pope Valley | Napa |  |  | v4 |  | N/A |  | N/A | 89 | 1.4772e-06 | Tier 3 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Marin | Region 1 - North Coast |  | Marin |  |  | v4 | 1087 | N/A | 707 | N/A | 90 | 0.00050552 | Tier 3 | 2027 | 2028 | 4.7 | 0 | 0 | 4.7
| TBD | SH | TBD | TBD | Pre-Scoping | Tulare | Region 5 - Central Valley | Shaver Lake | Tulare |  |  | v4 | 2756 | N/A | 171 | N/A | 93 | 2.5115e-05 | Tier 2 | 2027 | 2028 | 0.2 | 0 | 0 | 0.2
| TBD | SH | TBD | TBD | Pre-Scoping | San Luis Obispo | Region 4 - South Bay and Central Coast | Midpines | San Luis Obispo |  |  | v4 | 1248 | N/A | 743 | N/A | 94 | 0.00078575 | Tier 3 | 2027 | 2028 | 6.9 | 0 | 0 | 6.9
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast | Clearlake | Napa |  |  | v4 |  | N/A | 616 | N/A | 95 | 0.0004604 | Tier 2 | 2027 | 2028 | 3.8 | 0 | 0 | 3.8
| TBD | SH | TBD | TBD | Pre-Scoping | Contra Costa | Region 3 - Bay Area | Pioneer | Contra Costa |  |  | v4 |  | N/A | 552 | N/A | 99 | 0.00030666 | Tier 3 | 2027 | 2028 | 3.2 | 0 | 0 | 3.2
| TBD | SH | TBD | TBD | Pre-Scoping | Plumas | Region 2 - North Valley and Sierra | Alta | Plumas |  |  | v4 | 1658 | N/A | 404 | N/A | 101 | 3.0626e-05 | Tier 3 | 2027 | 2028 | 0.5 | 0 | 0 | 0.5
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra |  | Shasta |  |  | v4 |  | N/A |  | N/A | 106 | 1.6317e-08 | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley | Cazadero | Calaveras |  |  | v4 | 1906 | N/A | 198 | N/A | 109 | 0.001558 | Tier 2 | 2027 | 2028 | 15.4 | 0 | 0 | 15.4
| TBD | SH | TBD | TBD | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | North San Juan | Sierra |  |  | v4 | 1446 | N/A | 254 | N/A | 112 | 0.00085737 | Tier 3 | 2027 | 2028 | 9.2 | 0 | 0 | 9.2
| TBD | SH | TBD | TBD | Pre-Scoping | Santa Clara | Region 4 - South Bay and Central Coast |  | Santa Clara |  |  | v4 |  | N/A | 724 | N/A | 116 | 0.00026357 | Tier 2 & 3 | 2027 | 2028 | 3.1 | 0 | 0 | 3.1
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast |  | Napa |  |  | v4 |  | N/A | 873 | N/A | 119 | 3.7104e-05 | Tier 3 | 2027 | 2028 | 0.7 | 0 | 0 | 0.7
| TBD | SH | TBD | TBD | Pre-Scoping | Monterey | Region 4 - South Bay and Central Coast | MI Wuk Village | Monterey |  |  | v4 |  | N/A | 1659 | N/A | 120 | 2.0704e-08 | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Humboldt | Region 1 - North Coast | Lebec | Humboldt |  |  | v4 | 2925 | N/A | 1284 | N/A | 124 | 2.497e-07 | Tier 3 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Contra Costa | Region 3 - Bay Area | Mariposa | Contra Costa |  |  | v4 |  | N/A | 100 | N/A | 126 | 9.7013e-06 | Tier 2 & 3 | 2027 | 2028 | 0.1 | 0 | 0 | 0.1
| TBD | SH | TBD | TBD | Pre-Scoping | Solano | Region 1 - North Coast |  | Solano |  |  | v4 | 92 | N/A | 423 | N/A | 128 | 5.1046e-05 | Tier 2 | 2027 | 2028 | 0.6 | 0 | 0 | 0.6
| TBD | SH | TBD | TBD | Pre-Scoping | El Dorado | Region 2 - North Valley and Sierra | Groveland | El Dorado |  |  | v4 | 1433 | N/A | 380 | N/A | 134 | 0.00044927 | Tier 2 & 3 | 2027 | 2028 | 5.5 | 0 | 0 | 5.5
| TBD | SH | TBD | TBD | Pre-Scoping | Solano | Region 1 - North Coast |  | Solano |  |  | v4 |  | N/A |  | N/A | 136 | 4.5565e-06 | Tier 2 | 2027 | 2028 | 0.1 | 0 | 0 | 0.1
| TBD | SH | TBD | TBD | Pre-Scoping | Nevada | Region 2 - North Valley and Sierra | Lebec | Nevada |  |  | v4 | 167 | N/A | 173 | N/A | 137 | 1.0268e-06 | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Foresthill | Shasta |  |  | v4 | 1743 | N/A | 88 | N/A | 142 | 4.0188e-08 | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Marin | Region 1 - North Coast | Alta | Marin |  |  | v4 | 1323 | N/A | 1368 | N/A | 143 | 0.00024094 | Tier 2 & 3 | 2027 | 2028 | 3 | 0 | 0 | 3
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley | Middletown | Calaveras |  |  | v4 | 1530 | N/A | 154 | N/A | 144 | 0.0010809 | Tier 2 & 3 | 2027 | 2028 | 13.6 | 0 | 0 | 13.6
| TBD | SH | TBD | TBD | Pre-Scoping | Sonoma | Region 1 - North Coast | Napa | Sonoma |  |  | v4 |  | N/A | 1095 | N/A | 145 | 3.8741e-05 | Tier 3 | 2027 | 2028 | 0.5 | 0 | 0 | 0.5
| TBD | SH | TBD | TBD | Pre-Scoping | Yolo | Region 2 - North Valley and Sierra | Mariposa | Yolo |  |  | v4 | 293 | N/A | 11040 | N/A | 146 | 3.6113e-07 | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | El Dorado | Region 2 - North Valley and Sierra | Auberry | El Dorado |  |  | v4 | 1934 | N/A | 197 | N/A | 147 | 0.0016329 | Tier 2 & 3 | 2027 | 2028 | 20.9 | 0 | 0 | 20.9
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | Pioneer | Lake |  |  | v4 | 1803 | N/A | 332 | N/A | 148 | 0.00019554 | Tier 2 | 2027 | 2028 | 2.5 | 0 | 0 | 2.5
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Napa | Shasta |  |  | v4 | 2329 | N/A | 402 | N/A | 149 | 8.9499e-05 | Tier 2 | 2027 | 2028 | 1.2 | 0 | 0 | 1.2
| TBD | SH | TBD | TBD | Pre-Scoping | Amador | Region 5 - Central Valley | Calistoga | Amador |  |  | v4 | 1088 | N/A | 251 | N/A | 154 | 0.00050584 | Tier 2 | 2027 | 2028 | 6.4 | 0 | 0 | 6.4
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley | Brownsville | Tuolumne |  |  | v4 | 3063 | N/A | 1527 | N/A | 155 | 8.0182e-08 | Tier 3 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Middletown | Shasta |  |  | v4 | 1674 | N/A | 210 | N/A | 156 | 3.8557e-05 | Tier 2 | 2027 | 2028 | 0.5 | 0 | 0 | 0.5
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley | Calistoga | Calaveras |  |  | v4 | 1941 | N/A | 260 | N/A | 157 | 0.0014484 | Tier 2 & 3 | 2027 | 2028 | 17.8 | 0 | 0 | 17.8
| TBD | SH | TBD | TBD | Pre-Scoping | El Dorado | Region 2 - North Valley and Sierra |  | El Dorado |  |  | v4 | 1646 | N/A | 236 | N/A | 158 | 0.0015393 | Tier 2 & 3 | 2027 | 2028 | 20.2 | 0 | 0 | 20.2
| TBD | SH | TBD | TBD | Pre-Scoping | Santa Barbara | Region 4 - South Bay and Central Coast | Mariposa | Santa Barbara |  |  | v4 | 853 | N/A | 1033 | N/A | 161 | 0.00071061 | Tier 2 & 3 | 2027 | 2028 | 8.6 | 0 | 0 | 8.6
| TBD | SH | TBD | TBD | Pre-Scoping | Placer | Region 2 - North Valley and Sierra | Clearlake | Placer |  |  | v4 |  | N/A | 1420 | N/A | 162 | 0.0010053 | Tier 2 | 2027 | 2028 | 13.3 | 0 | 0 | 13.3
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | MI Wuk Village | Shasta |  |  | v4 | 1251 | N/A | 220 | N/A | 168 | 0.0012028 | Tier 2 | 2027 | 2028 | 16.5 | 0 | 0 | 16.5
| TBD | SH | TBD | TBD | Pre-Scoping | Mendocino | Region 1 - North Coast |  | Mendocino |  |  | v4 | 1623 | N/A | 638 | N/A | 169 | 9.0265e-05 | Tier 2 | 2027 | 2028 | 1.2 | 0 | 0 | 1.2
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Oak Run | Shasta |  |  | v4 |  | N/A |  | N/A | 172 | 2.2707e-05 | Tier 2 | 2027 | 2028 | 0.3 | 0 | 0 | 0.3
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley |  | Calaveras |  |  | v4 | 1696 | N/A | 206 | N/A | 173 | 0.00067438 | Tier 3 | 2027 | 2028 | 9.3 | 0 | 0 | 9.3
| TBD | SH | TBD | TBD | Pre-Scoping | Mendocino | Region 1 - North Coast | Redding | Mendocino |  |  | v4 | 3082 | N/A | 1825 | N/A | 174 | 7.0949e-09 | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Mariposa | Region 5 - Central Valley | Clayton | Mariposa |  |  | v4 | 503 | N/A |  | N/A | 177 | 2.3684e-05 | Tier 2 | 2027 | 2028 | 0.7 | 0 | 0 | 0.7
| TBD | SH | TBD | TBD | Pre-Scoping | Fresno | Region 5 - Central Valley | French Gulch | Fresno |  |  | v4 | 286 | N/A | 113 | N/A | 181 | 3.581e-05 | Tier 2 & 3 | 2027 | 2028 | 0.5 | 0 | 0 | 0.5
| TBD | SH | TBD | TBD | Pre-Scoping | Nevada | Region 2 - North Valley and Sierra | Alta | Nevada |  |  | v4 | 606 | N/A | 141 | N/A | 183 | 3.1742e-05 | Tier 2 & 3 | 2027 | 2028 | 0.5 | 0 | 0 | 0.5
| TBD | SH | TBD | TBD | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Davenport | Sierra |  |  | v4 |  | N/A |  | N/A | 186 | 1.5273e-05 | Tier 3 | 2027 | 2028 | 0.6 | 0 | 0 | 0.6
| TBD | SH | TBD | TBD | Pre-Scoping | Butte | Region 2 - North Valley and Sierra | Magalia | Butte |  |  | v4 | 2943 | N/A | 201 | N/A | 187 | 0.00014028 | Tier 3 | 2027 | 2028 | 2.3 | 0 | 0 | 2.3
| TBD | SH | TBD | TBD | Pre-Scoping | Contra Costa | Region 3 - Bay Area | Redding | Contra Costa |  |  | v4 |  | N/A | 223 | N/A | 190 | 0.00070198 | Tier 3 | 2027 | 2028 | 9.7 | 0 | 0 | 9.7
| TBD | SH | TBD | TBD | Pre-Scoping | Yolo | Region 2 - North Valley and Sierra | French Gulch | Yolo |  |  | v4 | 515 | N/A | 2094 | N/A | 195 | 2.8778e-06 | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Placer | Region 2 - North Valley and Sierra | Jamestown | Placer |  |  | v4 | 1885 | N/A | 120 | N/A | 197 | 7.1614e-06 | Tier 2 | 2027 | 2028 | 0.1 | 0 | 0 | 0.1
| TBD | SH | TBD | TBD | Pre-Scoping | El Dorado | Region 2 - North Valley and Sierra |  | El Dorado |  |  | v4 |  | N/A |  | N/A | 198 | 5.9914e-05 | Tier 2 | 2027 | 2028 | 1 | 0 | 0 | 1
| TBD | SH | TBD | TBD | Pre-Scoping | Sonoma | Region 1 - North Coast | Mill Valley | Sonoma |  |  | v4 |  | N/A |  | N/A | 199 | 0.00040187 | Tier 2 & 3 | 2027 | 2028 | 5.8 | 0 | 0 | 5.8
| TBD | SH | TBD | TBD | Pre-Scoping | Sonoma | Region 1 - North Coast | Long Barn | Sonoma |  |  | v4 | 2477 | N/A | 1481 | N/A | 200 | 5.0622e-08 | Tier 3 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 1495 | N/A | 539 | N/A | 205 | 2.2665e-05 | Tier 2 | 2027 | 2028 | 0.3 | 0 | 0 | 0.3
| TBD | SH | TBD | TBD | Pre-Scoping | Santa Clara | Region 4 - South Bay and Central Coast | Montgomery Creek | Santa Clara |  |  | v4 |  | N/A | 1002 | N/A | 206 | 0.00045136 | Tier 3 | 2027 | 2028 | 6.7 | 0 | 0 | 6.7
| TBD | SH | TBD | TBD | Pre-Scoping | Marin | Region 1 - North Coast | Montgomery Creek | Marin |  |  | v4 | 1663 | N/A | 648 | N/A | 207 | 8.4676e-05 | Tier 3 | 2027 | 2028 | 1.3 | 0 | 0 | 1.3
| TBD | SH | TBD | TBD | Pre-Scoping | Nevada | Region 2 - North Valley and Sierra | Middletown | Nevada |  |  | v4 |  | N/A |  | N/A | 212 | 3.9459e-06 | Tier 3 | 2027 | 2028 | 0.1 | 0 | 0 | 0.1
| TBD | SH | TBD | TBD | Pre-Scoping | Mariposa | Region 5 - Central Valley | Angwin | Mariposa |  |  | v4 | 1036 | N/A | 263 | N/A | 213 | 0.00016954 | Tier 2 | 2027 | 2028 | 2.5 | 0 | 0 | 2.5
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra | Cazadero | Shasta |  |  | v4 | 456 | N/A | 119 | N/A | 216 | 1.4951e-07 | Tier 3 | 2027 | 2028 | 0 | 0 | 0 | 0
| TBD | SH | TBD | TBD | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Santa Barbara | Sierra |  |  | v4 | 1944 | N/A | 953 | N/A | 217 | 2.043e-05 | Tier 3 | 2027 | 2028 | 0.3 | 0 | 0 | 0.3
| TBD | SH | TBD | TBD | Pre-Scoping | Tehama | Region 2 - North Valley and Sierra | Jamestown | Tehama |  |  | v4 | 157 | N/A | 280 | N/A | 220 | 2.9604e-05 | Tier 2 | 2027 | 2028 | 0.5 | 0 | 0 | 0.5
| TBD | SH | TBD | TBD | Pre-Scoping | Napa | Region 1 - North Coast |  | Napa |  |  | v4 |  | N/A |  | N/A | 221 | 0.001267 | Tier 2 & 3 | 2027 | 2028 | 20.1 | 0 | 0 | 20.1
| TBD | SH | TBD | TBD | Pre-Scoping | Yuba | Region 2 - North Valley and Sierra |  | Yuba |  |  | v4 | 1693 | N/A | 465 | N/A | 225 | 0.00085121 | Tier 3 | 2027 | 2028 | 14.1 | 0 | 0 | 14.1
| TBD | SH | TBD | TBD | Pre-Scoping | El Dorado | Region 2 - North Valley and Sierra |  | El Dorado |  |  | v4 | 1946 | N/A | 49 | N/A | 226 | 0.00012652 | Tier 2 & 3 | 2027 | 2028 | 2.1 | 0 | 0 | 2.1
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley |  | Calaveras |  |  | v4 | 1160 | N/A | 243 | N/A | 234 | 0.00021574 | Tier 2 & 3 | 2027 | 2028 | 3.5 | 0 | 0 | 3.5
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley |  | Tuolumne |  |  | v4 | 1716 | N/A | 296 | N/A | 235 | 0.0013846 | Tier 2 | 2027 | 2028 | 22.8 | 0 | 0 | 22.8
| TBD | SH | TBD | TBD | Pre-Scoping | Shasta | Region 2 - North Valley and Sierra |  | Shasta |  |  | v4 | 624 | N/A | 345 | N/A | 236 | 0.0012713 | Tier 2 & 3 | 2027 | 2028 | 20.8 | 0 | 0 | 20.8
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | French Gulch | Lake |  |  | v4 | 27 | N/A | 29 | N/A | 85 | 0.0012154 | Tier 2 & 3 | 2027 | 2028 | 11.3 | 0 | 0 | 11.3
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley |  | Calaveras |  |  | v4 |  | N/A | 331 | N/A | 88 | 0.0017374 | Tier 2 | 2027 | 2028 | 15 | 0 | 0 | 15
| TBD | SH | TBD | TBD | Pre-Scoping | Amador | Region 5 - Central Valley |  | Amador |  |  | v4 | 2447 | N/A | 233 | N/A | 91 | 7.7389e-05 | Tier 2 & 3 | 2027 | 2028 | 0.8 | 0 | 0 | 0.8
| TBD | SH | TBD | TBD | Pre-Scoping | Placer | Region 2 - North Valley and Sierra | Mountain Ranch | Placer |  |  | v4 |  | N/A |  | N/A | 96 | 5.8167e-05 | Tier 3 | 2027 | 2028 | 2.2 | 0 | 0 | 2.2
| TBD | SH | TBD | TBD | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Murphys | Sierra |  |  | v4 | 1308 | N/A | 162 | N/A | 129 | 3.3341e-05 | Tier 3 | 2027 | 2028 | 0.4 | 0 | 0 | 0.4
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | Pioneer | Lake |  |  | v4 | 58 | N/A | 486 | N/A | 130 | 0.00039297 | Tier 2 | 2027 | 2028 | 4.9 | 0 | 0 | 4.9
| TBD | SH | TBD | TBD | Pre-Scoping | Amador | Region 5 - Central Valley | Canyon Dam | Amador |  |  | v4 | 2334 | N/A | 6 | N/A | 165 | 9.9008e-05 | Tier 2 | 2027 | 2028 | 2.1 | 0 | 0 | 2.1
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley | Redding | Tuolumne |  |  | v4 | 56 | N/A | 95 | N/A | 167 | 0.00011415 | Tier 2 | 2027 | 2028 | 1.9 | 0 | 0 | 1.9
| TBD | SH | TBD | TBD | Pre-Scoping | Kern | Region 5 - Central Valley |  | Kern |  |  | v4 | 691 | N/A | 368 | N/A | 184 | 7.8897e-05 | Tier 2 | 2027 | 2028 | 0.9 | 0 | 0 | 0.9
| TBD | SH | TBD | TBD | Pre-Scoping | Mariposa | Region 5 - Central Valley | Cazadero | Mariposa |  |  | v4 | 187 | N/A | 531 | N/A | 191 | 0.00041738 | Tier 2 | 2027 | 2028 | 5.8 | 0 | 0 | 5.8
| TBD | SH | TBD | TBD | Pre-Scoping | Lake | Region 1 - North Coast | Lebec | Lake |  |  | v4 | 474 | N/A | 102 | N/A | 202 | 0.00094951 | Tier 2 & 3 | 2027 | 2028 | 15.7 | 0 | 0 | 15.7
| TBD | SH | TBD | TBD | Pre-Scoping | Calaveras | Region 5 - Central Valley | Sonora | Calaveras |  |  | v4 | 1412 | N/A | 66 | N/A | 210 | 0.00055242 | Tier 2 & 3 | 2027 | 2028 | 12.8 | 0 | 0 | 12.8
| TBD | SH | TBD | TBD | Pre-Scoping | Tuolumne | Region 5 - Central Valley |  | Tuolumne |  |  | v4 | 2550 | N/A | 67 | N/A | 224 | 0.00026022 | Tier 2 & 3 | 2027 | 2028 | 7.7 | 0 | 0 | 7.7
| TBD | SH | TBD | TBD | Pre-Scoping | El Dorado | Region 2 - North Valley and Sierra |  | El Dorado |  |  | v4 | 2732 | N/A | 278 | N/A | 233 | 6.3607e-06 | Tier 3 | 2027 | 2028 | 0.1 | 0 | 0 | 0.1

## Definitions
Definitions
Category
Category Type | Description
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds
FRRB - Fire Rebuild | System Hardening Scope as a result of fires in HFTD
Other | Non-08W projects (New Business, WRO, Capacity, Rule 20A, etc.)
SH - System Hardening | Planned projects in the base System Hardening (SH) program
TBD | Circuit segments have been identified, however, projects have not yet been scoped and separated into subprojects at the order-level
MAT Code
MAT Code | Description
08W | System Hardening Wildfire Resiliency Projects
30A | Rule 20A: Undergrounding Capital Projects
3UG | Targeted Undergrounding
95F | Electric Distribution Major Emergency
TBD | Circuit segments have been identified, however, projects have not yet been scoped and separated into subprojects at the order-level
SAP Status and Status
SAP Status | Status
N/A | Pre-scoping
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | * In-Construction
DOCC | * Post-Construction
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles
Location
Lat / Long
Latitude / Longitude | ∙ Latitude is how far north or south a location is from the Equator. ∙ Longitude is how far east or west a location is from the Prime Meridian. ∙ For subprojects (orders) that are scoped (currently 2026 work), the location of the lat/long is anywhere on the alignment of the subproject. ∙ If a subproject is not yet scoped (currently 2027-28 work), the lat/long is not provided, as this information is not yet available.
Risk Rank | Results of the relevant risk model (e.g. WDRM v2, WDRM v3, WDRM v4) where circuit segments are ranked on a 1 to N basis, where 1 is the highest risk circuit segment, and N is the lowest risk.
Estimated Wildfire Risk Reduction | Estimated wildfire risk provides the estimated risk reduction for each subproject. The risk reduction reported includes the reduction of additional mitigations on that subproject, if relevant (i.e., if a subproject has undergrounding, overhead hardening and line removal, the risk reduction includes all mitigations).
Total Planned UG Miles | Total undergrounding miles planned on a subproject, which can extend before or after the 2026-28 time period included in this workplan.