## GH-12 Workplan 2026-28
PG&E 2026-28 Overheard Hardening and Line Removal Workplan (GH-12)
Data as of March 31, 2025
[14 empty] | 0.3952% |  | 4.012% |  | 1.755% |  |  | Total | 296.4 | 24.2 | 294.3 | 24.4 | 0 | 0 | 0 | 0
Circuit Protection Zone | Order | Category | MAT Code | SAP Status | Status | Division | Regions | City | County | Latitude | Longitude | Applicable Risk Model | Risk Rank (V2) | Est. Wildfire Risk Reduction (V2) | Risk Rank (V3) | Est. Wildfire Risk Reduction (V3) | Risk Rank (V4) | Est. Wildfire Risk Reduction (V4) | HFTD Tier | Start Year | End Year | Total Planned OH Miles | Total Planned Removal Miles | 2026 Forecast OH Miles | 2026 Forecast Removal Miles | 2027 Forecast OH Miles | 2027 Forecast Removal Miles | 2028 Forecast OH Miles | 2028 Forecast Removal Miles
| 35572406 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | v3 | 0 | 0 | 126 | 0.00015737 | 322 | 0.002899% | Tier 3 | 2026 | 2026 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0
| 35544698 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 7.45847e-07 | 120 | 2.47976e-05 | 108 | 0.001629% | Tier 3 | 2026 | 2026 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0
| 35544720 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 1.81791e-06 | 120 | 5.9001e-05 | 108 | 0.002171% | Tier 3 | 2026 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35544721 | SH | 08W | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 1.47361e-06 | 120 | 4.71442e-05 | 108 | 0.001086% | Tier 3 | 2026 | 2026 | 0.2 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0
| 35544722 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 1.31192e-06 | 120 | 4.21762e-05 | 108 | 0.001086% | Tier 3 | 2026 | 2026 | 0.2 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0
| 35544723 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 3.01867e-06 | 120 | 9.46541e-05 | 108 | 0% | Tier 3 | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35544724 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 4.34947e-06 | 120 | 0.00013621 | 108 | 0% | Tier 3 | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35522102 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Downieville | SIERRA |  |  | v3 | 1885 | 1.75057e-06 | 120 | 5.56109e-05 | 108 | 0.001086% | Tier 3 | 2026 | 2026 | 0.2 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0
| 35546588 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 1791 | 6.91286e-06 | 143 | 0.00018982 | 1015 | 0.002551% | Tier 2 & 3 | 2026 | 2026 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0
| 35546590 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 1791 | 5.43238e-06 | 143 | 0.0001431 | 1015 | 0.0002686% | Tier 2 & 3 | 2025 | 2026 | 0.2 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0
| 35546591 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 1791 | 4.45281e-06 | 143 | 0.00011859 | 1015 | 0.0005371% | Tier 2 & 3 | 2026 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35522105 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 1791 | 7.54138e-06 | 143 | 0.00020708 | 1015 | 0.002686% | Tier 2 & 3 | 2026 | 2026 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 35526463 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Lakehead | SHASTA |  |  | v3 | 2207 | 2.08305e-06 | 94 | 0.00012718 | 470 | 0.0008304% | Tier 2 | 2025 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35277921 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | v2 | 163 | 0.00020299 | 569 | 6.80931e-05 | 458 | 0.007532% | Tier 2 | 2026 | 2026 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
| 35277922 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | v2 | 163 | 0.00013304 | 569 | 4.45849e-05 | 458 | 0.004821% | Tier 2 | 2026 | 2026 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0
| 35254243 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | v2 | 163 | 0.00023555 | 569 | 7.9015e-05 | 458 | 0.008737% | Tier 2 | 2026 | 2026 | 2.9 | 0 | 2.9 | 0 | 0 | 0 | 0 | 0
| 35254247 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | v2 | 163 | 0.00015784 | 569 | 5.29482e-05 | 458 | 0.006026% | Tier 2 | 2026 | 2026 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 35278890 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | v2 | 163 | 0.00014933 | 569 | 4.95206e-05 | 458 | 0.004821% | Tier 2 | 2026 | 2026 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0
| 35278891 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | v2 | 163 | 0.00020237 | 569 | 6.78823e-05 | 458 | 0.007532% | Tier 2 | 2026 | 2026 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
| 35278892 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Tollhouse | FRESNO |  |  | v2 | 163 | 0.00020681 | 569 | 6.91993e-05 | 458 | 0.007532% | Tier 2 | 2026 | 2026 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
| 35544232 | SH | 08W | ESTS | Estimating | Fresno | Region 5 - Central Valley | Shaver Lake | FRESNO |  |  | v3 | 136 | 0 | 5 | 0.00021833 | 10 | 0.04834% | Tier 2 | 2026 | 2026 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0
| 35519791 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Shaver Lake | FRESNO |  |  | v3 | 136 | 0 | 5 | 0.00034103 | 10 | 0.07653% | Tier 2 | 2026 | 2026 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0
| 35519778 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Shaver Lake | FRESNO |  |  | v3 | 136 | 0 | 84 | 0.00018788 | 11 | 0.05396% | Tier 2 | 2026 | 2026 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0
| 35544233 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Shaver Lake | FRESNO |  |  | v3 | 136 | 0 | 84 | 0.00024307 | 11 | 0.07083% | Tier 2 | 2026 | 2026 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0
| 35519776 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 844 | 5.07425e-05 | 76 | 0.00030721 | 431 | 0.008222% | Tier 2 | 2026 | 2026 | 2.4 | 0.1 | 2.4 | 0.1 | 0 | 0 | 0 | 0
| 35547351 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 844 | 4.89441e-05 | 76 | 0.00028776 | 431 | 0.001916% | Tier 2 | 2025 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35547347 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 165 | 0.00010472 | 125 | 0.00020268 | 362 | 0.006528% | Tier 2 | 2026 | 2026 | 1.9 | 0.1 | 1.9 | 0.1 | 0 | 0 | 0 | 0
| 35547348 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 165 | 9.05911e-05 | 125 | 0.00017555 | 362 | 0.005559% | Tier 2 | 2026 | 2026 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0
| 35547350 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 165 | 0.0001226 | 125 | 0.00023757 | 362 | 0.007521% | Tier 2 | 2026 | 2026 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0
| 35519789 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 165 | 0.00011229 | 125 | 0.0002176 | 362 | 0.006867% | Tier 2 | 2026 | 2026 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0
| 35519769 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | v3 | 1152 | 8.60209e-06 | 53 | 0.00036627 | 153 | 0.01039% | Tier 2 | 2026 | 2026 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0
| 35519770 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | v3 | 1152 | 1.44464e-06 | 53 | 6.15118e-05 | 153 | 0.001599% | Tier 2 | 2026 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35547196 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | v3 | 1152 | 4.43232e-06 | 53 | 0.00018873 | 153 | 0.005597% | Tier 2 | 2026 | 2026 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0
| 35547197 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 5.02336e-06 | 53 | 0.00021389 | 153 | 0.005997% | Tier 2 | 2025 | 2026 | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
| 35547198 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 3.71008e-06 | 53 | 0.00015797 | 153 | 0.004398% | Tier 2 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35547199 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 4.49527e-06 | 53 | 0.0001842 | 153 | 0.002798% | Tier 2 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35547340 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 4.0712e-06 | 53 | 0.00017335 | 153 | 0.004797% | Tier 2 | 2026 | 2026 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0
| 35547341 | SH | 08W | ADER | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 4.26816e-06 | 53 | 0.00018174 | 153 | 0.005197% | Tier 2 | 2026 | 2026 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0
| 35547342 | SH | 08W | ADER | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 3.93984e-06 | 53 | 0.00016776 | 153 | 0.004797% | Tier 2 | 2026 | 2026 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0
| 35547343 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 4.64675e-06 | 53 | 0.00019707 | 153 | 0.005318% | Tier 2 | 2026 | 2026 | 1.3 | 0.1 | 1.3 | 0.1 | 0 | 0 | 0 | 0
| 35547344 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 2.4296e-06 | 53 | 0.00010345 | 153 | 0.002798% | Tier 2 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35547345 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 2.33107e-06 | 53 | 9.92563e-05 | 153 | 0.002798% | Tier 2 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35547346 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Coulterville | MARIPOSA |  |  | v3 | 1152 | 3.51303e-06 | 53 | 0.00014958 | 153 | 0.004398% | Tier 2 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35519782 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Oroville | BUTTE |  |  | v3 | 1246 | 7.68667e-06 | 108 | 7.18111e-05 | 404 | 0.002134% | Tier 3 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35554840 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Oroville | BUTTE |  |  | v3 | 1246 | 2.90319e-05 | 108 | 0.00026541 | 404 | 0.007126% | Tier 3 | 2026 | 2026 | 1.6 | 0.3 | 1.6 | 0.3 | 0 | 0 | 0 | 0
| 35396566 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Oroville | BUTTE |  |  | v3 | 1608 | 1.48696e-05 | 318 | 0.00012845 | 182 | 0.01752% | Tier 3 | 2025 | 2026 | 0 | 1.8 | 0 | 1.8 | 0 | 0 | 0 | 0
| 35374564 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Twain | PLUMAS |  |  | v3 | 378 | 4.07469e-05 | 45 | 0.00027589 | 12 | 6.069e-05% | Tier 2 | 2025 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35430879 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Twain | PLUMAS |  |  | v3 | 378 | 2.45248e-05 | 45 | 0.00016549 | 12 | 4.248e-05% | Tier 2 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35430880 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Twain | PLUMAS |  |  | v3 | 378 | 6.01403e-05 | 45 | 0.00039844 | 12 | 2.427e-05% | Tier 2 | 2026 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35542493 | SH | 08W | ESTS | Estimating | North Bay | Region 1 - North Coast | Calistoga | NAPA |  |  | v3 | 1093 | 0 | 134 | 6.52134e-05 | 858 | 0.005688% | Tier 2 & 3 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35542494 | SH | 08W | PEND | Permitting/Dependency | North Bay | Region 1 - North Coast | Pope Valley | NAPA |  |  | v3 | 1093 | 0 | 134 | 8.06352e-05 | 858 | 0.007815% | Tier 2 & 3 | 2026 | 2026 | 0.5 | 0.3 | 0.5 | 0.3 | 0 | 0 | 0 | 0
| 35543589 | SH | 08W | ESTS | Estimating | North Bay | Region 1 - North Coast | Calistoga | NAPA |  |  | v3 | 1093 | 0 | 134 | 0.0001257 | 858 | 0.01056% | Tier 2 & 3 | 2026 | 2026 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0
| 35543590 | SH | 08W | ESTS | Estimating | North Bay | Region 1 - North Coast | Calistoga | NAPA |  |  | v3 | 1093 | 0 | 134 | 9.73483e-05 | 858 | 0.008126% | Tier 2 & 3 | 2026 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35543591 | SH | 08W | PEND | Permitting/Dependency | North Bay | Region 1 - North Coast | Calistoga | NAPA |  |  | v3 | 1093 | 0 | 134 | 5.19805e-05 | 858 | 0.004876% | Tier 2 & 3 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35544680 | SH | 08W | PEND | Permitting/Dependency | North Bay | Region 1 - North Coast | Calistoga | NAPA |  |  | v3 | 1093 | 0 | 134 | 4.2431e-05 | 858 | 0.004501% | Tier 3 | 2026 | 2026 | 0.4 | 0.1 | 0.4 | 0.1 | 0 | 0 | 0 | 0
| 35379381 | SH | 3UG | PEND | Permitting/Dependency | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00022857 | 56 | 0.02316% | Tier 2 & 3 | 2026 | 2026 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 35557830 | SH | 08W | ESTS | Estimating | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00024006 | 56 | 0.02663% | Tier 2 & 3 | 2025 | 2026 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0
| 35557833 | SH | 08W | ESTS | Estimating | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00029425 | 56 | 0.03242% | Tier 2 & 3 | 2025 | 2026 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0
| 35557885 | SH | 08W | ESTS | Estimating | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00029349 | 56 | 0.03242% | Tier 2 & 3 | 2025 | 2026 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0
| 35557886 | SH | 08W | ESTS | Estimating | Diablo | Region 3 - Bay Area | Brentwood | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00022272 | 56 | 0.02431% | Tier 2 | 2026 | 2026 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0
| 35557887 | SH | 08W | APPR | Estimating | Diablo | Region 3 - Bay Area | Brentwood | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00028308 | 56 | 0.03126% | Tier 2 | 2026 | 2026 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0
| 35522100 | SH | 08W | PEND | Permitting/Dependency | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00030493 | 56 | 0.03358% | Tier 2 | 2026 | 2026 | 2.9 | 0 | 2.9 | 0 | 0 | 0 | 0 | 0
| 35521819 | SH | 08W | ESTS | Estimating | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00028427 | 56 | 0.03126% | Tier 2 & 3 | 2026 | 2026 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0
| 35434253 | SH | 3UG | PEND | Permitting/Dependency | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.00029245 | 56 | 0.03937% | Tier 2 & 3 | 2026 | 2026 | 3.4 | 0 | 3.4 | 0 | 0 | 0 | 0 | 0
| 35434254 | SH | 3UG | PEND | Permitting/Dependency | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 0.0002759 | 56 | 0.03156% | Tier 2 & 3 | 2026 | 2026 | 2.4 | 0.2 | 2.4 | 0.2 | 0 | 0 | 0 | 0
| 35434255 | SH | 3UG | PEND | Permitting/Dependency | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 400 | 0 | 115 | 6.34856e-05 | 56 | 0.009262% | Tier 2 & 3 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35433371 | SH | 3UG | ESTS | Estimating | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 377 | 0.00013499 | 15 | 0.00058989 | 31 | 0.03414% | Tier 3 | 2026 | 2026 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| 35385802 | SH | 3UG | PEND | Permitting/Dependency | Diablo | Region 3 - Bay Area | Clayton | CONTRA COSTA |  |  | v3 | 377 | 9.32121e-05 | 15 | 0.0004005 | 31 | 0.02429% | Tier 3 | 2026 | 2026 | 1.7 | 0.3 | 1.7 | 0.3 | 0 | 0 | 0 | 0
| 35545295 | SH | 08W | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | NEVADA |  |  | v3 | 408 | 9.41121e-05 | 75 | 0.0002503 | 454 | 0.00403% | Tier 2 | 2026 | 2026 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0
| 35545296 | SH | 08W | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | NEVADA |  |  | v3 | 408 | 6.14887e-05 | 75 | 0.00016396 | 454 | 0.002879% | Tier 2 | 2026 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35545297 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | North San Juan | NEVADA |  |  | v3 | 408 | 4.5109e-05 | 75 | 0.00012175 | 454 | 0.002879% | Tier 2 | 2026 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35545298 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | North San Juan | NEVADA |  |  | v3 | 408 | 3.42236e-05 | 75 | 9.23403e-05 | 454 | 0.002303% | Tier 2 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35545299 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | NEVADA |  |  | v3 | 408 | 4.83934e-05 | 75 | 0.00012994 | 454 | 0.002879% | Tier 2 | 2026 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35334230 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Corning | TEHAMA |  |  | v2 | 413 | 0.00010025 | 694 | 0.00011861 | 1269 | 0.01007% | Tier 2 | 2025 | 2026 | 0 | 3.7 | 0 | 3.7 | 0 | 0 | 0 | 0
| 35380374 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Covelo | TEHAMA |  |  | v2 | 413 | 4.58863e-05 | 694 | 5.98996e-05 | 1269 | 0.005561% | Tier 2 | 2026 | 2026 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
| 35380375 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Covelo | TEHAMA |  |  | v2 | 413 | 3.3554e-05 | 694 | 4.38012e-05 | 1269 | 0.004226% | Tier 2 | 2026 | 2026 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0
| 35519764 | SH | 08W | PEND | Permitting/Dependency | Yosemite | Region 5 - Central Valley | Sonora | TUOLUMNE |  |  | v3 | 1062 | 2.04821e-05 | 34 | 0.00029818 |  | 0.02171% | Tier 2 | 2026 | 2026 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 35544236 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 1062 | 1.8599e-05 | 34 | 0.00027077 |  | 0.01954% | Tier 2 | 2026 | 2026 | 1.8 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0
| 35544237 | SH | 08W | ADER | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 1062 | 5.34799e-06 | 34 | 7.78571e-05 |  | 0.005427% | Tier 2 | 2026 | 2026 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| 35547191 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 2550 | 1.17285e-06 | 67 | 0.00023335 | 224 | 0% | Tier 2 | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35548785 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Alta | PLACER |  |  | v3 | 942 | 1.28335e-05 | 103 | 8.61854e-05 | 39 | 0.005798% | Tier 3 | 2026 | 2026 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| 35519781 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Alta | PLACER |  |  | v3 | 942 | 1.98691e-05 | 103 | 0.00013762 | 39 | 0.01623% | Tier 3 | 2026 | 2026 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0
| 35524571 | SH | 08W | PEND | Permitting/Dependency | Fresno | Region 5 - Central Valley | Woodlake | TULARE |  |  | v3 | 2774 | 2.63704e-07 | 482 | 0.00012924 | 680 | 0.01059% | Tier 2 | 2024 | 2026 | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0
| 35519763 | SH | 08W | ESTS | Estimating | Stockton | Region 5 - Central Valley | Jackson | AMADOR |  |  | v3 | 1414 | 5.89528e-06 | 28 | 0.00040921 | 23 | 0.03843% | Tier 2 | 2026 | 2026 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0
| 35519779 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Stonyford | COLUSA |  |  | v3 | 360 | 8.18609e-05 | 85 | 0.00034225 | 306 | 0.01286% | Tier 2 | 2026 | 2026 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| 35553433 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Stonyford | COLUSA |  |  | v3 | 360 | 6.02163e-05 | 85 | 0.00025176 | 306 | 0.009434% | Tier 2 | 2026 | 2026 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0
| 35553434 | SH | 08W | DOCC | * Post-Construction | North Valley | Region 2 - North Valley and Sierra | Stonyford | COLUSA |  |  | v3 | 360 | 0.0001171 | 85 | 0.0004896 | 306 | 0.01801% | Tier 2 | 2026 | 2026 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0
| 35226625 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Elk Creek | GLENN |  |  | v2 | 340 | 0.0003142 | 308 | 0.00060313 | 704 | 0.02048% | Tier 2 | 2026 | 2026 | 0 | 8.9 | 0 | 8.9 | 0 | 0 | 0 | 0
| 35435697 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 1.0119e-05 | 97 | 0.00010441 | 1173 | 0.00409% | Tier 2 | 2023 | 2026 | 0 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0
| 35538521 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 2.7621e-05 | 97 | 0.00028878 | 1173 | 0.0005842% | Tier 3 | 2026 | 2026 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0
| 35538524 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 3.2045e-05 | 97 | 0.0003506 | 1173 | 0.01155% | Tier 2 & 3 | 2026 | 2026 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| 35538525 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 1.94315e-05 | 97 | 0.00020798 | 1173 | 0.003081% | Tier 2 & 3 | 2025 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35538526 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 1.07035e-05 | 97 | 0.00011549 | 1173 | 0.002311% | Tier 2 & 3 | 2025 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35538527 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 6.85473e-05 | 97 | 0.00073513 | 1173 | 0.01078% | Tier 2 & 3 | 2026 | 2026 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0
| 35526464 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Foresthill | PLACER |  |  | v3 | 1301 | 7.78021e-06 | 97 | 8.40546e-05 | 1173 | 0.001926% | Tier 3 | 2026 | 2026 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| 35519780 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | French Gulch | SHASTA |  |  | v3 | 1743 | 4.8308e-06 | 88 | 0.00010495 | 142 | 0.002499% | Tier 2 | 2025 | 2026 | 0.8 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0
| 35553435 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | French Gulch | SHASTA |  |  | v3 | 1001 | 3.52719e-05 | 36 | 0.00021998 | 132 | 0% | Tier 2 | 2025 | 2026 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35519765 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | FRENCH GULCH | SHASTA |  |  | v3 | 1021 | 2.13184e-05 | 42 | 0.00021624 | 244 | 0.005922% | Tier 2 | 2026 | 2026 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0
| 35519788 | SH | 08W | ESTS | Estimating | Stockton | Region 5 - Central Valley | Angels Camp | CALAVERAS |  |  | v3 | 0 | 0 | 123 | 7.41839e-05 | 1381 | 0.0009614% | Tier 2 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35519773 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1403 | 1.2598e-05 | 73 | 0.0001391 | 507 | 0.003441% | Tier 2 & 3 | 2026 | 2026 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0
| 35544238 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1403 | 1.83044e-05 | 73 | 0.0002007 | 507 | 0.005048% | Tier 2 & 3 | 2026 | 2026 | 1.7 | 0.1 | 1.7 | 0.1 | 0 | 0 | 0 | 0
| 35544239 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1403 | 3.77945e-05 | 73 | 0.0004173 | 507 | 0.01006% | Tier 2 & 3 | 2026 | 2026 | 3.8 | 0 | 3.8 | 0 | 0 | 0 | 0 | 0
| 35544380 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1403 | 7.1075e-06 | 73 | 7.59601e-05 | 507 | 0.0005294% | Tier 2 & 3 | 2026 | 2026 | 0.2 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0
| 35284810 | FRRB | 08W | PEND | Permitting/Dependency | Peninsula | Region 3 - Bay Area | Pescadero | SAN MATEO |  |  | v2 | 2186 | 2.32892e-06 | 2434 | 4.7189e-06 | 1999 | 0% | Tier 2 | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35290514 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Clearlake | LAKE |  |  | v2 | 74 | 5.99115e-06 | 1256 | 5.87837e-07 | 1104 | 8.991e-05% | Tier 2 | 2026 | 2026 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0
| 35231625 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Clearlake | LAKE |  |  | v2 | 27 | 3.88929e-05 | 29 | 0.00011442 | 85 | 0.006441% | Tier 2 & 3 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35231627 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Clearlake | LAKE |  |  | v2 | 27 | 2.10077e-05 | 29 | 6.17999e-05 | 85 | 0.00322% | Tier 2 & 3 | 2026 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35522108 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 0.00020912 | 376 | 0.008292% | Tier 2 | 2026 | 2026 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0
| 35522109 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 0.00015042 | 376 | 0.005769% | Tier 2 | 2025 | 2026 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0
| 35561964 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 0.00016235 | 376 | 0.00649% | Tier 2 | 2026 | 2026 | 1.8 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0
| 35561966 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 0.0001706 | 376 | 0.00685% | Tier 2 | 2026 | 2026 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0
| 35562001 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 7.24568e-05 | 376 | 0.002884% | Tier 2 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35562002 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 0.00022547 | 376 | 0.009013% | Tier 2 | 2026 | 2026 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
| 35562003 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 5.86812e-05 | 376 | 0.002163% | Tier 2 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35562004 | SH | 08W | ADER | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 0.00027792 | 376 | 0.01082% | Tier 2 | 2026 | 2026 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| 35562005 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 0.00015776 | 376 | 0.006129% | Tier 2 | 2026 | 2026 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0
| 35562006 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 156 | 8.43841e-05 | 376 | 0.003245% | Tier 2 | 2026 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35568871 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v4 | 181 | 0 | 156 | 4.53927e-05 | 376 | 0.001803% | Tier 3 | 2026 | 2026 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| 35522106 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 144 | 6.76477e-05 | 530 | 0.001865% | Tier 2 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35561175 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 144 | 4.81734e-05 | 530 | 0.001332% | Tier 2 | 2026 | 2026 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| 35561177 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 144 | 0.00016789 | 530 | 0.003464% | Tier 2 | 2026 | 2026 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0
| 35561204 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 144 | 6.66227e-05 | 530 | 0.001865% | Tier 2 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35561205 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 181 | 0 | 144 | 0.00014144 | 530 | 0.00373% | Tier 2 | 2026 | 2026 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0
| 35451493 | SH | 3UG | PEND | Permitting/Dependency | Yosemite | Region 5 - Central Valley | El Portal | MARIPOSA |  |  | v3 | 555 | 8.75721e-05 | 10 | 0.00080741 | 78 | 0.03722% | Tier 2 | 2026 | 2026 | 3.4 | 0.1 | 3.4 | 0.1 | 0 | 0 | 0 | 0
| 35451494 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | El Portal | MARIPOSA |  |  | v3 | 555 | 1.46125e-05 | 10 | 0.00012928 | 78 | 0.001031% | Tier 2 | 2026 | 2026 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0
| 35372257 | SH | 3UG | APPR | Estimating | Yosemite | Region 5 - Central Valley | El Portal | MARIPOSA |  |  | v3 | 555 | 2.91044e-05 | 10 | 0.00026834 | 78 | 0.01134% | Tier 2 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35546442 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | French Gulch | SHASTA |  |  | v3 | 1135 | 4.93035e-06 | 83 | 0.00010445 | 661 | 0.002477% | Tier 2 & 3 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35519777 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1135 | 6.02599e-06 | 83 | 0.00012767 | 661 | 0.004955% | Tier 2 & 3 | 2026 | 2026 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0
| 35519790 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 848 | 4.47177e-05 | 135 | 0.00018191 | 566 | 0.005227% | Tier 3 | 2026 | 2026 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 35550934 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 848 | 4.65236e-05 | 135 | 0.00018926 | 566 | 0.005489% | Tier 3 | 2026 | 2026 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0
| 35550935 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 848 | 4.96854e-05 | 135 | 0.00020212 | 566 | 0.00575% | Tier 3 | 2026 | 2026 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0
| 35556756 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 456 | 0.00014605 | 119 | 0.00023911 | 216 | 0.01251% | Tier 3 | 2026 | 2026 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0
| 35556757 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 456 | 0.00014709 | 119 | 0.0002408 | 216 | 0.01251% | Tier 3 | 2026 | 2026 | 2.8 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0
| 35519786 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 456 | 0.00025108 | 119 | 0.00041006 | 216 | 0.02054% | Tier 3 | 2026 | 2026 | 4.6 | 0 | 4.6 | 0 | 0 | 0 | 0 | 0
| 35519766 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Shasta | SHASTA |  |  | v3 | 1614 | 1.12776e-05 | 43 | 0.00021738 | 321 | 0.006246% | Tier 3 | 2026 | 2026 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0
| 35519767 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Shasta | SHASTA |  |  | v3 | 1614 | 1.12394e-05 | 43 | 0.00021158 | 321 | 0.003123% | Tier 3 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35548717 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Shasta | SHASTA |  |  | v3 | 1614 | 6.90655e-06 | 43 | 0.00012922 | 321 | 0.001562% | Tier 3 | 2026 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35544220 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Shasta | SHASTA |  |  | v3 | 1614 | 3.5919e-05 | 43 | 0.00068838 | 321 | 0.01987% | Tier 3 | 2026 | 2026 | 4.7 | 0.2 | 4.7 | 0.2 | 0 | 0 | 0 | 0
| 35544221 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1614 | 1.23917e-05 | 43 | 0.00023885 | 321 | 0.007786% | Tier 3 | 2026 | 2026 | 1.8 | 0.1 | 1.8 | 0.1 | 0 | 0 | 0 | 0
| 35544222 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1614 | 9.8853e-06 | 43 | 0.00019054 | 321 | 0.005466% | Tier 3 | 2026 | 2026 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0
| 35544223 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1614 | 6.86712e-06 | 43 | 0.00013191 | 321 | 0.003514% | Tier 3 | 2026 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35544224 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1614 | 2.16417e-05 | 43 | 0.00039679 | 321 | 0.0007588% | Tier 3 | 2025 | 2026 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0
| 35544226 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1614 | 1.12776e-05 | 43 | 0.00021738 | 321 | 0.006246% | Tier 3 | 2026 | 2026 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0
| 35519768 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Lower Lake | LAKE |  |  | v3 | 2206 | 1.36829e-06 | 51 | 0.00011157 | 521 | 0.00239% | Tier 2 | 2025 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35379383 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | v3 | 679 | 7.02236e-05 | 126 | 0.00026039 | 322 | 0.004711% | Tier 2 & 3 | 2026 | 2026 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0
| 35397962 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | v3 | 679 | 0.00012197 | 126 | 0.00044944 | 322 | 0.007248% | Tier 2 & 3 | 2026 | 2026 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| 35397963 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | v3 | 679 | 6.11722e-06 | 126 | 2.26826e-05 | 322 | 0.0003624% | Tier 2 & 3 | 2026 | 2026 | 0.2 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0
| 35401011 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | v3 | 679 | 0.00012052 | 126 | 0.00043252 | 322 | 0.01081% | Tier 2 & 3 | 2026 | 2026 | 2.4 | 1.7 | 2.4 | 1.7 | 0 | 0 | 0 | 0
| 35401012 | SH | 3UG | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Midpines | MARIPOSA |  |  | v3 | 679 | 2.42373e-05 | 126 | 8.76995e-05 | 322 | 0.0007248% | Tier 2 & 3 | 2027 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35274591 | SH | 08W | PEND | Permitting/Dependency | Yosemite | Region 5 - Central Valley | Mariposa | MARIPOSA |  |  | v2 | 428 | 3.95051e-05 | 0 | 0 |  | 0% | Tier 2 & 3 | 2026 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35522107 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Middletown | LAKE |  |  | v3 | 3073 | 3.78012e-09 | 160 | 0.00010504 | 594 | 0.001375% | Tier 2 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35522110 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Middletown | LAKE |  |  | v3 | 3073 | 0 | 160 | 0.0001886 | 74 | 0.01974% | Tier 3 | 2026 | 2026 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0
| 35557357 | SH | 08W | ESTS | Estimating | Humboldt | Region 1 - North Coast | Middletown | LAKE |  |  | v3 | 3073 | 0 | 160 | 0.00012908 | 74 | 0.01316% | Tier 3 | 2026 | 2026 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0
| 35227161 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Middletown | LAKE |  |  | v2 | 8 | 0.00020179 | 392 | 3.78074e-05 | 817 | 0.001204% | Tier 2 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35521812 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Sonora | TUOLUMNE |  |  | v3 | 2426 | 6.45234e-07 | 50 | 8.64841e-05 | 72 | 0% | Tier 3 | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35538287 | SH | 08W | PEND | Permitting/Dependency | North Bay | Region 1 - North Coast | Napa | NAPA |  |  | v3 | 1227 | 2.57997e-05 | 27 | 0.00039709 | 576 | 0.01303% | Tier 2 | 2026 | 2026 | 2.3 | 0.6 | 2.3 | 0.6 | 0 | 0 | 0 | 0
| 35538289 | SH | 08W | ADER | Estimating | North Bay | Region 1 - North Coast | Napa | NAPA |  |  | v3 | 1227 | 1.08438e-05 | 27 | 0.00016791 | 576 | 0.003962% | Tier 2 | 2026 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35538290 | SH | 08W | PEND | Permitting/Dependency | North Bay | Region 1 - North Coast | Napa | NAPA |  |  | v3 | 1227 | 1.20528e-05 | 27 | 0.00018537 | 576 | 0.00501% | Tier 2 | 2026 | 2026 | 1.1 | 0.1 | 1.1 | 0.1 | 0 | 0 | 0 | 0
| 35538291 | SH | 08W | PEND | Permitting/Dependency | North Bay | Region 1 - North Coast | Napa | NAPA |  |  | v3 | 1227 | 8.73826e-06 | 27 | 0.00013531 | 576 | 0.003169% | Tier 2 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35519738 | SH | 08W | ADER | Estimating | North Bay | Region 1 - North Coast | Napa | NAPA |  |  | v3 | 775 | 1.32054e-05 | 19 | 9.57457e-05 | 559 | 0.0008854% | Tier 2 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35374570 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Smartsville | NEVADA |  |  | v3 | 658 | 8.38613e-05 | 46 | 0.00028838 | 356 | 0.008813% | Tier 2 | 2026 | 2026 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0
| 35551928 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Smartsville | NEVADA |  |  | v3 | 658 | 1.0848e-05 | 46 | 3.73038e-05 | 356 | 0.001017% | Tier 2 | 2026 | 2026 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0
| 35457108 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Penn Valley | NEVADA |  |  | v3 | 658 | 7.81567e-05 | 46 | 0.00026876 | 356 | 0.008135% | Tier 2 | 2026 | 2026 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0
| 35526467 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Chico | BUTTE |  |  | v3 | 73 | 0 | 155 | 0.00020026 | 578 | 0.004945% | Tier 2 & 3 | 2026 | 2026 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0
| 35550937 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Chico | BUTTE |  |  | v3 | 73 | 0 | 155 | 0.00022114 | 578 | 0.005394% | Tier 2 & 3 | 2026 | 2026 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0
| 35454651 | SH | 3UG | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Forest Ranch | BUTTE |  |  | v3 | 1043 | 2.67658e-05 | 37 | 0.00028222 | 123 | 0.0006323% | Tier 3 | 2026 | 2026 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0
| 35433763 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Chico | BUTTE |  |  | v3 | 1043 | 1.61895e-05 | 37 | 0.0001758 | 123 | 0.007588% | Tier 3 | 2025 | 2026 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0
| 35519739 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 2.30635e-07 | 22 | 1.01772e-05 | 301 | 0.0003429% | Tier 3 | 2026 | 2026 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0
| 35519761 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 9.17025e-06 | 22 | 0.00039546 | 301 | 0.003772% | Tier 3 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35543416 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 9.66019e-06 | 22 | 0.00042383 | 301 | 0.007544% | Tier 3 | 2025 | 2026 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0
| 35543418 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 6.05313e-06 | 22 | 0.00026663 | 301 | 0.005144% | Tier 3 | 2025 | 2026 | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
| 35543419 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 4.45894e-06 | 22 | 0.00019676 | 301 | 0.004458% | Tier 3 | 2025 | 2026 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0
| 35543440 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 6.19357e-06 | 22 | 0.00026485 | 301 | 0.001372% | Tier 3 | 2026 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35543441 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 3.79506e-06 | 22 | 0.00016472 | 301 | 0.002057% | Tier 3 | 2025 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35543443 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 5.89154e-06 | 22 | 0.0002556 | 301 | 0.003086% | Tier 3 | 2025 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35543444 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 8.13428e-06 | 22 | 0.00035411 | 301 | 0.004801% | Tier 3 | 2026 | 2026 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0
| 35543445 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 6.91102e-06 | 22 | 0.00029923 | 301 | 0.003772% | Tier 3 | 2025 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35543446 | SH | 08W | ADER | Estimating | Yosemite | Region 5 - Central Valley | Oakhurst | MADERA |  |  | v3 | 1854 | 4.34335e-06 | 22 | 0.00019166 | 301 | 0.003772% | Tier 3 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35543447 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Bass Lake | MADERA |  |  | v3 | 1854 | 5.5599e-06 | 22 | 0.00023872 | 301 | 0.001715% | Tier 3 | 2025 | 2026 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| 35539173 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Redding | SHASTA |  |  | v3 | 1773 | 8.32036e-06 | 64 | 0.00024211 | 350 | 0.006907% | Tier 2 | 2026 | 2026 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 35539176 | SH | 08W | PEND | Permitting/Dependency | North Valley | Region 2 - North Valley and Sierra | Shasta Lake | SHASTA |  |  | v3 | 1773 | 2.38405e-06 | 64 | 6.93707e-05 | 350 | 0.002072% | Tier 2 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35396570 | SH | 08W | ESTS | Estimating | Yosemite | Region 5 - Central Valley | Groveland | TUOLUMNE |  |  | v3 | 780 | 2.47933e-05 | 122 | 0.00017406 | 348 | 0.006509% | Tier 2 | 2026 | 2026 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0
| 35375449 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | North San Juan | SIERRA |  |  | v3 | 1484 | 2.70559e-05 | 116 | 0.00041689 | 492 | 0.003307% | Tier 3 | 2025 | 2026 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0
| 35553270 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Camptonville | YUBA |  |  | v3 | 1484 | 1.70908e-05 | 116 | 0.00026281 | 492 | 0.001945% | Tier 3 | 2025 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35524572 | SH | 08W | ADER | Estimating | North Valley | Region 2 - North Valley and Sierra | Montgomery Creek | SHASTA |  |  | v3 | 2224 | 1.58022e-06 | 104 | 9.55651e-05 | 69 | 0.002697% | Tier 2 | 2026 | 2026 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0
| 35391471 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 3.45519e-06 | 68 | 7.61203e-05 | 215 | 0.0009054% | Tier 2 & 3 | 2026 | 2026 | 0.2 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0
| 35391721 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 1.74505e-05 | 68 | 0.00038452 | 215 | 0.004074% | Tier 3 | 2026 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35391722 | SH | 3UG | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 2.32503e-05 | 68 | 0.00051088 | 215 | 0.004074% | Tier 3 | 2026 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35420105 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 7.10074e-06 | 68 | 0.00016019 | 215 | 0.007333% | Tier 2 & 3 | 2026 | 2026 | 1.4 | 0.1 | 1.4 | 0.1 | 0 | 0 | 0 | 0
| 35420106 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 6.36436e-06 | 68 | 0.00014358 | 215 | 0.005433% | Tier 2 & 3 | 2026 | 2026 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0
| 35420107 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 3.36608e-06 | 68 | 7.59368e-05 | 215 | 0.002716% | Tier 2 & 3 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35420108 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 6.67995e-06 | 68 | 0.0001507 | 215 | 0.005885% | Tier 2 & 3 | 2026 | 2026 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0
| 35420109 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 4.40796e-06 | 68 | 9.89123e-05 | 215 | 0.003169% | Tier 2 & 3 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35420110 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 1.12027e-05 | 68 | 0.00024801 | 215 | 0.004074% | Tier 2 & 3 | 2026 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35420112 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 8.58254e-06 | 68 | 0.00019091 | 215 | 0.004074% | Tier 2 & 3 | 2026 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35420113 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 1.36621e-05 | 68 | 0.00029977 | 215 | 0.001811% | Tier 2 & 3 | 2026 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35424580 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 2.01333e-05 | 68 | 0.0004467 | 215 | 0.008602% | Tier 3 | 2026 | 2026 | 1.9 | 0 | 1.9 | 0 | 0 | 0 | 0 | 0
| 35424581 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Garden Valley | EL DORADO |  |  | v3 | 1666 | 8.33624e-06 | 68 | 0.00018456 | 215 | 0.003169% | Tier 3 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35424356 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 1666 | 1.00781e-05 | 68 | 0.0002227 | 215 | 0.003169% | Tier 3 | 2025 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35353435 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Georgetown | EL DORADO |  |  | v2 | 1363 | 1.10795e-05 | 277 | 5.73864e-05 | 399 | 0.004046% | Tier 3 | 2025 | 2026 | 0 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0
| 35473991 | SH | 3UG | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Placerville | EL DORADO |  |  | v3 | 904 | 4.58267e-05 | 58 | 0.00027191 | 179 | 0% | Tier 3 | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35290507 | SH | 08W | UNSC | Ready for Construction | Humboldt | Region 1 - North Coast | Ukiah | MENDOCINO |  |  | v2 | 75 | 8.1967e-05 | 573 | 2.89123e-05 | 1598 | 0.0008181% | Tier 2 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35548782 | SH | 08W | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1885 | 4.74079e-06 | 120 | 0.00013107 | 197 | 0.004511% | Tier 2 | 2026 | 2026 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0
| 35548784 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1885 | 4.78484e-06 | 120 | 0.00013618 | 197 | 0.002713% | Tier 2 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35526460 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2201 | 1.31731e-06 | 71 | 9.42582e-05 | 241 | 0.003557% | Tier 2 | 2025 | 2026 | 0.7 | 0.1 | 0.7 | 0.1 | 0 | 0 | 0 | 0
| 35543504 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 2201 | 3.60921e-06 | 71 | 0.00025427 | 241 | 0.003888% | Tier 2 | 2025 | 2026 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0
| 35543514 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Grass Valley | NEVADA |  |  | v3 | 2201 | 1.17216e-06 | 71 | 8.31283e-05 | 241 | 0.001728% | Tier 2 | 2025 | 2026 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
| 35545063 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Gold Run | PLACER |  |  | v3 | 2022 | 2.22486e-06 | 93 | 0.00012591 | 453 | 0.001378% | Tier 2 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35544807 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Grass Valley | NEVADA |  |  | v3 | 1378 | 9.18986e-06 | 89 | 9.10622e-05 | 428 | 0.003404% | Tier 2 & 3 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35544808 | SH | 08W | PEND | Permitting/Dependency | Sierra | Region 2 - North Valley and Sierra | Grass Valley | NEVADA |  |  | v3 | 1378 | 1.66772e-05 | 89 | 0.00016169 | 428 | 0.002166% | Tier 2 & 3 | 2026 | 2026 | 0.7 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0
| 35544811 | SH | 3UG | ADER | Estimating | Sierra | Region 2 - North Valley and Sierra | Colfax | PLACER |  |  | v3 | 1378 | 1.94931e-05 | 89 | 0.00018825 | 428 | 0% | Tier 2 & 3 | 2025 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35526462 | SH | 08W | ESTS | Estimating | Sierra | Region 2 - North Valley and Sierra | Grass Valley | NEVADA |  |  | v3 | 1378 | 5.70846e-06 | 89 | 5.46959e-05 | 428 | 0.0005344% | Tier 2 & 3 | 2026 | 2026 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0
| 35428408 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 0 | 0 | 33 | 0.00016863 | 1995 | 0.005989% | Tier 3 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35535877 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 0 | 0 | 33 | 0.00028544 | 1995 | 0.0098% | Tier 3 | 2026 | 2026 | 1.8 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0
| 35535878 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Angwin | NAPA |  |  | v3 | 0 | 0 | 33 | 0.0001201 | 1995 | 0.004355% | Tier 3 | 2026 | 2026 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
| 35376559 | SH | 3UG | ESTS | Estimating | North Bay | Region 1 - North Coast | Saint Helena | SONOMA |  |  | v3 | 1361 | 8.25994e-06 | 105 | 0.00011448 | 918 | 0.001621% | Tier 3 | 2026 | 2026 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 35540573 | SH | 08W | ESTS | Estimating | Stockton | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | v3 | 56 | 0.00021846 | 95 | 0.00027616 | 167 | 0.01227% | Tier 2 | 2026 | 2026 | 2.6 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0
| 35540574 | SH | 08W | ESTS | Estimating | Stockton | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | v3 | 56 | 0.00018616 | 95 | 0.00023533 | 167 | 0.01039% | Tier 2 | 2026 | 2026 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0
| 35526196 | SH | 08W | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | v3 | 56 | 0.00014366 | 95 | 0.0001816 | 167 | 0.008026% | Tier 2 | 2025 | 2026 | 1.7 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0
| 35526199 | SH | 08W | PEND | Permitting/Dependency | Stockton | Region 5 - Central Valley | Murphys | CALAVERAS |  |  | v3 | 56 | 0.00012156 | 95 | 0.00015366 | 167 | 0.01039% | Tier 2 | 2026 | 2026 | 2.2 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0
| 35349642 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Upper Lake | LAKE |  |  | v2 | 335 | 1.70932e-06 | 35 | 5.78173e-06 |  | 0% | Tier 2 | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35285250 | SH | 08W | PEND | Permitting/Dependency | Humboldt | Region 1 - North Coast | Lakeport | LAKE |  |  | v2 | 335 | 2.45538e-05 | 35 | 8.30538e-05 |  | 0% | Tier 2 | 2026 | 2026 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| 35519785 | SH | 08W | ADER | Estimating | Stockton | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS |  |  | v3 | 1815 | 6.47182e-06 | 110 | 0.00018986 | 253 | 0.008961% | Tier 2 & 3 | 2026 | 2026 | 1.9 | 0.1 | 1.9 | 0.1 | 0 | 0 | 0 | 0
| 35554850 | SH | 08W | ESTS | Estimating | Stockton | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS |  |  | v3 | 1815 | 1.56241e-05 | 110 | 0.00044489 | 253 | 0.002708% | Tier 2 & 3 | 2026 | 2026 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
| 35554852 | SH | 08W | ESTS | Estimating | Stockton | Region 5 - Central Valley | Mokelumne Hill | CALAVERAS |  |  | v3 | 1815 | 7.40632e-06 | 110 | 0.00021728 | 253 | 0.009478% | Tier 2 & 3 | 2026 | 2026 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0
| 35546585 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Platina | SHASTA |  |  | v3 | 454 | 1.95849e-05 | 109 | 9.35134e-05 | 338 | 0.001536% | Tier 2 | 2026 | 2026 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| 35546586 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Platina | SHASTA |  |  | v3 | 454 | 5.92782e-05 | 109 | 0.00027238 | 338 | 0.0004955% | Tier 2 | 2026 | 2026 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0
| 35546587 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Platina | SHASTA |  |  | v3 | 454 | 3.66136e-05 | 109 | 0.00017534 | 338 | 0.00338% | Tier 2 | 2026 | 2026 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0
| 35519784 | SH | 08W | ESTS | Estimating | North Valley | Region 2 - North Valley and Sierra | Platina | SHASTA |  |  | v3 | 454 | 2.7177e-05 | 109 | 0.00012598 | 338 | 0% | Tier 2 | 2026 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra |  | El Dorado |  |  | v4 | 644 |  | 2 |  | 15 | 4.6035e-07 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | French Gulch | Shasta |  |  | v4 | 252 |  | 271 |  | 27 | 2.1138e-05 | Tier 2 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley |  | Amador |  |  | v4 | 1765 |  | 218 |  | 32 | 0.00013463 | Tier 3 | 2026 | 2027 | 1.1 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | French Gulch | Shasta |  |  | v4 | 2518 |  | 262 |  | 36 | 0.08461% | Tier 2 | 2026 | 2027 | 5.9 | 0 | 0 | 0 | 5.9 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Pope Valley | Napa |  |  | v4 | 614 |  | 389 |  | 37 | 1.8885e-05 | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sonoma | Region 1 - North Coast |  | Sonoma |  |  | v4 | 272 |  | 374 |  | 50 | 0.00017973 | Tier 2 & 3 | 2026 | 2027 | 1.9 | 0.4 | 0 | 0 | 1.9 | 0.4 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra |  | Sierra |  |  | v4 | 1700 |  | 41 |  | 58 | 8.1619e-05 | Tier 3 | 2026 | 2027 | 0.8 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Fresno | Region 5 - Central Valley | Shaver Lake | Fresno |  |  | v4 | 490 |  | 235 |  | 66 | 0.00033204 | Tier 2 | 2026 | 2027 | 3.2 | 0 | 0 | 0 | 3.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Midpines | Mariposa |  |  | v4 | 700 |  | 199 |  | 73 | 0.0011914 | Tier 2 & 3 | 2026 | 2027 | 12.3 | 0 | 0 | 0 | 12.3 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Calistoga | Napa |  |  | v4 |  |  | 134 |  | 858 | 9.9066e-06 | Tier 2 & 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Mountain Ranch | Calaveras |  |  | v4 |  |  | 331 |  | 88 | 8.8695e-05 | Tier 2 | 2026 | 2027 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Pioneer | Amador |  |  | v4 | 2447 |  | 233 |  | 91 | 3.6598e-05 | Tier 2 & 3 | 2026 | 2027 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Alta | Placer |  |  | v4 |  |  |  |  | 96 | 5.3681e-05 | Tier 3 | 2026 | 2027 | 1.7 | 0 | 0 | 0 | 1.7 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Jamestown | Tuolumne |  |  | v4 | 619 |  | 377 |  | 102 | 0.00010951 | Tier 2 | 2026 | 2027 | 1.4 | 0 | 0 | 0 | 1.4 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sonoma | Region 1 - North Coast | Cazadero | Sonoma |  |  | v4 | 1366 |  | 1226 |  | 107 | 6.763e-05 | Tier 2 & 3 | 2026 | 2027 | 1.1 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | North San Juan | Sierra |  |  | v4 | 1308 |  | 162 |  | 129 | 0.00048715 | Tier 3 | 2026 | 2027 | 7.9 | 0 | 0 | 0 | 7.9 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast |  | Lake |  |  | v4 | 58 |  | 486 |  | 130 | 0.00076151 | Tier 2 | 2026 | 2027 | 12.8 | 0 | 0 | 0 | 12.8 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Diablo | Region 3 - Bay Area | Clayton | Contra Costa |  |  | v4 | 377 |  | 15 |  | 31 | 0.00014118 | Tier 3 | 2026 | 2027 | 2.9 | 0 | 0 | 0 | 2.9 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Fresno | Region 5 - Central Valley |  | Fresno |  |  | v4 |  |  | 447 |  | 121 | 0.00066395 | HFRA | 2026 | 2027 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Fresno | Region 5 - Central Valley |  | Fresno |  |  | v4 | 0 |  | 447 |  | 121 | 0.1397% | HFRA | 2027 | 2028 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Groveland | Tuolumne |  |  | v4 | 2550 |  | 67 |  | 224 | 0.0004104% | Tier 2 & 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Groveland | Tuolumne |  |  | v4 | 2550 |  | 67 |  | 224 | 7.7788e-06 | Tier 2 & 3 | 2027 | 2028 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Alta | Placer |  |  | v4 | 942 |  | 103 |  | 39 | 1.0474e-05 | Tier 3 | 2026 | 2027 | 2.6 | 0 | 0 | 0 | 2.6 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Pioneer | Amador |  |  | v4 | 2589 |  | 352 |  | 219 | 0.00022181 | Tier 3 | 2026 | 2027 | 5.5 | 0 | 0 | 0 | 5.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | French Gulch | Shasta |  |  | v4 | 1743 |  | 88 |  | 142 | 4.723e-07 | Tier 2 | 2026 | 2027 | 0.3 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra |  | El Dorado |  |  | v4 | 2732 |  | 278 |  | 233 | 1.0191e-05 | Tier 3 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Kern | Region 5 - Central Valley | Lebec | Kern |  |  | v4 | 583 |  | 219 |  | 239 | 1.5878e-05 | Tier 2 | 2026 | 2027 | 0.4 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Foresthill | Placer |  |  | v4 | 1865 |  | 179 |  | 243 | 4.1747e-05 | Tier 3 | 2026 | 2027 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Alta | Placer |  |  | v4 | 2087 |  | 192 |  | 263 | 4.5103e-05 | Tier 3 | 2026 | 2027 | 1.1 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast | Middletown | Lake |  |  | v4 | 915 |  | 56 |  | 277 | 1.5181e-06 | Tier 2 & 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Napa | Napa |  |  | v4 | 1224 |  | 255 |  | 307 | 5.8772e-05 | Tier 2 & 3 | 2026 | 2027 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast | Clearlake | Lake |  |  | v4 | 74 |  | 1256 |  | 1104 | 2.5758e-05 | Tier 2 | 2026 | 2027 | 2.9 | 0 | 0 | 0 | 2.9 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Fresno | Region 5 - Central Valley | Auberry | Fresno |  |  | v4 | 330 |  | 734 |  | 325 | 0.00012028 | Tier 2 | 2026 | 2027 | 3.5 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Pioneer | Amador |  |  | v4 | 2468 |  | 107 |  | 368 | 1.993e-06 | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Napa | Napa |  |  | v4 |  |  | 338 |  | 483 | 2.9732e-05 | Tier 3 | 2026 | 2027 | 1.1 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Calistoga | Napa |  |  | v4 | 1005 |  | 105 |  | 501 | 0.0002607% | Tier 2 & 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Brownsville | Yuba |  |  | v4 | 1428 |  | 408 |  | 789 | 3.5327e-05 | Tier 2 & 3 | 2026 | 2027 | 1.9 | 0 | 0 | 0 | 1.9 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast | Clearlake | Lake |  |  | v4 | 27 |  | 29 |  | 85 | 0.00032669 | Tier 2 & 3 | 2026 | 2027 | 1.7 | 0 | 0 | 0 | 1.7 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Redding | Shasta |  |  | v4 | 456 |  | 119 |  | 216 | 1.5556e-06 | Tier 3 | 2027 | 2028 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sonoma | Region 1 - North Coast |  | Sonoma |  |  | v4 | 1313 |  | 1448 |  | 891 | 7.9247e-06 | Tier 2 & 3 | 2026 | 2027 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Mariposa | Mariposa |  |  | v4 | 655 |  | 504 |  | 940 | 3.4719e-05 | Tier 2 & 3 | 2026 | 2027 | 2.1 | 0 | 0 | 0 | 2.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Mariposa | Mariposa |  |  | v4 | 187 |  | 531 |  | 191 | 0.00015803 | Tier 2 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Canyon Dam | Plumas |  |  | v4 | 3328 |  | 969 |  | 3862 | 2.5555e-05 | Tier 2 | 2026 | 2027 | 7.2 | 0 | 0 | 0 | 7.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Redding | Shasta |  |  | v4 | 3032 |  | 153 |  | 7 | 1.11e-07 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | MI Wuk Village | Tuolumne |  |  | v4 | 911 |  | 335 |  | 8 | 6.9228e-08 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Kern | Region 5 - Central Valley |  | Kern |  |  | v4 |  |  | 821 |  | 14 | 3.245e-07 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Oak Run | Shasta |  |  | v4 | 563 |  | 1190 |  | 25 | 0.0007918% | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra |  | Nevada |  |  | v4 | 323 |  | 136 |  | 26 | 2.3167e-08 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Redding | Shasta |  |  | v4 |  |  |  |  | 29 | 0.00020625 | Tier 3 | 2026 | 2027 | 2.3 | 0 | 0 | 0 | 2.3 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Mariposa | Mariposa |  |  | v4 | 187 |  | 531 |  | 191 | 0.00068911 | Tier 2 | 2027 | 2028 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Mariposa | Mariposa |  |  | v4 | 679 |  | 126 |  | 322 | 5.3668e-05 | Tier 2 & 3 | 2026 | 2027 | 1.7 | 0 | 0 | 0 | 1.7 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Central Coast | Region 4 - South Bay and Central Coast |  | Santa Cruz |  |  | v4 |  |  |  |  | 40 | 1.7143e-08 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Central Coast | Region 4 - South Bay and Central Coast | Davenport | Santa Cruz |  |  | v4 | 226 |  | 2760 |  | 41 | 7.2868e-06 | Tier 2 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Magalia | Butte |  |  | v4 | 1287 |  | 129 |  | 44 | 1.2711e-05 | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Redding | Shasta |  |  | v4 | 7 |  | 48 |  | 46 | 5.6891e-05 | Tier 3 | 2026 | 2027 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sonoma | Region 1 - North Coast | Cazadero | Sonoma |  |  | v4 | 365 |  | 1955 |  | 47 | 3.31e-07 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Los Padres | Region 4 - South Bay and Central Coast |  | Santa Barbara |  |  | v4 | 462 |  | 650 |  | 59 | 3.3947e-07 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Mill Valley | Marin |  |  | v4 | 1714 |  | 680 |  | 60 | 0.00052199 | Tier 3 | 2026 | 2027 | 5.1 | 0 | 0 | 0 | 5.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Long Barn | Tuolumne |  |  | v4 | 3426 |  | 1283 |  | 61 | 4.3264e-08 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Kern | Region 5 - Central Valley | Lebec | Kern |  |  | v4 | 931 |  | 387 |  | 62 | 0.0011258 | Tier 2 | 2026 | 2027 | 5.4 | 0 | 0 | 0 | 5.4 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 3182 |  | 316 |  | 63 | 8.3707e-06 | Tier 2 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 2320 |  | 394 |  | 65 | 5.176e-05 | Tier 2 | 2026 | 2027 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 3139 |  | 224 |  | 67 | 6.9173e-06 | Tier 2 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast |  | Lake |  |  | v4 | 474 |  | 102 |  | 202 | 2.1467e-05 | Tier 2 & 3 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast |  | Lake |  |  | v4 | 474 |  | 102 |  | 202 | 2.6973e-05 | Tier 2 & 3 | 2027 | 2028 | 25.5 | 0 | 0 | 0 | 0 | 0 | 25.5 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Angwin | Napa |  |  | v4 |  |  | 14 |  | 76 | 1.015e-05 | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sonoma | Region 1 - North Coast | Cazadero | Sonoma |  |  | v4 | 2061 |  | 1445 |  | 79 | 1.376e-05 | Tier 3 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | De Anza | Region 4 - South Bay and Central Coast | Cupertino | Santa Clara |  |  | v4 | 1444 |  | 424 |  | 80 | 2.0681e-05 | Tier 2 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sacramento | Region 1 - North Coast | Fairfield | Solano |  |  | v4 |  |  |  |  | 87 | 1.0318e-05 | Tier 2 | 2026 | 2027 | 0.3 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Deer Park | Napa |  |  | v4 |  |  |  |  | 89 | 5.068e-08 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Mill Valley | Marin |  |  | v4 | 1087 |  | 707 |  | 90 | 0.001629% | Tier 3 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Fresno | Region 5 - Central Valley |  | Tulare |  |  | v4 | 2756 |  | 171 |  | 93 | 0.0002841 | Tier 2 | 2026 | 2027 | 3.4 | 0 | 0 | 0 | 3.4 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Los Padres | Region 4 - South Bay and Central Coast | Arroyo Grande | San Luis Obispo |  |  | v4 | 1248 |  | 743 |  | 94 | 0.00015434 | Tier 3 | 2026 | 2027 | 1.9 | 0 | 0 | 0 | 1.9 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Napa | Napa |  |  | v4 |  |  | 616 |  | 95 | 0.001479% | Tier 2 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Diablo | Region 3 - Bay Area | Danville | Contra Costa |  |  | v4 |  |  | 552 |  | 99 | 1.0205e-05 | Tier 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Los Padres | Region 4 - South Bay and Central Coast | Santa Barbara | Santa Barbara |  |  | v4 | 961 |  | 337 |  | 100 | 5.9153e-05 | Tier 3 | 2026 | 2027 | 0.9 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra |  | Plumas |  |  | v4 | 1658 |  | 404 |  | 101 | 2.7865e-05 | Tier 3 | 2026 | 2027 | 0 | 0.3 | 0 | 0 | 0 | 0.3 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra |  | Shasta |  |  | v4 |  |  |  |  | 106 | 2.0494e-07 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Mountain Ranch | Calaveras |  |  | v4 | 1906 |  | 198 |  | 109 | 4.9392e-05 | Tier 2 | 2026 | 2027 | 0.7 | 0 | 0 | 0 | 0.7 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Alleghany | Sierra |  |  | v4 | 1446 |  | 254 |  | 112 | 0.00016525 | Tier 3 | 2026 | 2027 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | De Anza | Region 4 - South Bay and Central Coast | Cupertino | Santa Clara |  |  | v4 |  |  | 724 |  | 116 | 0.00046093 | Tier 2 & 3 | 2026 | 2027 | 7.6 | 0 | 0 | 0 | 7.6 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Angwin | Napa |  |  | v4 |  |  | 873 |  | 119 | 1.2088e-06 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Central Coast | Region 4 - South Bay and Central Coast | Salinas | Monterey |  |  | v4 |  |  | 1659 |  | 120 | 2.4785e-07 | Tier 2 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast | Willow Creek | Humboldt |  |  | v4 | 2925 |  | 1284 |  | 124 | 8.6494e-09 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Diablo | Region 3 - Bay Area | Clayton | Contra Costa |  |  | v4 |  |  | 100 |  | 126 | 3.1106e-07 | Tier 2 & 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sacramento | Region 1 - North Coast | Winters | Solano |  |  | v4 | 92 |  | 423 |  | 128 | 0.00059866 | Tier 2 | 2026 | 2027 | 9.1 | 0 | 0 | 0 | 9.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Greenwood | El Dorado |  |  | v4 | 1433 |  | 380 |  | 134 | 0.00079043 | Tier 2 & 3 | 2026 | 2027 | 13.2 | 0 | 0 | 0 | 13.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sacramento | Region 1 - North Coast | Vacaville | Solano |  |  | v4 |  |  |  |  | 136 | 5.4637e-05 | Tier 2 | 2026 | 2027 | 0.9 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Smartsville | Nevada |  |  | v4 | 167 |  | 173 |  | 137 | 1.1534e-05 | Tier 2 | 2026 | 2027 | 0.2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast | Middletown | Lake |  |  | v4 |  |  | 160 |  | 74 | 2.9672e-05 | Tier 3 | 2026 | 2027 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Larkspur | Marin |  |  | v4 | 1323 |  | 1368 |  | 143 | 8.0297e-06 | Tier 2 & 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Wilseyville | Calaveras |  |  | v4 | 1530 |  | 154 |  | 144 | 0.0002122 | Tier 2 & 3 | 2026 | 2027 | 3.7 | 0 | 0 | 0 | 3.7 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sonoma | Region 1 - North Coast | Kenwood | Sonoma |  |  | v4 |  |  | 1095 |  | 145 | 1.1966e-06 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Camino | El Dorado |  |  | v4 | 1934 |  | 197 |  | 147 | 0.00032101 | Tier 2 & 3 | 2026 | 2027 | 5.6 | 0 | 0 | 0 | 5.6 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast | Lower Lake | Lake |  |  | v4 | 1803 |  | 332 |  | 148 | 6.4717e-06 | Tier 2 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Jackson | Amador |  |  | v4 | 1088 |  | 251 |  | 154 | 0.0009069 | Tier 2 | 2026 | 2027 | 15.3 | 0 | 0 | 0 | 15.3 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Twain Harte | Tuolumne |  |  | v4 | 3063 |  | 1527 |  | 155 | 9.8463e-07 | Tier 3 | 2026 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Lakehead | Shasta |  |  | v4 | 1674 |  | 210 |  | 156 | 0.00042638 | Tier 2 | 2026 | 2027 | 7.7 | 0 | 0 | 0 | 7.7 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Gustine | Merced |  |  | v4 |  |  | 751 |  | 51 | 0.0012 | HFRA | 2026 | 2027 | 0 | 5.1 | 0 | 0 | 0 | 5.1 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast | Middletown | Lake |  |  | v4 | 8 |  | 392 |  | 817 | 0.004096% | Tier 2 | 2026 | 2027 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sacramento | Region 2 - North Valley and Sierra | Winters | Yolo |  |  | v4 | 293 |  | 11040 |  | 146 | 3.7759e-06 | Tier 2 | 2027 | 2028 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 2329 |  | 402 |  | 149 | 0.01433% | Tier 2 | 2027 | 2028 | 2.7 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Mountain Ranch | Calaveras |  |  | v4 | 1941 |  | 260 |  | 157 | 4.2218e-05 | Tier 2 & 3 | 2027 | 2028 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Garden Valley | El Dorado |  |  | v4 | 1646 |  | 236 |  | 158 | 0.00027094 | Tier 2 & 3 | 2027 | 2028 | 4.9 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Los Padres | Region 4 - South Bay and Central Coast | Solvang | Santa Barbara |  |  | v4 | 853 |  | 1033 |  | 161 | 2.0263e-05 | Tier 2 & 3 | 2027 | 2028 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Colfax | Placer |  |  | v4 |  |  | 1420 |  | 162 | 0.00017861 | Tier 2 | 2027 | 2028 | 3.2 | 0 | 0 | 0 | 0 | 0 | 3.2 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Redding | Shasta |  |  | v4 | 1251 |  | 220 |  | 168 | 0.00022015 | Tier 2 | 2027 | 2028 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast | Laytonville | Mendocino |  |  | v4 | 1623 |  | 638 |  | 169 | 0.00089059 | Tier 2 | 2027 | 2028 | 16.9 | 0 | 0 | 0 | 0 | 0 | 16.9 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Lakehead | Shasta |  |  | v4 |  |  |  |  | 172 | 0.02361% | Tier 2 | 2027 | 2028 | 4.2 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | West Point | Calaveras |  |  | v4 | 1696 |  | 206 |  | 173 | 0.01182% | Tier 3 | 2027 | 2028 | 2.2 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Humboldt | Region 1 - North Coast |  | Mendocino |  |  | v4 | 3082 |  | 1825 |  | 174 | 7.3878e-08 | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Coulterville | Mariposa |  |  | v4 | 503 |  |  |  | 177 | 0.02499% | Tier 2 | 2027 | 2028 | 9.3 | 0 | 0 | 0 | 0 | 0 | 9.3 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Fresno | Region 5 - Central Valley |  | Fresno |  |  | v4 | 286 |  | 113 |  | 181 | 0.00037677 | Tier 2 & 3 | 2027 | 2028 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Nevada City | Nevada |  |  | v4 | 606 |  | 141 |  | 183 | 0.00031868 | Tier 2 & 3 | 2027 | 2028 | 6.4 | 0 | 0 | 0 | 0 | 0 | 6.4 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | North San Juan | Sierra |  |  | v4 |  |  |  |  | 186 | 0.00015452 | Tier 3 | 2027 | 2028 | 8.4 | 0 | 0 | 0 | 0 | 0 | 8.4 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Paradise | Butte |  |  | v4 | 2943 |  | 201 |  | 187 | 2.6647e-05 | Tier 3 | 2027 | 2028 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Diablo | Region 3 - Bay Area | Clayton | Contra Costa |  |  | v4 |  |  | 223 |  | 190 | 0.0001275 | Tier 3 | 2027 | 2028 | 2.3 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sacramento | Region 2 - North Valley and Sierra |  | Yolo |  |  | v4 | 515 |  | 2094 |  | 195 | 0.002941% | Tier 2 | 2027 | 2028 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Sonora | Tuolumne |  |  | v4 | 2426 |  | 50 |  | 72 | 6.4984e-07 | Tier 3 | 2026 | 2027 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Cool | El Dorado |  |  | v4 |  |  |  |  | 198 | 9.606e-05 | Tier 2 | 2027 | 2028 | 2.2 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sonoma | Region 1 - North Coast | Geyserville | Sonoma |  |  | v4 |  |  |  |  | 199 | 0.00066847 | Tier 2 & 3 | 2027 | 2028 | 12.6 | 0 | 0 | 0 | 0 | 0 | 12.6 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sonoma | Region 1 - North Coast |  | Sonoma |  |  | v4 | 2477 |  | 1481 |  | 200 | 5.5445e-07 | Tier 3 | 2027 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Montgomery Creek | Shasta |  |  | v4 | 1495 |  | 539 |  | 205 | 0.00022255 | Tier 2 | 2027 | 2028 | 4.7 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | De Anza | Region 4 - South Bay and Central Coast | Los Gatos | Santa Clara |  |  | v4 |  |  | 1002 |  | 206 | 8.6313e-05 | Tier 3 | 2027 | 2028 | 1.6 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Woodacre | Marin |  |  | v4 | 1663 |  | 648 |  | 207 | 2.4266e-06 | Tier 3 | 2027 | 2028 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Nevada City | Nevada |  |  | v4 |  |  |  |  | 212 | 3.943e-05 | Tier 3 | 2027 | 2028 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | Mariposa | Mariposa |  |  | v4 | 1036 |  | 263 |  | 213 | 0.00028915 | Tier 2 | 2027 | 2028 | 5.5 | 0 | 0 | 0 | 0 | 0 | 5.5 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley |  | Amador |  |  | v4 | 2334 |  | 6 |  | 165 | 3.642e-06 | Tier 2 | 2026 | 2027 | 1.2 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Alleghany | Sierra |  |  | v4 | 1944 |  | 953 |  | 217 | 0.00020918 | Tier 3 | 2027 | 2028 | 4.7 | 0 | 0 | 0 | 0 | 0 | 4.7 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Paynes Creek | Tehama |  |  | v4 | 157 |  | 280 |  | 220 | 0.00031029 | Tier 2 | 2027 | 2028 | 6.7 | 0 | 0 | 0 | 0 | 0 | 6.7 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Bay | Region 1 - North Coast | Pope Valley | Napa |  |  | v4 |  |  |  |  | 221 | 0.00023264 | Tier 2 & 3 | 2027 | 2028 | 4.9 | 0 | 0 | 0 | 0 | 0 | 4.9 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | North Valley | Region 2 - North Valley and Sierra | Challenge | Yuba |  |  | v4 | 1693 |  | 465 |  | 225 | 0.0001285 | Tier 3 | 2027 | 2028 | 0.5 | 1.3 | 0 | 0 | 0 | 0 | 0.5 | 1.3
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Pollock Pines | El Dorado |  |  | v4 | 1946 |  | 49 |  | 226 | 0.0013202 | Tier 2 & 3 | 2027 | 2028 | 28.9 | 0 | 0 | 0 | 0 | 0 | 28.9 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley |  | Amador |  |  | v4 | 2334 |  | 6 |  | 165 | 2.8985e-06 | Tier 2 | 2027 | 2028 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Sierra | Region 2 - North Valley and Sierra | Colfax | Placer |  |  | v4 | 1885 |  | 120 |  | 197 | 0.007163% | Tier 2 | 2027 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Murphys | Calaveras |  |  | v4 | 1412 |  | 66 |  | 210 | 9.8505e-06 | Tier 2 & 3 | 2026 | 2027 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Stockton | Region 5 - Central Valley | Murphys | Calaveras |  |  | v4 | 1412 |  | 66 |  | 210 | 1.5997e-05 | Tier 2 & 3 | 2027 | 2028 | 25.5 | 0 | 0 | 0 | 0 | 0 | 25.5 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | MI Wuk Village | Tuolumne |  |  | v4 | 56 |  | 95 |  | 167 | 9.6665e-05 | Tier 2 | 2026 | 2027 | 0 | 4.1 | 0 | 0 | 0 | 4.1 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Yosemite | Region 5 - Central Valley | MI Wuk Village | Tuolumne |  |  | v4 | 56 |  | 95 |  | 167 | 0.0012112 | Tier 2 | 2027 | 2028 | 1.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Kern | Region 5 - Central Valley | Lebec | Kern |  |  | v4 | 691 |  | 368 |  | 184 | 0.00023846 | Tier 2 | 2026 | 2027 | 0 | 4.1 | 0 | 0 | 0 | 4.1 | 0 | 0
| N/A | SH | TBD | N/A | Pre-Scoping | Kern | Region 5 - Central Valley | Lebec | Kern |  |  | v4 | 691 |  | 368 |  | 184 | 0.00013172 | Tier 2 | 2027 | 2028 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0

## Definitions
Definitions
Category
Category Type | Description
FRRB - Fire Rebuild | System Hardening Scope as a result of fires in HFTD
SH - System Hardening | Planned projects in the base System Hardening (SH) program
TBD | Circuit segments have been identified, however, projects have not yet been scoped and separated into subprojects at the order-level
MAT Code
MAT Code | Description
08W | System Hardening Wildfire Resiliency Projects
3UG | Targeted Undergrounding
SAP Status and Status
SAP Status | Status
N/A | Pre-scoping
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | * In-Construction
DOCC | * Post-Construction
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles
Location
Lat / Long
Latitude / Longitude | ∙ Latitude is how far north or south a location is from the Equator. ∙ Longitude is how far east or west a location is from the Prime Meridian. ∙ For subprojects (orders) that are scoped (currently 2026 work), the location of the lat/long is anywhere on the alignment of the subproject. ∙ If a subproject is not yet scoped (currently 2027-28 work), the lat/long is not provided, as this information is not yet available.
Risk Rank | Results of the relevant risk model (e.g. WDRM v2, WDRM v3, WDRM v4) where circuit segments are ranked on a 1 to N basis, where 1 is the highest risk circuit segment, and N is the lowest risk.
Estimated Wildfire Risk Reduction | Estimated wildfire risk provides the estimated risk reduction for each subproject. The risk reduction reported includes the reduction of additional mitigations on that subproject, if relevant (i.e., if a subproject has undergrounding, overhead hardening and line removal, the risk reduction includes all mitigations).
Total Planned OH Miles | Total overhead hardening miles planned on a subproject, which can extend before or after the 2026-28 time period included in this workplan.
Total Planned Removal Miles | Total removal miles planned on a subproject, which can extend before or after the 2026-28 time period included in this workplan.