## LU Table 6-5_DR-001
Table 6‑5: Summary of Risk Reduction for Top Circuits
Circuit | Initial Overall Utility Risk | 2026 Activities | 2026 Overall Utility Risk | 2027 Activities | 2027 Overall Utility Risk | 2028 Activities | 2028 Overall Activity Risk | 2026 Grid Hardening Planned (circuit mileage) | 2027 Grid Hardening Planned (circuit mileage) | 2028 Grid Hardening Planned (circuit mileage) | 2026 Covered Conductor Planned (circuit mileage) | 2027 Covered Conductor Planned (circuit mileage) | 2028 Covered Conductor Planned (circuit mileage)
MEY3400 | 0.10902 | Grid hardening, including covered conductor, VM, patrol inspections | 0.11156 | Grid hardening, including covered conductor, VM, patrol inspections | 0.11093 | Grid hardening, VM, patrol inspections | 0.11324 | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | 0 | 0 | 3.1
CEM41 | 0.0008171 | Grid hardening, VM, patrol inspections | 0.0008407 | Grid hardening, VM, patrol inspections | 0.0008354 | Grid hardening, VM, detailed inspections | 0.0008597 | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | 0 | 0 | 0
TPZ1202 | 0.032942 | Grid hardening, VM, patrol inspections | 0.034023 | Grid hardening, VM, detailed inspections | 0.03249 | Grid hardening, VM, patrol inspections | 0.033119 | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | 0 | 0 | 0
MULLER1296 | 0.019729 | Grid hardening, including covered conductor, VM, patrol inspections | 0.020288 | Grid hardening, including covered conductor, VM, detailed inspections | 0.020821 | Grid hardening, including covered conductor, VM, patrol inspections | 0.020755 | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | N/A - Grid hardening refers to all WMP initiative activities included in Section 8.2 of Liberty's 2026-2028 Base WMP and is not measured in circuit mileage. | 3.2 | 3.8 | 0