## OEIS 6.2
Circuit, Segment, or Span ID | Circuit Length (circuit miles) | HFTD Designation | Wildfire Risk Score | Terrain Score (Sum) | Max Terrain Score | Wind Score (Sum) | Max Wind Score | 2026 Activities | 2026 Covered Conductor Planned (Circuit Miles) | 2026 Undergrounding Planned (Circuit Miles) | 2026 Overall Maximum Fuel/Terrain Risk | 2027 Activities | 2027 Covered Conductor Planned (Circuit Miles) | 2027 Undergrounding Planned (Circuit Miles) | 2027 Overall Maximum Fuel/Terrain Risk | 2028 Activities | 2028 Covered Conductor Planned (Circuit Miles) | 2028 Undergrounding Planned (Circuit Miles) | 2028 Overall Maximum Fuel/Terrain Risk
5G39 | 24.3811 | Tier 2 | 134.9873 | 170.8711 | 0.97 | 85.1915 | 0.64 | GH-01 Line Rebuild GH044 System Automation Completed in 2023 GH-05 Expulsion Fuse Replacement Completed in 2024 | 6 | 0.5 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5R165 | 20.2226 | Tier 2 | 96.3087 | 121.8597 | 0.96 | 60.832 | 0.61 | GH-01 Line Rebuild GH-04 System Automation Planned to Complete in 2025 GH-05 Expulsion Fuse Replacement Completed in 2024 | 20 | 0.4 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
8G95 | 8.3347 | Tier 2 | 44.5615 | 55.376 | 0.94 | 29.1545 | 0.46 | GH-01 Line Rebuild Planned to Complete in 2025 GH-04 System Automation Completed in 2022 GH-05 Expulsion Fuse Replacement Completed in 2023 | 0.5 | 0.5 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5R171 | 19.7912 | Tier 2 | 97.2308 | 131.2512 | 0.9 | 53.1898 | 0.68 | GH-01 Line Rebuild GH-04 System Automation Completed in 2022 GH-05 Expulsion Fuse Replacement Completed in 2024 | 8.5 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5R170 | 18.1785 | Tier 2 | 64.5496 | 84.4266 | 0.89 | 38.0201 | 0.49 | GH-01 Line Rebuild GH-05 Expulsion Fuse Replacement Completed in 2024 | 1.7 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5G97 | 8.7391 | Tier 2 | 23.4539 | 33.6184 | 0.89 | 10.8723 | 0.36 | GH-01 Line Rebuild Planned to Complete in 2025 GH-04 System Automation Completed in 2022 GH-05 Expulsion Fuse Replacement Completed in 2024 | 7.3 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5R96 | 10.0047 | Tier 2 | 67.5297 | 87.4354 | 0.88 | 40.6644 | 0.48 | GH-01 Line Rebuild Planned to Complete in 2025 GH-04 System Automation Completed in 2022 GH-05 Expulsion Fuse Replacement Completed in 2024 | 10.2 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
7G75 | 3.5242 | Tier 2 | 28.7427 | 30.6719 | 0.84 | 23.8513 | 0.78 | GH-01 Line Rebuild Completed in 2022 GH-04 System Automation Completed in 2020 GH-05 Expulsion Fuse Replacement Completed in 2022 | 0 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5G16 | 34.9504 | Tier 2 | 175.9793 | 199.8928 | 0.83 | 133.9293 | 0.42 | GH-01 Line Rebuild GH-05 Expulsion Fuse Replacement Completed in 2021 GH-05 Expulsion Fuse Replacement Completed in 2022 | 17 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
7G73 | 1.9855 | Tier 2 | 18.7095 | 21.1213 | 0.8 | 14.3694 | 0.62 | GH-01 Line Rebuild Completed in 2022 GH-04 System Automation Completed in 2021 GH-05 Expulsion Fuse Replacement Completed in 2022 | 0 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5G83 | 78.5429 | Tier 2 | 557.3047 | 592.2862 | 0.79 | 464.8869 | 0.99 | GH-01 Line Rebuild Planned to Complete in 2025 GH-04 System Automation Completed in 2022 GH-05 Expulsion Fuse Replacement Planned to Complete in 2025 | 0 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5G41 | 86.5161 | Tier 2 | 424.3747 | 504.5275 | 0.78 | 300.4854 | 0.8 | GH-01 Line Rebuild GH-05 Expulsion Fuse Replacement Completed in 2022 GH-05 Expulsion Fuse Replacement Completed in 2024 | 50 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5G79 | 34.2018 | Tier 2 | 135.8 | 174.8952 | 0.77 | 82.7092 | 0.41 | GH-01 Line Rebuild Planned to Complete in 2025 GH-04 System Automation Completed in 2022 GH-05 Expulsion Fuse Replacement Completed in 2023 | 0 | 4 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
5G23 | 95.3366 | Tier 2 | 721.6398 | 709.9921 | 0.77 | 658.9147 | 0.96 | GH-01 Line Rebuild P7 miles in 2026, balance in 2031 after substation replacement GH-04 System Automation Completed in 2023 GH-05 Expulsion Fuse Replacement Completed in 2024 | 7 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
7G71 | 19.7912 | Tier 2 | 97.2308 | 131.2512 | 0.76 | 53.1898 | 0.37 | GH-01 Line Rebuild Completed in 2022 GH-04 System Automation Completed in 2021 GH-05 Expulsion Fuse Replacement Completed in 2022 | 0 | 0 | TBD | No 2027 Activities | 0 | 0 | TBD | No 2028 Activities | 0 | 0 | 0
1 GH-01 schedule in conjunction with planned substation replacement.
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Definition: The total length in miles of separate transmission and/or distribution circuits, regardless of the number of conductors used per circuit (i.e., different phases)