## Table 8-1
Initiative | Quantitative or Qualitative Target | Activity (Tracking ID #) | Previous Tracking ID (if applicable) | Target Unit | 2026 Target / Status | % Planned in HFTD for 2026 | % Planned in HFRA for 2026 | % Risk Reduction for 2026 | 2027 Target / Status | % Planned in HFTD for 2027 | % Planned in HFRA for 2027 | % Risk Reduction for 2027 | 2028 Target / Status | % Planned in HFTD for 2028 | % Planned in HFRA for 2028 | % Risk Reduction for 2028 | Three-year total | Section; Page number
Grid Design and System Hardening | Qualitative | Investigate advanced protection system enhancements for potential inclusion in project design (GD-01) | N/A | N/A | Begin review and investigation | 0 | 0 | N/A | Complete investigation | 0% | 0 | N/A | Implement design if applicable | 0% | 0% | N/A | N/A | 8.2.8; 66
Asset Inspections | Quantitative | Monthly Substation Inspections (GD-02) | N/A | # of inspections | 21 | 50% | N/A | 67% | 24 | 50% | N/A | 67% | 24 | 50% | N/A | 67% | 69 | 8.3.2; 69
Equipment Maintenance and Repair | Quantitative | Dissolved Gas Analysis Test at energized transformers (GD-03) | N/A | # of inspections | Q4 / 3 | N/A | N/A | N/A | Q4 / 6 | 50% | N/A | N/A | Q4 / 6 | N/A | N/A | N/A | 15 | 8.4.11; 80
Work Orders | Qualitative | Use Maximo to manage assets, inspections, and maintenance (GD-04) | N/A | N/A | initial system configuration | N/A | N/A | N/A | Expanded asset coverage | N/A | N/A | N/A | QA/QC reporting enhancement | N/A | N/A | N/A | N/A | 8.6; 89
Grid Operations and Procedures | Qualitative | Review Emergency Operations Plan and update annually (GD-05) | N/A | N/A | Q4 / Annual Update | N/A | N/A | N/A | Q4 / Annual Update | N/A | N/A | N/A | Q4 / Annual Update | N/A | N/A | N/A | N/A | 8.7.2; 92
Workforce Planning | Qualitative | Create and rollout HFTD safety training (GD-06) | N/A | N/A | Creation; Q2/2026 | N/A | N/A | N/A | Rollout; Q1,2027 | N/A | N/A | N/A | Maintained | N/A | N/A | N/A | N/A | 8.8;94

## LSPGC Table 8-1
Initiative/ Activity Being Audited | Program type | Applicable procedure | Revision and effective dates
Asset Inspections | QA | LSPGC Maintenance Plan | 2.0, 12/20/2024
Equipment Maintenance and Repair | QA | STATCOMs service agreement | 1.0, 03/12/2025
Grid Operations and Procedures | QA | LSPGC Emergency Operations Plan | 1.0, 01/01/2025

## LSPGC Table 8-3
LSPGC Priority | Risk Level | Response | Mapped GO 95 Rule
P0 | Immediate safety, reliability, or fire risk with potential for significant impact | Repair within 4 weeks (with immediate action if needed) | Level 1
P1 | Moderate to low safety or reliability risk | Repair within 4 weeks to 1 year | Level 2
P2 / P3 | Low impact or acceptable, non-emergency condition | Repair within 1 to 3+ years | Level 3

## Table 9-2
Activity (Program) | Tracking ID | Previous Tracking ID, if applicable | Target Unit | Cml Qtrly Target 2026, Q1 | Cml Qtrly Target 2026, Q2 | Cml Qtrly Target 2026, Q3 | Cml Qtrly Target 2026, Q4 | Cml Qtrly Target 2027, Q1 | Cml Qtrly Target 2027, Q2 | Cml Qtrly Target 2027, Q3 | Cml Qtrly Target 2027, Q4 | Cml Qtrly Target 2028, Q1 | Cml Qtrly Target 2028, Q2 | Cml Qtrly Target 2028, Q3 | Cml Qtrly Target 2028, Q4 | % HFTD Covered in 2026 | % Risk Reduction for 2026 | % Risk Reduction for 2027 | % Risk Reduction for 2028 | Three- Year Total | Activity Timeline Target | Section; Page Number
Defensible Space | VM-04 | LSP-04 | Number of substations inspected | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 50% | n/a | n/a | n/a | 23 | 90 days | 9.6; 109
Transmission Annual MVCD System Inspections | VM-05 | n/a | % Inspection completed and logged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | n/a | n/a | n/a | n/a | n/a | n/a | 9.2.1.1; 101
Transmission Detailed Ground Vegetation Evaluations | VM-06 | n/a | % Evaluation documented and reviewed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | n/a | n/a | n/a | n/a | n/a | n/a | 9.2.2.1; 103
Pole clearing | VM-07 | n/a | % of structures inspected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | n/a | n/a | n/a | n/a | n/a | n/a | 9.4; 106

## Table 10-1
Initiative | Quantitative or Qualitative Target | Activity (tracking ID #) | Previous Tracking ID, if applicable | Target Unit | 2026 End of year total/Completion Date | % risk reduction for 2026 | 2027 Total/Status | % risk reduction for 2027 | 2028 Total/Status | % risk reduction for 2028 | Three- year total | Section; Page number
Environmental Monitoring Systems | Quantitative | Install weather stations at planned project sites (SAF-03) | N/A | Weather stations | 0 | N/A | 1 | N/A | 4 | N/A | 5 | 10.2.3; 131
Environmental Monitoring Systems | Qualitative | Integrate weather stations feed from energized site as a standard feed into the operations center. (SAF-03) | N/A | N/A | In progress; July 2026 | N/A | Completed; October 2027 | N/A | Completed; October 2027 | N/A | N/A | 10.2; 131
Grid Monitoring Systems | Quantitative | Install perimeter cameras at substations (SAF-01) | LSP-06 | # of cameras installed | 0 | N/A | 0 | N/A | 72 | N/A | TBD | 10.4; 138
Grid Monitoring Systems | Qualitative | Install perimeter cameras from energized site as standard feed into the operations center. (SAF-01) | LSP-06 | N/A | In progress; July 2026 | N/A | Completed; July 2027 | N/A | Completed; July 2027 | N/A | N/A | 10.4; 139
Ignition Detection Systems | Qualitative | Complete ignition sensor feasibility study at HFTD energized assets (SAF-02) | N/A | N/A | Start; Q3 2026 | N/A | Completed; End of Q4 2027 | N/A | Completed; End of Q4 2027 | N/A | N/A | 10.4; 138
Ignition Detection Systems | Quantitative | Install integrated fire-detection systems in STATCOM buildings (SAF-02) | N/A | # of detections systems | 1 | N/A | 0 | N/A | 0 | N/A | 1 | 10.4; 138
Weather Station Maintenance and Calibration | Quantitative | Calibrate weather stations semi-annually (SAF-04) | N/A | # of weather stations | 2 | N/A | 2 | N/A | 2 | N/A | 6 | 10.5.5; 146
Weather Station Maintenance and Calibration | Qualitative | Follow manufacturer calibration procedures and document compliance (SAF-04) | N/A | N/A | Procedure followed and documented | N/A | Procedure followed and docuemented | N/A | Procedure followed and docuemented | N/A | 6 | 10.5.5; 145
Weather Forecasting | Quantitative | Expand weather forecasting capability at planned project sites. (SAF-05) | N/A | # of weather stations | 0 | N/A | 0 | N/A | 4 | N/A | 4 | 10.5.4; 145
Weather Forecasting | Qualitative | Integrate weather-forecasting support tool into operations (SAF-05) | N/A | N/A | In progress; Q2 2026 | N/A | Completed; Q2 2027 | N/A | Completed; Q2 2027 | N/A | N/A | 10.5.4; 146