## Tab 1 - Overview tab
IE AIR Attachments
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | LS Power Grid California
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | LS Power Grid California
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC AIR) | EC-Claimed Progress (DR) | IE Declared Actual | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | IE Declared Initiative Completion Percent (%) | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | LSP-01 | 8.1.8.3 | Implement Hot Work Programs | Focus & non-field verifiable | Implement Hot Work Programs | Maintain Hot Work Programs | 2 | 2 | WEAP, CFPP, TTR FPP, & Training Logs | WEAP, CFPP, TTR FPP, & Training Logs | Target met | N/A | 2 | 100% | Fern WEAP Documentation Fern WEAP Logs Fern CFPP Fern TTR FPP & Hot Work Orchard WEAP Training Orchard CFPP & FPP (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | LSP-02 | 8.1.3.1 | Implement Substation Inspection Program | Focus & non-field verifiable | Complete 15 Inspections | 15 | 10 | 10 | Substation Monthly Inspection Reports | 10 | Target not met | Although LSPGC did not meet the target of 15 inspections in 2025, the shortfall was not due to inspections that could have been conducted not being performed. Rather, the target was not met due to delays in the energization of both the Orchard and Fern Substations. Once the Orchard Substation was energized, LSPGC completed all remaining inspections in 2025. | 10 | 100% | 10 Substation Inspection Reports (Frontload Data & DR005) | 67% | 50000 | 14400 | -71.2% | Underspend | Due to the Fern Road Substation remaining under construction with a delayed planned 2025 energization, no inspection activities were conducted. The portion of the planned budget associated with Fern Road was not expended, and inspection activities will not commence until energization and operational status is achieved. Although the Orchard Substation was energized in 2025, it was delayed and did not become operational until March of that year. Inspections were conducted for the remainder of the year (March through December); however, no inspections took place in January and February. | No Goal Provided | N/A
Grid Design Operations and Maintenance | LSP-03 | 8.1.5 | Enhance Use of Computer Maintenance Management Systems (CMMS) | Focus & non-field verifiable | Enhance Use of Computer Maintenance Management Systems (CMMS) | 100% Integration | 100% | 100% | LSP-03 Written Response IBM Maximo Dashboard Screenshot DR004 Written Response | 100% | Target met | N/A | N/A | N/A | IBM Maximo ScrnSht (Frontload Data) LSPGC Written Response (DR004) | 100% | 10000 | 52252 | 422.5% | Overspend | One-time integration labor costs that the $10,000 budget did not account for. | No Goal Provided | N/A
Vegetation Management and Inspections | LSP-04 | 8.2.2 | Establish Risk-Based Buffer Zones & Implement Monthly Substation Inspection Program | Focus & non-field verifiable | Establish Risk-Based Buffer Zones & Implement Monthly Substation Inspection Program | 15 | 10 | 6 | LSP-04 Written Response Substation & Vegetation Monthly Inspection Reports | 6 | Target not met | Considering that the Orchard Substation was energized in March, a maximum of 10 dedicated substation defensible space inspections could have been conducted for 2025. While LSPGC did conduct ten total vegetation inspections, only six defensible space inspections were performed, falling four short of the ten possible dedicated inspections for 2025 | 10 | 100% | 10 Substation Inspection Reports (Frontload Data & DR005) | 40% | 0 | 39300 | 100% | Overspend | Not anticipating capital or contracted scope of work associated with the initiative. | No Goal Provided | N/A
Situational Awareness and Forecasting | LSP-05 | 8.3.2 | Integrate StormGeo | Focus & non-field verifiable | Integrate StormGeo | 100% Integration | Integration Completed in 2024 | Integration Completed in 2024 | StormGeo PO#3546 DR003 Written Response | Integration Completed in 2024 | Target met | N/A | N/A | N/A | LSPGC Written Response StormGeo Procurement DTN EEI Sample Report (DR003) | N/A | 10000 | 0 | -100% | Underspend | LSPGC integrated StormGeo at the Orchard Substation in 2024. | No Goal Provided | N/A
Situational Awareness and Forecasting | LSP-06 | 8.3.4.3 | Install Substation Cameras | Focus & non-field verifiable | Install Substation Cameras | 61 | 29 | 29 | PO LSP10116 PO LSP10121 | 29 | Target not met | Although LSPGC has only installed and claimed 29 of the 61 targeted cameras due to construction delays, all operable cameras are in service demonstrating progress toward initiative completion. | 29 | 100% | Purchase Orders LSP10116 & LSP10121 Notice for Services (NextGen) (Frontload Data) SME Interview: May 04, 2026 | 48% | 0 | 14326 | 100% | Overspend | No planned budget for LSP-06 because camera procurement and installation at both substations were included in the broader substation construction project budgets rather than a standalone WMP financial line item. Associated financial activity was expected to appear only when post-energization expenditures occurred. | No Goal Provided | N/A
Situational Awareness and Forecasting | LSP-07 | 8.3.4.4 | Evaluate and Enhance Use of Live Video | Focus & non-field verifiable | Evaluate and Enhance Use of Live Video | Camera Live Feed Analysis | 1 | 1 | Live Camera Use Meeting Agenda Live Camera Use Notes | 1 | Target met | N/A | 1 | 100% | Camera Notes Meeting Minutes Live Camera Use Internal Meeting Agenda (Frontload Data) SME Interview: May 04, 2026 | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Emergency Preparedness | LSP-09 | 8.4.3 | Establish Annual Contact with Local Fire Agencies | Focus & non-field verifiable | Establish Annual Contact with Local Fire Agencies | 2 | 2 | 2 | LSP-09 Written Response September WEAP Logs (LSP-01) | 2 | Target met | N/A | 2 | 100% | LSPGC Written Response (Frontload Data) | 100% | 0 | 3239 | 100% | Overspend | Site and personnel visits conducted in 2025. | No Goal Provided | N/A
Emergency Preparedness | LSP-10 | 8.4.2 | Formalized Review with Benchmarking | Focus & non-field verifiable | Formalized Review with Benchmarking | Formalized Review with Benchmarking | 2 Review Activities | 2 Review Activities | 2 | 2 | Target met | N/A | 2 | 100% | EOP-011 (Frontload Data) EOP Benchmark Meeting EOP-011 v.1 LSPGC Written Response (DR006) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Community Outreach and Engagement | LSP-11 | 8.5.5 | Best Practice Sharing | Focus & non-field verifiable | Best Practice Sharing | Instances of Collaboration | 8 | 8 | 8 | 8 | Target met | N/A | N/A | N/A | R.Y. EUCI Disaster Preparedness (Frontload Data) LSPGC Written Response AI & The Grid Agenda EUCI Wildfire Mitigation Agenda GridFWD Wildfire Symposium Agenda OEIS Wildfire Symposium Agenda (DR007) | 100% | 20000 | 19151 | -4.2% | Underspend | N/A | No Goal Provided | N/A
Note on K11: Number of "actuals" from which samples are selected

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | LS Power Grid California
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2026-02-19 | 2026-03-11 | All | Frontload Request | Initial Verification Documentation for All Initiatives (.docx; .xlsx; .pdf; .gdb)
2026-04-22 | Void | QAQC Program | DR001
2026-04-24 | 2026-05-08 | QAQC Program | DR001.b | LSPGC_BVNA_DR001b_QAQC Response_20260508
2026-04-24 | 2026-05-06 | Financial | DR002 | LSPGC_BVNA_DR002-007_Response_20260506
2026-04-28 | 2026-05-06 | LSP-05 | DR003 | DR004_Attachment_DTN-EEI_Sample_Report DR004_Attachment_PO3546_StormGeo_Procurement LSPGC_BVNA_DR002-007_Response_20260506
2026-04-28 | 2026-05-06 | LSP-03 | DR004 | LSPGC_BVNA_DR002-007_Response_20260506
2026-04-28 | 2026-05-06 | LSP-02; LSP-04 | DR005 | DR05_Attachment_Orchard_Inspection_Report_Oct2025 LSPGC_BVNA_DR002-007_Response_20260506
2026-04-30 | 2026-05-06 | LSP-10 | DR006 | DR004)Attachment_EOP011_v1_Emergency_Operations_Plan DR006_Attachment_EOP011_Benchmarking_Meeting LSPGC_BVNA_DR002-007_Response_20260506
2026-04-30 | 2026-05-06 | LSP-11 | DR007 | DR007_Conf_AI_and_the_Grid DR007_Conf_DUCI_Wildfire_Mitigation DR007_Conf_GridFWD_Wildfire_Symposium DR007_Conf_OEIS_Wildfire_Symposium LSPGC_BVNA_DR002-007_Response_20260506

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | LS Power Grid California
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2026-05-04 | LSP-02, LSP-04, LSP-06, LSP-07 | SME001 (Mtg. #10) | Associate Manager, Wildfire Mitigation | SME001 was conducted during weekly meeting #10. The IE gathered additional information on the aforementioned initiatives. LSP-02 and LSP-04 received clarification on number of inspections claimed. LSP-06 discussion pertained to claimed camera installations. LSP-07 discussion pertained to the Live Camera Analysis meeting.