## Tab 1 - Overview tab
IE AIR Attachments
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | Horizon West Transmission
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | Horizon West Transmission
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC AIR) | EC-Claimed Progress (DR) | IE Declared Actual | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | IE Declared Initiative Completion Percent (%) | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | 001 | 8.1.3.1 | Asset Inspections | Focus & non-field verifiable | Complete Monthly Inspections | Monthly Inspections | 12 Monthly Inspections | 12 | 11 Monthly Asset & Wildfire Condition Reports (22 total) HWT Written Response (DR002.b) AMP Export of Resolved Maintenance Issue (DR002.c) | 12 | Target met | N/A | 12 | 100% | Monthly Asset Condition Reports (DR002) Monthly Wildfire Condition Reports (DR002) HWT Written Response (DR002.b) AMP Export of Resolved Maintenance Issue (DR002.c) | 100% | 0 | 432953 | 100% | Overspend | HWT explained that revisions were made to how internal personnel engage in HWT asset management and inspection activities, specifically regarding the allocation and recording of their time. Due to this change, 2025 captured a larger portion of labor hours under the billing code associated with asset management and inspection (001). As 2025 was the first year operating under the revised billing protocol, HWT did not have a reliable basis to project expenditures for this initiative, resulting in no projected budget. | N/A | N/A
Vegetation Management and Inspections | 002 | 8.2.2.1 | Vegetation Inspections | Focus & non-field verifiable | Complete Monthly Inspections | Monthly Inspections | 12 Monthly Inspections | Monthly Inspections Complete | AECOM Proposal 11 Monthly Asset & Wildfire Condition Reports (22 total) HWT Written Response (DR001.b) | 12 | Target met | N/A | 12 | 100% | AECOM Proposal (DR001) Monthly Asset Condition Reports (DR002) Monthly Wildfire Condition Reports (DR002) HWT Written Response (DR001.b) | 100% | 17000 | 23895 | 40.6% | Overspend | The vegetation management activity consists of weed control occurring once per year with supplemental treatments up to four times per year. The planned budget represents a reasonable projection based on anticipated treatment frequence while the actual number of treatments required is variable and dependent on vegetation conditions observed during monthly inspections. HWT also detailed that the 2025 actual expenditure reflects invoicing for vegetation management work performed in late 2024 that was not invoiced until 2025, contributing to the higher recorded expenditure. | N/A | N/A
Note on K11: Number of "actuals" from which samples are selected

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | Horizon West Transmission
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2026-02-19 | 2027-03-31 | All | Frontload Request | Initial Verification Documentation for All Initiatives (.docx; .xlsx; .pdf; .gdb)
2026-04-22 | Void | QAQC Program | DR004
2026-04-23 | 2026-04-27 | Nov. Inspection | DR002.b | Horizon West - Response to DR002.b
2026-04-23 | 2026-04-24 | Spare Transformer Issue (Jan.) | DR002.c | AMPExport of Resolved maintenance issue Horizon West - Response to DR002.c
2026-04-24 | 2026-05-06 | QAQC Program | DR004.b | HWT_DR001-QAQC Questionnaire
2026-04-24 | 2026-05-01 | Financial | DR003 | Horizon West - Response to DR003 Horizon West - Response to DR003_#4
2026-04-27 | 2026-04-28 | Veg Inspection Reports | DR001.b | Horizon West - Response to DR001.b
2026-06-03 | 2026-06-08 | Spare Transformer Issue (Jan.) | DR002.d | HWT - Response to BV DR002.d
2026-06-03 | 2026-06-12 | Financial_VegInspec | DR003.b | HWT - Response to BV DR003.b
2026-06-03 | 2026-06-08 | Wildfire Risk Index | DR005 | Horizon West - Response to DR005

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | Horizon West Transmission
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2026-03-31 | Hitachi MACH System & Transformer Oil Gas Monitoring System | SME001 | Senior Engineer | Overview of the Hitachi MACH System for SVC protection and control and the transformer oil gas monitoring system. HWT provided a walkthrough on both systems.