## Tab 1 - Overview tab
IE AIR Attachments
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | Liberty Utilities
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | Liberty Utilities
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC AIR) | EC-Claimed Progress (DR) | IE Declared Actual | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | IE Declared Initiative Completion Percent (%) | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | WMP-GDOM-AI-01 | 8.1.3.1 | Detailed Inspections of Distribution Lines & Equipment | Focus & non-field verifiable | Inspect 260.90 Circuit Miles | 260.9 | 275.2 | 275.2 | 46,290 Points/ 275.20 Circuit Miles | 46,290 Points/ 275.20 Circuit Miles | Target met | N/A | 138 Asset Points | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) Asset Inspection Findings_2025 AI-01 (Frontload Data) 138 Inspection Records Meyers_3500_Pole Detailed Base Sample (DR015.b) | 105% | 500000 | 1871800 | 274.4% | Overspend | Liberty based its 2025 projection on its optimized detailed-inspection schedule and devoted additional resources to close the approximately 90-mile gap relative to the 2023-2025 WMP schedule; per Liberty’s DR003 response, it also captured 2025 other-discretionary (AI-04) and QA/QC (AI-05) inspection costs within this initiative under a shared work-order code (a 95% detailed / 5% QA/QC split). | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-AI-02 | 8.1.3.2 | Intrusive Pole Inspections | Focus & non-field verifiable | Inspect 2,411 Poles | 2411 | 2686 | 2686 | 2,829 Inspections 30 Poles Rejected 2,789 Unique Poles | 2,829 Inspections 30 Poles Rejected 2,789 Unique Poles | Target met | N/A | 132 | 100% | Liberty_Intrusive Data_10.31.25 (Frontload Data) 132 Inspection Records AI-02 Example PDF Report (DR016) | 117% | 175000 | 159720 | -8.7% | Underspend | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-AI-03 | 8.1.3.3 | Patrol Inspections of Distribution Lines & Equipment | Non-focus & non-field verifiable | Inspect 540.90 Circuit Miles | 540.9 | 585.7 | N/A | 85 Asset Inspections 585.7 Circuit Miles | 85 Asset Inspections 585.7 Circuit Miles | Target met | N/A | 25 Asset Points | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) Asset Inspection Findings_2025 AI-03 (Frontload Data) 25 Inspection Records Stateline 3101 Pole Report (DR017/.b) | 108% | 150000 | 72930 | -51.4% | Underspend | Liberty completed each helicopter inspection in a single day rather than the two days assumed in planning, lowering the unit cost. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-AI-04 | 8.1.3.4 | Other Discretionary Inspections of Distribution Electric Lines and Equipment | Focus & non-field verifiable | Inspect 1 Circuit Mile | 1 | 2.24 | 2.24 | 2.24 Circuit Miles 4.46 Circuit Miles | At Least 2.24 | Target not met | The IE has reasonable assurance that Liberty did conduct at least 2.24 circuit miles of drone inspections, however, the absence of the requested inspection reports and the discrepancy in the data does not enable the IE to validate this initiative. | 2 | 0% | Drone Flight Log (Frontload Data) 2025 Drone Inspection Flight Log Final (DR018) | 0% | 150000 | 0 | -100% | Underspend | 2025 costs for this initiative were captured under the same shared work-order code as detailed inspections (AI-01); Liberty was unable to estimate the discretionary portion separately for 2025. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-AI-05 | 8.1.3.5 | Quality Assurance / Quality Control of Inspections | Non-focus & non-field verifiable | Complete 12% Inspection QA/QCs (1,304) | 12% of Detailed Inspections 1,304 Inspections | 1603 | 12% Completion 1,603 Inspections | 14.7% of detailed inspections | 14.7% of detailed inspections | Target met | N/A | 34 | 100% | GDOM-AI-05 QAQC Of Inspections List (Frontload Data) Kings Beach 5200 Pole Sample GDOM-AI-05 Base Sample Request (DR019) | 123% | 30000 | 0 | -100% | Underspend | 2025 QA/QC inspection costs were captured under the shared detailed-inspection work order (AI-01), representing approximately 5% of that bundle. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-AI-06 | 8.1.3.6 | Substation Inspections | Non-focus & non-field verifiable | Inspect 42 Substations | 42 | 60 | 60 | 66 | 66 | Target met | N/A | 22 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) Substation Inspections_2025 AI-06 (Frontload Data) | 157% | 45000 | 0 | -100% | Underspend | 2025 costs were reported within operations and maintenance cost codes not reported in AIR Table 5, and were not also reported under another Tracking ID. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-01 | 8.1.2.1 | Covered Conductor Installation | Focus & field verifiable | Install Covered Conductors on 2.68 Circuit Miles | 2.68 | 3.5 | 3.5 | 3.5 | 3.5 | Target met | N/A | 3.5 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) (Frontload Data) Field Inspections | 131% | 7640000 | 5352321 | -29.9% | Underspend | The 2025 projects were closer to main roadways with easier ground-based access than the helicopter-intensive Tahoe-basin work assumed in planning, and engineering and contracting efficiencies further lowered the per-mile cost. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-02 | 8.1.2.2 | Undergrounding of Electric Lines and/or Equipment | Focus & field verifiable | Underground 0.40 Circuit Miles | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | Target not met | Liberty reported completing 0.3 circuit miles of undergrounding in 2025, below the 0.4-circuit-mile target, due to shifting the original planned project, Tahoe Vista Project, that is a Rule 20 undergrounding initiative to the Cave Rock undergrounding project based upon Liberty’s wildfire risk modeling providing greater wildfire risk reduction than the Tahoe Vista Project. | 0.3 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) Undergrounding_2025 GH-02 (Frontload Data) Field Inspections | 75% | 9100000 | 591700 | -93.5% | Underspend | the planned North Lake Tahoe project was deferred to the 2027 plan year due to permitting delays, and a lower-cost South Lake Tahoe project (completed at approximately $1.97 million per mile) was performed in its place; the substitute project costs are not reported under another WMP initiative. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-03 | 8.1.2.3 | Distribution Pole Replacements and Reinforcements | Focus & field verifiable | Replace and Reinforce 400 Poles | 400 | 1038 | 1038 | 1038 | 1038 | Target met | N/A | 153 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) (Frontload Data) Field Inspections | 260% | 5000000 | 15250370 | 210.4% | Overspend | Pole, expulsion-fuse, and open/grey-wire replacements are executed under single Resiliency Program work orders, and this initiative absorbs a share of expulsion-fuse (GH-12b) and open/grey-wire (GH-12e) costs; Liberty estimates the bundle as approximately 87% poles, 10% open/grey wire, and 3% fuses. Liberty also performed additional risk-driven replacements. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-04 | 8.1.2.4 | Transmission Pole/Tower Replacements and Reinforcements | Non-focus & non-field verifiable | Transmission Pole/Tower Replacements and Reinforcements | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | N/A | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-06 | 8.1.2.6 | Emerging Grid Hardening Technology Installations & Pilot Process | Non-focus & non-field verifiable | Emerging Grid Hardening Technology Installations & Pilot Process | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | N/A | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-08 | 8.1.2.8 | Installation of System Automation Equipment | Non-focus & non-field verifiable | Install 4 Reclosers | 4 | 6 | 6 | 6 | 6 | Target met | N/A | 6 | 100% | Field Inspections Recloser Locations & Test Reports (DR026) | 150% | 1200000 | 268560 | -77.6% | Underspend | Liberty completed the engineering of settings in-house and hired a full-time relay technician rather than relying on contractors, and the reclosers installed in 2025 were located along major highways, which simplified installation; equipment settings work was separated into GO-01. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-12a | 8.1.2.12 | Tree Attachment Removals | Focus & non-field verifiable | Remove 60 Tree Attachments | 60 | 78 | 78 | 78 | 78 | Target met | N/A | 50 | 100% | GDOM-GH-12a Tree Attachments List (Frontload Data) 50 Tree Attachment Records (DR028) | 130% | 1102000 | 1066700 | -3.2% | Underspend | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-12b | 8.1.2.12 | Expulsion Fuse Replacement | Focus & field verifiable | Replace 500 Fuses | 500 | 907 | 907 | 909 | 909 | Target met | N/A | 120 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) (Frontload Data) Field Inspections | 181% | 2000000 | 408290 | -79.6% | Underspend | Of 907 fuses replaced, 280 were charged directly to this initiative, and the remainder were captured under the bundled pole-replacement initiative (GH-03, where fuses represent approximately 3% of the Resiliency Program bundle per Liberty’s DR003 response), with the per-fuse cost also falling below the planning assumption. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-12c | 8.1.2.12 | Animal Guards | Non-focus & non-field verifiable | Install Animal Guards | None Planned | 2 | 2 | 2 | 2 | Target met | N/A | 2 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) (Frontload Data) Three Animal Guard Photos (DR030) | 100% | 0 | 117900 | 100% | Overspend | The spend reflects two installations originally planned for 2024 that were weather-delayed and completed in 2025 and that were not projected in the 2025 plan. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-12e | 8.1.2.12 | Open Wire/Grey Wire | Non-focus & non-field verifiable | Replace Old Service Wire with New Service Wire | 5.24 | 9.17 | 9.17 | 9.17 | 9.17 | Target met | N/A | 9 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) (Frontload Data) 9.17 Circuit Miles of Open/Grey Wire Records (DR031) | 175% | 3000000 | 1581300 | -47.3% | Underspend | A portion of the work was captured under the bundled pole-replacement initiative (GH-03, where open/grey wire represents approximately 10% of the Resiliency Program bundle per Liberty’s DR003 response), and offseason scheduling lowered the per-mile cost. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GH-12f | 8.1.2.12 | Substation Equipment Replacement | Non-focus & non-field verifiable | Replace Equipment in 1 Substation | 1 | N/A | 1 | 7 | 7 | Target met | N/A | 1 | 100% | Substation Equipment Replacement Log Stateline Fence Pictures QA Example (Frontload Data) | 700% | 608000 | 225210 | -63% | Underspend | Liberty realized savings by performing substation work with an internal hire rather than contractors, and additional unplanned substation projects completed in 2025 were not tracked under this initiative. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GO-01 | 8.1.8.1 | Equipment Settings to Reduce Wildfire Risk | Focus & non-field verifiable | Enable 7 Circuits | 7 | 7 | 16 | 16 | 16 | Target met | N/A | 14 | 100% | List of 16 Relays and Test Results 16 Test Reports (Frontload Data) | 229% | 500000 | 712000 | 42.4% | Overspend | Liberty reported implementation of sensitive relay profiles on 16 circuits, exceeding the 7-circuit target. The overspend reflects a reclassified scope rather than uncontrolled costs; funding did not constrain the initiative's progression. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GO-02 | 8.1.8.2 | Grid Response Procedures and Notifications | Non-focus & non-field verifiable | Grid Response Procedures and Notifications | No Target Provided | N/A | N/A | Call Records Outage Process Flow | Call Records Outage Process Flow | Target met | N/A | N/A | N/A | Call Browser Outage Process Flow (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GO-03 | 8.1.8.3 | Personnel Work Procedures & Training in Conditions of Elevated Fire Risk | Non-focus & non-field verifiable | Personnel Work Procedures & Training in Conditions of Elevated Fire Risk | No Target Provided | N/A | N/A | Continued Implementation of Work Procedures and Training in Conditions of Elevated Fire Risk | Continued Implementation of Work Procedures and Training in Conditions of Elevated Fire Risk | Target met | N/A | N/A | N/A | 2025 Annual FPP Training Invite & Roster VM FPP Sign-In Sheet Fire Refresher PPT Tailboard Briefing Checklist (Frontload Data) | 100% | 5000 | 0 | -100% | Underspend | Liberty reported no separately reported 2025 financial activity for this initiative. | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-GO-05 | 8.1.5 | Asset Management and Inspection Enterprise System | Non-focus & non-field verifiable | Asset Management and Inspection Enterprise System | No Target Provided | N/A | N/A | Maintenance of Asset Management & Inspection Enterprise System | Maintenance of Asset Management & Inspection Enterprise System | Target met | N/A | N/A | N/A | Liberty GDOM-GO-05 SME Interview 03.17.26 | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP-GDOM-MR-01 | 8.1.4 | Equipment Maintenance and Repair | Non-focus & non-field verifiable | Equipment Maintenance and Repair | No Target Provided | N/A | N/A | 4,143 Maintenance and Repairs | 4,143 Maintenance and Repairs | Target met | N/A | 34 | 100% | Equipment Maintenance and Repair List (Frontload Data) 34 Maintenance and Repair Records (DR037) | 100% | 500000 | 0 | -100% | Underspend | 2025 maintenance costs were reported within a single operations and maintenance cost code that did not allow the costs to be isolated for AIR Table 5 reporting, and were not also reported under another Tracking ID. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-ESG-01 | 8.2.4 | Vegetation Management Enterprise System | Non-focus & non-field verifiable | Maintenance of VM Enterprise System | No Target Provided | N/A | 3 Online Training Modules | Maintenance of VM Enterprise System | Maintenance of VM Enterprise System | Target met | N/A | N/A | N/A | Liberty VM-ESG-01 SME Interview 03.31.26 | 100% | 844000 | 493610 | -41.5% | Underspend | The original forecast was consistent with the amount submitted in the 2025 General Rate Case (developed in 2023); 2025 spend was lower because less work was required than the higher 2023 activity level that informed the forecast. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-INSP-01 | 8.2.2.1 | Vegetation Management Inspection Program - Detailed | Non-focus & non-field verifiable | Inspect 220 Circuit Miles | 220 | 227 | 227 | 227 | 227 | Target met | N/A | 30 | 100% | GDOM_VM_INSP_01 List (Frontload Data) 30 Miles of Inspection Records (DR045) | 103% | 918000 | 878700 | -4.3% | Underspend | N/A | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-INSP-02 | 8.2.2.2 | Vegetation Management Inspection Program - Patrol | Non-focus & non-field verifiable | Perform Patrol Vegetation Management Inspections | No Target Provided | 158.12 | N/A | 158.12 | 158.12 | Target met | N/A | 29 | 100% | GDOM-VM-INSP-02 List (Frontload Data) ~29 Miles (1024 points) of Inspection Records (DR046) | 100% | 330000 | 185310 | -43.8% | Underspend | The forecast was based on elevated 2021-2023 patrol activity driven by tree mortality; 2025 tree mortality was lower than expected, and prior-year maintenance in high-mortality areas reduced required effort, lowering actual spend. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-INSP-03 | 8.2.2.3 | Vegetation Management Inspection Program - LiDAR | Non-focus & non-field verifiable | Inspect 700 Circuit Miles | 700 | 700 | 700 | 20,000 Points Equaling 700 Circuit Miles | 20,000 Points Equaling 700 Circuit Miles | Target met | N/A | 35 Asset Points | 100% | LiDAR Span Data 2025 LiDAR Treetops 2025 (Frontload Data) | 100% | 735000 | 598550 | -18.6% | Underspend | Liberty over-forecasted costs for this initiative in 2025 and worked with its vendor to realize year-over-year efficiency improvements, which it reflected in a mid-2025 re-forecast of approximately $600,000. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-QAQC-01 | 8.2.5 | Quality Assurance and Quality Control | Non-focus & non-field verifiable | Perform QA/QC on 229 Circuit Miles | 229 | 237.5 | 237.5 | 237.5 | 237.5 | Target met | N/A | 33 Asset Points | 100% | QAQC Project Tracking Log VM-QAQC-01 Itemized List of Audits (Frontload Data) 33 Inspection Records (DR048) | 104% | 541000 | 543390 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-VFM-01 | 8.2.3.1 | Pole Clearing | Focus & non-field verifiable | Clear 4,960 Poles | 4960 | 5091 | 5091 | 5065 | 5065 | Target met | N/A | 135 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) (Frontload Data) 135 Pole Clearance Records (DR049) | 103% | 454000 | 526110 | 15.9% | Overspend | The forecast was aligned with the 2025 General Rate Case rate of $89.52 per pole; higher 2025 rates of $98.90 per pole caused costs to exceed the forecast. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-VFM-02 | 8.2.3.2 | Wood and Slash Management | Non-focus & non-field verifiable | Complete Wood and Slash Management for 280 Acres | 280 | 387 | 387 | 354.79 | 354.79 | Target met | N/A | 34 Assets Points | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) 2025 Fuel Management Tracker Wood and Slash Management List (Frontload Data) 34 Records of Fuels Management (DR050) | 127% | 1381000 | 1111610 | -19.5% | Underspend | Liberty over-forecasted costs for this initiative in 2025 and re-forecasted the initiative’s costs in mid-2025 to approximately $1,070,000. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-VFM-03 | 8.2.3.5 | Substation Defensible Space | Non-focus & non-field verifiable | Complete Defensible Space for 12 Substations | 12 | 12 | 12 | 12 | 12 | Target met | N/A | 12 | 100% | Liberty Substation Annual work Tracker 2025 Cycle 1 & Cycle 2 Work Description Cycle 1 & Cycle 2 Pre-Emergent Chemical Reports (Frontload Data) | 100% | 84000 | 38440 | -54.2% | Underspend | Liberty over-forecasted costs for this initiative in 2025 and re-forecasted the initiative’s costs in mid-2025 to approximately $40,000. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-VFM-04 | 8.2.3.7 | Fire-Resilient Rights-of-Way | Non-focus & non-field verifiable | Create Fire-Resilient Rights-of-Way | No Target Provided | 8.22 | N/A | 8.22 | 8.22 | Target met | N/A | 8 | 100% | VFM-04 Work List (Frontload Data) VFM-04 Work Order Details (DR052) | 100% | 577000 | 1446840 | 150.8% | Overspend | the 2025 workload increased due to overlap with planned Fall-In Mitigation activities; work orders in the overlap area were reclassified to Fire-Resilient Rights-of-Way, with approximately $800,000 of funding shifted from the Fall-In Mitigation budget (VFM-06). | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-VFM-05 | 8.2.3.3 | Clearance | Non-focus & non-field verifiable | Clear 700 Circuit Miles | 700 | 701.33 | 701.33 | 701.33 | 701.33 | Target met | N/A | 33 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) (Frontload Data) VM-VFM-05 Clearance Base Request Details (DR053) | 100% | 1406000 | 1766160 | 25.6% | Overspend | Approximately $70,000 reflects unplanned padmount-transformer clearing; of the remaining variance, one vendor (subsequently discontinued) accounted for approximately 45% of vendor cost while completing only 36% of the work. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-VFM-06 | 8.2.3.4 | Fall-In Mitigation | Focus & field verifiable | Perform Mitigation on 220 Circuit Miles | 220 | 382.62 | 382.62 | 382.62 | 382.62 | Target met | N/A | 102 | 100% | IE_FrontloadDataRequest.gdb (Geodatabase File) (Frontload Data) Field Inspections | 174% | 4810000 | 3063100 | -36.3% | Underspend | Approximately $800,000 was reallocated from this initiative to Fire-Resilient Rights-of-Way (VFM-04) for overlapping work, contributing to the underspend. | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-VFM-07 | 8.2.3.6 | High-Risk Species | Non-focus & non-field verifiable | High-Risk Species | No Target Provided | N/A | Assessment Concluded in 2023 | N/A | N/A | Target met | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Vegetation Management and Inspections | WMP-VM-VFM-08 | 8.2.3.8 | Emergency Response Vegetation Management | Non-focus & non-field verifiable | Emergency Response Vegetation Management | No Target Provided | N/A | N/A | Veg. Threat Procedure and Management Plan | Veg. Threat Procedure and Management Plan | Target met | N/A | N/A | N/A | Vegetation Management Plan Vegetation Threat Procedure (Frontload Data) | 100% | 0 | 10370 | 100% | Overspend | Liberty reported $10.4K in actual 2025 spend against a $0 planned amount for emergency-response vegetation management, as Liberty did not forecast any 2025 costs for this initiative. | No Goal Provided | N/A
Situational Awareness and Forecasting | WMP-SA-01 | 8.3.2 | Install Weather Stations | Non-focus & non-field verifiable | Install Weather Stations | Unknown | N/A | Zero - All Planned Weather Stations Have Been Installed | Statement | N/A | N/A | N/A | N/A | N/A | Liberty Frontload Written Response (Frontload Data) | N/A | 50000 | 199200 | 298.4% | Overspend | The 2025 forecast covered only weather-station maintenance and calibration (approximately $67,650); additional initiative costs of approximately $131,545 – spare parts, the data plan, and support services, and fuel-moisture sampling – were not included in the initial projection. | No Goal Provided | N/A
Situational Awareness and Forecasting | WMP-SA-02 | 8.3.3 | Fault Indicators | Focus & non-field verifiable | Install Fault Indicators on 7 Circuits | 7 | 7 | 7 | 8 | 8 | Target met | N/A | 7 | 100% | Fault Indicator Installation List (Frontload Data) 7 FI Notification Activity (DR039) Updated FI Installation List Muller1296 Response (DR039.b) | 114% | 300000 | 0 | -100% | Underspend | Grid-monitoring work was installed as part of the Sensitive Relay Profile program and the associated costs are reported under the Equipment Settings to Reduce Wildfire Risk initiative (GO-01); the costs are not also reported under another Tracking ID. | No Goal Provided | N/A
Situational Awareness and Forecasting | WMP-SA-03 | 8.3.4 | Alert Wildfire Cameras | Non-focus & non-field verifiable | Alert Wildfire Cameras | Unknown | N/A | Adoption of Existing ALERT Tahoe Camera Network – Adding 16 Camera Locations | 16 Cameras at UNR 2 Cameras at UCSD | 16 Cameras at UNR 2 Cameras at UCSD | Target met | N/A | N/A | N/A | SA-03 Installation Table (Frontload Data) | 100% | 0 | 126000 | 100% | Overspend | The costs are for wildfire-detection cameras (AlertWildfire) that were not included in the 2025 projected costs and are not also reported under another WMP initiative. | No Goal Provided | N/A
Situational Awareness and Forecasting | WMP-SA-04 | 8.3.5 | Weather Forecasting | Non-focus & non-field verifiable | Weather Forecasting | No Target Provided | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | LIB Calibration Liberty Calibration Summary 2025 (Frontload Data) | N/A | 0 | 276660 | 100% | Overspend | The costs reflect internal labor and overhead not included in the initial 2025 projection – the same pattern as CO-01 and EP-04. | No Goal Provided | N/A
Situational Awareness and Forecasting | WMP-SA-06 | 8.3.6 | Ignition Likelihood Calculation | Non-focus & non-field verifiable | Ignition Likelihood Calculation | Model Enhancements | N/A | N/A | Model Enhancements | Model Enhancements | Target met | N/A | N/A | N/A | WMP Model Documentation – Technosylva (Frontload Data) | 100% | 806000 | 1272700 | 57.9% | Overspend | The overspend reflects non-recurring professional services to expand modeling capabilities in response to updated WMP guidance and to support data-request responses and the WMP Revision Notice; supporting statements of work are on file. | No Goal Provided | N/A
Situational Awareness and Forecasting | WMP-SA-07 | N/A | Ignition Consequence Calculation | Non-focus & non-field verifiable | Ignition Consequence Calculation | Model Enhancements | N/A | N/A | Model Enhancements | Model Enhancements | Target met | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Emergency Preparedness | WMP-EP-01 | 8.4.2 | Wildfire and PSPS Emergency Preparedness Plan | Non-focus & non-field verifiable | Wildfire and PSPS Emergency Preparedness Plan | No Target Provided | N/A | Completed in 2023 | Completed in 2023 | Completed in 2023 | N/A | N/A | N/A | N/A | Liberty Written Response (Frontload Data) | N/A | 35000 | 0 | -100% | Underspend | No 2025 financial activity was reported; the preparedness plan was verified as complete in the prior cycle, and the implementation review reflects that the initiative is not applicable for the review year. | No Goal Provided | N/A
Emergency Preparedness | WMP-EP-02 | 8.4.3 | Collaboration and Coordination with Public Safety Partners | Non-focus & non-field verifiable | Complete Collaboration and Coordination with Public Safety Partners | Conduct emergency drills. Continue engagement with local stakeholders, meet with Community Advisory Board | 54 | 26 Events | 26 | 26 | Target met | N/A | 21 | 100% | After-Action Review Meeting June 26, 2025 PSPS Tabletop Exercise June 26, 2025 Evaluation of TTX May 28, 2025 (Frontload Data) Liberty Response DR_010_EP-02 22 Meeting Agenda/Minutes (DR010) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Emergency Preparedness | WMP-EP-03 | 8.4.4 | Public Notification & Comm. Strategy | Non-focus & non-field verifiable | Public Notification & Comm. Strategy | Continued engagement with local stakeholders to prepare for and respond to fire-related events. | N/A | Completed | Continued Outreach & Engagement 2025 | Continued Outreach & Engagement 2025 | Target met | N/A | N/A | N/A | 2025 Outreach & Engagement Log (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Emergency Preparedness | WMP-EP-04 | 8.4.5 | Preparedness and Planning for Service Restoration | Non-focus & non-field verifiable | Preparedness and Planning for Service Restoration | Enhanced documentation and use of lessons learned to update plans. | N/A | Lessons Learned Improvements | CEMP & PSPS Playbook Updates | CEMP & PSPS Playbook Updates | Target met | N/A | N/A | N/A | Corporate Emergency Management Plan (CEMP) PSPS Playbook 06.23.25 (Frontload Data) | 100% | 225000 | 479760 | 113.2% | Overspend | Actual costs exceeded projections due to internal labor and overhead not included in the initial 2025 projection. | No Goal Provided | N/A
Emergency Preparedness | WMP-EP-05 | 8.4.6 | Customer Support in Wildfire & PSPS Emergencies | Non-focus & non-field verifiable | Customer Support in Wildfire & PSPS Emergencies | Conduct incident command training, hold a virtual PSPS tabletop exercise. Continue implementation of AFN Plan. | 5 | 2025 PSPS took place 3/27/25 and 4/3/25; Tabletop conducted on 5/28/25; Full scale exercise conducted on 6/26/25; IMT Training completed in Q1 | 5 | 5 | Target met | N/A | 5 | 100% | 2025 ICS Training Log May 28, 2025, TTX Evaluation PSPS Tabletop Exercise, June 26, 2025 (Frontload Data) Nine Outreach Materials Two After-Action Reports California Wildfire Survey (DR013) | 100% | 55000 | 98630 | 79.3% | Overspend | late-season 2024 PSPS-event costs were invoiced in 2025 and not accrued in 2024 and were therefore recorded in 2025. | No Goal Provided | N/A
Emergency Preparedness | WMP-EP-06 | N/A | Learning After Wildfire & PSPS Events | Non-focus & non-field verifiable | Learning After Wildfire & PSPS Events | After action report for each event . | N/A | N/A | After Action Report for Each Event | After Action Report for Each Event | Target met | N/A | N/A | N/A | 7 After-Action Reports (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Community Outreach and Engagement | WMP-CO-01 | 8.5.2 | Public Outreach & Edu. Awareness for Wildfire, PSPS, Outages from Protective Equipment | Non-focus & non-field verifiable | Public Outreach & Edu. Awareness for Wildfire, PSPS, Outages from Protective Equipment | Two wildfire and PSPS outreach surveys. | 6 in-person events, 1 virtual event, and 22 rounds of emails, website posts, and social media posts | 76 in-person meetings and events, 27 virtual events, 70 rounds of emails, and social media posts, 3 AFN mailings, and 1 door hanger | 2 Wildfire & PSPS Outreach Surveys | 2 Wildfire & PSPS Outreach Surveys | Target met | N/A | 2 | 100% | Liberty Survey Results June 2025 Liberty Survey Results November 2025 (Frontload Data) | 100% | 90000 | 174515 | 93.9% | Overspend | Liberty tracked and reported internal labor supporting engagement with Community-Based Organizations (CBOs) that were not included in its projected expenditures. | No Goal Provided | N/A
Community Outreach and Engagement | WMP-CO-03 | 8.5.3 | Engagement w/ AFN Pop. Local Gov., & Tribal Communities | Non-focus & non-field verifiable | Engagement w/ AFN Pop. Local Gov., & Tribal Communities | Target Not Yet Set | N/A | Variety of Communication Methods | 229 Outreach Events | 229 Outreach Events | Target met | N/A | N/A | N/A | 2025 Outreach and Engagement Tracker (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Community Outreach and Engagement | WMP-CO-05 | 8.5.5 | Best Practice Sharing w/ Other ECs | Non-focus & non-field verifiable | Best Practice Sharing w/ Other ECs | Participation in working groups and Joint IOU Councils. | N/A | N/A | Participation in Working Groups & Joint IOU Councils | Participation in Working Groups & Joint IOU Councils | Target met | N/A | N/A | N/A | CO-05 Response (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Note on K11: Number of "actuals" from which samples are selected

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | Liberty Utilities
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2026-02-19 | 2026-03-06 | All | Frontload Request | Initial Verification Documentation for all Initiatives (.docx; .xlsx; .pdf; .gdb)
2026-02-19 | 2026-02-24 | EOY Financials | DR001 | Liberty Response_DR001.xlsx
2026-03-12 | 2026-03-17 | AI-01; AI-03; AI-06; GH-02 | DR002 | AI-01: Asset Inspection Findings_2025 AI-01.xlsx AI-03: Asset Inspection Findings_2025 AI-03.xlsx AI-06: Substation Inspections_2025 AI-06.xlsx GH-02: Undergrounding_2025 GH-02.xlsx
2026-03-25 | 2026-04-10 | EP-02 | DR010 | Workgroup Notes, Meeting Agendas, Slides, and Minutes (18)
2026-03-25 | 2026-04-10 | EP-05 | DR013 | After Action & Post Event Report (2) Outreach Materials (9) Survey (1)
2026-03-25 | 2026-04-10 | GDOM-AI-01 | DR015 | BASE: AI-01 Detailed Base Sample Request Workbook.xlsx, Meyers_3500_Pole Detailed Base Sample ALTERNATE: AI-01 Detailed Alternate Request Workbook.xlsx, MEY3300_146316_202-06-22
2026-03-25 | 2026-04-10 | GDOM-AI-02 | DR016 | BASE: AI-02 Example PDF Report, AI-02 Intrusive Pole Inspec Base Request.xlsx ALTERNATE: AI-02_IntrusivePoleInspec_AltRequest.xlsx
2026-03-25 | 2026-04-10 | GDOM-AI-03 | DR017 | BASE: AI-03 45096_Stateline_3101_Pole, AI-03 Patrol Base Sample Workbook.xlsx ALTERNATE: AI-03 Patrol Alternate Sample Workbook.xlsx, Tahoe_City_7300_Pole
2026-03-25 | 2026-04-10 | GDOM-AI-04 | DR018 | 2025 Drone inspection flight log final.xlsx
2026-03-25 | 2026-04-10 | GDOM-AI-05 | DR019 | BASE: GDOM-AI-05 Base Sample Request.csv, Kings_Beach_5200_Pole AI-05 Base Request ALTERNATE: GDOM-AI-05 Alternate Sample Request.csv, Kings_Beach_5200_Pole AI-05 Alternate Request
2026-03-25 | 2026-04-10 | GDOM-AI-06 | DR020 | Substation Inspectoins_2025 AI-06.xlsx
2026-03-25 | 2026-04-10 | GDOM-GH-12a | DR028 | BASE: GH-12a Tree Attachments Base Sample Request.csv ALTERNATE: GH-12a Tree Attachments Alternate Sample.csv
2026-03-25 | 2026-04-10 | GDOM-GH-12c | DR030 | processed-1BFE8A91-8775-4842-958E-52333A7501C1.jpeg processed-25B25FF0-EB2E-41E0-AE4E-F60D904167F2.jpeg processed-6968B424-086D-4855-B515-F8094326C8D6.jpeg
2026-03-25 | 2026-04-10 | GDOM-GH-12e | DR031 | GH-12e Open Wire Grey Wire Sample.csv
2026-03-25 | 2026-04-10 | SA-02 | DR039 | Work Order for Fault Indicator Installs (7)
2026-03-25 | 2026-04-10 | VM-INSP-01 | DR045 | BASE: VM-INSP-01 Detailed Base Sample Request.csv ALTERNATE: VM-INSP-01 Detailed Alternate Sample Request.csv
2026-03-25 | 2026-04-10 | VM-INSP-02 | DR046 | BASE: VM-INSP-02 Patrol Base Sample Request.csv ALTERNATE: VM-INSP-02 Patrol Alternate Sample Request.csv
2026-03-25 | 2026-04-10 | VM-INSP-03 | DR047 | LiDAR_Span_Data_2025.xlsx LiDAR_Treetops_2025.xlsx
2026-03-25 | 2026-04-10 | VM-QAQC-01 | DR048 | BASE: VM-QAQC-01 Base Sampling Request ALTERNATE: VM-QAQC-01-Sampling Request-Alternate
2026-03-25 | 2026-04-10 | VM-VFM-01 | DR049 | BASE: VM-VFM-01 Pole Clearing Base Request.csv ALTERNATE: VM-VFM-01 Pole Clearing Alternate Request.csv
2026-03-25 | 2026-04-10 | VM-VFM-02 | DR050 | BASE: VM-VFM-02 Wood and Slash Base Request.csv ALTERNATE: VM-VFM-02 Wood and Slash Alternate Request.csv
2026-03-25 | 2026-04-10 | VM-VFM-04 | DR052 | VM-VFM-04 FRC.csv
2026-03-25 | 2026-04-10 | VM-VFM-05 | DR053 | VM_VFM_05.xlsx
2026-04-13 | 2026-04-22 | GH-02 | DR022 | CaveRockUG_Amended (8 Files) Cave Rock UG - Asbuilt
2026-04-13 | 2026-04-21 | GH-08 | DR026 | WMP-GDOM-GH-08.xlsx CEM_41-CB_SEL-651RA_TEST-RESULTS_20241211.html CEM_42-CB_SEL-651RA_Test-Results_20241212.html Meyers 3100-R1 Commissioning Results.html Meyers 3211-R1 Commissioning.html Meyers 3500-R-1 SEL-651RA.html SRB_51-CB_SEL-651RA_TEST-RESULTS_20250123
2026-04-14 | 2026-04-21 | SA-02 | DR039.b | Muller1296_300500: LU_DR039.b_SA-02.Response.xlsx, Mueller1296 response.eml
2026-04-22 | 2026-04-29 | Financials | DR003 | DR003 Response.docx Item #8-1 SA-06: 2025 Direxyon Statements of Work
2026-04-22 | Void | QAQC Program | DR004
2026-04-24 | 2026-05-01 | QAQC Program | DR004.b | Asset Inspection QAQC Program Libery_DR004.b_QAQC Questionnaire.docx VM-04_Post_Work_Verification_3.0
2026-04-27 | 2026-04-29 | AI-01 | DR015.b | BASE: DR015.b Base Request.csv ALTERNATE: DR015.b Alternate Request.csv
2026-04-27 | 2026-04-29 | AI-03 | DR017.b | DR017.b AI-03 Resopnse.csv
2026-04-30 | 2026-05-07 | MR-01 | DR037 | DR037 Base Sample.xlsx DR037 Alternate Sample.xlsx
2026-05-05 | 2026-05-06 | GH-12f Financials | DR003.b | LU_Response_DR003.b.docx

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | Liberty Utilities
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2026-03-17 | GDOM-GO-05 | SME001 | Geodatabase Subject Matter Experts | Annual review of Liberty's enterprise asset data management systems. Walkthrough of the Fulcrum application which contains asset and inspection data and it's implementation with SQL/PowerBI
2026-03-31 | VM-ESG-01 | SME002 | Vegetation Management and Wildfire Prevention | Review of Liberty's Vegetation Management Enterprise System. Liberty provided a walkthrough of the FieldNote program and implementaion timeline/updates.