## Tab 1 - Overview tab
IE AIR Attachments
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | San Diego Gas & Electric
Legends
Tab 1 | Overview Tab - Instructions and overview
Tab 2 | Catalog of Initiatives - Initiative review and funding compliance of all initiatives
Tab 3 | Data Requests - Comprehensive list of documents reviewed
Tab 4 | SME Interviews - Summary of interviews conducted

## Tab 2 - Catalog of Initiatives
Catalog of Initiatives
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | San Diego Gas & Electric
WMP Category | Initiative Tracking ID | WMP Section Number | Initiative Name | Initiative Type | WMP - Initiative Description | WMP - Initiative Target | EC-Claimed Progress (Q4 QDR) | EC-Claimed Progress (EC AIR) | EC-Claimed Progress (DR) | IE Declared Actual | EC-Claimed Initiative Status | Target Not Met - Rationale | Sample Size (#) | Sample Validation Rate (%) | Verification Method | IE Declared Initiative Completion Percent (%) | WMP - Planned Spend ($) | EC-Claimed Actual Spend ($) | Variance (%) | Funding discrepancy - finding | Funding discrepancy - detail | Satisfied Risk Reduction Goal - finding | Satisfied Risk Reduction Goal - detail
Grid Design Operations and Maintenance | WMP.455 | 8.1.2.1 | Distribution Overhead Hardening (Covered Conductor) | Non-focus & non-field verifiable | Complete 50 Circuit Miles | 50 | 52.03 | 52.03 | 52.03 | 52.03 | Target met | N/A | 21 | 100% | Field Inspections Circuit Locations (Frontload Data) | 104% | 83473000 | 92501430 | 10.8% | Overspend | The variance is approximately 36 percent unit volume and 64 percent unit cost, consistent with implementation against the amended higher mileage target. | Yes | N/A
Grid Design Operations and Maintenance | WMP.459 | 8.1.4.4 | Expulsion Fuse Replacement | Focus & non-field verifiable | Replace 700 Fuses | 700 | 503 | 503 | 503 | 503 | Target not met | The quantity of installed fuses in 2025 was 72% of the total target and therefore falls outside the 95% initiative validation rate set by Energy Safety. | 109 | 100% | SDG&E Geodatabase File Expulsion Fuse Replacement List (Frontload Data) 109 Fuse Records (DR018) | 72% | 1549570 | 950300 | -38.7% | Underspend | The program was paused in April 2025 pending the Petition to Amend, and it was restarted after the amendment was denied in July 2025. | No | Only 72% of the total target was achieved, thus not meeting the risk reduction goal.
Grid Design Operations and Maintenance | WMP.461 | 8.1.2.11.1 | PSPS Sectionalizing | Focus & non-field verifiable | Install 10 Switches | 10 | 9 | 9 | 9 | 9 | Target not met | Although the sampling data was validated and the IE verified that the utility installed nine switches, SDG&E had a shortfall of one resulting in an initiative validation rate of 90%, outside of the 95% threshold set forth by Energy Safety. | 9 | 100% | PSPS Section Enhance List (Frontload Data) SDG&E Written Response 7 Install Records (9 Switches) (DR019) | 90% | 1485000 | 980510 | -34% | Underspend | The final device was delayed by municipal and agency permitting and was approved in January 2026 and installed in February 2026. | No | Only 9 of the 10 switches were installed, thus not meeting the risk reduction goal.
Grid Design Operations and Maintenance | WMP.462 | 8.1.2.7 | Microgrids |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1236000 | 2158000 | 75% | Overspend | full battery replacement at the Cameron Corners microgrid. SDG&E reports that the originally installed battery storage assets failed to meet minimum performance guarantees, including power output, energy capacity, and round-trip efficiency, and required replacement. The replacement cost is asset-specific and was not contemplated in the 2025 plan. | N/A | N/A
Grid Design Operations and Maintenance | WMP.463 | 8.1.2.8.1 | Advanced Protection | Focus & field verifiable | Advanced Protection on 8 Circuits | 8 | 7 | 7 | 7 | 7 | Target not met | 78 percent rate reflects both the seven of eight circuit completion and the installation level shortfall on the circuits counted as complete. | 7 | 88% | Field Inspections Circuit Structure Locations & As-builts (DR020/.b) SME Interview (DR020.b) | 78% | 8155000 | 8452640 | 3.6% | Overspend | N/A | Yes | N/A
Grid Design Operations and Maintenance | WMP.464 | 8.1.4.5 | Maintenance, Repair, and Replacement of Connectors, Including Hotline Clamps | Focus & field verifiable | Maintenance, Repair, and Replacement of Connectors, Including Hotline Clamps | 950 | 110 | 110 | 110 | 110 | Target not met | 2025 AIR classifies this initiative as Delayed, reflecting that only 110 of the 950 targeted hotline clamps were replaced in 2025. | 62 | 100% | Field Inspections Pole Locations (Frontload Data & DR003) | 12% | 1753180 | 453210 | -74.1% | Underspend | Front-loaded delivery in 2023 and 2024, measured against the unreduced 950-clamp 2025 baseline that Energy Safety upheld when it denied SDG&E's request for a reduction. | No | This initiative was delayed resulting in not meeting target and risk reduction goal.
Grid Design Operations and Maintenance | WMP.466 | 8.1.2.11.3 | Generator Grant Program | Non-focus & non-field verifiable | Continue to provide portable backup power solutions to vulnerable, electricity dependent customers. | Continue to provide portable backup power solutions to vulnerable, electricity dependent customers. | Eligibility List Updates/ Customer Training | The Qualitative Milestones for this Program Were Achieved | Portable Backup Power Solutions Provided | Portable Backup Power Solutions Provided | Target met | N/A | N/A | N/A | SDG&E Written Response (Frontload Data) | 100% | 3953000 | 2180000 | -44.9% | Underspend | Lower count of portable propane generators and backup battery units deployed under the Generator Grant Program to this planned realignment. | N/A | N/A
Grid Design Operations and Maintenance | WMP.467 | 8.1.2.11.4 | Generator Assistance Program | Non-focus & non-field verifiable | Continue to provide rebates on portable backup power solutions to customers who experience PSPS. | Continue to provide rebates on portable backup power solutions to customers who experience PSPS. | Eligibility List Updates/ Marketing Communications Distributed | The Qualitative Milestones for this Program Were Achieved | Rebate Support Provided | Rebate Support Provided | Target met | N/A | N/A | N/A | SDG&E Written Response 2025 GAP End of Program Report (Frontload Data) | 100% | 494000 | 670620 | 35.8% | Overspend | Increased customer participation, driven by PSPS de-energizations in late 2024 and early 2025. | N/A | N/A
Grid Design Operations and Maintenance | WMP.468 | 8.1.2.11.2 | Standby Power Programs | Non-focus & non-field verifiable | Provide 89 Generators | 89 | 88 | 88 | 88 | 88 | Target met | N/A | 54 | 100% | Fixed Power Backup List (Frontload Data) 54 Work Records (DR024) | 99% | 1000000 | 3965250 | 296.5% | Overspend | Reallocation of funding and accelerated deployment of higher-cost permanent resiliency solutions during a planned transition year. In 2025, the residential component of Fixed Backup Power transitioned to the Customized Resiliency Assessment Program, increasing installations of permanent backup battery systems, which carry higher per-unit costs than originally forecast. | No | Risk reduction goal was 19.9105% - fell short at 17.46%.
Grid Design Operations and Maintenance | WMP.473 | 8.1.2.2 | Strategic Undergrounding | Non-focus & field verifiable | Underground 28 Circuit Miles | 28 | 32.56 | 32.57 | 32.57 | 32.57 | Target met | N/A | 17 | 100% | Field Inspections Circuit Locations (Frontload Data) As-builts (DR025) | 116% | 87221000 | 88750980 | 1.8% | Overspend | N/A | Yes | N/A
Grid Design Operations and Maintenance | WMP.475 | 8.1.2.5.1 | Distribution Overhead System Hardening | Focus & field verifiable | Distribution Overhead System Hardening | 0 | 0.11 | 0.11 | 0.11 | 0.11 | N/A | N/A | 0.11 | 100% | Field Inspections Pole Locations (Frontload Data) | N/A | 5950000 | 7655780 | 28.7% | Overspend | Increased O&M costs that depend on true-up activities, remediation efforts, and final design packages that are difficult to estimate at planning. | N/A | N/A
Grid Design Operations and Maintenance | WMP.478 | 8.1.3.1 | Distribution Overhead Detailed Inspections | Non-focus & non-field verifiable | Complete 13,275 Inspections | 13275 | 17950 | 17950 | 17950 | 17950 | Target met | N/A | 35 | 100% | SDG&E Asset Inspection Points List (Frontload Data) 35 Inspection Records (DR027) | 135% | 10056630 | 9186040 | -8.7% | Underspend | N/A | Yes | N/A
Grid Design Operations and Maintenance | WMP.479 | 8.1.3.2 | Transmission Overhead Detailed Inspections | Focus & non-field verifiable | Complete 2,479 Inspections | 2479 | 2184 | 2184 | 2184 | 2184 | Target not met | Although the documentation reviewed was complete, SDG&E did not meet the 2025 goal set forth in the 2023-2025 WMP. | 130 | 100% | SDG&E Asset Inspection Points List (Frontload Data) 130 Inspection Records (DR028) | 88% | 1957920 | 1544780 | -21.1% | Underspend | Forecast variability on active structures on energized tielines and to the CAISO-approved six-month completion timeframe, which shifts anticipated completion timing across the boundary of the reporting year. | No | Target was not met thus the risk reduction goal was not achieved (goal of 0.9580%, 0.81% achieved).
Grid Design Operations and Maintenance | WMP.481 | 8.1.3.3 | Distribution Infrared Inspections | Non-focus & non-field verifiable | Complete 300 Inspections | 300 | 302 | 302 | 302 | 302 | Target met | N/A | 31 | 100% | SDG&E Asset Inspection Points List (Frontload Data) SDG&E Written Response 31 Inspection Records (DR029) | 101% | 5000 | 13580 | 171.6% | Overspend | Increased labor costs. | N/A | N/A
Grid Design Operations and Maintenance | WMP.482 | 8.1.3.4 | Transmission Infrared Inspections | Focue & non-field verifiable | Complete 7,331 Inspections | 7331 | 6976 | 6976 | 6976 | 6976 | Target met | N/A | 136 | 100% | SDG&E Asset Inspection Points List (Frontload Data) SDG&E Written Response 31 Inspection Records (DR030) | 95% | 0 | 0 | 0% | No discrepancy | N/A | Yes | N/A
Grid Design Operations and Maintenance | WMP.483 | 8.1.3.5 | Distribution Wood Pole Intrusive Inspections | Non-focus & non-field verifiable | Complete 344 Inspections | 344 | 1478 | 1478 | 1478 | 1478 | Target met | N/A | 34 | 430% | SDG&E Asset Inspection Points List (Frontload Data) 34 Inspection Records (DR031) | 430% | 1541420 | 1345920 | -12.7% | Underspend | Additional inspections beyond the 344 target were performed under GO 95, Rule 44, and charged to the requesting project rather than being recorded as O&M, so the WMP O&M expenditure was less than planned despite a higher inspection volume. | Yes | N/A
Grid Design Operations and Maintenance | WMP.488 | 8.1.3.8 | Distribution Overhead Patrol Inspections | Non-focus & non-field verifiable | Complete 86,535 Inspections | 86535 | 86040 | 86040 | 86040 | 86040 | Target met | N/A | 35 | 100% | SDG&E Asset Inspection Points List (Frontload Data) 35 Inspection Records (DR032) | 99% | 1183950 | 1165880 | -1.5% | Underspend | N/A | No | Met target for initiative, but fell short of 4.3679% risk reduction goal achieving 0.82%.
Grid Design Operations and Maintenance | WMP.489 | 8.1.3.9 | Transmission Overhead Patrol Inspections | Non-focus & non-field verifiable | Complete 7,533 Inspections | 7533 | 7263 | 7263 | 7263 | 7263 | Target met | N/A | 34 | 100% | SDG&E Asset Inspection Points List (Frontload Data) SDG&E Written Response 34 Inspection Records (DR033) | 96% | 0 | 0 | 0% | No discrepancy | N/A | No | The WMP outlined a risk reduction goal of .0298%. In the 2025 EC AIR, SDG&E claimed a 0.01% risk reduction goal satisfied the target.
Grid Design Operations and Maintenance | WMP.491 | 8.1.6.2 | Quality Assurance/Quality Control of Distribution Detailed Inspections | Non-focus & non-field verifiable | Complete QA/QC of 50% of Issues Identified Additional 5% of Inspections (1,104 Audits) | 50% of Issues Identified Additional 5% of Inspections (1,104 Audits) | 1078 | 59% | 1,078 Inspection Records | 1078 | Target not met | SDGE’s completion of 1,078 QA/QC audits fell 26 audits short of the outlined target goal (1,104) based on the methodology provided in the WMP. Further, the IE was only able to verify 25 inspection records of the 34 requested from SDG&E. | 34 | 74% | QA/QC Audit List (Frontload Data) 34 Audit Records (DR034) SDG&E Written Response (DR034.b) | 72% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP.492 | 8.1.3.11 | Substation Patrol Inspections | Non-focus & non-field verifiable | Complete 384 Inspections | 384 | 391 | 391 | 391 | 391 | Target met | N/A | 32 | 100% | SDG&E Asset Inspection Points List (Frontload Data) 32 Inspection Records (DR035) | 102% | 0 | 0 | 0% | No discrepancy | N/A | N/A | N/A
Grid Design Operations and Maintenance | WMP.543 | 8.1.2.5.2 | Transmission Overhead Hardening | Non-focus & field verifiable | Complete 2 Miles of Overhead Hardening | 2 | 2 | 2 | 2 | 2 | Target met | N/A | 2 | 100% | Field Inspections Circuit Locations (Frontload Data) As-builts (DR044/.b) | 100% | 0 | 0 | 0% | No discrepancy | N/A | Yes | N/A
Grid Design Operations and Maintenance | WMP.545 | 8.1.2.5.2 | Transmission Overhead Hardening (Distribution Underbuild) | Focus & field verifiable | Comlpete 2 Miles of Underbuild | 1.8 | 0 | 0 | 0 | 0 | Target not met | Environmental restrictions and adverse weather in 2025 delayed the underbuild work (setting of pole bases and tops) until January 2026. | 0 | N/A | SDG&E Written Response (DR045) | 0% | 3501000 | 2734920 | -21.9% | Underspend | Work completed in 2023 and 2024, along with delays due to environmental and permitting reviews, reduced the available completed scope in 2025. | No | N/A
Grid Design Operations and Maintenance | WMP.549 | 8.1.2.8.3 | Distribution Communications Reliability Improvements | Focus & field verifiable | Complete Improvement on 5 Stations | 5 | 4 | 4 | 4 | 4 | Target not met | SDG&E reported completing 4 of the 5 targeted stations, with the status set to Delayed. | 4 | 100% | Field Inspections DCRI Locations (Frontload Data) | 80% | 10987000 | 11989980 | 9.1% | Overspend | N/A | N/A | N/A
Grid Design Operations and Maintenance | WMP.550 | 8.1.4.6 | Lightning Arrester Removal and Replacement | Focus & field verifiable | Repalce 90 Lightning arresters | 90 | 1019 | 1015 | 1001 | 1001 | Target met | N/A | 122 | 100% | Field Inspections Pole Locations (Frontload Data) | 1128% | 0 | 508180 | 100% | Overspend | The Petition to Amend reduced the planned target and planned expenditures to align with the GRC decision; however, projects already in flight continued between petition submission and approval, resulting in completion above the amended target and associated actual spend. | Yes | N/A
Grid Design Operations and Maintenance | WMP.552 | 8.1.3.7 | Drone Assessments | Non-focus & non-field verifiable | Complete 13,500 Inspections | 13500 | 13500 | 13500 | 13500 | 13500 | Target met | N/A | 34 | 100% | SDG&E Asset Inspection Points List (Frontload Data) 34 Inspection Records 2 Findings Inspection Reports (DR048) | 100% | 86427190 | 67053480 | -22.4% | Underspend | Program maturation, a shift to desktop review by qualified internal inspectors, and completion of the 2021 to 2022 Drone Inspection Annual Report backlog repairs. | No | Met target for initiative, but fell short of 13.91% risk reduction goal achieving 9.47%.
Grid Design Operations and Maintenance | WMP.555 | 8.1.3.10 | Transmission 69kV Tier 3 Visual Inspections | Non-focus & non-field verifiable | Complete 1,632 Inspections | 1632 | 1601 | 1601 | 1601 | 1601 | Target met | N/A | 34 | 100% | SDG&E Asset Inspection Points List (Frontload Data) SDG&E Written Response 34 Inspection Records (DR049) | 98% | 0 | 0 | 0% | No discrepancy | N/A | No | Met target for initiative, but fell short of 0.02% risk reduction goal achieving 0.00%.
Grid Design Operations and Maintenance | WMP.972 | 8.1.2.10.1 | Avian Protection | Focus & field verifiable | Install Avian Protection on 200 Poles | 200 | 725 | 725 | 709 | 709 | Target met | N/A | 116 | 100% | Field Inspections Pole Locations (Frontload Data) | 363% | 1522650 | 347330 | -77.2% | Underspend | Avian protection installations completed in combination with covered conductor installations were recorded in the WMP.455 Covered Conductor budget rather than the avian protection budget. | Yes | N/A
Grid Design Operations and Maintenance | WMP.1189 | 8.1.2.10.2 | Strategic Pole Replacement Program | Non-focus & field verifiable | Replace 200 Poles | 200 | 228 | 228 | 224 | 224 | Target met | N/A | 30 | 100% | Field Inspections Pole Locations (Frontload Data) | 114% | 8226270 | 9070730 | 10.3% | Overspend | Over-delivery, with 228 poles replaced against the amended 200-pole target. | No
Grid Design Operations and Maintenance | WMP.1190 | 8.1.3.6 | Transmission Wood Pole Intrusive Inspections | Non-focus & non-field verifiable | Complete 141 Inspections | 141 | 163 | 163 | 163 | 163 | Target met | N/A | 29 | 100% | SDG&E Asset Inspection Points List (Frontload Data) 29 Inspection Records (DR008) | 116% | 0 | 0 | 0% | No discrepancy | N/A | N/A | N/A
Grid Design Operations and Maintenance | WMP.1191 | 8.1.6 | QA/QC – Transmission Inspection | Non-focus & non-field verifiable | Complete 100% QA/QC of Transmission Inspections | 100% | 100% | 212 Inspections | 212 Inspections | 212 Inspections | Target met | N/A | 30 | 100% | QA/QC Audit List (Frontload Data) SDG&E Written Response 30 Audit Records (DR009) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP.1192 | 8.1.6.3 | Quality Assurance/Quality Control of Distribution Drone Assessments | Non-focus & non-field verifiable | Complete 13,500 Internal Audits | 13500 | 13500 | 13500 | 13500 | 13500 | Target met | N/A | 34 | 100% | QA/QC Audit List (Frontload Data) 34 Audit Records (DR010) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP.1193 | 8.1.6 | QA/QC – Wood Pole Intrusive | Non-focus & non-field verifiable | Complete 10% Internal Inspection Audits | 10% | 1381 | 31.5% | 1381 | 1381 | Target met | N/A | 34 | 62% | QA/QC Audit List (Frontload Data) 34 Audit Records (DR011) | 195% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP.1194 | 8.1.6.5 | QA/QC – Substation Inspections | Non-focus & non-field verifiable | Complete 18 Audits | 18 | 18 | 18 | 17 | 17 | Target not met | Due to the duplicative nature of the Miguel audit forms, it is determined that the Miguel audit is being captured for completion twice, when only one audit was performed. | 12 | 100% | QA/QC Audit List (Frontload Data) 18 Audit Records (DR012) | 94% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Grid Design Operations and Maintenance | WMP.1195 | 8.1.2.8.2 | Early Fault Detection | Non-focus & field verifiable | Install 60 Early Fault Detection Nodes | 60 | 125 | 125 | 86 | 86 | Target met | N/A | 27 | 100% | Field Inspections Pole Locations (Frontload Data) | 208% | 4419000 | 5887620 | 33.2% | Overspend | Additional optimal installation locations were identified after the 2023 to 2025 Base WMP submission, and 125 nodes were completed against the 60-node target. | Yes | N/A
Vegetation Management and Inspections | WMP.494 | 8.2.2.1 | Detailed Inspections | Focus & non-field verifiable | Complete 485,400 Inspections | 485400 | 511362 | 511150 | 511150 | 511150 | Target met | N/A | 138 | 100% | SDG&E Vegetation Inspection Point List (Frontload Data) 138 Inspection Records (DR036) | 105% | 61886520 | 41338620 | -33.2% | Underspend | Cost aggregation and a lower authorized cost basis rather than reduced inspection activity. | Yes | N/A
Vegetation Management and Inspections | WMP.497 | 8.2.3 | Fuels Management | Non-focus & non-field verifiable | Complete Fuels Management for 500 Poles | 500 | 500 | 500 | 500 | 500 | Target met | N/A | 32 | 100% | SDG&E Geodatabase Files (Frontload Data) 32 Pole Records (DR037) | 100% | 5445000 | 3187330 | -41.5% | Underspend | Program's ability to target previously treated areas, a vendor transition that resulted in cost savings, and the number of community grants completed through fire safe councils and Tribal Nations. | Yes | N/A
Vegetation Management and Inspections | WMP.501 | 8.2.3.3 | Clearance | Focus & non-field verifiable | Complete Clearance for 11,200 Trees | 11200 | 11983 | 11921 | 11983 | 11983 | Target met | N/A | 137 | 100% | SDG&E Geodatabase Files (Frontload Data) 137 Pole Records (DR038) | 107% | 10542020 | 0 | -100% | Underspend | The $10,542K of clearance costs were absorbed within the WMP.494 | Yes | N/A
Vegetation Management and Inspections | WMP.505 | 8.2.5.1 | QA/QC Vegetation Management | Non-focus & non-field verifiable | Perform 15% (79,441) Internal Audits | 15% 79,441 Internal Audits | 96217 | 96217 | 79205 | 79205 | Target met | N/A | 35 | 100% | QA/QC Audit List (Frontload Data) 35 Audit Records (DR039) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Vegetation Management and Inspections | WMP.508 | 8.2.2.1.1 | Off-Cycle Patrol | Non-focus & non-field verifiable | Perform 106 VMAs | 106 | 106 | 106 | 106 | 106 | Target met | N/A | 26 | 100% | Vegetation Off-Cycle Patrol List (Frontload Data) 26 Inspection Records (DR040) | 100% | 0 | 0 | 0% | No discrepancy | N/A | N/A | N/A
Vegetation Management and Inspections | WMP.512 | 8.2.3.1 | Pole Clearing | Non-focus & non-field verifiable | Clear 33,010 Poles | 33010 | 33250 | 33250 | 33002 | 33002 | Target met | N/A | 35 | 100% | SDG&E Geodatabase File (Frontload Data) 35 Pole Records (DR041) | 100% | 8129980 | 4613350 | -43.3% | Underspend | 33,250 poles met Public Resources Code Section 4292 obligations in 2025, while approximately 16,672 previously forecast poles were exempt, reducing the work scope against the planned cost. | Yes | N/A
Situational Awareness and Forecasting | WMP.450 | 8.3.6 | Fire Potential Index |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4538000 | 3013000 | -34% | Underspend | Accounting reclassification of approximately $1,425K between WMPMA O&M, FPI, and FERC O&M | N/A | N/A
Situational Awareness and Forecasting | WMP.970 | 8.3.2.1.3 | AQI – Sensor Installation | Non-focus & non-field verifiable | Install 6 Sensors | 6 | N/A | N/A | 0 | 0 | Target not met | On April 2, 2024, SDG&E submitted an update to their 2023-2025 WMP. This update included a statement requesting to adjust the 2025 target goal for this initiative to zero (formally requested the target to be “reduced by 100%”) - was never or approved or denied by Energy Safety. | N/A | N/A | SDG&E 2025 WMP Update 04/02/24 Energy Safety Decision for WMP Update 10/30/24 (Frontload Data) SDG&E Extension Request 11/13/24 SDG&E Change Order Request 01/27/25 Energy Safety Extension/COR Response 02/24/25 SDG&E Petition to Amend 04/10/25 Energy Safety Petition to Amend Response 07/11/25 | 0% | 0 | 0 | 0% | No discrepancy | N/A | N/A | N/A
Situational Awareness and Forecasting | WMP.1430 | N/A | Weather Station Maintenance and Calibration | Non-focus & non-field verifiable | Perform 216 Inspections | 216 | 216 | 216 | 216 | 216 | Target met | N/A | 30 | 100% | Weather Station Maintenance Log (Frontload Data) 30 Inspection Records (DR015) | 100% | 260690 | 75130 | -71.2% | Underspend | Expenditures were less than projected because installations are performed on an as-needed basis and only one weather station was installed in 2025. | No Goal Provided | N/A
Situational Awareness and Forecasting | WMP.1431 | N/A | Air Quality Station Maintenance | Non-focus & non-field verifiable | Perform 192 Inspections | 192 | 194 | 194 | 194 | 194 | Target met | N/A | 29 | 100% | Air Quality Station Maintenance Log (Frontload Data) 29 Inspection Records (DR016) | 101% | 84000 | 62190 | -26% | Underspend | Expenditures were less than projected because maintenance costs were less than expected. | No Goal Provided | N/A
Emergency Preparedness | WMP.526 | 8.4.2.1.3 | Emergency Response Wildfire/PSPS Exercise & Training | Non-focus & non-field verifiable | Wildfire/PSPS response teams to participate and recertify by 9/1 annually. | To ensure readiness, Wildfire/PSPS response teams will participate and recertify by 9/1 annually. | N/A | N/A | 2025 Training and Attendance Record | 2025 Training and Attendance Record | Target met | N/A | N/A | N/A | Training Attendance Log Summer Readiness Training Materials (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | No Goal Provided | N/A
Emergency Preparedness | WMP.1008 | 5.4.2.1.1 | CEADPP Updated | Focus & non-field verifiable | Submit CEADPP updates as part of the annual report required by Standard 11 by 12/30. | Submit CEADPP updates as part of the annual report required by Standard 11 by 12/30. | N/A | 52 Plans Reviewed/ 17 Plans Updated | CEADPP Updates Submitted on June 29, 2025 | CEADPP Updates Submitted on June 29, 2025 | Target met | N/A | N/A | N/A | Kiteworks Submission ScrnSht (Frontload Data) CPUC GO166 Annual Reports Website | 100% | 22130420 | 34477710 | 55.8% | Overspend | Attributed to two unplanned PSPS activations in January 2025, each requiring Emergency Operations Center activation, extended staffing, overtime labor, contractor support, field patrols, damage inspections, re-energization activities, customer and community support, and incremental IT staffing. | No Goal Provided | N/A
Community Outreach and Engagement | WMP.532 | 8.5.2.1 | Customer Feedback Outreach Surveys | Non-focus & non-field verifiable | Continue soliciting large scale customer/stakeholder feedback at least twice annually to incorporate into future plans. | 2 Feedback Surveys | N/A | N/A | 2 Feedback Surveys | 2 Feedback Surveys | Target met | N/A | N/A | N/A | 2025 PSPS Pre- & Post-Season List Pre- & Post-Season Survey Overview (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | N/A | N/A
Community Outreach and Engagement | WMP.1337 | WMP.1337 | PSPS Stakeholder Education & Awareness | Non-focus & non-field verifiable | Host at least one functional PSPS exercise annually including relevant stakeholders. | Host at least one functional PSPS exercise annually including relevant stakeholders. | N/A | N/A | 1 PSPS Functional Exercise & 1 PSPS Tabletop Exercise | 1 PSPS Functional Exercise & 1 PSPS Tabletop Exercise | Target met | N/A | N/A | N/A | PSPS Functional Exercise Attendance Log PSPS Tabletop Exercise Attendance Log Exercise Training Materials (Frontload Data) | 100% | 0 | 0 | 0% | No discrepancy | N/A | N/A | N/A
Note on K11: Number of "actuals" from which samples are selected

## Tab 3 - Data Requests
Data Requests
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | San Diego Gas & Electric
Date Sent | Date Response Received | Section / Initiative | Data Request Number | List of Documents Received
2026-03-05 | 2026-03-09 | Geodatabase SME | DR001 | SME001 Interview on 03.09.26 @ 9AM
2026-03-12 | 2026-03-19 | Geodatabase Updates & Excel | DR002 | SDGE DR_002 Confidentiality Declaration BD SDGE Response IE-2026-DR002 SDGE_AssetInspectionPoint_2025_Combined.xlsx SDGE_VegetationInspectionPoint_2025_Combined.xlsx SDGE_2025_Combined_QDR-gbd (59 Files)
2026-03-19 | 2026-03-27 | Frontload Data | DR003 | WMP.461 - PSPSSectionEnhance.xlsx WMP.464 - HotlineClamps.xlsx WMP.466 - SDGE Response IE-2026-DR003 WMP.467 - SDGE Response ID-2026-DR003 WMP.468 - FixedBackupPower_Confidential.xlsx WMP.508 - VegInspec_2025_OffCyclePatrol.xlsx WMP.526 - 2025_summerReadinessTraining.pptx,SmrReadyTraining_Atten.xlsx WMP.532 - 2025 PSPS Post-season List.xlsx, 2025 PSPS Preseason List.xlsx, Pre_PostseasonSurveyOverview WMP.545 - SDGE Response IE-2026-DR003 WMP.1008 - Kiteworks Submission_4.30.25.PNG WMP.1337 - Conduct Briefing Slides_Day 1, Conduct Briefing Slides_Day 2, Conduct Briefing Slides_Day 3, FunctionalExercise_Atten.xlsx, PSPS FE_Exercise Plan, PSPS_ FE_PlayerBrief, PSPSEx_CO_IPM_PPT, PSPSEx_FPM_PPT, PSPSEx_MPM_PPT, PSPSEx_TTX_FacilGuide, PSPSTTExercise_ATTN.xlsx, PSPSTT_ConductSlides WMP.1430 - WeatherStationMaintenance.xlsx WMP.1431 - 2024 SDGE GO 166 Annual Report and Emergency Response Plan, 2025 GAP End of Program Report
2026-04-09 | 2026-04-27 | WMP.1190 | DR008 | SDGE DR Response_IE-2026-DR008_WMP.1190.xlsx SDGE Response IE-2026-DR008
2026-04-09 | 2026-04-21 | WMP.1191 | DR009 | SDGE Response IE-2026-DR009
2026-04-09 | 2026-04-21 | WMP.1192 | DR010 | SDGE Response IE-2026-DR010 SDGE Response IE-2026-DR010.xlsx
2026-04-09 | 2026-04-27 | WMP.1193 | DR011 | SDGE DR Response_IE-2026-DR011_WMP.1193.xlsx SDGE Response IE-2026-DR011
2026-04-09 | 2026-04-21 | WMP.1194 | DR012 | SDGE Response IE-2026-DR012 Substation Inspection Quality Reports (18)
2026-04-09 | 2026-04-22 | WMP.1430 | DR015 | IE-2026-DR015_Alternate Sample_2025 SDGE Calibration IE-2026-DR015_Base Sample_2025 SDGE Calibration SDGE Response IE-2026-DR015
2026-04-09 | 2026-04-23 | WMP.1431 | DR016 | SDGE Response IE-2026-DR016 BASE: Base Sample_Substation AQIMaintenance 2025.xlsx, Air Quality Maintenance Log - 24 Month (15 Locations) ALTERNATE: Alternate Sample_Substation AQI Maintenance 2025, Air Quality Maintenance Log - 24 Month (4 Locations)
2026-04-09 | 2026-04-27 | WMP.459 | DR018 | SDGE Response IE-2026-DR018 BASE: As-Builts/Sketches (30), SDGE Construction Order - Total Construction (16) ALTERNATE: As-Builts/Sketches (9), SDGE Construction Order - Total Construction (2)
2026-04-09 | 2026-04-27 | WMP.461 | DR019 | SDGE Response IE-2026-DR019 As-Builts/Sketches (7)
2026-04-09 | 2026-04-22 | WMP.468 | DR024 | SDGE Response IE-2026-DR024 BASE: Battery Installation - Work Completed (53 Customers/Locations) ALTERNATE: Battery Installation - Work Completed (14 Customers/Locations)
2026-04-09 | 2026-04-21 | WMP.478 | DR027 | SDGE Response IE-2026-DR027 SDGE Response IE-2026-DR027.xlsx
2026-04-09 | 2026-04-27 | WMP.479 | DR028 | SDGE DR Response_IE-SDG&E_DR028_WMP.479.xlsx SDGE Response IE-2026-DR028
2026-04-09 | 2026-04-27 | WMP.481 | DR029 | SDGE DR Response_IE-SDG&E_DR029_WMP.481.xlsx SDGE Response IE-2026-DR029
2026-04-09 | 2026-04-21 | WMP.482 | DR030 | SDGE Response IE-2026-DR030
2026-04-09 | 2026-04-27 | WMP.483 | DR031 | SDGE DR Response_IE-SDG&E_DR031.Q01_WMP.483.xlsx SDGE Response IE-2026-DR031
2026-04-09 | 2026-04-27 | WMP.488 | DR032 | SDGE DR Response_IE-SDG&E_DR032_WMP.488.xlsx SDGE Response IE-2026-DR032
2026-04-09 | 2026-04-21 | WMP.489 | DR033 | SDGE Response IE-2026-DR033
2026-04-09 | 2026-04-27 | WMP.491 | DR034 | SDGE DR Response_IE-SDG&E_DR034_WMP.491.xlsx SDGE Response IE-2026-DR034
2026-04-09 | 2026-04-21 | WMP.492 | DR035 | SDGE Response IE-2026-DR035 BASE: Patrol Inspection Forms (31 Inspections/15 Locations) ALTERNATE: Patrol Inspection Forms (8 Inspections/5 Locations)
2026-04-09 | 2026-04-23 | WMP.494 | DR036 | SDGE Response IE-2026-DR036 IE-2026-DR036_Alternate.xlsx IE-2026-DR036_Base.xlsx
2026-04-09 | 2026-04-23 | WMP.497 | DR037 | SDGE Response IE-2026-DR037 IE-2026-DR037_Alternate.xlsx IE-2026-DR037_Base.xlsx
2026-04-09 | 2026-04-23 | WMP.501 | DR038 | SDGE Response IE-2026-DR038 IE-2026-DR038_Alternate.xlsx IE-2026-DR038_Base.xlsx
2026-04-09 | 2026-04-23 | WMP.505 | DR039 | SDGE Response IE-2026-DR039 IE-2026-DR039_Alternate.xlsx IE-2026-DR039_Base.xlsx
2026-04-09 | 2026-04-23 | WMP.508 | DR040 | SDGE Response IE-2026-DR040 IE-2026-DR040_Alternate.xlsx IE-2026-DR040_Base.xlsx
2026-04-09 | 2026-04-23 | WMP.512 | DR041 | SDGE Response IE-2026-DR041 IE-2026-DR041_Alternate.xlsx IE-2026-DR041_Base.xlsx
2026-04-09 | 2026-04-27 | WMP.552 | DR048 | SDGE Response IE-2026-DR048 P40705_Alternate P775253_Base P876737_Base SDGE DR Response_IE-SDG&E_DR048_WMP.552.xlsx
2026-04-09 | 2026-04-21 | WMP.555 | DR049 | SDGE Response IE-2026-DR049
2026-04-13 | 2026-04-16 | WMP.463 | DR020 | SDGE Response_IE-2026-DR020 Confidentiality Declaration Will Speer SDGE Response IE-2026-DR020 Confidential As-Builts (24) WMP_APP_IE-2026-DR020_20260414.xlsx
2026-04-13 | 2026-04-16 | WMP.473 | DR025 | SDGE Response IE-2026-DR025 Attachments 1 - 56 As-Builts Attachments 2 - 53 As-Builts
2026-04-13 | 2026-04-16 | WMP.543 | DR044 | SDG&E_DR044_WMP.543_SME 04.16.26 R1 (Word and PDF) SDG&E_DR044_WMP.543_SME 04.16.26 (Word and PDF)
2026-04-13 | 2026-04-16 | WMP.545 | DR045 | SDGE Response IE-2026-DR045
2026-04-17 | 2026-04-21 | WMP.543 | DR44.b | SDGE Response IE-2026-DR044b TL675_WTS-IFC_CsontructionPackage_V2_DataRequest(1)
2026-04-22 | 2026-05-06 | Financials | DR004 | SDGE Response IE-2026-DR004_5.5.26 SDGE Response IE-2026-DR004_5.6.26
2026-04-22 | Void | QAQC Program | DR005
2026-04-23 | 2026-04-28 | QAQC Program | DR005.b | 510.040 Substation Inspector Maintenance Order Reporting and Tracking_Redacted ESP 612 - CMP Quality Assurance Audits_Redacted SDG&E_DR005.b_QAQC Questionnaire - Distribution SDG&E_DR005.b_QAQC Questionnaire - Substation SDG&E_DR005.b_QAQC Questionnaire - Transmission SDG&E_DR005.b_QAQC Questionnaire - Vegetation Management SDGE Response IE-2026-DR005.b
2026-05-12 | 2026-05-13 | WMP.491 | DR34.b | SDGE Response IE-2026-DR034.b
2026-05-15 | 2026-05-21 | Financials | DR004.b | SDGE Response IE-2026-DR004b SDGE Response IE-2026-DR004REVISEDQ3
2026-05-18 | 2026-05-20 | WMP.463 | DR020.b | APP_FCP_C448_530000294472_P43751_Asbuilt SDGE Response IE-2026-DR020b

## Tab 4 - SME Interviews
SME Interviews
Independent Evaluator: | Bureau Veritas North America
Electrical Corporation: | San Diego Gas & Electric
Interview date | Section / Initiative | SME interview number | Positions interviewed | Summary of interview
2026-03-09 | GIS Data | SME001 (DR001) | Geodatabase Experts | Demonstration of SDG&E's geodatabase and how to quantify metrics to verify initiative implementation.
2026-04-16 | WMP.543 | SME002 (DR044) | Transmission Engineering & Design Team | Discussion on the following: -How SDG&E internally tracks and claims progress toward hardening targets when individual spans are completed but the broader project is still in progress. -How that internal progress tracking relates to (and differs from) the as-built documentation process. -For the segments reported as complete in the geodatabase, the type of work performed (e.g., conductor replacement, pole replacement, reconductoring) and any available supporting documentation such as design drawings, so that our field verification team can align their field verification scope with the actual work completed.
2026-05-22 | WMP.463 | SME003 (DR020.c) | System Protection Manager | The Independent Evaluator (IE) conducted this SME interview under Data Request DR020.b to clarify the implementation and reporting methodology for the Advanced Protection initiative (WMP.463). Because the initiative is reported at the circuit level while scope is implemented across multiple poles per circuit, the IE sought to understand: (1) a high-level overview of the program and its components, including elements that extend beyond what is visible at the individual poles; (2) how a circuit is identified and claimed as complete for purposes of WMP reporting; and (3) how any construction that may extend beyond the WMP reporting year (for example, due to permitting) is handled.