## Actions 2025-2027 plan
Priority | Objective | KPI | Action | Who | Milestones | [9 empty] | Last update: | 2026-02-13
[5 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | Objective Outcome/status
[5 empty] | Jun. | Jul. | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. - May 2027 | Action Status
Priority 1: Actualizing Our Mission in Collaboration with the Office of Energy Infrastructure Safety Priority Steward: Chris Porter | Board Members and Energy Safety leadership and management are deepening collaboration and are satisfied with frequency and depth of communication. | Survey of Board Members and Energy Safety leadership | Participate in monthly and quarterly meetings, share information, bring questions | Executive Committee | Monthly meeting (PM out sick) | Monthly meeting | Monthly & quarterly meetings | Monthly meeting | Monthly meeting | Monthly meeting | Monthly & quarterly meetings | Monthly meeting | Monthly & quarterly meetings | Monthly & quarterly meetings | Ongoing | Meetings scheduled and are typically held and productive
| Board recommendations are informed by Energy Safety’s approach, timing, and constraints. | Board recommendations are delivered in sync with Energy Safety timelines | Collaborate with Energy Safety staff to understand their processes | Branch Staff | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in SB 254 scheduling discussions | Participate in SB 254 scheduling discussions | Participate in SB 254 scheduling discussions | Participate in SB 254 scheduling discussions | Participate in SB 254 scheduling discussions | Participate in SB 254 scheduling discussions | Ongoing | Program Manager and Branch Supervisor working to continue integration (REVISED for October 2025 & forward)
Priority 2: Building Collaborative Relationships with External Partners Priority Steward: Jessica Block | Board Members and staff have network of partners key to success. | Staff members add contacts to their networks | Staffers attend 4 conferences per year | Branch Staff | Q2 Sep.: Attend NCPA annual conference; Q2 Oct.: Attend SCPPA annual conference; Q2 Nov.: Attend CMUA WMP Forum; Q3 Dec.: Look up Distributech conference (Feb.) | Attend CMUA annual conference | In progress
|  | Board makes 4 site visits per year | Staff develops site visits | Branch Staff | Q1 Jun.: Site visit associated with June Board meeting (ArborWorks); site visits to SFPUC and MID; Q2 Sep.: Site visit associated with September Board meeting (Eaton fire); Q3 Dec.: Site visit associated with December Board meeting | Site visit associated with March Board meeting | In progress
| Board recommendations are informed by expert advice. | Board makes 4 site visits per year | Board Members attend site visits | Board Members | Q1 Jun.: Site visit associated with June Board meeting (ArborWorks); site visits to SFPUC and MID; Q2 Sep.: Site visit associated with September Board meeting (Eaton fire); Q3 Dec.: Site visit associated with December Board meeting | Site visit associated with March Board meeting | In progress
|  | Board presents 4 topical presentations/workshops per year | Board Members contribute contacts and expertise | Board Members | Q1 Jul.: Committees work with staff to develop presentation for September Board meeting; Q2 Sep.: Committees work with staff to develop presentations for Board meetings; Q3 Dec.: Committees work with staff to develop presentations for Board meetings | Committees work with staff to develop presentations for Board meetings | In progress | Board meeting schedule for December was thought to be too full. Presentation scheduled for March Board meeting
|  |  | Staff organize presentations | Branch Staff | Q2 Sep.: Expert presentation to Board at quarterly meeting; Q3 Dec.: Expert presentation to Board at quarterly meeting | Expert presentation to Board at quarterly meeting | Behind | Board meeting schedule for December was thought to be too full. Presentation scheduled for March Board meeting
| Board Committees and staff have established and are deepening relationships with external partners. | Branch staff review of relationships | Staff meet with key partners on cadence set by Committees | Branch Staff | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Ongoing | Did meet in 2025; revisit for 2026?
|  |  | Staff review relationships and report to Board | Branch Staff | Q1 Aug.: Staff and Committees review relationships; Q2 Sep.: Staff report to Board on external partner relationships; Q3 Dec.: Staff and Committees review relationships | Report to Board on external partner relationships | Not started | Staff did not bring to Board
| Board and staff have clear priorities for collaborative efforts. | There are clear priorities (and messages where appropriate) for interaction with key partners | Committees identify and review key partners and messages for their workstreams | Workstream Committees | Q1 Aug.: Staff and Committees review relationships; Q2 Sep.: Staff report to Board on external partner relationships; Q3 Dec.: Staff and Committees review relationships | Report to Board on external partner relationships | Not started
Priority 3: Retaining and Developing Staff Priority Steward: Mark | Staff are satisfied with their work, work-life balance, recognition, and professional development. | Results of staff survey | Provide each staffer with one or more projects on which they are the lead | Branch Supervisor | Onboard new staffer; identify projects | Ongoing work planning | Ongoing work planning | Ongoing work planning | Ongoing work planning | Ongoing work planning | Presentations from staff at Board meeting |  |  | Ongoing work planning | Ongoing | Each staffer is lead on their projects
|  |  | Build sense of teamwork among staff | Branch Supervisor, Branch Staff | Onboard new staffer; plan teambuilding exercises; collaborate | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Ongoing
|  |  | Recognize individual contributions | Branch Supervisor, Branch Staff | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings |  |  | In branch meetings, ESPD check-ins, Board meetings | Ongoing
|  |  | Encourage and allow time off for vacation and family responsibilities | Branch Supervisor | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Ongoing | New POU submission schedule should facilitate
|  |  | Maximize benefits of agency RTO policies | Branch Supervisor, Branch Staff | Communicate opportunities and challenges; plan activities | Work through transition to 4 days/week; plan activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | In progress | Team meetings and 1x1s are in person; supervisor drops by cubicles on common in-office days
|  |  | Survey staff semiannually | Branch Supervisor | Q1 Jul.: Semiannual survey; Q3 Jan.: Semiannual survey |  | In progress | Sent
| Board Members support staff development | Results of staff survey | Board members introduce staff to members of their networks | Board Members | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions |  |  | Use Committee meetings to identify areas of interest and key contacts; make introductions | In progress | Did with POU Committee, Strategic Planning Committee; Risk Modeling Committee
|  |  | Board members use committee meetings and products as staff development opportunities, in collaboration with supervisor | Board Members, Branch Supervisor | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls |  |  | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | In progress | Staff are doing more to lead Committee calls; (Shaun for POU and Risk Modeling, Gifford for Vegetation Management and Safety Culture)
| Branch staff develops in capacity to support increased Board effectiveness. | Staffers complete majority of trainings in individual development plans | Staffers identify training goals and opportunities | Branch Staff | Q1 Jun.: Review progress on 2025 IDPs; Q3 Dec.: Develop annual IDP (Dec.) |  | In progress | Done; all staff have individual development plans
|  |  | Staffers complete training that aligns with their job responsibilities and career development goals | Branch Staff | Q1 Jun.: As needed and as opportunities arise; Q1 Jul.: As needed and as opportunities arise; Q1 Aug.: As needed and as opportunities arise; Q2 Sep.: As needed and as opportunities arise; Q3 Dec.: As needed and as opportunities arise | As needed and as opportunities arise | In progress | All staff completed formal external training in 2026
Priority 4: Creating the Structures and Practices for Successful Implementation Priority Steward: Mark | Branch has and follows up-to-date processes, including project management, recordkeeping, and standard operating procedures | Staff meets product deadlines, positioning Board to meet its statutory deadlines | Develop and follow project plans for major work products | Branch Supervisor, Branch Staff | Finalize POU WMP review process and assignments | Execute project plans | Execute project plans | Finalize project plan for 2026 Recommendations to Energy Safety | Redo project planning with 254 | Redo project planning with 254 | Redo project planning with 254 | Redo project planning with 254 |  | Execute project plans | In progress | Project planning for 2026 WMP review completed
|  | Website and internal files are clearly organized and up to date | Establish, review, and revise Branch processes, Standard Operating Procedures, and checklists | Branch Supervisor, Branch Staff | Q1 Jun.: Onboard new staffer with SOPs; Q3 Dec.: Review all SOPs; revise as needed; Q3 Jan.: Review all SOPs; revise as needed |  | In progress | Staff reviewed SOPs in December; supervisor returned comments. To be completed in January
|  | Staff efficiency | Communicate and follow standard processes | Branch Supervisor, Branch Staff | Onboard new staffer with SOPs | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff |  |  | Clear communication between supervisor and staff | Ongoing
| Board focuses attention and resources on clear priorities | Priorities are reflected in Strategic Plan and Work Plans | Board members and staff establish clear priorities | Board, Branch Staff | Q2 Sep.: Review Priorities semiannually at March and September Board meetings | Review Priorities semiannually at March and September Board meetings | Not started | Brief update at September Board meeting; will be more explicit at March Board meeting.
|  | Staff resources are aligned with priorities | Supervisor plans staff resources to align with priorities and meet deadlines | Branch Supervisor | Q1 Jun.: Develop annual work plan; Q1 Jul.: Revise work plan as needed with new information; Q1 Aug.: Revise work plan as needed with new information; Q2 Sep.: Update Board on work plan at March and September meetings; Q3 Dec.: Revise work plan as needed with new information | Update Board on work plan at March and September meetings | Ongoing | Brief update at September Board meeting; will be more explicit at March Board meeting.
|  | Board Member input is focused, clear, and timely | Board members participate in Committee calls | Board Members | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing |  |  | Ongoing | Ongoing
|  |  | Board members review and provide feedback on documents | Board Members | Q2 Sep.: Board member review of POU Advisory Opinion; Q3 Dec.: Board member review of draft Recommendations to Energy Safety; Q3 Jan.: Committee feedback on draft response to Energy Safety on realistic extremes | Board member review of draft Recommendations to Energy Safety | Ongoing | Medium level of feedback from committees; very little from Board members not on a specific committee
| Board members are satisfied with frequency and depth of communication with staff | Results of Board Member survey | Staff communicate regular updates to Board and schedule Committee and Board Member briefings | Branch Staff | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Updates approximately monthly in 2026 (missed June)
|  |  | Supervisor conducts survey | Branch Supervisor | Q1 Jul.: Semiannual survey; Q3 Jan.: Semiannual survey |  | Complete

## 2026 Objectives and actions
Priority | Objective | Carried over (green), revised (yellow), new (blue), or removed (gray) Objective | KPI | Action | Who | Milestones | [7 empty] | Last update: | Proposal for Jan. '26 Strategic Planning Committee
[6 empty] | Q1 |  |  | Q2 | Q3 | Q4
[6 empty] | Mar. | Apr. | May | June - Aug. | Sep. - Nov. | Dec. '26 - Feb. '27 | Action Status | Notes
Priority 1: Actualizing Our Mission in Collaboration with the Office of Energy Infrastructure Safety Priority Steward: Chris Porter | Board Members and Energy Safety leadership and management are deepening collaboration and are satisfied with frequency and depth of communication. | Board Members and Energy Safety leadership and management are deepening collaboration and are satisfied with frequency and depth of communication. | Survey of Board Members and Energy Safety leadership | Participate in monthly and quarterly meetings, share information, bring questions | Executive Committee
|  | WSAB Branch staff regularly exchange information with IOU WMP Branch staff. | Meetings or consultations between staff | WSAB Branch staff interview IOU WMP Branch staff and get material review for "deep dives" | Branch staff
|  |  |  | WSAB Branch staff explain and elaborate on recommendations to IOU WMP Branch staff | Branch staff
| Board recommendations are informed by Energy Safety’s approach, timing, and constraints. | Board is responsive to Energy Safety requests for advice and recommendations, providing timely and helpful information | Consultations between Board members and Energy Safety staff | Board members participate in consultations requested by Energy Safety | Board members (Branch staff organize)
|  |  | Board recommendations are delivered in sync with Energy Safety timelines | Collaborate with Energy Safety staff to understand their processes | Branch Staff
Priority 2: Building Collaborative Relationships with External Partners Priority Steward: Jessica Block |  | Board Members and staff are deepening collaboration with and understanding of POUs and co-ops, including their local context | Number of meetings between Board staff and POUs and co-ops | Staffers attend 4 POU/co-op conferences per year | Branch Staff
|  |  |  | Board makes 4 site visits to POUs or co-ops per year | Branch Staff
|  |  |  | Board staff have up to six meetings with each POU or co-op that has overhead facilities in the High Fire Threat District and a WMP due in the current year | Branch Staff
|  |  | Whether advisory opinions reflect local context | Board staff have up to six meetings with each POU or co-op that has overhead facilities in the High Fire Threat District and a WMP due in the current year | Branch Staff
| Board Members and staff have network of partners key to success. | Board Members and staff have network of partners key to success. | Meetings with key partners | Staff meet with key partners on cadence set by Committees | Branch Staff
|  |  | Staff members add contacts to their networks | Through deep-dive research and conferences, staff expand networks | Branch Staff
| Board Committees and staff have established and are deepening relationships with external partners. | Board Committees and staff have established and are deepening relationships with external partners.
| Board recommendations are informed by expert advice. | Board recommendations are informed by expert advice.
| Board and staff have clear priorities for collaborative efforts. | Board and staff have clear priorities for collaborative efforts.
Priority 3: Retaining and Developing Staff Priority Steward: Mark | Staff are satisfied with their work, work-life balance, recognition, and professional development. | Staff are satisfied with their work, work-life balance, recognition, and professional development. | Results of staff survey | Provide each staffer with one or more projects on which they are the lead | Branch Supervisor
|  |  |  | Build sense of teamwork among staff | Branch Supervisor, Branch Staff
|  |  |  | Recognize individual contributions | Branch Supervisor, Branch Staff
|  |  |  | Encourage and allow time off for vacation and family responsibilities | Branch Supervisor
|  |  |  | Maximize benefits of agency RTO policies | Branch Supervisor, Branch Staff
|  |  |  | Survey staff semiannually | Branch Supervisor
| Board Members support staff development | Board Members support staff development | Results of staff survey | Board members introduce staff to members of their networks | Board Members
|  |  |  | Board members use committee meetings and products as staff development opportunities, in collaboration with supervisor | Board Members, Branch Supervisor
Priority 4: Creating the Structures and Practices for Successful Implementation Priority Steward: Mark | Branch staff develops in capacity to support increased Board effectiveness. | Branch staff develops in capacity to support increased Board effectiveness. | Staffers complete majority of trainings in individual development plans | Staffers identify training goals and opportunities | Branch Staff
|  |  |  | Staffers complete training that aligns with their job responsibilities and career development goals | Branch Staff
| Branch has and follows up-to-date processes, including project management, recordkeeping, and standard operating procedures | Branch has and follows up-to-date processes, including project management, recordkeeping, and standard operating procedures | Staff has, implements, and evolves new processes for POU and co-op review. | Staff implement review schedule | Branch Staff
|  |  |  | Staff update processes as needed and propose any changes to schedule to Board | Branch Staff
|  |  | Staff meets product deadlines, positioning Board to meet its deadlines | Develop and follow project plans for major work products | Branch Supervisor, Branch Staff
|  |  | Processes, website, and internal files are clearly organized and up to date | Establish, review, and revise Branch processes, Standard Operating Procedures, and checklists | Branch Supervisor, Branch Staff
| Board focuses attention and resources on clear priorities | Board sets and focuses attention on clear priorities | Board has established clear priorities | Board members engage in priority discussions at meetings, and informally | Board Members, Branch Staff organize
|  |  | Staff resources are aligned with priorities | Supervisor plans staff resources to align with priorities and meet deadlines | Branch Supervisor
|  |  | Board Member input is focused, clear, and timely | Board members participate in Committee calls | Board Members
|  |  |  | Board members review and provide feedback on documents | Board Members
| Board members are satisfied with frequency and depth of communication with staff | Board members are satisfied with frequency and depth of communication with staff | Results of Board Member survey | Staff communicate regular updates to Board and schedule Committee and Board Member briefings | Branch Staff
|  |  |  | Supervisor conducts survey | Branch Supervisor
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Different from “network of partners”?
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this “building collaborative relationships?” Reply: Moved to successful implementation (Priority 4) from External relationships (#2)
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could be read as downplaying role of Board expertise. Concept should be reflected in collaboration with external partners
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this one still necessary? Or maybe in a smaller/different form?