## WP002
Workpaper 002
Pacific Gas and Electric Company
Electrical Undergrounding Program
Target/Timeline Table
| Year of EUP | Date Range | UG Miles Completed(a) | OH Miles Deenergized | Cumulative UG Miles Completed | Preconstruction Miles(b) | Unit Cost Escalated(c) | Unit Cost Unescalated(c) | Change Instantaneous Wildfire Risk at Year 10(d)(e) | Change in Cumulative Wildfire Risk Over 55 Years(d)(e) | Change Instantaneous Outage Program Risk at Year 10(d)(e) | Change in Cumulative Outage Program Risk Over 55 Years(d)(e)
| 1 | 1/1/2028 - 12/31/2028 | 250 | 200 | 250 | 650 | 3.05 | 3.05 | 21.634 | 2220.714 | 51.325 | 6288.558
| 2 | 1/1/2029 - 12/31/2029 | 300 | 240 | 550 | 800 | 3.1006 | 3.03 | 27.612 | 2749.307 | 16.677 | 1795.708
| 3 | 1/1/2030 - 12/31/2030 | 350 | 280 | 900 | 1000 | 3.1419 | 3 | 25.159 | 2484.008 | 37.361 | 4106.463
| 4 | 1/1/2031 - 12/31/2031 | 450 | 360 | 1350 | 1150 | 3.1841 | 2.98 | 28.854 | 2816.088 | 51.246 | 5335.265
| 5 | 1/1/2032 - 12/31/2032 | 550 | 440 | 1900 | 1225 | 3.234 | 2.96 | 29.543 | 2845.795 | 48.353 | 6612.804
| 6 | 1/1/2033 - 12/31/2033 | 600 | 480 | 2500 | 1250 | 3.2974 | 2.95 | 29.865 | 2920.038 | 53.994 | 7273.509
| 7 | 1/1/2034 - 12/31/2034 | 625 | 500 | 3125 | 1250 | 3.3617 | 2.94 | 27.761 | 2758.637 | 58.256 | 7184.6
| 8 | 1/1/2035 - 12/31/2035 | 625 | 500 | 3750 | 1250 | 3.4206 | 2.92 | 24.516 | 2314.033 | 66.879 | 7124.642
| 9 | 1/1/2036 - 12/31/2036 | 625 | 500 | 4375 | 625 | 3.4892 | 2.91 | 21.226 | 2030.766 | 75.325 | 9319.24
| 10 | 1/1/2037 - 12/31/2037 | 625 | 500 | 5000 | 0 | 3.5623 | 2.9 | 19.193 | 1768.577 | 95.059 | 13629.206
| End/Total | 2037-12-31 | 5000 | 4000 | 5000 | 0 |  |  | 255.363 | 24907.963 | 554.476 | 68669.995
_______ (a) Underground mileage is estimated by applying a 1.25 multiplier to the corresponding overhead mileage deenergized. The 2028 undergrounding mileage shown in the EUP Target/Timeline Table (250 miles) differs from the mileage approved in the 2026 WMP (400 miles). The difference is primarily due to the time needed to transition the program and its supporting structure to meet the EUP requirements. Once the EUP is approved, PG&E will update the WMP mileage at the appropriate time. (b) Pre-construction miles are calculated as the sum of undergrounding miles required to be in the planning process in the next two years that are needed to meet execution targets. These miles reflect the number of miles passing Screen 3 and Screen 4. There is a two year lead time for pre construction miles (e.g., 650 miles in 2028 is the sum of planned miles for 2029 and 2030). (c) To establish 2028 unit cost values, 2025 actual costs are escalated to 2028 dollars. The "Unit Cost Escalated" column reflects annual unit cost values further escalated from 2028 dollars to the dollar value in the applicable year (2028–2037). The "Unit Cost Unescalated" column reflects annual unit cost values presented in unescalated 2028 dollars and incorporates assumed unit cost reductions over time as program efficiencies are realized. Cost assumptions applied in the current WBCA model for Screen 2 are based on average 2028 unit costs; however, costs for individual projects may vary based on project-specific feasibility multipliers. (d) Instantaneous and cumulative risk values represent unmitigated Wildfire and Outage Program Risk for all years prior to project completion, and post‑mitigated risk from the year the project is completed onward. PG&E applies the Risk Model Impact Factor, climate escalation, and inflation adjustments as described in this section. (e) Totals may not exactly equal the sum of individual values because figures are rounded independently.