## EUP Summary View
Workpaper 007
Pacific Gas and Electric Company
Electrical Undergrounding Program
Undergrounding Resource Model
Programmmatic Forecast - Required Effort to Deliver Planned Miles EUP Summary View: Chapter 5 Section 2 Summary of Resources
Resourcing Teams | Yearly Max Head Count (2028-2037)
Project Management | 162
Scoping | 25
Estimating | 50
Customer Outreach | 37
Encroachment | 111
Land | 477
Environmental | 319
Construction Management | 53
Civil Construction | 709
Electric Construction | 84
Post-Construction | 11

## Assumptions
Workpaper 007
Pacific Gas and Electric Company
Electrical Undergrounding Program
Undergrounding Resource Model
Assumptions
Key Assumptions Used to Build the Resource Model
| Project Size | The resource model uses a miles-based approach to determine the required effort to deliver one mile of undergrounding (FTE/mile). Project size and difficulty have been consolidated and incorporated into the outputs from the productivity analysis and inform productivity rates.
| Annual Mileage Target | The annual mileage targets are based on the overall program strategy as filed in the EUP. As planning scenarios are evaluated and implemented, the modeled mileage trajectory can be revised.
| Construction Seasonality | Construction Seasonality was developed using the available construction schedule information and aggregates underground miles based on when construction starts and finishes in terms of months, regardless of the year of construction.
| Schedule | The schedule assumptions are based on undergrounding project phase data (e.g. scoping, dependencies, construction etc., referred to as Workstream Progression data) developed by the Program to set non-construction target miles and is aligned with construction target miles.

## Program Wide View
Workpaper 007
Pacific Gas and Electric Company
Electrical Undergrounding Program
Undergrounding Resource Model
Program Wide View
EUP Programmmatic Forecast - Required Effort to Deliver Planned Miles
Dashboard
Table C1: Mile Target - Input
|  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | Total | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
| Construction - Target Miles | 247 | 285.1 | 213.9 | 306.5 | 417 | 307 | 250 | 300 | 350 | 450 | 550 | 600 | 625 | 625 | 625 | 625 | 6776.5
Table C2: Dependencies Mile Target - Based on Workstream Progression
|  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | Total
| Scoping - Target Miles | 247 | 366.6667 | 463.9091 | 448 | 507 | 292 | 396 | 422 | 580 | 625 | 670 | 684 | 580 | 580 | 0 | 0 | 6861.5758
| Estimating - Target Miles | 247 | 322.2222 | 320 | 401 | 308 | 291 | 359 | 405 | 555 | 625 | 658 | 675 | 595 | 595 | 504 | 0 | 6860.2222
| Permitting - Target Miles | 247 | 305.5556 | 319 | 400 | 245 | 291 | 336 | 375 | 478 | 594 | 647 | 675 | 677 | 677 | 660 | 0 | 6926.5556
Table C3: Resource Needs Based on Mile Targets
| Resourcing (FTEs) | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | MAX |  |  | Cevelop moCel baseC on hours rather than per mile? |  |  | prob not - neeC to figure out
| Project Management | 117.8759 | 108.0529 | 133.975 | 126.7401 | 140.4432 | 79.1654 | 105.0274 | 109.436 | 146.9912 | 154.7121 | 161.9025 | 161.2542 | 155.6138 | 151.6237 | 143.9264 | 132.6104 | 161.9025 |  |  | Internal vs external
| Associate Project Manager | 50 | 45.8333 | 56.8289 | 53.76 | 59.5725 | 33.58 | 44.55 | 46.42 | 62.35 | 65.625 | 68.675 | 68.4 | 66.0075 | 64.315 | 61.05 | 56.25 | 68.675 |  |  | resource planning
| Journey Project Manager | 30.7692 | 28.2051 | 34.9716 | 33.0831 | 36.66 | 20.6646 | 27.4154 | 28.5662 | 38.3692 | 40.3846 | 42.2615 | 42.0923 | 40.62 | 39.5785 | 37.5692 | 34.6154 | 42.2615 |  |  | Cevelpo assumption list
| Project Controls Analyst | 37.1066 | 34.0144 | 42.1746 | 39.8971 | 44.2107 | 24.9208 | 33.062 | 34.4498 | 46.272 | 48.7025 | 50.966 | 50.7619 | 48.9863 | 47.7303 | 45.3072 | 41.745 | 50.966
| Scoping | 17.5652 | 16.1014 | 19.9642 | 18.8861 | 20.9281 | 11.7968 | 15.6506 | 16.3075 | 21.9038 | 23.0543 | 24.1258 | 24.0292 | 19.8663 | 19.3569 | 0 | 0 | 24.1258
| Scoping Lead - Project Manager | 0.43478 | 0.39855 | 0.49416 | 0.46748 | 0.51802 | 0.292 | 0.38739 | 0.40365 | 0.54217 | 0.57065 | 0.59717 | 0.59478 | 0.49174 | 0.47913 | 0 | 0 | 0.59717
| Grid Design Team | 13.913 | 12.7536 | 15.8132 | 14.9593 | 16.5767 | 9.344 | 12.3965 | 12.9169 | 17.3496 | 18.2609 | 19.1096 | 19.033 | 15.7357 | 15.3322 | 0 | 0 | 19.1096
| Construction Manager | 1.9565 | 1.7935 | 2.2237 | 2.1037 | 2.3311 | 1.314 | 1.7433 | 1.8164 | 2.4398 | 2.5679 | 2.6873 | 2.6765 | 2.2128 | 2.1561 | 0 | 0 | 2.6873
| ADE / Estimating Support | 0.17391 | 0.15942 | 0.19767 | 0.18699 | 0.20721 | 0.1168 | 0.15496 | 0.16146 | 0.21687 | 0.22826 | 0.23887 | 0.23791 | 0.1967 | 0.19165 | 0 | 0 | 0.23887
| SME Reviews | 0.43478 | 0.39855 | 0.49416 | 0.46748 | 0.51802 | 0.292 | 0.38739 | 0.40365 | 0.54217 | 0.57065 | 0.59717 | 0.59478 | 0.49174 | 0.47913 | 0 | 0 | 0.59717
| Administrative | 0.65217 | 0.59783 | 0.74125 | 0.70122 | 0.77703 | 0.438 | 0.58109 | 0.60548 | 0.81326 | 0.85598 | 0.89576 | 0.89217 | 0.73761 | 0.7187 | 0 | 0 | 0.89576
| Estimating | 36.9704 | 29.7817 | 28.9848 | 35.5803 | 26.7592 | 24.7443 | 29.8629 | 32.9406 | 44.115 | 48.5237 | 49.8694 | 49.9101 | 42.8949 | 41.7951 | 34.4712 | 0 | 49.9101
| Estimator | 23.5209 | 18.9474 | 18.4404 | 22.6365 | 17.0245 | 15.7426 | 18.999 | 20.9572 | 28.0664 | 30.8712 | 31.7274 | 31.7533 | 27.2902 | 26.5904 | 21.9309 | 0 | 31.7533
| ADE | 12.8119 | 10.3207 | 10.0445 | 12.3302 | 9.2732 | 8.575 | 10.3488 | 11.4154 | 15.2878 | 16.8156 | 17.282 | 17.2961 | 14.865 | 14.4838 | 11.9458 | 0 | 17.2961
| Civil Engineer | 0.63759 | 0.51362 | 0.49987 | 0.61362 | 0.46149 | 0.42674 | 0.51501 | 0.56809 | 0.76081 | 0.83684 | 0.86005 | 0.86075 | 0.73977 | 0.7208 | 0.59449 | 0 | 0.86075
| Customer Outreach | 20.9073 | 15.686 | 22.0271 | 29.3568 | 21.1625 | 16.8667 | 19.8 | 22.5867 | 28.38 | 33.88 | 36.08 | 36.6667 | 35.75 | 34.8333 | 33.9167 | 33 | 36.6667
| Outreach Representative | 20.9073 | 15.686 | 22.0271 | 29.3568 | 21.1625 | 16.8667 | 19.8 | 22.5867 | 28.38 | 33.88 | 36.08 | 36.6667 | 35.75 | 34.8333 | 33.9167 | 33 | 36.6667
| Encroachment (EPCW) | 81.9476 | 62.5989 | 64.0462 | 78.6697 | 47.1813 | 54.8475 | 61.9524 | 67.6068 | 84.2176 | 102.2215 | 108.6912 | 110.6293 | 108.1832 | 105.4092 | 100.058 | 0 | 110.6293
| Permit Facilitator | 25.157 | 19.2172 | 19.6615 | 24.1508 | 14.4842 | 16.8376 | 19.0187 | 20.7546 | 25.8539 | 31.3809 | 33.367 | 33.962 | 33.2111 | 32.3595 | 30.7167 | 0 | 33.962
| Traffic Engineer | 38.4525 | 29.3734 | 30.0525 | 36.9144 | 22.139 | 25.7362 | 29.0701 | 31.7233 | 39.5176 | 47.9656 | 51.0014 | 51.9108 | 50.763 | 49.4614 | 46.9505 | 0 | 51.9108
| Agency Liaison | 18.3381 | 14.0083 | 14.3321 | 17.6046 | 10.5582 | 12.2737 | 13.8636 | 15.1289 | 18.8461 | 22.875 | 24.3228 | 24.7564 | 24.2091 | 23.5883 | 22.3908 | 0 | 24.7564
| Land | 352.8963 | 269.5735 | 275.8061 | 338.7804 | 203.18 | 236.1935 | 266.7896 | 291.1394 | 362.6715 | 440.2028 | 468.064 | 476.41 | 465.876 | 453.9305 | 430.8863 | 0 | 476.41
| Land Surveyor | 31.8854 | 24.3569 | 24.92 | 30.61 | 18.358 | 21.3409 | 24.1054 | 26.3055 | 32.7686 | 39.7739 | 42.2912 | 43.0453 | 42.0935 | 41.0142 | 38.9321 | 0 | 43.0453
| Field Surveyor | 31.8854 | 24.3569 | 24.92 | 30.61 | 18.358 | 21.3409 | 24.1054 | 26.3055 | 32.7686 | 39.7739 | 42.2912 | 43.0453 | 42.0935 | 41.0142 | 38.9321 | 0 | 43.0453
| Utility Locator | 31.8854 | 24.3569 | 24.92 | 30.61 | 18.358 | 21.3409 | 24.1054 | 26.3055 | 32.7686 | 39.7739 | 42.2912 | 43.0453 | 42.0935 | 41.0142 | 38.9321 | 0 | 43.0453
| LiDAR Surveyor | 31.8854 | 24.3569 | 24.92 | 30.61 | 18.358 | 21.3409 | 24.1054 | 26.3055 | 32.7686 | 39.7739 | 42.2912 | 43.0453 | 42.0935 | 41.0142 | 38.9321 | 0 | 43.0453
| Boundary surveyor | 31.8854 | 24.3569 | 24.92 | 30.61 | 18.358 | 21.3409 | 24.1054 | 26.3055 | 32.7686 | 39.7739 | 42.2912 | 43.0453 | 42.0935 | 41.0142 | 38.9321 | 0 | 43.0453
| Caltrans Permit Specialist | 31.8854 | 24.3569 | 24.92 | 30.61 | 18.358 | 21.3409 | 24.1054 | 26.3055 | 32.7686 | 39.7739 | 42.2912 | 43.0453 | 42.0935 | 41.0142 | 38.9321 | 0 | 43.0453
| Caltrans Project Manager | 16.0115 | 12.231 | 12.5138 | 15.371 | 9.2186 | 10.7165 | 12.1047 | 13.2095 | 16.455 | 19.9727 | 21.2368 | 21.6155 | 21.1376 | 20.5956 | 19.55 | 0 | 21.6155
| Land Agent | 31.8854 | 24.3569 | 24.92 | 30.61 | 18.358 | 21.3409 | 24.1054 | 26.3055 | 32.7686 | 39.7739 | 42.2912 | 43.0453 | 42.0935 | 41.0142 | 38.9321 | 0 | 43.0453
| ROW Agent | 49.641 | 37.9202 | 38.7969 | 47.6553 | 28.5808 | 33.2247 | 37.5286 | 40.9538 | 51.016 | 61.9222 | 65.8413 | 67.0153 | 65.5335 | 63.8532 | 60.6116 | 0 | 67.0153
| Land Project Manager | 32.023 | 24.462 | 25.0276 | 30.7421 | 18.4372 | 21.433 | 24.2094 | 26.419 | 32.91 | 39.9455 | 42.4737 | 43.231 | 42.2751 | 41.1912 | 39.1001 | 0 | 43.231
| Land/Acquisition Project Coordinator | 32.023 | 24.462 | 25.0276 | 30.7421 | 18.4372 | 21.433 | 24.2094 | 26.419 | 32.91 | 39.9455 | 42.4737 | 43.231 | 42.2751 | 41.1912 | 39.1001 | 0 | 43.231
| Environmental | 236.2334 | 180.4561 | 184.6282 | 226.7841 | 136.0114 | 158.111 | 178.5925 | 194.8926 | 242.7771 | 294.6776 | 313.3282 | 318.9151 | 311.8635 | 303.867 | 288.441 | 0 | 318.9151
| Land Planning Analyst | 7.8574 | 6.0022 | 6.141 | 7.5431 | 4.5239 | 5.259 | 5.9402 | 6.4824 | 8.0751 | 9.8013 | 10.4217 | 10.6075 | 10.373 | 10.107 | 9.5939 | 0 | 10.6075
| Land Planner | 19.8564 | 15.1681 | 15.5188 | 19.0621 | 11.4323 | 13.2899 | 15.0114 | 16.3815 | 20.4064 | 24.7689 | 26.3365 | 26.8061 | 26.2134 | 25.5413 | 24.2447 | 0 | 26.8061
| Biologist | 19.7114 | 15.0573 | 15.4054 | 18.9229 | 11.3488 | 13.1928 | 14.9018 | 16.2619 | 20.2574 | 24.588 | 26.1442 | 26.6103 | 26.022 | 25.3547 | 24.0676 | 0 | 26.6103
| Cultural Resource Specialist | 19.4149 | 14.8308 | 15.1737 | 18.6383 | 11.1781 | 12.9944 | 14.6776 | 16.0173 | 19.9526 | 24.2181 | 25.7509 | 26.2101 | 25.6305 | 24.9733 | 23.7055 | 0 | 26.2101
| Environmental Field Specialist (EFS) | 27.1595 | 20.7468 | 21.2265 | 26.0731 | 15.6371 | 18.1778 | 20.5326 | 22.4066 | 27.9118 | 33.8787 | 36.023 | 36.6653 | 35.8546 | 34.9352 | 33.1617 | 0 | 36.6653
| Water Quality Specialist | 10.5342 | 8.0469 | 8.233 | 10.1128 | 6.0651 | 7.0505 | 7.9638 | 8.6907 | 10.826 | 13.1403 | 13.972 | 14.2211 | 13.9067 | 13.5501 | 12.8622 | 0 | 14.2211
| GIS Specialist | 46.7485 | 35.7107 | 36.5363 | 44.8786 | 26.9155 | 31.2888 | 35.3419 | 38.5675 | 48.0435 | 58.3141 | 62.0049 | 63.1105 | 61.7151 | 60.1326 | 57.0799 | 0 | 63.1105
| Environmental Inspector (EI) | 36.3791 | 27.7896 | 28.4321 | 34.9239 | 20.9452 | 24.3485 | 27.5026 | 30.0127 | 37.3868 | 45.3792 | 48.2514 | 49.1117 | 48.0258 | 46.7944 | 44.4188 | 0 | 49.1117
| Compliance Specialist | 31.413 | 23.9961 | 24.5509 | 30.1565 | 18.086 | 21.0247 | 23.7482 | 25.9157 | 32.2832 | 39.1846 | 41.6647 | 42.4076 | 41.4699 | 40.4066 | 38.3553 | 0 | 42.4076
| Sample Coordinator | 17.1591 | 13.1077 | 13.4107 | 16.4728 | 9.8794 | 11.4846 | 12.9723 | 14.1563 | 17.6344 | 21.4043 | 22.759 | 23.1648 | 22.6526 | 22.0718 | 20.9513 | 0 | 23.1648
| Construction Management | 31.0514 | 35.4014 | 25.4435 | 34.2453 | 43.2173 | 31.0095 | 24.6235 | 28.7939 | 32.7128 | 40.9279 | 48.6402 | 51.5534 | 52.1301 | 50.5586 | 48.9872 | 47.4158 | 52.1301
| Construction Manager | 31.0514 | 35.4014 | 25.4435 | 34.2453 | 43.2173 | 31.0095 | 24.6235 | 28.7939 | 32.7128 | 40.9279 | 48.6402 | 51.5534 | 52.1301 | 50.5586 | 48.9872 | 47.4158 | 52.1301
| Civil Crew | 422.2994 | 481.4587 | 346.0315 | 465.7368 | 587.7558 | 421.7291 | 334.879 | 391.5965 | 444.8946 | 556.6199 | 661.5064 | 701.1268 | 708.969 | 687.5975 | 666.2261 | 644.8547 | 708.969
| Civil - Foreman | 62.1029 | 70.8027 | 50.887 | 68.4907 | 86.4347 | 62.019 | 49.2469 | 57.5877 | 65.4257 | 81.8559 | 97.2804 | 103.1069 | 104.2601 | 101.1173 | 97.9744 | 94.8316 | 104.2601
| Civil - Backhoe Operator | 62.1029 | 70.8027 | 50.887 | 68.4907 | 86.4347 | 62.019 | 49.2469 | 57.5877 | 65.4257 | 81.8559 | 97.2804 | 103.1069 | 104.2601 | 101.1173 | 97.9744 | 94.8316 | 104.2601
| Civil - Construction Operator | 111.7851 | 127.4449 | 91.5966 | 123.2833 | 155.5824 | 111.6342 | 88.6444 | 103.6579 | 117.7662 | 147.3406 | 175.1046 | 185.5924 | 187.6683 | 182.0111 | 176.354 | 170.6968 | 187.6683
| Civil - Utility Worker | 186.3086 | 212.4082 | 152.661 | 205.4721 | 259.304 | 186.0569 | 147.7407 | 172.7632 | 196.277 | 245.5676 | 291.8411 | 309.3206 | 312.7804 | 303.3519 | 293.9233 | 284.4947 | 312.7804
| Electrical Crew | 49.6823 | 56.6422 | 40.7096 | 54.7926 | 69.1477 | 49.6152 | 39.3975 | 46.0702 | 52.3405 | 65.4847 | 77.8243 | 82.4855 | 83.4081 | 80.8938 | 78.3795 | 75.8653 | 83.4081
| Electrical - Foreman | 12.4206 | 14.1605 | 10.1774 | 13.6981 | 17.2869 | 12.4038 | 9.8494 | 11.5175 | 13.0851 | 16.3712 | 19.4561 | 20.6214 | 20.852 | 20.2235 | 19.5949 | 18.9663 | 20.852
| Electrical - Journeyman Lineman | 24.8411 | 28.3211 | 20.3548 | 27.3963 | 34.5739 | 24.8076 | 19.6988 | 23.0351 | 26.1703 | 32.7423 | 38.9121 | 41.2428 | 41.7041 | 40.4469 | 39.1898 | 37.9326 | 41.7041
| Electrical - Groundman/Apprentices | 12.4206 | 14.1605 | 10.1774 | 13.6981 | 17.2869 | 12.4038 | 9.8494 | 11.5175 | 13.0851 | 16.3712 | 19.4561 | 20.6214 | 20.852 | 20.2235 | 19.5949 | 18.9663 | 20.852
| Post Construction | 6.0037 | 6.8448 | 4.9195 | 7.45 | 8.356 | 5.9956 | 4.7609 | 5.5672 | 6.325 | 7.9133 | 9.4045 | 9.9678 | 10.0793 | 9.7754 | 9.4716 | 9.1678 | 10.0793
| Clerical | 4.0228 | 4.5863 | 3.2963 | 4.9919 | 5.5989 | 4.0174 | 3.19 | 3.7303 | 4.238 | 5.3023 | 6.3015 | 6.6789 | 6.7536 | 6.55 | 6.3464 | 6.1429 | 6.7536
| Mapping | 1.9809 | 2.2584 | 1.6232 | 2.4581 | 2.7571 | 1.9783 | 1.5709 | 1.8369 | 2.0869 | 2.611 | 3.103 | 3.2889 | 3.3257 | 3.2254 | 3.1252 | 3.0249 | 3.3257
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Baboolal, Aleisha / @Alexander, Anthony - There are various “outputs” in table C2 and C3, however, all the values are hardcoded so it is challenging to trace the logic in the model. IS there a version with the formulas that can be reviewed Reply: INTERNAL_RESOURCE MODEL AEAG_CONF.xlsx Reply: @Noyer, Nick, with the link supplied above does this resolve your comment?