## Core Capability 5
Workpaper 012
Pacific Gas and Electric Company
Electrical Undergrounding Program
Core Capability 5: Supporting Formulas
Core Capability 5 Supporting Formulas
| Circuit Segment (B) | Circuit Segment Overhead Miles Removed (C) | Wildfire Risk (D) | PSPS Risk (E) | EPSS Risk (F) | Outage Risk (G) | Sub-Project Mitigation (H) | Circuit Segment and Mitigation Specific Wild Fire Mitigation Effectiveness (I) | Mitigation Specific PSPS Risk Mitigation Effectiveness (J) | Mitigation Specific EPSS Risk Mitigation Effectiveness (K) | Sub-Project Overhead Miles Removed (L) | Percentage of Circuit Segment Mitigated by Sub-Project (M) | Sub-Project Wildfire Risk (N) | Sub-Project PSPS Risk (O) | Sub-Project EPSS Risk (P) | Sub-Project Outage Risk (Q) | Sub Project Post Mitigation Wildfire Risk (R) | Circuit Segment Post Mitigation Wildfire Risk (S) | Sub-Project Post Mitigation PSPS Risk (T) | Circuit Segment Post Mitigation PSPS Risk (U) | Sub-Project Post Mitigation EPSS Risk (V) | Circuit Segment Post Mitigation EPSS Risk (W) | Sub-Project Post Mitigation Outage Risk (X) | Circuit Segment Post Mitigation Outage Risk (Y) | Energization Date (Z) | Year Risk Reduction can be Claimed (AA)
| Kangaroo Flats 1 | C | D | E | F | G = E + F | Undergrounding Primary | I1 | J1 | K1 | L1 | M1 = L1 / C | N1 = M1 * D1 | O1 = M1 * E1 | P1 = M1 * F1 | Q1 = O1 + P1 | R1 = N1 * (1 - I1) | S = R1 + R2 + R3 | T1 = O1 * (1 - J1) | U = T1 + T2 + T3 | V1 = P1 * (1 - K1) | W = V1 + V2 + V3 | X1 = T1 + V1 | Y = X1 + X2 + X3 | 2029-08-08 | 2029
[7 empty] | Undergrounding Primary | I2 | J2 | K2 | L2 | M2 = L2 / C | N2 = M2 * D2 | O2 = M2 * E2 | P2 = M2 * F2 | Q2 = O2 + P2 | R2 = N2 * (1 - I2) |  | T2 = O2 * (1 - J2) |  | V2 = P2 * (1 - K2) |  | X2 = T2 + V2 |  | 2028-12-02 | 2028
[7 empty] | Overhead Hardening | I3 | J3 | K3 | L3 | M3 = L3 / C | N3 = M3 * D3 | O3 = M3 * E3 | P3 = M3 * F3 | Q3 = O3 + P3 | R3 = N3 * (1 - I3) |  | T3 = O3 * (1 - J3) |  | V3 = P3 * (1 - K3) |  | X3 = T3 + V3 |  | 2030-09-21 | 2030
*In this scenario, PG&E assumes this exemplar Circuit Segment is crossing 2 County lines, therefore there are 2 Undergrounding Primary Sub-Projects **The methodology used to assess risk reduction for Fire Rebuild Projects is consistent with the methodology applied to standard EUP projects
Low Risk Scenario
| Circuit Segment (B) | Circuit Segment Overhead Miles Removed (C) | Wildfire Risk (D) | PSPS Risk (E) | EPSS Risk (F) | Outage Risk (G) | Sub-Project Mitigation (H) | Circuit Segment and Mitigation Specific Wild Fire Mitigation Effectiveness (I) | Mitigation Specific PSPS Risk Mitigation Effectiveness (J) | Mitigation Specific EPSS Risk Mitigation Effectiveness (K) | Sub-Project Overhead Miles Removed (L) | Percentage of Circuit Segment Mitigated by Sub-Project (M) | Sub-Project Wildfire Risk (N) | Sub-Project PSPS Risk (O) | Sub-Project EPSS Risk (P) | Sub-Project Outage Risk (Q) | Sub Project Post Mitigation Wildfire Risk (R) | Circuit Segment Post Mitigation Wildfire Risk (S) | Sub-Project Post Mitigation PSPS Risk (T) | Circuit Segment Post Mitigation PSPS Risk (U) | Sub-Project Post Mitigation EPSS Risk (V) | Circuit Segment Post Mitigation EPSS Risk (W) | Sub-Project Post Mitigation Outage Risk (X) | Circuit Segment Post Mitigation Outage Risk (Y) | Energization Date (Z) | Year Risk Reduction can be Claimed (AA)
| Alder Glen 1 | 1 | 1 | 0.07 | 0.02 | 0.09 | Undergrounding Primary | 95% | 100% | 100% | 0.35 | 35% | 0.35 | 0.0245 | 0.007 | 0.0315 | 0.0175 | 0.175 | 0 | 0.0175 | 0 | 0.0024 | 0 | 0.0199 | 2029-08-08 | 2029
[7 empty] | Undergrounding Primary | 95% | 100% | 100% | 0.4 | 40% | 0.4 | 0.028 | 0.008 | 0.036 | 0.02 |  | 0 |  | 0 |  | 0 |  | 2028-12-02 | 2028
[7 empty] | Overhead Hardening | 45% | 0% | 52% | 0.25 | 25% | 0.25 | 0.0175 | 0.005 | 0.0225 | 0.1375 |  | 0.0175 |  | 0.0024 |  | 0.0199 |  | 2030-09-21 | 2030
The figures in this table are examples only and do not represent actual data
Medium Risk Scenario
| Circuit Segment (B) | Circuit Segment Overhead Miles Removed (C) | Wildfire Risk (D) | PSPS Risk (E) | EPSS Risk (F) | Outage Risk (G) | Sub-Project Mitigation (H) | Circuit Segment and Mitigation Specific Wild Fire Mitigation Effectiveness (I) | Mitigation Specific PSPS Risk Mitigation Effectiveness (J) | Mitigation Specific EPSS Risk Mitigation Effectiveness (K) | Sub-Project Overhead Miles Removed (L) | Percentage of Circuit Segment Mitigated by Sub-Project (M) | Sub-Project Wildfire Risk (N) | Sub-Project PSPS Risk (O) | Sub-Project EPSS Risk (P) | Sub-Project Outage Risk (Q) | Sub Project Post Mitigation Wildfire Risk (R) | Circuit Segment Post Mitigation Wildfire Risk (S) | Sub-Project Post Mitigation PSPS Risk (T) | Circuit Segment Post Mitigation PSPS Risk (U) | Sub-Project Post Mitigation EPSS Risk (V) | Circuit Segment Post Mitigation EPSS Risk (W) | Sub-Project Post Mitigation Outage Risk (X) | Circuit Segment Post Mitigation Outage Risk (Y) | Energization Date (Z) | Year Risk Reduction can be Claimed (AA)
| Birch Ridge 2 | 1 | 2 | 2.82 | 3.78 | 6.6 | Undergrounding Primary | 95% | 100% | 100% | 0.35 | 35% | 0.7 | 0.987 | 1.323 | 2.31 | 0.035 | 0.35 | 0 | 0.705 | 0 | 0.4536 | 0 | 1.1586 | 2029-08-08 | 2029
[7 empty] | Undergrounding Primary | 95% | 100% | 100% | 0.4 | 40% | 0.8 | 1.128 | 1.512 | 2.64 | 0.04 |  | 0 |  | 0 |  | 0 |  | 2028-12-02 | 2028
[7 empty] | Overhead Hardening | 45% | 0% | 52% | 0.25 | 25% | 0.5 | 0.705 | 0.945 | 1.65 | 0.275 |  | 0.705 |  | 0.4536 |  | 1.1586 |  | 2030-09-21 | 2030
The figures in this table are examples only and do not represent actual data
High Risk Scenario
| Circuit Segment (B) | Circuit Segment Overhead Miles Removed (C) | Wildfire Risk (D) | PSPS Risk (E) | EPSS Risk (F) | Outage Risk (G) | Sub-Project Mitigation (H) | Circuit Segment and Mitigation Specific Wild Fire Mitigation Effectiveness (I) | Mitigation Specific PSPS Risk Mitigation Effectiveness (J) | Mitigation Specific EPSS Risk Mitigation Effectiveness (K) | Sub-Project Overhead Miles Removed (L) | Percentage of Circuit Segment Mitigated by Sub-Project (M) | Sub-Project Wildfire Risk (N) | Sub-Project PSPS Risk (O) | Sub-Project EPSS Risk (P) | Sub-Project Outage Risk (Q) | Sub Project Post Mitigation Wildfire Risk (R) | Circuit Segment Post Mitigation Wildfire Risk (S) | Sub-Project Post Mitigation PSPS Risk (T) | Circuit Segment Post Mitigation PSPS Risk (U) | Sub-Project Post Mitigation EPSS Risk (V) | Circuit Segment Post Mitigation EPSS Risk (W) | Sub-Project Post Mitigation Outage Risk (X) | Circuit Segment Post Mitigation Outage Risk (Y) | Energization Date (Z) | Year Risk Reduction can be Claimed (AA)
| Cedar Falls 3 | 1 | 4 | 6.51 | 16.08 | 22.59 | Undergrounding Primary | 95% | 100% | 100% | 0.35 | 35% | 1.4 | 2.2785 | 5.628 | 7.9065 | 0.07 | 0.7 | 0 | 1.6275 | 0 | 1.9296 | 0 | 3.5571 | 2029-08-08 | 2029
[7 empty] | Undergrounding Primary | 95% | 100% | 100% | 0.4 | 40% | 1.6 | 2.604 | 6.432 | 9.036 | 0.08 |  | 0 |  | 0 |  | 0 |  | 2028-12-02 | 2028
[7 empty] | Overhead Hardening | 45% | 0% | 52% | 0.25 | 25% | 1 | 1.6275 | 4.02 | 5.6475 | 0.55 |  | 1.6275 |  | 1.9296 |  | 3.5571 |  | 2030-09-21 | 2030
The figures in this table are examples only and do not represent actual data